## Sheet1
Project No | Project Type | Campaign | Customer | Property Name | Branch | ODP Quote | Designer | CRM | Design Manager | Design Engineer | Design Associate | Project Manager | Senior Project Manager | VRM | SM-Closing | VM | Status | Stage | Milestone Name | Project Value | Total Paid | Net Project Value | IDM Project Value | PKO Project Value | Active Days | Hold Days | Pending Design Fees | Pending Design Finalization fees | Pending First Slot | Pending Second Slot | Sales Handover Planned | Sales Handover Done | Prebook Agreement Signed Planned | Prebook Agreement Signed Done | DCM Planned | DCM Done | CDP Planned | CDP Done | 1st Design Presentation Planned | 1st Design Presentation Done | 2nd Design Presentation Planned | 2nd Design Presentation Done | 3rd Design Presentation Planned | 3rd Design Presentation Done | Design Fees Planned | Design Fees Done | Agreement Signed Planned | Agreement Signed Done | Intro Call Planned | Intro Call Done | Welcome Call Planned | Welcome Call Done | Estimation Check for 3D Planned | Estimation Check for 3D Done | Design Closure Meeting Planned | Design Closure Meeting Done | Design Finalization Fees Planned | Design Finalization Fees Done | Cross Measurement1 Planned | Cross Measurement1 Done | Cross Measurement1 Mom Planned | Cross Measurement1 Mom Done | Hoto Drawings Qc Planned | Hoto Drawings Qc Done | Hoto Pm Planned | Hoto Pm Done | Estimate Completion Drawings Planned | Estimate Completion Drawings Done | Client 3d Approval Planned | Client 3d Approval Done | First Slot Planned | First Slot Done | 2d Received De Planned | 2d Received De Done | Cutlist Qc Planned | Cutlist Qc Done | Procurement Start Date | Receive Raw Materials Planned | Receive Raw Materials Done | Packing Completion1 Planned | Packing Completion1 Done | Second Slot Planned | Second Slot Done | Ship Materials Planned | Ship Materials Done | Shipment Checklist Signed Planned | Shipment Checklist Signed Done | Quality Check Modular1 Planned | Quality Check Modular1 Done | Execution Rework1 Planned | Execution Rework1 Done | Quality Check Modular2 Planned | Quality Check Modular2 Done | Execution Rework2 Planned | Execution Rework2 Done | Customer Checklist Signed Planned | Customer Checklist Signed Done | Payment Settlements Completed Planned | Payment Settlements Completed Done | Site Readiness Planned | Site Readiness Done | Site Key Handover To Pm Planned | Site Key Handover To Pm Done | Initial Measurement Planned Date | Initial Measurement Done Date | Initial Measurement Basis On | Token Advance Planned | Token Advance Done | Net Sub total | Net Tax | IDM Sub total | IDM Tax | PKO Sub total | PKO Tax | Current Sub total | Current Tax | Notes1 Creation Date | Notes1 Creator | Notes1 Content | Notes2 Creation Date | Notes2 Creator | Notes2 Content | Notes3 Creation Date | Notes3 Creator | Notes3 Content | DEM 1 Planned Date | DEM 1 Done Date | DEM 2 Planned Date | DEM 2 Done Date | RTMI Status | Possession Date | Reported Net Date | Reported Net Collection | Reported Net By
6048 | Turnkey | May'26 | Warren Valentine | VSR Tranquil | BNG - HRBR |  | Vishnu S | Parasa Sri | Shibin Lal | [7 empty] | Hold | Preproduction | Site Readiness 1 | 1125919 | 363312 | 1125919 | 0 | 0 | 2 | 67 | 0 |  | 324039 | 438567.6 |  |  | 2022-09-28 | 2026-05-19 18:10 | 2026-05-19 | 2026-05-19 18:19 | 2026-05-22 | 2026-05-19 19:26 | 2026-05-23 | 2026-05-23 13:56 | 2026-08-15 |  | 2026-08-22 |  | 2026-05-19 | 2026-05-23 13:02 | 2026-05-20 | 2026-05-23 13:02 | 2026-05-23 | 2026-05-23 13:03 | 2026-05-24 | 2026-05-23 13:03 |  |  |  |  | 2026-05-23 | 2026-05-23 14:35 | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-05-24 | 2026-05-23 13:03 | Unknown | 2022-09-28 | 2026-05-19 18:09 | 1155419 | 207975 | 0 | 0 | 0 | 0 | 1155419 | 207975 | 2025-01-29 16:32:30 +0530 | Yogesh Patidar | Some Image was uploaded | 2025-01-17 12:50:45 +0530 | Yogesh Patidar | Some Image was uploaded | 2024-10-29 11:32:26 +0530 | Bhargavi Maddala | Some Image was uploaded | 2026-05-24 | 2026-05-23 13:58 | 2026-08-16
14948 | Turnkey | Dec'24 Campaign | Arunnarayanan k | kalapataru immensa | MUM - Thane | Yes |  | Avinash Jaiswal | Rushika More | [5 empty] | Vandana Preet |  | Lost | Prospect | Onboarding Due | 2123913 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 637174 | 728113 | 758626 |  |  | 2024-12-13 | 2026-04-10 11:32 | 2024-12-11 | 2026-04-10 11:32 | 2024-12-14 | 2026-04-10 11:32 | 2026-04-20 |  | 2026-04-23 |  | 2026-04-26 |  | 2026-04-10 | 2026-04-10 11:32 | 2026-04-11 | 2026-04-10 11:33 | 2026-04-11 |  | 2026-04-10 |  | 2026-04-26 |  | 2026-04-29 |  | 2026-04-29 |  | 2026-05-05 |  | 2026-05-06 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-16 |  | 2026-05-16 | [6 empty] | 2026-05-20 |  | 2026-05-29 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-06-01 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-07-08 | [5 empty] | 2026-05-16 |  | 2026-04-11 |  | Unknown | 2024-12-12 | 2026-04-10 11:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1799926 | 323986 | [13 empty] | RTMI
15706 | Test Mode | Apr'25 | Anas QA 2 |  | BNG - HRBR | Yes |  | Akshay Ds | Prashant Chhajer | [7 empty] | Active | Design | 30% Payment | 1941871 | 250000 | 978384 | 1941871 | 0 | 49 | 264 | 0 | 0 | 915123 | 776748.4 |  |  | 2025-04-11 | 2026-05-26 10:26 | 2026-05-26 | 2026-05-26 11:10 | 2026-05-26 | 2026-05-26 12:32 | 2026-05-27 | 2026-05-27 09:44 | 2026-05-27 | 2026-05-27 10:23 | 2026-05-27 | 2026-05-27 11:20 | 2026-05-26 | 2026-05-26 12:41 | 2026-05-27 | 2026-05-26 18:34 | 2026-05-25 | 2026-05-26 20:37 | 2026-05-26 | 2026-05-27 09:17 | 2026-05-27 | 2026-05-27 14:59 | 2026-05-28 |  | 2026-06-19 | 2026-05-26 | 2026-05-31 |  | 2026-05-31 |  |  |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 | [6 empty] | 2026-06-15 |  | 2026-06-24 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-08 |  | 2026-05-28 | 2026-05-27 09:32 | Site is Non-RTMI | 2025-04-10 | 2026-05-26 10:25 | 872778 | 157100 | 1732267 | 311808 | 0 | 0 | 1732267 | 311808 | [13 empty] | RTMI
17005 | Sub Project |  | Sundarrajan K D | kanakia silicon valley | MUM - GOR |  |  | Avinash Jaiswal | Shantanu Parakh |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 50000 | 126 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-10-05 | 2026-01-31 12:54 | 2025-10-05 | 2026-01-31 12:54 | 2026-02-02 | 2026-01-31 12:55 | 2026-02-02 | 2026-01-31 12:58 | 2026-02-01 | 2026-01-31 12:59 | 2026-02-01 | 2026-01-31 12:59 | 2026-01-31 | 2026-01-31 12:55 | 2026-02-01 | 2026-01-31 12:55 | 2026-01-31 | 2026-01-31 12:56 | 2026-02-01 | 2026-01-31 12:57 | 2026-01-31 | 2026-01-31 13:00 | 2026-02-03 | 2026-01-31 13:00 | 2026-01-31 | 2026-01-31 13:00 | 2026-02-01 | 2026-01-31 13:02 | 2026-02-01 | 2026-01-31 13:02 |  |  | 2026-02-02 | 2026-01-31 13:04 | 2026-02-01 | 2026-01-31 13:06 | 2026-02-03 | 2026-01-31 13:06 | 2026-01-31 | 2026-01-31 13:08 |  |  |  |  | 2026-02-20 10:52 | 2026-02-21 | 2026-02-20 19:48 | 2026-02-23 | 2026-02-21 14:32 | 2026-02-22 | 2026-03-10 13:40 | 2026-02-21 | 2026-03-10 16:35 | 2026-03-10 | 2026-03-10 16:37 | 2026-03-11 | 2026-03-10 16:48 |  |  | 2026-03-12 | 2026-03-10 18:10 | 2026-03-12 | 2026-03-10 18:12 | 2026-03-10 | 2026-03-10 18:14 |  |  |  |  | 2026-01-31 | 2026-02-19 18:37 | 2026-02-01 | 2026-01-31 12:57 | Unknown | 2025-10-04 | 2026-01-31 12:53 | 0 | 0 | 0 | 0 | 42372 | 7627 | 42372 | 7627 | 2026-03-08 22:15:41 +0530 | Savita Parab | Execution: site is ready to dispatch the material | 2026-03-01 19:31:55 +0530 | Savita Parab | Execution: site is ready to dispatch the material | 2026-02-20 09:54:11 +0530 | Savita Parab | Execution: site is ready to dispatch the material
17082 | Turnkey | Sep'25 | Ashutosh rout | Prestige | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 1160563 | 9999 | 0 | 0 | 0 | 276 | 0 | 106057 | 232113 | 375325 | 437069.2 |  |  | 2025-10-13 | 2026-04-28 17:12 | 2025-10-13 |  | 2025-10-19 |  | 2025-10-31 |  | 2025-11-03 |  | 2025-11-06 |  | 2025-10-19 |  | 2025-10-20 |  | 2025-10-20 |  | 2025-10-21 |  | 2025-11-06 |  | 2025-11-09 |  | 2025-11-09 |  | 2025-11-13 |  | 2025-11-14 |  |  |  | 2025-11-20 |  | 2025-11-21 |  | 2025-11-24 |  | 2025-11-24 | [6 empty] | 2025-11-30 |  | 2025-12-09 |  | 2025-12-08 |  | 2025-12-09 |  | 2025-12-10 |  | 2025-12-12 |  |  |  | 2026-01-03 |  | 2026-01-05 |  | 2026-01-06 | [5 empty] | 2025-11-24 |  | 2025-10-22 |  | Unknown | 2025-10-12 | 2026-04-28 17:11 | 0 | 0 | 0 | 0 | 0 | 0 | 983528 | 177035 | 2026-04-28 17:14:35 +0530 | Raghavendra S | Some Image was uploaded
17203 | Turnkey | Sep'25 | N Neelakanteswaran | Kalpataru Immensa | MUM - Thane | No Estimate | Rinisha Masurkar | [9 empty] | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 263 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-10-25 | 2026-03-10 13:25 | 2025-10-25 |  | 2025-10-25 |  | 2025-11-06 |  | 2025-11-09 |  | 2025-11-12 |  | 2025-10-25 |  | 2025-10-26 |  | 2025-10-26 |  | 2025-10-27 |  | 2025-11-12 |  | 2025-11-15 |  | 2025-11-15 |  | 2025-11-19 |  | 2025-11-20 |  |  |  | 2025-11-26 |  | 2025-11-27 |  | 2025-11-30 |  | 2025-11-30 | [6 empty] | 2025-12-06 |  | 2025-12-15 |  | 2025-12-14 |  | 2025-12-15 |  | 2025-12-16 |  | 2025-12-18 |  |  |  | 2026-01-09 |  | 2026-01-11 |  | 2026-01-12 | [5 empty] | 2025-11-30 |  | 2025-10-28 |  | Unknown | 2025-10-24 | 2025-10-25 17:03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17576 | Sub Project |  | Gitanjali Bhare | Nath Nivas | MUM - Thane | Yes |  | Divya Rahangdale |  |  |  | Faraz Soudagar | Aditya Vikram | Murali S |  |  | Completed | Complete | Completed | 19756 | 19756 | 0 | 0 | 19756 | 96 | 16 | 0 | 0 | 0 | 0 |  |  | 2025-12-04 | 2026-01-22 13:14 | 2025-12-04 | 2026-01-22 13:14 | 2026-01-24 | 2026-01-22 13:15 | 2026-01-24 | 2026-01-22 13:16 | 2026-01-23 | 2026-01-22 13:17 | 2026-01-23 | 2026-01-22 13:19 | 2025-12-10 | 2025-12-09 15:13 | 2026-01-23 | 2026-01-22 13:15 | 2026-01-22 | 2026-01-22 13:15 | 2026-01-23 | 2026-01-22 13:15 | 2026-01-22 | 2026-01-22 13:19 | 2025-12-31 | 2025-12-09 15:13 | 2025-12-09 | 2026-01-04 | 2026-01-23 | 2026-01-22 13:20 | 2026-01-23 | 2026-01-22 13:21 |  |  | 2026-01-24 | 2026-01-22 13:22 | 2026-01-23 | 2026-01-22 13:23 | 2025-12-24 | 2026-01-22 13:13 | 2025-12-24 | 2026-01-22 13:10 |  |  |  |  | 2026-01-23 10:24 | 2026-01-25 | 2026-02-06 17:26 | 2026-02-08 | 2026-02-06 19:18 | 2026-02-13 | 2026-01-22 13:21 | 2026-02-06 | 2026-02-11 14:28 | 2026-02-11 | 2026-02-16 18:04 | 2026-02-18 | 2026-02-23 14:30 |  |  | 2026-04-14 | 2026-04-06 10:48 | 2026-04-16 | 2026-04-06 12:01 | 2026-04-17 | 2026-04-06 14:57 |  |  |  |  | 2026-01-25 | 2026-01-22 19:26 | 2026-01-23 | 2026-01-22 13:16 | Unknown | 2025-12-03 | 2026-01-22 13:13 | 0 | 0 | 0 | 0 | 16743 | 3013 | 16743 | 3013
17591 | Sub Project |  | Madhuri H N | Independent House | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S |  |  |  | Shijin C C | Jairam Joshi | Murali S |  | Sunil Kumar S M | Completed | Complete | Completed | 61052 | 61052 | 0 | 0 | 61052 | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-06 | 2026-02-14 11:53 | 2025-12-06 | 2026-02-14 11:54 | 2026-02-16 | 2026-02-14 11:54 | 2026-02-16 | 2026-02-14 11:55 | 2026-02-15 | 2026-02-14 11:56 |  |  | 2025-12-12 | 2026-02-13 18:33 | 2026-02-15 | 2026-02-14 11:54 | 2026-02-14 | 2026-02-14 11:55 | 2026-02-15 | 2026-02-14 11:55 | 2026-02-14 | 2026-02-14 11:57 | 2026-02-17 | 2026-02-14 11:57 | 2026-01-02 | 2026-02-13 18:33 | 2026-02-17 | 2026-02-14 11:58 | 2026-02-15 | 2026-02-14 11:59 |  |  | 2026-02-16 | 2026-02-14 15:51 | 2026-02-15 | 2026-02-14 16:10 | 2026-02-17 | 2026-02-16 10:23 | 2026-02-16 | 2026-02-18 18:37 |  |  |  |  | 2026-02-21 16:48 | 2026-02-28 | 2026-02-27 16:58 | 2026-03-01 | 2026-02-27 20:51 | 2026-03-02 | 2026-02-18 18:37 | 2026-02-27 | 2026-03-04 12:07 | 2026-03-04 | 2026-03-04 20:05 | 2026-03-06 | 2026-03-06 09:03 |  |  | 2026-03-08 | 2026-03-06 09:56 | 2026-03-08 | 2026-03-06 10:33 | 2026-03-09 | 2026-03-06 11:54 |  |  |  |  | 2026-02-16 | 2026-02-19 18:44 | 2026-02-15 | 2026-02-14 11:55 | Unknown | 2025-12-05 | 2026-02-13 18:33 | 0 | 0 | 0 | 0 | 51739 | 9313 | 51739 | 9313 | 2026-02-15 13:45:38 +0530 | Rajasekar Ranganathan | Some Image was uploaded
17632 | Turnkey | Dec'25 | Vishal Soni | LODHA AMARA | MUM - Thane | Yes | Mayuri Patil | [9 empty] | Active | Prospect | DCM Due | 1452376 | 9999 | 0 | 0 | 0 | 220 | 0 | 135239 | 290475 | 444191 | 572472.4 |  |  | 2025-12-08 | 2026-01-25 11:11 | 2025-12-08 |  | 2025-12-07 |  | 2025-12-19 |  | 2025-12-22 |  | 2025-12-25 |  | 2025-12-07 |  | 2025-12-08 |  | 2025-12-08 |  | 2025-12-09 |  | 2025-12-25 |  | 2025-12-28 |  | 2025-12-28 |  | 2026-01-01 |  | 2026-01-02 |  |  |  | 2026-01-08 |  | 2026-01-09 |  | 2026-01-12 |  | 2026-01-12 | [6 empty] | 2026-01-18 |  | 2026-01-27 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-30 |  |  |  | 2026-02-21 |  | 2026-02-23 |  | 2026-02-24 | [5 empty] | 2026-01-12 |  | 2025-12-10 |  | Unknown | 2025-12-07 | 2026-01-25 11:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1230827 | 221548 | 2026-01-18 18:19:53 +0530 | Honey Thakkar | DCM SummaryDate: 18-01-2026 Attendees: Husband & Wife Profession: IT Professionals Family Members: Couple, Mother, and One Son Overall RequirementsStyle Preference: Simple, contemporary look across the houseColor Palette: Predominantly white or light shadesStorage Requirement: Maximum possible storage across the entire house, especially for books and toysBudget: 1012 lakhs (excluding loose furniture)Loose Furniture: Client will arrange through their own vendorsLiving RoomSafety door requiredPooja Unit:Large-sized unitProper closed storageColor preference: WhiteTV unit with dcor elementsAdditional storage for books and toys wherever feasibleConcept:Pure white or light color themeMirror elements preferredClean, contemporary aestheticKitchenSemi-modular kitchenLoft storage on both sidesAppliance provisions required for:MicrowaveRefrigeratorFood processorMixer (preferably in a tambour unit)Cooktop: GasChimney: DuctlessWashing machine to be placed in the utility areaBedroom 1 (Son + Dadi)Shared bedroomRequirement to optimally accommodate:BedStudy areaWardrobeDressing mirrorToy storageBook storageSpace planning to be done carefully to maximize functionalityMaster BedroomBedWardrobeStudy tableVanity Units (Bathrooms)Base vanity storage requiredWall-mounted storage also required
17644 | Sub Project |  | Ramchandran J . M | 100 Trees | MUM - GOR |  | Priyanka Patel | Manzoor Shaikh | Safalta Karkera |  | Priyanka Kamble | Uday Yadruk | Rizwan Mistry | Murali S |  |  | Active | Handover | Project Closure Pending | 0 | 0 | 0 | 0 | 0 | 79 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-10 | 2026-01-21 13:16 | 2025-12-10 | 2026-01-21 13:18 | 2026-01-23 | 2026-01-21 13:19 | 2026-01-23 | 2026-01-21 13:21 | 2026-01-22 | 2026-01-21 13:22 | 2026-01-22 | 2026-01-21 13:23 | 2026-01-21 | 2026-01-21 13:19 | 2026-01-22 | 2026-01-21 13:19 | 2026-01-21 | 2026-01-21 13:19 | 2026-01-22 | 2026-01-21 13:20 | 2026-01-21 | 2026-01-21 13:24 | 2026-01-24 | 2026-01-21 13:24 | 2026-01-21 | 2026-01-21 13:25 | 2026-01-22 | 2026-01-21 13:27 | 2026-01-22 | 2026-01-21 13:27 |  |  | 2026-01-23 | 2026-01-21 13:28 | 2026-01-22 | 2026-01-21 13:29 | 2026-01-24 | 2026-01-21 13:30 | 2026-01-31 | 2026-01-21 13:27 |  |  |  |  | 2026-01-23 12:57 | 2026-01-24 | 2026-01-23 18:44 | 2026-01-29 | 2026-01-27 10:15 | 2026-01-28 | 2026-01-30 14:39 | 2026-01-27 | 2026-01-31 16:52 | 2026-01-31 | 2026-01-31 16:54 | 2026-02-02 | 2026-02-03 15:19 |  |  | 2026-05-07 | 2026-04-27 22:48 | 2026-05-09 | 2026-04-27 22:50 | 2026-05-10 | 2026-04-27 22:58 |  |  |  |  | 2026-01-22 | 2026-01-23 12:56 | 2026-01-22 | 2026-01-21 13:20 | Unknown | 2025-12-09 | 2026-01-21 13:16 | 0 | 0 | 0 | 0 | 30083.9 | 0 | 30083.9 | 0 | 2026-04-26 10:54:26 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-25 17:22:01 +0530 | Manzoor Shaikh | Some Image was uploaded
17677 | Sub Project |  | Sachitha | Indepedent house | BNG - HRBR |  | Salpriyan Pm | Parasa Sri |  |  |  | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  |  | Completed | Complete | Completed | 177747 | 178641 | 0 | 0 | 177747 | 114 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-14 | 2026-01-15 11:30 | 2025-12-14 | 2026-01-15 11:31 | 2026-01-17 | 2026-01-15 11:31 | 2026-01-17 | 2026-01-15 11:32 | 2026-01-16 | 2026-01-15 11:33 | 2026-01-16 | 2026-01-15 11:33 | 2026-01-15 | 2026-01-15 11:31 | 2026-01-16 | 2026-01-15 11:31 | 2026-01-15 | 2026-01-15 11:31 | 2026-01-16 | 2026-01-15 11:32 | 2026-01-15 | 2026-01-15 11:34 | 2026-01-18 | 2026-01-15 11:34 | 2026-01-15 | 2026-01-15 11:34 | 2026-01-16 | 2026-01-15 11:35 | 2026-01-16 | 2026-01-15 11:35 |  |  | 2026-01-17 | 2026-01-15 11:36 | 2026-01-16 | 2026-01-18 12:15 | 2026-01-21 | 2026-01-18 16:46 | 2026-01-18 | 2026-01-18 16:46 |  |  |  |  | 2026-01-18 17:23 | 2026-01-20 | 2026-01-19 18:15 | 2026-01-23 | 2026-01-20 18:42 | 2026-01-21 | 2026-01-22 18:07 | 2026-01-20 | 2026-01-26 16:20 | 2026-01-26 | 2026-01-27 09:36 | 2026-01-31 | 2026-01-30 14:20 |  |  | 2026-03-24 | 2026-03-20 20:09 | 2026-03-26 | 2026-03-20 20:10 | 2026-03-23 | 2026-03-23 21:38 |  |  |  |  | 2026-01-18 | 2026-01-18 17:22 | 2026-01-16 | 2026-01-15 11:32 | Unknown | 2025-12-13 | 2026-01-13 14:08 | 0 | 0 | 0 | 0 | 150633 | 27114 | 150633 | 27114 | 2026-03-09 10:48:52 +0530 | Saddam Hussain Z M | Execution: Stool delivery - 14th March QC - 16th March HO - 16th March
17691 | Turnkey | Dec'25 | Mrs. Navya | Suraksha Springs | BNG - HSR | Yes | [8 empty] | Fuzail Girach |  | Active | Prospect | DCM Due | 1155955 | 9999 | 0 | 0 | 0 | 213 | 0 | 105597 | 231191 | 357467 | 451702 |  |  | 2025-12-15 | 2026-03-30 15:53 | 2025-12-15 |  | 2026-02-28 |  | 2026-03-12 |  | 2026-03-15 |  | 2026-03-18 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-18 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-25 |  | 2026-03-26 |  |  |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-05 |  | 2026-04-05 | [6 empty] | 2026-04-11 |  | 2026-04-20 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-23 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-04-05 |  | 2026-03-03 |  | Unknown | 2025-12-14 | 2025-12-14 18:00 | 0 | 0 | 0 | 0 | 0 | 0 | 982424 | 173530 | 2026-03-30 18:57:48 +0530 | Aparna | RGM DCM: RGM MOM Interior Design DiscussionClient DetailsClient Name:Â Navya / SriramMembers:Â 2 PeopleLocation:Â YelenahalliConfiguration:Â 3BHKFacing:Â EastProfession:Â ITBudget:Â 7- 8 LakhsTheme:Â To be finalizedEntrance / FoyerShoe unit planned onÂ left side of entrance doorIntegrated seating provisionÂ includedLiving RoomTV Unit:Â Base unit withÂ 4 ft wall panelingLighting:Â Provision within panelingSeating:Â L-shapeÂ 7-seater sofaPooja Unit:Â Planned onÂ kitchen-facing wallDining AreaCrockery Unit:Base + wall cabinetsOneÂ tall unit with solid shuttersMirror panelingÂ between unitsSink Placement:Â To beÂ checked at cornerDining Table:Â Yet to be finalizedKitchenLayout:Â U-shaped kitchenUnits:Base units withÂ cylinder unitWall cabinets +Â L-shaped loftAppliances Planned:CooktopMicrowaveRefrigeratorUtility AreaProvision for:Dishwasher (future)Washing machineUnits:Base unit for sinkWall cabinetsMaster Bedroom (MBR)WardrobeÂ with adjacentÂ long mirrorBed:Â King-size bedStudy Unit:Â Ledge near windowBedroom 1 & Bedroom 2WardrobeÂ in both roomsMirror placementÂ adjacent to wardrobeFinishes & MaterialsGranite:Â To be used inKitchenUtilityDining area | 2026-03-30 18:56:56 +0530 | Aparna | MOM Interior Design DiscussionClient DetailsClient Name: Navya / SriramMembers: 2 PeopleLocation: YelenahalliConfiguration: 3BHKFacing: EastProfession: ITBudget: 78 LakhsTheme: To be finalizedEntrance / FoyerShoe unit planned on left side of entrance doorIntegrated seating provision includedLiving RoomTV Unit: Base unit with 4 ft wall panelingLighting: Provision within panelingSeating: L-shape 7-seater sofaPooja Unit: Planned on kitchen-facing wallDining AreaCrockery Unit:Base + wall cabinetsOne tall unit with solid shuttersMirror paneling between unitsSink Placement: To be checked at cornerDining Table: Yet to be finalizedKitchenLayout: U-shaped kitchenUnits:Base units with cylinder unitWall cabinets + L-shaped loftAppliances Planned:CooktopMicrowaveRefrigeratorUtility AreaProvision for:Dishwasher (future)Washing machineUnits:Base unit for sinkWall cabinetsMaster Bedroom (MBR)Wardrobe with adjacent long mirrorBed: King-size bedStudy Unit: Ledge near windowBedroom 1 & Bedroom 2Wardrobe in both roomsMirror placement adjacent to wardrobeFinishes & MaterialsGranite: To be used inKitchenUtilityDining area
17708 | Sub Project |  | MSPARK TRADELINKS (OPC) PRIVATE LIMITED Hemani Mohammd Ali | Piramal Aranya | MUM - GOR |  |  | Manzoor Shaikh | Shantanu Parakh |  |  | Nilesh Patel |  | Murali S |  |  | Active | Handover | Project Closure Pending | 0 | 0 | 0 | 0 | 35499 | 78 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-17 | 2026-01-14 16:20 | 2025-12-17 | 2026-01-14 16:21 | 2026-01-16 | 2026-01-14 16:22 | 2026-01-16 | 2026-01-14 16:27 | 2026-01-15 | 2026-01-14 16:30 | 2026-01-15 | 2026-01-14 16:33 | 2026-01-14 | 2026-01-14 16:21 | 2026-01-15 | 2026-01-14 16:22 | 2026-01-14 | 2026-01-14 16:24 | 2026-01-15 | 2026-01-14 16:24 | 2026-01-14 | 2026-01-14 16:35 | 2026-01-17 | 2026-01-14 16:35 | 2026-01-14 | 2026-01-14 16:36 | 2026-01-15 | 2026-01-14 16:37 | 2026-01-15 | 2026-01-14 16:37 |  |  | 2026-01-16 | 2026-01-14 16:40 | 2026-01-15 | 2026-01-14 16:42 | 2026-01-17 | 2026-01-14 16:42 | 2026-01-14 | 2026-01-14 16:43 |  |  |  |  | 2026-01-23 10:44 | 2026-01-24 | 2026-01-23 16:21 | 2026-01-29 | 2026-01-27 10:11 | 2026-01-28 | 2026-02-12 13:42 | 2026-01-27 | 2026-02-19 15:12 | 2026-02-24 | 2026-02-25 13:50 | 2026-02-27 | 2026-03-17 11:32 |  |  | 2026-04-29 | 2026-04-28 22:52 | 2026-04-30 | 2026-04-28 23:15 | 2026-04-28 | 2026-04-28 23:18 |  |  |  |  | 2026-01-14 | 2026-01-15 14:05 | 2026-01-15 | 2026-01-14 16:25 | Unknown | 2025-12-16 | 2026-01-14 16:19 | 0 | 0 | 0 | 0 | 60166.8983 | 5415 | 30083.9 | 0
17710 | Sub Project |  | Tina Bade | Runwal Bliss | MUM - GOR |  |  | Avinash Jaiswal | Shantanu Parakh |  |  | Faizal Shaikh | Rizwan Mistry | Murali S |  |  | Active | Handover | Project Closure Pending | 0 | 0 | 0 | 0 | 50000 | 98 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-17 | 2026-02-05 17:18 | 2025-12-17 | 2026-02-05 17:18 | 2026-02-07 | 2026-02-05 17:19 | 2026-02-07 | 2026-02-05 17:20 | 2026-02-06 | 2026-02-05 17:21 | 2026-02-06 | 2026-02-05 17:22 | 2026-02-05 | 2026-02-05 17:19 | 2026-02-06 | 2026-02-05 17:19 | 2026-02-05 | 2026-02-05 17:19 | 2026-02-06 | 2026-02-05 17:19 | 2026-02-05 | 2026-02-05 17:22 | 2026-02-08 | 2026-02-05 17:23 | 2026-02-05 | 2026-02-05 17:23 | 2026-02-06 | 2026-02-05 17:24 | 2026-02-06 | 2026-02-05 17:24 |  |  | 2026-02-07 | 2026-02-05 17:25 | 2026-02-06 | 2026-02-05 17:26 | 2026-02-08 | 2026-02-05 17:26 | 2026-02-05 | 2026-02-05 17:26 |  |  |  |  | 2026-03-02 11:17 | 2026-03-15 | 2026-03-14 22:41 | 2026-03-18 | 2026-03-16 16:57 | 2026-03-17 | 2026-04-07 19:59 | 2026-03-16 | 2026-04-08 18:23 | 2026-04-08 | 2026-04-08 18:29 | 2026-04-09 | 2026-04-08 18:35 |  |  | 2026-04-10 | 2026-04-08 19:07 | 2026-04-10 | 2026-04-08 19:13 | 2026-04-08 | 2026-04-08 19:36 |  |  |  |  | 2026-02-20 | 2026-03-02 11:16 | 2026-02-06 | 2026-02-05 17:20 | Unknown | 2025-12-16 | 2026-02-05 17:18 | 0 | 0 | 0 | 0 | 42372 | 7627 | 42372 | 7627
17738 | Turnkey | Dec'25 | Navendu Kumar | venus apt | MUM - GOR | Yes | Shreya Sonavane |  | Shahid Chougley | [5 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 1064095 | 9999 | 0 | 0 | 0 | 207 | 0 | 96411 | 212819 | 351905 | 392961.2 |  |  | 2025-12-21 | 2026-01-21 18:17 | 2025-12-21 |  | 2026-01-21 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 | [6 empty] | 2026-03-04 |  | 2026-03-13 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-16 |  |  |  | 2026-04-07 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-02-26 |  | 2026-01-24 |  | Unknown | 2025-12-20 | 2025-12-31 15:31 | 0 | 0 | 0 | 0 | 0 | 0 | 901775 | 162319
17740 | Turnkey | Dec'25 | Fidgen X Advisors Private Limited | other | BNG - HSR | Yes | Aishwarya C | Akshay Ds | Kowshik |  | Sethuragavan R | Affaan Abdulla | Jairam Joshi | Murali S | Varun Mandana | Suchendra Shetty | Active | Handover | Project Closure Pending | 1033814 | 1033814 | 1142916 | 1131653 | 1081314 | 12 | 1 | 0 | 0 | 0 | 0 |  |  | 2025-12-21 | 2026-02-09 13:48 | 2026-02-09 | 2026-02-09 14:17 | 2026-02-11 | 2026-02-11 14:41 | 2026-03-07 | 2026-03-07 17:29 | 2026-03-15 | 2026-03-14 15:31 |  |  | 2026-02-11 | 2026-02-11 14:41 | 2026-02-12 | 2026-02-11 15:44 | 2026-02-11 | 2026-02-23 15:40 | 2026-02-25 | 2026-02-25 17:43 | 2026-03-15 | 2026-03-15 18:05 | 2026-03-18 | 2026-03-17 21:04 | 2026-03-18 | 2026-03-17 20:29 | 2026-03-25 | 2026-03-25 16:38 | 2026-03-26 | 2026-03-26 11:51 |  |  | 2026-04-15 | 2026-04-19 09:47 | 2026-04-19 | 2026-04-19 14:01 | 2026-04-22 | 2026-04-19 14:57 | 2026-04-19 | 2026-04-22 21:22 |  |  |  |  | 2026-04-24 14:22 | 2026-05-01 | 2026-04-30 22:28 | 2026-05-27 | 2026-05-20 18:04 | 2026-05-20 | 2026-05-19 19:44 | 2026-05-20 | 2026-05-21 13:22 | 2026-05-22 | 2026-05-22 18:40 | 2026-05-24 | 2026-05-26 14:57 |  |  | 2026-07-03 | 2026-07-03 21:44 | 2026-07-11 | 2026-07-03 21:45 | 2026-07-12 | 2026-07-03 22:26 |  |  |  |  | 2026-04-19 | 2026-04-23 19:56 | 2026-03-07 | 2026-03-07 16:57 | Site is Non-RTMI | 2025-12-20 | 2025-12-20 17:22 | 1200698.88 | 197224 | 1225686.1389 | 202370 | 1179165.9215 | 194692 | 1179165.9215 | 194692 | 2026-07-03 02:26:34 +0530 | Jairam Joshi | Execution: QC - 2nd July HO - 3rd July | 2026-06-16 17:57:05 +0530 | Jairam Joshi | Some Image was uploaded | 2026-06-04 18:50:58 +0530 | Jairam Joshi | Some Image was uploaded
17765 | Sub Project |  | Nagesh Patil | SKGS Sambha | MUM - GOR | Yes | Pratima Kajwe | Manzoor Shaikh | Safalta Karkera | Neha Singh | Neha Singh | [5 empty] | Active | Preproduction | Hoto | 112481 | 0 | 0 | 0 | 0 | 181 | 0 | 0 | 0 | 72232 | 40249.2 |  |  | 2025-12-22 | 2026-01-15 17:00 | 2025-12-22 | 2026-01-15 17:00 | 2026-01-17 | 2026-01-15 17:00 | 2026-01-17 | 2026-01-15 17:02 | 2026-01-16 | 2026-01-15 17:04 | 2026-01-16 | 2026-01-15 17:04 | 2026-01-15 | 2026-01-15 17:01 | 2026-01-16 | 2026-01-15 17:01 | 2026-01-15 | 2026-01-15 17:01 | 2026-01-16 | 2026-01-15 17:01 | 2026-01-15 | 2026-01-15 17:05 | 2026-01-18 | 2026-01-15 17:05 | 2026-01-15 | 2026-01-15 17:06 | 2026-01-16 | 2026-01-15 17:06 | 2026-01-23 | 2026-01-15 16:59 |  |  | 2026-01-18 |  | 2026-01-19 |  | 2026-01-22 |  | 2026-01-22 | [6 empty] | 2026-01-28 |  | 2026-02-06 |  | 2026-02-05 |  | 2026-02-06 |  | 2026-02-07 |  | 2026-02-09 |  |  |  | 2026-03-03 |  | 2026-03-05 |  | 2026-03-06 | [5 empty] | 2026-01-22 |  | 2026-01-16 | 2026-01-15 17:01 | Unknown | 2025-12-21 | 2026-01-15 17:00 | 0 | 0 | 0 | 0 | 0 | 0 | 95323 | 17158
17779 | Turnkey | Dec'25 | Debadatta Hota | Shobha Sentosa | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik |  | Sethuragavan R | Suchendra Shetty | Jairam Joshi |  | Chanakya Panigrahi | Vishwa Hiremath | Hold | Preproduction | 3D Sign off | 1959963 | 254934 | 1274668 | 1981955 | 1959963 | 5 | 41 | 0 | 0 | 960849 | 744179.6 |  |  | 2025-12-22 | 2026-01-07 11:49 | 2026-01-03 | 2026-01-11 18:53 | 2026-01-27 | 2026-01-27 13:13 | 2026-03-30 | 2026-03-30 17:49 | 2026-04-10 | 2026-04-19 20:01 | 2026-04-25 | 2026-04-24 12:56 | 2026-01-27 | 2026-01-30 10:15 | 2026-01-28 | 2026-01-30 10:16 | 2026-01-30 | 2026-01-31 17:34 | 2026-02-20 | 2026-02-20 15:05 | 2026-04-27 | 2026-04-27 13:27 | 2026-04-27 | 2026-04-27 15:42 | 2026-04-25 | 2026-04-20 10:28 | 2026-05-02 | 2026-05-01 23:42 | 2026-05-02 | 2026-05-02 00:38 |  |  | 2026-05-26 | 2026-05-30 16:40 | 2026-05-30 | 2026-05-30 19:05 | 2026-08-31 |  | 2026-08-31 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-31 |  | 2026-02-21 | 2026-03-30 17:45 | Site is RTMI | 2025-12-21 | 2026-01-07 11:48 | 1399277.2344 | 231051 | 2145101.2696 | 354196 | 2175644.3217 | 350841 | 2175644.3217 | 350841 | 2026-06-04 12:41:34 +0530 | Abhinandan K S | Some Image was uploaded | 2026-06-04 11:18:18 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-30 17:43:01 +0530 | Janush Bojamma C T | Some Image was uploaded
17784 | Turnkey | Dec'25 | Pradeep Shinde | Ashtavinayak | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Hold | Design | Design Finalization | 944553 | 126681 | 1029483 | 0 | 0 | 74 | 94 | 0 | 156685 | 295805 | 365382 |  |  | 2025-12-22 | 2026-01-08 11:58 | 2025-12-26 | 2026-01-08 14:57 | 2026-01-08 | 2026-01-08 15:01 | 2026-04-05 | 2026-04-05 11:32 | 2026-09-01 |  | 2026-09-04 |  | 2026-01-08 | 2025-12-31 05:30 | 2026-01-09 | 2026-01-09 17:42 | 2026-01-09 | 2026-01-28 12:49 | 2026-02-08 | 2026-02-08 17:08 | 2026-09-04 |  | 2026-09-07 |  | 2026-09-07 |  | 2026-09-11 |  | 2026-09-12 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-22 |  | 2026-09-22 | [6 empty] | 2026-09-28 |  | 2026-10-07 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-08 |  | 2026-10-10 |  |  |  | 2026-11-01 |  | 2026-11-03 |  | 2026-11-04 | [5 empty] | 2026-09-22 |  | 2026-02-09 | 2026-02-17 13:26 | Site is RTMI | 2025-12-21 | 2025-12-23 11:52 | 1077392.7525 | 179921 | 0 | 0 | 0 | 0 | 1055353.6675 | 176118 | 2026-06-05 12:11:57 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-15 14:47:04 +0530 | Vishakha Vaishnav | Cx said that due to some financial issues he will sell his apartment | 2026-04-12 18:16:17 +0530 | Reshma Melanta | Some Image was uploaded
17785 | Turnkey | Dec'25 | Tarun Negi | L&T Elixir Reserve | MUM - GOR | Yes | Yash Jain |  | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 2476209 | 9999 | 0 | 0 | 0 | 204 | 0 | 237622 | 495242 | 789519 | 943827.2 |  |  | 2025-12-22 | 2026-01-13 12:13 | 2025-12-22 |  | 2025-12-26 |  | 2026-01-07 |  | 2026-01-10 |  | 2026-01-13 |  | 2025-12-26 |  | 2025-12-27 |  | 2025-12-27 |  | 2025-12-28 |  | 2026-01-13 |  | 2026-01-16 |  | 2026-01-16 |  | 2026-01-20 |  | 2026-01-21 |  |  |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-31 |  | 2026-01-31 | [6 empty] | 2026-02-06 |  | 2026-02-15 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-18 |  |  |  | 2026-03-12 |  | 2026-03-14 |  | 2026-03-15 | [5 empty] | 2026-01-31 |  | 2025-12-29 |  | Unknown | 2025-12-21 | 2025-12-23 11:52 | 0 | 0 | 0 | 0 | 0 | 0 | 2098482 | 377726 | 2026-01-08 10:23:55 +0530 | Yash Jain | DCM: Mr & MR.NegiDCM 3-1-2025 Apartment hght 9'6'' Entry possession in 15 days 1230 SQ FT INCL balcony (excl 1130 sq ft) 3bhkÂ family of 5 Budget 20 lakhs end to end Entrance area kitchen renovate console with a niche cutting down the 6 inch wall inside Bedroom 1- grandmom and daughter Wardrobe qsb tv uni with drawer storage and mirrorÂ side tal unit storage besides bed and top more additional loft above bed All bathrooms - we need a vanity unit below basin. Living and dining Only seating maximum 14-16 seatings at a time and no tv unit in living area Mandir unit with crockery touching the bedroom 1 wall. Dining 6 seater round or rectangle dcor wall in dining table areaÂ Balcony bar unitÂ existing dining wooden table 6 seater to be used if possibleÂ master bedroomÂ top left Existing chairs to be used in this bedrom loose product New bed, wardrobe side table ,dressing table, additional storage for maam, other than wardrobe, Bedroom 2 Son's room King size bed, tall bed, wardrobes Tv unit, sleek ledge , ottoman with wing chair. 5' by 3' painting behind main sofa unitÂ Â tv unit and cx bedroom
17795 | Turnkey | Dec'25 | Yashaswini P | independent house | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [7 empty] | Hold | Preproduction | Site Readiness 1 | 2548042 | 492999 | 2297413 | 2548042 | 0 | 2 | 15 | 0 | 0 | 1102336 | 952706.8 |  |  | 2025-12-25 | 2026-01-02 12:00 | 2025-12-24 | 2026-01-02 12:16 | 2026-01-04 | 2026-01-02 12:23 | 2026-06-27 | 2026-06-25 11:17 | 2026-06-26 | 2026-06-26 11:58 |  |  | 2026-01-02 | 2025-12-31 05:30 | 2026-01-03 | 2026-01-07 11:14 | 2026-01-07 | 2026-01-10 15:55 | 2026-01-15 | 2026-01-15 14:08 | 2026-06-26 | 2026-06-26 12:10 | 2026-07-06 | 2026-06-28 13:10 | 2026-06-30 | 2026-06-22 | 2026-09-15 |  | 2026-09-16 |  |  |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-26 |  | 2026-09-26 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-26 |  | 2026-06-11 | 2026-06-13 13:04 | Site is RTMI | 2025-12-24 | 2025-12-26 11:53 | 1946960 | 350452 | 2818275.6027 | 456947 | 0 | 0 | 2818275.6027 | 456947 | 2026-04-15 17:57:50 +0530 | Parasa Sri | The client is out of station this week. She will share the site pictures in the group once she returns. | 2026-01-16 13:02:00 +0530 | Parasa Sri | Welcome call done | 2026-01-10 15:55:15 +0530 | Bency Chacko | Possession - April mid 2026 Design meetings - Weekends IDM - 25th Jan 2026 B2C - Self-funded No on-site civil work No Vendor work is planned Checklist cleared, timelines cleared. Offers, Quote is cleared.
17813 | Turnkey | Dec'25 | Mr.Avinash Bhaskar Sonawane | Raymond Ten X | MUM - Thane | Yes | Sagarika Gawai | Divya Rahangdale | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Lost | Design | Design Finalization | 946279 | 105999 | 946279 | 0 | 0 | 183 | 0 | 0 | 177885 | 292362 | 370033.6 |  |  | 2025-12-26 | 2026-01-03 13:05 | 2026-01-03 | 2026-01-03 13:07 | 2026-01-07 | 2026-01-07 19:31 | 2026-03-02 | 2026-02-20 12:01 | 2026-04-30 |  | 2026-05-03 |  | 2026-01-07 | 2026-01-07 19:47 | 2026-01-08 | 2026-01-07 19:47 | 2026-01-07 | 2026-01-13 11:13 | 2026-01-21 | 2026-01-21 16:36 | 2026-05-03 |  | 2026-05-06 |  | 2026-05-06 |  | 2026-05-10 |  | 2026-05-11 |  |  |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-21 |  | 2026-05-21 | [6 empty] | 2026-05-27 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-08 |  |  |  | 2026-06-30 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-05-21 |  | 2026-02-17 | 2026-02-04 19:36 | Site is RTMI | 2025-12-25 | 2025-12-26 13:31 | 1080148.6612 | 174474 | 0 | 0 | 0 | 0 | 1080148.6612 | 174474 | 2026-02-11 18:21:14 +0530 | Sagarika Gawai | DDM1: Based on 27th Jan 2026, Tuesday meeting, below is a list of all the requirements that were discussed during the meeting: Living area- Design on hold, based on the position of the projector and sound system placement, the entire seating arrangement distance will be finalised, which would be post possession. For now, the space planning which was considered during CDP initial meeting, the same placement will be considered. Kitchen- Wall units- only on one side glass shutters and cooking side one 900mm length shutter only, to make the space look spacious. Base unit- wicker basket, bottle pull out, 5 drawers and rest shutters Loft unit- both sides Bedroom 1- Single invisible bed Two door openable shutter wardrobe + one door openable shutter wardrobe - internals finalised Placement finalised Master Bedroom- 4 family members will stay in the room- 2 toodlers and parents Based on the size- huge matteress requirement is considered as bed is not required Based on the mattress size placement the study table needs to be aligned as monitor and WFH requirement needs to be adjusted As mentioned there are budget constraint issues, the costing might increase with top storage and study unit Along with Sliding wardrobe, tall unit with 3 drawers needs to be added, although budget needs to be increased if another unit is required. The same has been conveyed during the meeting Based on the above discussion, the costing would increase if we add any other line item as mentioned during the meeting, please note. | 2026-01-21 16:34:13 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-01-13 11:13:08 +0530 | Royden Henriques | Cx will pay 20% between 27th - 31st Jan
17816 | Turnkey | Dec'25 | Dr Mahajan | Icon | MUM - GOR | Yes | Karan Chavda |  | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 3303957 | 9999 | 0 | 0 | 0 | 202 | 0 | 320397 | 660791 | 1101518 | 1211251.6 |  |  | 2025-12-26 | 2026-01-09 18:10 | 2025-12-27 |  | 2025-12-25 |  | 2026-01-06 |  | 2026-01-09 |  | 2026-01-12 |  | 2025-12-25 |  | 2025-12-26 |  | 2025-12-26 |  | 2025-12-27 |  | 2026-01-12 |  | 2026-01-15 |  | 2026-01-15 |  | 2026-01-19 |  | 2026-01-20 |  |  |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-01-30 | [6 empty] | 2026-02-05 |  | 2026-02-14 |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-17 |  |  |  | 2026-03-11 |  | 2026-03-13 |  | 2026-03-14 | [5 empty] | 2026-01-30 |  | 2025-12-28 |  | Unknown | 2025-12-25 | 2026-01-09 18:09 | 0 | 0 | 0 | 0 | 0 | 0 | 2799964 | 503993 | 2026-01-14 16:46:09 +0530 | Nachiket Patel | Some Image was uploaded
17821 | Turnkey | Dec'25 | PARSHVANATH ENTERPRISES | Kalpatru shrishti namah | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Akash Jadhav | Sandeep Tiwari | Murali S | Harshaan Tiku | Abdul Shafeen | Active | Production | 100% Payment | 2207631 | 1817631 | 2004277 | 2123212 | 2302631 | 15 | 0 | 0 | 0 | 0 | 390000 |  |  | 2025-12-26 | 2026-01-01 17:18 | 2026-01-03 | 2026-01-03 18:47 | 2026-01-09 | 2026-01-03 20:00 | 2026-04-14 | 2026-04-12 20:59 | 2026-04-17 | 2026-04-12 21:00 | 2026-04-20 | 2026-04-19 15:26 | 2026-01-03 | 2025-12-28 10:59 | 2026-01-04 | 2026-01-07 16:41 | 2026-01-07 | 2026-01-09 12:47 | 2026-01-15 | 2026-01-15 17:29 | 2026-04-29 | 2026-04-29 19:43 | 2026-05-02 | 2026-04-29 19:55 | 2026-04-22 | 2026-04-29 | 2026-05-20 | 2026-05-19 11:10 | 2026-05-20 | 2026-05-19 11:36 |  |  | 2026-05-22 | 2026-06-12 20:55 | 2026-06-12 | 2026-06-12 22:00 | 2026-06-15 | 2026-06-12 22:04 | 2026-06-12 | 2026-06-17 18:45 |  |  |  |  | 2026-06-19 17:00 | 2026-06-25 | 2026-06-24 19:27 | 2026-07-02 | 2026-06-30 19:27 | 2026-07-01 |  | 2026-06-30 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-08-20 | [5 empty] | 2026-06-21 | 2026-06-19 16:59 | 2026-01-16 | 2026-04-12 20:16 | Site is RTMI | 2025-12-25 | 2025-12-26 22:14 | 1832467.9934 | 305737 | 2336711.0947 | 392524 | 2859210.9275 | 458028 | 2859210.9275 | 458028 | 2026-06-18 19:35:01 +0530 | Reshma Melanta | RECLINER NEED TO CHECK IF THE SAME CAN BE CHANGED IF THE ADD ON RECLINER IN BONITO STUDIO | 2026-06-18 19:15:34 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-03 16:30:03 +0530 | Reshma Melanta | 5% DM FEE ALREADY ADDED IN THE QUOTE HAS DISCOUNT.
17823 | Turnkey | Dec'25 | Anantha Kumar | Devagiri Opal | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1046604 | 9999 | 1046604 | 0 | 0 | 169 | 0 | 94661 | 209321 | 321256 | 411367.2 |  |  | 2025-12-27 | 2026-01-21 11:22 | 2026-01-21 | 2026-01-21 12:56 | 2026-01-27 | 2026-01-27 19:34 | 2026-02-08 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-21 |  | 2026-02-22 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-01-30 |  | Unknown | 2025-12-26 | 2026-01-20 18:29 | 886953 | 159651 | 0 | 0 | 0 | 0 | 886953 | 159651 | 2026-01-21 12:54:31 +0530 | Adarsh K | DCM: Client - Anantha Kumar Property - Devagiri Opal - 2bhk Low maintanance - Functional Spaces, Less decor. - Utilitarian. Main door is facing North RGM Budget - Within 10 lakhs Area Wise -Â Footwear storage - Outside scope Living - TV Unit unit on longer wall opp sofa Sofa - 4 seater - L shape Dining - Foldable dining table & Chairs in Living room near TV unit as per layout. Dining area - Bay window seater and Pooja Kitchen - As per layout, Loft required, Effective StorageÂ Utility - Washing Machine & Dishwasher space. Master Bedrrom - As per layout, Wardrobe Dresser, and Foldable study desk Bedroom 2 - Wardrobe & Dresser - Sliding. Dining wash basin - Vanity. 31st - next meeting.
17826 | Turnkey | Dec'25 | Nilesh Shivaji Chalke | Shivkrupa | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera |  |  | Rajkumar Suthar | Rizwan Mistry | Murali S | Avi Thakkar | Aakash Gaikwad | Active | Production | 100% Payment | 1100406 | 859421 | 859726 | 1049838 | 1120406 | 12 | 0 | 0 | 0 | 0 | 240985 |  |  | 2025-12-26 | 2026-01-13 12:24 | 2026-01-13 | 2026-01-13 16:01 | 2026-01-13 | 2026-01-13 16:19 | 2026-03-29 | 2026-03-29 18:23 | 2026-05-09 | 2026-05-09 11:48 | 2026-05-12 | 2026-05-09 15:02 | 2026-01-13 | 2026-01-15 18:21 | 2026-01-14 | 2026-01-16 10:56 | 2026-01-16 | 2026-01-20 13:05 | 2026-01-29 | 2026-01-29 17:16 | 2026-05-09 | 2026-05-09 18:18 | 2026-05-12 | 2026-05-09 20:01 | 2026-05-22 | 2026-04-23 | 2026-05-13 | 2026-05-10 15:55 | 2026-05-11 | 2026-05-10 15:56 |  |  | 2026-05-27 | 2026-06-10 19:40 | 2026-06-11 | 2026-06-11 19:41 | 2026-06-14 | 2026-06-12 19:49 | 2026-06-12 | 2026-06-13 17:32 |  |  |  |  | 2026-06-22 11:52 | 2026-06-27 | 2026-06-26 20:52 | 2026-07-04 | 2026-07-03 19:53 | 2026-07-12 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-14 | 2026-06-22 11:51 | 2026-01-30 | 2026-02-07 14:24 | Site is Non-RTMI | 2025-12-25 | 2026-01-13 12:15 | 944807.2225 | 154026 | 1060669.6689 | 183026 | 1123055.2036 | 193790 | 1123055.2036 | 193790 | 2026-07-03 16:21:45 +0530 | Meet Shah | Others: | 2026-06-20 18:22:56 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-05 11:50:08 +0530 | Manzoor Shaikh | Some Image was uploaded
17832 | Turnkey | Dec'25 | Sharavani Sawant | Lodha Palava phase 2 | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1359402 | 407821 | 1264023 | 1359402 | 0 | 2 | 44 | 0 | 0 | 475444 | 476137.2 |  |  | 2025-12-28 | 2026-01-12 12:00 | 2026-01-10 | 2026-01-13 11:03 | 2026-01-19 | 2026-01-13 12:41 | 2026-03-26 | 2026-03-05 16:08 | 2026-04-18 | 2026-04-18 18:02 |  |  | 2026-01-13 | 2026-01-13 12:56 | 2026-01-14 | 2026-01-13 12:57 | 2026-01-13 | 2026-01-15 12:22 | 2026-02-05 | 2026-02-05 12:38 | 2026-06-24 | 2026-06-24 15:21 | 2026-06-26 | 2026-06-26 19:35 | 2026-06-24 | 2026-06-25 | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-11 |  | 2026-07-11 | [6 empty] | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-07-11 |  | 2026-03-10 | 2026-03-05 11:26 | Site is RTMI | 2025-12-27 | 2025-12-31 11:33 | 1392839.999 | 215698 | 1534233.1586 | 237874 | 0 | 0 | 1534233.1586 | 237874 | 2026-04-16 19:38:18 +0530 | Sagarika Gawai | Entrance Area Safety door and shoe rack design to be considered post site measurement. Final design will depend on available space and society norms. Living Area TV unit design was finalized in the previous meeting. Reference has been shared; 2 design options will be proposed. Mandir Area Mandir to be designed next to the entrance door. Design to include jali work on both sides. Wallpaper to be added at the back. Provision for tray, 2 drawers, and a seating stool. Dining Area 4-seater dining table planned. Wall behind dining to be highlighted with wallpaper. Multiple wallpaper/design options to be shared. Sofa / Seating Area Seating options: L-shaped or 3+1+1 to be suggested. Sofa back wall design options to be provided. False ceiling and pelmet design to be aligned accordingly. Passage Area Design option already discussed. Lighting plan to be incorporated and shown in 3D view. Bedroom 2 (Guest / Multipurpose Room) Furniture layout finalized (wardrobe, study table, sofa-cum-bed). 2-door wardrobe with loft included. Study table with loft provided. Wallpaper and wall design concepts to be shared. False ceiling with profile lighting to be designed. Sons Bedroom Bed back wall reference shared. Design to be adjusted as per room size. Additional design options to be suggested. 3-door wardrobe planned (1 with mirror, 2 shutters). Wardrobe internals finalized. Color options selected; 23 design options to be shared. False ceiling design to be included. Master Bedroom Dressing table replaced with wardrobe design (as per sample flat concept). No loft storage due to beam constraints. 6-door wardrobe planned; internals finalized. Color options to be provided. Bed back wall design options to be shared. TV unit / TV wall design options to be suggested. Curtain and bed color to be finalized based on overall theme. False ceiling to include periphery design with profile lighting. Master Washroom Vanity design and color options to be suggested post site consideration. Kitchen Color options finalized. 3D views to be presented in the next meeting. General Note Overall design concepts and render views will be presented in the next meeting. | 2026-03-24 17:02:18 +0530 | Anamika Dolai | Hold 10th of april | 2026-03-13 15:30:22 +0530 | Divya Rahangdale | Some Image was uploaded
17850 | Turnkey | Dec'25 | Vaibhavi Patki | * | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Shashwat Joshi | Rizwan Mistry | Murali S | Manasi Patil | Vinay Surve | Active | Production | Dispatch Due | 2369125 | 2369125 | 1786240 | 2535088 | 2491689 | 20 | 4 | 0 | 0 | 0 | 0 |  |  | 2025-12-28 | 2026-01-04 19:00 | 2026-01-04 | 2026-01-04 19:37 | 2026-01-07 | 2026-01-07 11:43 | 2026-02-10 | 2026-02-05 12:58 | 2026-03-15 | 2026-03-15 12:18 | 2026-03-26 | 2026-03-26 12:46 | 2026-01-07 | 2026-01-07 18:21 | 2026-01-08 | 2026-01-08 14:37 | 2026-01-08 | 2026-01-10 16:51 | 2026-01-14 | 2026-01-14 18:30 | 2026-03-26 | 2026-03-26 16:32 | 2026-03-29 | 2026-03-30 16:12 | 2026-02-14 | 2026-02-09 20:13 | 2026-04-19 | 2026-04-23 16:38 | 2026-04-24 | 2026-04-23 16:38 |  |  | 2026-04-25 | 2026-05-10 18:28 | 2026-05-10 | 2026-05-12 16:25 | 2026-05-13 | 2026-05-14 17:04 | 2026-05-14 | 2026-05-21 18:29 |  |  |  |  | 2026-06-04 15:30 | 2026-06-23 | 2026-06-22 21:20 | 2026-06-26 | 2026-06-24 20:58 | 2026-06-25 | 2026-06-25 18:06 | 2026-06-24 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-05-25 | 2026-06-04 15:29 | 2026-01-15 | 2026-02-01 15:02 | Site is RTMI | 2025-12-27 | 2025-12-28 17:41 | 1891398.8517 | 318240 | 2592354.3335 | 440098 | 2512078.4722 | 433477 | 2512077.9444 | 414781 | 2026-06-21 18:53:55 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-19 16:58:10 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-17 11:00:06 +0530 | Manzoor Shaikh | Some Image was uploaded
17862 | Turnkey | Dec'25 | Aarya Capital Advisory Private Limited ( Pankaj Kumar Tripathi | Urban Grandeur | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh |  |  |  | Harshaan Tiku | Abdul Shafeen | Hold | Design | 60% Payment | 910566 | 250501 | 932051 | 861071 | 910566 | 3 | 109 | 0 | 0 | 318301 | 341763.6 |  |  | 2025-12-29 | 2026-01-02 01:56 | 2026-01-02 | 2026-01-02 17:19 | 2026-01-07 | 2026-01-07 11:25 | 2026-01-29 | 2026-01-29 17:49 | 2026-02-01 | 2026-01-29 17:54 | 2026-01-29 | 2026-01-29 18:00 | 2026-01-08 | 2025-12-31 05:30 | 2026-01-06 | 2026-01-03 21:27 | 2026-01-08 | 2026-01-09 14:04 | 2026-01-13 | 2026-01-13 18:18 | 2026-01-29 | 2026-01-29 18:59 | 2026-04-30 | 2026-01-31 19:31 | 2026-04-30 | 2026-01-31 | 2026-06-02 | 2026-05-20 14:44 | 2026-05-21 | 2026-05-20 14:45 |  |  | 2026-05-26 | 2026-05-28 18:11 | 2026-05-29 | 2026-05-29 19:48 | 2026-06-01 | 2026-05-29 20:02 | 2026-08-05 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-05-29 |  | 2026-01-14 | 2026-01-29 17:45 | Site is RTMI | 2025-12-28 | 2025-12-28 17:26 | 1039286.3489 | 168872 | 975609.8727 | 158044 | 1041139.1295 | 165594 | 1041139.1295 | 165594 | 2026-06-26 10:55:21 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-23 10:58:20 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-14 17:36:41 +0530 | Avinash Jaiswal | Some Image was uploaded
17864 | Turnkey | Dec'25 | Diksha Shah | Bhoomi Celestia | MUM - GOR | Yes | Yogini Chavan |  | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 5187916 | 9999 | 0 | 0 | 0 | 199 | 0 | 508793 | 1037583 | 1693341 | 1938200 |  |  | 2025-12-29 | 2026-01-09 18:12 | 2025-12-29 |  | 2026-01-15 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-01-16 |  | 2026-01-17 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-09 |  | 2026-02-10 |  |  |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-20 |  | 2026-02-20 | [6 empty] | 2026-02-26 |  | 2026-03-07 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-10 |  |  |  | 2026-04-01 |  | 2026-04-03 |  | 2026-04-04 | [5 empty] | 2026-02-20 |  | 2026-01-18 |  | Unknown | 2025-12-28 | 2026-01-09 18:11 | 0 | 0 | 0 | 0 | 0 | 0 | 4396539 | 791377 | 2026-01-13 18:28:38 +0530 | Safalta Karkera | DCM: 1. Please select your budget for Interior Designing? 2. Interior Designing to commence on the basis of 3. What is your Profession? 4. Who will be living in this home? 5. What activities do you usually perform at home? (Choose top 23) 6. What is your preferred entertainment style? 7. Do you prefer any Smart home features? 8. What is your possession date? ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Dcor & Living Room1. Choose your decor inspirations 2. Any specific signature design feature required Chandelier 3. Whats the primary use of your living room? Multipurpose 4. Any absolute no-go styles, colors, or materials? 5. Must-have furniture or features? Sofa, TV unit, Puja unit, Display unit , Statement Wall/ Feature Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Built-in oven, Microwave, Fridge, Hob, Chimney, Washing machine BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Sliding Master Bedroom - Additional units Study table, Dresser Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Sliding Other Bedroom - Additional units Study table , Bookshelf , Dresser BathroomsPreferred vanity style What do you prefer? Shower partitions What are your requirements for Utility Area? Bottom Storage Balcony & OutdoorHow do you intend to use your balcony for? b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? Final Vision1. Any space in the home that you want to put in Spotlight? Living room 2. Do you want the design to reflect any personal story, cultural influence, or special memory
17866 | Turnkey | Dec'25 | Krishna Dubey | REGENCY AVANA | MUM - Thane | Yes | Rinisha Masurkar | [9 empty] | Active | Prospect | DCM Due | 2443954 | 9999 | 0 | 0 | 0 | 199 | 0 | 234396 | 488791 | 840155 | 870612.8 |  |  | 2025-12-29 | 2026-01-08 18:49 | 2026-01-11 |  | 2026-01-10 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-11 |  | 2026-02-12 |  |  |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-22 |  | 2026-02-22 | [6 empty] | 2026-02-28 |  | 2026-03-09 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-12 |  |  |  | 2026-04-03 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-02-22 |  | 2026-01-20 |  | Unknown | 2025-12-28 | 2026-01-08 18:47 | 0 | 0 | 0 | 0 | 0 | 0 | 2071147 | 372806
17868 | Turnkey | Dec'25 | Sheth Mihir | Ajmera eden | MUM - GOR | Yes | Rajnish Mishra | Reshma Melanta | Safalta Karkera |  |  | Naushad Ansari | Rizwan Mistry | Murali S | Avi Thakkar | Aakash Gaikwad | Active | Production | Dispatch Due | 845904 | 845904 | 2248357 | 2592172 | 845904 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-29 | 2026-01-13 14:29 | 2026-01-11 | 2026-01-13 17:11 | 2026-01-11 | 2026-01-13 17:14 | 2026-03-07 | 2026-03-04 17:31 | 2026-03-23 | 2026-03-21 12:28 |  |  | 2026-01-13 | 2026-01-17 17:58 | 2026-01-14 | 2026-01-17 17:58 | 2026-01-18 | 2026-01-20 14:51 | 2026-01-24 | 2026-01-24 19:20 | 2026-03-25 | 2026-03-25 18:54 | 2026-03-26 | 2026-03-29 19:19 | 2026-03-26 | 2026-03-29 19:13 | 2026-04-06 | 2026-04-15 14:01 | 2026-04-15 | 2026-04-15 14:01 |  |  | 2026-05-26 | 2026-05-27 18:14 | 2026-06-03 | 2026-06-04 13:34 | 2026-06-24 | 2026-06-04 15:21 | 2026-06-05 | 2026-06-09 13:44 |  |  |  |  | 2026-06-22 11:26 | 2026-06-30 | 2026-06-29 21:53 | 2026-07-05 | 2026-07-03 16:13 | 2026-07-04 | 2026-07-10 12:01 | 2026-07-13 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-04 | [5 empty] | 2026-06-18 | 2026-06-22 11:25 | 2026-01-25 | 2026-03-04 17:30 | Site is RTMI | 2025-12-28 | 2026-01-04 15:47 | 2297020.3712 | 396359 | 2600937.8833 | 448805 | 801613 | 144290 | 801613 | 144290 | 2026-07-13 17:24:24 +0530 | Naushad Ansari | Execution: Modular furniture dispatch on site Cx on site carpentery work in progress at site. Floor covering Done. | 2026-07-09 00:14:39 +0530 | Naushad Ansari | Execution: Cx scope work going on. Modular in production. | 2026-06-24 02:25:02 +0530 | suraj kumar | Our Scope: Services - FC & DCModularGlass & MirrorProject status: Currently, Modular material is in progress.Floor covering to be planned.
17872 | Sub Project |  | Dinesh | Solaris | MUM - GOR |  | Pratima Kajwe | Avinash Jaiswal | Shantanu Parakh |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | -1058 | 0 | 0 | 0 | 53941 | 145 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-29 | 2026-01-09 12:26 | 2025-12-29 | 2026-01-09 12:27 | 2026-01-11 | 2026-01-09 12:27 | 2026-01-11 | 2026-01-09 12:43 | 2026-01-10 | 2026-01-09 12:44 | 2026-01-10 | 2026-01-09 12:46 | 2026-01-09 | 2026-01-09 12:27 | 2026-01-10 | 2026-01-09 12:27 | 2026-01-09 | 2026-01-09 12:27 | 2026-01-10 | 2026-01-09 12:28 | 2026-01-09 | 2026-01-09 12:46 | 2026-01-12 | 2026-01-09 12:47 | 2026-01-09 | 2026-01-09 12:47 | 2026-01-10 | 2026-01-09 12:54 | 2026-01-10 | 2026-01-09 12:54 |  |  | 2026-01-12 | 2026-01-09 12:56 | 2026-01-10 | 2026-01-09 12:56 | 2026-01-12 | 2026-01-09 12:57 | 2026-01-09 | 2026-01-09 12:57 |  |  |  |  | 2026-01-19 12:33 | 2026-01-21 | 2026-01-20 18:59 | 2026-01-23 | 2026-01-21 15:35 | 2026-01-22 | 2026-02-10 19:56 | 2026-01-21 | 2026-02-10 21:55 | 2026-02-10 | 2026-02-10 22:06 | 2026-02-11 | 2026-02-11 14:58 |  |  | 2026-02-13 | 2026-02-11 15:28 | 2026-02-13 | 2026-02-11 15:37 | 2026-02-11 | 2026-02-11 16:49 |  |  |  |  | 2026-01-14 | 2026-01-19 12:32 | 2026-01-10 | 2026-01-09 12:28 | Unknown | 2025-12-28 | 2026-01-09 12:26 | 0 | 0 | 0 | 0 | 45713 | 8228 | 45713 | 8228 | 2026-02-20 09:53:15 +0530 | Savita Parab | Execution: material delivered at site will close this project on 27th Feb | 2026-02-10 15:52:21 +0530 | Avinash Jaiswal | Some Image was uploaded | 2026-02-09 11:22:36 +0530 | Savita Parab | Execution: Site is ready for delivery profile mirror delivered ETA pending for chimney
17877 | Turnkey | Dec'25 | Pasalkar Infra (Prashant) Pasalkar | Yeno | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Suraj Jaiswar | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Active | Installation | Execution | 2407125 | 2419126 | 2710347 | 2626050 | 2704137 | 4 | 29 | 0 | 0 | 0 | 0 |  |  | 2025-12-29 | 2026-01-02 21:16 | 2025-12-30 | 2026-01-03 15:37 | 2026-01-09 | 2026-01-03 15:42 | 2026-03-06 | 2026-03-04 15:00 | 2026-03-09 | 2026-03-04 15:06 | 2026-03-29 | 2026-03-24 19:32 | 2026-01-05 | 2025-12-31 17:36 | 2026-01-10 | 2026-01-03 15:38 | 2026-01-04 | 2026-01-10 14:02 | 2026-01-15 | 2026-01-15 17:39 | 2026-03-25 | 2026-03-26 15:00 | 2026-03-29 | 2026-03-29 12:24 | 2026-03-27 | 2026-03-07 11:01 | 2026-04-30 | 2026-04-30 16:23 | 2026-05-01 | 2026-04-30 16:24 |  |  | 2026-05-12 | 2026-05-19 15:01 | 2026-05-21 | 2026-05-21 19:00 | 2026-05-24 | 2026-05-21 20:42 | 2026-05-21 | 2026-05-22 16:51 |  |  |  |  | 2026-05-30 13:15 | 2026-06-11 | 2026-06-10 19:45 | 2026-06-25 | 2026-06-22 23:59 | 2026-06-23 | 2026-07-03 17:05 | 2026-06-22 | 2026-07-09 11:28 | 2026-07-11 | 2026-07-11 17:15 | 2026-07-13 |  |  |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 | [5 empty] | 2026-05-28 | 2026-05-30 13:14 | 2026-01-16 | 2026-01-17 15:14 | Site is RTMI | 2025-12-28 | 2025-12-29 16:47 | 2296904 | 413442 | 2733749.9 | 480668 | 2766640.9 | 492580 | 2766640.6351 | 471985 | 2026-07-13 11:06:37 +0530 | Suraj Jaiswar | Execution: Modular material delivered at site on 11th July. Work has been start on 13th july. | 2026-07-06 23:12:50 +0530 | Suraj Jaiswar | Execution: Site is ready for modular. electrical qty sent to cx, | 2026-06-30 15:55:37 +0530 | Reshma Melanta | Some Image was uploaded
17880 | Turnkey | Dec'25 | Chheda Agro Food PArk Pvt. Limited datta | Shrishti Namah | MUM - GOR | Yes | Manisha Dubey | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Active | Design | Design Finalization | 806026 | 110818 | 806026 | 0 | 0 | 96 | 53 | 0 | 130990 | 272739 | 291479.6 |  |  | 2025-12-29 | 2026-01-30 13:01 | 2026-01-30 | 2026-01-30 15:00 | 2026-02-04 | 2026-02-04 20:08 | 2026-07-10 |  | 2026-07-13 |  | 2026-07-16 |  | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-05 16:42 | 2026-02-05 | 2026-02-16 14:00 | 2026-02-20 | 2026-02-20 16:10 | 2026-07-16 |  | 2026-07-19 |  | 2026-07-19 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-03 |  | 2026-08-03 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-08-03 |  | 2026-07-01 |  | Site is RTMI | 2025-12-28 | 2025-12-29 13:30 | 895585.4576 | 141258 | 0 | 0 | 0 | 0 | 895585.4576 | 141258 | 2026-05-15 15:17:12 +0530 | Vishakha Vaishnav | cx said that he has not received OC yet, asked for tentative possession customer said that he have no update he will connect us on whatsApp once he will receive possession | 2026-04-29 17:04:07 +0530 | Reshma Melanta | Some Image was uploaded | 2026-02-20 16:09:01 +0530 | Reshma Melanta | Welcome call done along with the DM DDM Dates -Â Ddm - 1Â - TBD Ddm -2Â - TBD Ddm-3 - TBD Possession date :Â MARCH END MIGHT GET PUSJED NOT SURE IDM dates: 18 Days payment Price protection for 150 days from the NET date. IM NOT ALIGN HAS NOT RECEIVE THE POSSESSION ADDED MYSELF TO THE GROUP
17882 | Turnkey | Dec'25 | Sonali Sule | Gurukrupa Dhyanam | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Moni Sahani |  | Active | Design | Design Finalization | 1259660 | 198970.84 | 1587819 | 0 | 0 | 152 | 0 | 0 | 178927 | 420624 | 461138 |  |  | 2025-12-28 | 2026-01-13 13:00 | 2026-01-13 | 2026-01-13 13:01 | 2026-01-13 | 2026-01-13 13:06 | 2026-05-31 | 2026-03-08 18:51 | 2027-01-14 |  | 2027-01-17 |  | 2026-01-13 | 2026-01-16 18:36 | 2026-01-14 | 2026-01-17 11:38 | 2026-01-17 | 2026-02-13 11:43 | 2026-02-20 | 2026-02-20 10:57 | 2027-01-17 |  | 2027-01-20 |  | 2027-01-20 |  | 2027-01-24 |  | 2027-01-25 |  |  |  | 2027-01-31 |  | 2027-02-01 |  | 2027-02-04 |  | 2027-02-04 | [6 empty] | 2027-02-10 |  | 2027-02-19 |  | 2027-02-18 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-22 |  |  |  | 2027-03-16 |  | 2027-03-18 |  | 2027-03-19 | [5 empty] | 2027-02-04 |  | 2026-05-22 | 2026-03-08 14:32 | Site is RTMI | 2025-12-27 | 2025-12-29 17:14 | 1673612.75 | 272718 | 0 | 0 | 0 | 0 | 1414468.735 | 227999 | 2026-06-14 19:35:36 +0530 | Shraddha Badgujar | The NET for this project was completed on 13 Jan 2026 with an estimated project value of 15,87,819.During the first DEM meeting, the client requested multiple design modifications, resulting in a project cost increase of approximately 3 lakhs - 4 lakhs.The client has also referred to online reviews and expressed concerns regarding the revised costing. Despite multiple attempts to explain the impact of the design changes and the costing process, the client has not aligned with the explanation | 2026-06-07 17:58:41 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-02 14:08:58 +0530 | Manzoor Shaikh | Called the customer as a retention effort, however, said couldn't continue as the cost is too high.
17887 | Turnkey | Dec'25 | Sheshmal Bhatia | 34 PARK ESTATE | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Shashwat Joshi | Rizwan Mistry | Murali S | Harshaan Tiku | Vinay Surve | Active | Installation | Execution | 1190187 | 1190187 | 1468245 | 1327881 | 1200187 | 55 | 24 | 0 | 0 | 0 | 0 |  |  | 2025-12-31 | 2026-01-02 19:36 | 2026-01-03 | 2026-01-03 18:33 | 2026-01-09 | 2026-01-03 20:00 | 2026-01-24 | 2026-01-14 12:49 | 2026-01-27 | 2026-01-14 12:51 | 2026-01-30 | 2026-01-15 08:49 | 2026-01-03 | 2025-12-31 05:30 | 2026-01-04 | 2026-01-07 16:31 | 2026-01-07 | 2026-01-10 09:42 | 2026-01-14 | 2026-01-14 11:05 | 2026-01-24 | 2026-01-24 18:13 | 2026-01-26 | 2026-01-26 20:04 | 2026-01-26 | 2026-01-26 | 2026-02-03 | 2026-02-04 12:54 | 2026-02-05 | 2026-02-04 20:50 |  |  | 2026-02-12 | 2026-02-17 12:37 | 2026-02-21 | 2026-02-21 18:33 | 2026-02-24 | 2026-02-21 19:31 | 2026-02-21 | 2026-02-27 15:35 |  |  |  |  | 2026-03-02 17:23 | 2026-03-11 | 2026-03-10 22:19 | 2026-03-22 | 2026-03-20 18:44 | 2026-03-21 | 2026-04-08 13:37 | 2026-03-20 | 2026-04-23 16:22 | 2026-04-23 | 2026-04-27 12:37 | 2026-06-16 |  |  |  | 2026-04-02 |  | 2026-04-04 |  | 2026-07-23 | [5 empty] | 2026-02-27 | 2026-03-02 17:22 | 2026-01-15 | 2026-01-14 11:12 | Site is RTMI | 2025-12-30 | 2025-12-31 14:08 | 1244275 | 223969 | 1439040.5337 | 248320 | 1326162.431 | 228842 | 1326162.431 | 228842 | 2026-07-13 19:03:37 +0530 | Shashwat Joshi | Execution: Execution: FLOOR COVERING IS COMPLETED ON SITE False ceiling framing work is completed on site Electrical conducting work is completed onsite gypsum sheet fixing work completed onsite Modular installation is completed on site Final coat of paint work is in progress HO Date - 23rd July | 2026-06-30 12:18:00 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-29 17:48:31 +0530 | Reshma Melanta | Some Image was uploaded
17888 | Turnkey | Dec'25 | Manoj Nawale | Sadguru Avenue | MUM - GOR | Yes | Saif Shaikh | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Rajkumar Suthar | Rizwan Mistry | Murali S | Umang Shah | Abdul Shafeen | Active | Production | 100% Payment | 1086691 | 1086691 | 1397120 | 1134066 | 1086691 | 14 | 9 | 0 | 0 | 0 | 0 |  |  | 2025-12-31 | 2026-01-08 12:10 | 2026-01-15 | 2026-01-15 19:21 | 2026-01-21 | 2026-01-15 19:24 | 2026-03-02 | 2026-02-28 16:38 | 2026-02-28 | 2026-02-28 16:46 | 2026-04-09 | 2026-04-28 12:23 | 2026-01-15 | 2026-01-16 18:30 | 2026-01-16 | 2026-01-16 19:04 | 2026-01-16 | 2026-01-21 13:21 | 2026-01-30 | 2026-01-30 16:56 | 2026-04-28 | 2026-04-28 16:21 | 2026-05-01 | 2026-04-29 18:03 | 2026-03-30 | 2026-03-26 13:15 | 2026-05-18 | 2026-05-16 12:20 | 2026-05-17 | 2026-05-17 11:11 |  |  | 2026-05-21 | 2026-05-29 10:11 | 2026-05-31 | 2026-05-31 16:39 | 2026-06-03 | 2026-05-31 16:49 | 2026-05-31 | 2026-06-04 15:05 |  |  |  |  | 2026-06-15 10:12 | 2026-07-04 | 2026-06-30 11:30 | 2026-07-02 | 2026-07-01 19:52 | 2026-07-01 |  | 2026-07-01 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-20 | 2026-06-15 10:11 | 2026-01-31 | 2026-02-28 16:37 | Site is RTMI | 2025-12-30 | 2026-01-03 14:45 | 1217285 | 213120 | 1160123.0688 | 195874 | 1181470.6207 | 188647 | 1181470.6207 | 188647 | 2026-07-12 09:51:55 +0530 | Rajkumar Suthar | Execution: PI scope : Completed Site is ready for modular delivery and installation. | 2026-06-21 15:29:58 +0530 | Rajkumar Suthar | Execution: Kick off and floor covering : 18th June False ceiling : 20th-26th June Electrical : 24th-25th June 1st coat paint : 26th-2nd July Site readiness : 4th July | 2026-06-02 12:48:32 +0530 | Manzoor Shaikh | Out called the customer said he will be receiving the keys by 9th or 10th June and have some plumbing work at the bathroom, will update us on keys.
17891 | Sub Project |  | Sam Sundar Palaparthi | Hiranandani | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [6 empty] | Vinay Surve | Active | Preproduction | 3D Sign off | 145353 | 0 | 0 | 0 | 0 | 117 | 0 | 0 | 0 | 157102 | 0 |  |  | 2025-12-31 | 2026-01-24 14:04 | 2025-12-31 | 2026-01-24 14:04 | 2026-01-26 | 2026-01-24 14:05 | 2026-01-26 | 2026-01-24 14:07 | 2026-01-25 | 2026-01-24 14:08 | 2026-01-25 | 2026-01-24 14:09 | 2026-01-24 | 2026-01-24 14:05 | 2026-01-25 | 2026-01-24 14:05 | 2026-01-24 | 2026-01-24 14:06 | 2026-01-25 | 2026-01-24 14:06 | 2026-01-24 | 2026-01-24 14:10 | 2026-01-27 | 2026-01-24 14:10 | 2026-01-24 | 2026-01-24 14:10 | 2026-02-24 | 2026-01-24 14:05 | 2026-02-01 | 2026-01-24 14:02 |  |  | 2026-03-11 | 2026-03-20 17:05 | 2026-03-20 | 2026-03-28 11:51 | 2026-03-31 |  | 2026-03-31 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-31 |  | 2026-01-25 | 2026-01-24 14:06 | Unknown | 2025-12-30 | 2026-01-24 14:04 | 0 | 0 | 0 | 0 | 0 | 0 | 236739 | 33613 | 2026-03-25 12:05:32 +0530 | Neha Yadav | Some Image was uploaded | 2026-03-13 11:36:05 +0530 | Neha Yadav | Some Image was uploaded | 2026-03-12 13:42:48 +0530 | Neha Yadav | Some Image was uploaded
17892 | Turnkey | Dec'25 | Bhavesh Arora | Aaradhya Parkwood | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Lost | Design | Design Finalization | 1248296 | 76499 | 1248296 | 0 | 0 | 183 | 0 | 0 | 297990 | 386449 | 487358 |  |  | 2025-12-31 | 2026-01-03 13:29 | 2026-01-09 | 2026-01-09 17:37 | 2026-01-15 | 2026-01-13 11:10 | 2026-07-09 |  | 2026-07-12 |  | 2026-07-15 |  | 2026-01-13 | 2026-01-13 11:11 | 2026-01-14 | 2026-01-13 11:21 | 2026-01-13 | 2026-01-13 16:04 | 2026-02-12 | 2026-02-12 14:43 | 2026-07-15 |  | 2026-07-18 |  | 2026-07-18 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-02 |  | 2026-08-02 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-08-02 |  | 2026-06-30 |  | Site is RTMI | 2025-12-30 | 2026-01-03 13:26 | 1263318.8608 | 213299 | 0 | 0 | 0 | 0 | 1263318.8608 | 213299 | 2026-04-27 15:15:15 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-14 12:56:00 +0530 | Christopher Macwan | Some Image was uploaded | 2026-03-26 16:27:03 +0530 | Anil Kuwar | Tried calling cx twice,cx is not responding calls
17894 | Turnkey | Dec'25 | Balachandra Achary | Purva atmosphereï¿½ | BNG - HRBR | Yes | Arjun M V | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Completed | Complete | Completed | 1683051 | 1693314 | 1847169 | 1667941 | 1683051 | 27 | 6 | 0 | 0 | 0 | 0 |  |  | 2025-12-31 | 2026-01-07 11:05 | 2025-12-31 | 2026-01-07 11:21 | 2026-01-13 | 2026-01-09 10:57 | 2026-01-18 | 2026-01-16 16:41 |  |  |  |  | 2026-01-09 | 2026-01-10 13:12 | 2026-01-10 | 2026-01-10 19:56 | 2026-01-10 | 2026-01-12 14:11 | 2026-01-16 | 2026-01-16 12:25 | 2026-01-28 | 2026-01-28 18:17 | 2026-01-31 | 2026-01-30 20:59 | 2026-01-31 | 2026-01-29 | 2026-02-04 | 2026-02-04 16:07 | 2026-02-05 | 2026-02-04 20:09 |  |  | 2026-02-14 | 2026-02-18 16:20 | 2026-02-18 | 2026-02-20 18:33 | 2026-02-22 | 2026-02-22 20:09 | 2026-02-22 | 2026-02-24 19:46 |  |  |  |  | 2026-02-26 12:41 | 2026-03-07 | 2026-03-06 20:46 | 2026-03-21 | 2026-03-18 18:36 | 2026-03-19 | 2026-03-17 19:36 | 2026-03-18 | 2026-03-20 19:50 | 2026-03-20 | 2026-03-21 11:29 | 2026-03-28 | 2026-04-01 16:17 |  |  | 2026-05-30 | 2026-05-31 11:12 | 2026-06-10 | 2026-05-31 11:14 | 2026-06-11 | 2026-05-31 11:18 |  |  |  |  | 2026-02-22 | 2026-02-25 21:33 | 2026-01-17 | 2026-01-16 15:18 | Site is RTMI | 2025-12-30 | 2025-12-31 13:46 | 1565398 | 281771 | 1831795.4308 | 307440 | 1843665.4765 | 309745 | 1843665.4765 | 309745 | 2026-05-31 11:23:57 +0530 | Saddam Hussain Z M | Execution: Vanity shutter replacement ETA 15th June | 2026-05-19 08:40:16 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 13-5-2026 to 19-3-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scopeElectrification - bonito scope- in progressFalse ceiling - bonito scope- in progressKey Dates: Modular materials dispatched - 21/03/26Handover as per TAT- 27/04/2636 working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of execution | 2026-04-28 10:42:42 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 21-04-2026 to 28-04-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scopeElectrification - bonito scope- in progressFalse ceiling - bonito scope- in progressKey Dates: Modular materials dispatched - 21/03/26Handover as per TAT- 27/04/2636 working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of executionSink is in your scope. Kindly get the sink by 22nd aprilTile required by 22nd aprilNote : Sir we required all material as early as possible .
17896 | Turnkey | Dec'25 | Bharat Shah | Nilgiri | MUM - GOR | Yes | Yash Jain |  | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 3024901 | 9999 | 0 | 0 | 0 | 196 | 0 | 292491 | 604980 | 980921 | 1136510 |  |  | 2025-12-30 | 2026-01-08 12:01 | 2025-12-30 |  | 2025-12-31 |  | 2026-01-12 |  | 2026-01-15 |  | 2026-01-18 |  | 2025-12-31 |  | 2026-01-01 |  | 2026-01-01 |  | 2026-01-02 |  | 2026-01-18 |  | 2026-01-21 |  | 2026-01-21 |  | 2026-01-25 |  | 2026-01-26 |  |  |  | 2026-02-01 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-05 | [6 empty] | 2026-02-11 |  | 2026-02-20 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-23 |  |  |  | 2026-03-17 |  | 2026-03-19 |  | 2026-03-20 | [5 empty] | 2026-02-05 |  | 2026-01-03 |  | Unknown | 2025-12-29 | 2026-01-07 19:13 | 0 | 0 | 0 | 0 | 0 | 0 | 2563475 | 461425
17899 | Sub Project |  | Rahul Maji | Assets 63 Degrees east | BNG - HSR |  | Shefali | Abhinandan K S |  |  |  | Yogeshwaran | Ranjith Kumar | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-01 | 2026-01-09 18:38 | 2026-01-01 | 2026-01-09 18:38 | 2026-01-11 | 2026-01-09 18:39 | 2026-01-11 | 2026-01-09 18:40 | 2026-01-10 | 2026-01-09 18:40 | 2026-01-10 | 2026-01-09 18:41 | 2026-01-09 | 2026-01-09 18:39 | 2026-01-10 | 2026-01-09 18:39 | 2026-01-09 | 2026-01-09 18:39 | 2026-01-10 | 2026-01-09 18:39 | 2026-01-09 | 2026-01-09 18:41 | 2026-01-12 | 2026-01-09 18:42 | 2026-01-09 | 2026-01-09 18:42 | 2026-01-10 | 2026-01-09 18:43 | 2026-01-10 | 2026-01-09 18:43 |  |  | 2026-01-12 | 2026-01-09 19:10 | 2026-01-10 | 2026-01-10 15:22 | 2026-01-13 | 2026-01-10 18:46 | 2026-01-10 | 2026-01-10 18:46 |  |  |  |  | 2026-01-24 18:12 | 2026-01-25 | 2026-01-24 18:15 | 2026-01-26 | 2026-01-24 19:07 | 2026-01-25 | 2026-01-24 19:15 | 2026-01-24 | 2026-01-24 19:16 | 2026-01-24 | 2026-01-24 19:17 | 2026-02-09 | 2026-01-24 19:09 |  |  | 2026-01-26 | 2026-01-24 19:20 | 2026-01-26 | 2026-01-24 19:21 | 2026-01-27 | 2026-01-27 14:42 |  |  |  |  | 2026-01-24 | 2026-01-24 18:11 | 2026-01-10 | 2026-01-09 18:39 | Unknown | 2025-12-31 | 2026-01-09 18:37 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0
17905 | Turnkey | Dec'25 | Piyush Ranjan | * | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | CDP Due | 1650799 | 9999 | 0 | 0 | 0 | 189 | 0 | 155081 | 330160 | 517807 | 637752.4 |  |  | 2026-01-03 | 2026-01-06 12:55 | 2026-01-02 | 2026-01-07 15:43 | 2026-03-27 |  | 2026-04-08 |  | 2026-04-11 |  | 2026-04-14 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-04-14 |  | 2026-04-17 |  | 2026-04-17 |  | 2026-04-21 |  | 2026-04-22 |  |  |  | 2026-04-28 |  | 2026-04-29 |  | 2026-05-02 |  | 2026-05-02 | [6 empty] | 2026-05-08 |  | 2026-05-17 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-20 |  |  |  | 2026-06-11 |  | 2026-06-13 |  | 2026-06-14 | [5 empty] | 2026-05-02 |  | 2026-03-30 |  | Unknown | 2026-01-02 | 2026-01-02 17:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1398982 | 251816 | 2026-01-02 17:09:06 +0530 | Keerthan M | DCM: 3BHK SW facing main-door Family of 5 15L Servant room conv as walk-in closet and toilet-store room - Shoe rack with seating with tall storage - lobby convert to study and office. - ceiling work outside. - Partition for lobby -Â GBR - walk-in closet L shape wardrobe and 2 mirrors full and half - Existing wardrobe -Â Common area - False ceiling - TV unit with minimal storage and speakers - Crockery with sink (no mirror) - 6.5*4' dining table - pooja room. MBR(Parents) - existing bed, wardrobe,Â -TV unit with storage for meds - Wall highlight - washroom renovation Son's room - Storage with book shelf - study table(gaming setup) - basket ball, games,Â - wooden flooring existing bed and wardrobe, work on dresser. Kitchen - loft on one side - space for MW and OTG - roller shutters - sink in Utility - W/M in utility with janitor storage - 2Pantry unit - spice rack on both the sides
17906 | Turnkey | Dec'25 | Geeta Sharma | * | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | 10% Payment | 3937258 | 9999 | 3937258 | 0 | 0 | 179 | 0 | 383727 | 787452 | 1288717 | 1467364 |  |  | 2026-01-03 | 2026-01-02 18:53 | 2026-01-07 | 2026-01-07 11:32 | 2026-01-17 | 2026-01-17 14:44 | 2026-02-01 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-02-09 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-02-13 |  |  |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-21 | [6 empty] | 2026-02-28 |  | 2026-03-23 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-25 |  |  |  | 2026-04-27 |  | 2026-04-29 |  | 2026-05-01 | [5 empty] | 2026-02-21 |  | 2026-01-20 |  | Unknown | 2026-01-02 | 2026-01-02 18:53 | 3336659 | 600598 | 0 | 0 | 0 | 0 | 3336659 | 600598 | 2026-01-24 13:57:46 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-01-07 11:28:28 +0530 | Rutuja Kotwal | DCM: Geeta sharmaÂ 1000sqftÂ Safety door .Â tv unit - picture is already shared - would like to remove the old one .Â Family member - 4Â kids age group - 17 & 9 both are girls .Â 6 seater diningÂ sofa 3 + 2 you already haveÂ Lighter colour in living roomÂ NO false ceilin gÂ wooden panel id possible for highlightÂ change balcony little - 2 chairs & small tableÂ want to change counter - fully modular kitchenÂ appliancesÂ washing machineÂ dryerÂ dishwasherÂ chimneyÂ hobÂ Beroom1 - younger daughter sofa cum bedÂ wardrobeÂ study tableÂ mirror on wardribe shutter balcony convert into seating area - kind of benchÂ Â Length of balcony 2 - 2.5 feetÂ Bedroom 2 elderÂ wardrobeÂ studyÂ queen bedÂ seating dresserÂ convert the balcony in study tableÂ need to take all the balconyÂ Hobbies of both daughterÂ younger - bbinge watchingÂ archery elderoneÂ Bathroom - vanityÂ loft in bathroomÂ mASTER BEDROOMÂ wARDROBEÂ BEDÂ BALCONY CONVERT INTO SEATING AREAÂ MIRRORÂ PAINITINGÂ ELECTRICALSÂ Renovate bathroomÂ flooring of the entire houseÂ The overall budgetÂ 25Lac - 30 lacÂ and civilÂ Next meetingÂ SaturdayÂ 11am .
17907 | Turnkey | Dec'25 | Nagednra KumarPulindla | Aspen Greens @ The Prestige City | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | Onboarding Reject | 949711 | 132513 | 1179944 | 0 | 0 | 147 | 0 | 0 | 152400 | 311253 | 353544.4 |  |  | 2026-01-04 | 2026-01-03 13:21 | 2026-01-03 | 2026-01-03 15:57 | 2026-01-12 | 2026-01-12 10:40 | 2026-04-18 |  | 2026-04-21 |  | 2026-04-24 |  | 2026-01-12 | 2026-02-14 16:03 | 2026-01-13 | 2026-02-18 11:20 | 2026-02-18 |  | 2026-02-19 |  | 2026-04-24 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-05-01 |  | 2026-05-02 |  |  |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-12 |  | 2026-05-12 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-05-12 |  | 2026-04-09 |  | Unknown | 2026-01-03 | 2026-01-03 13:17 | 999953 | 179991 | 0 | 0 | 0 | 0 | 1117589.95 | 184532 | 2026-03-05 15:13:25 +0530 | Bency Chacko | Some Image was uploaded | 2026-02-20 13:19:14 +0530 | Bency Chacko |  | 2026-02-20 13:11:07 +0530 | Nidhi Shaw | Some Image was uploaded
17908 | Turnkey | Dec'25 | Rohit Kothari | Purva Skywood | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | CDP Due | 1787243 | 9999 | 0 | 0 | 0 | 191 | 0 | 168725 | 357449 | 551907 | 699163.6 |  |  | 2026-01-04 | 2026-01-03 13:50 | 2026-01-03 | 2026-01-05 12:36 | 2026-01-10 |  | 2026-01-22 |  | 2026-01-25 |  | 2026-01-28 |  | 2026-01-10 |  | 2026-01-11 |  | 2026-01-11 |  | 2026-01-12 |  | 2026-01-28 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-04 |  | 2026-02-05 |  |  |  | 2026-02-11 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 | [6 empty] | 2026-02-21 |  | 2026-03-02 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-05 |  |  |  | 2026-03-27 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-02-15 |  | 2026-01-13 |  | Unknown | 2026-01-03 | 2026-01-03 13:49 | 0 | 0 | 0 | 0 | 0 | 0 | 1514613 | 272630 | 2026-01-05 12:37:43 +0530 | Ankita Agarwal | DCM: CLIENT REQUIREMENTS MRS. SWATIPurva Skywood East Entrance (EF)** Family Members: 3 Meeting Scheduled: Sunday, 11th Jan 2026 3:00 PM Estimated Budget: 1011 Lakhs Suggested Design Estimate: 15 Lakhs LIVING ROOMFoyerBase cabinet (3 ft)Optional wall concept panelingTV UnitMinimal storage designTV with indirect lightingGypsum back panel OR wallpaper backdropPooja UnitWith seatingSpace for 45 idols34 backlit framesBacklit decorative backdropSofa WallWall trims + wallpaper behind sofaCeilingFalse ceiling for living roomDiningDining table to be placed adjacent to sofa KITCHENSpace for Air FryerMixer / Grinder placementStandalone OvenBase cabinetsWall cabinetsDedicated Big Dabba StorageNO LoftUtilityBasic storage wall cabinetExtra sink in utility areaConfirm plumbing points with client BEDROOM 2 (GBR)Swing wardrobeStudy table with minimal book storageMirrorSide tableBed back wall conceptBEDROOM 3 BOYS ROOM (7-year-old Ayaan)5 ft study tableLacquer glass writing boardShelf storage for cars & LEGO displayBook storageSwing wardrobeQueen-size bedBed back wall design MASTER BEDROOMSwing wardrobeWindow seating with storageKing-size bedDresser areaBed back wall design BUDGET SUMMARYClient budget: 1011 LakhsYour design estimate: 15 LakhsGap: 4 Lakhs (Can prepare 2 options: Essential vs Premium)
17909 | Turnkey | Dec'25 | Varun Saxena | Prestige Green Gables | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Shijin C C | Jairam Joshi | Murali S | Kushal S | Sunil Kumar S M | Completed | Complete | Completed | 817415 | 817415 | 734588 | 813567 | 817415 | 76 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-01-09 19:35 | 2026-01-10 | 2026-01-10 12:58 | 2026-01-10 | 2026-01-10 13:12 | 2026-01-28 | 2026-01-28 13:55 | 2026-01-28 | 2026-01-28 14:01 |  |  | 2026-01-10 | 2026-01-09 19:03 | 2026-01-11 | 2026-01-12 18:21 | 2026-01-12 | 2026-01-16 13:08 | 2026-01-21 | 2026-01-21 11:21 | 2026-01-29 | 2026-01-29 16:57 | 2026-02-01 | 2026-01-31 07:52 | 2026-02-01 | 2026-01-30 | 2026-02-04 | 2026-02-03 23:24 | 2026-02-04 | 2026-02-04 09:09 |  |  | 2026-02-13 | 2026-02-17 17:40 | 2026-02-17 | 2026-02-17 19:16 | 2026-02-20 | 2026-02-19 10:57 | 2026-02-19 | 2026-02-23 18:22 |  |  |  |  | 2026-02-24 19:07 | 2026-03-05 | 2026-03-04 20:10 | 2026-03-17 | 2026-03-14 18:58 | 2026-03-15 | 2026-03-23 12:48 | 2026-03-14 | 2026-03-24 15:23 | 2026-03-24 | 2026-03-24 20:54 | 2026-03-29 | 2026-03-28 14:24 |  |  | 2026-04-14 | 2026-04-14 16:28 | 2026-04-25 | 2026-04-14 19:00 | 2026-04-26 | 2026-04-15 18:07 |  |  |  |  | 2026-02-24 | 2026-02-24 19:06 | 2026-01-22 | 2026-01-28 13:53 | Site is RTMI | 2026-01-03 | 2026-01-09 19:03 | 814878.3 | 134555 | 959976.394 | 158044 | 960679.0784 | 158631 | 960679.0784 | 158631 | 2026-04-25 13:57:40 +0530 | Losii Athisa | Some Image was uploaded | 2026-04-15 18:17:01 +0530 | Jairam Joshi | Project Closure Pending: Observation points closure - 30th April | 2026-04-13 16:57:37 +0530 | Jairam Joshi | Execution: All works completed Cleaning - WIP - 13th QC -15th April HO-16th April
17911 | Turnkey | Dec'25 | Sheldon Pereira | Ranbir castle | MUM - GOR | Yes | Priyanka Patel |  | Aparna | [5 empty] | Nivesh Gupta |  | Active | Prospect | CDP Due | 1345018 | 9999 | 0 | 0 | 0 | 188 | 0 | 124503 | 269004 | 436658 | 504854.8 |  |  | 2026-01-04 | 2026-01-07 18:22 | 2026-01-08 | 2026-01-08 20:22 | 2026-01-13 |  | 2026-01-26 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-01-14 |  | 2026-01-15 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-08 |  | 2026-02-09 |  |  |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-19 |  | 2026-02-19 | [6 empty] | 2026-02-25 |  | 2026-03-06 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-09 |  |  |  | 2026-03-31 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-02-19 |  | 2026-01-17 |  | Unknown | 2026-01-03 | 2026-01-03 16:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1139846 | 205172 | 2026-01-08 20:19:56 +0530 | Priyanka Patel | DCM: Lifestyle1. Please select your budget for Interior Designing? Rs. 10-15 Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? 4. Who will be living in this home? Couple, Elderly Members 5. What activities do you usually perform at home? (Choose top 23) Working from Home, Hosting Guests, Family Bonding, Relaxing & Unwinding, Pursuing Hobbies, Prayer 6. What is your preferred entertainment style? Casual get-togethers, Large Gatherings 7. Do you prefer any Smart home features? Security, Automation 8. What is your possession date? 2026-03-15 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Safety door, Digital lock, Shoe rack Dcor & Living Room1. Choose your decor inspirations Plants 2. Any specific signature design feature required 3. Whats the primary use of your living room? TV focus , Entertaining guests 4. Any absolute no-go styles, colors, or materials? dark colours 5. Must-have furniture or features? Sofa, Puja unit, Display unit , Statement Wall/ Feature Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Bar unit, Crockery unit, Partitions 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Microwave, Fridge, Hob, Washing machine BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Sliding, Swing Master Bedroom - Additional units Study table, Dresser Other Bedroom - Bed Type Other Bedroom - Wardrobe style Other Bedroom - Additional units BathroomsPreferred vanity style What do you prefer? What are your requirements for Utility Area? Laundry space, Washing machine space Balcony & OutdoorHow do you intend to use your balcony for? b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? Final Vision1. Any space in the home that you want to put in Spotlight? 2. Do you want the design to reflect any personal story, cultural influence, or special memory
17912 | Turnkey | Dec'25 | Praveen Pawar | Lodha palava central | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | CDP Due | 1522682 | 9999 | 0 | 0 | 0 | 174 | 0 | 142269 | 304536 | 471686 | 594191.6 |  |  | 2026-01-04 | 2026-01-03 17:14 | 2026-01-22 | 2026-01-22 11:51 | 2026-01-24 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-03 | 2026-01-03 17:13 | 0 | 0 | 0 | 0 | 0 | 0 | 1290409 | 232273 | 2026-01-25 14:31:55 +0530 | Ishan Patle | cdp done but quote not showing to cx due to medical problem cx left | 2026-01-22 11:47:19 +0530 | Rutuja Kotwal | DCM: Mrs. RupaliÂ Praveen PawarÂ 2.5 BHK.Â Lodha PalavaÂ DombivliÂ Â Move in 3 peopleÂ Â Husband,Â wifeÂ and daughter 1.5 yrs.Â Â Design as per VastuÂ Possession in handÂ 808sq.ft.Â Â Living room- TV unit, Additional display on both sides of tvÂ KitchenÂ Â Base,Â wall, and lofts.Â Â Study roomÂ Â wardrobe, StudyÂ tall storage for books,Â Â Bedroom 2-Â ParentsÂ BedroomÂ Â Wardrobe, Bed 5X6.Â ,Â Side tablesÂ Bedroom 3 Master bedroom-Â Side tables,Â bed.Â ,Â wardrobe with tall Storage,Â and drawerÂ Â Vanity cabinetsÂ Â AdditionalÂ ShoerackÂ ShoerackÂ cabinet andÂ storage aboveÂ machine.Â Â Budget - 8LÂ Budget suggested-Â 12-15 lakhsÂ Â CDP-Â 24thÂ januaryÂ 2025.Â Â | 2026-01-03 18:41:57 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
17913 | Turnkey | Dec'25 | Aatish vartak | Hum Solaris | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Safalta Karkera |  | Rashmi Visave |  | Rizwan Mistry |  | Manasi Patil | Vinay Surve | Lost | Preproduction | 3D Sign off | 1245185 | 167610 | 1149384 | 1109351 | 1245185 | 87 | 1 | 0 | 0 | 610716 | 466859.2 |  |  | 2026-01-04 | 2026-01-03 17:00 | 2026-01-12 | 2026-01-11 23:01 | 2026-01-17 | 2026-01-13 17:22 | 2026-03-13 | 2026-03-04 12:26 | 2026-03-16 | 2026-03-04 16:00 | 2026-03-19 | 2026-03-08 15:45 | 2026-01-13 | 2026-01-14 16:50 | 2026-01-14 | 2026-01-15 14:49 | 2026-01-15 | 2026-01-20 13:46 | 2026-02-03 | 2026-02-03 13:39 | 2026-03-08 | 2026-03-08 17:32 | 2026-03-11 | 2026-03-09 19:22 | 2026-03-22 | 2026-02-10 18:10 | 2026-03-18 | 2026-03-20 10:52 | 2026-03-21 | 2026-03-20 10:52 |  |  | 2026-04-17 | 2026-04-19 19:00 | 2026-04-19 | 2026-04-19 23:00 | 2026-10-28 |  | 2026-10-28 | [6 empty] | 2026-11-03 |  | 2026-11-12 |  | 2026-11-11 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-15 |  |  |  | 2026-12-07 |  | 2026-12-09 |  | 2026-12-10 | [5 empty] | 2026-10-28 |  | 2026-02-04 | 2026-03-04 12:23 | Site is RTMI | 2026-01-03 | 2026-01-03 16:59 | 974054 | 175329 | 1160400.3888 | 195918 | 1283121.1005 | 216638 | 1283121.1005 | 216638 | 2026-05-13 11:27:35 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-07 17:37:59 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-19 12:47:20 +0530 | Manzoor Shaikh | Some Image was uploaded
17915 | Turnkey | Dec'25 | Ekta | Sobha royal pavilion | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik |  | Sethuragavan R | Sachin I Betageri | Ranjith Kumar | Murali S | Pulivarthi Nirosha | Suchendra Shetty | Completed | Complete | Completed | 955206 | 955206 | 1455178 | 1180984 | 955206 | 72 | 1 | 0 | 0 | 0 | 0 |  |  | 2025-12-28 | 2026-01-04 10:33 | 2026-01-04 | 2026-01-04 11:02 | 2026-01-04 | 2026-01-04 11:21 | [6 empty] | 2026-01-04 | 2026-01-05 19:34 | 2026-01-05 | 2026-01-10 17:20 | 2026-01-10 | 2026-01-12 19:17 | 2026-01-20 | 2026-01-20 18:04 | 2026-02-05 | 2026-02-06 16:36 | 2026-02-09 | 2026-02-06 17:15 | 2026-02-19 | 2026-02-04 | 2026-02-14 | 2026-02-13 19:18 | 2026-02-14 | 2026-02-17 18:49 |  |  | 2026-02-25 | 2026-02-27 19:02 | 2026-02-28 | 2026-02-28 13:24 | 2026-03-03 | 2026-02-28 13:57 | 2026-02-28 | 2026-03-01 00:32 |  |  |  |  | 2026-03-06 15:29 | 2026-03-13 | 2026-03-12 22:14 | 2026-03-22 | 2026-03-22 10:25 | 2026-03-21 | 2026-03-27 11:13 | 2026-03-22 | 2026-03-28 12:10 | 2026-03-28 | 2026-03-28 18:10 | 2026-04-03 | 2026-04-03 09:55 |  |  | 2026-04-14 | 2026-04-15 09:49 | 2026-04-16 | 2026-04-15 18:14 | 2026-04-17 | 2026-04-15 18:47 |  |  |  |  | 2026-02-28 | 2026-03-05 16:28 | 2026-01-21 | 2026-02-01 19:32 | Site is RTMI | 2025-12-27 | 2026-01-03 17:40 | 1233201 | 221976 | 1458253.5992 | 240785 | 1258017.2275 | 198717 | 1258017.2275 | 198717 | 2026-06-26 12:38:47 +0530 | Mahimn Bhatt | Some Image was uploaded | 2026-04-24 15:08:16 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-04-23 17:49:53 +0530 | Patil Madhavi | Some Image was uploaded
17916 | Turnkey | Dec'25 | Smita | Innovative Placia | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Hold | Preproduction | Site Readiness 1 | 1640619 | 433621 | 1804842 | 1640619 | 0 | 37 | 69 | 0 | 0 | 558553 | 648445.2 |  |  | 2026-01-04 | 2026-01-03 17:58 | 2026-01-03 | 2026-01-03 19:07 | 2026-01-14 | 2026-01-15 10:55 | 2026-03-31 | 2026-03-31 18:05 |  |  |  |  | 2026-01-15 | 2026-01-31 14:33 | 2026-01-16 | 2026-02-12 17:40 | 2026-02-12 | 2026-03-04 11:39 | 2026-03-06 | 2026-03-06 17:26 | 2026-03-31 | 2026-03-31 19:51 | 2026-04-18 | 2026-03-31 20:18 | 2026-04-08 | 2026-03-31 | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-04 |  | 2026-08-04 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-08-04 |  | 2026-03-07 | 2026-03-31 17:15 | Site is RTMI | 2026-01-03 | 2026-01-03 17:56 | 1529527 | 275314 | 1881822.3784 | 318526 | 0 | 0 | 1881822.3784 | 318526 | 2026-03-23 15:49:56 +0530 | Chittipireddy Sriharish | DDM2: Living room Puja unit - width need to extended to the wall size (post cross measurements as per space ) Master bedroom Dresser placement need to be confirmed by clients Kids bedroom mirror with alu shutter Guest bedroom bed side wall - need some wall light with panel and texture paints No wallpapers | 2026-03-15 15:41:49 +0530 | Chittipireddy Sriharish | DDM1: Vanity unit - wall storage need to be designed as per the references | 2026-03-15 15:34:40 +0530 | Chittipireddy Sriharish | DDM1: Foyer shoe rack - 30 pair of shoe rack Main door - Need to be high lighted Wall accent options needed for foyer Living room partition - 3/4 partition Window need to be considered in the Living room false ceiling need to be continued till dining space Dining Area bar cum crockery unit Puja unit Need extra ledges on left and right CNC with back lights Kitchen left side wall need to be retained as per the floor plan Right side no changes Left side wall cabinets possibility need to be cross checked Master bedroom Sliding Wardrobe inside the walk in closet (1.5 feet depth) bed need to be placed on the walk in wardrobe wall wooden flooring False ceiling Bathroom Glass partition Kids bedroom Bedroom need to be moved towards the right side study unit - l shape wardrobe remain same as it is Used clothes storage required Post initial measurements need to check wardrobe feasibility for hinged/ sliders
17917 | Turnkey | Dec'25 | Suhas Purohit | Puraniks Tokyo Bay Zuisen, 2BHK,683 SqFt | MUM - Thane | Yes | Honey Thakkar | Divya Rahangdale | Anil Kuwar |  |  | Faraz Soudagar | Aditya Vikram | Murali S | Aryan Singh | Aakash Gaikwad | Active | Handover | Project Closure Pending | 1755384 | 1755384.01 | 1552862 | 1598842 | 1755384 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-01-03 23:28 | 2026-01-04 | 2026-01-04 21:53 | 2026-01-08 | 2026-01-08 10:52 | 2026-02-06 | 2026-02-06 12:43 | 2026-02-14 | 2026-02-21 11:01 | 2026-02-22 | 2026-02-22 11:07 | 2026-01-08 | 2026-01-08 16:54 | 2026-01-09 | 2026-01-08 19:03 | 2026-01-08 | 2026-01-13 10:17 | 2026-01-22 | 2026-01-22 15:17 | 2026-02-22 | 2026-02-23 14:42 | 2026-02-28 | 2026-02-24 18:40 | 2026-02-28 | 2026-02-24 16:16 | 2026-02-27 | 2026-02-26 19:10 | 2026-02-27 | 2026-02-26 19:11 |  |  | 2026-03-22 | 2026-03-26 12:49 | 2026-03-26 | 2026-03-26 21:32 | 2026-03-28 | 2026-03-27 08:23 | 2026-03-27 | 2026-03-27 19:34 |  |  |  |  | 2026-03-28 16:33 | 2026-04-09 | 2026-04-08 19:11 | 2026-04-17 | 2026-04-16 19:20 | 2026-04-16 | 2026-04-17 18:31 | 2026-04-16 | 2026-04-27 20:06 | 2026-04-24 | 2026-04-27 20:13 | 2026-04-29 | 2026-05-13 17:08 |  |  | 2026-06-27 | 2026-06-23 11:17 | 2026-06-29 | 2026-06-24 09:18 | 2026-06-30 | 2026-06-24 11:08 |  |  |  |  | 2026-03-27 | 2026-03-27 18:54 | 2026-02-25 | 2026-02-03 16:19 | Site is RTMI | 2026-01-03 | 2026-01-03 23:24 | 1588046.2344 | 267385 | 1628354.3285 | 274399 | 1765550.9608 | 298278 | 1765550.9608 | 298278 | 2026-06-23 22:25:12 +0530 | Faraz Soudagar | Execution: Deep cleaning done. QC done. HO - 23rd June | 2026-06-01 14:12:00 +0530 | Faraz Soudagar | Execution: Profile shutter pending FInal coat of Paint done. Bed & sofa ETA - 8th June Deep cleaning - 9th June QC- 10th Jnue HO - 11th June | 2026-05-18 15:01:06 +0530 | Faraz Soudagar | Execution: Snag installation done. rafter installation ETA - 19th May Final coat of paint ETA - 25th May Blocker - Ibed
17918 | Turnkey | Dec'25 | Nikhil Deole | jayanthi gaedens apartment | BNG - HSR | Yes | Priyanka Mathur | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 993573 | 9999 | 0 | 0 | 0 | 193 | 0 | 89358 | 198715 | 298072 | 397429.2 |  |  | 2026-01-04 | 2026-01-03 18:11 | 2026-01-04 |  | 2026-01-17 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-11 |  | 2026-02-12 |  |  |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-22 |  | 2026-02-22 | [6 empty] | 2026-02-28 |  | 2026-03-09 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-12 |  |  |  | 2026-04-03 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-02-22 |  | 2026-01-20 |  | Site is RTMI | 2026-01-03 | 2026-01-03 18:07 | 0 | 0 | 0 | 0 | 0 | 0 | 842011 | 151562 | 2026-01-14 11:55:33 +0530 | Chanakya Panigrahi | * TV unit * Crockery unit * Kitchen renovation * All wardrobe shutter changes * Full house painting * Demolition of common washroom and new common vanity setup * Dressing area setup * Puja unit * French window with sitting area in the hall * French windows in both bedrooms * Detailed planning for both washrooms * Two balconies to be merged with bedrooms and converted into study/office setups * C-shaped kitchen with the dry balcony brought inside * Dedicated space for a dishwasher * Outside shoe rack with sitting * Safety gate * Kids bedroom planning * Aluminium panel sound-proof windows * Main balcony planning * Hall foyer area Budget-10l-13l
17919 | Turnkey | Dec'25 | Amit Anand | Saritha Serene | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Kowshik |  | Sethuragavan R | Suchendra Shetty | Jairam Joshi | Murali S | Aman Kumar | Affaan Abdulla | Active | Handover | Project Closure Pending | 782292 | 782292 | 1125442 | 930593 | 872292 | 16 | 11 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-01-03 18:30 | 2026-01-03 | 2026-01-09 13:35 | 2026-01-10 | 2026-01-14 16:38 | 2026-03-24 | 2026-03-25 15:28 | 2026-03-28 | 2026-03-28 15:50 | 2026-03-28 | 2026-03-28 15:58 | 2026-01-14 | 2026-01-14 16:46 | 2026-01-15 | 2026-01-15 11:39 | 2026-01-15 | 2026-01-16 16:30 | 2026-01-21 | 2026-01-24 19:25 | 2026-03-28 | 2026-03-28 16:17 | 2026-04-10 | 2026-03-28 17:49 | 2026-02-12 | 2026-01-29 19:01 | 2026-04-13 | 2026-04-16 11:40 | 2026-04-17 | 2026-04-17 11:59 |  |  | 2026-04-19 | 2026-04-22 13:19 | 2026-04-22 | 2026-04-23 14:21 | 2026-04-26 | 2026-04-23 21:38 | 2026-04-23 | 2026-04-28 19:47 |  |  |  |  | 2026-04-29 13:49 | 2026-05-07 | 2026-05-07 16:14 | 2026-05-28 | 2026-05-23 18:54 | 2026-05-24 | 2026-05-25 19:19 | 2026-05-23 | 2026-05-27 15:01 | 2026-05-27 | 2026-05-27 19:00 | 2026-06-02 | 2026-06-01 15:39 |  |  | 2026-06-27 | 2026-06-29 11:05 | 2026-06-27 | 2026-06-29 11:20 | 2026-06-29 | 2026-06-29 13:10 |  |  |  |  | 2026-04-23 | 2026-04-29 11:45 | 2026-02-28 | 2026-03-23 13:01 | Site is RTMI | 2026-01-03 | 2026-01-03 18:26 | 1178260.344 | 194558 | 1108241.397 | 173988 | 1041439.431 | 171959 | 1041439.431 | 171959 | 2026-07-03 14:11:15 +0530 | Abhinandan K S | Additional Payment collected for additional requirement from the Cx's side requested during the installation phase. | 2026-06-29 15:47:17 +0530 | Jairam Joshi | Project Closure Pending: snag raised for kithcen shutters ETA 15th July Closure 16th July | 2026-06-16 18:27:58 +0530 | Jairam Joshi | Some Image was uploaded
17920 | Sub Project |  | Faisal Khan | lnt | MUM - GOR |  | Priyanka Murarka | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Yash Metha | Aditya Vikram | Murali S | Avi Thakkar | Vinay Surve | Active | Handover | Project Closure Pending | -731 | 0 | 0 | 0 | -731 | 90 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-03-21 13:55 | 2026-01-04 | 2026-03-21 13:55 | 2026-03-23 | 2026-03-21 13:56 | 2026-03-23 | 2026-03-21 13:57 | 2026-03-23 | 2026-03-21 13:57 | 2026-03-22 | 2026-03-21 13:57 | 2026-03-21 | 2026-03-21 13:56 | 2026-03-22 | 2026-03-21 13:56 | 2026-03-20 | 2026-03-21 13:56 | 2026-03-22 | 2026-03-21 13:56 | 2026-03-21 | 2026-03-21 13:58 | 2026-03-22 | 2026-03-21 13:58 | 2026-03-21 | 2026-03-21 13:58 | 2026-03-22 | 2026-03-21 13:59 | 2026-03-21 | 2026-03-21 13:59 |  |  | 2026-03-22 | 2026-03-22 15:21 | 2026-03-24 | 2026-03-24 12:43 | 2026-03-25 | 2026-03-24 13:00 | 2026-03-25 | 2026-03-24 13:00 |  |  |  |  | 2026-03-24 13:12 | 2026-03-26 | 2026-03-25 20:09 | 2026-03-28 | 2026-03-26 20:57 | 2026-04-02 | 2026-03-26 14:48 | 2026-03-26 | 2026-04-10 15:10 | 2026-04-10 | 2026-04-10 15:12 | 2026-04-16 | 2026-04-16 12:11 |  |  | 2026-04-18 | 2026-04-16 13:47 | 2026-04-18 | 2026-04-16 13:57 | 2026-04-16 | 2026-04-16 18:48 |  |  |  |  | 2026-03-25 | 2026-03-24 13:04 | 2026-03-23 | 2026-03-21 13:56 | Unknown | 2026-01-03 | 2026-03-21 13:55 | 0 | 0 | 0 | 0 | 34973 | 6295 | 34973 | 6295 | 2026-03-17 13:43:22 +0530 | Avinash Jaiswal |  | 2026-03-14 12:08:08 +0530 | Manzoor Shaikh | Some Image was uploaded
17921 | Turnkey | Dec'25 | Mr. Tirathdas. C | Leo Tower | MUM - GOR | Yes | Shweta Dalvi |  | Shahid Chougley | [5 empty] | Umang Shah |  | Active | Prospect | CDP Due | 1973424 | 9999 | 0 | 0 | 0 | 188 | 0 | 187343 | 394685 | 646945 | 734451.6 |  |  | 2026-01-04 | 2026-01-03 19:51 | 2026-01-08 | 2026-01-08 15:18 | 2026-01-10 |  | 2026-01-26 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-01-14 |  | 2026-01-15 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-08 |  | 2026-02-09 |  |  |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-19 |  | 2026-02-19 | [6 empty] | 2026-02-25 |  | 2026-03-06 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-09 |  |  |  | 2026-03-31 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-02-19 |  | 2026-01-17 |  | Unknown | 2026-01-03 | 2026-01-03 19:50 | 0 | 0 | 0 | 0 | 0 | 0 | 1701678 | 301030 | 2026-02-23 19:04:20 +0530 | Umang Shah | Some Image was uploaded
17922 | Turnkey | Dec'25 | Janani Katarey | Rohan Upavan | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  | Sethuragavan R | Banka H Suthar | Saddam Hussain Z M | Murali S | Varun Mandana | Sunil Kumar S M | Completed | Complete | Completed | 846572 | 846573 | 1118234 | 953192 | 957302 | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-01-04 13:12 | 2026-01-04 | 2026-01-04 16:17 | 2026-01-04 | 2026-01-04 16:22 | 2026-01-29 | 2026-01-29 11:07 | 2026-01-29 | 2026-01-29 19:28 |  |  | 2026-01-04 | 2026-01-05 19:27 | 2026-01-05 | 2026-01-06 18:52 | 2026-01-06 | 2026-01-12 19:01 | 2026-01-20 | 2026-01-20 15:22 | 2026-01-29 | 2026-01-29 20:05 | 2026-02-01 | 2026-01-29 21:30 | 2026-02-01 | 2026-01-29 | 2026-02-07 | 2026-02-08 13:06 | 2026-02-09 | 2026-02-08 13:06 |  |  | 2026-02-21 | 2026-02-22 18:20 | 2026-02-22 | 2026-02-22 20:09 | 2026-03-01 | 2026-02-22 21:11 | 2026-02-22 | 2026-02-25 11:55 |  |  |  |  | 2026-03-04 12:09 | 2026-03-11 | 2026-03-10 22:19 | 2026-03-22 | 2026-03-20 17:17 | 2026-03-21 | 2026-03-28 16:16 | 2026-03-20 | 2026-03-30 16:12 | 2026-03-30 | 2026-03-30 21:42 | 2026-04-07 | 2026-04-06 10:45 |  |  | 2026-05-15 | 2026-05-15 20:28 | 2026-05-17 | 2026-05-16 16:33 | 2026-05-18 | 2026-05-18 16:11 |  |  |  |  | 2026-02-25 | 2026-03-04 12:08 | 2026-01-21 | 2026-01-20 16:57 | Site is RTMI | 2026-01-03 | 2026-01-03 21:14 | 947656 | 170578 | 1019169.209 | 168283 | 1022938.349 | 168910 | 1022938.349 | 168910 | 2026-05-18 16:15:29 +0530 | Saddam Hussain Z M | Execution: Observation Points - 3rd June | 2026-04-21 08:12:17 +0530 | Banka H Suthar | Enclosed please find theÂ WeeklyÂ Report for the reporting period from 06/04/26 to 11/04/2026 for your kind perusal. Project Status: pre installation work Key Decisions (Client): Electrical work- bonito scope- completed Floor covering - bonito scope -completed False ceiling - none Key Risk: Electrical (lights) Key Dates: Modular Items Delivery - installation completed Granite - work completed VRM Items Delivery - Profile shutter - installation completed Request you to kindly go through the report and request for providing the decisions on priority to avoid any impact on the overall project delivery | 2026-04-18 16:35:33 +0530 | Saddam Hussain Z M | Some Image was uploaded
17923 | Turnkey | Dec'25 | Rakesh Katarey | Rohan Upavan | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  | Sethuragavan R | Banka H Suthar | Saddam Hussain Z M | Murali S | Varun Mandana | Sunil Kumar S M | Completed | Complete | Completed | 2115905 | 2115905 | 1446544 | 2081276 | 2184403 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-01-04 13:11 | 2026-01-04 | 2026-01-04 16:14 | 2026-01-04 | 2026-01-04 16:24 | 2026-01-29 | 2026-01-29 10:49 | 2026-01-30 | 2026-01-29 17:55 |  |  | 2026-01-04 | 2026-01-05 19:25 | 2026-01-05 | 2026-01-06 18:52 | 2026-01-06 | 2026-01-12 19:01 | 2026-01-20 | 2026-01-20 15:10 | 2026-01-29 | 2026-01-29 19:02 | 2026-02-01 | 2026-01-29 21:17 | 2026-02-01 | 2026-01-29 | 2026-02-07 | 2026-02-08 14:29 | 2026-02-09 | 2026-02-08 14:30 |  |  | 2026-02-25 | 2026-02-27 18:50 | 2026-02-28 | 2026-02-28 15:39 | 2026-03-03 | 2026-02-28 17:25 | 2026-03-03 | 2026-02-25 10:53 |  |  |  |  | 2026-03-06 15:02 | 2026-03-15 | 2026-03-14 22:46 | 2026-03-26 | 2026-03-26 20:39 | 2026-03-25 | 2026-03-30 10:53 | 2026-03-26 | 2026-03-30 16:15 | 2026-03-30 | 2026-03-30 21:43 | 2026-04-07 | 2026-04-06 10:23 |  |  | 2026-05-30 | 2026-05-29 20:34 | 2026-06-01 | 2026-05-29 20:38 | 2026-05-30 | 2026-05-31 11:39 |  |  |  |  | 2026-02-28 | 2026-03-04 12:07 | 2026-01-21 | 2026-01-20 16:56 | Site is RTMI | 2026-01-03 | 2026-01-03 21:15 | 1225885 | 220659 | 2199899.7275 | 363245 | 2531189.0054 | 417950 | 2531189.0054 | 417950 | 2026-06-26 10:06:08 +0530 | Saddam Hussain Z M | Execution: Metal Fabrication Replacement - 27th June | 2026-05-31 11:41:53 +0530 | Saddam Hussain Z M | Execution: Metal Fabrication Replacement - 15th June | 2026-04-21 07:51:39 +0530 | Banka H Suthar | Enclosed please find theÂ WeeklyÂ Report for the reporting period from 13/04/26 to 18/04/2026 for your kind perusal. Project Status: pre installation work Key Decisions (Client): Electrical work- bonito scope- completed Floor covering - bonito scope -completed False ceiling - done Painting - 1st coat painting completed Quartz - ETA 23/04/26 Granite - work completed Key Risk: Electrical (lights) Key Dates: Modular Items Delivery - installation completed VRM Items Delivery - Profile shutter - installation completed Request you to kindly go through the report and request for providing the decisions on priority to avoid any impact on the overall project delivery
17924 | Turnkey | Dec'25 | Shailendra Vasantrao Deshmukh | BC Corp Arista | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera |  | Mohammed Lal | Nilesh Patel | Rizwan Mistry | Murali S | Harshaan Tiku | Vinay Surve | Active | Installation | Execution | 1430792 | 1430793 | 1469573 | 1323157 | 1426572 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-04 | 2026-01-03 21:26 | 2026-01-15 | 2026-01-15 21:33 | 2026-01-22 | 2026-01-22 14:00 | 2026-03-15 | 2026-03-15 17:05 | 2026-03-30 | 2026-03-29 18:34 | 2026-03-31 | 2026-03-31 22:33 | 2026-01-21 | 2026-01-16 18:11 | 2026-01-23 | 2026-01-22 20:57 | 2026-01-22 | 2026-01-23 13:18 | 2026-02-03 | 2026-02-03 17:35 | 2026-04-03 | 2026-04-03 19:26 | 2026-04-03 | 2026-04-03 19:55 | 2026-03-17 | 2026-02-28 16:29 | 2026-04-25 | 2026-04-23 20:59 | 2026-04-24 | 2026-04-23 21:00 |  |  | 2026-05-02 | 2026-05-09 15:06 | 2026-05-09 | 2026-05-12 15:19 | 2026-05-12 | 2026-05-12 17:15 | 2026-05-12 | 2026-05-13 11:38 |  |  |  |  | 2026-05-31 14:17 | 2026-06-07 | 2026-06-08 21:32 | 2026-06-28 | 2026-06-26 14:36 | 2026-06-26 | 2026-06-25 09:05 | 2026-06-26 | 2026-07-09 11:27 | 2026-06-20 | 2026-07-13 15:37 | 2026-07-15 |  |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-05-15 | 2026-05-31 14:16 | 2026-02-04 | 2026-02-07 14:57 | Site is Non-RTMI | 2026-01-03 | 2026-01-03 21:26 | 1245401 | 224172 | 1407308.1986 | 224718 | 1502667.4427 | 248121 | 1509490.9427 | 248764 | 2026-07-13 12:14:46 +0530 | Nilesh Patel | PI works has been completed at site with 1st coat of paint Modulars has been delivered on 11th July and installation has been started at the site | 2026-05-09 15:17:42 +0530 | Swapnali Shedekar | Some Image was uploaded | 2026-05-08 23:48:33 +0530 | Swapnali Shedekar | Some Image was uploaded
17926 | Turnkey | Dec'25 | Parshawa Corporation (Aliya Shaikh) | Piramal Revanta | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | suraj kumar | Aditya Vikram | Murali S | Mustufa Sohagpurwala | Shailendra Mishra | Hold | Preproduction | Site Readiness 2 | 954754 | 611598 | 1066614 | 1052924 | 946586 | 7 | 111 | 0 | 0 | 0 | 343156 |  |  | 2026-01-04 | 2026-01-03 23:24 | 2026-01-10 | 2026-01-10 18:28 | 2026-01-11 | 2026-01-13 10:50 | 2026-02-20 | 2026-02-18 17:16 | 2026-02-23 | 2026-02-18 18:31 |  |  | 2026-01-13 | 2026-01-14 16:48 | 2026-01-14 | 2026-01-21 19:20 | 2026-01-21 | 2026-01-22 18:19 | 2026-02-15 | 2026-02-15 16:15 | 2026-02-19 | 2026-02-19 16:11 | 2026-02-22 | 2026-02-25 10:45 | 2026-02-22 | 2026-02-24 18:18 | 2026-05-12 | 2026-05-09 22:25 | 2026-05-10 | 2026-05-09 22:26 |  |  | 2026-05-13 | 2026-05-15 13:05 | 2026-05-16 | 2026-05-16 22:14 | 2026-05-19 | 2026-05-17 14:03 | 2026-06-20 | 2026-06-19 18:46 | [5 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-31 |  | 2026-02-16 | 2026-02-18 12:47 | Site is RTMI | 2026-01-03 | 2026-01-03 23:23 | 903910 | 162703 | 1019427 | 183496 | 929310 | 167275 | 936232 | 168521 | 2026-07-10 11:24:50 +0530 | Divya Rahangdale | CX will receive the possession by September. | 2026-06-12 13:33:56 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-17 11:00:22 +0530 | Anil Jagtap | Some Image was uploaded
17927 | Turnkey | Dec'25 | Sunil Shigwan | RUNWAL FOREST | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1147954 | 299050 | 1120127 | 1147954 | 0 | 2 | 118 | 0 | 0 | 461242 | 387662 |  |  | 2026-01-05 | 2026-01-12 17:22 | 2026-01-13 | 2026-01-13 11:00 | 2026-01-19 | 2026-01-13 11:08 | 2026-03-12 | 2026-03-12 13:03 | 2026-03-12 | 2026-03-12 13:12 |  |  | 2026-01-10 | 2026-01-12 15:08 | 2026-01-14 | 2026-01-13 13:24 | 2026-01-13 | 2026-01-13 17:50 | 2026-02-04 | 2026-02-04 13:11 | 2026-03-17 | 2026-03-17 19:29 | 2026-04-05 | 2026-03-17 20:47 | 2026-02-28 | 2026-02-06 19:00 | 2026-11-03 |  | 2026-11-04 |  |  |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-14 |  | 2026-11-14 | [6 empty] | 2026-11-20 |  | 2026-11-29 |  | 2026-11-28 |  | 2026-11-29 |  | 2026-11-30 |  | 2026-12-02 |  |  |  | 2026-12-24 |  | 2026-12-26 |  | 2026-12-27 | [5 empty] | 2026-11-14 |  | 2026-03-07 | 2026-03-12 13:00 | Site is RTMI | 2026-01-04 | 2026-01-10 12:30 | 949260 | 170866 | 1099961 | 197993 | 0 | 0 | 1099961 | 197993 | 2026-07-10 11:26:41 +0530 | Divya Rahangdale | CX will receive the possession by October. | 2026-06-29 13:53:01 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: Possession is delayed for 3 months because site is not ready | 2026-04-12 16:22:04 +0530 | Anil Jagtap | As discussed with the customer, possession will be received in june
17928 | Turnkey | Dec'25 | Vinayak Raj Sharma | L&T Elixir Reserve | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Safalta Karkera |  | Mohammed Lal | Naushad Ansari | Rizwan Mistry | Murali S | Saloni Sagwekar | Aakash Gaikwad | Active | Installation | Execution | 3044576 | 3044577 | 2102830 | 2894639 | 3044576 | 23 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-07 12:43 | 2026-01-11 | 2026-01-11 15:10 | 2026-01-11 | 2026-01-11 21:11 | 2026-03-04 | 2026-03-04 13:50 | 2026-03-07 | 2026-03-07 14:25 | 2026-03-14 | 2026-03-14 14:56 | 2026-01-11 | 2026-01-12 11:54 | 2026-01-12 | 2026-01-13 14:44 | 2026-01-13 | 2026-01-14 16:32 | 2026-01-17 | 2026-01-17 18:38 | 2026-03-14 | 2026-03-14 18:22 | 2026-03-17 | 2026-03-14 18:59 | 2026-03-13 | 2026-03-10 18:53 | 2026-03-25 | 2026-03-25 20:52 | 2026-03-26 | 2026-03-25 20:56 |  |  | 2026-04-28 | 2026-05-07 12:36 | 2026-05-08 | 2026-05-08 18:46 | 2026-05-15 | 2026-05-08 21:36 | 2026-05-08 | 2026-05-09 12:28 |  |  |  |  | 2026-05-13 16:39 | 2026-05-29 | 2026-05-28 19:21 | 2026-06-11 | 2026-06-09 19:37 | 2026-06-09 | 2026-06-04 17:27 | 2026-06-09 | 2026-06-18 23:08 | 2026-06-17 | 2026-06-22 08:28 | 2026-06-23 | 2026-07-02 18:23 |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-05-08 | 2026-05-11 18:01 | 2026-01-18 | 2026-02-06 19:42 | Site is RTMI | 2026-01-04 | 2026-01-07 12:40 | 2168246.4372 | 366533 | 3031479.5889 | 517826 | 3133442.4503 | 540698 | 3133442.4503 | 540698 | 2026-07-09 00:20:03 +0530 | Naushad Ansari | Execution: Floor covering done false ceiling framing done electrical wiring done sprinkler shifting done false ceiling sheet installation done pop grooving done carpentry done first coat done. Modular delivered done 22nd june Modular installation work in progress. Due to the modular team not align for 10 days delayed. | 2026-07-04 17:56:16 +0530 | Reshma Melanta | Others: | 2026-06-17 23:24:48 +0530 | Savita Parab | Execution: Floor covering done false ceiling framing done electrical wiring done sprinkler shifting done false ceiling sheet installation done pop grooving done carpentry done first coat in progress
17929 | Turnkey | Dec'25 | Naresh Kumar Reddy | Devagiri Opal | BNG - HRBR | Yes |  | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | CDP Due | 1503669 | 9999 | 0 | 0 | 0 | 188 | 0 | 140368 | 300734 | 469010 | 583558 |  |  | 2026-01-05 | 2026-01-06 12:46 | 2026-01-06 | 2026-01-08 18:55 | 2026-01-10 |  | 2026-01-26 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-01-14 |  | 2026-01-15 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-08 |  | 2026-02-09 |  |  |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-19 |  | 2026-02-19 | [6 empty] | 2026-02-25 |  | 2026-03-06 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-09 |  |  |  | 2026-03-31 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-02-19 |  | 2026-01-17 |  | Unknown | 2026-01-04 | 2026-01-06 12:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1274295 | 229373 | 2026-01-09 06:07:18 +0530 | Bhargavi Maddala | DCM: Possession-March 2nd week Devagiri (NF) Mint green with oak finishes-living/dining Foyer shoe rack along with wall highlighter Living room tv unit paneling behind the door wall paper/pvc louvers False ceiling Dining area crockery with glass finishes Glass/mirror highlighter pooja room in place of refrigerator Vanity cabinet with wall highlighter partition Kitchen tall unit-pantry(shelves) fluted glass finishes tandem draw base, wall, loft Utility common wall b/w utility & balcony-demolishedÂ washing machine-wall unit sink, w/m Master Bedroom wardrobe with lot of storage-AristoÂ dresser Gallery wall Bedroom-1(kbr) B-3M, G-4.5Y(pink/blue) wardrobe, loft work station cum bay window seater Dresser false ceiling Bedroom-2(PBR/GBR) Wardrobe, loft foldable table top restrooms vanity cabinets wall highlighter in b/w bedrooms Balcony decor Budget-10-12L cdp-9th 2P.m
17930 | Turnkey | Dec'25 | omkar bhosale | Natasha Atlantis | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [7 empty] | Hold | Design | Design Finalization | 850836 | 109999 | 1046493 | 0 | 0 | 25 | 135 | 0 | 145252 | 284434 | 311151.6 |  |  | 2026-01-05 | 2026-01-04 14:27 | 2026-01-07 | 2026-01-07 11:05 | 2026-01-31 | 2026-02-01 18:43 | 2027-01-09 |  | 2027-01-12 |  | 2027-01-15 |  | 2026-02-01 | 2026-01-31 05:30 | 2026-02-02 | 2026-02-03 18:38 | 2026-02-03 | 2026-02-05 13:02 | 2026-03-05 | 2026-03-05 16:40 | 2027-01-15 |  | 2027-01-18 |  | 2027-01-18 |  | 2027-01-22 |  | 2027-01-23 |  |  |  | 2027-01-29 |  | 2027-01-30 |  | 2027-02-02 |  | 2027-02-02 | [6 empty] | 2027-02-08 |  | 2027-02-17 |  | 2027-02-16 |  | 2027-02-17 |  | 2027-02-18 |  | 2027-02-20 |  |  |  | 2027-03-14 |  | 2027-03-16 |  | 2027-03-17 | [5 empty] | 2027-02-02 |  | 2026-12-31 |  | Unknown | 2026-01-04 | 2026-01-04 13:01 | 966143 | 159634 | 0 | 0 | 0 | 0 | 967487.021 | 152669 | 2026-07-10 11:29:57 +0530 | Divya Rahangdale | CX will receive the possession by December. | 2026-06-25 17:47:00 +0530 | Naved Malik | Some Image was uploaded | 2026-06-14 16:39:54 +0530 | Divya Rahangdale | Some Image was uploaded
17931 | Turnkey | Dec'25 | Sangeeta Gupta | Prestige Song Of The South | BNG - HSR | Yes | Shefali | Akshay Ds | Soumya KP |  |  | Sachin I Betageri | Ranjith Kumar |  | Ramesh Nayak | Raghavendra Gowda | Active | Preproduction | 2D | 2673745 | 501944 | 1971515 | 2673745 | 0 | 7 | 12 | 0 | 0 | 1211179 | 960622 |  |  | 2026-01-05 | 2026-01-06 15:18 | 2026-02-11 | 2026-02-11 15:34 | 2026-02-17 | 2026-02-15 16:26 | 2026-04-24 | 2026-04-24 16:26 | 2026-05-07 | 2026-05-07 14:08 | 2026-05-20 | 2026-05-21 02:24 | 2026-02-13 | 2026-02-14 16:07 | 2026-02-14 | 2026-02-15 12:40 | 2026-02-16 | 2026-02-20 16:10 | 2026-02-25 | 2026-02-25 17:31 | 2026-06-24 | 2026-06-24 17:14 | 2026-06-24 | 2026-06-24 18:50 | 2026-06-08 | 2026-05-30 17:36 | 2026-07-11 | 2026-07-08 11:12 | 2026-07-09 | 2026-07-08 11:13 |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-18 |  | 2026-07-18 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-18 |  | 2026-04-01 | 2026-04-24 11:44 | Site is RTMI | 2026-01-04 | 2026-01-06 15:16 | 2052252.14 | 346502 | 2910408.1494 | 491376 | 0 | 0 | 2910408.1494 | 491376 | 2026-06-04 11:24:49 +0530 | Priyanka Mathur | Hello ma'am, As per our discussion following are the points that we need to modify: Living room - TV unit - Louver need to be changed as per photo shared, Tall unit internal laminate countertop same color. - Adjacent wall - wall panel with rose gold mirror and egg white and wooden laminate to be added, additional curtain pelmet, - Crockery unit - Tall unit internal laminate countertop same color, brown tinted glass, rose gold profile, add profile light on open unit, add hanging light, wooden ceiling panel will have cove light. crockery back panel will have rose gold mirror.Â - Sofa back panel- panel cutting for MCB box KitchenÂ - done, fluted grey glass with black profile.Â Daughter roomÂ - profile light bottom of loft, lacquered glass, scale light below study wall ledge, blue color bed back panel, Wardrobe pattern as per image shared, rose gold and black handle option, remove wallpaper, False ceiling aligned to bed, Study roomÂ - rose gold handle,Â Master bedroomÂ - door loft bottom light, used cloth unit to be matt finish, matt skirting, change the louvers, wardrobe pattern need to change, mirror full height from bottom | 2026-06-04 11:24:15 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-27 19:28:29 +0530 | Sanjeev Jha | Some Image was uploaded
17932 | Turnkey | Dec'25 | Sandeep Rajadhyaksha | 10 BKC | MUM - GOR | Yes | Mandar Ambre | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Nilesh Patel | Rizwan Mistry | Murali S | Umang Shah | Vinay Surve | Active | Installation | Execution | 4331153 | 4331153 | 5236412 | 5024752 | 4331153 | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-04 13:27 | 2026-01-04 | 2026-01-04 18:33 | 2026-01-04 | 2026-01-04 18:37 | 2026-02-17 | 2026-02-17 11:55 | 2026-02-17 | 2026-02-17 15:35 | 2026-02-25 | 2026-02-25 21:04 | 2026-01-04 | 2026-01-05 19:23 | 2026-01-05 | 2026-01-05 19:41 | 2026-01-05 | 2026-01-12 17:21 | 2026-01-13 | 2026-01-13 17:06 | 2026-02-27 | 2026-02-27 14:06 | 2026-03-02 | 2026-02-27 14:26 | 2026-02-26 | 2026-02-24 13:48 | 2026-03-01 | 2026-03-04 17:06 | 2026-03-05 | 2026-03-11 20:24 |  |  | 2026-03-30 | 2026-04-08 11:09 | 2026-04-08 | 2026-04-08 14:41 | 2026-04-11 | 2026-04-08 14:54 | 2026-04-08 | 2026-04-08 16:14 |  |  |  |  | 2026-04-08 18:27 | 2026-04-16 | 2026-04-15 21:07 | 2026-04-26 | 2026-04-24 19:11 | 2026-04-25 | 2026-04-28 12:54 | 2026-04-24 | 2026-05-18 14:11 | 2026-05-16 | 2026-05-18 16:45 | 2026-05-20 | 2026-05-23 10:59 |  |  | 2026-06-22 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-04-08 | 2026-04-08 17:16 | 2026-01-14 | 2026-02-15 15:41 | Site is RTMI | 2026-01-04 | 2026-01-04 13:26 | 4437637 | 798774 | 5041349.0655 | 842758 | 4364964.2788 | 736955 | 4364964.2788 | 736955 | 2026-07-13 11:34:33 +0530 | Nilesh Patel | Modulars Installation works has been completed at site 3 Bedrooms completed Scope of works has been completed at site along with Deep cleaning except Wallpaper Living room Paint base works has been completed (1st coat paint pending will be done once CX scope Civil works is done ETA 16th July for completion of Civil works) | 2026-06-16 12:13:09 +0530 | Nilesh Patel | Execution: False Ceiling Frame works has been completed on site Electrical Wiring works has been completed Living room wiring works has been completed washroom Electrical Wiring works has been completed On site Carpentry works is in progress Gypsm Sheet installation works has been completed at site (rectification works is in progress) Modular Installation works is in progress Blocker Carpentry works are delayed at siteLaminate for TV unit and Dining area has not been delivered at siteCarpentry Rectification works pending | 2026-06-01 12:36:39 +0530 | Nilesh Patel | Execution: False Ceiling Frame works has been completed on site Electrical Wiring for 3 bedrooms has been completed Living room wiring works has been completed washroom Electrical Wiring works has been completed On site Carpentry works is in progress Gypsm Sheet installation works has been completed at site Modular Installation works is in progress Blocker Light cut outs in 2 bedrooms are wrongly done at siteModular Team is not aligned on daily Basis.Bedroom 1 Bathroom door frame works not started yetDebris clearing pending at site due to which Final coat cannot be startedFloor Coverings to be replaced
17933 | Turnkey | Dec'25 | Deepak Gowda | Independent House | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Ruthwik S K | Ranjith Kumar | Murali S | Raghavendra S | Vishwa Hiremath | Hold | Production | 100% Payment | 3135947 | 2007999 | 2253865 | 3283932 | 3160947 | 5 | 9 | 0 | 0 | 0 | 1127948 |  |  | 2026-01-05 | 2026-01-16 12:58 | 2026-01-10 | 2026-01-28 12:17 | 2026-01-28 | 2026-01-28 12:24 | 2026-03-10 | 2026-03-10 17:34 | 2026-03-26 | 2026-03-26 12:58 | 2026-03-26 | 2026-03-26 14:55 | 2026-01-31 | 2026-01-27 12:37 | 2026-01-29 | 2026-01-28 12:51 | 2026-01-28 | 2026-01-28 16:32 | 2026-02-01 | 2026-02-01 12:55 | 2026-03-26 | 2026-03-26 18:05 | 2026-04-15 | 2026-03-26 19:18 | 2026-04-15 | 2026-03-26 19:12 | 2026-04-01 | 2026-04-03 00:24 | 2026-04-07 | 2026-04-12 01:55 |  |  | 2026-05-19 | 2026-05-21 15:30 | 2026-05-23 | 2026-05-23 13:50 | 2026-06-08 | 2026-05-26 09:20 | 2026-05-26 | 2026-06-04 15:03 |  |  |  |  | 2026-06-09 12:10 | 2026-06-19 | 2026-06-18 19:58 | 2026-07-10 | 2026-07-04 18:08 | 2026-07-05 |  | 2026-07-15 |  | 2026-07-02 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-26 | 2026-06-06 17:27 | 2026-02-06 | 2026-03-10 17:25 | Site is RTMI | 2026-01-04 | 2026-01-04 14:12 | 2301842.2564 | 397199 | 3393685.0139 | 577210 | 3236319.5015 | 558449 | 3236319.5015 | 558449 | 2026-07-06 15:03:38 +0530 | Ranjith Kumar | Some Image was uploaded | 2026-07-01 10:02:13 +0530 | Ranjith Kumar | Some Image was uploaded | 2026-06-08 23:09:29 +0530 | Ruthwik S K | Bonito Side Only Floor Covering Cx Side - Electrical, False Ceiling, Civil, Floor Polishing & Cleaning
17934 | Turnkey | Dec'25 | Shripad Kawathekar | arihant Advik's | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-04 14:41 | 2026-01-05 |  | 2026-01-10 |  | 2026-01-22 |  | 2026-01-25 |  | 2026-01-28 |  | 2026-01-10 |  | 2026-01-11 |  | 2026-01-11 |  | 2026-01-12 |  | 2026-01-28 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-04 |  | 2026-02-05 |  |  |  | 2026-02-11 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 | [6 empty] | 2026-02-21 |  | 2026-03-02 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-05 |  |  |  | 2026-03-27 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-02-15 |  | 2026-01-13 |  | Unknown | 2026-01-04 | 2026-01-04 14:22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-01-04 14:40:22 +0530 | Aryan Singh | Some Image was uploaded
17935 | Sub Project |  | Mrs Hemani | Piramal Aranya | MUM - GOR |  |  | Manzoor Shaikh | Shantanu Parakh |  |  | Nilesh Patel | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-14 14:50 | 2026-01-05 | 2026-01-14 14:50 | 2026-01-16 | 2026-01-14 14:50 | 2026-01-16 | 2026-01-14 14:52 | 2026-01-15 | 2026-01-14 14:53 | 2026-01-15 | 2026-01-14 14:54 | 2026-01-14 | 2026-01-14 14:51 | 2026-01-15 | 2026-01-14 14:51 | 2026-01-14 | 2026-01-14 14:51 | 2026-01-15 | 2026-01-14 14:51 | 2026-01-14 | 2026-01-14 14:55 | 2026-01-17 | 2026-01-14 14:56 | 2026-01-14 | 2026-01-14 14:56 | 2026-01-15 | 2026-01-14 14:57 | 2026-01-15 | 2026-01-14 14:57 |  |  | 2026-01-17 | 2026-01-14 14:59 | 2026-01-15 | 2026-01-14 15:00 | 2026-01-17 | 2026-01-14 15:00 | 2026-01-14 | 2026-01-14 15:01 |  |  |  |  | 2026-01-26 21:12 | 2026-02-03 | 2026-02-02 16:05 | 2026-02-06 | 2026-02-04 14:23 | 2026-02-05 | 2026-02-16 16:28 | 2026-02-04 | 2026-02-16 16:37 | 2026-02-16 | 2026-02-16 17:11 | 2026-02-17 | 2026-02-16 17:47 |  |  | 2026-02-18 | 2026-02-18 13:04 | 2026-02-20 | 2026-02-18 13:05 | 2026-02-18 | 2026-02-18 13:11 |  |  |  |  | 2026-01-15 | 2026-01-26 21:11 | 2026-01-15 | 2026-01-14 14:52 | Unknown | 2026-01-04 | 2026-01-14 14:49 | 0 | 0 | 0 | 0 | 46609 | 0 | 46609 | 0 | 2026-02-16 15:19:56 +0530 | Nilesh Patel | Execution: HOB & Chimney Delivered on site | 2026-02-10 16:57:22 +0530 | Nilesh Patel | Execution: HOB & Chimney at warehouse
17936 | Turnkey | Dec'25 | Nishkam Ojha | The Views Adani | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [7 empty] | Hold | Design | Design Finalization | 1425713 | 181804 | 1810868 | 0 | 0 | 81 | 86 | 0 | 245910 | 446113 | 551886.4 |  |  | 2026-01-05 | 2026-01-04 15:50 | 2026-01-10 | 2026-01-10 18:32 | 2026-01-11 | 2026-01-11 19:54 | 2027-01-09 |  | 2027-01-12 |  | 2027-01-15 |  | 2026-01-11 | 2026-01-21 17:18 | 2026-01-12 | 2026-01-27 15:10 | 2026-01-27 | 2026-01-29 13:13 | 2026-02-27 | 2026-02-27 19:01 | 2027-01-15 |  | 2027-01-18 |  | 2027-01-18 |  | 2027-01-22 |  | 2027-01-23 |  |  |  | 2027-01-29 |  | 2027-01-30 |  | 2027-02-02 |  | 2027-02-02 | [6 empty] | 2027-02-08 |  | 2027-02-17 |  | 2027-02-16 |  | 2027-02-17 |  | 2027-02-18 |  | 2027-02-20 |  |  |  | 2027-03-14 |  | 2027-03-16 |  | 2027-03-17 | [5 empty] | 2027-02-02 |  | 2026-12-31 |  | Unknown | 2026-01-04 | 2026-01-04 15:44 | 1534634 | 276234 | 0 | 0 | 0 | 0 | 1491856.032 | 247990 | 2026-07-10 11:38:05 +0530 | Divya Rahangdale | CX will receive the possession by December. | 2026-07-02 13:56:50 +0530 | Divya Rahangdale | Hold | 2026-06-25 17:49:33 +0530 | Naved Malik | Some Image was uploaded
17937 | Turnkey | Dec'25 | Vijay D | Devagiri Opal | BNG - HRBR | Yes | Chandini Nj | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | DCM Due | 941048 | 9999 | 0 | 0 | 0 | 192 | 0 | 84106 | 188210 | 295517 | 363216.8 |  |  | 2026-01-05 | 2026-01-06 12:51 | 2026-01-04 |  | 2026-01-11 |  | 2026-01-23 |  | 2026-01-26 |  | 2026-01-29 |  | 2026-01-11 |  | 2026-01-12 |  | 2026-01-12 |  | 2026-01-13 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-05 |  | 2026-02-06 |  |  |  | 2026-02-12 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-16 | [6 empty] | 2026-02-22 |  | 2026-03-03 |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-06 |  |  |  | 2026-03-28 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-02-16 |  | 2026-01-14 |  | Unknown | 2026-01-04 | 2026-01-04 16:02 | 0 | 0 | 0 | 0 | 0 | 0 | 797498 | 143549 | 2026-01-04 16:28:47 +0530 | Chandini Nj | Possession - mayÂ BudgetÂ Â - 8 to 10L Apartment-devagiri opal Theme- Jepandi Direction - EAST facing How many people are going to stay - Husband and wife. Work Profile -both are at it filed Purpose (Rental/Own) -OWN Purpose Deeper understanding (Usual hobbies):drawing, reading books work profile - levis itÂ Living area - Instead of tv, looking for projector. Book shelf in the corner. and foyer wall designs. Shape sofa and wallpaper some of area with wallÂ beading designsÂ Kitchen - single bowl sink, 2ft hob unit, 2ft fridge, breakfast table, tall unit, shelves above the breakfast counter. and wall unit, Utility - one storage for keeping liquid items. Dining - wall mounting pooja unitÂ Â Â MBR - Hinged wardrobe with loft, Dresser with ledges, Foldable ledge next to the bed. Bedroom - Hinged wardrobe with loft. Vanities in both the washrooms.
17938 | Turnkey | Dec'25 | Rita Khatri | Piramal Vaikunth | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Aryan Singh |  | Hold | Design | Design Finalization | 1073772 | 209999 | 1333072 | 0 | 0 | 44 | 88 | 0 | 112133 | 345332 | 406308.8 |  |  | 2026-01-05 | 2026-01-04 17:27 | 2026-02-22 | 2026-02-22 12:54 | 2026-03-02 | 2026-03-02 21:39 | 2026-07-20 |  | 2026-07-23 |  | 2026-07-26 |  | 2026-03-02 | 2026-03-04 18:48 | 2026-03-03 | 2026-03-04 19:07 | 2026-03-04 | 2026-03-05 17:47 | 2026-03-11 | 2026-03-11 11:10 | 2026-07-26 |  | 2026-07-29 |  | 2026-07-29 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-13 |  | 2026-08-13 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-08-13 |  | 2026-07-15 |  | Site is RTMI | 2026-01-04 | 2026-01-04 17:18 | 1129722 | 203350 | 0 | 0 | 0 | 0 | 1111628.0777 | 188202 | 2026-07-10 10:59:40 +0530 | Anil Jagtap | cx will receive the possession by August*26 | 2026-06-27 14:43:47 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-25 16:11:53 +0530 | Siddhi Chaphekar | Client has asked to do site visit ,as they dont have keys they will confirm the meeting.
17939 | Turnkey | Dec'25 | Seema Prakash | Prestige Prim Rose | BNG - HSR | Yes | Shefali | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 1750248 | 9999 | 0 | 0 | 0 | 192 | 0 | 165026 | 350050 | 525074 | 700099.2 |  |  | 2026-01-05 | 2026-01-04 17:45 | 2026-01-04 |  | 2026-01-10 |  | 2026-01-22 |  | 2026-01-25 |  | 2026-01-28 |  | 2026-01-10 |  | 2026-01-11 |  | 2026-01-11 |  | 2026-01-12 |  | 2026-01-28 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-04 |  | 2026-02-05 |  |  |  | 2026-02-11 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 | [6 empty] | 2026-02-21 |  | 2026-03-02 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-05 |  |  |  | 2026-03-27 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-02-15 |  | 2026-01-13 |  | Unknown | 2026-01-04 | 2026-01-04 17:38 | 0 | 0 | 0 | 0 | 0 | 0 | 1483261 | 266987 | 2026-01-04 17:48:38 +0530 | Muralikrishna Udupi | Some Image was uploaded
17940 | Turnkey | Dec'25 | Anu Sudhir Thakur | Prestige City | MUM - Thane | Yes | Pooja Nakul Sharma | [9 empty] | Active | Prospect | CDP Due | 1211723 | 9999 | 0 | 0 | 0 | 188 | 0 | 111173 | 242345 | 364923 | 483283.2 |  |  | 2026-01-05 | 2026-01-04 22:35 | 2026-01-08 | 2026-01-08 12:55 | 2026-01-14 |  | 2026-01-26 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-01-14 |  | 2026-01-15 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-08 |  | 2026-02-09 |  |  |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-19 |  | 2026-02-19 | [6 empty] | 2026-02-25 |  | 2026-03-06 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-09 |  |  |  | 2026-03-31 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-02-19 |  | 2026-01-17 |  | Unknown | 2026-01-04 | 2026-01-04 22:33 | 0 | 0 | 0 | 0 | 0 | 0 | 1119399.032 | 184839 | 2026-01-08 14:57:33 +0530 | Pooja Nakul Sharma | DCM: Mr Thakur 2.5 bhkÂ Prestige MulundÂ Poss- January endÂ Family of 2 1. Kitchen- sink and cooktop space to be swapped.Â 2. There will be 2 sinks, smaller one in kitchen and bigger in dry area. 3. Need tall unit for appliances. m/o, otg 4. No wall cabinets above cooktop. 5. A small unit for small appliances.Â 6. LR- Tv unit, crockery unit, shoerack, 3 doors.Â 7. MBR- bed and tv to be swapped, addtional walk in wardrobe if builder approves, dresser beside bed, king bed, wardrobe, tv unit. 8. Bedroom1 - Queen bed, walk in wardrobe 9. Bedroom 2- mandir, study, wardrobe and sofa cum bed. 10. Budget- 8L | 2026-01-04 18:04:38 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-01-04 18:01:51 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
17941 | Turnkey | Dec'25 | Saurabh S | godrej splendor | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1518102 | 353951 | 1174463 | 1518102 | 0 | 3 | 135 | 0 | 0 | 570101 | 594049.6 |  |  | 2026-01-05 | 2026-01-04 18:18 | 2026-01-09 | 2026-01-09 11:59 | 2026-01-09 | 2026-01-09 19:47 | 2026-02-26 | 2026-02-26 18:15 |  |  |  |  | 2026-01-09 | 2026-01-10 17:18 | 2026-01-10 | 2026-01-11 10:16 | 2026-01-11 | 2026-01-12 12:31 | 2026-01-14 | 2026-01-14 16:10 | 2026-02-27 | 2026-02-27 11:34 | 2026-03-02 | 2026-02-27 16:08 | 2026-03-02 | 2026-02-27 12:09 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-15 |  | 2026-08-15 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-15 |  | 2026-02-13 | 2026-02-26 18:11 | Site is RTMI | 2026-01-04 | 2026-01-04 18:15 | 1170820.8435 | 202036 | 1383983.0421 | 238820 | 0 | 0 | 1383983.0421 | 238820 | 2026-07-10 12:14:48 +0530 | Chittipireddy Sriharish | Foyer - No changes Living room - Tv unit no changes Kitchen Window - need to be placed above the sink Kids bedroom - need one more option References will be shared by client Master bedroom - need on more option Lofts need to be wall to wall Guest bedroom No sliding - wall will be constructed by client (civil work need to be checked) wall accents options required Dining side crockery unit - possiblity need to be checked Balcony - bar unit designs are pending | 2026-03-01 17:08:15 +0530 | Chittipireddy Sriharish | Incremental Sign-Off: False ceiling - designs need to be suggested a prt from peripheral ceiling Pooja unit - need to be removed | 2026-03-01 16:42:56 +0530 | Chittipireddy Sriharish | Design Finalization Fees: Theme Abstract & japandi style Foyer - shoe rack will be moved out side Wall accent - need to come up with another option MBR - Wall accent Dresser unit - need to be changed Full length mirror with storage Kids bedroom Blue color theme
17942 | Turnkey | Dec'25 | Sakshi Airen | HM Scottsville | BNG - HSR | Yes | Priyanka Inchoor | Akshay Ds | Kowshik | [7 empty] | Hold | Preproduction | Site Readiness 1 | 943027 | 278048 | 1081825 | 943027 | 0 | 19 | 88 | 0 | 0 | 310790 | 354188.8 |  |  | 2026-01-05 | 2026-01-04 18:37 | 2026-01-09 | 2026-01-09 14:47 | 2026-01-13 | 2026-01-13 10:48 | 2026-03-13 | 2026-03-11 19:20 | 2026-03-30 | 2026-03-29 15:17 | 2026-03-30 | 2026-03-29 15:21 | 2026-01-13 | 2026-01-20 16:41 | 2026-01-14 | 2026-01-21 12:27 | 2026-01-21 | 2026-01-22 18:30 | 2026-02-05 | 2026-02-05 16:35 | 2026-03-29 | 2026-03-29 19:52 | 2026-04-01 | 2026-03-30 15:08 | 2026-02-25 | 2026-02-11 17:30 | 2026-10-04 |  | 2026-10-05 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-15 |  | 2026-10-15 | [6 empty] | 2026-10-21 |  | 2026-10-30 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-02 |  |  |  | 2026-11-24 |  | 2026-11-26 |  | 2026-11-27 | [5 empty] | 2026-10-15 |  | 2026-02-07 | 2026-02-15 14:59 | Site is RTMI | 2026-01-04 | 2026-01-04 18:35 | 1022423.65 | 165024 | 1089825.7076 | 167495 | 0 | 0 | 1089825.7076 | 167495 | 2026-07-03 13:30:20 +0530 | Akshay Ds | As per latest communication from the customre, sit epossession has been delayed and now its expected timelines for handover has been revised to September hence project will be on HOLD Sep end | 2026-04-18 12:19:45 +0530 | Akshay Ds | Some Image was uploaded | 2026-04-18 12:17:37 +0530 | Akshay Ds | Some Image was uploaded
17943 | Turnkey | Dec'25 | Vivek Shrivastava | Kalpataru Shristi Namah | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Rajkumar Suthar | Rizwan Mistry |  | Avi Thakkar | Vinay Surve | Lost | Preproduction | 2D | 880056 | 197509 | 1007545 | 1090921 | 975008 | 97 | 5 | 0 | 0 | 351074 | 331473.2 |  |  | 2026-01-05 | 2026-02-17 12:21 | 2026-02-17 | 2026-02-17 13:18 | 2026-02-17 | 2026-02-17 13:30 | 2026-03-15 | 2026-03-06 19:33 | 2026-03-13 | 2026-03-13 18:17 | 2026-03-13 | 2026-03-13 18:59 | 2026-02-17 | 2026-02-17 19:02 | 2026-02-18 | 2026-02-18 16:51 | 2026-02-18 | 2026-02-19 12:07 | 2026-02-25 | 2026-03-01 13:49 | 2026-03-13 | 2026-03-14 11:56 | 2026-03-17 | 2026-03-17 17:39 | 2026-03-17 | 2026-03-17 13:53 | 2026-03-27 | 2026-03-25 20:17 | 2026-03-26 | 2026-03-25 20:18 |  |  | 2026-04-04 | 2026-04-09 13:45 | 2026-04-07 |  | 2026-10-22 |  | 2026-10-22 | [6 empty] | 2026-10-28 |  | 2026-11-06 |  | 2026-11-05 |  | 2026-11-06 |  | 2026-11-07 |  | 2026-11-09 |  |  |  | 2026-12-01 |  | 2026-12-03 |  | 2026-12-04 | [5 empty] | 2026-10-22 |  | 2026-02-26 | 2026-03-06 14:30 | Site is RTMI | 2026-01-04 | 2026-02-11 16:40 | 1153531.7544 | 176574 | 1251411.7758 | 192343 | 1144302.2824 | 174662 | 1056585.062 | 160178 | 2026-04-11 21:02:03 +0530 | Shantanu Parakh | Hi Team, The client had approved the FDM design, and the project was progressing as per standard timelines. Post sharing the PKO design docket, the client has expressed the intent to cancel the project, citing that Bonito is expensive. However, there has been no significant increase in cost, and the estimation was clearly explained at every stage. The client is not open to exploring optimization options and is inclined towards direct cancellation. The no-refund policy has been explained to the client. | 2026-04-11 18:49:41 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-07 16:24:34 +0530 | Zoya Bhatkar | Some Image was uploaded
17944 | Turnkey | 2026-06-01 | Nima desai | Godrej Exquisite | MUM - Thane | Yes | Mehnaz Ashraf | Anamika Dolai | Rachna Abhyankar | [5 empty] | Nishtha Valawalkar |  | Active | Prospect | Onboarding Due | 1849369 | 541799 | 2658748 | 0 | 0 | 5 | 0 | 0 | 13012 | 566613 | 727945.6 |  |  | 2026-01-05 | 2026-06-29 12:41 | 2026-01-14 | 2026-06-30 16:19 | 2026-07-06 | 2026-07-07 16:30 | 2026-07-21 |  | 2026-07-24 |  | 2026-07-27 |  | 2026-07-07 | 2026-07-08 13:07 | 2026-07-08 | 2026-07-10 12:28 | 2026-07-10 |  | 2026-07-11 |  | 2026-07-27 |  | 2026-07-30 |  | 2026-07-30 |  | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-14 |  | 2026-08-14 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-08-14 |  | 2026-07-12 |  | Site is RTMI | 2026-01-04 | 2026-06-29 12:29 | 2253176 | 405571 | 0 | 0 | 0 | 0 | 2169159.0421 | 358176 | 2026-07-13 13:55:50 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: December 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: The site is not accessible. DEM 1 â€“ 18th July 2026 10% Payment Stage â€“ already paid 29% No civil work planned. Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (3000) Special Offer (50000) Special Offer (40000 Free Shoerack Offer May'26 100% GST waiver PM fee waiver (5%) Design fee waiver (5% Laminate Upgrade Offer - June 26 Final Closing Value Discussed: â‚¹ 18,49,369 Checklist terms - descoping clear delay compensation, agreement terms are not clear. Rejections: Approval for extended price protection is required, as the client expects possession in December 2026. Client wants to complete the design stage before site handover from the builder and begin production/execution only after site access. Client is not aligned with the project timeline and expects handover within 3 months of site accessibility along with additional scope of work. Client expects project handover within 3 months from December and seeks delayed compensation as committed by the sales team if timelines are exceeded. | 2026-07-13 12:33:09 +0530 | Sanjana Swami | number busy (called on alternate number 7984906099) | 2026-07-13 11:54:15 +0530 | Sanjana Swami | number busy | [6 empty] | 2026-06-28 | 541799 | Ravi Roy
17945 | Turnkey | Dec'25 | Prashanth Rao | Samhita serene mtb | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [7 empty] | Hold | Preproduction | Site Readiness 1 | 1288846 | 384218 | 1016570 | 1288846 | 0 | 18 | 69 | 0 | 0 | 389090 | 515538.4 |  |  | 2026-01-06 | 2026-01-16 13:25 | 2026-02-03 | 2026-02-03 12:57 | 2026-02-03 | 2026-02-03 13:43 | 2026-03-06 | 2026-03-06 10:30 | 2026-04-19 | 2026-04-19 15:40 |  |  | 2026-01-12 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-05 12:44 | 2026-02-05 | 2026-02-05 18:13 | 2026-02-13 | 2026-02-13 11:53 | 2026-04-19 | 2026-04-19 16:02 | 2026-05-30 | 2026-04-19 16:58 | 2026-05-30 | 2026-04-19 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-14 |  | 2026-08-14 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-08-14 |  | 2026-02-14 | 2026-03-06 10:20 | Site is RTMI | 2026-01-05 | 2026-01-08 16:32 | 1121564.825 | 185197 | 1424925.426 | 234357 | 0 | 0 | 1424925.426 | 234357 | 2026-06-17 00:21:57 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-30 15:26:49 +0530 | Yogesh B | Some Image was uploaded | 2026-02-05 18:13:12 +0530 | Bency Chacko | Possession - 2nd week of March 2026 Design meeting - Weekends IDM - 20th Feb 2026 B2C - self-funded No on-site work is planned No Vendor work is planned as well Offers, Quote and timelines are cleared Checklist cleared. Plan 10,20,30,40
17946 | Turnkey | Dec'25 | Sunny Rajput rajput | Raymond | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [7 empty] | Lost | Design | Design Finalization | 822834 | 84999 | 1021383 | 0 | 0 | 113 | 61 | 0 | 161851 | 246850 | 329133.6 |  |  | 2026-01-05 | 2026-01-05 13:25 | 2026-01-11 | 2026-01-11 17:54 | 2026-01-22 | 2026-01-22 13:32 | 2026-06-30 |  | 2026-07-03 |  | 2026-07-15 |  | 2026-01-22 | 2026-01-22 15:52 | 2026-01-23 | 2026-01-22 15:55 | 2026-01-22 | 2026-01-22 16:49 | 2026-03-05 | 2026-03-05 16:37 | 2026-07-15 |  | 2026-07-18 |  | 2026-07-18 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-02 |  | 2026-08-02 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-08-02 |  | 2026-06-20 |  | Unknown | 2026-01-04 | 2026-01-04 22:35 | 865579 | 155804 | 0 | 0 | 0 | 0 | 833741.6697 | 140771 | 2026-06-10 11:14:21 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-03-10 13:39:17 +0530 | Anamika Dolai | WC done, Client is yet to receive the possession, as informed by client will receive the possession by the end of the march 2026. Hence , client communicated the same through whatsapp group. | 2026-02-22 17:08:16 +0530 | Chaitali Sawant | KitchenÂ - Add loft on other side Living roomÂ - add display unit for books and show pcs, sofa cum bed Bedroom 1- glass wardrobe , sofa cum bed with storage (from outside maybe not in bonito scope) Master bedroom - Bed position will change. Wardrobe and dresser is ok. study table removed , hydraulic bed with storage, with round edges.Â vanity - glass partition is the requirement but need to add in design stage .Â Not included -Â curtain , mattress , lights switch plates
17947 | Turnkey | Dec'25 | madhavi bhatt | Prestige siesta | MUM - Thane | Yes | Maasoumeh Raza | [7 empty] | Vandana Preet |  | Active | Prospect | CDP Due | 2796745 | 9999 | 0 | 0 | 0 | 189 | 0 | 269676 | 559349 | 977328 | 980393.2 |  |  | 2026-01-05 | 2026-01-07 17:07 | 2026-01-07 | 2026-01-07 19:44 | 2026-01-12 |  | 2026-01-24 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-01-12 |  | 2026-01-13 |  | 2026-01-13 |  | 2026-01-14 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-06 |  | 2026-02-07 |  |  |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 | [6 empty] | 2026-02-23 |  | 2026-03-04 |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-07 |  |  |  | 2026-03-29 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-02-17 |  | 2026-01-15 |  | Site is RTMI | 2026-01-04 | 2026-01-07 17:04 | 0 | 0 | 0 | 0 | 0 | 0 | 2370123 | 426622 | 2026-01-07 19:34:30 +0530 | Maasoumeh Raza | Some Image was uploaded | 2026-01-07 17:10:01 +0530 | Vandana Preet | Some Image was uploaded
17948 | Turnkey | Dec'25 | vinayak sawant | ** | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 2478383 | 9999 | 0 | 0 | 0 | 192 | 0 | 237839 | 495677 | 863093 | 871775.6 |  |  | 2026-01-05 | 2026-03-06 14:32 | 2026-01-05 |  | 2026-01-18 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-01-19 |  | 2026-01-20 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-08 |  | 2026-02-12 |  | 2026-02-13 |  |  |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-23 | [6 empty] | 2026-03-01 |  | 2026-03-10 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-13 |  |  |  | 2026-04-04 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-02-23 |  | 2026-01-21 |  | Site is RTMI | 2026-01-04 | 2026-03-06 14:25 | 0 | 0 | 0 | 0 | 0 | 0 | 2100325 | 378058 | 2026-01-10 20:28:03 +0530 | Karuna Shinde | Some Image was uploaded
17949 | Turnkey | Dec'25 | sarvari pawar | Lodha Crown | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Tanveer Patel | Akshat Shrivastava | Murali S | Nishtha Valawalkar | Shailendra Mishra | Active | Installation | Execution | 1082481 | 1082482 | 1227697 | 1122248 | 1082481 | 21 | 40 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-04 22:10 | 2026-01-07 | 2026-01-07 19:15 | 2026-01-13 | 2026-01-11 11:06 | 2026-03-05 | 2026-03-05 13:14 | 2026-03-05 | 2026-03-05 14:00 |  |  | 2026-01-11 | 2026-01-12 15:30 | 2026-01-12 | 2026-01-12 15:49 | 2026-01-12 | 2026-01-13 13:53 | 2026-02-20 | 2026-02-20 14:05 | 2026-03-17 | 2026-03-17 19:03 | 2026-03-20 | 2026-03-19 11:35 | 2026-03-20 | 2026-03-18 16:12 | 2026-05-29 | 2026-05-05 14:14 | 2026-05-06 | 2026-05-05 14:15 |  |  | 2026-05-12 | 2026-05-21 19:15 | 2026-05-21 | 2026-05-21 20:11 | 2026-05-24 | 2026-05-21 20:24 | 2026-05-21 | 2026-05-26 13:57 |  |  |  |  | 2026-05-28 01:07 | 2026-06-05 | 2026-06-04 21:19 | 2026-06-15 | 2026-06-15 17:26 | 2026-06-14 | 2026-06-19 17:12 | 2026-06-15 | 2026-06-23 14:03 | 2026-06-24 | 2026-06-24 18:17 | 2026-06-30 | 2026-07-11 13:38 |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-08-05 | [5 empty] | 2026-05-21 | 2026-05-26 20:14 | 2026-05-07 | 2026-03-05 12:49 | Site is RTMI | 2026-01-04 | 2026-01-04 22:10 | 1040421 | 187275 | 1128659.9521 | 194071 | 1168875.5914 | 188005 | 1168875.5914 | 188005 | 2026-06-23 00:53:42 +0530 | Tanveer Patel | Execution: Material is in transit will reach by 25th to 27th june | 2026-06-16 00:03:30 +0530 | Tanveer Patel | Procurement: Electrical work completed false ceiling work completed pop punning work completed From 18th June painting will start | 2026-06-11 10:54:11 +0530 | Tanveer Patel | Procurement: pop punning started - 11 june gala cutting done on 10th june
17950 | Turnkey | Dec'25 | Mr Melroy Fernandes | Kalpataru Srishti Namaah | MUM - Thane | Yes | Rutuja Kotwal | Divya Rahangdale | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | CDP Due | 1828710 | 9999 | 0 | 0 | 0 | 117 | 0 | 172872 | 365742 | 609631 | 670465.6 |  |  | 2026-01-05 | 2026-01-04 22:12 | 2026-03-08 | 2026-03-20 19:12 | 2026-01-04 |  | 2026-04-07 |  | 2026-04-10 |  | 2026-04-13 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-04-13 |  | 2026-04-16 |  | 2026-04-16 |  | 2026-04-20 |  | 2026-04-21 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-05-01 |  | 2026-05-01 | [6 empty] | 2026-05-07 |  | 2026-05-16 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-19 |  |  |  | 2026-06-10 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-05-01 |  | 2026-03-29 |  | Unknown | 2026-01-04 | 2026-01-04 22:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1552555 | 276154 | 2026-03-08 19:45:29 +0530 | Rutuja Kotwal | RE- DCM: Mr. Melroy FernandesÂ 2 BHK.Â Â Sq.ft.-628+22Â Direction - SEÂ Safety door,Â L- shaped sofa, Reading corner near the window,Â open kitchen concept with l-shaped platform.Â Kitchen renovation.Â Â Balcony decoration.Â And swing.Â Â Daughter's Room 15 years.Â Â Bed, wardrobe, study tableÂ with storageÂ Â CommonÂ bathroomÂ will beÂ dividedÂ intoÂ powder room andÂ one WC area.Â MBR -Â Queen size BedÂ Wardrobe with LoftÂ Side table with StorageÂ Â Â TV LedgeÂ Â CDP 14 March 11 am.Â Â Budget 10 12 lakhsÂ Â BudgetÂ 16-17 lakhs with LF and w/o civilÂ Â WithÂ civilÂ it willÂ reach tillÂ 20 lakhs.Â Â | 2026-01-07 22:35:23 +0530 | Moksh Mehta | DCM: Client Name: - Melroy Fernandes Property: - Kalpataru Srishti Namah Possession Date: - Mar'26 Sq Ft: - 628 + 22 sqft No of Members: - Couple (40+) (HR Professionals) + Daughter (15+) ( Archer) Ent: Shoe Rack (15 - 20 Pairs) outside or InsideWall Concepts. Living Room: - TV Unit 46" inch with Home Theater provision of controls from each room to be Switch on & Off3-Seater Sofa + 1 Chair (4 People).Wall concepts.Showcase for medals & AwardsFamily Photos Seating reference to be shared by Cx Dining Area: - 4 Seater Dining areaCrockery UnitTemple & Altar Kitchen: - Semi Modular KitchenBase - 2 no's , Wall - 2nos & Loft - 1 no'sMicrowave spaceAmbient Lighting Master Bedroom :- Queen size BedWardrobe with LoftSide tale with StorageReading Nook with Book Storage TV Ledge Daughter's Bedroom :- Queen size Bed / Sofa cum Bed / Murphy BedWardrobe with loftStudy with Storage Bathroom's Base Vanity Unit's for all Misc:- False CeilingPaintingElectrification | 2026-01-04 22:13:06 +0530 | Nishtha Valawalkar | Some Image was uploaded
17951 | Turnkey | Dec'25 | Saharsh Sawant | Highland Park | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Faraz Soudagar | Akshat Shrivastava | Murali S | Saloni Chawan | Aakash Gaikwad | Active | Handover | Project Closure Pending | 1269929 | 1273748 | 1154971 | 1540493 | 1269929 | 5 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-20 18:33 | 2026-01-21 | 2026-01-21 13:58 | 2026-01-27 | 2026-01-22 11:47 | 2026-02-12 | 2026-02-12 19:10 | 2026-02-24 | 2026-02-24 19:04 |  |  | 2026-01-22 | 2026-01-23 11:39 | 2026-01-23 | 2026-01-23 17:33 | 2026-01-23 | 2026-01-29 15:48 | 2026-02-08 | 2026-02-08 14:34 | 2026-02-25 | 2026-02-25 18:19 | 2026-02-28 | 2026-02-26 13:03 | 2026-02-26 | 2026-02-09 16:26 | 2026-03-07 | 2026-03-11 09:34 | 2026-03-12 | 2026-03-11 09:34 |  |  | 2026-03-26 | 2026-03-30 16:37 | 2026-03-30 | 2026-03-31 12:18 | 2026-04-03 | 2026-03-31 12:24 | 2026-04-15 | 2026-04-06 22:15 |  |  |  |  | 2026-04-09 11:59 | 2026-04-19 | 2026-04-18 21:45 | 2026-04-29 | 2026-04-27 20:44 | 2026-04-28 | 2026-04-30 18:54 | 2026-04-27 | 2026-05-09 17:32 | 2026-05-08 | 2026-05-11 23:16 | 2026-05-13 | 2026-05-23 18:45 |  |  | 2026-07-09 | 2026-07-10 18:09 | 2026-07-11 | 2026-07-10 18:25 | 2026-07-12 | 2026-07-10 18:37 |  |  |  |  | 2026-03-31 | 2026-04-07 11:24 | 2026-02-09 | 2026-02-08 16:02 | Site is RTMI | 2026-01-04 | 2026-01-05 15:51 | 1142653.8057 | 199063 | 1514660.5566 | 265498 | 1267150.9961 | 216599 | 1267150.9961 | 216599 | 2026-07-01 23:08:28 +0530 | Faraz Soudagar | Execution: Deep cleaning done Qc rejected due to painting issue FInal coat of paint - 4th July | 2026-06-29 16:10:53 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-23 22:26:59 +0530 | Faraz Soudagar | Execution: Profile shutter installationd done - 23rd June Final coat of paint ETA - 27th June Deep cleaning - 28th June QC - 29th June HO - 29th June
17953 | Turnkey | Dec'25 | Umashankar Tilak Dhari Nag | poonam estate cluster 1 | MUM - Thane | Yes | Honey Thakkar | Divya Rahangdale | Rushika More |  | Vaishali G | Akash Jadhav | Sandeep Tiwari | Murali S | Prashant Panigrahi | Aakash Gaikwad | Completed | Complete | Completed | 774756 | 774757 | 849987 | 814251 | 811967 | 9 | 13 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-07 14:51 | 2026-01-10 | 2026-01-10 19:02 | 2026-01-22 | 2026-01-22 17:38 | 2026-02-06 | 2026-02-06 13:09 | 2026-02-18 | 2026-02-10 19:07 | 2026-02-13 | 2026-02-11 11:04 | 2026-01-22 | 2026-01-23 12:21 | 2026-01-23 | 2026-01-23 12:26 | 2026-01-23 | 2026-01-23 12:57 | 2026-01-23 | 2026-01-23 19:42 | 2026-02-15 | 2026-02-15 17:35 | 2026-02-24 | 2026-02-17 19:13 | 2026-02-24 | 2026-02-17 | 2026-02-19 | 2026-02-21 18:10 | 2026-02-22 | 2026-02-21 18:12 |  |  | 2026-02-27 | 2026-02-28 13:11 | 2026-02-28 | 2026-02-28 18:43 | 2026-02-28 | 2026-02-28 22:29 | 2026-02-28 | 2026-03-10 19:15 |  |  |  |  | 2026-03-11 17:16 | 2026-03-21 | 2026-03-20 21:25 | 2026-03-30 | 2026-03-28 23:51 | 2026-03-29 | 2026-04-21 17:07 | 2026-05-30 | 2026-04-23 16:26 | 2026-04-23 | 2026-04-27 13:47 | 2026-04-29 | 2026-05-02 17:36 |  |  | 2026-04-19 | 2026-06-05 19:28 | 2026-04-21 | 2026-06-05 19:34 | 2026-05-30 | 2026-06-05 19:41 |  |  |  |  | 2026-03-11 | 2026-03-11 17:15 | 2026-02-06 | 2026-02-06 12:59 | Site is RTMI | 2026-01-04 | 2026-01-07 14:50 | 920724.2538 | 153303 | 846532.1916 | 140224 | 833989.6146 | 139876 | 833989.8455 | 138013 | 2026-06-29 16:12:36 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-04-21 01:29:04 +0530 | Snehankit Agre | Execution: POP & Paneling work completed. | 2026-04-17 14:24:17 +0530 | Christopher Macwan
17954 | Turnkey | Dec'25 | Uday Malap | RUNWAL FOREST | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Saloni Chawan |  | Active | Design | Design Finalization | 1625377 | 174911 | 1300020 | 0 | 0 | 160 | 0 | 0 | 312702 | 487613 | 650150.8 |  |  | 2026-01-05 | 2026-01-20 18:37 | 2026-01-31 | 2026-01-31 10:37 | 2026-02-03 | 2026-02-03 11:03 | 2026-03-12 | 2026-03-12 12:36 | 2026-03-12 | 2026-03-12 13:37 |  |  | 2026-02-03 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-04 18:34 | 2026-02-04 | 2026-02-05 11:48 | 2026-02-11 | 2026-02-11 18:32 | 2027-12-31 |  | 2028-01-03 |  | 2028-01-03 |  | 2028-01-07 |  | 2028-01-08 |  |  |  | 2028-01-14 |  | 2028-01-15 |  | 2028-01-18 |  | 2028-01-18 | [6 empty] | 2028-01-24 |  | 2028-02-02 |  | 2028-02-01 |  | 2028-02-02 |  | 2028-02-03 |  | 2028-02-05 |  |  |  | 2028-02-27 |  | 2028-02-29 |  | 2028-03-01 | [5 empty] | 2028-01-18 |  | 2026-04-15 | 2026-03-12 12:33 | Site is Non-RTMI | 2026-01-04 | 2026-01-05 15:51 | 1358044.341 | 224240 | 0 | 0 | 0 | 0 | 1686293.239 | 278447 | 2026-06-27 15:46:33 +0530 | Asavari Vare | Some Image was uploaded | 2026-03-10 12:47:25 +0530 | Asavari Vare | Some Image was uploaded | 2026-02-11 18:36:25 +0530 | Divya Rahangdale | DDM1 - 1st MarchÂ DDM2 - 8th MarchÂ DDM3 - 15th March
17955 | Turnkey | Dec'25 | Prabha Panchanadan | Aspen Greens @ The Prestige City | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2801623 | 9999 | 2801623 | 0 | 0 | 172 | 0 | 270163 | 560325 | 884573 | 1076562.8 |  |  | 2026-01-06 | 2026-01-05 14:48 | 2026-01-06 | 2026-01-06 16:18 | 2026-01-24 | 2026-01-24 11:25 | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-05 | 2026-01-05 14:47 | 2374257 | 427366 | 0 | 0 | 0 | 0 | 2374257 | 427366 | 2026-01-06 16:18:35 +0530 | Janush Bojamma C T | RGM- 17955 Bedroom - simple and minimalÂ Kitchen , Living , foyer - Main areaÂ Bedroom -1 - GuestÂ Queen size bed Study area 2.5ft- larger spaceÂ Openable wardrobe + Dresser+ 7ft no loftf Entry - east facingÂ Entry - Slight slopeÂ Table setup on the rightÂ Shoe rack under the stairsÂ Wash basin plumbing - Stairs Washing machine , dryer , small sink Window - Utility - Right bottom ( To check window) Maid room - Integration - Plan to be worked on Vacuum lift - Plan near living or dining optionsÂ Living room Tv unit area - Plan with and without Â Sofa ideas- Living roomÂ Dining room - Crockery + bar unit near Dining seater -Â Open to open kitchenÂ God facing eastÂ Half of Maids room KitchenÂ 2ft hob, 3ft chimneyÂ Both side working space - Hob AppliancesÂ Roller shutter oil rack -BPO micro oven Fridge - 3ft 615ltr Samsung Single sink Crockery- Units - Inside glass shutter for crockery Loft above both sides Utility - cylinder storage-2 Dish washerÂ Glass - Shutters , lift up mechanisms Glass- lights Mechanisms- On the cornerÂ Bedroom 1 washroomÂ Vanity below + mirrorÂ Rods near walking way to shower + wc area Curtains automated with pressÂ Deck- two walls can be planned with Finesta slidingÂ Use it for study 0r leisure areaÂ Family roomÂ Tv unit areaÂ Bookshelves - decor not much storageÂ Bedroom 2- Master bedroom Wardrobe + loftÂ 2 seaterÂ Small lounge with coffee table +2 chair Vanity + storageÂ Tall units storageÂ Bedroom 3- Guest room/ KidsÂ Wardrobe + loftÂ Study space Bedroom 4- GBR/ Kids Wardrobe + loftÂ WorkstationÂ Dresser + mirrorÂ Vanity Toiler 3 + 4Â Vanity Mirror Already provided + the shower partitionÂ False ceiling - concept in the rooms+ Living area + diningÂ Stair case- Highlight landing area designÂ First to ground (memory wall) Terrace floor Party area- Electric stoveÂ ClosedÂ Dyson , vacuum cleaner spaceÂ Â Budget - 20 - 2r lakhs
17956 | Turnkey | Dec'25 | Amit Chand Thakur | Eden Park Prestige | BNG - HRBR | Yes |  | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Lost | Design | Design Finalization | 777040 | 94999 | 954585 | 0 | 0 | 124 | 50 | 0 | 138113 | 241488 | 302439.6 |  |  | 2026-01-05 | 2026-01-06 18:44 | 2026-01-07 | 2026-01-07 16:38 | 2026-01-16 | 2026-01-14 13:22 | 2026-02-07 | 2026-02-07 15:40 | 2026-02-12 | 2026-02-12 11:26 | 2026-02-14 | 2026-02-15 12:17 | 2026-01-14 | 2026-01-19 19:21 | 2026-01-15 | 2026-01-20 15:32 | 2026-01-20 | 2026-01-22 17:52 | 2026-01-29 | 2026-01-29 16:25 | 2026-12-31 |  | 2027-01-03 |  | 2027-01-03 |  | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-18 |  | 2027-01-18 | [6 empty] | 2027-01-24 |  | 2027-02-02 |  | 2027-02-01 |  | 2027-02-02 |  | 2027-02-03 |  | 2027-02-05 |  |  |  | 2027-02-27 |  | 2027-03-01 |  | 2027-03-02 | [5 empty] | 2027-01-18 |  | 2026-02-06 | 2026-02-05 13:01 | Site is RTMI | 2026-01-04 | 2026-01-06 11:43 | 808971 | 145614 | 0 | 0 | 0 | 0 | 810230.1282 | 133785 | 2026-05-15 23:02:18 +0530 | Rajeshwari S | Some Image was uploaded | 2026-02-19 17:45:06 +0530 | Rajeshwari S | Some Image was uploaded | 2026-02-03 14:28:13 +0530 | Rajeshwari S | Client is aligned with the process Aligned with the meetings. Nikita to share the details and take it forward. Estimation closed for Rs.7,57,916. After all the offers.
17957 | Turnkey | Dec'25 | Mr. Amit Pratap Singh | lake view apartment | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S | Janvi Nagdeo | Vishwa Hiremath | Completed | Complete | Completed | 1138367 | 1138368 | 1196772 | 1087322 | 1138367 | 35 | 12 | 0 | 0 | 0 | 0 |  |  | 2026-01-05 | 2026-01-06 18:44 | 2026-01-07 | 2026-01-07 14:47 | 2026-01-14 | 2026-01-14 14:51 | 2026-02-11 | 2026-02-11 19:31 | 2026-02-11 | 2026-02-11 19:39 |  |  | 2026-01-14 | 2026-01-15 12:37 | 2026-01-15 | 2026-01-15 19:26 | 2026-01-15 | 2026-01-16 16:03 | 2026-01-21 | 2026-01-21 12:30 | 2026-02-13 | 2026-02-13 19:23 | 2026-02-13 | 2026-02-13 22:01 | 2026-02-13 | 2026-02-13 21:37 | 2026-02-18 | 2026-02-19 15:41 | 2026-02-20 | 2026-02-20 23:14 |  |  | 2026-03-04 | 2026-03-05 16:16 | 2026-03-05 | 2026-03-06 15:13 | 2026-03-10 | 2026-03-06 16:40 | 2026-03-15 | 2026-03-06 20:20 |  |  |  |  | 2026-03-07 11:50 | 2026-03-14 | 2026-03-14 22:00 | 2026-03-28 | 2026-03-26 19:01 | 2026-03-27 | 2026-03-30 23:14 | 2026-03-26 | 2026-04-04 14:55 | 2026-04-04 | 2026-04-06 08:06 | 2026-04-17 | 2026-04-16 12:13 |  |  | 2026-04-30 | 2026-04-30 16:59 | 2026-05-11 | 2026-04-30 18:28 | 2026-05-12 | 2026-04-30 23:05 |  |  |  |  | 2026-03-22 | 2026-03-06 18:34 | 2026-02-04 | 2026-02-11 19:16 | Site is RTMI | 2026-01-04 | 2026-01-06 11:54 | 1014214 | 182558 | 1095421.078 | 188744 | 1191098.6619 | 196530 | 1191098.6619 | 196530 | 2026-05-30 17:31:40 +0530 | Saddam Hussain Z M | Execution: Scale Light installation pending due to client dependency, ETA 3rd June. | 2026-05-03 13:10:10 +0530 | Saddam Hussain Z M | Execution: Wallpaper & scale Light installation pending due to client dependency, acknowledgement taken ETA 12th May | 2026-04-18 17:08:03 +0530 | Saddam Hussain Z M | Some Image was uploaded
17958 | Turnkey | Dec'25 | Merlyn Correa | Purva atmosphere | BNG - HRBR | Yes | Chandini Nj | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Harshit Choudhary | Saddam Hussain Z M | Murali S | Mohammed Rasick | Abdul Shafeen | Active | Installation | Execution | 1635081 | 1635081 | 2256972 | 1793725 | 1635081 | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-12-31 | 2026-02-01 13:12 | 2026-02-03 | 2026-02-03 13:24 | 2026-02-03 | 2026-02-03 13:41 | 2026-03-22 | 2026-03-22 22:17 | 2026-03-28 | 2026-03-28 17:43 | 2026-04-12 | 2026-04-12 10:31 | 2026-02-03 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-12 19:47 | 2026-02-12 | 2026-02-16 13:49 | 2026-02-19 | 2026-02-19 12:17 | 2026-04-12 | 2026-04-12 14:12 | 2026-04-15 | 2026-04-13 07:27 | 2026-04-15 | 2026-04-11 | 2026-05-08 | 2026-05-13 19:43 | 2026-05-14 | 2026-05-13 20:14 |  |  | 2026-05-22 | 2026-05-26 17:47 | 2026-05-28 | 2026-05-28 16:03 | 2026-05-30 | 2026-05-30 10:17 | 2026-05-30 | 2026-05-31 13:45 |  |  |  |  | 2026-06-02 12:04 | 2026-06-10 | 2026-06-11 21:00 | 2026-06-23 | 2026-06-22 13:36 | 2026-06-22 | 2026-06-24 17:57 | 2026-06-22 | 2026-06-26 12:46 | 2026-06-26 | 2026-06-26 18:43 | 2026-07-02 | 2026-07-02 13:19 |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-05-31 | 2026-06-02 12:03 | 2026-02-20 | 2026-03-06 11:17 | Site is RTMI | 2025-12-30 | 2026-01-13 13:02 | 1912688 | 344283 | 2071916.3156 | 326627 | 1953614.1041 | 314173 | 1953614.1041 | 314173 | 2026-05-26 18:30:10 +0530 | Chandini Nj | Some Image was uploaded | 2026-05-26 18:28:48 +0530 | Chandini Nj | Some Image was uploaded | 2026-05-26 18:28:22 +0530 | Chandini Nj | Some Image was uploaded
17959 | Turnkey | Dec'25 | Srihari J | Brigade Orchards | BNG - HRBR | Yes | Arjun M V | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Handover | Project Closure Pending | 780445 | 780445 | 824478 | 706608 | 780445 | 15 | 18 | 0 | 0 | 0 | 0 |  |  | 2026-01-09 | 2026-01-16 22:35 | 2026-01-16 | 2026-01-16 22:46 | 2026-01-17 | 2026-01-17 11:10 | 2026-02-03 | 2026-02-03 15:37 | 2026-02-22 | 2026-02-22 21:08 |  |  | 2026-01-17 | 2026-01-17 11:11 | 2026-01-18 | 2026-01-17 13:33 | 2026-01-17 | 2026-01-20 10:48 | 2026-01-23 | 2026-01-23 11:03 | 2026-02-22 | 2026-02-22 21:29 | 2026-04-05 | 2026-03-30 18:13 | 2026-04-05 | 2026-03-30 | 2026-04-07 | 2026-04-10 19:35 | 2026-04-11 | 2026-04-22 01:37 |  |  | 2026-04-24 | 2026-04-25 15:50 | 2026-04-26 | 2026-04-26 13:34 | 2026-04-29 | 2026-04-27 09:12 | 2026-04-27 | 2026-04-28 19:54 |  |  |  |  | 2026-04-29 15:03 | 2026-05-07 | 2026-05-06 22:17 | 2026-05-26 | 2026-05-26 18:46 | 2026-05-14 | 2026-05-23 19:13 | 2026-05-26 | 2026-05-30 20:35 | 2026-05-30 | 2026-05-31 10:18 | 2026-06-09 | 2026-06-08 11:04 |  |  | 2026-06-27 | 2026-06-29 18:07 | 2026-06-29 | 2026-06-30 08:24 | 2026-06-30 | 2026-06-30 21:22 |  |  |  |  | 2026-04-27 | 2026-04-29 13:24 | 2026-01-24 | 2026-01-28 13:14 | Site is RTMI | 2026-01-08 | 2026-01-16 21:25 | 967281.0615 | 159708 | 812205.9998 | 134101 | 880403.089 | 145364 | 880403.089 | 145364 | 2026-07-07 00:49:37 +0530 | Saddam Hussain Z M | Execution: Observation Points - 16th July | 2026-06-15 13:13:19 +0530 | Saddam Hussain Z M | Some Image was uploaded | 2026-06-02 09:17:18 +0530 | Banka H Suthar | Enclosed please find the Weekly Report for the reporting period from 01/06/26 to 06/06/2026 for your kind perusal. Project status Execution Key Decisions : Electrical work- bomito Floor covering - bonito scope False ceiling - Bonito Modular - installation in progress Request you to kindly go through the report and request for providing the decisions on priority to avoid any impact on the overall project delivery
17961 | Turnkey | Dec'25 | Ramesh hingad jain | reserve grove | MUM - GOR | Yes | Rahul Agrawal |  | Shahid Chougley | [7 empty] | Active | Prospect | 10% Payment | 4173251 | 9999 | 3825746 | 0 | 0 | 175 | 0 | 407326 | 834650 | 1342338 | 1578937.6 |  |  | 2026-01-08 | 2026-01-09 15:27 | 2026-01-20 | 2026-01-20 20:01 | 2026-01-21 | 2026-01-21 13:11 | 2026-02-02 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 | [6 empty] | 2026-03-04 |  | 2026-03-13 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-16 |  |  |  | 2026-04-07 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-02-26 |  | 2026-01-24 |  | Unknown | 2026-01-07 | 2026-01-09 15:26 | 3242158 | 583588 | 0 | 0 | 0 | 0 | 3536654 | 636597 | 2026-01-20 12:04:56 +0530 | Safalta Karkera | DCM: 1. Please select your budget for Interior Designing? Rs. 20-25 Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? 4. Who will be living in this home? Joint Family 5. What activities do you usually perform at home? (Choose top 23) Working from Home, Hosting Guests, Family Bonding, Relaxing & Unwinding, Prayer 6. What is your preferred entertainment style? Casual get-togethers 7. Do you prefer any Smart home features? Lighting Control, Security, Automation 8. What is your possession date? 2026-01-09 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Safety door, Digital lock, Shoe rack, Console, Seating Dcor & Living Room1. Choose your decor inspirations Heritage items, Travel souvenirs 2. Any specific signature design feature required Chandelier, Art installation 3. Whats the primary use of your living room? TV focus , Multipurpose 4. Any absolute no-go styles, colors, or materials? 5. Must-have furniture or features? Sofa, TV unit, Home speakers, Speakers, Coffee table, Bookshelves, Puja unit, Display unit , Statement Wall/ Feature Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Microwave, Fridge, Hob, Chimney BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Swing Master Bedroom - Additional units Study table, Dresser Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Swing Other Bedroom - Additional units Study table , Bookshelf , Dresser BathroomsPreferred vanity style What do you prefer? Shower partitions What are your requirements for Utility Area? Top Storage, Bottom Storage, Laundry space, Washing machine space Balcony & OutdoorHow do you intend to use your balcony for? Seating, Planters, Storage b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? Final Vision1. Any space in the home that you want to put in Spotlight? 2. Do you want the design to reflect any personal story, cultural influence, or special memory | 2026-01-09 15:30:55 +0530 | Rishu | Some Image was uploaded
17962 | Turnkey | Dec'25 | benjamin jacob | gee cee emrald | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Hold | Design | Design Finalization | 1409543 | 140999 | 1409543 | 0 | 0 | 47 | 130 | 0 | 281864 | 477047 | 509632.8 |  |  | 2026-01-08 | 2026-01-12 17:05 | 2026-01-13 | 2026-01-13 11:16 | 2026-01-19 | 2026-01-14 13:24 | 2026-10-25 |  | 2026-10-28 |  | 2026-10-31 |  | 2026-01-14 | 2026-01-14 13:44 | 2026-01-15 | 2026-01-14 13:44 | 2026-01-14 | 2026-01-19 14:01 | 2026-03-05 | 2026-03-05 16:36 | 2026-10-31 |  | 2026-11-03 |  | 2026-11-03 |  | 2026-11-07 |  | 2026-11-08 |  |  |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-18 |  | 2026-11-18 | [6 empty] | 2026-11-24 |  | 2026-12-03 |  | 2026-12-02 |  | 2026-12-03 |  | 2026-12-04 |  | 2026-12-06 |  |  |  | 2026-12-28 |  | 2026-12-30 |  | 2026-12-31 | [5 empty] | 2026-11-18 |  | 2026-10-16 |  | Unknown | 2026-01-07 | 2026-01-07 14:28 | 1507565.0525 | 245523 | 0 | 0 | 0 | 0 | 1507565.0525 | 245523 | 2026-07-14 12:43:19 +0530 | Divya Rahangdale | The client will receive possession by September. | 2026-06-26 17:27:15 +0530 | Shraddha Pansare | Client possession delayed till Septemeber. Its an old process project hence I tried to convince him for designing and then to keep the project on hold but he refused to do the designing before intial measurement of the apartment. | 2026-06-04 12:07:22 +0530 | Shraddha Pansare | Some Image was uploaded
17963 | Turnkey | Dec'25 | Hiren Sheth | Shikkhar | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Rajkumar Suthar | Rizwan Mistry | Murali S | Manasi Patil | Vinay Surve | Active | Installation | Execution | 2934481 | 2934482 | 3321521 | 2771754 | 3013629 | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-08 | 2026-01-11 16:51 | 2026-01-13 | 2026-01-13 12:00 | 2026-01-19 | 2026-01-13 12:32 | 2026-02-27 | 2026-02-27 16:22 | 2026-02-27 | 2026-02-27 20:02 | 2026-03-01 | 2026-03-01 11:12 | 2026-01-13 | 2026-01-14 16:47 | 2026-01-14 | 2026-01-15 14:51 | 2026-01-15 | 2026-01-20 14:03 | 2026-01-21 | 2026-01-21 14:39 | 2026-03-11 | 2026-03-11 12:50 | 2026-03-11 | 2026-03-11 13:00 | 2026-03-17 | 2026-03-10 17:24 | 2026-03-20 | 2026-03-21 15:27 | 2026-03-22 | 2026-03-21 15:27 |  |  | 2026-04-06 | 2026-04-18 19:46 | 2026-04-19 | 2026-04-19 13:25 | 2026-04-22 | 2026-04-19 14:57 | 2026-04-19 | 2026-04-20 19:37 |  |  |  |  | 2026-04-23 15:35 | 2026-05-06 | 2026-05-05 21:19 | 2026-05-28 | 2026-05-26 09:26 | 2026-05-22 | 2026-05-25 18:48 | 2026-05-26 | 2026-06-05 21:50 | 2026-06-05 | 2026-06-05 22:02 | 2026-06-07 | 2026-06-13 10:43 |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-04-21 | 2026-04-23 15:34 | 2026-01-22 | 2026-02-27 15:44 | Site is RTMI | 2026-01-07 | 2026-01-11 16:47 | 2814849 | 506672 | 3022542.5086 | 499081 | 3245950.5341 | 535977 | 3245949.9006 | 523903 | 2026-06-01 16:35:51 +0530 | Suraj Jaiswar | Execution: kick off planned on 25th April False ceiling done. electrical wiring done. Carpentry work is in progress. Painting work is going on Site is ready for Modular Dispatch - 4th Jun | 2026-05-23 11:35:46 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-22 19:42:19 +0530 | Reshma Melanta | Some Image was uploaded
17964 | Turnkey | Dec'25 | Sanjana Sanjay Bole | LODHA AMARA | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Asif Shaikh | Aditya Vikram | Murali S | Nishtha Valawalkar | Aakash Gaikwad | Completed | Complete | Completed | 1251151 | 1252832 | 1634699 | 1498262 | 1626353 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-08 | 2026-01-07 19:15 | 2026-01-09 | 2026-01-09 11:18 | 2026-01-12 | 2026-01-10 20:31 | 2026-01-30 | 2026-01-30 18:25 | 2026-02-06 | 2026-02-06 14:32 | 2026-02-06 | 2026-02-06 15:09 | 2026-01-09 | 2026-01-10 13:15 | 2026-01-11 | 2026-01-11 11:10 | 2026-01-11 | 2026-01-13 18:05 | 2026-01-29 | 2026-01-29 12:36 | 2026-02-12 | 2026-02-12 19:44 | 2026-02-12 | 2026-02-12 20:08 | 2026-02-10 | 2026-02-09 | 2026-02-16 | 2026-02-13 20:24 | 2026-02-14 | 2026-02-13 20:24 |  |  | 2026-02-18 | 2026-02-25 10:01 | 2026-02-27 | 2026-02-27 13:07 | 2026-03-02 | 2026-02-27 14:22 | 2026-02-27 | 2026-02-28 19:28 |  |  |  |  | 2026-03-08 18:30 | 2026-03-17 | 2026-03-17 21:14 | 2026-03-29 | 2026-03-27 21:54 | 2026-03-28 | 2026-03-31 12:52 | 2026-03-27 | 2026-04-05 23:32 | 2026-04-04 | 2026-04-07 16:39 | 2026-04-13 | 2026-04-20 12:00 |  |  | 2026-05-13 | 2026-05-21 14:31 | 2026-05-14 | 2026-05-27 11:39 | 2026-05-26 | 2026-05-27 11:45 |  |  |  |  | 2026-03-04 | 2026-03-08 18:29 | 2026-01-30 | 2026-01-29 13:44 | Site is RTMI | 2026-01-07 | 2026-01-07 19:14 | 1385338 | 249360 | 1532578.3772 | 259056 | 1645812.1402 | 278596 | 1269941.3565 | 213735 | 2026-07-08 17:42:12 +0530 | Asif Shaikh | Project Closure Pending: Project Closure Pending: Snag installation Completed. One Bed refund to be Iniatited. | 2026-06-29 16:08:11 +0530 | Asif Shaikh | Some Image was uploaded | 2026-06-25 23:12:17 +0530 | Asif Shaikh | Some Image was uploaded
17965 | Turnkey | Dec'25 | Raju pvs | MXOthers | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1990272 | 9999 | 1990272 | 0 | 0 | 166 | 0 | 189028 | 398054 | 597082 | 796108.8 |  |  | 2026-01-08 | 2026-01-10 17:17 | 2026-01-30 | 2026-01-30 17:25 | 2026-02-05 | 2026-01-30 17:32 | 2026-02-11 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-17 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-24 |  | 2026-02-25 |  |  |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-03-07 | [6 empty] | 2026-03-13 |  | 2026-03-22 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-25 |  |  |  | 2026-04-16 |  | 2026-04-18 |  | 2026-04-19 | [5 empty] | 2026-03-07 |  | 2026-02-02 |  | Site is RTMI | 2026-01-07 | 2026-01-10 17:14 | 1686671 | 303600 | 0 | 0 | 0 | 0 | 1686671 | 303600 | 2026-01-30 17:24:40 +0530 | Adarsh K | RGM Budget - Actual Budget : 7-10 lakhs Requirement Budget : 20-25 lakhs | 2026-01-14 13:18:04 +0530 | Pulivarthi Nirosha | 1. Budget -8 to 10L 2. Property Name & Possession - 3bhk, individual house 3. Carpet Area - 4. BHK - 3 BHK individual duplex 5. Family Size - 4ppl Name - Nagaraju Spouse - Child 1 - Child 2 - 6. Shoe Rake/Foyer - yes 4. Living/Dining Room Inclusions - TV Unit, Crockery Unit, Pooja unit 5. Bed Room Inclusions - Wardrobe, Study Unit, Dresser Unit 6. Kitchen Inclusions -Â : Tall unit - : Base unit - : Wall unit - : Loft -Â : Granite/Quartz - no 7. Service Scope - :False Ceiling -Â Living :Painting - :Electricity - 8. Utility/Janitor Unit -Â 9. Timeline -March end
17966 | Turnkey | Dec'25 | Ms Sheetal V Sarveiya | L&T Rejuve 360 | MUM - Thane | Yes | Rutuja Kotwal | [7 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 1931483 | 14000 | 0 | 0 | 0 | 188 | 0 | 179148 | 386297 | 605067 | 746971.2 |  |  | 2026-01-06 | 2026-01-08 11:37 | 2026-01-06 |  | 2026-01-23 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-17 |  | 2026-02-18 |  |  |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-28 |  | 2026-02-28 | [6 empty] | 2026-03-06 |  | 2026-03-15 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-18 |  |  |  | 2026-04-09 |  | 2026-04-11 |  | 2026-04-12 | [5 empty] | 2026-02-28 |  | 2026-01-26 |  | Site is RTMI | 2026-01-05 | 2026-01-08 11:32 | 0 | 0 | 0 | 0 | 0 | 0 | 1636850 | 294633
17967 | Turnkey | Dec'25 | Alliance and rewards pvt ltd | Aim | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Akash Jadhav | Sandeep Tiwari | Murali S | Avi Thakkar | Vinay Surve | Active | Installation | Execution | 1393602 | 1398689 | 1059685 | 1051415 | 1393602 | 41 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-06 | 2026-01-23 11:30 | 2026-01-23 | 2026-01-23 16:02 | 2026-01-23 | 2026-01-23 16:06 | 2026-03-05 | 2026-03-05 19:57 | 2026-03-07 | 2026-03-07 17:36 | 2026-03-08 | 2026-03-08 16:25 | 2026-01-23 | 2026-01-23 17:07 | 2026-01-24 | 2026-01-26 13:04 | 2026-01-26 | 2026-02-03 11:27 | 2026-02-08 | 2026-02-08 11:09 | 2026-03-08 | 2026-03-08 17:32 | 2026-03-11 | 2026-03-12 14:07 | 2026-03-11 | 2026-03-12 14:03 | 2026-04-18 | 2026-04-15 16:10 | 2026-04-16 | 2026-04-15 16:10 |  |  | 2026-04-29 | 2026-05-02 13:10 | 2026-05-03 | 2026-05-03 16:21 | 2026-05-06 | 2026-05-03 16:52 | 2026-05-04 | 2026-04-30 18:42 |  |  |  |  | 2026-05-05 14:37 | 2026-05-16 | 2026-05-15 22:44 | 2026-05-26 | 2026-05-26 15:21 | 2026-05-26 | 2026-05-29 13:37 | 2026-05-26 | 2026-06-02 21:50 | 2026-06-02 | 2026-06-04 17:36 | 2026-06-06 | 2026-06-09 13:45 |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-05-03 | 2026-05-05 08:58 | 2026-02-09 | 2026-03-05 19:53 | Site is RTMI | 2026-01-05 | 2026-01-23 11:25 | 1140088.6385 | 196731 | 1132782.8277 | 195470 | 1479481.9529 | 255295 | 1479481.9529 | 255295 | 2026-06-02 22:33:14 +0530 | Akash Jadhav | Procurement: floor covering work done false ceiling work done modular deliver at site 5th june | 2026-05-16 15:52:53 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-29 18:49:07 +0530 | Karan Chavda | Some Image was uploaded
17969 | Turnkey | Dec'25 | Sangita Sanjay Raje | Wadhwa asteria | MUM - Thane | Yes | Hemant Sonar | Divya Rahangdale | Anil Kuwar |  | Viraj Jadhav | Faraz Soudagar | Aditya Vikram | Murali S | Aryan Singh | Shailendra Mishra | Active | Handover | Project Closure Pending | 1781070 | 1781070 | 1568007 | 1675434 | 1781070 | 15 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-01-09 | 2026-01-08 19:17 | 2026-01-13 | 2026-01-15 12:43 | 2026-01-31 | 2026-02-03 11:08 | 2026-02-18 | 2026-02-18 17:26 | 2026-02-18 | 2026-02-18 17:29 | 2026-03-13 | 2026-03-13 10:49 | 2026-01-31 | 2026-01-31 05:30 | 2026-02-01 | 2026-02-02 18:54 | 2026-02-04 | 2026-02-03 15:23 | 2026-02-18 | 2026-02-18 11:55 | 2026-03-14 | 2026-03-14 16:02 | 2026-03-14 | 2026-03-18 16:37 | 2026-03-14 | 2026-03-18 11:33 | 2026-03-25 | 2026-03-23 17:55 | 2026-03-24 | 2026-03-23 20:28 |  |  | 2026-04-02 | 2026-04-04 17:24 | 2026-04-09 | 2026-04-09 12:48 | 2026-04-13 | 2026-04-09 16:09 | 2026-04-11 | 2026-04-14 14:16 |  |  |  |  | 2026-04-15 12:13 | 2026-04-24 | 2026-04-23 19:21 | 2026-05-15 | 2026-05-16 18:12 | 2026-05-14 | 2026-05-15 21:58 | 2026-05-16 | 2026-05-20 15:17 | 2026-05-19 | 2026-05-22 14:52 | 2026-05-24 | 2026-06-16 13:02 |  |  | 2026-07-09 | 2026-06-30 20:10 | 2026-07-11 | 2026-06-30 20:45 | 2026-07-12 | 2026-06-30 21:54 |  |  |  |  | 2026-04-11 | 2026-04-14 15:57 | 2026-02-19 | 2026-02-18 17:14 | Site is RTMI | 2026-01-08 | 2026-01-08 19:09 | 1687856.5058 | 269696 | 1907269.0104 | 305913 | 2004877.2686 | 322027 | 2004877.2686 | 322027 | 2026-06-23 22:30:34 +0530 | Faraz Soudagar | Execution: Shorts supply delivery done - 20th June Profile delivery done - 21st June Snag raised ETA not recieved. Mirrors not delivered - measurement done on -16th June Measurment team requested - 11th June Deep cleaning - 25th June QC- 26th Jnue HO - 27th June | 2026-06-01 14:24:16 +0530 | Faraz Soudagar | Execution: Modular delivery done - 22th May Modular start date - 26th may Profile shutters ETA pending. | 2026-05-18 15:27:53 +0530 | Faraz Soudagar | Dispatch Due: Floor covering done SRD task closed,
17970 | Turnkey | Dec'25 | Vicky Ambwani | Regency Avana | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Saloni Chawan |  | Lost | Design | Design Finalization | 849870 | 114904 | 1103973 | 0 | 0 | 110 | 65 | 0 | 140057 | 284559 | 310350 |  |  | 2026-01-09 | 2026-01-09 12:10 | 2026-01-13 | 2026-01-13 16:37 | 2026-01-19 | 2026-01-13 16:39 | 2026-06-11 |  | 2026-06-14 |  | 2026-06-17 |  | 2026-01-13 | 2026-01-14 11:45 | 2026-01-14 | 2026-01-16 15:04 | 2026-01-16 | 2026-01-21 13:37 | 2026-01-23 | 2026-01-23 19:38 | 2026-06-17 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-24 |  | 2026-06-25 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-05 |  | 2026-07-05 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-07-05 |  | 2026-02-08 | 2026-02-18 18:14 | Site is RTMI | 2026-01-08 | 2026-01-08 21:04 | 935571 | 168402 | 0 | 0 | 0 | 0 | 916935.1075 | 154810 | 2026-06-02 18:44:36 +0530 | Anamika Dolai | Client is not responding, asked for refund . | 2026-04-30 10:15:36 +0530 | Anil Jagtap | The customer wants a refund and has started the work with another vendor | 2026-03-24 15:20:10 +0530 | Hitesh Rawal | Some Image was uploaded
17971 | Sub Project |  | Manish Katole | Hiranandani | MUM - Thane |  |  | Divya Rahangdale | Rushika More |  |  | suraj kumar |  | Murali S |  |  | Completed | Complete | Completed | 6332 | 6333 | 0 | 0 | 6332 | 48 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-10 | 2026-02-10 | 2026-01-10 | 2026-02-10 | 2026-01-16 | 2026-02-10 | 2026-02-05 | 2026-02-10 | 2026-02-08 | 2026-02-10 | 2026-02-11 | 2026-02-10 | 2026-01-16 | 2026-02-10 | 2026-01-17 | 2026-01-25 18:30 | 2026-01-25 | 2026-02-10 | 2026-01-26 | 2026-02-10 | 2026-02-11 | 2026-01-25 18:30 | 2026-01-28 | 2026-02-10 | 2026-01-28 | 2026-02-10 | 2026-02-01 | 2026-02-10 | 2026-02-02 | 2026-02-10 |  |  | 2026-02-08 | 2026-02-11 14:17 | 2026-02-12 | 2026-02-11 14:18 | 2026-02-14 | 2026-03-09 14:14 | 2026-02-12 | 2026-02-10 |  |  |  |  | 2026-03-10 18:42 | 2026-03-15 | 2026-03-16 15:03 | 2026-03-18 | 2026-03-16 16:49 | 2026-03-23 | 2026-03-11 17:53 | 2026-03-16 | 2026-03-23 15:39 | 2026-03-23 | 2026-03-23 19:28 | 2026-04-25 | 2026-04-24 11:23 |  |  | 2026-05-04 | 2026-05-09 23:05 | 2026-05-06 | 2026-05-09 23:06 | 2026-05-08 | 2026-05-09 23:50 |  |  |  |  | 2026-03-09 | 2026-03-10 18:41 | 2026-01-27 | 2026-02-10 | Unknown | 2026-01-09 | 2026-01-25 18:30 | 0 | 0 | 0 | 0 | 43301 | 7794 | 43301 | 7794
17972 | Turnkey | Dec'25 | Swathi Harish Cn | null | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 950012 | 9999 | 0 | 0 | 0 | 112 | 0 | 85002 | 190002 | 297080 | 367928 |  |  | 2026-01-09 | 2026-01-23 18:58 | 2026-01-28 | 2026-01-28 17:04 | 2026-01-11 | 2026-03-25 19:49 | 2026-04-06 |  | 2026-04-09 |  | 2026-04-12 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-04-30 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-30 |  | 2026-03-28 |  | Unknown | 2026-01-08 | 2026-01-09 11:37 | 0 | 0 | 0 | 0 | 0 | 0 | 805094 | 144917 | 2026-01-13 14:57:48 +0530 | Priyanka Gs | Ground FloorÂ Family of 5Â Home theatre /LivingÂ Minimal storage for electronics Sofa cum bed,Â Need a Wardrobe spaceÂ Existing Furniture (Placement) Glass lift - All the 4 sides ,Â Highlight the wall Minimal kitchen Small sink , Hob on NW sideÂ GBRÂ Window seater Wardrobe +Loft +TV unitÂ Existing queen size cotÂ Vanity units , Shower partitions required for all the bathrooms. First FloorÂ Plan for existing wall paintingsÂ Living - TV unit, Planning for swingÂ Dining - Crockery unitÂ (Grey seater ) (Dark brown , dark blue , Greys - Color of the existing furniture) Pooja - Few drawersÂ (Exterior to be designed) Kitchen - Island requiredÂ Fridge - 750mmÂ Built in Appliance unitÂ Undermount RO Provision required for electrical appliances Dishwasher space next to the sinkÂ Display unitÂ and place for loungeÂ Parents Bedroom. Wardrobe + Loft +TV unitÂ Queen size cot , side tablesÂ Window seater Second floorÂ Existing - BedÂ toy storage - Glass tall unitsÂ WardrobeÂ MBRÂ Workspace for 2Â | 2026-01-09 11:59:38 +0530 | Janvi Nagdeo | Customer Budget:30-40L Inclusive of everything Loose furniture, modulars , VRMÂ Â Living/ dining room inclusions:TV Unit ,wall decor concept, ,dining area crockery ,shoe rack,Pooja mandirÂ Bedroom inclusions:wardrobe ,dresser ,workstation Kitchen inclusions:full kitchen with lofts, utilityÂ Service scope :Â False ceiling, painting, Electricity etc. Timeline related commitment, if any:property is under constructionÂ Â Any Vastu preference or specific donts : Vastu orientedÂ Â Other commitments made to customer:Cx is design centricÂ
17973 | Sub Project |  | Mayank Chandra Srivastava srivastava | Godrej Urban Park | MUM - GOR |  | Neha Yadav | Manzoor Shaikh | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Active | Handover | Project Closure Pending | 51916 | 51915 | 0 | 0 | 51916 | 106 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-10 | 2026-01-24 14:15 | 2026-01-10 | 2026-01-24 14:18 | 2026-01-26 | 2026-01-24 14:18 | 2026-01-26 | 2026-01-24 14:20 | 2026-01-25 | 2026-01-24 14:21 | 2026-01-25 | 2026-01-24 14:22 | 2026-01-24 | 2026-01-24 14:19 | 2026-01-25 | 2026-01-24 14:19 | 2026-01-24 | 2026-01-24 14:19 | 2026-01-25 | 2026-01-24 14:19 | 2026-01-24 | 2026-01-24 14:24 | 2026-01-27 | 2026-01-24 14:25 | 2026-01-24 | 2026-01-24 14:25 | 2026-01-25 | 2026-01-24 14:26 | 2026-02-11 | 2026-01-24 14:12 |  |  | 2026-02-21 | 2026-02-18 16:21 | 2026-02-19 | 2026-02-18 16:22 | 2026-02-21 | 2026-02-18 16:23 | 2026-02-04 | 2026-02-04 18:08 |  |  |  |  | 2026-02-19 18:40 | 2026-02-21 | 2026-02-20 19:47 | 2026-02-23 | 2026-02-21 14:31 | 2026-02-22 | 2026-02-25 10:35 | 2026-02-21 | 2026-02-25 15:57 | 2026-02-25 | 2026-03-06 16:31 | 2026-03-23 | 2026-03-31 20:25 |  |  | 2026-04-02 | 2026-03-31 21:51 | 2026-04-02 | 2026-03-31 21:55 | 2026-03-31 | 2026-03-31 21:59 |  |  |  |  | 2026-02-19 | 2026-02-19 18:39 | 2026-01-25 | 2026-01-24 14:20 | Unknown | 2026-01-09 | 2026-01-24 14:14 | 0 | 0 | 0 | 0 | 43997 | 7919 | 43997 | 7919 | 2026-05-12 00:24:04 +0530 | Savita Parab | Execution: shutter snag done need to align team for molding paint | 2026-04-01 18:52:47 +0530 | Savita Parab | Execution: no pending work after 15 days will close this project | 2026-03-22 18:37:01 +0530 | Savita Parab | Execution: Paneling done Awaiting for mirror and laminate delivery with installation
17974 | Turnkey | Dec'25 | Ruchi | aims | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  |  | Akash Jadhav | Sandeep Tiwari | Murali S | Avi Thakkar | Vinay Surve | Active | Installation | Execution | 807054 | 807054 | 999662 | 1197865 | 807054 | 41 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-09 | 2026-01-23 11:43 | 2026-01-23 | 2026-01-23 16:10 | 2026-01-23 | 2026-01-23 16:12 | 2026-02-26 | 2026-02-26 14:56 | 2026-02-26 | 2026-02-26 14:59 | 2026-02-26 | 2026-02-26 19:45 | 2026-01-23 | 2026-01-23 17:21 | 2026-01-24 | 2026-01-24 12:22 | 2026-01-24 | 2026-01-30 12:48 | 2026-02-03 | 2026-02-03 16:42 | 2026-02-26 | 2026-02-26 20:43 | 2026-03-06 | 2026-03-12 14:10 | 2026-03-06 | 2026-03-12 14:05 | 2026-04-18 | 2026-04-15 15:58 | 2026-04-16 | 2026-04-15 16:08 |  |  | 2026-04-30 | 2026-05-02 19:10 | 2026-05-03 | 2026-05-03 16:31 | 2026-05-06 | 2026-05-03 16:32 | 2026-05-08 | 2026-05-01 17:30 |  |  |  |  | 2026-05-05 14:25 | 2026-05-16 | 2026-05-15 19:26 | 2026-05-27 | 2026-05-25 21:41 | 2026-05-26 | 2026-05-31 11:57 | 2026-05-25 | 2026-06-02 21:54 | 2026-06-02 | 2026-06-04 17:35 | 2026-06-06 | 2026-06-09 13:43 |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-05-03 | 2026-05-05 08:57 | 2026-02-04 | 2026-02-26 14:34 | Site is RTMI | 2026-01-08 | 2026-01-23 11:37 | 1016474.8265 | 175372 | 1235712.9435 | 213233 | 890245.0296 | 153618 | 890245.0296 | 153618 | 2026-06-02 22:30:12 +0530 | Akash Jadhav | Procurement: floor covering work done false ceiling work done 1st coat of paint done modular will deliver at site 5th june | 2026-05-16 15:53:13 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-28 13:41:55 +0530 | Manzoor Shaikh | Some Image was uploaded
17975 | Sub Project |  | Sujith Surendranath | Nikoo Homes | BNG - HRBR |  | Priyanka Gs | Parasa Sri |  |  |  | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-10 | 2026-01-09 16:08 | 2026-01-10 | 2026-01-09 16:08 | 2026-01-11 | 2026-01-09 16:09 | 2026-01-11 | 2026-01-09 16:11 | 2026-01-10 | 2026-01-09 16:12 | 2026-01-10 | 2026-01-09 16:14 | 2026-01-09 | 2026-01-09 16:09 | 2026-01-10 | 2026-01-09 16:09 | 2026-01-09 | 2026-01-09 16:09 | 2026-01-10 | 2026-01-09 16:09 | 2026-01-09 | 2026-01-09 16:15 | 2026-01-12 | 2026-01-09 16:15 | 2026-01-09 | 2026-01-09 16:16 | 2026-01-10 | 2026-01-09 16:17 | 2026-01-10 | 2026-01-09 16:17 |  |  | 2026-01-12 | 2026-01-09 16:40 | 2026-01-10 | 2026-01-13 15:53 | 2026-01-16 | 2026-01-14 14:45 | 2026-01-14 | 2026-01-15 11:54 |  |  |  |  | 2026-01-15 12:13 | 2026-01-16 | 2026-01-16 10:25 | 2026-01-18 | 2026-01-16 11:18 | 2026-01-17 | 2026-01-20 11:25 | 2026-01-16 | 2026-01-20 11:47 | 2026-01-19 | 2026-01-20 12:52 | 2026-01-21 | 2026-01-20 13:43 |  |  | 2026-01-30 | 2026-01-20 13:53 | 2026-02-01 | 2026-01-20 13:54 | 2026-02-02 | 2026-01-20 14:44 |  |  |  |  | 2026-01-15 | 2026-01-15 12:12 | 2026-01-10 | 2026-01-09 16:09 | Unknown | 2026-01-09 | 2026-01-09 16:08 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0
17976 | Turnkey | Dec'25 | Rajesh Doshi | Swapnalok | MUM - GOR | Yes | Mandar Ambre | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Shashwat Joshi | Rizwan Mistry | Murali S | Rashmita Das | Vinay Surve | Active | Production | 100% Payment | 4681339 | 2902144 | 4894536 | 4923781 | 4681339 | 11 | 11 | 0 | 0 | 0 | 1779195 |  |  | 2026-01-10 | 2026-01-17 11:27 | 2026-01-17 | 2026-01-17 13:22 | 2026-01-17 | 2026-01-17 13:35 | 2026-03-08 | 2026-03-08 13:32 | 2026-03-30 | 2026-03-30 11:45 | 2026-04-19 | 2026-04-19 13:23 | 2026-01-17 | 2026-01-22 17:02 | 2026-01-18 | 2026-01-26 12:42 | 2026-01-26 | 2026-01-29 14:59 | 2026-02-03 | 2026-02-03 16:48 | 2026-04-19 | 2026-04-19 15:36 | 2026-04-22 | 2026-04-19 19:08 | 2026-03-18 | 2026-03-17 16:09 | 2026-04-25 | 2026-04-26 19:07 | 2026-04-27 | 2026-04-26 19:07 |  |  | 2026-05-15 | 2026-05-26 17:38 | 2026-05-26 | 2026-05-26 19:01 | 2026-05-27 | 2026-05-26 19:09 | 2026-05-26 | 2026-06-01 10:56 |  |  |  |  | 2026-06-03 15:13 | 2026-06-19 | 2026-06-18 19:56 | 2026-06-26 | 2026-06-23 19:28 | 2026-06-24 |  | 2026-07-05 |  | 2026-07-02 |  | 2026-07-04 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-05-26 | 2026-06-01 12:42 | 2026-02-04 | 2026-02-19 12:30 | Site is RTMI | 2026-01-09 | 2026-01-10 11:55 | 4147912 | 746624 | 5130004.279 | 838034 | 4900487.1933 | 801051 | 4900487.1933 | 801051 | 2026-06-23 14:28:46 +0530 | Avinash Jaiswal | Some Image was uploaded | 2026-06-13 19:37:49 +0530 | Nishant Jadhav | Execution: Ceiling Framing work done 13th June 2026 Pop punning & electric work will be started on 15th June 2026 | 2026-06-07 13:57:21 +0530 | Nishant Jadhav | Execution: KOM Done at site on 3rd June 2026 Existing ceiling slab cleaning work started will be complete on 8th June 2026
17977 | Turnkey | Dec'25 | SRIDHARAN | L&T Seawoods | MUM - Thane | Yes | Mayuri Patil | [7 empty] | Saloni Chawan |  | Active | Prospect | CDP Due | 1251862 | 9999 | 0 | 0 | 0 | 186 | 0 | 115187 | 250372 | 406482 | 469821.6 |  |  | 2026-01-10 | 2026-01-09 17:14 | 2026-01-10 | 2026-01-10 18:56 | 2026-01-12 |  | 2026-01-24 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-01-12 |  | 2026-01-13 |  | 2026-01-13 |  | 2026-01-14 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-06 |  | 2026-02-07 |  |  |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 | [6 empty] | 2026-02-23 |  | 2026-03-04 |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-07 |  |  |  | 2026-03-29 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-02-17 |  | 2026-01-15 |  | Unknown | 2026-01-09 | 2026-01-09 17:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1060900 | 190962 | 2026-01-10 18:44:39 +0530 | Mayuri Patil | DCM: Minutes of Meeting (MoM)Project: 2 BHK Amber (West Square) Client: Shridharan Location: Amber, West Square Carpet Area: Approx. 572 sq. ft. Entrance Orientation: As discussed on site (refer sketch) Date & Time: Sunday, 2nd Half, 3:00 PM AttendeesClient: ShridharanDesign Team Project Brief2 BHK L&T apartmentSingle person stayingOccasional guests (approx. 34 people)Usage primarily for work logistics and comfortable living Living & Dining Area RequirementsMandir unit combined with TV unitMandir unit width to be approx. 3 ftSofa: 3-seaterTV size: 55" to 60"Dining: 4-seater dining tableOverall layout to ensure comfortable circulation for guests Kitchen RequirementsFull-height modular kitchenStorage optimization to be prioritized Bedroom 2 RequirementsSliding wardrobe with loftLaptop/study tableQueen-size bed without storageTV unit with ledgeSide table and mirror Master Bedroom RequirementsWardrobe with dresserStudy unit / TV unitQueen or King-size bed with hydraulic storageSide tables (2 nos.) with mirrorVanity units (2 nos.) Scope of Work IncludedFalse ceilingPaintingElectrical works Scope ExclusionsLoose furniture (to be finalized separately)
17978 | Turnkey | Dec'25 | Uresh Jhaveri | Dns Anuutham | MUM - Thane | Yes | Pooja Nakul Sharma | [9 empty] | Active | Prospect | CDP Due | 3581423 | 9999 | 0 | 0 | 0 | 183 | 0 | 348143 | 716285 | 1173534 | 1333462 |  |  | 2026-01-10 | 2026-01-09 19:11 | 2026-01-13 | 2026-01-13 17:21 | 2026-01-16 |  | 2026-01-28 |  | 2026-01-31 |  | 2026-02-03 |  | 2026-01-16 |  | 2026-01-17 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-02-03 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-10 |  | 2026-02-11 |  |  |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-21 |  | 2026-02-21 | [6 empty] | 2026-02-27 |  | 2026-03-08 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-11 |  |  |  | 2026-04-02 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-02-21 |  | 2026-01-19 |  | Site is RTMI | 2026-01-09 | 2026-01-09 19:09 | 0 | 0 | 0 | 0 | 0 | 0 | 3035104 | 546318
17979 | Turnkey | Dec'25 | nilesh dange | vraj green valley | MUM - Thane | Yes | Maasoumeh Raza | [9 empty] | Active | Prospect | DCM Due | 1330736 | 9999 | 0 | 0 | 0 | 187 | 0 | 123075 | 266147 | 421305 | 510210.4 |  |  | 2026-01-10 | 2026-01-10 10:51 | 2026-01-23 |  | 2026-01-18 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-02-16 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-23 |  | 2026-02-24 |  |  |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-06 |  | 2026-03-06 | [6 empty] | 2026-03-12 |  | 2026-03-21 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-24 |  |  |  | 2026-04-15 |  | 2026-04-17 |  | 2026-04-18 | [5 empty] | 2026-03-06 |  | 2026-02-01 |  | Unknown | 2026-01-09 | 2026-01-10 10:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1127742 | 202993
17980 | Turnkey | Dec'25 | Yashashrri | 3bhk Villa | BNG - HSR | No Estimate | Nayan Reddy |  | Kowshik | [5 empty] | Fuzail Girach |  | Active | Prospect | CDP Due | 0 | 9999 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-10 | 2026-01-10 11:28 | 2026-02-12 | 2026-02-11 16:52 | 2026-01-22 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-14 |  | 2026-03-15 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-25 |  | 2026-03-25 | [6 empty] | 2026-03-31 |  | 2026-04-09 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-12 |  |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | 2026-03-25 |  | 2026-02-20 |  | Unknown | 2026-01-09 | 2026-01-10 10:49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-02-05 11:00:40 +0530 | Fuzail Girach | RGM FOR YASHASHRI Property name: Independent Villa Budget: 18 L Max Unit: 3 BHK Ground Floor: Entrance, Foyer area, shoes rack (20 pair) With seater Entrance: Tv unit (55 inch), Floating unit with storage and wall panel Patio Area: Need swing, with matching foyer area design Living Area: Wall decor, Beading, wallpaper Pooja Area: Client scope 1st Floor Sons room study Unit, L shaped with cabinet for storage, wall ledges, wall decor with gaming theme, window bay sitting area, walking closet, sliding wardrobe with loft Dining Area: wall decor, mirror work Kitchen: Full kitchen with storage Island kitchen, pantry area with lost & wall unit Utility: Open storage compartment 2nd Floor Daughter Bedroom/ Guest Swing wardrobe, window sitting area with storage Master Bedroom Walking closet, Glass Sutter wardrobe, Headboard with wall decor, Dresser, side table Washroom vanity unit Home Office L corner Workstation with cabinet storage below open panel storage in wall unit | 2026-02-05 10:55:37 +0530 | Fuzail Girach | Others: RGM FOR YASHASHRI Property name: Independent Villa Budget: 18 L Max Unit: 3 BHK Ground Floor : Inertance, Foyer area, shoes rack (30 pair) With seater enterance : Tv unit (55 inch) , Floating unit , Patio Area : Need swing Living Area : Wall decor , Bidding , Pooja Area : Client scope 1st Floor Sons room study Unit , L shaped with cabinet for storage , wall ledges , window bay sitting area , walking closet , sliding wardbode with loft Dining Area : wall decor , mirror work Kitchen :Full kitchen with storage Island kitchen, pantry area with lost & wall unit Utility : Open storage compartment 2nd Floor Daughter Bedroom/ Guest Swing wardbore , window sitting area , Master Bedroom Walking closet , Glass Sutter wardrobe , Headboard with wall decor , Dresser , side table , Home Office L corner Work station with cabinet storage below open panel storage in wall unit
17981 | Turnkey | Dec'25 | Neelam Takwani | Lodha AMara | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1385039 | 9999 | 0 | 0 | 0 | 186 | 0 | 128505 | 277008 | 475234 | 494293.2 |  |  | 2026-01-11 | 2026-01-10 12:43 | 2026-01-11 |  | 2026-02-20 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-03-10 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-28 |  | 2026-03-28 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-28 |  | 2026-02-23 |  | Unknown | 2026-01-10 | 2026-01-10 12:42 | 0 | 0 | 0 | 0 | 0 | 0 | 1173761 | 211277 | 2026-01-10 20:40:19 +0530 | Karuna Shinde | DCM: Client DetailsName: Ketanj Takvani Profession: Businessman Property DetailsProject Name: Lodha Amara Building: 25, room number:- 4001, 2 BHK Carpet Area: 722 sq. ft. Possession: February 2026 Rental Property Scope of WorkPaintingModular furnitureDesign as per Vastu complianceEntrance & Living AreaSafety door with integrated shoe rack3-seater sofasmall TV unitPooja unitKitchenBase unitsWall unitsLoft on any one sideChimney provisionSingle-door refrigerator provisionRO systemMicrowave unitBedroom 1Wardrobe with loftBedMaster BedroomWardrobe without loftBedside tableBathroomsVanity unit in common (living) bathroomDesign ThemeTo be finalized (Currently inclined towards simple, functional, budget-optimized design) Budget12,00,000
17982 | Turnkey | Dec'25 | Santoshwer | Obel Shanti | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Kushal S |  | Active | Design | Design Finalization | 1454260 | 436278 | 1879630 | 0 | 0 | 151 | 0 | 0 | 0 | 447100 | 570882 |  |  | 2026-01-11 | 2026-01-10 12:59 | 2026-01-10 | 2026-01-21 10:54 | 2026-01-23 | 2026-01-21 17:58 | 2026-05-02 | 2026-05-02 12:34 | 2026-07-02 |  | 2026-07-05 |  | 2026-01-21 | 2026-01-31 12:08 | 2026-01-22 | 2026-02-13 18:59 | 2026-02-13 | 2026-02-14 10:54 | 2026-02-15 | 2026-02-15 19:28 | 2026-07-05 |  | 2026-07-08 |  | 2026-07-08 | 2026-06-04 | 2026-08-24 |  | 2026-08-25 |  |  |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-04 |  | 2026-09-04 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-09-04 |  | 2026-03-06 | 2026-05-02 12:32 | Site is RTMI | 2026-01-10 | 2026-01-10 12:52 | 1592907 | 286723 | 0 | 0 | 0 | 0 | 1551330.66 | 256158 | 2026-02-14 10:54:15 +0530 | Bency Chacko | Possession - March end Design meetings - Feb end IDM - 22nd Feb 2026 Scheme - 10,20,30,40 Checklist cleared, Timelines cleared, Offers cleared, Quote cleared. No on-site work is planned No vendor work is planned B2C - Self-funding KYC cleared | 2026-02-13 12:41:24 +0530 | Kushal S | Some Image was uploaded | 2026-02-04 20:31:03 +0530 | Kushal S | Some Image was uploaded
17983 | Turnkey | Dec'25 | Avinash Paul | prestige Green gables | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1850601 | 9999 | 1850601 | 0 | 0 | 169 | 0 | 175061 | 370120 | 576014 | 719407.2 |  |  | 2026-01-11 | 2026-01-10 14:59 | 2026-01-11 | 2026-01-17 16:45 | 2026-01-23 | 2026-01-27 19:30 | 2026-02-08 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-21 |  | 2026-02-22 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-01-30 |  | Unknown | 2026-01-10 | 2026-01-10 14:46 | 1568306 | 282295 | 0 | 0 | 0 | 0 | 1568306 | 282295 | 2026-01-11 12:59:50 +0530 | Adarsh K | DCM: Art Deco with Tropical wallpapers Green - Common, Blue & Red For Rooms False ceiling - Minimal Living Area wise - Foyer - Shoe storage - 25 pairs Ledges - Key holders - Mirror Dining - 4 Seater, Sleeker Crockery Unit TV unit - Simple with Pooja Unit - Cross Sofa - L shape sofa - 4 seater, 1 Chair Kitchen - As per layout, No Loft - Duct covering, Storage heavy, Sleeker RO. No Tall Unit Utility - Washing Machine, Dishwasher MBR - As Per Layout, - Wardrobe, Study Corner, DresserÂ in place of TV. Queen Size Bedroom 2 - Queen Size Bed in centre, Wardrobe as per layout and additional storage near window next to bed - Wall paper behind bed. TV space - Study Unit Bedroom 3 - Single Bed - Pushed towards Window, Two door wardrobe,Â Partition at the window, Door side for the Kids - Play, study and storage - Books and toys. All Study Units to have Closed horizontal storage on wall above desk,Â with Fluted glass shutters. Bathroom - Generic storage. Balcony - Ledges for planters. Next Meeting - 18th Sunday 3pm. RGM Budget - Upto 15 Lakhs for Modular fixed furnitures. | 2026-01-10 14:47:36 +0530 | Ramesh Nayak | ::::::::---------------RGM Notes For DCM Meeting---------------:::::::: 1. Budget - 12-15 2. Property Name & Possession -Â 3. Carpet Area - 950 SQF Carpet Area 4. BHK -3 BHKÂ 5. Family Size - 4 Name - Avinash Paul Spouse - Anusha A Child 1 - Aaron Paul Child 2 - Aadhya Paul 6. Shoe Rake/Foyer - Foyer Req 4. Living/Dining Room Inclusions - TV Unit, Crockery Unit,Â 5. Bed Room Inclusions - 3 Wardrobe, 2 Study Unit, 1 in Master Bedroom Dresser Unit, Play Station in Kids Room 6. Kitchen Inclusions -Â : Tall unit - Yes : Base unit - Yes : Wall unit -Â : Loft - Yes : Granite/Quartz - Yes 7. Service Scope - :False Ceiling - Living Area :Painting - Walpaper :Electricity - Yes 8. Utility/Janitor Unit -Â 9. Timeline - 90 Working Days
17984 | Turnkey | Dec'25 | tushare more | Natasha avana | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | DCM Due | 1467094 | 9999 | 0 | 0 | 0 | 186 | 0 | 136710 | 293419 | 519171 | 507794.4 |  |  | 2026-01-11 | 2026-01-14 16:52 | 2026-01-11 |  | 2026-01-31 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 |  | 2026-02-18 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-25 |  | 2026-02-26 |  |  |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-03-08 | [6 empty] | 2026-03-14 |  | 2026-03-23 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-26 |  |  |  | 2026-04-17 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-03-08 |  | 2026-02-03 |  | Unknown | 2026-01-10 | 2026-01-14 16:51 | 0 | 0 | 0 | 0 | 0 | 0 | 1243300 | 223794 | 2026-02-14 13:19:18 +0530 | Ishan Patle | Possession in Nov already discussion done the cx he will plan nearby possession | 2026-02-14 13:17:16 +0530 | Ishan Patle | silver coin pending | 2026-01-15 14:57:17 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
17985 | Turnkey | Dec'25 | Mohit Bansal | Rohan Ekanta | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 1708442 | 9999 | 0 | 0 | 0 | 112 | 0 | 160845 | 341688 | 553018 | 642891.6 |  |  | 2026-01-10 | 2026-01-12 18:15 | 2026-01-12 | 2026-01-21 21:56 | 2026-01-23 | 2026-03-25 17:35 | 2026-04-06 |  | 2026-04-09 |  | 2026-04-12 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-04-30 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-30 |  | 2026-03-28 |  | Unknown | 2026-01-09 | 2026-01-10 13:37 | 0 | 0 | 0 | 0 | 0 | 0 | 1447832 | 260609 | 2026-01-22 09:31:39 +0530 | Shibin Lal | Some Image was uploaded
17986 | Turnkey | Dec'25 | Kokila Venkatesh | jeevan octave | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Deekshith P | Jairam Joshi | Murali S | Raghavendra S | Vishwa Hiremath | Completed | Complete | Completed | 853782 | 853782 | 1006966 | 860552 | 849188 | 12 | 7 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-10 14:58 | 2026-01-10 | 2026-01-25 14:38 | 2026-01-28 | 2026-01-28 21:07 | 2026-03-28 | 2026-03-19 12:19 | 2026-03-21 | 2026-03-21 11:16 |  |  | 2026-01-28 | 2026-01-29 14:27 | 2026-01-29 | 2026-01-31 11:51 | 2026-01-31 | 2026-02-03 09:59 | 2026-02-06 | 2026-02-06 16:56 | 2026-03-26 | 2026-03-27 10:39 | 2026-04-06 | 2026-03-28 15:49 | 2026-04-06 | 2026-03-27 17:35 | 2026-04-08 | 2026-04-18 10:54 | 2026-04-19 | 2026-04-19 01:05 |  |  | 2026-04-22 | 2026-04-22 17:35 | 2026-04-22 | 2026-04-22 20:13 | 2026-04-25 | 2026-04-22 21:56 | 2026-04-22 | 2026-04-24 18:05 |  |  |  |  | 2026-04-28 19:33 | 2026-05-07 | 2026-05-06 22:18 | 2026-05-28 | 2026-05-21 20:46 | 2026-05-11 | 2026-05-01 17:23 | 2026-05-21 | 2026-05-23 14:12 | 2026-05-23 | 2026-05-23 17:46 | 2026-05-26 | 2026-05-28 11:15 |  |  | 2026-06-16 | 2026-06-17 10:32 | 2026-06-11 | 2026-06-17 11:27 | 2026-06-17 | 2026-06-17 16:49 |  |  |  |  | 2026-04-24 | 2026-04-28 19:32 | 2026-02-07 | 2026-03-19 11:55 | Site is RTMI | 2026-01-10 | 2026-01-10 14:14 | 1168811.09 | 192503 | 1030553.614 | 170168 | 1020056.907 | 168435 | 1027490.107 | 169136 | 2026-06-22 17:50:08 +0530 | Jairam Joshi | Project Closure Pending: Observation points Closure -2nd July | 2026-06-16 16:55:14 +0530 | Jairam Joshi | Execution: QC - 16th HO-17th | 2026-06-04 15:46:20 +0530 | Jairam Joshi | Some Image was uploaded
17987 | Turnkey | Dec'25 | Harshad Agarwal | Suraksha Springs | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [7 empty] | Active | Prospect | DCM Due | 1563697 | 9999 | 0 | 0 | 0 | 186 | 0 | 146371 | 312739 | 472495 | 622093.2 |  |  | 2026-01-11 | 2026-01-10 14:21 | 2026-01-11 |  | 2026-01-18 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-11 |  | 2026-02-12 |  |  |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-22 |  | 2026-02-22 | [6 empty] | 2026-02-28 |  | 2026-03-09 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-12 |  |  |  | 2026-04-03 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-02-22 |  | 2026-01-20 |  | Unknown | 2026-01-10 | 2026-01-10 14:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1325167 | 238530 | 2026-01-17 16:08:27 +0530 | Mahathi Nama | DCM: Changes in plans: -sliding door in btw kitchen & utility @centre -M.bedroom door to be shifted back. LIVING ROOM: - Shoe rack with sitting outside main door(15-20pairs). - tv unit -4 seater dinning -3+1+1 sofa - crockery unit on bed2 wall - washbasin in NE wall - pooja unit on SE corner wall of living. - KITCHEN: - L shaped - tall unit - loft - single bowl sink - under counter ro unit - granite CX scope UTILITY: - single bowl sink with drainer - W.M(TOP LOADED), D.W - Plumbing ppt on SE wall TOILETS: - All toilet vanity KIDS WALL(BEDROOM1): - Window side wall design - Q size bed - openable wardrobe with loft - desktop study unit - dressing(mirror) M. BEDROOM: - tv unit - openable wardrobe with loft - K size bed(hydraulic bed) - Adjustable study unit(only counter is needed) - dressing BEDROOM 2: - openable wardrobe with loft - tv unit - K size bed - dressing(mirror) | 2026-01-11 11:29:00 +0530 | Sharone Singh | Budget - 10-15 Lacs 1.Living, 2.Dining & KitchenÂ 3.All 3 BedroomsÂ 4.Foyer 5.BalconyÂ Falls Ceiling 6.PaintingÂ 7.Electricty point shifting 8Â Vastu - Yes 9.Design Centric
17988 | Turnkey | Dec'25 | POOJA RAMESH POOJARI | Flamingo | MUM - Thane | Yes | Mayuri Patil | [7 empty] | Aryan Singh |  | Active | Prospect | CDP Due | 1001825 | 9999 | 0 | 0 | 0 | 175 | 0 | 90184 | 200365 | 356811 | 344466.4 |  |  | 2026-01-11 | 2026-01-14 11:38 | 2026-01-21 | 2026-01-21 11:56 | 2026-01-24 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-21 |  | 2026-02-22 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-01-30 |  | Unknown | 2026-01-10 | 2026-01-11 11:56 | 0 | 0 | 0 | 0 | 0 | 0 | 849004 | 152820 | 2026-01-21 11:48:09 +0530 | Mayuri Patil | Minutes of Meeting (MoM)Client Name: Pooja Poojary Profession: CA Budget: Approx. 8 Lakhs Family Details: 4 members (Brother stays in Gulf) Current Residence: Bhiwandi Property Status: Single ¦ Rented ¦ Parents house Pets: Cats Balcony Orientation: West 1. Entry AreaSafety door with shoe rackEntry panelling 2. Living RoomTV unitL-shaped sofa (lounger type, dark shade preferred)Coffee tableBookshelfMosquito net provisionBalcony to include cats playing area 3. KitchenBase units providedEntire kitchen to be given newWall units and loft to be included 4. BedroomStudy unitQueen-size bed with storage (drawers)Side table and dresserWardrobe with internal lightingAC panellingFalse ceiling with electrical workPainting 5. ToiletsVanity units 2 nos. | 2026-01-14 11:52:13 +0530 | Rishabh Borikar | Some Image was uploaded
17989 | Turnkey | Dec'25 | Diksha Gandhi | Auram q Park | MUM - Thane | Yes | Rutuja Kotwal | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | CDP Due | 1203044 | 9999 | 0 | 0 | 0 | 183 | 0 | 110305 | 240609 | 374736 | 467395.2 |  |  | 2026-01-11 | 2026-01-10 18:33 | 2026-01-13 | 2026-01-13 18:52 | 2026-01-14 |  | 2026-01-31 |  | 2026-02-03 |  | 2026-02-06 |  | 2026-01-19 |  | 2026-01-20 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-13 |  | 2026-02-14 |  |  |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-24 |  | 2026-02-24 | [6 empty] | 2026-03-02 |  | 2026-03-11 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-14 |  |  |  | 2026-04-05 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-02-24 |  | 2026-01-22 |  | Unknown | 2026-01-10 | 2026-01-10 18:32 | 0 | 0 | 0 | 0 | 0 | 0 | 1019529 | 183515 | 2026-01-13 18:50:35 +0530 | Rutuja Kotwal | DCM: Mrs. Diksha Gandhi.Â 2 BHK.Â Â Area- 59.72sq.mtr.Â Possession In handÂ ( inÂ 10Â daysÂ )Â Â Move in 2Â peopleÂ husband and wife.Â Â Profession Entrepreneur- SchoolÂ Â No design as perÂ vastu.Â Â Â Budget Â uptoÂ 10 lakhs.Â Living roomÂ Shoe rackÂ with 2Â drawersÂ Â 10 shoes., sofa,Â TV unitÂ wall mounted,Â dining table low seatedÂ Â Kitchen-Â changing ofÂ laminatesÂ Bedroom 1Â Â NO BEDÂ Â Wardrobe with Lofts, Bay window, folding table.Â Â MBR-Â BedÂ low seated,Â Wardrobe with mirror,Â Â CDP- 14thÂ jan.Â Â atÂ 11.30 am.Â Â Budget suggested 12-13 Lakhs.Â Â | 2026-01-10 18:34:16 +0530 | Nishtha Valawalkar | Some Image was uploaded
17990 | Turnkey | Dec'25 | santosh karangutkar | raymond realty | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar |  |  | Tanveer Patel | Aditya Vikram | Murali S |  | Prasad Bhivaji Hande | Active | Preproduction | Procurement | 1658625 | 1022804 | 1313571 | 1474741 | 1658625 | 6 | 33 | 0 | 0 | 0 | 635821 |  |  | 2026-01-11 | 2026-01-16 16:48 | 2026-01-16 | 2026-01-16 17:22 | 2026-01-20 | 2026-01-20 16:51 | 2026-06-02 | 2026-05-24 13:40 | 2026-05-31 | 2026-05-31 17:10 | 2026-06-07 | 2026-06-07 18:54 | 2026-01-20 | 2026-01-20 19:10 | 2026-01-21 | 2026-01-23 12:21 | 2026-01-23 | 2026-01-27 15:44 | 2026-02-27 | 2026-03-05 16:34 | 2026-06-07 | 2026-06-07 19:27 | 2026-06-10 | 2026-06-12 17:45 | 2026-06-10 | 2026-06-12 16:54 | 2026-06-19 | 2026-06-16 18:26 | 2026-06-17 | 2026-06-16 18:26 |  |  | 2026-06-23 | 2026-06-26 12:11 | 2026-06-26 | 2026-06-26 21:20 | 2026-06-29 | 2026-06-26 21:55 | 2026-06-26 | 2026-06-30 13:34 |  |  |  |  | 2026-07-09 18:28 | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-07-03 | 2026-07-09 18:27 | 2026-05-15 | 2026-05-24 13:36 | Site is RTMI | 2026-01-10 | 2026-01-16 16:47 | 1434288.8558 | 230883 | 1569917.6298 | 255469 | 1862863.7336 | 306019 | 1862863.7336 | 306019 | 2026-05-31 17:01:29 +0530 | Hemant Sonar | DDM2: Hi @115526080659520Â @168856656064532Â As discussed, please find the Minutes of Meeting (MoM) below for your reference. Minutes of Meeting (MoM): 1. Common washroom wall unit has been added.(as per site condition)Â 2. Bedroom 1 wallpaper has been finalised. 3. Master Bedroom (MBR) wallpaper has been finalised. 4. Kitchen wall unit to be executed with glass shutters. 5. Both wardrobes to be made sliding, as per site conditions. 6. In master bedroom locker provision required.Â 7. all the laminates finalised. | 2026-05-23 18:52:38 +0530 | kanishka mittal | DDM1: Hi @~K Santosh sir & @~Smita K. Mam, As discussed in todays meeting, please find the Minutes of Meeting (MOM) below: Living Room * Storage unit size increased for bag storage purpose (costing will vary accordingly). * * Kitchen: Wicker basket removed. * * Shoe unit removed. * * Vanity unit added. Bedroom 1 * Sofa-cum-bed planned. * Bed back wallpaper planned. * Side unit planned.for used clothesÂ * Open shelf provided above the study unit. * Study unit width increased (costing will vary accordingly). * study wall unit removed. Master Bedroom (MBR) * Drawer-type bed planned. * Ledge added above the study unit. * Bed back wallpaper planned. * Dresser removed. | 2026-04-15 18:13:16 +0530 | Anil Jagtap | cx will receive the possession by mid of may
17991 | Turnkey | Dec'25 | Amirish Dhamecha | Mahaveer Groups | MUM - GOR | Yes |  |  | Shantanu Parakh | [5 empty] | Manasi Patil |  | Active | Prospect | CDP Due | 1891533 | 9999 | 0 | 0 | 0 | 175 | 0 | 179154 | 378307 | 573555 | 750518.4 |  |  | 2026-01-11 | 2026-01-10 16:14 | 2026-01-21 | 2026-01-21 13:40 | 2026-01-26 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-20 |  | 2026-02-21 |  |  |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-03 |  | 2026-03-03 | [6 empty] | 2026-03-09 |  | 2026-03-18 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-21 |  |  |  | 2026-04-12 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-03-03 |  | 2026-01-29 |  | Unknown | 2026-01-10 | 2026-01-10 16:13 | 0 | 0 | 0 | 0 | 0 | 0 | 1602994 | 288539
17992 | Turnkey | Dec'25 | Anshul Agrawal | shapoorji Pallonji Parkwest | BNG - HSR | No Estimate | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-10 18:27 | 2026-01-15 |  | 2026-01-18 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 | [6 empty] | 2026-03-04 |  | 2026-03-13 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-16 |  |  |  | 2026-04-07 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-02-26 |  | 2026-01-24 |  | Unknown | 2026-01-10 | 2026-01-10 16:44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-01-14 13:20:18 +0530 | Varun Mandana | FM Preebooking Meeting Notes: Customer Budget: 35-40L (End 2 End)Living/ dining room inclusions: Shoerack,Tv Unit,Crockery,PujaBedroom inclusions:Wardrobes (Aristo),dresser, study, vanityKitchen inclusions:BU,WU,Loft,Utility, Janitor.Service scope :Â Wall Concepts, False Ceiling, Appliances, Lighting, Automation, counter tops.Timeline related commitment, if any: NoneAny Vastu preference or specific donts : YesOther commitments made to customer: NALooking for some high end designs. They are also discussing with Chattels Design and KariGhars as well. So our designs should match or be better than theirs. Very Design Centric.
17993 | Turnkey | Dec'25 | rojalin mishra | Prestige Meridian Park | BNG - HSR | Yes | Mahathi Nama | Akshay Ds | Kowshik | [7 empty] | Active | Prospect | CDP Due | 2580030 | 9999 | 0 | 0 | 0 | 173 | 0 | 248004 | 516006 | 778338 | 1027683.2 |  |  | 2026-01-11 | 2026-01-10 17:21 | 2026-01-23 | 2026-01-23 10:24 | 2026-01-25 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-19 |  | 2026-02-20 |  |  |  | 2026-02-26 |  | 2026-02-27 |  | 2026-03-02 |  | 2026-03-02 | [6 empty] | 2026-03-08 |  | 2026-03-17 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-20 |  |  |  | 2026-04-11 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-03-02 |  | 2026-01-28 |  | Unknown | 2026-01-10 | 2026-01-10 17:20 | 0 | 0 | 0 | 0 | 0 | 0 | 2186466 | 393563 | 2026-01-15 15:39:24 +0530 | Mahathi Nama | DCM: Budget - 10 lacs Parents &daughter (painting is hobby) Reading nook very minimal and clean house, painting art display corner family photo wall Travel souvenirs Wine corner Victorian part Kitchen: Pantry with accessories base &wall unit with minimal loft Foyer: Mirror with console Workspace -shoe rack with photo wall Dining - book storage with art wall Dining - 6-seater Living area TV wall: Base unit sofa wall: wall trims Bedroom 1: Swing wardrobe Dresser Ledge next to mirror Foldable study Bedroom 2 Wardrobe TV cum study Dressing mirror Bedroom 3 Wardrobe sofa cum bed library corner window paint corner work area Washroom bathroom base unit and wall units Might go up 13-15 | 2026-01-11 11:28:04 +0530 | Sharone Singh | Budget - 10-15 Lacs 1.Living, 2.Dining & KitchenÂ 3.All 3 BedroomsÂ 4.Foyer 5.BalconyÂ Falls Ceiling 6.PaintingÂ 7.Electricty point shifting 8Â Vastu - Yes 9.Design Centric
17994 | Turnkey | Dec'25 | sachin s mundaye | Bhavya Elites | MUM - GOR | No Estimate | Pratima Kajwe |  | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-10 17:22 | 2026-01-11 |  | 2026-01-17 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-11 |  | 2026-02-12 |  |  |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-22 |  | 2026-02-22 | [6 empty] | 2026-02-28 |  | 2026-03-09 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-12 |  |  |  | 2026-04-03 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-02-22 |  | 2026-01-20 |  | Unknown | 2026-01-10 | 2026-01-10 17:20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-01-10 17:23:22 +0530 | Sanskruti Yadav | Some Image was uploaded
17995 | Turnkey | Dec'25 | S Hiraan Sojitra | ray roswalt dahisar | MUM - GOR | Yes | Saif Shaikh |  | Shantanu Parakh | [7 empty] | Active | Prospect | CDP Due | 1947497 | 9999 | 0 | 0 | 0 | 181 | 0 | 184751 | 389499 | 637472 | 725775.6 |  |  | 2026-01-11 | 2026-01-14 18:45 | 2026-01-15 | 2026-01-15 08:53 | 2026-01-17 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 | [6 empty] | 2026-03-04 |  | 2026-03-13 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-16 |  |  |  | 2026-04-07 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-02-26 |  | 2026-01-24 |  | Unknown | 2026-01-10 | 2026-01-10 17:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1650421 | 297075
17996 | Turnkey | Dec'25 | Kajal Damania | Antariksh ace | MUM - GOR | Yes | Swapnali Shedekar |  | Shantanu Parakh | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 1020816 | 9999 | 1020816 | 0 | 0 | 176 | 0 | 92083 | 204163 | 325438 | 389133.6 |  |  | 2026-01-11 | 2026-01-18 14:04 | 2026-01-20 | 2026-01-20 11:49 | 2026-01-20 | 2026-01-20 12:16 | 2026-02-01 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-14 |  | 2026-02-15 |  |  |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-25 |  | 2026-02-25 | [6 empty] | 2026-03-03 |  | 2026-03-12 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-15 |  |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-02-25 |  | 2026-01-23 |  | Unknown | 2026-01-10 | 2026-01-10 17:57 | 1146651.307 | 178599 | 0 | 0 | 0 | 0 | 1146651.307 | 178599 | 2026-02-23 19:08:30 +0530 | Umang Shah | Some Image was uploaded
17997 | Turnkey | Dec'25 | Shilpi Srivastava | Meridian Park @ The Prestige City | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Priyanka Mathur |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Varun Mandana | Sunil Kumar S M | Active | Installation | Execution | 1693564 | 1693564 | 1295953 | 1642499 | 1693564 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-10 18:28 | 2026-02-01 | 2026-02-01 13:47 | 2026-02-07 | 2026-02-05 16:59 | 2026-04-28 | 2026-04-26 15:17 | 2026-04-27 | 2026-04-26 15:21 | 2026-05-11 | 2026-05-13 10:44 | 2026-02-05 | 2026-01-31 05:30 | 2026-02-06 | 2026-02-05 19:38 | 2026-02-05 | 2026-02-06 17:47 | 2026-02-12 | 2026-02-12 19:30 | 2026-05-13 | 2026-05-13 11:12 | 2026-05-16 | 2026-05-13 12:23 | 2026-05-06 | 2026-05-09 | 2026-05-15 | 2026-05-14 17:54 | 2026-05-15 | 2026-05-14 19:09 |  |  | 2026-05-29 | 2026-05-31 11:15 | 2026-05-31 | 2026-05-31 14:40 | 2026-06-03 | 2026-05-31 14:41 | 2026-05-31 | 2026-05-31 17:56 |  |  |  |  | 2026-06-03 12:51 | 2026-06-17 | 2026-06-17 19:53 | 2026-06-27 | 2026-06-26 10:39 | 2026-06-26 | 2026-06-30 15:15 | 2026-06-26 | 2026-07-06 12:02 | 2026-07-06 | 2026-07-06 13:02 | 2026-07-11 | 2026-07-10 18:49 |  |  | 2026-08-08 |  | 2026-08-10 |  | 2026-08-11 | [5 empty] | 2026-05-31 | 2026-06-02 14:00 | 2026-04-11 | 2026-04-26 15:12 | Site is RTMI | 2026-01-10 | 2026-01-10 18:01 | 1369683.7118 | 231247 | 1974673.5734 | 317669 | 2021848.887 | 325458 | 2021848.887 | 325458 | 2026-07-06 15:47:39 +0530 | Ranjith Kumar | Execution: | 2026-06-29 10:47:06 +0530 | Ranjith Kumar | Cx Side Civil Work & Electrical - WIP Bonito Side Floor Covering Done & False Ceiling - WIP, Cx Delayed | 2026-06-22 13:19:45 +0530 | Ranjith Kumar | Cx Side Civil Work & Electrical - WIP Bonito Side Floor Covering Done & False Ceiling - WIP, Cx Delayed
17998 | Turnkey | Dec'25 | Rakesh Pai | Silver Rock | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Savita Parab | Rizwan Mistry | Murali S | Umang Shah | Aakash Gaikwad | Active | Installation | Execution | 1706181 | 1621359 | 3873465 | 1679510 | 1868931 | 37 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-10 18:02 | 2026-01-18 | 2026-01-18 10:44 | 2026-01-27 | 2026-01-27 11:30 | 2026-02-05 | 2026-03-24 17:03 | 2026-02-09 | 2026-03-24 17:04 | 2026-02-11 | 2026-03-24 19:54 | 2026-01-27 | 2026-01-29 17:05 | 2026-01-28 | 2026-01-29 17:07 | 2026-01-26 | 2026-01-30 18:27 | 2026-02-03 | 2026-02-03 17:50 | 2026-03-27 | 2026-03-28 12:36 | 2026-02-16 | 2026-03-31 13:12 | 2026-02-16 | 2026-03-31 | 2026-02-18 | 2026-04-02 10:46 | 2026-04-03 | 2026-04-02 10:46 |  |  | 2026-04-09 | 2026-04-14 17:29 | 2026-04-15 | 2026-04-15 19:20 | 2026-03-02 | 2026-04-16 12:18 | 2026-04-16 | 2026-04-20 19:45 |  |  |  |  | 2026-04-21 16:26 | 2026-05-04 | 2026-04-30 22:21 | 2026-05-20 | 2026-05-21 20:49 | 2026-03-16 | 2026-05-19 17:28 | 2026-05-21 | 2026-06-05 10:54 | 2026-06-04 | 2026-06-08 23:57 | 2026-06-10 | 2026-06-16 12:27 |  |  | 2026-07-22 |  | 2026-07-24 |  | 2026-07-25 | [5 empty] | 2026-04-16 | 2026-04-21 13:50 | 2026-03-18 | 2026-03-23 16:41 | Site is RTMI | 2026-01-10 | 2026-01-10 18:01 | 3282597 | 590867 | 2250835 | 405150 | 2490427 | 448276 | 2490427 | 411222 | 2026-07-08 23:28:15 +0530 | Savita Parab | Execution: floor covering done false ceiling done electrical wiring done and again rework happened due to cx wants to check dimmer with light paint work on hold due to this modular installation in progress awaiting for snag delivery bed fitting and master bedroom shutter s all received bend | 2026-06-17 23:20:50 +0530 | Savita Parab | Execution: Floor covering done false ceiling done electrical done First coat in progress 1st june to 7th june Modular material delivery plan on 8th June Modular installation in progress so many material not deliver with main load Master bedroom wardrobe shutters, skirting, filler not receivedÂ Master bedroom VRM material not receivedÂ Master bedroom tv unit side panel and above openable shutter carcass not receivedÂ Guest bedroom tv storage and side storage back panel not receivedÂ Guest bedroom loft shutter damaged receivedÂ Kids room shutter damaged receivedÂ snag raised | 2026-06-08 23:58:17 +0530 | Savita Parab | Execution: Floor covering done false ceiling done electrical done First coat in progress 1st june to 7th june Modular material delivery plan on 8th June
17999 | Turnkey | Dec'25 | Muthu Krishnan Chollamuthu | LODHA AMARA | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Akash Jadhav | Sandeep Tiwari | Murali S | Harshaan Tiku | Aakash Gaikwad | Active | Installation | Execution | 2177673 | 2177673 | 1434066 | 2158049 | 2177673 | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-11 21:18 | 2026-01-13 | 2026-01-13 14:15 | 2026-01-13 | 2026-01-13 17:36 | 2026-03-20 | 2026-02-27 19:14 | 2026-03-23 | 2026-02-27 19:14 | 2026-03-26 | 2026-02-28 18:02 | 2026-01-13 | 2026-01-13 19:52 | 2026-01-14 | 2026-01-14 13:25 | 2026-01-14 | 2026-01-21 12:35 | 2026-01-29 | 2026-01-29 16:34 | 2026-03-01 | 2026-03-01 19:30 | 2026-03-09 | 2026-03-06 20:29 | 2026-03-29 | 2026-02-23 | 2026-03-12 | 2026-03-13 00:30 | 2026-03-14 | 2026-03-13 00:30 |  |  | 2026-04-05 | 2026-04-12 11:48 | 2026-04-14 | 2026-04-14 19:47 | 2026-04-17 | 2026-04-14 19:49 | 2026-04-14 | 2026-04-17 18:28 |  |  |  |  | 2026-04-19 14:45 | 2026-05-04 | 2026-04-30 22:25 | 2026-05-16 | 2026-05-15 18:31 | 2026-05-16 | 2026-05-21 18:47 | 2026-05-15 | 2026-05-27 15:09 | 2026-05-27 | 2026-05-29 20:30 | 2026-05-31 | 2026-06-16 13:04 |  |  | 2026-06-18 |  | 2026-05-25 |  | 2026-07-21 | [5 empty] | 2026-04-14 | 2026-04-18 11:27 | 2026-01-30 | 2026-02-27 19:02 | Site is RTMI | 2026-01-10 | 2026-01-11 21:16 | 1515959.6986 | 249264 | 2266013.7556 | 382583 | 2343561.6167 | 377950 | 2343561.6167 | 377950 | 2026-06-15 13:52:36 +0530 | Akash Jadhav | Execution: Modular installation work in progess Final painting start 20th June to 26th June Cleaning : 26th June Per Qc 28th June Qc 29th june site handover 12th July | 2026-06-08 00:18:58 +0530 | Akash Jadhav | Execution: Modular installation in progress Cleaning: 18th June Per Qc 19th June Qc 20th june site handover 12th July | 2026-06-02 23:33:46 +0530 | Akash Jadhav | Execution: Modular deliver on site 28th may modular installation work in progress
18001 | Turnkey | Dec'25 | Shwetank pateria | Sai Balaji urban retreat | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | CDP Due | 3037448 | 9999 | 0 | 0 | 0 | 150 | 0 | 293746 | 607490 | 934090 | 1192124 |  |  | 2026-01-11 | 2026-01-10 19:19 | 2026-01-11 | 2026-02-15 15:46 | 2026-02-21 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-03-11 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 |  | 2026-03-11 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-18 |  | 2026-03-19 |  |  |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-29 |  | 2026-03-29 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-29 |  | 2026-02-24 |  | Unknown | 2026-01-10 | 2026-01-10 19:13 | 0 | 0 | 0 | 0 | 0 | 0 | 2574108 | 463339 | 2026-01-11 11:38:32 +0530 | Aman Kumar | CDP: 1. Budget - 15L 2. Property Name & Possession -Â sri balaji urban retreat ( March ) 4. BHK - 4 BHK Villa 5. Family Size - 4
18002 | Turnkey | Dec'25 | Chandan | lodha amara thane | MUM - Thane | Yes | Pooja Nakul Sharma | [9 empty] | Active | Prospect | CDP Due | 1242171 | 9999 | 0 | 0 | 0 | 185 | 0 | 114218 | 248434 | 388215 | 481304.8 |  |  | 2026-01-11 | 2026-01-10 20:20 | 2026-01-11 | 2026-01-11 12:31 | 2026-01-18 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-01-19 |  | 2026-01-20 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-08 |  | 2026-02-12 |  | 2026-02-13 |  |  |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-23 | [6 empty] | 2026-03-01 |  | 2026-03-10 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-13 |  |  |  | 2026-04-04 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-02-23 |  | 2026-01-21 |  | Unknown | 2026-01-10 | 2026-01-10 20:16 | 0 | 0 | 0 | 0 | 0 | 0 | 1052687 | 189483 | 2026-01-17 19:10:00 +0530 | Pooja Nakul Sharma | DCM: Mr ParmarÂ Lodha Amara - 2BHKÂ W25- 3605 Poss- 4th Feb 2026 Family of 6Â Profession- HR , father- TMC CA- 720 sqft incl balcony, w/o balcony- 680 sq ftÂ To be vastu compliantÂ 1. Safety door, shoerack can be planned inside.Â 2. Tv unit minimal, sofa 3+1, Puja unit with storage, balcony- pvc ceiling, chairs, wall decor.Â 3. Kitchen- Base, wall , loft cabinets, utility storage.Â 4. Common bedroom- Queen/ king bed as per space with storage, wardrobes, Tv provision (optional), dresser, side tables.Â 5. MBR- Queen/ king bed as per space with storage, wardrobes, Tv provision (optional), dresser, side tables, work desk, space for shoes. 6. False ceiling - full home, painting, electricals.Â 7. Bathrooms- Wall mount unit. 8. Common bathroom- sink to be changed. Base vanity unit. 9. Kitchen- dado tiles to be changed.Â 10. Additional storages to be planned.Â 11. Kitchen door to be changed to sliding. 12. Panelling needed near safety door.Â 13. CDP- 18th @ 11 am 14. Budget- 10L
18003 | Turnkey | Dec'25 | Prashanth Srinivas G | adani the views | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Kashmira Nerurkar |  |  | Naushad Ansari | Rizwan Mistry | Murali S | Saloni Sagwekar | Aakash Gaikwad | Hold | Preproduction | Site Readiness 2 | 2228930 | 1360401.6 | 1504937 | 2172971 | 2228930 | 13 | 70 | 0 | 0 | 0 | 868528.4 |  |  | 2026-01-11 | 2026-01-11 14:02 | 2026-01-11 | 2026-01-11 14:19 | 2026-01-16 | 2026-01-16 11:23 | 2026-03-04 | 2026-03-04 13:46 | 2026-03-08 | 2026-03-08 19:05 | 2026-03-15 | 2026-03-15 15:17 | 2026-01-16 | 2026-01-16 18:38 | 2026-01-17 | 2026-01-16 18:45 | 2026-01-16 | 2026-01-27 10:35 | 2026-02-03 | 2026-02-03 18:17 | 2026-03-15 | 2026-03-15 15:21 | 2026-03-18 | 2026-03-15 15:23 | 2026-03-22 | 2026-02-13 16:49 | 2026-05-24 | 2026-05-24 12:05 | 2026-05-25 | 2026-05-24 12:05 |  |  | 2026-05-27 | 2026-05-31 13:27 | 2026-06-03 | 2026-06-03 16:34 | 2026-06-06 | 2026-06-06 11:07 | 2026-06-06 | 2026-06-09 18:04 | [5 empty] | 2026-08-08 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-08-02 |  | 2026-02-04 | 2026-03-04 13:36 | Site is RTMI | 2026-01-10 | 2026-01-10 20:34 | 1551273.718 | 260075 | 2274432.7784 | 384860 | 2317034.7742 | 393396 | 2317034.7742 | 393396 | 2026-07-07 12:08:18 +0530 | Manzoor Shaikh | Others: Not having the Keys | 2026-07-03 16:11:17 +0530 | Meet Shah | Others: | 2026-06-21 16:20:25 +0530 | Manzoor Shaikh | Some Image was uploaded
18004 | Turnkey | Dec'25 | Sheetal Gaud | ashtavinyak | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Uday Yadruk | Rizwan Mistry | Murali S | Moni Sahani | Aakash Gaikwad | Active | Handover | Project Closure Pending | 1268636 | 1268636 | 1395555 | 1324448 | 1268636 | 25 | 2 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-13 12:22 | 2026-01-13 | 2026-01-13 12:26 | 2026-01-13 | 2026-01-13 12:45 | 2026-03-03 | 2026-02-23 10:33 | 2026-02-24 | 2026-02-24 14:01 | 2026-02-28 | 2026-02-28 18:53 | 2026-01-13 | 2026-01-14 11:47 | 2026-01-14 | 2026-01-28 15:59 | 2026-01-28 | 2026-02-09 14:50 | 2026-02-17 | 2026-02-17 18:12 | 2026-03-01 | 2026-03-01 17:15 | 2026-03-04 | 2026-03-01 19:58 | 2026-03-04 | 2026-03-01 19:49 | 2026-03-07 | 2026-03-07 20:35 | 2026-03-08 | 2026-03-07 20:36 |  |  | 2026-03-20 | 2026-03-25 13:04 | 2026-03-26 | 2026-03-26 19:47 | 2026-03-29 | 2026-03-26 21:01 | 2026-03-26 | 2026-03-27 19:36 |  |  |  |  | 2026-04-01 00:19 | 2026-04-16 | 2026-04-15 21:08 | 2026-04-25 | 2026-04-25 14:02 | 2026-04-25 | 2026-04-30 19:43 | 2026-04-25 | 2026-05-05 16:44 | 2026-05-06 | 2026-05-22 10:58 | 2026-05-24 | 2026-05-23 12:22 |  |  | 2026-06-15 | 2026-06-19 23:49 | 2026-06-15 | 2026-06-19 23:51 | 2026-06-15 | 2026-06-20 00:04 |  |  |  |  | 2026-03-28 | 2026-04-01 00:18 | 2026-02-18 | 2026-02-22 17:51 | Site is RTMI | 2026-01-10 | 2026-01-11 18:53 | 1182674 | 212881 | 1415567.5126 | 228729 | 1358916.0724 | 220215 | 1358916.0724 | 220215 | 2026-06-08 20:08:34 +0530 | Uday Yadruk | Execution: Modular installation - 90 % completed ( handle and lock fixing pending ) 1st coat of paint - in progress Electrical work - completed Blockers - The site has been on hold for the last 15 /20 days due to the PI vendor ( flame interior ). We have been continuously following up with the vendor, Flame Interior, but have not received any response we unable to complete the site with just 1 painter, client is already escalated | 2026-06-01 12:39:57 +0530 | Uday Yadruk | Execution: Modular installation - 90 % completed ( handle and lock fixing pending ) 1st coat of paint - in progress Electrical work - completed Blockers - The site has been on hold for the last 1520 days due to the PI vendor. We have been continuously following up with the vendor, Flame Interior, but have not received any response. The client is escalating the issue as debris removal is still pending, and the painting work has also not been completed. | 2026-05-13 18:40:04 +0530 | Reshma Melanta | Modular Delivery: May 12, 2026 Execution Start Date: May 14, 2026 Estimated Handover Date: June 30th, 2026 I completely understand the concerns regarding the delay and will surely try to expedite the process from our end to see if we can move the date forward. We will formally address and work on the delay compensation once the site handover is successfully completed. Thank you for your continued patience and really sorry for the same, will surely get this aligned. @Uday BONITO DESIGNÂ @Rizwan mistry BONITO DESIGNÂ FYI
18005 | Turnkey | Dec'25 | Nilesh Nigade | Eastern Grooves | MUM - Thane | Yes | Mayuri Patil | [7 empty] | Vandana Preet |  | Active | Prospect | CDP Due | 854561 | 9999 | 0 | 0 | 0 | 182 | 0 | 75457 | 170912 | 277468 | 320725.2 |  |  | 2026-01-11 | 2026-01-13 14:22 | 2026-01-14 | 2026-01-14 12:45 | 2026-01-11 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-14 |  | 2026-02-15 |  |  |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-25 |  | 2026-02-25 | [6 empty] | 2026-03-03 |  | 2026-03-12 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-15 |  |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-02-25 |  | 2026-01-23 |  | Site is RTMI | 2026-01-10 | 2026-01-13 14:18 | 0 | 0 | 0 | 0 | 0 | 0 | 936418.8624 | 145611 | 2026-04-29 13:36:10 +0530 | Vandana Preet | Some Image was uploaded | 2026-01-14 12:46:27 +0530 | Mayuri Patil | DCM: MINUTES OF MEETING (MoM)Client Name: Nilesh Nigade Location: Panvel Project Type: Residential Interior 2 BHK Community: Eastern Grooves Family Details: Parents + 2 couples + 1 daughter Profession: Oil & Gas Engineer Cultural Preference: Maharashtrian traditional Current Residence: Panvel OrientationFlat orientation discussed (as per site notes).Client Requirements Scope of WorkGeneralSafety doorPainting for the entire flatFalse ceiling with complete electrificationAC panelling in Living Room & BedroomsWall breaking (as discussed)Living / Hall AreaTV unit with panellingMandir / temple unitShoe rack (02 units)KitchenModular kitchen with wall units & loftsLoft units on both sidesMain counter: wall unit + loftService counter with loftBedroomsBedroom Unit 05Sliding wardrobe with loftDressing unitSide tables (02)Foldable study tableBedroom Unit 04Same requirements as Unit 05Additional ItemsWardrobes: Total 02Dressing + study units includedDoor opening modifications (01 door)Quotation DiscussionTwo separate quotations to be shared for:Safety door with panellingShoe unitsDoor openingTV unitMandir unit
18006 | Turnkey | Dec'25 | Irfan khan | L&T Elixir Reserve | MUM - GOR | Yes | Mandar Ambre | Manzoor Shaikh | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Naushad Ansari | Rizwan Mistry | Murali S | Saloni Sagwekar | Aakash Gaikwad | Active | Installation | Execution | 1538487 | 1538487 | 1553928 | 1415404 | 1538487 | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-12 | 2026-01-11 13:49 | 2026-01-16 | 2026-01-17 16:36 | 2026-01-20 | 2026-01-20 12:10 | 2026-02-27 | 2026-02-27 18:37 | 2026-02-27 | 2026-02-27 19:37 | 2026-02-27 | 2026-02-27 20:35 | 2026-01-20 | 2026-01-20 18:58 | 2026-01-21 | 2026-01-21 12:32 | 2026-01-21 | 2026-01-21 16:22 | 2026-01-29 | 2026-01-29 15:08 | 2026-03-29 | 2026-03-30 11:34 | 2026-04-02 | 2026-03-30 13:23 | 2026-03-01 | 2026-02-17 19:21 | 2026-04-10 | 2026-04-16 19:13 | 2026-04-17 | 2026-04-16 19:13 |  |  | 2026-04-19 | 2026-04-22 13:23 | 2026-04-27 | 2026-04-27 00:13 | 2026-04-30 | 2026-04-27 12:54 | 2026-04-30 | 2026-04-28 19:47 |  |  |  |  | 2026-05-03 21:39 | 2026-05-10 | 2026-05-11 21:43 | 2026-06-01 | 2026-05-29 19:18 | 2026-05-29 | 2026-06-03 19:43 | 2026-05-29 | 2026-06-10 17:59 | 2026-06-11 | 2026-06-15 23:35 | 2026-06-16 | 2026-06-19 18:17 |  |  | 2026-07-25 |  | 2026-07-27 |  | 2026-07-28 | [5 empty] | 2026-04-29 | 2026-05-03 21:38 | 2026-01-30 | 2026-02-27 18:24 | Site is RTMI | 2026-01-11 | 2026-01-11 13:16 | 1316888 | 237039 | 1583189.6173 | 246417 | 1715370.493 | 268243 | 1715370.493 | 268243 | 2026-07-09 00:27:14 +0530 | Naushad Ansari | Execution: Floor covering done electrical wiring done pop grooving started from 18th May painting started from 29th may to 6th June ( Cx 7 days delayed for painting colour selection) site get ready on 7th June Modular delivery done on 13th June Day 1 done on 16th June Modular vendor not aligned for 14days delayed. Modular installation is progress and now is hold due to plumbing work from cx side 4 days delayed. Final paints colour not selected by Cx. Mandir top panel colour variation is not as per Cx. Mandir Door jali design is not as per the Cx requirement. | 2026-06-16 18:23:12 +0530 | Savita Parab | Execution: loor covering done electrical wiring done pop grooving started from 18th May painting started from 29th may to 6th June site get ready on 7th June Modular delivery done on 13th June Day 1 done on 16th June vendor not assign yet | 2026-06-08 23:42:24 +0530 | Savita Parab | Execution: loor covering done electrical wiring done pop grooving started from 18th May painting started from 29th may to 6th June site get ready on 7th June awaiting for modular delivery
18007 | Turnkey | Dec'25 | kapil gupta | Pelican Square | BNG - HSR | Yes | Preksha Sajjanshettar | Akshay Ds | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Hold | Preproduction | Site Readiness 1 | 2675215 | 314378 | 3101252 | 2675215 | 0 | 2 | 17 | 0 | 0 | 1375453 | 985383.6 |  |  | 2026-01-12 | 2026-01-11 13:53 | 2026-01-17 | 2026-01-17 14:24 | 2026-01-19 | 2026-01-19 12:53 | 2026-02-07 | 2026-02-07 11:48 | 2026-06-04 | 2026-06-04 14:58 | 2026-06-24 | 2026-06-24 16:13 | 2026-01-19 | 2026-01-19 20:01 | 2026-01-20 | 2026-01-20 17:00 | 2026-01-20 | 2026-01-22 10:58 | 2026-01-29 | 2026-01-29 11:23 | 2026-06-24 | 2026-06-24 17:53 | 2026-06-27 | 2026-06-26 13:14 | 2026-02-09 | 2026-01-19 | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-31 |  | 2026-07-31 | [6 empty] | 2026-08-06 |  | 2026-08-15 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-12 | [5 empty] | 2026-07-31 |  | 2026-01-30 | 2026-02-05 14:46 | Site is RTMI | 2026-01-11 | 2026-01-11 13:52 | 2628180 | 473072 | 2508129.4131 | 414185 | 0 | 0 | 2508129.4131 | 414185 | 2026-06-11 17:39:24 +0530 | Preethi Shetty | Material selection is done - working on the design changes as per the last discussion and need to update the quotation as per changes | 2026-06-03 17:24:12 +0530 | Preethi Shetty | Some Image was uploaded | 2026-06-03 17:23:10 +0530 | Preethi Shetty | Some Image was uploaded
18008 | Turnkey | Dec'25 | Yogita B | Silicon height | BNG - HRBR | Yes |  | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1722733 | 9999 | 1722733 | 0 | 0 | 178 | 0 | 162274 | 344547 | 562204 | 643709.6 |  |  | 2026-01-12 | 2026-01-11 15:43 | 2026-01-12 | 2026-01-14 10:59 | 2026-01-18 | 2026-01-18 18:56 | 2026-01-30 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-01-19 |  | 2026-01-20 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-08 |  | 2026-02-12 |  | 2026-02-13 |  |  |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-23 | [6 empty] | 2026-03-01 |  | 2026-03-10 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-13 |  |  |  | 2026-04-04 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-02-23 |  | 2026-01-21 |  | Unknown | 2026-01-11 | 2026-01-11 14:05 | 1459943 | 262789 | 0 | 0 | 0 | 0 | 1459943 | 262789 | 2026-01-12 15:23:29 +0530 | Brunda LR | DCM: MOm - CDP , west facing,Sai silicon heightsÂ Possession - April Move in - asapÂ Theme - minimalist themeÂ 4 people, 2 adults, 2kidsÂ Budget -10-12 lakhs. Foyer -Shoe rack with Storage & mirror & wall designÂ Living & Dinning- Tv unit will be shifted to opposite wall, with minimal storage, grand wall designÂ L-shape SofaÂ tv - 65 inches , beiges, yellow, blue, greenÂ foldable dinning table -4 seaterÂ crockery unit -with glass unit & StorageÂ Vanity unit with storageÂ Kitchen, Olive green & beigeÂ Utility wall will be demolished,Â Base, wall & loft. Space for microwave & Other AppliancesÂ Â loft Should be on top of sink & L-shapeÂ Master bedroomÂ wardrobe will on either side of bathroom wallÂ Study table with storageÂ wall concept of earthy vibesÂ Mbr balcony - two sofa & seating With minimal StorageÂ Â BedroomÂ Window bay seating with loftÂ only study & foldable bedÂ Â Bedroom -Bunker bed, study, Wardrobe with external DrawersÂ Â Balcony -To keep brooms & storageÂ Shower partition In two Bathrooms.Â Â False ceiling - Living & dinningÂ Bar unit in balcony.
18009 | Turnkey | Dec'25 | Anitha Shetty | Dombivli Lodha palava | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 1245528 | 10000 | 0 | 0 | 0 | 185 | 0 | 114553 | 249106 | 452601 | 419268.4 |  |  | 2026-01-11 | 2026-01-14 11:55 | 2026-01-14 |  | 2026-01-13 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-14 |  | 2026-02-15 |  |  |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-25 |  | 2026-02-25 | [6 empty] | 2026-03-03 |  | 2026-03-12 |  | 2026-03-08 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-15 |  |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-02-25 |  | 2026-01-23 |  | Unknown | 2026-01-10 | 2026-01-13 19:37 | 0 | 0 | 0 | 0 | 0 | 0 | 1055532 | 189995
18011 | Turnkey | Dec'25 | bharti .. | Lotus apartment | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Lost | Design | Design Finalization | 1644032 | 200443 | 2033270 | 0 | 0 | 172 | 0 | 0 | 292767 | 554846 | 595976 |  |  | 2026-01-12 | 2026-01-11 14:58 | 2026-01-11 | 2026-01-14 14:21 | 2026-01-20 | 2026-01-20 12:44 | 2026-03-21 | 2026-03-21 16:54 | 2026-03-24 | 2026-03-21 19:12 | 2026-12-03 |  | 2026-01-20 | 2026-01-22 18:48 | 2026-01-21 | 2026-01-23 11:47 | 2026-01-23 | 2026-01-24 15:47 | 2026-02-20 | 2026-02-20 16:10 | 2026-12-03 |  | 2026-12-06 |  | 2026-12-06 |  | 2026-12-10 |  | 2026-12-11 |  |  |  | 2026-12-17 |  | 2026-12-18 |  | 2026-12-21 |  | 2026-12-21 | [6 empty] | 2026-12-27 |  | 2027-01-05 |  | 2027-01-04 |  | 2027-01-05 |  | 2027-01-06 |  | 2027-01-08 |  |  |  | 2027-01-30 |  | 2027-02-01 |  | 2027-02-02 | [5 empty] | 2026-12-21 |  | 2026-02-21 | 2026-03-12 11:58 | Site is RTMI | 2026-01-11 | 2026-01-11 14:57 | 1723110 | 310159 | 0 | 0 | 0 | 0 | 1874549.9943 | 309513 | 2026-06-28 19:52:53 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-24 11:02:52 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-03-29 10:56:58 +0530 | Abhinandan K S | Customer is not available due to medical emergency. They will be visiting our EC on 5th April 2026 to discuss and finalize on the designs along with the 20% payment.
18012 | Turnkey | Dec'25 | Diwakar Belavadi | Total Environment Homes - The Magic Faraway Tree | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | Design Finalization | 716034 | 88955 | 2622814 | 0 | 0 | 152 | 0 | 0 | 125855 | 214810 | 286413.6 |  |  | 2026-01-12 | 2026-01-11 15:12 | 2026-01-14 | 2026-01-24 15:26 | 2026-02-04 | 2026-02-04 10:55 | 2026-08-10 |  | 2026-08-13 |  | 2026-08-16 |  | 2026-02-04 | 2026-02-11 16:17 | 2026-02-05 | 2026-02-12 11:35 | 2026-02-12 | 2026-02-13 11:59 | 2026-02-20 | 2026-02-20 17:58 | 2026-08-16 |  | 2026-08-19 |  | 2026-08-19 |  | 2026-08-23 |  | 2026-08-24 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-03 |  | 2026-09-03 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-09-03 |  | 2026-08-01 |  | Site is RTMI | 2026-01-11 | 2026-01-11 15:07 | 2222724 | 400090 | 0 | 0 | 0 | 0 | 753857.795 | 124479 | 2026-07-14 14:50:24 +0530 | Akshay Ds | Customer want to redesign the entire house according to new designer, he is ready to connect on saturday or sunday, he want to see how its going to look then he will proceed with next steps | 2026-07-14 13:09:05 +0530 | Akshay Ds |  | 2026-07-14 13:08:47 +0530 | Kiran Agarampalli
18013 | Turnkey | Dec'25 | Mohit Mohan Ambawade | Puranik city Reserva | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Faraz Soudagar | Akshat Shrivastava | Murali S | Saloni Chawan | Shailendra Mishra | Active | Installation | Execution | 1171975 | 1171975 | 1720856 | 1265432 | 1171975 | 1 | 54 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-11 15:13 | 2026-01-14 | 2026-01-14 22:29 | 2026-01-20 | 2026-01-17 12:41 | 2026-02-26 | 2026-02-26 13:26 |  |  |  |  | 2026-01-17 | 2026-01-17 18:24 | 2026-01-18 | 2026-01-17 18:24 | 2026-01-17 | 2026-01-19 15:00 | 2026-01-23 | 2026-01-23 15:23 | 2026-02-28 | 2026-02-28 20:52 | 2026-02-28 | 2026-02-28 22:24 | 2026-02-28 | 2026-02-28 22:00 | 2026-04-06 | 2026-04-04 20:28 | 2026-04-05 | 2026-04-05 11:41 |  |  | 2026-04-16 | 2026-04-18 19:21 | 2026-04-19 | 2026-04-19 15:21 | 2026-04-22 | 2026-04-19 17:10 | 2026-06-15 | 2026-05-28 19:07 |  |  |  |  | 2026-06-04 13:01 | 2026-06-13 | 2026-06-12 19:19 | 2026-07-01 | 2026-06-29 21:08 | 2026-06-30 | 2026-07-10 12:02 | 2026-06-29 | 2026-07-13 12:41 | 2026-07-14 | 2026-07-14 18:22 | 2026-07-16 |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-08 | [5 empty] | 2026-05-31 | 2026-06-04 13:00 | 2026-02-18 | 2026-02-19 13:24 | Site is RTMI | 2026-01-10 | 2026-01-11 15:08 | 1458352 | 262503 | 1364485.6009 | 217438 | 1281877.5987 | 203182 | 1281877.5987 | 203182 | 2026-07-12 13:49:40 +0530 | Faraz Soudagar | Dispatch Due: Material is in transite Modular delievery ETA 14th July | 2026-06-29 18:59:41 +0530 | Anamika Dolai | Some Image was uploaded | 2026-06-27 17:22:41 +0530 | Anamika Dolai | 40% payment would be done by 30th.
18014 | Turnkey | Dec'25 | Christopher | * | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [7 empty] | Active | Prospect | CDP Due | 2757251 | 9999 | 0 | 0 | 0 | 180 | 0 | 265726 | 551450 | 885774 | 1044301.6 |  |  | 2026-01-12 | 2026-01-12 12:05 | 2026-01-11 | 2026-01-16 15:29 | 2026-01-17 |  | 2026-02-03 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-27 |  | 2026-02-27 | [6 empty] | 2026-03-05 |  | 2026-03-14 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-17 |  |  |  | 2026-04-08 |  | 2026-04-10 |  | 2026-04-11 | [5 empty] | 2026-02-27 |  | 2026-01-25 |  | Unknown | 2026-01-11 | 2026-01-11 15:37 | 0 | 0 | 0 | 0 | 0 | 0 | 2336653 | 420597 | 2026-01-11 17:05:28 +0530 | Keerthan M | DCM: Christopher 5BHK CX Budget 15-20L Foyer - Outside - Shoe rack with seating Living - Open for suggestion - TV unit with storageÂ - Wall detailing - Crockery unit (Dining) Kitchen - Entry from dining - U Shape - Bottom unit, top units, Loft(optional) - Island/ BF counter - Tall units, OTG units, Roller shutters. - Counter top GBR (GF) - Queen size Bed from Our scope - Wall detailing - washroom - Vanity MBR (FF) for daughter - Walk in closet - Foyer area opposite to the door - U shape closet with dresser - Storage in the center - combi of glass shutters and laminate. - Washroom - Vanity and glass partition. - king size bed - TV Unit KBR - 2 Single beds - Kids theme - Study Unit Bedroom 2 - wardrobe - foldable table (Study unit) - Wall highlight Bedroom 3 (Prayer room with study) - study table - Seating space. - Prayer room. Note: - False ceiling - Vanity in all the bathrooms and shower partition. - WM in terrace - Landscaping/Sit out in terrace.
18015 | Turnkey | Dec'25 | Siddhant Srivastava | individual flat | BNG - HSR | Yes | Chittipireddy Sriharish | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Lost | Design | Design Finalization | 2062713 | 236216 | 2362157 | 0 | 0 | 165 | 0 | 0 | 382598 | 618814 | 825085.2 |  |  | 2026-01-12 | 2026-01-11 17:14 | 2026-01-11 | 2026-01-11 19:09 | 2026-01-26 | 2026-01-26 13:19 | 2026-03-03 | 2026-03-04 11:41 | 2026-12-03 |  | 2026-12-06 |  | 2026-01-26 | 2026-01-27 15:19 | 2026-01-27 | 2026-01-28 10:46 | 2026-01-28 | 2026-01-31 17:45 | 2026-02-06 | 2026-02-06 19:40 | 2026-12-06 |  | 2026-12-09 |  | 2026-12-09 |  | 2026-12-13 |  | 2026-12-14 |  |  |  | 2026-12-20 |  | 2026-12-21 |  | 2026-12-24 |  | 2026-12-24 | [6 empty] | 2026-12-30 |  | 2027-01-08 |  | 2027-01-07 |  | 2027-01-08 |  | 2027-01-09 |  | 2027-01-11 |  |  |  | 2027-02-02 |  | 2027-02-04 |  | 2027-02-05 | [5 empty] | 2026-12-24 |  | 2026-02-07 | 2026-02-17 11:28 | Site is RTMI | 2026-01-11 | 2026-01-11 17:13 | 2001828 | 360329 | 0 | 0 | 0 | 0 | 2275814.116 | 366515 | 2026-07-09 17:35:32 +0530 | Abhinandan K S |  | 2026-07-09 17:33:39 +0530 | Abhinandan K S |  | 2026-06-28 19:56:21 +0530 | Abhinandan K S | Some Image was uploaded
18016 | Turnkey | Dec'25 | Mr. Muralidharan | Godrej Ananda | BNG - HRBR | Yes | Sanjay Kulkarni | Rajeshwari S | Shibin Lal | [7 empty] | Active | Prospect | CDP Due | 931772 | 9999 | 0 | 0 | 0 | 182 | 0 | 83178 | 186354 | 294889 | 357351.6 |  |  | 2026-01-12 | 2026-01-13 14:02 | 2026-01-14 | 2026-01-14 11:45 | 2026-01-18 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-01-19 |  | 2026-01-20 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-08 |  | 2026-02-12 |  | 2026-02-13 |  |  |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-23 | [6 empty] | 2026-03-01 |  | 2026-03-10 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-13 |  |  |  | 2026-04-04 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-02-23 |  | 2026-01-21 |  | Unknown | 2026-01-11 | 2026-01-13 13:01 | 0 | 0 | 0 | 0 | 0 | 0 | 789638 | 142134 | 2026-01-11 19:04:22 +0530 | Rhea Rathod | DCM: GODREJ ANANDA 18016 - Murali - RGMÂ East facing Family of 5 Budget - 8- 9 lakhsÂ LIVING - - Tv unit - Wall mounted - Rich wall concept , minimalist, modern - 3 seater sofa wit a coffee table KITCHEN - - Pooja unit placement to be checked - Base cabinetsÂ - Wall units - Dish washed placement to be checked - Cylinder cabinet in the utility DINING - - 4 seater/ 6 seater dining table - Wall concept MASTER BEDROOM- (Kids bedroom) - 3 kids- bunker bed - WardrobeÂ - Study unit - for 2 BEDROOM 1 - (Parents bedroom) - wardrobe - study unit - Queen size bed BATHROOMS - - Vanity unit with mirrorÂ - Shower partition RADIANCE GARDANIA Rental South facing Budget - 4 lakhs KITCHEN - - Full modular kitchen BATHROOMS - - Vanity unit
18017 | Turnkey | Dec'25 | Rashmi | independent house | BNG - HSR | Yes | Priyanka Inchoor | Akshay Ds | Kowshik |  | Sethuragavan R | Shijin C C | Jairam Joshi | Murali S | Chanakya Panigrahi | Sunil Kumar S M | Completed | Complete | Completed | 1701078 | 1701079 | 1824841 | 1592579 | 1701078 | 65 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-12 | 2026-01-11 17:47 | 2026-01-14 | 2026-01-17 18:10 | 2026-01-23 | 2026-01-18 11:22 | 2026-01-30 | 2026-01-30 10:50 | 2026-02-23 | 2026-02-23 12:24 | 2026-02-24 | 2026-02-23 13:46 | 2026-01-18 | 2026-01-21 10:39 | 2026-01-19 | 2026-01-21 10:41 | 2026-01-21 | 2026-01-22 19:45 | 2026-01-27 | 2026-01-27 16:17 | 2026-02-23 | 2026-02-23 15:03 | 2026-03-01 | 2026-02-23 15:08 | 2026-03-01 | 2026-02-23 13:13 | 2026-02-27 | 2026-03-03 09:51 | 2026-03-04 | 2026-03-03 15:14 |  |  | 2026-03-05 | 2026-03-07 16:50 | 2026-03-07 | 2026-03-07 19:59 | 2026-03-10 | 2026-03-07 20:50 | 2026-03-07 | 2026-03-11 18:07 |  |  |  |  | 2026-03-12 13:37 | 2026-03-21 | 2026-03-20 19:47 | 2026-04-02 | 2026-03-31 20:03 | 2026-04-01 | 2026-04-01 17:28 | 2026-03-31 | 2026-04-04 14:53 | 2026-04-04 | 2026-04-06 15:38 | 2026-04-11 | 2026-04-10 17:18 |  |  | 2026-04-24 | 2026-04-25 10:59 | 2026-04-30 | 2026-04-25 11:33 | 2026-05-01 | 2026-04-25 14:02 |  |  |  |  | 2026-03-07 | 2026-03-11 16:58 | 2026-01-28 | 2026-01-30 10:46 | Site is RTMI | 2026-01-11 | 2026-01-11 17:43 | 1546475 | 278365 | 1849999.7407 | 305478 | 1950231.1819 | 322028 | 1950231.1819 | 322028 | 2026-04-25 14:18:26 +0530 | Jairam Joshi | Project Closure Pending: Observation points closure ETA - 11th May | 2026-04-23 18:01:52 +0530 | Jairam Joshi | Some Image was uploaded | 2026-04-23 11:21:56 +0530 | Patil Madhavi | Some Image was uploaded
18018 | Turnkey | Dec'25 | Fazal Naushad Khan | Dottom domain | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [7 empty] | Hold | Design | Design Finalization | 1595257 | 479999 | 2097625 | 0 | 0 | 37 | 131 | 0 | 0 | 502494 | 612764.4 |  |  | 2026-01-12 | 2026-01-11 18:21 | 2026-01-13 | 2026-01-13 12:30 | 2026-01-20 | 2026-01-20 12:28 | 2027-01-08 |  | 2027-01-11 |  | 2027-01-14 |  | 2026-01-20 | 2026-01-22 11:48 | 2026-01-21 | 2026-01-24 14:29 | 2026-01-24 | 2026-01-28 14:28 | 2026-02-17 | 2026-02-17 12:48 | 2027-01-14 |  | 2027-01-17 |  | 2027-01-17 | 2026-06-29 14:39 | 2027-01-22 |  | 2027-01-23 |  |  |  | 2027-01-29 |  | 2027-01-30 |  | 2027-02-02 |  | 2027-02-02 | [6 empty] | 2027-02-08 |  | 2027-02-17 |  | 2027-02-16 |  | 2027-02-17 |  | 2027-02-18 |  | 2027-02-20 |  |  |  | 2027-03-14 |  | 2027-03-16 |  | 2027-03-17 | [5 empty] | 2027-02-02 |  | 2026-12-30 |  | Site is RTMI | 2026-01-11 | 2026-01-11 18:19 | 1827647 | 319976 | 0 | 0 | 0 | 0 | 1768492.1064 | 283005 | 2026-07-10 15:59:15 +0530 | Anil Jagtap | cx will receive the possession by October end | 2026-06-12 19:18:07 +0530 | Anamika Dolai | Some Image was uploaded | 2026-03-25 12:06:27 +0530 | Anamika Dolai | As per the communication, client is gonna receive possession by December,2026
18019 | Turnkey | Dec'25 | K K Divakar Reddy | Devagiri opal kr Puram | BNG - HRBR | Yes | Hemalatha D | Rajeshwari S | [8 empty] | Active | Prospect | CDP Due | 832299 | 9999 | 0 | 0 | 0 | 180 | 0 | 73231 | 166460 | 268371 | 314238.8 |  |  | 2026-01-12 | 2026-01-12 11:57 | 2026-01-16 | 2026-01-16 15:50 | 2026-01-17 |  | 2026-02-03 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-27 |  | 2026-02-27 | [6 empty] | 2026-03-05 |  | 2026-03-14 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-17 |  |  |  | 2026-04-08 |  | 2026-04-10 |  | 2026-04-11 | [5 empty] | 2026-02-27 |  | 2026-01-25 |  | Unknown | 2026-01-11 | 2026-01-12 11:56 | 0 | 0 | 0 | 0 | 0 | 0 | 705338 | 126960
18020 | Turnkey | Dec'25 | BUILDCARE CONSTRUCTION(RAVÄ°NDRA GANPAT DHEMARE) | Aim Heritage | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Uday Yadruk | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Hold | Production | 100% Payment | 1235970 | 770759 | 1148579 | 1219661 | 1235970 | 13 | 85 | 0 | 0 | 0 | 465211 |  |  | 2026-01-12 | 2026-01-14 18:54 | 2026-01-28 | 2026-01-28 13:36 | 2026-01-28 | 2026-01-28 13:49 | 2026-02-20 | 2026-02-20 10:47 | 2026-02-23 | 2026-02-23 17:15 | 2026-02-23 | 2026-02-23 18:38 | 2026-01-28 | 2026-01-31 05:30 | 2026-01-29 | 2026-02-05 12:31 | 2026-02-05 | 2026-02-05 16:39 | 2026-02-10 | 2026-02-10 19:05 | 2026-02-23 | 2026-02-23 18:46 | 2026-02-26 | 2026-02-27 12:32 | 2026-02-26 | 2026-02-26 19:37 | 2026-03-07 | 2026-03-07 14:15 | 2026-03-08 | 2026-03-07 14:15 |  |  | 2026-03-12 | 2026-03-13 18:15 | 2026-03-14 | 2026-03-14 20:29 | 2026-03-17 | 2026-03-15 12:49 | 2026-03-15 | 2026-03-17 19:35 |  |  |  |  | 2026-03-28 11:12 | 2026-04-11 | 2026-04-10 11:27 | 2026-04-19 | 2026-04-17 19:02 | 2026-05-01 |  | 2026-07-15 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-03 |  | 2026-05-05 |  | 2026-05-06 | [5 empty] | 2026-03-18 | 2026-03-28 11:11 | 2026-02-11 | 2026-02-18 21:08 | Site is RTMI | 2026-01-11 | 2026-01-11 18:24 | 1052656 | 175206 | 1339665.9817 | 216558 | 1354077.1938 | 219046 | 1354077.1938 | 219046 | 2026-05-15 16:18:10 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-08 16:32:58 +0530 | Reshma Melanta | FLAT NUMBER : 504 | 2026-05-02 19:15:50 +0530 | Reshma Melanta | Some Image was uploaded
18021 | Turnkey | Dec'25 | SANJAY JADHAV & ASSOCIATES(SanjayJadhav) Jadhav | Ratan Heritage | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Uday Yadruk | Rizwan Mistry |  |  | Aakash Gaikwad | Hold | Design | 60% Payment | 1179321 | 353928 | 1179202 | 1179760 | 1179321 | 11 | 107 | 0 | 0 | 384329 | 441064.4 |  |  | 2026-01-12 | 2026-01-13 13:04 | 2026-01-28 | 2026-01-28 13:43 | 2026-01-28 | 2026-01-28 13:46 | 2026-02-20 | 2026-02-20 10:53 | 2026-02-23 | 2026-02-23 17:26 | 2026-02-23 | 2026-02-23 18:47 | 2026-01-28 | 2026-01-30 16:37 | 2026-01-29 | 2026-01-31 13:04 | 2026-01-31 | 2026-02-03 15:24 | 2026-02-10 | 2026-02-10 19:05 | 2026-02-23 | 2026-02-23 19:17 | 2026-02-26 | 2026-02-28 13:36 | 2026-02-26 | 2026-02-27 13:14 | 2026-03-07 | 2026-03-07 15:34 | 2026-03-08 | 2026-03-07 15:34 |  |  | 2026-03-18 | 2026-03-19 17:54 | 2026-03-19 | 2026-03-19 21:15 | 2026-03-22 | 2026-03-22 14:50 | 2026-09-30 | [6 empty] | 2026-03-28 |  | 2026-04-06 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-09 |  |  |  | 2026-05-01 |  | 2026-05-03 |  | 2026-05-04 | [5 empty] | 2026-03-22 |  | 2026-02-11 | 2026-02-18 21:07 | Site is RTMI | 2026-01-11 | 2026-01-11 18:29 | 1078608 | 179878 | 1304388.3724 | 210471 | 1304002.3535 | 210404 | 1304002.3535 | 210404 | 2026-06-02 15:53:05 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-15 16:17:46 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-08 16:33:23 +0530 | Reshma Melanta | FLAT NUMBER - 503
18022 | Turnkey | Dec'25 | Lalita Mohan Iyer | Sanghvi Nesta | MUM - Thane | Yes | Rachna Abhyankar | Divya Rahangdale | Rushika More |  | Deepa kamboj | Faraz Soudagar | Aditya Vikram | Murali S | Nishtha Valawalkar | Aakash Gaikwad | Completed | Complete | Completed | 1037998 | 1037998 | 1328310 | 981099 | 1037998 | 28 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-12 | 2026-01-11 20:38 | 2026-01-15 | 2026-01-15 15:10 | 2026-01-21 | 2026-01-16 12:42 | 2026-02-05 | 2026-02-05 13:24 | 2026-02-06 | 2026-02-05 13:56 | 2026-02-10 | 2026-02-10 11:12 | 2026-01-16 | 2026-01-16 18:21 | 2026-01-17 | 2026-01-16 18:25 | 2026-01-16 | 2026-01-20 11:04 | 2026-01-21 | 2026-01-21 13:06 | 2026-02-10 | 2026-02-10 15:46 | 2026-02-13 | 2026-02-11 14:50 | 2026-02-09 | 2026-02-09 20:23 | 2026-02-20 | 2026-02-19 11:50 | 2026-02-20 | 2026-02-28 18:59 |  |  | 2026-03-07 | 2026-03-10 20:30 | 2026-03-10 | 2026-03-10 21:39 | 2026-03-13 | 2026-03-10 21:59 | 2026-03-10 | 2026-03-12 19:03 |  |  |  |  | 2026-03-14 18:44 | 2026-03-26 | 2026-03-25 12:11 | 2026-03-28 | 2026-03-27 15:25 | 2026-04-07 | 2026-04-01 17:58 | 2026-03-27 | 2026-04-11 15:44 | 2026-04-13 | 2026-04-16 15:23 | 2026-04-18 | 2026-05-23 18:48 |  |  | 2026-06-08 | 2026-05-30 19:15 | 2026-06-10 | 2026-05-30 19:15 | 2026-06-11 | 2026-05-30 20:23 |  |  |  |  | 2026-03-10 | 2026-03-14 00:08 | 2026-01-22 | 2026-01-28 18:10 | Site is RTMI | 2026-01-11 | 2026-01-11 20:35 | 1125687 | 202623 | 1132277.9789 | 172540 | 1188429.441 | 181220 | 1188429.441 | 181220 | 2026-06-29 16:15:03 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-01 15:36:17 +0530 | Faraz Soudagar | Project Closure Pending: Observation stage ETA - 15th June Project closure - 15th June | 2026-05-18 15:03:34 +0530 | Faraz Soudagar | Execution: Snag installation ETA - 19th May Final coat of paint - 23th May Deep cleaning - 24th May QC- 26th may
18023 | Turnkey | Dec'25 | Dhruv gandhi | Beverly hills | MUM - GOR | Yes | Saif Shaikh |  | Shantanu Parakh | [5 empty] | Rashmita Das |  | Active | Prospect | CDP Due | 1761986 | 9999 | 0 | 0 | 0 | 181 | 0 | 166200 | 352397 | 555835 | 677555.6 |  |  | 2026-01-12 | 2026-01-12 12:43 | 2026-01-15 | 2026-01-15 08:51 | 2026-01-20 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-14 |  | 2026-02-15 |  |  |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-25 |  | 2026-02-25 | [6 empty] | 2026-03-03 |  | 2026-03-12 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-15 |  |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-02-25 |  | 2026-01-23 |  | Unknown | 2026-01-11 | 2026-01-11 20:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1493208 | 268777 | 2026-01-13 11:35:54 +0530 | Saif Shaikh | DCM: MOM LIVING ROOMÂ seating arrangement and TV unit will be mirror 2 mandir units 1 closed 1 open for ganpati ONE big frame Dining table can be 4 & 6 seater ONE additional sofa cum bed in living room accent/rocking chair KITCHEN microwave pantry unit cooktop facing window chopping and cutting tray comes out of base unit dishwasher, washing machine, fridge, rolling shutter unit SON'S BEDROOM single murphy bed with sofa option study unit with wall storage & sliding wardrobe for 2 people dresser unit and iron board provision MASTERBEDROOM queen size bed 2 wardrobe walk in wardrobe provision one option with bathroom entry through the walk in wardrobe study desk with drawer book storage with open shelves and closed unit reading corner safety door sleek shoe rack if possible foldable seating wall paneling in the foyer area MIRROR ON TV AND MANDIR UNIT WALL WAHSROOM MIRROR LIKE OUR EC DINING AREA IN BLUISH THEME, FLYING BIRDS, PEOCOCK WINDOW AND SEATING AREA CAN BE IN SAGE GREEN & OLIVE GREEN THEME WORLD MAP THEME IN SON'S BEDROOM BETWEEN STUDY WALL STORAGE MEDITATION ZONE AS WELL SINGLE SWING IF CAN BE ADDED DECORATIVE PARTITION HANGING FROM CEILING NEAR DINING AREA
18024 | Turnkey | Dec'25 | Pradeep Nayak | Highland Park | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  |  | Faraz Soudagar | Akshat Shrivastava |  | Vandana Preet | Prasad Bhivaji Hande | Active | Design | Design Finalization | 1879918 | 334793 | 2121651 | 0 | 0 | 14 | 103 | 0 | 0 | 877511 | 667614.4 |  |  | 2026-01-12 | 2026-01-13 14:24 | 2026-03-04 | 2026-03-10 19:02 | 2026-03-15 | 2026-03-15 20:00 | 2026-07-15 | 2026-07-14 17:17 | 2026-07-15 | 2026-07-14 17:39 | 2026-07-15 | 2026-07-14 18:02 | 2026-03-15 | 2026-03-17 16:22 | 2026-03-16 | 2026-03-20 13:10 | 2026-03-20 | 2026-03-20 17:34 | 2026-03-26 | 2026-03-26 14:59 | 2026-07-14 |  | 2026-07-17 |  | 2026-10-18 | 2026-07-14 18:35 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-26 |  | 2026-07-26 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-26 |  | 2026-09-30 | 2026-07-14 15:48 | Site is RTMI | 2026-01-11 | 2026-01-13 14:23 | 1798009 | 323641 | 0 | 0 | 0 | 0 | 1980134.3699 | 341682 | 2026-07-14 18:18:36 +0530 | Anil Jagtap |  | 2026-07-14 17:49:05 +0530 | Rachna Abhyankar |  | 2026-07-12 10:55:54 +0530 | Amisha Ahuja
18025 | Turnkey | Dec'25 | Mayank Sohar | Sobha City rk hegde nagar | BNG - HRBR | Yes |  | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | CDP Due | 1748113 | 9999 | 0 | 0 | 0 | 178 | 0 | 164812 | 349623 | 542135 | 681544 |  |  | 2026-01-12 | 2026-01-12 16:41 | 2026-01-18 | 2026-01-18 05:42 | 2026-01-15 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-11 | 2026-01-11 21:16 | 0 | 0 | 0 | 0 | 0 | 0 | 1481452 | 266661 | 2026-01-18 05:33:41 +0530 | Brunda LR | Mom - Mayank soharÂ RGM -Shobha City Budget -10-15 lakhsÂ Theme -Indian traditional themeÂ 4 people will be staying in homeÂ Foyer -Seating with StorageÂ Living -Simple traditional tv unit with more lighting Sofa - 3seater 2 accent chairs with some wall designÂ crockery unit - Base unit & wall unitÂ 6 seater Dinning table with walnut finish Kitchen -base wall & Loft with full storageÂ Utility -Space for Dishwasher , Washing machine , Sink unitÂ Â Bedroom 01Â Openable wardrobe Mirror with some storage , no tv & StudyÂ Â with neutral colors & some nice wallpaperÂ Bedroom 02 Only openable wardrobe with vanity are storageÂ Bedroom 3Â Bay window with seating , no Dresser, a wider Study table. pooja unitÂ Bathroom 3 should be fully renovated with tiles & everything.Â the ExistingÂ Wardrobes in both the Bedrooms Should be shifted to Utility areaÂ Half wall & Half glass partition should be created in all bathroomsÂ Â Â
18026 | Turnkey | Dec'25 | Deepak Israni | avrone | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Savita Parab | Rizwan Mistry | Murali S | Prashant Panigrahi | Aakash Gaikwad | Active | Handover | Project Closure Pending | 1334622 | 1334623 | 1344708 | 1358092 | 1334622 | 51 | 9 | 0 | 0 | 0 | 0 |  |  | 2026-01-12 | 2026-01-12 17:27 | 2026-01-16 | 2026-01-21 14:56 | 2026-01-28 | 2026-01-30 11:45 | 2026-02-26 | 2026-02-24 16:26 |  |  |  |  | 2026-01-30 | 2026-01-31 12:15 | 2026-01-31 | 2026-02-01 12:39 | 2026-02-01 | 2026-02-03 14:20 | 2026-02-20 | 2026-02-20 14:33 | 2026-02-24 | 2026-02-24 19:48 | 2026-02-27 | 2026-02-25 22:06 | 2026-02-27 | 2026-02-24 19:38 | 2026-03-11 | 2026-03-08 12:28 | 2026-03-09 | 2026-03-08 12:28 |  |  | 2026-03-12 | 2026-03-18 14:15 | 2026-03-19 | 2026-03-19 15:40 | 2026-03-22 | 2026-03-19 22:05 | 2026-03-19 | 2026-03-25 18:24 |  |  |  |  | 2026-04-04 20:51 | 2026-04-22 | 2026-04-21 21:28 | 2026-04-29 | 2026-04-27 20:28 | 2026-04-17 | 2026-04-21 12:20 | 2026-04-27 | 2026-04-29 17:51 | 2026-04-29 | 2026-05-02 11:46 | 2026-05-04 | 2026-05-09 17:48 |  |  | 2026-05-30 | 2026-05-25 23:23 | 2026-05-15 | 2026-05-25 23:24 | 2026-06-03 | 2026-05-25 23:36 |  |  |  |  | 2026-03-27 | 2026-04-04 20:50 | 2026-02-21 | 2026-02-24 16:09 | Site is RTMI | 2026-01-11 | 2026-01-12 17:26 | 1417710.3345 | 235633 | 1412066.45 | 237675 | 1312411.86 | 226467 | 1312411.86 | 226467 | 2026-07-08 23:28:53 +0530 | Savita Parab | Execution: project closing on 9th july all work done | 2026-05-18 18:39:18 +0530 | Faizal Shaikh | Execution: Main Load Received on 2nd May Day 01 04th May Day 04 7th May Modular work will get finish as per material Cleaning completed 17th May Qc Planned for 20th May. | 2026-05-18 16:41:06 +0530 | Faizal Shaikh | Execution: Main Load Received on 2nd May Day 01 04th May Day 04 7th May Modular work will get finish as per material Cleaning completed 17th May Qc Planned for 19th May.
18027 | Turnkey | Dec'25 | Suman Mishra | Rustomjee | MUM - Thane | No Estimate | Pooja Nakul Sharma | [9 empty] | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-11 | 2026-01-14 16:44 | 2026-01-11 |  | 2026-01-15 |  | 2026-01-27 |  | 2026-01-30 |  | 2026-02-02 |  | 2026-01-15 |  | 2026-01-16 |  | 2026-01-16 |  | 2026-01-17 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-09 |  | 2026-02-10 |  |  |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-20 |  | 2026-02-20 | [6 empty] | 2026-02-26 |  | 2026-03-07 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-10 |  |  |  | 2026-04-01 |  | 2026-04-03 |  | 2026-04-04 | [5 empty] | 2026-02-20 |  | 2026-01-18 |  | Unknown | 2026-01-10 | 2026-01-14 16:38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-01-14 14:10:36 +0530 | Rishabh Borikar | Some Image was uploaded
18028 | Turnkey | Dec'25 | Archana chauhan | Samrin heritage | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Saloni Chawan | Shailendra Mishra | Hold | Preproduction | 2D | 1219393 | 365999 | 1218629 | 1219393 | 0 | 37 | 65 | 0 | 0 | 383572 | 469822 |  |  | 2026-01-12 | 2026-01-20 18:39 | 2026-02-03 | 2026-02-03 10:54 | 2026-02-03 | 2026-02-03 13:18 | 2026-03-05 | 2026-03-05 12:46 | 2026-03-24 | 2026-03-23 11:53 |  |  | 2026-02-03 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-04 19:06 | 2026-02-04 | 2026-02-05 15:46 | 2026-02-27 | 2026-02-27 19:09 | 2026-03-31 | 2026-03-31 17:59 | 2026-03-31 | 2026-03-31 18:54 | 2026-03-31 | 2026-03-31 | 2026-04-06 | 2026-04-04 20:37 | 2026-04-05 | 2026-04-06 12:09 |  |  | 2027-01-05 |  | 2027-01-06 |  | 2027-01-09 |  | 2027-01-09 | [6 empty] | 2027-01-15 |  | 2027-01-24 |  | 2027-01-23 |  | 2027-01-24 |  | 2027-01-25 |  | 2027-01-27 |  |  |  | 2027-02-18 |  | 2027-02-20 |  | 2027-02-21 | [5 empty] | 2027-01-09 |  | 2026-04-29 | 2026-03-05 12:02 | Site is RTMI | 2026-01-11 | 2026-01-15 18:08 | 1248777.0125 | 208774 | 1210540.0688 | 208890 | 0 | 0 | 1210540.0688 | 208890 | 2026-07-10 12:09:07 +0530 | Divya Rahangdale | CX will receive the possession by September. | 2026-07-02 14:07:26 +0530 | Divya Rahangdale | Hold | 2026-06-26 17:02:55 +0530 | Shraddha Pansare | The client is unsure about the property since the builder is not giving a confirm date of the possession. Client has asked to put the project on hold till the month oif August.
18029 | Turnkey | Dec'25 | Mr. Sankalp | RUNWAL FOREST | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Aryan Singh |  | Hold | Design | Design Finalization | 1313517 | 262999 | 1736111 | 0 | 0 | 33 | 104 | 0 | 131056 | 425104 | 494358.4 |  |  | 2026-01-12 | 2026-01-12 17:17 | 2026-02-03 | 2026-02-03 12:09 | 2026-02-21 | 2026-02-24 11:34 | 2026-09-08 |  | 2026-09-11 |  | 2026-09-14 |  | 2026-02-24 | 2026-02-24 11:50 | 2026-02-25 | 2026-02-26 12:57 | 2026-02-26 | 2026-02-28 19:07 | 2026-03-05 | 2026-03-05 12:14 | 2026-09-14 |  | 2026-09-17 |  | 2026-09-17 |  | 2026-09-21 |  | 2026-09-22 |  |  |  | 2026-09-28 |  | 2026-09-29 |  | 2026-10-02 |  | 2026-10-02 | [6 empty] | 2026-10-08 |  | 2026-10-17 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-20 |  |  |  | 2026-11-11 |  | 2026-11-13 |  | 2026-11-14 | [5 empty] | 2026-10-02 |  | 2026-08-30 |  | Site is RTMI | 2026-01-11 | 2026-01-12 17:16 | 1471281 | 264830 | 0 | 0 | 0 | 0 | 1471280.878 | 233926 | 2026-07-10 11:01:09 +0530 | Anil Jagtap | cx will receive the possession by July end 2026 | 2026-06-30 11:19:58 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-27 18:45:27 +0530 | Parnavi Joshi | Some Image was uploaded
18030 | Turnkey | Dec'25 | Supriya U | Runwal Sanctuary | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Snehankit Agre | Akshat Shrivastava |  | Aryan Singh | Shailendra Mishra | Active | Installation | Execution | 2116587 | 2119788 | 3939976 | 3090677 | 2310124 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-12 | 2026-01-12 17:15 | 2026-01-16 | 2026-01-18 01:50 | 2026-01-20 | 2026-01-20 16:57 | 2026-03-07 | 2026-03-05 12:25 | 2026-03-06 | 2026-03-05 12:40 |  |  | 2026-01-18 | 2026-01-19 19:52 | 2026-01-23 | 2026-01-20 16:30 | 2026-01-21 | 2026-01-28 16:57 | 2026-02-08 | 2026-02-08 16:59 | 2026-03-27 | 2026-03-27 19:07 | 2026-05-10 | 2026-03-28 20:14 | 2026-05-10 | 2026-03-28 15:10 | 2026-04-02 | 2026-03-31 17:27 | 2026-04-01 | 2026-04-01 21:49 |  |  | 2026-04-17 | 2026-04-24 10:40 | 2026-04-24 | 2026-04-24 16:30 | 2026-04-27 | 2026-04-24 19:57 | 2026-04-24 | 2026-04-27 17:37 |  |  |  |  | 2026-04-30 19:04 | 2026-05-03 | 2026-06-11 19:22 | 2026-06-27 | 2026-06-23 20:29 | 2026-05-10 | 2026-06-01 10:59 | 2026-06-23 | 2026-06-25 19:00 | 2026-06-26 | 2026-06-28 21:39 | 2026-06-30 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-31 | [5 empty] | 2026-04-30 | 2026-04-30 19:03 | 2026-02-28 | 2026-03-05 10:58 | Site is RTMI | 2026-01-11 | 2026-01-12 17:13 | 3762691 | 677284 | 2641044.89 | 471459 | 2273128.6048 | 405781 | 2065021.6137 | 368632 | 2026-07-13 11:17:10 +0530 | Snehankit Agre | Execution: 13th Installation work in progress | 2026-07-07 02:03:27 +0530 | Snehankit Agre | Execution: Material received on site 26th June Painting work 27th june to 4 july No team from 28th june to 5th july, Modular work start from 6 july | 2026-07-02 00:50:43 +0530 | Snehankit Agre | Execution: work was hold from 5 may to 20 june for sprinkler position changes, ceiling design changes because AC placement, from CX side. Ceiling work completed 25 june.
18031 | Turnkey | Dec'25 | Sasmitha | Independent villa | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | CDP Due | 4347859 | 9999 | 0 | 0 | 0 | 172 | 0 | 424787 | 869572 | 1423950 | 1619551.6 |  |  | 2026-01-12 | 2026-01-12 16:46 | 2026-01-24 | 2026-01-24 16:57 | 2026-01-26 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-20 |  | 2026-02-21 |  |  |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-03 |  | 2026-03-03 | [6 empty] | 2026-03-09 |  | 2026-03-18 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-21 |  |  |  | 2026-04-12 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-03-03 |  | 2026-01-29 |  | Unknown | 2026-01-11 | 2026-01-12 16:45 | 0 | 0 | 0 | 0 | 0 | 0 | 3684627 | 663232 | 2026-01-15 19:14:35 +0530 | Vishnu S | Title:Â Design Consultation Meeting Project No:Â 18031 Client:Â Sasmitha Hi, Minutes of Meeting held on Date:Â 15/01/2026 Attendees:Â Vishnu & Client Discussion:Â Requirement gathering meeting North facing House Family of 5 People Husband & Wife, Son & Daughter with senior citizen Girl-20years & Boy-14years Ground floor Living Area -Shoe rack with seater (40pairs) -wall Treatment -Semi partition -Tv unit Area (No Tv) -Left & Right glass Window & Center highlighter wall with Fireplace -3+2 Seater sofa + 1 Recliner -false ceiling ( Minimal with profile lightings) -Garden proposal on balcony Dining Area -6 seater dining -Crockery unit Kitchen -Acrylic finish Base,top,tall & chimney patta with one side loft -Quartz -Under Ro -Prefers Fluted glass -Double door fridge Utility -Dishwasher , Doube bowl sink Staircase -wall highlighter -Storages Senior Citizen room -Sliding wardrobe + Loft -Dresser -Tv provision (55") -wall treatment -Window seater -Vanity First Floor Forma Living -Pooja unit -Tv unit -Nook corner -Snooker table with wall treatment Study Area -Library unit -workspace -Arch panel ( Carpentry) Master Bedroom -Wall treatment -Kings size bed -Walkin wardrobe + Loft -Dresser unit + Mirror -Vanity -Shower Partition-Sliding -Laundry storages Kids Bedroom-1 (Sons)-Car theme -Wall treatment -Kings size bed -Walkin wardrobe + Loft -Vanity -Shower Partition-Sliding -Study + Bookshelfs Kids Bedroom-2 (Daughter) -Wall treatment -Kings size bed -Walkin wardrobe + Loft -Vanity -Shower Partition-Sliding -Window seater (Arch) -Dresser unit + Mirror Terrace -washing machine + Storages -Linen storages Guest Bedroom -Wall treatment -Kings size bed -Walkin wardrobe + Loft -Vanity -Shower Partition-Sliding -Study -Chest of drawers Client are mostly aligned with mix of traditional theme for senior citizen & More into modern luxury especially in common area & Master bedroom & kids bedroom to be not funky but teenagers feel to have more proposal on Functionality & Durability Note : Before CDP they wanted to see the completed house Executed visit & Needs to planned asap. RGM : 15/01/2026 CDP : Post 25/01/2026 (Need to be reconfirmed once site visit is aligned)
18032 | Turnkey | Dec'25 | shriram date | MXOthers | MUM - GOR | Yes | Priyanka Patel |  | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 1961031 | 9999 | 0 | 0 | 0 | 183 | 0 | 186104 | 392206 | 707093 | 665629.2 |  |  | 2026-01-11 | 2026-01-13 12:29 | 2026-01-11 |  | 2026-01-21 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 | [6 empty] | 2026-03-04 |  | 2026-03-13 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-16 |  |  |  | 2026-04-07 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-02-26 |  | 2026-01-24 |  | Unknown | 2026-01-10 | 2026-01-13 12:28 | 0 | 0 | 0 | 0 | 0 | 0 | 2051004.4173 | 344903 | 2026-05-26 13:38:52 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-09 16:38:53 +0530 | Christopher Macwan | Some Image was uploaded
18033 | Turnkey | Dec'25 | RAJESH PATRI | SSVR NIYARA | BNG - HRBR | Yes | Chandini Nj | Rajeshwari S | Yogesh Patidar | [5 empty] | Ankur Kumar |  | Active | Prospect | CDP Due | 1251188 | 9999 | 1251188 | 0 | 0 | 178 | 0 | 115120 | 250238 | 377476 | 498356 |  |  | 2026-01-14 | 2026-01-17 18:16 | 2026-01-18 | 2026-01-18 17:34 | 2026-01-20 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-01-20 |  | 2026-01-21 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-10 |  | 2026-02-14 |  | 2026-02-15 |  |  |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-25 |  | 2026-02-25 | [6 empty] | 2026-03-03 |  | 2026-03-12 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-15 |  |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-02-25 |  | 2026-01-23 |  | Unknown | 2026-01-13 | 2026-01-13 12:51 | 1060328 | 190859 | 0 | 0 | 0 | 0 | 1060328 | 190859 | 2026-01-14 16:51:27 +0530 | Chandini Nj | Possession - 2026 june BudgetÂ Â Â -10L Apartment-SSVR NIYARA Theme- Italian mid centuryÂ Work profile - Technical manager, manyatta tech park How many people are going to stay - 4 members, husband and wife, 2 kids, 13 years old son, 6year old son Purpose (Rental/Own) -OWN PURPOSEÂ Deeper understanding (Usual hobbies):Â Living area - TV unit, Side storage, Lshape sofa Dining area- only wallpaper Kitchen - Cylinder unit, 3 ft hob, sink, tall unit, loft, crockery unit Master bed room - Wardrobe with loft, wall designs Kids bed room 1 - wardrobe with loft and 2 study units Office room -Â study unit and wardrobe. False ceiling living mbr, kbr, office room, taken the quotation by qok interior 8.5lakh, urben company (discussion happening still not taken the quotation)
18034 | Turnkey | Dec'25 | Kiran Reddy | Shah Kingdom | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Saloni Chawan |  | Hold | Design | Design Finalization | 1119998 | 224000 | 1149998 | 0 | 0 | 66 | 90 | 0 | 0 | 455720 | 440278 |  |  | 2026-01-11 | 2026-01-13 13:32 | 2026-01-21 | 2026-01-21 11:14 | 2026-01-21 | 2026-01-21 13:52 | 2026-03-12 | 2026-03-12 12:47 | 2026-04-01 | 2026-04-04 13:57 | 2026-07-31 |  | 2026-01-21 | 2026-01-22 11:46 | 2026-01-22 | 2026-01-30 14:13 | 2026-03-17 | 2026-02-09 09:46 | 2026-02-20 | 2026-02-20 12:25 | 2026-07-31 |  | 2026-08-03 |  | 2026-08-03 | 2026-04-16 15:40 | 2026-08-25 |  | 2026-08-26 |  |  |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-05 |  | 2026-09-05 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-09-05 |  | 2026-03-10 | 2026-03-05 16:08 | Site is RTMI | 2026-01-10 | 2026-01-13 13:22 | 1255508.3212 | 198304 | 0 | 0 | 0 | 0 | 1255508.3212 | 198304 | 2026-07-11 19:08:16 +0530 | Anamika Dolai | Possession- Nov'26 | 2026-05-25 11:59:38 +0530 | Swami Vadnere | DDM2: MomÂ 24-05-2026 Living Room * Need to explore folding dining option behind the sofa wall. * Mandir unit design options. * Mandir unit to be planned within the base unit. * Check feasibility for pull-out tray in the mandir unit. * Need sofa wall options with hidden foldable dining table integration. * Maximise overall seating capacity in the living room. * Add AC location in the 3D views. * Create a memory wall beside the mandir wall. * Need to shift the projector location. Master Bedroom * Need to explore wardrobe option with Aristo shutters. * One more option for the bed back wall. * Need one option with hidden bathroom door concept. Kids Room * Need a football-themed room design. * Add seating space beside the window. * Study table design is fixed. * Bed back design is fixed. Kitchen Design is finalised. Bathrooms Need to explore some bathroom options with mirror designs and accessories. | 2026-03-13 11:40:43 +0530 | Sagarika Gawai | Some Image was uploaded
18035 | Turnkey | Dec'25 | Mona Ramesh Nathawani | Ethos century | BNG - HRBR | Yes | Arjun M V | Rajeshwari S | Yogesh Patidar |  | Sagarika Venkatesh |  |  |  | Janvi Nagdeo |  | Active | Prospect | CDP Due | 6761352 | 9999 | 0 | 0 | 0 | 182 | 0 | 666136 | 1352270 | 2308055 | 2424891.2 |  |  | 2026-01-12 | 2026-01-13 16:22 | 2026-01-13 | 2026-01-14 11:10 | 2026-01-28 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-11 | 2026-01-13 16:20 | 0 | 0 | 0 | 0 | 0 | 0 | 5729959 | 1031392 | 2026-01-13 18:00:08 +0530 | Nikita Raj | Next meeting - 18th Jan 2026 - 12 pm Cx wants end to end from bonito Budget - 50L end to end | 2026-01-13 17:55:29 +0530 | Nikita Raj | RGM - 13.01.26 Century ethos 5 members(son and daughter in law, daughter) 4BHK, 2800sft+300 balcony, 2nd floor Possession is in Jan end Home automation Dresser and study as per Vastu in each area Curtain and lights in full house False ceiling minimal full house All bedrooms are in wooden floor, living and dining marble(bridge), kitchen and all bathrooms in tiles. h - 9.5feet Theme - ART Decor(main theme), Abstract luxury, Japandi Cx do painting also Main door is single door Foyer- Shoe rack (40-50 pairs), inside, one outside(removable, 20 pairs), wall decor, open space below shoe rack with sitting in both shoe rack, 1-2 chair, shoe rack on left wall and wall decor on opposite wall, mirror on wall Living - Open to change the living area layout, TV unit, sofa sitting(recliner), for 8 people sitting, formal sitting, 85" TV, bar unit, curtains Balcony - Decor, swing, sitting, plants, vertical garden, sliding invisible door Dining - bigger mandir area (luxury look), 8-seater dining table with curve edges, decor, mirror, artwork, artwork in ceiling Kitchen - open kitchen, HOB and chimney on maid room wall(leave space of 2 feet left side), double bowl sink, dish washer, double door fridge, breakfast counter, crockery storage till ceiling on outer wall, decor, tall unit appliances, pantry unit(2 if possible), base, wall and loft units, RO unit, Hot water, rolling shutter, onion potato basket(don't want wicker ones), waste bins for wet waste, sink with flexy tap with hot and cold water, matka storage, induction, quartz, low maintenance material Utility - dry waste bin, washing machine, dryer, sink(flexy tap with hot and cold water), janitor unit, pull out dryer, quartz, ironing table, 2-cylinder unit, ladder storage(6feet),robot cleaner space, Dyson space Maid - bed for 2 people, wardrobe MBR - leg massager space(chair), walking closet, aristo wardrobe sliding, study unit with 2 chairs, dresser with full length mirror, one more wardrobe, king bed with two side table, wall decor, Shetty MBR balcony - Â wall decor space for Tulsi plant, sitting MBR bathroom - vanity, sitting ledge, storage for towels, mirror Study room, GBR(BEDROOM 3) - multipurpose room, sofa cum bed, work station for 2 people(sitting and standing both), home theater, 70"tv, wardrobe with loft, mirror, sliding door between bedroom and wardrobe area Bathroom - vanity, mirror Bedroom 1- aristo wardrobe, study for 2 people with wall storage, king bed with two side table, dresser, wall decor Bathroom - vanity, mirror Bedroom 2 - aristo wardrobe, study for 2 people with wall storage, king bed with two side table, dresser, wall decor, apart from given space for wardrobe plan more wardrobe storage in bedroom. Bathroom - vanity, mirror
18036 | Sub Project |  | Chetan mistry | Lodha woods kandivali | MUM - GOR |  | Priyanka Murarka | Reshma Melanta | Shantanu Parakh |  |  | Rajkumar Suthar | Aditya Vikram | Murali S |  |  | Active | Production | 100% Payment | 68921 | 67753 | 0 | 0 | 68921 | 32 | 0 | 0 | 0 | 0 | 1168 |  |  | 2026-01-14 | 2026-02-27 13:56 | 2026-01-14 | 2026-02-27 13:56 | 2026-03-01 | 2026-02-27 13:56 | 2026-03-01 | 2026-02-27 13:58 | 2026-03-01 | 2026-02-27 13:58 | 2026-02-28 | 2026-02-27 14:06 | 2026-02-27 | 2026-02-27 13:56 | 2026-02-28 | 2026-02-27 13:57 | 2026-02-26 | 2026-02-27 13:57 | 2026-02-28 | 2026-02-27 13:57 | 2026-02-27 | 2026-02-27 14:07 | 2026-02-28 | 2026-02-27 14:08 | 2026-02-27 | 2026-02-27 14:08 | 2026-02-28 | 2026-02-27 14:10 | 2026-02-27 | 2026-02-27 14:10 |  |  | 2026-02-28 | 2026-02-27 14:12 | 2026-02-28 | 2026-02-27 14:13 | 2026-02-28 | 2026-02-27 14:15 | 2026-02-28 | 2026-03-04 13:06 |  |  |  |  | 2026-03-04 14:27 | 2026-06-12 | 2026-06-11 21:12 | 2026-06-15 | 2026-06-13 12:13 | 2026-06-14 |  | 2026-06-13 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-03-04 | 2026-03-04 14:26 | 2026-03-01 | 2026-02-27 13:57 | Unknown | 2026-01-13 | 2026-02-27 13:55 | 0 | 0 | 0 | 0 | 58407 | 10513 | 58407 | 10513
18037 | Turnkey | Dec'25 | I CON (Sunil Kumar) | lodha upper thane | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Asif Shaikh | Akshat Shrivastava | Murali S | Shreyash Kotecha | Aakash Gaikwad | Active | Installation | Execution | 1361234 | 1361234 | 1499518 | 1443020 | 1361234 | 63 | 16 | 0 | 0 | 0 | 0 |  |  | 2026-01-12 | 2026-01-13 17:29 | 2026-01-14 | 2026-01-15 12:34 | 2026-01-20 | 2026-01-20 11:35 | 2026-02-20 | 2026-02-19 11:07 | 2026-02-19 | 2026-02-19 11:34 |  |  | 2026-01-20 | 2026-01-20 19:12 | 2026-01-20 | 2026-01-23 16:27 | 2026-02-25 | 2026-02-02 11:40 | 2026-02-18 | 2026-02-18 15:52 | 2026-02-27 | 2026-02-27 18:27 | 2026-03-02 | 2026-02-28 16:23 | 2026-03-06 | 2026-02-28 15:29 | 2026-03-08 | 2026-03-11 12:40 | 2026-03-12 | 2026-03-11 12:41 |  |  | 2026-03-18 | 2026-03-27 12:29 | 2026-03-27 | 2026-03-27 16:39 | 2026-03-30 | 2026-03-27 18:48 | 2026-03-27 | 2026-03-30 18:50 |  |  |  |  | 2026-03-31 18:07 | 2026-04-16 | 2026-04-15 20:54 | 2026-04-21 | 2026-04-21 11:13 | 2026-04-21 | 2026-04-25 12:43 | 2026-04-21 | 2026-04-28 20:20 | 2026-04-28 | 2026-04-30 15:55 | 2026-05-14 | 2026-05-13 17:19 |  |  | 2026-07-15 |  | 2026-07-02 |  | 2026-07-15 | [5 empty] | 2026-03-27 | 2026-03-31 15:40 | 2026-02-19 | 2026-02-18 17:03 | Site is RTMI | 2026-01-11 | 2026-01-13 17:28 | 1554544.5325 | 259248 | 1609415.9336 | 256731 | 1497722.6808 | 247306 | 1497722.6808 | 247306 | 2026-07-05 13:01:25 +0530 | Asif Shaikh | Execution: Modular Work will be resuming by 30th & will be completed by 8th July All customer carpentry & POP Grooving completing by 8th July. Final Painting Work Commencing from 8th July & will be completed by 14th July DC & Wallpaper installation - - 16th July. QC - 17th July. Snag : Kitchen base shutter - ETA - 15th July (Blocker) Project Delayed by 2 week due to manpower Crunch by wiffy vendor | 2026-06-28 17:56:25 +0530 | Asif Shaikh | Execution: Modular Work will be resuming by 30th & will be completed by 7th JulyAll customer carpentry & POP Grooving completing by 7th July.Final Painting Work Commencing from 7th July & will be completed by 14th JulyDC & Wallpaper installation - - 15th July.QC - 16th July. Project Delayed by 2 week due to manpower Crunch by wiffy vendor | 2026-06-23 22:45:09 +0530 | Asif Shaikh | Execution: Modular Work will be resuming by 23rd June & will be completed by 2rd July.All customer carpentry & POP Grooving completing by 3rd July.Final Painting Work Commencing from 4th July & will be completed by 14th July.DC & Wallpaper installation - - 15th July.QC - 16th July. Project Delayed by one week due to manpower Crunch by wiffy vendor
18038 | Turnkey | Dec'25 | Prashant Mudholkar | icon | MUM - Thane | Yes | Rutuja Kotwal | [7 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 2802936 | 9999 | 0 | 0 | 0 | 183 | 0 | 270295 | 560587 | 923073 | 1038982.4 |  |  | 2026-01-14 | 2026-01-13 20:01 | 2026-01-14 |  | 2026-01-25 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-19 |  | 2026-02-20 |  |  |  | 2026-02-26 |  | 2026-02-27 |  | 2026-03-02 |  | 2026-03-02 | [6 empty] | 2026-03-08 |  | 2026-03-17 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-20 |  |  |  | 2026-04-11 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-03-02 |  | 2026-01-28 |  | Unknown | 2026-01-13 | 2026-01-13 17:56 | 0 | 0 | 0 | 0 | 0 | 0 | 2375370 | 427566 | 2026-01-13 19:01:20 +0530 | Moksh Mehta | DCM: Name:- Prashant Mudholkar Property Name :- The Icon ( P2 - 2805 & 2806 ) Carpet Area:- 1350Sqft Possession:- Mar'26 No Of Memeber:- Couple ( 47 & 40 ) Son's ( 19 & 12 ) East facing Window
18039 | Turnkey | Dec'25 | Satish | Bluejay Ananda | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Hold | Design | Design Finalization | 1990482 | 398096 | 2051307 | 0 | 0 | 74 | 92 | 0 | 199049 | 619326 | 774011.6 |  |  | 2026-01-14 | 2026-01-14 12:12 | 2026-01-14 | 2026-01-14 14:20 | 2026-01-21 | 2026-01-22 18:05 | 2026-02-28 | 2026-02-19 12:29 | 2026-12-23 |  | 2026-12-26 |  | 2026-01-22 | 2026-01-29 19:07 | 2026-01-23 | 2026-01-29 19:17 | 2026-01-29 | 2026-01-30 15:09 | 2026-02-12 | 2026-02-12 15:37 | 2026-12-26 |  | 2026-12-29 |  | 2026-12-29 |  | 2027-01-02 |  | 2027-01-03 |  |  |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-13 |  | 2027-01-13 | [6 empty] | 2027-01-19 |  | 2027-01-28 |  | 2027-01-27 |  | 2027-01-28 |  | 2027-01-29 |  | 2027-01-31 |  |  |  | 2027-02-22 |  | 2027-02-24 |  | 2027-02-25 | [5 empty] | 2027-01-13 |  | 2026-04-04 | 2026-02-19 12:28 | Site is Non-RTMI | 2026-01-13 | 2026-01-13 18:55 | 2078543.3175 | 358673 | 0 | 0 | 0 | 0 | 2078542.762 | 349395 | 2026-04-14 16:41:37 +0530 | Akshay Ds | Some Image was uploaded | 2026-03-31 17:04:46 +0530 | Akshay Ds | This project is 10,10,40,40 process as per that customer have paid the 20% payment. but in app we are unable to tick off the payment task as app is showing old process, Possession is delayed and we need to place the project on HOLD. | 2026-03-25 13:11:15 +0530 | Kiran Agarampalli | Master Bedroom Add 2 fan points in the ceiling add 1 fan point for walk in closetÂ add light point on wardrobe wallsÂ Corridor: Add 1 light pointÂ Staircase: add additional light pointsÂ KBR Remove 5A socket from bay seater.Â Living:Â change the AC position in the living to main door wall TV point change it to 15A Guest bedroom:Â add light point on the wardrobe wallÂ Â
18041 | Turnkey | Dec'25 | Mohan Goswami Goswami | MIRA CHEMBUR | MUM - Thane | Yes | Nazneen Chovvakkaran | Divya Rahangdale | Anil Kuwar |  |  | Savita Parab | Rizwan Mistry | Murali S | Nishtha Valawalkar | Aakash Gaikwad | Active | Handover | Project Closure Pending | 858474 | 859980 | 942865 | 927506 | 850557 | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-15 | 2026-01-14 13:30 | 2026-01-23 | 2026-01-23 15:25 | 2026-01-29 | 2026-01-23 17:23 | 2026-02-13 | 2026-02-13 13:47 | 2026-02-20 | 2026-02-20 15:09 |  |  | 2026-01-23 | 2026-01-24 18:28 | 2026-01-24 | 2026-01-25 11:31 | 2026-01-25 | 2026-01-28 14:39 | 2026-02-12 | 2026-02-12 14:41 | 2026-03-07 | 2026-03-07 14:07 | 2026-03-07 | 2026-03-08 14:48 | 2026-03-17 | 2026-02-19 16:27 | 2026-03-13 | 2026-03-10 20:38 | 2026-03-11 | 2026-03-10 20:39 |  |  | 2026-03-18 | 2026-03-25 17:41 | 2026-03-26 | 2026-03-26 16:13 | 2026-03-29 | 2026-03-26 18:16 | 2026-03-26 | 2026-03-28 16:30 |  |  |  |  | 2026-04-06 18:29 | 2026-04-19 | 2026-04-21 21:30 | 2026-04-27 | 2026-04-25 19:00 | 2026-04-26 | 2026-05-07 13:38 | 2026-04-25 | 2026-05-08 17:03 | 2026-05-08 | 2026-05-12 20:24 | 2026-05-14 | 2026-05-16 11:47 |  |  | 2026-06-30 | 2026-06-15 17:29 | 2026-07-02 | 2026-06-15 17:52 | 2026-07-03 | 2026-06-15 17:58 |  |  |  |  | 2026-03-29 | 2026-04-06 18:28 | 2026-02-13 | 2026-02-13 13:40 | Site is RTMI | 2026-01-14 | 2026-01-14 13:30 | 955441 | 166708 | 942426 | 164365 | 877214 | 152627 | 883924 | 153835 | 2026-07-08 23:29:39 +0530 | Savita Parab | Execution: metal fabrication delivery plan on 9th july and awaiting for snag delivery which planed on 15th july | 2026-06-08 23:36:14 +0530 | Savita Parab | Execution: Floor covering done Modular installation in progress awaiting for snag delivery hanger rod, study table shelf and metal leg for study table molding and flat patti installation done | 2026-06-01 17:21:30 +0530 | Savita Parab | Execution: Modular delivered 11th May installation in progress vendor delayed not sending team from last 8 days Handover plan on 30th June
18042 | Turnkey | Dec'25 | Scale Gaurd | Northern Hills | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Hold | Preproduction | Site Readiness 1 | 1418458 | 498157 | 1054350 | 1418458 | 0 | 2 | 37 | 0 | 0 | 362828 | 557473.2 |  |  | 2026-01-12 | 2026-01-14 12:47 | 2026-01-27 | 2026-01-27 15:51 | 2026-01-28 | 2026-01-28 13:25 | 2026-03-30 | 2026-04-07 11:32 | 2026-04-08 | 2026-04-08 17:28 | 2026-05-21 | 2026-05-21 15:22 | 2026-01-28 | 2026-01-30 12:13 | 2026-01-29 | 2026-01-30 12:14 | 2026-01-30 | 2026-02-03 11:05 | 2026-02-12 | 2026-02-12 18:51 | 2026-05-21 | 2026-05-21 17:52 | 2026-06-15 | 2026-06-30 17:14 | 2026-06-15 | 2026-06-30 | 2026-12-05 |  | 2026-12-06 |  |  |  | 2026-12-12 |  | 2026-12-13 |  | 2026-12-16 |  | 2026-12-16 | [6 empty] | 2026-12-22 |  | 2026-12-31 |  | 2026-12-30 |  | 2026-12-31 |  | 2027-01-01 |  | 2027-01-03 |  |  |  | 2027-01-25 |  | 2027-01-27 |  | 2027-01-28 | [5 empty] | 2026-12-16 |  | 2026-02-13 | 2026-03-22 18:19 | Site is RTMI | 2026-01-11 | 2026-01-14 12:46 | 1144159.143 | 183714 | 1538799.932 | 246883 | 0 | 0 | 1538799.932 | 246883 | 2026-07-04 15:21:57 +0530 | Reshma Melanta | Others: | 2026-07-04 12:38:18 +0530 | Reshma Melanta | Others: | 2026-06-30 14:59:22 +0530 | Reshma Melanta | Some Image was uploaded
18044 | Turnkey | Dec'25 | Animesh Kumar | Abhee Silicon Shine | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Hold | Design | Design Finalization | 1294556 | 259717.55 | 1648161 | 0 | 0 | 26 | 139 | 0 | 128649 | 395138 | 511050.8 |  |  | 2026-01-15 | 2026-01-14 17:04 | 2026-01-14 | 2026-01-14 18:31 | 2026-01-23 | 2026-01-24 15:37 | 2026-08-29 |  | 2026-09-01 |  | 2026-09-04 |  | 2026-01-24 | 2026-01-29 18:33 | 2026-01-25 | 2026-01-29 18:33 | 2026-01-29 | 2026-01-31 18:05 | 2026-02-12 | 2026-02-12 13:13 | 2026-09-04 |  | 2026-09-07 |  | 2026-09-07 |  | 2026-09-11 |  | 2026-09-12 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-22 |  | 2026-09-22 | [6 empty] | 2026-09-28 |  | 2026-10-07 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-08 |  | 2026-10-10 |  |  |  | 2026-11-01 |  | 2026-11-03 |  | 2026-11-04 | [5 empty] | 2026-09-22 |  | 2026-08-20 |  | Unknown | 2026-01-14 | 2026-01-14 17:01 | 1396746 | 251414 | 0 | 0 | 0 | 0 | 1396745.973 | 232712 | 2026-05-29 16:18:48 +0530 | Akshay Ds | Customer paid the 20% payment and project is hold till august as the possession is not received | 2026-02-13 18:45:03 +0530 | Akshay Ds | Layout discussion to be conducted immediately Post that project will go on HOLD customer will be making the next 10% payment in April 2nd week(exception approval taken by sales team) Possession is expected by August end | 2026-02-02 18:26:18 +0530 | Bency Chacko
18045 | Turnkey | Dec'25 | Mahendra Maru | ms gateway | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Active | Design | Design Finalization | 1687182 | 148045 | 1480453 | 0 | 0 | 117 | 9 | 0 | 358110 | 516825 | 664202.8 |  |  | 2026-01-15 | 2026-01-14 20:47 | 2026-01-15 | 2026-01-15 10:26 | 2026-01-20 | 2026-01-20 11:21 | 2026-03-03 | 2026-02-22 20:06 | 2026-02-27 | 2026-02-27 15:25 | 2026-02-27 | 2026-02-27 16:40 | 2026-01-20 | 2026-01-22 19:07 | 2026-01-21 | 2026-01-29 12:48 | 2026-01-29 | 2026-02-16 12:55 | 2026-02-17 | 2026-02-17 19:18 | 2026-08-19 |  | 2026-08-22 |  | 2026-08-22 |  | 2026-08-26 |  | 2026-08-27 |  |  |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-06 |  | 2026-09-06 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-09-06 |  | 2026-02-18 | 2026-02-22 20:04 | Site is Non-RTMI | 2026-01-14 | 2026-01-14 20:46 | 1254621 | 225831 | 0 | 0 | 0 | 0 | 1705003.2908 | 287875 | 2026-03-11 11:59:33 +0530 | Avinash Jaiswal | CX is not happy with the design. Required re-designing therefore reactivated the estimate task | 2026-03-05 16:34:04 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-02-26 19:14:51 +0530 | Reshma Melanta | Spoke to the clinet Daugther, She was not happy with the way things are going around, it took the team 1 month to close the ON BOARDING, and she is like no one from the sale team will reverted her during that time, she tried reaching Rashmita and Sahil and both never reverted to her call. She mentioned her IM which was aligned on 24th Feb 2026, was canceeled has the deigner gave wrong address and the same is aligned on 27th Feb 2026. She mentioned she has still not frezzed her design and nothing has been finalized and she is waitng for the same. She needs some clarity reagrding the same. and needs DDM meeting has only her 1 DDM meeting has been done 22nd Feb 2026.
18046 | Turnkey | Dec'25 | Sushant | Equinox | MUM - Thane | No Estimate | Rinisha Masurkar | [7 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-15 | 2026-01-20 20:03 | 2026-01-15 |  | 2026-01-22 |  | 2026-02-03 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-27 |  | 2026-02-27 | [6 empty] | 2026-03-05 |  | 2026-03-14 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-17 |  |  |  | 2026-04-08 |  | 2026-04-10 |  | 2026-04-11 | [5 empty] | 2026-02-27 |  | 2026-01-25 |  | Unknown | 2026-01-14 | 2026-01-19 12:53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-01-15 11:46:56 +0530 | Hemant Sonar | Some Image was uploaded | 2026-01-15 11:46:38 +0530 | Hemant Sonar | DCM: DCM Notes This is a joint flat originally planned as a 6 BHK, which the client has merged into a 4 BHK. The client has requested two quotations: One including loose furniture One excluding loose furniture The final decision on loose furniture procurement will be taken later by the client. Civil work is currently in progress. Expected possession: JulyAugust. Client Details Occupation: Husband IT Professional Wife Government Employee (BMC) Residence Type: 4 BHK (Sushant) Family Size: 3 members Husband, wife, and a 4-year-old child Budget Initial budget discussed: 1520 lakhs During the meeting, a design budget range of 2530 lakhs was discussed. Clients mentioned that they have not finalized the interiors yet and have therefore shared only basic requirements. Detailed requirements and design discussions will be taken up during the design phase meetings. Area-wise Requirements Foyer Area Safety door with panelling Shoe unit Living & Dining Area TV unit with display 3+2+1 sofa seating 4-seater dining table Floor-mounted crockery unit Temple unit carpentry or modular (to be discussed) Kitchen Modular kitchen including quartz countertop Common vanity 1 No. Office Room 1 Study unit only Master Bedroom (MBR) King-size bed with bed back design Bedside tables Dresser Walk-in/openable wardrobes with partitions Wardrobe with integrated dresser MBR vanity with wall-mounted storage Childs Bedroom Theme-based complete room design (Cars & Bikes theme) Storage units Wardrobe Bay window Utility / Washing Area Washing machine provision Wall-mounted storage Common Bathrooms Common vanity 2 Nos Office Room 2 / Multi-purpose Room Study unit with storage Sofa-cum-bed Bay window Vanity Guest Bedroom Queen-size bed Wardrobe Bedside table Dresser Scope of Work (Overall) False ceiling Painting Electrical work
18047 | Turnkey | Dec'25 | Poonam Jewels (Ravi Parasmal Mehta) | Nakshatra | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Active | Design | Design Finalization | 1501320 | 195439 | 1864401 | 0 | 0 | 48 | 125 | 0 | 254957 | 528614 | 522309.6 |  |  | 2026-01-15 | 2026-01-15 15:05 | 2026-01-16 | 2026-01-16 13:51 | 2026-01-22 | 2026-01-16 13:55 | 2026-09-02 |  | 2026-09-05 |  | 2026-09-08 |  | 2026-01-16 | 2026-01-20 20:04 | 2026-01-17 | 2026-01-21 13:11 | 2026-01-21 | 2026-01-23 10:28 | 2026-02-03 | 2026-02-03 17:13 | 2026-09-08 |  | 2026-09-11 |  | 2026-09-11 |  | 2026-09-15 |  | 2026-09-16 |  |  |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-26 |  | 2026-09-26 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-26 |  | 2026-02-04 |  | Unknown | 2026-01-14 | 2026-01-15 15:04 | 1580001 | 284400 | 0 | 0 | 0 | 0 | 1580000.5669 | 259523 | 2026-02-26 15:37:09 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-02-26 13:31:26 +0530 | Manzoor Shaikh | Out called the customer for the due, however, said he will pay on possession, informed as per the agreement has to clear the due in 18 days to activate the price protection. The customer disconnected the call, tried calling again, however, did not answer. | 2026-02-22 18:24:19 +0530 | Manzoor Shaikh | Some Image was uploaded
18048 | Turnkey | Dec'25 | Arun | MJR North Park | BNG - HRBR | Yes | Alekhya Korada | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | DCM Due | 1296861 | 9999 | 0 | 0 | 0 | 182 | 0 | 119687 | 259372 | 410252 | 497550.4 |  |  | 2026-01-15 | 2026-01-14 18:14 | 2026-01-15 |  | 2026-01-24 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-14 | 2026-01-14 18:07 | 0 | 0 | 0 | 0 | 0 | 0 | 1099035 | 197826 | 2026-01-15 17:36:00 +0530 | Salpriyan Pm | FoyerÂ Bottom storage full wall - as we are changing the directionÂ Guru ji frameÂ door- Ganesha on both the sidesÂ LivingÂ tv unitÂ left side spacing - lockerÂ sofa back wall designs Â Puja room - partition on the right of the tv unit and create a puja white Marble top dining - 4 seaterÂ swing lots of green star lights in the centreÂ False ceiling - warm lights with the dim Crockery unit - facing the dining near fridge - or on the tv wall right sideÂ Passage areaÂ picture wallÂ BalconyÂ lights water foun vertical gardenÂ connection for lightÂ Ceiling fanÂ KitchenÂ bottom unitsÂ top unitsÂ loft on both sidesÂ fridge - 2 door -EC tall unitÂ tall unit with groceries like EC right cabinet- place of fridgeÂ sliding door to utilityÂ water purifierÂ MV- on the eye level on the right of the HOBÂ OTG - right of the hob bottomÂ UtiltyÂ WM, DW- wm on topÂ RO- the line will be going inside, and the unit will be placed above the Sink (WP) GY bottom Sink unitÂ Janitor unitÂ dish tray GBR(MBR) Sofa/bed workstation- furnitureÂ Wardrobe with loft - Open dressing table - mirror and storage behindÂ Drawer-4 one for bottom of dresser MBR(GBR) Queen size bedÂ wardrobe with loftÂ MBR Bathroom top storageÂ mirror with cove lightÂ bottom storageÂ Frosted glass with light on the topÂ sliding doorÂ Common bathroomÂ top storageÂ mirror with cove lightÂ bottom storageÂ Frosted glass with light on the topÂ sliding doorÂ Budget- 10L designer proposed estimate: 15-20L | 2026-01-15 17:30:36 +0530 | Salpriyan Pm | FoyerÂ Bottom storage full wall - as we are changing the directionÂ Guru ji frameÂ door- Ganesha on both the sidesÂ LivingÂ tv unitÂ left side spacing - lockerÂ sofa back wall designs Â Puja room - partition on the right of the tv unit and create a puja white Marble top dining - 4 seaterÂ swing lots of green star lights in the centerÂ Flase ceiling - warm lights with the dim Crockery unit - facing the dining near fridge - or on the tv wall right sideÂ Passage areaÂ picture wallÂ BalconyÂ lights water foun vertical gardenÂ connection for lightÂ Ceiling fanÂ KitchenÂ bottom unitsÂ top unitsÂ loft on both sidesÂ fridge - 2 door -EC tall unitÂ tall unit with groceries like EC right cabinet- place of fridgeÂ sliding door to utilityÂ water purifierÂ MV- on the eye level on the right of the HOBÂ OTG - right of the hob bottomÂ UtiltyÂ WM, DW- wm on topÂ RO- the line will be going inside, and the unit will be placed above the Sink (WP) GY bottom Sink unitÂ Janitor unitÂ dish tray GBR(MBR) Sofa/bed workstation- furnitureÂ Wardrobe with loft - Open dressing table - mirror and storage behindÂ Drawer-4 one for bottom of dresser MBR(GBR) Queen size bedÂ wardrobe with loftÂ MBR Bathroom top storageÂ mirror with cove lightÂ bottom storageÂ Frosted glass with light on the topÂ sliding doorÂ Common bathroomÂ top storageÂ mirror with cove lightÂ bottom storageÂ Frosted glass with light on the topÂ sliding doorÂ | 2026-01-15 17:03:23 +0530 | Salpriyan Pm | FoyerÂ Bottom storage full wall - as we are changing the directionÂ Guru ji frameÂ door- Ganesha on both the sidesÂ LivingÂ tv unitÂ left side spacing - lockerÂ sofa back wall designs Â Puja room - partition on the right of the tv unit and create a puja white Marble top dining - 4 seaterÂ swing lots of green star lights in the centreÂ False ceiling - warm lights with the dim Crockery unit - facing the dining near fridge - or on the tv wall right sideÂ Passage areaÂ picture wallÂ BalconyÂ lights water foun vertical gardenÂ connection for lightÂ Ceiling fanÂ KitchenÂ bottom unitsÂ top unitsÂ loft on both sidesÂ fridge - 2 door -EC tall unitÂ tall unit with groceries like EC right cabinet- place of fridgeÂ sliding door to utilityÂ water purifierÂ MV- on the eye level on the right of the HOBÂ OTG - right of the hob bottomÂ UtilityÂ WM, DW- wm on topÂ RO- the line will be going inside, and the unit will be placed above the Sink (WP) GY bottom Sink unitÂ Janitor unitÂ dish tray GBR(MBR) Sofa/bed workstation- furnitureÂ Wardrobe with loft - Open dressing table - mirror and storage behindÂ MBR(GBR) Queen size bedÂ wardrobe with loftÂ MBR Bathroom top storageÂ mirror with cove lightÂ bottom storageÂ Frosted glass with light on the topÂ sliding doorÂ Common bathroomÂ top storageÂ mirror with cove lightÂ bottom storageÂ Frosted glass with light on the topÂ sliding doorÂ Budget - 10L
18050 | Sub Project |  | Abhinaya Nagarajan Sir | Rustomjee Azzaino | MUM - GOR |  | Priyanka Murarka | Reshma Melanta | Shantanu Parakh |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-15 | 2026-01-31 13:12 | 2026-01-15 | 2026-01-31 13:12 | 2026-02-02 | 2026-01-31 13:13 | 2026-02-02 | 2026-01-31 13:16 | 2026-02-02 | 2026-01-31 13:17 | 2026-02-01 | 2026-01-31 13:18 | 2026-01-31 | 2026-01-31 13:13 | 2026-02-01 | 2026-01-31 13:14 | 2026-01-30 | 2026-01-31 13:14 | 2026-02-01 | 2026-01-31 13:14 | 2026-01-31 | 2026-01-31 13:20 | 2026-02-01 | 2026-01-31 13:20 | 2026-01-31 | 2026-01-31 13:20 | 2026-02-01 | 2026-01-31 13:22 | 2026-01-31 | 2026-01-31 13:27 |  |  | 2026-02-01 | 2026-01-31 13:29 | 2026-02-01 | 2026-01-31 13:30 | 2026-02-01 | 2026-01-31 13:31 | 2026-02-01 | 2026-01-31 13:31 |  |  |  |  | 2026-02-20 16:32 | 2026-02-22 | 2026-02-22 15:34 | 2026-02-25 | 2026-02-23 11:34 | 2026-02-24 | 2026-03-04 12:07 | 2026-02-23 | 2026-03-04 15:21 | 2026-03-04 | 2026-03-04 15:22 | 2026-03-12 | 2026-03-11 17:17 |  |  | 2026-03-12 | 2026-03-11 19:19 | 2026-03-13 | 2026-03-11 19:19 | 2026-03-12 | 2026-03-11 19:22 |  |  |  |  | 2026-02-19 | 2026-02-20 16:31 | 2026-02-02 | 2026-01-31 13:14 | Unknown | 2026-01-14 | 2026-01-31 13:12 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | 2026-03-08 22:05:13 +0530 | Savita Parab | Execution: site is ready to dispatch the material waiting for material delivery | 2026-03-01 19:20:07 +0530 | Savita Parab | Execution: site is ready to dispatch the material | 2026-02-22 20:45:11 +0530 | Savita Parab | Execution: site is ready to dispatch the material
18051 | Sub Project |  | Terence Rodriguez | Kalpatru Bliss | MUM - GOR | Yes | Shreya Sonavane | Reshma Melanta | Shahid Chougley |  |  | Faizal Shaikh | Rizwan Mistry |  |  |  | Active | Preproduction | Hoto | 743717 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 446230 | 297486.8 |  |  | 2026-01-15 | 2026-02-18 18:15 | 2026-01-15 | 2026-02-18 18:16 | 2026-02-20 | 2026-02-18 18:16 | 2026-02-20 | 2026-02-18 18:18 | 2026-02-19 | 2026-02-18 18:19 | 2026-02-19 | 2026-02-18 18:19 | 2026-02-18 | 2026-02-18 18:16 | 2026-02-19 | 2026-02-18 18:17 | 2026-02-18 | 2026-02-18 18:17 | 2026-02-19 | 2026-02-18 18:17 | 2026-02-18 | 2026-02-18 18:20 | 2026-02-21 | 2026-02-18 18:20 | 2026-02-18 | 2026-02-18 18:20 | 2026-02-14 | 2026-02-18 18:15 | 2026-02-22 | 2026-02-25 12:22 |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-02-19 | 2026-02-18 18:17 | Unknown | 2026-01-14 | 2026-02-18 18:15 | 0 | 0 | 0 | 0 | 0 | 0 | 630268 | 113448
18052 | Turnkey | Dec'25 | Sam Scaria | gina shalom | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [5 empty] | Ankur Kumar |  | Active | Prospect | 10% Payment | 812717 | 9999 | 812717 | 0 | 0 | 112 | 0 | 71273 | 162543 | 287864 | 281038 |  |  | 2026-01-16 | 2026-01-15 12:38 | 2026-01-15 | 2026-01-16 15:31 | 2026-03-27 | 2026-03-25 17:50 | 2026-04-06 |  | 2026-04-09 |  | 2026-04-12 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-04-30 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-30 |  | 2026-03-28 |  | Unknown | 2026-01-15 | 2026-01-15 12:08 | 688743 | 123973 | 0 | 0 | 0 | 0 | 688743 | 123973 | 2026-04-28 19:02:13 +0530 | Losii Athisa | Some Image was uploaded | 2026-01-15 13:45:38 +0530 | Keerthan M | DCM: Sam Scaria 3BHK 5 Ppl Renovation Foyer - Tall unit space for shoe, newspaper, CricketÂ bat. - Hide the DB box - wall detailing opposite to main-door Living - TV unit wall highlight - TV back panel - sofa behind wall highlight(wainscoting) - False ceiling in common area - Curtains Kitchen - Entrance panel 18mm. MBR - Minimal False ceiling - Wall detailing - Storage for dresser - top storage for Study. - Bottom storage near W/B for laundry basket Wash basin - Beautification KBR - Study table with storage. - cot need to convert- 2 single beds. Toilet (Both) - wall storage. | 2026-01-15 12:36:49 +0530 | Ankur Kumar | Design Fees:
18053 | Turnkey | Dec'25 | Denzil | Sattva Gold Summit | BNG - HRBR | Yes | Salpriyan Pm | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Harshit Choudhary | Saddam Hussain Z M |  | Janvi Nagdeo | Abdul Shafeen | Active | Preproduction | Hoto | 1859040 | 452369 | 1827707 | 1859040 | 0 | 1 | 59 | 0 | 0 | 724037 | 682634.4 |  |  | 2026-01-16 | 2026-01-16 15:25 | 2026-01-23 | 2026-01-23 11:52 | 2026-01-25 | 2026-01-25 19:30 | 2026-04-19 | 2026-04-19 19:40 | 2026-04-27 | 2026-04-27 18:59 |  |  | 2026-01-25 | 2026-01-27 16:55 | 2026-01-26 | 2026-01-28 10:10 | 2026-01-28 | 2026-01-30 12:19 | 2026-02-15 | 2026-02-15 19:21 | 2026-04-27 | 2026-04-27 20:56 | 2026-04-30 | 2026-04-27 21:09 | 2026-05-07 | 2026-04-25 | 2026-07-14 | 2026-07-05 14:23 | 2026-07-06 | 2026-07-05 14:24 |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-18 |  | 2026-07-18 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-18 |  | 2026-03-05 | 2026-04-19 19:33 | Site is RTMI | 2026-01-15 | 2026-01-15 12:33 | 1548904 | 278802 | 1908617.0634 | 329345 | 0 | 0 | 1908617.0634 | 329345 | 2026-07-14 18:39:11 +0530 | Salpriyan Pm |  | 2026-07-12 16:44:43 +0530 | Rajeshwari S | CM is done. PKO is expected to complete by July 2026 | 2026-06-16 23:36:10 +0530 | Rajeshwari S | Some Image was uploaded
18054 | Turnkey | Dec'25 | Abhijit hota | Prestige Meridian Park | BNG - HSR | Yes | Priyanka Mathur | Akshay Ds | Kowshik |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Nidhi Shaw | Sunil Kumar S M | Completed | Complete | Completed | 1875688 | 1875688 | 1955156 | 1833870 | 1875688 | 6 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-01-16 | 2026-01-15 12:38 | 2026-01-24 | 2026-01-24 10:40 | 2026-02-11 | 2026-02-11 12:17 | 2026-03-13 | 2026-03-13 19:11 | 2026-03-13 | 2026-03-13 19:27 | 2026-03-13 | 2026-03-13 19:41 | 2026-02-11 | 2026-02-12 11:49 | 2026-02-12 | 2026-02-12 14:27 | 2026-02-12 | 2026-02-14 15:43 | 2026-02-20 | 2026-02-20 16:22 | 2026-03-13 | 2026-03-13 20:12 | 2026-03-16 | 2026-03-14 18:51 | 2026-03-16 | 2026-03-14 18:43 | 2026-03-23 | 2026-03-21 18:03 | 2026-03-22 | 2026-03-21 19:38 |  |  | 2026-03-31 | 2026-03-31 18:27 | 2026-03-31 | 2026-03-31 22:12 | 2026-04-03 | 2026-03-31 23:43 | 2026-03-31 | 2026-04-11 14:18 |  |  |  |  | 2026-04-14 16:55 | 2026-04-24 | 2026-04-25 21:34 | 2026-05-06 | 2026-05-06 17:21 | 2026-05-11 | 2026-05-06 18:21 | 2026-05-06 | 2026-05-07 15:37 | 2026-05-07 | 2026-05-08 11:43 | 2026-05-09 | 2026-05-13 11:30 |  |  | 2026-06-12 | 2026-06-13 09:30 | 2026-06-15 | 2026-06-13 17:10 | 2026-06-16 | 2026-06-13 20:15 |  |  |  |  | 2026-04-18 | 2026-04-14 16:54 | 2026-03-04 | 2026-03-12 10:53 | Site is RTMI | 2026-01-15 | 2026-01-15 12:36 | 1656911 | 298244 | 1927934.3384 | 325505 | 2015417.7664 | 331884 | 2015417.7664 | 331884 | 2026-07-06 15:38:07 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-07-01 18:10:44 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-05-11 08:16:09 +0530 | Ranjith Kumar | Hettich Shutter Handles & Knobs Metal Fab Lights Beading Glass & Mirrors Flat Strips Wallpapers Wallpapers Beading Appliances Counter Top
18055 | Turnkey | Dec'25 | AKSHAY SHETTI | LODHA UPPER THANE | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Saloni Chawan |  | Hold | Preproduction | Site Readiness 1 | 1658581 | 498064 | 1599230 | 1658581 | 0 | 2 | 136 | 0 | 0 | 512587 | 647929.6 |  |  | 2026-01-16 | 2026-01-15 18:07 | 2026-02-03 | 2026-02-03 11:07 | 2026-02-05 | 2026-02-03 11:48 | 2026-03-07 | 2026-02-26 12:22 | 2026-03-10 | 2026-02-26 12:24 |  |  | 2026-02-03 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-03 11:52 | 2026-02-03 | 2026-02-03 13:21 | 2026-02-07 | 2026-02-07 18:55 | 2026-02-27 | 2026-02-27 19:08 | 2026-02-27 | 2026-02-27 19:24 | 2026-03-02 | 2026-02-27 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-15 |  | 2026-08-15 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-15 |  | 2026-02-08 | 2026-02-26 12:21 | Site is RTMI | 2026-01-15 | 2026-01-15 14:11 | 1833329.0525 | 309543 | 1886965.7594 | 318597 | 0 | 0 | 1886965.7594 | 318597 | 2026-07-14 12:55:46 +0530 | Shraddha Pansare |  | 2026-05-07 19:24:06 +0530 | Sneha Kadam | RNR | 2026-04-02 12:40:56 +0530 | Shraddha Pansare | Some Image was uploaded
18056 | Turnkey | Dec'25 | Hanni David | Villa Maria | BNG - HRBR | Yes | Keerthan M | Rajeshwari S | Yogesh Patidar | [7 empty] | Active | Prospect | 10% Payment | 1974860 | 9999 | 0 | 0 | 0 | 112 | 0 | 187487 | 394972 | 625745 | 756657.2 |  |  | 2026-01-16 | 2026-01-15 19:51 | 2026-01-29 | 2026-02-09 18:41 | 2026-03-27 | 2026-03-25 17:47 | 2026-04-06 |  | 2026-04-09 |  | 2026-04-12 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-04-12 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-30 |  | 2026-04-30 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-30 |  | 2026-03-28 |  | Unknown | 2026-01-15 | 2026-01-15 19:49 | 0 | 0 | 0 | 0 | 0 | 0 | 1673610 | 301249 | 2026-01-29 13:26:44 +0530 | Chandini Nj | Possession - Ready to move BudgetÂ Â Â -10L Apartment- Villa maria Theme- JEPANDI Work profile - Travel field How many people are going to stay - 5 peoples and husband wife, 2kids (boys (7 and 4 age))and mom Purpose (Rental/Own) -OWN PURPOSEÂ Deeper understanding (Usual hobbies): Play area, book area Living room - TV unit, sofa back wall Dining area - as per reference images, 6 seater dining table Living area- UPS provision. Kitchen - Base unit , wall unit, loft,Â Master bedroom - Hinged wardrobe with loft and study unit bed.Â Bedroom 1 - Hinged wardrobe with loft and bed bedroom 2 - Hinge wardrobe with loft, Study unit and bed. Vanities for the washrooms. Bedroom 1 balcony - WASHING MACHINEÂ Mbr entrance - Base unit. Wooden flooring entire house | 2026-01-29 13:26:15 +0530 | Chandini Nj | Possession - Ready to move BudgetÂ Â Â -10L Apartment- Villa maria Theme- JEPANDI Work profile - Travel field How many people are going to stay - 5 peoples and husband wife, 2kids (boys (7 and 4 age))and mom Purpose (Rental/Own) -OWN PURPOSEÂ Deeper understanding (Usual hobbies): Play area, book area Living room - TV unit, sofa back wall Dining area - as per reference images, 6 seater dining table Living area- UPS provision. Kitchen - Base unit , wall unit, loft,Â Master bedroom - Hinged wardrobe with loft and study unit bed.Â Bedroom 1 - Hinged wardrobe with loft and bed bedroom 2 - Hinge wardrobe with loft, Study unit and bed. Vanities for the washrooms. Bedroom 1 balcony - WASHING MACHINEÂ Mbr entrance - Base unit.
18057 | Turnkey | Dec'25 | Rajeev Nair | L&T Elixir Reserve | MUM - GOR | Yes | Pratima Kajwe |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | CDP Due | 2186504 | 9999 | 0 | 0 | 0 | 179 | 0 | 208651 | 437301 | 708899 | 821653.6 |  |  | 2026-01-16 | 2026-01-15 17:34 | 2026-01-17 | 2026-01-17 13:32 | 2026-01-23 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-02-13 |  | 2026-02-17 |  | 2026-02-18 |  |  |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-28 |  | 2026-02-28 | [6 empty] | 2026-03-06 |  | 2026-03-15 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-18 |  |  |  | 2026-04-09 |  | 2026-04-11 |  | 2026-04-12 | [5 empty] | 2026-02-28 |  | 2026-01-26 |  | Unknown | 2026-01-15 | 2026-01-15 17:33 | 0 | 0 | 0 | 0 | 0 | 0 | 1852969 | 333534 | 2026-02-23 19:06:23 +0530 | Umang Shah | Some Image was uploaded
18058 | Turnkey | Dec'25 | Pradip Kale | Raymond Tenx Habitat | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Tanveer Patel | Akshat Shrivastava | Murali S |  | Shailendra Mishra | Active | Installation | Execution | 1049735 | 1053050 | 1142322 | 1073844 | 1041914 | 11 | 64 | 0 | 0 | 0 | 0 |  |  | 2026-01-16 | 2026-01-15 17:47 | 2026-01-21 | 2026-01-21 12:12 | 2026-01-25 | 2026-01-25 11:07 | [6 empty] | 2026-01-25 | 2026-01-28 11:06 | 2026-01-26 | 2026-01-28 11:06 | 2026-01-28 | 2026-01-30 11:57 | 2026-04-22 | 2026-03-26 15:01 | 2026-05-19 | 2026-05-19 14:35 | 2026-06-07 | 2026-05-19 15:23 | 2026-06-07 | 2026-05-17 | 2026-05-22 | 2026-05-22 18:23 | 2026-05-23 | 2026-05-22 18:27 |  |  | 2026-05-24 | 2026-05-26 11:50 | 2026-05-26 | 2026-05-26 17:11 | 2026-05-29 | 2026-05-26 17:49 | 2026-05-26 | 2026-05-26 19:46 |  |  |  |  | 2026-05-28 17:48 | 2026-06-05 | 2026-06-05 21:33 | 2026-06-30 | 2026-06-28 20:07 | 2026-06-24 | 2026-06-21 14:05 | 2026-06-28 | 2026-07-01 16:31 | 2026-06-30 | 2026-07-04 10:19 | 2026-07-06 | 2026-07-11 11:50 |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-24 | [5 empty] | 2026-05-28 | 2026-05-28 17:47 | 2026-05-20 | 2026-05-17 10:34 | Site is RTMI | 2026-01-15 | 2026-01-15 17:41 | 968069 | 174252 | 1081866.162 | 186688 | 1053638.8385 | 181817 | 1062334.5385 | 183010 | 2026-06-23 00:45:50 +0530 | Tanveer Patel | Procurement: Floor Covering work will be done once received keyFurniture will be ready for dispatched by 25th- 27th June. | 2026-06-15 23:59:29 +0530 | Tanveer Patel | Procurement: Key handover pendingMaterial will dispatch once work completion confirmation received from cx | 2026-06-11 10:50:24 +0530 | Tanveer Patel | Procurement: Key handover pendingMaterial will dispatch once work completion confirmation received from cx
18059 | Turnkey | Dec'25 | ES Jobs | Kalpataru Immensa | MUM - Thane | Yes | Rachna Abhyankar | Anil Jagtap | Anil Kuwar | [5 empty] | Vandana Preet |  | Active | Design | Design Finalization | 1530347 | 195499 | 1945160 | 0 | 0 | 155 | 0 | 0 | 263605 | 470308 | 600935.2 |  |  | 2026-01-16 | 2026-01-15 18:40 | 2026-01-26 | 2026-01-26 19:47 | 2026-02-01 | 2026-01-28 13:32 | 2026-03-29 | 2026-03-29 15:14 | 2026-03-29 | 2026-03-29 15:16 | 2027-12-12 |  | 2026-01-28 | 2026-01-31 05:30 | 2026-01-29 | 2026-02-05 14:20 | 2026-02-05 | 2026-02-10 16:42 | 2026-02-28 | 2026-02-28 17:34 | 2027-12-12 |  | 2027-12-15 |  | 2027-12-15 |  | 2027-12-19 |  | 2027-12-20 |  |  |  | 2027-12-26 |  | 2027-12-27 |  | 2027-12-30 |  | 2027-12-30 | [6 empty] | 2028-01-05 |  | 2028-01-14 |  | 2028-01-13 |  | 2028-01-14 |  | 2028-01-15 |  | 2028-01-17 |  |  |  | 2028-02-08 |  | 2028-02-10 |  | 2028-02-11 | [5 empty] | 2027-12-30 |  | 2026-04-08 | 2026-03-29 15:04 | Site is RTMI | 2026-01-15 | 2026-01-15 18:01 | 1648441 | 296719 | 0 | 0 | 0 | 0 | 1587555.8519 | 263951 | 2026-05-28 18:40:13 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-15 10:58:28 +0530 | Anil Jagtap | Customer doesn't want to continue with Bonito they started their tier with another vendor. | 2026-05-07 19:51:49 +0530 | Rachna Abhyankar | Some Image was uploaded
18060 | Turnkey | Dec'25 | Parvinder Bedi | Prestige - Siesta | MUM - Thane | Yes | Pooja Nakul Sharma | [7 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 2384577 | 9999 | 0 | 0 | 0 | 181 | 0 | 228459 | 476915 | 758833 | 910371.2 |  |  | 2026-01-16 | 2026-01-15 18:38 | 2026-01-16 |  | 2026-01-24 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-15 | 2026-01-15 18:03 | 0 | 0 | 0 | 0 | 0 | 0 | 2020828 | 363749 | 2026-03-24 15:30:00 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-01-20 13:35:33 +0530 | Ritika Rathod | DCM: Mr. BediÂ 3bhk - unit siesta a 3403 Family membersÂ Husband + wife + pet + son - 19 year oldÂ Â More open spacesÂ Safety & main doorÂ some panelingÂ Foyer area a small shoe rack - niche - video door phoneÂ Mc b is shifted and concealed in the new wall - mcb should not be seenÂ new wiring is doneÂ Platform is exchangedÂ glass sliding doorÂ semi modular base wall & loftÂ ApplianceÂ air fryer + mixerÂ Â aquaÂ platform - whiteÂ full body 15 mm tilesÂ chimney - without exhaustÂ duct & kitchen door is not a partÂ kitchen has a sliding window in the utilityÂ 44 inch space kept for fridgeÂ UtilityÂ sink and machine outsideÂ open kitchen conceptÂ will have ONLY base unit near the dining area . Theme base - bar chair/ breakfast nookÂ Onyx - highlighted - breakfast table . Dining table - compact - 2 seaterÂ crockery unit - smallÂ ac pipe is done - and is conceal on the same wallÂ Tv unitÂ sleek and subtleÂ Planning to have a home theatreÂ 3 seater + one single rotating chairÂ common bathroomÂ vanityÂ window is packed in the bathroomÂ storage on both sidesÂ above Wc 6 - 8 inchÂ Bedroom 2- study room - 1 personÂ husband - work from homeÂ planning to put a PC screenÂ sofa cum bed - cozy cornerÂ puja unitÂ if we have space - we can plan storageÂ Master bedroomÂ King size bedÂ wardrobe & loft - hanging clothesÂ Â side tableÂ Full size mirrorÂ double curtainsÂ Tv to planned - may beÂ Picture ( family photo wall ) Vanity in bathroomÂ shelfs to addÂ glass partition is addedÂ duct area can be utilize for some storage . bedroom 1 - sons bedroomÂ niche wardrobeÂ profile in pop ceilingÂ wooden floorÂ deck leveling is doneÂ same tile is there in the balconyÂ double bedÂ studyÂ tvÂ side tableÂ football is something what he likesÂ theme can be plannedÂ balcony ideas to be given what best can be done buddha statue with water flowing . vertical garden Painting work - to minimizeÂ Phase 1Â Phase 2Â Budget -Â 25 - 26th Jan balcony highlight wall is the bigger wallÂ refuge area is upper floorÂ Wall height 11 feet .Â Â Â False ceiling / electricals / civil / doneÂ wooden tile concept for all roomsÂ
18061 | Turnkey | Dec'25 | sanjeev srinivas | Suraksha Springs | BNG - HSR | Yes | Priyanka Inchoor | Akshay Ds | Kowshik |  | Parvez Syed | Sachin I Betageri | Ranjith Kumar | Murali S | Nidhi Shaw | Affaan Abdulla | Active | Installation | Execution | 853662 | 853662 | 1003193 | 871749 | 853662 | 12 | 49 | 0 | 0 | 0 | 0 |  |  | 2026-01-16 | 2026-01-15 18:28 | 2026-01-23 | 2026-01-23 19:31 | 2026-01-23 | 2026-01-24 10:51 | 2026-03-15 | 2026-03-10 11:38 | 2026-03-24 | 2026-03-24 16:56 |  |  | 2026-01-24 | 2026-01-25 20:48 | 2026-01-25 | 2026-01-25 20:50 | 2026-01-25 | 2026-02-19 17:15 | 2026-02-20 | 2026-02-20 16:24 | 2026-03-25 | 2026-03-25 20:51 | 2026-03-28 | 2026-03-26 10:49 | 2026-03-19 | 2026-03-23 | 2026-05-17 | 2026-05-17 19:06 | 2026-05-18 | 2026-05-17 19:19 |  |  | 2026-05-26 | 2026-05-27 12:06 | 2026-05-27 | 2026-05-27 19:17 | 2026-05-30 | 2026-05-27 23:45 | 2026-05-27 | 2026-05-30 18:43 |  |  |  |  | 2026-06-03 10:24 | 2026-06-20 | 2026-06-19 20:17 | 2026-06-25 | 2026-06-23 18:19 | 2026-06-24 | 2026-06-30 19:07 | 2026-06-23 | 2026-07-03 16:09 | 2026-07-03 | 2026-07-03 19:55 | 2026-07-05 | 2026-07-09 10:09 |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-05-27 | 2026-06-02 16:57 | 2026-03-01 | 2026-03-06 18:17 | Site is RTMI | 2026-01-15 | 2026-01-15 18:23 | 850164 | 153029 | 1008608.711 | 158148 | 991915.025 | 155389 | 991915.025 | 155389 | 2026-07-02 10:32:41 +0530 | Ranjith Kumar | Dispatch Due: | 2026-07-01 10:39:54 +0530 | Ranjith Kumar | Dispatch Due: | 2026-06-05 16:26:00 +0530 | Ranjith Kumar | Bonito Side - Floor Covering Only Cx Side - Electrical.
18062 | Turnkey | Dec'25 | Nitheesh Raj | Prestige City sarjapur | BNG - HSR | Yes | Manoj Kumar R | Abhinandan K S | Kowshik |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Chanakya Panigrahi | Sunil Kumar S M | Completed | Complete | Completed | 1014937 | 1014937 | 1190352 | 1020656 | 1014937 | 20 | 18 | 0 | 0 | 0 | 0 |  |  | 2026-01-16 | 2026-01-15 18:37 | 2026-01-16 | 2026-01-16 11:04 | 2026-01-24 | 2026-01-25 12:22 | 2026-02-26 | 2026-02-26 11:33 | 2026-02-27 | 2026-02-26 11:59 |  |  | 2026-01-25 | 2026-01-27 15:18 | 2026-01-26 | 2026-01-27 15:30 | 2026-01-27 | 2026-01-28 15:24 | 2026-02-07 | 2026-02-07 19:40 | 2026-02-26 | 2026-02-26 17:25 | 2026-03-01 | 2026-02-27 13:46 | 2026-03-01 | 2026-02-26 17:35 | 2026-03-09 | 2026-03-08 14:35 | 2026-03-09 | 2026-03-08 14:35 |  |  | 2026-03-15 | 2026-03-14 16:42 | 2026-03-15 | 2026-03-15 19:35 | 2026-03-18 | 2026-03-15 20:50 | 2026-03-15 | 2026-03-20 19:22 |  |  |  |  | 2026-04-03 19:09 | 2026-04-17 | 2026-04-16 18:41 | 2026-05-16 | 2026-05-14 18:34 | 2026-05-10 | 2026-05-05 14:25 | 2026-05-14 | 2026-05-14 18:40 | 2026-05-14 | 2026-05-15 10:54 | 2026-05-21 | 2026-05-20 12:01 |  |  | 2026-06-06 | 2026-06-07 22:42 | 2026-06-08 | 2026-06-08 13:12 | 2026-06-09 | 2026-06-08 19:11 |  |  |  |  | 2026-04-10 | 2026-04-03 19:08 | 2026-02-08 | 2026-02-26 11:26 | Site is RTMI | 2026-01-15 | 2026-01-15 18:36 | 1008773 | 181579 | 1118438.6841 | 184676 | 1163999.4207 | 183804 | 1163999.4207 | 183804 | 2026-06-08 19:13:20 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-05-18 17:38:51 +0530 | Ranjith Kumar | Flat Strips Louvers / Rafters Wallpapers Beading Hettich Shutter Appliances Metal Fab | 2026-04-20 11:53:23 +0530 | Ranjith Kumar | Procurement:
18063 | Turnkey | Dec'25 | Shatrugna Kalavar | Vinee Garden | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble |  |  |  | Mrunali Mitkari | Aakash Gaikwad | Lost | Preproduction | 2D | 2043400 | 203680 | 1019950 | 2043400 | 0 | 61 | 7 | 0 | 0 | 1029284 | 810436.4 |  |  | 2026-01-16 | 2026-01-21 17:38 | 2026-02-03 | 2026-02-03 16:15 | 2026-02-11 | 2026-02-11 13:50 | 2026-03-26 | 2026-03-26 16:19 | 2026-05-07 | 2026-05-06 19:15 | 2026-05-13 | 2026-05-13 14:01 | 2026-02-09 | 2026-02-10 19:04 | 2026-02-12 | 2026-02-12 12:12 | 2026-02-12 | 2026-02-20 12:08 | 2026-03-01 | 2026-03-01 13:33 | 2026-05-13 | 2026-05-13 15:21 | 2026-05-16 | 2026-05-13 17:36 | 2026-05-16 | 2026-05-13 15:53 | 2026-05-17 | 2026-05-15 13:05 | 2026-05-16 | 2026-05-16 21:08 |  |  | 2026-05-22 |  | 2026-05-23 |  | 2026-06-20 |  | 2026-06-20 | [6 empty] | 2026-06-26 |  | 2026-07-05 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-06-20 |  | 2026-03-02 | 2026-03-25 16:07 | Site is RTMI | 2026-01-15 | 2026-01-17 10:48 | 1113874.1255 | 178467 | 2164858.273 | 357467 | 0 | 0 | 2164858.273 | 357467 | 2026-06-09 18:21:41 +0530 | Reshma Melanta | RCAProject OverviewPID: 18063Client Name: Shatrugna KalavarProject Type: 2BHK Renovation (Civil, Modulars, Paint, False Ceiling, Electricals)Project Value: 10,19,951NET Date: 11 February 2026Initial Commitment: A maximum budget escalation cap of 5% on the initial BOQ (Bill of Quantities). Additionally, a Semi-Modular Kitchen Cabinet was committed, though the actual requirement/delivery is Fully Modular. The Issue & Timeline1. Initial Scoping & Commitments (11 Feb 2026)The project was booked as a comprehensive 2BHK renovation. Initial commitments included full-house flooring (excluding washrooms), false ceiling, electrical, and modular works with no chance of quote getting higher. 2. Cross-Measurement & Estimation Variance (14 May 2026)Following the mandatory site cross-measurements, significant scoping and estimation gaps were identified: Electrical & False Ceiling: Both categories were heavily under-quoted during the initial pitching phase.Scope Discrepancy: The full-house flooring (civil work) and the transition from semi-modular to fully modular kitchen cabinets dramatically altered the cost dynamics.Result: The final estimation increased significantly past the committed 5% threshold, causing a severe budget mismatch that the client is fundamentally unaligned with. 3. Escalation & Client Meet (6 June 2026)The client visited the Andheri Experience Center (EC) to address the budget blowout. Client Position: Their absolute upper limit for the entire project remains firmly between 10 Lakhs and 11 Lakhs. Current Status: The client refuses to approve the revised estimation without a correction or an commercial discount to bring it back within their expected budget window. | 2026-06-09 13:08:19 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-28 15:50:56 +0530 | Reshma Melanta | MEETING ALIGN ALONG WITH THE DESIGNER AND AVINASH 5:00 PM
18064 | Turnkey | Dec'25 | Indranil Sengupta | Alchemy one by Aratt | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [7 empty] | Active | Prospect | 10% Payment | 1783194 | 9999 | 1783194 | 0 | 0 | 168 | 0 | 168320 | 356639 | 543436 | 704800 |  |  | 2026-01-16 | 2026-01-15 19:56 | 2026-01-23 | 2026-01-23 18:34 | 2026-01-28 | 2026-01-28 16:53 | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-15 | 2026-01-15 19:55 | 1511181 | 272012 | 0 | 0 | 0 | 0 | 1511181 | 272012 | 2026-01-23 18:20:47 +0530 | Priyanka Gs | Some Image was uploaded
18066 | Turnkey | Dec'25 | Rajneesh Chaube | LODHA AMARA | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  | Krutika Date | Asif Shaikh | Akshat Shrivastava | Murali S | Saloni Chawan | Prasad Bhivaji Hande | Active | Installation | Execution | 800540 | 800540 | 1309572 | 881265 | 800540 | 23 | 44 | 0 | 0 | 0 | 0 |  |  | 2026-01-16 | 2026-01-16 16:19 | 2026-01-28 | 2026-01-28 13:41 | 2026-01-29 | 2026-01-29 12:50 | 2026-03-07 | 2026-02-27 12:17 | 2026-03-10 | 2026-02-27 12:27 | 2026-04-16 | 2026-03-06 15:40 | 2026-01-29 | 2026-01-29 16:15 | 2026-01-30 | 2026-01-29 16:36 | 2026-01-29 | 2026-01-30 11:07 | 2026-02-06 | 2026-02-06 13:05 | 2026-03-12 | 2026-03-13 11:58 | 2026-04-19 | 2026-03-14 19:38 | 2026-04-19 | 2026-03-13 12:55 | 2026-05-03 | 2026-05-03 14:29 | 2026-05-04 | 2026-05-06 10:16 |  |  | 2026-05-06 | 2026-05-07 18:46 | 2026-05-10 | 2026-05-10 16:53 | 2026-05-13 | 2026-05-10 17:42 | 2026-05-10 | 2026-05-14 18:52 |  |  |  |  | 2026-05-15 22:04 | 2026-05-28 | 2026-05-27 19:52 | 2026-06-11 | 2026-06-17 09:49 | 2026-06-10 | 2026-06-15 18:09 | 2026-06-17 | 2026-06-20 23:40 | 2026-06-19 | 2026-06-22 12:57 | 2026-06-24 | 2026-07-02 18:15 |  |  | 2026-07-24 |  | 2026-06-25 |  | 2026-07-27 | [5 empty] | 2026-05-15 | 2026-05-15 22:03 | 2026-02-07 | 2026-02-26 14:41 | Site is Non-RTMI | 2026-01-15 | 2026-01-16 16:17 | 1402940.1344 | 222646 | 1007252.658 | 157311 | 878567.7453 | 137370 | 878567.7453 | 137370 | 2026-07-12 17:19:20 +0530 | Asif Shaikh | Execution : Modular End date - 15th July. Customer carpentry work - 20th July Glass shutter - 20th July Wallpaper - Post Cx painting work , Tentative ETA - 30th July. Metal fabrication - 20th July. Sofa - ETA awaited. DC- 21st July. QC - 22nd July. | 2026-07-02 11:47:02 +0530 | Asif Shaikh | Execution: Modular End date - 12th July. Customer carpentry work - 12th July. Glass shutter - 10th July. Wallpaper - Post Cx painting work , Tentative ETA - 30th July. Metal fabrication - 10th July. Sofa - ETA awaited. QC - 13th July. | 2026-06-28 19:13:00 +0530 | Asif Shaikh | Execution: Modular srtart date - 25th JuneModular end date - 10th July.Glass shutter , Mirror & glass shelf - 10th July.Custom carpentry work - 10th july.POP punning work - 10th July.Metal fabrication - 10th July.Oil Primer work - 15th July.Wallpaper - Cx dependency- Tentative - 25th July
18067 | Turnkey | Dec'25 | Dilip Chavan | The Baya Midtown | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Nilesh Patel | Rizwan Mistry |  | Harshaan Tiku | Sunil Poojary | Active | Preproduction | 2D | 1250165 | 316354 | 1409367 | 1233220 | 1250165 | 16 | 82 | 0 | 0 | 458198 | 475612.8 |  |  | 2026-01-16 | 2026-01-15 22:10 | 2026-01-21 | 2026-01-21 20:39 | 2026-01-31 | 2026-01-31 20:15 | 2026-03-19 | 2026-03-17 18:41 | 2026-03-29 | 2026-03-28 16:46 | 2026-04-01 | 2026-03-28 17:47 | 2026-01-31 | 2026-01-31 05:30 | 2026-02-01 | 2026-02-04 19:00 | 2026-02-04 | 2026-02-13 12:49 | 2026-02-20 | 2026-02-20 13:17 | 2026-03-28 | 2026-03-28 18:40 | 2026-03-31 | 2026-03-29 16:28 | 2026-03-31 | 2026-03-29 15:19 | 2026-06-24 | 2026-06-22 14:34 | 2026-06-23 | 2026-06-22 15:14 |  |  | 2026-06-25 | 2026-06-29 09:18 | 2026-07-06 |  | 2026-07-07 |  | 2026-07-07 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-08-15 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-07-07 |  | 2026-02-21 | 2026-03-17 16:19 | Site is RTMI | 2026-01-15 | 2026-01-15 22:07 | 1194379 | 214988 | 1334325.2658 | 210999 | 1303127.1342 | 213584 | 1303127.1342 | 213584 | 2026-06-27 15:23:21 +0530 | Saif Shaikh | Some Image was uploaded | 2026-05-15 15:38:52 +0530 | Vishakha Vaishnav | Cx said that he will update us tomorrow about the demolition work and then in next week we can plan for CM | 2026-05-15 15:34:32 +0530 | Reshma Melanta | Some Image was uploaded
18069 | Turnkey | Dec'25 | Darrshan Surresh B. | Oberoi Enigma | MUM - Thane | Yes | Pooja Nakul Sharma | [7 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 2359877 | 9999 | 0 | 0 | 0 | 180 | 0 | 225989 | 471975 | 799583 | 852330.8 |  |  | 2026-01-17 | 2026-01-16 16:23 | 2026-01-17 |  | 2026-01-21 |  | 2026-02-02 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-01-21 |  | 2026-01-22 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 | [6 empty] | 2026-03-04 |  | 2026-03-13 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-16 |  |  |  | 2026-04-07 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-02-26 |  | 2026-01-24 |  | Unknown | 2026-01-16 | 2026-01-16 16:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1999896 | 359981 | 2026-01-20 18:24:17 +0530 | Pooja Nakul Sharma | DCM: Mr BhindeÂ Oberoi EterniaÂ CA- 912 Sq ftÂ Poss- Mid feb 2026 Family- of 3. 9 yr old daughter. Vastu compliant White and pastels. 1. LR- Sofa 3+2, dining, 4 seater, Minimal Tv unit, crockery unit (optional), wallpapers, Traditional wallpaperÂ at the entrance. 2. To be modern contemporary with traditional touch.Â 3. Kitchen wall can be broken and made to an open kitchen with breakfast counter.Â 4. Kitchen- Base, wall, loft (only 1 side). All standard appliances (m/o).Â 5. Bedroom1- GBR- sofa cum bed, mandir and study, wardrobe with dresser. 6. Bedroom 2- Duaghters room.- Queen bed with storage, wardrobe, study, dresser. Lavender theme. 7. MBR- King bed, wardrobe, dresser, side tables.Â 8. Good lighting in washrooms.Â 9. Minimal false ceiling.Â 10. CDP- 25LÂ
18070 | Turnkey | Dec'25 | Manish | Brigade | BNG - HRBR | Yes |  | Rajeshwari S | [8 empty] | Active | Prospect | CDP Due | 2732603 | 9999 | 0 | 0 | 0 | 174 | 0 | 263261 | 546521 | 823991 | 1088831.6 |  |  | 2026-01-18 | 2026-01-21 15:33 | 2026-01-22 | 2026-01-22 16:40 | 2026-01-24 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-17 | 2026-01-19 18:34 | 0 | 0 | 0 | 0 | 0 | 0 | 2315765 | 416837 | 2026-01-18 17:15:46 +0530 | Yogesh Patidar | Part of RGM- Ms.Anu, Kushal, Yogesh Apartment - Brigade Metropolis Typology- 3.5BHK ( Renovation) Theme- Yet to be selected (Site RGM) Budge- 20-25L Existing furniture- Coffee table and Decors, swing People staying at Flat- 2 + 1 Kid(10Yrs) and Guest will be Often. Renovation Includes: Full house Flooring to be changed Bathroom Renovation Kitchen-Door and window door change Living- Balcony extension PBR- Balcony Extension Foyer - Shoe Rack for 30- 35Pairs Partition and Arch to be created opposite to Door Living area- TV unit Placement can be suggested either on Door wall/ Pooja wall and sofa suggestion to be given False ceiling Since he plays Football in common area, the decors needs to be aligned accordingly Sofa placement based on TV unit wall Pooja unit-Bigger free space to be planned in front of Pooja Room Pooja unit to have Door, Bells, internal storage with back panel either with CNC/Mantra Dinning- As we extending the Balcony door, bar unit to be planned, existing siwng to be aligned Storage for snacks on wall with base and bottom storage. Existing Dinning Table to reused Window to be changed and side wall to be covered Kitchen- New Kitchen to be planned with under sink RO and Granite and tiles. Window to be changed Big wider Fridge, Rolling shutter, Microwave. Ductless chimney, Mixer Double Bowl sink, loft to added where its necessary Utility: Tiles to be done on walls till full height Dishwasher, WM, sliding needs to be changed, tiles on wall sill Generator Unit and Storage Office Room Study for 1 person with bottom and top storage, space for Printer and 2 Desptop Single bed and maximum storage to be planned keep for toys, cricket bats, Tennis rackets MBR- Window seater, Dresser, Storage adjacent to seater and Loft Existing bed, False ceiling Wardrobe -Hinged PBR- Wardrobe placement to be changed and to be kept on other side of wall Balcony Extension Bed placement to be moved with king size bed Storage opposite to bed with foldable study table GBR/ Study Room Study table with base and top Single bed Single wardrobe Balcony to remain same Common Space- Vanity unit with Partition Base storage Bathroom- All Bathroom Changes with shower Partition
18071 | Sub Project |  | Prashant jagtap | Panache | MUM - Thane |  | Chaitali Sawant | Divya Rahangdale | Sneha Kadam |  |  | suraj kumar | Aditya Vikram | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-18 | 2026-01-23 15:16 | 2026-01-18 | 2026-01-23 15:16 | 2026-01-25 | 2026-01-23 15:16 | 2026-01-25 | 2026-01-23 15:18 | 2026-01-24 | 2026-01-23 15:18 | 2026-01-24 | 2026-01-23 15:19 | 2026-01-23 | 2026-01-23 15:16 | 2026-01-24 | 2026-01-23 15:16 | 2026-01-23 | 2026-01-23 15:17 | 2026-01-24 | 2026-01-23 15:17 | 2026-01-23 | 2026-01-23 15:19 | 2026-01-26 | 2026-01-23 15:20 | 2026-01-23 | 2026-01-23 15:20 | 2026-01-24 | 2026-01-23 15:20 | 2026-01-24 | 2026-01-23 15:21 |  |  | 2026-01-26 | 2026-01-23 15:21 | 2026-01-24 | 2026-01-23 15:29 | 2026-01-26 | 2026-01-23 15:23 | 2026-01-26 | 2026-01-23 15:30 |  |  |  |  | 2026-01-23 18:19 | 2026-01-25 | 2026-01-24 19:44 | 2026-02-12 | 2026-02-04 13:45 | 2026-02-05 | 2026-02-13 18:48 | 2026-02-04 | 2026-02-13 18:49 | 2026-02-13 | 2026-02-13 18:49 | 2026-02-09 | 2026-02-13 18:44 |  |  | 2026-02-15 | 2026-02-13 18:53 | 2026-02-15 | 2026-02-13 18:54 | 2026-02-13 | 2026-02-13 18:54 |  |  |  |  | 2026-01-23 | 2026-01-23 18:18 | 2026-01-24 | 2026-01-23 15:17 | Unknown | 2026-01-17 | 2026-01-23 15:16 | 0 | 0 | 0 | 0 | 66221.5 | 0 | 66221.5 | 0
18072 | Turnkey | Dec'25 | Neelabja Chakrabarty | Raymond GS | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Aryan Singh |  | Hold | Preproduction | Site Readiness 1 | 4175280 | 1251763 | 4458811 | 4175280 | 0 | 2 | 14 | 0 | 0 | 1485248 | 1438269.2 |  |  | 2026-01-18 | 2026-01-17 13:41 | 2026-02-18 | 2026-02-18 13:03 | 2026-03-26 | 2026-03-26 17:07 | 2026-06-10 | 2026-06-10 15:17 | 2026-06-10 | 2026-06-10 15:36 |  |  | 2026-03-26 | 2026-03-28 15:32 | 2026-03-27 | 2026-03-28 17:45 | 2026-03-28 | 2026-03-30 13:02 | 2026-04-03 | 2026-04-03 15:53 | 2026-06-27 | 2026-06-28 18:49 | 2026-07-01 | 2026-06-29 14:58 | 2026-07-01 | 2026-06-28 19:23 | 2026-10-14 |  | 2026-10-15 |  |  |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-25 |  | 2026-10-25 | [6 empty] | 2026-10-31 |  | 2026-11-09 |  | 2026-11-08 |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-12 |  |  |  | 2026-12-04 |  | 2026-12-06 |  | 2026-12-07 | [5 empty] | 2026-10-25 |  | 2026-07-01 | 2026-06-09 18:16 | Site is RTMI | 2026-01-17 | 2026-01-17 13:40 | 3778653 | 680157 | 4270750.7133 | 697924 | 0 | 0 | 4270750.7133 | 697924 | 2026-07-10 13:07:31 +0530 | Divya Rahangdale | CX will receive the possession by August. | 2026-07-02 14:18:30 +0530 | Divya Rahangdale | Hold | 2026-06-28 19:10:26 +0530 | Divya Rahangdale | Some Image was uploaded
18073 | Turnkey | Dec'25 | Pankaj Chougule | Raymond GS | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | CDP Due | 1850867 | 9999 | 0 | 0 | 0 | 166 | 0 | 175088 | 370173 | 555260 | 740346.8 |  |  | 2026-01-18 | 2026-01-17 13:53 | 2026-01-20 | 2026-01-30 23:43 | 2026-04-30 |  | 2026-05-12 |  | 2026-05-15 |  | 2026-05-18 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-18 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-25 |  | 2026-05-26 |  |  |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-05 |  | 2026-06-05 | [6 empty] | 2026-06-11 |  | 2026-06-20 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-23 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-06-05 |  | 2026-05-03 |  | Site is RTMI | 2026-01-17 | 2026-01-17 13:50 | 0 | 0 | 0 | 0 | 0 | 0 | 1568531 | 282335 | 2026-01-17 20:23:30 +0530 | Moksh Mehta | DCM: Client Name:- Pankaj Chougule Property:- Raymond by GS Possesion Date:- Apr'26 Sq Ft:- 1396 sqft No of Members : - Couple ( 40+) + Daughter (9) + Son (2) + Parents (70+) Budget :- 25-30L E to E Ent: Shoe Rack (25 - 30 Pairs) x 2 Nos inside and outside Wall Concepts.Console storage.Safety Door. Living Room :- TV Unit with Display unit3 Seater Sofa + 1 Chair + 2 Seater (7 - 8 people)Wall concepts. Dining Area :- Crockery Unit.8 Seater Square Dining Table. Wall Concepts. Kitchen :- Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos.All generic appliances. Master Bedroom :- Right side top Queen size Bed with StorageWardrobe with LoftSide tale with Storage & Dresser / Study cum side TableRecliner / Arm ChairAdditional Wardrobe space if Possible Kid's Bedroom :- below the master bedroom Bunk BedWardrobe with loftStudy Table with Storage x 2 nos in different area's Parent's Bedroom :- Near Entrance on the Left Queen size Bed above the bed storage to keep the phonesWardrobe with LoftDresser with Side TableTV Ledge Guest Bedroom:- Single wardrobe with Temple besides it Sofa cum BedAdditional Storage space Bathroom's Base Vanity Unit's for all Misc:- False CeilingPaintingElectrification | 2026-01-17 19:44:07 +0530 | Nishtha Valawalkar | Free Hob Chimney - 26th Jan offer | 2026-01-17 19:43:46 +0530 | Nishtha Valawalkar | Some Image was uploaded
18074 | Turnkey | Dec'25 | Satyendra Vishwakarma | Royal Heights | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | CDP Due | 1890926 | 9999 | 0 | 0 | 0 | 174 | 0 | 179094 | 378185 | 634034 | 689614.4 |  |  | 2026-01-18 | 2026-01-17 13:50 | 2026-01-22 | 2026-01-22 11:43 | 2026-01-24 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-17 | 2026-01-17 13:49 | 0 | 0 | 0 | 0 | 0 | 0 | 1602480 | 288446 | 2026-01-22 11:36:10 +0530 | Rutuja Kotwal | DCM: Mr.Â Satyendra Vishwakarma.Â Â 2BHK.Â Â 700Â sq.ft.Â Â MoveinÂ 4+2Â Â Husband ,Â wife, parents and 2 Kids- daughter 7yrs. And son 3 yrs.Â Â Profession Purchase managerÂ Design as perÂ vastuÂ Â Direction- Entering west.Â Â Living Room Â safetyÂ door,Â MandirÂ 2ft. With Storage, Crockery unitÂ withÂ Â 6Â seater diningÂ table.,Â sofa, TV unit,Â SwingÂ if possible, Shoe rack.Â KitchenÂ NeedÂ to make another platform. Need to check withÂ builderÂ whether he is giving the Granite or not.Â Â Base units, wallÂ unitsÂ andÂ Lofts .Â Â NeedÂ to check the fridge position.Â Â Parents bedroom Â Bed, Wardrobe with Lofts, Folding table.Â Â Master Bedroom-Â Bed 6X6 ,Â Wardrobe with Lofts, study table, DressingÂ tableÂ Â Budget 15 20 lakhs.Â Â CDP 24Â thÂ januaryÂ at 3pm.Â Â
18075 | Turnkey | Dec'25 | Gaurav Shah | Lodha divino | MUM - GOR | No Estimate | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 179 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-18 | 2026-01-17 14:10 | 2026-03-04 |  | 2027-03-16 |  | 2027-03-28 |  | 2027-03-31 |  | 2027-04-03 |  | 2027-03-16 |  | 2027-03-17 |  | 2027-03-17 |  | 2027-03-18 |  | 2027-04-03 |  | 2027-04-06 |  | 2027-04-06 |  | 2027-04-10 |  | 2027-04-11 |  |  |  | 2027-04-17 |  | 2027-04-18 |  | 2027-04-21 |  | 2027-04-21 | [6 empty] | 2027-04-27 |  | 2027-05-06 |  | 2027-05-05 |  | 2027-05-06 |  | 2027-05-07 |  | 2027-05-09 |  |  |  | 2027-05-31 |  | 2027-06-02 |  | 2027-06-03 | [5 empty] | 2027-04-21 |  | 2027-03-19 |  | Unknown | 2026-01-17 | 2026-01-17 14:04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18077 | Turnkey | Dec'25 | Abbas Chikani | LODHA AMARA | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Asif Shaikh | Aditya Vikram | Murali S | Prashant Panigrahi | Aakash Gaikwad | Active | Handover | Project Closure Pending | 1485755 | 1485755 | 1307036 | 1462219 | 1485755 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-18 | 2026-01-27 11:17 | 2026-01-28 | 2026-01-28 12:10 | 2026-01-29 | 2026-01-29 12:45 | 2026-02-12 | 2026-02-12 18:44 | 2026-02-21 | 2026-02-20 18:38 |  |  | 2026-01-27 | 2026-01-27 16:21 | 2026-01-31 | 2026-01-28 15:46 | 2026-01-30 | 2026-01-30 12:18 | 2026-02-11 | 2026-02-11 18:19 | 2026-02-20 | 2026-02-20 19:21 | 2026-02-23 | 2026-02-20 22:56 | 2026-02-23 | 2026-02-20 20:51 | 2026-02-25 | 2026-02-22 18:36 | 2026-02-23 | 2026-02-22 18:37 |  |  | 2026-02-25 | 2026-02-28 21:48 | 2026-03-05 | 2026-03-06 11:56 | 2026-03-09 | 2026-03-08 18:08 | 2026-03-08 | 2026-03-12 18:59 |  |  |  |  | 2026-03-14 18:20 | 2026-03-22 | 2026-03-22 10:43 | 2026-04-01 | 2026-03-31 16:25 | 2026-03-31 | 2026-03-31 20:42 | 2026-03-31 | 2026-04-17 17:11 | 2026-04-18 | 2026-04-20 17:05 | 2026-05-02 | 2026-05-23 11:34 |  |  | 2026-06-29 | 2026-06-29 19:13 | 2026-07-01 | 2026-06-29 19:48 | 2026-07-02 | 2026-06-29 20:00 |  |  |  |  | 2026-03-08 | 2026-03-14 13:51 | 2026-02-12 | 2026-02-12 18:31 | Site is RTMI | 2026-01-17 | 2026-01-20 20:09 | 1375689.248 | 222259 | 1586448.8728 | 256609 | 1605468.3541 | 260199 | 1605468.3541 | 260199 | 2026-07-10 11:02:01 +0530 | Asif Shaikh |  | 2026-07-08 18:02:08 +0530 | Asif Shaikh | Project Closure Pending: Final painting work -- Vendor transferring in process -- Housmatic is asssigned - PO under Process. Refund For sofa requested. Modular Snag - In cost Approval -- Tentative ETA - 20th July | 2026-06-29 16:51:26 +0530 | Asif Shaikh | Execution: QC - 29th June Post Customer Move in work Sofa Delivery - 5th June.Final painting work for full house -- Vendor PO is under process. SQC / Fitout Clousure : Filler , Skirting -- ETA - 20th July.
18079 | Turnkey | Dec'25 | Chetan Mishra | Adarsh Park Heights | BNG - HSR | Yes | Shefali | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | CDP Due | 1822965 | 9999 | 0 | 0 | 0 | 176 | 0 | 172298 | 364593 | 547736 | 728339.6 |  |  | 2026-01-18 | 2026-01-17 17:33 | 2026-01-20 | 2026-01-20 19:41 | 2026-01-25 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-19 |  | 2026-02-20 |  |  |  | 2026-02-26 |  | 2026-02-27 |  | 2026-03-02 |  | 2026-03-02 | [6 empty] | 2026-03-08 |  | 2026-03-17 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-20 |  |  |  | 2026-04-11 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-03-02 |  | 2026-01-28 |  | Unknown | 2026-01-17 | 2026-01-17 17:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1544886 | 278079
18080 | Turnkey | Dec'25 | Jyotsna Soni Soni | Lodha NCP | MUM - GOR | Yes | Pratima Kajwe |  | Shraddha Badgujar | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 4458664 | 9999 | 4458664 | 0 | 0 | 148 | 0 | 435867 | 891733 | 1461503 | 1659562 |  |  | 2026-01-18 | 2026-01-30 13:08 | 2026-02-17 | 2026-02-17 11:44 | 2026-02-23 | 2026-02-17 18:52 | 2026-03-01 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-14 |  | 2026-03-15 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-25 |  | 2026-03-25 | [6 empty] | 2026-03-31 |  | 2026-04-09 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-12 |  |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | 2026-03-25 |  | 2026-02-20 |  | Unknown | 2026-01-17 | 2026-01-30 13:07 | 3778528 | 680135 | 0 | 0 | 0 | 0 | 3778528 | 680135 | 2026-02-07 13:54:38 +0530 | Pratima Kajwe | DCM: L shaped kitchen or parallel shaped. Slightly bigger with retractable door with utility space to be taken inside and servant quarters to be considered as pantry or utility dry area. 6 seater dining. Crockery to be considered in sky garden section and inside (2 options). Bedroom 1 (guest room) Murphy bed with studio room for utility study and music room. Balcony to be taken inside. Bedroom 2 (parent's room) changing position of bathroom of top right corner and keep it adjacent to the guest room bathroom. Mandir to be considered in this room. Wardrobe bigger in length. King size bed to be considered. Bedroom 3 (master bedroom) Remove bathtub from the master bedroom walk -in closet and king size bed. Storage space in balcony. Drying space to be checked out and space for folding work out set-up.
18082 | Turnkey | Dec'25 | Prajakta Vaidya | bay midtowndadar | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | [5 empty] | Rashmita Das |  | Active | Design | Design Finalization | 1316324 | 164921 | 1579382 | 0 | 0 | 121 | 25 | 0 | 229976 | 402063 | 519363.6 |  |  | 2026-01-18 | 2026-01-18 10:53 | 2026-01-27 | 2026-01-27 11:23 | 2026-02-02 | 2026-01-27 11:28 | 2026-04-07 | 2026-04-07 11:27 | 2026-04-13 | 2026-04-12 16:39 | 2026-04-19 | 2026-04-18 17:55 | 2026-01-27 | 2026-01-29 14:40 | 2026-01-28 | 2026-01-30 23:32 | 2026-01-30 | 2026-02-19 12:53 | 2026-02-20 | 2026-02-20 19:01 | 2026-06-02 |  | 2026-06-05 |  | 2026-06-05 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-07-12 |  | 2026-07-12 | [6 empty] | 2026-07-18 |  | 2026-07-27 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-30 |  |  |  | 2026-08-21 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-07-12 |  | 2026-02-21 | 2026-03-14 13:55 | Site is RTMI | 2026-01-17 | 2026-01-18 10:48 | 1338459 | 240922 | 0 | 0 | 0 | 0 | 1468453.0297 | 238930 | 2026-07-14 15:34:30 +0530 | Reshma Melanta | Others: CX IS ASKING FOR A REFUND HAS CLIENT IS NEEDS CIVIL WORK AND ALL DONE UNDER THE BUDGET OF NET, WHICH IS NOT POSSIBLE, HAD MENTIOEND CLIENT WE CAN WORK AROUND THE SAME BUT THE CLEINT IS NOT READY TO LISTEN, THE QUOTE NET 11LK CLIENT WANTS EVRYTHING TO HAPPEN IN 11LK HAS THE SAME WAS INFORMED TO THE CLIENT DURING THE NET AND QUOTE POST THE DEM 1 MEETING INCREASED TO 16LK ALONG WITH THE CIVIL WORK. HEENA WANTED TO GO ON WITH THE CLIENT BUT THE CX IS NOT READY TO COME ON CALL AND ASKING FOR A REFUND. NOR WANT TO GO ON A MINIMUM BUDGET HAS WELL. | 2026-06-28 17:25:56 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-27 15:23:45 +0530 | Vishakha Vaishnav | Tried connecting the cx , did not answered the call
18083 | Turnkey | Dec'25 | Mr. Jivan Jyoti Maity | Independent House | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Soumya KP | [5 empty] | Pulivarthi Nirosha |  | Active | Design | Design Finalization | 2067378 | 289249 | 2833034 | 0 | 0 | 163 | 0 | 0 | 330964 | 654354 | 792810.4 |  |  | 2026-01-18 | 2026-01-18 12:10 | 2026-01-18 | 2026-01-18 14:54 | 2026-01-27 | 2026-01-27 12:23 | 2026-08-13 |  | 2026-08-16 |  | 2026-08-19 |  | 2026-01-27 | 2026-01-29 19:30 | 2026-01-28 | 2026-01-29 19:31 | 2026-01-29 | 2026-02-02 14:48 | 2026-02-08 | 2026-02-08 18:16 | 2026-08-19 |  | 2026-08-22 |  | 2026-08-22 |  | 2026-09-04 |  | 2026-09-05 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-26 |  | 2026-09-26 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-26 |  | 2026-08-04 |  | Unknown | 2026-01-17 | 2026-01-18 12:04 | 2400876 | 432157 | 0 | 0 | 0 | 0 | 2390298.113 | 394684 | 2026-02-08 18:21:36 +0530 | Abhinandan K S | Indepenedent House- Site readiness by June 2026. Explained the project milestones and timeline Project will be on hold till 15th April 2026 - Deviation approval taken. Next payment- 10% will be collected on 15th April 2026. Customer wants to have 1 design meeting to have the furniture layout and then keep the project on hold till April 2026. New designer to be assigned to the project. | 2026-02-02 18:07:06 +0530 | Bency Chacko |  | 2026-02-02 14:43:58 +0530 | Rishi Pandey | Some Image was uploaded
18084 | Turnkey | Dec'25 | Sulekha Umesh Omashe | LODHA UPPER THANE | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 2065934 | 9999 | 0 | 0 | 0 | 179 | 0 | 196594 | 413187 | 703954 | 742200 |  |  | 2026-01-18 | 2026-01-17 19:42 | 2026-01-18 |  | 2026-01-17 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-17 | 2026-01-17 19:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1750791 | 315142 | 2026-01-17 19:44:21 +0530 | Nishtha Valawalkar | Free Hob Chimney - 26th Jan offer | 2026-01-17 19:43:10 +0530 | Nishtha Valawalkar | Some Image was uploaded
18085 | Turnkey | Dec'25 | Bobin James James | Sheth 72 West | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  |  | Shashwat Joshi | Rizwan Mistry | Murali S | Rashmita Das | Aakash Gaikwad | Active | Preproduction | Procurement | 1613811 | 968287 | 1290491 | 1530475 | 1613811 | 1 | 13 | 0 | 0 | 0 | 645524 |  |  | 2026-01-18 | 2026-02-20 19:00 | 2026-02-17 | 2026-02-24 15:03 | 2026-03-02 | 2026-02-24 15:11 | 2026-03-24 | 2026-03-24 16:37 | 2026-03-28 | 2026-03-28 20:21 | 2026-03-29 | 2026-03-29 12:19 | 2026-02-24 | 2026-02-24 15:31 | 2026-02-25 | 2026-02-24 15:32 | 2026-02-24 | 2026-02-24 17:25 | 2026-03-08 | 2026-03-08 10:57 | 2026-04-28 | 2026-04-29 19:07 | 2026-04-29 | 2026-04-30 23:57 | 2026-04-01 | 2026-03-29 13:36 | 2026-05-16 | 2026-05-15 18:00 | 2026-05-16 | 2026-05-21 12:13 |  |  | 2026-06-13 | 2026-06-17 12:29 | 2026-06-18 | 2026-06-18 19:51 | 2026-06-21 | 2026-06-25 14:27 | 2026-07-07 | 2026-07-07 19:17 |  |  |  |  | 2026-07-14 11:00 | 2026-07-20 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-07-09 | 2026-07-14 10:59 | 2026-03-09 | 2026-03-21 12:28 | Site is RTMI | 2026-01-17 | 2026-01-18 10:48 | 1405356.8513 | 228888 | 1622166.3738 | 265496 | 1697454.3354 | 278208 | 1697454.3354 | 278208 | 2026-06-25 16:23:45 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-25 16:22:18 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-25 14:44:12 +0530 | Manzoor Shaikh | Some Image was uploaded
18086 | Turnkey | Dec'25 | Mrs Padmavati Thevar | Raymond Tenex | MUM - Thane | Yes | Rinisha Masurkar | [9 empty] | Active | Prospect | DCM Due | 1624437 | 9999 | 0 | 0 | 0 | 179 | 0 | 152445 | 324887 | 524590 | 612515.6 |  |  | 2026-01-18 | 2026-01-17 19:51 | 2026-01-30 |  | 2026-01-30 |  | 2026-02-17 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-05 |  | 2026-02-06 |  | 2026-02-06 |  | 2026-02-07 |  | 2026-02-23 |  | 2026-02-26 |  | 2026-02-26 |  | 2026-03-02 |  | 2026-03-03 |  |  |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-13 |  | 2026-03-13 | [6 empty] | 2026-03-19 |  | 2026-03-28 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-31 |  |  |  | 2026-04-22 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-03-13 |  | 2026-02-08 |  | Unknown | 2026-01-17 | 2026-01-17 19:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1376641 | 247795 | 2026-01-29 16:38:47 +0530 | Rinisha Masurkar | 18086 - Mrs Padmavati Thevar Unit no. 1 597 sqftÂ family of 4Â 2 daughter - 10, 6Â 1 catÂ poc - marchÂ mbr - daughter bedroom b2 - master bedroomÂ shoe rack 10- 15 in foyerÂ safety doorÂ foldable dining prefered, not a must a must to haveÂ planning for a projectorÂ seating place will be the focusÂ mandir - standing provisionÂ kitchen: storage above the washing machineÂ base, Â topÂ loftÂ mbrÂ ibed sliding door wardrobeÂ foldable deskÂ tv provisionÂ daughters bedroomÂ 2 wardrobeÂ 2 studyÂ bunk bedÂ false ceiling in living onlyÂ 10 -15 budgetÂ european & traditional combo partition in washroomsÂ vanity unitÂ balcony idea pet friendlyÂ 29th at 3:00pmÂ | 2026-01-29 16:38:21 +0530 | Rinisha Masurkar | Some Image was uploaded | 2026-01-18 21:36:29 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
18087 | Turnkey | Dec'25 | Rajesh Rane | Raymond Tenex | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | 10% Payment | 1428105 | 9999 | 1428105 | 0 | 0 | 145 | 0 | 132812 | 285621 | 482329 | 517344.4 |  |  | 2026-01-18 | 2026-01-17 19:55 | 2026-01-26 | 2026-01-26 14:26 | 2026-02-18 | 2026-02-20 15:21 | 2026-03-04 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-03-10 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-28 |  | 2026-03-28 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-28 |  | 2026-02-23 |  | Unknown | 2026-01-17 | 2026-01-17 19:54 | 1210259 | 217846 | 0 | 0 | 0 | 0 | 1210259 | 217846 | 2026-01-26 13:48:42 +0530 | Karuna Shinde | Some Image was uploaded | 2026-01-25 13:56:51 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-01-25 13:55:31 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
18088 | Turnkey | Dec'25 | MLVN Satyanarayana | Avalon Park @ The Prestige City | BNG - HSR | Yes | Kiran Agarampalli | Abhinandan K S | Kowshik |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Varun Mandana | Sunil Kumar S M | Completed | Complete | Completed | 1201654 | 1201654 | 1266158 | 1372685 | 1201654 | 23 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-18 | 2026-01-18 12:01 | 2026-01-25 | 2026-01-25 11:21 | 2026-01-25 | 2026-01-25 11:31 | 2026-03-26 | 2026-03-17 11:35 | 2026-03-29 | 2026-03-22 19:25 |  |  | 2026-01-25 | 2026-01-27 14:46 | 2026-01-26 | 2026-01-29 17:32 | 2026-01-29 | 2026-01-30 13:05 | 2026-02-07 | 2026-02-07 19:24 | 2026-03-22 | 2026-03-22 19:56 | 2026-03-25 | 2026-03-23 14:29 | 2026-03-25 | 2026-03-22 21:24 | 2026-03-27 | 2026-03-24 19:06 | 2026-03-25 | 2026-03-24 19:22 |  |  | 2026-03-28 | 2026-03-29 19:49 | 2026-03-30 | 2026-03-30 17:29 | 2026-04-02 | 2026-03-30 18:28 | 2026-04-02 | 2026-03-31 19:58 |  |  |  |  | 2026-04-02 10:02 | 2026-04-22 | 2026-04-21 21:36 | 2026-05-06 | 2026-05-06 17:43 | 2026-05-06 | 2026-05-06 13:56 | 2026-05-06 | 2026-05-06 21:54 | 2026-05-07 | 2026-05-08 13:32 | 2026-05-09 | 2026-05-12 11:47 |  |  | 2026-06-10 | 2026-06-06 17:18 | 2026-06-12 | 2026-06-06 17:19 | 2026-06-13 | 2026-06-06 17:21 |  |  |  |  | 2026-04-02 | 2026-04-02 10:01 | 2026-02-28 | 2026-03-17 11:33 | Site is RTMI | 2026-01-17 | 2026-01-17 20:41 | 1308255.635 | 216024 | 1508329.568 | 249053 | 1341361.365 | 215337 | 1341361.365 | 215337 | 2026-06-06 17:25:02 +0530 | Ranjith Kumar | KBR - Handles and lock installation pending. - Changed from Rose Gold to Black Colour in Good Will Gesture | 2026-05-11 08:17:15 +0530 | Ranjith Kumar | Execution: Hettich Shutter Handles & Knobs Metal Fab Flat Strips Loose Furniture | 2026-04-29 18:40:54 +0530 | Ranjith Kumar | Procurement:
18089 | Turnkey | Dec'25 | Jayesh Sojitra | Godrej Park Retreat | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | CDP Due | 1358778 | 9999 | 0 | 0 | 0 | 169 | 0 | 125879 | 271756 | 423651 | 527493.6 |  |  | 2026-01-18 | 2026-01-17 20:53 | 2026-01-18 | 2026-01-27 10:10 | 2026-01-27 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-21 |  | 2026-02-22 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-01-30 |  | Unknown | 2026-01-17 | 2026-01-17 20:52 | 0 | 0 | 0 | 0 | 0 | 0 | 1151506 | 207271 | 2026-01-27 10:06:48 +0530 | Priyanka Inchoor | DCM: Possession- Mid Feb Move in- May mid week 2BHK CDP-27th Members-2adult 1kid(8yr) Budget- 7L (5 to 6) Property- Godrej park, Sarjapur Requirement Entry area Shoe rack (extra wall extended) entry design to the wall Foyer Foyer with storage and wall design plan space for pooja (small) TV wall (dining wall) Wiring hide and simple tv unit deign Dining table (plan the space ) Kitchen Microwave (planning) granite consider Wall tilesÂ Utility sink base cabinet small wall cabinet for storage Loft in utility for sink wall Â Bedroom-1 (Kids bedroom and design for Kids theme) space planning (bed position) Work station (Big) hinged wardrobe if not possible sliding Kid theme Dressing next to bed (storage) MBR Wardrobe (hinged) Bed position panning small work station Dressing next to bed (storage) vanity in living (dining) vanity storage for both the bathroom Ac ducting false ceiling in livingÂ painting Balcony sitting storage
18090 | Turnkey | Dec'25 | Girish Sarda | Raymond Address Season 1 | MUM - Thane | Yes | Rutuja Kotwal | [7 empty] | Saloni Chawan |  | Active | Prospect | 10% Payment | 3637978 | 9999 | 3637978 | 0 | 0 | 145 | 0 | 353799 | 727596 | 1158086 | 1388498.4 |  |  | 2026-01-18 | 2026-01-17 21:29 | 2026-02-07 | 2026-02-07 19:37 | 2026-02-13 | 2026-02-20 15:34 | 2026-03-04 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-03-10 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-28 |  | 2026-03-28 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-28 |  | 2026-02-23 |  | Unknown | 2026-01-17 | 2026-01-17 21:26 | 3083032 | 554945 | 0 | 0 | 0 | 0 | 3083032 | 554945 | 2026-04-07 19:24:08 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-02-07 19:33:39 +0530 | Rutuja Kotwal | DCM: Mr. Girish SardaÂ 3 BHK.Â Â 1093Â Sq.ft.Â Â Design as per basicÂ vastuÂ Â Direction -Â Â Move in 4 peopleÂ Â Husband, wife and 2 kids daughter 16 yrs and 1 son 14 yrs.Â Â Profession entrepreneurÂ Wife HomeÂ maker.Â Â Living roomÂ Breaking of wall of the foyer to make the kitchen big,Â tiles will be in black, shoe rack will be outside,Â TV unitÂ with displayÂ unitÂ ,Â sofa, Mandir,Â 5 seaterÂ dining table,Â crockery if possibleÂ Â Kitchen Base units, WallÂ unitsÂ and lofts.Â Â Kitchen Renovation.Â Â Passage storage in the passage,Â Â MasterÂ BedroomÂ Â 2Â wardrobe,Â Bed,Â Workstation ,Â dresserÂ Bedroom 3Â Â wardrobeÂ with lofts,Â sofa cumÂ Bed and Study table, dresser.Â Â Bedroom 1 - wardrobe with lofts,Â 2 single bedsÂ and Study table, dresser.Â Vanity cabinets.Â Â BudgetÂ 35 lakhsÂ Â Budget suggestedÂ 40 42 lakhs includingÂ civil.Â Â CDPÂ 1stÂ Feb. 2026Â @Â 11am.Â Â
18092 | Turnkey | Dec'25 | Mr.Sushil Sanchetti | Abhee Riveria | BNG - HSR | Yes | Swati Rathod | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1969225 | 9999 | 1969225 | 0 | 0 | 117 | 0 | 186924 | 393845 | 600913 | 777544.8 |  |  | 2026-01-18 | 2026-01-17 21:49 | 2026-03-17 | 2026-03-17 16:56 | 2026-03-17 | 2026-03-20 11:40 | 2026-04-01 |  | 2026-04-04 |  | 2026-04-07 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-04-07 |  | 2026-04-10 |  | 2026-04-10 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-25 |  | 2026-04-25 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-25 |  | 2026-03-23 |  | Unknown | 2026-01-17 | 2026-01-17 21:47 | 1668834 | 300390 | 0 | 0 | 0 | 0 | 1668834 | 300390 | 2026-03-13 13:26:17 +0530 | Swati Rathod | Minutes of Meeting held on Date: 25-01-2026 Attendees: Nayan Reddy Discussion: Based on 25-01-2026 meeting, below is a list of all the requirements that were discussed during the meeting: F TO C - 9' MODULAR KITCHENÂ BASE UNITÂ Â WALL UNITÂ LOFTÂ TALL UNIT - OVEN SPACE WICKER BASKET GLASS SHUTERÂ OPEN UNIT Â UTILITYÂ SINK CABINETÂ WALL CABINET Â LIVING ROOMÂ 3SEATER + 1 SEATER SOFAÂ TV UNIT 5'10" WITH PARTITION Â SOFA BACK SIDE DESIGNEÂ PARTITION WOODEN PARTIION Â DINNIN AREAÂ POOJA UNIT Â FOYER UNIT IS MAIN TIHING Â FALSE CEILING IN LIVING AND DINNING Â GBR 02 Â STUDY UNITÂ WARDROBE +MIRRORÂ QUEEN SIZE REFERENCE Â BR 01 MBRÂ WARDROBE +LOFTÂ DRESSING UNITÂ
18093 | Turnkey | Dec'25 | Shraddha Golatkar | Raymond GS | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 179 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-18 | 2026-01-17 22:52 | 2026-01-18 |  | 2026-01-17 |  | 2026-01-29 |  | 2026-02-01 |  | 2026-02-04 |  | 2026-01-17 |  | 2026-01-18 |  | 2026-01-18 |  | 2026-01-19 |  | 2026-02-04 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-11 |  | 2026-02-12 |  |  |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-22 |  | 2026-02-22 | [6 empty] | 2026-02-28 |  | 2026-03-09 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-12 |  |  |  | 2026-04-03 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-02-22 |  | 2026-01-20 |  | Unknown | 2026-01-17 | 2026-01-17 22:48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18094 | Turnkey | Dec'25 | Prasad Nayak | Hiranandani meadows | MUM - Thane | Yes | Hemant Sonar | Divya Rahangdale | Anil Kuwar |  |  | Faraz Soudagar | Aditya Vikram | Murali S | Aryan Singh | Prasad Bhivaji Hande | Completed | Complete | Completed | 855923 | 856840 | 1137808 | 977452 | 895923 | 7 | 19 | 0 | 0 | 0 | 0 |  |  | 2026-01-18 | 2026-01-17 22:58 | 2026-01-25 | 2026-01-25 11:31 | 2026-01-26 | 2026-01-26 19:46 | 2026-01-30 | 2026-01-30 19:02 | 2026-01-30 | 2026-01-30 19:33 | 2026-02-06 | 2026-02-06 17:02 | 2026-01-26 | 2026-01-29 14:13 | 2026-01-27 | 2026-01-29 14:40 | 2026-01-29 | 2026-01-29 17:07 | 2026-01-30 | 2026-01-30 16:23 | 2026-02-06 | 2026-02-06 20:30 | 2026-02-09 | 2026-02-06 23:38 | 2026-02-16 | 2026-01-29 | 2026-03-10 | 2026-03-08 17:05 | 2026-03-09 | 2026-03-18 16:40 |  |  | 2026-03-20 | 2026-03-21 16:32 | 2026-03-21 | 2026-03-21 19:21 | 2026-03-24 | 2026-03-24 18:59 | 2026-03-24 | 2026-03-26 19:24 |  |  |  |  | 2026-03-27 15:45 | 2026-05-04 | 2026-04-30 22:19 | 2026-05-05 | 2026-05-04 20:25 | 2026-05-04 | 2026-05-09 19:15 | 2026-05-04 | 2026-05-12 14:42 | 2026-05-12 | 2026-05-14 16:28 | 2026-05-16 | 2026-05-23 18:57 |  |  | 2026-05-05 | 2026-06-23 18:28 | 2026-05-07 | 2026-06-23 18:29 | 2026-06-10 | 2026-06-23 18:57 |  |  |  |  | 2026-03-24 | 2026-03-26 18:15 | 2026-01-31 | 2026-01-30 16:50 | Site is RTMI | 2026-01-17 | 2026-01-17 22:48 | 1189706.868 | 196445 | 1115489.9225 | 184187 | 1040137.238 | 171751 | 1040137.238 | 171751 | 2026-06-01 14:27:58 +0530 | Faraz Soudagar | Execution: Modular installation done as per material availaibility. Profile shutter pending - Mirror measurment pending (request raised on 23rd may) | 2026-05-18 15:06:21 +0530 | Faraz Soudagar | Execution: Modular delivery datre - 14th may Installation start date - 16th may | 2026-05-08 18:24:04 +0530 | Bency Chacko | Some Image was uploaded
18095 | Turnkey | Dec'25 | Megha | Purva Atmoshphere | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Yogesh Patidar | [5 empty] | Mohammed Rasick |  | Active | Prospect | DCM Due | 2378404 | 9999 | 0 | 0 | 0 | 178 | 0 | 227841 | 475681 | 727257 | 937626 |  |  | 2026-01-18 | 2026-01-21 17:45 | 2026-01-21 |  | 2026-01-28 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-17 | 2026-01-18 11:43 | 0 | 0 | 0 | 0 | 0 | 0 | 2015597 | 362807 | 2026-01-21 17:40:22 +0530 | Vishnu S | Mr Sandeep & Mrs MedhaÂ RGM : 21/01/2026 CDP : 29/01/2026 (4PM at HRBR Office) Own Purpose-3ppl (50+plus , Daughter-20) Facing-North facing Main Door Suttle colours (Muted colours) Spending More time in balcony & terrace Prefers more landscaping Radiance Floresta External Foyer -Shoe rackÂ -Drawer to have keys Internal Foyer -Wall Treatment with Designer Mirror -Space to have umbrella Living Area -Tv unit with wall panel with sounding system (Elegant Cabinets) with wall treatment -Tv Size (65") -Sofa (Open to Suggestion) -Minimal False ceiling -Wall treatment Pooja Unit -CNC Door with Duco & Base Cabinets -Photo frames & Smaller Idols -Wall treatment Dining Unit -Crockery unitÂ (Handwash area to be highlighted) Kitchen -Modular (Base,top,tall unit& Loft)-Laminate-Glossy -20MM granite -Single door fridge -Cylinder unit Utility -Double bowl sink unit -Dishwasher Terrace / Balcony (Open to Sky) -Washing Machine -Closed roof when its raining Bedroom-1 (Parent Bedroom) -Hinged wardrobe + Loft -Wall treatment (Minimal)-Solid Wooden Beading -Workstation -Prefer wall mounted Tv -Queen Size Bed with storage -Dresser with mirror -Vanity (Base & Top) with granite -Shower curtains Family Living -Bar unit & Art galleryÂ -Library unit -Arm chair / Recliner Study room (MBR & Study room to be clubbed) -Workstation & Sliding wardrobe(Walk-in wardrobe + Loft -Sliding doorÂ -Dresser + Design Mirror -Filing cabinet -Art galleryÂ -Kings Bed with & without storageÂ -Existing wooden flooring) -Wall Treatment Bedroom-3 (Daughter Bedroom) -Prefers music -Queen Size Bed with storage -Walk in wardrobe (Combination of sliding, hinged & Dresser with mirror) -Wall treatment -Workstation -Vanity (Base & Top) with granite -Shower partition Terrace / Balcony (Open to Sky) -Landscaping -Closed roof when its raining Form link : https://app.bonito.in/survey/lg4V3aGmzz3pXoS71odU7g
18096 | Turnkey | Dec'25 | Darshan Utekar | Ashar Arise | MUM - Thane | Yes | Karuna Shinde | [9 empty] | Active | Prospect | DCM Due | 2533872 | 9999 | 0 | 0 | 0 | 178 | 0 | 243388 | 506774 | 842950 | 930760.8 |  |  | 2026-01-19 | 2026-01-18 21:30 | 2026-01-19 |  | 2026-01-26 |  | 2026-02-07 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-20 |  | 2026-02-21 |  |  |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-03 |  | 2026-03-03 | [6 empty] | 2026-03-09 |  | 2026-03-18 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-21 |  |  |  | 2026-04-12 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-03-03 |  | 2026-01-29 |  | Unknown | 2026-01-18 | 2026-01-18 13:47 | 0 | 0 | 0 | 0 | 0 | 0 | 2147349 | 386522 | 2026-05-28 15:28:15 +0530 | Bhagyashree Salunkhe | tried calling cx but went rnr | 2026-03-24 15:23:13 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-01-18 21:35:57 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
18097 | Turnkey | Dec'25 | Asif K | mjrdivine meadows | BNG - HSR | No Estimate | [8 empty] | Fuzail Girach |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-18 13:47 | 2026-01-19 |  | 2026-01-24 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-18 | 2026-01-18 13:46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18098 | Sub Project |  | DEVFAST SOLUTIONS (LAKSHMANA RAMARAO VADAGA) | Lodha Woods | MUM - GOR |  |  | Reshma Melanta | Shantanu Parakh |  |  | Rajkumar Suthar | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-18 15:50 | 2026-01-19 | 2026-01-18 15:51 | 2026-01-20 | 2026-01-18 15:52 | 2026-01-20 | 2026-01-18 15:58 | 2026-01-19 | 2026-01-18 15:59 | 2026-01-19 | 2026-01-18 16:00 | 2026-01-18 | 2026-01-18 15:52 | 2026-01-19 | 2026-01-18 15:52 | 2026-01-18 | 2026-01-18 15:53 | 2026-01-19 | 2026-01-18 15:57 | 2026-01-18 | 2026-01-18 16:01 | 2026-01-21 | 2026-01-18 16:01 | 2026-01-18 | 2026-01-18 16:01 | 2026-01-19 | 2026-01-18 16:02 | 2026-01-19 | 2026-01-18 16:03 |  |  | 2026-01-21 | 2026-01-18 16:04 | 2026-01-19 | 2026-01-18 16:05 | 2026-01-21 | 2026-01-18 16:05 | 2026-03-01 | 2026-02-18 18:44 |  |  |  |  | 2026-02-19 12:17 | 2026-02-21 | 2026-02-20 19:46 | 2026-02-23 | 2026-02-21 14:29 | 2026-02-22 | 2026-03-10 13:38 | 2026-02-21 | 2026-03-23 15:43 | 2026-03-23 | 2026-03-25 20:27 | 2026-03-26 | 2026-03-25 22:09 |  |  | 2026-03-27 | 2026-03-26 17:55 | 2026-03-28 | 2026-03-26 17:57 | 2026-03-26 | 2026-03-26 18:00 |  |  |  |  | 2026-02-19 | 2026-02-19 12:16 | 2026-01-19 | 2026-01-18 15:57 | Unknown | 2026-01-18 | 2026-01-18 15:50 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | 2026-03-02 12:36:55 +0530 | Rajkumar Suthar | Execution: Only Sofa in scope
18099 | Turnkey | Dec'25 | Subhasish Padhi | Mahendra Arya | BNG - HSR | Yes | Chittipireddy Sriharish | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | Design Finalization | 1162054 | 147593 | 1162054 | 0 | 0 | 120 | 46 | 0 | 201023 | 357503 | 455935.2 |  |  | 2026-01-19 | 2026-01-18 13:54 | 2026-01-18 | 2026-01-18 15:37 | 2026-01-27 | 2026-01-27 17:33 | 2026-09-09 |  | 2026-09-12 |  | 2026-09-15 |  | 2026-01-28 | 2026-01-27 16:52 | 2026-01-29 | 2026-01-27 16:59 | 2026-01-28 | 2026-01-30 09:39 | 2026-02-06 | 2026-02-06 19:38 | 2026-09-15 |  | 2026-09-18 |  | 2026-09-18 |  | 2026-10-04 |  | 2026-10-05 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-24 |  | 2026-10-24 | [6 empty] | 2026-10-30 |  | 2026-11-08 |  | 2026-11-07 |  | 2026-11-08 |  | 2026-11-09 |  | 2026-11-11 |  |  |  | 2026-12-03 |  | 2026-12-05 |  | 2026-12-06 | [5 empty] | 2026-10-24 |  | 2026-02-07 | 2026-02-18 16:12 | Site is RTMI | 2026-01-18 | 2026-01-18 13:52 | 1292933.6165 | 213491 | 0 | 0 | 0 | 0 | 1292933.6165 | 213491 | 2026-07-09 17:46:30 +0530 | Abhinandan K S |  | 2026-06-16 14:28:33 +0530 | Kowshik | Some Image was uploaded | 2026-04-16 16:24:52 +0530 | Lalitha Ajay Kumar | Some Image was uploaded
18100 | Turnkey | Dec'25 | ACROBULK SHIPPING (OPC) PRIVATE LIMITED | Lodha Upper Thane | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Asif Shaikh | Akshat Shrivastava |  | Prashant Panigrahi | Shailendra Mishra | Active | Installation | Execution | 1130676 | 1130676 | 1470412 | 1301205 | 1130676 | 12 | 2 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-20 20:02 | 2026-01-24 | 2026-01-24 12:13 | 2026-01-26 | 2026-01-26 19:42 | 2026-02-26 | 2026-02-17 16:56 | 2026-02-28 | 2026-02-28 16:08 | 2026-03-17 | 2026-03-17 17:51 | 2026-01-26 | 2026-01-29 19:25 | 2026-01-27 | 2026-01-29 19:26 | 2026-01-29 | 2026-01-30 17:05 | 2026-02-15 | 2026-02-15 16:30 | 2026-03-19 | 2026-03-19 18:09 | 2026-03-21 | 2026-03-19 18:34 | 2026-03-18 | 2026-03-16 17:37 | 2026-03-23 | 2026-03-25 19:59 | 2026-03-30 | 2026-03-27 19:04 |  |  | 2026-04-09 | 2026-05-06 13:45 | 2026-05-15 | 2026-05-15 19:30 | 2026-05-18 | 2026-05-16 12:46 | 2026-04-27 | 2026-04-27 19:11 |  |  |  |  | 2026-05-21 19:07 | 2026-05-31 | 2026-05-30 20:58 | 2026-06-12 | 2026-06-10 17:54 | 2026-06-11 | 2026-06-15 18:02 | 2026-06-10 | 2026-07-02 13:58 | 2026-06-26 | 2026-07-03 14:44 | 2026-07-05 | 2026-07-11 11:54 |  |  | 2026-06-29 |  | 2026-07-01 |  | 2026-07-30 | [5 empty] | 2026-05-19 | 2026-05-21 19:06 | 2026-02-16 | 2026-02-17 12:33 | Site is RTMI | 2026-01-18 | 2026-01-20 19:46 | 1689730.529 | 264723 | 1478870.4687 | 238912 | 1334735.2607 | 211374 | 1334735.2607 | 211374 | 2026-07-12 18:18:37 +0530 | Asif Shaikh | Execution: Furniture Installation completing - 15th July. POP Cornice Design - 15th July. Customer Carpentry work -- 20th July. Bed Delivery -- No ETA by vendor - Final Painting work shall be commencing by 20th July & will be completed by 26th July for 2 BHK DC , Wallpaper installation , Bed installation - 26th July. QC - 27th July. Snag . Kitchen wooden panel snag, PTO -- OM approval pending, ETA yet to be received. Beading patti not received from main load. | 2026-07-05 14:01:38 +0530 | Asif Shaikh | Furniture Installation completing - 10th July. POP Cornice Design - 10th July. Customer Carpentry work -- 12th July. Bed Po yet to raised . Final Painting work shall be commencing by 15th July & will be completed by 25th July. DC , Wallpaper installation , Bed installation - 26th July. QC - 27th July Snag . Kitchen wooden panel snag, PTO -- OM approval pending, ETA yet to be received | 2026-07-05 13:59:40 +0530 | Asif Shaikh | Execution: Furniture Installation completing - 10th July. POP Cornice Design - 10th July. Customer Carpentry work -- 12th July. Bed Po yet to raised . Final Painting work shall be commencing by 15th July & will be completed by 25th July. DC , Wallpaper installation , Bed installation - 26th July. QC - 27th July.
18101 | Turnkey | Dec'25 | Ronak Shah | Ray Rosewalt | MUM - GOR | Yes | Yogini Chavan | [7 empty] | Umang Shah |  | Active | Prospect | CDP Due | 1619492 | 9999 | 0 | 0 | 0 | 178 | 0 | 151950 | 323898 | 558077 | 575567.2 |  |  | 2026-01-19 | 2026-01-18 16:09 | 2026-01-18 | 2026-01-18 20:25 | 2026-01-22 |  | 2026-02-05 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-01-24 |  | 2026-01-25 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-01 | [6 empty] | 2026-03-07 |  | 2026-03-16 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-19 |  |  |  | 2026-04-10 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-03-01 |  | 2026-01-27 |  | Unknown | 2026-01-18 | 2026-01-18 16:09 | 0 | 0 | 0 | 0 | 0 | 0 | 1372451 | 247041 | 2026-02-23 19:07:00 +0530 | Umang Shah | Some Image was uploaded | 2026-01-18 20:23:37 +0530 | Shweta Dalvi | DCM: User ResponseLifestyle1. Please select your budget for Interior Designing? Rs. 10-15 Lacs 2. Interior Designing to commence on the basis of Actual Site Measurement 3. What is your Profession? Husband - Business, Wife - Tutor 4. Who will be living in this home? Nuclear Family 5. What activities do you usually perform at home? (Choose top 23) Working from Home, Hosting Guests, Family Bonding, Relaxing & Unwinding, Pursuing Hobbies, Prayer 6. What is your preferred entertainment style? Casual get-togethers 7. Do you prefer any Smart home features? Security 8. What is your possession date? 2026-03-18 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Digital lock, Shoe rack Dcor & Living Room1. Choose your decor inspirations Artwork, Plants 2. Any specific signature design feature required Statement wall 3. Whats the primary use of your living room? TV focus , Entertaining guests, Multipurpose 4. Any absolute no-go styles, colors, or materials? No dark colours 5. Must-have furniture or features? Sofa, TV unit, Coffee table, Puja unit, Statement Wall/ Feature Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Fridge, Hob, Dishwasher, Washing machine BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Swing Master Bedroom - Additional units Bookshelf , Dresser Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Swing Other Bedroom - Additional units TV unit BathroomsPreferred vanity style What do you prefer? What are your requirements for Utility Area? Washing machine space Balcony & OutdoorHow do you intend to use your balcony for? I don't have a balcony b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? Final Vision1. Any space in the home that you want to put in Spotlight? 2. Do you want the design to reflect any personal story, cultural influence, or special memory
18102 | Turnkey | Dec'25 | Sandesh Sawant | lok prabha | MUM - GOR | Yes | Preeti Agarwal | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Manasi Patil |  | Active | Preproduction | Site Readiness 1 | 1300971 | 239717 | 1278848 | 1300971 | 0 | 10 | 68 | 0 | 0 | 607957 | 453297.2 |  |  | 2026-01-19 | 2026-01-27 15:40 | 2026-01-28 | 2026-01-28 18:20 | 2026-02-03 | 2026-01-28 18:26 | 2026-03-21 | 2026-03-21 14:01 | 2026-06-01 | 2026-05-21 18:36 | 2026-05-25 | 2026-05-26 15:28 | 2026-01-28 | 2026-01-29 15:02 | 2026-01-29 | 2026-01-29 15:03 | 2026-01-29 | 2026-01-30 16:55 | 2026-02-03 | 2026-02-03 17:41 | 2026-05-26 | 2026-05-26 17:02 | 2026-05-29 | 2026-05-26 17:27 | 2026-03-29 | 2026-03-04 12:12 | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-21 |  | 2026-07-21 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-21 |  | 2026-02-04 | 2026-03-21 13:58 | Site is RTMI | 2026-01-18 | 2026-01-25 21:13 | 1083770 | 195078 | 1497951.6046 | 228961 | 0 | 0 | 1497951.6046 | 228961 | 2026-06-18 19:36:24 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-21 15:24:25 +0530 | Manzoor Shaikh | Preeti has to close the FDM, hence made the project Active. | 2026-04-23 16:01:51 +0530 | Manzoor Shaikh | Some Image was uploaded
18103 | Turnkey | Dec'25 | Mr. Rohit Kumar Sharma | Adarsh Park Heights161 | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 2642533 | 9999 | 0 | 0 | 0 | 117 | 0 | 254254 | 528507 | 799118 | 1050655.2 |  |  | 2026-01-19 | 2026-01-18 20:50 | 2026-01-22 | 2026-01-23 11:14 | 2026-01-25 | 2026-03-20 12:08 | 2026-04-01 |  | 2026-04-04 |  | 2026-04-07 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-04-07 |  | 2026-04-10 |  | 2026-04-10 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-25 |  | 2026-04-25 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-25 |  | 2026-03-23 |  | Unknown | 2026-01-18 | 2026-01-18 20:48 | 0 | 0 | 0 | 0 | 0 | 0 | 2239435 | 403098 | 2026-01-23 11:16:05 +0530 | Kiran Agarampalli | Some Image was uploaded | 2026-01-23 11:15:27 +0530 | Kiran Agarampalli | DCM: RGM Â False ceiling: Yes Civil changes: No No loud colors Â Foyer:Â Shoe rackabove the shoe rack wall concept with a mirror on one cornerÂ storage space for helmets and stuffÂ pullout stool for shoe rack to be consideredmcb box to be coveredkey holder on the wall (covered one)Â Living/ Dining: tv unit with suspended drawersand tall unit next to it.Â all the wires to be concealed.Â sofa back wall to have wall conceptÂ Living and dining 2 or 3 options. in terms of design and costingÂ Pooja unit position YTC by CX(north or south wall)if placed on south wall add crockery next to it (minimal one not too big) add some console table with wall design to north wall.Â crockery unit to accommodate bottles and glassessome storage space to keep our extra mattress kind of stuff(optional) Pooja unit: (glass shutters) 2 options one with pocket doorÂ other with regular doorsÂ Kitchen: Appliances unitÂ Tall unit(otg) next to fridgeÂ tall pantry unitÂ undercounter ro unitÂ wall unit and loftÂ Utility: dishwasherÂ sinkÂ washing machineÂ washing machine to be placed on the raised levelÂ Master bedroom:Â walking space - wardrobeÂ dresser unitÂ bay seater and study along with itÂ small tv ledgeÂ headboard wall to be designedÂ Bedroom 1:Â only wardrobe.Â Bedroom 2: walkin space with wardrobe with dresserÂ tv unit and study unitÂ headboard designÂ add some tall unit to put decorsÂ Toilet: vanity storage for all the toiletsÂ Budget: 15-18L Â
18104 | Turnkey | Dec'25 | Vibhavari mantri | Dem Siddhivinayak | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Rajkumar Suthar | Sandeep Tiwari | Murali S | Nivesh Gupta | Aakash Gaikwad | Active | Installation | Execution | 1319980 | 1319980 | 947254 | 1717310 | 1319980 | 17 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-18 18:17 | 2026-01-21 | 2026-01-21 13:52 | 2026-01-31 | 2026-01-31 12:59 | 2026-02-27 | 2026-02-27 15:53 | 2026-03-02 | 2026-02-27 16:31 | 2026-03-11 | 2026-03-07 18:26 | 2026-01-31 | 2026-01-31 17:57 | 2026-02-01 | 2026-02-01 11:32 | 2026-02-01 | 2026-02-04 11:33 | 2026-02-20 | 2026-02-20 17:47 | 2026-03-26 | 2026-03-27 12:40 | 2026-03-27 | 2026-03-28 10:23 | 2026-03-15 | 2026-03-06 20:25 | 2026-04-06 | 2026-04-05 20:58 | 2026-04-06 | 2026-04-05 20:58 |  |  | 2026-05-06 | 2026-05-12 15:47 | 2026-05-14 | 2026-05-14 17:04 | 2026-05-17 | 2026-05-14 17:58 | 2026-05-17 | 2026-05-17 14:03 |  |  |  |  | 2026-05-20 11:32 | 2026-05-29 | 2026-05-28 19:25 | 2026-06-15 | 2026-06-13 21:17 | 2026-06-14 | 2026-06-18 14:57 | 2026-06-13 | 2026-06-24 16:14 | 2026-06-23 | 2026-06-28 00:25 | 2026-06-30 | 2026-07-11 13:15 |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-05-17 | 2026-05-19 19:30 | 2026-02-21 | 2026-02-27 15:45 | Site is RTMI | 2026-01-18 | 2026-01-18 18:14 | 1102212.301 | 173479 | 1845235.2495 | 304674 | 1505837.7483 | 248641 | 1505837.7483 | 248641 | 2026-07-09 09:01:06 +0530 | Nishant Jadhav | Execution: Modular work start on 4th July Bed will be ready for delivery on 10th july handover date 30th july | 2026-07-02 11:48:44 +0530 | Nishant Jadhav | Execution: Modular Material delivered on 29 June 2026 Modular team not align yet As per cx requirement painting correction started on side today | 2026-06-13 19:14:38 +0530 | Nishant Jadhav | Execution: Fire Sprinkler shifting work done on 8th June 2026 Ceiling Gypsum sheet packing work done 13th June 2026 Painting Work start 15th June 2026
18105 | Turnkey | Dec'25 | Kanwal Kohli | Raheja interface Malad | MUM - GOR | Yes | Priyanka Murarka |  | Shantanu Parakh | [5 empty] | Umang Shah |  | Active | Prospect | CDP Due | 1819955 | 9999 | 0 | 0 | 0 | 173 | 0 | 171997 | 363991 | 593275 | 680694 |  |  | 2026-01-19 | 2026-01-18 19:17 | 2026-01-23 | 2026-01-23 12:44 | 2026-01-21 |  | 2026-02-10 |  | 2026-02-13 |  | 2026-02-16 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-02-16 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-23 |  | 2026-02-24 |  |  |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-06 |  | 2026-03-06 | [6 empty] | 2026-03-12 |  | 2026-03-21 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-24 |  |  |  | 2026-04-15 |  | 2026-04-17 |  | 2026-04-18 | [5 empty] | 2026-03-06 |  | 2026-02-01 |  | Unknown | 2026-01-18 | 2026-01-18 19:16 | 0 | 0 | 0 | 0 | 0 | 0 | 1542335 | 277620
18106 | Turnkey | Dec'25 | Kashyap Rao | Independent Duplex | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 3409836 | 9999 | 0 | 0 | 0 | 178 | 0 | 330985 | 681967 | 1028030 | 1358855.6 |  |  | 2026-01-19 | 2026-01-20 11:48 | 2026-01-19 |  | 2026-01-27 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-21 |  | 2026-02-22 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-01-30 |  | Site is Non-RTMI | 2026-01-18 | 2026-01-20 11:46 | 0 | 0 | 0 | 0 | 0 | 0 | 2889692 | 520144
18107 | Turnkey | Dec'25 | Anoop Kumar Gupta | Adarsh Park Heights | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | CDP Due | 3120191 | 9999 | 0 | 0 | 0 | 174 | 0 | 302020 | 624038 | 968640 | 1215493.6 |  |  | 2026-01-19 | 2026-01-18 20:59 | 2026-01-21 | 2026-01-22 13:21 | 2026-01-28 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-18 | 2026-01-18 20:58 | 0 | 0 | 0 | 0 | 0 | 0 | 2644230 | 475961 | 2026-01-21 20:32:21 +0530 | Swati Rathod | DCM: PID: 18107 Property - 3BHK possession -01-05-2026 Budget - 10L-15L Members - 3ppl - west face - main door wall design(with shoerack Cx scope) - wall concept with 3D - curved surface for bottom units - full house false ceiling(living lil grand) FOYER :Â - shoe rack with seating(15-20pairs) - tall unit LIVING: - tv unit(setup box space) - curved wall design( minimal elements)Â - split sofa DINNING: - 6 seater - pooja unit(2 stepped)(closed unit) - crockery unit KITCHEN: - OTG unit - bottom unit - top units - loft - 3-4 burner - 2' sink(1 bowl)(double drawer unit) - under Ro - dustbin - black granite(only installion) - pantry unit -air frierÂ - roller shutter for mixer - panel on entry(below beam) UTILITY:(open)? - 2 bowl sink - WM (@ some ht) - top units - janitor unit Â Â TOILETS: - wall bottom vanityÂ - top unit - glass partn M.BEDROOM: (MOTHER room) - k bed (recliner)CX scope (side table BD scope) - openable wardrobe - dresser without skrt - wall design - tall unit with full mirror on shutter Â M. BATHROOM: - top storage(open-closed) - bottom wall unit BEDROOM1: - k bed CX scope (side table BD scope) - openable wardrobe - dresser without skrt - wall design - tall unit with full mirror on shutter - study unit adjustable) BATHROOM: - top storage(open-closed) - bottom wall unit Â BEDROOM2: - sliding wardrobe - study unit CX scope - sofa cum bed CX scope
18108 | Turnkey | Dec'25 | Eshmeet Singh | Purva Zenium Phase 2 | BNG - HSR | Yes | Avishkar Sargam | Akshay Ds | Soumya KP |  |  | Nikhil Mogeraya | Saddam Hussain Z M |  | Nidhi Shaw | Raghavendra Gowda | Active | Preproduction | 2D | 1315940 | 394782 | 1335388 | 1315940 | 0 | 1 | 25 | 0 | 0 | 396223 | 524934.8 |  |  | 2026-01-19 | 2026-01-18 21:02 | 2026-01-24 | 2026-03-03 16:33 | 2026-03-05 | 2026-03-05 11:30 | 2026-06-01 | 2026-06-04 11:32 | 2026-06-25 | 2026-06-25 16:51 | 2026-06-25 | 2026-06-25 17:57 | 2026-03-05 | 2026-02-28 | 2026-03-06 | 2026-03-10 12:34 | 2026-03-10 | 2026-03-12 17:48 | 2026-03-20 | 2026-03-20 16:24 | 2026-06-26 | 2026-06-26 17:36 | 2026-07-02 | 2026-06-27 21:42 | 2026-07-02 | 2026-06-27 | 2026-07-05 | 2026-07-07 08:35 | 2026-07-08 | 2026-07-07 08:35 |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-18 |  | 2026-07-18 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-18 |  | 2026-05-20 | 2026-05-28 11:47 | Site is RTMI | 2026-01-18 | 2026-01-18 21:00 | 1354853.5235 | 233789 | 1458637.5831 | 240855 | 0 | 0 | 1458637.5831 | 240855 | 2026-06-04 15:41:17 +0530 | Avishkar Sargam | MOM 30th May Living Room - Foyer design to remain unchanged; add a display shelf. - Provide flap-down shutters in the TV unit for access to electrical points. - Add cable management holes in the TV unit. - Dining wall: Provide 2 design options: Â - Wallpaper with wall art Â - Texture paint with wall art - Add a panel above the crockery unit to close the gap up to the ceiling. - Add lighting inside the crockery unit. - Shoe rack location outside the main door to be confirmed. - Add a false ceiling design and provide the corresponding quotation. Common Washroom - Remove the vanity unit. - Add a wall-mounted storage unit with a mirror. Kitchen - Add a partition to screen the utility area. - Add a detergent basket and dustbin provision within the sink unit. - Remove the tall unit. - Add a wall-mounted microwave unit. Study Room - Remove the glass display unit. - Modify the wardrobe to a 4-door configuration. - Convert one wardrobe shutter into book storage. - Provide a study unit in the remaining space. - Add a sofa-cum-bed on the adjacent wall. - Add wallpaper on the same wall. Master Bedroom - Redesign the dresser unit to accommodate a study space. - Retain the existing wall design concept. - Add a pendant light above the dresser/study area for reading. Bedroom 2 - No changes required. | 2026-05-24 14:40:50 +0530 | Avishkar Sargam | DDM1: MOM 23rd May Theme * Zen Design Theme Living Room * Foyer area design to be changed according to the shared reference. * TV unit and sofa positions to be changed. * Provide 2 design options for the TV unit. * Dining wall design to be changed. * Add crockery unit with service counter. Kitchen Main Counter * Remove the partition. * Add a cylinder unit next to the hob/cooktop. * Place sink and dishwasher next to each other. * Add SS thali basket for plate storage. Service Counter * Create a second design option with larger counter space. Master Bedroom Existing Layout * Add dresser with seating next to the bed. * Provide space for a crib next to the bed. * Wardrobe to remain the same. Layout Option 2 * Bed on the entrance wall. * Study on the adjacent wall. Master Bathroom * No changes. Bedroom 2 * No changes in the existing layout. * Add dresser with side table. * Reuse the existing recliner. Study Room Existing Layout * Extend the study unit on the window wall. * Extend the wardrobe. * Provide space for sofa-cum-bed. Layout Option 2 * Wardrobe on both sides of the window. * Study under the window. * Reuse the bookshelf on the entrance wall along with a dresser. Pointers I need to Revert On * Layout options for sofa placement. * Surface light options. * Possibility of curves in furniture design. * Vanity design in common bathroom. Requirements from you * Sizes and photos of all existing furniture and appliances required. Additional Notes * Sharing all downloaded Â Pinterest references discussed yesterday for further reference. | 2026-04-22 17:38:48 +0530 | Patil Madhavi | Some Image was uploaded
18109 | Turnkey | Dec'25 | Mikesh Matalia | Runwal Pinnacle | MUM - Thane | Yes | Hemant Sonar | Anamika Dolai | Anil Kuwar | [5 empty] | Nishtha Valawalkar |  | Hold | Design | Design Finalization | 1952678 | 250999 | 2609535 | 0 | 0 | 56 | 42 | 0 | 334804 | 593345 | 773529.6 |  |  | 2026-01-19 | 2026-01-18 21:29 | 2026-02-17 | 2026-02-17 11:53 | 2026-04-04 | 2026-04-04 23:47 | 2026-08-12 |  | 2026-08-17 |  | 2026-08-20 |  | 2026-04-04 | 2026-04-07 13:39 | 2026-04-05 | 2026-04-08 11:51 | 2026-04-08 | 2026-04-08 16:50 | 2026-04-10 | 2026-04-10 15:17 | 2026-08-20 |  | 2026-08-21 |  | 2026-08-21 |  | 2026-08-24 |  | 2026-08-24 |  |  |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 | [6 empty] | 2026-09-08 |  | 2026-10-01 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-01 |  | 2026-10-03 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-09 | [5 empty] | 2026-09-01 |  | 2026-07-31 |  | Site is RTMI | 2026-01-18 | 2026-01-18 21:24 | 2211470 | 398064 | 0 | 0 | 0 | 0 | 2160036.155 | 356671 | 2026-07-14 13:54:43 +0530 | Anamika Dolai | Client not responding | 2026-06-12 19:09:31 +0530 | Anamika Dolai | Some Image was uploaded | 2026-05-13 11:19:39 +0530 | Hemant Sonar | Some Image was uploaded
18110 | Turnkey | Dec'25 | Abhay Kulkarni | Shiv Shrusti | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Preproduction | Site Readiness 1 | 991664 | 297500 | 1031485 | 991664 | 0 | 2 | 107 | 0 | 0 | 319446 | 374717.6 |  |  | 2026-01-19 | 2026-01-18 22:48 | 2026-01-31 | 2026-01-31 11:18 | 2026-02-03 | 2026-02-03 10:57 | 2026-03-05 | 2026-03-05 11:59 | 2026-03-28 | 2026-03-27 15:59 |  |  | 2026-02-03 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-04 15:58 | 2026-02-04 | 2026-02-10 14:45 | 2026-02-21 | 2026-02-21 15:53 | 2026-03-28 | 2026-03-28 19:21 | 2026-03-31 | 2026-03-28 22:53 | 2026-03-31 | 2026-03-28 20:09 | 2026-10-05 |  | 2026-10-06 |  |  |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-16 |  | 2026-10-16 | [6 empty] | 2026-10-22 |  | 2026-10-31 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-01 |  | 2026-11-03 |  |  |  | 2026-11-25 |  | 2026-11-27 |  | 2026-11-28 | [5 empty] | 2026-10-16 |  | 2026-03-25 | 2026-03-05 11:50 | Site is RTMI | 2026-01-18 | 2026-01-18 22:46 | 1091471.266 | 180226 | 1073193.0163 | 177203 | 0 | 0 | 1073193.0163 | 177203 | 2026-04-30 11:35:16 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-03-24 15:02:56 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-05 10:57:51 +0530 | Shraddha Pansare | - Design Discussion Meeting 1 : 1-Mar-26 (Design discussion) - Design Discussion Meeting 2 : 8-Mar-26 (Design finalization) - Design Discussion Meeting 3 : 15-Mar-26 (Material Selection) - *20% payment Milestone.Â - Final Design approval (20-Feb-26) Client is ready to pay
18111 | Turnkey | Dec'25 | Gupta Radheshyam | Radheshyam Gupta | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Design | Design Finalization | 1707387 | 237999 | 1707387 | 0 | 0 | 79 | 81 | 0 | 274217 | 574228 | 620942.8 |  |  | 2026-01-19 | 2026-01-18 22:45 | 2026-01-22 | 2026-01-22 17:56 | 2026-01-26 | 2026-01-29 12:01 | 2026-09-07 |  | 2026-09-10 |  | 2026-09-13 |  | 2026-01-29 | 2026-01-30 11:29 | 2026-01-30 | 2026-01-30 12:03 | 2026-03-17 | 2026-02-05 12:17 | 2026-02-27 | 2026-02-27 19:05 | 2026-09-13 |  | 2026-09-16 |  | 2026-09-16 |  | 2026-09-20 |  | 2026-09-21 |  |  |  | 2026-09-27 |  | 2026-09-28 |  | 2026-10-01 |  | 2026-10-01 | [6 empty] | 2026-10-07 |  | 2026-10-16 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-19 |  |  |  | 2026-11-10 |  | 2026-11-12 |  | 2026-11-13 | [5 empty] | 2026-10-01 |  | 2026-08-29 |  | Unknown | 2026-01-18 | 2026-01-18 22:44 | 1885079.9263 | 309262 | 0 | 0 | 0 | 0 | 1885079.9263 | 309262 | 2026-07-10 13:13:44 +0530 | Divya Rahangdale | CX will receive the possession by August. | 2026-06-29 15:04:37 +0530 | Naved Malik | Some Image was uploaded | 2026-06-02 13:34:16 +0530 | Divya Rahangdale | Some Image was uploaded
18112 | Turnkey | Dec'25 | Swati Anand zalte | Ajmera | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Shashwat Joshi | Rizwan Mistry | Murali S | Nivesh Gupta | Vinay Surve | Active | Installation | Execution | 859213 | 859213 | 875868 | 895116 | 859213 | 29 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-18 22:09 | 2026-01-20 | 2026-01-20 15:00 | 2026-01-26 | 2026-01-27 13:19 | 2026-03-04 | 2026-03-04 13:26 | 2026-03-21 | 2026-03-21 12:53 | 2026-03-22 | 2026-03-22 17:47 | 2026-01-27 | 2026-01-27 15:06 | 2026-01-28 | 2026-01-28 11:13 | 2026-01-28 | 2026-01-28 12:08 | 2026-02-03 | 2026-02-03 16:59 | 2026-03-22 | 2026-03-22 18:46 | 2026-03-28 | 2026-03-22 19:17 | 2026-03-19 | 2026-03-20 22:18 | 2026-03-31 | 2026-03-31 19:41 | 2026-04-01 | 2026-03-31 19:41 |  |  | 2026-04-23 | 2026-04-26 12:24 | 2026-04-26 | 2026-04-26 15:10 | 2026-04-29 | 2026-04-26 20:27 | 2026-04-26 | 2026-05-01 16:34 |  |  |  |  | 2026-05-06 17:54 | 2026-05-16 | 2026-05-15 22:45 | 2026-06-02 | 2026-05-28 20:25 | 2026-05-29 | 2026-06-09 16:49 | 2026-05-28 | 2026-06-13 19:02 | 2026-06-15 | 2026-06-16 18:55 | 2026-06-18 | 2026-07-03 13:18 |  |  | 2026-07-28 |  | 2026-06-09 |  | 2026-07-28 | [5 empty] | 2026-04-26 | 2026-05-06 10:59 | 2026-02-04 | 2026-03-04 12:51 | Site is RTMI | 2026-01-18 | 2026-01-18 22:08 | 1057732.607 | 164115 | 1075516.4365 | 167051 | 996158.6317 | 153947 | 996158.6317 | 153947 | 2026-07-09 08:56:57 +0530 | Nishant Jadhav | Execution: Modular furniture work in progress will be completed on 12th July bed confirmation is pending | 2026-06-22 09:49:47 +0530 | Nishant Jadhav | Execution: Modular Main load received Day 1 - 16th June 2026 Day 4 - 19th June 2026 Modular Team not align yet | 2026-06-16 15:46:58 +0530 | Riddhi Deshpande | Execution: spoke with automation team and sanskaar we cannot recommend any light fixtures or fan compatible with automation. any lights are compatible
18114 | Turnkey | Dec'25 | Mr.Dilip Gindomal Kalwani | Raymond GS | MUM - Thane | No Estimate | Rinisha Masurkar | [7 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-20 16:26 | 2026-02-08 |  | 2026-01-26 |  | 2026-02-26 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-16 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-11 |  | 2026-03-12 |  |  |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-22 |  | 2026-03-22 | [6 empty] | 2026-03-28 |  | 2026-04-06 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-09 |  |  |  | 2026-05-01 |  | 2026-05-03 |  | 2026-05-04 | [5 empty] | 2026-03-22 |  | 2026-02-17 |  | Unknown | 2026-01-18 | 2026-01-18 23:08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18115 | Turnkey | Dec'25 | Naresh Kor | Tharwani Majestic | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Asif Shaikh | Aditya Vikram | Murali S | Prashant Panigrahi | Prasad Bhivaji Hande | Completed | Complete | Completed | 963098 | 963098 | 1029033 | 951158 | 997314 | 9 | 16 | 0 | 0 | 0 | 0 |  |  | 2026-01-19 | 2026-01-20 20:01 | 2026-01-21 | 2026-01-21 19:30 | 2026-01-27 | 2026-01-27 11:23 | 2026-02-19 | 2026-02-19 11:33 | 2026-02-19 | 2026-02-19 11:40 | 2026-02-27 | 2026-02-27 13:45 | 2026-01-27 | 2026-01-28 15:06 | 2026-01-28 | 2026-01-28 15:07 | 2026-01-28 | 2026-01-30 12:09 | 2026-02-14 | 2026-02-14 15:38 | 2026-02-27 | 2026-02-27 16:04 | 2026-03-02 | 2026-02-27 23:46 | 2026-03-02 | 2026-02-27 | 2026-03-20 | 2026-03-18 16:29 | 2026-03-19 | 2026-03-18 16:29 |  |  | 2026-03-22 | 2026-03-24 21:38 | 2026-03-25 | 2026-03-25 19:53 | 2026-03-28 | 2026-03-26 11:55 | 2026-03-28 | 2026-03-30 14:18 |  |  |  |  | 2026-03-30 23:24 | 2026-05-24 | 2026-04-15 20:53 | 2026-04-21 | 2026-04-18 20:46 | 2026-04-19 | 2026-04-22 21:08 | 2026-04-18 | 2026-04-27 20:08 | 2026-04-28 | 2026-04-28 17:13 | 2026-05-11 | 2026-05-13 17:26 |  |  | 2026-06-27 | 2026-06-08 11:14 | 2026-06-29 | 2026-06-08 12:24 | 2026-06-30 | 2026-06-08 12:29 |  |  |  |  | 2026-03-30 | 2026-03-30 23:23 | 2026-02-15 | 2026-02-19 11:27 | Site is RTMI | 2026-01-18 | 2026-01-20 20:00 | 1121983.3482 | 179852 | 1047482.7455 | 167973 | 1089705.7848 | 175014 | 1058378.5689 | 169794 | 2026-06-21 16:02:56 +0530 | Asif Shaikh | Project Closure Pending: New Bed Installation - ETA - 10th July. | 2026-06-11 12:41:42 +0530 | Asif Shaikh | Project Closure Pending: Wallpaper Installtion Will be done after cx painting work -- ETA -- 20th June.New Bed ordere placed -- ETA --10th July.Closure - 10th July. | 2026-05-31 14:54:18 +0530 | Asif Shaikh | Execution: DC Completed .Pre Qc - 1st June.QC - 2nd June.
18116 | Turnkey | Dec'25 | Anand Kumar Mishra | Urban Grandeur | MUM - Thane | Yes | Sakshi Hire |  | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1413899 | 9999 | 0 | 0 | 0 | 177 | 0 | 131391 | 282780 | 502239 | 487490 |  |  | 2026-01-20 | 2026-01-19 18:01 | 2026-01-27 |  | 2026-01-19 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-20 |  | 2026-02-02 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-04 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-27 |  | 2026-02-28 |  |  |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-03-10 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-03-10 |  | 2026-02-05 |  | Unknown | 2026-01-19 | 2026-01-19 17:59 | 0 | 0 | 0 | 0 | 0 | 0 | 1198220 | 215679
18117 | Turnkey | Dec'25 | Ajith Kumar | Vaishnavi ARS Gardenia | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | Arun Kumar | Sagarika Venkatesh | Ruthwik S K | Ranjith Kumar | Murali S | Mohammed Rasick | Abdul Shafeen | Completed | Complete | Completed | 889821 | 889822 | 1061831 | 930372 | 889821 | 64 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-21 | 2026-01-20 12:21 | 2026-01-23 | 2026-01-23 12:21 | 2026-02-04 | 2026-02-04 11:18 | 2026-02-14 | 2026-02-14 16:37 | 2026-02-14 | 2026-02-14 16:43 | 2026-02-11 |  | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-05 16:05 | 2026-02-05 | 2026-02-07 20:31 | 2026-02-13 | 2026-02-13 11:20 | 2026-02-14 | 2026-02-14 18:44 | 2026-02-17 | 2026-02-15 14:23 | 2026-02-17 | 2026-02-15 14:05 | 2026-02-19 | 2026-02-19 15:40 | 2026-02-20 | 2026-02-22 17:50 |  |  | 2026-02-27 | 2026-02-28 13:33 | 2026-02-28 | 2026-02-28 15:49 | 2026-03-03 | 2026-02-28 15:58 | 2026-02-28 | 2026-03-02 11:46 |  |  |  |  | 2026-03-04 18:15 | 2026-03-13 | 2026-03-12 22:12 | 2026-03-20 | 2026-03-18 18:15 | 2026-03-19 | 2026-03-23 14:57 | 2026-03-18 | 2026-03-24 13:59 | 2026-03-24 | 2026-03-24 19:26 | 2026-04-04 | 2026-04-03 17:40 |  |  | 2026-04-23 | 2026-04-24 10:13 | 2026-04-25 | 2026-04-27 15:16 | 2026-04-26 | 2026-04-27 20:49 |  |  |  |  | 2026-02-28 | 2026-02-28 21:34 | 2026-02-14 | 2026-02-14 11:33 | Site is RTMI | 2026-01-20 | 2026-01-20 12:19 | 899856 | 161974 | 955046.8488 | 164802 | 919203.8973 | 158616 | 919203.8973 | 158616 | 2026-06-28 11:17:33 +0530 | Yogesh B | Some Image was uploaded | 2026-04-27 20:49:50 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-03-28 10:52:22 +0530 | Ranjith Kumar | Execution:
18118 | Turnkey | Dec'25 | Pankaj Kothari | Nava Bajra | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1389325 | 9999 | 0 | 0 | 0 | 176 | 0 | 128934 | 277865 | 459428 | 513099.2 |  |  | 2026-01-21 | 2026-02-27 18:07 | 2026-01-25 |  | 2026-01-31 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 |  | 2026-02-18 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-25 |  | 2026-02-26 |  |  |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-03-08 | [6 empty] | 2026-03-14 |  | 2026-03-23 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-26 |  |  |  | 2026-04-17 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-03-08 |  | 2026-02-03 |  | Unknown | 2026-01-20 | 2026-01-25 12:19 | 0 | 0 | 0 | 0 | 0 | 0 | 1177394 | 211931 | 2026-01-26 11:44:13 +0530 | Oviya A | PID: 18118 Project Timeline: Proposed project commencement during AugustSeptember. Budget: Client has not disclosed a fixed budget; however, they are comfortable within an estimated range of INR 1012 Lakhs. Occupancy Details: The residence will be occupied by 4 members. Design Theme: The overall interior design theme to follow a Minimal and Modern aesthetic. Vastu Considerations: As per the clients request, Vastu guidelines must be considered during planning and design. The house is east-facing, and layouts should be aligned accordingly wherever feasible. Client RequirementsA. Living RoomTV unit with storage and a unique design concept.Decorative treatment required on the wall opposite the main door (MD wall).False ceiling provision required.B. Dining Room4-seater dining table.Option for a foldable dining table to be explored, if feasible.False ceiling provision required.C. KitchenBase units, wall units, and loft units required.Tall unit and pantry unit to be included.Existing kitchen and utility wall to be demolished.Washing machine to be placed at the utility corner; sink provision required nearby.Wall unit with at least one glass shutter.D. Master Bedroom (MBR)Cot.Wardrobe with loft.Dressing unit.Vanity unit.E. Kids Bedroom (2 Girls)Two single cots.Separate wardrobes with loft.Study table.Vanity unit.
18120 | Turnkey | Dec'25 | Annurag Tyagi | Hiranandini estate | MUM - Thane | Yes | Mayuri Patil | [9 empty] | Active | Prospect | CDP Due | 4242351 | 9999 | 0 | 0 | 0 | 169 | 0 | 414236 | 848470 | 1495502 | 1474144 |  |  | 2026-01-21 | 2026-01-21 12:33 | 2026-01-21 | 2026-01-27 11:25 | 2026-01-20 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-20 |  | 2026-02-02 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-04 |  | 2026-02-20 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-27 |  | 2026-02-28 |  |  |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-03-10 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-03-10 |  | 2026-02-05 |  | Unknown | 2026-01-20 | 2026-01-21 12:32 | 0 | 0 | 0 | 0 | 0 | 0 | 3595213 | 647138 | 2026-01-21 12:06:45 +0530 | Mayuri Patil | Minutes of Meeting (MOM): Residential Interior ProjectProject: Anurag Tyagi Residence (Hiranandani Cardinal) Date: Sunday, May 2nd Time: 2:00 PM Location: 16th Floor, Hiranandani Cardinal Client: Anurag Tyagi & Family Project Scope: Full Interior Fit-out (1324 Sqft) 1. Client Profile & General RequirementsOccupants: Couple, pet dog (Labrador), visiting parents (75+ years), son (working in Pune), and daughter (studying in Delhi).Work Profile: Anurag works for an MNC with a "Work From Home" requirement at least once a week.Core Philosophy: Strict adherence to Vastu considerations.Budget/Estimate: 25 Lacs 35 Lacs.2. Civil & General WorksEntry: Install a safety door and shoe rack (with bench seating). The existing main door is to be retained.Flooring: Epoxy flooring for the Living and Dining areas. Anti-slip tiles specifically for the parents' room.Ceiling & Walls: Full false ceiling, painting, and electrical work across the apartment.Balcony: Leveling of the balcony floor is required.3. Kitchen & DiningConcept: Open kitchen concept with a French door for the fridge area.Specs: Full-fledged modular kitchen with Quartz countertops.Dining: 6-seater dining table with bench-style seating.Bar: Dedicated bar area to be planned in the utility space.4. Living AreaEntertainment: 6065 inch TV with a dedicated TV unit.Seating: Recliner sofas and a swing in the deck/balcony area.Mandir: To be placed strictly on the East wall.Lighting: Spotlights and track lights to be installed.5. Bedroom SpecificationsMaster BedroomBed: King-size bed (7ft length) with side tables (x2) and a dresser.Storage: Sliding wardrobe with loft and a chest of drawers.Features: Dedicated TV unit.Kids' Room (Ruchir & Ridhima)Bed: King-size bed with hydraulic storage.Storage: 7ft sliding wardrobe (Aristo) with loft.Study: Study unit with wall shelves.Features: TV unit, side table, and mirror.Bedroom 2 (Parents / Guests)User: Elderly parents (75+ yrs).Furniture: King-size bed (The Sleep Company) with hydraulic storage and side tables.Safety/Accessibility: Sliding washroom door (without lock) and anti-slip tiles.Storage: Wardrobe and TV unit.6. Specialized Spaces & UtilityShaft Area: Utilized for an "Invisible Bed" (pull-down/murphy bed) and general utility.Library: A library unit/area to be integrated.Walk-in Wardrobe: Sliding walk-in wardrobe to be designed.Common Toilet: Integrated utility area.
18121 | Turnkey | Dec'25 | nitin bhurke | taruvel society | MUM - GOR | Yes | Manisha Dubey | Reshma Melanta | Shantanu Parakh | [5 empty] | Umang Shah |  | Hold | Design | Design Finalization | 1226184 | 159999 | 1529789 | 0 | 0 | 57 | 67 | 0 | 207856 | 423183 | 435146 |  |  | 2026-01-19 | 2026-02-11 15:42 | 2026-03-07 | 2026-03-07 22:01 | 2026-03-07 | 2026-03-07 22:03 | 2026-11-09 |  | 2026-11-12 |  | 2026-11-15 |  | 2026-03-07 | 2026-03-11 17:46 | 2026-03-08 | 2026-03-12 12:36 | 2026-03-12 | 2026-03-13 11:45 | 2026-03-31 | 2026-03-31 17:08 | 2026-11-15 |  | 2026-11-18 |  | 2026-11-18 |  | 2026-11-22 |  | 2026-11-23 |  |  |  | 2026-11-29 |  | 2026-11-30 |  | 2026-12-03 |  | 2026-12-03 | [6 empty] | 2026-12-09 |  | 2026-12-18 |  | 2026-12-17 |  | 2026-12-18 |  | 2026-12-19 |  | 2026-12-21 |  |  |  | 2027-01-12 |  | 2027-01-14 |  | 2027-01-15 | [5 empty] | 2026-12-03 |  | 2026-10-31 |  | Unknown | 2026-01-18 | 2026-02-11 15:41 | 1296431 | 233357 | 0 | 0 | 0 | 0 | 1269617.0208 | 219079 | 2026-05-09 16:29:16 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-09 11:26:36 +0530 | Reshma Melanta | ADDED MYSELF TO THE GROUP | 2026-03-31 17:04:11 +0530 | Reshma Melanta | WELCOME CALL DONE POSSESSION IN THE MONTH OF - SEPT - OCT 2026 THE CLIENT IN 1 MONTH TIME WILL NEED ELECTRITRAL DRAWING TO BE PROVIDED BY THE DESIGNERR TO BE GIVEN TO THE BUILDER NOT ADDED MYSELF TO THE GROUP NEW DESIGNER NOT ADDED THE NET DESIGNER IS YASH
18122 | Turnkey | Dec'25 | Chirag Shah | Vasupuja darshan | MUM - GOR | Yes | Priyanka Patel |  | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 3227358 | 9999 | 3227358 | 0 | 0 | 147 | 0 | 312737 | 645472 | 1047540 | 1211610.8 |  |  | 2026-01-19 | 2026-01-20 15:06 | 2026-01-21 | 2026-01-21 13:02 | 2026-02-18 | 2026-02-18 19:31 | 2026-03-02 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-03-08 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-15 |  | 2026-03-16 |  |  |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-26 |  | 2026-03-26 | [6 empty] | 2026-04-01 |  | 2026-04-10 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-13 |  |  |  | 2026-05-05 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-03-26 |  | 2026-02-21 |  | Site is RTMI | 2026-01-18 | 2026-01-20 15:06 | 2735049 | 492308 | 0 | 0 | 0 | 0 | 2735049 | 492308
18123 | Turnkey | Dec'25 | Neha Dhani | Manan water leaf | BNG - HRBR | Yes | Chandini Nj | Rajeshwari S | Yogesh Patidar | [5 empty] | Janvi Nagdeo |  | Active | Prospect | CDP Due | 1491698 | 9999 | 1491698 | 0 | 0 | 176 | 0 | 139171 | 298340 | 471663 | 572526 |  |  | 2026-01-19 | 2026-01-20 17:57 | 2026-01-20 | 2026-01-20 19:03 | 2026-01-25 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-01-25 |  | 2026-01-26 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-19 |  | 2026-02-20 |  |  |  | 2026-02-26 |  | 2026-02-27 |  | 2026-03-02 |  | 2026-03-02 | [6 empty] | 2026-03-08 |  | 2026-03-17 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-20 |  |  |  | 2026-04-11 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-03-02 |  | 2026-01-28 |  | Unknown | 2026-01-18 | 2026-01-20 15:29 | 1264151 | 227547 | 0 | 0 | 0 | 0 | 1264151 | 227547 | 2026-01-20 19:03:15 +0530 | Chandini Nj | Possession - ready to move in Budget - 10 to 15L Apartment-manan water liaf Theme-Italian mid century but client is looking for indiam theme and we have to work on reference images Direction - east How many people are going to stay - 2 peopleÂ Â Work ProfileÂ husband (transportation business) wife (it) Purpose (Rental/Own) -OWN Purpose Deeper understanding (Usual hobbies):travelling Living area - TV unit (as per the reference) U shape sofa (Will check the space) Dining area - as per reference along with drawers.Â and swingÂ Guest bedroom - Study unit, wardrobe with bay seating storageÂ Kitchen - Breakfast table, Crockery Tall unit with base wall glass and loft, 2ft hob chimney. 2FT fridge as per that Â reference and Base and wall unit and loft wooden entry panelling,. Master bedroom - Walk in wardrobe as per the reference image, Other side closed wardrobe with loft. Â Â Â Â Â Â Â Â Â King size bed, wardrobe with loft (Rattan pattern) Â Vanities for both the rooms, | 2026-01-20 19:02:13 +0530 | Chandini Nj | Possession - ready to move in Budget -Â Apartment-manan water liaf Theme- Direction - east How many people are going to stay - 2 peopleÂ Â Work ProfileÂ husband (transportation business) wife (it) Purpose (Rental/Own) -OWN Purpose Deeper understanding (Usual hobbies):travelling Living area - TV unit (as per the reference) U shape sofa (Will check the space) Dining area - as per reference along with drawers.Â and swingÂ Guest bedroom - Study unit, wardrobe with bay seating storageÂ Kitchen - Breakfast table, Crockery Tall unit with base wall glass and loft, 2ft hob chimney. 2FT fridge as per that Â reference and Base and wall unit and loft wooden entry panelling,. Master bedroom - Walk in wardrobe as per the reference image, Other side closed wardrobe with loft. Â Â Â Â Â Â Â Â Â King size bed, wardrobe with loft (Rattan pattern) Â Vanities for both the rooms,
18124 | Turnkey | Dec'25 | diksha sapkal Sapkal | RUNWAL FOREST | MUM - Thane | Yes | Maasoumeh Raza | [9 empty] | Active | Prospect | CDP Due | 2485823 | 9999 | 0 | 0 | 0 | 174 | 0 | 238583 | 497165 | 826464 | 913612.4 |  |  | 2026-01-21 | 2026-01-20 17:06 | 2026-01-22 | 2026-01-22 11:02 | 2026-01-23 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-20 | 2026-01-20 16:18 | 0 | 0 | 0 | 0 | 0 | 0 | 2106629 | 379193 | 2026-01-20 17:54:17 +0530 | Moksh Mehta | DCM: Client Name: - Diksha Sapkal Property: - Runwal Forest Possession Date: - In Hand Sq Ft: - 1081 sqft No of Members: - 4 Member's (Couple 47+, Daughter 20 & 13) Budget:- 15 L Ent: Shoe Rack (25 - 30 Pairs) Inside Wall Concepts. Living Room :- TV Unit existing 56" inch / Expandable upto 65" inch3 Seater Sofa + 1 Chair + 1 Chair (4 - 5 People's)Wall concepts.Texture Paint. Dining Area :- 6 Seater Dining Table ( Chair's + Bench Combination ).Crockery Unit only base.Mandir Space to be provided with East - West Direction.Wall Concepts. Kitchen :- Semi Modular KitchenBase - 2 nos , Wall - 2nos & Loft - 1 nosCrockery Storage. Master Bedroom :- Design Simple & Elegant Queen size Bed.Wardrobe with Loft.Side tale with Dresser.Folding study Table (900mm width) Second Bedroom :- Queen size BedWardrobe with loftDresser with Side TableFolding Study with Wall Storage ( As per Vastu )Bean Bag Third Master Bedroom :- Queen size BedWardrobe with LoftSide TableFixed Study with wall Storage (900mm) for PCMirror on the side of wardrobe Bathroom's Base Vanity Unit's for all.2 Shelves in Utility area. Misc:- False CeilingPaintingElectrification | 2026-01-20 16:47:43 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-01-20 16:47:19 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
18125 | Turnkey | Dec'25 | Sandeep Yasodharan (ICON Engineering Construction & Consultants) | Lodha Upper | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [7 empty] | Hold | Design | Design Finalization | 1438017 | 157800 | 1438017 | 0 | 0 | 91 | 62 | 0 | 273605 | 483740 | 522872.4 |  |  | 2026-01-21 | 2026-01-23 13:50 | 2026-01-31 | 2026-01-31 15:43 | 2026-01-31 | 2026-01-31 20:32 | 2026-09-09 |  | 2026-09-12 |  | 2026-09-15 |  | 2026-01-31 | 2026-01-31 05:30 | 2026-02-01 | 2026-02-02 16:53 | 2026-02-02 | 2026-02-12 18:19 | 2026-02-26 | 2026-02-26 18:55 | 2026-09-15 |  | 2026-09-18 |  | 2026-09-18 |  | 2026-09-22 |  | 2026-09-23 |  |  |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-03 |  | 2026-10-03 | [6 empty] | 2026-10-09 |  | 2026-10-18 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-21 |  |  |  | 2026-11-12 |  | 2026-11-14 |  | 2026-11-15 | [5 empty] | 2026-10-03 |  | 2026-08-31 |  | Unknown | 2026-01-20 | 2026-01-21 17:16 | 1604809.386 | 255968 | 0 | 0 | 0 | 0 | 1604809.386 | 255968 | 2026-07-03 16:15:43 +0530 | Anamika Dolai | Hold till 31st of August | 2026-07-03 16:10:38 +0530 | Anamika Dolai | Client is not responding | 2026-03-30 17:58:37 +0530 | Pooja Metre | Some Image was uploaded
18126 | Turnkey | Dec'25 | Sucheta Jadhao | Kamdhenu | MUM - Thane | No Estimate | [10 empty] | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-21 | 2026-01-23 12:35 | 2026-01-21 |  | 2026-02-20 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-03-10 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-28 |  | 2026-03-28 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-28 |  | 2026-02-23 |  | Unknown | 2026-01-20 | 2026-01-21 17:29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18127 | Turnkey | Dec'25 | Anamika patil | Gottigere Balaji Gardens | MUM - Thane | Yes | Mayuri Patil | [9 empty] | Active | Prospect | CDP Due | 1654366 | 9999 | 0 | 0 | 0 | 151 | 0 | 155438 | 330873 | 522934 | 635122.4 |  |  | 2026-01-21 | 2026-02-13 13:32 | 2026-02-13 | 2026-02-14 11:26 | 2026-02-20 |  | 2026-03-04 |  | 2026-03-07 |  | 2026-03-10 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-03-10 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-28 |  | 2026-03-28 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-28 |  | 2026-02-23 |  | Unknown | 2026-01-20 | 2026-02-06 10:57 | 0 | 0 | 0 | 0 | 0 | 0 | 1676172.4931 | 276767 | 2026-01-30 19:30:54 +0530 | Moksh Mehta | DCM: Name: - Anamika Patil Possession Date: - In Hand Sqft :- 765 Sqft No of Members: - Mother ( 47+) + Son (21+) Flat No: - B-305 Budget:- 15L Ent: - Shoe Unit Out side. (Optional).Wall Concepts. Living: - 3-seater SofaTV Unit ( 50 - 60")4-seater dining tableCrockery UnitMandir UnitWall Concepts Kitchen: - Base Unit x 2 NosWall Unit x 2 NosLoft Unit x 1nosFully Modular Kitchen with Civil work Master Bedroom: - Queen size Bed.Wardrobe with Loft & Dresser Unit.Side table wall mounted.TV Ledge.Arm Chair or Window Bay Seating. Son Bedroom: - Queen size Bed Wardrobe with Loft / Glass Door'sStudy Table Full size mirror Side Table Bathroom's: - Vanity unit base x 2nos Misc: - False ceilingPaintingElectricalDeck Area Brief: - Neutral ShadesSpacious Look & FeelContrast furnitureLuxe look & Feel | 2026-01-20 21:50:57 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-01-20 21:49:28 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded
18128 | Turnkey | Dec'25 | Kapil Umare | Lodha Crown Kolshet | MUM - Thane | Yes | Pooja Nakul Sharma | [9 empty] | Active | Prospect | CDP Due | 3546236 | 9999 | 0 | 0 | 0 | 174 | 0 | 344625 | 709247 | 1074241 | 1408124 |  |  | 2026-01-11 | 2026-01-21 12:30 | 2026-01-22 | 2026-01-22 11:55 | 2026-01-21 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-05 |  | 2026-03-05 | [6 empty] | 2026-03-11 |  | 2026-03-20 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-23 |  |  |  | 2026-04-14 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-03-05 |  | 2026-01-31 |  | Unknown | 2026-01-10 | 2026-01-21 12:28 | 0 | 0 | 0 | 0 | 0 | 0 | 3005284 | 540951
18129 | Sub Project |  | Pravin Varade | Mangeshi Tulip | MUM - Thane |  | Rinisha Masurkar | Divya Rahangdale |  |  |  | Asif Shaikh | Aditya Vikram | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-22 | 2026-01-21 17:42 | 2026-01-22 | 2026-01-21 17:42 | 2026-01-23 | 2026-01-21 17:42 | 2026-01-23 | 2026-01-21 17:44 | 2026-01-22 | 2026-01-21 17:44 | 2026-01-22 | 2026-01-21 17:45 | 2026-01-21 | 2026-01-21 17:43 | 2026-01-22 | 2026-01-21 17:43 | 2026-01-21 | 2026-01-21 17:43 | 2026-01-22 | 2026-01-21 17:43 | 2026-01-21 | 2026-01-21 17:45 | 2026-01-24 | 2026-01-21 17:46 | 2026-01-21 | 2026-01-21 17:46 | 2026-01-24 | 2026-01-21 17:47 | 2026-01-23 | 2026-01-21 17:47 |  |  | 2026-01-24 | 2026-01-21 17:49 | 2026-01-22 | 2026-01-21 18:05 | 2026-01-24 | 2026-01-21 18:08 | 2026-01-21 | 2026-01-21 18:08 |  |  |  |  | 2026-01-22 18:22 | 2026-01-23 | 2026-01-22 18:54 | 2026-01-28 | 2026-01-23 15:37 | 2026-01-24 | 2026-02-24 15:26 | 2026-01-23 | 2026-02-24 15:47 | 2026-02-19 | 2026-02-24 15:48 | 2026-02-25 | 2026-02-24 17:05 |  |  | 2026-02-26 | 2026-02-24 17:22 | 2026-02-26 | 2026-02-24 17:24 | 2026-02-24 | 2026-02-24 18:00 |  |  |  |  | 2026-01-21 | 2026-01-22 12:33 | 2026-01-22 | 2026-01-21 17:43 | Unknown | 2026-01-21 | 2026-01-21 17:42 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | 2026-01-23 08:58:27 +0530 | Asif Shaikh | Some Image was uploaded
18130 | Sub Project |  | sheetal pandey | MXOthers | MUM - GOR |  | Pratima Kajwe | Manzoor Shaikh | Safalta Karkera |  |  | Uday Yadruk | Rizwan Mistry | Murali S |  |  | Active | Handover | Project Closure Pending | 173442 | 174606 | 0 | 0 | 178450 | 153 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-22 | 2026-01-29 13:18 | 2026-01-22 | 2026-01-29 13:18 | 2026-01-31 | 2026-01-29 13:19 | 2026-01-31 | 2026-01-29 13:21 | 2026-01-30 | 2026-01-29 13:22 | 2026-01-30 | 2026-01-29 13:23 | 2026-01-29 | 2026-01-29 13:19 | 2026-01-30 | 2026-01-29 13:19 | 2026-01-29 | 2026-01-29 13:20 | 2026-01-30 | 2026-01-29 13:20 | 2026-01-29 | 2026-01-29 13:24 | 2026-02-01 | 2026-01-29 13:24 | 2026-01-29 | 2026-01-29 13:24 | 2026-01-30 | 2026-01-29 13:25 | 2026-01-30 | 2026-01-29 13:25 |  |  | 2026-02-01 | 2026-01-29 13:31 | 2026-01-30 | 2026-01-29 13:32 | 2026-02-01 | 2026-01-29 13:33 | 2026-03-05 | 2026-01-29 13:17 |  |  |  |  | 2026-01-29 22:14 | 2026-02-03 | 2026-02-02 16:04 | 2026-02-06 | 2026-02-04 14:29 | 2026-02-05 | 2026-02-12 14:51 | 2026-02-04 | 2026-02-12 15:21 | 2026-02-12 | 2026-02-12 15:23 | 2026-02-12 | 2026-02-12 19:34 |  |  | 2026-02-14 | 2026-02-12 22:58 | 2026-02-14 | 2026-02-12 23:01 | 2026-02-12 | 2026-02-12 23:04 |  |  |  |  | 2026-01-29 | 2026-01-29 22:13 | 2026-01-30 | 2026-01-29 13:20 | Unknown | 2026-01-21 | 2026-01-22 19:16 | 0 | 0 | 0 | 0 | 151228 | 27221 | 146985 | 26457 | 2026-01-22 11:25:46 +0530 | Pratima Kajwe | Some Image was uploaded
18131 | Turnkey | Dec'25 | Naga Deepthi | Ankura Meridian | BNG - HRBR | Yes |  | Rajeshwari S | [8 empty] | Active | Prospect | DCM Due | 2149399 | 9999 | 0 | 0 | 0 | 175 | 0 | 204941 | 429880 | 661369 | 843210 |  |  | 2026-01-22 | 2026-01-21 15:29 | 2026-01-21 |  | 2026-01-25 |  | 2026-02-08 |  | 2026-02-11 |  | 2026-02-14 |  | 2026-01-27 |  | 2026-01-28 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-02-14 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-21 |  | 2026-02-22 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-04 |  | 2026-03-04 | [6 empty] | 2026-03-10 |  | 2026-03-19 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-22 |  |  |  | 2026-04-13 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-03-04 |  | 2026-01-30 |  | Unknown | 2026-01-21 | 2026-01-21 13:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1821524 | 327874 | 2026-01-25 15:45:38 +0530 | Losii Athisa | Some Image was uploaded | 2026-01-21 15:31:34 +0530 | Rhea Rathod | DCM: - East facing - Family of 4 - Budget - 18 lakhs Foyer - Wall depth on the right to be checked. - A wall on the left to be constructed - Shoe rack to be checked - outside or inside Dining /kitchen - - Pooja unit - north east corner - pooja - sit and pray, decorativeÂ - Continue the kitchen as per the plan after crockery unit - Utility wall to be checked - crockery unit next to pooja - base units, wall units, no loft - Appliance unitÂ - Wooden false ceiling with chandelier Living area - - Wall to be constructedÂ - Tv unit on the north wall - Sofa - l seater with pouf - swing to be accommodatedÂ - Wall mounted tv unit - 65" tvÂ - wall concepts to be proposed - False ceiling - designs to be proposed Master bedroom - - 2 work stations- one next to the wardrobe the other next to the balcony - L shaped wardrobe with loft - Queen size bed - Dresser to be planned on the right side of the bed Bedroom 1 - Left - Son's bedroom - Wardrobe With loft - Study tableÂ - Bay window seater - loose furniture Â Bedroom 2 - Right - Daughter's bedroom - Wardrobe With loft - Study tableÂ - Bay window seater - loose furniture
18134 | Turnkey | Dec'25 | Amit Edvankar | L$T west square | MUM - GOR | Yes | Shweta Dalvi | Reshma Melanta | Safalta Karkera |  | Ehtesham Bhati | Yash Metha | Akshat Shrivastava | Murali S | Rashmita Das | Prasad Bhivaji Hande | Active | Installation | Execution | 2533924 | 2533924 | 1685248 | 2634332 | 2533924 | 55 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-01-22 | 2026-01-31 00:37 | 2026-02-01 | 2026-02-01 18:46 | 2026-02-01 | 2026-02-01 19:01 | 2026-02-26 | 2026-02-26 14:21 | 2026-02-26 | 2026-02-26 14:23 | 2026-02-27 | 2026-02-26 16:46 | 2026-02-01 | 2026-01-31 05:30 | 2026-02-02 | 2026-02-05 18:37 | 2026-02-05 | 2026-02-13 18:19 | 2026-02-17 | 2026-02-17 13:49 | 2026-02-26 | 2026-02-27 16:47 | 2026-03-02 | 2026-02-27 17:05 | 2026-02-26 | 2026-02-26 16:58 | 2026-03-13 | 2026-03-13 00:16 | 2026-03-14 | 2026-03-13 00:16 |  |  | 2026-03-30 | 2026-04-03 16:11 | 2026-04-11 | 2026-04-11 20:28 | 2026-04-14 | 2026-04-11 20:53 | 2026-04-11 | 2026-04-14 18:55 |  |  |  |  | 2026-04-15 19:11 | 2026-04-24 | 2026-04-23 19:32 | 2026-05-15 | 2026-05-14 19:14 | 2026-05-14 | 2026-05-07 19:34 | 2026-05-14 | 2026-05-19 11:24 | 2026-05-19 | 2026-05-21 16:53 | 2026-05-23 | 2026-06-19 14:00 |  |  | 2026-05-16 |  | 2026-05-18 |  | 2026-07-22 | [5 empty] | 2026-04-11 | 2026-04-15 16:20 | 2026-02-18 | 2026-02-26 14:19 | Site is RTMI | 2026-01-21 | 2026-01-21 18:03 | 1742944.5975 | 287580 | 2943938.4097 | 478118 | 2791922.6206 | 446022 | 2791922.6206 | 446022 | 2026-07-13 11:00:00 +0530 | Yash Metha | Execution: All modular done Final painting ETA - 14th July (Aapka Painter) Deep cleaning - 15th July 2 beds, and sofa, headboard - ready at vendor's place - Delivery date - 14th July (Aadeshwar) SQC 2 & HO - 16th July For the record, Sprinkler Extension work under the Client scope is yet to be completed and is currently pending. | 2026-07-13 08:46:59 +0530 | Yash Metha | Execution: All modular done Final painting ETA - 14th July (Aapka Painter) Deep cleaning - 15th July 2 beds, and sofa, headboard - ready at vendor's place - Delivery date - 14th July (Aadeshwar) SQC 2 & HO - 16th July | 2026-06-24 08:02:16 +0530 | Yash Metha | Some Image was uploaded
18135 | Turnkey | Dec'25 | Poongothai Senthil Kumar | NA | BNG - HRBR | Yes |  |  |  |  | Sagarika Venkatesh |  |  |  | Janvi Nagdeo |  | Active | Prospect | DCM Due | 1586099 | 9999 | 0 | 0 | 0 | 175 | 0 | 148611 | 317220 | 505049 | 605220 |  |  | 2026-01-22 | 2026-01-23 19:00 | 2026-01-22 |  | 2026-01-31 |  | 2026-02-12 |  | 2026-02-15 |  | 2026-02-18 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 |  | 2026-02-18 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-25 |  | 2026-02-26 |  |  |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-03-08 | [6 empty] | 2026-03-14 |  | 2026-03-23 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-26 |  |  |  | 2026-04-17 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-03-08 |  | 2026-02-03 |  | Unknown | 2026-01-21 | 2026-01-21 20:09 | 0 | 0 | 0 | 0 | 0 | 0 | 1344152 | 241947 | 2026-04-14 16:37:18 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-04-14 16:35:26 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-01-22 11:17:38 +0530 | Sagarika Venkatesh | Some Image was uploaded
18136 | Turnkey | Dec'25 | Sunil Khapne | krishna residency | MUM - GOR | Yes | Saif Shaikh |  | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1163708 | 9999 | 0 | 0 | 0 | 174 | 0 | 106372 | 232742 | 381005 | 433590.4 |  |  | 2026-01-23 | 2026-01-22 16:09 | 2026-01-23 |  | 2026-01-22 |  | 2026-02-03 |  | 2026-02-06 |  | 2026-02-09 |  | 2026-01-22 |  | 2026-01-23 |  | 2026-01-23 |  | 2026-01-24 |  | 2026-02-09 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-27 |  | 2026-02-27 | [6 empty] | 2026-03-05 |  | 2026-03-14 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-17 |  |  |  | 2026-04-08 |  | 2026-04-10 |  | 2026-04-11 | [5 empty] | 2026-02-27 |  | 2026-01-25 |  | Unknown | 2026-01-22 | 2026-01-22 16:08 | 0 | 0 | 0 | 0 | 0 | 0 | 986193 | 177514
18137 | Turnkey | Dec'25 | Ankit | wing 7 Royal Pavillion (3) | BNG - HSR | Yes | Shefali | Akshay Ds | Kowshik |  | Sethuragavan R | Yogeshwaran | Ranjith Kumar | Murali S | Pulivarthi Nirosha | Sunil Kumar S M | Active | Handover | Project Closure Pending | 425941 | 425941 | 1165947 | 426446 | 425941 | 12 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-01-23 | 2026-01-28 12:05 | 2026-01-28 | 2026-01-28 12:17 | 2026-01-30 | 2026-01-28 12:39 | 2026-02-27 | 2026-02-27 14:44 | 2026-03-05 | 2026-03-05 19:31 | 2026-05-15 | 2026-05-15 15:58 | 2026-01-28 | 2026-01-31 05:30 | 2026-01-29 | 2026-02-03 17:36 | 2026-02-03 | 2026-02-03 18:33 | 2026-02-05 | 2026-02-05 16:02 | 2026-09-06 | 2026-05-16 19:34 | 2026-09-09 | 2026-05-16 19:47 | 2026-09-09 | 2026-05-16 19:31 | 2026-05-20 | 2026-05-20 15:47 | 2026-05-21 | 2026-05-20 17:02 |  |  | 2026-05-24 | 2026-05-21 19:39 | 2026-05-21 | 2026-05-21 22:10 | 2026-09-24 | 2026-05-22 04:12 | 2026-05-22 | 2026-05-25 17:56 |  |  |  |  | 2026-05-28 17:25 | 2026-06-05 | 2026-06-04 21:19 | 2026-06-12 | 2026-06-10 18:11 | 2026-06-11 | 2026-06-11 18:43 | 2026-06-10 | 2026-06-13 15:40 | 2026-06-13 | 2026-06-13 21:45 | 2026-06-15 | 2026-06-17 11:48 |  |  | 2026-07-02 | 2026-07-03 21:47 | 2026-07-04 | 2026-07-03 21:48 | 2026-07-05 | 2026-07-03 22:38 |  |  |  |  | 2026-05-25 | 2026-05-28 17:24 | 2026-02-06 | 2026-02-27 14:34 | Site is RTMI | 2026-01-22 | 2026-01-27 14:02 | 1163281.8635 | 200737 | 434368.634 | 66576 | 433922.244 | 66499 | 433922.244 | 66499 | 2026-06-17 12:41:56 +0530 | Ranjith Kumar | Execution: | 2026-06-12 07:24:36 +0530 | Ranjith Kumar | Dispatch Due: | 2026-05-28 17:25:03 +0530 | Ranjith Kumar | Procurement:
18138 | Turnkey | Dec'25 | Aakanksha Tavhare | Raymond Tenex Haitat | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Design | Design Finalization | 1082627 | 156999 | 1464272 | 0 | 0 | 77 | 70 | 0 | 167789 | 337546 | 420293.2 |  |  | 2026-01-23 | 2026-01-28 15:37 | 2026-02-17 | 2026-02-17 11:17 | 2026-02-17 | 2026-02-17 13:38 | 2027-02-13 |  | 2027-02-16 |  | 2027-02-19 |  | 2026-02-17 | 2026-02-17 19:07 | 2026-02-18 | 2026-02-17 20:18 | 2026-02-17 | 2026-02-18 17:00 | 2026-02-26 | 2026-02-26 18:56 | 2027-02-19 |  | 2027-02-22 |  | 2027-02-22 |  | 2027-02-26 |  | 2027-02-27 |  |  |  | 2027-03-05 |  | 2027-03-06 |  | 2027-03-09 |  | 2027-03-09 | [6 empty] | 2027-03-15 |  | 2027-03-24 |  | 2027-03-23 |  | 2027-03-24 |  | 2027-03-25 |  | 2027-03-27 |  |  |  | 2027-04-18 |  | 2027-04-20 |  | 2027-04-21 | [5 empty] | 2027-03-09 |  | 2026-12-31 |  | Unknown | 2026-01-22 | 2026-01-28 15:36 | 1240909 | 223363 | 0 | 0 | 0 | 0 | 1202519.2707 | 189553 | 2026-07-10 13:41:44 +0530 | Divya Rahangdale | The client has received possession and would like to proceed with the design meeting. | 2026-07-02 14:11:18 +0530 | Divya Rahangdale | Hold | 2026-06-26 13:28:03 +0530 | Harshali Bhuyar | Some Image was uploaded
18140 | Turnkey | Dec'25 | Manan Savla | Arham Mourya | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 2422690 | 9999 | 2422690 | 0 | 0 | 147 | 0 | 232270 | 484538 | 733772 | 962111.2 |  |  | 2026-01-24 | 2026-02-01 12:15 | 2026-02-01 | 2026-02-18 19:17 | 2026-02-24 | 2026-02-18 19:23 | 2026-03-02 |  | 2026-03-05 |  | 2026-03-08 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-03-08 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-15 |  | 2026-03-16 |  |  |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-26 |  | 2026-03-26 | [6 empty] | 2026-04-01 |  | 2026-04-10 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-13 |  |  |  | 2026-05-05 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-03-26 |  | 2026-02-21 |  | Unknown | 2026-01-23 | 2026-01-23 16:04 | 2053127 | 369562 | 0 | 0 | 0 | 0 | 2053127 | 369562 | 2026-03-24 15:21:49 +0530 | Hitesh Rawal | Some Image was uploaded
18141 | Turnkey | 2026-01-01 | Amita Mistry | Kabra Garnet Â­ | MUM - GOR | Yes | Swapnali Shedekar | Reshma Melanta | Safalta Karkera |  |  | Nishant Jadhav | Sandeep Tiwari |  | Saloni Sagwekar | Siddhesh Gujrathi | Active | Preproduction | DEM2 | 1102642 | 220529 | 1102642 | 0 | 0 | 93 | 0 | 0 | 0 | 453677 | 428435.6 |  |  | 2026-01-23 | 2026-01-24 11:15 | 2026-02-05 | 2026-02-05 12:01 | 2026-02-05 | 2026-02-05 17:43 | 2026-03-27 | 2026-03-28 19:38 | 2026-05-24 | 2026-06-21 10:32 | 2026-06-27 |  | 2026-02-05 | 2026-01-31 05:30 | 2026-02-06 | 2026-02-07 12:03 | 2026-02-07 | 2026-02-10 10:52 | 2026-02-20 | 2026-02-20 19:03 |  |  |  |  | 2026-03-28 | 2026-04-13 19:46 | 2026-06-22 |  | 2026-06-23 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-02-21 | 2026-03-26 17:45 | Site is RTMI | 2026-01-23 | 2026-01-24 11:12 | 1160680.6155 | 191081 | 0 | 0 | 0 | 0 | 1160680.6155 | 191081 | 2026-04-27 18:18:02 +0530 | Swapnali Shedekar | Some Image was uploaded | 2026-04-11 19:07:39 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-09 18:20:34 +0530 | Swapnali Shedekar | Material selection meeting is aligned on 11th April Saturday at 3:00pm - 7:00pm | 2026-03-29 | 2026-03-28 19:44 | 2026-06-22 | 2026-06-21 10:33
18143 | Turnkey | 2026-01-01 | Haradhan Hait | sejal reality | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Kashmira Nerurkar |  |  | Nilesh Patel | Rizwan Mistry | Murali S | Ashish Jha | Aakash Gaikwad | Hold | Preproduction | Site Readiness 2 | 1439207 | 910871 | 1539659 | 0 | 1439207 | 8 | 21 | 0 | 0 | 0 | 528336 |  |  | 2026-01-23 | 2026-01-25 14:08 | 2026-01-26 | 2026-01-26 10:17 | 2026-01-26 | 2026-01-26 10:54 | 2026-02-03 | 2026-03-25 15:44 | 2026-02-10 | 2026-04-15 12:45 | 2026-05-15 | 2026-05-15 13:52 | 2026-01-26 | 2026-01-28 12:54 | 2026-01-27 | 2026-01-30 10:40 | 2026-01-28 | 2026-02-03 15:23 | 2026-02-08 | 2026-02-08 13:42 |  |  |  |  | 2026-02-04 | 2026-04-06 18:28 | 2026-02-12 | 2026-04-15 18:33 | 2026-04-16 | 2026-04-15 18:34 |  |  | 2026-05-26 | 2026-05-29 13:16 | 2026-06-05 | 2026-06-05 17:39 | 2026-06-06 | 2026-06-06 17:34 | 2026-06-21 | 2026-06-25 18:04 | [5 empty] | 2026-08-05 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-06-05 |  | 2026-02-09 | 2026-03-17 12:30 | Site is RTMI | 2026-01-23 | 2026-01-24 14:52 | 1304796 | 234863 | 0 | 0 | 1582730.6055 | 257675 | 1582730.6055 | 257675 | 2026-07-03 12:46:16 +0530 | Manzoor Shaikh | Others: The client has not received the possession. | 2026-05-27 12:28:14 +0530 | Saakshi Bhute | Some Image was uploaded | 2026-05-26 18:11:30 +0530 | Saakshi Bhute | Some Image was uploaded | 2026-03-26 | 2026-03-25 15:47 | 2026-04-16 | 2026-04-15 12:58
18144 | Turnkey | 2026-01-01 | Saveetha Rudramoorthy | DNR Arista | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 1932373 | 9999 | 1932373 | 0 | 0 | 165 | 0 | 183238 | 193237 | 775488 | 770410 |  |  | 2026-01-24 | 2026-01-24 14:33 | 2026-01-30 | 2026-01-30 18:28 | 2026-01-31 | 2026-01-31 18:55 | 2026-02-07 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 | [5 empty] | 2026-02-08 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-27 | [6 empty] | 2026-03-17 |  | 2026-03-26 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-29 |  |  |  | 2026-04-20 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-02-25 |  | 2026-02-03 |  | Unknown | 2026-01-24 | 2026-01-24 14:32 | 1637604 | 294768 | 0 | 0 | 0 | 0 | 1637604 | 294768 | 2026-01-26 16:03:45 +0530 | Oviya A | PID 18144 1.Project OverviewCeiling Height: 9-0Budget Range: 1015 LakhsOccupancy: 4 membersDesign Theme: ModernColor Palette: Light shades of Green and BlueProject Status: The apartment is ready to move in; interior design and execution to be planned in alignment with the July shifting schedule. 2. Foyer AreaShoe rack with integrated seaterOne tall storage unitAdditional storage provisionsBottom open shelf in shoe rack design 3. Living AreaOption 1TV unit placement as per architectural drawingSemi-foldable partition between living and diningPeripheral false ceilingOption 2Fixed partition wall between living and diningPartition wall to function as TV unitPeripheral false ceiling 4. Dining AreaPooja unit integrated with crockery storage near partition wallHighlight wall treatment on bedroom-facing wallIsland-style false ceiling 5. KitchenL-shaped kitchen layoutDouble-door refrigerator placement near breakfast counterTall unitWall-mounted cabinetsRolling shutter unit for grinder and mixerLoft storageBreakfast counter at refrigerator location 6. Utility AreaSink provisionWashing machine spaceStorage for two gas cylindersWall-mounted storage unitDishwasher provision (preferred in utility; or to be placed in kitchen if required) 7. Master BedroomAristo sliding wardrobeKing-size bedFalse ceilingTV unit integrated with study and bookshelf storageDressing mirror near bedside tableAttached BathroomVanity unitGlass shower partition 8. Bedroom Near Dining Area (Girls Room)Sliding wardrobe with full loft storageStudy unit with bookshelf and dressing unitFull-length dressing mirrorVanity unitNeed opt for loft above study unit 9. Bedroom (Boys Room)Sliding wardrobe with full loft storageStudy unit with bookshelf and dressing unitFull-length dressing mirrorVanity unitNeed opt for loft above study unit 10. Balconies (All)Pull-out clothes drying systemProvision for small planters/pots | [6 empty] | 2026-02-08 |  | 2026-02-15
18145 | Turnkey | Dec'25 | Sharad Borade | Runwal Sanctury | MUM - Thane | Yes | Hemant Sonar | Divya Rahangdale | Anil Kuwar |  | Krutika Date | suraj kumar | Akshat Shrivastava | Murali S | Nishtha Valawalkar | Aakash Gaikwad | Active | Installation | Execution | 1361768 | 1361768 | 1673877 | 1333473 | 1361768 | 65 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-25 | 2026-01-24 14:10 | 2026-01-25 | 2026-01-26 19:37 | 2026-01-31 | 2026-01-26 19:39 | 2026-02-12 | 2026-01-31 19:53 |  |  |  |  | 2026-01-31 | 2026-01-28 11:14 | 2026-02-01 | 2026-01-28 12:26 | 2026-02-01 | 2026-01-29 09:56 | 2026-02-02 | 2026-01-31 19:31 | 2026-02-20 | 2026-02-20 15:15 | 2026-02-23 | 2026-02-20 15:53 | 2026-02-21 | 2026-02-16 19:11 | 2026-02-21 | 2026-02-24 19:01 | 2026-02-25 | 2026-02-24 19:01 |  |  | 2026-03-15 | 2026-03-27 12:21 | 2026-03-27 | 2026-03-27 16:00 | 2026-03-30 | 2026-03-27 16:56 | 2026-03-27 | 2026-03-28 14:54 |  |  |  |  | 2026-04-03 15:33 | 2026-04-16 | 2026-04-15 19:12 | 2026-04-29 | 2026-04-27 20:46 | 2026-04-26 | 2026-04-25 10:53 | 2026-04-27 | 2026-05-09 15:26 | 2026-05-08 | 2026-05-11 13:45 | 2026-05-13 | 2026-05-23 19:01 |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-03-29 | 2026-04-03 15:32 | 2026-02-03 | 2026-01-31 19:35 | Site is RTMI | 2026-01-24 | 2026-01-24 14:09 | 1418540 | 255337 | 1479595.757 | 226292 | 1551871.0058 | 238235 | 1551871.0058 | 238235 | 2026-07-13 14:35:51 +0530 | suraj kumar | Site Report: Modular installation work is in progress. Profile shutter has been delivered to the site and installation is in progress. All electric fixtures have been installed. Beading nd flat Patti installation work planned for 24th June. Debris removal work planned for 24th June. Final coat of paint work has been completed. DC Planned- 14th July Qc- 15th July HO- 16th Or 17th July | 2026-06-24 00:40:17 +0530 | suraj kumar | Site Report: Modular installation work is in progress.Profile shutter has been delivered to the site and installation is in progress.All electric fixtures have been installed.Beading nd flat patti installation work planned for 24th June.Debris removal work planned for 24th June.Upcoming work: Final coat of paint work. ( Starting from 26th June- ETA 30th June)DC Planned- 1st JulyQc- 2nd JulyHO- 3rd July | 2026-06-01 12:32:31 +0530 | Snehankit Agre | Execution: 1. Modular work is in progress, but the team hasn't been on-site since Eid.
18146 | Turnkey | 2026-01-01 | Pulkit Gupta | Godrej Exquisite | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [7 empty] | Hold | Preproduction | Site Readiness 1 | 2700428 | 540086 | 3226794 | 0 | 0 | 0 | 99 | 0 | 0 | 1165414 | 994928 |  |  | 2026-01-24 | 2026-01-24 13:54 | 2026-02-03 | 2026-02-03 12:38 | 2026-02-08 | 2026-02-08 20:36 | 2026-06-20 | 2026-04-07 12:24 | 2026-07-05 |  | 2026-07-12 |  | 2026-02-08 | 2026-02-11 11:58 | 2026-02-09 | 2026-02-11 14:07 | 2026-02-11 | 2026-02-12 10:44 | 2026-02-20 | 2026-02-20 14:42 |  |  |  |  | 2026-06-21 | 2026-03-27 19:49 | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-16 | 2026-04-07 12:13 | Site is Non-RTMI | 2026-01-24 | 2026-01-24 13:54 | 2734571 | 492222 | 0 | 0 | 0 | 0 | 2757734.5 | 488201 | 2026-07-10 15:54:50 +0530 | Anil Jagtap | cx will receive the possession by last week of September | 2026-06-12 18:58:40 +0530 | Honey Thakkar | Some Image was uploaded | 2026-06-12 18:56:09 +0530 | Honey Thakkar | Some Image was uploaded | 2026-04-08 | 2026-04-07 12:27 | 2026-07-06
18147 | Turnkey | 2026-01-01 | SNEHAL KESARKAR | Purvankara The Sound of Water | BNG - HSR | No Estimate | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 172 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-23 | 2026-01-24 17:45 | 2026-01-24 |  | 2026-01-30 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-01 | [5 empty] | 2026-02-07 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-02-24 |  | 2026-02-02 |  | Unknown | 2026-01-23 | 2026-01-24 17:43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-02-07 |  | 2026-02-14
18148 | Turnkey | 2026-01-01 | MR. BURUGANA SADHU PRASAD PATRO | Rohan Ekanta | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1791138 | 142869 | 1791138 | 0 | 0 | 91 | 32 | 0 | 215359 | 735908 | 697002.4 |  |  | 2026-01-24 | 2026-01-24 15:20 | 2026-02-07 | 2026-02-07 18:13 | 2026-03-06 | 2026-03-06 16:33 | 2027-01-04 |  | 2027-01-11 |  | 2027-02-02 |  | 2026-03-06 | 2026-03-07 12:14 | 2026-03-07 | 2026-03-11 13:37 | 2026-03-11 | 2026-03-14 11:18 | 2026-03-20 | 2026-03-20 19:45 |  |  |  |  | 2027-01-05 |  | 2027-01-28 |  | 2027-01-29 |  |  |  | 2027-02-05 |  | 2027-02-06 |  | 2027-02-07 |  | 2027-02-08 | [6 empty] | 2027-02-26 |  | 2027-03-07 |  | 2026-04-06 |  | 2027-03-07 |  | 2027-03-08 |  | 2027-03-10 |  |  |  | 2027-04-01 |  | 2027-04-03 |  | 2027-04-04 | [5 empty] | 2027-02-06 |  | 2026-12-31 |  | Unknown | 2026-01-24 | 2026-01-24 15:18 | 1517914 | 273224 | 0 | 0 | 0 | 0 | 1517914 | 273224 | 2026-07-14 15:02:17 +0530 | Preksha Sajjanshettar | The site is currently in the painting stage and is expected to be ready by the end of next month. Until then, the project will remain on hold. | 2026-04-14 12:32:53 +0530 | Lalitha Ajay Kumar | Some Image was uploaded | 2026-03-14 11:22:19 +0530 | Bency Chacko |  | 2027-01-05 |  | 2027-01-12
18149 | Turnkey | 2026-01-01 | Arpan Roy | Soparnika oliva nest | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Nanda Kumar | Ranjith Kumar | Murali S | Raghavendra S | Abdul Shafeen | Active | Installation | Execution | 1086404 | 1086404 | 782863 | 0 | 1083189 | 28 | 32 | 0 | 0 | 0 | 0 |  |  | 2026-01-24 | 2026-01-30 11:48 | 2026-01-31 | 2026-01-31 08:49 | 2026-02-03 | 2026-02-03 12:24 | 2026-03-14 | 2026-03-14 19:13 | 2026-05-18 | 2026-05-19 08:13 | 2026-05-20 | 2026-05-19 10:57 | 2026-02-01 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-08 15:27 | 2026-02-08 | 2026-02-09 17:40 | 2026-02-15 | 2026-02-15 19:27 |  |  |  |  | 2026-03-04 | 2026-02-28 11:08 | 2026-05-10 | 2026-05-13 22:49 | 2026-05-14 | 2026-05-13 23:08 |  |  | 2026-05-22 | 2026-05-24 11:15 | 2026-05-24 | 2026-05-26 16:27 | 2026-05-27 | 2026-05-26 17:10 | 2026-05-27 | 2026-05-26 18:05 |  |  |  |  | 2026-05-27 12:27 | 2026-06-04 | 2026-06-03 22:03 | 2026-06-10 | 2026-06-10 11:54 | 2026-06-11 | 2026-06-10 12:01 | 2026-06-10 | 2026-06-16 16:35 | 2026-06-16 | 2026-06-17 11:23 | 2026-06-24 | 2026-06-24 09:45 |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-05-26 | 2026-05-27 10:17 | 2026-03-06 | 2026-03-14 19:08 | Site is Non-RTMI | 2026-01-24 | 2026-01-24 15:37 | 769487.3857 | 127047 | 0 | 0 | 1220921.2744 | 198791 | 1225161.2744 | 199282 | 2026-06-24 15:48:24 +0530 | Ranjith Kumar | Execution: | 2026-06-08 15:58:34 +0530 | Ranjith Kumar | Floor Covering Done False Ceiling & False Ceiling Electrical - WIP Painting - 13/Jun Cx Side No work. | 2026-05-27 10:19:43 +0530 | Ranjith Kumar | Procurement: | 2026-03-15 | 2026-03-14 19:17 | 2026-05-20 | 2026-05-19 10:57
18150 | Turnkey | 2026-01-01 | Gaurav Singh Singh | JRC PALLADIO | BNG - HSR | Yes | Shefali | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2870939 | 9999 | 0 | 0 | 0 | 165 | 0 | 277095 | 287094 | 1177336 | 1119415.2 |  |  | 2026-01-24 | 2026-01-24 17:43 | 2026-01-25 | 2026-01-31 12:48 | 2026-02-03 |  | 2026-02-10 |  | 2026-02-17 |  | 2026-02-24 |  | 2026-02-03 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-05 | [5 empty] | 2026-02-11 |  | 2026-02-19 |  | 2026-02-20 |  |  |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-02 | [6 empty] | 2026-03-20 |  | 2026-03-29 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-04-01 |  |  |  | 2026-04-23 |  | 2026-04-25 |  | 2026-04-26 | [5 empty] | 2026-02-28 |  | 2026-02-06 |  | Unknown | 2026-01-24 | 2026-01-24 17:42 | 0 | 0 | 0 | 0 | 0 | 0 | 2432999 | 437939 | 2026-01-26 12:06:33 +0530 | Oviya A | Budget Range: 1520 LakhsHouse Orientation: East-facingOccupancy: 3 membersDesign Theme: Blend of Traditional & ModernVaastu Compliance: To be strictly followedProject Status: House is ready to move in; interiors to be planned and executed accordingly to meet the March shifting schedule. Ground Floor (GF) Entrance / Staircase AreaShoe rack below staircase with flap-down mechanism Drawing RoomTV unitDecorative treatment for double-height ceilingFeature wall behind seatingCurtains (design to be proposed)Dining AreaOption 1: Semi-partitionCrockery unit integrated on dressing room wallOption 2: Constructed partition wallCrockery unit on the partition wallNo false ceilingPelmet provision requiredKitchenBase cabinets, wall cabinets, and loft storageTall unitPantry unitDefined refrigerator placementCommon washroom wall unit with mirrorWashbasin AreaWall dcor around mirrorStorage solution below staircase with frame and shutterMaster Bedroom Ground FloorDressing unit with L-shaped wardrobeHeadboard designFalse ceilingVanity with mirror 3. First Floor RequirementsStaircaseWall art along stairwayMaster Bedroom First FloorHeadboard designFalse ceilingSame wardrobe design as GF master bedroomFull study unit with overhead bookshelfBay window seating with closed storage on both sidesVanity with mirrorPooja RoomBottom storageTwo-stage platform for idolsBedroom 1 First FloorStraight wardrobe with integrated study unitHeadboard designFalse ceilingVanity with mirror 4. Second Floor RequirementsCommon AreaChandelier or pendant lightingWall artMaster Bedroom Second FloorStraight wardrobeDressing unitFalse ceilingVanity with mirrorLaundry AreaStorage cabinets | [6 empty] | 2026-02-11 |  | 2026-02-18
18151 | Turnkey | Dec'25 | Ravi Kumar | RUNWAL FOREST | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Nishtha Valawalkar |  | Hold | Preproduction | Site Readiness 1 | 935275 | 280587 | 1098253 | 935275 | 0 | 0 | 113 | 0 | 0 | 306653 | 348034.8 |  |  | 2026-01-25 | 2026-01-24 20:15 | 2026-01-25 | 2026-01-26 17:50 | 2026-01-31 | 2026-01-26 18:12 | 2026-06-26 | 2026-03-08 20:21 | 2026-06-29 | 2026-03-11 18:09 | 2026-03-15 | 2026-03-15 14:20 | 2026-01-31 | 2026-01-27 17:39 | 2026-02-01 | 2026-01-28 12:43 | 2026-02-01 | 2026-01-29 17:45 | 2026-02-02 | 2026-02-06 13:08 | 2026-03-15 | 2026-03-15 15:08 | 2026-07-05 | 2026-03-24 13:12 | 2026-07-05 | 2026-03-23 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-15 |  | 2026-08-15 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-15 |  | 2026-06-17 | 2026-03-05 16:11 | Site is Non-RTMI | 2026-01-24 | 2026-01-24 20:14 | 930723 | 167530 | 939140.3579 | 165550 | 0 | 0 | 939140.3579 | 165550 | 2026-04-30 11:42:27 +0530 | Honey Thakkar | Some Image was uploaded | 2026-01-29 17:45:19 +0530 | Royden Henriques | Possession : June'2026 Payment Mode : B2CÂ Self funding - Yes CX will pay 20% on 17th Feb sugandhisubbiah@gmail.com vravi085@gmail.com,Â Flat no. 2002, Tower 10,, Runwal Forest, Kanjurmarg 400078 Post offers the amount is 899291/- as per the offer email. Informed the below timelines: 105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays/possession delays It also depends on timely closure on designs and PKO docket approval | 2026-01-29 16:41:41 +0530 | Royden Henriques
18152 | Turnkey | 2026-01-01 | Rajath | prestige lake ridge | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1395683 | 9999 | 1395683 | 0 | 0 | 161 | 0 | 129569 | 139568 | 574915 | 541631.2 |  |  | 2026-01-24 | 2026-01-24 17:41 | 2026-01-31 | 2026-02-04 11:25 | 2026-02-04 | 2026-02-04 11:57 | 2026-02-11 |  | 2026-02-18 |  | 2026-02-25 |  | 2026-02-04 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-06 | [5 empty] | 2026-02-12 |  | 2026-02-20 |  | 2026-02-21 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-03 | [6 empty] | 2026-03-21 |  | 2026-03-30 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-02 |  |  |  | 2026-04-24 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-03-01 |  | 2026-02-07 |  | Unknown | 2026-01-24 | 2026-01-24 17:40 | 1182782 | 212900 | 0 | 0 | 0 | 0 | 1182782 | 212900 | 2026-02-04 15:23:54 +0530 | Preksha Sajjanshettar | RGMÂ - 2.5BHK Foyer SHOE RACK - 50 PAIR - with seating provisionÂ foyer design-simple and minimalisticÂ Living sofa - 3+2Â Tv unitÂ - on sofa wallÂ sofa - on tv unit wallÂ TV - base with some wall ledge and Tall unit on right cover beam between living and dining Dining - 4 seater Crockery(small) - with pooja unitÂ storage at bathroom wallÂ KitchenÂ stove - 4 burner - with chimney BASE-TOP-LOFT-TALL UNIT -Â FRIGE - DOUBLE DOORÂ RO TOP MOUNT SINKÂ Utility BIGGER SINKÂ WASHING MACHINEÂ JANITOR UNITÂ 2 CYLINDER UNITÂ Master bedroom wardrobe - openable with loftÂ dresser - next to toilet wallÂ bed - queen sizeÂ wall treatment - bed headboard wall Bathroom (BOTH) vanity - wall mountÂ Shower partitionÂ Grab handle to considerÂ Study room - as kids bedroomÂ single bedÂ wardrobe - openable - with loftÂ study unitÂ False ceilingÂ foyer - living with dining | 2026-01-25 13:00:11 +0530 | Ramesh Nayak | *Master bedroom*Â - complete end to end wardrobeÂ Mirror unit next to bath room Office space near the window Study room - Â small wardrobe Small study table Foyer spaceÂ Living and dining separation needed? Pooja room change needed? Fridge -different place? Utility woodwork Bathroom - storage Â *Hall*Â Space next to common bathroom utilisation Curtain double rods Dining table options Kids/Study Room : Space for 1 cot Study desk Kids Wardrobe Living room : Tv unit to opposite wall with showcase n storage Flase ceilingÂ Wood rods to wall Dining and hall ceiling separation with lights Forier shoe storageÂ Forier extension ? Dead space next in dining hall utilization ?Â Pooja room suggestions False ceilingÂ Utility : SinkÂ Dustbin and janitor unitÂ ShelvesÂ Division with kitchen ? Master bed Room : Complete wardrobe with better storage space Along with side door Seperate Mirror unitÂ Dead space next to bathroomÂ Bathroom storage and hangersÂ Glass wall separation Office space socket Bedroom-2 : Side wardrobeÂ Storage solution in loft Grab handles near camod |  |  |  | 2026-02-12 |  | 2026-02-19
18153 | Turnkey | 2026-01-01 | Aditya Bhatt | Godrej | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Safalta Karkera |  | Ehtesham Bhati | Naushad Ansari | Rizwan Mistry | Murali S | Rashmita Das | Vinay Surve | Active | Installation | Execution | 1736188 | 1736188 | 1654899 | 0 | 1736188 | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-24 | 2026-01-31 00:46 | 2026-02-04 | 2026-02-04 11:36 | 2026-02-04 | 2026-02-04 11:44 | 2026-03-04 | 2026-03-04 12:55 | 2026-03-05 | 2026-03-06 10:57 | 2026-04-16 | 2026-04-16 17:23 | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-06 20:57 | 2026-02-06 | 2026-02-09 18:18 | 2026-02-20 | 2026-02-20 10:53 |  |  |  |  | 2026-03-15 | 2026-02-28 13:02 | 2026-03-13 | 2026-03-20 10:30 | 2026-03-21 | 2026-03-20 10:30 |  |  | 2026-04-19 | 2026-04-22 17:49 | 2026-04-23 | 2026-04-23 16:10 | 2026-04-24 | 2026-04-24 12:05 | 2026-04-25 | 2026-04-24 18:45 |  |  |  |  | 2026-04-27 13:31 | 2026-05-05 | 2026-05-04 20:30 | 2026-06-07 | 2026-06-04 21:49 | 2026-06-04 | 2026-05-30 17:03 | 2026-06-04 | 2026-06-13 12:23 | 2026-06-15 | 2026-06-15 23:32 | 2026-06-16 | 2026-06-19 15:19 |  |  | 2026-07-25 |  | 2026-07-27 |  | 2026-07-28 | [5 empty] | 2026-04-23 | 2026-04-25 12:51 | 2026-02-21 | 2026-03-04 12:41 | Site is RTMI | 2026-01-24 | 2026-01-24 20:57 | 1731413.4601 | 282950 | 0 | 0 | 1941914.9161 | 295350 | 1941914.9161 | 295350 | 2026-07-09 00:29:55 +0530 | Naushad Ansari | Execution: Floor covering done false ceiling framing done electrical wiring done Carpentry work done for ac pelmet first coat done Modular delivery done on 15th June Day 1 done on 16th June Modular installation is progress Site is hold for 20 days due to the modular vendor is not aligned Electrical delivery materials pending from cx side. | 2026-06-16 17:54:01 +0530 | Savita Parab | Execution: Floor covering done false ceiling framing done electrical wiring done Carpentry work done for ac pelmet first coat done Modular delivery done on 15th June Day 1 done on 16th June | 2026-06-08 23:21:14 +0530 | Savita Parab | Execution: Floor covering done false ceiling framing done electrical wiring done Carpentry work done for ac pelmet first coat started from 1st june to 9th June Site ready for modular on 10th June | 2026-03-05 | 2026-03-04 12:58 | 2026-03-07 | 2026-03-06 10:58
18154 | Turnkey | 2026-01-01 | Deepak | Sharavati apartment | BNG - HSR | Yes | Shefali | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 1716534 | 9999 | 0 | 0 | 0 | 172 | 0 | 161654 | 171653 | 701544 | 671683.2 |  |  | 2026-01-24 | 2026-01-24 18:56 | 2026-01-25 |  | 2026-02-03 |  | 2026-02-10 |  | 2026-02-17 |  | 2026-02-24 |  | 2026-02-03 |  | 2026-02-04 |  | 2026-02-04 |  | 2026-02-05 | [5 empty] | 2026-02-11 |  | 2026-02-19 |  | 2026-02-20 |  |  |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-02 | [6 empty] | 2026-03-20 |  | 2026-03-29 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-04-01 |  |  |  | 2026-04-23 |  | 2026-04-25 |  | 2026-04-26 | [5 empty] | 2026-02-28 |  | 2026-02-06 |  | Unknown | 2026-01-24 | 2026-01-24 18:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1454690 | 261844 | [9 empty] | 2026-02-11 |  | 2026-02-18
18155 | Turnkey | 2026-01-01 | Kavita Pandey | landmark nest villa | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1459306 | 9999 | 1459306 | 0 | 0 | 157 | 0 | 135932 | 145931 | 604136 | 563309.2 |  |  | 2026-01-24 | 2026-01-24 17:55 | 2026-01-30 | 2026-01-30 13:24 | 2026-02-08 |  | 2026-02-15 |  | 2026-02-22 |  | 2026-03-01 |  | 2026-02-08 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-10 | [5 empty] | 2026-02-16 |  | 2026-02-24 |  | 2026-02-25 |  |  |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 | [6 empty] | 2026-03-25 |  | 2026-04-03 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-06 |  |  |  | 2026-04-28 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-03-05 |  | 2026-02-11 |  | Unknown | 2026-01-24 | 2026-01-24 17:54 | 1236700 | 222606 | 0 | 0 | 0 | 0 | 1236700 | 222606 | 2026-02-08 11:31:41 +0530 | Kiran Agarampalli | CDP: Island counter- Move it to right side, and add a crockery on top of it along with ceiling units. L sofa with lounger, with additional seating like ottoman. Kitchen- Add tambour unit next to tall unit, spice rack unit below the wall unit on the left. Utility- WM- top Load Add GTBT unit for the sink Cylinder under the sink Add laundry storage- janitor on top Above the Washing machine- storage to be given Cloth drier also in the kitchen Pooja- white and light shades with rose gold or gold handles. Library bookshelf around the window with bay seater Traditional mirror for master bedroom Bed opposite wall, nice wall concept tall mirror on the opposite wall KBR kids room with cars themed, Moraco, Hitler, Satoshi naka moto. Balcony: Shiva- themed wall concept with cladding | 2026-01-30 13:24:56 +0530 | Kiran Agarampalli | DCM: Minutes of Meeting held on Date: 30.01.2026 Attendees: Kiran, Nirosha, Mrs. Kavita Pandey Discussion: Based on 30.01.2026 meeting, below is a list of all the requirements that were discussed during the meeting: Mrs. Kavita Pandey RGM: Kitchen and Bedroom wardrobes provided by the builder Parking: In the parking a cat houseShoe rack to be planned in the car parkingÂ Â Kitchen: A tall unit in kitchen (microwave unit)Â Tambour unit to store appliancesÂ Utility: DishwasherÂ Washing machineÂ Sink for vessel washingÂ Storage to keep the cylinderÂ Dining: Island counter in between living and kitchenÂ Island to include (bar counter, vegetable cutting, dustbin storage)Other side kind of crockery unit kind of thingÂ Living: Sofa to be place in SE cornerÂ TV unit to be planned in-between north side 2 windowsÂ NW corner washbasin and Dining to be plannedÂ Storage under staircase (inverter, shoe, other storage)Â Living toilet- vanity storageÂ GF bedroom:Â Study tableÂ Dressing tableÂ bed side tableÂ 5'x6'6"- Queenloft to be added on top of the wardrobe First floor:Â Bedrooms- same as ground floorÂ Pooja and library (pooja to be as room with glass partition)Â existing wardrobe size- 5'6"x7' Balcony: - sit out area (no plants)Â 5'-6' swingÂ first floor NW corner small counter space for induction, boiler, wash basin with storageÂ Terrace: - barbecue counter spaceÂ Budget: 10-15L CDP date: 6th Feb |  |  |  | 2026-02-16 |  | 2026-02-23
18156 | Turnkey | 2026-01-01 | Gavin Shah | Aventus height | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati |  |  | Murali S | Moni Sahani | Vinay Surve | Hold | Preproduction | Site Readiness 2 | 1929966 | 1191700 | 1653087 | 0 | 1979863 | 1 | 24 | 0 | 0 | 0 | 738266 |  |  | 2026-01-24 | 2026-02-01 17:41 | 2026-01-29 | 2026-02-01 18:36 | 2026-02-04 | 2026-02-04 14:46 | 2026-03-10 | 2026-03-10 19:16 | 2026-04-08 | 2026-04-07 14:39 | 2026-05-23 | 2026-05-23 12:56 | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-12 14:42 | 2026-02-12 | 2026-03-02 14:07 | 2026-03-05 | 2026-03-05 16:59 |  |  |  |  | 2026-03-17 | 2026-03-26 19:34 | 2026-04-04 | 2026-04-04 15:23 | 2026-04-05 | 2026-04-04 15:23 |  |  | 2026-05-24 | 2026-05-26 18:44 | 2026-06-10 | 2026-06-10 16:19 | 2026-06-11 | 2026-06-13 20:15 | 2026-06-29 | 2026-06-27 15:52 | [5 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-06-10 |  | 2026-03-06 | 2026-03-10 19:14 | Site is RTMI | 2026-01-24 | 2026-01-29 17:08 | 1824733.031 | 296403 | 0 | 0 | 2288306.1593 | 371419 | 2288470.0773 | 371435 | 2026-07-08 13:40:49 +0530 | Manzoor Shaikh | Good Afternoon @~Ravi Shah Sir, As we spoke over the phone, we are waiting the builder to fix the seepage issue once the rain stops. Request you to kindly confirm accordingly will proceed with the next milestone. | 2026-07-08 13:02:04 +0530 | Manzoor Shaikh | Civil work is ongoing | 2026-06-28 19:34:55 +0530 | Manzoor Shaikh | Site not ready civil work is ongoing | 2026-03-11 | 2026-03-10 19:19 | 2026-04-08 | 2026-04-07 14:39
18157 | Turnkey | 2026-01-01 | Kavya Srivastav | Ruparel Palacio | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Santosh Kamat | Rizwan Mistry | Murali S | Saloni Sagwekar | Vinay Surve | Hold | Preproduction | Site Readiness 2 | 2380317 | 1433601 | 2071257 | 0 | 2385799 | 37 | 8 | 0 | 0 | 0 | 946716 |  |  | 2026-01-24 | 2026-01-25 20:04 | 2026-01-27 | 2026-01-27 11:26 | 2026-01-30 | 2026-01-27 15:16 | 2026-02-27 | 2026-02-27 15:23 | 2026-02-28 | 2026-02-27 15:39 | 2026-04-28 | 2026-04-28 19:35 | 2026-01-27 | 2026-01-31 05:30 | 2026-01-28 | 2026-02-03 16:54 | 2026-02-03 | 2026-02-04 16:33 | 2026-02-08 | 2026-02-08 18:24 |  |  |  |  | 2026-02-14 | 2026-02-25 19:14 | 2026-04-09 | 2026-04-10 17:20 | 2026-04-11 | 2026-04-10 17:20 |  |  | 2026-04-30 | 2026-05-07 18:55 | 2026-05-17 | 2026-05-17 20:31 | 2026-05-18 | 2026-05-28 18:23 | 2026-05-29 | 2026-05-31 18:26 | [5 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-05-17 |  | 2026-02-09 | 2026-02-27 15:11 | Site is RTMI | 2026-01-24 | 2026-01-25 20:02 | 1755303 | 315954 | 0 | 0 | 2531280.7799 | 424952 | 2547429.7299 | 427167 | 2026-07-03 12:51:59 +0530 | Manzoor Shaikh | Please ignore the below message and refer to this one | 2026-07-03 12:50:01 +0530 | Manzoor Shaikh | Others: Builder is not allowing to work, need Autocad file, the design team is working and will share with the client. | 2026-06-10 18:34:49 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-02-28 | 2026-02-27 15:32 | 2026-02-28 | 2026-02-27 15:40
18158 | Turnkey | 2026-01-01 | Ankit Raonka | Snn serenity garden | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1351852 | 9999 | 1351852 | 0 | 0 | 155 | 0 | 125186 | 135185 | 545070 | 536412 |  |  | 2026-01-24 | 2026-01-24 20:03 | 2026-02-05 | 2026-02-06 17:40 | 2026-02-09 | 2026-02-10 11:36 | 2026-02-17 |  | 2026-02-24 |  | 2026-03-03 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-12 | [5 empty] | 2026-02-18 |  | 2026-02-26 |  | 2026-02-27 |  |  |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-09 | [6 empty] | 2026-03-27 |  | 2026-04-05 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-08 |  |  |  | 2026-04-30 |  | 2026-05-02 |  | 2026-05-03 | [5 empty] | 2026-03-07 |  | 2026-02-13 |  | Unknown | 2026-01-24 | 2026-01-24 20:02 | 1145637 | 206214 | 0 | 0 | 0 | 0 | 1145637 | 206214 | 2026-02-05 11:26:45 +0530 | Ankita Agarwal | DCM: . MOM CX ANKIT Budget 810 Lakhs Floor to Ceiling Height9 feet Modular KitchenScope Includes: Base UnitsWall UnitsLoftTall Unit (with oven space + wicker basket)Glass ShuttersOpen UnitsUtility AreaSink CabinetWall Cabinet Living Room3-Seater Sofa + 1-Seater SofaTV Unit 510 with partitionSofa Backside Design TreatmentWooden Partition Dining AreaPooja UnitFalse Ceiling (Living & Dining Area) FoyerFoyer Unit Main Focus Area GBR 02Study UnitWardrobe with MirrorQueen Size Bed (Reference) BR 01 Master BedroomWardrobe with LoftDressing Unit | [6 empty] | 2026-02-18 |  | 2026-02-25
18159 | Turnkey | 2026-01-01 | Suraj Kumar | Prestige City | BNG - HRBR | Yes |  | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 1226092 | 9999 | 0 | 0 | 0 | 170 | 0 | 112610 | 122609 | 512319 | 468554.4 |  |  | 2026-01-24 | 2026-01-26 14:24 | 2026-01-26 |  | 2026-01-31 |  | 2026-02-05 |  | 2026-02-12 |  | 2026-02-19 |  | 2026-01-29 |  | 2026-01-30 |  | 2026-01-30 |  | 2026-01-31 | [5 empty] | 2026-02-06 |  | 2026-02-14 |  | 2026-02-15 |  |  |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 | [6 empty] | 2026-03-15 |  | 2026-03-24 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-27 |  |  |  | 2026-04-18 |  | 2026-04-20 |  | 2026-04-21 | [5 empty] | 2026-02-23 |  | 2026-02-01 |  | Unknown | 2026-01-24 | 2026-01-24 20:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1039061 | 187031 | 2026-03-07 18:39:59 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-01-26 15:50:54 +0530 | Bhargavi Maddala | DCM: Possession-Feb end fond of travelling/Nature(mountains/trekking) Prestige city(NF) Vaastu to be considered Entrance beside wall shoe rack-check for provision(movable) Living area tv cum pooja unit wall highlighters Dining area crockery gallery wall/highlighter Kitchen loft, base, wall Modular microwave oven, wicker basket-not req granite countertop Utility sink, cylinder cabinet wall unit-detergents washing machine/dish washer-check MBR wardrobe, loft(mirror on shutter) work station/tv unit wall highlighter-optional Br-2/PBR Wardrobe, loft foldable table top wall shelf-tv panel Restrooms Wall unit vanity cabinet-CT End-end mirror-MBR false ceiling-living Budjet-7-8L CDP-31-2nd half |  |  |  | 2026-02-06 |  | 2026-02-13
18160 | Turnkey | 2026-01-01 | Dattaprasad | Raymond GS | MUM - Thane | Yes | Mayuri Patil |  | Safalta Karkera | [7 empty] | Active | Prospect | 10% Payment | 3851166 | 9999 | 0 | 0 | 0 | 147 | 0 | 375118 | 385117 | 1748273 | 1332660 |  |  | 2026-01-24 | 2026-02-05 13:09 | 2026-02-06 | 2026-02-06 13:57 | 2026-02-18 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Unknown | 2026-01-24 | 2026-02-05 13:08 | 0 | 0 | 0 | 0 | 0 | 0 | 3263700 | 587466 | 2026-05-26 16:56:14 +0530 | Bhagyashree Salunkhe | Cx is in the office meeting he said he shall contact us and disconnected the call | 2026-02-06 13:57:22 +0530 | Mayuri Patil | Minutes of Meeting (MOM)Project: Residential Interior Design Discussion Summary & Requirements 1. General & PlanningTotal area approx. 1396 sq.ft.Carpet area approx. 759 sq.ft.Configuration: 3 BHKProperty possession expected by end of FebruaryCP (Concept Plan) to be prepared and shared; planned discussion on Saturday or Sunday2. BudgetOverall suggested budget: 3035 LakhsClient expected budget: 1520 LakhsScope to include painting, false ceiling, and electrical work3. Living Room & Dining AreaTV unit size approx. 65 inchesDining table: 6-seaterSideboard with crockery unitConsole table on the opposite sidePartition to conceal washroom visibility from living room4. Kitchen & UtilityExisting kitchen platform to be retainedPantry unit with:Breakfast counterFixed foldable partitionStorage provision in utilityPantry room to be created in place of utility toilet3-layer kitchen storageOne-on-one refrigeratorSliding glass door for kitchenMandatory storage in dry area5. BedroomsGuest BedroomInvisible bed with sofaWardrobe with storageSeating area + study unitPrefer darker shades Master BedroomKing bed with hydraulic storage Wardrobe with storageSeating areadresser unitside tables Bedroom 2 Parents roomQueen-size bedSide tables (2 units)Wardrobe Bedroom 3 (Kids / Twin Room)Twin beds or single bedsFancy double bed option discussedWardrobeSide tablesStudy unit Dresser 6. BathroomsAll bathroom vanity units to be provided 7. Mandir & Storage Mandir height to be 1 to 2 ft above ground levelDedicated mandir areaPreferably darker shadesSide tables and additional storage wherever feasible8. Additional NotesDry area must have sufficient storageOverall design to balance functionality with storage optimization | 2026-02-06 13:51:57 +0530 | Mayuri Patil | DCM: Minutes of Meeting (MOM)Project: Residential Interior Design Discussion Summary & Requirements 1. General & PlanningTotal area approx. 1396 sq.ft.Carpet area approx. 759 sq.ft.Configuration: 3 BHKTV unit size approx. 65 inchesProperty possession expected by end of FebruaryCP (Concept Plan) to be prepared and shared; planned discussion on Saturday or Sunday2. BudgetOverall suggested budget: 3035 LakhsClient expected budget: 1520 LakhsScope to include painting, false ceiling, and electrical work3. Living Room & Dining AreaDining table: 6-seaterSideboard with crockery unitConsole table on the opposite sidePartition to conceal washroom visibility from living room4. Kitchen & UtilityExisting kitchen platform to be retainedPreferably darker colour shades for kitchenPantry unit with:Breakfast counterFixed foldable partitionStorage provision in utilityPantry room to be created in place of utility toilet3-layer kitchen storageOne-on-one refrigeratorSliding glass door for kitchenMandatory storage in dry area5. BedroomsMaster BedroomInvisible bed with sofaWardrobe with storageSeating area + study unitPrefer darker shadesBedroom 2 (Study / Guest Room)Queen-size bedSide tables (2 units)WardrobeStudy unitWork stationBedroom 3 (Kids / Twin Room)Twin beds or single bedsFancy double bed option discussedWardrobeSide tables6. BathroomsAll bathroom vanity units to be providedMandir height to be 1 to 2 ft above ground level7. Mandir & StorageDedicated mandir areaPreferably darker shadesSide tables and additional storage wherever feasible8. Additional NotesDry area must have sufficient storageOverall design to balance functionality with storage optimization | 2026-02-26 |  | 2026-03-05
18162 | Turnkey | 2026-01-01 | prashant jain | Lodha AMara | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 1735992 | 9999 | 0 | 0 | 0 | 172 | 0 | 163600 | 173599 | 702875 | 685918.8 |  |  | 2026-01-24 | 2026-01-24 23:14 | 2026-01-25 |  | 2026-01-26 |  | 2026-02-02 |  | 2026-02-09 |  | 2026-02-16 |  | 2026-01-26 |  | 2026-01-27 |  | 2026-01-27 |  | 2026-01-28 | [5 empty] | 2026-02-03 |  | 2026-02-11 |  | 2026-02-12 |  |  |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-22 | [6 empty] | 2026-03-12 |  | 2026-03-21 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-24 |  |  |  | 2026-04-15 |  | 2026-04-17 |  | 2026-04-18 | [5 empty] | 2026-02-20 |  | 2026-01-29 |  | Unknown | 2026-01-24 | 2026-01-24 23:10 | 0 | 0 | 0 | 0 | 0 | 0 | 1471179 | 264812 | [9 empty] | 2026-02-03 |  | 2026-02-10
18163 | Turnkey | 2026-01-01 | Amit Singh | Raymond Address Season 1 | MUM - Thane | Yes | Honey Thakkar | Sarita Jangid | Anil Kuwar | [5 empty] | Saloni Chawan | Shailendra Mishra | Active | Preproduction | CM | 2424384 | 484876 | 2424384 | 0 | 0 | 45 | 61 | 0 | 0 | 1001136 | 938372.4 |  |  | 2026-01-24 | 2026-01-24 23:18 | 2026-01-28 | 2026-02-03 10:58 | 2026-02-14 | 2026-02-18 11:48 | 2026-03-22 | 2026-03-22 19:15 | 2026-04-01 | 2026-03-31 14:16 | 2026-08-05 |  | 2026-02-14 | 2026-02-16 19:37 | 2026-02-15 | 2026-02-18 11:32 | 2026-02-19 | 2026-02-19 11:55 | 2026-04-30 | 2026-02-20 14:38 |  |  |  |  | 2026-03-22 | 2026-03-23 15:25 | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-05-15 | 2026-03-22 17:23 | Site is RTMI | 2026-01-24 | 2026-01-24 23:18 | 2653677.4202 | 424278 | 0 | 0 | 0 | 0 | 2653677.4202 | 424278 | 2026-07-10 13:48:22 +0530 | Honey Thakkar |  | 2026-05-06 13:03:16 +0530 | Anil Kuwar | Some Image was uploaded | 2026-04-07 12:56:05 +0530 | Pooja Metre | Renders are created for the flat as per last MOM for the next meeting | 2026-05-20 | 2026-03-22 19:51 | 2026-04-01 | 2026-03-31 14:18 | Under Construction | 2026-06-01
18164 | Turnkey | 2026-01-01 | Anjali Hardik doshi | Raymond Reality | MUM - Thane | Yes | Mayuri Patil |  | Safalta Karkera | [5 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 1198980 | 9999 | 0 | 0 | 0 | 172 | 0 | 109899 | 119898 | 479592 | 479592 |  |  | 2026-01-24 | 2026-01-24 23:50 | 2026-01-28 | 2026-01-28 11:20 | 2026-01-29 |  | 2026-02-07 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 | [5 empty] | 2026-02-08 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-27 | [6 empty] | 2026-03-17 |  | 2026-03-26 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-29 |  |  |  | 2026-04-20 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-02-25 |  | 2026-02-03 |  | Site is RTMI | 2026-01-24 | 2026-01-24 23:49 | 0 | 0 | 0 | 0 | 0 | 0 | 1016085 | 182895 | 2026-04-19 21:07:02 +0530 | Mustufa Sohagpurwala | Some Image was uploaded | 2026-01-28 11:17:10 +0530 | Karuna Shinde | Some Image was uploaded |  |  |  | 2026-02-08 |  | 2026-02-15
18165 | Turnkey | 2026-01-01 | Nishita Abhishek Nair | Risland Icon | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 2240000 | 448000 | 2240000 | 0 | 0 | 2 | 115 | 0 | 0 | 972533 | 819467.2 |  |  | 2026-01-24 | 2026-01-29 21:54 | 2026-02-03 | 2026-02-04 14:43 | 2026-02-07 | 2026-02-04 16:27 | 2026-03-19 | 2026-03-19 13:38 | 2026-06-04 |  | 2026-06-23 |  | 2026-02-04 | 2026-02-04 17:54 | 2026-02-05 | 2026-02-05 22:17 | 2026-02-05 | 2026-02-09 14:09 | 2026-02-20 | 2026-02-20 14:38 |  |  |  |  | 2026-03-20 | 2026-03-20 22:22 | 2026-06-18 |  | 2026-06-19 |  |  |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-29 | [6 empty] | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-06-27 |  | 2026-06-05 | 2026-03-19 13:25 | Site is Non-RTMI | 2026-01-24 | 2026-01-29 21:53 | 2428903.7257 | 395084 | 0 | 0 | 0 | 0 | 2428903.7257 | 395084 | 2026-07-10 15:35:52 +0530 | Anil Jagtap | cx will receive the possession by 1st week of September*26 | 2026-06-10 18:55:19 +0530 | Anamika Dolai | The client will receive Possession around mid july. | 2026-03-24 18:12:02 +0530 | Anil Jagtap | He informed that possession might be received by end of may | 2026-03-20 | 2026-03-20 17:21 | 2026-06-05
18166 | Turnkey | 2026-01-01 | Bhupinder Pal Singh | Kalpataru Shristi Namah | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Akash Jadhav | Sandeep Tiwari | Murali S | Avi Thakkar | Vinay Surve | Active | Installation | Execution | 1299925 | 1299926 | 1662456 | 1721163 | 1333817 | 46 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-24 | 2026-02-17 12:30 | 2026-02-03 | 2026-02-17 12:34 | 2026-02-17 | 2026-02-17 14:31 | 2026-03-24 | 2026-03-22 18:07 | 2026-03-27 | 2026-03-26 19:04 | 2026-04-09 | 2026-04-08 18:58 | 2026-02-17 | 2026-02-18 19:19 | 2026-02-18 | 2026-02-18 19:34 | 2026-02-18 | 2026-02-23 16:19 | 2026-02-28 | 2026-02-28 12:12 |  |  |  |  | 2026-03-23 | 2026-03-25 12:51 | 2026-03-31 | 2026-04-02 10:38 | 2026-04-03 | 2026-04-02 10:38 |  |  | 2026-04-11 | 2026-04-14 19:27 | 2026-04-15 | 2026-04-15 20:48 | 2026-04-15 | 2026-04-15 22:42 | 2026-04-16 | 2026-04-21 12:21 |  |  |  |  | 2026-04-22 12:39 | 2026-05-04 | 2026-05-02 19:50 | 2026-05-21 | 2026-05-19 18:29 | 2026-05-20 | 2026-05-26 16:29 | 2026-05-19 | 2026-05-28 17:36 | 2026-05-28 | 2026-05-30 13:37 | 2026-06-01 | 2026-06-13 10:53 |  |  | 2026-05-23 |  | 2026-05-25 |  | 2026-06-17 | [5 empty] | 2026-04-15 | 2026-04-21 19:19 | 2026-03-01 | 2026-03-11 16:53 | Site is RTMI | 2026-01-24 | 2026-02-03 13:44 | 1742706.464 | 284103 | 1726629.6997 | 293058 | 1388665.7005 | 226345 | 1388665.2512 | 221175 | 2026-07-04 13:04:33 +0530 | Reshma Melanta | Others: | 2026-06-15 13:48:01 +0530 | Akash Jadhav | Execution: Execution: Modular work is completed Cx civil work in progress | 2026-06-08 00:14:31 +0530 | Akash Jadhav | Execution: Modular work in progress Cleaning : 13th june Per Qc14th june Qc :15th June site handover 17th June | 2026-03-23 | 2026-03-22 18:12 | 2026-03-27 | 2026-03-26 19:12
18167 | Turnkey | 2026-01-01 | Bharat Pualsa | bhanu jyoti | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Nishant Jadhav | Sandeep Tiwari | Murali S | Manasi Patil | Aakash Gaikwad | Active | Production | Production | 1273851 | 897193 | 1297945 | 0 | 1273851 | 1 | 28 | 0 | 0 | 0 | 376658 |  |  | 2026-01-11 | 2026-01-28 12:57 | 2026-01-28 | 2026-01-28 13:03 | 2026-01-28 | 2026-01-28 13:09 | 2026-04-08 | 2026-03-28 19:33 | 2026-04-05 | 2026-04-07 16:32 | 2026-06-03 | 2026-06-03 19:52 | 2026-01-28 | 2026-01-29 18:41 | 2026-01-29 | 2026-01-30 12:04 | 2026-01-30 | 2026-01-31 19:56 | 2026-02-08 | 2026-02-08 18:10 |  |  |  |  | 2026-02-25 | 2026-02-09 16:21 | 2026-05-30 | 2026-05-31 15:06 | 2026-06-01 | 2026-06-01 15:56 |  |  | 2026-06-05 | 2026-06-10 17:18 | 2026-06-19 | 2026-06-19 14:53 | 2026-06-20 | 2026-06-19 17:56 | 2026-06-27 | 2026-06-30 13:55 |  |  |  |  | 2026-07-04 18:49 | 2026-07-15 | 2026-07-14 21:08 | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-19 | 2026-06-30 20:40 | 2026-02-09 | 2026-03-28 19:01 | Site is RTMI | 2026-01-11 | 2026-01-27 17:26 | 1372364.3149 | 220873 | 0 | 0 | 1515118.961 | 234740 | 1515118.961 | 234740 | 2026-07-14 18:46:55 +0530 | Reshma Melanta | 100% Payment: | 2026-07-10 19:13:03 +0530 | Reshma Melanta | 100% Payment: | 2026-07-07 16:54:02 +0530 | Reshma Melanta | Others: | 2026-03-29 | 2026-03-28 19:35 | 2026-04-08 | 2026-04-07 16:36
18168 | Turnkey | 2026-01-01 | Riyaz Mohamed | prestige city | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Muralikrishna Udupi |  | Lost | Design | 20% Payment | 1325690 | 138670 | 1386697 | 0 | 0 | 141 | 0 | 0 | 126468 | 559763 | 500788.8 |  |  | 2026-01-25 | 2026-01-25 12:29 | 2026-01-30 | 2026-01-30 15:30 | 2026-01-30 | 2026-01-30 16:43 | 2026-02-24 | 2026-02-24 19:40 | 2026-04-05 |  | 2026-04-12 |  | 2026-01-30 | 2026-01-31 12:10 | 2026-01-31 | 2026-02-04 10:38 | 2026-02-04 | 2026-02-04 12:11 | 2026-02-15 | 2026-02-15 19:19 |  |  |  |  | 2026-04-02 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-02-16 | 2026-02-20 15:20 | Site is RTMI | 2026-01-25 | 2026-01-25 12:27 | 1175167 | 211530 | 0 | 0 | 0 | 0 | 1250585 | 225105 | 2026-03-18 13:42:38 +0530 | Akshay Ds | Some Image was uploaded | 2026-03-12 17:38:57 +0530 | Akshay Ds | The customer does not wish to proceed further as the total project cost has exceeded his expectations. We have provided multiple design iterations and explored other possible options; however, the customer is not willing to move forward. Additionally, the customer has already proceeded with another vendor. | 2026-02-20 15:17:02 +0530 | Kiran Agarampalli | DDM1: Living: Add tall unit to the tv unit change the sofa wall design Need wall concept for dining wall add base unit for crockery and loft bedroom passage- add loft on top of MBR door and add some wall detail to that area need to change the false ceiling design Kitchen: add architrave for the entrance Utility: Add loft on the right side Kids Bedroom: Add open unit in in-between wall and sliding wardrobe. add dresser unit to this bedroom add wall storage for the study unit and make the study unit foldable change the orientation of the study unit adding queen size murphy bed Master Bedroom want other option for headboard bed to be placed along the wall | 2026-02-25 | 2026-02-24 19:42 | 2026-04-06
18169 | Turnkey | 2026-01-01 | Barath Kb | individual apartment | BNG - HRBR | Yes |  | Rajeshwari S | Yogesh Patidar | [5 empty] | Ankur Kumar |  | Active | Prospect | 10% Payment | 1208215 | 9999 | 1208215 | 0 | 0 | 164 | 0 | 110823 | 120822 | 499165 | 467406.8 |  |  | 2026-01-25 | 2026-01-25 18:47 | 2026-01-25 | 2026-01-27 18:11 | 2026-01-31 |  | 2026-02-07 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 | [5 empty] | 2026-02-08 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-27 | [6 empty] | 2026-03-17 |  | 2026-03-26 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-29 |  |  |  | 2026-04-20 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-02-25 |  | 2026-02-03 |  | Unknown | 2026-01-25 | 2026-01-25 12:33 | 1023911 | 184304 | 0 | 0 | 0 | 0 | 1023911 | 184304 | 2026-04-28 19:04:09 +0530 | Losii Athisa | Some Image was uploaded | 2026-01-25 13:05:25 +0530 | Nikita Raj | 25.01.26 3BHK, 2400sft, 2nd floor, H - 10feet new property Doctor 4 members(2 son - 3,1) Theme - Abstract lux and art decor Foyer - shoe rack Living -TV unit, false ceiling Dining - dining area sit out wall is starting from bathroom and need sliding door there, 6 seater, crockery, fridge Kitchen - open kitchen, u shape kitchen, base, wall, tall unit, breakfast counter utility - wall unit, loft MBR - wardrobe and loft(sliding) in walking area with dresser, bay window KBR(bedroom 1) - wardrobe with loft, study unit, two separate beds, dresser GBR - Multipurpose room, small wardrobe, study, sofa cum bed Bathrooms - vanity, glass partition Budget - 8-10L (modular units) Next meeting - 31st Jan 4pm |  |  |  | 2026-02-08 |  | 2026-02-15
18170 | Turnkey | 2026-01-01 | Pritesh Shetty | Divam | MUM - GOR | Yes | Priyanka Patel |  | Shraddha Badgujar |  |  |  | Rizwan Mistry |  | Moni Sahani |  | Active | Prospect | Onboarding Reject | 1730948 | 225154 | 1724432 | 0 | 0 | 160 | 0 | 0 | 121036 | 717900 | 666858.4 |  |  | 2026-01-24 | 2026-01-29 14:55 | 2026-02-01 | 2026-02-01 14:59 | 2026-02-04 | 2026-02-04 16:57 | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-05 18:35 | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-05-20 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-23 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-01-24 | 2026-01-25 13:44 | 1866291.251 | 316438 | 0 | 0 | 0 | 0 | 1873541.601 | 317432 | 2026-03-12 11:44:50 +0530 | Sahil Sethi | Tarnish and Mangal discussed with the client and tried to convince him. However, the client wants the project delivery by the end of April, which is not possible from our end. Therefore, the client is requesting a refund. | 2026-02-09 12:47:39 +0530 | Royden Henriques | 1. The customer had clearly communicated, prior to closure and sign-up, that the handover was required by 20th April 2026. The 10% payment was made solely based on the commitment provided by Moni and the design team that the handover would be delivered within the agreed timeline. 2. He further stated that in the event the handover is not completed as committed, he will seek a refund and intends to escalate the matter to the consumer court. 3. There is civil work which will finish approx. Mid MarchÂ 4. The 20% payment will be made only if we confirm on the handover date. He visited Andheri EC on 8th Feb and has informed Sahil on his experience so far CX is also upset that the IM which was scheduled on 4th Feb dis not happen.Â ----------------------------------------------------------------- Possession : RTMI Payment Mode : B2C Self funding - Yes pritesh1989@gmail.com,Â 2901,Divum, pimpri pada,filmcity rd, Malad east, 400097 Post offers the amount is 1678911/- as per the offer email. Informed the below timelines:Â CX does not agreeÂ 105 -110 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays/possession delays It also depends on timely closure on designs and PKO docket approval | 2026-02-09 12:07:02 +0530 | Royden Henriques |  | 2026-04-04 |  | 2026-04-11
18171 | Turnkey | 2026-01-01 | Mr.Gagan Garg | Mahendra eden | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 1806315 | 9999 | 0 | 0 | 0 | 120 | 0 | 170633 | 180632 | 732624 | 712427.6 |  |  | 2026-01-25 | 2026-01-25 17:47 | 2026-02-04 | 2026-02-04 12:07 | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 | [5 empty] | 2026-03-28 |  | 2026-04-05 |  | 2026-04-06 |  |  |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 | [6 empty] | 2026-05-04 |  | 2026-05-13 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-16 |  |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-04-14 |  | 2026-03-23 |  | Unknown | 2026-01-25 | 2026-01-25 17:45 | 0 | 0 | 0 | 0 | 0 | 0 | 1530775 | 275539 | 2026-02-04 15:22:17 +0530 | Preksha Sajjanshettar | RGMÂ PID - 18171 3BHK 3person Budget - 10-15LAKH Changes in plans: in sit-out duct is going to change veranda: wall concept(minimal design) False ceiling - except kitchen and toilet all area LivingÂ Pooja unit with tv unit with concealed door for guest bedroomÂ pooja unit: ledges, pocket door, curve design, bottom seating with storage 65" tv Curve sofaÂ DiningÂ 8-Seate dining tableÂ dry kitchen with microwaveÂ crockery unit with bar unit with highlight piece in center pantry at poojaÂ KitchenÂ Base-top-loft cabinetÂ fridge - normal double doorÂ small sink (smart) breakfast counterÂ Under counter RO Unit UtilityÂ Door-sliding washing machineÂ bigger sinkÂ dishwasherÂ janitor unitÂ top cabinet with drain tray BathroomÂ MBR - vanity with top cabinet(on WC ledge) Â Â - shower partitionÂ Common Toilet - vanity with top cabinet (WC ledge) GBR - vanity with top cabinet(on WC ledge) Â Â - shower partitionÂ Master bedroom L-Shape wardrobe with loft unit bay seating below windowÂ dresser unit next to balcony Tv unit with slick storage below it Cosy corner to create bed - king sizeÂ wall treatment - bed headboard and tv wallÂ Kids bedroomÂ Kids themeÂ bunker bed activityÂ wardrobe - openable with loftÂ wall treatment photo collage and some activityÂ Guest bedroomÂ Folding bedÂ Â Wardrobe - openableÂ | 2026-01-25 17:48:21 +0530 | Chanakya Panigrahi | RGM Sheet 1. Budget -Â 2. Property Name & Possession - Mahindra Eden 3. Carpet Area - 1135 4. BHK - 3BHK 5. Family Size - 3 Name - Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer -Yes 4. Living/Dining Room Inclusions -Yes 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz - No Service Scope -Â False Ceiling - Expect Kitchen Painting -Â Electricity -Â 8. Utility/Janitor Unit -Â 9. Timeline - July 2nd Week |  |  |  | 2026-03-28 |  | 2026-04-04
18172 | Turnkey | 2026-01-01 | Mrs. Reema Hazra & Mr. Ajoy Das | Ankuraa Meridian | BNG - HRBR | Yes |  | Rajeshwari S | [6 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 846244 | 9999 | 0 | 0 | 0 | 166 | 0 | 74625 | 84624 | 361410 | 315585.6 |  |  | 2026-01-25 | 2026-01-30 11:49 | 2026-01-30 | 2026-01-30 17:20 | 2026-01-31 |  | 2026-02-09 |  | 2026-02-16 |  | 2026-02-23 |  | 2026-02-02 |  | 2026-02-03 |  | 2026-02-03 |  | 2026-02-04 | [5 empty] | 2026-02-10 |  | 2026-02-18 |  | 2026-02-19 |  |  |  | 2026-02-26 |  | 2026-02-27 |  | 2026-02-28 |  | 2026-03-01 | [6 empty] | 2026-03-19 |  | 2026-03-28 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-31 |  |  |  | 2026-04-22 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-02-27 |  | 2026-02-05 |  | Unknown | 2026-01-25 | 2026-01-25 14:05 | 0 | 0 | 0 | 0 | 0 | 0 | 717156 | 129088 | 2026-04-28 19:14:52 +0530 | Raghavendra S | Some Image was uploaded | 2026-01-27 21:15:26 +0530 | Rhea Rathod | DCM: Possession - May Family of - 2 East facing Budget - 8 - 10 Lakhs Browns and beige, minimalist design Living area - - Demolish the wall that separates the Living and study - Sofa - 3 + 1 + 1 seater - Tv unit - Wall mounted unit - Minimal , Aesthetic , no storage , ledges - Tv - 55" existing - wall concepts on sofa back wall and study wall, memory wall - keyboard, GuitarÂ - foldable study, ledges Dining -Â - 6 seater - existing table - Vanity unit Kitchen - - The wall that separates the kitchen and utility to be demolished - Double door fridge - washing machine - Sink unit at the corner - Tall appliance unit, Gas cylinder unit - loft / Panel Master bedroom - - Headboard - cushioning with wall concept - Wardrobe with LoftÂ - DresserÂ Washrooms- - Vanity unit - Open unit in the Master bedroom |  |  |  | 2026-02-10 |  | 2026-02-17
18173 | Turnkey | 2026-01-01 | Gaurav Aggarwal | Pavani mirabilia | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | 10% Payment | 2800627 | 9999 | 2800627 | 0 | 0 | 139 | 0 | 270064 | 280063 | 1121944 | 1118558 |  |  | 2026-01-25 | 2026-02-06 13:10 | 2026-01-30 | 2026-02-10 15:35 | 2026-02-21 | 2026-02-26 13:11 | 2026-03-05 |  | 2026-03-12 |  | 2026-03-19 |  | 2026-02-26 |  | 2026-02-27 |  | 2026-02-27 |  | 2026-02-28 | [5 empty] | 2026-03-06 |  | 2026-03-14 |  | 2026-03-15 |  |  |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 | [6 empty] | 2026-04-12 |  | 2026-04-21 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-24 |  |  |  | 2026-05-16 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-03-23 |  | 2026-03-01 |  | Unknown | 2026-01-25 | 2026-02-06 13:08 | 2373412 | 427214 | 0 | 0 | 0 | 0 | 2373412 | 427214 | 2026-01-31 13:20:41 +0530 | Swati Rathod | DCM: PID: 18173 Property - 4BHK possession - March-April Budget - 20L-25L Members - 4ppl - west facing LIVING:Â - shoe rack (15-20pair) - tv unit(bottom, tall unit) - L shaped sofa - east wall bottom unit with wall concept DINNING: - 6 seater - wall concepts POOJA ROOM: - bottom unit with ledges @ sum lvl - glass door KITCHEN: - OTG unit - tall unit - bottom unit - top units - loft - 2bowl sink - under ro - dark granite - double door fridge - roller shutter UTILITY: - W.M, D.W - 1 bowl sink - top unit TOILETS: - vanityÂ M.BEDROOM: - k size bed with side unit with 2 drawers -walk in wardrobe: l openable wardrobe or sliding wardrobe with full mirror and ledges(op-1) - dresser with bottom unit and wardrobe(op-2) aristo wardrobe BEDROOM 1:(workstation) - single bed - top units for study(no bottom unit or platform) BEDROOM 2: - king size bed - sliding wardrobe - with some ledges BEDROOM 3: Q size bed bay window setting sliding wardrobe Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. | [6 empty] | 2026-03-06 |  | 2026-03-13
18174 | Turnkey | 2026-01-01 | Nitesh Shelole | Balaji Empresso | MUM - Thane | Yes | Maasoumeh Raza | [7 empty] | Ishan Patle |  | Active | Prospect | DCM Due | 1185478 | 9999 | 0 | 0 | 0 | 164 | 0 | 108549 | 118548 | 480550 | 467832.8 |  |  | 2026-01-25 | 2026-02-01 12:14 | 2026-01-26 |  | 2026-01-28 |  | 2026-02-04 |  | 2026-02-11 |  | 2026-02-18 |  | 2026-01-28 |  | 2026-01-29 |  | 2026-01-29 |  | 2026-01-30 | [5 empty] | 2026-02-05 |  | 2026-02-13 |  | 2026-02-14 |  |  |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-24 | [6 empty] | 2026-03-14 |  | 2026-03-23 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-26 |  |  |  | 2026-04-17 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-02-22 |  | 2026-01-31 |  | Unknown | 2026-01-25 | 2026-02-01 12:13 | 0 | 0 | 0 | 0 | 0 | 0 | 1113639.55 | 183886 | 2026-01-25 16:07:12 +0530 | Sneha Kadam | DCM: 5 members 2 couple - 2 kids - 2 years and 6 years old 1 younger brother I.T - MOtilal oswal wife house wife parents retired Brother is Insurance distributer Living Room Safety door Shoe rack outside TV unit - sofa on window - existing sofa Existing folding dining to be relocated in this house Passage - storage above washing machine Kitchen base wall and loft with mandir space Bedroom 1 Bed wardrobe Side table + dressing Folding study Master Bed Sofa cum bed and its side table - bought out item Wardrobe at the tv space - big size Study foldable Mirror - full height Full ceiling, elc and painting No vanity storage as no granite available | [6 empty] | 2026-02-05 |  | 2026-02-12
18175 | Turnkey | 2026-01-01 | Priti Tiwari | Elite group | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Savita Parab | Rizwan Mistry | Murali S | Avi Thakkar | Prasad Bhivaji Hande | Active | Installation | Execution | 1091151 | 1091151 | 900221 | 0 | 1120243 | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-25 | 2026-01-26 12:59 | 2026-01-25 | 2026-01-26 13:16 | 2026-01-29 | 2026-01-26 13:24 | 2026-02-21 | 2026-02-21 18:00 | 2026-02-26 | 2026-02-26 15:38 | 2026-03-28 | 2026-03-28 18:07 | 2026-01-26 | 2026-01-27 13:09 | 2026-01-27 | 2026-01-28 16:10 | 2026-01-28 | 2026-01-31 18:09 | 2026-02-06 | 2026-02-06 16:05 |  |  |  |  | 2026-02-21 | 2026-02-23 12:45 | 2026-03-13 | 2026-03-17 09:08 | 2026-03-18 | 2026-03-17 09:32 |  |  | 2026-03-30 | 2026-04-01 00:33 | 2026-04-04 | 2026-04-05 20:09 | 2026-04-06 | 2026-04-05 20:33 | 2026-04-11 | 2026-04-09 18:51 |  |  |  |  | 2026-04-12 13:03 | 2026-05-04 | 2026-05-09 19:24 | 2026-05-12 | 2026-05-10 20:34 | 2026-05-11 | 2026-05-18 18:47 | 2026-05-10 | 2026-05-22 11:19 | 2026-05-22 | 2026-05-31 15:14 | 2026-06-02 | 2026-06-10 16:18 |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-04-05 | 2026-04-09 11:54 | 2026-02-07 | 2026-02-21 16:55 | Site is RTMI | 2026-01-25 | 2026-01-25 16:42 | 1074279.803 | 167830 | 0 | 0 | 1273045.8302 | 201393 | 1274865.8942 | 196955 | 2026-07-08 23:32:22 +0530 | Savita Parab | Execution: floor covering done false ceiling done electrical and painting in cx scope modular delivered installation in progress profile shutter delivery plan on 8th july carpentry work is on hold due to designer not shared drawing for passage mdf grooving work crework panel delivery planned on 12th july delyed due to po issue rafetr need to order designer error drawing and 3d mismatch | 2026-07-07 19:24:29 +0530 | Reshma Melanta | Others: | 2026-06-16 14:38:17 +0530 | Savita Parab | Execution: Floor covering done false ceiling done electrical wiring and painting in cx scope material delivered 26th June Installation 27th June to 20th June (vendor assign from 3rd june but yet 2 days take leave) Tandem drawers and kitchen filler delivery pending from main load metal fabrication measurements taken Profile shutter delivery awaited | 2026-02-22 | 2026-02-21 18:02 | 2026-02-27 | 2026-02-26 16:11
18176 | Turnkey | 2026-01-01 | Aijaz Pasha | MXOthers | BNG - HSR | No Estimate | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-25 | 2026-01-25 17:19 | 2026-02-14 | 2026-02-14 10:36 | 2026-01-28 |  | 2026-02-24 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 | [5 empty] | 2026-02-25 |  | 2026-03-05 |  | 2026-03-06 |  |  |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-14 |  | 2026-02-20 |  | Unknown | 2026-01-25 | 2026-01-25 17:18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-02-25 |  | 2026-03-04
18177 | Turnkey | 2026-01-01 | Kashish Chaurasia | Vaishno Ambaram | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [7 empty] | Active | Prospect | 10% Payment | 2545055 | 9999 | 0 | 0 | 0 | 112 | 0 | 244507 | 254506 | 1099097 | 936946.8 |  |  | 2026-01-25 | 2026-01-25 19:28 | 2026-01-25 | 2026-01-28 12:32 | 2026-03-25 | 2026-03-25 17:44 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-01-25 | 2026-01-25 19:24 | 0 | 0 | 0 | 0 | 0 | 0 | 2156826 | 388228 | 2026-01-25 20:15:46 +0530 | Keerthan M | DCM: Log Prakash 3BHK 15-20L August-hand over Living - Dining - TV Unit with minimal storage - Pooja unit with glass shutter (pocket door) - Partition Behind sofa - 65" TV - 6 seater dining table - Mirror near pooja unit - storage for decor left side of pooja unit - Storage near partition Kitchen - BF counter with storage - single door fridge - Base, top and loft. - Pantry unit, roller shutter(check space) - dishwasher (In-built) Utility - Janitor unit - w/m Space - Sink (single) - Top storage MBR - Sliding w/b with used cloth storage - King size bed - Dresser unit beside bed - Wall detailing - TV Unit GBR - Sliding Wardrobe (Optional) - Dresser opposite to washroom - Ledge for TV unit KBR - Bay window seating with tall storage - study unit(WFH) - I bed with table - Statement wall with storage in bottom(Reference will be shared) Note: - Full house false ceiling - Vanity units in all washroom. - Mirrors need to be included. | [6 empty] | 2026-04-02 |  | 2026-04-09
18178 | Turnkey | 2026-01-01 | MR. KRISHNA CHAITANYA VEMURI | Rohan Ekanta | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1411039 | 9999 | 1411039 | 0 | 0 | 139 | 0 | 131105 | 141104 | 570341 | 558490.4 |  |  | 2026-01-25 | 2026-02-20 13:59 | 2026-02-20 | 2026-02-20 19:10 | 2026-02-25 | 2026-02-26 12:24 | 2026-03-05 |  | 2026-03-12 |  | 2026-03-19 |  | 2026-02-26 |  | 2026-02-27 |  | 2026-02-27 |  | 2026-02-28 | [5 empty] | 2026-03-06 |  | 2026-03-14 |  | 2026-03-15 |  |  |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 | [6 empty] | 2026-04-12 |  | 2026-04-21 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-24 |  |  |  | 2026-05-16 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-03-23 |  | 2026-03-01 |  | Unknown | 2026-01-25 | 2026-02-20 13:55 | 1195796 | 215243 | 0 | 0 | 0 | 0 | 1195796 | 215243 | 2026-02-24 13:11:47 +0530 | Swati Rathod | PID: 18178 Property - 3BHK possession - 01-06-2026 Budget - 10L-12L Members - 3ppl(son-8yrs) Â - shoe rack (10-15 Pair) in corridor. LIVING:Â - TV Unit - 3+1 sofa - pooja unit space (4'0") (CX scope) DINNING: - 4 seater(foldable) - try crockery unit with dining table - double bottom vanityÂ KITCHEN: - microwave top unit - bottom unit - top units - loft - 4 burner HOB (over counter) - 2 fridge(top-bottom) - single bowl UTILITY: - sink with drain - W.M M.BEDROOM: - King size bed - sliding wardrobe - Dresser, TV unit with study unit(foldable) - vanityÂ kids room(11'6"x13'0") - single bed - openable wardrobe - study unit (try L-shaped) - vanityÂ BEDROOM: - Murphy Bed with openable wardrobe inside - Study Table (4'-5') (foldable) Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. Meeting Date: 25-02-2026 (Wednesday) | [6 empty] | 2026-03-06 |  | 2026-03-13
18179 | Turnkey | 2026-01-01 | Dinesh Kushwaha | SK Heights | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 1263211 | 9999 | 1263211 | 0 | 0 | 148 | 0 | 116322 | 126321 | 546413 | 464156 |  |  | 2026-01-25 | 2026-01-26 11:26 | 2026-02-01 | 2026-02-16 20:07 | 2026-02-19 | 2026-02-17 15:51 | 2026-02-24 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 | [5 empty] | 2026-02-25 |  | 2026-03-05 |  | 2026-03-06 |  |  |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-14 |  | 2026-02-20 |  | Unknown | 2026-01-25 | 2026-01-26 11:24 | 1070518 | 192693 | 0 | 0 | 0 | 0 | 1070518 | 192693 | [9 empty] | 2026-02-25 |  | 2026-03-04
18180 | Turnkey | Dec'25 | Reeyans Enterprises (Prashant parab) |  | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  | Krutika Date | Asif Shaikh | Akshat Shrivastava | Murali S | Mustufa Sohagpurwala | Shailendra Mishra | Active | Handover | Project Closure Pending | 1281042 | 1281042 | 954983 | 1246076 | 1281042 | 1 | 2 | 0 | 0 | 0 | 0 |  |  | 2026-01-26 | 2026-01-25 20:19 | 2026-01-26 | 2026-01-27 12:04 | 2026-02-01 | 2026-02-01 12:24 | 2026-03-27 | 2026-03-05 16:01 | 2026-03-05 | 2026-03-05 16:43 | 2026-03-15 | 2026-03-15 14:17 | 2026-02-01 | 2026-01-31 05:30 | 2026-02-02 | 2026-02-04 11:32 | 2026-02-02 | 2026-02-05 15:12 | 2026-02-26 | 2026-02-26 18:09 | 2026-03-15 | 2026-03-15 16:10 | 2026-04-05 | 2026-03-29 19:54 | 2026-04-05 | 2026-03-29 15:20 | 2026-04-06 | 2026-04-04 20:31 | 2026-04-05 | 2026-04-07 17:09 |  |  | 2026-04-16 | 2026-04-20 17:51 | 2026-04-21 | 2026-04-21 19:43 | 2026-04-24 | 2026-04-21 21:48 | 2026-04-21 | 2026-04-24 18:57 |  |  |  |  | 2026-04-26 13:01 | 2026-05-01 | 2026-05-02 19:48 | 2026-05-26 | 2026-05-21 17:47 | 2026-05-21 | 2026-05-26 16:44 | 2026-05-21 | 2026-05-30 14:45 | 2026-05-30 | 2026-06-04 15:56 | 2026-06-13 | 2026-06-13 18:34 |  |  | 2026-07-10 | 2026-07-14 22:12 | 2026-07-09 | 2026-07-14 22:14 | 2026-07-10 | 2026-07-14 22:19 |  |  |  |  | 2026-04-25 | 2026-04-26 13:00 | 2026-03-18 | 2026-02-27 14:38 | Site is RTMI | 2026-01-25 | 2026-01-25 20:18 | 1107345.263 | 168556 | 1321675.415 | 212960 | 1408526.29 | 218294 | 1408526.29 | 218294 | 2026-06-28 18:25:40 +0530 | Asif Shaikh | Execution: 90% Furniture installation doneÂ 80% electrical work completedÂ Glass shutter delivery & installation will be done after final painting workÂ Wallpaper installation will be done after final cleaningFinal painting work is commencing by 29th June & will be Completed by 8th JuneDeep cleaning & wallpaper installation -- 9th JulyFinal Alignment of furniture - 10th July.New Bed Delivery : ETA : 15th July. Project Delayed by 7 days due to manpower issue. | 2026-06-21 13:25:02 +0530 | Asif Shaikh | Execution: Furniture Delivered on 4th JuneInstallation started on 10th June.Furniture work Completion -- 25th JuneCustom Carpentry work -- 25th June.POP Punning work -- 25th June.Final Painting Commencing by 25th June & will be completed by 2nd JulyDC - 3rd JulyPre QC - 4th July.QC - 5th July VRM : Sofa -- Required by 25th June.Wallpaer - ETA - 30th JuneGlass shutter - ETA - 25th June Project Delayed -- No vendor assign from last 7 days.due manpower issue after dispatched | 2026-06-14 13:01:00 +0530 | Asif Shaikh | Execution: Furniture Delivered on 4th JuneInstallation started on 10th June.Furniture work Completion -- 25th June Custom Carpentry work -- 20th June.POP Punning work -- 20th June.Final Painting Commencing by 25th June & will be completed by 2nd JulyDC - 3rd JulyPre QC - 4th July.QC - 5th July VRM : Sofa -- Required by 25th June.Wallpaer - ETA - 30th JuneGlass shutter - ETA - 35th June Project Delayed -- No vendor assign from last 7 days.due manpower issue after dispatched
18181 | Turnkey | 2026-01-01 | Rakesh inch | Ankura Meridian | BNG - HRBR | Yes | Sanjay Kulkarni |  | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | DCM Due | 1802185 | 9999 | 0 | 0 | 0 | 164 | 0 | 170220 | 180219 | 744092 | 697656 |  |  | 2026-01-24 | 2026-02-01 12:57 | 2026-01-26 | 2026-02-21 13:24 | 2026-01-31 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-01-24 | 2026-01-25 20:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1527276 | 274909 | 2026-01-26 12:59:13 +0530 | Salpriyan Pm | LivingÂ Tv unit - Same like EC till end of the wallÂ L shaped sofaÂ Wall back design for behind the sofaÂ DiningÂ Table - 6 seaterÂ pooja - 7'*4'-existingÂ partition wall - 4'6" * ceiling - 6' in lengthÂ washing machineÂ crockery unit - wall of the mbr bathroomÂ KitchenÂ bottom storageÂ top storageÂ Microwave, air fry, toasterÂ Fridge- 2 door (2*2) UtilityÂ Nonveg sectionÂ hob unit and separate sinkÂ 4' wall above - need partition with glassÂ The current sink in same position for vegÂ dish drainerÂ MBR wardrobe with loft-slidingÂ Study unit -big with storage with loftÂ Parents' bedroomÂ wardrobe with loftÂ Queen size bedÂ Storage unit with loftÂ Kids bedroomÂ wardrobe with loftÂ King size with study - for 2 Â common Bathroom IndianÂ Bathrooms - 2 partitionÂ bottom storageÂ brush spacesÂ Bud- 15L-20L | [6 empty] | 2026-03-04 |  | 2026-03-11
18182 | Turnkey | 2026-01-01 | Vivek Pratap Singhh | L & T Seawoods At West Square | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Yash Metha | Akshat Shrivastava | Murali S | Nishtha Valawalkar | Prasad Bhivaji Hande | Active | Installation | Execution | 2712631 | 2719512 | 2267236 | 0 | 2712631 | 36 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-25 | 2026-01-25 21:46 | 2026-02-06 | 2026-02-06 15:42 | 2026-02-17 | 2026-02-17 00:24 | 2026-03-10 | 2026-03-10 18:07 | 2026-03-25 | 2026-03-24 08:01 | 2026-04-05 | 2026-04-05 22:04 | 2026-02-17 | 2026-02-17 19:11 | 2026-02-18 | 2026-02-18 00:15 | 2026-02-18 | 2026-02-23 10:36 | 2026-02-26 | 2026-02-26 16:26 |  |  |  |  | 2026-03-10 | 2026-03-13 12:29 | 2026-03-25 | 2026-03-25 12:35 | 2026-03-26 | 2026-03-26 07:38 |  |  | 2026-04-11 | 2026-04-18 13:15 | 2026-04-21 | 2026-04-21 23:09 | 2026-04-22 | 2026-04-23 00:01 | 2026-04-30 | 2026-04-28 11:45 |  |  |  |  | 2026-05-02 17:47 | 2026-05-08 | 2026-05-08 14:29 | 2026-05-29 | 2026-05-28 21:56 | 2026-05-27 | 2026-05-26 18:50 | 2026-05-28 | 2026-06-08 15:55 | 2026-06-05 | 2026-06-09 09:02 | 2026-06-11 | 2026-06-16 13:08 |  |  | 2026-05-30 |  | 2026-06-01 |  | 2026-07-31 | [5 empty] | 2026-04-28 | 2026-04-28 13:55 | 2026-03-07 | 2026-03-05 13:15 | Site is RTMI | 2026-01-25 | 2026-01-25 21:43 | 2417905.9977 | 399239 | 0 | 0 | 2967897.7958 | 490062 | 2967897.7958 | 490062 | 2026-07-13 09:48:28 +0530 | Yash Metha | As of today, the execution status is as below: Modular installation with material is completed. The work is currently on hold due to pending Membrane & Profile Shutters. Mirror measurements were taken on 11th July. ETA for delivery is 15th July. Final painting is scheduled from 15th July to 20th July, followed by texture paint on 20th July. Deep cleaning is planned for 26th July Aristo shutter is required by 25th July. Wallpaper installation is planned for 27th July. Marshalls wallpaper is delivered and LnC color is in transit. SQC 2 & HO is scheduled for 27th July. | 2026-06-24 10:13:23 +0530 | Yash Metha | *Modular Work:*Â Â Installation is in process. ETA for completion: 10th July. Dependency on S3. *Schedule & Deliveries:*Â Â 1. *Mirror Measurement* - Planned for 29th JuneÂ Â 2. *Profile Shutter Delivery* - ETA: 2nd JulyÂ Â 3. *Wallpaper Delivery (LnC)* - ETA: 5th July. Designer approval pendingÂ Â 4. *Marshalls Wallpaper* - Yet to be dispatchedÂ Â 5. *Carpentry Work* - Planned for 30th JuneÂ Â 6. *Profile Shutter* - ETA: 5th July *Pending Items / Issues:*Â Â 1. *Counter Top* - PO not yet raised. BOM is approved.Â Â 2. *Spacewood Material* - ETA not confirmed by VM yet due to PO rate issues. | 2026-05-18 16:09:46 +0530 | Yash Metha | PI work in process - Floor covering done False ceillig framing done Gypsum board installtion in process Electrical wiring in process - Electrical materil will be shared with client waiting for delivery on-site | 2026-03-11 | 2026-03-10 18:09 | 2026-03-25 | 2026-03-24 08:03
18183 | Turnkey | 2026-01-01 | Sanika Sanjay Sawant , Chinmayi Sanjay Sawant | Agastya infra | MUM - Thane | Yes | Hemant Sonar | Anamika Dolai | Anil Kuwar |  | Krutika Date | suraj kumar | Aditya Vikram | Murali S | Nishtha Valawalkar | Aakash Gaikwad | Active | Handover | Project Closure Pending | 810009 | 810009 | 1045862 | 0 | 850009 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-25 | 2026-01-25 21:43 | 2026-02-01 | 2026-02-03 14:33 | 2026-02-15 | 2026-02-15 19:54 | 2026-03-23 | 2026-03-22 14:06 | 2026-03-23 | 2026-03-22 14:08 | 2026-04-15 | 2026-04-15 19:28 | 2026-02-15 | 2026-02-16 19:24 | 2026-02-16 | 2026-02-16 20:57 | 2026-02-16 | 2026-02-19 09:40 | 2026-02-20 | 2026-02-26 16:49 |  |  |  |  | 2026-03-13 | 2026-03-09 19:24 | 2026-04-01 | 2026-04-02 18:35 | 2026-04-03 | 2026-04-02 18:37 |  |  | 2026-04-16 | 2026-04-17 17:14 | 2026-04-18 | 2026-04-18 13:08 | 2026-04-19 | 2026-04-18 13:31 | 2026-04-19 | 2026-04-22 21:08 |  |  |  |  | 2026-04-23 18:34 | 2026-05-01 | 2026-05-02 19:59 | 2026-05-19 | 2026-05-15 19:04 | 2026-05-15 | 2026-05-19 17:40 | 2026-05-15 | 2026-05-22 22:44 | 2026-05-22 | 2026-05-27 20:44 | 2026-06-10 | 2026-06-16 13:10 |  |  | 2026-07-06 | 2026-06-26 22:46 | 2026-07-08 | 2026-06-27 22:03 | 2026-07-09 | 2026-06-28 18:42 |  |  |  |  | 2026-04-18 | 2026-04-23 15:40 | 2026-04-22 | 2026-03-08 15:29 | Site is RTMI | 2026-01-25 | 2026-01-25 21:42 | 886324 | 159538 | 0 | 0 | 966736.0713 | 152543 | 966736.0713 | 152543 | 2026-06-24 01:01:47 +0530 | suraj kumar | Site Report: Modular installation work has been completed.Metal fabrication has been delivered nd installed.Beading nd Flat patti has been installed.Wallpaper has been delivered and installed.Profile shutter delivered nd installed.Final coat of paint work is in progress. ( ETA- 24th June)DC Planned- 25th JuneQc- 26thHO- 27th or 28th Need to be refund the febonic bed amount. | 2026-06-01 15:30:24 +0530 | suraj kumar | Some Image was uploaded | 2026-06-01 15:26:15 +0530 | suraj kumar | All The base work has been completed.Modular material delivered on 29th may.Currently, modular installation work is in progress.Day 1 done on 1st june.Day 4 done by 4th june.Electric lights fixtures installation work is in progress. | 2026-03-23 | 2026-03-22 14:06 | 2026-03-23 | 2026-03-22 14:09
18184 | Turnkey | Dec'25 | Raj Bhanushali | Runwal Forest | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [7 empty] | Hold | Preproduction | Site Readiness 1 | 802200 | 109999 | 874130 | 802200 | 0 | 2 | 104 | 0 | 0 | 389723 | 302478 |  |  | 2026-01-26 | 2026-01-28 10:48 | 2026-01-26 | 2026-01-30 14:46 | 2026-02-01 | 2026-02-01 11:39 | 2026-03-12 | 2026-03-12 12:40 | 2026-03-12 | 2026-03-12 13:14 |  |  | 2026-02-01 | 2026-01-30 18:06 | 2026-02-02 | 2026-02-01 12:46 | 2026-02-02 | 2026-02-03 12:39 | 2026-02-03 | 2026-02-10 13:48 | 2026-03-31 | 2026-03-31 22:29 | 2026-04-03 | 2026-03-31 22:51 | 2026-04-15 | 2026-03-31 | 2026-08-11 |  | 2026-08-12 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-22 |  | 2026-08-22 | [6 empty] | 2026-08-28 |  | 2026-09-06 |  | 2026-03-27 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-09 |  |  |  | 2026-10-01 |  | 2026-10-03 |  | 2026-10-04 | [5 empty] | 2026-08-22 |  | 2026-06-09 | 2026-03-11 19:01 | Site is Non-RTMI | 2026-01-25 | 2026-01-27 16:42 | 1021323.9387 | 156223 | 908844.7893 | 137623 | 0 | 0 | 908844.7893 | 137623 | 2026-07-10 13:45:44 +0530 | Divya Rahangdale | CX will receive the possession by December. | 2026-05-07 19:35:29 +0530 | Sneha Kadam | he is expecting Bonito to close IM by requesting the builder. Possession is by Aug Sept 2026 | 2026-02-03 13:06:01 +0530 | Mayuri Patil | Some Image was uploaded
18185 | Turnkey | 2026-01-01 | Sonali Prakash | dosti | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Faraz Soudagar | Aditya Vikram | Murali S |  | Prasad Bhivaji Hande | Hold | Preproduction | Site Readiness 2 | 1665332 | 1027688 | 2662012 | 0 | 1665332 | 13 | 78 | 0 | 0 | 0 | 637644 |  |  | 2026-01-25 | 2026-01-28 10:35 | 2026-01-30 | 2026-01-30 11:00 | 2026-02-07 | 2026-02-07 21:32 | 2026-03-11 | 2026-03-11 15:31 | 2026-05-18 | 2026-05-17 12:12 | 2026-05-25 | 2026-05-24 23:57 | 2026-02-07 | 2026-02-10 16:30 | 2026-02-08 | 2026-02-10 18:36 | 2026-02-10 | 2026-02-12 15:35 | 2026-02-20 | 2026-02-20 13:24 |  |  |  |  | 2026-03-12 | 2026-03-18 14:07 | 2026-05-19 | 2026-05-21 05:38 | 2026-05-22 | 2026-05-21 05:38 |  |  | 2026-05-27 | 2026-05-30 10:07 | 2026-05-30 | 2026-05-30 11:55 | 2026-05-31 | 2026-05-30 13:20 | 2026-05-31 | 2026-05-31 13:07 | [5 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-05-30 |  | 2026-02-21 | 2026-02-26 12:26 | Site is RTMI | 2026-01-25 | 2026-01-27 16:44 | 2255943 | 406069 | 0 | 0 | 1896180.9698 | 306660 | 1896180.9698 | 306660 | 2026-07-05 13:17:35 +0530 | Divya Rahangdale | Hold till 20th July | 2026-06-09 18:04:52 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-29 14:23:24 +0530 | Asavari Vare | Some Image was uploaded | 2026-03-12 | 2026-03-12 12:28 | 2026-05-18 | 2026-05-17 12:14
18186 | Turnkey | 2026-01-01 | Swapnil Amale | Shantinath Temporary | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Akash Jadhav | Sandeep Tiwari | Murali S |  | Shailendra Mishra | Active | Production | Dispatch Due | 1378813 | 1378813 | 1704705 | 1480518 | 1378813 | 17 | 6 | 0 | 0 | 0 | 0 |  |  | 2026-01-25 | 2026-01-25 22:15 | 2026-01-27 | 2026-01-27 13:16 | 2026-02-01 | 2026-02-03 10:53 | 2026-03-06 | 2026-03-05 17:03 | 2026-05-01 | 2026-04-30 15:58 | 2026-05-06 | 2026-05-06 13:23 | 2026-02-03 | 2026-02-03 18:58 | 2026-02-04 | 2026-02-04 14:21 | 2026-02-04 | 2026-02-05 11:58 | 2026-02-20 | 2026-02-20 13:26 |  |  |  |  | 2026-03-05 | 2026-03-09 19:13 | 2026-05-02 | 2026-05-05 10:46 | 2026-05-06 | 2026-05-05 10:46 |  |  | 2026-05-10 | 2026-05-17 11:04 | 2026-05-17 | 2026-05-17 12:13 | 2026-05-18 | 2026-05-17 19:32 | 2026-05-18 | 2026-05-22 18:57 |  |  |  |  | 2026-05-24 14:34 | 2026-06-03 | 2026-06-03 20:09 | 2026-06-30 | 2026-06-28 20:01 | 2026-06-25 | 2026-06-25 18:05 | 2026-06-28 | 2026-07-09 20:26 | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-07-09 | [5 empty] | 2026-05-17 | 2026-05-22 20:04 | 2026-02-21 | 2026-02-21 12:31 | Site is RTMI | 2026-01-25 | 2026-01-25 22:15 | 1444666 | 260039 | 1466628.656 | 256350 | 1429374.7862 | 240835 | 1429374.7862 | 240835 | 2026-06-17 13:23:48 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-15 13:45:24 +0530 | Akash Jadhav | Procurement: CX PI work in progress Cx handover the key at 22th June | 2026-02-22 17:04:37 +0530 | Chaitali Sawant | DDM1 Conclusion Compared to the booking estimate, we need confirmation on the below: Customised dining table design is not possible in modular.Demolition of existing false ceiling and minor refurbishment to be done from outside (client scope).Additional scope: Shutters for kitchen and water tank area.Removed items: MandirMBR Separate dresser storageKBR BedWashroom storageLiving Room:Fish tank in balconyFoldable dining table custom work (client scope)Rafters for TV wall + sharing few design optionsRemoving existing false ceiling and furniture (client scope)Pending: Shoe unit positionKitchen:Need appliance sizes: Fridge size requiredMicrowave client will purchase as per available spaceRO client will purchase as per available spaceHob & Chimney please select from shared referencesWashing machine Dry area in MBRPooja unit in carpentry (client scope)KBR:We will keep existing bed need full bed size (all 3 dimensions + headboard size)CPU & keyboard size is mandatory4 ft wide study unit with storage belowMBR:Mirror with side storage confirmedDDM2 8th March Agenda: Material selection & finalise estimateÂ | 2026-03-06 | 2026-03-05 17:04 | 2026-05-01 | 2026-05-03 15:24
18187 | Turnkey | 2026-01-01 | Paresh Sahu | UNIQUE VISTAS | MUM - Thane | Yes | Pooja Nakul Sharma | [7 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 2943354 | 9999 | 0 | 0 | 0 | 168 | 0 | 284336 | 294335 | 1180824 | 1173859.2 |  |  | 2026-01-24 | 2026-01-28 15:13 | 2026-01-26 | 2026-02-04 16:21 | 2026-01-30 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-02-28 |  | 2026-02-07 |  | 2026-02-08 |  | 2026-02-08 |  | 2026-02-09 | [5 empty] | 2026-02-15 |  | 2026-02-23 |  | 2026-02-24 |  |  |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 | [6 empty] | 2026-03-24 |  | 2026-04-02 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-05 |  |  |  | 2026-04-27 |  | 2026-04-29 |  | 2026-04-30 | [5 empty] | 2026-03-04 |  | 2026-02-10 |  | Site is RTMI | 2026-01-24 | 2026-01-28 15:11 | 0 | 0 | 0 | 0 | 0 | 0 | 2494368 | 448986 | 2026-01-26 14:10:31 +0530 | Karuna Shinde | Some Image was uploaded | [6 empty] | 2026-02-15 |  | 2026-02-22
18189 | Turnkey | 2026-01-01 | Hareesh | Affinity brundaavana | BNG - HRBR | Yes | Sanjay Kulkarni | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | DCM Due | 1156913 | 9999 | 0 | 0 | 0 | 77 | 0 | 105692 | 115691 | 484278 | 441252.8 |  |  | 2026-01-26 | 2026-04-29 12:15 | 2026-01-27 |  | 2026-01-30 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-01 | [5 empty] | 2026-02-07 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-02-24 |  | 2026-02-02 |  | Unknown | 2026-01-26 | 2026-02-04 19:11 | 0 | 0 | 0 | 0 | 0 | 0 | 980435 | 176478 | 2026-04-29 12:13:12 +0530 | Kushal S | Some Image was uploaded | 2026-01-26 13:39:15 +0530 | Sreelakshmi M | DCM: 2BHK Interior Requirements Budget 8 Lakhs Family Details Occupants: 3 members Budget: Below 10 lakhs (Target: 8 lakhs) *Living Room TV Unit: Wall-mounted storage Back panel Tall unit with glass shutter Feature wall design False ceiling: Peripheral design with lighting Wooden framing with integrated lighting at dining entry dining area *DINING AREA Crockery unit with center mirror Minimal false ceiling Wall concept treatment Wooden pooja unit as per the reference photo *Kitchen Modular layout with: One-side loft storage Bottom cabinets Top cabinets with rolling shutter Hydraulic lift cabinets Wicker basket pull-out RO unit provision Sink Space for single-door refrigerator Finish: Glossy laminate in lighter shade *Utility Area Top storage cabinets Ledge/shelf on opposite wall Washing machine provision *Master Bedroom Openable wardrobe with loft King-size bed Center arch-shaped headboard wall design with wallpaper Dresser unit on left side wall Foldable study with top ledges *Master Bathroom Vanity unit *Guest Bedroom Wardrobe with loft Dresser mirror with ledge Beading frame detailing with wallpaper accent wall |  |  |  | 2026-02-07 |  | 2026-02-14
18190 | Turnkey | 2026-01-01 | Manoj Sathyan Thekkethil | Marina | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera |  | Ehtesham Bhati | Suraj Jaiswar | Rizwan Mistry | Murali S | Sanskruti Yadav | Aakash Gaikwad | Active | Installation | Execution | 1904016 | 1904016 | 1981962 | 0 | 1904016 | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-26 | 2026-01-27 12:48 | 2026-01-27 | 2026-01-27 12:56 | 2026-01-30 | 2026-01-27 13:23 | 2026-02-27 | 2026-02-27 14:58 | 2026-02-28 | 2026-02-27 15:23 | 2026-03-25 | 2026-03-28 11:46 | 2026-01-27 | 2026-01-30 11:55 | 2026-01-28 | 2026-01-30 15:21 | 2026-01-30 | 2026-02-02 12:56 | 2026-02-19 | 2026-02-19 16:59 |  |  |  |  | 2026-02-25 | 2026-02-26 19:32 | 2026-03-06 | 2026-03-06 15:42 | 2026-03-07 | 2026-03-21 11:11 |  |  | 2026-04-11 | 2026-04-18 16:32 | 2026-04-18 | 2026-04-18 19:12 | 2026-04-19 | 2026-04-18 20:24 | 2026-04-19 | 2026-04-20 12:16 |  |  |  |  | 2026-04-22 18:09 | 2026-05-04 | 2026-04-30 22:27 | 2026-05-22 | 2026-05-23 17:34 | 2026-05-21 | 2026-05-21 18:31 | 2026-05-23 | 2026-05-26 17:24 | 2026-05-27 | 2026-05-29 15:58 | 2026-06-16 | 2026-06-16 13:13 |  |  | 2026-07-16 |  | 2026-07-18 |  | 2026-07-19 | [5 empty] | 2026-04-18 | 2026-04-22 18:08 | 2026-02-20 | 2026-02-27 14:53 | Site is RTMI | 2026-01-26 | 2026-01-26 12:45 | 1679629 | 302333 | 0 | 0 | 2053563.7038 | 337807 | 2053563.7038 | 337807 | 2026-07-06 23:04:48 +0530 | Suraj Jaiswar | Execution: PID -18190 Living room 1. Paint touch up. 2. Jhula hook clean 3. Moulding patti installation pending. 4. Sofa wall paint code confirm with designer. 5. Electrical switch board checking. 6. Modular alignment. 7. Strip light installation on TV panelling. Kitchen 1. Chimney tiles change. 2. Cement cleaning. 3. Granite polish. 4. Rolling unit shelf shifting. 5. Above the wall unit finishing is pending. 6. Alignment and chain installation. Kids room 1. Rafter installation. 2. Texture on bed wall. 3. Paint touch up. 4. Hanging light point. 5. Strip light installation 6. Modular alignment and chain installation. Master room. 1. Paint touch up. 2. Electrical check. 3. Moulding patti install. 4. Hanging light point check for separate button. 5. Modular alignment, chain installation and handle installation. 6. Ceiling fan noise. | 2026-07-01 23:40:29 +0530 | Suraj Jaiswar | Execution: | 2026-07-01 23:37:19 +0530 | Suraj Jaiswar | Execution: Painting Work is in progress. it will be done by 3rd july. cleaning work is in progress. cx. moving on 3rd july. Blocker:- Bed and Chimney, | 2026-02-28 | 2026-02-27 15:01 | 2026-02-28 | 2026-02-27 15:24
18191 | Turnkey | 2026-01-01 | Aboli Sorte Telawne | Raymond Address Season 1 | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Nishtha Valawalkar |  | Active | Design | DEM1 | 8162494 | 659999 | 8162494 | 0 | 0 | 35 | 77 | 0 | 972500 | 3563405 | 2966590.4 |  |  | 2026-01-26 | 2026-01-26 20:09 | 2026-03-21 | 2026-03-21 22:08 | 2026-03-24 | 2026-03-21 22:13 | 2026-09-04 |  | 2026-09-11 |  | 2026-09-18 |  | 2026-03-21 | 2026-03-23 18:29 | 2026-03-22 | 2026-03-25 13:23 | 2026-03-25 | 2026-03-25 16:00 | 2026-04-05 | 2026-04-05 14:30 |  |  |  |  | 2026-09-05 |  | 2026-09-13 |  | 2026-09-14 |  |  |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 | [6 empty] | 2026-10-12 |  | 2026-10-21 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-24 |  |  |  | 2026-11-15 |  | 2026-11-17 |  | 2026-11-18 | [5 empty] | 2026-09-22 |  | 2026-08-31 |  | Unknown | 2026-01-26 | 2026-01-26 20:07 | 6917368 | 1245126 | 0 | 0 | 0 | 0 | 6917368 | 1245126 | 2026-07-10 16:11:49 +0530 | Divya Rahangdale | CX will receive possession by August. | 2026-06-26 12:18:38 +0530 | Naved Malik | Some Image was uploaded | 2026-06-11 18:12:02 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-09-05 |  | 2026-09-12
18192 | Turnkey | 2026-01-01 | Ashok k | Greenfinch Meadows | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [5 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 3445344 | 9999 | 0 | 0 | 0 | 112 | 0 | 334535 | 344534 | 1432604 | 1323671.6 |  |  | 2026-01-26 | 2026-02-06 12:16 | 2026-01-26 | 2026-03-25 19:43 | 2026-02-07 | 2026-03-25 19:45 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-01-26 | 2026-01-26 14:10 | 0 | 0 | 0 | 0 | 0 | 0 | 2919783 | 525561 | 2026-01-26 16:57:52 +0530 | Salpriyan Pm | Some Image was uploaded | 2026-01-26 15:57:57 +0530 | Salpriyan Pm | FoyerÂ seater unit and shoe rack (storage not for shoes) mirror rafters on top with lightÂ Living - 205Â Tv unit -refer imageÂ sofa back wall - beading wall -EC Dining -206 (the living part) bar stool, counter, right wall of the bar with design and hanging lightsÂ ledges design on that wall with some cover on the edges. - refer image (vintage) Crockery on the opp wall -EC (dark glass ) 8'Â 5' height pooja -2'6" wide poojaÂ V groove mirror (wooden finishes) RustyÂ The wall - removed (3feet wall on the entry wall) (then partition wall wooden for 2 feet more) Top wall rafters and spotlights through out 2feet beam on the top all the way till the toilet wallÂ The main wall - where the actual dining is coming, need a design excluding rafters (stone cladding) or some unique design. 10' wallÂ 206 Kitchen- MainÂ No utility separationÂ In place of WM- dishwasherÂ wooden laminate, acrylic, lacq glass - mixÂ Rolling shutterÂ bottle pullout tall unitÂ pantry pull out-EC open ledgesÂ Quartz sink -Big oneÂ Fridge - 2 doorÂ Fridge- either on the opp wall or if on this wall need sugg for the open area with some designÂ 205 kitchen - utilty and storeroomÂ WM ' Tall unit, bottom cabinets and top cabinetsÂ sliding door - for both the kitchen entry Passage areasÂ the toilet wall on each side will have photo framesÂ Profile lights - l shapeÂ And a diff colour from the livingÂ 206-MBR wooden flooring - costing requiredÂ King size bedÂ Aristo wardrobe - 9' wideÂ 4' dressing - with storageÂ 205-MBR wooden flooring - costing requiredÂ Queen size bed sliding wardrobe with loft - 9' wide Seater unit on the window wall merging into a study on one side and the tall unit on the other. - Refer the videoÂ Storage above the studyÂ chocolate colourÂ Mirror - long one on the right end of the wardrobeÂ 206-GBR Â Queen bedÂ 6' sliding wardrobe with dressing unitÂ study unit with top storageÂ 205-GBR single bed or diwan- storge above the bed.Â L shape workstationÂ tv with storageÂ single tall unit with loft for few clothsÂ False ceiling - vibrantÂ every other room - simple and elegant All bathroomsÂ bottom storage and top storage, mirror in centre 206 balconies fully designed with wooden theme- refer imageÂ 205 balconiesÂ some designsÂ False ceiling -All rooms and living and dining - refer image (wooden design) |  |  |  | 2026-04-02 |  | 2026-04-09
18193 | Turnkey | 2026-01-01 | Pooja Petkar | Yogakshema Residency | MUM - GOR | Yes | Sakshi Hire |  | Shahid Chougley | [5 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1237271 | 9999 | 1237271 | 0 | 0 | 145 | 0 | 113728 | 123727 | 512334 | 477482.4 |  |  | 2026-01-26 | 2026-02-06 19:37 | 2026-02-04 | 2026-02-08 13:49 | 2026-02-14 | 2026-02-20 15:18 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-01-26 | 2026-02-06 19:37 | 1370126.65 | 211617 | 0 | 0 | 0 | 0 | 1370126.65 | 211617 | 2026-02-04 20:17:59 +0530 | Sakshi Hire | DCM: 2 adults 1 teenager trader by profession gas hob on opp side 4seater dining table marble 3+1 seater sofa pooja unitÂ tv unit with side shelf 55" tv size queen size bed study table foldable with storage king size bedÂ workstation 2 laption dresser with side table fc in living dining wifi point inverterÂ planter in livingÂ window seating possible vanity in wc & mirror shelfÂ safetyÂ | [6 empty] | 2026-02-28 |  | 2026-03-07
18194 | Turnkey | 2026-01-01 | Farha | Prestige Green Gables | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 1882610 | 9999 | 0 | 0 | 0 | 170 | 0 | 178262 | 188261 | 753044 | 753044 |  |  | 2026-01-26 | 2026-01-26 14:27 | 2026-01-26 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-16 | [5 empty] | 2026-02-22 |  | 2026-03-02 |  | 2026-03-03 |  |  |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 | [6 empty] | 2026-03-31 |  | 2026-04-09 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-12 |  |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | 2026-03-11 |  | 2026-02-17 |  | Unknown | 2026-01-26 | 2026-01-26 14:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1595432 | 287177 | [9 empty] | 2026-02-22 |  | 2026-03-01
18195 | Turnkey | 2026-01-01 | Shadab Akhlaq | Confident Mayfair | BNG - HSR | Yes | Priyanka Mathur | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Hold | Preproduction | Site Readiness 1 | 1266055 | 264938 | 1705566 | 0 | 0 | 2 | 120 | 0 | 0 | 551282 | 449834.8 |  |  | 2026-01-26 | 2026-01-26 14:30 | 2026-02-07 | 2026-02-07 11:44 | 2026-02-10 | 2026-02-08 13:25 | 2026-03-15 | 2026-03-15 16:04 | 2026-11-05 |  | 2026-11-12 |  | 2026-02-08 | 2026-02-11 12:22 | 2026-02-09 | 2026-02-12 19:05 | 2026-02-12 | 2026-02-13 17:17 | 2026-02-20 | 2026-02-20 16:57 |  |  |  |  | 2026-03-15 | 2026-03-15 18:18 | 2026-11-07 |  | 2026-11-08 |  |  |  | 2026-11-15 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 | [6 empty] | 2026-12-06 |  | 2026-12-15 |  | 2026-12-14 |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-18 |  |  |  | 2027-01-09 |  | 2027-01-11 |  | 2027-01-12 | [5 empty] | 2026-11-16 |  | 2026-03-27 | 2026-03-15 15:54 | Site is Non-RTMI | 2026-01-26 | 2026-01-26 14:29 | 1445395 | 260171 | 0 | 0 | 0 | 0 | 1437600.8318 | 237364 | 2026-07-14 17:05:13 +0530 | Abhinandan K S |  | 2026-04-16 12:56:50 +0530 | Athul Ajaykumar | Call disconnected. | 2026-03-24 15:16:05 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-03-16 | 2026-03-15 16:19 | 2026-11-06
18196 | Turnkey | Dec'25 | Sukanya soumen samanta |  | MUM - Thane | Yes | Rachna Abhyankar | Anil Jagtap | Anil Kuwar |  | Krutika Date |  |  |  | Mustufa Sohagpurwala | Shailendra Mishra | Hold | Preproduction | 2D | 1971672 | 561391 | 2342821 | 1971672 | 0 | 53 | 46 | 0 | 0 | 676753 | 733528.4 |  |  | 2026-01-27 | 2026-01-26 17:05 | 2026-01-27 | 2026-01-27 13:15 | 2026-02-02 | 2026-01-31 13:25 | 2026-03-13 | 2026-03-13 12:19 | 2026-03-13 | 2026-03-13 12:42 | 2026-03-13 | 2026-03-13 18:46 | 2026-02-02 | 2026-01-31 19:42 | 2026-02-03 | 2026-02-01 12:11 | 2026-02-03 | 2026-02-04 12:36 | 2026-02-04 | 2026-02-17 12:43 | 2026-03-13 | 2026-03-13 19:19 | 2026-03-16 | 2026-03-18 14:45 | 2026-03-16 | 2026-03-18 14:26 | 2026-03-27 | 2026-03-25 19:52 | 2026-03-26 | 2026-03-27 16:59 |  |  | 2026-04-07 | 2026-04-10 17:04 | 2026-07-15 |  | 2027-12-31 |  | 2027-12-31 | [6 empty] | 2028-01-06 |  | 2028-01-15 |  | 2028-01-14 |  | 2028-01-15 |  | 2028-01-16 |  | 2028-01-18 |  |  |  | 2028-02-09 |  | 2028-02-11 |  | 2028-02-12 | [5 empty] | 2027-12-31 |  | 2026-02-05 | 2026-02-20 17:42 | Site is RTMI | 2026-01-26 | 2026-01-26 17:04 | 1985442 | 357379 | 1983092.6044 | 349577 | 0 | 0 | 1983092.6044 | 349577 | 2026-06-26 16:50:36 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-18 17:14:14 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-02 19:22:20 +0530 | Sarita Jangid | Some Image was uploaded
18197 | Turnkey | 2026-01-01 | Kalyan Koti | ATZ Areva | BNG - HSR | Yes |  |  | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | DCM Due | 1454216 | 9999 | 0 | 0 | 0 | 170 | 0 | 135423 | 145422 | 599125 | 564247.6 |  |  | 2026-01-26 | 2026-01-26 15:07 | 2026-02-18 | 2026-02-18 09:55 | 2026-02-15 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 | [5 empty] | 2026-03-01 |  | 2026-03-09 |  | 2026-03-10 |  |  |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 | [6 empty] | 2026-04-07 |  | 2026-04-16 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-19 |  |  |  | 2026-05-11 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-03-18 |  | 2026-02-24 |  | Unknown | 2026-01-26 | 2026-01-26 15:06 | 0 | 0 | 0 | 0 | 0 | 0 | 1232386 | 221829 | [9 empty] | 2026-03-01 |  | 2026-03-08
18198 | Turnkey | 2026-01-01 | Venkat Kubendran | ArK Oak Tree | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Suchendra Shetty | Jairam Joshi | Murali S |  | Vishwa Hiremath | Active | Production | 100% Payment | 1905260 | 1905260 | 1888388 | 0 | 1898805 | 11 | 8 | 0 | 0 | 0 | 0 |  |  | 2026-01-26 | 2026-02-08 11:21 | 2026-01-26 | 2026-02-24 15:55 | 2026-02-26 | 2026-02-26 17:45 | 2026-04-04 | 2026-04-07 11:43 | 2026-05-04 | 2026-05-03 12:27 | 2026-05-16 | 2026-05-16 11:30 | 2026-02-26 | 2026-02-28 13:00 | 2026-02-27 | 2026-02-28 22:38 | 2026-02-28 | 2026-03-05 12:00 | 2026-03-07 | 2026-03-07 11:10 |  |  |  |  | 2026-05-02 | 2026-05-02 18:20 | 2026-05-05 | 2026-05-05 19:52 | 2026-05-06 | 2026-05-10 19:34 |  |  | 2026-05-17 | 2026-05-19 20:00 | 2026-05-28 | 2026-05-28 20:21 | 2026-05-28 | 2026-05-28 20:22 | 2026-06-05 | 2026-06-10 11:29 |  |  |  |  | 2026-06-10 15:26 | 2026-06-26 | 2026-06-25 20:56 | 2026-07-06 | 2026-07-04 19:06 | 2026-07-05 |  | 2026-07-04 |  | 2026-07-09 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-05-28 | 2026-06-03 16:01 | 2026-03-08 | 2026-04-04 15:31 | Site is RTMI | 2026-01-26 | 2026-01-26 15:14 | 1600328 | 288059 | 0 | 0 | 2101718.9244 | 339224 | 2115241.3244 | 340209 | 2026-07-09 13:19:20 +0530 | Jairam Joshi | 100% Payment: CX side PI wip- delayed Key - 7th july FC- 8th June Ele & False cieling - 9th July - 19th July SRD- 20th July | 2026-06-19 15:53:32 +0530 | Jairam Joshi | Procurement: CX side PI wip- delayed Key - 29th June FC- 30th June Ele & False cieling - 1st July - 10th July SRD- 11th July | 2026-06-15 17:04:49 +0530 | Jairam Joshi | Procurement: CX side PI wip- delayed Key - 19th FC- 20th Ele & False cieling - 22nd - 27th SRD- 29th | 2026-04-08 | 2026-04-07 11:47 | 2026-05-04 | 2026-05-03 12:30
18199 | Turnkey | 2026-01-01 | Manu Madhavan | Sattva east crest | BNG - HRBR | Yes | Arjun M V | Rajeshwari S | Yogesh Patidar | [5 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 1683117 | 79999 | 1683117 | 0 | 0 | 165 | 0 | 88313 | 168312 | 676729 | 669764.4 |  |  | 2026-01-26 | 2026-01-28 12:50 | 2026-01-28 | 2026-01-28 16:44 | 2026-02-01 | 2026-02-01 10:42 | 2026-02-08 |  | 2026-02-15 |  | 2026-02-22 |  | 2026-02-01 |  | 2026-02-02 |  | 2026-02-02 |  | 2026-02-03 | [5 empty] | 2026-02-09 |  | 2026-02-17 |  | 2026-02-18 |  |  |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-27 |  | 2026-02-28 | [6 empty] | 2026-03-18 |  | 2026-03-27 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-30 |  |  |  | 2026-04-21 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-02-26 |  | 2026-02-04 |  | Unknown | 2026-01-26 | 2026-01-26 15:37 | 1426370 | 256746 | 0 | 0 | 0 | 0 | 1426370 | 256746 | 2026-01-28 16:17:59 +0530 | Arjun M V | Property:Sattva East Crest Type:3BHK Location:Budhigere cross RTMI:Yes Budget:12L Foyer inside Shoerack with seater(Reference shared) Behind shoerack -wall concepts (mirror ,buddha) Dining and Living Dining (existing table and chair) TV unit(Minimal storage)-Reference shared Pooja Unit(Reference shared) Crockery Unit cum bar unit Sofa back wall-Wall concepts False ceiling required-Living, dining, Foyer (Peripheral) Kitchen Hob &Chimney:Movable(client has it) Sink:Utility RO:utility Loft:Both side loft Refrigerator: Side by side MW-Movable Countertop:Granite WM:utility Cylinder: Piping Master bedroom Bed in place of wardrobe Wardrobe in place of bed and add a dresser next to it and next to bed -study unit placement. NO TV False ceiling-Not required Bed back designs Bedroom 1(Kids bedroom)-Son age:4yrs No kiddish room Study +Bookshelves+ Wardrobe (on existing bed side) Bed moving to the opposite side Miror on the wardrobe door Bedroom 2(GBR) Wardrobe opposite to the bed Bed side dresser(facing the door) Try for a window seater Bathroom: No scope for bonito. Passage area: Wall concepts needed(photo frames) 31st Jan at 4pm meeting scheduled for CDP. | [6 empty] | 2026-02-09 |  | 2026-02-16
18200 | Turnkey | 2026-01-01 | Mr.Amit Mondal, Mrs.Satabdi Chowdhury | Sobha Sentosa | BNG - HRBR | Yes | Arjun M V | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Shijin C C | Jairam Joshi | Murali S | Janvi Nagdeo | Abdul Shafeen | Completed | Complete | Completed | 1498920 | 1498920 | 1207435 | 0 | 1498920 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-26 | 2026-01-26 19:49 | 2026-01-31 | 2026-01-31 08:56 | 2026-02-03 | 2026-02-03 12:19 | 2026-02-28 | 2026-02-28 21:10 | 2026-03-02 | 2026-03-01 19:23 | 2026-03-19 | 2026-03-19 19:06 | 2026-02-03 | 2026-01-31 05:30 | 2026-02-04 | 2026-02-06 17:33 | 2026-02-06 | 2026-02-09 18:24 | 2026-02-14 | 2026-02-14 12:19 |  |  |  |  | 2026-02-28 | 2026-03-01 18:47 | 2026-03-08 | 2026-03-08 19:11 | 2026-03-09 | 2026-03-10 17:26 |  |  | 2026-03-21 | 2026-03-22 13:51 | 2026-03-22 | 2026-03-22 20:14 | 2026-03-23 | 2026-03-24 10:23 | 2026-03-25 | 2026-03-26 18:41 |  |  |  |  | 2026-03-27 11:22 | 2026-04-03 | 2026-04-02 21:34 | 2026-04-16 | 2026-04-14 18:59 | 2026-04-15 | 2026-04-14 18:55 | 2026-04-14 | 2026-04-15 20:37 | 2026-04-15 | 2026-04-16 11:27 | 2026-04-23 | 2026-04-24 22:27 |  |  | 2026-05-26 | 2026-05-26 21:40 | 2026-06-06 | 2026-05-28 12:29 | 2026-06-07 | 2026-05-28 18:36 |  |  |  |  | 2026-03-22 | 2026-03-27 11:21 | 2026-02-15 | 2026-02-28 21:08 | Site is RTMI | 2026-01-26 | 2026-01-26 16:45 | 1023250 | 184185 | 0 | 0 | 1647163.5631 | 262970 | 1647163.5631 | 262970 | 2026-05-28 18:38:01 +0530 | Jairam Joshi | Project Closure Pending: Observation points Closure ETA - 11th June | 2026-05-19 18:23:04 +0530 | Jairam Joshi | Some Image was uploaded | 2026-05-14 12:08:01 +0530 | Jairam Joshi | Some Image was uploaded | 2026-03-10 | 2026-02-28 21:12 | 2026-03-02 | 2026-03-01 19:24
18201 | Turnkey | 2026-01-01 | Manoj sawant | silicon heritage tilak nagar | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 1776333 | 9999 | 0 | 0 | 0 | 170 | 0 | 167634 | 177633 | 775782 | 645284 |  |  | 2026-01-26 | 2026-01-26 17:23 | 2026-01-29 | 2026-01-29 22:17 | 2026-02-14 |  | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-16 | [5 empty] | 2026-02-22 |  | 2026-03-02 |  | 2026-03-03 |  |  |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 | [6 empty] | 2026-03-31 |  | 2026-04-09 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-12 |  |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | 2026-03-11 |  | 2026-02-17 |  | Unknown | 2026-01-26 | 2026-01-26 17:22 | 0 | 0 | 0 | 0 | 0 | 0 | 1505367 | 270966 | 2026-03-25 11:21:15 +0530 | Mustufa Sohagpurwala | Some Image was uploaded | 2026-01-29 20:08:15 +0530 | Pooja Nakul Sharma | DCM: Mr SawantÂ Silicon heritage Poss- in handÂ Family- 3 people Proff- telecom- sir ma'am- homemaker duaghter- CA studentÂ -To be vastu complaintÂ 1. Safety door + main door integrated, shoerack (15-18). 2. Folding dining table, Tv console, display unit, mandir unit.Â 3. 3+1 or L shape sofa. 4. Hidden/ sliding door for kitchen on tv wall.Â 5. Balcony beautification.Â 6. False ceiling in LR and bedrooms.Â 7. Kitchen- Standard applainces. KItchen- civil as hob and sink placement is swapped. Fully modular kitchen. Base, wall, loft storages. Space for M/O 8.Â Bedroom 1- Parents- King bed w storage, sliding wardrobe w loft, dresser, bed back design.Â 9. Bathroom - Base vanity storages.Â 10. Bedroom 2- Murphy bed (queen size), sliding wardrobe, study, dresser.Â 11. Hidden door for bathroom (MBR). 12. Budget- 15L 13. CDP- 31st at 3 pm | 2026-01-29 11:29:49 +0530 | Mustufa Sohagpurwala | Some Image was uploaded | 2026-02-22 |  | 2026-03-01
18202 | Turnkey | 2026-01-01 | Zaheed Shaikh | Runwal Forest | MUM - GOR | Yes | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera |  |  | suraj kumar | Aditya Vikram |  | Nivesh Gupta | Sunil Poojary | Active | Preproduction | DEM2 | 947772 | 284332 | 952772 | 0 | 0 | 22 | 0 | 0 | 0 | 304512 | 358928 |  |  | 2026-01-26 | 2026-01-26 19:52 | 2026-01-30 | 2026-01-30 12:19 | 2026-02-01 | 2026-02-01 19:11 | 2026-03-28 | 2026-03-28 19:46 | 2026-04-23 | 2026-04-22 17:49 | 2026-06-26 |  | 2026-02-01 | 2026-01-31 05:30 | 2026-02-02 | 2026-02-05 10:00 | 2026-02-05 | 2026-02-10 11:37 | 2026-02-20 | 2026-02-20 11:15 |  |  |  |  | 2026-04-08 | 2026-02-28 22:43 | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-07-03 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-04-03 | 2026-03-25 18:49 | Site is RTMI | 2026-01-26 | 2026-01-26 19:49 | 1115393.168 | 169744 | 0 | 0 | 0 | 0 | 1115393.168 | 169744 | 2026-06-03 16:54:57 +0530 | Heena Neogi | Cross Measurement: No posession till mid june . After posession CM to be aligned | 2026-05-07 14:09:44 +0530 | Manzoor Shaikh | Kindly ignore the previous notes - Out called the customer said the possession is in mid June and will check with the builder by today EOD when the CM can be planned. Accordingly will place the project on Hold | 2026-05-03 12:22:43 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-29 | 2026-03-28 19:48 | 2026-04-23 | 2026-04-22 18:09
18203 | Turnkey | 2026-01-01 | MOHAMMED AKRAM BORA | Rose gold Zaiden | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Design | DEM1 | 906869 | 139999 | 1374214 | 0 | 0 | 47 | 102 | 0 | 41375 | 362748 | 362747.6 |  |  | 2026-01-26 | 2026-02-10 19:23 | 2026-02-03 | 2026-02-10 19:40 | 2026-02-13 | 2026-02-11 17:58 | 2026-09-19 |  | 2026-09-26 |  | 2026-10-03 |  | 2026-02-11 | 2026-02-12 19:34 | 2026-02-12 | 2026-02-13 15:25 | 2026-02-13 | 2026-02-16 16:52 | 2026-02-21 | 2026-02-21 16:53 |  |  |  |  | 2026-09-20 |  | 2026-09-28 |  | 2026-09-29 |  |  |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-08 |  | 2026-10-09 | [6 empty] | 2026-10-27 |  | 2026-11-05 |  | 2026-11-04 |  | 2026-11-05 |  | 2026-11-06 |  | 2026-11-08 |  |  |  | 2026-11-30 |  | 2026-12-02 |  | 2026-12-03 | [5 empty] | 2026-10-07 |  | 2026-09-15 |  | Site is RTMI | 2026-01-26 | 2026-01-26 18:43 | 1164588 | 209625 | 0 | 0 | 0 | 0 | 986074.5162 | 161217 | 2026-04-04 14:20:10 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-29 11:38:03 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-11 10:31:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-09-20 |  | 2026-09-27
18204 | Turnkey | 2026-01-01 | Faisal Noorani | AB Cascal | MUM - GOR | Yes | Priyanka Patel |  | Shahid Chougley | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 1467664 | 9999 | 1467664 | 0 | 0 | 148 | 0 | 136767 | 146766 | 633212 | 540918.8 |  |  | 2026-01-26 | 2026-01-26 19:57 | 2026-02-17 | 2026-02-17 19:18 | 2026-02-20 | 2026-02-17 19:35 | 2026-02-24 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 | [5 empty] | 2026-02-25 |  | 2026-03-05 |  | 2026-03-06 |  |  |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-14 |  | 2026-02-20 |  | Unknown | 2026-01-26 | 2026-01-26 19:14 | 1243783 | 223881 | 0 | 0 | 0 | 0 | 1243783 | 223881 | [9 empty] | 2026-02-25 |  | 2026-03-04
18206 | Turnkey | 2026-01-01 | Mukesh Kothari | 24k Residency By Hirani | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 2311540 | 9999 | 2311540 | 0 | 0 | 157 | 0 | 221155 | 231154 | 954681 | 894550.8 |  |  | 2026-01-26 | 2026-01-30 12:11 | 2026-02-09 | 2026-02-08 23:28 | 2026-02-09 | 2026-02-08 23:34 | 2026-02-15 |  | 2026-02-22 |  | 2026-03-01 |  | 2026-02-08 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-10 | [5 empty] | 2026-02-16 |  | 2026-02-24 |  | 2026-02-25 |  |  |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 | [6 empty] | 2026-03-25 |  | 2026-04-03 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-06 |  |  |  | 2026-04-28 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-03-05 |  | 2026-02-11 |  | Unknown | 2026-01-26 | 2026-01-30 12:10 | 1958932 | 352607 | 0 | 0 | 0 | 0 | 1958932 | 352607 | 2026-02-05 20:20:32 +0530 | Yash Jain | DCM: Mrs/Mr.Kothari 16th flr - 799 sq ft Poss - RTMIÂ Living RoomÂ 5-6seater sofa set Tv unit - Max size available, with storageÂ Dining area - foldable or looseÂ Pooja Mandir area right top cornerÂ Study table folding table in living room Kitchen - washing machine and refrigerator space is already there. base wall loft stoage cabinets Left bedroom 60plus age parents- bed qsb , wardrobe , bed align to east ( open point ) middle room - 16 yr son, girl 11 age qsb, wardrobe ,folding or permanent study table besides bed,book storage above folding tableÂ Â M.bedroom - Cx QSB ,Wardrobe, dresser side tableÂ k upar , tall storage unit.loungre window seating. | [6 empty] | 2026-02-16 |  | 2026-02-23
18207 | Turnkey | 2026-01-01 | Rupesh Shankar Rupesh | independent house | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Yogesh Patidar | [5 empty] | Ankur Kumar |  | Active | Prospect | 10% Payment | 1348991 | 9999 | 0 | 0 | 0 | 112 | 0 | 124900 | 134899 | 549535 | 529658 |  |  | 2026-01-26 | 2026-01-30 13:21 | 2026-02-10 | 2026-02-12 16:09 | 2026-02-27 | 2026-03-25 19:47 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-01-26 | 2026-01-26 19:49 | 0 | 0 | 0 | 0 | 0 | 0 | 1143213 | 205778 | 2026-02-12 16:07:25 +0530 | Priyanka Gs | DCM Both clients work from home: Husband: Marketing manager Wife: Vedic Maths teacher (fully online teaching) They have a 6yearold child (standard considerations for safety & storage). Parents visit occasionally Guest stay arrangements may be needed. Family of 3Â Couple and a daughter - 6 years old A shoe rack - 30 pairs - Not in scopeÂ LivingÂ Wall mounted TV unit is requiredÂ Wall treatment will be doe by Cx - Using cladding tilesÂ Pooja unitÂ Traditional Pooja unit is requiredÂ DiningÂ Vanity unit is required Staircase area - It can be designed in either waysÂ For storage / FountainÂ Looking for a right place for the fountainÂ KitchenÂ Fridge - 600Â Hob & Chimney - 70cmÂ Oven - WallÂ Mixer- AirfyerÂ Undermount RO will be plannedÂ Do need a functional kitchen with Bottom cabinets, wall cabinets & Loft BedroomÂ Aristo wardrobe / Sliding wardrobeÂ Prefers adding the the dresser within the wardrobe space Master Bedroom Aristo WardrobeÂ WorkspaceÂ Workspace to be planned for 2Â Study for kidÂ Private balcony suggestions required Vanity units required for allÂ both the washroomsÂ | [6 empty] | 2026-04-02 |  | 2026-04-09
18208 | Turnkey | 2026-01-01 | Santosh Singh | utopia complex | MUM - GOR | Yes | Swapnali Shedekar | Reshma Melanta | Safalta Karkera | [5 empty] | Moni Sahani |  | Hold | Design | 20% Payment | 1605966 | 204462 | 1605966 | 0 | 0 | 0 | 55 | 0 | 116731 | 682851 | 601922 |  |  | 2026-01-26 | 2026-01-29 14:20 | 2026-01-29 | 2026-01-29 19:36 | 2026-02-01 | 2026-02-04 13:46 | 2026-06-16 | 2026-06-16 13:07 | 2026-09-01 |  | 2026-09-08 |  | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-04 20:17 | 2026-02-04 | 2026-02-26 15:57 | 2026-03-06 | 2026-03-06 11:56 |  |  |  |  | 2026-06-17 |  | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-03-07 | 2026-06-12 16:17 | Site is RTMI | 2026-01-26 | 2026-01-26 20:00 | 1708081.9112 | 283113 | 0 | 0 | 0 | 0 | 1708081.9112 | 283113 | 2026-06-21 14:32:06 +0530 | Avinash Jaiswal | Spoke to client he is requesting cancellation and finding excuse to cancel Done RCA for entire project and chat. Client's site was not ready still we have done 2 meetings and 1 site visit to help with his civil. Now since he has started the work with other vendor he is requesting cancellation and not ready to pay any further amount. Informed client no refund policy and minimum PV of 8 lacs We discussed the full chat history and the root cause analysis (RCA) of your project over a call. Our team was waiting for your site to be ready. In the meantime, we still conducted 2 meetings and 1 site visit even though the site was not ready. I understand you are unhappy with the process, especially since you previously did interiors with Livspace. However, with Bonito, I can assure you that our approach is different and we are here to support you throughout. If you still wish to cancel, as per our agreement, we do not offer refunds and the amount paid will be forfeited. | 2026-06-17 15:53:39 +0530 | Avinash Jaiswal | Client is not ready to adhere payment milestone as mentioned in the agreement. He has mentioned he will not pay any further amount until we start work on the site. Informed our payment milestone as mentioned in the agreement however, he is not ready to accept the same and has asked for cancellation and doesnt want any refund. | 2026-06-17 15:51:57 +0530 | Avinash Jaiswal | Some Image was uploaded | 2026-06-17 | 2026-06-17 13:18 | 2026-09-02
18209 | Turnkey | 2026-01-01 | Pinakin Mehta | Hirani 24K | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Nivesh Gupta | Aakash Gaikwad | Active | Preproduction | DEM2 | 1009768 | 201954 | 1014768 | 0 | 0 | 41 | 0 | 0 | 0 | 427464 | 380350.4 |  |  | 2026-01-26 | 2026-01-28 12:17 | 2026-02-07 | 2026-02-07 19:26 | 2026-02-17 | 2026-02-17 13:58 | 2026-04-09 | 2026-04-09 12:48 | 2026-06-05 | 2026-06-04 12:40 | 2026-07-30 |  | 2026-02-10 | 2026-02-16 19:34 | 2026-02-18 | 2026-02-18 16:53 | 2026-02-18 | 2026-02-23 13:15 | 2026-02-25 | 2026-02-25 18:07 |  |  |  |  | 2026-04-06 | 2026-03-17 19:20 | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-04-01 | 2026-04-09 12:33 | Site is RTMI | 2026-01-26 | 2026-01-28 12:15 | 1123726.7597 | 177676 | 0 | 0 | 0 | 0 | 1123726.7597 | 177676 | 2026-06-10 18:30:44 +0530 | Neha Yadav | DDM3: DDM 3 Discussion: 1)TV unit need to redesign as per shared reference and need to add tall unit display unit 2) Crockery with shelf above need to add with metal fabricationÂ 3)Need to add mirror on dining wallÂ 4)passage design as per reference need to do 5)kitchen roller unit confirmation neededÂ Feel free to add a pointers if missed any. | 2026-06-10 18:30:19 +0530 | Neha Yadav | DDM2: DDM 2 Discussion: 1)Mandir unit with shutter needs to add which will be add on to cost. 2) Master room behind bed there will be a curve panel which will be add on to costÂ 3)Master room - need to add console unit in modular which will be additional Feel free to add a pointers if missed any | 2026-04-17 11:12:11 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-10 | 2026-04-09 13:06 | 2026-06-05 | 2026-06-04 12:41
18210 | Turnkey | 2026-01-01 | hiren pancholi | Vijay Nagari | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Lost | Design | DEM1 | 957517 | 126736 | 1267352 | 0 | 0 | 152 | 0 | 0 | 64767 | 410517 | 355496.8 |  |  | 2026-01-26 | 2026-02-01 21:21 | 2026-02-03 | 2026-02-03 13:54 | 2026-02-06 | 2026-02-04 11:07 | 2026-09-05 |  | 2026-09-12 |  | 2026-09-19 |  | 2026-02-04 | 2026-01-31 05:30 | 2026-02-05 | 2026-02-06 11:17 | 2026-02-06 | 2026-02-13 17:25 | 2026-02-20 | 2026-02-20 10:34 |  |  |  |  | 2026-09-06 |  | 2026-09-14 |  | 2026-09-15 |  |  |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 | [6 empty] | 2026-10-13 |  | 2026-10-22 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-25 |  |  |  | 2026-11-16 |  | 2026-11-18 |  | 2026-11-19 | [5 empty] | 2026-09-23 |  | 2026-09-01 |  | Site is RTMI | 2026-01-26 | 2026-01-26 20:41 | 1074027 | 193324 | 0 | 0 | 0 | 0 | 1053970.4375 | 168943 | 2026-06-16 13:59:58 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-06 18:14:43 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-02 13:23:45 +0530 | Manzoor Shaikh | Out called the customer, said he was not having any proper information on the designing and due to the change of the designer as well he was unhappy. Initial measurement was delayed by the 10 days and customer want to move in by the March End. Have done the Modular's work from outside. | 2026-09-06 |  | 2026-09-13
18211 | Turnkey | 2026-01-01 | Shipra Agarwal Agarwal | NRI complex | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Saloni Chawan |  | Active | Prospect | 10% Payment | 3131343 | 9999 | 3131343 | 0 | 0 | 147 | 0 | 303135 | 313134 | 1337818 | 1167256.4 |  |  | 2026-01-25 | 2026-01-28 16:17 | 2026-01-30 | 2026-02-04 14:32 | 2026-02-07 | 2026-02-18 19:24 | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Unknown | 2026-01-25 | 2026-01-28 16:12 | 2653680 | 477662 | 0 | 0 | 0 | 0 | 2653680 | 477662 | 2026-02-04 14:32:57 +0530 | Maasoumeh Raza | Name:Â 18211 - Shipra Agarwal Agarwal Property Name: NIR Complex Property type: 4BHK [penthouse] Possession: In handÂ Move in: August Member: 4 memberÂ Occupation: ITÂ Budget: 25L to 30L Requirements: Living room: Shoe RackÂ Safety door Tv Unit with display Bar Unit below stairs MandirÂ Crockery Unit 3+2 Seater sofaÂ 6 Seater diningÂ Extending windowÂ Â Kitchen :Â Existing Utility wall storage and sink shutterÂ Guest BedRoom: Queen size BedÂ Wardrobe with loft [Swing wardrobe] Side table Study Table Master bedroom: Queen size BedÂ Wardrobe with loft [Swing wardrobe] Dressing Unit Side table TV unit Kid's bedroom: Queen size BedÂ Wardrobe with loft [Swing wardrobe] Dressing Unit Side table Study table Rooftop Room: Work stationÂ Â Hiding pipesÂ SeatingÂ Bathroom Below vanity in all bathroom Balcony: wash basin below unit Additional scope:Full home False ceiling Painting Electrical Â Â Â | [6 empty] | 2026-02-26 |  | 2026-03-05
18212 | Turnkey | 2026-01-01 | Krishna rawat | L&T Rejuve 360 | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  |  | Snehankit Agre | Akshat Shrivastava | Murali S |  | Prasad Bhivaji Hande | Active | Production | 100% Payment | 1836172 | 1143983 | 2373612 | 0 | 1836172 | 5 | 51 | 0 | 0 | 0 | 692189 |  |  | 2026-01-29 | 2026-01-28 09:58 | 2026-01-29 | 2026-01-29 18:36 | 2026-02-07 | 2026-02-10 15:24 | 2026-03-11 | 2026-03-10 11:47 | 2026-06-04 | 2026-06-03 12:19 | 2026-06-07 | 2026-06-07 10:36 | 2026-02-10 | 2026-02-10 17:32 | 2026-02-11 | 2026-02-10 17:59 | 2026-02-10 | 2026-02-12 14:41 | 2026-02-20 | 2026-02-20 16:34 |  |  |  |  | 2026-03-10 | 2026-03-10 19:13 | 2026-06-04 | 2026-06-03 13:04 | 2026-06-04 | 2026-06-03 21:46 |  |  | 2026-06-09 | 2026-06-18 12:14 | 2026-06-18 | 2026-06-18 15:34 | 2026-06-19 | 2026-06-18 16:00 | 2026-06-19 | 2026-06-20 16:49 |  |  |  |  | 2026-06-27 16:23 | 2026-07-10 | 2026-07-09 20:33 | 2026-07-12 | 2026-07-10 17:51 | 2026-07-11 |  | 2026-07-10 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-18 | 2026-06-27 16:22 | 2026-05-15 | 2026-03-10 11:03 | Site is RTMI | 2026-01-26 | 2026-01-28 09:56 | 2011536 | 362076 | 0 | 0 | 2031093.0699 | 323055 | 2031093.0699 | 323055 | 2026-07-13 11:15:57 +0530 | Snehankit Agre | Execution: 13th july False ceiling installation in progress. | 2026-07-07 01:58:17 +0530 | Snehankit Agre | Execution: Electrical work in progress Ac copper piping pending ( CX dependency) | 2026-07-02 00:35:10 +0530 | Snehankit Agre | Execution: Floor covering done 30 june channel fixing for ceiling done 1 july | 2026-03-11 | 2026-03-10 11:55 | 2026-06-04 | 2026-06-03 12:54 | Under Construction | 2026-04-01
18214 | Turnkey | 2026-01-01 | Suresh | Nyra Sunterra | BNG - HSR | Yes | Mahathi Nama | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 2661609 | 9999 | 0 | 0 | 0 | 169 | 0 | 256162 | 266161 | 1071137 | 1058150.4 |  |  | 2026-01-27 | 2026-01-27 13:29 | 2026-01-27 |  | 2026-01-31 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-01 | [5 empty] | 2026-02-07 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-02-24 |  | 2026-02-02 |  | Unknown | 2026-01-27 | 2026-01-27 13:14 | 0 | 0 | 0 | 0 | 0 | 0 | 2255601 | 406008 | 2026-01-31 13:54:20 +0530 | Mahathi Nama | DCM: MR.SURESH 4BHK 15L-BUDGET GROUND FLOOR FOYER AREA(OUTSIDE RIGHT SIDE WALL) SHOE RACK WITH SEATTER (4' X 3') LIVING AREA 1.TV UNIT 12'(SUSPENDED DREAWER ,WALL PANEL ,DISPLAY UNIT) 2.POOJA ROOM BOTTOM STORGAGE WITH DRAWERS +TRAY CNC SHUTTERS 3.PARTITION B/W KITCHEN & POOJA UNIT WOODEN PARTITION WITH GLASS 4.MODULAR KITCHEN L SHAPE KITCHEN BASE UNIT WALL UNIT LOFT TALL UNIT APPLIANCE UNIT 5.PANTRY 3D X 4.8W 6.DINNING AREA CROCKERY UNIT ONLY WALL 7.STORAGE UNDER STEPS 8.GBR WARDROBE BAY SEATER DRESSER FOLADABLE STUDY UNIT + WALL CABINET WALL PANELING BEDBACK SIDE SIMPLE 9.WASHROOM VANITY AND WITH MIRROR FOR WASHROOM 10.STAIR CASE WALL DESINE 11.MBR WARDROBE + LOFT BAY SEATER WALKIN WARDROBE DRESSING UNIT WITHOUT STORAGE BED WITH HEADBOARD TV UNIT STORAGE ONLY DRAWER BED BACK WALL DESIGNE 12.KBR BED WARDROBE + LOFT WORK STATION 2 KIDS BEDBACK KIDS DESIGNE 5X6.6 BED 13.FAMILY ROOM TV UNIT SIMPLE WITH ACCENT WALL 14.FALSE CEILING LIVING MBR KBR STUDY ROOM GBR 15.STUDY ROOM DRESSER FOR EXISTING WARDROBE BOOK SHELF FOR WORK STATION 16.HOME THEATER SETUP DOLBY SETUP IF WE ARE DOING 17.BARCOUNTER ONLY WALL STORAGE | [6 empty] | 2026-02-07 |  | 2026-02-14
18215 | Sub Project |  | Vyantara Ventures Private Limited (Nupur Vashisht) | Applaud 38 | MUM - GOR |  | Yogini Chavan | Reshma Melanta | Shantanu Parakh |  |  | Uday Yadruk | Rizwan Mistry | Murali S |  |  | Active | Installation | Execution | 4300 | 4300 | 0 | 0 | 4300 | 97 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-27 | 2026-03-12 17:36 | 2026-01-28 | 2026-03-12 17:38 | 2026-03-12 | 2026-03-12 17:40 | 2026-03-13 | 2026-03-12 17:42 | 2026-03-13 | 2026-03-12 17:44 | 2026-03-13 | 2026-03-12 17:46 | 2026-03-12 | 2026-03-12 17:40 | 2026-03-13 | 2026-03-12 17:40 | 2026-03-12 | 2026-03-12 17:41 | 2026-03-13 | 2026-03-12 17:42 |  |  |  |  | 2026-03-12 | 2026-03-12 17:43 | 2026-03-13 | 2026-03-12 17:45 | 2026-03-13 | 2026-03-12 17:45 |  |  | 2026-02-24 | 2026-03-12 17:35 | 2026-02-25 | 2026-03-12 17:35 | 2026-03-14 | 2026-03-13 13:27 | 2026-03-14 | 2026-03-13 13:32 |  |  |  |  | 2026-03-13 15:39 | 2026-03-15 | 2026-03-14 22:39 | 2026-03-18 | 2026-03-16 16:41 | 2026-03-17 | 2026-03-20 15:21 | 2026-03-16 | 2026-04-03 12:27 | 2026-04-03 | 2026-04-09 15:45 | 2026-04-11 | 2026-05-23 19:03 |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-03-15 | 2026-03-13 11:30 | 2026-03-13 | 2026-03-12 17:42 | Unknown | 2026-01-27 | 2026-03-12 17:36 | 0 | 0 | 0 | 0 | 41779 | 7520 | 41779 | 7520 | 2026-04-21 18:40:10 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-13 11:55:04 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-12 14:27:54 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-13 | 2026-03-12 17:43 | 2026-03-13 | 2026-03-12 17:44
18216 | Turnkey | 2026-01-01 | sharmila | serene | BNG - HRBR | No Estimate | Alekhya Korada | Rajeshwari S | Yogesh Patidar | [5 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-27 | 2026-02-08 11:41 | 2026-01-28 |  | 2026-01-31 |  | 2026-02-07 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-01-31 |  | 2026-02-01 |  | 2026-02-01 |  | 2026-02-02 | [5 empty] | 2026-02-08 |  | 2026-02-16 |  | 2026-02-17 |  |  |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-27 | [6 empty] | 2026-03-17 |  | 2026-03-26 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-29 |  |  |  | 2026-04-20 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-02-25 |  | 2026-02-03 |  | Unknown | 2026-01-27 | 2026-01-27 19:10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-01-30 17:18:01 +0530 | Alekhya Korada | Some Image was uploaded | [6 empty] | 2026-02-08 |  | 2026-02-15
18217 | Turnkey | 2026-01-01 | Vipul shah | Umang Heights | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Umang Shah |  | Lost | Design | 20% Payment | 2069952 | 80000 | 1284154 | 0 | 0 | 91 | 34 | 0 | 333990 | 860561 | 795400.8 |  |  | 2026-01-26 | 2026-01-30 12:59 | 2026-01-27 | 2026-01-30 15:30 | 2026-01-30 | 2026-01-30 15:43 | 2026-03-12 | 2026-03-12 18:23 | 2026-05-02 |  | 2026-05-09 |  | 2026-01-30 | 2026-01-31 05:30 | 2026-01-31 | 2026-02-12 19:23 | 2026-02-12 | 2026-02-13 13:03 | 2026-02-20 | 2026-02-20 15:45 |  |  |  |  | 2026-03-12 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-03-25 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-02-21 | 2026-03-04 14:58 | Site is RTMI | 2026-01-26 | 2026-01-29 18:23 | 1386051.548 | 234023 | 0 | 0 | 0 | 0 | 1959068.6794 | 323382 | 2026-05-02 13:44:00 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-15 17:05:04 +0530 | Umang Shah | Some Image was uploaded | 2026-03-30 14:19:51 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-13 | 2026-03-12 19:24 | 2026-05-03
18218 | Turnkey | Dec'25 | Rupali Khedekar | Lodha Amara | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Tanveer Patel | Aditya Vikram | Murali S | Vandana Preet | Shailendra Mishra | Active | Production | Dispatch Due | 826532 | 971836 | 1038712 | 1300327 | 826532 | 9 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-01-26 | 2026-01-28 15:39 | 2026-01-26 | 2026-01-30 18:47 | 2026-02-01 | 2026-02-02 22:13 | 2026-04-07 | 2026-04-07 12:35 |  |  |  |  | 2026-02-01 | 2026-01-31 17:53 | 2026-02-02 | 2026-02-01 19:39 | 2026-02-02 | 2026-02-03 14:09 | 2026-03-05 | 2026-03-05 16:33 | 2026-04-29 | 2026-04-29 19:00 | 2026-05-02 | 2026-04-30 20:59 | 2026-05-06 | 2026-04-30 | 2026-05-12 | 2026-05-12 20:54 | 2026-05-13 | 2026-05-12 20:54 |  |  | 2026-05-17 | 2026-05-30 16:05 | 2026-05-30 | 2026-05-30 16:38 | 2026-06-02 | 2026-05-30 20:04 | 2026-06-04 | 2026-06-03 19:07 |  |  |  |  | 2026-06-09 17:54 | 2026-06-17 | 2026-06-16 21:29 | 2026-07-06 | 2026-07-06 20:29 | 2026-06-30 | 2026-06-30 14:47 | 2026-07-10 |  | 2026-06-30 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-05 | [5 empty] | 2026-06-04 | 2026-06-09 17:53 | 2026-05-08 | 2026-03-25 12:35 | Site is RTMI | 2026-01-25 | 2026-01-28 15:38 | 1205240.279 | 184379 | 1412849.999 | 224287 | 1022479.36 | 144386 | 1022479.36 | 144386 | 2026-06-26 13:38:13 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-23 00:35:27 +0530 | Tanveer Patel | Procurement: Furniture is ready for disptached 25th june.Floor covering would be done on 24th june | 2026-06-15 23:54:55 +0530 | Tanveer Patel | Procurement: Key handover pendingMaterial will dispatch once work completion confirmation received from cx
18221 | Turnkey | 2026-01-01 | Khushi/Vaibhav Gupta | Suncity Apartments | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 784036 | 9999 | 784036 | 0 | 0 | 155 | 0 | 68405 | 78404 | 313614 | 313614.4 |  |  | 2026-01-28 | 2026-01-28 15:49 | 2026-01-28 | 2026-02-04 10:27 | 2026-02-07 | 2026-02-10 18:37 | 2026-02-17 |  | 2026-02-24 |  | 2026-03-03 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-12 | [5 empty] | 2026-02-18 |  | 2026-02-26 |  | 2026-02-27 |  |  |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-09 | [6 empty] | 2026-03-27 |  | 2026-04-05 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-08 |  |  |  | 2026-04-30 |  | 2026-05-02 |  | 2026-05-03 | [5 empty] | 2026-03-07 |  | 2026-02-13 |  | Unknown | 2026-01-28 | 2026-01-28 15:48 | 664437 | 119598 | 0 | 0 | 0 | 0 | 664437 | 119598 | 2026-01-28 17:34:38 +0530 | Adarsh K | Hi, Minutes of Meeting (MoM)Project: Renovation Residential Apartment Location: Suncity, Ibloor Area: ~2000 sq.ft Client: IT Professional (Microsoft) ¦ From UP Email: bpg.manit@gmail.com Budget Range: 2025 Lakhs 1. Project Scope OverviewRenovation project with selective revamp across major areasFocus on a cohesive design language running through living, dining, study, and bedroomsEmphasis on wall panelling, false ceiling, lighting, flooring, doors, and automationKitchen & crockery units to be retained (no major changes)2. Area-wise Requirements & DiscussionFoyerCreate a defined foyer spacePartition element to visually separate from livingConsole unit to be providedLiving AreaTV unit to be designed on Wall 01 (Toilet Wall)Conceptual wall panelling to be introducedFalse ceiling to be revampedLighting plan:Magnetic track lights for Living, Dining, and Study areasDining & StudyIntegrated design language with LivingFalse ceiling redesignMagnetic track lighting to continue for visual continuityBedrooms GeneralWall panelling at bed head wallFalse ceiling with lighting focused around the bedConsistent material and colour language across roomsMaster Bedroom (MBR)No wardrobe requiredFocus on wall panelling and ceiling designBedroom 3 Guest BedroomIdentified as the largest bedroomWardrobe placement: Next to the doorSpecial design attention due to size and guest usageKids RoomTo be redesigned as part of renovation scopeDetails to be explored in concept stageKitchen & CrockeryNo revamp requiredExisting membrane kitchen to be retained3. Key Revamp Elements (Confirmed)FlooringDoorsHome automationFalse ceiling (Living, Dining, Study, Bedrooms)Wall panelling (Living & Bedrooms)4. Design Direction & Colour PaletteOverall concept to run seamlessly across main spacesPreferred colour tones:BeigeGreenBlue5. Next StepsDevelop concept design based on discussed scopePresent mood boards and material optionsShare preliminary layouts and ceiling conceptsBudget alignment with proposed design solutions | 2026-01-28 16:14:03 +0530 | Ramesh Nayak | Apartment - Suncity Budget - 20-25L 3 BHK 3 Person - 2 Adults 1 Child Husband Works in Microsoft Wife also Working They are from Kanpur |  |  |  | 2026-02-18 |  | 2026-02-25
18222 | Turnkey | 2026-01-01 | Suresh Gawade | Piramal Vaikunth | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Nishtha Valawalkar |  | Hold | Design | DEM1 | 948894 | 93999 | 1164659 | 0 | 0 | 16 | 123 | 0 | 95780 | 404946 | 354168.8 |  |  | 2026-01-26 | 2026-01-28 16:08 | 2026-02-24 | 2026-02-24 11:41 | 2026-02-24 | 2026-02-24 11:44 | 2026-08-16 |  | 2026-08-23 |  | 2026-09-11 |  | 2026-02-24 | 2026-02-24 18:23 | 2026-02-25 | 2026-02-25 01:08 | 2026-02-25 | 2026-02-26 17:37 | 2026-03-05 | 2026-03-05 11:51 |  |  |  |  | 2026-08-17 |  | 2026-09-06 |  | 2026-09-07 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-14 | [6 empty] | 2026-11-01 |  | 2026-11-10 |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-13 |  |  |  | 2026-12-05 |  | 2026-12-07 |  | 2026-12-08 | [5 empty] | 2026-10-12 |  | 2026-04-15 | 2026-03-05 12:11 | Site is RTMI | 2026-01-26 | 2026-01-28 16:07 | 986999 | 177659 | 0 | 0 | 0 | 0 | 987498.3218 | 163051 | 2026-06-26 12:37:31 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-14 13:59:14 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-07 19:37:41 +0530 | Sneha Kadam | Client is not interested in paying the next milestone payment. June july possession expected | 2026-08-17 |  | 2026-08-24
18223 | Turnkey | 2026-01-01 | Amrit Kashyap | Transcon | MUM - GOR | Yes | Batskhem Marpna | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Moni Sahani |  | Hold | Preproduction | Site Readiness 1 | 1492926 | 298585 | 1948447 | 0 | 0 | 6 | 89 | 0 | 0 | 632942 | 561399.2 |  |  | 2026-01-25 | 2026-01-29 14:13 | 2026-01-29 | 2026-01-29 15:41 | 2026-02-01 | 2026-02-01 18:31 | 2026-06-02 | 2026-03-31 13:58 | 2026-07-06 |  | 2026-07-13 |  | 2026-02-01 | 2026-01-31 05:30 | 2026-02-02 | 2026-02-06 15:10 | 2026-02-06 | 2026-02-16 13:37 | 2026-02-20 | 2026-02-20 19:03 |  |  |  |  | 2026-03-31 | 2026-04-11 14:35 | 2026-07-08 |  | 2026-07-09 |  |  |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 | [6 empty] | 2026-08-06 |  | 2026-08-15 |  | 2026-03-17 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-12 | [5 empty] | 2026-07-17 |  | 2026-02-21 | 2026-03-25 15:58 | Site is Non-RTMI | 2026-01-25 | 2026-01-29 14:11 | 1651226 | 297220 | 0 | 0 | 0 | 0 | 1630721.5425 | 265870 | 2026-05-27 15:17:01 +0530 | Vishakha Vaishnav | Cx said that as per Rera it is June 2026 , cx said that he will confirm again and update us in the group | 2026-05-15 16:18:44 +0530 | Vishakha Vaishnav | Tried connecting cx , cx didn't responded | 2026-04-15 17:48:53 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-01 | 2026-03-31 14:06 | 2026-07-07 |  | Under Construction | 2026-06-01
18224 | Turnkey | 2026-01-01 | Ms.Maria Priyanka | Ankura Meridian | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Hold | Design | DEM1 | 990616 | 125713 | 1282044 | 0 | 0 | 46 | 100 | 0 | 72410 | 401032 | 391460.4 |  |  | 2026-01-28 | 2026-01-29 13:09 | 2026-02-05 | 2026-02-08 11:53 | 2026-02-15 | 2026-02-15 15:57 | 2026-09-14 |  | 2026-09-21 |  | 2026-09-28 |  | 2026-02-15 | 2026-02-18 15:48 | 2026-02-16 | 2026-02-18 16:07 | 2026-02-18 | 2026-02-19 12:13 | 2026-02-25 | 2026-02-25 18:11 |  |  |  |  | 2026-09-15 |  | 2026-09-23 |  | 2026-09-24 |  |  |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-04 | [6 empty] | 2026-10-22 |  | 2026-10-31 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-01 |  | 2026-11-03 |  |  |  | 2026-11-25 |  | 2026-11-27 |  | 2026-11-28 | [5 empty] | 2026-10-02 |  | 2026-09-10 |  | Unknown | 2026-01-28 | 2026-01-29 13:08 | 1086478 | 195566 | 0 | 0 | 0 | 0 | 1065362.59 | 175517 | 2026-07-14 15:20:00 +0530 | Abhinandan K S |  | 2026-05-16 13:33:56 +0530 | Abhinandan K S | Some Image was uploaded | 2026-03-13 19:42:23 +0530 | Abhinandan K S | Some Image was uploaded | 2026-09-15 |  | 2026-09-22
18226 | Turnkey | 2026-01-01 | Ashish Gupta | raghuvanshi | MUM - GOR | Yes | Karan Chavda |  | Safalta Karkera | [7 empty] | Active | Prospect | DCM Due | 1211545 | 9999 | 0 | 0 | 0 | 165 | 0 | 111156 | 121155 | 493000 | 476236 |  |  | 2026-01-27 | 2026-01-31 11:44 | 2026-01-28 |  | 2026-01-30 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-01 | [5 empty] | 2026-02-07 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-02-24 |  | 2026-02-02 |  | Unknown | 2026-01-27 | 2026-01-30 12:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1257213.7544 | 212269 | [9 empty] | 2026-02-07 |  | 2026-02-14
18227 | Turnkey | 2026-01-01 | Nargish Salmani | Aim heritage | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Active | Design | DEM1 | 932817 | 206563 | 955108 | 0 | 0 | 145 | 0 | 0 | 0 | 372850 | 353404.4 |  |  | 2026-01-29 | 2026-02-07 13:36 | 2026-02-07 | 2026-02-07 19:20 | 2026-02-08 | 2026-02-08 17:22 | 2026-09-17 |  | 2026-09-24 |  | 2026-10-01 |  | 2026-02-08 | 2026-02-09 17:55 | 2026-02-09 | 2026-02-09 17:56 | 2026-02-09 | 2026-02-20 18:00 | 2026-02-21 | 2026-02-21 15:21 |  |  |  |  | 2026-05-05 | 2026-03-12 18:37 | 2026-09-26 |  | 2026-09-27 |  |  |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-07 | [6 empty] | 2026-10-25 |  | 2026-11-03 |  | 2026-11-02 |  | 2026-11-03 |  | 2026-11-04 |  | 2026-11-06 |  |  |  | 2026-11-28 |  | 2026-11-30 |  | 2026-12-01 | [5 empty] | 2026-10-05 |  | 2026-04-30 |  | Unknown | 2026-01-30 | 2026-02-07 12:11 | 1081687.0444 | 168575 | 0 | 0 | 0 | 0 | 1078665.2944 | 168226 | 2026-06-16 15:29:20 +0530 | Riddhi Deshpande | DDM1: possession not done. unknown | 2026-06-16 15:28:57 +0530 | Riddhi Deshpande | DDM1: transition done | 2026-05-27 19:13:49 +0530 | Riddhi Deshpande | DDM1: have asked for transition cx has not received possession | 2026-09-18 |  | 2026-09-25 |  | Under Construction | 2026-06-01
18228 | Turnkey | 2026-01-01 | raj Bathija | hiranandani | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Saloni Chawan |  | Hold | Preproduction | DEM2 | 1410235 | 374999 | 1410235 | 0 | 0 | 20 | 75 | 0 | 0 | 580022 | 455214 |  |  | 2026-01-29 | 2026-01-29 13:44 | 2026-04-02 | 2026-04-02 12:26 | 2026-04-05 | 2026-04-02 13:08 | 2026-04-15 | 2026-04-11 12:42 | 2027-04-01 |  | 2027-04-08 |  | 2026-03-31 | 2026-03-31 | 2026-04-03 | 2026-04-02 19:11 | 2026-04-02 | 2026-04-03 11:49 | 2026-04-10 | 2026-04-10 13:29 |  |  |  |  | 2026-04-08 | 2026-04-01 19:00 | 2027-04-03 |  | 2027-04-04 |  |  |  | 2027-04-11 |  | 2027-04-12 |  | 2027-04-13 |  | 2027-04-14 | [6 empty] | 2027-05-02 |  | 2027-05-11 |  | 2027-05-10 |  | 2027-05-11 |  | 2027-05-12 |  | 2027-05-14 |  |  |  | 2027-06-05 |  | 2027-06-07 |  | 2027-06-08 | [5 empty] | 2027-04-12 |  | 2026-04-14 | 2026-04-11 12:35 | Site is RTMI | 2026-01-29 | 2026-01-29 13:41 | 1550110.895 | 255925 | 0 | 0 | 0 | 0 | 1550110.895 | 255925 | 2026-07-02 19:40:32 +0530 | Divya Rahangdale | Hold till march 2027 | 2026-07-01 16:01:27 +0530 | Naved Malik | Project on Hold till first Quarter of 2027 | 2026-05-07 19:38:52 +0530 | Sneha Kadam | Cx is unclear of possesion date. june it is expected | 2026-04-12 | 2026-04-11 12:55 | 2027-04-02
18229 | Turnkey | 2026-01-01 | Mahantesh CTI - Lead | Prestige Jindal City | BNG - HRBR | Yes | Sanjay Kulkarni | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | DCM Due | 1122021 | 9999 | 0 | 0 | 0 | 160 | 0 | 102203 | 112202 | 455763 | 441853.6 |  |  | 2026-01-26 | 2026-02-05 19:15 | 2026-02-06 | 2026-02-08 10:58 | 2026-02-06 |  | 2026-02-18 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-02-11 |  | 2026-02-12 |  | 2026-02-12 |  | 2026-02-13 | [5 empty] | 2026-02-19 |  | 2026-02-27 |  | 2026-02-28 |  |  |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-10 | [6 empty] | 2026-03-28 |  | 2026-04-06 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-09 |  |  |  | 2026-05-01 |  | 2026-05-03 |  | 2026-05-04 | [5 empty] | 2026-03-08 |  | 2026-02-14 |  | Unknown | 2026-01-26 | 2026-01-29 16:49 | 0 | 0 | 0 | 0 | 0 | 0 | 950865 | 171155 | 2026-04-29 12:24:58 +0530 | Kushal S | Some Image was uploaded | 2026-02-05 19:26:41 +0530 | Sanjay Kulkarni | Some Image was uploaded |  |  |  | 2026-02-19 |  | 2026-02-26
18230 | Turnkey | 2026-01-01 | Nishant bisht | Prestige Meridian Park | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | DCM Due | 2088452 | 9999 | 0 | 0 | 0 | 138 | 0 | 198846 | 208845 | 848539 | 822222.8 |  |  | 2026-01-29 | 2026-02-27 15:39 | 2026-01-30 |  | 2026-02-04 |  | 2026-02-11 |  | 2026-02-18 |  | 2026-02-25 |  | 2026-02-04 |  | 2026-02-05 |  | 2026-02-05 |  | 2026-02-06 | [5 empty] | 2026-02-12 |  | 2026-02-20 |  | 2026-02-21 |  |  |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-03 | [6 empty] | 2026-03-21 |  | 2026-03-30 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-02 |  |  |  | 2026-04-24 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-03-01 |  | 2026-02-07 |  | Unknown | 2026-01-29 | 2026-01-29 16:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1769875 | 318577 | [9 empty] | 2026-02-12 |  | 2026-02-19
18231 | Turnkey | 2026-01-01 | Mohammed Shahid | Prestige city | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | 10% Payment | 2556886 | 9999 | 2556886 | 0 | 0 | 150 | 0 | 245690 | 255689 | 1062404 | 983105.2 |  |  | 2026-01-28 | 2026-01-29 17:40 | 2026-01-31 | 2026-01-31 18:02 | 2026-02-15 | 2026-02-15 16:48 | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 | [5 empty] | 2026-02-23 |  | 2026-03-03 |  | 2026-03-04 |  |  |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 | [6 empty] | 2026-04-01 |  | 2026-04-10 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-13 |  |  |  | 2026-05-05 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-03-12 |  | 2026-02-18 |  | Unknown | 2026-01-28 | 2026-01-29 17:38 | 2166852 | 390033 | 0 | 0 | 0 | 0 | 2166852 | 390033 | 2026-01-31 18:03:21 +0530 | Sakshi Pawar | DCM: PID: 18231 Property - 3BHK possession - 01-03-2026 Budget - 15L-20L Members - 5ppl(1kid-2yr)(Irha) profession - IT Â - no grooving or chipping is allowed - Dark colours - east facing - BED LEG SHOULD NOT BE ON LEFT - Bright lights - 9'ht - false ceiling: living room with foyer and passage, M bedroom - minimal plants Â Â FOYER :Â - Arabic wall art Â WORKSPACE : - shoerack with seating(15-20 pair) Â LIVING: - tv unit - ledges with metal fabrication - Arabic wall art behind sofa Â DINNING: - 6 seaters - crockery unit - wall concept with mirror Â KITCHEN: - OTG unit - bottom unit - top units - loft(1 side) - bottom Ro - quartz - 4 burner -2door fridge Â UTILITY: - wm, 1bowlsink unit, top unit - granite for sink top Â Â TOILETS: - vanityÂ - no granite Â M.BEDROOM:(BEDROOM1) - Aristro wardrobe - tv unit - k size bed - dresser(full length mirror) BEDROOM:(BEDROOM3)(kids room cum g room) - Q bed - openable wardrobeÂ - study unit - only mirrorÂ - kids theme Â BEDROOM:(BEDROOM2)(parents room) - Aristro wardrobe - bay window seating suggestion - Q size bed - ledges above side table(for books) - try study unit if not seating - dresser with storage Â MAIDS ROOM: - work station - vanity Â BALCONY: false ceiling to be asked Â Â Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. | [6 empty] | 2026-02-23 |  | 2026-03-02
18234 | Turnkey | 2026-01-01 | PRASAD NARAYAN POOJARY | Flamingo | MUM - GOR | No Estimate | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 161 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-29 | 2026-02-04 17:24 | 2026-01-30 |  | 2026-01-30 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-01-30 |  | 2026-01-31 |  | 2026-01-31 |  | 2026-02-01 | [5 empty] | 2026-02-07 |  | 2026-02-15 |  | 2026-02-16 |  |  |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-26 | [6 empty] | 2026-03-16 |  | 2026-03-25 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-28 |  |  |  | 2026-04-19 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-02-24 |  | 2026-02-02 |  | Unknown | 2026-01-29 | 2026-01-30 11:56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-02-07 |  | 2026-02-14
18235 | Turnkey | 2026-01-01 | Raushan Mishra | Sterling Ascentia | BNG - HSR | Yes | Preksha Sajjanshettar | Akshay Ds | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 2104432 | 420886 | 2009979 | 0 | 0 | 23 | 25 | 0 | 0 | 871656 | 811890.4 |  |  | 2026-01-30 | 2026-01-31 15:34 | 2026-01-31 | 2026-02-05 12:48 | 2026-03-17 | 2026-03-17 12:44 | 2026-06-20 | 2026-06-20 17:03 | 2026-06-25 |  | 2026-08-05 |  | 2026-03-17 | 2026-03-17 17:48 | 2026-03-18 | 2026-03-18 12:13 | 2026-03-18 | 2026-03-18 18:40 | 2026-03-25 | 2026-03-25 17:32 |  |  |  |  | 2026-06-25 | 2026-06-22 19:09 | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-06-04 | 2026-06-20 16:38 | Site is RTMI | 2026-01-30 | 2026-01-31 11:12 | 1703372 | 306606 | 0 | 0 | 0 | 0 | 2350617.9436 | 388133 | 2026-07-03 15:49:18 +0530 | Preksha Sajjanshettar | MOM - 03-07-2026 | 2026-06-20 17:42:13 +0530 | Preksha Sajjanshettar | PID - 18235 - Raushan Mishra DEM 1Â DATE - 20-06-2026 Next meeting - YET TO SCHEDULE (site will be ready post 15th JULY) Foyer Cushion costing need to consider LivingÂ Granite need to be added for crockery unitMetal fabrication costing need to consider for crockery unit Master bedroomÂ Metal fabrication costing need to consider Kids bedroom BED - Queen size or invisible bed (client scope) need to confirmÂ Foldable study table and reduce wardrobe width to add glass tall unitÂ Cushion costing need to consider Kitchen / UtilityÂ RO Unit location need to confirmWicker basket need to be addedÂ About cylinder unit need confirmationGranite need to be added for Utility Toilets Master bedroom - base vanity unit with top unit on ledge wall need to designGuest bedroom and Common toilet - base vanity unit with wall unit above wash basin False ceiling - Foyer - plain false ceilingMaster bedroom - plain false ceilingKids bedroom - plain false ceilingGuest bedroom - plain false ceilingLiving - periphery false ceiling | 2026-06-13 15:46:57 +0530 | Preksha Sajjanshettar | PID - 18235 - Raushan Mishra Initial Meeting MOM - 13-06-2026Â Next meeting - 20/21 June 2026 FoyerÂ Add loft cabinet on tall units(both)LivingÂ Sofa back wall - design will be finalised in next meeting based on some reference (need to share the reference)TV - 55/60 INCHESFull length curtain (client scope)Crockery unitÂ Design will be same with beading and mirror(client scope) in centerWall design at dining area is finalisedMaster bedroomÂ King size bed to be consideredBed orientation need to be changedÂ Some design options to be considered according to window openingÂ Try to consider the initial design option(CDP)Full length curtain at balcony and blinders at bedhead board wall window (client scope)Kids bedroomÂ BED - Queen size or invisible bedÂ (client scope)Study unit need to be considered (for one person to use with one desktop setup)Guest BedroomÂ Bed orientation need to be changedÂ BED - king sizeÂ One option with Aristo wardrobe (will be finalised based on costing)Study unit or workstationÂ Bay seating - can be considered or can be removed according to alinementKitchenÂ Location of hobÂ Alinement need to worked outToilets Master bedroom - base vanity unit with top unit on ledge wall need to designGuest bedroom and Common toilet - base vanity unit with wall unit above wash basin False ceiling - Foyer - plain false ceilingLiving - periphery false ceilinf | 2026-06-21 | 2026-06-20 17:43 | 2026-06-26 |  | Under Construction | 2026-10-30
18236 | Turnkey | 2026-01-01 | Mr Viknesh | L&T Seawoods | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 1671881 | 9999 | 1671881 | 0 | 0 | 145 | 0 | 157189 | 167188 | 720630 | 616875.2 |  |  | 2026-01-30 | 2026-01-30 17:00 | 2026-02-05 | 2026-02-05 15:51 | 2026-02-08 | 2026-02-20 15:27 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-01-30 | 2026-01-30 16:59 | 1416848 | 255032 | 0 | 0 | 0 | 0 | 1416848 | 255032 | 2026-02-01 12:02:35 +0530 | Moksh Mehta | DCM: Client Name:- Viknesh Property:- L & T Seawoods Amber G1 706 Possesion Date:- In Hand Sq Ft:- 950 + Sqft No of Members : - Parents + Self + Pet Budget :- 13 - 14 L Ent: Shoe Rack (20 - 25 Pairs) Loose Furniture Living Room:- TV Unit (65" Inch) with Display 3 Seater Sofa + 1 ChairWall ConceptsStorage in Passage for Inverter Dining Area :- 4 Seater Folding Dining TableCrockery unit with Mandir ( 5ft wide )Wall Concepts Kitchen:- Semi Modular KitchenBase & Wall & Loft on all Sides.Rolling ShutterWicker Basket 3+2 Drawer Bedroom:- Bed direction to be flipped Single size Bed with Storage Openable Wardrobe with LoftSide TableStudy Table with Monitor with a Gaming Chair provisionTV Unit (55")Dresser or Mirror Bathroom's Vanity Unit - 2 Nos base & Top Misc:- False CeilingPaintingElectrification Design Brief: - Neo Industrial Two Tone Kitchen Easy Maintence CDP :- 05/02/2026 @ 3:00pm. | 2026-01-30 16:56:28 +0530 | Nishtha Valawalkar | 2.5 BHK CX wants to do 1 bedroom, kitchen and LR Budget - 10L Property - L&T Seawoods | 2026-01-30 16:34:55 +0530 | Nishtha Valawalkar | 15 Grams silver coin to be given | 2026-02-28 |  | 2026-03-07
18237 | Sub Project |  | Dolly Desai | DS Max Skygrand | BNG - HRBR |  | Vishnu S | Rajeshwari S | Yogesh Patidar |  |  | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 47367 | 137 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-31 | 2026-02-01 20:14 | 2026-02-01 | 2026-02-01 20:14 | 2026-02-01 | 2026-02-01 20:15 | 2026-02-02 | 2026-02-01 20:16 | 2026-02-02 | 2026-02-01 20:17 | 2026-02-02 | 2026-02-01 20:19 | 2026-02-01 | 2026-02-01 20:15 | 2026-02-02 | 2026-02-01 20:15 | 2026-02-01 | 2026-02-01 20:15 | 2026-02-02 | 2026-02-01 20:15 |  |  |  |  | 2026-02-01 | 2026-02-01 20:16 | 2026-02-02 | 2026-02-01 20:18 | 2026-02-02 | 2026-02-01 20:18 |  |  | 2026-02-02 | 2026-02-01 20:24 | 2026-02-02 | 2026-02-01 20:30 | 2026-02-02 | 2026-02-01 20:30 | 2026-02-02 | 2026-02-01 20:30 |  |  |  |  | 2026-02-01 20:32 | 2026-02-03 | 2026-02-02 16:03 | 2026-02-06 | 2026-02-04 14:18 | 2026-02-05 | 2026-02-28 12:38 | 2026-02-04 | 2026-02-28 13:34 | 2026-02-28 | 2026-02-28 13:34 | 2026-03-01 | 2026-02-28 15:55 |  |  | 2026-03-10 | 2026-02-28 19:12 | 2026-03-12 | 2026-02-28 19:13 | 2026-03-13 | 2026-02-28 19:14 |  |  |  |  | 2026-02-01 | 2026-02-01 20:30 | 2026-02-02 | 2026-02-01 20:15 | Unknown | 2026-01-31 | 2026-02-01 20:14 | 0 | 0 | 0 | 0 | 40142 | 7225 | 40142 | 0 | [9 empty] | 2026-02-02 | 2026-02-01 20:16 | 2026-02-02 | 2026-02-01 20:17
18238 | Turnkey | 2026-01-01 | Deepa | Duplex 4bhk independent house | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Preproduction | DEM2 | 1665442 | 333088 | 2167515 | 0 | 0 | 22 | 0 | 0 | 0 | 666177 | 666176.8 |  |  | 2026-01-31 | 2026-01-31 12:56 | 2026-02-10 | 2026-02-10 14:52 | 2026-02-10 | 2026-02-10 17:32 | 2026-06-18 | 2026-06-20 10:47 | 2026-07-15 |  | 2026-07-22 |  | 2026-02-10 | 2026-05-20 12:15 | 2026-02-11 | 2026-05-21 14:52 | 2026-05-21 | 2026-05-22 13:42 | 2026-05-23 | 2026-05-23 17:52 |  |  |  |  | 2026-06-20 | 2026-06-23 18:25 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-05-24 | 2026-06-18 16:12 | Site is RTMI | 2026-01-31 | 2026-01-31 12:55 | 1836877 | 330637 | 0 | 0 | 0 | 0 | 1861875.208 | 307440 | 2026-06-18 16:29:04 +0530 | Purva Shiravle | DDM1: Living and dining room: sofa back wall and tv unit wall concept discussed and finalised addition of ledge above tv unit crockery unit design discussed with tall unit as well as base units (need options with some closed unit also)kitchen: base units & wall units placements discussed addition of 2 glass wall units need provision for dishwasher in kitchen beside sink son's Bedroom1: placement of wardrobe, bed, dressing unit and study unit finalised wardrobe internals are yet to be finalised addition of ledge on opposite side of bed Master Bedroom 2: placement of wardrobe, bed, dressing unit and study unit finalised wardrobe internals are yet to be finalised Study room: storage unit design discussed combination of open, glass and closed units required addition of glass units above study table | 2026-05-23 18:40:09 +0530 | Akshay Ds | The customer is clear about the process. The site is currently not ready, and tile work is scheduled to begin next week. The customer is also planning to make some structural changes and requires suggestions from our side based on the proposed designs. He would like the designer to visit the site for a detailed discussion. | 2026-05-22 13:05:10 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: 10th June 2026 Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Tomorrow itself * DEM 1 Next weekends * 10% Payment Stage 2nd June 2026 Informed that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,61,876 Offers Discussed During the Call: Special Offer (25000) PM fee waiver (5%) Design fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Free Bed Offer Final Closing Value Discussed: 16,65,442 Checklist terms - descoping, delay compensation, agreement terms are cleared Extra commitments - nothingÂ | 2026-06-21 | 2026-06-20 10:48 | 2026-07-16 |  | Under Construction | 2026-06-10
18239 | Turnkey | 2026-01-01 | Mangesh Chaudhari | Majestic Tower | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | Asif Shaikh | Aditya Vikram |  | Prashant Panigrahi |  | Lost | Design | DEM1 | 1706588 | 229999 | 1462603 | 0 | 0 | 156 | 0 | 0 | 111319 | 728968 | 636302 |  |  | 2026-01-31 | 2026-02-04 17:34 | 2026-02-04 | 2026-02-04 17:44 | 2026-02-07 | 2026-02-04 17:45 | 2026-07-15 |  | 2026-07-22 |  | 2026-07-29 |  | 2026-02-04 | 2026-02-04 17:48 | 2026-02-05 | 2026-02-04 19:36 | 2026-02-04 | 2026-02-09 17:04 | 2026-02-10 | 2026-02-10 17:12 |  |  |  |  | 2026-07-16 |  | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-02-11 | 2026-02-26 15:02 | Site is RTMI | 2026-01-31 | 2026-02-03 14:36 | 1607960.8766 | 253617 | 0 | 0 | 0 | 0 | 1829071.6672 | 290835 | 2026-05-14 11:51:24 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-04-22 17:17:15 +0530 | Anil Jagtap | Some Image was uploaded | 2026-04-19 16:03:08 +0530 | Anil Jagtap | Some Image was uploaded | 2026-07-16 |  | 2026-07-23
18240 | Turnkey | 2026-01-01 | Sandeep Mayekar | Piramal Revanta | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | 10% Payment | 1431543 | 9999 | 0 | 0 | 0 | 144 | 0 | 133155 | 143154 | 581095 | 564139.2 |  |  | 2026-01-31 | 2026-01-31 15:03 | 2026-02-21 | 2026-02-21 11:50 | 2026-02-24 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-01-31 | 2026-01-31 15:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1213172 | 218371 | 2026-02-21 11:35:03 +0530 | Rutuja Kotwal | DCM: Mr. Sandeep MayekarÂ Â 2BHK.Â Â 560 sq. Ft.Â Â EnteringÂ East.Â Â Design as per VastuÂ Â PiramalÂ revantaÂ mulundÂ Â Possession in hand.Â Â Profession Banking sectorÂ Â Move in 5 people Husband, wife, 2 sons 16 yrs, 8Â yrs..Â And Mother sometimes.Â Â Budget- 10 lakhsÂ Living roomÂ TV unitÂ withÂ barÂ unit,Â sofa,Â 4 seaterÂ dining table,Â shoe rackÂ KitchenÂ baseÂ units ,Â wallÂ units ,Â loftsÂ one side.Â Â Sons bedroomÂ Bed, Wardrobe with lofts,Â study table and Mandir and Side table, mirrorÂ Â MBR- Bed, Wardrobe with loftsÂ and place for used clothes,Â workstationÂ ,andÂ Side table, mirror.Â Â FC, painting, Electricals.Â Vanity cabinets in all bathrooms.Â Â CDPÂ -Â Â TBDÂ Budget suggested-Â 15 lakhs.Â Â Â Â | 2026-02-07 11:11:36 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-01-31 15:03:32 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-03-04 |  | 2026-03-11
18241 | Turnkey | 2026-01-01 | Vishwanath | Lodha Amara | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Faraz Soudagar | Akshat Shrivastava | Murali S | Sanskruti Yadav | Prasad Bhivaji Hande | Active | Installation | Execution | 1138698 | 1138699 | 1312248 | 0 | 1168540 | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-31 | 2026-01-31 19:45 | 2026-02-01 | 2026-02-01 18:15 | 2026-02-01 | 2026-02-01 18:35 | 2026-03-07 | 2026-03-06 14:32 | 2026-04-09 | 2026-04-10 17:09 | 2026-04-15 | 2026-04-15 20:29 | 2026-02-01 | 2026-01-31 05:30 | 2026-02-02 | 2026-02-03 06:33 | 2026-02-03 | 2026-02-03 18:04 | 2026-02-19 | 2026-02-19 12:33 |  |  |  |  | 2026-03-06 | 2026-03-25 16:12 | 2026-04-11 | 2026-04-11 17:56 | 2026-04-12 | 2026-04-11 19:29 |  |  | 2026-04-16 | 2026-04-24 10:08 | 2026-04-24 | 2026-04-24 15:20 | 2026-04-25 | 2026-04-24 17:08 | 2026-04-25 | 2026-04-29 11:55 |  |  |  |  | 2026-05-06 16:57 | 2026-05-16 | 2026-05-18 21:43 | 2026-05-28 | 2026-05-27 18:03 | 2026-05-27 | 2026-05-30 18:39 | 2026-05-27 | 2026-06-10 20:33 | 2026-06-11 | 2026-06-15 15:38 | 2026-06-17 | 2026-06-19 14:13 |  |  | 2026-07-22 |  | 2026-07-24 |  | 2026-07-28 | [5 empty] | 2026-04-24 | 2026-04-29 23:16 | 2026-03-05 | 2026-03-06 11:35 | Site is RTMI | 2026-01-31 | 2026-01-31 15:09 | 1112075 | 200173 | 0 | 0 | 1223274.1898 | 201133 | 1223273.7591 | 196581 | 2026-07-12 14:22:42 +0530 | Faraz Soudagar | Execution: Modular installation done. Rafter installation done. POP punning ETA - 14th July Eletrical work ETA - 15th July Final coat of paint ETA - 22nd july Deep cleaning - 23rd july HO - 24th July | 2026-07-01 23:09:42 +0530 | Faraz Soudagar | Execution: Modular installation done. Profile shutter pending - ETA pending Eletrical work ETA - 7th July rafter installation ETA - 4th July Final coat of paint - 15th July | 2026-06-23 22:20:24 +0530 | Faraz Soudagar | Execution: Modular delivery done - 13th June Installation start date - 22nd June Installation completion ETA - 29th June | 2026-03-07 | 2026-03-06 14:39 | 2026-04-11 | 2026-04-10 17:10
18242 | Turnkey | 2026-01-01 | Meenakshi Suresh | JRC Wild Woods | BNG - HSR | Yes | Aishwarya C | Akshay Ds | Soumya KP | [5 empty] | Chanakya Panigrahi |  | Active | Preproduction | DEM2 | 1965113 | 393022 | 2396339 | 0 | 0 | 31 | 76 | 0 | 0 | 788852 | 783238.8 |  |  | 2026-01-31 | 2026-01-31 16:40 | 2026-02-04 | 2026-02-04 19:11 | 2026-02-10 | 2026-02-10 16:15 | 2026-03-30 | 2026-03-30 18:09 | 2026-07-31 |  | 2026-08-07 |  | 2026-02-10 | 2026-02-11 12:25 | 2026-02-11 | 2026-02-13 19:15 | 2026-02-13 | 2026-02-16 17:51 | 2026-02-20 | 2026-02-20 17:56 |  |  |  |  | 2026-04-04 | 2026-03-30 22:53 | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-03-02 | 2026-03-30 17:59 | Site is RTMI | 2026-01-31 | 2026-01-31 16:28 | 2030796 | 365543 | 0 | 0 | 0 | 0 | 2101767.2701 | 347051 | 2026-04-16 16:37:17 +0530 | Akshay Ds | Some Image was uploaded | 2026-03-11 12:20:37 +0530 | Kowshik | Some Image was uploaded | 2026-02-16 17:51:18 +0530 | Bency Chacko |  | 2026-03-31 | 2026-03-30 18:11 | 2026-08-01
18243 | Turnkey | 2026-01-01 | Mr. Saurabh Kumar | Mahendra Aarya | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 1489484 | 9999 | 0 | 0 | 0 | 165 | 0 | 138949 | 148948 | 609185 | 582402.4 |  |  | 2026-01-31 | 2026-01-31 16:53 | 2026-02-01 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-03-18 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-26 |  | 2026-02-27 | [5 empty] | 2026-03-05 |  | 2026-03-13 |  | 2026-03-14 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 | [6 empty] | 2026-04-11 |  | 2026-04-20 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-23 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-03-22 |  | 2026-02-28 |  | Unknown | 2026-01-31 | 2026-01-31 16:52 | 0 | 0 | 0 | 0 | 0 | 0 | 1262275 | 227209 | [9 empty] | 2026-03-05 |  | 2026-03-12
18244 | Turnkey | 2026-01-01 | Premit Chopra | Raymond Address Season 1 | MUM - Thane | Yes | Mayuri Patil |  | Safalta Karkera | [5 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 2059194 | 9999 | 2059194 | 0 | 0 | 153 | 0 | 195920 | 205919 | 881868 | 765487.2 |  |  | 2026-01-31 | 2026-02-01 12:18 | 2026-02-03 | 2026-02-03 16:22 | 2026-02-19 | 2026-02-19 12:13 | 2026-02-26 |  | 2026-03-05 |  | 2026-03-12 |  | 2026-02-19 |  | 2026-02-20 |  | 2026-02-20 |  | 2026-02-21 | [5 empty] | 2026-02-27 |  | 2026-03-07 |  | 2026-03-08 |  |  |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 | [6 empty] | 2026-04-05 |  | 2026-04-14 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-17 |  |  |  | 2026-05-09 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-03-16 |  | 2026-02-22 |  | Unknown | 2026-01-31 | 2026-02-01 12:17 | 1745080 | 314114 | 0 | 0 | 0 | 0 | 1745080 | 314114 | 2026-02-03 16:21:46 +0530 | Mayuri Patil | MINUTES OF MEETING (MOM)Project: Residential Interior Design Chopra Residence Client: Chopra Family Meeting Date: 14th February Time: 2:00 PM 7:00 PM Purpose: Finalising design brief, requirements, scope & budget 1. Client DetailsFamily of 3 members (Couple + 1 Son)Sons age: 8 yearsPossession: AprilOC: Expected in March (site visit planned)2. Design PreferencesStyle: MinimalistVastu: To be considered across all spacesOverall Look: Clean, functional, and practical3. Living & Dining AreaShoe rack with wall panellingSafety main doorDining table + sofa included in execution scopeDining: 4-seaterTV unit (TV size: 40 inches)TV unit to be placed on opposite wallFoyer unit to be provided insideKitchen planning discussedOne-side loft with base & wall units4. Bedroom DetailsBedroom 1 Kids Room (Temple included)MandirBed with storageStudy unit (height adjustable) external scope Books rack integrated with wardrobeMaster Bedroom (MBR)King-size bed with hydraulic storageSwing wardrobeSide tables with dressing unitTall unitStudy table (height adjustable) with shelves- external scope Bedroom 3 Guest / Kids RoomWardrobe with loftKing-size bed (hydraulic)Side table with mirror5. WashroomsVanity units in all washrooms6. Electrical & FinishesFalse ceilingPaintingElectrical work included7. BudgetEstimated Budget: 1520 LakhsIncludes: Modular work + loose furniture | [6 empty] | 2026-02-27 |  | 2026-03-06
18245 | Turnkey | 2026-01-01 | Abhijit Ahirrao | godrej Amerald | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Faraz Soudagar | Aditya Vikram |  |  | Shailendra Mishra | Active | Handover | Project Closure Pending | 1165550 | 1166350 | 1468468 | 0 | 1165550 | 18 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-31 | 2026-01-31 21:20 | 2026-02-04 | 2026-02-04 12:59 | 2026-02-10 | 2026-02-10 20:59 | 2026-03-07 | 2026-03-07 16:09 | 2026-04-02 | 2026-04-01 14:38 | 2026-04-14 | 2026-04-14 18:52 | 2026-02-10 | 2026-02-10 16:15 | 2026-02-11 | 2026-02-10 16:38 | 2026-02-11 | 2026-02-11 14:09 | 2026-02-26 | 2026-02-26 16:53 |  |  |  |  | 2026-03-08 | 2026-03-11 13:27 | 2026-04-02 | 2026-04-01 22:02 | 2026-04-02 | 2026-04-05 20:25 |  |  | 2026-04-16 | 2026-04-18 14:47 | 2026-04-19 | 2026-04-19 19:27 | 2026-04-20 | 2026-04-22 19:09 | 2026-04-23 | 2026-04-27 19:12 |  |  |  |  | 2026-05-03 18:49 | 2026-05-10 | 2026-05-11 21:42 | 2026-06-01 | 2026-05-30 20:30 | 2026-06-01 | 2026-05-25 18:46 | 2026-05-30 | 2026-06-03 11:47 | 2026-06-02 | 2026-06-06 15:49 | 2026-06-08 | 2026-06-16 13:17 |  |  | 2026-06-01 | 2026-06-27 22:48 | 2026-06-03 | 2026-06-27 22:51 | 2026-07-25 | 2026-06-27 23:12 |  |  |  |  | 2026-04-19 | 2026-04-28 14:52 | 2026-04-15 | 2026-03-06 16:44 | Site is RTMI | 2026-01-31 | 2026-01-31 21:19 | 1244465 | 224003 | 0 | 0 | 1170982.5205 | 206328 | 1170982.5205 | 206328 | 2026-06-23 22:31:35 +0530 | Faraz Soudagar | Execution: Installation completion ETA - 23rd June Flat patti ETA - 24th June Profile shutter pending | 2026-06-01 15:00:37 +0530 | Faraz Soudagar | Dispatch Due: PI work - Only floor covering SRD date - 2nd June | 2026-03-04 14:42:46 +0530 | Harshali Bhuyar | DDM dates tentative - 5th March DDM1 & IM 7th March DDM2 | 2026-03-08 | 2026-03-22 14:17 | 2026-04-02 | 2026-04-01 14:39
18246 | Turnkey | 2026-01-01 | Anish Pillai | My Buildcon Serene | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik |  | RaviKumar Battala | Yogeshwaran | Ranjith Kumar |  | Nidhi Shaw | Sunil Kumar S M | Active | Preproduction | Site Readiness 2 | 765403 | 465925 | 1474577 | 0 | 765403 | 2 | 0 | 0 | 0 | 0 | 299478 |  |  | 2026-01-31 | 2026-01-31 21:40 | 2026-02-08 | 2026-02-24 11:12 | 2026-02-24 | 2026-02-24 11:35 | 2026-05-24 | 2026-05-24 11:25 | 2026-06-12 | 2026-06-11 21:01 | 2026-06-23 | 2026-06-23 14:04 | 2026-02-24 | 2026-02-24 11:42 | 2026-02-25 | 2026-03-04 19:35 | 2026-03-04 | 2026-03-05 16:33 | 2026-03-06 | 2026-03-06 17:49 |  |  |  |  | 2026-05-12 | 2026-05-22 19:07 | 2026-06-12 | 2026-06-13 19:14 | 2026-06-14 | 2026-06-13 19:15 |  |  | 2026-06-27 | 2026-07-08 12:40 | 2026-07-09 | 2026-07-09 19:52 | 2026-07-10 | 2026-07-10 20:24 | 2026-07-11 | 2026-07-13 15:49 | [5 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-09 |  | 2026-06-13 | 2026-05-10 18:25 | Site is RTMI | 2026-01-31 | 2026-01-31 21:38 | 1513166 | 249342 | 0 | 0 | 966358.9062 | 151459 | 966358.9062 | 151459 | 2026-07-10 19:37:04 +0530 | Arun Shankar | Even though this is a 3BHK project, cleaning charges of only 2BHK will apply since the client is doing his interiors only for a part (not whole) of the apartment. | 2026-07-10 19:22:53 +0530 | Chittipireddy Sriharish | Incremental Sign-Off: | 2026-07-03 14:55:56 +0530 | Chittipireddy Sriharish | Some Image was uploaded | 2026-05-25 | 2026-05-24 11:27 | 2026-06-12 | 2026-06-11 21:07
18247 | Turnkey | 2026-01-01 | Gokul shenoy Francis | Adarsh Park Heights | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1552065 | 210615 | 2106152 | 0 | 0 | 70 | 0 | 0 | 99798 | 620826 | 620826 |  |  | 2026-01-31 | 2026-01-31 21:41 | 2026-04-09 | 2026-04-09 15:02 | 2026-04-21 | 2026-04-21 11:49 | 2026-09-04 |  | 2026-09-11 |  | 2026-09-18 |  | 2026-04-21 | 2026-04-30 | 2026-04-22 | 2026-05-01 20:59 | 2026-05-01 | 2026-05-06 17:57 | 2026-05-22 | 2026-05-22 16:52 |  |  |  |  | 2026-09-05 |  | 2026-09-13 |  | 2026-09-14 |  |  |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 | [6 empty] | 2026-10-12 |  | 2026-10-21 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-24 |  |  |  | 2026-11-15 |  | 2026-11-17 |  | 2026-11-18 | [5 empty] | 2026-09-22 |  | 2026-08-31 |  | Unknown | 2026-01-31 | 2026-01-31 21:40 | 1784875 | 321277 | 0 | 0 | 0 | 0 | 1720185.2 | 284043 | 2026-06-30 20:50:37 +0530 | Soumya KP | Some Image was uploaded | 2026-06-09 17:06:52 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-06-04 18:27:36 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-09-05 |  | 2026-09-12 |  | Under Construction | 2026-06-01
18248 | Turnkey | 2026-01-01 | Binvy | Sai Raghvendra Tiara | BNG - HRBR | Yes | Salpriyan Pm | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Shivakumar Ms | Jairam Joshi | Murali S | Mohammed Rasick | Abdul Shafeen | Completed | Complete | Completed | 1141088 | 1141089 | 1620432 | 1023399 | 1141088 | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-31 | 2026-02-06 11:24 | 2026-02-06 | 2026-02-06 18:47 | 2026-02-10 | 2026-02-10 16:49 | 2026-03-11 | 2026-03-06 20:03 | 2026-04-01 | 2026-03-31 12:54 | 2026-04-08 | 2026-04-08 16:06 | 2026-02-10 | 2026-02-11 12:21 | 2026-02-11 | 2026-02-12 19:15 | 2026-02-12 | 2026-02-14 11:35 | 2026-02-16 | 2026-02-16 09:28 |  |  |  |  | 2026-03-07 | 2026-03-07 10:54 | 2026-04-01 | 2026-04-02 14:22 | 2026-04-03 | 2026-04-02 14:22 |  |  | 2026-04-11 | 2026-04-12 18:27 | 2026-04-12 | 2026-04-14 17:38 | 2026-04-15 | 2026-04-15 13:02 | 2026-04-16 | 2026-04-20 19:32 |  |  |  |  | 2026-04-21 15:36 | 2026-04-26 | 2026-04-25 21:52 | 2026-05-17 | 2026-05-15 18:56 | 2026-05-03 | 2026-04-30 19:14 | 2026-05-15 | 2026-05-18 21:31 | 2026-05-18 | 2026-05-19 08:34 | 2026-05-23 | 2026-05-22 17:40 |  |  | 2026-06-16 | 2026-06-17 10:31 | 2026-06-27 | 2026-06-17 20:29 | 2026-06-28 | 2026-06-17 22:18 |  |  |  |  | 2026-04-14 | 2026-04-21 15:35 | 2026-02-26 | 2026-03-06 11:16 | Site is RTMI | 2026-01-31 | 2026-02-01 12:21 | 1373247 | 247184 | 1127881.442 | 178993 | 1313371.0756 | 196945 | 1313371.0756 | 196945 | 2026-06-19 13:15:18 +0530 | Jairam Joshi | Project Closure Pending: Observtion points Closure - 3rd July | 2026-06-16 17:24:02 +0530 | Jairam Joshi | Some Image was uploaded | 2026-06-04 17:58:04 +0530 | Jairam Joshi | Some Image was uploaded | 2026-03-07 | 2026-03-06 20:03 | 2026-04-01 | 2026-03-31 12:55
18249 | Turnkey | 2026-01-01 | Rajan Khandpekar | Raymond | MUM - Thane | Yes | Rutuja Kotwal | [7 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 2717097 | 9999 | 0 | 0 | 0 | 164 | 0 | 261711 | 271710 | 1210612 | 963065.2 |  |  | 2026-02-01 | 2026-02-01 13:09 | 2026-02-10 | 2026-02-24 17:06 | 2026-02-12 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-02-27 |  | 2026-02-28 |  | 2026-02-28 |  | 2026-03-01 | [5 empty] | 2026-03-07 |  | 2026-03-15 |  | 2026-03-16 |  |  |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 | [6 empty] | 2026-04-13 |  | 2026-04-22 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-25 |  |  |  | 2026-05-17 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-03-24 |  | 2026-03-02 |  | Unknown | 2026-02-01 | 2026-02-01 13:04 | 0 | 0 | 0 | 0 | 0 | 0 | 2302625 | 414472 | 2026-02-04 13:09:34 +0530 | Rutuja Kotwal | DCM: Mr. Rajan khandpekar 3 BHK. 1093 sq. ft. Move in - 3 people husband , wife , and FIL- 88 yrs. Profession - retired from TMC. Direction - Entering EAST Design as per basic Vastu. Living room- Shoe rack 20 pairs, 4 seater Dining table, Crockery unit, TV unit, Sofa, Mandir Kitchen - Storage in utility, Base units, Wall units and Lofts Guest Bedroom- Wardrobe with lofts, Bed, Side table with mirror, Study unit. parent's Bedroom - Existing Bed, Existing Wardrobe and existing chest of drawer. MBR- Wardrobe with lofts, Bed, Side table with mirror, Study unit. Vanity in all bathroom. false ceiling, painting and electricals. Budget- 15 - 20 lakhs. Budget suggestion - 22- 25 lakhs CCP- 10 th or 12th February 2026. | [6 empty] | 2026-03-07 |  | 2026-03-14
18250 | Turnkey | 2026-01-01 | SANTOSH VELUNDE | Ashtavinayak Apartments | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Mohammed Lal | Uday Yadruk | Rizwan Mistry | Murali S | Sanskruti Yadav | Aakash Gaikwad | Active | Production | 100% Payment | 1087155 | 684583 | 1181315 | 0 | 1087155 | 13 | 0 | 0 | 0 | 0 | 402572 |  |  | 2026-02-01 | 2026-02-01 13:23 | 2026-02-11 | 2026-02-11 15:36 | 2026-02-14 | 2026-02-11 16:23 | 2026-03-31 | 2026-03-31 16:11 | 2026-05-21 | 2026-05-20 18:25 | 2026-05-27 | 2026-05-27 16:42 | 2026-02-11 | 2026-02-11 17:53 | 2026-02-12 | 2026-02-11 17:53 | 2026-02-11 | 2026-02-13 11:33 | 2026-02-20 | 2026-02-20 12:31 |  |  |  |  | 2026-04-09 | 2026-04-13 19:32 | 2026-05-16 | 2026-05-17 11:49 | 2026-05-18 | 2026-05-17 12:03 |  |  | 2026-05-30 | 2026-06-05 16:14 | 2026-06-09 | 2026-06-09 13:46 | 2026-06-10 | 2026-06-09 16:09 | 2026-06-11 | 2026-06-17 10:50 |  |  |  |  | 2026-06-19 17:55 | 2026-06-26 | 2026-06-25 20:57 | 2026-07-02 | 2026-07-02 19:23 | 2026-07-01 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-06-09 | 2026-06-19 17:54 | 2026-03-31 | 2026-03-29 14:22 | Site is RTMI | 2026-02-01 | 2026-02-01 13:15 | 1001114 | 180200 | 0 | 0 | 1155867.3005 | 188718 | 1155867.3005 | 188718 | 2026-07-08 16:09:18 +0530 | Manzoor Shaikh | Informed client to clear the due, however, said the painting work is pending | 2026-06-03 18:21:43 +0530 | Khyati Bandi | Some Image was uploaded | 2026-05-30 19:20:45 +0530 | Mohammed Lal | Some Image was uploaded | 2026-04-01 | 2026-03-31 16:11 | 2026-05-21 | 2026-05-20 18:25
18251 | Turnkey | 2026-01-01 | Swarna Dhakad | L Andheri T Elexa Reserve | MUM - GOR | Yes | Khushi Khandelwal |  | Shraddha Badgujar | [5 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 1702248 | 9999 | 1702248 | 0 | 0 | 147 | 0 | 160226 | 170225 | 729922 | 631876.8 |  |  | 2026-02-01 | 2026-02-17 19:11 | 2026-02-18 | 2026-02-18 15:47 | 2026-02-21 | 2026-02-18 19:22 | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Unknown | 2026-02-01 | 2026-02-06 15:16 | 1800565.47 | 305427 | 0 | 0 | 0 | 0 | 1800565.47 | 305427 | 2026-02-04 15:03:38 +0530 | Khushi Khandelwal | DCM: LIVING ROOMÂ 3 Seater sofa+ 2 arm chair Seating arrangement in front of door with coffee tableÂ Break kitchen wall (left side) Left kitchen Study unit and pooja unitÂ | [6 empty] | 2026-02-26 |  | 2026-03-05
18252 | Sub Project |  | Mainak Chakravarty | Kalpataru Vienta | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Rajkumar Suthar | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Active | Installation | Execution | 996944 | 996944 | 0 | 0 | 1045213 | 63 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-01 | 2026-02-21 16:39 | 2026-02-02 | 2026-02-21 16:39 | 2026-02-21 | 2026-02-21 16:40 | 2026-02-22 | 2026-02-21 16:41 | 2026-02-22 | 2026-02-21 16:42 | 2026-02-22 | 2026-02-21 16:44 | 2026-02-21 | 2026-02-21 16:40 | 2026-02-22 | 2026-02-21 16:40 | 2026-02-21 | 2026-02-21 16:40 | 2026-02-22 | 2026-02-21 16:40 |  |  |  |  | 2026-02-21 | 2026-02-21 16:41 | 2026-02-22 | 2026-02-21 16:43 | 2026-02-22 | 2026-02-21 17:41 |  |  | 2026-02-26 | 2026-03-04 12:24 | 2026-03-07 | 2026-03-07 16:21 | 2026-03-13 | 2026-03-14 14:16 | 2026-03-15 | 2026-03-21 12:17 |  |  |  |  | 2026-03-25 11:12 | 2026-03-26 | 2026-04-30 22:22 | 2026-05-09 | 2026-05-07 18:52 | 2026-03-28 | 2026-03-30 19:21 | 2026-05-07 | 2026-05-11 13:03 | 2026-05-13 | 2026-05-13 14:13 | 2026-05-15 | 2026-05-23 11:37 |  |  | 2026-04-17 |  | 2026-04-19 |  | 2026-06-15 | [5 empty] | 2026-03-07 | 2026-03-12 16:24 | 2026-02-22 | 2026-02-21 16:40 | Unknown | 2026-02-01 | 2026-02-21 16:38 | 0 | 0 | 0 | 0 | 1167618.0428 | 188138 | 1167618.1283 | 179449 | 2026-04-25 19:46:32 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-25 15:34:36 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-30 14:14:02 +0530 | Reshma Melanta | Some Image was uploaded | 2026-02-22 | 2026-02-21 16:41 | 2026-02-22 | 2026-02-21 16:42
18253 | Turnkey | 2026-01-01 | Dinesh Upadhyaya | Kalpatru shrishti namah | MUM - Thane | Yes | Pooja Nakul Sharma | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 2402663 | 9999 | 2402663 | 0 | 0 | 147 | 0 | 230267 | 240266 | 1036465 | 885665.6 |  |  | 2026-02-01 | 2026-02-01 17:40 | 2026-02-07 | 2026-02-07 10:53 | 2026-02-10 | 2026-02-24 11:48 | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-02-01 | 2026-02-01 14:37 | 2036155 | 366508 | 0 | 0 | 0 | 0 | 2036155 | 366508 | 2026-02-01 18:10:20 +0530 | Sagarika Gawai | kalpataru srishti namaah 2bhk wing A - 6th floor, 605 4 members - husband, wife, 2 sons (21,16 yrs old) European theme/ pastel shades house to be arranged as per vastu maintenance free possession- end of feb foyer- safety door/automation + panelling shoe rack (to be considered later post possession) kitchen- semi modular open to options storage above washing machine (civil changes to be considered post possession) living area- 3+2/ l-shape sofa Tv unit - minimal look 50/55" tv dining table (4 seater) mandir Ganpati celebration sons bedroom- queen bed book shelf study table open to options openable shutter wardrobes with loft Master bedroom- openable shutter wardrobes with loft queen bed tv unit 45" open to options Vanity units- both washrooms False ceiling- basic but open for options budget - 15 to 17 lakhs CDP planned on 8th Feb 2026, Sunday 12 noon | 2026-02-01 14:38:33 +0530 | Nishtha Valawalkar | Budget - 12 to 15L 15 Grams Silver coin pitched 2 BHK 750 sq ft. Silver coin is pending 4 people having cafe, would prefer b2b |  |  |  | 2026-03-04 |  | 2026-03-11
18254 | Turnkey | 2026-01-01 | Amrathraj | Park East by Ruchira | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1594433 | 9999 | 1594433 | 0 | 0 | 112 | 0 | 149444 | 159443 | 645533 | 630013.6 |  |  | 2026-02-01 | 2026-02-08 11:17 | 2026-02-01 | 2026-02-12 13:51 | 2026-03-25 | 2026-03-25 17:17 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-02-01 | 2026-02-01 14:47 | 1351215 | 243218 | 0 | 0 | 0 | 0 | 1351215 | 243218 | 2026-02-01 16:30:22 +0530 | Keerthan M | DCM: Amrathraj 3BHK 5 ppl 12L Foyer - one tall unit, base unit, seating, display Living - False ceiling in common area - floating unit with glass storage Dining - Pooja with crockery next to foyer - 6 seater dining table - pooja low height(closed unit) - crockery top storage need to be glass shutters. - mirror in B/W Kitchen - Bottom, top &loft - washing machine space and cylinder storage need to be planned in utility - storage below utility window. - loft on one side in kitchen. KBR(near living) - WardrobeÂ - bay window seating - study for 2 (try to consider with by window) - 2 single beds - Mirror on bed wall PBR - Bay window with wardrobe. - study left side of bed - dresser near bed - queen bed MBR -King bed - TV unitÂ - Study top storage. - wardrobe L shape - Mirror near washroom door. Note: Vanity in all the rooms top storage in 2 room. | [6 empty] | 2026-04-02 |  | 2026-04-09
18255 | Turnkey | 2026-01-01 | Mrs. Rose Mary | Purva Meraki | BNG - HSR | No Estimate | [8 empty] | Varun Mandana |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-01 | 2026-02-01 14:49 | 2026-02-02 |  | 2026-02-15 |  | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 | [5 empty] | 2026-02-23 |  | 2026-03-03 |  | 2026-03-04 |  |  |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 | [6 empty] | 2026-04-01 |  | 2026-04-10 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-13 |  |  |  | 2026-05-05 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-03-12 |  | 2026-02-18 |  | Unknown | 2026-02-01 | 2026-02-01 14:48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-02-23 |  | 2026-03-02
18256 | Turnkey | 2026-01-01 | Pandharinath khade | Kasturi Housing Society Plot No. 195 | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 1857541 | 9999 | 0 | 0 | 0 | 164 | 0 | 175755 | 185754 | 766616 | 719417.2 |  |  | 2026-02-01 | 2026-02-01 18:39 | 2026-02-02 |  | 2026-02-08 |  | 2026-02-15 |  | 2026-02-22 |  | 2026-03-01 |  | 2026-02-08 |  | 2026-02-09 |  | 2026-02-09 |  | 2026-02-10 | [5 empty] | 2026-02-16 |  | 2026-02-24 |  | 2026-02-25 |  |  |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-07 | [6 empty] | 2026-03-25 |  | 2026-04-03 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-06 |  |  |  | 2026-04-28 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-03-05 |  | 2026-02-11 |  | Unknown | 2026-02-01 | 2026-02-01 17:22 | 0 | 0 | 0 | 0 | 0 | 0 | 1574187 | 283353 | 2026-04-24 15:04:51 +0530 | Vandana Preet | Some Image was uploaded | 2026-04-07 12:44:07 +0530 | Vandana Preet | Some Image was uploaded | 2026-02-03 11:07:55 +0530 | Mayuri Patil | DCM: | 2026-02-16 |  | 2026-02-23
18257 | Turnkey | 2026-01-01 | Sagar Mule | mahendra Arya | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  | RaviKumar Battala | Yogeshwaran | Ranjith Kumar | Murali S | Ramesh Nayak | Affaan Abdulla | Active | Installation | Execution | 1359837 | 1359844 | 1681367 | 0 | 1417337 | 6 | 4 | 0 | 0 | 0 | 0 |  |  | 2026-02-01 | 2026-02-01 16:26 | 2026-02-01 | 2026-02-04 19:07 | 2026-02-12 | 2026-02-12 16:25 | 2026-04-10 | 2026-04-10 12:09 | 2026-05-14 | 2026-05-21 00:24 | 2026-05-29 | 2026-05-27 11:03 | 2026-02-12 | 2026-02-13 21:22 | 2026-02-13 | 2026-02-13 21:23 | 2026-02-13 | 2026-02-19 14:30 | 2026-02-20 | 2026-02-20 17:57 |  |  |  |  | 2026-04-13 | 2026-04-24 18:50 | 2026-05-22 | 2026-05-24 00:52 | 2026-05-25 | 2026-05-24 00:52 |  |  | 2026-05-27 | 2026-05-30 21:42 | 2026-05-31 | 2026-05-31 12:29 | 2026-06-02 | 2026-05-31 18:24 | 2026-06-01 | 2026-06-08 18:45 |  |  |  |  | 2026-06-10 14:46 | 2026-06-21 | 2026-06-20 22:12 | 2026-07-06 | 2026-07-06 20:27 | 2026-07-05 | 2026-07-06 19:20 | 2026-07-06 | 2026-07-09 11:22 | 2026-07-09 | 2026-07-09 14:47 | 2026-07-12 |  |  |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-15 | [5 empty] | 2026-05-31 | 2026-06-10 14:45 | 2026-03-30 | 2026-04-08 15:27 | Site is RTMI | 2026-02-01 | 2026-02-01 16:22 | 1424887 | 256479 | 0 | 0 | 1538143.1916 | 248237 | 1538143.1916 | 248237 | 2026-07-06 15:57:47 +0530 | Ranjith Kumar | Procurement: | 2026-06-17 12:54:26 +0530 | Ranjith Kumar | Bonito Side Floor Covering Done, Electrical & False Ceiling - WIP Cx Side - Flase Ceiling Painting | 2026-05-27 12:21:22 +0530 | Kiran Agarampalli | Some Image was uploaded | 2026-04-11 | 2026-04-10 12:13 | 2026-05-22 | 2026-05-21 00:25
18258 | Turnkey | 2026-01-01 | Chandan Kumar | Sumadhura Folium | BNG - HRBR | Yes | Vijin Venu | Rajeshwari S | Shibin Lal | [5 empty] | Ankur Kumar |  | Active | Preproduction | DEM2 | 1706971 | 341393 | 2107159 | 0 | 0 | 58 | 0 | 0 | 0 | 686669 | 678908.8 |  |  | 2026-02-01 | 2026-02-05 19:08 | 2026-02-06 | 2026-02-06 15:32 | 2026-02-08 | 2026-02-08 11:01 | 2026-05-21 | 2026-05-17 15:03 | 2026-07-05 |  | 2026-07-17 |  | 2026-02-07 | 2026-02-10 16:46 | 2026-02-09 | 2026-02-11 16:00 | 2026-02-11 | 2026-02-14 18:05 | 2026-02-16 | 2026-02-16 09:33 |  |  |  |  | 2026-05-22 | 2026-05-18 18:53 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-23 |  | 2026-05-10 | 2026-05-17 14:49 | Site is RTMI | 2026-02-01 | 2026-02-01 16:44 | 1785728 | 321431 | 0 | 0 | 0 | 0 | 1774138.0698 | 306148 | 2026-06-30 13:25:05 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-17 15:46:04 +0530 | Chandini Nj | Kitchen - double door fridge, oven,Â MBR - HEADREST WALL need to be changed, no rafters. Used cloth storage provision KBR - CIRCLE WITH DECOR, Instead tall unit some designs Locker provision as per the Vastu False ceiling with profile lightingÂ Vanities need to be provided with some storage in MBR vanity Store room - looking for shoe rack. 50pair of shoes, kitchen setup foldable table outdoor unit. Living area - speakers 4 provision. | 2026-05-14 15:16:28 +0530 | Parasa Sri | Some Image was uploaded | 2026-05-18 | 2026-05-17 15:06 | 2026-07-06
18259 | Turnkey | 2026-01-01 | Saylee Ramchandra Mestri | Arihant Aspire | MUM - Thane | Yes | Maasoumeh Raza | [9 empty] | Active | Prospect | DCM Due | 2057333 | 9999 | 0 | 0 | 0 | 164 | 0 | 195734 | 205733 | 925342 | 720524.8 |  |  | 2026-02-01 | 2026-02-01 17:36 | 2026-02-07 | 2026-02-07 13:11 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-04-22 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-04-09 |  | 2026-04-17 |  | 2026-04-18 |  |  |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 | [6 empty] | 2026-05-16 |  | 2026-05-25 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-28 |  |  |  | 2026-06-19 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-04-26 |  | 2026-04-04 |  | Site is RTMI | 2026-02-01 | 2026-02-01 16:45 | 0 | 0 | 0 | 0 | 0 | 0 | 1743503 | 313830 | 2026-02-07 13:11:31 +0530 | Maasoumeh Raza | Some Image was uploaded | 2026-02-07 13:07:07 +0530 | Maasoumeh Raza | Name: 18259 - Saylee Ramchandra Mestri Property Name:Arihant Aspire Property type: 2BHK Possession: MarchÂ Move in: Not decidedÂ Member: 4 memberÂ Occupation: DoctorÂ Budget: 12L to 15L Requirements: Living room: Shoe Rack [30 pairs]Â Safety door Tv Unit with display [55 inch] MandirÂ 3 seater sofa + bench seat 6 Seater diningÂ Mandir Extention of window Kitchen :Â Base unit Wall unitÂ Loft unitÂ Need maximum storage Extention of window Master BedRoom: Queen size Bed Drawer Wardrobe with loft [Swing wardrobe] Used cloth storage Dressing Unit Side table Extention of window Bay window [seating] Common bedroom: Queen size Bed hydrolic Wardrobe with loft [Swing wardrobe] Used cloth storage Dressing Unit Side table Study Table Extention of window Window seating if possible Bathroom: Below vanity unit Additional scope: False ceilingÂ Painting Electrical |  |  |  | 2026-04-09 |  | 2026-04-16
18260 | Turnkey | 2026-01-01 | saurabh doshi | Akshay residency | MUM - GOR | Yes | Shweta Dalvi |  | Shahid Chougley | [5 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 2788746 | 9999 | 2788746 | 0 | 0 | 148 | 0 | 268876 | 278875 | 1185945 | 1045051.6 |  |  | 2026-02-01 | 2026-02-12 13:12 | 2026-02-12 | 2026-02-12 19:21 | 2026-02-18 | 2026-02-18 19:48 | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Site is RTMI | 2026-02-01 | 2026-02-12 13:11 | 2363344 | 425401 | 0 | 0 | 0 | 0 | 2363344 | 425401 | 2026-04-15 18:31:56 +0530 | Manasi Patil | Some Image was uploaded | 2026-02-01 18:41:04 +0530 | Shweta Dalvi | DCM: User ResponseLifestyle1. Please select your budget for Interior Designing? Rs. 15-20 Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? Husband- Banking , Wife - Advocate 4. Who will be living in this home? Nuclear Family, Elderly Members 5. What activities do you usually perform at home? (Choose top 23) Working from Home, Hosting Guests, Family Bonding, Relaxing & Unwinding, Pursuing Hobbies, Prayer 6. What is your preferred entertainment style? Casual get-togethers 7. Do you prefer any Smart home features? Security 8. What is your possession date? 2026-03-31 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Safety door, Digital lock, Shoe rack, Seating Dcor & Living Room1. Choose your decor inspirations Artwork, Plants 2. Any specific signature design feature required Chandelier, Statement wall 3. Whats the primary use of your living room? TV focus , Entertaining guests, Multipurpose 4. Any absolute no-go styles, colors, or materials? No dark colours 5. Must-have furniture or features? Sofa, TV unit, Home speakers, Coffee table, Bookshelves, Puja unit, Statement Wall/ Feature Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Microwave, Fridge, Hob, Chimney, Washing machine BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Swing Master Bedroom - Additional units Bookshelf , Dresser Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Swing Other Bedroom - Additional units Study table , Bookshelf , Dresser , TV unit BathroomsPreferred vanity style What do you prefer? Shower partitions What are your requirements for Utility Area? Top Storage, Tall Storage, Washing machine space Balcony & OutdoorHow do you intend to use your balcony for? I don't have a balcony b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? NA Final Vision1. Any space in the home that you want to put in Spotlight? 2. Do you want the design to reflect any personal story, cultural influence, or special memory CDP Next Sunday. Cx will confirm the same in the group | 2026-02-01 18:40:13 +0530 | Shweta Dalvi | Some Image was uploaded | 2026-02-26 |  | 2026-03-05
18261 | Turnkey | 2026-01-01 | Vinayakumar Hanasi | Archita Arana | BNG - HSR | Yes | Kiran Agarampalli | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Lost | Design | DEM1 | 1087961 | 0 | 1404023 | 0 | 0 | 151 | 0 | 0 | 217592 | 447398 | 422970.4 |  |  | 2026-02-01 | 2026-02-01 17:58 | 2026-02-01 | 2026-02-03 17:00 | 2026-02-07 | 2026-02-07 11:51 | 2026-08-07 |  | 2026-08-14 |  | 2026-08-21 |  | 2026-02-07 | 2026-02-10 15:06 | 2026-02-08 | 2026-02-12 19:19 | 2026-02-12 | 2026-02-14 13:07 | 2026-02-20 | 2026-02-20 17:00 |  |  |  |  | 2026-08-08 |  | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-08-03 |  | Site is Non-RTMI | 2026-02-01 | 2026-02-01 17:47 | 1189850 | 214173 | 0 | 0 | 0 | 0 | 1189848.286 | 196468 | 2026-06-23 12:43:51 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-24 19:04:38 +0530 | Christopher Macwan |  | 2026-04-23 18:10:52 +0530 | Kowshik | Some Image was uploaded | 2026-08-08 |  | 2026-08-15
18262 | Turnkey | 2026-01-01 | Ashok Bagrecha | Independent house | BNG - HSR | Yes | Shefali | Abhinandan K S | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | DCM Due | 2488847 | 9999 | 0 | 0 | 0 | 164 | 0 | 238886 | 248885 | 1053847 | 937230.4 |  |  | 2026-02-01 | 2026-02-01 17:46 | 2026-02-16 | 2026-02-16 12:18 | 2026-02-16 |  | 2026-02-23 |  | 2026-03-02 |  | 2026-03-09 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-18 | [5 empty] | 2026-02-24 |  | 2026-03-04 |  | 2026-03-05 |  |  |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 | [6 empty] | 2026-04-02 |  | 2026-04-11 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-14 |  |  |  | 2026-05-06 |  | 2026-05-08 |  | 2026-05-09 | [5 empty] | 2026-03-13 |  | 2026-02-19 |  | Unknown | 2026-02-01 | 2026-02-01 17:44 | 0 | 0 | 0 | 0 | 0 | 0 | 2109192 | 379654 | [9 empty] | 2026-02-24 |  | 2026-03-03
18263 | Turnkey | 2026-01-01 | Kartik V | legacy saviero | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [7 empty] | Active | Preproduction | DEM2 | 1721805 | 344361 | 1330711 | 0 | 0 | 77 | 6 | 0 | 0 | 715184 | 662260.4 |  |  | 2026-02-01 | 2026-02-13 11:32 | 2026-02-13 | 2026-02-14 07:55 | 2026-02-19 | 2026-02-24 12:00 | 2026-03-29 | 2026-03-29 18:45 | 2026-07-21 |  | 2026-07-28 |  | 2026-02-24 | 2026-02-24 12:00 | 2026-02-25 | 2026-02-27 13:48 | 2026-02-27 | 2026-03-02 14:09 | 2026-03-05 | 2026-03-05 15:22 |  |  |  |  | 2026-03-31 | 2026-04-29 17:17 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-08-01 |  | 2026-03-06 | 2026-03-29 18:01 | Site is RTMI | 2026-02-01 | 2026-02-01 18:15 | 1367945.5561 | 225871 | 0 | 0 | 0 | 0 | 1890901.7957 | 312224 | 2026-03-11 17:30:08 +0530 | Alekhya Korada | Some Image was uploaded | 2026-03-02 14:09:28 +0530 | Bency Chacko | Possession - June 2026 Can start the IMs - Can start as the site is available The IDM - 15th March 2026 Design meeting - Weekends - Saturday No on site work is planned Checklist cleared Offers and Quote cleared B2C - Self-funded - EMI | 2026-03-02 13:22:54 +0530 | Bency Chacko |  | 2026-03-30 | 2026-03-29 18:46 | 2026-07-22 |  | Under Construction | 2026-06-01
18264 | Turnkey | 2026-01-01 | Amol Belekar | Tharwani palladian | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Hold | Design | 20% Payment | 1139063 | 164033 | 1550339 | 0 | 0 | 47 | 78 | 0 | 63780 | 480638 | 430612 |  |  | 2026-02-01 | 2026-02-03 19:44 | 2026-02-05 | 2026-02-05 12:56 | 2026-02-10 | 2026-02-10 12:12 | 2026-05-05 | 2026-03-12 12:18 | 2026-10-06 |  | 2026-10-13 |  | 2026-02-10 | 2026-02-10 19:27 | 2026-02-11 | 2026-02-10 19:28 | 2026-02-10 | 2026-02-11 15:02 | 2026-02-20 | 2026-02-20 15:01 |  |  |  |  | 2026-07-15 |  | 2026-10-08 |  | 2026-10-09 |  |  |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 | [6 empty] | 2026-11-06 |  | 2026-11-15 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-16 |  | 2026-11-18 |  |  |  | 2026-12-10 |  | 2026-12-12 |  | 2026-12-13 | [5 empty] | 2026-10-17 |  | 2026-05-13 | 2026-03-11 17:12 | Site is Non-RTMI | 2026-02-01 | 2026-02-03 18:59 | 1313846 | 236492 | 0 | 0 | 0 | 0 | 1271321.2595 | 196636 | 2026-07-10 14:12:35 +0530 | Anil Jagtap | cx will receive the possession by November end *26 | 2026-06-04 12:32:35 +0530 | Anamika Dolai | Some Image was uploaded | 2026-05-14 12:54:09 +0530 | Anamika Dolai | Some Image was uploaded | 2026-03-12 | 2026-03-12 12:40 | 2026-10-07 |  | Under Construction | 2026-09-01
18265 | Turnkey | 2026-01-01 | Anshu | Prestige | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 3959327 | 9999 | 3959327 | 0 | 0 | 95 | 0 | 385934 | 395933 | 1660744 | 1506718 |  |  | 2026-02-01 | 2026-02-01 19:42 | 2026-02-05 | 2026-02-07 13:26 | 2026-02-10 | 2026-04-12 14:51 | 2026-04-19 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-04-20 |  | 2026-04-28 |  | 2026-04-29 |  |  |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 | [6 empty] | 2026-05-27 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-08 |  |  |  | 2026-06-30 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-05-07 |  | 2026-04-15 |  | Unknown | 2026-02-01 | 2026-02-01 19:41 | 3355362 | 603965 | 0 | 0 | 0 | 0 | 3355362 | 603965 | 2026-02-07 13:25:31 +0530 | Ankita Agarwal | DCM: MOM Mrs. AnshuProject: RGM Residence Date: 05/02/2026 Family Members: 6 Children: 1 Boy (10 yrs), 1 Girl (6 yrs) Expected Possession: 23 Months Budget: 3035 Lakhs GROUND FLOOR1. Formal LivingStorage with seating below windowConsole unit with highlight lightingOpposite sofa wall to have gypsum design with focused lightingCenter feature wall with Indian marble mural2. CourtyardTree design to be suggestedLandscape concept with appropriate lighting3. Informal Living70 TV unit on parking wallSofa placement near windowSofa back wall to remain simple with large painting4. Dining Area8-seater dining setupCrockery unitTall unit with highlight wallCommon vanity next to fridge wall5. KitchenW3 window to be closedDouble door refrigerator spaceTall pantry unitTambor unitTall unit for appliancesWicker baskets for storage6. Powder RoomMirror design to be recommendedStorage under staircase to be added7. Parents BedroomW1 window to be closedDresser on W1 wallWardrobe with used clothes sectionShoe storage provisionWallpaper at bed back wallMinimal TV unit (40)8. Pooja RoomSit-and-pray conceptStorage provision as requiredFIRST FLOOR1. Kids Room 2 (Boy 10 yrs)Bunk bed concept (bed at lower level, upper level for activity/reading space)Wardrobe with loftTwo separate study units with book storageDresser unitTrophy display unitQuotation to be checked from Bonito; external option to be provided2. Kids Room 1 (Girl 6 yrs)Wardrobe on washroom wallWardrobe niche to be converted into studyPeg board with display storageUnicorn wallpaper at bed backCanopy design to be consideredDresser area3. Family RoomW7 window to be closedLayout and furniture to be planned accordingly4. Master BedroomKing size bedOttoman9 workstation for two personsLarge mirror dresser with storageMinimal TV unitOlive green theme5. Walk-in WardrobeL-shaped wardrobeUsed clothes hanging sectionShoe storageSwing wardrobe shutters6. Master Bedroom BathroomW5 window to be closed (towards V1)Platform extended towards shower areaNo bathtub provisionSECOND FLOOR1. Media Room / Home TheatreFalse ceiling designHome theatre setupBar counterSeating layout2. LaundrySmall sinkStorage cabinets3. Store RoomNo windowWardrobe with loftGranite shelves | [6 empty] | 2026-04-20 |  | 2026-04-27
18266 | Turnkey | 2026-01-01 | Maninder Kaur | Transcon Triumph | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1498755 | 449626 | 1879098 | 0 | 0 | 87 | 65 | 0 | 0 | 490365 | 558764 |  |  | 2026-02-01 | 2026-02-06 19:36 | 2026-02-07 | 2026-02-07 07:53 | 2026-02-09 | 2026-02-08 23:36 | 2026-08-04 |  | 2026-08-11 |  | 2026-08-18 |  | 2026-02-08 | 2026-02-12 19:06 | 2026-02-09 | 2026-02-13 15:23 | 2026-02-13 | 2026-02-13 16:40 | 2026-02-20 | 2026-02-20 17:56 |  |  |  |  | 2026-07-11 | 2026-06-01 16:48 | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-07-31 |  | Unknown | 2026-02-01 | 2026-02-05 13:11 | 1592456 | 286642 | 0 | 0 | 0 | 0 | 1563763.4593 | 259132 | 2026-05-05 11:13:10 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-03 14:01:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-30 15:29:12 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-08-05 |  | 2026-08-12
18267 | Turnkey | 2026-01-01 | Satya Pal Singh | Transcon | MUM - GOR | Yes | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1457386 | 185226 | 1852258 | 0 | 0 | 69 | 64 | 0 | 106251 | 610881 | 555027.6 |  |  | 2026-02-01 | 2026-02-18 01:02 | 2026-02-23 | 2026-02-23 10:31 | 2026-02-26 | 2026-02-24 11:44 | 2026-10-04 |  | 2026-10-11 |  | 2026-10-18 |  | 2026-02-24 | 2026-02-27 17:37 | 2026-02-25 | 2026-02-27 17:38 | 2026-02-27 | 2026-03-04 14:22 | 2026-03-11 | 2026-03-11 16:59 |  |  |  |  | 2026-10-05 |  | 2026-10-13 |  | 2026-10-14 |  |  |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 | [6 empty] | 2026-11-11 |  | 2026-11-20 |  | 2026-11-19 |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-23 |  |  |  | 2026-12-15 |  | 2026-12-17 |  | 2026-12-18 | [5 empty] | 2026-10-22 |  | 2026-08-05 |  | Unknown | 2026-02-01 | 2026-02-18 01:02 | 1569710 | 282547 | 0 | 0 | 0 | 0 | 1534986.5315 | 255872 | 2026-05-03 14:04:22 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-27 10:37:54 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-26 17:33:56 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-10-05 |  | 2026-10-12 |  | Under Construction | 2026-04-01
18268 | Turnkey | 2026-01-01 | YUKTIS PAREKH & CO (Deepak Vasant Lad) | Ashtavinayak Apartments | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera |  | Ehtesham Bhati | Uday Yadruk | Rizwan Mistry | Murali S | Harshaan Tiku | Aakash Gaikwad | Active | Handover | Project Closure Pending | 915847 | 915849 | 1058451 | 0 | 913208 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-01 | 2026-02-11 15:42 | 2026-02-13 | 2026-02-13 14:49 | 2026-02-16 | 2026-02-13 16:02 | 2026-04-01 | 2026-03-25 18:56 | 2026-03-30 | 2026-03-29 18:10 | 2026-04-25 | 2026-04-24 15:12 | 2026-02-13 | 2026-02-13 17:57 | 2026-02-14 | 2026-02-14 13:03 | 2026-02-14 | 2026-02-18 16:04 | 2026-02-20 | 2026-02-20 12:09 |  |  |  |  | 2026-04-02 | 2026-03-18 14:46 | 2026-04-10 | 2026-04-12 14:24 | 2026-04-13 | 2026-04-12 14:25 |  |  | 2026-04-25 | 2026-04-28 13:40 | 2026-04-29 | 2026-04-29 13:43 | 2026-04-30 | 2026-04-29 16:58 | 2026-04-30 | 2026-04-30 18:36 |  |  |  |  | 2026-05-05 15:55 | 2026-05-29 | 2026-05-28 19:19 | 2026-06-13 | 2026-06-11 16:17 | 2026-06-07 | 2026-06-03 19:04 | 2026-06-11 | 2026-06-11 17:13 | 2026-06-11 | 2026-06-16 16:19 | 2026-06-30 | 2026-06-29 16:46 |  |  | 2026-07-02 | 2026-06-30 21:33 | 2026-07-02 | 2026-06-30 21:58 | 2026-06-30 | 2026-06-30 22:33 |  |  |  |  | 2026-04-29 | 2026-05-04 13:14 | 2026-03-28 | 2026-03-25 18:52 | Site is RTMI | 2026-02-01 | 2026-02-11 15:42 | 896992 | 161458 | 0 | 0 | 1013899.2585 | 162184 | 1017375.1335 | 162586 | 2026-06-08 20:41:05 +0530 | Uday Yadruk | Some Image was uploaded | 2026-06-01 16:55:44 +0530 | Uday Yadruk | Execution: Floor protection - completed Gypsum work - completed 1st coat of painting work - 02/06/2026 site ready for the modular installation - 03/06/2026 | 2026-04-29 11:49:15 +0530 | Swapnali Shedekar | Some Image was uploaded | 2026-03-26 | 2026-03-27 11:43 | 2026-03-30 | 2026-03-29 18:11
18269 | Turnkey | 2026-01-01 | Popat khot | Nicco Residency | MUM - GOR | Yes | Khushi Khandelwal |  | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1369869 | 9999 | 1369869 | 0 | 0 | 148 | 0 | 126988 | 136987 | 577334 | 518561.6 |  |  | 2026-02-01 | 2026-02-06 19:35 | 2026-02-04 | 2026-02-10 13:11 | 2026-02-17 | 2026-02-17 14:09 | 2026-02-24 |  | 2026-03-03 |  | 2026-03-10 |  | 2026-02-17 |  | 2026-02-18 |  | 2026-02-18 |  | 2026-02-19 | [5 empty] | 2026-02-25 |  | 2026-03-05 |  | 2026-03-06 |  |  |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 | [6 empty] | 2026-04-03 |  | 2026-04-12 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-15 |  |  |  | 2026-05-07 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-03-14 |  | 2026-02-20 |  | Unknown | 2026-02-01 | 2026-02-06 19:35 | 1160906 | 208963 | 0 | 0 | 0 | 0 | 1160906 | 208963 | 2026-02-04 19:55:37 +0530 | Khushi Khandelwal | DCM: ENTRANCEÂ Safety door & Main doorÂ Shoe unit Living & Dining area 4/6 seater diningÂ 3+2 sofa seating TV Unit Mandir (closed)Floor mounted Balcony area Placement of AC outdoor unit KITCHEN Appliances-Microwave & ref.Â washing machineÂ dishwasherÂ HOB on left platformÂ BEDROOM-1 (KIDS BEDROOM) Wardrobe Queen size bedÂ Study tableÂ Dresser MASTER BEDROOMÂ Queen size bedÂ WardrobeÂ DresserÂ WASHROOMÂ Vanity unit | [6 empty] | 2026-02-25 |  | 2026-03-04
18271 | Turnkey | 2026-01-01 | Ritesh Vitekar | Ambit Vista | MUM - GOR | Yes | Priyanka Patel |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1362289 | 9999 | 0 | 0 | 0 | 112 | 0 | 126230 | 136229 | 580884 | 508946.8 |  |  | 2026-02-01 | 2026-02-18 15:45 | 2026-02-26 | 2026-02-26 19:31 | 2026-03-22 | 2026-03-22 13:05 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-02-01 | 2026-02-01 21:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1398754.57 | 241366 | 2026-02-27 13:31:19 +0530 | Priyanka Patel | DCM: 1. Please select your budget for Interior Designing? Rs. 10-15 Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? IT 4. Who will be living in this home? Pets, Nuclear Family 5. What activities do you usually perform at home? (Choose top 23) Pursuing Hobbies, Relaxing & Unwinding, Hosting Guests, Working from Home 6. What is your preferred entertainment style? Casual get-togethers 7. Do you prefer any Smart home features? Automation, Security, Lighting Control 8. What is your possession date? 2026-06-29 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Partition, Seating, Shoe rack, Digital lock, Safety door Dcor & Living Room1. Choose your decor inspirations Travel souvenirs, Artwork 2. Any specific signature design feature required Art installation, Statement wall, Chandelier 3. Whats the primary use of your living room? Multipurpose 4. Any absolute no-go styles, colors, or materials? Dull dark colors 5. Must-have furniture or features? Statement Wall/ Feature, Display unit , Puja unit, Bookshelves, Coffee table, Speakers, Home speakers, TV unit, Sofa Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit, Bar unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Washing machine, Chimney, Hob, Fridge, Microwave, Built-in oven BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Swing Master Bedroom - Additional units TV unit, Dresser, Study table Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Swing Other Bedroom - Additional units Dresser , Bookshelf , Study table BathroomsPreferred vanity style What do you prefer? What are your requirements for Utility Area? Dryer, Washing machine space, Laundry space, Top Storage Balcony & OutdoorHow do you intend to use your balcony for? b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? Final Vision1. Any space in the home that you want to put in Spotlight? 2. Do you want the design to reflect any personal story, cultural influence, or special memory | [6 empty] | 2026-04-02 |  | 2026-04-09
18272 | Turnkey | 2026-01-01 | Neha Jagshettiwar | Inspira Tropical Garden | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1876305 | 9999 | 1876305 | 0 | 0 | 155 | 0 | 177632 | 187631 | 754752 | 746291.6 |  |  | 2026-02-02 | 2026-02-04 16:21 | 2026-02-04 | 2026-02-04 18:37 | 2026-02-10 | 2026-02-10 18:58 | 2026-02-17 |  | 2026-02-24 |  | 2026-03-03 |  | 2026-02-10 |  | 2026-02-11 |  | 2026-02-11 |  | 2026-02-12 | [5 empty] | 2026-02-18 |  | 2026-02-26 |  | 2026-02-27 |  |  |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-09 | [6 empty] | 2026-03-27 |  | 2026-04-05 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-08 |  |  |  | 2026-04-30 |  | 2026-05-02 |  | 2026-05-03 | [5 empty] | 2026-03-07 |  | 2026-02-13 |  | Unknown | 2026-02-02 | 2026-02-04 16:13 | 1590089 | 286216 | 0 | 0 | 0 | 0 | 1590089 | 286216 | 2026-02-04 18:39:40 +0530 | Swati Rathod | DCM: Based on 04-02-2026 meeting, below is a list of all the requirements that were discussed during the meeting: PID: 18272 Property - 3BHK possession - 25-04-2026 Budget - 10L- 12L Members - 4ppl, (kids-1(2yr) profession - IT - North facing - no dark colours FOYER : - shoe rack with seating, some extra storage(min 2 seater space)(bottom units with more ht) - no more rafter designs LIVING: - TV unit(bottom unit) DINNING: - 6 seaters - crockery unit(place to be thought) - pooja unit(standing)(seating chair to be provided) - wash basin place KITCHEN: - OTG unit - tall unit - bottom unit - top units - loft - double door fridge - 4 burner - single bowl sink with top drainer - under Ro unit with dust bin - wicker backet - black granite(installation)Â UTILITY: - W.M, D.W(space) - janitor unit - bottom and top unit TOILETS: - vanityÂ M.BEDROOM: - king size bed - openable wardrobe(tall unit @ centre)Â - loftÂ - tall unit for hand bagsÂ - mirror with bottom unit - tv unit(wallpaper concept) BEDROOM 2(Grand mom): - Queen size bed - foldable study unit - wardrobe with dresser - loftÂ - TV unit to be look after BEDROOM 3(kid)(Ira): - Queen size bed or invisible bed - openable wardrobe - loftÂ Â - dresser - study table Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. Meeting Date: 08-02-2026 at 2:00 PM (Sunday) | [6 empty] | 2026-02-18 |  | 2026-02-25
18273 | Sub Project |  | Pankaj Kumar | jeevan octave | BNG - HRBR |  | Sanjay Kulkarni | Parasa Sri | Shibin Lal |  |  | Deekshith P | Jairam Joshi | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-03 | 2026-02-03 11:46 | 2026-02-04 | 2026-02-03 11:47 | 2026-02-03 | 2026-02-03 11:47 | 2026-02-04 | 2026-02-03 11:53 | 2026-02-04 | 2026-02-03 11:54 | 2026-02-04 | 2026-02-03 11:56 | 2026-02-03 | 2026-02-03 11:47 | 2026-02-04 | 2026-02-03 11:48 | 2026-02-03 | 2026-02-03 11:48 | 2026-02-04 | 2026-02-03 11:48 |  |  |  |  | 2026-02-03 | 2026-02-03 11:54 | 2026-02-04 | 2026-02-03 11:55 | 2026-02-04 | 2026-02-03 11:55 |  |  | 2026-02-04 | 2026-02-03 11:56 | 2026-02-04 | 2026-02-03 12:03 | 2026-02-04 | 2026-02-03 12:26 | 2026-02-04 | 2026-02-03 12:26 |  |  |  |  | 2026-02-04 12:47 | 2026-02-05 | 2026-02-04 13:12 | 2026-02-07 | 2026-02-05 17:43 | 2026-02-06 | 2026-02-06 17:10 | 2026-02-05 | 2026-02-06 17:58 | 2026-02-07 | 2026-02-07 11:41 | 2026-02-20 | 2026-02-05 18:21 |  |  | 2026-02-13 | 2026-02-13 18:50 | 2026-02-15 | 2026-02-13 18:51 | 2026-02-16 | 2026-02-14 18:43 |  |  |  |  | 2026-02-03 | 2026-02-03 12:04 | 2026-02-04 | 2026-02-03 11:48 | Unknown | 2026-02-03 | 2026-02-03 11:46 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | [9 empty] | 2026-02-04 | 2026-02-03 11:53 | 2026-02-04 | 2026-02-03 11:54
18274 | Turnkey | 2026-01-01 | Sripriya Govindarajan / Ranganath | Govinanu jodidhar atlantis | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Banka H Suthar | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Production | Dispatch Due | 2099904 | 2099904 | 2243569 | 1710561 | 2099904 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-03 | 2026-02-03 16:35 | 2026-02-03 | 2026-03-18 18:55 | 2026-03-21 | 2026-03-20 11:24 | 2026-04-22 | 2026-04-22 16:29 | 2026-05-16 | 2026-05-19 16:23 | 2026-06-05 | 2026-06-05 15:36 | 2026-03-20 | 2026-03-20 12:07 | 2026-03-21 | 2026-03-20 12:14 | 2026-02-23 | 2026-03-20 15:00 | 2026-04-10 | 2026-04-10 13:06 |  |  |  |  | 2026-04-22 | 2026-04-27 18:17 | 2026-05-21 | 2026-05-23 00:41 | 2026-05-24 | 2026-05-23 00:42 |  |  | 2026-06-10 | 2026-06-13 17:59 | 2026-06-14 | 2026-06-14 19:43 | 2026-06-15 | 2026-06-15 19:48 | 2026-06-16 | 2026-06-17 15:05 |  |  |  |  | 2026-06-18 14:55 | 2026-07-01 | 2026-06-30 20:01 | 2026-07-13 | 2026-07-11 15:51 | 2026-07-12 | 2026-07-14 16:26 | 2026-07-11 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-14 | 2026-06-18 13:35 | 2026-04-22 | 2026-04-22 16:16 | Site is RTMI | 2026-02-03 | 2026-02-03 13:54 | 1901330 | 342239 | 1839064.8538 | 310509 | 2190849.6755 | 369900 | 2190849.6755 | 369900 | 2026-03-27 11:49:09 +0530 | Rhea Rathod | CDP: KT Pooja room - Sliding partition descoped Loft to be descoped Master bedroom - L shaped wardrobe behind the bedroom door. Existing godrej almirah to be placed inside a wardrobe. Door of the washrooom to be on the opp wall of the entrance door, Kids bedroom- Whinnie the Pooh theme. Layout to be relooked into. existing study to be accomodate Client is inclined towards pastel yellow colour- to match with the theme. Guest bedroom - L shaped wardrobe to be provided Kitchen- Layout to be relooked into as per existing services. Sink to be positioned on the right wall. Membrane kitchen was changed to british green laminate. | 2026-03-20 14:56:43 +0530 | Bency Chacko | Possession - RTMI IMs can be done Design meetings - Weekends design fees - 30th March 2026 email - sripriya.g@gmail.com - Email needs to be updated No on-site work is planned B2C - Self-funding Agreement terms are cleared Timelines are cleared checklist is cleared Offers and quotes are discussed and cleared | 2026-03-20 12:12:31 +0530 | Pradeep Kumar | Some Image was uploaded | 2026-04-23 | 2026-04-22 19:20 | 2026-05-20 | 2026-05-19 16:27 | RTMI
18275 | Turnkey | 2026-01-01 | Sanjib Das- | Purva Atmoshphere | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Affaan Abdulla | Active | Installation | Execution | 2433932 | 2433932 | 1833279 | 0 | 2498726 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-01 | 2026-02-26 12:30 | 2026-02-26 | 2026-02-26 13:31 | 2026-03-01 | 2026-02-27 13:55 | 2026-04-02 | 2026-03-30 15:41 | 2026-04-23 | 2026-04-22 18:10 | 2026-04-24 | 2026-04-24 12:28 | 2026-02-27 | 2026-02-27 14:19 | 2026-02-28 | 2026-02-28 11:53 | 2026-02-28 | 2026-03-07 18:02 | 2026-03-12 | 2026-03-12 19:00 |  |  |  |  | 2026-03-30 | 2026-03-31 12:44 | 2026-04-18 | 2026-04-18 15:28 | 2026-04-19 | 2026-04-18 15:28 |  |  | 2026-04-25 | 2026-04-29 08:12 | 2026-04-29 | 2026-04-30 17:12 | 2026-05-04 | 2026-05-03 12:26 | 2026-05-04 | 2026-05-11 16:47 |  |  |  |  | 2026-05-14 11:04 | 2026-06-01 | 2026-05-31 18:28 | 2026-06-15 | 2026-06-13 19:06 | 2026-06-14 | 2026-06-14 18:51 | 2026-06-13 | 2026-06-15 15:13 | 2026-06-16 | 2026-06-16 08:08 | 2026-06-23 | 2026-06-23 16:00 |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-05-03 | 2026-05-14 11:03 | 2026-03-13 | 2026-03-29 16:35 | Site is RTMI | 2026-02-01 | 2026-02-03 14:44 | 1994004.303 | 329229 | 0 | 0 | 2655003.9809 | 438365 | 2655003.2357 | 428481 | 2026-07-14 08:54:26 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 7-07-2026 to 14-07-2026 for your kind perusal. Project Status: Execution work Floor covering - bonito scope completed Electrification - bonito scope in progress false ceiling - Bonito scope in completed Key Dates: Modular materials dispatched -15th june Handover as per TAT- 30th July 45working days required to complete project post material dispatch to site metal fabrication received glass and mirror installation will be planned on 16th july debris cleaning planned today deep cleaning will be planned tommorrow electrical work will be planned today Key Risk [ Client ] No third party vendors are allowed to site until completion of bonito work No designs changes will be done at the time of execution Note - Ad this is priority project we are speeding up the our execution workabd we will try to finish the work as soon as possible. trying to finish all work by 18th july | 2026-06-23 10:37:46 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 2-06-2026 to 08-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scope completedElectrification - bonito scope in progressfalse ceiling - Bonito scope in completedKey Dates: Modular materials dispatched -15th juneHandover as per TAT- 30th July 45working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of executionNote - Ad this is priority project we are speeding up the our execution workabd we will try to finish the work as soon as possible | 2026-06-10 15:52:15 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 2-06-2026 to 08-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scope completedElectrification - bonito scope in progressfalse ceiling - Bonito scope in completedKey Dates: Modular materials dispatched - PH will update youHandover as per TAT- TBD45working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of executionNote - we have completed all work and site is ready for dispatch | 2026-03-31 | 2026-03-30 15:46 | 2026-04-23 | 2026-04-22 18:14
18276 | Turnkey | 2026-01-01 | Mrs.Pooja Vijay Dodeja | Raymond GS | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 4876639 | 9999 | 0 | 0 | 0 | 147 | 0 | 477665 | 487664 | 2095712 | 1805599.2 |  |  | 2026-02-18 | 2026-02-18 12:23 | 2026-02-24 | 2026-02-24 11:43 | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-03-18 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-26 |  | 2026-02-27 | [5 empty] | 2026-03-05 |  | 2026-03-13 |  | 2026-03-14 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 | [6 empty] | 2026-04-11 |  | 2026-04-20 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-23 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-03-22 |  | 2026-02-28 |  | Unknown | 2026-02-03 | 2026-02-04 18:50 | 0 | 0 | 0 | 0 | 0 | 0 | 4132745 | 743894 | 2026-02-18 12:23:43 +0530 | Shreyash Kotecha |  | 2026-02-04 12:07:06 +0530 | Shreyash Kotecha | Some Image was uploaded | 2026-02-03 17:03:37 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-05 |  | 2026-03-12
18277 | Turnkey | 2026-01-01 | Sanjay Shah | Mansarovar | MUM - GOR | Yes | Rishika Malviya | Manzoor Shaikh | Shraddha Badgujar | [5 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 1747691 | 9999 | 1747691 | 0 | 0 | 150 | 0 | 164770 | 174769 | 826770 | 571383.2 |  |  | 2026-01-31 | 2026-02-06 15:10 | 2026-02-06 | 2026-02-06 19:45 | 2026-02-09 | 2026-02-15 11:48 | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  | 2027-01-02 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 | [5 empty] | 2026-02-23 |  | 2026-03-03 |  | 2026-03-04 |  |  |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 | [6 empty] | 2026-04-01 |  | 2026-04-10 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-13 |  |  |  | 2026-05-05 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-03-12 |  | 2026-02-18 |  | Unknown | 2026-01-31 | 2026-02-03 17:29 | 1810247.1375 | 312359 | 0 | 0 | 0 | 0 | 1810247.1375 | 312359 | 2026-02-06 14:14:33 +0530 | Rishika Malviya | DCM: User ResponseLifestyle1. Please select your budget for Interior Designing? Rs. 10-15 Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? Printing industry business 4. Who will be living in this home? Nuclear Family 5. What activities do you usually perform at home? (Choose top 23) Family Bonding, Relaxing & Unwinding 6. What is your preferred entertainment style? Formal Dinners 7. Do you prefer any Smart home features? Others 8. What is your possession date? 2026-03-15 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Shoe rack, Seating Dcor & Living Room1. Choose your decor inspirations Artwork 2. Any specific signature design feature required Statement wall 3. Whats the primary use of your living room? Multipurpose 4. Any absolute no-go styles, colors, or materials? White & Shuttle colors for living /Master bedroom, Highlighting shades in Bedroom, texture paints 5. Must-have furniture or features? Sofa, TV unit, Puja unit, Display unit Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Fridge, Hob, Chimney, Dishwasher, Washing machine BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Swing Master Bedroom - Additional units Dresser, TV unit Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Swing Other Bedroom - Additional units Study table BathroomsPreferred vanity style What do you prefer? What are your requirements for Utility Area? Not Applicable Balcony & OutdoorHow do you intend to use your balcony for? I don't have a balcony b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? No Final Vision1. Any space in the home that you want to put in Spotlight? Living Room & Entrance 2. Do you want the design to reflect any personal story, cultural influence, or special memory NO | [6 empty] | 2026-02-23 |  | 2026-03-02
18278 | Turnkey | 2026-01-01 | Mr.Laxman | Preeti iska ville | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2426492 | 9999 | 0 | 0 | 0 | 112 | 0 | 232650 | 242649 | 997075 | 944118.8 |  |  | 2026-01-31 | 2026-02-08 11:12 | 2026-02-28 | 2026-03-14 10:33 | 2026-03-14 | 2026-03-25 19:46 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-01-31 | 2026-02-08 11:08 | 0 | 0 | 0 | 0 | 0 | 0 | 2056349 | 370142 | 2026-03-14 10:33:16 +0530 | Priyanka Gs | Some Image was uploaded | [6 empty] | 2026-04-02 |  | 2026-04-09
18281 | Turnkey | 2026-01-01 | Archana das | null | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Fuzail Girach |  | Active | Prospect | 10% Payment | 1419357 | 9999 | 1419357 | 0 | 0 | 114 | 0 | 131937 | 141936 | 570989 | 564496.4 |  |  | 2026-02-01 | 2026-03-18 12:09 | 2026-03-20 | 2026-03-20 12:58 | 2026-03-20 | 2026-03-20 15:09 | 2026-03-30 |  | 2026-04-06 |  | 2026-04-13 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-25 | [5 empty] | 2026-03-31 |  | 2026-04-08 |  | 2026-04-09 |  |  |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 | [6 empty] | 2026-05-07 |  | 2026-05-16 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-19 |  |  |  | 2026-06-10 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-04-17 |  | 2026-03-26 |  | Unknown | 2026-02-01 | 2026-03-05 13:17 | 1202845 | 216512 | 0 | 0 | 0 | 0 | 1202845 | 216512 | 2026-02-20 15:28:05 +0530 | Fuzail Girach | DCM: RGM for Archana Das & Sanjay Foyer - Entrance Shoe Rack, 14 pairs Living - TV 65"(Existing 50") Floating unit with flaps, wall pannel, rafters on both sides Sofa Wall - Beading with wallpaper in between Dining - One sided wall with beadings, other wall to left free, movable furnitures to procure from outside i.e Puja Unit and storage unit Washroom's - Vanity Units only Master Bedroom - Wardrobe Swing shutter, walppaper with flutted, beadings, bed side dresserÂ Master Washroom - Vanity, storage unit on top of WC BedroomÂ 2 - Entrance Dresser unit, wardrobe next to bed, Girl Theme, wallpaper with metal strips, corner study unit with upper cabinet for book storage. Bedroom 3 - wardrobe with space for existing table 3.5 ft, Guest cum Office design Kitchen - Base Unit, wall unit and cimney patta in hob side, opposite side sink area - Tall Unit with open panels for OTG and Microwave, Base units, RO unit above the sink, wall units with alluminum shutters, loft unit Utility - Storage for detergents and other accessories, try an option for sink and drainer and vanity with storage False Ceiling - Only Living unit and hallway passage. | [6 empty] | 2026-03-31 |  | 2026-04-07
18283 | Sub Project |  | Shailesh Wavdhane | Lodha AMara | MUM - Thane |  | Naved Malik |  | Sneha Kadam |  |  | Vinay Bulani | Aditya Vikram | Murali S |  |  | Active | Handover | Project Closure Pending | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-04 | 2026-02-04 18:17 | 2026-02-05 | 2026-02-04 18:17 | 2026-02-04 | 2026-02-04 18:18 | 2026-02-05 | 2026-02-04 18:20 | 2026-02-05 | 2026-02-04 18:22 | 2026-02-05 | 2026-02-04 18:25 | 2026-02-04 | 2026-02-04 18:18 | 2026-02-05 | 2026-02-04 18:19 | 2026-02-04 | 2026-02-04 18:19 | 2026-02-05 | 2026-02-04 18:19 |  |  |  |  | 2026-02-04 | 2026-02-04 18:20 | 2026-02-05 | 2026-02-04 18:23 | 2026-02-05 | 2026-02-04 18:23 |  |  | 2026-02-05 | 2026-02-05 11:37 | 2026-02-06 | 2026-02-05 11:38 | 2026-02-06 | 2026-02-05 11:40 | 2026-02-06 | 2026-02-05 11:40 |  |  |  |  | 2026-02-05 11:41 | 2026-02-11 | 2026-02-10 19:09 | 2026-02-12 | 2026-02-10 19:35 | 2026-02-11 | 2026-02-24 19:18 | 2026-02-10 | 2026-03-04 14:40 | 2026-03-04 | 2026-03-04 14:40 | 2026-03-21 | 2026-03-20 15:40 |  |  | 2026-03-22 | 2026-03-20 15:47 | 2026-03-22 | 2026-03-20 16:30 | 2026-03-20 | 2026-03-20 16:46 |  |  |  |  | 2026-02-05 | 2026-02-05 11:40 | 2026-02-05 | 2026-02-04 18:19 | Unknown | 2026-02-04 | 2026-02-04 18:17 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | [9 empty] | 2026-02-05 | 2026-02-04 18:20 | 2026-02-05 | 2026-02-04 18:22
18287 | Sub Project |  | Dipti Khetam | VistaOne | MUM - GOR |  | Shweta Dalvi |  | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-05 | 2026-02-05 15:46 | 2026-02-06 | 2026-02-05 15:46 | 2026-02-05 | 2026-02-05 15:47 | 2026-02-06 | 2026-02-05 15:48 | 2026-02-06 | 2026-02-05 15:50 | 2026-02-06 | 2026-02-05 15:56 | 2026-02-05 | 2026-02-05 15:47 | 2026-02-06 | 2026-02-05 15:47 | 2026-02-05 | 2026-02-05 15:47 | 2026-02-06 | 2026-02-05 15:48 |  |  |  |  | 2026-02-05 | 2026-02-05 15:49 | 2026-02-06 | 2026-02-05 15:52 | 2026-02-06 | 2026-02-05 15:52 |  |  | 2026-02-06 | 2026-02-05 15:57 | 2026-02-06 | 2026-02-05 15:58 | 2026-02-06 | 2026-02-06 13:13 | 2026-02-07 | 2026-02-06 13:13 |  |  |  |  | 2026-02-06 14:20 | 2026-02-06 | 2026-02-05 16:13 | 2026-02-26 | 2026-02-23 11:54 | 2026-02-06 | 2026-02-05 16:15 | 2026-02-23 | 2026-02-23 14:17 | 2026-02-24 | 2026-02-25 08:24 | 2026-02-26 | 2026-02-25 10:41 |  |  | 2026-02-27 | 2026-02-25 11:03 | 2026-02-27 | 2026-02-25 11:03 | 2026-02-25 | 2026-02-25 13:08 |  |  |  |  | 2026-02-05 | 2026-02-05 15:58 | 2026-02-06 | 2026-02-05 15:48 | Unknown | 2026-02-05 | 2026-02-05 15:46 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | [9 empty] | 2026-02-06 | 2026-02-05 15:48 | 2026-02-06 | 2026-02-05 15:50
18291 | Turnkey | 2026-01-01 | Raghavendra Kulkarni | Kalpataru Magnus | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Shantanu Parakh | [5 empty] | Mrunali Mitkari | Vinay Surve | Lost | Preproduction | DEM2 | 1348202 | 269641 | 1738588 | 0 | 0 | 86 | 19 | 0 | 0 | 539280 | 539280.8 |  |  | 2026-02-05 | 2026-02-05 18:28 | 2026-02-08 | 2026-02-11 13:21 | 2026-02-14 | 2026-02-11 13:25 | 2026-03-29 | 2026-03-29 18:58 | 2026-04-05 | 2026-04-04 15:59 | 2026-05-20 |  | 2026-02-08 | 2026-02-10 16:00 | 2026-02-12 | 2026-02-11 13:27 | 2026-02-11 | 2026-02-12 14:36 | 2026-02-20 | 2026-02-20 17:25 |  |  |  |  | 2026-03-29 | 2026-04-01 17:50 | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-02-21 | 2026-03-04 12:12 | Site is RTMI | 2026-02-05 | 2026-02-05 18:22 | 1473379 | 265208 | 0 | 0 | 0 | 0 | 1452071.5375 | 236166 | 2026-06-10 11:37:31 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-28 20:29:45 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-27 18:18:31 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-30 | 2026-03-29 19:14 | 2026-04-05 | 2026-04-27 17:41
18293 | Turnkey | 2026-01-01 | Ankit Kulkarni | Edifice | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1133387 | 9999 | 1263490 | 0 | 0 | 153 | 0 | 103340 | 113339 | 457594 | 449116 |  |  | 2026-02-05 | 2026-02-06 13:36 | 2026-02-11 | 2026-02-10 22:45 | 2026-02-16 | 2026-02-16 20:05 | 2026-02-23 |  | 2026-03-02 |  | 2026-03-09 |  | 2026-02-16 |  | 2026-02-17 |  | 2026-02-17 |  | 2026-02-18 | [5 empty] | 2026-02-24 |  | 2026-03-04 |  | 2026-03-05 |  |  |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-15 | [6 empty] | 2026-04-02 |  | 2026-04-11 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-14 |  |  |  | 2026-05-06 |  | 2026-05-08 |  | 2026-05-09 | [5 empty] | 2026-03-13 |  | 2026-02-19 |  | Unknown | 2026-02-05 | 2026-02-06 13:33 | 1070754 | 192735 | 0 | 0 | 0 | 0 | 960497 | 172889 | [9 empty] | 2026-02-24 |  | 2026-03-03
18294 | Turnkey | 2026-01-01 | gopal kakadia | Transcon Triumph | MUM - GOR | No Estimate | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 158 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-01-22 | 2026-02-07 11:43 | 2026-01-23 |  | 2026-02-06 |  | 2026-02-13 |  | 2026-02-20 |  | 2026-02-27 |  | 2026-02-06 |  | 2026-02-07 |  | 2026-02-07 |  | 2026-02-08 | [5 empty] | 2026-02-14 |  | 2026-02-22 |  | 2026-02-23 |  |  |  | 2026-03-02 |  | 2026-03-03 |  | 2026-03-04 |  | 2026-03-05 | [6 empty] | 2026-03-23 |  | 2026-04-01 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-04 |  |  |  | 2026-04-26 |  | 2026-04-28 |  | 2026-04-29 | [5 empty] | 2026-03-03 |  | 2026-02-09 |  | Unknown | 2026-01-22 | 2026-02-07 11:19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-02-14 |  | 2026-02-21
18296 | Turnkey | 2026-01-01 | Shruti Sarang | Aditya Raj | MUM - Thane | Yes | Mayuri Patil | [7 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 1450456 | 9999 | 1450456 | 0 | 0 | 145 | 0 | 135047 | 145046 | 612638 | 547726.8 |  |  | 2026-02-06 | 2026-02-06 18:15 | 2026-02-07 | 2026-02-07 10:33 | 2026-02-10 | 2026-02-20 15:29 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-06 | 2026-02-06 18:13 | 1229200 | 221256 | 0 | 0 | 0 | 0 | 1229200 | 221256 | 2026-02-07 10:33:57 +0530 | Mayuri Patil | MINUTES OF MEETING (MOM)Client Name: Shruti Sarang Contact No.: 18296 Property Location: Aditya Raj, Vikhroli Carpet Area: 399 sq. ft. Occupancy: 4 Members Profession: Automobile Engineer (Dubai) Possession Timeline: End of February (OC expected) Meeting ObjectiveDiscussion on interior design requirements, scope of work, and tentative budget planning for the residential apartment. Client Requirements & Scope of Work1. Living & Dining AreaShoe rack unit with safety doorDining table for 4-seaters (2+2 seating configuration)Mandir unitTV unit (TV size: 40 inches)3-seater sofaL-shaped sofa with drawer storageWall moulding design with feminine & luxury theme3 photo frames to be installed in living room3 hanging decorative lights2. KitchenPlatform change: Not requiredBase units and wall unitsLoft storageMicrowave unit (roller shutter type)3. BedroomWardrobe with loft storage1 Queen-size bed1 Single bedFoldable study unit4. Bathrooms / WashroomsCivil and plumbing work (Indian toilet)Vanity units 2 Nos.Washroom sunroof false ceilingHidden portable partition near door5. Common WorksFalse ceilingPaintingElectrical workTentative Budget10 12 Lakhs | [6 empty] | 2026-02-28 |  | 2026-03-07
18301 | Turnkey | 2026-01-01 | Dipti Pramodrao Mohod | Raymond Tenex | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 1035175 | 120999 | 1203373 | 0 | 0 | 102 | 51 | 0 | 86036 | 414070 | 414070 |  |  | 2026-02-07 | 2026-02-09 18:41 | 2026-02-10 | 2026-02-10 11:23 | 2026-02-10 | 2026-02-10 21:02 | 2027-09-26 |  | 2027-10-03 |  | 2027-10-10 |  | 2026-02-10 | 2026-02-11 12:29 | 2026-02-11 | 2026-02-11 23:55 | 2026-02-11 | 2026-02-12 16:50 | 2026-02-26 | 2026-02-26 17:29 |  |  |  |  | 2027-09-27 |  | 2027-10-05 |  | 2027-10-06 |  |  |  | 2027-10-13 |  | 2027-10-14 |  | 2028-02-03 |  | 2028-02-04 | [6 empty] | 2028-02-22 |  | 2028-03-02 |  | 2028-03-01 |  | 2028-03-02 |  | 2028-03-03 |  | 2028-03-05 |  |  |  | 2028-03-27 |  | 2028-03-29 |  | 2028-03-30 | [5 empty] | 2028-02-02 |  | 2026-04-14 | 2026-03-05 11:56 | Site is RTMI | 2026-02-07 | 2026-02-09 18:39 | 1019807 | 183565 | 0 | 0 | 0 | 0 | 1127601.94 | 180789 | 2026-07-08 12:36:48 +0530 | Nishtha Valawalkar | At the time of closure, cx was aligned with the scope of wor where painting, false celling and electrification they will get done from their vendor. However, DEM is done. Now cx dont want it. | 2026-06-26 16:28:54 +0530 | Shraddha Pansare | RCA - RCA - She had 2 meetings for DEM 1 stage, she selected materials as well so that she will get a proper quote at this stage. She was reluctant to pay money. Post final quote, there was an increase of approx 1.5 lakhs. Hence she refused to pay the DEM 1 amount | 2026-04-30 12:50:31 +0530 | Anil Jagtap | CX has raised the cancellation with Bonito, and she has already contacted Nishtha and Prashant. She has spoken with them | 2027-09-27 |  | 2027-10-04
18302 | Turnkey | 2026-01-01 | Bahubali | Visista By Vista Spaces Okas | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | [5 empty] | Raghavendra S |  | Active | Preproduction | DEM2 | 1468402 | 289065 | 1917771 | 0 | 0 | 61 | 25 | 0 | 0 | 617771 | 561566.4 |  |  | 2026-02-07 | 2026-02-08 11:39 | 2026-02-14 | 2026-02-14 17:42 | 2026-03-30 | 2026-03-30 14:09 | 2026-04-12 | 2026-04-12 13:08 | 2026-07-10 |  | 2026-08-07 |  | 2026-03-30 | 2026-03-30 23:31 | 2026-03-31 | 2026-04-02 12:52 | 2026-04-02 | 2026-04-04 13:57 | 2026-04-11 | 2026-04-11 14:11 |  |  |  |  | 2026-04-12 | 2026-04-20 14:57 | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-04-12 | 2026-04-12 10:50 | Site is RTMI | 2026-02-07 | 2026-02-07 17:54 | 1625229 | 292541 | 0 | 0 | 0 | 0 | 1539715.3784 | 254235 | 2026-04-11 14:10:43 +0530 | Parasa Sri | Welcome call done. The site is not ready for initial measurement and will be ready at month end. meeting availability is on weekends. | 2026-04-10 13:39:00 +0530 | Alekhya Korada | Some Image was uploaded | 2026-04-04 13:57:55 +0530 | Bency Chacko | Possession - May - June 2026 IMs can't be done - The customer will check and get back, but access will be given to the sample flats He can close the 10% after the LFM is closed (15th April 2027) No on-site work is planned No civil work is planned Agreements are cleared Timelines are cleared B2C - Self-funded | 2026-04-13 | 2026-04-12 13:21 | 2026-07-11 |  | Under Construction | 2026-06-30
18303 | Turnkey | 2026-01-01 | Arpita Samala | Valmark Cityville | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | 10% Payment | 3501138 | 9999 | 3501138 | 0 | 0 | 138 | 0 | 340115 | 350114 | 1428284 | 1372626 |  |  | 2026-02-07 | 2026-02-07 15:04 | 2026-02-07 | 2026-02-13 11:09 | 2026-02-27 | 2026-02-27 13:17 | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-02-27 |  | 2026-02-28 |  | 2026-02-28 |  | 2026-03-01 | [5 empty] | 2026-03-07 |  | 2026-03-15 |  | 2026-03-16 |  |  |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 | [6 empty] | 2026-04-13 |  | 2026-04-22 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-25 |  |  |  | 2026-05-17 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-03-24 |  | 2026-03-02 |  | Unknown | 2026-02-07 | 2026-02-07 15:03 | 2967066 | 534071 | 0 | 0 | 0 | 0 | 2967066 | 534071 | [9 empty] | 2026-03-07 |  | 2026-03-14
18304 | Turnkey | 2026-01-01 | Vijay Mhatre | Ashar | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [7 empty] | Hold | Preproduction | Site Readiness 1 | 1216442 | 214659 | 1356607 | 0 | 0 | 2 | 104 | 0 | 0 | 538653 | 463130.4 |  |  | 2026-02-07 | 2026-02-07 14:56 | 2026-02-07 | 2026-02-08 16:36 | 2026-02-14 | 2026-02-14 19:42 | 2026-03-31 | 2026-03-31 14:50 | 2026-11-26 |  | 2026-12-03 |  | 2026-02-14 | 2026-02-16 18:06 | 2026-02-15 | 2026-02-18 08:25 | 2026-02-18 | 2026-02-19 16:15 | 2026-02-26 | 2026-02-26 18:04 |  |  |  |  | 2026-03-31 | 2026-03-31 15:01 | 2026-11-28 |  | 2026-11-29 |  |  |  | 2026-12-06 |  | 2026-12-07 |  | 2026-12-08 |  | 2026-12-09 | [6 empty] | 2026-12-27 |  | 2027-01-05 |  | 2027-01-04 |  | 2027-01-05 |  | 2027-01-06 |  | 2027-01-08 |  |  |  | 2027-01-30 |  | 2027-02-01 |  | 2027-02-02 | [5 empty] | 2026-12-07 |  | 2026-05-12 | 2026-03-31 14:01 | Site is Non-RTMI | 2026-02-07 | 2026-02-07 14:55 | 1149667 | 206940 | 0 | 0 | 0 | 0 | 1234555.9472 | 208440 | 2026-07-14 17:37:07 +0530 | Divya Rahangdale | Client will receive possession by the end of October. | 2026-06-29 13:56:09 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: Possession is delayed for 3 months because site is not ready | 2026-04-30 13:23:37 +0530 | Anil Jagtap | cx will receive possession by 1st week of June | 2026-04-01 | 2026-03-31 14:54 | 2026-11-27
18305 | Turnkey | 2026-01-01 | Raju Khairnar | Raymond GS | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Aryan Singh |  | Hold | Preproduction | CM | 2011964 | 402163 | 2521640 | 0 | 0 | 0 | 80 | 0 | 0 | 862918 | 746883.2 |  |  | 2026-02-07 | 2026-02-08 22:35 | 2026-02-15 | 2026-02-17 10:47 | 2026-02-20 | 2026-02-19 19:43 | 2026-04-07 | 2026-04-07 16:38 | 2026-08-06 |  | 2026-07-20 |  | 2026-02-19 | 2026-02-21 15:17 | 2026-02-20 | 2026-02-21 17:08 | 2026-02-21 | 2026-02-26 16:57 | 2026-02-27 | 2026-02-27 15:08 |  |  |  |  | 2026-05-15 | 2026-04-09 10:40 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-04-30 | 2026-04-07 16:35 | Site is Non-RTMI | 2026-02-07 | 2026-02-07 23:24 | 2136983 | 384656 | 0 | 0 | 0 | 0 | 2135915.076 | 352672 | 2026-07-10 14:09:53 +0530 | Anil Jagtap | cx will receive the possession by 16th July 2026 | 2026-05-08 12:32:06 +0530 | Anamika Dolai | Some Image was uploaded | 2026-04-07 15:46:05 +0530 | Pooja Metre | Some Image was uploaded | 2026-04-08 | 2026-04-07 16:40 | 2026-08-07 |  | Under Construction | 2026-04-01
18306 | Turnkey | 2026-01-01 | Abhijit Bhasme (Gauri Bhasme) | Veena Synergy | MUM - GOR | Yes | Saif Shaikh | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Design | DEM1 | 1678576 | 209999 | 1684030 | 0 | 0 | 6 | 122 | 0 | 125716 | 725190 | 617670.8 |  |  | 2026-02-07 | 2026-02-07 16:17 | 2026-02-17 | 2026-02-17 11:36 | 2026-03-02 | 2026-03-02 09:19 | 2027-01-24 |  | 2027-01-31 |  | 2027-02-07 |  | 2026-03-02 | 2026-02-28 | 2026-03-03 | 2026-03-04 11:21 | 2026-03-04 | 2026-03-09 13:42 | 2026-03-13 | 2026-03-13 17:24 |  |  |  |  | 2027-01-25 |  | 2027-02-02 |  | 2027-02-03 |  |  |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-12 |  | 2027-02-13 | [6 empty] | 2027-03-03 |  | 2027-03-12 |  | 2027-03-11 |  | 2027-03-12 |  | 2027-03-13 |  | 2027-03-15 |  |  |  | 2027-04-06 |  | 2027-04-08 |  | 2027-04-09 | [5 empty] | 2027-02-11 |  | 2027-01-20 |  | Unknown | 2026-02-07 | 2026-02-07 16:16 | 1826592.176 | 306462 | 0 | 0 | 0 | 0 | 1820526.176 | 305630 | 2026-05-27 11:29:21 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-24 15:20:56 +0530 | Meet Shah | Some Image was uploaded | 2026-03-15 11:02:49 +0530 | Manzoor Shaikh | Some Image was uploaded | 2027-01-25 |  | 2027-02-01 |  | Under Construction | 2026-12-01
18307 | Turnkey | 2026-01-01 | Kishor Dang | ajmera ivera | MUM - GOR | Yes | Pratima Kajwe |  | Shraddha Badgujar | [5 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 970144 | 9999 | 970144 | 0 | 0 | 136 | 0 | 87015 | 97014 | 392296 | 383818.8 |  |  | 2026-02-07 | 2026-02-16 14:53 | 2026-02-20 | 2026-02-20 16:16 | 2026-03-01 | 2026-03-01 14:18 | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-03 | [5 empty] | 2026-03-09 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-28 | [6 empty] | 2026-04-15 |  | 2026-04-24 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-27 |  |  |  | 2026-05-19 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-03-26 |  | 2026-03-04 |  | Unknown | 2026-02-07 | 2026-02-16 14:52 | 822156 | 147988 | 0 | 0 | 0 | 0 | 822156 | 147988 | 2026-02-19 14:43:27 +0530 | Pratima Kajwe | DCM: MOM Living room Partition position on the left along with shoe-rack. Keeping 2 options for mandir, Facing towards entrance and facing towards kitchen. Kitchen. Revamping of kitchen through-out. reference of EC with pantry unit and storage. Master bedroom Folding study table next to door opening Full wardrobe to be added Kids room Design elements. Storage space above study table. | [6 empty] | 2026-03-09 |  | 2026-03-16
18308 | Turnkey | 2026-01-01 | Mr. SIVARAMAKRISHNAN IYER | Assetz Marq | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Mohammed Rasick |  | Hold | Preproduction | Site Readiness 1 | 2056700 | 411340 | 1933718 | 0 | 0 | 2 | 50 | 0 | 0 | 867727 | 777633.2 |  |  | 2026-02-07 | 2026-02-19 12:09 | 2026-02-08 | 2026-02-19 12:55 | 2026-03-05 | 2026-03-05 14:57 | 2026-05-24 | 2026-05-24 15:54 | 2026-07-05 |  | 2026-08-21 |  | 2026-03-05 | 2026-02-28 | 2026-03-06 | 2026-03-17 15:27 | 2026-03-17 | 2026-03-20 14:33 | 2026-03-24 | 2026-03-25 12:17 |  |  |  |  | 2026-05-25 | 2026-05-24 15:56 | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-04-16 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-03-26 | 2026-05-02 18:01 | Site is Non-RTMI | 2026-02-07 | 2026-02-07 16:54 | 2017416.8394 | 333109 | 0 | 0 | 0 | 0 | 2149504.3386 | 354920 | 2026-04-23 18:54:23 +0530 | Yogesh B | Some Image was uploaded | 2026-04-17 17:24:02 +0530 | Rajeshwari S | Some Image was uploaded | 2026-03-25 12:48:19 +0530 | Priyanka Gs | CDP MOM 1. Foyer AreaThe client requested additional storage with drawers to be incorporated within the foyer unit for improved functionality. Change implemented as discussed. 2. Living RoomTV UnitA double tall unit configuration was confirmed.The TV panel dimensions were adjusted and reduced to align proportionally with the tall units for a balanced elevation. Revised design accepted by the client. Crockery UnitThe model of the crockery unit was changed based on the clients requirement and preference.3.Kitchen Planning for dishwasher placement was discussed and will be incorporated into the kitchen layout during detailed design and service planning. To be finalized during design development stage. 4. Master BedroomThe client confirmed that they will not proceed with Aristo wardrobes.A swing wardrobe system was finalized instead. 5. Parents BedroomDue to limited storage availability, the client prefers an endtoend wardrobe.The previously proposed study unit is to be removed to accommodate maximum wardrobe storage. Layout revised accordingly and accepted. 6. Guest BedroomWardrobe width to be increased to improve storage capacity. Design updated as per discussion. 7. False Ceiling & ElectricalFalse ceiling scope was initially added to the quotation and later removed as per client decision.Electrical work will be addressed and finalized during crossmeasurement stage, based on site conditions. Scope clarity noted and acknowledged. Wardrobe Internals All wardrobe internal configurations were shown to the client for understanding. The client is informed that; Internals can be personalized further during the design phase Any additional drawers may impact the final cost Painting - Cx Scope | 2026-05-25 | 2026-05-24 15:56 | 2026-07-06
18309 | Turnkey | 2026-01-01 | Anand Desai | Lodha amara | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  |  | Tanveer Patel | Akshat Shrivastava | Murali S | Saloni Chawan | Prasad Bhivaji Hande | Active | Installation | Execution | 1754398 | 1754399 | 1549646 | 0 | 1758860 | 30 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-07 | 2026-02-07 17:19 | 2026-02-10 | 2026-02-17 15:36 | 2026-02-18 | 2026-02-18 19:07 | 2026-03-18 | 2026-03-18 11:24 | 2026-04-09 | 2026-04-08 17:18 | 2026-04-16 | 2026-04-15 11:28 | 2026-02-15 | 2026-02-16 19:23 | 2026-02-16 | 2026-02-17 12:35 | 2026-02-21 | 2026-02-17 16:42 | 2026-02-20 | 2026-02-20 14:51 |  |  |  |  | 2026-03-18 | 2026-03-18 14:49 | 2026-04-09 | 2026-04-09 18:40 | 2026-04-10 | 2026-04-09 19:57 |  |  | 2026-04-16 | 2026-04-24 12:58 | 2026-04-27 | 2026-04-27 11:41 | 2026-04-28 | 2026-04-27 20:11 | 2026-04-28 | 2026-04-30 18:40 |  |  |  |  | 2026-05-07 12:09 | 2026-05-16 | 2026-05-15 22:50 | 2026-05-30 | 2026-05-31 18:55 | 2026-06-02 | 2026-06-05 16:39 | 2026-05-31 | 2026-06-10 20:28 | 2026-05-29 | 2026-06-15 20:57 | 2026-06-18 | 2026-06-19 18:31 |  |  | 2026-06-30 |  | 2026-06-30 |  | 2026-07-10 | [5 empty] | 2026-04-27 | 2026-05-07 12:08 | 2026-03-12 | 2026-03-14 18:17 | Site is RTMI | 2026-02-07 | 2026-02-07 17:08 | 1630557.9747 | 266895 | 0 | 0 | 1909625.7096 | 314063 | 1910331.9596 | 314145 | 2026-06-23 00:25:05 +0530 | Tanveer Patel | Execution: furniture delivered on 15th junemodular team is allign on 23rd june | 2026-06-15 23:45:57 +0530 | Tanveer Patel | Procurement: furniture delivered on 15th june | 2026-06-04 21:58:37 +0530 | Asif Shaikh | Execution: Site is ready for dispatched | 2026-03-19 | 2026-03-18 11:25 | 2026-04-09 | 2026-04-08 17:19
18312 | Turnkey | 2026-01-01 | Dr. Jyoti Saigaonkar | Piramal | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Mustufa Sohagpurwala |  | Hold | Preproduction | Site Readiness 1 | 1050792 | 210179 | 1241781 | 0 | 0 | 1 | 97 | 0 | 0 | 438048 | 402565.2 |  |  | 2026-02-07 | 2026-02-07 17:45 | 2026-02-26 | 2026-02-26 17:51 | 2026-02-28 | 2026-02-28 21:14 | 2026-07-08 | 2026-04-08 17:41 | 2026-07-15 |  | 2026-07-22 |  | 2026-02-28 | 2026-02-28 | 2026-03-01 | 2026-03-06 11:35 | 2026-03-06 | 2026-03-09 14:50 | 2026-03-10 | 2026-03-10 14:20 |  |  |  |  | 2026-07-20 | 2026-03-25 18:25 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-07-04 | 2026-04-08 17:33 | Site is RTMI | 2026-02-07 | 2026-02-07 17:44 | 1052357 | 189424 | 0 | 0 | 0 | 0 | 1034649.8982 | 184697 | 2026-07-10 14:05:37 +0530 | Anil Jagtap | cx will receive the possession by 1st week of August*2026 | 2026-04-02 14:16:17 +0530 | Pooja Metre | Some Image was uploaded | 2026-03-24 15:00:09 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-04-09 | 2026-04-08 17:52 | 2026-07-16 |  | Under Construction | 2026-06-01
18316 | Turnkey | 2026-01-01 | Sandeep Kumar Gupta | Sobha Royal Pavilion | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP |  |  | Yogeshwaran | Ranjith Kumar |  | Chanakya Panigrahi |  | Lost | Design | DEM1 | 2527374 | 213466 | 2134658 | 0 | 0 | 142 | 0 | 0 | 292009 | 1102634 | 919265.2 |  |  | 2026-02-07 | 2026-02-08 11:10 | 2026-02-10 | 2026-02-10 19:16 | 2026-02-23 | 2026-02-23 09:58 | 2027-02-01 |  | 2027-02-08 |  | 2027-02-15 |  | 2026-02-23 | 2026-02-23 14:37 | 2026-02-24 | 2026-02-23 14:42 | 2026-02-23 | 2026-02-23 17:19 | 2026-02-24 | 2026-02-24 19:40 |  |  |  |  | 2027-02-02 |  | 2027-02-10 |  | 2027-02-11 |  |  |  | 2027-02-18 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-21 | [6 empty] | 2027-03-11 |  | 2027-03-20 |  | 2027-03-19 |  | 2027-03-20 |  | 2027-03-21 |  | 2027-03-23 |  |  |  | 2027-04-14 |  | 2027-04-16 |  | 2027-04-17 | [5 empty] | 2027-02-19 |  | 2026-02-25 | 2026-03-04 15:52 | Site is RTMI | 2026-02-07 | 2026-02-08 11:05 | 1809033 | 325625 | 0 | 0 | 0 | 0 | 2612119.7847 | 431294 | 2026-06-28 19:43:12 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-30 15:14:49 +0530 | Patil Madhavi | Some Image was uploaded | 2026-03-24 14:54:04 +0530 | Muskan Agarwal | Some Image was uploaded | 2027-02-02 |  | 2027-02-09
18317 | Turnkey | 2026-01-01 | Chaitra | RR wishtales | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | 10% Payment | 960851 | 119999 | 1187358 | 0 | 0 | 146 | 0 | 0 | 72171 | 384340 | 384340.4 |  |  | 2026-02-07 | 2026-02-08 11:30 | 2026-02-13 | 2026-02-13 22:42 | 2026-02-16 | 2026-02-19 13:12 | 2026-02-26 |  | 2026-03-05 |  | 2026-03-12 |  | 2026-02-19 | 2026-02-28 | 2026-02-20 |  | 2026-02-20 |  | 2026-02-21 | [5 empty] | 2026-02-27 |  | 2026-03-07 |  | 2026-03-08 |  |  |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 | [6 empty] | 2026-04-05 |  | 2026-04-14 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-17 |  |  |  | 2026-05-09 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-03-16 |  | 2026-02-22 |  | Unknown | 2026-02-07 | 2026-02-07 18:34 | 1006236 | 181122 | 0 | 0 | 0 | 0 | 1000343.196 | 165180 | 2026-03-13 10:30:55 +0530 | Kushal S | Some Image was uploaded | 2026-02-15 18:24:33 +0530 | Keerthan M | CDP: Living Partition design need to be changed, reference will be shared during design stage.Pooja unit will be procured from outside.Vanity unit - wall, stone cladding need to be doneTV back panel, 4*8 tile has been suggested.MBR wall highlight, Wainscoting need to be considered. PBR Remove Study and extend wardrobewall highlight go with cement texture, grey theme Bedroom 3 give wooden theme and give similar design as per referencemove W?B to opposite wall and add study unit near window. | 2026-02-12 10:55:34 +0530 | Keerthan M | Based on <10-2-2026> meeting, below is a list of all the requirements that were discussed during the meeting: 3BHK Budget 8-10L 3people going to stay Foyer Partition. Living TV unit Pooja unit near kitchen Dining table near to MBR door wall Vanity unit entrance panelling Kitchen Bottom unit top storage loft Utility Sink unit W/M space MBR Wardrobe hinged Study table opposite to bed Wall detailing PBR Wardrobe Study table Wall detailing Bedroom 3 Wardrobe Study table wall detailing Note: False ceiling in common area and MBR | 2026-02-27 |  | 2026-03-06
18318 | Turnkey | 2026-01-01 | Lijo John | JRC Wild Woods | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 4439777 | 9999 | 0 | 0 | 0 | 158 | 0 | 433979 | 443978 | 1815780 | 1736041.2 |  |  | 2026-02-07 | 2026-02-07 18:44 | 2026-02-07 | 2026-02-08 11:38 | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 | [5 empty] | 2026-03-01 |  | 2026-03-09 |  | 2026-03-10 |  |  |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 | [6 empty] | 2026-04-07 |  | 2026-04-16 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-19 |  |  |  | 2026-05-11 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-03-18 |  | 2026-02-24 |  | Unknown | 2026-02-07 | 2026-02-07 18:42 | 0 | 0 | 0 | 0 | 0 | 0 | 3762523 | 677254 | [9 empty] | 2026-03-01 |  | 2026-03-08
18320 | Turnkey | 2026-01-01 | San Industrial Goods Private Limited | Raymond GS | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Saloni Chawan |  | Hold | Design | DEM1 | 2150005 | 430001 | 2698725 | 0 | 0 | 67 | 66 | 0 | 0 | 883232 | 836772.4 |  |  | 2026-02-07 | 2026-02-07 19:22 | 2026-02-21 | 2026-02-20 23:57 | 2026-02-24 | 2026-02-24 13:29 | 2026-10-09 |  | 2026-10-16 |  | 2026-10-23 |  | 2026-02-24 | 2026-02-28 11:55 | 2026-02-25 | 2026-03-02 18:51 | 2026-03-02 | 2026-03-04 12:03 | 2026-03-05 | 2026-03-05 11:36 |  |  |  |  | 2026-04-10 | 2026-04-01 17:27 | 2026-10-18 |  | 2026-10-19 |  |  |  | 2026-10-26 |  | 2026-10-27 |  | 2026-10-28 |  | 2026-10-29 | [6 empty] | 2026-11-16 |  | 2026-11-25 |  | 2026-11-24 |  | 2026-11-25 |  | 2026-11-26 |  | 2026-11-28 |  |  |  | 2026-12-20 |  | 2026-12-22 |  | 2026-12-23 | [5 empty] | 2026-10-27 |  | 2026-09-30 |  | Unknown | 2026-02-07 | 2026-02-07 19:18 | 2287055 | 411670 | 0 | 0 | 0 | 0 | 2221670.4356 | 366102 | 2026-06-30 11:36:49 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-27 18:52:18 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-06-02 10:33:41 +0530 | Anil Jagtap | Some Image was uploaded | 2026-10-10 |  | 2026-10-17 |  | Under Construction | 2026-04-01
18321 | Turnkey | 2026-01-01 | Mrs.Sakambhari Nayak | SOBHA Dream Acres | BNG - HSR | Yes | Nayan Reddy |  | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 1245094 | 9999 | 0 | 0 | 0 | 158 | 0 | 114510 | 124509 | 519398 | 476676.8 |  |  | 2026-02-07 | 2026-02-07 19:47 | 2026-02-10 | 2026-02-10 18:58 | 2026-02-14 |  | 2026-02-20 |  | 2026-02-27 |  | 2026-03-06 |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-15 | [5 empty] | 2026-02-21 |  | 2026-03-01 |  | 2026-03-02 |  |  |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 | [6 empty] | 2026-03-30 |  | 2026-04-08 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-11 |  |  |  | 2026-05-03 |  | 2026-05-05 |  | 2026-05-06 | [5 empty] | 2026-03-10 |  | 2026-02-16 |  | Unknown | 2026-02-07 | 2026-02-07 19:47 | 0 | 0 | 0 | 0 | 0 | 0 | 1055164 | 189929 | [9 empty] | 2026-02-21 |  | 2026-02-28
18322 | Turnkey | 2026-01-01 | SANJAY M TORASKAR | bhoomi pratishtha | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Rajkumar Suthar | Sandeep Tiwari | Murali S | Rashmita Das | Aakash Gaikwad | Active | Installation | Execution | 1013160 | 1013160 | 938176 | 0 | 1013160 | 22 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-07 | 2026-02-16 14:54 | 2026-02-14 | 2026-02-17 11:21 | 2026-02-20 | 2026-02-19 11:47 | 2026-03-12 | 2026-03-12 18:15 | 2026-03-26 | 2026-03-31 19:49 | 2026-05-14 | 2026-05-14 17:26 | 2026-02-19 | 2026-02-19 17:09 | 2026-02-20 | 2026-02-20 22:31 | 2026-02-20 | 2026-02-25 16:58 | 2026-03-05 | 2026-03-05 17:41 |  |  |  |  | 2026-03-12 | 2026-03-07 12:16 | 2026-04-14 | 2026-04-14 15:20 | 2026-04-15 | 2026-04-14 15:21 |  |  | 2026-05-03 | 2026-05-14 20:08 | 2026-05-14 | 2026-05-14 20:41 | 2026-05-15 | 2026-05-14 23:50 | 2026-05-16 | 2026-05-14 18:57 |  |  |  |  | 2026-05-16 12:32 | 2026-05-31 | 2026-05-30 20:57 | 2026-06-18 | 2026-06-17 19:32 | 2026-06-17 | 2026-06-11 18:39 | 2026-06-17 | 2026-06-18 23:02 | 2026-06-18 | 2026-06-23 13:58 | 2026-06-25 | 2026-07-11 13:10 |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-05-14 | 2026-05-16 12:31 | 2026-03-06 | 2026-03-12 18:11 | Site is RTMI | 2026-02-07 | 2026-02-07 19:31 | 1059887.244 | 165992 | 0 | 0 | 1129129.216 | 177431 | 1129129.216 | 177431 | 2026-07-09 16:05:51 +0530 | Manzoor Shaikh |  | 2026-07-09 16:03:59 +0530 | Manzoor Shaikh | Others: | 2026-07-09 16:01:00 +0530 | Manzoor Shaikh |  | 2026-03-13 | 2026-03-25 18:18 | 2026-04-01 | 2026-03-31 19:51
18323 | Turnkey | 2026-01-01 | Pramod Pandey | Dheeraj dreams | MUM - Thane | Yes | Pooja Nakul Sharma | [7 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 1836802 | 9999 | 0 | 0 | 0 | 155 | 0 | 173681 | 183680 | 776717 | 692724.8 |  |  | 2026-02-07 | 2026-02-10 12:10 | 2026-02-08 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-08 | [5 empty] | 2026-03-14 |  | 2026-03-22 |  | 2026-03-23 |  |  |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 | [6 empty] | 2026-04-20 |  | 2026-04-29 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-02 |  |  |  | 2026-05-24 |  | 2026-05-26 |  | 2026-05-27 | [5 empty] | 2026-03-31 |  | 2026-03-09 |  | Unknown | 2026-02-07 | 2026-02-10 12:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1556612 | 280190 | 2026-02-13 11:46:21 +0530 | Pooja Nakul Sharma | DCM: Mr Pramod HDIL DreamsÂ Bhandup west Renovation Family- 4 membersÂ Prof- Job Pet dog 1. LR- Currently there is indian seating/baithak in living room to be converted to full height window. 2. Existing false ceiling to be changed to have minimal one.Â 3. Existing wooden crockery unit, can be re-used, open for ideas.Â 4. New TV wall design.Â 5. Mandir to be planned in living room along with storage. 6. 4 Seater diningÂ 7. Leakage issue in lining room balcony corner. 8. Kitchen has dry balcony.Â 9. Utility- WM + dryer, Dishwasher. Janitor storage. 10. Kitchen - completely new. Inbuilt m/o appliance unit. Complete modular kitchen.Â 11. Both bathrooms to be completley renovated.Â 12. Bedroom1 - Space for used clothes, wardrobe, bed, Tv (optional).Â 13. MBR- Existing wardrobe to be made into sliding, used clothes storage. Foldable table for ironing. 14. Entrance- safety door along with panelling. 15. Budget-10-12L | [6 empty] | 2026-03-14 |  | 2026-03-21
18324 | Turnkey | 2026-01-01 | Makhdoom Ansari | Roswalt Zaiden | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Nivesh Gupta |  | Hold | Design | DEM1 | 1579169 | 209999 | 1934844 | 0 | 0 | 18 | 85 | 0 | 105835 | 676145 | 587190.4 |  |  | 2026-02-07 | 2026-02-15 11:46 | 2026-02-17 | 2026-02-17 11:21 | 2026-03-30 | 2026-03-31 12:38 | 2027-01-14 |  | 2027-01-21 |  | 2027-01-28 |  | 2026-03-31 | 2026-03-31 16:52 | 2026-04-01 | 2026-04-02 13:53 | 2026-04-02 | 2026-04-03 15:03 | 2026-04-10 | 2026-04-10 18:27 |  |  |  |  | 2027-01-15 |  | 2027-01-23 |  | 2027-01-24 |  |  |  | 2027-01-31 |  | 2027-02-01 |  | 2027-02-02 |  | 2027-02-03 | [6 empty] | 2027-02-21 |  | 2027-03-02 |  | 2027-03-01 |  | 2027-03-02 |  | 2027-03-03 |  | 2027-03-05 |  |  |  | 2027-03-27 |  | 2027-03-29 |  | 2027-03-30 | [5 empty] | 2027-02-01 |  | 2027-01-10 |  | Unknown | 2026-02-07 | 2026-02-15 11:44 | 1639699 | 295145 | 0 | 0 | 0 | 0 | 1632370.246 | 274449 | 2026-04-21 10:49:26 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-10 18:28:54 +0530 | Manzoor Shaikh | "Welcome call done. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : December 2026 Customer will make 10% post December 2026 as per approval received from Dipen FDM dates: TBD Price protection until December 2026 s per approval received from Dipen" | 2026-04-03 14:10:20 +0530 | Royden Henriques | ________________________________________ Possession : Dec'26Â Payment Mode : B2C Self funding - Yes CX will pay the next milestone in December'26 when he receives Possession and price protection until Dec'26 - As per Approval from Dipen.Â CX wanted to know what if the possession gets delayed beyond December'26 -Informed basis approval price protection is given until Dec'26. Post December he will need to pay as per new pricing incase of inflation. ayeshaansari12@gmail.com makhdoom.ansari@gmail.com Flat - A-2301/2302 , roswalt zaiden, off SV Road in Jogeshwari West, Mumbai (400102), near Oshiwara, Andheri West Post offers the amount is 15,79,169/- as per the offer email. 90+15=105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays | 2027-01-15 |  | 2027-01-22
18325 | Turnkey | 2026-01-01 | Shubhangi .m. Rane ( Mauli Transport) | Atul horizon | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Safalta Karkera | [5 empty] | Ashish Jha |  | Hold | Preproduction | DEM2 | 894516 | 178903 | 1058219 | 0 | 0 | 63 | 40 | 0 | 0 | 383429 | 332184.4 |  |  | 2026-02-07 | 2026-02-08 12:34 | 2026-02-10 | 2026-02-11 13:54 | 2026-02-22 | 2026-02-22 22:31 | 2026-03-29 | 2026-03-29 12:11 | 2026-12-05 |  | 2026-12-12 |  | 2026-02-22 | 2026-02-27 13:45 | 2026-02-23 | 2026-02-27 15:47 | 2026-02-27 | 2026-02-28 15:34 | 2026-03-07 | 2026-03-07 15:59 |  |  |  |  | 2026-03-29 | 2026-04-03 17:17 | 2026-12-07 |  | 2026-12-08 |  |  |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-18 | [6 empty] | 2027-01-05 |  | 2027-01-14 |  | 2027-01-13 |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-17 |  |  |  | 2027-02-08 |  | 2027-02-10 |  | 2027-02-11 | [5 empty] | 2026-12-16 |  | 2026-03-08 | 2026-03-29 12:04 | Site is RTMI | 2026-02-07 | 2026-02-08 12:25 | 988494.688 | 161423 | 0 | 0 | 0 | 0 | 984377.138 | 160858 | 2026-06-05 18:03:59 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-05 17:57:34 +0530 | Manzoor Shaikh | The customer called stating he has some OC issue with the builder, and asked for a refund, however, informed the customer we does not have any cancellation or refund policy. Also the customer is not sure how much time it will take to fix the OC issue, hence informed the customer will place the project on Hold until August, if he has any update asked to keep us posted and accordingly will make the project Active. | 2026-05-10 10:56:50 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-30 | 2026-03-29 12:12 | 2026-12-06
18326 | Turnkey | 2026-01-01 | Paras Baid | null | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1594231 | 9999 | 1594231 | 0 | 0 | 122 | 0 | 149424 | 159423 | 651084 | 624301.2 |  |  | 2026-02-07 | 2026-02-07 21:05 | 2026-03-15 | 2026-03-15 13:52 | 2026-03-15 | 2026-03-15 13:59 | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-02-07 | 2026-02-07 21:03 | 1351044 | 243187 | 0 | 0 | 0 | 0 | 1351044 | 243187 | 2026-04-22 18:05:53 +0530 | Patil Madhavi | Some Image was uploaded | 2026-03-07 10:40:19 +0530 | Rajasekar Ranganathan | Minimalistic Interior Scope & Budget PlanBudget: 1518 Lakhs (Including Beds & Sofa) 1. FOYERShoe rack with closed storageMinimal overhead storageDecorative wall panel / mirrorFalse ceiling with profile lights2. LIVING ROOMMinimal false ceiling with cove lightingTV UnitDesigned for 65 TVStorage for set-top box and accessoriesTall storage unit beside TVCorner tall unit beside sofaFeature back wallWallpaper / fluted panel / texture paintSpace for big paintingPooja Unit (Room Concept)As per Vastu directionSliding door / jaali partitionStorage for pooja items3. DINING ROOMFalse ceiling with pendant light above diningBreakfast counter4-seater dining tableBase storage cabinetBack wall design panel / wallpaperIntegrated study table4. STUDY ROOM (Daughters Room)WardrobeBedStudy table with storageMinimal wall shelves5. BEDROOM 2 (Parents Bedroom)Wardrobe with loftBay window seating with storageQueen size bedTV unit with storage provision6. MASTER BEDROOMWardrobe with loftStudy tableDressing table with mirror and drawers7. WASHROOMSVanity unit with storageMirror cabinet8. KITCHENSingle shutter entry doorBase unitsWall cabinetsLoft storageSpace for chimney & hob9. UTILITYBase storage unitsWall cabinets for cleaning materials |  |  |  | 2026-03-23 |  | 2026-03-30
18327 | Turnkey | 2026-01-01 | Archana Jadhav | Aim Heritage | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 1215173 | 9999 | 0 | 0 | 0 | 119 | 0 | 111518 | 121517 | 486069 | 486069.2 |  |  | 2026-02-07 | 2026-03-18 16:25 | 2026-02-08 |  | 2026-03-19 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-20 |  | 2026-03-21 | [5 empty] | 2026-03-27 |  | 2026-04-04 |  | 2026-04-05 |  |  |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 | [6 empty] | 2026-05-03 |  | 2026-05-12 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-15 |  |  |  | 2026-06-06 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-04-13 |  | 2026-03-22 |  | Unknown | 2026-02-07 | 2026-03-18 16:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1029808 | 185365 | [9 empty] | 2026-03-27 |  | 2026-04-03
18329 | Turnkey | 2026-01-01 | Tejas Tipre | Lodha Amara | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Tanveer Patel | Akshat Shrivastava | Murali S | Aryan Singh | Shailendra Mishra | Active | Installation | Execution | 1350683 | 1350684 | 1761694 | 0 | 1350683 | 23 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-07 | 2026-02-22 17:10 | 2026-02-22 | 2026-02-22 18:46 | 2026-02-25 | 2026-02-24 12:36 | 2026-03-29 | 2026-03-29 19:31 | 2026-04-23 | 2026-04-22 15:50 | 2026-04-22 | 2026-04-22 20:19 | 2026-02-25 | 2026-02-23 18:30 | 2026-02-25 | 2026-02-26 12:55 | 2026-02-26 | 2026-02-27 16:00 | 2026-03-05 | 2026-03-05 11:41 |  |  |  |  | 2026-03-29 | 2026-04-03 15:10 | 2026-04-29 | 2026-04-22 16:50 | 2026-04-23 | 2026-04-22 16:50 |  |  | 2026-04-24 | 2026-04-29 15:45 | 2026-04-29 | 2026-04-29 17:15 | 2026-04-30 | 2026-04-30 16:23 | 2026-05-01 | 2026-05-05 14:27 |  |  |  |  | 2026-05-12 19:51 | 2026-05-28 | 2026-05-27 21:34 | 2026-06-04 | 2026-06-02 18:55 | 2026-06-03 | 2026-06-01 17:49 | 2026-06-02 | 2026-06-16 11:55 | 2026-06-19 | 2026-06-22 16:35 | 2026-06-28 | 2026-07-03 12:54 |  |  | 2026-06-20 |  | 2026-06-22 |  | 2026-07-18 | [5 empty] | 2026-04-29 | 2026-05-12 19:50 | 2026-03-06 | 2026-03-29 19:25 | Site is Non-RTMI | 2026-02-07 | 2026-02-07 23:30 | 1492961 | 268733 | 0 | 0 | 1472411.676 | 239595 | 1472411.676 | 239595 | 2026-06-23 00:17:09 +0530 | Tanveer Patel | Execution: Furniture delivered on 19 junemodular team not assigned | 2026-06-15 23:29:51 +0530 | Tanveer Patel | Procurement: Furniture is in transit.Floor Covering work done .First coat paint work done | 2026-06-12 22:39:09 +0530 | Asif Shaikh | Execution: Vendor Delyed -- Swastik Imterior Floor Covering done on 16th May.False ceiling & electrical completed - 5th JuneFirst coat painting work -- 13th JuneSRD - 13th June | 2026-03-30 | 2026-03-29 19:46 | 2026-04-23 | 2026-04-22 16:14 | Under Construction | 2026-04-01
18332 | Turnkey | 2026-01-01 | Prashanth Shetty | JRC PALLADIO | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 533586 | 9999 | 0 | 0 | 0 | 155 | 0 | 43360 | 53359 | 213434 | 213434.4 |  |  | 2026-02-07 | 2026-02-10 11:23 | 2026-02-10 | 2026-02-10 13:48 | 2026-02-13 |  | 2026-02-20 |  | 2026-02-27 |  | 2026-03-06 |  | 2026-02-13 |  | 2026-02-14 |  | 2026-02-14 |  | 2026-02-15 | [5 empty] | 2026-02-21 |  | 2026-03-01 |  | 2026-03-02 |  |  |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 | [6 empty] | 2026-03-30 |  | 2026-04-08 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-11 |  |  |  | 2026-05-03 |  | 2026-05-05 |  | 2026-05-06 | [5 empty] | 2026-03-10 |  | 2026-02-16 |  | Unknown | 2026-02-07 | 2026-02-10 11:20 | 0 | 0 | 0 | 0 | 0 | 0 | 452192 | 81394 | 2026-02-10 13:39:01 +0530 | Adarsh K | MINUTES OF MEETING (MOM)Client Name: Prashath Shetty Client Background: Business in IT Project : JRC Palladio villa, Sarjapurâ€“Attibele Road Date: Requirement Gathering Meeting, 10th Feb, 11:30am - 1:00pm RGM Budget - 25+ Lakhs Next Meeting: 15th February â€“ at EC 1. Project OverviewTotal Built-up Area: Approx. 3,800 sq. ft. Main Door Facing: East Property Current Status & Possession: Flooring completed, Handover by March 30th. Key View: Corner property, North-facing view towards play area 2. Design Style & PreferencesOverall Style: Blend of Luxury Contemporary + Neoclassical Contemporary to be dominant Wall Treatment: Plain walls with attractive artifacts No beadings / mouldings Statement Wall: At Sofa wall & 2 Double height ceiling walls 3. Flooring & FinishesOverall Flooring: Matt finish â€“ Morning Glory Off-White Tiles Bedrooms: Wooden flooring 4. Floor-wise Space PlanningGround FloorGuest Bedroom: Designed like a hotel-style room First FloorHome Tutor Setup: Tuition / Library area Bedrooms: Kids Bedroom Master Bedroom (MBR) Pooja Room: East-facing at corner towards open terrace. Family Memory Wall: Located near staircase Second FloorBar Counter Office cum Bedroom Additional Master Bedroom: Full-wall study + office setup Sofa-cum-bed Travel Souvenirs Display Area Balcony: Minimal plants - Lounge 5. Living, Dining & KitchenDiningDining Table: 6-seater Breakfast Counter: 2-seater Extended from kitchen KitchenStorage: No loft Tall wall units Dedicated tall grocery units 6. Bedroom-wise RequirementsMaster Bedroom (1st Floor)Features: Walk-in Wardrobe (WIW) Concealed Godrej Treasure Safe â€“ 200 kg Recliner TV Unit TV & Bed positions to be swapped Bathroom: Villeroy & Boch commode & sink Vanity unit Glass partitions Kids BedroomAge: 13 years Design Direction: Bold & colourful Highlighted as â€œmost beautiful room in the houseâ€ 7. Special Areas & UtilitiesLaundry Area (2nd Floor)RO Unit & Sink Washing Machine & Dryer side-by-side Counter above WM & Dryer Lift control panel: Size: 1 ft wide x 6 ft tall Location: Laundry area 8. Foyer & Decor ElementsFoyer: Glass door Heritage Items Display: 1st & 2nd floors 9. External / TerraceReference Images Required For: Metal fabrication Open terrace seating Staircase covered roof Next MeetingðŸ“… 15th February ðŸ“ EC | [6 empty] | 2026-02-21 |  | 2026-02-28
18333 | Turnkey | 2026-01-01 | Kishore Kanji Jadhav | Tigon Elite | MUM - Thane | Yes | Rinisha Masurkar | [9 empty] | Active | Prospect | 10% Payment | 1322981 | 9999 | 1322981 | 0 | 0 | 141 | 0 | 122299 | 132298 | 536914 | 521471.2 |  |  | 2026-02-08 | 2026-02-08 12:41 | 2026-02-21 | 2026-02-21 20:50 | 2026-02-24 | 2026-02-24 11:48 | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-02-08 | 2026-02-08 12:24 | 1121170 | 201810 | 0 | 0 | 0 | 0 | 1121170 | 201810 | 2026-02-08 14:35:52 +0530 | Rinisha Masurkar | Title:Â Design Consultation Meeting Project No:Â 18333 Client:Â Kishore Kanji Jadhav Hi, Minutes of Meeting (MOM)Project ID:Â 18333 Client Name:Â Mr. Kishor Kanji Jadhav Configuration:Â 2 BHK ¦ 630 sq.ft Family Members:Â 4 Design Stage:Â CDP TBS Budget Range:Â 1015 Lakhs Design Understanding & RequirementsOverall ThemeClient prefers aÂ minimalist designÂ withÂ open and spacious planningNo existing furniture; complete new interior scopeDesign to be clean, functional, and visually unclutteredLiving RoomMovableÂ shoe rackSafety doorÂ at the main entranceMandirÂ required with a simple and minimal designSeating:Â 3 + 1 sofa arrangementDining:Â 6-seater dining tableTV Unit:Â Designed forÂ 52 TVWall treatment:Â Minimal wall conceptBedroom 1TV provisionStudy unitWardrobeFoldable tableDresserFalse ceiling with subtle lightingBedroom 2TV provisionStudy unitWardrobeFoldable tableDresserFalse ceiling with subtle lightingCeiling & LightingFalse ceiling to be provided inÂ all roomsLighting to be simple, elegant, and minimalBathrooms / Vanity AreaVanity unit with storageGlass partition for shower areaAdditional NotesDesign to balance aesthetics, functionality, and budgetFinal materials and finishes to be proposed during design developmentNext StepsDesign team to proceed withÂ CDP planningLayouts and material concepts to be discussed in the next meeting. | 2026-02-08 12:39:26 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded |  |  |  | 2026-03-04 |  | 2026-03-11
18335 | Turnkey | 2026-01-01 | Abhijeet Marathe | Raymond GS | MUM - Thane | Yes | Rutuja Kotwal | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 4543445 | 9999 | 4543445 | 0 | 0 | 145 | 0 | 444346 | 454345 | 2003638 | 1631117.6 |  |  | 2026-02-08 | 2026-02-08 20:25 | 2026-02-20 | 2026-02-20 15:39 | 2026-02-23 | 2026-02-20 15:42 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-08 | 2026-02-08 20:23 | 3850377 | 693067 | 0 | 0 | 0 | 0 | 3850377 | 693067 | 2026-02-08 20:27:12 +0530 | Nishtha Valawalkar | 4 BHK 1500 ssq.ft 45L 50L | 2026-02-08 20:26:36 +0530 | Nishtha Valawalkar |  | 2026-02-08 14:15:15 +0530 | Rutuja Kotwal | DCM: Mr. Abhijeet marathe 4 BHK. 1400 sq. ft. Direction - mentioned in Layout design as per basic vastu. Profession - Service in Sun pharma Wife - Dr. Poorva Marathe- occupational Therapist. Possession - April /May 2026. Move in - 4 people Husband, wife and 2 daughters - 12 yrs. and 4 yrs. Living Room - shoe rack till the ceiling ,Breaking of wall between bedroom and living room, Sofa, existing dining table of 6 seater, bay window with Storage, indian seating, mandir, with crockery unit and Book shelf in glass. Arch design to be implemented. Kitchen - Base unit, Wall Unit and lofts. kitchen renovation. Kitchen Platform to raise by 3", kitchen door. Parent's Bedroom - Existing Bed, Wardrobe with Lofts, chest of drawers in the front wall, side table. CDP- 14 Feb. 2026 or 22nd feb. Budget- 45 lakhs Daughter's Bedroom - Wardrobe with Lofts and some open sections to keep toys, existing bed to be used, Study unit with above cabinet, chest of drawers, bay window if possible . MBR- Closing of wall and making toilet entry from bedroom, Aristo Wardrobe with Lofts, existing study unit | 2026-02-28 |  | 2026-03-07
18337 | Turnkey | 2026-01-01 | Udaykumar Pandurang Waghe | AdityaRaj | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  | Hiba Shaikh | suraj kumar | Aditya Vikram |  | Mrunali Mitkari | Aakash Gaikwad | Active | Design | 60% Payment | 1357319 | 216289 | 1357227 | 0 | 1357319 | 3 | 0 | 0 | 0 | 601528 | 539502 |  |  | 2026-02-07 | 2026-02-11 15:26 | 2026-02-12 | 2026-02-12 14:03 | 2026-02-24 | 2026-02-24 15:01 | 2026-03-31 | 2026-03-31 14:21 | 2026-05-03 | 2026-05-02 12:49 | 2026-06-18 | 2026-06-17 16:47 | 2026-02-24 | 2026-02-26 19:14 | 2026-02-25 | 2026-02-27 18:41 | 2026-02-27 | 2026-03-02 13:00 | 2026-03-05 | 2026-03-06 12:47 |  |  |  |  | 2026-03-30 | 2026-03-10 19:01 | 2026-05-26 | 2026-05-26 14:50 | 2026-05-27 | 2026-05-26 14:51 |  |  | 2026-06-26 | 2026-07-11 12:59 | 2026-07-12 | 2026-07-12 19:29 | 2026-07-13 | 2026-07-12 19:30 | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-12 |  | 2026-04-16 | 2026-03-28 14:52 | Site is RTMI | 2026-02-07 | 2026-02-08 13:19 | 1150192 | 207034 | 0 | 0 | 1394331.9927 | 240608 | 1394331.9927 | 240608 | 2026-05-24 13:23:06 +0530 | Manzoor Shaikh | I met the client and communicated her the Standard timeline of the handover also informed her about the delay if she is eligible have to send an email at wecare@bonito.in | 2026-04-19 19:12:47 +0530 | Shweta Dalvi | Living RoomTV Unit:3-drawer base unitTall open unit (considered)Wallpaper:To be provided behind the TVPillar:In the client scopeMandir:Same as CDPWall Paneling:As per the reference designKitchenMain Counter (Base Units)1 Sink unit1 Two-drawer unit1 Bottle pull-out1 Three-drawer unitWall Units1 Aquaguard unitChimney space provision1 Shutter with 1 shelfLoftAs per the wall unit layoutService PlatformBase Unit1 Double shutter with 1 shelfWall Unit1 Microwave unit1 Double shutter with 1 shelfLoftNot requiredParents' Bedroom3-door wardrobe1 Tall unit (for used clothes) with mirror profile shutter1 Side tableBed:In client scope (due to space constraints)Master BedroomWardrobe + 1 Tall unit (used clothes) with profile shutter & mirrorStudy table:4 ft base unitWall Unit:1 Double shutter1 Open unitBed: In the client scopeDresser:Wall unit and side table considered | 2026-04-13 20:19:29 +0530 | Shweta Dalvi | Transition Meeting Client Name: Uday Kumar Pandurang Waghe Project ID: 18337 1. Living RoomShoe RackSize: 700 x 700 x 350 mmConfiguration: 1 vertical + 1 horizontal shelfHandles: Not consideredTV UnitÂ Legs shown in 3D design are missing in the quoteWooden Poles are present in the 3D design but are missing in the quoteRafters (Behind Sofa)Shown in 3D design but not included in the quoteWall Paneling (Dining Area) is present in the 3D design, but is missing in the quoteRafters Behind Mandir: Not included in the quoteMandir Metal Fabrication is missing in the quoteMandir UnitSize: 650 x 600 x 350 mmConfiguration: 1 vertical + 1 horizontal shelf2. KitchenTall UnitSize: 580 x 1990 x 300 mmShelves: 5 shelves consideredMain PlatformBase Units:Â 1 three-drawer unit1 bottle pull-out (2-tier)1 sink unit1 shelf unit (horizontal shelf missing)Wall UnitsÂ 1 Aquaguard unit1 open unit1 wall unit with 1 shelf (handle missing)LoftConsideredFillers: Not consideredBottom panel above chimney: MissingService PlatformBase Units:Â Double shutter unit consideredNo internal shelf providedWall Units:Â 2 units consideredHandles: MissingLoft is not considered3. Parents' BedroomWardrobeSize: 800 x 1990 x 580 mmIncludes: 2 drawers, 1 hanging rod, 1 shelfLoftConsideredSide Wardrobe:Â 5 shelves includedHandles: Missing4. Master BedroomWardrobeSize: 1600 x 1990 x 560 mmConfiguration:Each 800 mm unit includes:2 drawers1 hanging rod1 shelfLoft: ConsideredHandles: MissingStudy TableSize: 1050 x 700 x 450 mmHandles: MissingStudy Wall UnitÂ 1 double shutter unit with 1 shelf1 open unitDresser Wall UnitSize: 600 x 1200 x 150 mmInternal: 1 shelf onlyAC Paneling is missing in the quote5. Additional Items / ObservationsKitchen sliding door: Missing in the quoteFalse ceiling: Only periphery (120 sq. ft.) consideredBathroom vanity:Size: 450 x 600 x 450 mmProvided in both bathroomsHandles & fillers: Not consideredDesign Services:Amount considered: 20,861Beds:Febonic beds are considered for both bedrooms6. Key Summary of Missing ItemsTV unit legsWooden poles (living room)Rafters (living room & mandir area)Wall paneling (dining area)Mandir metal fabricationMultiple handles across unitsAC panelingKitchen sliding doorCertain shelves and fillers in the kitchen | 2026-04-01 | 2026-04-19 19:11 | 2026-05-03 | 2026-05-25 10:36
18339 | Turnkey | 2026-01-01 | Susmit Mukherjee | RUNWAL FOREST | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-08 15:46 | 2026-02-09 |  | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 | [5 empty] | 2026-03-01 |  | 2026-03-09 |  | 2026-03-10 |  |  |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 | [6 empty] | 2026-04-07 |  | 2026-04-16 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-19 |  |  |  | 2026-05-11 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-03-18 |  | 2026-02-24 |  | Unknown | 2026-02-08 | 2026-02-08 15:32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-01 |  | 2026-03-08
18340 | Turnkey | 2026-01-01 | Ankur Vohra | Shobha Rajvillas | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Shijin C C | Jairam Joshi | Murali S | Kushal S | Vishwa Hiremath | Completed | Complete | Completed | 1160795 | 1160796 | 1522078 | 0 | 1160795 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-27 15:38 | 2026-02-14 | 2026-03-05 08:56 | 2026-03-05 | 2026-03-05 11:55 | 2026-03-24 | 2026-03-24 14:25 | 2026-03-26 | 2026-03-25 15:53 | 2026-04-12 | 2026-04-12 11:41 | 2026-03-05 | 2026-03-06 13:03 | 2026-03-06 | 2026-03-06 13:08 | 2026-03-06 | 2026-03-06 15:33 | 2026-03-08 | 2026-03-08 19:14 |  |  |  |  | 2026-03-24 | 2026-03-24 15:11 | 2026-03-26 | 2026-03-27 17:45 | 2026-03-28 | 2026-03-27 19:06 |  |  | 2026-04-14 | 2026-04-16 13:05 | 2026-04-16 | 2026-04-16 19:16 | 2026-04-17 | 2026-04-19 13:02 | 2026-04-20 | 2026-04-20 14:42 |  |  |  |  | 2026-04-22 11:07 | 2026-04-30 | 2026-04-29 19:44 | 2026-05-27 | 2026-05-20 19:47 | 2026-05-21 | 2026-05-25 14:36 | 2026-05-20 | 2026-05-25 14:43 | 2026-05-25 | 2026-05-25 20:18 | 2026-06-06 | 2026-06-05 13:29 |  |  | 2026-06-26 | 2026-06-27 08:13 | 2026-06-30 | 2026-06-27 11:21 | 2026-07-01 | 2026-06-27 22:32 |  |  |  |  | 2026-04-16 | 2026-04-22 11:06 | 2026-03-09 | 2026-03-22 14:06 | Site is RTMI | 2026-02-08 | 2026-02-12 18:20 | 1289896 | 232181 | 0 | 0 | 1297206.708 | 213680 | 1297206.708 | 213680 | 2026-06-16 17:05:35 +0530 | Jairam Joshi | Some Image was uploaded | 2026-06-04 17:31:41 +0530 | Jairam Joshi | Some Image was uploaded | 2026-05-07 19:27:24 +0530 | Yogesh B | Some Image was uploaded | 2026-03-25 | 2026-03-24 14:33 | 2026-03-26 | 2026-03-25 16:00
18341 | Turnkey | 2026-01-01 | Mounica V | Elixir reserve | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry |  | Umang Shah | Sunil Poojary | Active | Preproduction | DEM2 | 1243232 | 209999 | 1188145 | 0 | 0 | 36 | 0 | 0 | 0 | 550507 | 482726.4 |  |  | 2026-02-08 | 2026-02-11 12:11 | 2026-02-11 | 2026-02-11 12:19 | 2026-02-17 | 2026-02-17 18:44 | 2026-04-08 | 2026-03-29 18:01 | 2026-04-19 | 2026-04-18 17:54 | 2026-08-13 |  | 2026-02-17 | 2026-02-28 | 2026-02-18 | 2026-03-03 14:23 | 2026-03-03 | 2026-03-07 18:12 | 2026-03-14 | 2026-03-14 17:40 |  |  |  |  | 2026-03-29 | 2026-04-06 22:18 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-04-04 | 2026-03-29 17:59 | Site is RTMI | 2026-02-08 | 2026-02-08 15:46 | 1006902 | 181242 | 0 | 0 | 0 | 0 | 1296340.1029 | 214052 | 2026-06-27 17:09:11 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-09 18:19:35 +0530 | Swapnali Shedekar | Material selection meeting is aligned on 12th April Sunday at 2:30pm - 5:30pm | 2026-04-08 14:00:20 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-30 | 2026-03-29 18:02 | 2026-04-19 | 2026-05-15 12:00 | Under Construction | 2026-06-01
18343 | Turnkey | 2026-01-01 | SUMAN KUMARI Suman | SSVR Niyaraa | BNG - HSR | Yes | Aishwarya C | Akshay Ds | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1004342 | 200868 | 1425722 | 0 | 0 | 25 | 0 | 0 | 0 | 407549 | 395925.2 |  |  | 2026-02-08 | 2026-02-08 17:26 | 2026-02-10 | 2026-02-18 11:13 | 2026-02-21 | 2026-02-18 18:50 | 2026-06-20 | 2026-06-19 15:22 | 2026-08-08 |  | 2026-08-15 |  | 2026-02-18 | 2026-02-19 16:49 | 2026-02-19 | 2026-02-20 17:17 | 2026-02-20 | 2026-02-24 12:39 | 2026-03-05 | 2026-03-05 20:01 |  |  |  |  | 2026-06-19 | 2026-06-20 14:24 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-04-07 | 2026-04-12 16:31 | Site is RTMI | 2026-02-08 | 2026-02-08 17:25 | 1208239 | 217483 | 0 | 0 | 0 | 0 | 1164218.1653 | 187908 | 2026-06-03 16:31:30 +0530 | Priyanka Inchoor | Some Image was uploaded | 2026-04-23 15:16:09 +0530 | Priyanka Mathur | We have already explained the cost comparison sheet in detail. Regarding electrification, we would like to clarify that it was mentioned initially; however, as per our standard process, electrification is not included in the initial estimation and is added separately at a later stage. Client is saying I want clarification on the same until that I will not proceed with 10% payment | 2026-04-21 16:31:17 +0530 | Priyanka Inchoor | DDM1: 11/06/2026 TV unit design with lighting option Sofa wall design with beading Console table cx will procure and above beading rectangle design is needed painting options to minimize the quotation Kitchen Sink position and hob position swapper as per the site condition client will clarify that dishwash provision will come in kitchen or not MBR Wardrobe study and cloth hanging storage unit will come in the same wall (opposite to bed) dressing unit next to bed add one side table Cot wall design with beading give space for AC KBR bed position changed as per the site condition study is attached to wardrobe L-shape PBR Sliding wardrobe will come instead of Hinged wardrobe due to space Need pooja unit with CNC shutter design | 2026-06-20 | 2026-06-19 15:23 | 2026-08-09
18344 | Turnkey | 2026-01-01 | Nilesh kumar | Nikoo Homes 4 | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Hold | Preproduction | Site Readiness 1 | 1402630 | 280526 | 1686532 | 0 | 0 | 2 | 107 | 0 | 0 | 674962 | 447142.4 |  |  | 2026-02-08 | 2026-02-08 17:38 | 2026-02-08 | 2026-02-10 11:00 | 2026-02-21 | 2026-02-21 18:25 | 2026-03-28 | 2026-03-28 16:18 | 2026-07-19 |  | 2026-07-26 |  | 2026-02-21 | 2026-02-24 17:28 | 2026-02-22 | 2026-03-01 12:17 | 2026-03-01 | 2026-03-02 12:49 | 2026-03-05 | 2026-03-05 15:29 |  |  |  |  | 2026-03-27 | 2026-03-17 19:38 | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-30 |  | 2026-03-06 | 2026-03-28 16:11 | Site is RTMI | 2026-02-08 | 2026-02-08 17:36 | 1429264 | 257267 | 0 | 0 | 0 | 0 | 1400686.874 | 241418 | 2026-07-07 12:54:33 +0530 | Ashiya Sanam | Living Room; 1.Foyer unit design is finalised and materials are finalised 2. TV unit design is finalised and laminate are finalised 3.Crockery unit to have same design as per EC reference 4.Pooja Unit to have back pichwai glass design and shutters to be completely fluted and internal drawers Kitchen: 1.Units demolition to be done in bonito scope 2.Tall unit to be included with both glass and tandem drawes and include a wicker basket 3. on the either side include a microwave hanging unit 4. wall unit to have glass shutter 5.Pull out unit to be included 6.Panel to cover the chimney pipe 7.Tandem drawers to be included instead of shelf units 8.In hob Unit one cutlery with other two tandem drawers Utility: 1.Both sink and washing machine space to be checked Master bedroom: 1.To go with Membrane shutter as per reference image and internals 2.Dresser unit to include mirror 3.Tv unit to be added with extra drawer for set up box 4.Wall designs are finalised Guest Bedroom: 1.To go with aristo shutter 2.Internals as per reference Son's Bedroom: 1.Internals are finalised 2.To go with wall designs and wallpaper is added in all three rooms Both washrooms to have shower partition with door NOTE: 1.Electricals and painting in bonito scope 2.Loose furniture included in bonito scope 3.HOB and chimney in bonito offer | 2026-06-16 23:18:35 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-23 19:00:35 +0530 | Yogesh B | Some Image was uploaded | 2026-03-29 | 2026-03-28 16:45 | 2026-07-20
18345 | Turnkey | 2026-01-01 | Abhinav | Brigade eldorado | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [5 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 2412773 | 9999 | 0 | 0 | 0 | 132 | 0 | 231278 | 241277 | 1035880 | 894338.8 |  |  | 2026-02-08 | 2026-02-08 17:38 | 2026-02-08 | 2026-02-12 16:19 | 2026-02-22 | 2026-03-25 19:28 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-02-08 | 2026-02-08 17:37 | 0 | 0 | 0 | 0 | 0 | 0 | 2044723 | 368050 | 2026-02-12 16:19:02 +0530 | Priyanka Gs | 08-02-2026 Family of 3Â Kid -Boy- 3.5 year old Entrance wallÂ Need a wall decor concept, where can displayÂ Pooja unitÂ Need space for IdolsÂ Would prefer simple yet elegant design for pooja unit Dining table - 6 Seater - NewÂ Require a crockery unit which is not bulky TV unitÂ 65"inchesÂ Need a Tall unit next to the TV unitÂ Wall concept behind the sofa with wall lightsÂ KitchenÂ Fridge - 900MMÂ Microwave +OvenÂ Mixer , airfryer Sink - With 2 bowls Pantry Unit Base , wall & LoftÂ RO unit - Wall mountÂ Cook top & Chimney - 900mmÂ Bedroom - 3 - Guest +StudyÂ Wall cabinet above the Ht adjustable tableÂ Sliding wardrobe +loft Shower Partitions for washroomsÂ Bedroom -2 - Kids bedroom MBRÂ Sliding wardrobeÂ Study Cum TV unit 49"Â Vanity open cabinet +Mirror Budget - 20L For modulars CDP date - 21/02/2026 10:30AM to 2:00PM | [6 empty] | 2026-04-02 |  | 2026-04-09
18346 | Turnkey | 2026-01-01 | Shreeya Sanjay Mugdar |  | MUM - GOR | Yes | Manisha Dubey | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Rajkumar Suthar | Sandeep Tiwari | Murali S | Harshaan Tiku | Aakash Gaikwad | Active | Installation | Execution | 993684 | 993685 | 1180353 | 979724 | 993684 | 3 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-11 15:41 | 2026-02-13 | 2026-02-13 11:49 | 2026-02-14 | 2026-02-14 11:44 | 2026-03-17 | 2026-03-17 13:48 | 2026-04-09 | 2026-04-08 12:16 | 2026-04-21 | 2026-04-21 20:32 | 2026-02-14 | 2026-02-14 16:11 | 2026-02-15 | 2026-02-16 13:03 | 2026-02-16 | 2026-02-17 13:15 | 2026-02-20 | 2026-02-20 17:33 |  |  |  |  | 2026-03-17 | 2026-04-06 22:27 | 2026-04-17 | 2026-04-21 10:43 | 2026-04-22 | 2026-04-21 10:48 |  |  | 2026-04-24 | 2026-04-29 18:04 | 2026-04-29 | 2026-04-29 20:35 | 2026-05-01 | 2026-04-29 21:14 | 2026-05-02 | 2026-05-08 19:10 |  |  |  |  | 2026-05-15 14:20 | 2026-05-30 | 2026-05-29 21:03 | 2026-06-17 | 2026-06-15 18:37 | 2026-06-16 | 2026-06-30 13:41 | 2026-06-15 | 2026-07-08 11:08 | 2026-07-04 | 2026-07-12 17:01 | 2026-07-14 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-29 | 2026-05-15 14:19 | 2026-02-21 | 2026-03-15 18:53 | Site is RTMI | 2026-02-08 | 2026-02-08 17:51 | 1000299 | 180053 | 1077618.4749 | 168974 | 1104701.8425 | 177511 | 1104701.8425 | 177511 | 2026-06-28 12:29:19 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-26 13:46:08 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-25 12:31:25 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-18 | 2026-03-17 13:51 | 2026-04-09 | 2026-04-16 11:23
18347 | Turnkey | 2026-01-01 | Devraj Sirohi | the mansion | MUM - Thane | Yes | Pooja Nakul Sharma | [9 empty] | Active | Prospect | 10% Payment | 3878722 | 9999 | 3878722 | 0 | 0 | 147 | 0 | 377873 | 387872 | 1627433 | 1475544.4 |  |  | 2026-02-08 | 2026-02-08 18:24 | 2026-02-10 | 2026-02-10 12:06 | 2026-02-15 | 2026-02-18 19:28 | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Unknown | 2026-02-08 | 2026-02-08 17:58 | 3617305.44 | 591669 | 0 | 0 | 0 | 0 | 3617305.44 | 591669 | 2026-05-07 14:10:16 +0530 | Ishan Patle | Call done 07/05/26 But cx not pick up the call | 2026-02-15 09:35:13 +0530 | Pooja Nakul Sharma | DCM: Mr Devraj Sirohi 4BHKÂ The mansionÂ Soft poss- Dec 2026Â Family- 4 membersÂ Proff- Sir- sales Â To be vastu compliant Clear room height- 10.4 ft 1. King bed and sofa can be re-used.Â 2. Shoerack , safety door + wall concepts outside.Â 3. Swing to be planned in LR 4. Dining area can have sliding partition 5. 2 existing vases can be used for highlight 6. Ideas to be explored for dining and puja area 7. Tv unit with semi-option partition (option 1) 8. Dining side board can be planned. 9. 3.5x4.5 ft frame can be used for decor 10. 6-8 seater dining. 11. Decorative light+ fan above dining. 12. Existing mandir will be used 4 ft width approx. To plan a storage below. 13. Parallel kitchen- Granite platform will be provided by builder 14. Pantry and appliance unit to be planned.Â 15. Washing machine space is given in dry area 16. sliding door to be planned both - passage area, dry area. 17. Bed 1- Ex. bed, wardrobes, hidden mirror, rocking chair (if possible), wall mount work desk.Â 18. Used clothes space in all 3 bedrooms.Â 19. Bed 2- Tv provision (all 3 bedrooms). 20. Bed 2- (son)- Wardrobe, king bed, one pullout bed provision (future), work desk wall mount, dresser with storage. Wardrobe+ dresserÂ 21. Hidden locker (bed 1 and 2) 22. All 3 bathrooms- vanities. 23. Bed 4- GBR- 2 existing wardrobes only shutters to be done. Sofa cum bed. 24. Bed 3- King bed, wardrobes, study, dresser with storage, swing/ window seatingÂ 25. Bookshelf, space for trophies.Â 26. Dry bal- detergent storage. 27. Additional small corncer storage in B1 and B2. 28. Additional loft- wherever possibleÂ 29. Balcony- seating and minimal concepts. 30. CDP- weekend 14th/15th FebÂ | 2026-02-08 18:11:42 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded | 2026-02-26 |  | 2026-03-05
18348 | Turnkey | 2026-01-01 | Bijal Sunil Shah | Shreeji Sharan skyrise | MUM - GOR | Yes | Batskhem Marpna | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Sanskruti Yadav |  | Hold | Design | 20% Payment | 1675625 | 209999 | 2114342 | 0 | 0 | 14 | 19 | 0 | 125126 | 693331 | 647168.8 |  |  | 2026-02-08 | 2026-02-10 14:49 | 2026-02-17 | 2026-02-17 11:49 | 2026-02-22 | 2026-02-22 20:52 | 2026-06-06 | 2026-06-06 19:48 | 2026-08-02 |  | 2026-08-09 |  | 2026-02-22 | 2026-02-25 12:14 | 2026-02-23 | 2026-02-27 11:22 | 2026-02-27 | 2026-03-02 12:10 | 2026-03-06 | 2026-03-06 11:41 |  |  |  |  | 2026-08-04 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-03-07 | 2026-06-06 16:37 | Site is RTMI | 2026-02-08 | 2026-02-08 18:10 | 1791815 | 322526 | 0 | 0 | 0 | 0 | 1768546.3657 | 305180 | 2026-07-07 12:18:21 +0530 | Reshma Melanta | Others: | 2026-06-21 17:14:47 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-13 16:16:00 +0530 | Vishakha Vaishnav | Tried calling cx , didn't answered | 2026-06-07 | 2026-06-12 16:13 | 2026-08-03 |  | Under Construction | 2026-07-01
18349 | Turnkey | 2026-01-01 | rohit gurumukhi | Swastik Platinum | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1692717 | 9999 | 1692717 | 0 | 0 | 147 | 0 | 159273 | 169272 | 728460 | 625714 |  |  | 2026-02-08 | 2026-02-10 11:22 | 2026-02-12 | 2026-02-12 18:12 | 2026-02-15 | 2026-02-18 19:15 | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Unknown | 2026-02-08 | 2026-02-08 18:27 | 1434506 | 258211 | 0 | 0 | 0 | 0 | 1434506 | 258211 | [9 empty] | 2026-02-26 |  | 2026-03-05
18350 | Turnkey | 2026-01-01 | Rashmi | Sizzle Maplewood | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Shivakumar Ms | Jairam Joshi | Murali S | Raghavendra S | Abdul Shafeen | Completed | Complete | Completed | 1514402 | 1514402 | 1628905 | 0 | 1514402 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-08 19:10 | 2026-02-12 | 2026-02-12 11:40 | 2026-02-22 | 2026-02-25 12:05 | 2026-03-13 | 2026-03-13 17:13 | 2026-04-05 | 2026-04-04 18:32 | 2026-04-11 | 2026-04-11 19:56 | 2026-02-22 | 2026-02-24 17:22 | 2026-02-26 | 2026-02-26 16:06 | 2026-02-26 | 2026-02-27 14:22 | 2026-03-05 | 2026-03-05 16:07 |  |  |  |  | 2026-03-15 | 2026-03-13 13:15 | 2026-04-05 | 2026-04-10 19:37 | 2026-04-11 | 2026-04-10 19:57 |  |  | 2026-04-19 | 2026-04-23 14:54 | 2026-04-23 | 2026-04-23 21:00 | 2026-04-24 | 2026-04-25 09:56 | 2026-04-26 | 2026-04-29 11:55 |  |  |  |  | 2026-04-29 21:04 | 2026-05-08 | 2026-05-07 21:00 | 2026-05-26 | 2026-05-22 18:48 | 2026-05-23 | 2026-05-22 18:59 | 2026-05-22 | 2026-05-25 16:16 | 2026-05-23 | 2026-05-25 16:16 | 2026-05-29 | 2026-05-28 18:53 |  |  | 2026-06-18 | 2026-06-25 10:46 | 2026-06-24 | 2026-06-25 10:49 | 2026-06-25 | 2026-06-25 17:03 |  |  |  |  | 2026-04-23 | 2026-04-29 21:03 | 2026-03-27 | 2026-03-13 12:03 | Site is RTMI | 2026-02-08 | 2026-02-08 18:31 | 1380428 | 248477 | 0 | 0 | 1606886.6815 | 265332 | 1606886.6815 | 265332 | 2026-06-25 17:05:38 +0530 | Jairam Joshi | Project Closure Pending: Observation points closure ETA 7th July | 2026-06-20 17:58:23 +0530 | Jairam Joshi | Execution: All works completed CX not available in town till 22nd June | 2026-06-16 17:26:02 +0530 | Jairam Joshi | Some Image was uploaded | 2026-03-14 | 2026-03-13 17:20 | 2026-04-05 | 2026-04-08 12:29
18351 | Turnkey | 2026-01-01 | Hardik Shah | Kalpataru Aura | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Savita Parab | Rizwan Mistry | Murali S | Umang Shah | Aakash Gaikwad | Active | Installation | Execution | 2360134 | 2360134 | 2120911 | 0 | 2510134 | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-11 12:11 | 2026-02-15 | 2026-02-15 21:45 | 2026-02-18 | 2026-02-17 14:00 | 2026-03-04 | 2026-03-04 12:18 | 2026-03-12 | 2026-03-26 11:01 | 2026-04-17 | 2026-04-17 19:37 | 2026-02-17 | 2026-02-17 15:52 | 2026-02-18 | 2026-02-17 20:03 | 2026-02-17 | 2026-02-18 18:13 | 2026-02-20 | 2026-02-20 13:34 |  |  |  |  | 2026-03-04 | 2026-03-09 11:50 | 2026-04-04 | 2026-04-06 19:36 | 2026-04-07 | 2026-04-06 19:37 |  |  | 2026-04-22 | 2026-04-30 18:46 | 2026-05-07 | 2026-05-07 17:44 | 2026-05-12 | 2026-05-07 22:19 | 2026-05-08 | 2026-05-09 19:14 |  |  |  |  | 2026-05-13 16:36 | 2026-05-29 | 2026-05-28 19:21 | 2026-06-12 | 2026-06-12 20:15 | 2026-06-11 | 2026-06-11 18:41 | 2026-06-12 | 2026-06-17 10:13 | 2026-06-17 | 2026-06-19 09:31 | 2026-06-20 | 2026-07-01 13:06 |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-05-07 | 2026-05-11 17:54 | 2026-02-21 | 2026-03-04 12:12 | Site is RTMI | 2026-02-08 | 2026-02-08 18:32 | 1797382 | 323528 | 0 | 0 | 2780816.3249 | 459173 | 2780816.3249 | 459173 | 2026-07-08 23:35:04 +0530 | Savita Parab | Execution: Floor covering done electrical wiring done carpenter paneling done False ceiling done first coat done lights and fan installation in progress modular delivered and installation in progress civil in cx scope for platform installation vedor delay from last 15days | 2026-06-16 14:30:52 +0530 | Savita Parab | Execution: Floor covering done electrical wiring done carpenter paneling done False ceiling done first coat in progress site is ready for material dispatch | 2026-06-10 13:23:16 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-05 | 2026-03-04 19:26 | 2026-03-13 | 2026-03-12 13:44
18352 | Turnkey | 2026-01-01 | Shailendra Singh | Runwal Sanctuary | MUM - Thane | Yes | Hemant Sonar | Anamika Dolai | Anil Kuwar |  | Krutika Date | suraj kumar | Akshat Shrivastava | Murali S | Nishtha Valawalkar | Shailendra Mishra | Active | Production | Dispatch Due | 1576538 | 1576538 | 1839969 | 0 | 1576538 | 20 | 35 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-08 20:21 | 2026-02-11 | 2026-02-11 12:02 | 2026-02-15 | 2026-02-17 15:29 | 2026-03-07 | 2026-03-11 13:23 | 2026-05-08 |  | 2026-05-17 | 2026-05-18 11:07 | 2026-02-17 | 2026-02-18 19:20 | 2026-02-18 | 2026-02-18 19:20 | 2026-02-18 | 2026-02-20 14:39 | 2026-02-26 | 2026-02-26 17:25 |  |  |  |  | 2026-03-11 | 2026-03-13 11:40 | 2026-05-10 | 2026-05-13 16:48 | 2026-05-14 | 2026-05-13 16:48 |  |  | 2026-05-20 | 2026-05-22 19:50 | 2026-05-26 | 2026-05-26 17:27 | 2026-05-27 | 2026-05-26 17:31 | 2026-05-27 | 2026-05-28 19:03 |  |  |  |  | 2026-06-11 01:50 | 2026-06-17 | 2026-06-16 21:27 | 2026-06-27 | 2026-06-25 17:45 | 2026-06-26 | 2026-06-25 19:12 | 2026-06-25 |  | 2026-06-30 |  | 2026-07-02 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-08-15 | [5 empty] | 2026-06-06 | 2026-06-11 01:49 | 2026-03-18 | 2026-03-07 12:13 | Site is RTMI | 2026-02-08 | 2026-02-08 20:20 | 1559296 | 280673 | 0 | 0 | 1570492.8053 | 270997 | 1570492.8053 | 270997 | 2026-07-08 12:03:08 +0530 | suraj kumar | Site report: ( Delay from Cx side) - The floor covering work has been completed. ( Other PI work is in Cx scope) - Wall base preparation work is in progress. ( ETA- 10th July) | 2026-05-07 17:49:21 +0530 | Anil Kuwar | Some Image was uploaded | 2026-03-13 15:34:40 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-03-07 | 2026-03-11 13:51 | 2026-05-09
18353 | Turnkey | 2026-01-01 | Kirti Jindal | Radha Vallabh | MUM - GOR | Yes | Priyanka Patel |  | Shraddha Badgujar | [5 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 3454340 | 9999 | 3454340 | 0 | 0 | 150 | 0 | 335435 | 345434 | 1520294 | 1243178.4 |  |  | 2026-02-08 | 2026-02-15 12:12 | 2026-02-15 | 2026-02-15 12:24 | 2026-02-15 | 2026-02-15 13:33 | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  | 2026-02-15 |  | 2026-02-16 |  | 2026-02-16 |  | 2026-02-17 | [5 empty] | 2026-02-23 |  | 2026-03-03 |  | 2026-03-04 |  |  |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-14 | [6 empty] | 2026-04-01 |  | 2026-04-10 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-13 |  |  |  | 2026-05-05 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-03-12 |  | 2026-02-18 |  | Unknown | 2026-02-08 | 2026-02-10 11:58 | 2927407 | 526933 | 0 | 0 | 0 | 0 | 2927407 | 526933 | [9 empty] | 2026-02-23 |  | 2026-03-02
18355 | Turnkey | 2026-01-01 | siddhart Dass | kalpataru shrishti namah | MUM - GOR | Yes | Rahul Agrawal |  | Shahid Chougley | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 2195202 | 9999 | 2195202 | 0 | 0 | 145 | 0 | 209521 | 219520 | 1033225 | 722936.4 |  |  | 2026-02-08 | 2026-02-20 16:18 | 2026-02-20 | 2026-02-20 16:28 | 2026-02-20 | 2026-02-20 16:47 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-08 | 2026-02-08 20:03 | 2028236.363 | 334861 | 0 | 0 | 0 | 0 | 2028236.363 | 334861 | [9 empty] | 2026-02-28 |  | 2026-03-07
18356 | Turnkey | 2026-01-01 | Chirag Jain | Ekta | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 1800483 | 9999 | 1800483 | 0 | 0 | 145 | 0 | 170049 | 180048 | 762971 | 677415.2 |  |  | 2026-02-08 | 2026-02-11 15:35 | 2026-02-19 | 2026-02-19 22:38 | 2026-02-22 | 2026-02-20 15:15 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-08 | 2026-02-11 15:34 | 1525833 | 274649 | 0 | 0 | 0 | 0 | 1525833 | 274649 | 2026-02-12 12:31:25 +0530 | Yash Jain | Some Image was uploaded | [6 empty] | 2026-02-28 |  | 2026-03-07
18357 | Turnkey | 2026-01-01 | Ramcharan | AVANI ABODE | BNG - HRBR | Yes | Palak Thakur | Rajeshwari S | [6 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 2576123 | 9999 | 2576123 | 0 | 0 | 112 | 0 | 247613 | 257612 | 1083387 | 977511.2 |  |  | 2026-02-08 | 2026-02-16 13:25 | 2026-02-15 | 2026-02-16 17:55 | 2026-03-01 | 2026-03-25 18:48 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-02-08 | 2026-02-10 11:28 | 2183155 | 392968 | 0 | 0 | 0 | 0 | 2183155 | 392968 | 2026-02-15 19:10:02 +0530 | Palak Thakur | Minutes of Meeting held on Date: Title:rgm Project:avani abode Client: MR.Ramcharan and mrs indu -son tejas Attendees:MR.Ramcharan and mrs indu -son tejas Objective:rgm Discussion Based on <15/02/26> meeting, below is a list of all the requirements that were discussed during the meeting: FINAL MOM -2026 PID- Client Name: RamcharanÂ and indu and son tejas ( family of 3 ) Â Property: vavani abode CONFIRGURATION 4bhk villa Â Floor: g+2 Â Main Door Facing: east facing entrance when going outside Â Possession: After 6 months HANDOVER EXPECTED before december /or after jan 15th ( not be be btw dec 15Â to jan 15) Ceiling height to be considered as 9'6" approx Budhgari cross closer to Current residence is also near by PROFESSION softaware manager ( lam research ) Assistant professior (junior colledge) engineering college Son age 9 class 4th PURPOSE own living ( outer structiure is complete + plumbing ) Inner works are not done including tiling Â Lighting control from phone Family Details Budget 15 to 20 (master bed and sofa and swingÂ in living to be considered in costing ) Theme Design Preferences Colors, Finishes & Lighting Kitchen: abstract luxe Living Area: abstract luxe Overall Preference: peacefula nd un cluttered with good design Kitchen Countertop: quartz Lighting:sutle Ceiling: only living dining Bedroom 1st floor ( 02 master bedroom ) No to wooden flooring Electrical to be accomodated King bed ( bigger than king ) custom bed 7' x7' No false ceiling ( explosed ceiling concept ) good lighting 4 feet window middle of the wall Â Partition for walk in wardrobe ( Wardrobe sliding on both side Â Dressser unit + mirror Â No tv unit Open concepts Â End to end curtains Â Toilet Master Base storage + led mirror More height Partition shower Box room Aqauariun and budha statue with console Office space Office space For 2Â 32" monter (1-2 montor) 5 6 feet study 1 study table Â 1 bookshelf Good lighting Bedroom 1st floor ( 03 kids bedroom ) Wardrobe fancy ( with display for decorative Â StudyÂ unit with wall stoarge Football /cricket / badminton FootballÂ more emphasis Queen bed Â RedÂ fav color 2 side table space can be planed for tall display Shelves for prizes above bed Good ceiling light ( disco light) Curtain wall Wall light to be continued for disco light Staircase Sequenced wall works kids toilet Wall storage with mirror Home theatere Window is shifted 2 window on 1 wall Â And 1 wall without window (small window side) 100" tv Sound bar Â Speakers on both sides Â Buffer Bar counter on other Wall unitÂ + wall concepts Wallpaper 2 recliner 2 seater Track light needed Family and gym Standing pooja 4-5 feet pooja unit Closed door pooja Storage wardrobe + base storage Swing seatingÂ Toilet 2nd floor Â Door is shifted to the side Base storage + led mirror More height Open terrace Janitor unit Â + storage with detergents Childhood journey wall to be designed emphasis on tejas Dining Area (perphery + wooden paneling ceiling ) Chandilier concept on wooden paneling in ceiling 1 tall unit + base unit concept for crockery Below stair case 1 1 vanity basin And corner to be used as storage for 1 cylinder + extra stoarge Â Living areaÂ (perphery + wooden paneling ceiling ) 50" tv More asthetic than storage Some book storage ( open and frosted glass) Some laptopn space might have Â Sofa side wall to be consideredÂ for statement wall ( embroosed radha on wall to be preferedÂ with good lighting Â 3 + 2 sofa HeightedÂ more in standard both sofa nd tv base uniit Foyer area Partition with storageÂ and ligtingÂ amd console unitÂ with budha idol Shoe storeage outsideÂ (if possible ) 1 feet space in corner o4 long Â stretched Â Initial (R and I) to be designed for entrance bedroom ground floor ( guest bedroom ) Partition wall to dressing is not present Wardrobe bay window seating with dresser unit same as Â Bed ( king existing ) HingeÂ + loft ( more of a display unit ) (half wardrobe + half crockery) Â Dresser can be on one side and mirror on another Â Bed back wall ( wall concept G toilet Wall storage with mirror Kitchen 2 door fridge outside kitchen ( position not finalized ) Â Counter top quartz to be considered 2bowl sink ( existing ) Handless less Open + glass + clsed concept Dishwasher on side of sink countop place to be extended Hob unit 3' Â Base + wall + loft units 1 pantry + 1 appliance unit ( micro + otg ) Fridge either in kitchen or near the entrance Â Aqua unit in bottom and heater in top exposed Utility Area 1 cylinder in the utility and 1sink unit in baseÂ Wall is not presenr wall closed unit can be planned later SinkÂ side top dishdraner Cylinder side wall open + closed concept | [6 empty] | 2026-04-02 |  | 2026-04-09
18358 | Turnkey | 2026-01-01 | Mrinmay Shekhar | Royal view | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1468231 | 9999 | 1804155 | 0 | 0 | 138 | 0 | 136824 | 146823 | 615075 | 559509.6 |  |  | 2026-02-08 | 2026-02-10 11:28 | 2026-02-12 | 2026-02-11 18:22 | 2026-02-21 | 2026-02-27 13:11 | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-02-27 |  | 2026-02-28 |  | 2026-02-28 |  | 2026-03-01 | [5 empty] | 2026-03-07 |  | 2026-03-15 |  | 2026-03-16 |  |  |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 | [6 empty] | 2026-04-13 |  | 2026-04-22 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-25 |  |  |  | 2026-05-17 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-03-24 |  | 2026-03-02 |  | Unknown | 2026-02-08 | 2026-02-08 23:01 | 1528945 | 275210 | 0 | 0 | 0 | 0 | 1244264 | 223967 | 2026-02-27 13:14:38 +0530 | Saranya Thiyagarajan | CDP: Client coming for CDP Rediscussion on 28/02/26 | 2026-02-11 18:23:30 +0530 | Saranya Thiyagarajan | 1.west facing 2.Shoe storage 3.tv - opposite wall 4.kitchen- Tall unit and microwave ,air fryer,mixer, rice cooker and granite and cylinder cabinet 5.Utility- wm,Sink cabinet,sink,DW, Top cabinets 6.6 seater 7.MBR- open wardrobe and tv cabinets study table and small book shelves or book corner, dresser 8.NE corner- dining area- pooja unit 9.Gbedroom- Wardrobe, Tv unit, Study table and cabinets and dresser 10.vanity units 11.Pastel shades 12.8 to 10 lakhs 13.peripheral false ceiling 14.modern theme 15.charcoal beading Utility wall- crockery unit |  |  |  | 2026-03-07 |  | 2026-03-14
18359 | Turnkey | 2026-01-01 | Anuj Sunil Shah | 7 dhuleva | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Nilesh Patel | Rizwan Mistry | Murali S | Umang Shah | Vinay Surve | Active | Installation | Execution | 1412025 | 1412025 | 1530465 | 0 | 1406329 | 17 | 8 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-08 20:35 | 2026-02-10 | 2026-02-11 11:45 | 2026-02-11 | 2026-02-11 13:29 | 2026-03-04 | 2026-03-04 11:42 | 2026-03-27 | 2026-03-26 19:22 | 2026-04-08 | 2026-04-08 19:59 | 2026-02-11 | 2026-02-11 15:23 | 2026-02-12 | 2026-02-12 12:18 | 2026-02-12 | 2026-02-13 13:09 | 2026-02-15 | 2026-02-15 12:12 |  |  |  |  | 2026-03-04 | 2026-03-26 19:04 | 2026-03-27 | 2026-04-02 13:32 | 2026-04-03 | 2026-04-02 13:32 |  |  | 2026-04-11 | 2026-04-16 14:46 | 2026-04-17 | 2026-04-17 15:33 | 2026-04-17 | 2026-04-18 11:57 | 2026-04-19 | 2026-04-29 18:12 |  |  |  |  | 2026-05-06 17:16 | 2026-05-29 | 2026-05-28 19:20 | 2026-06-18 | 2026-06-16 18:54 | 2026-06-17 | 2026-06-20 18:01 | 2026-06-16 | 2026-06-24 16:20 | 2026-06-23 | 2026-06-28 00:28 | 2026-06-30 | 2026-07-11 13:17 |  |  | 2026-06-20 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-04-17 | 2026-05-06 10:27 | 2026-02-16 | 2026-02-18 21:11 | Site is RTMI | 2026-02-08 | 2026-02-08 20:18 | 1724510.465 | 270071 | 0 | 0 | 1607422.4813 | 251135 | 1616636.7813 | 252003 | 2026-07-13 11:31:40 +0530 | Nilesh Patel | Modulars Installation works is in Progress Scope only Modulars and Plywood panelling | 2026-06-18 17:06:25 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-02 17:27:52 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-05 | 2026-03-04 12:48 | 2026-03-27 | 2026-03-26 19:22
18361 | Turnkey | 2026-01-01 | Edward Cooper | Roswalt Zaiden | MUM - Thane | No Estimate | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-12 14:22 | 2026-02-09 |  | 2026-02-14 |  | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-02-14 |  | 2026-02-15 |  | 2026-02-15 |  | 2026-02-16 | [5 empty] | 2026-02-22 |  | 2026-03-02 |  | 2026-03-03 |  |  |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-13 | [6 empty] | 2026-03-31 |  | 2026-04-09 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-12 |  |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | 2026-03-11 |  | 2026-02-17 |  | Unknown | 2026-02-08 | 2026-02-11 16:39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-02-22 |  | 2026-03-01
18362 | Turnkey | 2026-01-01 | Ananya Kulkarni | Lodha crown | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam |  |  | Tanveer Patel | Akshat Shrivastava | Murali S | Aryan Singh | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 874867 | 877634.55 | 1152490 | 0 | 874867 | 9 | 68 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-08 22:28 | 2026-02-13 | 2026-02-13 11:40 | 2026-02-13 | 2026-02-13 11:52 | 2026-06-11 | 2026-06-10 18:15 | 2026-06-11 | 2026-06-10 19:29 | 2026-06-15 | 2026-06-14 17:27 | 2026-02-13 | 2026-02-16 17:57 | 2026-02-14 | 2026-02-16 18:03 | 2026-02-16 | 2026-02-27 18:14 | 2026-03-05 | 2026-03-05 11:45 |  |  |  |  | 2026-07-20 | 2026-06-10 19:21 | 2026-06-11 | 2026-06-13 09:25 | 2026-06-14 | 2026-06-13 09:25 |  |  | 2026-06-17 | 2026-06-19 20:48 | 2026-06-19 | 2026-06-19 21:03 | 2026-06-20 | 2026-06-19 21:34 | 2026-06-20 | 2026-06-20 15:24 |  |  |  |  | 2026-06-25 12:23 | 2026-07-01 | 2026-06-30 20:02 | 2026-07-06 | 2026-07-06 14:02 | 2026-07-05 | 2026-07-05 14:57 | 2026-07-10 | 2026-07-13 15:31 | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-19 | 2026-06-20 15:47 | 2026-07-15 | 2026-06-10 18:03 | Site is RTMI | 2026-02-08 | 2026-02-08 20:41 | 976686 | 175803 | 0 | 0 | 894655.3777 | 148708 | 894655.3777 | 148708 | 2026-06-20 15:57:18 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-11 19:36:57 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-11 19:33:54 +0530 | Sakshi Pokharkar | DDM3: 11/06/2026 IN PERSON MEETING LIVINGROOM * As discussed selected 3 seater sofa is not possible due to the less space available, suggested 2 seater and 1 single chair not in bonito scope, buying from outside. * 48" tv size assumed and one shelf added above the tv same size of tv. * dining table size reduced to 3'8"Â * seating with storage is removed as you want moveable puff's buying from outside. GUEST BEDROOM * Due to high cost wardrobe is removed. * END TO END box loft added at left side of the entrance wall. * Bathroom top storge removed.(both bathrooms) MASTER BEDROOM Another bed selected for free bed offer fabric is also finalized. KITCHEN * Hob side loft removed due to the exhaust fan and gas pipe and meter. * END TO END box loft added in the space between the sunk slab. * Oven Unit shifted above by client request- suggested not to shift but client want's to shift above at the same level of wall units, and open unit above the oven unit. Painting in clients scope color code will be shared from our end. | 2026-06-11 | 2026-06-10 18:50 | 2026-06-11 | 2026-06-10 19:30 | Under Construction | 2026-04-01
18365 | Turnkey | 2026-01-01 | Rukaiya | Roswalt Zaiden | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Design | DEM1 | 833128 | 109999 | 1016249 | 0 | 0 | 45 | 102 | 0 | 56627 | 407048 | 259454 |  |  | 2026-02-08 | 2026-02-10 19:22 | 2026-02-10 | 2026-02-10 19:47 | 2026-02-11 | 2026-02-11 18:20 | 2026-12-11 |  | 2026-12-18 |  | 2026-12-25 |  | 2026-02-11 | 2026-02-16 19:39 | 2026-02-12 | 2026-02-16 19:50 | 2026-02-16 | 2026-02-18 15:39 | 2026-02-20 | 2026-02-20 11:44 |  |  |  |  | 2026-12-12 |  | 2026-12-20 |  | 2026-12-21 |  |  |  | 2026-12-28 |  | 2026-12-29 |  | 2026-12-30 |  | 2026-12-31 | [6 empty] | 2027-01-18 |  | 2027-01-27 |  | 2027-01-26 |  | 2027-01-27 |  | 2027-01-28 |  | 2027-01-30 |  |  |  | 2027-02-21 |  | 2027-02-23 |  | 2027-02-24 | [5 empty] | 2026-12-29 |  | 2026-09-07 |  | Unknown | 2026-02-08 | 2026-02-10 19:21 | 861228 | 155021 | 0 | 0 | 0 | 0 | 843145.4119 | 142341 | 2026-04-04 14:20:18 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-29 11:38:12 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-11 10:31:42 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-12-12 |  | 2026-12-19 |  | Under Construction | 2026-07-01
18366 | Sub Project |  | M S INDIA STEEL TRADERS / S R CONSTRECTION (Shahbaz Ahmed) | Alabbas | MUM - Thane |  |  |  | Rushika More | [7 empty] | Active | Prospect | DCM Due | 56696 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 56336 | 360 |  |  | 2026-02-09 | 2026-02-13 | 2026-02-10 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-20 | 2026-02-13 | 2026-02-27 | 2026-02-13 | 2026-03-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-13 | 2026-02-14 | 2026-02-13 | 2026-02-15 | 2026-02-13 |  |  |  |  | 2026-02-21 | 2026-02-13 | 2026-03-01 | 2026-02-13 | 2026-03-02 | 2026-02-13 |  |  | 2026-03-09 | 2026-02-13 | 2026-03-10 |  | 2026-03-11 |  | 2026-03-12 | [30 empty] | 2026-03-10 |  | 2026-02-16 | 2026-02-13 | Unknown | 2026-02-09 | 2026-02-13 | 0 | 0 | 0 | 0 | 0 | 0 | 52285 | 9411 | [9 empty] | 2026-02-21 | 2026-02-13 | 2026-02-28 | 2026-02-13
18367 | Turnkey | 2026-01-01 | Reyana NAHID SABIR ALI RAFI | Roswalt Zaiden | MUM - GOR | Yes | Sweta Bhise |  | Shahid Chougley | [5 empty] | Avi Thakkar |  | Active | Prospect | 10% Payment | 1063850 | 139999 | 1398707 | 0 | 0 | 138 | 0 | 0 | 72771 | 439362 | 411717.6 |  |  | 2026-02-09 | 2026-02-27 17:33 | 2026-02-17 | 2026-02-27 17:45 | 2026-03-02 | 2026-04-09 14:36 | 2026-04-16 |  | 2026-04-23 |  | 2026-04-30 |  | 2026-04-09 | 2026-02-28 | 2026-04-10 |  | 2026-04-10 |  | 2026-04-11 | [5 empty] | 2026-04-17 |  | 2026-04-25 |  | 2026-04-26 |  |  |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-06 | [6 empty] | 2026-05-24 |  | 2026-06-02 |  | 2026-04-24 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-05 |  |  |  | 2026-06-27 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-05-04 |  | 2026-04-12 |  | Unknown | 2026-02-09 | 2026-02-12 11:04 | 1185345 | 213362 | 0 | 0 | 0 | 0 | 1154174.733 | 185163 | 2026-04-09 18:47:13 +0530 | Sahil Sethi | Some Image was uploaded | 2026-04-09 16:48:58 +0530 | Sahil Sethi | Some Image was uploaded | 2026-02-25 17:55:46 +0530 | Sahil Sethi | Some Image was uploaded | 2026-04-17 |  | 2026-04-24
18368 | Turnkey | Dec'25 | WERMORE SOLUTIONS PVT LTD | Raymond | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Faraz Soudagar | Aditya Vikram | Murali S | Prashant Panigrahi | Aakash Gaikwad | Active | Handover | Project Closure Pending | 669469 | 669470 | 1747130 | 1444938 | 669469 | 15 | 15 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-10 19:06 | 2026-02-08 | 2026-02-10 19:14 | 2026-02-14 | 2026-02-11 13:02 | 2026-02-23 | 2026-02-21 11:29 |  |  |  |  | 2026-02-14 | 2026-02-13 18:37 | 2026-02-15 | 2026-02-13 18:56 | 2026-02-15 | 2026-02-16 13:17 | 2026-02-16 | 2026-02-17 11:23 | 2026-02-21 | 2026-02-21 13:18 | 2026-02-24 | 2026-02-21 13:21 | 2026-03-07 | 2026-02-19 18:03 | 2026-02-23 | 2026-02-22 17:47 | 2026-02-23 | 2026-02-22 18:15 |  |  | 2026-02-24 | 2026-02-26 22:11 | 2026-02-27 | 2026-02-27 17:46 | 2026-03-02 | 2026-02-28 12:59 | 2026-03-05 | 2026-03-14 21:32 |  |  |  |  | 2026-04-07 16:53 | 2026-05-04 | 2026-04-30 22:20 | 2026-05-25 | 2026-05-22 19:21 | 2026-05-20 | 2026-05-21 18:30 | 2026-05-22 | 2026-05-26 17:13 | 2026-05-27 | 2026-06-01 13:36 | 2026-06-03 | 2026-06-16 13:21 |  |  | 2026-07-09 | 2026-06-30 19:35 | 2026-07-11 | 2026-06-30 19:35 | 2026-07-12 | 2026-06-30 19:54 |  |  |  |  | 2026-03-31 | 2026-04-07 16:52 | 2026-02-17 | 2026-02-21 11:27 | Site is RTMI | 2026-02-07 | 2026-02-10 12:05 | 1480618 | 266511 | 1517349.1402 | 250922 | 726466.3505 | 117376 | 726466.3505 | 117376 | 2026-06-27 16:40:35 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-23 22:32:47 +0530 | Faraz Soudagar | Execution: short supply delivery done - 23rd june Installation ETA - 25th June Deep cleaning - 26th June QC - 28th June HO - 28th June | 2026-06-01 14:30:38 +0530 | Faraz Soudagar | Execution: modular delivery done - 29th may Modular team not aligned
18374 | Turnkey | 2026-01-01 | Jagadeesh Katta | Adarsh Green | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Banka H Suthar | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Handover | Project Closure Pending | 1084754 | 1084755 | 788108 | 0 | 1080475 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-10 | 2026-02-19 13:14 | 2026-02-19 | 2026-02-19 13:39 | 2026-02-24 | 2026-02-24 11:59 | 2026-04-04 | 2026-04-03 15:52 | 2026-04-16 | 2026-04-15 19:34 | 2026-04-27 | 2026-04-27 13:24 | 2026-02-22 | 2026-02-19 17:16 | 2026-02-25 | 2026-02-24 15:41 | 2026-02-24 | 2026-02-24 16:30 | 2026-02-25 | 2026-02-25 16:46 |  |  |  |  | 2026-04-05 | 2026-04-15 18:53 | 2026-04-16 | 2026-04-19 01:51 | 2026-04-20 | 2026-04-19 02:25 |  |  | 2026-04-29 | 2026-04-30 11:58 | 2026-04-30 | 2026-04-30 20:42 | 2026-05-01 | 2026-04-30 21:05 | 2026-05-24 | 2026-05-05 14:33 |  |  |  |  | 2026-05-06 12:56 | 2026-05-15 | 2026-05-15 22:43 | 2026-05-27 | 2026-05-25 18:40 | 2026-05-31 | 2026-05-05 18:53 | 2026-05-25 | 2026-05-27 15:19 | 2026-05-27 | 2026-05-28 18:20 | 2026-06-03 | 2026-06-02 13:48 |  |  | 2026-06-30 | 2026-06-29 11:47 | 2026-07-02 | 2026-06-30 20:48 | 2026-07-03 | 2026-06-30 21:23 |  |  |  |  | 2026-05-22 | 2026-05-06 12:55 | 2026-03-07 | 2026-03-26 13:22 | Site is RTMI | 2026-02-10 | 2026-02-10 16:33 | 821968.6944 | 135474 | 0 | 0 | 1191335.566 | 187699 | 1198258.166 | 188352 | 2026-07-07 00:50:59 +0530 | Saddam Hussain Z M | Execution: Observation Points - 16th July | 2026-06-15 13:15:48 +0530 | Saddam Hussain Z M | Some Image was uploaded | 2026-06-15 11:49:29 +0530 | Saddam Hussain Z M | Some Image was uploaded | 2026-04-04 | 2026-04-03 16:25 | 2026-04-16 | 2026-04-15 19:35
18375 | Turnkey | 2026-01-01 | Pallavi More | Pearl Gardens | MUM - GOR | Yes | Sweta Bhise |  | Shahid Chougley | [5 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 1720585 | 9999 | 0 | 0 | 0 | 148 | 0 | 162060 | 172059 | 725456 | 651012 |  |  | 2026-02-08 | 2026-02-10 12:30 | 2026-02-17 | 2026-02-17 11:20 | 2026-02-20 |  | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-08 | 2026-02-10 12:28 | 0 | 0 | 0 | 0 | 0 | 0 | 1795405.975 | 308224 | [9 empty] | 2026-02-28 |  | 2026-03-07
18377 | Turnkey | 2026-01-01 | Mrig Shekhar | null | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Pulivarthi Nirosha | Raghavendra Gowda | Active | Preproduction | CM | 2065585 | 368382 | 2482832 | 0 | 0 | 2 | 34 | 0 | 0 | 904984 | 792218.8 |  |  | 2026-02-08 | 2026-02-10 15:02 | 2026-02-22 | 2026-02-22 11:11 | 2026-02-25 | 2026-02-24 15:30 | 2026-03-28 | 2026-03-28 15:30 | 2026-07-13 | 2026-07-12 19:47 | 2026-07-19 |  | 2026-02-24 | 2026-02-28 11:54 | 2026-02-25 | 2026-03-02 14:50 | 2026-03-02 | 2026-03-05 16:37 | 2026-03-06 | 2026-03-06 17:48 |  |  |  |  | 2026-03-12 | 2026-03-26 19:26 | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-03-07 | 2026-03-28 10:48 | Site is RTMI | 2026-02-08 | 2026-02-10 15:01 | 2104095 | 378737 | 0 | 0 | 0 | 0 | 2254690.503 | 372292 | 2026-06-04 12:25:23 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-04-10 17:07:51 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-10 17:04:04 +0530 | Abhinandan K S | Some Image was uploaded | 2026-03-29 | 2026-03-28 15:34 | 2026-07-13
18378 | Turnkey | 2026-01-01 | swapnil jaid | Wadhwa atmosphere O2 | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh |  |  |  | Moni Sahani | Aakash Gaikwad | Lost | Preproduction | 2D | 1790125 | 272464 | 1362321 | 0 | 0 | 54 | 0 | 0 | 0 | 862645 | 655015.6 |  |  | 2026-02-07 | 2026-02-17 14:32 | 2026-02-18 | 2026-02-18 15:13 | 2026-02-18 | 2026-02-18 16:09 | 2026-04-05 | 2026-04-05 12:06 | 2026-04-18 | 2026-05-12 12:25 | 2026-05-20 | 2026-05-20 19:37 | 2026-02-18 | 2026-02-18 18:35 | 2026-02-19 | 2026-02-18 18:35 | 2026-02-18 | 2026-02-20 16:09 | 2026-02-25 | 2026-02-25 15:30 |  |  |  |  | 2026-04-05 | 2026-04-14 16:41 | 2026-05-14 | 2026-05-15 11:22 | 2026-05-16 | 2026-05-15 11:22 |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 | [6 empty] | 2026-07-22 |  | 2026-07-31 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-03 |  |  |  | 2026-08-25 |  | 2026-08-27 |  | 2026-08-28 | [5 empty] | 2026-07-02 |  | 2026-02-26 | 2026-03-12 16:02 | Site is RTMI | 2026-02-07 | 2026-02-10 13:28 | 1411662.6564 | 238320 | 0 | 0 | 0 | 0 | 1878256.6046 | 318832 | 2026-07-03 19:51:31 +0530 | Reshma Melanta | Others: | 2026-06-05 19:16:14 +0530 | Christopher Macwan | Some Image was uploaded | 2026-06-02 17:01:32 +0530 | Reshma Melanta | HEENA NEEDS TO MENTION NOTE AND WRITE A RCA FOR THE SAME. THE CX HAS ALREADY MAILED TO WECARE FOR THE ISSUE THAT THEIR FACED | 2026-04-06 | 2026-04-05 12:08 | 2026-05-13 | 2026-05-12 12:27 | Under Construction | 2026-04-01
18379 | Turnkey | 2026-01-01 | Pankaj Jain | Urban Grandeur | MUM - GOR | Yes | Priyanka Patel |  | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 1676018 | 9999 | 0 | 0 | 0 | 155 | 0 | 157603 | 167602 | 765197 | 575617.2 |  |  | 2026-02-10 | 2026-02-10 16:16 | 2026-02-15 |  | 2026-02-18 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-02-18 |  | 2026-02-19 |  | 2026-02-19 |  | 2026-02-20 | [5 empty] | 2026-02-26 |  | 2026-03-06 |  | 2026-03-07 |  |  |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-17 | [6 empty] | 2026-04-04 |  | 2026-04-13 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-16 |  |  |  | 2026-05-08 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-03-15 |  | 2026-02-21 |  | Unknown | 2026-02-10 | 2026-02-10 15:24 | 0 | 0 | 0 | 0 | 0 | 0 | 1695778 | 305240 | [9 empty] | 2026-02-26 |  | 2026-03-05
18381 | Turnkey | 2026-01-01 | Kiran Kumar | Avalon Park @ The Prestige City | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Suchendra Shetty | Jairam Joshi | Murali S | Raghavendra S | Abdul Shafeen | Completed | Complete | Completed | 1175991 | 1175992 | 1151556 | 1176218 | 1171283 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-10 | 2026-02-11 15:58 | 2026-02-18 | 2026-02-18 15:51 | 2026-02-21 | 2026-02-27 06:33 | 2026-04-11 | 2026-04-11 19:11 | 2026-04-18 | 2026-04-17 18:49 |  |  | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-03-07 11:42 | 2026-03-07 | 2026-03-10 17:50 | 2026-03-20 | 2026-03-20 19:52 |  |  |  |  | 2026-04-11 | 2026-04-14 19:01 | 2026-04-18 | 2026-04-19 18:53 | 2026-04-20 | 2026-04-19 19:17 |  |  | 2026-04-24 | 2026-04-28 13:00 | 2026-04-29 | 2026-04-29 16:56 | 2026-04-30 | 2026-04-29 17:13 | 2026-04-30 | 2026-04-30 19:30 |  |  |  |  | 2026-05-02 15:10 | 2026-05-08 | 2026-05-08 13:31 | 2026-06-01 | 2026-05-30 19:32 | 2026-05-16 | 2026-05-13 19:23 | 2026-05-30 | 2026-06-01 17:57 | 2026-06-01 | 2026-06-01 18:02 | 2026-06-06 | 2026-06-05 13:36 |  |  | 2026-06-23 | 2026-06-24 21:17 | 2026-06-25 | 2026-06-24 21:24 | 2026-06-26 | 2026-06-24 21:42 |  |  |  |  | 2026-04-29 | 2026-05-02 15:09 | 2026-04-10 | 2026-04-11 10:36 | Site is RTMI | 2026-02-10 | 2026-02-10 17:00 | 1107390 | 199330 | 1288947.053 | 203829 | 1280755.4087 | 203077 | 1288375.4087 | 203795 | 2026-06-25 17:10:37 +0530 | Jairam Joshi | Project Closure Pending: Observation points Closure ETA -9th July | 2026-06-16 18:30:31 +0530 | Jairam Joshi | Some Image was uploaded | 2026-06-05 02:03:17 +0530 | Jairam Joshi | Some Image was uploaded | 2026-04-12 | 2026-04-11 19:13 | 2026-04-18 | 2026-04-17 19:01
18383 | Turnkey | 2026-01-01 | Prashant Shekhar | Meridian Park @ The Prestige City | BNG - HSR | Yes | Priyanka Inchoor | Abhinandan K S | Kowshik |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Varun Mandana | Affaan Abdulla | Completed | Complete | Completed | 1247567 | 1247568 | 1746186 | 1225238 | 1247567 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-10 | 2026-02-12 18:47 | 2026-02-12 | 2026-02-24 11:14 | 2026-02-24 | 2026-02-24 12:31 | 2026-04-12 | 2026-04-12 18:06 | 2026-04-15 | 2026-04-14 15:30 | 2026-04-18 | 2026-04-18 16:39 | 2026-02-24 | 2026-02-28 11:53 | 2026-02-25 | 2026-03-06 12:57 | 2026-03-06 | 2026-03-12 11:38 | 2026-03-20 | 2026-03-20 19:49 |  |  |  |  | 2026-04-12 | 2026-04-14 13:14 | 2026-04-15 | 2026-04-17 16:38 | 2026-04-18 | 2026-04-17 16:38 |  |  | 2026-04-19 | 2026-04-19 19:08 | 2026-04-19 | 2026-04-19 22:11 | 2026-04-20 | 2026-04-24 11:45 | 2026-04-25 | 2026-04-28 11:28 |  |  |  |  | 2026-04-28 15:33 | 2026-05-06 | 2026-05-05 21:22 | 2026-05-23 | 2026-05-20 13:05 | 2026-05-21 | 2026-05-26 18:10 | 2026-05-20 | 2026-05-29 16:37 | 2026-05-29 | 2026-05-30 11:51 | 2026-06-05 | 2026-06-04 14:42 |  |  | 2026-06-23 | 2026-06-24 21:12 | 2026-05-30 | 2026-06-24 21:16 | 2026-06-24 | 2026-06-24 21:20 |  |  |  |  | 2026-04-19 | 2026-04-28 15:32 | 2026-04-02 | 2026-04-12 18:02 | Site is RTMI | 2026-02-10 | 2026-02-11 11:34 | 1479819 | 266367 | 1476650.199 | 234188 | 1512869.255 | 241408 | 1512869.255 | 241408 | 2026-06-24 21:22:40 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-06-24 15:47:51 +0530 | Ranjith Kumar | Execution: | 2026-05-25 14:58:55 +0530 | Ranjith Kumar | Cx SideFalse CeilingElectrical Bonito Side only Floor Covering | 2026-04-13 | 2026-04-12 18:08 | 2026-04-15 | 2026-04-14 15:35
18385 | Turnkey | 2026-01-01 | pranay dilip gavhale | Lodha crown Kolshet | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [7 empty] | Hold | Preproduction | DEM2 | 1051359 | 210272 | 0 | 0 | 0 | 17 | 89 | 0 | 0 | 463995 | 377092.4 |  |  | 2026-02-08 | 2026-02-18 12:54 | 2026-02-21 | 2026-02-26 19:26 | 2026-03-01 | 2026-02-26 19:29 | 2026-06-17 | 2026-06-16 11:24 | 2026-07-21 |  | 2026-07-28 |  | 2026-02-24 | 2026-02-25 19:26 | 2026-02-27 | 2026-02-27 14:04 | 2026-02-27 | 2026-03-09 17:54 | 2026-03-10 | 2026-03-10 18:57 |  |  |  |  | 2026-07-30 | 2026-06-15 18:11 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-06-15 | 2026-06-14 17:35 | Site is RTMI | 2026-02-08 | 2026-02-18 12:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1118240.8454 | 178681 | 2026-07-02 18:44:14 +0530 | Anil Jagtap | Hold | 2026-06-14 18:32:27 +0530 | Rachna Abhyankar | Hi Sir/Maam @~Kshama Chavan @~Pranay Gavhale M.O.M. Entrance Base console unit to be added. Crockery unit to be added above the console. Living Room Sofa design to remain the same, with beading on the back wall. TV wall: Louvers to be removed and stucco paint to be done. Mandir unit to be added. Kids Bedroom Layout to remain the same. Loft shutters to be added. Sofa-cum-bed back wall to have a map-themed wallpaper. Master Bedroom Placement to remain the same. Tropical wallpaper on the bedÂ back wall and half dark shadeÂ wardrobe sizes to be reduced and loft to be addedÂ to utilise space above itÂ Louvers to be removed. Kitchen During cross measurements, we need to check the feasibility of the loft cabinets. Please let us know if any further changes are required Thank youÂ Amisha AhujaÂ Interior Designer | 2026-06-14 18:32:13 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-17 | 2026-06-16 11:26 | 2026-07-22 |  | Under Construction | 2026-04-01
18387 | Turnkey | 2026-01-01 | Pratik Shetty | antheya | MUM - Thane | No Estimate | [8 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-08 | 2026-02-11 19:35 | 2026-02-09 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-05-21 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-01 |  | 2026-05-02 | [5 empty] | 2026-05-08 |  | 2026-05-16 |  | 2026-05-17 |  |  |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 | [6 empty] | 2026-06-14 |  | 2026-06-23 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-26 |  |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-05-25 |  | 2026-05-03 |  | Unknown | 2026-02-08 | 2026-02-11 19:21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-05-08 |  | 2026-05-15
18389 | Turnkey | 2026-01-01 | Tony Mary Kuttiachen | Indepenedent House | BNG - HRBR | Yes | Keerthan M |  | Shibin Lal | [5 empty] | Mohammed Rasick |  | Active | Prospect | Onboarding Due | 1543469 | 197515 | 1913539 | 0 | 0 | 131 | 0 | 0 | 111179 | 644321 | 590454.4 |  |  | 2026-02-11 | 2026-02-19 12:56 | 2026-02-12 | 2026-02-23 13:58 | 2026-02-26 | 2026-02-26 11:36 | 2026-03-12 |  | 2026-03-19 |  | 2026-03-26 |  | 2026-02-26 | 2026-02-28 | 2026-02-27 | 2026-03-06 08:41 | 2026-03-06 |  | 2026-03-07 | [5 empty] | 2026-03-13 |  | 2026-03-21 |  | 2026-03-22 |  |  |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 | [6 empty] | 2026-04-19 |  | 2026-04-28 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-05-01 |  |  |  | 2026-05-23 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-03-30 |  | 2026-03-08 |  | Unknown | 2026-02-11 | 2026-02-11 15:54 | 1621644 | 291895 | 0 | 0 | 0 | 0 | 1610677.3933 | 265953 | 2026-05-26 12:46:14 +0530 | Bency Chacko |  | 2026-04-20 12:12:52 +0530 | Bency Chacko |  | 2026-03-06 14:36:43 +0530 | Bency Chacko | Some Image was uploaded | 2026-03-13 |  | 2026-03-20
18392 | Sub Project |  | Manoj Ahire | Lodha Sterling | MUM - Thane |  | Rinisha Masurkar | Divya Rahangdale |  |  |  | Asif Shaikh | Aditya Vikram | Murali S |  | Aakash Gaikwad | Active | Handover | Project Closure Pending | 151040 | 37137 | 0 | 0 | 151040 | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-11 | 2026-03-13 15:23 | 2026-02-12 | 2026-03-13 15:23 | 2026-03-13 | 2026-03-13 15:23 | 2026-03-14 | 2026-03-13 15:25 | 2026-03-14 | 2026-03-13 15:26 | 2026-03-14 | 2026-03-13 15:29 | 2026-03-13 | 2026-03-13 15:24 | 2026-03-14 | 2026-03-13 15:24 | 2026-03-13 | 2026-03-13 15:24 | 2026-03-14 | 2026-03-13 15:24 |  |  |  |  | 2026-03-13 | 2026-03-13 15:25 | 2026-03-14 | 2026-03-13 15:27 | 2026-03-14 | 2026-03-13 15:27 |  |  | 2026-03-14 | 2026-03-14 17:04 | 2026-03-15 | 2026-03-15 15:12 | 2026-03-16 | 2026-03-17 10:56 | 2026-03-18 | 2026-04-10 15:11 |  |  |  |  | 2026-04-11 18:06 | 2026-04-16 | 2026-04-15 18:58 | 2026-04-17 | 2026-04-15 20:06 | 2026-04-13 | 2026-04-10 12:42 | 2026-04-15 | 2026-06-25 22:14 | 2026-06-25 | 2026-06-25 22:14 | 2026-06-26 | 2026-06-25 22:36 |  |  | 2026-06-27 | 2026-06-25 22:44 | 2026-06-27 | 2026-06-25 22:45 | 2026-06-25 | 2026-06-26 07:56 |  |  |  |  | 2026-03-15 | 2026-03-15 15:26 | 2026-03-14 | 2026-03-13 15:25 | Unknown | 2026-02-11 | 2026-03-13 15:23 | 0 | 0 | 0 | 0 | 128000 | 23040 | 128000 | 23040 | [9 empty] | 2026-03-14 | 2026-03-13 15:25 | 2026-03-14 | 2026-03-13 15:26
18393 | Turnkey | 2026-01-01 | Jyothi Salian | kalpataru shrishti namah | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Saloni Chawan |  | Lost | Design | 20% Payment | 1563962 | 152170 | 1521699 | 0 | 0 | 56 | 0 | 0 | 160622 | 625585 | 625584.8 |  |  | 2026-02-11 | 2026-02-11 18:28 | 2026-02-17 | 2026-02-19 00:36 | 2026-02-19 | 2026-02-19 20:22 | 2026-05-21 | 2026-05-20 14:08 | 2026-07-31 |  | 2026-08-07 |  | 2026-02-19 | 2026-02-21 12:27 | 2026-02-20 | 2026-02-24 11:10 | 2026-02-24 | 2026-03-09 11:34 | 2026-03-11 | 2026-03-11 11:12 |  |  |  |  | 2026-10-30 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-06-01 | 2026-05-14 14:17 | Site is RTMI | 2026-02-11 | 2026-02-11 18:27 | 1289576 | 232123 | 0 | 0 | 0 | 0 | 1497547.6987 | 238570 | 2026-06-20 10:49:25 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-16 12:07:05 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-13 12:33:50 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-21 | 2026-05-20 14:09 | 2026-08-01 |  | Under Construction | 2026-04-01
18396 | Turnkey | 2026-01-01 | Vaishali Harurkar | Sky rise 205 | MUM - GOR | Yes | Pratima Kajwe |  | Shraddha Badgujar | [5 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 7279299 | 9999 | 7279299 | 0 | 0 | 133 | 0 | 717931 | 727930 | 3065235 | 2758204 |  |  | 2026-02-11 | 2026-02-12 13:23 | 2026-03-04 | 2026-03-04 11:34 | 2026-03-04 | 2026-03-04 12:08 | 2026-03-11 |  | 2026-03-18 |  | 2026-03-25 |  | 2026-03-04 |  | 2026-03-05 |  | 2026-03-05 |  | 2026-03-06 | [5 empty] | 2026-03-12 |  | 2026-03-20 |  | 2026-03-21 |  |  |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-31 | [6 empty] | 2026-04-23 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-23 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-03-29 |  | 2026-03-07 |  | Unknown | 2026-02-11 | 2026-02-12 12:50 | 6168897 | 1110401 | 0 | 0 | 0 | 0 | 6168897 | 1110401 | 2026-04-10 20:07:34 +0530 | Sanskruti Yadav | Customer was not okay with Payment Terms, He needed flexible payment and 30% retention during execution stage. Her husband is a MHADA contractor and found a very big gap within the civil cost. With the total scope we were exceeding his budget, Vaishali even mentioned she did not like the approach of paying 10% as 6 Lakhs the same day as CDP. She also wanted to see full home renders before making the initial payment to which we were trying to accomodate with a re-CDP, however after giving us a feedback she stopped answering the calls. | 2026-04-10 19:48:56 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-04-10 19:46:38 +0530 | Pratima Kajwe | DCM: Lifestyle1. Please select your budget for Interior Designing? Rs. 25+ Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? Contractor in mhada, Daughter is architect, Son in USA, mother is home-maker 4. Who will be living in this home? Nuclear Family 5. What activities do you usually perform at home? (Choose top 23) Relaxing & Unwinding, Family Bonding, Hosting Guests, Working from Home 6. What is your preferred entertainment style? Large Gatherings, Casual get-togethers 7. Do you prefer any Smart home features? Automation, Lighting Control 8. What is your possession date? ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Seating, Shoe rack, Safety door Dcor & Living Room1. Choose your decor inspirations Plants, Artwork 2. Any specific signature design feature required Art installation, Statement wall, Chandelier 3. Whats the primary use of your living room? Entertaining guests, TV focus 4. Any absolute no-go styles, colors, or materials? 5. Must-have furniture or features? Statement Wall/ Feature, Display unit , Puja unit, Coffee table, Speakers, TV unit, Sofa Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit, Bar unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Washing machine, Dishwasher, Chimney, Hob, Fridge, Microwave, Built-in oven BedroomsMaster Bedroom - Bed type Storage Master Bedroom - Wardrobe style Sliding Master Bedroom - Additional units TV unit, Dresser Other Bedroom - Bed Type Storage Other Bedroom - Wardrobe style Swing , Sliding Other Bedroom - Additional units TV unit, Dresser , Study table BathroomsPreferred vanity style What do you prefer? Shower partitions What are your requirements for Utility Area? Balcony & OutdoorHow do you intend to use your balcony for? Planters, Seating b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? Final Vision1. Any space in the home that you want to put in Spotlight? 2. Do you want the design to reflect any personal story, cultural influence, or special memory | 2026-03-12 |  | 2026-03-19
18397 | Turnkey | 2026-01-01 | Urvi Aradhya | Raheja Vivarea | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Varun Mandana |  | Active | Design | DEM1 | 2941143 | 399259 | 3992592 | 0 | 0 | 12 | 0 | 0 | 188970 | 1196515 | 1156399.2 |  |  | 2026-02-06 | 2026-02-27 10:39 | 2026-03-14 | 2026-03-14 13:46 | 2026-06-23 | 2026-06-23 12:43 | 2026-07-23 |  | 2026-07-30 |  | 2026-08-06 |  | 2026-06-23 | 2026-06-24 18:58 | 2026-06-24 | 2026-07-03 13:25 | 2026-07-03 | 2026-07-03 18:33 | 2026-07-14 | 2026-07-14 13:10 |  |  |  |  | 2026-07-24 |  | 2026-08-01 |  | 2026-08-02 |  |  |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 | [6 empty] | 2026-08-30 |  | 2026-09-08 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-11 |  |  |  | 2026-10-03 |  | 2026-10-05 |  | 2026-10-06 | [5 empty] | 2026-08-10 |  | 2026-07-15 |  | Unknown | 2026-02-06 | 2026-02-12 14:42 | 3383552 | 609039 | 0 | 0 | 0 | 0 | 3302338.2254 | 533005 | 2026-07-03 18:28:09 +0530 | Sanjana Swami | Possession Status: Under construction Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 160+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible. * IM â€“ Anytime as the client has given the contact details of the coordinator for the site measurement * DEM 1 â€“ client wants to have after 6.30pm * 10% Payment Stage â€“ 13th July 2026 *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Referred Customer Bonus Design fee waiver (5%) PM fee waiver (7.5%) May'26 100% GST waiver May'26 laminate Campaign Final Closing Value Discussed: â‚¹ 29,41,143 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-03 13:56:19 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-03 13:42:11 +0530 | Varun Mandana | Others: | 2026-07-24 |  | 2026-07-31 |  | RTMI |  | 2026-06-23 | 399259 | Ravi Roy
18398 | Turnkey | 2026-01-01 | Purushotham | Villa | BNG - HRBR | Yes | Alekhya Korada | Rajeshwari S | Yogesh Patidar | [7 empty] | Active | Prospect | 10% Payment | 3962644 | 9999 | 0 | 0 | 0 | 112 | 0 | 386265 | 396264 | 1692084 | 1478031.2 |  |  | 2026-02-12 | 2026-02-12 17:46 | 2026-03-07 | 2026-03-25 18:19 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-02-12 | 2026-02-12 16:50 | 0 | 0 | 0 | 0 | 0 | 0 | 3358172 | 604471 | 2026-03-25 18:16:55 +0530 | Alekhya Korada | Some Image was uploaded | 2026-03-25 18:16:00 +0530 | Alekhya Korada | Some Image was uploaded |  |  |  | 2026-04-05 |  | 2026-04-12
18400 | Turnkey | 2026-01-01 | AG Dixit | shobha dream Garden | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Active | Installation | Execution | 1143890 | 1143890 | 956014 | 1186697 | 1143890 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-13 | 2026-02-20 19:01 | 2026-02-23 | 2026-02-24 12:16 | 2026-02-25 | 2026-02-26 15:47 | 2026-03-26 | 2026-03-26 13:26 | 2026-04-25 | 2026-04-30 12:51 | 2026-05-12 | 2026-05-12 14:26 | 2026-02-26 | 2026-02-26 16:32 | 2026-02-27 | 2026-02-26 18:02 | 2026-02-26 | 2026-02-28 11:20 | 2026-03-04 | 2026-03-04 13:10 |  |  |  |  | 2026-03-26 | 2026-03-27 19:41 | 2026-05-02 | 2026-05-03 15:55 | 2026-05-04 | 2026-05-03 16:34 |  |  | 2026-05-15 | 2026-05-22 11:26 | 2026-05-22 | 2026-05-22 16:01 | 2026-05-22 | 2026-05-22 17:25 | 2026-05-23 | 2026-05-25 18:44 |  |  |  |  | 2026-05-26 17:04 | 2026-06-04 | 2026-06-03 23:24 | 2026-06-12 | 2026-06-11 12:38 | 2026-06-11 | 2026-06-10 11:31 | 2026-06-11 | 2026-06-12 15:16 | 2026-06-13 | 2026-06-13 10:04 | 2026-06-20 | 2026-06-23 10:02 |  |  | 2026-07-16 |  | 2026-07-18 |  | 2026-07-19 | [5 empty] | 2026-05-22 | 2026-05-26 17:03 | 2026-03-05 | 2026-03-26 13:19 | Site is RTMI | 2026-02-13 | 2026-02-20 19:00 | 810181 | 145832 | 1285716.892 | 203902 | 1246170.696 | 197373 | 1246170.696 | 197373 | 2026-06-23 11:07:40 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 15-06-2026 to 23-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scopeKey Dates: Modular materials dispatched -13th juneHandover as per TAT- 19th july36working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of execution | 2026-06-10 15:57:48 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 26-05-2026 to 2-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scopeKey Dates: Modular materials dispatched - PH will update youHandover as per TAT- TBD36working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of execution | 2026-06-02 07:38:50 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 26-05-2026 to 2-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scope Key Dates: Modular materials dispatched - PH will update youHandover as per TAT- TBD36working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of execution | 2026-03-27 | 2026-03-26 13:30 | 2026-05-01 | 2026-04-30 12:51
18403 | Sub Project |  | Harshan Ravindra Vanjiwale | runawal eirene | MUM - Thane |  | Pooja Nakul Sharma |  | Anil Kuwar |  |  | Faraz Soudagar | Aditya Vikram |  |  | Prasad Bhivaji Hande | Active | Preproduction | 3D Sign off | 66649 | 0 | 0 | 0 | 66649 | 90 | 0 | 0 | 0 | 64289 | 2360 |  |  | 2026-02-13 | 2026-03-27 11:40 | 2026-02-14 | 2026-03-27 11:40 | 2026-03-27 | 2026-03-27 11:41 | 2026-03-28 | 2026-03-27 11:41 | 2026-03-28 | 2026-03-27 11:45 | 2026-04-02 | 2026-03-27 11:46 | 2026-03-27 | 2026-03-27 11:41 | 2026-03-28 | 2026-03-27 11:41 | 2026-03-27 | 2026-03-27 11:41 | 2026-03-28 | 2026-03-27 11:41 |  |  |  |  | 2026-03-27 | 2026-03-27 11:42 | 2026-03-28 | 2026-03-27 11:47 | 2026-03-28 | 2026-03-27 11:47 |  |  | 2026-03-31 | 2026-04-16 13:42 | 2026-04-17 | 2026-04-17 18:11 | 2026-04-18 |  | 2026-04-19 | [6 empty] | 2026-05-07 |  | 2026-05-16 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-19 |  |  |  | 2026-06-10 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-04-17 |  | 2026-03-28 | 2026-03-27 11:41 | Unknown | 2026-02-13 | 2026-03-27 11:40 | 0 | 0 | 0 | 0 | 56482 | 10166 | 56482 | 10166 | [9 empty] | 2026-03-28 | 2026-03-27 11:42 | 2026-03-28 | 2026-03-27 11:45
18405 | Sub Project |  | Rajesh Bane | 100 Trees | MUM - GOR |  | Karan Chavda |  | Shahid Chougley | [7 empty] | Active | Preproduction | 3D Sign off | 96332 | 0 | 0 | 0 | 0 | 126 | 0 | 0 | 0 | 93972 | 2360 |  |  | 2026-02-13 | 2026-03-11 14:16 | 2026-02-14 | 2026-03-11 14:17 | 2026-03-11 | 2026-03-11 14:18 | 2026-03-12 | 2026-03-11 14:19 | 2026-03-12 | 2026-03-11 14:21 | 2026-03-12 | 2026-03-11 14:23 | 2026-03-11 | 2026-03-11 14:18 | 2026-03-12 | 2026-03-11 14:18 | 2026-03-11 | 2026-03-11 14:18 | 2026-03-12 | 2026-03-11 14:19 |  |  |  |  | 2026-03-12 | 2026-03-11 14:20 | 2026-03-12 | 2026-03-11 14:24 | 2026-03-13 | 2026-03-11 14:24 |  |  | 2026-03-20 | 2026-03-11 14:22 | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-03-12 | 2026-03-11 14:19 | Unknown | 2026-02-13 | 2026-03-11 14:16 | 0 | 0 | 0 | 0 | 0 | 0 | 81637 | 14694 | 2026-04-14 12:30:10 +0530 | Reshma Melanta | Some Image was uploaded | [6 empty] | 2026-03-12 | 2026-03-11 14:20 | 2026-03-12 | 2026-03-11 14:21
18408 | Turnkey | 2026-01-01 | Antima Surendra Kumar Yadav | Veena Synergy | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Design | DEM1 | 863465 | 209999 | 1151995 | 0 | 0 | 13 | 125 | 0 | 0 | 330160 | 323306.4 |  |  | 2026-02-13 | 2026-02-19 12:43 | 2026-02-16 | 2026-02-24 11:48 | 2026-02-27 | 2026-02-24 14:59 | 2026-09-06 |  | 2026-09-13 |  | 2026-09-20 |  | 2026-02-24 | 2026-02-24 17:13 | 2026-02-25 | 2026-02-24 19:55 | 2026-02-24 | 2026-02-27 15:40 | 2026-03-05 | 2026-03-05 17:40 |  |  |  |  | 2026-03-04 | 2026-02-24 17:13 | 2026-09-15 |  | 2026-09-16 |  |  |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 | [6 empty] | 2026-10-14 |  | 2026-10-23 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-26 |  |  |  | 2026-11-17 |  | 2026-11-19 |  | 2026-11-20 | [5 empty] | 2026-09-24 |  | 2026-05-05 |  | Unknown | 2026-02-13 | 2026-02-15 16:40 | 976267 | 175728 | 0 | 0 | 0 | 0 | 957908.6112 | 156121 | 2026-05-16 10:43:27 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-15 16:31:43 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-15 16:26:19 +0530 | Vishakha Vaishnav | Tried connecting cx, incoming service is not available | 2026-09-07 |  | 2026-09-14 |  | Under Construction | 2026-04-01
18410 | Turnkey | 2026-01-01 | Sanket mehta | Pearl GArden | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1067291 | 9999 | 0 | 0 | 0 | 137 | 0 | 96730 | 106729 | 475088 | 378744.8 |  |  | 2026-02-13 | 2026-02-19 12:30 | 2026-02-28 | 2026-02-28 08:44 | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 | [5 empty] | 2026-03-08 |  | 2026-03-16 |  | 2026-03-17 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 | [6 empty] | 2026-04-14 |  | 2026-04-23 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-18 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-03-25 |  | 2026-03-03 |  | Unknown | 2026-02-13 | 2026-02-16 17:19 | 0 | 0 | 0 | 0 | 0 | 0 | 904484 | 162807 | 2026-02-19 22:05:22 +0530 | Yash Jain | DCM: PID- Sanket Mehta & Family fam of 3Â client wife and Mom shoe rack outside with seating above 3 seater sofa/ tea table Tv unit minimal with shelves for artifacts and dcor/ plantersÂ 43'' Tv North on top, south below Mandir as per vastu ,bench for viewing area Kitchen Loft units to be added, glass storage instead of existing top wall storage on service platform. Bedroom 1 single bed ,wardrobe ,foldable study table with storage as shown. Master bedroom Wardrobe ,bed attached to window , side dresser, study table foldable. Single curtain vanity with mirror storage in both bathrooms Light shade, , English pastle tones,Â Modern design, safety door | [6 empty] | 2026-03-08 |  | 2026-03-15
18412 | Turnkey | 2026-01-01 | Mehernosh Chhapgar | Lodha Upper Thane | MUM - Thane | Yes | Pooja Nakul Sharma | [7 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1263141 | 9999 | 1263141 | 0 | 0 | 145 | 0 | 116315 | 126314 | 530898 | 479614.4 |  |  | 2026-02-14 | 2026-02-16 16:21 | 2026-02-20 | 2026-02-20 13:19 | 2026-02-21 | 2026-02-24 11:33 | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-02-14 | 2026-02-16 13:45 | 1070458 | 192682 | 0 | 0 | 0 | 0 | 1070458 | 192682 | 2026-02-19 11:39:49 +0530 | Karuna Shinde | Some Image was uploaded | [6 empty] | 2026-03-04 |  | 2026-03-11
18413 | Turnkey | 2026-01-01 | Tanima Darji | Ashford Regal | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1432899 | 9999 | 1432899 | 0 | 0 | 132 | 0 | 133291 | 143290 | 573160 | 573159.6 |  |  | 2026-02-14 | 2026-02-18 15:47 | 2026-03-05 | 2026-03-05 12:54 | 2026-03-05 | 2026-03-05 15:11 | 2026-03-12 |  | 2026-03-19 |  | 2026-03-26 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-07 | [5 empty] | 2026-03-13 |  | 2026-03-21 |  | 2026-03-22 |  |  |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 | [6 empty] | 2026-04-19 |  | 2026-04-28 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-05-01 |  |  |  | 2026-05-23 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-03-30 |  | 2026-03-08 |  | Unknown | 2026-02-14 | 2026-02-14 14:03 | 1214321 | 218577 | 0 | 0 | 0 | 0 | 1214321 | 218577 | [9 empty] | 2026-03-13 |  | 2026-03-20
18414 | Turnkey | 2026-01-01 | Sumant Gajanan Sathe | others | MUM - Thane | Yes | Hemant Sonar | Anamika Dolai | Anil Kuwar |  |  | Asif Shaikh | Akshat Shrivastava | Murali S | Prashant Panigrahi | Prasad Bhivaji Hande | Active | Installation | Execution | 827280 | 827281 | 1217251 | 0 | 827280 | 8 | 18 | 0 | 0 | 0 | 0 |  |  | 2026-02-14 | 2026-02-16 16:20 | 2026-02-19 | 2026-02-19 11:32 | 2026-02-21 | 2026-02-24 11:33 | 2026-03-29 | 2026-03-28 12:33 | 2026-04-16 | 2026-04-15 19:23 | 2026-05-28 | 2026-05-28 19:09 | 2026-02-24 | 2026-02-24 18:34 | 2026-02-25 | 2026-02-24 20:48 | 2026-02-24 | 2026-02-27 13:21 | 2026-03-05 | 2026-03-05 11:49 |  |  |  |  | 2026-03-22 | 2026-03-09 12:17 | 2026-05-16 | 2026-05-20 09:21 | 2026-05-21 | 2026-05-20 09:21 |  |  | 2026-05-29 | 2026-05-31 13:30 | 2026-05-31 | 2026-05-31 18:07 | 2026-06-01 | 2026-05-31 19:04 | 2026-06-01 | 2026-05-31 20:09 |  |  |  |  | 2026-06-05 18:52 | 2026-06-17 | 2026-06-16 21:26 | 2026-07-01 | 2026-06-30 16:36 | 2026-06-27 | 2026-06-25 18:09 | 2026-06-30 | 2026-07-04 11:57 | 2026-07-04 | 2026-07-07 16:49 | 2026-07-09 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-08-08 | [5 empty] | 2026-05-31 | 2026-06-05 18:51 | 2026-03-17 | 2026-03-15 11:07 | Site is RTMI | 2026-02-14 | 2026-02-16 16:19 | 1031569 | 185682 | 0 | 0 | 853599.0223 | 142212 | 853599.0223 | 142212 | 2026-07-12 18:37:14 +0530 | Asif Shaikh | Execution: Execution End date - 25th July. Metal Fabrication - 20th July. Custom carpentry work - 25th July. Life & Colour wallpaper - ETA - 20th July , In transit . Charcoal beading patti not received in main load. - NO ETA by MAnu & sanju | 2026-06-28 21:31:01 +0530 | Asif Shaikh | Some Image was uploaded | 2026-06-14 14:09:45 +0530 | Asif Shaikh | Procurement: Floor covering work will be done during furniture dispatched.23rd June to 26th June 2026 ( 20 days for Production) ,29th July 2026 (36 days for Modular installation + 10 days for wallpaper )Site Handover Date : 8th August. 2026 | 2026-03-29 | 2026-03-28 12:33 | 2026-04-16 | 2026-04-15 19:24
18416 | Turnkey | 2026-01-01 | SUPRIYA SANDEEP DORUGADE SANDEEP DORUGADE | Eastern Groves | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Mustufa Sohagpurwala |  | Active | Prospect | 10% Payment | 1382056 | 9999 | 1382056 | 0 | 0 | 145 | 0 | 128207 | 138206 | 609549 | 496095.6 |  |  | 2026-02-14 | 2026-02-14 17:47 | 2026-02-20 | 2026-02-20 12:51 | 2026-02-20 | 2026-02-20 13:32 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-14 | 2026-02-14 17:46 | 1171234 | 210822 | 0 | 0 | 0 | 0 | 1171234 | 210822 | 2026-02-19 11:15:36 +0530 | Karuna Shinde | DCM: Client DetailsNames: Supriya & Sandeep Dorugade Property DetailsProject: Eastern Groves Location: Vikhroli Wing: A Flat No.: 1101 Carpet Area: 541 sq. ft. Status: Ready to Move Family ProfileFamily of 3 (Couple + Son 4 years)Parents visit frequentlyScope of WorkModular furnitureDecor stylingFalse ceiling in living roomDesign as per Vastu complianceLiving RoomFolding shoe rackDining placement on TV wall (subject to space feasibility)TV on dining wallTV unit with provision for 43 smart TVL-shaped sofa-cum-bedLoose decorative pooja unit (no doors)Indoor plantsConsole table (if space permits)Hanging light provision above diningEntrance wall decor (frames / accents)KitchenExisting grey base units retainedWall units + loftGlass crockery unitAir fryer spaceRO systemSingle-door refrigerator spaceWashing machine provisionShelves under wall unitsMaster Bedroom (Couple)Queen-size bedWardrobeDresser with side tableCorner unit for used clothesWallpaper: Neutral sage green with leaf pattern + soft peach accentsKids BedroomSofa-cum-bedStudy table with overhead storageWardrobeWallpaperMirror near wardrobeBathroomsVanity unitsLED mirrorsLoft covering for tank in common bathroomDesign ThemeModern Minimal Fresh colorsNo dark tonesLight, airy, functionalBudget12,00,000 15,00,000 For CDP Meeting (19 Feb 3 PM)You should prepare: 2 layout options for living (dining swap possibility)Fresh color palette boardStorage optimization strategy (since 541 sq.ft.)Budget zoning (to keep within 1215L) | [6 empty] | 2026-02-28 |  | 2026-03-07
18417 | Sub Project |  | Sumi Pradeep & Pradeep Vasudevan | Purva Atmosphere | BNG - HRBR | Yes | Arjun M V | Rajeshwari S |  | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Ankith Rodrigues | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Completed | Complete | Completed | 97132 | 97132 | 0 | 0 | 97132 | 60 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-14 | 2026-02-15 | 2026-02-15 | 2026-02-15 | 2026-02-18 | 2026-02-15 | 2026-02-25 | 2026-02-15 | 2026-03-04 | 2026-02-15 | 2026-03-11 | 2026-02-15 | 2026-02-18 | 2026-02-15 | 2026-02-19 | 2026-02-15 | 2026-02-19 | 2026-02-15 | 2026-02-20 | 2026-02-15 |  |  |  |  | 2026-02-26 | 2026-02-15 | 2026-03-06 | 2026-02-15 | 2026-03-07 | 2026-02-15 |  |  | 2026-02-23 | 2026-02-27 12:41 | 2026-02-27 | 2026-02-27 13:15 | 2026-02-28 | 2026-03-04 16:46 | 2026-03-01 | 2026-02-28 22:52 |  |  |  |  | 2026-03-13 11:42 | 2026-03-14 | 2026-03-14 22:38 | 2026-03-19 | 2026-03-17 13:19 | 2026-03-18 | 2026-04-08 18:38 | 2026-03-17 | 2026-04-08 18:39 | 2026-03-18 | 2026-04-08 19:51 | 2026-04-09 | 2026-04-11 09:56 |  |  | 2026-04-21 | 2026-04-11 13:06 | 2026-04-23 | 2026-04-11 13:25 | 2026-04-24 | 2026-04-11 16:45 |  |  |  |  | 2026-02-27 | 2026-02-27 14:01 | 2026-02-21 | 2026-02-15 | Unknown | 2026-02-14 | 2026-02-15 | 0 | 0 | 0 | 0 | 82315 | 14816 | 82315 | 14816 | 2026-02-27 13:04:08 +0530 | Arjun M V | Some Image was uploaded | 2026-02-22 16:29:03 +0530 | Arjun M V | Some Image was uploaded |  |  |  | 2026-02-26 | 2026-02-15 | 2026-03-05 | 2026-02-15
18418 | Turnkey | 2026-01-01 | Alimbasha Gudikal | Roswalt Zaiden | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera | [7 empty] | Hold | Preproduction | Site Readiness 1 | 867723 | 173941 | 1102823 | 0 | 0 | 2 | 66 | 0 | 0 | 380465 | 313317.2 |  |  | 2026-02-14 | 2026-02-15 13:04 | 2026-02-17 | 2026-02-17 17:40 | 2026-02-17 | 2026-02-17 18:47 | 2026-04-18 | 2026-04-18 18:11 | 2026-12-09 |  | 2026-12-16 |  | 2026-02-17 | 2026-02-18 18:17 | 2026-02-18 | 2026-02-19 08:45 | 2026-02-19 | 2026-02-23 13:33 | 2026-03-01 | 2026-03-01 13:25 |  |  |  |  | 2026-06-16 | 2026-05-08 17:21 | 2026-12-11 |  | 2026-12-12 |  |  |  | 2026-12-19 |  | 2026-12-20 |  | 2026-12-21 |  | 2026-12-22 | [6 empty] | 2027-01-09 |  | 2027-01-18 |  | 2027-01-17 |  | 2027-01-18 |  | 2027-01-19 |  | 2027-01-21 |  |  |  | 2027-02-12 |  | 2027-02-14 |  | 2027-02-15 | [5 empty] | 2026-12-20 |  | 2026-08-15 | 2026-04-18 16:04 | Site is Non-RTMI | 2026-02-14 | 2026-02-14 18:06 | 934596 | 168227 | 0 | 0 | 0 | 0 | 919516.9715 | 155245 | 2026-05-05 13:37:18 +0530 | Manzoor Shaikh | Kindly ignore the below invite, since the DEM1 is not completed. | 2026-05-05 13:32:13 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-22 10:47:14 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-19 | 2026-04-19 17:59 | 2026-12-10 |  | Under Construction | 2026-07-01
18419 | Turnkey | 2026-01-01 | Sachin Gogri | Goregaon | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 1862745 | 9999 | 1862745 | 0 | 0 | 145 | 0 | 176276 | 186275 | 776929 | 713266.8 |  |  | 2026-02-14 | 2026-02-20 16:51 | 2026-02-20 | 2026-02-20 19:43 | 2026-02-21 | 2026-02-21 15:31 | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 | [5 empty] | 2026-03-01 |  | 2026-03-09 |  | 2026-03-10 |  |  |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 | [6 empty] | 2026-04-07 |  | 2026-04-16 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-19 |  |  |  | 2026-05-11 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-03-18 |  | 2026-02-24 |  | Unknown | 2026-02-14 | 2026-02-20 13:46 | 1578598 | 284147 | 0 | 0 | 0 | 0 | 1578598 | 284147 | 2026-02-18 11:42:58 +0530 | Yash Jain | Some Image was uploaded | [6 empty] | 2026-03-01 |  | 2026-03-08
18420 | Turnkey | 2026-01-01 | Sindhu G Mohan | Mahendra Aarya | BNG - HSR | Yes | Kiran Agarampalli | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1773045 | 221471 | 1617035 | 0 | 0 | 132 | 0 | 0 | 133138 | 732652 | 685783.6 |  |  | 2026-02-14 | 2026-02-14 19:53 | 2026-02-15 | 2026-02-15 17:17 | 2026-02-27 | 2026-02-27 22:17 | 2026-08-01 |  | 2026-08-08 |  | 2026-09-06 |  | 2026-02-27 | 2026-02-28 11:02 | 2026-02-28 | 2026-02-28 11:51 | 2026-02-28 | 2026-03-05 18:19 | 2026-03-06 | 2026-03-06 17:47 |  |  |  |  | 2026-08-02 |  | 2026-09-01 |  | 2026-09-02 |  |  |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 | [6 empty] | 2026-09-30 |  | 2026-10-09 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-12 |  |  |  | 2026-11-03 |  | 2026-11-05 |  | 2026-11-06 | [5 empty] | 2026-09-10 |  | 2026-05-08 | 2026-06-04 17:42 | Site is RTMI | 2026-02-14 | 2026-02-14 19:49 | 1569785.0764 | 280225 | 0 | 0 | 0 | 0 | 1912381.4273 | 320040 | 2026-07-14 13:03:00 +0530 | Kiran Agarampalli | Client is not responding | 2026-06-04 17:43:22 +0530 | Kiran Agarampalli | TV unit has been finalized as per the last conversation. . Beading behind the sofa is agreed on. . On the wall adjacent to the door opening (DB board wall), a seamless design solution is required so it blends when the door is closed, along with a way to conceal the DB board. . Crockery unit has been finalized. . Suggestions are needed for the pooja unit; the client prefers a curved design concept. . Vanity unit is finalized and approved. . Kitchen has minor changes pending; overall layout and design are fine. . Above the kitchen sink, there is no GTPT unit; in the utility area, wall cabinets are not needed. . In the master bedroom, the client prefers a three-door Aristo shutter running end-to-end. . Headwall treatment in the master bedroom is not yet finalized; additional design options need to be presented . No dressing unit is discussed. . False ceiling has been finalized as discussed; key requirement is to ensure the fan is centered to the bed in the rooms and peripheral is needed in the living area. . In the kids room, the wardrobe design is approved; false ceiling was finalized. . Wall treatment in the kids room will follow the initial design concept. | 2026-06-02 21:49:21 +0530 | Kiran Agarampalli | Some Image was uploaded | 2026-08-02 |  | 2026-08-09
18421 | Turnkey | 2026-01-01 | SWASTIK RANJAN BEHERA | SSVR Niyaraa | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 2104933 | 9999 | 0 | 0 | 0 | 150 | 0 | 200494 | 210493 | 891828 | 792118.8 |  |  | 2026-02-14 | 2026-02-15 16:42 | 2026-02-21 | 2026-02-25 17:31 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-02-14 | 2026-02-15 16:40 | 0 | 0 | 0 | 0 | 0 | 0 | 1783841 | 321091 | 2026-03-01 10:16:20 +0530 | Sakshi Pawar | DCM: GMÂ 3BHK Orientation - door facing east 6 peopleÂ LivingÂ -Sofa to shifted to windowÂ -Tv unit to be shifted to sofa wall -TV - 65 or 75 inches -TV Unit - base cabinet and wall ledge and wall design DiningÂ - 6 seater diningÂ - Crockery unit with small bar unit WITH provision of wash basin at corner - Pooja unit at east KitchenÂ -Base, Top, and loft CabinetÂ -OTG unit -Fridge - top-bottom double door -HOB- 4burner -Granite - To be considered -No sink Utility -Wall mount RO above sink(bigger) -Drain tray above sink -Washing machine- front load -top and loft cabinetÂ PassageÂ -Bedroom Wall - photo displayÂ Master bedroom (Bedroom 12'0"x11'0") (Blue tone) -King size bed -Wardrobe - OpenableÂ -TV with study unit -Dresser unit -Wall treatment to be doneÂ All Toilet vanityÂ top cabinet above WC Parent Bedroom (M Bedroom) -Wardrobe - openable at toilet wall -King size -Dresser unit at left corner -TV unitÂ -Wall treatment to be doneÂ Kids bedroom(Bedroom 10'6"x11'0") -Wardrobe-openableÂ -sofa-cum-bed -Kids theme activity spaceÂ -proper study unitÂ False Ceiling - living and diningÂ Budget - 15-18Lakhs | 2026-02-17 12:04:05 +0530 | Chanakya Panigrahi | 1. Budget - 13-15 2. Property Name & Possession - SSVR Niyara 3. Carpet Area - 1030 4. BHK - 3BHK 5. Family Size -Â Name - Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer - No 4. Living/Dining Room Inclusions - TV Unit 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Yes Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz - Granite Service Scope -Â False Ceiling - No Painting - Yes |  |  |  | 2026-04-05 |  | 2026-04-12
18422 | Turnkey | 2026-01-01 | Prashanth M | Eavetop Dhanisha | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Hold | Preproduction | Site Readiness 1 | 1457442 | 291489 | 1517442 | 0 | 0 | 4 | 119 | 0 | 0 | 613843 | 552110 |  |  | 2026-02-14 | 2026-02-14 19:49 | 2026-02-15 | 2026-02-15 15:45 | 2026-02-24 | 2026-02-24 18:40 | 2026-03-13 | 2026-03-12 15:01 | 2026-11-05 |  | 2026-11-12 |  | 2026-02-24 | 2026-02-24 18:48 | 2026-02-25 | 2026-02-28 12:24 | 2026-02-28 | 2026-02-28 17:55 | 2026-03-11 | 2026-03-11 16:15 |  |  |  |  | 2026-03-12 | 2026-03-14 14:27 | 2026-11-07 |  | 2026-11-08 |  |  |  | 2026-11-15 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 | [6 empty] | 2026-12-06 |  | 2026-12-15 |  | 2026-12-14 |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-18 |  |  |  | 2027-01-09 |  | 2027-01-11 |  | 2027-01-12 | [5 empty] | 2026-11-16 |  | 2026-03-12 | 2026-03-11 16:32 | Site is Non-RTMI | 2026-02-14 | 2026-02-14 19:48 | 1586641.201 | 261982 | 0 | 0 | 0 | 0 | 1586641.201 | 261982 | 2026-02-28 17:55:38 +0530 | Bency Chacko | Possession - Aug 2026 - Deviation Given till Oct Site condition - plastering Pending, and he will let us know by tommorw speaking with the builder, how soon he can get the possession or the site accessibilty Keys - Don't Have He will have a word with the developer to give the site by or before October to complete the kick-off procedure from Bonito. His ask - Designer/ME visit on Sunday, along with the customer. The customer mentioned he will close the IDM by 13th March 2026. B2C - Self-funding No outside work is planned by the customer Checklist, timelines, scope, Quote and Offers are cleared | 2026-02-28 12:36:24 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-02-27 20:44:48 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-03-13 | 2026-03-12 15:02 | 2026-11-06
18424 | Turnkey | 2026-01-01 | Raghavendra | Mahendra Aarya | BNG - HSR | Yes | Priyanka Inchoor | Akshay Ds | Kowshik |  | Sethuragavan R | Ruthwik S K | Ranjith Kumar | Murali S | Ramesh Nayak | Affaan Abdulla | Active | Handover | Project Closure Pending | 1270928 | 1270928 | 1188544 | 0 | 1318428 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-14 | 2026-02-14 20:34 | 2026-02-18 | 2026-02-19 10:44 | 2026-02-19 | 2026-02-19 11:23 | 2026-03-23 | 2026-03-23 12:15 | 2026-04-13 | 2026-04-15 16:14 | 2026-04-28 | 2026-04-28 19:51 | 2026-02-19 | 2026-02-20 11:18 | 2026-02-20 | 2026-02-20 16:20 | 2026-02-20 | 2026-02-23 14:21 | 2026-03-05 | 2026-03-05 18:47 |  |  |  |  | 2026-04-02 | 2026-03-23 18:07 | 2026-04-23 | 2026-04-28 12:59 | 2026-04-29 | 2026-04-28 12:59 |  |  | 2026-04-29 | 2026-04-30 14:37 | 2026-04-30 | 2026-04-30 16:55 | 2026-05-08 | 2026-04-30 20:02 | 2026-05-01 | 2026-05-01 17:35 |  |  |  |  | 2026-05-06 09:46 | 2026-05-15 | 2026-05-14 21:24 | 2026-06-02 | 2026-05-29 19:50 | 2026-05-31 | 2026-05-27 18:51 | 2026-05-29 | 2026-06-01 17:32 | 2026-06-01 | 2026-06-02 10:14 | 2026-06-04 | 2026-06-05 22:47 |  |  | 2026-06-30 | 2026-06-30 21:00 | 2026-07-11 | 2026-06-30 21:42 | 2026-07-12 | 2026-06-30 22:18 |  |  |  |  | 2026-04-30 | 2026-05-06 09:45 | 2026-03-28 | 2026-03-18 16:30 | Site is RTMI | 2026-02-14 | 2026-02-14 20:34 | 1209335.895 | 204184 | 0 | 0 | 1371862.3746 | 231624 | 1371862.3746 | 231624 | 2026-07-06 14:48:55 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-07-01 18:12:49 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-06-24 15:50:55 +0530 | Ranjith Kumar | Execution: | 2026-03-24 | 2026-03-23 12:46 | 2026-04-16 | 2026-04-15 16:26
18425 | Turnkey | 2026-01-01 | Ravi Kulkarni | RUNWAL FOREST | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Saloni Chawan |  | Active | Prospect | 10% Payment | 1164887 | 9999 | 0 | 0 | 0 | 144 | 0 | 106490 | 116489 | 514896 | 417013.6 |  |  | 2026-02-14 | 2026-02-15 12:04 | 2026-02-17 | 2026-02-17 15:00 | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 | [5 empty] | 2026-03-01 |  | 2026-03-09 |  | 2026-03-10 |  |  |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 | [6 empty] | 2026-04-07 |  | 2026-04-16 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-19 |  |  |  | 2026-05-11 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-03-18 |  | 2026-02-24 |  | Unknown | 2026-02-14 | 2026-02-15 12:03 | 0 | 0 | 0 | 0 | 0 | 0 | 987192 | 177694 | 2026-02-17 14:57:05 +0530 | Moksh Mehta | DCM: Client Name:- Ravi Kulkarni Property:- Runwal Forest T3A 401 Possesion Date:- In 15 Days Sq Ft:- 471 Sqft No of Members : - Couple ( 40+) & Daughter (6+) Budget:- 8-10L Ent: Shoe Rack (15 - 20 Pairs)Safety DoorWall Concepts Living Room: - TV Unit (42" Inch) existing to be retained3-Seater Sofa existing to be retainedWall Concepts Dining Area:- 2-Seater Dining Table Existing to be retainedWall Concepts Kitchen:- Fully Modular KitchenBase & Wall & Loft on one side.Civil work scope to be explored. Master Bedroom:- Openable Wardrobe with Loft Mirror with StorageBed existing to be retained Bedroom2:- Single Bed with storageWardrobe with LoftMandir UnitCivil Changes of Door to be flipped Passage:- Storage Unit above Washing Machine Bathroom's No Vanities Misc:- False Ceiling in Living onlyPVC Ceiling in Bathroom (Optional)PaintingElectrification Design Brief: - MinimalisticOff white shade CDP :- 21/02/2026 @ 3:00pm. | [6 empty] | 2026-03-01 |  | 2026-03-08
18426 | Turnkey | 2026-01-01 | Shiv Bhagat | Lodha Amara | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Asif Shaikh | Aditya Vikram |  | Nishtha Valawalkar | Prasad Bhivaji Hande | Active | Preproduction | 3D Sign off | 1402483 | 314460 | 1594039 | 1350880 | 1402483 | 1 | 8 | 0 | 0 | 574079 | 513944.4 |  |  | 2026-02-14 | 2026-05-23 16:50 | 2026-05-15 | 2026-05-23 17:10 | 2026-05-26 | 2026-05-23 22:09 | 2026-06-07 | 2026-06-02 19:09 | 2026-06-17 | 2026-06-16 18:30 | 2026-07-06 | 2026-07-04 00:25 | 2026-05-23 | 2026-05-25 18:52 | 2026-05-24 | 2026-05-26 12:25 | 2026-05-26 | 2026-05-26 15:01 | 2026-06-02 | 2026-06-02 14:21 |  |  |  |  | 2026-05-31 | 2026-05-25 18:52 | 2026-06-21 | 2026-06-21 20:05 | 2026-06-22 | 2026-06-21 20:07 |  |  | 2026-07-04 | 2026-07-14 12:42 | 2026-07-14 | 2026-07-14 21:37 | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-03 | 2026-06-02 18:29 | Site is Non-RTMI | 2026-02-14 | 2026-05-19 12:04 | 1350881 | 243158 | 1350881 | 243158 | 1402483 | 252447 | 1402483 | 252447 | 2026-07-11 12:33:14 +0530 | Viraj Jadhav | Others: | 2026-07-05 18:48:10 +0530 | Preet Karania | mom for cm | 2026-07-05 18:46:56 +0530 | Preet Karania | Cross Measurement: Hello @~S Bhagat sir Good evening PFA for the cm done on site MOM for CM PID-18426-Shiv Bhagat living room switch board need to be added near crockery unit wall molding near window needs to resize because of switch board kitchen on the left platform switch board need to be shifted inside the tall unit on the left platform near window switch board need to be shifted inside the rolling shutter unit chimney switch board need to be added daughter's bedroom study table need to foldable instead of fix one small back panel need to be added above the study table for switch to be moved master bedroom loft need to be added only in half width of the wardrobe switch board behind the wardrobe need to packed and wire from that switch need to be connected for the wardrobe sensor Thanks and Regards Preet Karania Interior Designer | 2026-06-03 | 2026-06-02 19:16 | 2026-06-17 | 2026-06-16 18:30 | RTMI
18427 | Turnkey | 2026-01-01 | Ketana Sayani | others | MUM - GOR | Yes | [8 empty] | Ashish Jha |  | Active | Prospect | 10% Payment | 32780899 | 9999 | 0 | 0 | 0 | 43 | 0 | 3268091 | 3278090 | 13112360 | 13112359.6 |  |  | 2026-02-14 | 2026-02-15 11:51 | 2026-03-11 | 2026-03-25 16:31 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-17 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-16 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Site is RTMI | 2026-02-14 | 2026-02-15 11:49 | 0 | 0 | 0 | 0 | 0 | 0 | 27780423 | 5000476 | 2026-06-02 13:16:37 +0530 | Priyanka Patel | CDP: Recap: PID 18427 Ketna Sayani Review Thursday, March 26 ¦ Meeting ¦ Microsoft Teams | 2026-06-02 13:10:16 +0530 | Priyanka Patel | CDP: The site visit has been completed. However, the client was not fully satisfied with the finishing quality of the project. She would like to visit another site with a cleaner and better finish to evaluate the workmanship before proceeding further. | 2026-03-26 16:29:18 +0530 | Priyanka Patel | DCM: DCM: Bungalow Design Requirement Super Luxury ConceptThis is a luxury bungalow project designed with a focus on comfort, functionality, and high-end aesthetics. The planning is divided floor-wise with detailed requirements as follows: Entrance LevelA grand entrance foyer with a premium finish and statement lightingA dedicated spa room designed for relaxation, including space for massage beds, ambient lighting, and soothing materialsFirst Floor PlanningSpacious Living Room Double-height or large-format living areaPremium furniture layout with formal and informal seatingDesigner lighting and feature wall (marble/veneers/panels)Open Modular Kitchen Fully modular kitchen with high-end finishesIsland counter or breakfast counterIntegrated appliances (details below)Dining Area Connected to the kitchen and livingSpace for 68 seater dining with a statement chandelierParking Area with Garden Covered car parkingLandscaped garden with seating and greeneryMultipurpose Room Can be used as a study, office, or hobby roomFitness Room (Home Gym) Equipped with gym machines and mirrored wallsMaids Room Compact but functional with attached washroomBedroom 1 (Guest/Family Bedroom) Fully furnished with wardrobe and attached bathroomDry Balcony / Utility Area Dedicated for washing, drying, and utility functionsSwimming Pool Area Designed with deck flooring and lounging spaceHome Theater Room Acoustic paneling, recliner seating, projector/screen setupDeck Area & Balconies Outdoor seating with premium flooring and railing designBedroom Design Details (All Bedrooms Super Luxury)Each bedroom will include: King-size bed (minimum 6 x 6.5 or larger) with upholstered headboardSide tables with designer lightingFull-height walk-in wardrobe or sliding wardrobeDressing unit with mirror and storageStudy/work desk (if required)Lounge or seating cornerFalse ceiling with ambient, cove, and accent lightingFeature wall (marble, wallpaper, veneer, or paneling)Curtains (sheer + blackout combination)Smart storage solutionsAttached bathroom with premium fittingsKitchen Fully Modular with AppliancesCabinetry & Layout Base and wall cabinets with premium finishes (laminate/acrylic/glass)Soft-close channels and hardwareTall units for storagePantry unitCountertop & Backsplash Quartz/granite countertopDesigner backsplash (tiles/glass/stone)Appliances (Fully Integrated) Hob and chimneyBuilt-in oven (approx. 21L or as required)MicrowaveRefrigerator (double door or side-by-side)DishwasherWater purifier (Aqua guard)Sink with designer faucetAdditional Features Under-cabinet lightingIsland/breakfast counterProper ventilation and electrical planningAdditional Interior Features (Entire Bungalow)Complete false ceiling design with layered lightingCentralized or split air conditioning provisionsSmart home automation (lighting, curtains, security)CCTV and security systemPremium flooring (marble/wooden/vitrified tiles)Designer doors and hardwareWall paneling and luxury finishes throughoutCX Scope (Client Scope)All civil work including structural modifications, masonry, plastering, and waterproofingSwimming pool execution including structure, waterproofing, tiling, and filtration systemÂ | 2026-04-05 |  | 2026-04-12
18430 | Turnkey | 2026-01-01 | Thapan Akavoo | Sobha Manhattan | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Preproduction | DEM2 | 1277659 | 255532 | 1685468 | 0 | 0 | 60 | 19 | 0 | 0 | 524455 | 497672.4 |  |  | 2026-02-15 | 2026-02-15 10:58 | 2026-02-18 | 2026-02-19 10:46 | 2026-02-22 | 2026-02-24 11:32 | 2026-04-24 | 2026-04-24 19:29 | 2026-07-25 |  | 2026-08-01 |  | 2026-02-24 | 2026-02-24 17:40 | 2026-02-25 | 2026-02-27 11:48 | 2026-02-27 | 2026-02-27 12:58 | 2026-03-05 | 2026-03-05 20:02 |  |  |  |  | 2026-04-29 | 2026-04-27 17:36 | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-04-14 | 2026-04-24 19:00 | Site is RTMI | 2026-02-15 | 2026-02-15 10:57 | 1428363 | 257105 | 0 | 0 | 0 | 0 | 1420522.1 | 234558 | 2026-07-05 19:55:43 +0530 | Chittipireddy Sriharish | DDM1: Foyer - wallpaper Living room - Tv unit (loose furniture) client scope Puja unit - Glass shutters with bottom storage Wall beading for living room Balcony - janitry unit Kitchen - loft extension | 2026-05-14 16:32:43 +0530 | Akshay Ds | Some Image was uploaded | 2026-02-27 12:58:15 +0530 | Bency Chacko | Possession - June 2026 Designs can start immediately IDM - 10% can be collected by 25th March - Deviation taken Checklist cleared, Timelines cleared B2C - Loan (sanctioned) No on-site work is planned, nor vendor work is planned T&Cs cleared | 2026-04-25 | 2026-04-24 19:29 | 2026-07-26
18431 | Turnkey | 2026-01-01 | Valay Shende | Amaryllis nahar | MUM - GOR | Yes | Sweta Bhise |  | Shahid Chougley | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 5242971 | 9999 | 0 | 0 | 0 | 131 | 0 | 514298 | 524297 | 2228623 | 1965753.6 |  |  | 2026-02-14 | 2026-02-15 12:50 | 2026-03-06 | 2026-03-06 14:33 | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-08 | [5 empty] | 2026-03-14 |  | 2026-03-22 |  | 2026-03-23 |  |  |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 | [6 empty] | 2026-04-25 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-28 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-21 | [5 empty] | 2026-03-31 |  | 2026-03-09 |  | Unknown | 2026-02-14 | 2026-02-15 12:27 | 0 | 0 | 0 | 0 | 0 | 0 | 4443196 | 799775 | 2026-03-06 14:19:45 +0530 | Shahid Chougley | 1. Overall Design Direction Agreed theme:Â JapandiÂ (minimal, warm, functional, neutral tones with natural finishes). All windows to be designed withÂ curved detailingÂ as part of the aesthetic language. Presentation to include detailedÂ 3D viewsÂ for all rooms. Approximate cost estimate to be shared room-wise based on finalized scope.2. Kitchen Design direction:Â Minimal Vastu compliant layout Fully modular kitchen. Full-wall storage units. Standard appliance integration. No balcony extension required.3. Sons Bedroom (13 Years) Theme:Â Minimal Provision forÂ pull-up bar setup Study table with storage. Queen-size bed with storage (as per Vastu alignment). Additional utility storage space.4. Master Bedroom Design theme:Â Luxury with functional basics King-size bed. Side tables with additional seating. Integrated medicine storage. Walk-in wardrobe with accessory organizers and full-length mirror. Storage provision in room extensions.5. Daughters Bedroom Theme: Teenager-inspired room. Queen-size bed. Side table. Basic study setup. Utility storage matching overall design aesthetic.6. Drawing / Living Room L-shaped sofa. Two separate accent chairs. No center table (side tables preferred). 6-seater dining table (Marble top or Oak wooden finish to be finalized). TV unit. Entrance partition with Buddha element to block direct visibility.7. Meditation / Multipurpose Room Yoga + Study + Multipurpose functionality. Two large chairs with desk. End-to-end storage for books and yoga mats. Cozy reading corner. | [6 empty] | 2026-03-14 |  | 2026-03-21
18432 | Turnkey | 2026-01-01 | Subhash Shetty | Runwal Sanctuary | MUM - Thane | Yes | Krutika Vernekar | Anamika Dolai | Rushika More | [7 empty] | Active | Prospect | 10% Payment | 2586409 | 9999 | 0 | 0 | 0 | 133 | 0 | 248642 | 258641 | 1108288 | 960839.2 |  |  | 2026-02-15 | 2026-02-15 13:53 | 2026-02-19 | 2026-02-19 11:18 | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 | [5 empty] | 2026-03-08 |  | 2026-03-16 |  | 2026-03-17 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 | [6 empty] | 2026-04-14 |  | 2026-04-23 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-18 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-03-25 |  | 2026-03-03 |  | Unknown | 2026-02-15 | 2026-02-15 13:52 | 0 | 0 | 0 | 0 | 0 | 0 | 2191872 | 394537 | 2026-02-19 11:15:35 +0530 | Moksh Mehta | DCM: Name: - Subhash Shetty Possession Date: - Mar End Sqft :- 1030 Sqft No of Members: - Couple (45+) & Daughter (10 & 5+), Caretaker (50+) Flat No: - T5 - 3802 Budget: - 20L Ent: - Shoe Unit (20-25Pairs). Living: - 3-seater + 1 Chair + 1 ChairTV Unit ( 55" )6-seater dining tableWall ConceptsMirror works to be usedBuffet Counter Kitchen: - Semi Modular KitchenBase, Wall, Loft on One Side Master Bedroom: - Queen size Bed.Wardrobe with Loft.Side table cum Dresser. Kid's Bedroom: - Queen size bedWardrobe with LoftStudy AreaMirror Study Room:- Work from Setup for Books & StorageMandir Unit with StorageWardrobe with Loft Bathroom's: - Vanity unit base x 3nos Misc: - False ceilingPaintingElectrical Brief: - Neutral ShadesModernSmart StorageMinimalistic CDP:- 28/02/2026 @ 10:30am. | [6 empty] | 2026-03-08 |  | 2026-03-15
18433 | Turnkey | 2026-01-01 | Mohit Agarwal | NCP Lodha | MUM - Thane | Yes | Maasoumeh Raza | [7 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 3001018 | 9999 | 3001018 | 0 | 0 | 145 | 0 | 290103 | 300102 | 1277770 | 1123044.8 |  |  | 2026-02-15 | 2026-02-15 14:07 | 2026-02-17 | 2026-02-17 11:13 | 2026-02-20 | 2026-02-20 15:25 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-15 | 2026-02-15 14:00 | 2543235 | 457782 | 0 | 0 | 0 | 0 | 2543235 | 457782 | 2026-02-17 11:13:26 +0530 | Maasoumeh Raza | Name: 18433 - Mohit Agarwal Property Name: Lodha Property type: 3BHK Possession: MarchÂ Move in: MayÂ Member: 4 memberÂ Budget: 15L to 20L Requirements: Living room: Shoe RackÂ Safety door Tv UnitÂ Â 3 seater sofa + Jhula 6 Seater diningÂ Crockery unitÂ Bar Unit in balcony Mandir : Mandir with base storage Kitchen :Â Base unit Wall unitÂ Loft unitÂ Wicker basketÂ Appliance unit Storage for broom & mop Storage above Washing machine Sink if possible in utility area Shelves for pantry Parent BedRoom: Queen size Bed with storage Wardrobe with loft [Swing wardrobe] Used cloth storage Dressing Unit Side table Study table TV UnitÂ Kids bedroom: Bunk bed Wardrobe with loft [Swing wardrobe] Dressing Mirror Study table Bookshelf with seatingÂ Master BedRoom: Queen size Bed [Head position south direction only] Wardrobe with loft [Walk-in closet if possible] Dressing Unit Side table Study table Bathroom: 4 Below vanity unit Additional scope: Full home False ceilingÂ Painting Electrical | 2026-02-15 13:58:38 +0530 | Aryan Singh | Some Image was uploaded |  |  |  | 2026-02-28 |  | 2026-03-07
18435 | Turnkey | 2026-01-01 | Vineet Dsilva |  | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 1745065 | 221999 | 1745065 | 0 | 0 | 124 | 18 | 0 | 127014 | 782689 | 613363.2 |  |  | 2026-02-15 | 2026-02-16 16:18 | 2026-02-17 | 2026-02-17 14:01 | 2026-02-20 | 2026-02-20 13:08 | 2026-08-19 |  | 2026-09-01 |  | 2026-09-08 |  | 2026-02-20 | 2026-02-20 18:38 | 2026-02-21 | 2026-02-20 18:52 | 2026-02-20 | 2026-02-23 16:06 | 2026-03-05 | 2026-03-05 16:24 |  |  |  |  | 2026-08-20 |  | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-03-06 | 2026-03-22 17:43 | Site is RTMI | 2026-02-15 | 2026-02-16 16:17 | 1889403.0851 | 311959 | 0 | 0 | 0 | 0 | 1889403.0851 | 311959 | 2026-07-03 13:06:45 +0530 | Naved Malik | * Layout Finalization Initiated - Following the above discussion, I started coordinating with the client to proceed with Layout Finalization along with the service drawings. * 2nd July 2026 â€“ System-Generated Hold Email - While discussions for layout finalization and service drawings were in progress, a system-generated email was sent to the client informing him that the project would be placed on hold. The project is not going to be started as cx site work is still work in progress. he is not willing to come but to only connect on teams and discuss Kitchen layout. The major escalation is due to the drawings not provided. - Impact: - The issue escalated further. - The client eventually requested a refund. | 2026-07-03 13:06:17 +0530 | Naved Malik | * 10th June 2026 â€“ Sales Team Intervention Requested - After discussing the matter internally with my peers, I requested the Sales Team through the project group to reconnect with the client and clarify the commitments made during the sales phase. * Management Decision - Subsequently, we spoke to Prashant Chajjer and decided to provide the client with the requested detailed service drawings as an exception. - A discussion regarding the revised approach and further process was conducted by Sneha Kadam with the client on 28th June 2026. | 2026-07-03 13:04:17 +0530 | Naved Malik | * 30th May 2026 â€“ Site Visit - To support the client, a site visit was arranged with the intention of guiding the client and his vendors regarding the on-site execution. - The client attended the visit without his vendors. - Prior to the visit, it had already been communicated that: - Detailed service drawings would not be provided. - Only one technical guidance site visit would be conducted. - Despite this, the client continued requesting the detailed service drawings, citing the commitments made during the CDP meeting. - Outcome: Site guidance was provided within the available project scope; however, the client's concerns regarding service drawings remained unresolved. | 2026-08-20 |  | 2026-09-02
18436 | Turnkey | 2026-01-01 | Vikas Pichad | MANAS SOCIETY | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [7 empty] | Active | Prospect | DCM Due | 1747605 | 9999 | 0 | 0 | 0 | 150 | 0 | 164762 | 174761 | 784401 | 613682.8 |  |  | 2026-02-15 | 2026-02-15 15:17 | 2026-02-18 |  | 2026-02-15 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-02-21 |  | 2026-02-22 |  | 2026-02-22 |  | 2026-02-23 | [5 empty] | 2026-03-01 |  | 2026-03-09 |  | 2026-03-10 |  |  |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 | [6 empty] | 2026-04-07 |  | 2026-04-16 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-19 |  |  |  | 2026-05-11 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-03-18 |  | 2026-02-24 |  | Unknown | 2026-02-15 | 2026-02-15 15:07 | 0 | 0 | 0 | 0 | 0 | 0 | 1481021 | 266583 | 2026-02-19 12:12:22 +0530 | Karuna Shinde | Some Image was uploaded | [6 empty] | 2026-03-01 |  | 2026-03-08
18437 | Turnkey | 2026-01-01 | Jyothi | Adarsh Palm Retreat | BNG - HSR | Yes | Aishwarya C | Akshay Ds | Priyanka Mathur |  | Sethuragavan R | Affaan Abdulla | Jairam Joshi | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Active | Installation | Execution | 3304466 | 3304467 | 2447171 | 0 | 3299264 | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-15 | 2026-02-15 15:28 | 2026-02-15 | 2026-02-15 17:08 | 2026-02-24 | 2026-02-24 12:11 | 2026-03-12 | 2026-03-12 13:35 | 2026-05-04 | 2026-05-03 10:43 | 2026-05-14 | 2026-05-14 10:59 | 2026-02-24 | 2026-02-24 18:30 | 2026-02-25 | 2026-02-27 10:36 | 2026-02-27 | 2026-02-27 18:10 | 2026-03-05 | 2026-03-05 18:48 |  |  |  |  | 2026-03-12 | 2026-03-12 19:41 | 2026-05-04 | 2026-05-05 19:06 | 2026-05-06 | 2026-05-05 19:06 |  |  | 2026-05-20 | 2026-05-28 16:24 | 2026-05-28 | 2026-05-28 18:48 | 2026-05-29 | 2026-05-28 23:48 | 2026-05-29 | 2026-05-30 18:41 |  |  |  |  | 2026-06-03 13:03 | 2026-06-17 | 2026-06-17 19:49 | 2026-07-03 | 2026-06-29 19:00 | 2026-06-30 | 2026-06-30 14:47 | 2026-06-29 | 2026-07-03 16:06 | 2026-07-03 | 2026-07-04 01:39 | 2026-07-05 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-05-28 | 2026-05-31 08:09 | 2026-03-06 | 2026-03-05 19:13 | Site is RTMI | 2026-02-15 | 2026-02-15 15:27 | 2073874 | 373297 | 0 | 0 | 3560764.4932 | 579548 | 3569182.8932 | 580342 | 2026-07-02 18:53:26 +0530 | Jairam Joshi | Dispatch Due: SRD task closed | 2026-06-30 13:54:51 +0530 | Jairam Joshi | 100% Payment: CX side Ele work - 17th June Key 18th June FC - 19th 20-21st builder not allowed False cieling -22nd June -30th CX side ele work SRD - 1st July | 2026-06-19 14:50:54 +0530 | Jairam Joshi | Procurement: CX side Ele work - 17th June Key 18th June FC - 18th False cieling -20th - 27th CX side ele work SRD - 27th June | 2026-03-13 | 2026-03-12 13:41 | 2026-05-04 | 2026-05-03 10:43
18438 | Turnkey | 2026-01-01 | Gaurav Rawal Rawal | Svamitva Terravana | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 2301498 | 9999 | 0 | 0 | 0 | 120 | 0 | 220151 | 230150 | 1033556 | 807642 |  |  | 2026-02-15 | 2026-02-15 17:18 | 2026-03-10 | 2026-03-10 11:20 | 2026-03-17 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-02-15 | 2026-02-15 17:16 | 0 | 0 | 0 | 0 | 0 | 0 | 1950422 | 351076 | 2026-03-10 11:24:44 +0530 | Preksha Sajjanshettar | RGM Mr. Gaurav - Individual property Â NotesÂ Current Site conditionsÂ floor electrification and flooring is completed , expected site will be ready by end of may. Â All are new Fitouts. Â Requirements. Â No tv unit in the Living roomÂ Foyer shoe rack with seating storage. Â Entrance wall design concept Â Living area Recliners. Â Kitchen. Â Parallel kitchen with Built-in dishwasher and Fridge Cylinder will be placed in the utility area. Janitor unit in the utility. Â Pooja unit Suggesting being done. Â Bedroom- Guest Â Warm lights to be planned. personal workspaces. Desk with Monitors. Â Family Living tv unit (Simplified Version) 2-3 Seats. Â First floor bedroom King size bed with storage wall design concept Walk in wardrobe unitÂ dresser and display for collections. Â Â bedroom 2 Wardrobe cabinet ad Books Shelf Â TerraceÂ washing machine and Drier, Sit outs Â ONE OF THE bedrooms Terrarium, 5-6 fit for aquarium rodents' pets, Birds, | 2026-03-10 11:23:07 +0530 | Preksha Sajjanshettar | DCM: | 2026-03-07 10:50:26 +0530 | Chanakya Panigrahi | Â Â Â Â Â Â Â Â Â Â Â Â Â RGM Sheet 1. Budget - 25-30L 2. Property Name & Possession - Swamitva Villas 3. Carpet Area - 1800 4. BHK - G+ 2 5. Family Size - 1 Name - Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer - No 4. Living/Dining Room Inclusions - TV Unit 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Yes Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz - Granite Service Scope -Â False Ceiling - No Painting - Yes Electricity - No 8. Utility/Janitor Unit -Â 9. Timeline - August | 2026-03-25 |  | 2026-04-01
18439 | Turnkey | 2026-01-01 | Vikas wilson S | **************** | MUM - GOR | Yes | Rishika Malviya |  | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 3449698 | 9999 | 3449698 | 0 | 0 | 103 | 0 | 334971 | 344970 | 1379879 | 1379879.2 |  |  | 2026-02-15 | 2026-02-17 11:06 | 2026-02-17 | 2026-02-17 17:38 | 2026-03-20 | 2026-04-03 15:27 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-02-15 | 2026-02-17 11:05 | 2923473 | 526225 | 0 | 0 | 0 | 0 | 2923473 | 526225 | 2026-03-24 12:17:05 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-02-18 12:03:46 +0530 | Rishika Malviya | DCM: Detailed Summary Individual HouseG+1 Location : Lodha Villa Royale, Dombivali EastExterior walls are there all the interior walls has to be added in our scope of work, pluming provisions are given Ground Floor ParkingThere is a good parking space and from there only we have the main entrance Entrance foyer They need a good entrance with shoe cabinet with atleast storage of 20 pairs of shoes.(Beadings and mirror design can be given here)Main door to be kept same Store Room To be converted in pooja roomToilet to remove & a basin provision is to be given Entrance is from front, need to change & give the entry from inside the house Living/Dining Room Living sitting area, dining 6 seater to be placed (existing table to be kept)Crockery /Bar Unit to be considered Kitchen With basic requirementsUtility - Washing machine provision Servant Room & it's Toilet To be converted to store room (Combination of closed & open cabinets)Need to remove toilet from there Bedroom Can be kept as guest bedroom or can be used for different activity or purpose.Basic requirement of furniture. Backyard Sitting needs to be created First Floor Study AreaTo be created or thought of any other space to implement can be any activity area. Family RoomTo be created or thought of any other space to implement can be any activity area(can be planned as mini theatre) Master BedroomBasic requirement with the walk in closet (Bed, Wardrobe, TV unit) Kids Bedroom (2 kids)Basic furniture (Bed, Wardrobe, Study table) NOTE: Budget - 35-40L with civilCDP next month end | 2026-02-17 17:43:12 +0530 | Rishika Malviya | DCM: Lifestyle1. Please select your budget for Interior Designing? Rs. 25+ Lacs 2. Interior Designing to commence on the basis of Floor Plan/ Layout File 3. What is your Profession? Sir - Ex-Defence forces, Mam- Regional director AUA 4. Who will be living in this home? Nuclear Family 5. What activities do you usually perform at home? (Choose top 23) Prayer, Pursuing Hobbies, Relaxing & Unwinding, Family Bonding, Working from Home 6. What is your preferred entertainment style? Casual get-togethers 7. Do you prefer any Smart home features? Automation 8. What is your possession date? 2027-03-25 ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice Textures3. Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience 4. What kind of lighting do you prefer? Color palettes5. Please select a maximum of 2 color palettes of your choice Entrance & Foyer1. How would you like your entrance to feel? 2. Any must-haves? Console, Shoe rack Dcor & Living Room1. Choose your decor inspirations Travel souvenirs, Heritage items, Plants, Artwork 2. Any specific signature design feature required Chandelier 3. Whats the primary use of your living room? Multipurpose 4. Any absolute no-go styles, colors, or materials? Black colors, red or dark shades 5. Must-have furniture or features? Statement Wall/ Feature, Display unit , Puja unit, Bookshelves, Coffee table, Speakers, TV unit, Sofa Dining & Kitchen1. Do you prefer a formal dining setup, casual breakfast counter, or both? 2. Any special furniture? Crockery unit, Bar unit 3. Preferred kitchen layout 4. Storage style preferred in the kitchen 5. Must-have appliances? Washing machine, Dishwasher, Chimney, Hob, Fridge, Microwave, Built-in oven BedroomsMaster Bedroom - Bed type No storage Master Bedroom - Wardrobe style Swing Master Bedroom - Additional units TV unit, Dresser Other Bedroom - Bed Type No storage Other Bedroom - Wardrobe style Swing Other Bedroom - Additional units Dresser , Bookshelf , Study table BathroomsPreferred vanity style What do you prefer? Shower partitions What are your requirements for Utility Area? Washing machine space, Laundry space, Top Storage Balcony & OutdoorHow do you intend to use your balcony for? Planters, Seating b. If Yes, Outdoor mood Do you have any existing furniture that must be accommodated? 1 bed, 1 dining table, closet Final Vision1. Any space in the home that you want to put in Spotlight? Foyer & 1st floor open space 2. Do you want the design to reflect any personal story, cultural influence, or special memory special memory | 2026-04-11 |  | 2026-04-18
18440 | Turnkey | 2026-01-01 | MR. DURGADAS MADHUKAR REGE | Veena Synergy | MUM - GOR | Yes | Pratima Kajwe |  | Shraddha Badgujar | [5 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 1090472 | 9999 | 1090472 | 0 | 0 | 132 | 0 | 99048 | 109047 | 474115 | 398262.4 |  |  | 2026-02-15 | 2026-02-16 14:51 | 2026-02-17 | 2026-02-17 11:23 | 2026-03-08 | 2026-03-05 13:47 | 2026-03-12 |  | 2026-03-19 |  | 2026-03-26 |  | 2026-03-05 |  | 2026-03-06 |  | 2026-03-06 |  | 2026-03-07 | [5 empty] | 2026-03-13 |  | 2026-03-21 |  | 2026-03-22 |  |  |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 | [6 empty] | 2026-04-19 |  | 2026-04-28 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-05-01 |  |  |  | 2026-05-23 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-03-30 |  | 2026-03-08 |  | Unknown | 2026-02-15 | 2026-02-15 18:35 | 924129 | 166343 | 0 | 0 | 0 | 0 | 924129 | 166343 | 2026-02-17 11:21:57 +0530 | Pratima Kajwe | DCM: Hi, Minutes of Meeting held on Date: 15/02/2026 Attendees: 4 Discussion: Requirement gathering and design consultation meeting Based on Sunday's meeting, below is a list of all the requirements that were discussed during the meeting: Wing C flat 1 & 2 Flat no. 2 fully furnished. Sqft 426 height - 9'6" Main Entrance to be kept no. 2 VDP provided by builder Shoe-rack movable option Living room mid-wall to be broken 6 seater dining space along with Bar unit placement. Indian seating and sofa seating to be kept as options for living room False ceiling to be aligned as per the other furnished flat Re-iteration of one flat by demolition of kitchen and converted into guest room/study room. Wardrobe, bed, dresser, common in all rooms King size bed in master bedroom Folding study option in new bedroom along with folding bed or sofa cum bed. Bathroom vanity and mirror in bathrooms. TV unit not required in bedrooms only small ledge placement. World map/ magnetic pin board option in son's bedroom Master bedroom bathroom to be converted to walk-in wardrobe and common bathroom to be attached. | [6 empty] | 2026-03-13 |  | 2026-03-20
18441 | Turnkey | 2026-01-01 | Mr. Manish | Brigade Lakefront | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran |  |  | Deekshith P | Jairam Joshi | Murali S | Kushal S | Vishwa Hiremath | Active | Production | Dispatch Due | 1342851 | 1342851 | 1397341 | 1338700 | 1342851 | 2 | 8 | 0 | 0 | 0 | 0 |  |  | 2026-02-14 | 2026-02-22 12:30 | 2026-02-28 | 2026-02-28 00:06 | 2026-03-05 | 2026-03-05 16:48 | 2026-04-14 | 2026-04-14 12:00 | 2026-05-20 | 2026-05-24 11:26 | 2026-05-25 | 2026-05-25 13:55 | 2026-03-05 | 2026-02-28 | 2026-03-06 | 2026-03-11 14:04 | 2026-03-11 | 2026-03-20 19:49 | 2026-03-25 | 2026-03-25 19:02 |  |  |  |  | 2026-04-14 | 2026-04-15 18:54 | 2026-05-26 | 2026-05-25 12:00 | 2026-05-26 | 2026-05-25 12:01 |  |  | 2026-05-26 | 2026-05-27 14:41 | 2026-05-28 | 2026-05-28 18:42 | 2026-05-29 | 2026-05-29 19:38 | 2026-06-06 | 2026-06-06 11:54 |  |  |  |  | 2026-06-10 14:53 | 2026-06-19 | 2026-06-18 19:57 | 2026-07-06 | 2026-07-04 18:15 | 2026-07-05 | 2026-07-13 16:04 | 2026-07-04 | 2026-07-14 15:25 | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-28 | 2026-06-10 14:52 | 2026-03-26 | 2026-04-14 11:48 | Site is RTMI | 2026-02-14 | 2026-02-17 10:53 | 1184187 | 213153 | 1439945.06 | 237767 | 1442496.1809 | 238188 | 1442496.1809 | 238188 | 2026-06-18 17:51:58 +0530 | Jairam Joshi | Procurement: PI works completed SRD task cosure pending due to pending proc. tasks | 2026-06-15 17:06:32 +0530 | Jairam Joshi | Procurement: CX side WIP - done Key - 19th FC - 20th SRD - 22nd | 2026-06-11 12:12:55 +0530 | Jairam Joshi | Procurement: CX side WIP - done Key - 13th FC - 16th SRD 17th | 2026-04-15 | 2026-04-14 12:10 | 2026-05-25 | 2026-05-24 11:30
18442 | Turnkey | 2026-01-01 | Abbas | ** | MUM - GOR | Yes | Karan Chavda |  | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Prospect | DCM Due | 1534906 | 9999 | 0 | 0 | 0 | 149 | 0 | 143492 | 153491 | 670149 | 557776 |  |  | 2026-02-15 | 2026-02-16 14:50 | 2026-02-17 |  | 2026-02-28 |  | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-15 | 2026-02-16 14:44 | 0 | 0 | 0 | 0 | 0 | 0 | 1595482.531 | 258545 | 2026-02-17 11:31:40 +0530 | Sakshi Hire | DCM: 6 adult 6th floor possesion july 3 wardobe 3 bed instruments placement 1 wfh setup soundproof musical theme colourful cost effective 4 seater dining harmonium placement teaching | [6 empty] | 2026-02-28 |  | 2026-03-07
18443 | Turnkey | 2026-01-01 | Ashutosh Kumar | Prestige | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2165562 | 9999 | 2165562 | 0 | 0 | 142 | 0 | 206557 | 216556 | 887419 | 845030.8 |  |  | 2026-02-15 | 2026-02-15 18:54 | 2026-02-15 | 2026-02-15 20:38 | 2026-02-22 | 2026-02-23 11:02 | 2026-03-02 |  | 2026-03-09 |  | 2026-03-16 |  | 2026-02-23 |  | 2026-02-24 |  | 2026-02-24 |  | 2026-02-25 | [5 empty] | 2026-03-03 |  | 2026-03-11 |  | 2026-03-12 |  |  |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 | [6 empty] | 2026-04-09 |  | 2026-04-18 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-21 |  |  |  | 2026-05-13 |  | 2026-05-15 |  | 2026-05-16 | [5 empty] | 2026-03-20 |  | 2026-02-26 |  | Unknown | 2026-02-15 | 2026-02-15 18:51 | 1835222 | 330340 | 0 | 0 | 0 | 0 | 1835222 | 330340 | 2026-02-15 20:38:15 +0530 | Adarsh K | Minutes of Meeting (MOM)Requirement Gathering MeetingClient Name: Asthutosh Kumar Location: Prestige Lavender Client Background: IT Professional ¦ Travel Enthusiasts Budget (RGM): 1520 Lakhs Facing: East-facing Main Door Occupancy: 2 Adults + 1 Child Child Name: Vihaan (4.5 years) Area-wise DiscussionFoyerConsole unit.Living RoomSimple TV unit.Sofa: 3 + 1 + 1 seating configuration.Proposed Pooja unit next to sofa:Sitting-down setup.Drawer extension provision.Pocket door.Height: 7 ft.Dining Area4-seater dining table.Crockery unit.Bifold unit inclusion.KitchenLayout as per plan.Sink unit with GTPT rack.Pantry tall unit.Appliance tall unit (OTG + Microwave) next to fridge.Side-by-side door refrigerator space.Slab provision above Dishwasher & Washing Machine.Loft not requiredUtilityWashing Machine point.No sink in utility area.Common Bathroom (6' x 9')To check feasibility for bathtub option.BedroomsGeneralBeds in all three rooms (Master, Kids, Guest).Bed wall paneling with artwork/painting feature.Bedroom 1 (Master Bedroom)Combination wardrobe: Swing + Sliding.Dresser provision.Nominal vanity.Bedroom 2 (Kids Bedroom)Sliding wardrobe (78 ft).Bedroom 3 (Guest Bedroom)Sliding wardrobe (78 ft).DresserOnly in Bedroom 1. Next MeetingTo Be Decided (TBD) | [6 empty] | 2026-03-03 |  | 2026-03-10
18444 | Turnkey | 2026-01-01 | Mr.Siva Sanker | Folium by Sumadhura | BNG - HRBR | Yes | Sreelakshmi M | Parasa Sri | Shibin Lal | [5 empty] | Raghavendra S |  | Active | Design | 20% Payment | 1462734 | 74999 | 889848 | 0 | 0 | 4 | 66 | 0 | 217548 | 627146 | 543041.2 |  |  | 2026-02-15 | 2026-02-17 10:53 | 2026-02-15 | 2026-02-25 11:08 | 2026-02-28 | 2026-03-13 17:37 | 2026-07-11 | 2026-07-11 16:09 | 2026-07-23 |  | 2026-07-30 |  | 2026-02-28 | 2026-02-28 | 2026-03-14 | 2026-03-13 17:42 | 2026-03-02 | 2026-03-14 11:43 | 2026-03-20 | 2026-03-20 22:53 |  |  |  |  | 2026-07-11 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-06-15 | 2026-07-11 15:46 | Site is Non-RTMI | 2026-02-15 | 2026-02-15 18:55 | 754109 | 135739 | 0 | 0 | 0 | 0 | 1434345.329 | 247535 | 2026-07-11 14:52:20 +0530 | Sreelakshmi M | Minutes of Meeting (MOM) Date 11/07/26 Time :12:30pm Living Room * TV unit ledge to be swapped to the right side. * Add a back panel to the TV unit. * Add a glass display unit in the middle of the bottom unit. * Crockery Unit: * Add two glass shutters for the top units. * Bottom unit is not required. Kitchen * Loft added. * Top unit with glass shutters added. * Wicker basket unit added. * All other elements are finalized. * Utility: Design remains the same. Check the gas pipe connection with the builder. Guest Bedroom * Existing pooja unit to be retained. * Add a study unit adjacent to the pooja unit. * Add ledges for books. * Wardrobe updated by adding one additional unit with a mirror. Parentsâ€™ Bedroom * No changes. Design remains the same. Master Bedroom * No changes as of now. * Dresser unit added. General * Layout is finalized. * Furniture positions are confirmed. * No changes in orientation. | 2026-07-03 11:18:45 +0530 | Parasa Sri | Possession is delayed and the client meeting on the 18th july | 2026-06-19 16:07:03 +0530 | Parasa Sri | Client is expecting possession by the first week of July; post that, he wants to start with design phase | 2026-07-12 | 2026-07-11 16:19 | 2026-07-24 |  | Under Construction | 2026-04-01
18445 | Turnkey | 2026-01-01 | Malay Dey | Codename Godrej Park Retreat Ph 2 / Codename Carmelaram | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Fuzail Girach |  | Active | Design | DEM1 | 1511179 | 205871 | 2058712 | 0 | 0 | 17 | 80 | 0 | 96365 | 607011 | 601932.4 |  |  | 2026-02-15 | 2026-03-03 12:50 | 2026-03-05 | 2026-03-05 12:39 | 2026-03-05 | 2026-03-05 16:28 | 2026-09-04 |  | 2026-10-05 |  | 2026-10-12 |  | 2026-03-05 | 2026-03-06 20:24 | 2026-03-06 | 2026-04-05 15:45 | 2026-03-06 | 2026-04-09 11:52 | 2026-04-11 | 2026-04-11 19:07 |  |  |  |  | 2026-09-05 |  | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-23 |  | 2026-10-24 | [6 empty] | 2026-11-11 |  | 2026-11-20 |  | 2026-11-19 |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-23 |  |  |  | 2026-12-15 |  | 2026-12-17 |  | 2026-12-18 | [5 empty] | 2026-10-16 |  | 2026-08-31 |  | Unknown | 2026-02-15 | 2026-03-03 12:46 | 1744671 | 314040 | 0 | 0 | 0 | 0 | 1712988 | 282383 | 2026-04-14 16:36:45 +0530 | Lalitha Ajay Kumar | Some Image was uploaded | 2026-04-09 11:51:35 +0530 | Bency Chacko | Some Image was uploaded | 2026-04-08 11:34:32 +0530 | Bency Chacko | Possession - Sept 2026 The customer will get site access around July-August, then he will come for design meetings after us taking the measurements. Only after he finalises the designs (1st cut) will he pay. Deviation needs to be rechecked. He is clear with Offers and Quotes B2C - Self-funding No on-site work is planned | 2026-09-05 |  | 2026-10-06 |  | Under Construction | 2026-04-09
18446 | Turnkey | 2026-01-01 | Uchit Sheth | Lodha Belajio | MUM - GOR | Yes | Priyanka Murarka | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Sanskruti Yadav |  | Hold | Preproduction | Site Readiness 1 | 1417127 | 304728 | 1920031 | 0 | 0 | 34 | 73 | 0 | 0 | 602305 | 510094.4 |  |  | 2026-02-15 | 2026-02-24 13:13 | 2026-02-17 | 2026-02-24 18:55 | 2026-02-27 | 2026-02-24 22:22 | 2026-03-25 | 2026-03-25 19:01 | 2026-10-10 |  | 2026-10-17 |  | 2026-02-24 | 2026-02-28 | 2026-02-25 | 2026-03-06 12:44 | 2026-03-06 | 2026-03-09 11:58 | 2026-03-13 | 2026-03-13 17:09 |  |  |  |  | 2026-03-25 | 2026-03-30 22:46 | 2026-10-12 |  | 2026-10-13 |  |  |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 | [6 empty] | 2026-11-10 |  | 2026-11-19 |  | 2026-11-18 |  | 2026-11-19 |  | 2026-11-20 |  | 2026-11-22 |  |  |  | 2026-12-14 |  | 2026-12-16 |  | 2026-12-17 | [5 empty] | 2026-10-21 |  | 2026-03-14 | 2026-03-25 16:11 | Site is Non-RTMI | 2026-02-15 | 2026-02-19 17:32 | 1627145 | 292886 | 0 | 0 | 0 | 0 | 1447519.319 | 243629 | 2026-05-03 19:25:44 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-23 16:12:12 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-10 16:35:03 +0530 | Priyanka Murarka | Some Image was uploaded | 2026-03-26 | 2026-03-25 19:16 | 2026-10-11 |  | Under Construction | 2026-09-01
18447 | Turnkey | 2026-01-01 | Jayadeep Save | Akshay residency | MUM - GOR | Yes | Saif Shaikh | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Preproduction | DEM2 | 953901 | 190780 | 1211175 | 0 | 0 | 63 | 14 | 0 | 0 | 417527 | 345593.6 |  |  | 2026-02-15 | 2026-02-16 13:02 | 2026-03-07 | 2026-03-10 19:58 | 2026-03-10 | 2026-03-10 20:28 | 2026-04-25 | 2026-04-24 14:17 | 2027-01-02 |  | 2027-01-09 |  | 2026-03-10 | 2026-03-11 12:58 | 2026-03-11 | 2026-03-11 13:23 | 2026-03-11 | 2026-03-12 14:23 | 2026-03-18 | 2026-03-18 18:27 |  |  |  |  | 2026-04-24 | 2026-04-30 19:20 | 2027-01-04 |  | 2027-01-05 |  |  |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 |  | 2027-01-15 | [6 empty] | 2027-02-02 |  | 2027-02-11 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-12 |  | 2027-02-14 |  |  |  | 2027-03-08 |  | 2027-03-10 |  | 2027-03-11 | [5 empty] | 2027-01-13 |  | 2026-03-19 | 2026-04-24 13:55 | Site is RTMI | 2026-02-15 | 2026-02-16 13:02 | 1068792 | 192382 | 0 | 0 | 0 | 0 | 1051584.4153 | 177544 | 2026-07-02 16:35:10 +0530 | Vishakha Vaishnav | Others: Cx will receive the possession in month of august | 2026-06-23 15:38:33 +0530 | Manzoor Shaikh | Dear Mr. Jayadeep Save, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 24th June at 10:30 AM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, @~Saif Saif will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-04-29 20:12:49 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-25 | 2026-04-24 14:18 | 2027-01-03 |  | Under Construction | 2026-05-01
18448 | Turnkey | 2026-01-01 | Swaru Paresh Ramdaras chauhan | Tharwani Majestic | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Nishtha Valawalkar |  | Active | Design | DEM1 | 898965 | 89999 | 898965 | 0 | 0 | 47 | 94 | 0 | 89794 | 375439 | 343732.8 |  |  | 2026-02-15 | 2026-02-18 16:14 | 2026-02-17 | 2026-02-22 21:19 | 2026-02-25 | 2026-02-23 12:15 | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-02-23 | 2026-02-23 17:58 | 2026-02-24 | 2026-02-23 18:01 | 2026-02-23 | 2026-02-24 12:04 | 2026-02-26 | 2026-02-26 18:06 |  |  |  |  | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-02-15 | 2026-02-18 16:12 | 761835 | 137130 | 0 | 0 | 0 | 0 | 761835 | 137130 | 2026-07-03 13:07:43 +0530 | Monika Pal | Possession delay | 2026-07-03 13:06:31 +0530 | Monika Pal | Possession delay | 2026-07-02 17:27:36 +0530 | Anamika Dolai | Client has no information regarding the possession, will pay the next milestone on 15th of July. | 2026-07-05 |  | 2026-07-12
18449 | Turnkey | 2026-01-01 | asif | Dhananjay heights | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1025924 | 9999 | 1025924 | 0 | 0 | 141 | 0 | 92593 | 102592 | 477442 | 343296.8 |  |  | 2026-02-15 | 2026-02-15 21:08 | 2026-02-24 | 2026-02-24 12:32 | 2026-02-27 | 2026-02-24 12:35 | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-02-15 | 2026-02-15 20:52 | 869427 | 156496 | 0 | 0 | 0 | 0 | 869427 | 156496 | 2026-02-20 12:34:53 +0530 | Maasoumeh Raza | DCM: Name: Asif Possession: May Move-in Date: Not decided Budget: 8 Lakhs Member : 8 Â Requirements: Â Living Room: Shoe rack TV unit 3-seater sofa Dining table Window extension (options required: with and without extension) Â Kitchen: Base unit provided by the builder Only loft and wall units required Â Bedroom: Wardrobe Queen-size bed Dressing unit Study table Â Bathroom: Vanity unit Â Additional Work: False ceiling Painting Electrical work | [6 empty] | 2026-03-04 |  | 2026-03-11
18450 | Turnkey | 2026-01-01 | VIKAS KANJI BHANUSHALI | Runwal Santuary | MUM - Thane | Yes | Hemant Sonar | Divya Rahangdale | Anil Kuwar |  | Vaishali G | suraj kumar | Aditya Vikram | Murali S | Aryan Singh | Aakash Gaikwad | Active | Handover | Project Closure Pending | 875948 | 875948 | 1202715 | 0 | 875948 | 63 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-15 | 2026-02-15 22:18 | 2026-02-18 | 2026-02-18 20:23 | 2026-02-18 | 2026-02-18 20:27 | 2026-02-25 | 2026-02-20 11:39 | 2026-04-22 | 2026-02-27 12:45 | 2026-02-27 | 2026-02-27 15:36 | 2026-02-18 | 2026-02-19 11:00 | 2026-02-19 | 2026-02-19 11:38 | 2026-02-19 | 2026-02-19 17:51 | 2026-02-20 | 2026-02-20 11:29 |  |  |  |  | 2026-02-26 | 2026-02-19 11:00 | 2026-02-21 | 2026-02-24 12:58 | 2026-02-25 | 2026-02-26 11:50 |  |  | 2026-02-28 | 2026-02-28 20:19 | 2026-02-28 | 2026-02-28 23:14 | 2026-03-01 | 2026-03-01 07:19 | 2026-03-02 | 2026-03-04 19:37 |  |  |  |  | 2026-03-06 19:27 | 2026-03-17 | 2026-03-17 21:27 | 2026-03-24 | 2026-03-25 16:54 | 2026-03-24 | 2026-03-25 16:19 | 2026-03-25 | 2026-03-30 15:59 | 2026-03-31 | 2026-04-02 10:01 | 2026-04-04 | 2026-04-16 19:06 |  |  | 2026-05-17 | 2026-05-11 13:00 | 2026-05-19 | 2026-05-12 21:27 | 2026-05-20 | 2026-05-13 11:25 |  |  |  |  | 2026-02-28 | 2026-03-06 19:26 | 2026-02-21 | 2026-02-20 11:31 | Site is RTMI | 2026-02-15 | 2026-02-15 22:03 | 1019250 | 183465 | 0 | 0 | 1012239.0363 | 156500 | 1012239.0363 | 156500 | 2026-06-24 13:51:00 +0530 | suraj kumar | Snag materials has been received in MUM Wh, Need to delivered on site as per cx tenant availability. ( Also, Febonic headborad to be replaced or refund the amount) | 2026-05-11 01:16:30 +0530 | suraj kumar | NON FTR- Qc has been done on 9th may.Project to be closed by 12th May. ( Cx checklist to be received.)Snag- Wardrobe shutter replacement - ETA 18th MayBed headboard replacement - ETA 18th May | 2026-05-11 01:16:17 +0530 | suraj kumar | NON FTR- Qc has been done on 9th may.Project to be closed by 12th May. ( Cx checklist to be received.) Snag- Wardrobe shutter replacement - ETA 18th MayBed headboard replacement - ETA 18th May | 2026-02-21 | 2026-02-20 11:40 | 2026-02-28 | 2026-02-27 12:45
18451 | Turnkey | 2026-01-01 | Dr Pallavi Shelke | ** | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Saloni Chawan |  | Active | Preproduction | DEM2 | 891595 | 249999 | 1260873 | 0 | 0 | 7 | 90 | 0 | 0 | 313917 | 327678.8 |  |  | 2026-02-15 | 2026-02-16 12:53 | 2026-03-05 | 2026-03-05 12:05 | 2026-03-08 | 2026-03-07 22:17 | 2026-07-08 | 2026-07-08 12:08 | 2026-07-17 |  | 2026-07-24 |  | 2026-03-07 | 2026-03-09 18:55 | 2026-03-08 | 2026-03-10 13:25 | 2026-03-10 | 2026-03-10 15:43 | 2026-03-18 | 2026-03-18 18:32 |  |  |  |  | 2026-03-15 | 2026-03-09 18:55 | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-06-30 | 2026-07-08 12:00 | Site is RTMI | 2026-02-15 | 2026-02-15 22:01 | 1068536 | 192336 | 0 | 0 | 0 | 0 | 912005.8584 | 152023 | 2026-06-28 11:12:00 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-03-10 16:22:39 +0530 | Saloni Chawan | Some Image was uploaded | 2026-03-10 15:06:22 +0530 | Royden Henriques |  | 2026-07-09 | 2026-07-11 20:08 | 2026-07-18
18452 | Turnkey | 2026-01-01 | Aditya P Raut & Binty Goswamee Raut | Parsn Bhagyalakshmi | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Savita Parab | Rizwan Mistry | Murali S | Rashmita Das | Aakash Gaikwad | Active | Production | Dispatch Due | 1749285 | 1749285 | 1837011 | 0 | 1853151 | 12 | 16 | 0 | 0 | 0 | 0 |  |  | 2026-02-16 | 2026-02-16 14:49 | 2026-02-17 | 2026-02-17 11:27 | 2026-02-20 | 2026-02-20 15:14 | 2026-03-17 | 2026-03-13 12:49 | 2026-04-28 | 2026-04-29 13:11 | 2026-05-08 | 2026-05-08 21:08 | 2026-02-20 | 2026-02-20 18:26 | 2026-02-21 | 2026-02-21 14:21 | 2026-02-21 | 2026-02-27 14:22 | 2026-02-28 | 2026-02-28 17:08 |  |  |  |  | 2026-03-13 | 2026-04-06 22:06 | 2026-05-07 | 2026-05-06 21:43 | 2026-05-07 | 2026-05-07 23:03 |  |  | 2026-05-20 | 2026-05-22 13:42 | 2026-05-23 | 2026-05-23 15:09 | 2026-06-22 | 2026-05-23 15:11 | 2026-06-10 | 2026-06-16 18:57 |  |  |  |  | 2026-06-21 19:53 | 2026-06-27 | 2026-06-26 21:14 | 2026-07-04 | 2026-07-03 14:09 | 2026-07-03 | 2026-07-02 12:35 | 2026-07-10 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-05-23 | 2026-06-20 11:52 | 2026-03-01 | 2026-03-13 12:46 | Site is RTMI | 2026-02-16 | 2026-02-16 14:43 | 2060715.368 | 325984 | 0 | 0 | 2128842.1056 | 336073 | 2128842.2228 | 320229 | 2026-07-08 23:36:52 +0530 | Savita Parab | Execution: site is on hold due to water and electric supply not inside the flat | 2026-07-02 12:19:51 +0530 | Reshma Melanta | Design Fees: | 2026-06-03 16:28:03 +0530 | Reshma Melanta | CX IS APPLYING FOR A LOAN THROUGH BANK, KEYS HAVE BEEN PROVIDED THE SAME WILL BE CLEARED BY 8TH JUNE 2026 | 2026-03-14 | 2026-03-13 12:52 | 2026-04-30 | 2026-05-06 09:41
18453 | Turnkey | 2026-01-01 | Rahul Singh | kalpataru shrishti namah | MUM - GOR | Yes | Rahul Agrawal |  | Shahid Chougley | [5 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 2195575 | 9999 | 2195575 | 0 | 0 | 141 | 0 | 209559 | 219558 | 947647 | 808813.2 |  |  | 2026-02-16 | 2026-02-18 00:56 | 2026-02-24 | 2026-02-24 13:55 | 2026-02-27 | 2026-02-24 14:02 | 2026-03-03 |  | 2026-03-10 |  | 2026-03-17 |  | 2026-02-24 |  | 2026-02-25 |  | 2026-02-25 |  | 2026-02-26 | [5 empty] | 2026-03-04 |  | 2026-03-12 |  | 2026-03-13 |  |  |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 | [6 empty] | 2026-04-10 |  | 2026-04-19 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-22 |  |  |  | 2026-05-14 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-03-21 |  | 2026-02-27 |  | Unknown | 2026-02-16 | 2026-02-18 00:56 | 1860657 | 334918 | 0 | 0 | 0 | 0 | 1860657 | 334918 | [9 empty] | 2026-03-04 |  | 2026-03-11
18456 | Turnkey | 2026-01-01 | Abhinav Prakash | AVANI ABODE - 4BHK Luxury Villas Near Whitefield | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [7 empty] | Hold | Preproduction | Site Readiness 1 | 2040035 | 408007 | 2488082 | 0 | 0 | 37 | 69 | 0 | 0 | 875984 | 756044.4 |  |  | 2026-02-15 | 2026-02-22 12:26 | 2026-02-18 | 2026-02-27 16:28 | 2026-03-02 | 2026-03-05 11:52 | 2026-03-31 | 2026-03-31 18:37 | 2026-08-06 |  | 2026-08-13 |  | 2026-03-05 | 2026-02-28 | 2026-03-06 | 2026-03-11 15:16 | 2026-03-11 | 2026-03-12 10:54 | 2026-03-20 | 2026-03-20 18:31 |  |  |  |  | 2026-03-31 | 2026-03-31 20:44 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-09-30 | 2026-03-31 18:29 | Site is Non-RTMI | 2026-02-15 | 2026-02-17 10:52 | 2108544 | 379538 | 0 | 0 | 0 | 0 | 2097606.3309 | 358835 | 2026-03-25 19:03:34 +0530 | Parasa Sri | Welcome call done He will pay on 26th march - 10% | 2026-03-25 13:16:05 +0530 | Priyanka Gs | CDP: The TV unit design was reviewed, and the client confirmed that it looks good and meets their expectations. The previously suggested breakfast counter and crockery unit were revisited. As the intended breakfast counter was not practically feasible in the given layout, the client chose not to proceed with it. Instead, the client preferred to go ahead with a 4seater dining arrangement, which works better for the space and their lifestyle needs. Kitchen kitchen layout was reviewed in detail. The client confirmed that the layout works well A blind corner accessory is required Master Bedroom the addition of a dresser unit, which was discussed and added to the design in their presence.A TV cum bookshelf unit was also requested and has been noted for design development. Requirements incorporated as discussed. Library AreaThe client expressed the need for a different design approach for the library.Additional storage , keeping functionality in mind, and this was added to the scope during the meeting. Kids BedroomThe overall layout was reviewed, and the client confirmed Theatre Room a 3foot wide wardrobe to be included in the theatre room.An extended loft was also discussed and added Pooja AreaThe position and dimensions of the pooja unit were reviewed. All the above discussions, changes, and confirmations were done in the presence of the client. The client has clearly understood the scope and acknowledged all the decisions made during the meeting. 7. False Ceiling & ElectricalFalse ceiling - Cx Scope Electrical work will be addressed and finalized during crossmeasurement stage, based on site conditions. Scope clarity noted and acknowledged. Painting - Cx Scope Wardrobe Internals All wardrobe internal configurations were shown to the client for understanding. The client is informed that; Internals can be personalized further during the design phase Any additional drawers may impact the final cost | 2026-03-12 10:53:56 +0530 | Bency Chacko | Possession -July - Sept, but Aug he is expecting soft possession. IMs can be taken -site access is available 1st LFM - March end or April 26th March 2026 - Design fee will be closed B2C - No cost EMI No on-site work is planned Checklist closed Timelines discussed No additional scope of work is planned Quote and Offers closed | 2026-04-01 | 2026-03-31 18:37 | 2026-08-07
18457 | Turnkey | 2026-01-01 | Sunny Awsare | Lakhani | MUM - Thane | Yes | Rutuja Kotwal | [9 empty] | Active | Prospect | 10% Payment | 2102273 | 9999 | 2102273 | 0 | 0 | 145 | 0 | 200228 | 210227 | 888374 | 793444 |  |  | 2026-02-14 | 2026-02-17 11:34 | 2026-02-19 | 2026-02-19 11:20 | 2026-02-20 | 2026-02-20 15:24 | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-02-20 |  | 2026-02-21 |  | 2026-02-21 |  | 2026-02-22 | [5 empty] | 2026-02-28 |  | 2026-03-08 |  | 2026-03-09 |  |  |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-19 | [6 empty] | 2026-04-06 |  | 2026-04-15 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-18 |  |  |  | 2026-05-10 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-03-17 |  | 2026-02-23 |  | Unknown | 2026-02-14 | 2026-02-17 11:31 | 1781587 | 320685 | 0 | 0 | 0 | 0 | 1781587 | 320685 | 2026-03-24 15:27:08 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-02-19 11:19:57 +0530 | Rutuja Kotwal | DCM: Mr. SunnyÂ AwsareÂ Â 3 BHK.Â Â Property Empire tower LakhaniÂ 3Â haatÂ nakaÂ thane west.Â Â Move in 3 people- Husband,Â wifeÂ and son 7years.Â Â Possession Soft possession in next weekÂ Â Possession MarchÂ end.Â Â Design as per Vastu.Â Â Direction entering NW.Â Â Profession Deputy engineer.Â Â VijayaÂ maamÂ Doctor in Ayurveda.Â Â LivingÂ roomÂ Room between living and bedroom will be demolished by builder.Â Â Room divider to be provided for study area., wall paneling to be done with shoe rack, safety door,Â safety door to be taken out,Â TV unitÂ with DisplayÂ unitÂ ,Â existingÂ Â sofaÂ ,Â swing provisionÂ Â Removing ofÂ WC from commonÂ toilet ,Â Mandir on dining wall,Â 4 seaterÂ dining table.Â Â Kitchen Base units, wall units, Lofts.Â Â Bedroom 1 Â ExistingÂ Bed on toilet wall,Â sideÂ tableÂ with above dresser and mirror to be hidden.Â NO WARDROBE ONLY LOFTSÂ Â MBR- Bed, WardrobeÂ with lofts,Â dressing tableÂ Vanity inÂ all bathroomsÂ Â Glass partition in Master bathroom.Â Â FC,Â paintingÂ and electricals.Â Budget 20-25 lakhs.Â Â CDP-Â Â 21stÂ februaryÂ 26 at 11 am.Â Â |  |  |  | 2026-02-28 |  | 2026-03-07
18460 | Sub Project |  | Prachi singh | Kalpataru Crest | MUM - Thane |  | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | Snehankit Agre | Rizwan Mistry | Murali S |  | Shailendra Mishra | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-17 | 2026-04-03 19:42 | 2026-02-18 | 2026-04-03 19:42 | 2026-04-03 | 2026-04-03 19:42 | 2026-04-03 | 2026-04-03 19:47 | 2026-05-06 | 2026-05-05 14:22 | 2026-05-06 | 2026-05-05 14:24 | 2026-04-03 | 2026-04-03 19:42 | 2026-04-04 | 2026-04-03 19:42 | 2026-04-03 | 2026-04-03 19:42 | 2026-04-04 | 2026-04-03 19:42 |  |  |  |  | 2026-04-07 | 2026-05-05 14:21 | 2026-05-06 | 2026-05-05 14:23 | 2026-05-06 | 2026-05-05 14:23 |  |  | 2026-05-15 | 2026-05-15 20:06 | 2026-05-16 | 2026-05-16 12:14 | 2026-05-17 | 2026-05-16 14:03 | 2026-05-17 | 2026-05-16 14:03 |  |  |  |  | 2026-05-23 13:09 | 2026-05-30 | 2026-05-30 13:23 | 2026-06-01 | 2026-05-30 15:56 | 2026-05-31 |  | 2026-05-30 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-05-16 | 2026-05-21 16:12 | 2026-04-04 | 2026-04-03 19:44 | Site is RTMI | 2026-02-17 | 2026-04-03 19:41 | 0 | 0 | 0 | 0 | 16222.5 | 0 | 16222.5 | 0 | 2026-06-24 13:09:55 +0530 | Snehankit Agre | Execution: . Paints finish pending . Snags pending . Pop rectification | 2026-06-01 12:35:29 +0530 | Snehankit Agre | Execution: 1. Ceiling design has changes according to cx requirment, Execution pending, | 2026-06-01 12:30:28 +0530 | Snehankit Agre | Execution: 1. Master bedroom final paint completed wallpaper pending, wardrobe sliding shutter soft close. Extra work:- Wall lights starts from today. 2. Daughters bedroom final paint completed, Error:- wire joint open in ceiling juction that why the curtain lights, & 8M socket not working. 3. Living room 2 coat completed, final paint in progress. Extra work:- Cx required t.v panel replacement. 4. All Bathrooms paint completed. 5. Kitchen paints completed. | 2026-04-04 | 2026-04-07 12:16 | 2026-05-06 | 2026-05-05 14:22
18461 | Sub Project |  | rahul Nalawde | Indepent house | MUM - Thane |  | Rutuja Kotwal | [9 empty] | Active | Preproduction | Hoto | 5900 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 3540 | 2360 |  |  | 2026-02-17 | 2026-03-17 14:24 | 2026-02-18 | 2026-03-17 14:24 | 2026-03-17 | 2026-03-17 14:26 | 2026-03-18 | 2026-03-17 14:27 | 2026-03-18 | 2026-03-17 14:29 | 2026-03-18 | 2026-03-17 14:34 | 2026-03-17 | 2026-03-17 14:26 | 2026-03-18 | 2026-03-17 14:26 | 2026-03-17 | 2026-03-17 14:27 | 2026-03-18 | 2026-03-17 14:27 |  |  |  |  | 2026-03-17 | 2026-03-17 14:28 | 2026-03-18 | 2026-03-17 14:32 | 2026-03-18 | 2026-03-17 14:32 |  |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 | [6 empty] | 2026-04-08 |  | 2026-04-17 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-20 |  |  |  | 2026-05-12 |  | 2026-05-14 |  | 2026-05-15 | [5 empty] | 2026-03-19 |  | 2026-03-18 | 2026-03-17 14:27 | Unknown | 2026-02-17 | 2026-03-17 14:23 | 0 | 0 | 0 | 0 | 0 | 0 | 54999 | 900 | [9 empty] | 2026-03-18 | 2026-03-17 14:28 | 2026-03-18 | 2026-03-17 14:29
18464 | Sub Project |  | Lodha Goldcrest _04 ( Abhinandan Ventures) |  | MUM - GOR | Yes | Mandar Ambre | Manzoor Shaikh | Shantanu Parakh |  |  | Yash Metha | Aditya Vikram | Murali S | Umang Shah |  | Active | Installation | Execution | 742287 | 788681 | 0 | 0 | 742287 | 71 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-17 | 2026-03-08 14:13 | 2026-02-18 | 2026-03-08 14:15 | 2026-03-08 | 2026-03-08 14:15 | 2026-03-09 | 2026-03-08 14:17 | 2026-03-09 | 2026-03-08 14:18 | 2026-03-11 | 2026-03-12 11:03 | 2026-03-08 | 2026-03-08 14:15 | 2026-03-09 | 2026-03-08 14:16 | 2026-03-08 | 2026-03-08 14:16 | 2026-03-09 | 2026-03-08 14:16 |  |  |  |  | 2026-03-08 | 2026-03-08 14:17 | 2026-03-09 | 2026-03-08 14:21 | 2026-03-09 | 2026-03-11 20:05 |  |  | 2026-03-14 | 2026-03-31 11:04 | 2026-03-31 | 2026-03-31 11:56 | 2026-04-01 | 2026-03-31 12:38 | 2026-04-01 | 2026-04-03 16:50 |  |  |  |  | 2026-04-11 13:07 | 2026-04-23 | 2026-04-22 19:18 | 2026-05-03 | 2026-04-30 21:32 | 2026-04-27 | 2026-04-03 16:50 | 2026-04-30 | 2026-05-02 16:40 | 2026-05-02 | 2026-05-05 13:30 | 2026-05-13 | 2026-05-23 19:07 |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-03-21 | 2026-03-24 12:45 | 2026-03-09 | 2026-03-08 14:16 | Unknown | 2026-03-24 | 2026-03-08 14:13 | 0 | 0 | 0 | 0 | 938891 | 169000 | 938891 | 169000 | 2026-04-01 15:09:31 +0530 | Mandar Ambre | Some Image was uploaded | 2026-03-31 12:42:56 +0530 | Mandar Ambre | Some Image was uploaded | 2026-03-30 19:37:07 +0530 | Mandar Ambre | Others: need to open the task from backend cx has approved the final docket | 2026-03-09 | 2026-03-08 14:17 | 2026-03-09 | 2026-03-08 14:18
18466 | Turnkey | 2026-01-01 | Sainath Sk | * | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 3934011 | 9999 | 3934011 | 0 | 0 | 148 | 0 | 383402 | 393401 | 1680408 | 1466801.2 |  |  | 2026-02-17 | 2026-02-17 16:46 | 2026-03-26 | 2026-04-03 11:07 | 2026-04-02 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Site is RTMI | 2026-02-17 | 2026-02-17 16:24 | 3337453 | 596558 | 0 | 0 | 0 | 0 | 3337453 | 596558 | 2026-02-17 16:44:56 +0530 | Nishtha Valawalkar | 3 BHK 25L to 30L Civil work is there which is suggested to get done from outside. Silver coin is not pitched hence no need to give. | [6 empty] | 2026-04-14 |  | 2026-04-21
18467 | Turnkey | 2026-01-01 | Santhosh | Prestige Kew Gardens | BNG - HSR | Yes | Nayan Reddy |  | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 2103435 | 9999 | 0 | 0 | 0 | 148 | 0 | 200345 | 210344 | 934999 | 747748.8 |  |  | 2026-02-17 | 2026-02-17 17:16 | 2026-02-26 | 2026-02-26 18:14 | 2026-02-21 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-03 | [5 empty] | 2026-03-09 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-28 | [6 empty] | 2026-04-15 |  | 2026-04-24 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-27 |  |  |  | 2026-05-19 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-03-26 |  | 2026-03-04 |  | Unknown | 2026-02-17 | 2026-02-17 17:15 | 0 | 0 | 0 | 0 | 0 | 0 | 1782572 | 320863 | 2026-02-17 16:25:16 +0530 | Unknown | Design Brief He has done few things and staying there and he might rent it out after sometime want a nice peaceful, house, nothing flashy. | [6 empty] | 2026-03-09 |  | 2026-03-16
18473 | Turnkey | 2026-01-01 | Shubhangi Singh and Aayush Shrivastava | Brigade Valencia | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Priyanka Mathur | [5 empty] | Nidhi Shaw |  | Hold | Preproduction | DEM2 | 1191635 | 238327 | 1629680 | 0 | 0 | 0 | 55 | 0 | 0 | 487768 | 465540.4 |  |  | 2026-02-18 | 2026-02-18 12:37 | 2026-02-23 | 2026-02-23 20:26 | 2026-03-17 | 2026-03-17 12:58 | 2026-05-19 | 2026-05-19 19:52 | 2026-10-05 |  | 2026-10-12 |  | 2026-03-17 | 2026-03-19 21:09 | 2026-03-18 | 2026-03-19 21:09 | 2026-03-19 | 2026-03-24 15:50 | 2026-03-27 | 2026-03-27 19:09 |  |  |  |  | 2026-05-19 | 2026-05-21 12:34 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-04-11 | 2026-05-16 19:29 | Site is RTMI | 2026-02-18 | 2026-02-18 12:18 | 1381085 | 248595 | 0 | 0 | 0 | 0 | 1356679.0787 | 229063 | 2026-05-21 17:51:09 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-19 12:04:36 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-05-13 19:05:27 +0530 | Priyanka Mathur | Client we called they said we will have meeting next week. | 2026-05-20 | 2026-05-19 19:53 | 2026-10-06 |  | Under Construction | 2026-10-31
18474 | Turnkey | 2026-01-01 | Suresh Kumarreddy | Sohan exotica | BNG - HRBR | Yes | Arjun M V | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S | Raghavendra S | Abdul Shafeen | Active | Installation | Execution | 3212394 | 3212395 | 3513382 | 0 | 3205036 | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-18 | 2026-02-25 18:38 | 2026-02-25 | 2026-02-25 18:41 | 2026-02-26 | 2026-02-26 19:39 | 2026-03-13 | 2026-03-13 18:40 | 2026-04-12 | 2026-04-11 12:25 | 2026-04-26 | 2026-04-26 14:06 | 2026-02-26 | 2026-02-28 10:55 | 2026-02-27 | 2026-02-28 12:29 | 2026-02-28 | 2026-03-02 15:11 | 2026-03-05 | 2026-03-05 12:16 |  |  |  |  | 2026-03-13 | 2026-03-13 21:08 | 2026-04-14 | 2026-04-19 11:15 | 2026-04-20 | 2026-04-19 18:18 |  |  | 2026-04-27 | 2026-04-28 20:19 | 2026-04-29 | 2026-04-30 12:06 | 2026-05-01 | 2026-04-30 12:12 | 2026-05-18 | 2026-05-05 14:30 |  |  |  |  | 2026-05-05 19:04 | 2026-05-21 | 2026-05-23 19:05 | 2026-06-03 | 2026-05-31 19:29 | 2026-06-01 | 2026-06-02 12:35 | 2026-05-31 | 2026-06-02 16:17 | 2026-06-02 | 2026-06-03 01:37 | 2026-06-11 | 2026-06-10 18:02 |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-05-16 | 2026-05-04 19:12 | 2026-03-06 | 2026-03-13 18:34 | Site is RTMI | 2026-02-18 | 2026-02-18 13:58 | 2977442 | 535939 | 0 | 0 | 3469164.5184 | 572802 | 3481076.5184 | 573924 | 2026-04-29 20:04:30 +0530 | Arjun M V | Some Image was uploaded | 2026-04-27 19:43:56 +0530 | Abdul Shafeen | HOTO: need to clear before QC closure 1) living - ele H side measurements are not generated from walls 2) approval required from cx - tile hollow sound acknowledgement and wall tiles side will be visible after its installation, will project outside after the beadings installaiton | 2026-03-05 19:13:37 +0530 | Rajeshwari S | Some Image was uploaded | 2026-03-14 | 2026-03-13 18:40 | 2026-04-12 | 2026-04-11 12:25
18476 | Test Mode | 2026-01-01 | test abc |  | BNG - HSR | Yes | Pragati Yadav | Reshma Melanta |  | Sushma Hm |  |  |  |  | Syed Mehdi |  | Active | Preproduction | 3D Sign off | 2129428 | 350000 | 3055869 | 3055869 | 0 | 41 | 0 | 0 | 0 | 1016394 | 0 |  |  | 2026-02-18 | 2026-06-01 14:52 | 2026-06-01 | 2026-06-01 15:37 | 2026-06-01 | 2026-06-01 17:14 | 2026-06-02 | 2026-06-02 14:36 | 2026-06-03 | 2026-06-02 16:23 | 2026-06-03 | 2026-06-03 18:15 | 2026-06-01 | 2026-06-02 11:30 | 2026-06-02 | 2026-06-02 11:59 | 2026-06-02 | 2026-06-02 12:24 | 2026-06-02 | 2026-06-02 12:51 |  |  |  |  | 2026-06-02 | 2026-06-02 15:47 | 2026-06-05 | 2026-06-02 18:31 | 2026-06-03 | 2026-06-02 18:37 |  |  | 2026-06-04 | 2026-06-04 15:48 | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-04-16 | 2026-06-01 14:47 | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-06-03 | 2026-06-02 14:07 | Unknown | 2026-02-18 | 2026-06-01 14:47 | 2589720 | 466149 | 2589720 | 466149 | 0 | 0 | 1804600 | 324828 | [9 empty] | 2026-06-03 | 2026-06-02 15:05 | 2026-06-03 | 2026-06-02 16:32 | RTMI
18483 | Turnkey | 2026-01-01 | M/s M Vora Construction (Sagar Avasthi) | Raj heritage | MUM - GOR | Yes | Zoya Ansari | Reshma Melanta | Safalta Karkera |  | Anamika Ghate | Akash Jadhav | Sandeep Tiwari | Murali S | Saloni Sagwekar | Vinay Surve | Active | Installation | Execution | 793207 | 793206 | 1307948 | 0 | 790621 | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-19 | 2026-02-20 13:03 | 2026-02-24 | 2026-02-24 14:04 | 2026-03-01 | 2026-03-01 13:20 | 2026-03-31 | 2026-03-31 14:05 | 2026-04-19 | 2026-04-18 13:54 | 2026-05-02 | 2026-05-02 19:31 | 2026-03-01 | 2026-02-28 | 2026-03-02 | 2026-03-04 11:20 | 2026-03-04 | 2026-03-05 11:31 | 2026-03-06 | 2026-03-06 11:31 |  |  |  |  | 2026-03-31 | 2026-04-11 11:24 | 2026-04-19 | 2026-04-23 18:20 | 2026-04-24 | 2026-04-23 18:25 |  |  | 2026-05-06 | 2026-05-08 15:35 | 2026-05-21 | 2026-05-21 20:44 | 2026-05-22 | 2026-05-21 21:38 | 2026-05-29 | 2026-05-27 18:32 |  |  |  |  | 2026-05-29 18:09 | 2026-06-06 | 2026-06-05 21:24 | 2026-06-28 | 2026-06-26 19:06 | 2026-06-27 | 2026-06-27 12:18 | 2026-06-26 | 2026-07-04 22:15 | 2026-07-04 | 2026-07-04 22:16 | 2026-07-06 |  |  |  | 2026-06-28 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-05-21 | 2026-05-27 13:12 | 2026-03-07 | 2026-03-30 16:54 | Site is RTMI | 2026-02-19 | 2026-02-19 15:40 | 1210125 | 217822 | 0 | 0 | 791721.9703 | 136620 | 794596.1203 | 137014 | 2026-06-25 18:43:17 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-08 00:05:59 +0530 | Akash Jadhav | Procurement: Key task close : 27th may False ceiling Work In progress Floor covering done Electrical work 8th june to 9th june Site readiness 16th june | 2026-06-02 22:58:49 +0530 | Akash Jadhav | Procurement: key task close on 27th may Team as align Tomorrow for floor covering | 2026-04-01 | 2026-03-31 14:16 | 2026-04-19 | 2026-04-18 13:55
18484 | Turnkey | 2026-01-01 | Rahul gopal | Nikoo Homes 4 | BNG - HRBR | Yes | Sanjay Kulkarni | Rajeshwari S | Surabhi Ravichandran | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Nikhil Mogeraya | Saddam Hussain Z M | Murali S | Shashank Singh | Abdul Shafeen | Active | Installation | Execution | 964671 | 964672 | 711438 | 866171 | 964671 | 7 | 34 | 0 | 0 | 0 | 0 |  |  | 2026-02-21 | 2026-02-27 20:28 | 2026-02-28 | 2026-02-28 14:12 | 2026-03-03 | 2026-03-04 14:09 | 2026-03-23 | 2026-03-22 11:37 | 2026-04-16 | 2026-04-15 16:18 | 2026-04-27 | 2026-04-27 19:32 | 2026-02-20 | 2026-02-28 00:20 | 2026-03-05 | 2026-03-06 16:43 | 2026-03-06 | 2026-03-07 16:44 | 2026-03-10 | 2026-03-10 12:23 |  |  |  |  | 2026-03-22 | 2026-03-23 14:10 | 2026-04-24 | 2026-04-26 15:19 | 2026-04-27 | 2026-04-26 15:38 |  |  | 2026-04-28 | 2026-04-30 17:54 | 2026-05-08 | 2026-05-08 13:01 | 2026-07-17 | 2026-05-08 13:18 | 2026-07-18 | 2026-05-11 16:06 |  |  |  |  | 2026-06-22 10:56 | 2026-06-27 | 2026-06-26 20:53 | 2026-07-02 | 2026-07-01 19:36 | 2026-07-01 | 2026-07-02 11:47 | 2026-07-01 | 2026-07-08 18:59 | 2026-07-08 | 2026-07-08 20:13 | 2026-07-15 | 2026-07-14 19:04 |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-30 | 2026-06-22 10:55 | 2026-03-11 | 2026-03-22 11:33 | Site is RTMI | 2026-02-21 | 2026-02-27 11:32 | 687659 | 123778 | 861162 | 155009 | 1029752.7138 | 170034 | 1029752.7138 | 170034 | 2026-06-23 11:55:02 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 15-06-2026 to 23-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scopeKey Dates: Modular materials dispatched - PH will update youHandover as per TAT- TBD36working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of executionNote Hi sir kindly let me know when will be the site ready. as disscused with you . You told me that that by 28th june it will ready and I will get the key | 2026-05-13 11:30:07 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-07 16:49:05 +0530 | Rajeshwari S | Client is visiting office on 7th May for design meeting will collect 10% payment and proceed furthre | 2026-03-23 | 2026-03-22 11:47 | 2026-04-16 | 2026-04-15 16:18
18485 | Turnkey | 2026-01-01 | Akash | PURVA ATMOSPHERE | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  | Sethuragavan R | Harshit Choudhary | Saddam Hussain Z M | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Completed | Complete | Completed | 2120276 | 2120276 | 2547328 | 2123404 | 2120276 | 22 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-19 | 2026-02-20 12:35 | 2026-02-20 | 2026-02-20 14:48 | 2026-02-20 | 2026-02-21 11:59 | 2026-03-15 | 2026-03-11 19:05 | 2026-03-22 | 2026-03-21 23:21 | 2026-03-29 | 2026-03-29 17:08 | 2026-02-21 | 2026-02-23 12:31 | 2026-02-22 | 2026-02-25 15:16 | 2026-02-25 | 2026-02-25 18:16 | 2026-03-06 | 2026-03-06 18:18 |  |  |  |  | 2026-03-11 | 2026-03-16 18:19 | 2026-03-22 | 2026-03-24 18:19 | 2026-03-25 | 2026-03-24 18:51 |  |  | 2026-03-30 | 2026-04-03 19:29 | 2026-04-04 | 2026-04-04 18:59 | 2026-04-05 | 2026-04-04 19:31 | 2026-04-05 | 2026-04-07 11:10 |  |  |  |  | 2026-04-07 17:08 | 2026-04-18 | 2026-04-17 19:35 | 2026-05-02 | 2026-04-30 19:13 | 2026-04-30 | 2026-04-28 19:55 | 2026-04-30 | 2026-05-04 16:44 | 2026-05-04 | 2026-05-05 13:32 | 2026-05-10 | 2026-05-09 18:34 |  |  | 2026-06-09 | 2026-06-10 16:16 | 2026-06-11 | 2026-06-10 17:15 | 2026-06-12 | 2026-06-10 21:51 |  |  |  |  | 2026-04-04 | 2026-04-07 17:07 | 2026-03-07 | 2026-03-11 19:03 | Site is RTMI | 2026-02-19 | 2026-02-19 18:53 | 2158753 | 388575 | 2494731.4132 | 411926 | 2491830.5093 | 411448 | 2491830.5093 | 411448 | 2026-06-11 09:59:20 +0530 | Saddam Hussain Z M | Execution: Wallpaper installation pending due to client dependency work, ETA 17th June | 2026-03-31 20:12:24 +0530 | Kiran Agarampalli | Some Image was uploaded | 2026-03-31 19:52:14 +0530 | Kiran Agarampalli | Pooja Unit Back frame visible side will be Creamy white SD | 2026-03-12 | 2026-03-11 19:08 | 2026-03-22 | 2026-03-21 23:23
18486 | Turnkey | 2026-01-01 | Piyush shankarani | Kalpataru Elitus | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Saloni Chawan |  | Active | Preproduction | Site Readiness 1 | 1700156 | 340031 | 2319297 | 0 | 0 | 5 | 111 | 0 | 0 | 774787 | 585338.4 |  |  | 2026-02-19 | 2026-02-19 20:15 | 2026-02-27 | 2026-02-27 20:11 | 2026-02-27 | 2026-02-27 20:14 | 2026-03-19 | 2026-03-18 19:27 | 2026-07-17 |  | 2026-07-24 |  | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-03-04 20:02 | 2026-03-04 | 2026-03-09 11:02 | 2026-03-11 | 2026-03-11 11:03 |  |  |  |  | 2026-03-19 | 2026-03-18 11:44 | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-03-12 | 2026-03-18 11:26 | Site is Non-RTMI | 2026-02-19 | 2026-02-19 19:09 | 1965506 | 353791 | 0 | 0 | 0 | 0 | 1936447.0394 | 308922 | 2026-03-21 12:54:35 +0530 | Sagarika Gawai | Parent's Bedroom & Son's Bedroom swapped Parent's Bedroom-Wardrobe and bed to be aligned in one line to look integrated as oneTwo door wardrobeSingle bed against the windowCNC jaali design theme in bedroomColor options to be suggestedMirror on wall & Drawer below as dresser unit Son's Bedroom-Wardrobe and study table to be integrated as oneBed wall to be highlighted with trophies and other decor with shelvesBed size 6ft by 6ftWallpaper concept on bed wallTwo door wardrobe with mirror on one shutterStudy table with shelves and top storage Study Room-Study table for 2Long ledge with no drawers belowSmall shelf above ledge to keep small items or decor piecesStorage on topLights below ledge Master Bedroom-Two options to be given on furniture placementBed size 6ft by 6ftWall concept on bed wall options to be providedWardrobe placement options along with dresser Vanity unit colors to be discussed in next meeting Living & Dining Areas-3 seater sofa1 Jhula4 seater dining setSon's photo to be placed on wall adjacent to sofaDecor element on Kitchen wall and Dining wallPartition to cover fridge with shelves and metal gridTV unit design options to be givenWall clock Kitchen-Membrane shuttersColor options to be given for overall spaceGlass shutter options to be shown False ceiling-Living & Dining area Next DDM 2 meeting planned in the month of April | 2026-03-11 11:02:00 +0530 | Anil Jagtap | WC - shared all details about next steps | 2026-03-09 11:01:59 +0530 | Royden Henriques |  | 2026-03-17 | 2026-03-21 13:00 | 2026-07-18
18487 | Turnkey | 2026-01-01 | Sushant Vats | Jeevans Octave | BNG - HRBR | Yes | Sanjay Kulkarni | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Deekshith P | Jairam Joshi | Murali S | Raghavendra S | Abdul Shafeen | Completed | Complete | Completed | 701029 | 701030 | 862809 | 700228 | 701029 | 49 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-20 | 2026-02-24 19:16 | 2026-02-24 | 2026-02-24 19:16 | 2026-02-24 | 2026-02-24 19:29 | 2026-03-22 | 2026-03-22 11:26 | 2026-03-27 | 2026-03-26 10:20 | 2026-03-29 | 2026-03-29 11:37 | 2026-02-24 | 2026-02-25 12:13 | 2026-02-25 | 2026-02-26 15:26 | 2026-02-26 | 2026-02-26 16:36 | 2026-02-28 | 2026-02-28 20:18 |  |  |  |  | 2026-03-27 | 2026-03-23 14:04 | 2026-03-27 | 2026-03-28 16:04 | 2026-03-29 | 2026-03-28 16:57 |  |  | 2026-03-30 | 2026-03-30 12:27 | 2026-03-30 | 2026-03-30 15:23 | 2026-03-31 | 2026-03-30 15:35 | 2026-03-31 | 2026-04-03 17:45 |  |  |  |  | 2026-04-07 15:02 | 2026-04-19 | 2026-04-18 21:42 | 2026-04-26 | 2026-04-24 20:17 | 2026-04-25 | 2026-04-25 11:10 | 2026-04-24 | 2026-04-25 12:46 | 2026-04-25 | 2026-04-26 00:01 | 2026-04-29 | 2026-05-02 15:03 |  |  | 2026-05-12 | 2026-05-12 17:25 | 2026-05-14 | 2026-05-12 17:48 | 2026-05-15 | 2026-05-13 17:11 |  |  |  |  | 2026-03-30 | 2026-04-04 10:55 | 2026-03-10 | 2026-03-22 11:20 | Site is RTMI | 2026-02-20 | 2026-02-24 18:26 | 731194 | 131615 | 776208.143 | 128170 | 776948.363 | 128292 | 776948.363 | 128292 | 2026-05-13 17:18:22 +0530 | Jairam Joshi | Project Closure Pending: Observation points Closure - 27th May | 2026-04-24 16:11:27 +0530 | Jairam Joshi | Procurement: PI works completed SRD task closed | 2026-04-24 10:57:20 +0530 | Yogesh B | Some Image was uploaded | 2026-03-23 | 2026-03-22 11:31 | 2026-03-27 | 2026-03-26 10:21
18488 | Sub Project |  | Kartik Pandit | vivajvasu | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera |  |  | Nilesh Patel | Rizwan Mistry | Murali S |  | Vinay Surve | Completed | Complete | Completed | 95574 | 95574 | 0 | 0 | 95574 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-20 | 2026-02-20 16:41 | 2026-02-21 | 2026-02-20 16:41 | 2026-02-20 | 2026-02-20 16:42 | 2026-02-21 | 2026-02-20 16:43 | 2026-03-10 | 2026-02-20 16:41 | 2026-02-21 | 2026-02-21 16:41 | 2026-02-20 | 2026-02-20 16:42 | 2026-02-21 | 2026-02-20 16:42 | 2026-02-20 | 2026-02-20 16:42 | 2026-02-21 | 2026-02-20 16:42 |  |  |  |  | 2026-02-20 | 2026-02-20 16:43 | 2026-03-12 | 2026-02-20 16:40 | 2026-03-13 | 2026-02-20 16:40 |  |  | 2026-02-22 | 2026-02-26 12:38 | 2026-02-26 | 2026-02-26 16:34 | 2026-02-27 | 2026-02-27 13:42 | 2026-02-28 | 2026-02-27 13:43 |  |  |  |  | 2026-03-06 18:17 | 2026-03-15 | 2026-03-28 14:53 | 2026-03-30 | 2026-03-28 18:52 | 2026-03-26 | 2026-02-27 17:09 | 2026-03-28 | 2026-03-30 16:06 | 2026-03-31 | 2026-04-09 15:42 | 2026-04-28 | 2026-04-27 21:36 |  |  | 2026-05-07 | 2026-04-28 11:42 | 2026-05-09 | 2026-04-28 11:44 | 2026-05-10 | 2026-04-28 11:46 |  |  |  |  | 2026-02-23 | 2026-02-24 10:07 | 2026-02-21 | 2026-02-20 16:42 | Unknown | 2026-02-20 | 2026-02-20 16:41 | 0 | 0 | 0 | 0 | 158113 | 28460 | 158113 | 28460 | 2026-04-13 15:34:06 +0530 | Nilesh Patel | Execution: Bed has been assembled but due to moulding behind the bed wall, the wall mounted headboard cannot be fixed. Pending Installation - Side table knobs -Headboard ply (Modulars) -Headboard (ready at warehouse Aadeshwar) | 2026-02-24 16:10:03 +0530 | Avinash Jaiswal | Some Image was uploaded |  |  |  | 2026-02-21 | 2026-02-20 16:43 | 2026-03-11 | 2026-02-20 16:41
18490 | Turnkey | 2026-01-01 | Prachi Joshi Bhombay | Purva Palm beach | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S | Janvi Nagdeo | Vishwa Hiremath | Completed | Complete | Completed | 1438103 | 1438108 | 1300755 | 0 | 1425267 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-20 | 2026-02-20 15:27 | 2026-02-21 | 2026-02-25 11:25 | 2026-03-01 | 2026-03-05 13:48 | 2026-03-22 | 2026-03-22 19:20 | 2026-03-26 | 2026-03-25 16:05 | 2026-03-31 | 2026-03-31 09:27 | 2026-03-01 | 2026-03-04 18:49 | 2026-03-06 | 2026-03-05 13:50 | 2026-03-05 | 2026-03-05 15:45 | 2026-03-07 | 2026-03-07 17:51 |  |  |  |  | 2026-03-22 | 2026-03-23 14:57 | 2026-03-26 | 2026-03-29 11:09 | 2026-03-30 | 2026-03-29 12:05 |  |  | 2026-03-31 | 2026-03-31 19:47 | 2026-03-31 | 2026-03-31 22:45 | 2026-04-01 | 2026-03-31 22:53 | 2026-04-01 | 2026-04-02 18:04 |  |  |  |  | 2026-04-07 14:59 | 2026-04-16 | 2026-04-15 21:07 | 2026-04-29 | 2026-04-27 21:44 | 2026-04-23 | 2026-04-20 19:34 | 2026-04-27 | 2026-04-28 20:08 | 2026-04-28 | 2026-04-28 20:24 | 2026-05-06 | 2026-05-06 18:09 |  |  | 2026-06-12 | 2026-06-13 15:13 | 2026-06-23 | 2026-06-13 15:31 | 2026-06-24 | 2026-06-13 20:07 |  |  |  |  | 2026-03-31 | 2026-04-04 11:27 | 2026-03-08 | 2026-03-22 18:54 | Site is RTMI | 2026-02-20 | 2026-02-20 15:20 | 1102334 | 198420 | 0 | 0 | 1423721.3213 | 250972 | 1436068.9963 | 252931 | 2026-06-13 20:11:06 +0530 | Saddam Hussain Z M | Execution: Observation Points - 29th June | 2026-04-14 16:00:54 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-03-22 19:29:01 +0530 | Priyanka R | DDM2: 21/03/2026 Foyer- No ChangesTV unit- N0 changesCrockery unit- Wall unit till top , open box, ledgesKitchen- remove Graniteutility- No chnageMBR- wardrobe add stripMBR- remove mirrorBedroom-1- no changesVanity- Remove wall unitBalcony- No changes Material selection done Foyer Lam SL AW 1mm 2292 Meraki Walnut (Gold) Mysore Ivory(Platinum) TV unit Lam SL AW 1mm 2292 Meraki Walnut (Gold) Mysore Ivory(Platinum) Lam SL HG 1mm 1462 Bianco Carrara Venato(Gold) Crockery Lam SL AW 1mm 2292 Meraki Walnut (Gold) Mysore Ivory(Platinum) Utility Lam SL AW 1mm 2292 Meraki Walnut (Gold) MBR Lam SL LUV 1mm 1638 Sicily Bright(Platinum) Lam SL AFP 1mm 1005 Creamy White(Diamond) Lam SL AW 1mm 2292 Meraki Walnut (Gold Bedroom-1 Lam SL AFP 1mm 1005 Creamy White(Diamond) Lam SL SD 1mm 2164 Salix Oak(Gold) | 2026-03-23 | 2026-03-22 19:33 | 2026-03-26 | 2026-03-25 16:08
18493 | Turnkey | 2026-01-01 | Mihika Sharma ,Manoj Sharma Ravi Shankar Sharma | ** | MUM - GOR | Yes | Pratima Kajwe |  | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 2112238 | 29999 | 2112238 | 0 | 0 | 106 | 0 | 181225 | 211224 | 857109 | 832681.2 |  |  | 2026-02-20 | 2026-02-20 18:42 | 2026-03-07 | 2026-03-07 21:51 | 2026-03-15 | 2026-03-31 19:00 | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-02-20 | 2026-02-20 18:39 | 1790032 | 322205 | 0 | 0 | 0 | 0 | 1790032 | 322205 | 2026-04-14 14:34:57 +0530 | Mrunali Mitkari | Client has holded the cheque reading the negative reviews, Wants a discussion before he does the payment. He is out of town will conduct the meeting once he is back | 2026-04-04 12:25:05 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-04 12:24:32 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-08 |  | 2026-04-15
18496 | Turnkey | 2026-01-01 | Amitava Dutta | Rohan Ekanta | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1536221 | 307244.05 | 1536221 | 0 | 0 | 36 | 78 | 0 | 0 | 646479 | 582498 |  |  | 2026-02-21 | 2026-02-21 12:27 | 2026-02-21 | 2026-02-21 13:47 | 2026-03-04 | 2026-03-04 11:20 | 2026-04-11 | 2026-04-10 10:50 | 2026-07-12 |  | 2026-08-04 |  | 2026-02-26 | 2026-02-28 | 2026-02-27 | 2026-03-02 12:54 | 2026-03-02 | 2026-03-03 11:52 | 2026-03-05 | 2026-03-05 20:03 |  |  |  |  | 2026-05-21 | 2026-04-08 19:37 | 2026-07-30 |  | 2026-07-31 |  |  |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 | [6 empty] | 2026-08-28 |  | 2026-09-06 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-09 |  |  |  | 2026-10-01 |  | 2026-10-03 |  | 2026-10-04 | [5 empty] | 2026-08-08 |  | 2026-05-16 | 2026-04-10 10:46 | Site is RTMI | 2026-02-21 | 2026-02-21 12:25 | 1622466.0916 | 267898 | 0 | 0 | 0 | 0 | 1622466.0916 | 267898 | 2026-05-28 19:32:02 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-10 11:03:33 +0530 | Abhinandan K S | Some Image was uploaded | 2026-03-18 12:23:20 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-11 | 2026-04-10 10:51 | 2026-07-13
18498 | Turnkey | 2026-01-01 | Anoop | Jai Royal Park | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [7 empty] | Active | Prospect | 10% Payment | 1835257 | 9999 | 0 | 0 | 0 | 112 | 0 | 173527 | 183526 | 805945 | 662260.8 |  |  | 2026-02-21 | 2026-02-21 13:22 | 2026-02-21 | 2026-03-25 18:48 | 2026-03-28 | 2026-03-25 19:11 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-02-21 | 2026-02-21 13:08 | 0 | 0 | 0 | 0 | 0 | 0 | 1555302 | 279954 | 2026-04-30 15:27:16 +0530 | Yogesh B | Some Image was uploaded | 2026-03-25 18:27:21 +0530 | Priyanka Gs | Some Image was uploaded |  |  |  | 2026-04-02 |  | 2026-04-09
18500 | Turnkey | 2026-01-01 | VijayKumar Laxmidas Parikh ( Sejal Parikh) | Adani The View | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Design | DEM1 | 1750515 | 232590 | 2325903 | 0 | 0 | 132 | 0 | 0 | 117513 | 710546 | 689866.4 |  |  | 2026-02-21 | 2026-02-21 20:11 | 2026-02-22 | 2026-02-22 11:23 | 2026-03-01 | 2026-03-01 14:17 | 2026-09-06 |  | 2026-09-13 |  | 2026-09-20 |  | 2026-03-01 | 2026-02-28 | 2026-03-02 | 2026-03-04 11:20 | 2026-03-04 | 2026-03-05 15:46 | 2026-03-14 | 2026-03-14 17:54 |  |  |  |  | 2026-09-07 |  | 2026-09-15 |  | 2026-09-16 |  |  |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 | [6 empty] | 2026-10-14 |  | 2026-10-23 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-26 |  |  |  | 2026-11-17 |  | 2026-11-19 |  | 2026-11-20 | [5 empty] | 2026-09-24 |  | 2026-09-02 |  | Unknown | 2026-02-21 | 2026-02-21 13:32 | 1971104 | 354798 | 0 | 0 | 0 | 0 | 1917975.53 | 316604 | 2026-06-17 17:44:23 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-15 12:08:59 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-03 17:50:53 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-09-07 |  | 2026-09-14 |  | Under Construction | 2026-04-01
18502 | Turnkey | 2026-01-01 | Alifiya Magar | Lodha Amara | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | Asif Shaikh | Aditya Vikram | Murali S | Aryan Singh | Prasad Bhivaji Hande | Active | Preproduction | Procurement | 1562700 | 1041840 | 1683990 | 0 | 1562700 | 12 | 41 | 0 | 0 | 0 | 520860 |  |  | 2026-02-21 | 2026-02-21 14:37 | 2026-02-22 | 2026-02-21 15:32 | 2026-03-04 | 2026-03-04 17:47 | 2026-05-09 | 2026-05-09 20:18 | 2026-06-12 | 2026-06-11 11:55 | 2026-06-19 | 2026-06-17 00:46 | 2026-03-04 | 2026-03-06 13:51 | 2026-03-05 | 2026-03-06 13:53 | 2026-03-06 | 2026-03-06 17:27 | 2026-03-11 | 2026-03-11 11:05 |  |  |  |  | 2026-06-19 | 2026-05-09 17:47 | 2026-06-14 | 2026-06-13 13:01 | 2026-06-14 | 2026-06-15 10:31 |  |  | 2026-06-19 | 2026-06-27 16:26 | 2026-06-27 | 2026-06-27 19:44 | 2026-06-30 | 2026-06-27 20:24 | 2026-06-28 | 2026-07-02 12:28 |  |  |  |  | 2026-07-03 17:41 | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-09-08 | [5 empty] | 2026-06-27 | 2026-07-03 08:29 | 2026-05-20 | 2026-05-09 19:10 | Site is Non-RTMI | 2026-02-21 | 2026-02-21 14:36 | 1427110 | 256879 | 0 | 0 | 1698872.5651 | 284140 | 1698872.5651 | 284140 | 2026-07-12 11:56:18 +0530 | Asif Shaikh | Procurement: False Ceiling & electrical work in progress & will be completed by 20thÂ July (Tentative). First coat painting work shall be commencing from 20thÂ July & will be completed by 27thÂ July (Tentative) Furniture shall be ready for dispatched between 27thÂ July to 30thÂ July (Tentative). Delayed Reason in PI work : 1. BOM closed on 3rd July. Vendor PO share on 6th July Vendor has started the work on site -- 11th July. | 2026-07-06 23:22:06 +0530 | Asif Shaikh | Procurement: PI work yet to assigned. Floor Covering work will be done on 8thÂ July. False Ceiling & electrical work shall be commencing from 9thÂ July & will be completed by 20thÂ July (Tentative). First coat painting work shall be commencing from 20thÂ July & will be completed by 27thÂ July (Tentative) Furniture shall be ready for dispatched between 27thÂ July to 30thÂ July (Tentative). | 2026-06-27 13:20:20 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-10 | 2026-05-09 20:24 | 2026-06-12 | 2026-06-11 11:59 | Under Construction | 2026-05-01
18503 | Turnkey | 2026-01-01 | Bapu R MORE | Pearl garden Vasai west | MUM - GOR | Yes | Yash Jain |  | Shraddha Badgujar | [5 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1717140 | 9999 | 1717140 | 0 | 0 | 141 | 0 | 161715 | 171714 | 746027 | 627685.2 |  |  | 2026-02-21 | 2026-02-22 22:04 | 2026-02-24 | 2026-02-24 12:20 | 2026-02-28 | 2026-02-28 08:40 | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 | [5 empty] | 2026-03-08 |  | 2026-03-16 |  | 2026-03-17 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 | [6 empty] | 2026-04-14 |  | 2026-04-23 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-18 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-03-25 |  | 2026-03-03 |  | Unknown | 2026-02-21 | 2026-02-22 22:03 | 1455203 | 261936 | 0 | 0 | 0 | 0 | 1455203 | 261936 | 2026-02-23 19:47:48 +0530 | Yash Jain | DCM: PID - Bapu More - 10L-15L bonito's scope North on right side, south on left side Pearl Garden - 917sqft Rera Carpet Area Family of 4 - 2 daughter and couple Living room sofa seating - 4-6 seater no mandir unit req Vastu - bedÂ buddha idol/statue dining table - 6 seater tv unit on right wall near balcony storage 2 drawer and 1 open unit, crockery unit - glass storages tall unit 2 swingÂ Shoe rack - 30-40pairs Carrom board storage, book storageÂ Ch - bed (DAUGHTER 9YRS) STUDY CUM/GUEST Storage for clothes and books, wardrobe, study table , single bedÂ right master bedroom, QSB,Wardrobe,Dresser table with mirror, Foldable study ledge,Tv unit. No kitchen. Left master bedroom - Shreya QSB, Wardrobe, dresser with mirror,Â suitcase for rifle shooting, with gun, study table book storage. medal storage ,Timeless, wood finihses, warm cozy, moulding, wallpaper modern home,open to designs | [6 empty] | 2026-03-08 |  | 2026-03-15
18504 | Sub Project |  | Rohit Satish | Lodha AMara | MUM - Thane |  | Asavari Vare | Sarita Jangid | Sneha Kadam |  |  | Faraz Soudagar | Aditya Vikram | Murali S |  |  | Completed | Complete | Completed | -165 | 0 | 0 | 0 | -165 | 95 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-21 | 2026-02-26 15:14 | 2026-02-22 | 2026-02-26 15:14 | 2026-02-26 | 2026-02-26 15:15 | 2026-02-27 | 2026-02-26 15:16 | 2026-02-27 | 2026-02-26 15:18 | 2026-02-27 | 2026-02-26 15:19 | 2026-02-26 | 2026-02-26 15:15 | 2026-02-27 | 2026-02-26 15:15 | 2026-02-26 | 2026-02-26 15:15 | 2026-02-27 | 2026-02-26 15:16 |  |  |  |  | 2026-02-26 | 2026-02-26 15:17 | 2026-02-27 | 2026-02-26 15:18 | 2026-02-27 | 2026-02-26 15:18 |  |  | 2026-02-28 | 2026-03-04 17:16 | 2026-03-04 | 2026-03-04 19:14 | 2026-03-06 | 2026-03-08 12:53 | 2026-03-09 | 2026-03-08 12:53 |  |  |  |  | 2026-03-08 16:40 | 2026-03-15 | 2026-03-14 22:36 | 2026-03-18 | 2026-03-16 16:25 | 2026-03-17 | 2026-03-20 17:34 | 2026-03-16 | 2026-04-09 15:52 | 2026-04-09 | 2026-04-09 19:33 | 2026-04-12 | 2026-04-11 18:50 |  |  | 2026-04-13 | 2026-04-11 18:54 | 2026-04-13 | 2026-04-11 18:54 | 2026-04-11 | 2026-04-11 18:56 |  |  |  |  | 2026-03-04 | 2026-03-05 11:05 | 2026-02-27 | 2026-02-26 15:16 | Unknown | 2026-02-21 | 2026-02-26 15:14 | 0 | 0 | 0 | 0 | 53249 | 9584 | 53249 | 9584 | [9 empty] | 2026-02-27 | 2026-02-26 15:16 | 2026-02-27 | 2026-02-26 15:18
18506 | Turnkey | 2026-01-01 | Amit Kumar | Lodha Splendora | MUM - Thane | Yes | Chaitali Sawant | Divya Rahangdale | Sneha Kadam | [5 empty] | Mustufa Sohagpurwala |  | Lost | Preproduction | DEM2 | 991578 | 198316 | 1549426 | 0 | 0 | 119 | 0 | 0 | 0 | 424457 | 368804.8 |  |  | 2026-02-21 | 2026-02-21 16:12 | 2026-02-24 | 2026-02-24 11:43 | 2026-02-27 | 2026-03-04 11:26 | 2026-03-13 | 2026-03-13 19:08 | 2026-07-11 |  | 2026-09-30 |  | 2026-03-04 | 2026-02-28 | 2026-03-05 | 2026-03-06 12:30 | 2026-03-06 | 2026-03-12 13:16 | 2026-03-13 | 2026-03-13 18:03 |  |  |  |  | 2026-03-14 | 2026-03-18 14:45 | 2026-09-25 |  | 2026-09-26 |  |  |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-06 | [6 empty] | 2026-10-24 |  | 2026-11-02 |  | 2026-11-01 |  | 2026-11-02 |  | 2026-11-03 |  | 2026-11-05 |  |  |  | 2026-11-27 |  | 2026-11-29 |  | 2026-11-30 | [5 empty] | 2026-10-04 |  | 2026-03-14 | 2026-03-13 18:18 | Site is RTMI | 2026-02-21 | 2026-02-21 16:11 | 1313073 | 236353 | 0 | 0 | 0 | 0 | 1048392.6485 | 169562 | 2026-05-28 18:57:38 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-28 18:08:32 +0530 | Sneha Kadam | Some Image was uploaded | 2026-04-14 14:01:34 +0530 | Chaitali Sawant | There is ongoing floor tile work on 7th March.Â Since initial measurement was planned for 8th march and client was available before that,Â So DEM 1 was done on floor plan. MOM for DEM 1 in EC.- 7th March Need Kitchen appliances size Existing Fridge - 24"x29"x 64" - WxDxH Existing Microwave -Â 20"x14"x11" - WxDXH Existing Ro unit - 15"x 11' x 18"Â - wxdxh We removed spice pullout. only drawers Chimney - Filter chimneyÂ Existing Cooktop - 3 burnerÂ Guest room- Bed - 5'2"x 7' Master bedroom -Â Existing bed - king size - 6' x 7' Side table removed and added tall dresser unit , Wallpaper horizontally.Â PBR-Â Only wardrobe in scope Living room -Â Curtain till ceiling,Â only periphery ceiling, middle portion may show slab undulation which is OK. tv wallÂ No store roomÂ DEM 1 - 13th March- Online meeting to go through the revised design scope due to cost concern.Â Â TV unit will not have set top box - Confirmed TV only in Living After discussing layout and costing line items are fixed. Tentative costing shared on mail.Â once 10% payment is done, we can confirm site visit slot.Â Tentatively 3rd April is booked . Client paid 10% on 18th March due to funds.and mentioned in onboarding mail as well.Â Â 3rd April - Material selection in EC KitchenÂ Living room metallic accent changed to black.To avoid diff color shade in diff materials Sofa color to check and cofirm- blue or cream brown. pending Material selection donr.Â CM site visit confirmed for 15th April by client. | 2026-03-14 | 2026-03-21 18:30 | 2026-07-12
18507 | Turnkey | 2026-01-01 | Ajay Doshi | Lodha Woods | MUM - GOR | No Estimate | Yash Jain |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-12 | 2026-05-13 18:44 | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 | [5 empty] | 2026-03-08 |  | 2026-03-16 |  | 2026-03-17 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 | [6 empty] | 2026-04-14 |  | 2026-04-23 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-18 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-03-25 |  | 2026-03-03 |  | Unknown | 2026-02-12 | 2026-05-13 18:38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-13 17:08:44 +0530 | Saloni Sagwekar | Some Image was uploaded | 2026-05-13 17:03:35 +0530 | Saloni Sagwekar | Some Image was uploaded |  |  |  | 2026-03-08 |  | 2026-03-15
18510 | Turnkey | 2026-01-01 | Sunil Anantrao Pantoji | Mahindra Eden | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Varun Mandana |  | Active | Preproduction | DEM2 | 2483980 | 496808 | 3303077 | 0 | 0 | 78 | 0 | 0 | 0 | 1083637 | 903534.8 |  |  | 2026-02-21 | 2026-02-21 16:43 | 2026-02-22 | 2026-02-22 13:30 | 2026-02-28 | 2026-02-28 20:17 | 2026-04-30 | 2026-05-01 17:27 | 2026-07-26 |  | 2026-08-02 |  | 2026-02-28 | 2026-02-28 | 2026-03-01 | 2026-03-04 13:17 | 2026-03-04 | 2026-03-04 16:51 | 2026-03-06 | 2026-03-06 17:46 |  |  |  |  | 2026-05-01 | 2026-04-28 19:46 | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-04-04 | 2026-04-26 17:28 | Site is RTMI | 2026-02-21 | 2026-02-21 16:20 | 2799218 | 503859 | 0 | 0 | 0 | 0 | 2741199.0737 | 462810 | 2026-07-14 13:04:40 +0530 | Kiran Agarampalli |  | 2026-04-26 17:26:25 +0530 | Kiran Agarampalli | DDM1: Veranda:Add Shoe rack with seater. Straight wall to be kind of a feature wall with wall concept and platers to be placed. Foyer:Feature wall with wall concept, mirror and console table. Living: TV Unit design to be changed on the wall Crockery unit, right side existing pooja cabinet to be placed. need to see if it can be covered. Niche area to have pantry unit with Mio pullout Kitchen: Proper alignment to be done, requirement wise everything is fineUnder counter RO Utility:Grill side washing machine and dishwasher to be planned Shaft side Sink to be provided Daughter bedroom 1: Add bay seater with storage, add study and bed side table together Headboard deign to be added Add mirror full height ceiling to be as per reference with wave pattern, need to check the feasibility. Wardrobe with curve design. Toilet add drawer for vanity Master Bedroom:Walkin space- one side with wall-to-wall wardrobe Mirror with dresser on the adjacent wall Wardrobe right corner to be open unit wardrobe inside the bedroom to be with some combination of open and glass shutter not fully plain or add drawers in the bottom and wardrobe on the topMBR existing bed is retained, wooden bed Match the headboard accordingly Daughter Bedroom 2:To be discussed Entire house false ceiling to be considered | 2026-03-04 16:51:08 +0530 | Bency Chacko | Possession - April end - Non RTMI IDM - 14th March 2026 - 10% pay B2C - Self-funded No on-site work is planned Will start designs after April Checklist cleared, timelines cleared Scope cleared | 2026-05-02 | 2026-05-01 17:28 | 2026-07-27
18511 | Turnkey | 2026-01-01 | ARPAN SARKAR | ASSETZ BLOOM & DELL - PHASE 2- TOWER 2 | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Hold | Preproduction | Site Readiness 1 | 1722898 | 344502 | 2225201 | 0 | 0 | 6 | 90 | 0 | 0 | 730442 | 647954 |  |  | 2026-02-21 | 2026-02-21 19:44 | 2026-02-22 | 2026-02-22 19:13 | 2026-03-15 | 2026-03-17 11:56 | 2026-04-10 | 2026-04-10 11:01 | 2026-09-15 |  | 2026-09-22 |  | 2026-03-17 | 2026-03-17 18:46 | 2026-03-18 | 2026-03-18 19:34 | 2026-03-18 | 2026-03-20 18:17 | 2026-03-24 | 2026-03-24 19:18 |  |  |  |  | 2026-10-05 | 2026-04-06 22:11 | 2026-09-17 |  | 2026-09-18 |  |  |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-28 | [6 empty] | 2026-10-16 |  | 2026-10-25 |  | 2026-10-24 |  | 2026-10-25 |  | 2026-10-26 |  | 2026-10-28 |  |  |  | 2026-11-19 |  | 2026-11-21 |  | 2026-11-22 | [5 empty] | 2026-09-26 |  | 2026-09-30 | 2026-04-10 10:43 | Site is Non-RTMI | 2026-02-21 | 2026-02-21 19:27 | 1885763 | 339437 | 0 | 0 | 0 | 0 | 1890811.3803 | 312205 | 2026-04-16 15:03:25 +0530 | Lalitha Ajay Kumar | Some Image was uploaded | 2026-03-28 13:19:17 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-03-20 18:16:46 +0530 | Bency Chacko | Possession - Sept 2026, but deviation given up to March 2027 - IMs can start design meeting - immediately Will close the 10% on 30th Dec after LFM No on-site work is planned No civil work B2C - Self-funded Clear with timelines and scope of work | 2026-04-11 | 2026-04-10 15:17 | 2026-09-16 |  | Under Construction | 2026-09-30
18512 | Turnkey | 2026-01-01 | mukesh kumar | **************** | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 1592555 | 9999 | 0 | 0 | 0 | 144 | 0 | 149257 | 159256 | 637022 | 637022 |  |  | 2026-02-21 | 2026-02-21 19:46 | 2026-02-22 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-03-18 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-26 |  | 2026-02-27 | [5 empty] | 2026-03-05 |  | 2026-03-13 |  | 2026-03-14 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 | [6 empty] | 2026-04-11 |  | 2026-04-20 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-23 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-03-22 |  | 2026-02-28 |  | Unknown | 2026-02-21 | 2026-02-21 19:45 | 0 | 0 | 0 | 0 | 0 | 0 | 1349622 | 242932 | [9 empty] | 2026-03-05 |  | 2026-03-12
18513 | Turnkey | 2026-01-01 | BHUSHAN NARKAR | Veena Synergy | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  |  | Uday Yadruk | Rizwan Mistry |  | Saloni Sagwekar | Sunil Poojary | Active | Design | DEM3 | 679378 | 209999 | 1181153 | 0 | 0 | 3 | 68 | 0 | 0 | 211450 | 257928.8 |  |  | 2026-02-21 | 2026-02-21 20:09 | 2026-02-22 | 2026-02-22 11:19 | 2026-03-08 | 2026-03-08 21:05 | 2026-04-04 | 2026-04-04 20:51 | 2026-07-11 |  | 2026-07-16 |  | 2026-03-08 | 2026-03-11 13:17 | 2026-03-09 | 2026-03-11 22:41 | 2026-03-11 | 2026-03-13 14:05 | 2026-03-18 | 2026-03-18 18:19 |  |  |  |  | 2026-04-05 | 2026-04-09 12:07 | 2026-07-13 | 2026-07-12 19:12 | 2026-07-13 | 2026-07-12 19:48 |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-05-15 | 2026-04-04 20:45 | Site is Non-RTMI | 2026-02-21 | 2026-02-21 19:25 | 1000977 | 180176 | 0 | 0 | 0 | 0 | 711072.95 | 122701 | 2026-05-03 19:27:33 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-13 20:25:41 +0530 | Shweta Dalvi | Minutes of Meeting (MoM)Client Name: Bhushan Narkar Project ID: 18513 Area: Residential Interior Multiple Spaces Date: [Insert Date] Prepared By: [Insert Name] 1. Living RoomTV UnitConfiguration: 3 drawers + 1 open unit consideredTV Back PanelÂ Mirror paneling shown in 3D designMissing in the quoteMirror Paneling (Near Dining Area) is present in 3D designNot included in the quoteMDF Paneling, shown in 3D designMissing in the quote2. KitchenLoft Units:Â To be designed as per existing wall unitsNot considered in the quote3. Master BedroomBedÂ Febonic bed is considered in the quoteClient requirement: Hydraulic bed (change requested)Wardrobe, Side Table & Loft, as per the initial discussion4. Sons BedroomStudy Storage is missing in the 3D design but included in the quoteBed: Platform bed shown in 3D designFebonic box storage bed is considered in the quote (design mismatch)5. Additional ScopePainting, floor area: 650 sq. ft.Wall area: 1450 sq. ft.Electrification:Â Total cost considered: 34,0636. Key Observations / DiscrepanciesMultiple design elements shown in 3D are missing in the quote:TV back mirror panelDining mirror panelingMDF panelingKitchen loft units are not included in the quoteBedroom inconsistencies:Bed type mismatch (Febonic vs Hydraulic requirement)Sons bedroom bed mismatch (platform vs box storage)Study storage inconsistency (missing in design but included in quote) | 2026-04-03 18:48:37 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-05 | 2026-04-19 15:16 | 2026-07-12 |  | Under Construction | 2026-04-01
18515 | Turnkey | 2026-01-01 | Rajesh Singh | Lodha Upper | MUM - GOR | Yes |  |  | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 1466972 | 9999 | 1466972 | 0 | 0 | 103 | 0 | 136698 | 146697 | 634751 | 538826.4 |  |  | 2026-02-21 | 2026-02-21 19:58 | 2026-03-05 | 2026-03-05 16:37 | 2026-03-14 | 2026-04-03 16:13 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-02-21 | 2026-02-21 19:23 | 1519627.2052 | 257334 | 0 | 0 | 0 | 0 | 1519627.2052 | 257334 | 2026-03-24 15:34:05 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-06 19:34:40 +0530 | Mrunali Mitkari | Gross Notes Name- Rajesh Singh The following fields are required to be filled: Customer Budget:10-12 L Living/ dining room inclusions:decor and sofa Bedroom inclusions:bed wardrobe study Kitchen inclusions:lift if needed Service scope : Example False ceiling, painting, Electricity etc. Timeline related commitment, if any:no any commitments but want to move asap Any Vastu preference or specific donts : Basic Vastu pref Other commitments made to customer:No If the customer has not specified any room-wise inclusion expectations, please mention NA. | 2026-02-28 15:22:19 +0530 | akansha arora | DCM: 28-02-26 (11:30AM) 2.5BHK Possession - Yes (In hand) No. of People will stay - 4 Any theme liked- Japandi & Neo Classical n Son's Bedroom Living & Dining Area + Foyer Area - 1 Shoe Rack + 1 wooden Partition in Foyer AreaExisting 3 seater sofa with 2 seater sofaNew Dining Table - 4 Seater (Outsource)Crockery unit with mirror panelling Highlighter wall (Sofa back)TV unit will back panelling.NOTE - Liked minimal & Japandi theme. Kitchen - Existing Platform (Semi Modular)Base Units Wall Units Loft cabinetsNo Dishwasher provision required. Bedroom 1 (Daughters Bedroom) - Single size bed1 wardrobe1 book shelf on wall1 study unit with storage above. Bedroom 2 (Son's Bedroom) - 1 Nish wardrobe1 king / Queen sized bed1 bed side table1 long study table (might use his existing one)NOTE - Navy blue paint on 2 walls and other furniture's will be in grey finish.No TV provision required. Master Bedroom (Parent's Bedroom) - 1 Nish wardrobeSleek 1 long suspended drawer unit on opposite wall of the bed and on the extreme left corner of the room, 1 floor standing mirror required.1 king size/ queen bed with 2 side tables.NOTE- minimalist with beautification. Washrooms (Common & Master toilet) - 1 Base vanities in each washroom2 shower glass partitions.2 wall mirrors. NOTES- No civil change is required. Quite restricted on the budget part. CDP aligned for Next Saturday 7th March 2026 at 11:30AM. | 2026-04-11 |  | 2026-04-18
18516 | Turnkey | 2026-01-01 | Indira kothakapu | Lodha Splendora | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [7 empty] | Lost | Design | DEM1 | 1583999 | 158999 | 1583999 | 0 | 0 | 132 | 0 | 0 | 157801 | 666936 | 600263.2 |  |  | 2026-02-21 | 2026-02-21 19:41 | 2026-02-25 | 2026-03-02 12:13 | 2026-03-05 | 2026-03-05 15:20 | 2027-12-05 |  | 2027-12-12 |  | 2027-12-19 |  | 2026-03-05 | 2026-03-04 19:12 | 2026-03-06 | 2026-03-05 12:14 | 2026-03-05 | 2026-03-05 14:10 | 2026-03-10 | 2026-03-10 19:27 |  |  |  |  | 2027-12-06 |  | 2027-12-14 |  | 2027-12-15 |  |  |  | 2027-12-22 |  | 2027-12-23 |  | 2027-12-24 |  | 2027-12-25 | [6 empty] | 2028-01-12 |  | 2028-01-21 |  | 2028-01-20 |  | 2028-01-21 |  | 2028-01-22 |  | 2028-01-24 |  |  |  | 2028-02-15 |  | 2028-02-17 |  | 2028-02-18 | [5 empty] | 2027-12-23 |  | 2027-12-01 |  | Unknown | 2026-02-21 | 2026-02-21 19:39 | 1392371 | 241627 | 0 | 0 | 0 | 0 | 1392371 | 241627 | 2026-06-02 14:41:07 +0530 | Anamika Dolai | The client was looking for one-stop solution , we tried retaining but the client is not ready to move forward as the needs doesnot our services. Hence, raised lost request. | 2026-04-22 17:56:25 +0530 | Anil Jagtap | Some Image was uploaded | 2026-04-15 18:31:21 +0530 | Anil Kuwar | Some Image was uploaded | 2027-12-06 |  | 2027-12-13
18517 | Turnkey | 2026-01-01 | Mrs. Megha Vijay Mahorkar | Arihant Aspire | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-21 | 2026-02-22 12:23 | 2026-02-22 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-02-21 | 2026-02-21 22:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-02-22 12:23:19 +0530 | Aryan Singh | Some Image was uploaded | [6 empty] | 2026-04-05 |  | 2026-04-12
18518 | Turnkey | 2026-01-01 | Kundan Kumar Karn | Rohan Ekanta | BNG - HSR | Yes |  | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 940125 | 9999 | 0 | 0 | 0 | 144 | 0 | 84014 | 94013 | 376050 | 376050 |  |  | 2026-02-21 | 2026-02-21 22:11 | 2026-02-22 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 | [5 empty] | 2026-03-08 |  | 2026-03-16 |  | 2026-03-17 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 | [6 empty] | 2026-04-14 |  | 2026-04-23 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-18 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-03-25 |  | 2026-03-03 |  | Unknown | 2026-02-21 | 2026-02-21 22:10 | 0 | 0 | 0 | 0 | 0 | 0 | 796716 | 143409 | [9 empty] | 2026-03-08 |  | 2026-03-15
18520 | Turnkey | 2026-01-01 | Deepak | Purva Almosphere | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Harshit Choudhary | Saddam Hussain Z M | Murali S | Mohammed Rasick | Abdul Shafeen | Completed | Complete | Completed | 1155982 | 1155983 | 1162528 | 1154819 | 1155982 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-21 | 2026-02-26 16:54 | 2026-02-23 | 2026-02-26 19:26 | 2026-03-04 | 2026-03-04 19:32 | 2026-04-01 | 2026-04-01 11:01 | 2026-04-03 | 2026-04-03 11:45 | 2026-04-15 | 2026-04-14 18:23 | 2026-03-04 | 2026-02-28 | 2026-03-05 | 2026-03-04 19:39 | 2026-03-04 | 2026-03-05 13:49 | 2026-03-12 | 2026-03-12 19:03 |  |  |  |  | 2026-04-01 | 2026-04-01 17:29 | 2026-04-04 | 2026-04-05 11:11 | 2026-04-06 | 2026-04-05 11:11 |  |  | 2026-04-15 | 2026-04-17 13:17 | 2026-04-18 | 2026-04-18 15:27 | 2026-04-19 | 2026-04-18 17:15 | 2026-04-21 | 2026-04-20 15:09 |  |  |  |  | 2026-04-21 14:49 | 2026-04-26 | 2026-04-25 21:53 | 2026-05-14 | 2026-05-12 18:36 | 2026-04-21 | 2026-02-27 18:50 | 2026-05-12 | 2026-05-14 20:01 | 2026-05-14 | 2026-05-14 20:10 | 2026-05-19 | 2026-05-19 18:21 |  |  | 2026-06-12 | 2026-06-13 15:12 | 2026-06-14 | 2026-06-13 15:30 | 2026-06-15 | 2026-06-13 20:06 |  |  |  |  | 2026-04-18 | 2026-04-19 11:53 | 2026-03-13 | 2026-03-17 18:07 | Unknown | 2026-02-21 | 2026-02-22 11:31 | 1135784.4682 | 200216 | 1129107.903 | 199040 | 1130113.6106 | 199217 | 1130113.6106 | 199217 | 2026-06-13 20:10:23 +0530 | Saddam Hussain Z M | Execution: Observation Points - 29th June | 2026-05-07 18:46:47 +0530 | Yogesh B | Some Image was uploaded | 2026-04-15 15:44:30 +0530 | Abdul Shafeen | HOTO: need to clear a point before QC closure kitchen ele A loft corner filler required of 50mm | 2026-04-02 | 2026-04-01 11:06 | 2026-04-04 | 2026-04-03 13:23
18521 | Turnkey | 2026-01-01 | Kirti | Samhita Serene Mtb | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Active | Preproduction | Site Readiness 1 | 878924 | 174872 | 1104816 | 0 | 0 | 4 | 51 | 0 | 0 | 363525 | 340527.2 |  |  | 2026-02-21 | 2026-02-22 13:22 | 2026-02-28 | 2026-02-28 16:19 | 2026-03-03 | 2026-03-05 12:31 | 2026-07-11 | 2026-07-10 19:19 | 2026-08-23 |  | 2026-08-30 |  | 2026-03-05 | 2026-03-05 20:52 | 2026-03-06 | 2026-03-06 12:09 | 2026-03-06 | 2026-03-06 19:15 | 2026-03-08 | 2026-03-10 11:21 |  |  |  |  | 2026-07-02 | 2026-05-25 18:40 | 2026-08-25 |  | 2026-08-26 |  |  |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 | [6 empty] | 2026-09-23 |  | 2026-10-02 |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-05 |  |  |  | 2026-10-27 |  | 2026-10-29 |  | 2026-10-30 | [5 empty] | 2026-09-03 |  | 2026-07-31 | 2026-07-10 19:04 | Site is Non-RTMI | 2026-02-21 | 2026-02-22 12:22 | 936284 | 168531 | 0 | 0 | 0 | 0 | 870841.5599 | 150090 | 2026-05-19 17:15:44 +0530 | Rajeshwari S | 10% payment of Rs.65,000/- will be paid by 22nd May. She wanted price protection 5 months from the date of NET as she doesnt have the possession yet. Project is on hold till 30th June. | 2026-04-17 17:27:32 +0530 | Rajeshwari S | Some Image was uploaded | 2026-03-10 11:21:06 +0530 | Rajeshwari S | Welcome call done along with Designer Priyanka Client has not yet got the possession of the Apartment They dont have the permission for IM. client will call us by 14th March and confirm on IM Date and than proceed further. | 2026-07-10 | 2026-07-11 14:02 | 2026-08-24
18523 | Turnkey | 2026-01-01 | Jyotsna Desai | Asher Arize | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Hold | Preproduction | Site Readiness 1 | 1224244 | 244849 | 1627785 | 0 | 0 | 0 | 97 | 0 | 0 | 560571 | 418824 |  |  | 2026-02-22 | 2026-02-22 20:14 | 2026-03-06 | 2026-03-07 13:21 | 2026-03-13 | 2026-03-13 19:58 | 2026-04-07 | 2026-04-07 15:06 | 2026-12-06 |  | 2026-12-13 |  | 2026-03-13 | 2026-03-14 17:02 | 2026-03-14 | 2026-03-20 15:24 | 2026-03-20 | 2026-03-20 16:22 | 2026-03-25 | 2026-03-25 14:08 |  |  |  |  | 2026-06-30 | 2026-05-07 11:39 | 2026-12-08 |  | 2026-12-09 |  |  |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-18 |  | 2026-12-19 | [6 empty] | 2027-01-06 |  | 2027-01-15 |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-18 |  |  |  | 2027-02-09 |  | 2027-02-11 |  | 2027-02-12 | [5 empty] | 2026-12-17 |  | 2026-05-15 | 2026-04-07 12:12 | Site is Non-RTMI | 2026-02-22 | 2026-02-22 20:12 | 1379479 | 248306 | 0 | 0 | 0 | 0 | 1334336.3394 | 220308 | 2026-07-10 14:00:56 +0530 | Anil Jagtap | cx will receive the possession by July end 2026 | 2026-03-25 15:04:45 +0530 | Anil Jagtap | welcome call completed. Possession - December 2026(expected) | 2026-03-20 16:21:54 +0530 | Royden Henriques | _______________________________________ Possession : December'26 ( Price protection has been extended until Dec'2026 Payment Mode : B2C Self funding - Yes CX will pay 10% between 26th March - 31st March geeta.d1234@gmail.com akshadadesai1995@gmail.com C-1601, Ashar Arize, station road, Kalwa (W). 400605. Post offers the amount is 12,30,000/- as per the offer email. 90 + 15 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays/possession delay | 2026-04-08 | 2026-04-07 15:08 | 2026-12-07
18524 | Turnkey | 2026-01-01 | Mackey Agarwal | SNN serinity garden Benglore | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | DCM Due | 3191202 | 9999 | 0 | 0 | 0 | 143 | 0 | 309121 | 319120 | 1276481 | 1276480.8 |  |  | 2026-02-22 | 2026-02-22 16:01 | 2026-02-22 | 2026-03-04 11:02 | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 | [5 empty] | 2026-03-16 |  | 2026-03-24 |  | 2026-03-25 |  |  |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-04 | [6 empty] | 2026-04-22 |  | 2026-05-01 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-04 |  |  |  | 2026-05-26 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-04-02 |  | 2026-03-11 |  | Unknown | 2026-02-22 | 2026-02-22 14:12 | 0 | 0 | 0 | 0 | 0 | 0 | 2704408 | 486793 | 2026-02-22 19:03:37 +0530 | Ankita Agarwal | DCM: MINUTES OF MEETING (MOM)Project Name: RGM Residence Client Name: Mr. Mackey Agarwal Date: No. of Family Members: 3 Kid: 5-year-old Boy Possession Timeline: March / April Facing: South-West Facing Floor: 11th Floor 1. FOYERShoe unit with seating provision (capacity: 6070 pairs) outside placementDecorative feature wall at entrancePooja unit (67 ft height)Wall mural design for pooja backgroundProvision for 67 photo framesSeating arrangement for pooja setup2. LIVING ROOML-shaped lounge seatingOttomans / Armchair seating optionsMinimal TV unit for 80 TV (no storage)Sofa back wall design to be proposedBar unit provision3. KITCHEN & DININGKitchen to be partially closed using half-wall partitionRunning window on half wall with glass shuttersSliding door for kitchen entryKitchen door positioned towards South-East side68 seater dining setupTall appliance unitDishwasher placement in balconyAdequate storage planning requiredLoft storage provisionPantry unit inclusionAdditional small sink for vegetables & fruits4. UTILITYExtra sink provisionWashing machine spaceClosed utility with sliding window5. STUDY ROOMSingle bed provisionWardrobe storageFoldable / flap iron table6. COMMON VANITYDesigner vanity unitDecorative lightingFeature tile backdrop7. BEDROOM 2 (STUDY / WORK FROM HOME)Work-from-home setup (monitor + laptop space)Book display unitOttoman seating near windowYoga space with mirror (if feasible)Minimal storage8. MASTER BEDROOM (MBR)Window seating provisionBed back wall feature designUpholstered headboardDresser unitWalk-in wardrobe unitCouch seating for 34 peopleHidden drawer storage within wardrobeTV unit9. KIDS ROOMStudy table suitable for 510 year age groupBunk bed setupSpace theme conceptActivity/play area10. GUEST BEDROOM (GBR)Wardrobe unitPlatform seating space for guest useBed back wall designSide tablesDresser unit | [6 empty] | 2026-03-16 |  | 2026-03-23
18525 | Turnkey | 2026-01-01 | Manoj Kulaskar | Lodha Amara W41 | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 933307 | 9999 | 0 | 0 | 0 | 138 | 0 | 83332 | 93331 | 381044 | 365601.6 |  |  | 2026-02-22 | 2026-02-27 11:47 | 2026-03-04 | 2026-03-04 11:20 | 2026-02-28 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-08 |  | 2026-03-09 | [5 empty] | 2026-03-15 |  | 2026-03-23 |  | 2026-03-24 |  |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 | [6 empty] | 2026-04-21 |  | 2026-04-30 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-03 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-04-01 |  | 2026-03-10 |  | Unknown | 2026-02-22 | 2026-02-26 11:46 | 0 | 0 | 0 | 0 | 0 | 0 | 1065447.79 | 175928 | 2026-03-24 15:27:46 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-14 10:40:44 +0530 | Ishan Patle | Some Image was uploaded | 2026-03-11 18:21:35 +0530 | Ishan Patle | Some Image was uploaded | 2026-03-15 |  | 2026-03-22
18526 | Turnkey | 2026-01-01 | Gayathri | JP Lavender | BNG - HSR | Yes | Nayan Reddy |  | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 1578289 | 9999 | 0 | 0 | 0 | 142 | 0 | 147830 | 157829 | 653040 | 609590.8 |  |  | 2026-02-21 | 2026-02-23 12:07 | 2026-02-21 |  | 2026-02-28 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-02-28 |  | 2026-03-01 |  | 2026-03-01 |  | 2026-03-02 | [5 empty] | 2026-03-08 |  | 2026-03-16 |  | 2026-03-17 |  |  |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 | [6 empty] | 2026-04-14 |  | 2026-04-23 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-26 |  |  |  | 2026-05-18 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-03-25 |  | 2026-03-03 |  | Unknown | 2026-02-21 | 2026-02-23 12:04 | 0 | 0 | 0 | 0 | 0 | 0 | 1337533 | 240756 | 2026-03-07 10:48:29 +0530 | Chanakya Panigrahi | Â Â Â Â Â Â Â Â Â Â Â Â Â RGM Sheet 1. Budget - 10-12 2. Property Name & Possession - JP Lavender 3. Carpet Area - 1050 4. BHK - 3BHK 5. Family Size -Â Name - Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer - No 4. Living/Dining Room Inclusions - TV Unit 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Yes Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz - Granite Service Scope -Â False Ceiling - No Painting - Yes Electricity - No 8. Utility/Janitor Unit -Â 9. Timeline - July | [6 empty] | 2026-03-08 |  | 2026-03-15
18527 | Turnkey | 2026-01-01 | Sudheer Kumar | Samhita Serene Mtb | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [7 empty] | Lost | Design | 20% Payment | 1156208 | 5500 | 1228345 | 0 | 0 | 80 | 12 | 0 | 225742 | 493404 | 431562.4 |  |  | 2026-02-22 | 2026-02-22 16:12 | 2026-02-22 | 2026-02-26 19:28 | 2026-03-05 | 2026-03-05 19:25 | 2026-04-15 | 2026-04-14 12:29 | 2026-07-01 |  | 2026-07-08 |  | 2026-03-05 | 2026-03-06 17:17 | 2026-03-06 | 2026-03-06 17:17 | 2026-03-06 | 2026-03-10 15:17 | 2026-03-20 | 2026-03-20 18:52 |  |  |  |  | 2026-06-20 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-03-21 | 2026-04-14 12:25 | Site is RTMI | 2026-02-22 | 2026-02-22 16:07 | 1040970 | 187374 | 0 | 0 | 0 | 0 | 1209984.167 | 199787 | 2026-05-23 11:19:45 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-23 11:17:36 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-23 11:15:27 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-15 | 2026-04-14 12:33 | 2026-07-02
18529 | Sub Project |  | Vivek Ghadi | jp barcelona | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Shantanu Parakh |  |  | Akash Jadhav | Aditya Vikram | Murali S |  |  | Active | Production | Dispatch Due | 39978 | 39978 | 0 | 0 | 39978 | 48 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-22 | 2026-02-26 16:41 | 2026-02-23 | 2026-02-26 16:41 | 2026-02-26 | 2026-02-26 16:41 | 2026-02-27 | 2026-02-26 16:42 | 2026-02-27 | 2026-02-26 16:44 | 2026-02-27 | 2026-02-26 16:50 | 2026-02-26 | 2026-02-26 16:41 | 2026-02-27 | 2026-02-26 16:41 | 2026-02-26 | 2026-02-26 16:41 | 2026-02-27 | 2026-02-26 16:42 |  |  |  |  | 2026-02-26 | 2026-02-26 16:43 | 2026-02-27 | 2026-02-26 16:44 | 2026-02-27 | 2026-02-26 16:44 |  |  | 2026-04-15 | 2026-04-15 18:08 | 2026-04-16 | 2026-04-17 12:39 | 2026-04-19 | 2026-04-18 19:17 | 2026-04-19 | 2026-05-07 19:02 |  |  |  |  | 2026-05-08 13:50 | 2026-05-28 | 2026-05-27 19:44 | 2026-05-30 | 2026-05-28 13:53 | 2026-05-15 | 2026-05-07 19:02 | 2026-05-28 | 2026-07-06 14:03 | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-06-19 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-04-17 | 2026-04-18 16:54 | 2026-02-27 | 2026-02-26 16:42 | Unknown | 2026-02-22 | 2026-02-26 16:41 | 0 | 0 | 0 | 0 | 33880 | 6098 | 33880 | 6098 | 2026-06-08 00:01:15 +0530 | Akash Jadhav | Procurement: Waiting for the modular dispatch | 2026-04-16 16:07:16 +0530 | Swapnali Shedekar | Some Image was uploaded |  |  |  | 2026-02-27 | 2026-02-26 16:42 | 2026-02-27 | 2026-02-26 16:44
18531 | Turnkey | 2026-01-01 | Joshua Devaraj | Sri Krishna Boulevard | BNG - HRBR | Yes | Chandini Nj | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S | Raghavendra S | Vishwa Hiremath | Active | Handover | Project Closure Pending | 971760 | 971760 | 1041829 | 997807 | 971760 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-21 | 2026-03-06 13:00 | 2026-02-23 | 2026-03-11 12:06 | 2026-03-14 | 2026-03-11 16:52 | 2026-04-02 | 2026-04-01 15:50 | 2026-04-17 | 2026-04-16 17:46 | 2026-04-23 | 2026-04-23 12:20 | 2026-03-07 | 2026-03-07 18:37 | 2026-03-08 | 2026-03-10 14:43 | 2026-03-12 | 2026-03-11 18:36 | 2026-03-20 | 2026-03-20 22:55 |  |  |  |  | 2026-04-05 | 2026-04-10 11:56 | 2026-04-18 | 2026-04-19 01:50 | 2026-04-20 | 2026-04-19 01:50 |  |  | 2026-04-23 | 2026-04-25 16:25 | 2026-04-25 | 2026-04-25 17:55 | 2026-04-26 | 2026-04-26 20:49 | 2026-04-27 | 2026-04-30 23:39 |  |  |  |  | 2026-05-02 17:22 | 2026-05-10 | 2026-05-09 19:36 | 2026-05-27 | 2026-05-22 10:31 | 2026-05-22 | 2026-05-29 17:24 | 2026-05-22 | 2026-05-30 09:58 | 2026-05-30 | 2026-05-30 10:55 | 2026-06-06 | 2026-06-05 18:03 |  |  | 2026-07-09 | 2026-06-30 18:54 | 2026-07-11 | 2026-06-30 19:30 | 2026-07-12 | 2026-06-30 21:25 |  |  |  |  | 2026-04-25 | 2026-05-02 12:20 | 2026-03-21 | 2026-04-01 15:43 | Site is RTMI | 2026-02-21 | 2026-02-22 18:50 | 882906 | 158923 | 976009 | 175681 | 957169 | 172290 | 957169 | 172290 | 2026-07-07 00:47:02 +0530 | Saddam Hussain Z M | Execution: Observation Points - 16th July | 2026-04-25 16:23:18 +0530 | Chandini Nj | Some Image was uploaded | 2026-03-30 17:53:58 +0530 | Alekhya Korada | Some Image was uploaded | 2026-04-02 | 2026-04-01 15:51 | 2026-04-17 | 2026-04-16 17:50
18532 | Turnkey | 2026-01-01 | Shripal Mohanlal Jain | Lodha park | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Nilesh Patel | Rizwan Mistry | Murali S | Harshaan Tiku | Sunil Poojary | Hold | Preproduction | Site Readiness 2 | 1396648 | 847393 | 1650697 | 0 | 1396648 | 9 | 71 | 0 | 0 | 0 | 549255 |  |  | 2026-02-22 | 2026-02-22 21:49 | 2026-02-22 | 2026-02-22 21:55 | 2026-03-01 | 2026-03-01 17:07 | 2026-03-25 | 2026-03-24 14:05 | 2026-04-13 | 2026-04-12 13:42 | 2026-06-18 | 2026-06-18 21:02 | 2026-03-01 | 2026-02-28 | 2026-03-02 | 2026-03-04 18:38 | 2026-03-04 | 2026-03-05 18:27 | 2026-03-12 | 2026-03-12 16:20 |  |  |  |  | 2026-03-24 | 2026-04-11 14:37 | 2026-06-17 | 2026-06-17 12:22 | 2026-06-18 | 2026-06-17 19:50 |  |  | 2026-06-25 | 2026-06-29 20:06 | 2026-06-29 | 2026-06-29 21:48 | 2026-07-13 | 2026-06-29 22:08 | 2026-06-30 | 2026-07-02 11:43 | [5 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-12 |  | 2026-03-13 | 2026-03-13 19:53 | Site is RTMI | 2026-02-22 | 2026-02-22 19:03 | 1398895 | 251801 | 0 | 0 | 1460586.4359 | 246607 | 1460586.4359 | 246607 | 2026-07-04 16:30:11 +0530 | Reshma Melanta | Others: | 2026-07-04 15:31:14 +0530 | Reshma Melanta | Site Readiness 2: | 2026-07-03 14:17:07 +0530 | Reshma Melanta | Execution: | 2026-03-25 | 2026-03-24 14:10 | 2026-04-13 | 2026-04-12 13:42
18533 | Turnkey | 2026-01-01 | Aurnav Anand | Assetz Sun & Sanctum | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Janvi Nagdeo |  | Active | Preproduction | Site Readiness 1 | 1223706 | 244749 | 1516463 | 0 | 0 | 2 | 65 | 0 | 0 | 507872 | 471085.2 |  |  | 2026-02-22 | 2026-02-27 13:10 | 2026-02-22 | 2026-02-27 17:53 | 2026-03-02 | 2026-02-27 17:59 | 2026-04-03 | 2026-04-03 17:46 | 2026-07-30 |  | 2026-08-06 |  | 2026-02-27 | 2026-02-28 | 2026-02-28 | 2026-03-10 15:50 | 2026-03-10 | 2026-03-12 12:05 | 2026-03-20 | 2026-03-20 14:45 |  |  |  |  | 2026-06-30 | 2026-07-13 15:43 | 2026-08-01 |  | 2026-08-02 |  |  |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 | [6 empty] | 2026-08-30 |  | 2026-09-08 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-11 |  |  |  | 2026-10-03 |  | 2026-10-05 |  | 2026-10-06 | [5 empty] | 2026-08-10 |  | 2026-03-21 | 2026-04-03 16:29 | Site is Non-RTMI | 2026-02-22 | 2026-02-22 19:08 | 1285138 | 231325 | 0 | 0 | 0 | 0 | 1246525.9112 | 210462 | 2026-04-08 11:41:30 +0530 | Rajeshwari S | First design meeting is done on 22nd March Client will pay 10% May first week. We have approval for the same from Management. Project will go on hold till then. Raised the request for the same | 2026-03-31 12:29:52 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-03-22 19:28:53 +0530 | Shivani Shet | DDM1: MOMÂ Project: DEM 1Â Â Foyer UnitÂ Aquarium to be incorporatedÂ Â One open space for keeping sandalsÂ Â Closed shoe storage (no seatingÂ required)Â Â Handles to be provided (no push-to-open mechanism)Â Â Gypsum board arch at entry with integrated lightingÂ Â Same wallpaper to be continued on foyer wallÂ Â AdditionalÂ arch near the entranceÂ Â Â Living Room / TV UnitÂ No false ceiling across the houseÂ Â Suspended TV unitÂ Â Glass storage on the left with paneling to conceal wiringÂ Â Provision for Marshall speaker and PlayStationÂ Â Accent chair (no gold trims)Â Â Space allocation for swingÂ Â Highlight wall behind swing for photo framesÂ Â 3-seater green sofaÂ Â Â KitchenÂ 750 mmÂ stove (hob notÂ required)Â Â 750 mmÂ chimneyÂ Â No cylinder unitÂ requiredÂ (GAIL connection available)Â Â Provision for dishwasher and washing machineÂ Â AquaguardÂ pending discussionÂ Â Built-in microwave/oven preferredÂ Â Granite: Bonito rangeÂ Â Breakfast table provisionÂ Â Chopping thing and wicker basket in steelÂ Â Â Master Bedroom (MBR)Â Cane finish side tablesÂ Â Wardrobe shutters: combination of half drawers and half glassÂ Â Loft extension with integrated dresser and storageÂ Â Feature wall with wallpaper:Â LifenColorsÂ Kusum (CN/6001), Indian FloralÂ JharokhaÂ and Stripes (Canvas Paper)Â Â Â Parent Bedroom (PBR)Â Mirror provision inside wardrobeÂ Â Cane finish console table (to function as TV unit)Â Â Loose furniture for bay window seatingÂ Â Â Kids Bedroom (KBR)Â Study tableÂ Â Shelf near study areaÂ Â Provision for invisible (Murphy) bed, ifÂ feasibleÂ Â Â Dining AreaÂ Pooja unit (designed for sitting and performing pooja)Â Â Minimal crockery unitÂ Â Â | 2026-04-04 | 2026-04-03 17:57 | 2026-07-31
18534 | Turnkey | 2026-01-01 | Rupashri K | INDEPENDENT HOUSE | BNG - HSR | No Estimate | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-22 | 2026-02-26 17:05 | 2026-02-23 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-03-18 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-26 |  | 2026-02-27 | [5 empty] | 2026-03-05 |  | 2026-03-13 |  | 2026-03-14 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 | [6 empty] | 2026-04-11 |  | 2026-04-20 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-23 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-03-22 |  | 2026-02-28 |  | Unknown | 2026-02-22 | 2026-02-26 17:02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-05 |  | 2026-03-12
18537 | Turnkey | 2026-01-01 | Jiten Thakkar | Runwal Sanctury | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Hold | Preproduction | Site Readiness 1 | 1275022 | 256739 | 1749504 | 0 | 0 | 0 | 89 | 0 | 0 | 555078 | 463205.2 |  |  | 2026-02-22 | 2026-02-22 20:17 | 2026-03-20 | 2026-03-20 21:47 | 2026-03-23 | 2026-03-20 21:51 | 2026-04-30 | 2026-04-30 18:46 | 2026-07-05 |  | 2026-07-12 |  | 2026-03-20 | 2026-03-25 17:13 | 2026-03-21 | 2026-03-26 11:27 | 2026-03-26 | 2026-03-26 14:38 | 2026-04-05 | 2026-04-05 14:16 |  |  |  |  | 2026-04-25 | 2026-04-09 18:54 | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-07-16 |  | 2026-06-30 | 2026-04-30 18:35 | Site is Non-RTMI | 2026-02-22 | 2026-02-22 20:12 | 1485432 | 264072 | 0 | 0 | 0 | 0 | 1448922.859 | 235930 | 2026-07-14 13:59:25 +0530 | Anamika Dolai | Possession- September'26 | 2026-04-05 14:14:54 +0530 | Anamika Dolai | Done, explained about milestones, client will proceed with 2nd 10% by tom. | 2026-03-26 14:38:35 +0530 | Royden Henriques | ----------------------------------- Possession : may'26 Payment Mode : B2C Self funding - Yes CX will pay 10% on 6th April jitenkthakkar@gmail.com Flat no.1203, T2, Runwal Sanctuary, LBS Road , Mulund west , Mumbai 400080 Post offers the amount is 12,75,022/- as per the offer email. 90+15 = 105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays/possession delays | 2026-05-01 | 2026-04-30 18:48 | 2026-07-06
18538 | Turnkey | 2026-01-01 | Bhavesh purohit | Hirani 24K | MUM - GOR | Yes | Rahul Agrawal |  | Shahid Chougley | [5 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 1621100 | 9999 | 1621100 | 0 | 0 | 136 | 0 | 152111 | 162110 | 697277 | 599602.8 |  |  | 2026-02-22 | 2026-02-22 20:22 | 2026-02-22 | 2026-02-22 20:45 | 2026-03-01 | 2026-03-01 13:35 | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-01 |  | 2026-03-02 |  | 2026-03-02 |  | 2026-03-03 | [5 empty] | 2026-03-09 |  | 2026-03-17 |  | 2026-03-18 |  |  |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-27 |  | 2026-03-28 | [6 empty] | 2026-04-15 |  | 2026-04-24 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-27 |  |  |  | 2026-05-19 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-03-26 |  | 2026-03-04 |  | Unknown | 2026-02-22 | 2026-02-22 20:17 | 1373814 | 247286 | 0 | 0 | 0 | 0 | 1373814 | 247286 | 2026-02-28 11:41:41 +0530 | Avinash Jaiswal | Some Image was uploaded | [6 empty] | 2026-03-09 |  | 2026-03-16
18539 | Turnkey | 2026-01-01 | Lucy Kumari | Regency luxury | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Asif Shaikh | Aditya Vikram | Murali S | Prashant Panigrahi | Shailendra Mishra | Active | Installation | Execution | 2487034 | 2492034 | 3740638 | 0 | 2492034 | 23 | 3 | 0 | 0 | 0 | 0 |  |  | 2026-02-22 | 2026-02-27 11:46 | 2026-03-04 | 2026-03-04 11:08 | 2026-03-07 | 2026-03-04 11:25 | 2026-03-29 | 2026-03-29 16:13 | 2026-04-13 | 2026-04-16 16:53 | 2026-04-16 | 2026-04-16 17:04 | 2026-03-04 | 2026-02-28 | 2026-03-05 | 2026-03-04 12:53 | 2026-03-04 | 2026-03-04 15:46 | 2026-03-05 | 2026-03-05 11:37 |  |  |  |  | 2026-03-29 | 2026-03-30 22:55 | 2026-04-13 | 2026-04-11 19:58 | 2026-04-12 | 2026-04-11 19:59 |  |  | 2026-04-18 | 2026-04-26 11:19 | 2026-04-26 | 2026-04-26 15:33 | 2026-04-27 | 2026-04-26 16:13 | 2026-04-27 | 2026-04-30 19:31 |  |  |  |  | 2026-05-03 17:09 | 2026-05-10 | 2026-05-11 21:41 | 2026-06-05 | 2026-06-05 20:02 | 2026-06-04 | 2026-06-08 11:02 | 2026-06-23 | 2026-06-20 14:58 | 2026-05-23 | 2026-06-22 15:29 | 2026-06-21 | 2026-07-02 18:53 |  |  | 2026-08-18 |  | 2026-08-18 |  | 2026-08-18 | [5 empty] | 2026-04-26 | 2026-05-03 14:25 | 2026-03-18 | 2026-03-17 11:36 | Site is RTMI | 2026-02-22 | 2026-02-26 11:45 | 3170032 | 570605 | 0 | 0 | 2519056.7926 | 429071 | 2519056.7926 | 429071 | 2026-07-13 13:56:27 +0530 | Asif Shaikh | Execution: Modular start date - 26th June Modular end date 24th July Custom carpentry work - 15th July (Flat patti). Glass Shutter , Mirror & glass shelf - 20th July. QC - 25th July | 2026-07-12 19:36:48 +0530 | Asif Shaikh | Execution: Modular start date - 26th June Modular end date 20th July Custom carpentry work - 20th July Glass Shutter , Mirror & glass shelf - 20th July. | 2026-06-28 18:57:14 +0530 | Asif Shaikh | Execution: HVP - Wiffy Vendor Modular start date - 26th JuneModular end date 15th JulyCustom carpentry work - 10th JulyGlass Shutter , Mirror & glass shelf - 10th July. | 2026-03-30 | 2026-03-29 16:14 | 2026-04-17 | 2026-04-16 16:59
18540 | Turnkey | 2026-01-01 | Manoj Roy | kalpataru shrishti namah | MUM - GOR | No Estimate | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-22 | 2026-02-22 22:01 | 2026-02-23 |  | 2026-02-22 |  | 2026-03-01 |  | 2026-03-08 |  | 2026-03-15 |  | 2026-02-22 |  | 2026-02-23 |  | 2026-02-23 |  | 2026-02-24 | [5 empty] | 2026-03-02 |  | 2026-03-10 |  | 2026-03-11 |  |  |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-21 | [6 empty] | 2026-04-08 |  | 2026-04-17 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-20 |  |  |  | 2026-05-12 |  | 2026-05-14 |  | 2026-05-15 | [5 empty] | 2026-03-19 |  | 2026-02-25 |  | Unknown | 2026-02-22 | 2026-02-22 22:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-02 |  | 2026-03-09
18543 | Turnkey | 2026-01-01 | Ravi Kumar K | independent house | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 2867143 | 9999 | 0 | 0 | 0 | 115 | 0 | 276715 | 286714 | 1203884 | 1089830 |  |  | 2026-02-22 | 2026-02-26 17:02 | 2026-02-25 | 2026-03-22 14:43 | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-25 |  | 2026-03-26 | [5 empty] | 2026-04-01 |  | 2026-04-09 |  | 2026-04-10 |  |  |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 | [6 empty] | 2026-05-08 |  | 2026-05-31 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-09 | [5 empty] | 2026-04-18 |  | 2026-03-27 |  | Unknown | 2026-02-22 | 2026-02-25 19:30 | 0 | 0 | 0 | 0 | 0 | 0 | 2429782 | 437360 | 2026-03-22 14:38:42 +0530 | Ankita Agarwal | DCM: MOM Interior Design DiscussionClient Name: Mr. Ravi Kumar Designation: RGM Meeting Date: 25-02-2026 Possession Timeline: August Ground FloorLiving AreaTV unit to be placed opposite sofa wallTV unit to include storageSofa back wall to have trims detailingWooden partition near sofaMid-height pooja unit setupPooja unit positioned near entrance (opposite washroom)Highlight wall with rafters + texture paintConsole table to be addedKitchen (Ground Floor)Hob to be placed on hob-side wallSink to be on same wall along with washing machineUtility to be aligned with hob placementFridge to be placed near entrance cornerBedroom 1 (Kids Bedroom / GBR)6 ft hinged wardrobeLoft storageDresser areaSeating near balconyWallpaper on feature wallBedroom 2 (Attached / GBR)Wardrobe (67 ft) with loftSeating near window integrated with wardrobeDresser spaceBed back wall designFirst Floor (Living Space)Living AreaCommon washroom to be removedDouble-height TV wallTV unit in same locationSofa to be suggested (L-shape recommended)Console table at entrance with decorative mirrorTV wall with texture paint + flat strip designSofa back wall (double height) with trims & POP punningDecorative painting and lighting to be addedKitchen (First Floor)To follow layout planPooja RoomSeating pooja setup1 idolSize: 4 x 5Door to be addedGBR (Parents Bedroom)Wardrobe (56 ft) with loftDresser spaceWallpaperSecond FloorMaster Bedroom (Son's Bedroom)Walk-in wardrobe with loftStudy unitDark themeReading cornerMaster Bedroom (Parents)Two wardrobes (entrance + behind door)Dresser unitBed back wall designThird FloorBedroom (GBR)WardrobeLoftDresserNotes / Key Design DirectionOverall functional + modern design approachEmphasis on storage (lofts, wardrobes, multifunctional units)Use of texture paint, trims, and double-height elements for feature areasMix of neutral base with highlighted feature walls | [6 empty] | 2026-04-01 |  | 2026-04-08
18544 | Turnkey | 2026-01-01 | Harshad Prabhu | Mandarmala Chs | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | vinaya thakur |  | Hold | Design | DEM1 | 839277 | 112999 | 1024146 | 0 | 0 | 50 | 83 | 0 | 54856 | 337626 | 333795.2 |  |  | 2026-02-22 | 2026-02-26 11:56 | 2026-02-24 | 2026-02-26 11:57 | 2026-03-04 | 2026-03-04 11:04 | 2026-08-02 |  | 2026-08-09 |  | 2026-08-16 |  | 2026-03-04 | 2026-03-04 11:05 | 2026-03-05 | 2026-03-04 12:30 | 2026-03-04 | 2026-03-04 16:46 | 2026-03-05 | 2026-03-05 16:22 |  |  |  |  | 2026-08-03 |  | 2026-08-11 |  | 2026-08-12 |  |  |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-08-20 |  | 2026-07-30 |  | Unknown | 2026-02-22 | 2026-02-23 18:12 | 867920 | 156225 | 0 | 0 | 0 | 0 | 841990.2992 | 144042 | 2026-06-26 12:47:14 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-26 12:46:11 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-07 12:48:22 +0530 | Anil Jagtap | Some Image was uploaded | 2026-08-03 |  | 2026-08-10 |  | Under Construction | 2026-05-01
18545 | Turnkey | 2026-01-01 | Soumik Roy | spring park apartments | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Soumya KP | [5 empty] | Aman Kumar |  | Active | Design | 20% Payment | 924544 | 122648 | 1226478 | 0 | 0 | 1 | 74 | 0 | 62261 | 369818 | 369817.6 |  |  | 2026-02-23 | 2026-02-23 14:47 | 2026-02-23 | 2026-03-13 13:27 | 2026-03-17 | 2026-03-17 12:36 | 2026-07-18 | 2026-07-14 12:31 | 2026-10-12 |  | 2026-10-19 |  | 2026-03-17 | 2026-03-18 10:56 | 2026-03-18 | 2026-03-19 10:20 | 2026-03-19 | 2026-03-20 11:47 | 2026-03-26 | 2026-03-26 16:45 |  |  |  |  | 2026-07-14 |  | 2026-10-14 |  | 2026-10-15 |  |  |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-25 | [6 empty] | 2026-11-12 |  | 2026-11-21 |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-22 |  | 2026-11-24 |  |  |  | 2026-12-16 |  | 2026-12-18 |  | 2026-12-19 | [5 empty] | 2026-10-23 |  | 2026-10-01 | 2026-07-14 12:27 | Site is Non-RTMI | 2026-02-23 | 2026-02-23 14:46 | 1039388 | 187089 | 0 | 0 | 0 | 0 | 1038527.821 | 171540 | 2026-07-14 11:48:45 +0530 | Vidya Sree | Minutes of Meeting held on Date: Attendees: Discussion: ï»¿ Based on meeting, below is a list of all the requirements that were discussed during the meeting: The customer has made the payment according to the net quotation, and no design changes were made During the DEM1 Meeting. | 2026-04-18 12:46:50 +0530 | Akshay Ds | Some Image was uploaded | 2026-04-11 18:57:31 +0530 | Akshay Ds | This is to inform you that the customer has requested a pause on the project, as his father is currently undergoing treatment for cancer and he is occupied with personal commitments. As a result, the customer will not be able to proceed with the design meetings at this time. We are placing the project on hold until the end of May 2026. | 2026-07-15 | 2026-07-14 12:35 | 2026-10-13 |  | Under Construction | 2026-12-31
18549 | Turnkey | 2026-01-01 | Neelakash | SNN Serenity Garden | BNG - HSR | Yes | Swati Rathod | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 1282265 | 9999 | 0 | 0 | 0 | 140 | 0 | 118228 | 128227 | 517138 | 508673.6 |  |  | 2026-02-23 | 2026-02-25 11:19 | 2026-02-24 |  | 2026-02-25 |  | 2026-03-04 |  | 2026-03-11 |  | 2026-03-18 |  | 2026-02-25 |  | 2026-02-26 |  | 2026-02-26 |  | 2026-02-27 | [5 empty] | 2026-03-05 |  | 2026-03-13 |  | 2026-03-14 |  |  |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-24 | [6 empty] | 2026-04-11 |  | 2026-04-20 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-23 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-03-22 |  | 2026-02-28 |  | Unknown | 2026-02-23 | 2026-02-25 11:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1086665 | 195599 | 2026-03-13 16:10:08 +0530 | Nayan Reddy | DCM: Cx NameÂ - NeelakashÂ crm - Aman 28/02/26 Move in date - 1/04/26 Budget - within 10LÂ Property name - s and n serenity gardensÂ Direction - NW facingÂ fc - 10' Modular kitchenÂ tall unitÂ - oven spaceÂ 1000mm for fridge spaceÂ Gail connection is thereÂ Under sink ro unitÂ base unitÂ wall unitÂ lighter shades colorsÂ matt finiish utilityÂ sink cabinet + 1 storage cabinetÂ wall unitÂ washing +dishwasher prov Dinning areaÂ 4 seaterÂ bar unit cum crockery unitÂ Pooja unit as per vastuÂ handwash cabinet optional suggestion from designer sideÂ foyer areaÂ create partition near entrance left sideÂ onel ledgeÂ shoe rackÂ - loos furnitureÂ Living roomÂ tv unitÂ suspended drawersÂ wall ledgesÂ sleek and cleanÂ wooden and pastal shaedesÂ Fasle ceiling in Living and dinningÂ BR - 01 (mbr)Â Wardrobe + loft hing wardrobeÂ full size mirrorÂ + dressing unitÂ study unit wallmounted Queen sizeÂ wall cabinet + mirror unit in mwashroom in all washroomsÂ false ceilingÂ Bay window we want cozyÂ BR -02 (gbr) L shape wardrobeÂ full size mirror + study unitÂ Â study room - KBRÂ Bunker bedÂ 2 foldable stuyd unitÂ partition btw study | [6 empty] | 2026-03-05 |  | 2026-03-12
18550 | Turnkey | 2026-01-01 | Nishant Bhatnagar | Prestige Siesta | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Saloni Chawan |  | Active | Preproduction | DEM2 | 2031589 | 406318 | 2583456 | 0 | 0 | 90 | 17 | 0 | 0 | 880469 | 744802 |  |  | 2026-02-21 | 2026-02-26 11:36 | 2026-03-06 | 2026-03-06 20:36 | 2026-03-09 | 2026-03-07 22:20 | 2026-04-02 | 2026-03-29 11:41 | 2027-04-08 |  | 2027-04-15 |  | 2026-03-07 | 2026-03-09 19:09 | 2026-03-08 | 2026-03-10 13:15 | 2026-03-10 | 2026-03-12 10:11 | 2026-03-18 | 2026-03-18 17:32 |  |  |  |  | 2026-03-29 | 2026-03-30 19:59 | 2027-04-10 |  | 2027-04-11 |  |  |  | 2027-04-18 |  | 2027-04-19 |  | 2027-04-20 |  | 2027-04-21 | [6 empty] | 2027-05-09 |  | 2027-05-18 |  | 2027-05-17 |  | 2027-05-18 |  | 2027-05-19 |  | 2027-05-21 |  |  |  | 2027-06-12 |  | 2027-06-14 |  | 2027-06-15 | [5 empty] | 2027-04-19 |  | 2026-03-19 | 2026-03-29 11:34 | Site is RTMI | 2026-02-21 | 2026-02-24 11:34 | 2189369 | 394086 | 0 | 0 | 0 | 0 | 2189369.3699 | 359479 | 2026-06-26 13:31:28 +0530 | Harshali Bhuyar | RCA - Client is planning to not Shift to the property currently as there is a dispute between the builders in which his payment is stuck. The whole Legal situation is going on since months , hence he has decided to backout. | 2026-06-26 13:29:33 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-04-30 17:34:52 +0530 | Harshali Bhuyar | PENDING PAPER WORK WILL TAKE MORE 20 DAYS , PROJECT ON HOLD TILL 20TH MAY. CLIENT IS ALSO PLANNING TO CHANGE THE FLAT HENCE WAS ASKING IF ANYTHING CAN BE DONE ABOUT THE AMOUNT PAID TILL NOW. | 2026-04-03 | 2026-03-29 11:44 | 2027-04-09
18551 | Turnkey | 2026-01-01 | Anushka Jagtap Jagtap | Mahavir Spring | MUM - Thane | Yes | Amisha Ahuja | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Aditya Vikram | Murali S | Saloni Chawan | Prasad Bhivaji Hande | Active | Handover | Project Closure Pending | 1108829 | 1043091 | 1353948 | 0 | 1148829 | 15 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-02-21 | 2026-02-26 11:38 | 2026-03-04 | 2026-03-04 11:10 | 2026-03-04 | 2026-03-04 11:24 | 2026-03-07 | 2026-03-07 19:17 | 2026-03-23 | 2026-03-23 23:15 | 2026-03-24 | 2026-03-24 21:53 | 2026-02-28 | 2026-02-28 | 2026-03-05 | 2026-03-04 13:44 | 2026-03-04 | 2026-03-04 17:39 | 2026-03-05 | 2026-03-05 11:39 |  |  |  |  | 2026-03-12 | 2026-03-13 12:48 | 2026-03-24 | 2026-03-24 11:30 | 2026-03-25 | 2026-03-24 11:44 |  |  | 2026-03-27 | 2026-03-30 16:10 | 2026-03-31 | 2026-03-31 17:06 | 2026-04-01 | 2026-03-31 17:53 | 2026-04-09 | 2026-04-10 11:35 |  |  |  |  | 2026-04-11 14:43 | 2026-04-19 | 2026-04-21 21:31 | 2026-05-12 | 2026-05-08 20:47 | 2026-05-09 | 2026-05-12 16:50 | 2026-05-08 | 2026-05-14 20:05 | 2026-05-14 | 2026-05-18 13:52 | 2026-05-20 | 2026-05-23 19:10 |  |  | 2026-07-09 | 2026-06-30 21:34 | 2026-07-11 | 2026-06-30 21:41 | 2026-07-12 | 2026-06-30 21:43 |  |  |  |  | 2026-03-31 | 2026-04-07 11:27 | 2026-03-06 | 2026-03-07 19:12 | Site is Non-RTMI | 2026-02-21 | 2026-02-24 11:34 | 1475415.295 | 240093 | 0 | 0 | 1214458.335 | 196032 | 1214458.335 | 196032 | 2026-06-23 22:37:45 +0530 | Faraz Soudagar | Execution: Profile shutter installation ETA - 24th June Deep cleaning done TV Legs pending Wallpaper ETA pending - | 2026-06-12 11:47:51 +0530 | Sarita Jangid | Some Image was uploaded | 2026-06-01 14:40:28 +0530 | Faraz Soudagar | Execution: Modular delivery done - 26th May Installation start dare - 1st June Installatio ETA - 7th June Profile shutter ETA pending Sofa delivery ETA pending | 2026-03-08 | 2026-03-12 19:32 | 2026-03-24 | 2026-03-23 23:21
18552 | Turnkey | 2026-01-01 | Bhupender Kumar | Folium by Sumadhura | BNG - HSR | Yes | Purva Shiravle | Abhinandan K S | Kowshik |  | Sethuragavan R | Deekshith P | Jairam Joshi | Murali S | Varun Mandana | Sunil Kumar S M | Active | Production | Production | 1675647 | 1012668 | 2319886 | 0 | 1675647 | 6 | 0 | 0 | 0 | 0 | 662979 |  |  | 2026-02-24 | 2026-02-24 12:31 | 2026-02-28 | 2026-02-28 19:10 | 2026-02-28 | 2026-02-28 19:52 | 2026-04-18 | 2026-04-19 17:12 | 2026-06-05 | 2026-06-04 17:22 | 2026-06-18 | 2026-06-18 17:28 | 2026-02-28 | 2026-02-28 | 2026-03-01 | 2026-03-05 20:32 | 2026-03-05 | 2026-03-31 10:12 | 2026-04-03 | 2026-04-03 19:40 |  |  |  |  | 2026-04-19 | 2026-04-20 15:00 | 2026-06-05 | 2026-06-05 16:09 | 2026-06-06 | 2026-06-05 17:06 |  |  | 2026-06-19 | 2026-06-21 16:37 | 2026-06-21 | 2026-06-21 19:49 | 2026-06-25 | 2026-06-21 20:50 | 2026-06-22 | 2026-06-30 12:06 |  |  |  |  | 2026-07-02 15:57 | 2026-07-10 | 2026-07-09 20:37 | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-21 | 2026-07-02 15:56 | 2026-04-04 | 2026-04-10 12:23 | Site is RTMI | 2026-02-24 | 2026-02-24 11:34 | 1966005 | 353880 | 0 | 0 | 1751223.086 | 289166 | 1751223.086 | 289166 | 2026-07-07 18:14:56 +0530 | Jairam Joshi | Procurement: CX side WIP - key will be provided 6 days before dispatch FC - 18th Ele work - 20th SRD 21st July | 2026-07-03 19:05:37 +0530 | Jairam Joshi | Procurement: CX side WIP - key will be provided 2 days before dispatch FC - 16th July SRD 17th July | 2026-06-19 16:02:01 +0530 | Adarsh Nambiar | Some Image was uploaded | 2026-04-20 | 2026-04-19 17:12 | 2026-06-05 | 2026-06-04 17:23
18553 | Turnkey | 2026-01-01 | Shirish Ghoge | Rustomjee crown | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Preproduction | DEM2 | 2511605 | 502321 | 3349627 | 0 | 0 | 32 | 0 | 0 | 0 | 1043561 | 965722.8 |  |  | 2026-02-24 | 2026-02-24 14:11 | 2026-04-13 | 2026-04-13 12:52 | 2026-04-13 | 2026-04-13 15:56 | 2026-07-24 |  | 2026-08-18 |  | 2026-08-25 |  | 2026-04-13 | 2026-04-14 18:11 | 2026-04-14 | 2026-04-14 18:18 | 2026-04-14 | 2026-04-14 19:12 | 2026-04-15 | 2026-04-15 11:25 |  |  |  |  | 2026-05-06 | 2026-05-26 18:34 | 2026-08-20 |  | 2026-08-21 |  |  |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 | [6 empty] | 2026-09-18 |  | 2026-09-27 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-28 |  | 2026-09-30 |  |  |  | 2026-10-22 |  | 2026-10-24 |  | 2026-10-25 | [5 empty] | 2026-08-29 |  | 2026-07-10 | 2026-06-13 16:26 | Site is RTMI | 2026-02-24 | 2026-02-24 13:41 | 2838666 | 510960 | 0 | 0 | 0 | 0 | 2799304.726 | 467024 | 2026-07-07 18:07:30 +0530 | Manzoor Shaikh | DEM 1 meeting aligned on 24th July at 12 pm. | 2026-07-02 17:13:31 +0530 | Vishakha Vaishnav | hold till july 2026 | 2026-07-02 17:06:37 +0530 | Vishakha Vaishnav | Others: TRIED CONNECTING CX , DIDN'T ANSWERED THE CALL | 2026-07-25 |  | 2026-08-19 |  | Under Construction | 2026-06-30
18560 | Turnkey | 2026-01-01 | R. Srivatsan | TVS Emerald Jardin | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Priyanka Mathur |  |  | Sachin I Betageri | Ranjith Kumar |  | Aman Kumar |  | Lost | Preproduction | DEM2 | 1556366 | 0 | 2266855 | 0 | 0 | 71 | 0 | 0 | 0 | 941648 | 614717.6 |  |  | 2026-02-22 | 2026-02-27 10:55 | 2026-02-27 | 2026-02-27 15:59 | 2026-03-30 | 2026-03-30 17:00 | 2026-04-27 | 2026-04-27 22:29 | 2026-04-29 | 2026-04-28 12:55 | 2026-06-04 |  | 2026-03-30 | 2026-03-31 12:16 | 2026-03-31 | 2026-04-03 13:18 | 2026-04-03 | 2026-04-06 16:42 | 2026-04-11 | 2026-04-11 19:21 |  |  |  |  | 2026-04-28 | 2026-04-28 12:51 | 2026-05-30 |  | 2026-05-31 |  |  |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 | [6 empty] | 2026-06-28 |  | 2026-07-07 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-08 |  | 2026-04-12 | 2026-04-27 22:00 | Site is RTMI | 2026-02-22 | 2026-02-26 19:17 | 1925448 | 341406 | 0 | 0 | 0 | 0 | 1939907.2145 | 310632 | 2026-05-11 15:04:49 +0530 | Bency Chacko | Some Image was uploaded | 2026-04-23 18:31:22 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-04-23 18:29:58 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-04-28 | 2026-04-27 22:41 | 2026-04-29 | 2026-04-28 12:56 | RTMI
18565 | Turnkey | 2026-01-01 | Rajiv Kaushal | Purva claymount | MUM - GOR | Yes | Yash Jain |  | Safalta Karkera | [5 empty] | Ashish Jha |  | Active | Prospect | DCM Due | 1526517 | 9999 | 0 | 0 | 0 | 139 | 0 | 142653 | 152652 | 666343 | 554870.4 |  |  | 2026-02-26 | 2026-02-26 14:23 | 2026-02-26 |  | 2026-04-24 |  | 2026-05-01 |  | 2026-05-08 |  | 2026-05-15 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-25 |  | 2026-04-26 | [5 empty] | 2026-05-02 |  | 2026-05-10 |  | 2026-05-11 |  |  |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 | [6 empty] | 2026-06-08 |  | 2026-06-17 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-20 |  |  |  | 2026-07-12 |  | 2026-07-14 |  | 2026-07-15 | [5 empty] | 2026-05-19 |  | 2026-04-27 |  | Unknown | 2026-02-26 | 2026-02-26 14:19 | 0 | 0 | 0 | 0 | 0 | 0 | 1295946 | 230571 | 2026-04-15 13:52:24 +0530 | Ashish Jha | Some Image was uploaded | 2026-02-26 13:27:10 +0530 | Yash Jain | DCM: Cx Rajiv K Kaushal Possesion - march end 2026 family of 3 couple/son 11th td Purva Clermont - 2bhk rera 629sq feet Budget - 12L to 15L entry lobby mirror- Kitchen- L shape with storage units, refrigerator. 11' Height right side east -Â Living room - mandir can also go outside in 7 no room 5 Seater - Sofa ,tv 55'' existingÂ Dining table set - 4 seating Bedroom no 3 - Son's Bedroom Wardrobe , 1 existing queen size bed/new bed foldable study table.Â Master bedroom -Â Â new bed, wardrobe , side table with mirror. Vanity in both bathrooms. Colour pallete - neutral colours, matte finish , vintage look, accent colours for some walls.Â |  |  |  | 2026-05-02 |  | 2026-05-09
18567 | Turnkey | 2026-01-01 | Lima | Raj Grandeur | MUM - GOR | Yes | Shreya Sonavane |  | Shahid Chougley | [5 empty] | Umang Shah |  | Active | Prospect | DCM Due | 6443387 | 10000 | 0 | 0 | 0 | 137 | 0 | 634339 | 644339 | 2630552 | 2524157.6 |  |  | 2026-02-23 | 2026-02-28 13:53 | 2026-02-24 |  | 2026-02-27 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-02-27 |  | 2026-02-28 |  | 2026-02-28 |  | 2026-03-01 | [5 empty] | 2026-03-07 |  | 2026-03-15 |  | 2026-03-16 |  |  |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-26 | [6 empty] | 2026-04-13 |  | 2026-04-22 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-25 |  |  |  | 2026-05-17 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-03-24 |  | 2026-03-02 |  | Unknown | 2026-02-23 | 2026-02-27 12:03 | 0 | 0 | 0 | 0 | 0 | 0 | 5460498 | 982889 | 2026-02-27 17:58:18 +0530 | Shreya Sonavane | DCM: Lobby- 1. Duct space to be take inside, add base for duct. 2. flooring need to change for full house 3. servent room not required, required small seating instead. 4. dry balcony to be take inside the kitchen 5. required island kitchen 6. all balcony floor to be raisedÂ 7. alter required in living room 8. slider for kitchen 9. Fully modular kitchen 10. Common wash basin to be take inside the living roomÂ 11. safety door required 12. common bedroom will be media room/ gust room 13. duct space in bathrooms to be utilizeÂ 14. master duct to be used in bathroom space for bath or jacuzzi area. 15. basic requirments for bedroom_TV, Bed with storage, wardrobe, dresser, side table, study for kids 16. walkin wardrobe if possibleÂ Â | [6 empty] | 2026-03-07 |  | 2026-03-14
18568 | Turnkey | 2026-01-01 | Sarita Umesh Joshi | Veena synergy | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Active | Preproduction | DEM2 | 1498880 | 299776 | 1938769 | 0 | 0 | 97 | 0 | 0 | 0 | 680937 | 518166.8 |  |  | 2026-02-25 | 2026-03-04 13:33 | 2026-02-28 | 2026-03-05 12:52 | 2026-03-10 | 2026-03-10 16:04 | 2026-04-02 | 2026-03-29 14:01 | 2026-07-01 |  | 2026-08-08 |  | 2026-03-10 | 2026-03-11 12:52 | 2026-03-11 | 2026-03-13 23:33 | 2026-03-13 | 2026-03-14 14:25 | 2026-03-18 | 2026-03-18 17:47 |  |  |  |  | 2026-03-29 | 2026-04-09 19:15 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-03-19 | 2026-03-29 13:54 | Site is RTMI | 2026-02-25 | 2026-02-28 12:45 | 1643025 | 295744 | 0 | 0 | 0 | 0 | 1611772.2695 | 272117 | 2026-05-05 14:11:21 +0530 | Khyati Bandi | KITCHEN -Â 1. Rolling shutter provision if possible 2. Wicker basket - 120MM+210MM+300MM KIDS ROOM -Â 1. Mandir base storage to be in shutters 2. PinkÂ FOYER -Â Â 1. Unit to keep 50 pairs of footwear with one tall unit for guitarÂ Living area - Glitter wall paint on sofa bed wallÂ | 2026-05-05 10:48:22 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-31 11:29:17 +0530 | Manzoor Shaikh | Spoken with the customer, he needs the the changes discussed on the DEM1 meeting, post that only he will be paying the amount. | 2026-03-30 | 2026-03-29 14:02 | 2026-07-02 |  | Under Construction | 2026-04-01
18569 | Turnkey | 2026-01-01 | Sai Rajesh/ Srilekha duggi | Samhita Serene Mtb | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Kushal S |  | Active | Preproduction | DEM2 | 1181408 | 236284 | 1536107 | 0 | 0 | 62 | 0 | 0 | 0 | 484332 | 460792.4 |  |  | 2026-02-24 | 2026-02-27 15:41 | 2026-03-06 | 2026-03-06 18:48 | 2026-03-25 | 2026-03-25 17:31 | 2026-04-28 | 2026-04-28 15:23 | 2026-09-17 |  | 2026-09-24 |  | 2026-03-25 | 2026-03-31 | 2026-03-26 | 2026-04-02 11:23 | 2026-04-02 | 2026-04-02 14:48 | 2026-04-04 | 2026-04-04 18:50 |  |  |  |  | 2026-04-28 | 2026-05-14 18:50 | 2026-09-19 |  | 2026-09-20 |  |  |  | 2026-09-27 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 | [6 empty] | 2026-10-18 |  | 2026-10-27 |  | 2026-10-26 |  | 2026-10-27 |  | 2026-10-28 |  | 2026-10-30 |  |  |  | 2026-11-21 |  | 2026-11-23 |  | 2026-11-24 | [5 empty] | 2026-09-28 |  | 2026-04-05 | 2026-04-28 12:35 | Site is RTMI | 2026-02-24 | 2026-02-26 14:13 | 1301785 | 234321 | 0 | 0 | 0 | 0 | 1254836.1338 | 211867 | 2026-07-12 10:49:32 +0530 | Yogesh B |  | 2026-07-08 15:19:00 +0530 | Rajeshwari S | Client is getting possession between 15-20th. He wants to start with material selection and design finalization | 2026-04-20 13:58:24 +0530 | Keerthan M | CDP: Living: give design option for sofa wall ad TV wallDining Crockery unit with sink units need to be planned accordinglyKitchen Changes has been done asper CX requirementGBR check for storage space behind doordiscuss on the loft above sliding doorMBR Add bay window seating with study tall storage Note: vanity unit added in quote, check at site for granite provision and add in drawingsBalcony units added in quote | 2026-04-29 | 2026-04-28 15:27 | 2026-09-18 |  | Under Construction | 2026-04-16
18570 | Turnkey | 2026-01-01 | Tejas parab | Runwal Nirvana | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Moni Sahani |  | Hold | Design | 20% Payment | 2004977 | 6500 | 2566769 | 0 | 0 | 9 | 79 | 0 | 394495 | 848093 | 755888.8 |  |  | 2026-02-26 | 2026-03-05 17:46 | 2026-02-26 | 2026-03-05 17:50 | 2026-03-08 | 2026-03-05 18:02 | 2026-04-15 | 2026-04-15 16:27 | 2027-03-01 |  | 2027-03-08 |  | 2026-03-05 | 2026-03-06 13:42 | 2026-03-06 | 2026-03-06 14:43 | 2026-03-06 | 2026-03-07 12:36 | 2026-03-12 | 2026-03-12 18:49 |  |  |  |  | 2026-09-30 |  | 2027-03-03 |  | 2027-03-04 |  |  |  | 2027-03-11 |  | 2027-03-12 |  | 2027-03-13 |  | 2027-03-14 | [6 empty] | 2027-04-01 |  | 2027-04-10 |  | 2027-04-09 |  | 2027-04-10 |  | 2027-04-11 |  | 2027-04-13 |  |  |  | 2027-05-05 |  | 2027-05-07 |  | 2027-05-08 | [5 empty] | 2027-03-12 |  | 2026-04-13 | 2026-04-09 14:06 | Site is RTMI | 2026-02-26 | 2026-02-26 15:09 | 2175228 | 391541 | 0 | 0 | 0 | 0 | 2152533.9237 | 355420 | 2026-06-06 18:48:17 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-21 13:51:44 +0530 | Moni Sahani | Some Image was uploaded | 2026-04-27 18:10:08 +0530 | Manzoor Shaikh | The client arrived at the EC for the cancellation, however, informed we does not have any option for a cancellation. The customer was stating the design is delayed, however, we have aligned DEM1 meeting on 17th March due to schedule was unavailable, however, the customer asked to do an IM first post he will do the meeting. Later the IM was aligned on 26th March, however, when the executive reached the site and got to know that the customer was doing the flooring tiles (CIVIL WORK ONGOING) Later the customer was unavailable for the meeting on 05th April, hence aligned on 07th April. The customer is writing at Wecare demanding a refund, email id shared by Sahil Sethi. Tried retaining, however, the customer is not willing to continue. Informed will connect with Heena for retention purpose, however, the client is not responding. | 2026-04-16 | 2026-04-18 18:23 | 2027-03-02
18572 | Turnkey | 2026-01-01 | Akram Ali Shaikh ( Aasna Jewellers ) | others | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | [5 empty] | Umang Shah |  | Hold | Design | DEM1 | 2495237 | 339999 | 3384238 | 0 | 0 | 97 | 5 | 0 | 159048 | 1052698 | 943491.2 |  |  | 2026-02-26 | 2026-02-26 16:49 | 2026-03-31 | 2026-03-31 13:55 | 2026-03-31 | 2026-03-31 14:00 | 2026-08-07 |  | 2026-08-02 |  | 2026-08-09 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 16:21 | 2026-04-03 | 2026-04-04 16:09 | 2026-04-10 | 2026-04-10 19:20 |  |  |  |  | 2026-08-08 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-13 |  | 2026-04-11 | 2026-04-18 16:35 | Site is RTMI | 2026-02-26 | 2026-02-26 15:18 | 2867999 | 516239 | 0 | 0 | 0 | 0 | 2823184.3243 | 471773 | 2026-07-10 13:28:11 +0530 | Reshma Melanta | Others: CX has 2 PID currently the CX wants to focus on his brother PID currently his civil work is going on he will start with the DEM 1 MEETING TO KEEP THE PROJECT ON HOLD TILL 1ST AUG 2026 | 2026-05-13 15:05:21 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-04-15 17:00:27 +0530 | Umang Shah | Some Image was uploaded | 2026-08-08 |  | 2026-08-03 |  | Under Construction | 2026-05-21
18574 | Turnkey | 2026-01-01 | Leena Jogiin | Jairam elysium | MUM - Thane | Yes | Mayuri Patil |  | Safalta Karkera | [5 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 5079561 | 9999 | 0 | 0 | 0 | 139 | 0 | 497957 | 507956 | 2206958 | 1856690.4 |  |  | 2026-02-26 | 2026-02-26 18:45 | 2026-03-18 | 2026-03-18 12:00 | 2026-03-11 |  | 2026-03-18 |  | 2026-03-25 |  | 2026-04-01 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-13 | [5 empty] | 2026-03-19 |  | 2026-03-27 |  | 2026-03-28 |  |  |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 | [6 empty] | 2026-04-25 |  | 2026-05-04 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-07 |  |  |  | 2026-05-29 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-04-05 |  | 2026-03-14 |  | Unknown | 2026-02-26 | 2026-02-26 16:30 | 0 | 0 | 0 | 0 | 0 | 0 | 4304712 | 774848 | 2026-04-11 13:40:01 +0530 | Saloni Chawan | The client owns a 3 BHK residence with an overall budget of 50 lakhs. Our proposal, which included both civil work and interior execution, was also quoted at 50 lakhs. Subsequently, the client obtained a separate quotation for civil work ranging between 3035 lakhs. As a result, they decided not to finalize the project during the discussion. Their preference is to initiate the civil work first and then assess the remaining budget available for interiors. Given this approach, the client has requested additional time to evaluate their financial allocation before making a final decision. | 2026-03-18 11:58:35 +0530 | Mayuri Patil | Minutes of Meeting (MOM)Client Name: Leena Jogin Profession: Real Estate (DCM) Project Type: Residential Interior Design Meeting Date: [Add Date] Client ProfileFamily: Couple + 2 Kids + Father & Father-in-lawPreferred Theme: European ThemeLifestyle Note: Enjoys social gatheringsKids Interests: Reading & MusicProject DetailsPossession Timeline: 1015 days (Site visit available)Carpet Area: 1290 sq.ft (1560 sq.ft including dry area)Floor: 17th FloorProject Type: B2B (GST claim applicable)Vastu: Planning completedDesign RequirementsEntrance / FoyerDedicated foyer areaSit-out / shoe storage spaceSafety door with panelingMandir area provisionCommon AreasPassage design modificationGanpati placement near windowLiving Room8-seater dining (bench seating preferred)Crockery unit with arch designBase + wall-mounted crockery unitL-shaped sofaTV size: 80 inchesTV unit: Wall-mounted with loose shelvesFlooring: Italian marbleKitchenUtility entry from kitchenEnd-to-end wardrobe/storage in dry areaDouble sink to be shifted outsideSeparate vegetable sink insideFull-height tiling above countertopMoroccan tile flooringRetain kitchen doorBedroomsKids Bedroom (Ayesha & Rian)Full wardrobe with loft2 single beds with storageStudy unit with full storageNiche seating (arch design) with storage below (bay seating)Dresser unitOpen bookshelf/storageFathers BedroomQueen-size bed with storageWardrobe with loftStudy unit with storageDresser beside studySide tableMaster BedroomSouthwest locker placementQueen-size bed with storageStudy areaBay seating with storageTV unitDresser unitBathroomsCommon bathroom: WC & washbasin to be repositioned as per VastuWashroom to be partially modifiedBathtub provisionSink relocation as discussedAdditional storage in bathroomsAdditional ScopeFalse ceilingPaintingElectrical workInvisible grillsFlower bed areaBudgetApprox. 50 Lakhs (End-to-end including civil work) |  |  |  | 2026-03-19 |  | 2026-03-26
18577 | Turnkey | 2026-01-01 | Shabuddin Shaikh ( Noorani Jewellers ) | 100 Trees | MUM - GOR | Yes | Saif Shaikh | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Umang Shah |  | Active | Preproduction | DEM2 | 1165572 | 233114 | 1578537 | 0 | 0 | 55 | 0 | 0 | 0 | 482522 | 449935.6 |  |  | 2026-02-26 | 2026-03-31 14:05 | 2026-03-31 | 2026-03-31 14:12 | 2026-04-03 | 2026-04-03 11:53 | 2026-04-28 | 2026-04-28 20:23 | 2026-06-12 |  | 2026-09-06 |  | 2026-04-03 | 2026-03-31 | 2026-04-04 | 2026-04-04 11:34 | 2026-04-04 | 2026-04-04 16:08 | 2026-04-11 | 2026-04-11 14:02 |  |  |  |  | 2026-04-28 | 2026-05-21 18:32 | 2026-09-01 |  | 2026-09-02 |  |  |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 | [6 empty] | 2026-09-30 |  | 2026-10-09 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-12 |  |  |  | 2026-11-03 |  | 2026-11-05 |  | 2026-11-06 | [5 empty] | 2026-09-10 |  | 2026-04-12 | 2026-04-28 19:52 | Site is RTMI | 2026-02-26 | 2026-02-26 16:50 | 1337743 | 240793 | 0 | 0 | 0 | 0 | 1328018.3463 | 209451 | 2026-06-09 13:13:38 +0530 | Saif Shaikh | Some Image was uploaded | 2026-05-14 16:55:45 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-10 13:13:55 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-29 | 2026-04-28 20:35 | 2026-06-13 |  | RTMI
18578 | Turnkey | 2026-01-01 | Mr. Chaitanya | signature | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Foram Joshi |  | Hold | Design | DEM1 | 2128870 | 314895 | 3120366 | 0 | 0 | 18 | 92 | 0 | 110879 | 917477 | 785619.2 |  |  | 2026-02-26 | 2026-02-26 18:22 | 2026-03-09 | 2026-03-17 17:16 | 2026-03-24 | 2026-03-24 11:06 | 2026-10-19 |  | 2026-10-26 |  | 2026-11-02 |  | 2026-03-24 | 2026-03-24 17:08 | 2026-03-25 | 2026-03-26 16:15 | 2026-03-26 | 2026-03-27 13:38 | 2026-04-05 | 2026-04-05 14:06 |  |  |  |  | 2026-10-20 |  | 2026-10-28 |  | 2026-10-29 |  |  |  | 2026-11-05 |  | 2026-11-06 |  | 2026-11-07 |  | 2026-11-08 | [6 empty] | 2026-11-26 |  | 2026-12-05 |  | 2026-12-04 |  | 2026-12-05 |  | 2026-12-06 |  | 2026-12-08 |  |  |  | 2026-12-30 |  | 2027-01-01 |  | 2027-01-02 | [5 empty] | 2026-11-06 |  | 2026-10-15 |  | Unknown | 2026-02-26 | 2026-02-26 18:14 | 2644378 | 475988 | 0 | 0 | 0 | 0 | 2573631.9285 | 402081 | 2026-07-09 16:44:43 +0530 | Anil Jagtap | cx will receive the possession by January *27 | 2026-05-27 14:02:36 +0530 | Amisha Ahuja | Some Image was uploaded | 2026-05-08 14:35:59 +0530 | Anil Jagtap | The client said he will pay 10% after the design meeting, and since he expects to receive possession by mid-October, he plans to start the design meetings at the beginning of October. | 2026-10-20 |  | 2026-10-27
18579 | Turnkey | 2026-01-01 | Manisha Manmohan | Bollineni Astra | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Banka H Suthar | Saddam Hussain Z M | Murali S | Shashank Singh | Affaan Abdulla | Active | Installation | Execution | 1762618 | 1762618 | 1765946 | 0 | 1859330 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-26 | 2026-03-07 16:13 | 2026-03-08 | 2026-03-08 14:53 | 2026-03-11 | 2026-03-08 15:00 | 2026-04-19 | 2026-04-19 19:57 | 2026-05-14 | 2026-05-13 16:55 | 2026-05-22 | 2026-05-22 20:15 | 2026-03-08 | 2026-03-09 19:19 | 2026-03-09 | 2026-03-10 15:43 | 2026-03-10 | 2026-03-13 11:14 | 2026-03-18 | 2026-03-18 17:34 |  |  |  |  | 2026-04-19 | 2026-05-02 18:19 | 2026-04-27 | 2026-04-29 19:00 | 2026-04-30 | 2026-04-29 19:01 |  |  | 2026-05-25 | 2026-05-31 11:09 | 2026-05-31 | 2026-05-31 13:52 | 2026-06-01 | 2026-05-31 15:17 | 2026-06-01 | 2026-05-31 15:42 |  |  |  |  | 2026-06-01 15:34 | 2026-06-21 | 2026-06-20 22:12 | 2026-06-27 | 2026-06-25 19:06 | 2026-06-26 | 2026-06-25 18:16 | 2026-06-25 | 2026-06-27 17:03 | 2026-06-27 | 2026-06-28 18:29 | 2026-07-04 | 2026-07-03 15:40 |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-05-31 | 2026-06-01 15:33 | 2026-04-19 | 2026-04-19 19:47 | Site is RTMI | 2026-02-26 | 2026-03-06 18:07 | 1496564 | 269381 | 0 | 0 | 2017947.217 | 333202 | 2017947.1627 | 325696 | 2026-06-09 09:25:56 +0530 | Banka H Suthar | Enclosed please find the Weekly Report for the reporting period from 18/05/26 to 23/05/2026 for your kind perusal. Project status pre installation work Key Decisions : Electrical work- Bonito Floor covering - bonito scope False ceiling - NA Request you to kindly go through the report and request for providing the decisions on priority to avoid any impact on the overall project delivery | 2026-05-31 13:35:42 +0530 | Sagarika Venkatesh | Some Image was uploaded | 2026-05-28 17:56:35 +0530 | Sagarika Venkatesh | Some Image was uploaded | 2026-04-20 | 2026-04-19 20:00 | 2026-05-14 | 2026-05-22 20:14
18586 | Turnkey | 2026-01-01 | Kush Kumar and Lakshmi Narayanan | Radiance Platinum | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 2990166 | 424968 | 4117482 | 0 | 0 | 93 | 30 | 0 | 173065 | 1271794 | 1120338.8 |  |  | 2026-02-27 | 2026-02-27 13:14 | 2026-03-05 | 2026-03-05 11:46 | 2026-03-08 | 2026-03-07 11:37 | 2026-09-14 |  | 2026-09-21 |  | 2026-09-28 |  | 2026-03-07 | 2026-03-10 11:46 | 2026-03-08 | 2026-03-12 13:17 | 2026-03-12 | 2026-03-14 11:20 | 2026-03-20 | 2026-03-20 19:09 |  |  |  |  | 2026-09-15 |  | 2026-09-23 |  | 2026-09-24 |  |  |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-04 | [6 empty] | 2026-10-27 |  | 2026-11-25 |  | 2026-11-24 |  | 2026-11-25 |  | 2026-11-25 |  | 2026-11-29 |  |  |  | 2027-01-18 |  | 2027-01-19 |  | 2027-01-22 | [5 empty] | 2026-10-02 |  | 2026-09-10 |  | Unknown | 2026-02-27 | 2026-02-27 13:13 | 3489391 | 628090 | 0 | 0 | 0 | 0 | 3465865.0109 | 572273 | 2026-04-03 19:42:53 +0530 | Abhinandan K S | Some Image was uploaded | 2026-03-14 11:21:33 +0530 | Bency Chacko |  | 2026-03-14 11:08:53 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-09-15 |  | 2026-09-22
18590 | Turnkey | 2026-01-01 | Amol Vishe Vishe | godrej Nirvaan | MUM - Thane | No Estimate | Rinisha Masurkar | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-27 | 2026-02-27 15:00 | 2026-03-04 | 2026-03-04 11:22 | 2026-02-27 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-08 |  | 2026-03-09 | [5 empty] | 2026-03-15 |  | 2026-03-23 |  | 2026-03-24 |  |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 | [6 empty] | 2026-04-21 |  | 2026-04-30 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-03 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-04-01 |  | 2026-03-10 |  | Unknown | 2026-02-27 | 2026-02-27 14:59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-02-27 19:59:14 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-02-27 19:57:21 +0530 | Nishtha Valawalkar | Godrej Nirvan 2 BHK 670 sq.ft. Budget - 12 to 14L Expected Budget idea given by Designer is 15L CX wants to change flooring and tiling of washrooms CDP planned for 19th March at 10:30 AM Silver coin given 15+15 2 coins |  |  |  | 2026-03-15 |  | 2026-03-22
18591 | Turnkey | 2026-01-01 | ARUN BAHAL | SSVR Niyaraa | BNG - HRBR | Yes | Vishal Bandi | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Hold | Preproduction | Site Readiness 1 | 820136 | 164027 | 1186242 | 0 | 0 | 2 | 44 | 0 | 0 | 328055 | 328054.4 |  |  | 2026-02-27 | 2026-03-01 11:09 | 2026-02-28 | 2026-03-01 17:31 | 2026-03-22 | 2026-03-29 15:17 | 2026-05-27 | 2026-05-27 19:28 | 2026-08-01 |  | 2026-08-08 |  | 2026-03-29 | 2026-03-30 12:35 | 2026-03-30 | 2026-03-31 12:44 | 2026-03-31 | 2026-04-06 13:04 | 2026-04-10 | 2026-04-10 17:47 |  |  |  |  | 2026-06-05 | 2026-06-03 15:09 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-04-27 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-04-11 | 2026-05-27 19:16 | Site is Non-RTMI | 2026-02-27 | 2026-02-27 14:56 | 1005290 | 180952 | 0 | 0 | 0 | 0 | 971209.2785 | 156758 | 2026-06-20 10:58:53 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-10 12:32:27 +0530 | Shivani Shet | DDM1: Â 18591 - ARUN BAHAL DEM - 1 MOM Living Room / TV Unit Double beading can be proposed. No changes to the TV unit. Provide floor-to-ceiling pooja unit with internal drawers and front glass shutters. Adjacent floor-to-ceiling crockery unit to be included. Dining table to be positioned on the left side. No console table required. False ceiling to be provided in dining and living area. Kitchen Add loft in L-shape layout. Consider provision for cylinder unit. Remove tall unit and add sink unit. Provide wall-mounted microwave unit as per available space. Master Bedroom (MBR) No changes in overall layout. Provide storage for dresser unit. Add base unit with 2 drawers for dresser. Guest Bedroom (GBR) Provide dresser unit adjacent to wardrobe (minimum possible size). Loose study table with shelf to be included. Kids Bedroom (KBR) Dresser unit to be considered. Bed position to be aligned facing south direction. Space to be allocated for wardrobe and study unit. Top of Form Bottom of Form Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â | 2026-06-03 15:11:46 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-28 | 2026-05-27 19:31 | 2026-08-02 |  | Under Construction | 2026-05-01
18593 | Turnkey | 2026-01-01 | Mr Krishna | Lodha Amara | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 1617209 | 9999 | 1617209 | 0 | 0 | 78 | 0 | 151722 | 161721 | 658338 | 635429.2 |  |  | 2026-02-27 | 2026-02-28 23:13 | 2026-04-21 | 2026-04-21 16:19 | 2026-05-11 | 2026-05-11 12:47 | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-02-27 | 2026-02-27 16:22 | 1370516 | 246692 | 0 | 0 | 0 | 0 | 1370516 | 246692 | 2026-04-23 12:54:35 +0530 | Anjali Singh | DCM: colour theme - white and golden wall concepts as per reel shared on whatsapp | 2026-04-23 12:52:26 +0530 | Anjali Singh | DCM: MR. KRISHNAÂ 4 people , mother sister 2 brothersÂ master - mother and sisterÂ brothers in guest bedroomÂ mother - 56 y/o housewife sister - 35 y/oÂ wfhÂ brother 1 - 33 y/o merchant navyÂ brother 2 - 28 y/0Â business owner and content creatorÂ shoe rack outside - not in foyerÂ KITCHENÂ new slab graniteÂ slider with archÂ microwaveÂ NO otgÂ double door fridgeÂ laminate kitchen with glass shutters in over headÂ more storage - loft and over head cabinetsÂ hob - 4 burnerÂ chimney is neededÂ sink - double bowlÂ dishwasherÂ space for RO.Â LIVING ROOMÂ - existing sofa 3+2 - tv unit - 50"Â - dining table - 6 seaterÂ guest bedroomÂ Â 2 brotherÂ wardrobeÂ bed 6 by 6Â tv unit minimalÂ 1 study + leadges openÂ back wall - pop grooves and paintÂ white + golden whole themeÂ Master bedroom -Â wardrobeÂ bedÂ dresserÂ tv unitÂ washrooms - vanityÂ glass partitionÂ golden and beige themeÂ t-profiles or groovesÂ utility -Â over head cabinetsÂ deck area -Â clothes hangingÂ false ceiling - yes in living diningÂ bedrooms if pop punning - if neededÂ cove lights budget - 12-13 lakhÂ max 10 lakhÂ possession - 10 may - keys handoverÂ CDP - Friday 24th AprilÂ 12pmÂ 1 safety door - to be addedÂ shoe rack - in cx scope | 2026-02-27 16:24:53 +0530 | Aryan Singh | Some Image was uploaded | 2026-05-19 |  | 2026-05-26
18597 | Turnkey | 2026-01-01 | Vivek Gavin Dsouza | Auris Serenity Malad West | MUM - GOR | No Estimate | Priyanka Patel |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-27 | 2026-02-27 21:14 | 2026-02-27 | 2026-03-04 12:41 | 2026-03-05 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-08 |  | 2026-03-09 | [5 empty] | 2026-03-15 |  | 2026-03-23 |  | 2026-03-24 |  |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 | [6 empty] | 2026-04-21 |  | 2026-04-30 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-03 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-04-01 |  | 2026-03-10 |  | Unknown | 2026-02-27 | 2026-02-27 18:41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-15 |  | 2026-03-22
18598 | Turnkey | 2026-01-01 | Poonam Sachin Goradia | auris serenity | MUM - GOR | Yes | Rahul Agrawal |  | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 1786265 | 9999 | 1786265 | 0 | 0 | 137 | 0 | 168628 | 178627 | 771244 | 657768 |  |  | 2026-02-27 | 2026-02-28 13:44 | 2026-03-04 | 2026-03-04 12:18 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-02-27 | 2026-02-28 13:43 | 1517140 | 269124 | 0 | 0 | 0 | 0 | 1517140 | 269124 | 2026-06-23 17:29:18 +0530 | Rahul Agrawal | CDP: Cx needs some time to take decision as he is having some legal issues ongoing with the builder. | 2026-06-23 17:13:31 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-05-21 12:57:00 +0530 | Umang Shah | Some Image was uploaded | 2026-06-29 |  | 2026-07-06
18599 | Turnkey | 2026-01-01 | Pawan Bhageria | Sriram spandana | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 858681 | 9999 | 858681 | 0 | 0 | 120 | 0 | 75869 | 85868 | 355508 | 331436.4 |  |  | 2026-02-27 | 2026-02-27 19:11 | 2026-03-17 | 2026-03-17 15:00 | 2026-03-17 | 2026-03-17 16:27 | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-02-27 | 2026-02-27 19:09 | 727696 | 130985 | 0 | 0 | 0 | 0 | 727696 | 130985 | 2026-03-13 13:19:23 +0530 | Swati Rathod | Cx NameÂ - PawanÂ crm - NiroshaÂ 06/03/26 Move in date -Â Budget -8L Property name - Renovation work (Shriram Sapndhana unit no B2202) direction -E facing Â Phase 1 Â Improve foyer area - behind door we have spaceÂ 5' 1.Wall concept for foyer unit Â 2.Pooja unit -Suggestion for pooja unit inside roomÂ 3.Tv unit -Â improve the designÂ as per the existing tv unitÂ 4.Balcony looking for office room setupÂ 5.use it for study unit and add sofa cum bed Â 6.GBR (10.6 * 11.9") we have two steel wardrobe cx wants to retain one wardrobeÂ | [6 empty] | 2026-03-25 |  | 2026-04-01
18605 | Turnkey | 2026-01-01 | Swarna Pardesi | infinia grand | MUM - GOR | No Estimate | Priyanka Patel |  | Safalta Karkera | [7 empty] | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 132 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-27 | 2026-03-05 19:37 | 2026-03-05 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-15 | [5 empty] | 2026-03-21 |  | 2026-03-29 |  | 2026-03-30 |  |  |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 | [6 empty] | 2026-04-27 |  | 2026-05-06 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-09 |  |  |  | 2026-05-31 |  | 2026-06-02 |  | 2026-06-03 | [5 empty] | 2026-04-07 |  | 2026-03-16 |  | Unknown | 2026-02-27 | 2026-02-28 14:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-06 14:22:14 +0530 | Priyanka Patel | DCM: 1. Living Room Seating arrangement for 68 people. 12-seater dining table. Crockery unit / crockery table. Coffee table. Complete TV unit. TV wall to have wall panelling or marble luxury finish. No fluted or wooden design preferred. Console unit required. Some greenery / planter space. Bookshelf / display shelves. Need open and spacious layout. 2. Kitchen Modular kitchen with good European colour theme. Breakfast counter required. Tall unit storage. Microwave and oven space. Other kitchen wall to have study table. Study table storage required. After entry foyer area kitchen & utility access. 3. Dining Area Located on the right side of the living area. Dining console unit. Ample storage. 4. Mandir Area Mandir door required. Mandir to be designed with marble finish. Makrana marble suggested. Door design to look beautiful and premium. 5. Master Bedroom (Client Bedroom) King size bed. Huge bed with storage. Chest of drawers. Study table. Seating corner. Gaming console unit. Wardrobe storage. Some greenery. Bookshelf. (Same furniture concept required for husbands bedroom as well.) 6. Guest Room Murphy bed. Gym equipment space. Wardrobe. Clothing rack. 7. Sons Room More storage required. Office shoe storage. Luxury feel required. 8. Lobby Area Lobby wall to have artwork. Shelves in lobby area. 9. Washroom Only 1 washroom in the house. Separate washroom required for maid. 10. Additional Requirements Estimated property value: 30005000 per sq ft. Need tall / high furniture. Bed height more than 7 feet (headboard height). Total family members: 45 people. 1 elderly person in the house. Inside concealed doors preferred. Minimalist but luxury design language. | [6 empty] | 2026-03-21 |  | 2026-03-28
18606 | Turnkey | 2026-01-01 | Tarun Juneja | keya tke lake terraces | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | 10% Payment | 2065578 | 9999 | 0 | 0 | 0 | 130 | 0 | 196559 | 206558 | 855581 | 796881.6 |  |  | 2026-02-28 | 2026-02-28 15:09 | 2026-02-28 | 2026-03-07 11:36 | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-08 |  | 2026-03-09 | [5 empty] | 2026-03-15 |  | 2026-03-23 |  | 2026-03-24 |  |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 | [6 empty] | 2026-04-21 |  | 2026-04-30 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-03 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-04-01 |  | 2026-03-10 |  | Unknown | 2026-02-28 | 2026-02-28 15:08 | 0 | 0 | 0 | 0 | 0 | 0 | 1750489 | 315088 | 2026-03-05 11:21:24 +0530 | Swati Rathod | Based on 28-02-2026 meeting, below is a list of all the requirements that were discussed during the meeting: PID: 18606Â Property - 3BHK possession - end of march Budget - 10L- 12L Members -Â 2ppl, Kid- 2(12girl-15boyyrs) - common area false ceiling - 7th room for pooja unit with chair - consider 4 lights for all bedroom in qÂ FOYER : - shoe rack with seating (20 pair) - Bottom unit Storage(more ht) LIVING: - TV unit - sofa DINNING: - 4-5 seater(small as per space) - ledges for plants with metal fab. POOJA ROOM: - smallÂ - standing units KITCHEN:(all most closed units)(no glass shutters)(1 colour) - OTG unitÂ - bottom unit - top units - loft - spice storage of min 1' below top units(top lift)(half of top unit width) - 4 burner - no sink UTILITY: - W.M, D.W - TOP UNITS Above WM - Single blow with drainer - top unit drainer TOILETS: - vanityÂ M.BEDROOM:NO9 - king size bed - openable wardrobe (try L shaped) - TV unit - dresser BEDROOM:No6(Daughter room)(Nayra)(Aditya) - Girl Theme (unicorn) - study unit (storage tall unit) - q sizeÂ - dresser - openable wardrobe - used cloths space wardrobe BEDROOM:No7 - q size - openable wardrobe - near window pooja unit with highchair - Dresser (more storage) Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements | 2026-02-28 15:11:13 +0530 | Muralikrishna Udupi | Some Image was uploaded |  |  |  | 2026-03-15 |  | 2026-03-22
18610 | Turnkey | 2026-01-01 | Ms. SONAL AGRAWAL | Assetz Sun santrum | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2275913 | 9999 | 0 | 0 | 0 | 120 | 0 | 217592 | 227591 | 958794 | 861936 |  |  | 2026-02-28 | 2026-02-28 19:06 | 2026-03-10 | 2026-03-17 15:57 | 2026-03-17 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-02-28 | 2026-02-28 19:06 | 0 | 0 | 0 | 0 | 0 | 0 | 1928740 | 347173 | 2026-03-13 13:36:39 +0530 | Preksha Sajjanshettar | RGM FoyerÂ shoe rackÂ entry wall to be treated LivingÂ L-Shape sofaÂ TV UnitÂ Base and wall ledge to be considered if possibleÂ Wall treatment - tv wall and sofa wall DiningÂ Crockery with pooja unit bedroom wallÂ 6 seater diningÂ hand wash provision at toilet wall for diningÂ wall treatment to be doneÂ Kitchen Base-top-loft unitÂ fridge - normal double door (top-bottom) OTG UnitÂ HOB - 4 burner Cylinder UnitÂ UtilityÂ Washing machineÂ dishwasherÂ Sink TOP CabinetÂ Top mount RO Unit Granite Bonito ScopeÂ Master Bedroom (Bedroom - 2) King size bed W-I-W - Openable wardrobeÂ Dresser unit next bed bed headboard wall to be treated TV Unit with foldable study unit (option 2 - fixed study unit) Mbr toiletÂ Vanity with wall unitÂ Guest bedroom (Bedroom 1) Existing bed - 5'0"x6'6" minimal wall treatment on bed headboard dresser unit next to toilet wallÂ Wardrobe - openable Work stationÂ TOILETÂ VanityÂ Multi-purposeÂ W-I-W as storageÂ Niche - as cosy corner with book shelfÂ Foldable or sofa cum bed work stationÂ ToiletÂ VanityÂ False ceiling - living and diningÂ Budget 15 -23lakhs | [6 empty] | 2026-03-25 |  | 2026-04-01
18611 | Turnkey | 2026-01-01 | BABAJI SHIVRAM CLEARING AND CARRIES PRIVATE LIMITED | asscent regency | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Lost | Design | 20% Payment | 1300945 | 149365 | 1493654 | 0 | 0 | 56 | 55 | 0 | 110824 | 530362 | 510393.6 |  |  | 2026-02-28 | 2026-03-05 15:22 | 2026-02-28 | 2026-03-07 15:30 | 2026-03-10 | 2026-03-07 22:18 | 2026-03-30 | 2026-03-26 14:08 | 2026-06-01 |  | 2026-06-08 |  | 2026-03-07 | 2026-03-11 12:39 | 2026-03-08 | 2026-03-11 19:13 | 2026-03-11 | 2026-03-13 15:10 | 2026-03-25 | 2026-03-25 16:06 |  |  |  |  | 2026-03-26 |  | 2026-06-03 |  | 2026-06-04 |  |  |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 | [6 empty] | 2026-07-02 |  | 2026-07-11 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-14 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-12 |  | 2026-03-26 | 2026-03-25 19:26 | Site is RTMI | 2026-02-28 | 2026-02-28 17:27 | 1265808 | 227845 | 0 | 0 | 0 | 0 | 1382282 | 238527 | 2026-06-14 19:54:00 +0530 | Shraddha Badgujar | The NET for this project was completed on 7 March 2026 with an estimated project value of 14,93,654. During the first DEM meeting, the client requested multiple design modifications, resulting in a project cost increase of approximately 4 lakhs.Additionally, due to his wife's medical condition and the resulting financial constraints, the client has decided to cancel the project. The revised project cost, along with personal financial priorities, contributed to this decision. | 2026-06-10 14:14:41 +0530 | Reshma Melanta | RCA1. Project & Case DetailsProject ID (PID): 18611Client Name: Babaji Shivram Clearing and Carriers Private LimitedOriginal Quote Value: 11,94,074Revised Minimum Value: 8,00,000Current Case Status: High Escalation / Refund Demand 2. Timeline of EventsDateEvent / InteractionKey Outcomes & Client Response26th March 2026First DEM 1 Meeting Disaster/Gap: Client was highly dissatisfied. Crucial design/scope discussions held during the meeting were not updated or documented in the system/minutes. April 2026 Escalation & Refund RequestClient escalated the lack of progress/tracking and demanded a full project refund. Post-April 2026Retention & Scope NegotiationAvinash intervened and successfully negotiated a retained scope with a reduced minimum budget of 8,00,000. April May 2026On-site Civil Delays (Client-side)Project paused for 2 months while the client completed independent civil work on-site. Late May 2026Scope Discussion Meeting Internal team met with the client to finalize the 8L scope. Complication: Client backtracked on the agreement, refusing the minimum value and demanding a refund again. Current StatusRefund Refusal & Threat to EscalateClient cited a severe medical/financial emergency (wife's upcoming surgery). Despite being informed of the "No Refund" policy, the client remains highly agitated and has threatened to escalate to we.care. 3. Problem StatementThe client is demanding a total refund and threatening formal brand escalation due to a combination of early-stage service delivery gaps (undocumented DEM 1 requirements) and subsequent severe personal financial constraints arising from a medical emergency. | 2026-06-03 17:46:18 +0530 | Reshma Melanta | Some Image was uploaded | 2026-03-27 | 2026-03-26 14:13 | 2026-06-02 |  | Under Construction | 2026-05-01
18612 | Turnkey | 2026-01-01 | Prakash Thanki | BDA gunjur | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 701876 | 93559 | 935789 | 0 | 0 | 126 | 0 | 0 | 46816 | 284983 | 276518 |  |  | 2026-02-28 | 2026-02-28 17:54 | 2026-03-10 | 2026-03-10 14:33 | 2026-03-11 | 2026-03-20 11:36 | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-03-11 | 2026-03-11 18:12 | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 | [5 empty] | 2026-03-28 |  | 2026-04-05 |  | 2026-04-06 |  |  |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 | [6 empty] | 2026-05-04 |  | 2026-05-13 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-16 |  |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-04-14 |  | 2026-03-23 |  | Unknown | 2026-02-28 | 2026-02-28 17:53 | 793042 | 142747 | 0 | 0 | 0 | 0 | 773119.39 | 127659 | 2026-03-20 12:41:12 +0530 | Varun Mandana | Some Image was uploaded | 2026-03-06 13:06:04 +0530 | Swati Rathod | Cx NameÂ -Â Prakash ThankiÂ crm - amanÂ 01/03/26 Move in date -Â Budget -7-8L Property name - BDA gunjurÂ direction - e facingÂ Â Must to haveÂ Modular kitchenÂ C shape kitchenÂ dishwasherÂ merging kitchen and utilityÂ Â base unitÂ wall unitÂ loftÂ sink 900mmÂ Wall tiles - vendor quoteÂ Tall unit Â Living roomÂ Tv unit - northÂ wall 7ftÂ with storage planning to keep ups Consider standard dimensionsÂ Â Â Pooja unit - 2.8*6' Â DinningÂ areaÂ 4 seater dinning tableÂ crockery unit Â Fc in living ,dinning ,mbr, passage area Â Bedroom 2 andÂ bedroom 3 Only loft -optional 10ftÂ loft Â Â Good to have Â MBR 5ft wardrobeÂ end to end loft Â Â Good to haveÂ Wardrobe with bedÂ 2 + 2 wardrobe and end to end loft Â bedroom - 03(KBR)Â 4ft window opp to entranceÂ bay window with wardrobeÂ 3ft + 2ft and 1ft wall ledge Â GBRÂ wardrobe + mirror handwash cabinet near mbr space Â |  |  |  | 2026-03-28 |  | 2026-04-04
18613 | Turnkey | 2026-01-01 | Dilip Patil | Runwal Greens | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  |  | suraj kumar | Aditya Vikram |  | Foram Joshi | Shailendra Mishra | Active | Design | DEM3 | 2622701 | 709999 | 3493700 | 0 | 0 | 15 | 44 | 0 | 0 | 905205 | 1007497.2 |  |  | 2026-02-27 | 2026-03-01 12:14 | 2026-03-11 | 2026-03-11 11:53 | 2026-03-19 | 2026-03-19 16:10 | 2026-03-30 | 2026-03-29 16:15 | 2026-05-06 | 2026-05-05 20:17 | 2026-08-09 |  | 2026-03-19 | 2026-03-20 19:29 | 2026-03-20 | 2026-03-20 19:42 | 2026-03-20 | 2026-03-24 15:11 | 2026-03-26 | 2026-03-26 15:20 |  |  |  |  | 2026-03-27 | 2026-03-20 19:29 | 2026-07-01 | 2026-06-30 12:12 | 2026-07-01 | 2026-06-30 12:13 |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-03-27 | 2026-03-29 16:05 | Site is RTMI | 2026-02-27 | 2026-02-28 20:54 | 2960762 | 532937 | 0 | 0 | 0 | 0 | 2700086.5045 | 445835 | 2026-05-08 12:39:42 +0530 | Anamika Dolai | Some Image was uploaded | 2026-05-06 14:19:19 +0530 | Nazneen Chovvakkaran | DDM3: designs have been finalised and cx is going to start their onsite civil work in which we need to put on hold for 20 days to completer the onsite work | 2026-04-08 18:29:02 +0530 | Nazneen Chovvakkaran | DDM2: MOM 08-04-2026 1. entrance foyer need to work on the designs with fluted panels 2. dining area finalised with the beading and mirror design 3. TV wall desihn with back panel and rafters to be planned 4. mandir unit to be kept open 5. master bedroom and guest bedroom design discussed 6. daughters bedroom design to be finalised with Grisha's presence. | 2026-03-30 | 2026-03-29 16:18 | 2026-05-06 | 2026-05-06 12:29
18615 | Turnkey | 2026-01-01 | Alluri Reddy Seelam | SNN RAJ SERENITY | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Preproduction | DEM2 | 1541130 | 308226 | 2017250 | 0 | 0 | 49 | 0 | 0 | 0 | 616452 | 616452 |  |  | 2026-02-28 | 2026-02-28 21:07 | 2026-03-13 | 2026-03-13 12:05 | 2026-03-29 | 2026-03-29 11:47 | 2026-04-24 | 2026-04-23 18:27 | 2026-09-06 |  | 2026-09-13 |  | 2026-03-29 | 2026-03-30 18:10 | 2026-03-30 | 2026-03-31 13:20 | 2026-03-31 | 2026-03-31 14:38 | 2026-04-03 | 2026-04-03 19:41 |  |  |  |  | 2026-05-15 | 2026-05-27 13:09 | 2026-09-08 |  | 2026-09-09 |  |  |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 | [6 empty] | 2026-10-07 |  | 2026-10-16 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-19 |  |  |  | 2026-11-10 |  | 2026-11-12 |  | 2026-11-13 | [5 empty] | 2026-09-17 |  | 2026-04-04 | 2026-04-23 11:14 | Site is RTMI | 2026-02-28 | 2026-02-28 21:05 | 1709533 | 307716 | 0 | 0 | 0 | 0 | 1571512.1 | 259494 | 2026-07-01 15:48:07 +0530 | Janush Bojamma C T | Alluri Reddy - 1st July Dining area - Wallpaper and beading Living - rafters and beading as per ref Mirror - towards- rosegold mirror sofa wall Crockery green reference image glass shelves Membrane check Tv unit - open or glass shutter 2ft rafters 1ft marble MBR MBR bed back mirror and storage split Tv unit + study reference Drawers - sleek Wall units study - 1.5ft depth - open unit 1ft depth | 2026-05-24 10:52:57 +0530 | Janush Bojamma C T | False ceiling - Accordingly dining area check for the chandelierÂ Foyer area- Partition - False ceilingÂ Above partitionÂ As per ref - Partition foyerÂ Foyer- Spot + hanging lightsÂ Kitchen - Crockery - Glass shutters-MembraneÂ Crockery as per refÂ Kitchen - No tallÂ Kitchen - Top RO Kitchen- rice unit - open unitÂ Â Utility Storage as loft + wall units left side of doorÂ Above washing machineÂ Cylinder unitÂ Â Kitchen - Bottom - matte Glossy wall unitÂ Fluted top ceiling - loft areaÂ Crockery - Matte GlassÂ Pooja unit sitting design - 2ft widthÂ height Need referenceÂ Fluted 1.5ft widthÂ Bottom tv- 2.5ft wdithÂ On panel SS strips - 4 ,12mm False ceiling - No cove only spotlight MBR- 1ft from the bottomÂ mirror from 1ft from floor- metal with corner curves MBR -TV cum study- withÂ curve as per ref | 2026-04-23 11:12:09 +0530 | Janush Bojamma C T | The meeting was done on 18th of April The customer has mentioned the inputs on the deisgn. The initial measurement has been planned on 3rd may. Customer is yet to pay | 2026-05-15 | 2026-05-27 15:49 | 2026-09-07 |  | Under Construction | 2026-05-07
18617 | Turnkey | 2026-01-01 | akash goswami | Brigade Laguna | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Ankith Rodrigues | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Completed | Complete | Completed | 761764 | 771765 | 1129912 | 855459 | 834301 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-03-01 12:47 | 2026-03-01 | 2026-03-01 18:26 | 2026-03-18 | 2026-03-21 12:46 | 2026-04-03 | 2026-04-03 19:43 | 2026-04-05 | 2026-04-04 18:27 | 2026-04-14 | 2026-04-14 20:54 | 2026-03-18 | 2026-03-21 12:42 | 2026-03-22 | 2026-03-23 12:47 | 2026-03-02 | 2026-03-24 17:43 | 2026-04-03 | 2026-04-03 19:18 |  |  |  |  | 2026-04-03 | 2026-04-04 06:28 | 2026-04-05 | 2026-04-11 17:51 | 2026-04-12 | 2026-04-11 18:07 |  |  | 2026-04-17 | 2026-04-19 13:13 | 2026-04-19 | 2026-04-19 17:32 | 2026-04-20 | 2026-04-19 17:44 | 2026-04-20 | 2026-04-22 21:03 |  |  |  |  | 2026-04-24 12:25 | 2026-05-01 | 2026-04-30 22:26 | 2026-05-23 | 2026-05-19 14:33 | 2026-05-19 | 2026-05-25 18:32 | 2026-05-19 | 2026-05-27 14:59 | 2026-05-27 | 2026-05-28 07:41 | 2026-06-03 | 2026-06-02 13:10 |  |  | 2026-06-19 | 2026-06-20 13:45 | 2026-06-30 | 2026-06-20 13:46 | 2026-07-01 | 2026-06-20 14:01 |  |  |  |  | 2026-04-19 | 2026-04-24 12:24 | 2026-04-04 | 2026-04-03 19:34 | Site is RTMI | 2026-02-28 | 2026-02-28 19:24 | 957552 | 172359 | 936366.2692 | 161578 | 936226.0774 | 161554 | 933435.3055 | 161074 | 2026-06-21 23:32:26 +0530 | Saddam Hussain Z M | Execution: Observation Points - 6th July | 2026-06-15 11:40:10 +0530 | Saddam Hussain Z M | Some Image was uploaded | 2026-04-18 19:44:31 +0530 | Abdul Shafeen | HOTO: need to clear one point before QC closure 1) in kitchen both elevation chimney Patta to be fix on the carcass level. | 2026-04-04 | 2026-04-03 19:45 | 2026-04-05 | 2026-04-04 18:29 | RTMI
18619 | Turnkey | 2026-01-01 | Manasvi Manoj Tirlotkar | Mahavir Spring | MUM - GOR | Yes | Saakshi Bhute | Reshma Melanta | Kashmira Nerurkar |  | Priyanka Kamble | Faraz Soudagar | Aditya Vikram |  | Mrunali Mitkari | Prasad Bhivaji Hande | Active | Preproduction | 2D | 1217336 | 195762 | 1246499 | 0 | 0 | 32 | 0 | 0 | 0 | 591781 | 429792.8 |  |  | 2026-02-28 | 2026-03-04 12:23 | 2026-03-04 | 2026-03-06 12:36 | 2026-03-09 | 2026-03-06 18:39 | 2026-04-09 | 2026-04-09 16:12 | 2026-05-03 | 2026-05-02 13:37 | 2026-06-07 | 2026-06-07 12:36 | 2026-03-06 | 2026-03-10 17:30 | 2026-03-07 | 2026-03-11 11:44 | 2026-03-11 | 2026-03-12 15:14 | 2026-03-20 | 2026-03-20 18:29 |  |  |  |  | 2026-04-09 | 2026-04-11 14:26 | 2026-05-27 | 2026-05-26 19:23 | 2026-05-27 | 2026-05-27 11:21 |  |  | 2026-06-10 |  | 2026-06-14 |  | 2026-06-24 |  | 2026-06-25 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-14 |  | 2026-03-21 | 2026-03-29 12:28 | Site is RTMI | 2026-02-28 | 2026-02-28 19:46 | 1056355 | 190143 | 0 | 0 | 0 | 0 | 1244118.0818 | 214678 | 2026-07-14 15:35:57 +0530 | Reshma Melanta | Others: CX IS ASKING FOR A REFUND HAS WANTED TO MOVE IN EARLY, DID CALL HER AND ASK HER WE WILL GET ONE ROOM DONE BUT THE CX DOESNT WANT TO GO AHEAD WITH THE SAME NOR WANT TO GO WITH THE MINIMUM BUDGET 8LKH | 2026-06-06 13:47:43 +0530 | Reshma Melanta | Client Refund Request & Partial Move-in Proposal Situation: The client is requesting a refund because she needs to move into her property as early as possible due to having no other accommodation. She originally wanted to move in by the end of June. ALREADY MOVED IN THE PROPERTY. Proposed Alternative: Offered to check with execution about completing the kitchen, living room, and one bedroom first so she can stay there, and then finish the remaining bedroom later. Next Steps: Client is discussing the option with her husband and will get back to us. Current Stage: Currently in the PKO Stage, with the project docket scheduled to be shared between June 16th 20th, 2026. | 2026-06-02 13:15:28 +0530 | Reshma Melanta | CROSS MEASUREMENT FOR THE SAME IS DONE PKO DOCKET STAGE | 2026-04-10 | 2026-04-09 16:15 | 2026-05-03 | 2026-05-02 13:38
18621 | Turnkey | 2026-01-01 | Preeti Pawar | Puranik city Reserva | MUM - Thane | No Estimate | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-02-28 20:54 | 2026-07-12 |  | 2026-03-14 |  | 2026-07-22 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-07-23 |  | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-07-18 |  | Unknown | 2026-02-28 | 2026-02-28 20:52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-07-23 |  | 2026-07-30
18622 | Turnkey | 2026-01-01 | indrajeet patil | Seth Zuri | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [6 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 3600862 | 9999 | 0 | 0 | 0 | 123 | 0 | 350087 | 360086 | 1596449 | 1284240.4 |  |  | 2026-02-28 | 2026-03-02 12:24 | 2026-03-10 | 2026-03-10 18:53 | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-15 |  | 2026-03-16 | [5 empty] | 2026-03-22 |  | 2026-03-30 |  | 2026-03-31 |  |  |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 | [6 empty] | 2026-04-28 |  | 2026-05-07 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-10 |  |  |  | 2026-06-01 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-04-08 |  | 2026-03-17 |  | Unknown | 2026-02-28 | 2026-02-28 19:58 | 0 | 0 | 0 | 0 | 0 | 0 | 3051578 | 549284 | 2026-03-10 18:53:23 +0530 | Rutuja Kotwal | DCM: Mr. Indrajeet Patil.Â Â JodiÂ FlatÂ 3BHK + 2 BHK.Â Â 6Â BHK.Â Â Move in Â Husband ,Â Wife, 2 sons 13yrs. And 8 yrs. And Mother 72 yrs.Â Â Direction -Â Â Design as per basicÂ Vastu.Â Â Profession CA. Salaried.Â Â Clinical Research. Salaried.Â Â Sq.ft.Â - 1437Â sq.ft.Â Â Budget 25 lakhs- 30 lakhs.Â Â Shoe rack outside the door.Â Â Living roomÂ Demolishing center wall,Â Â Unit 1 3 BHK. - Master bedroom will beÂ kidsÂ bedroom,Â Â Demolition ofÂ centerÂ wall to combine 2 bedrooms for Master Bedroom.Â Â Closing ofÂ one door for the entrance.Â Â Demolition of kitchen wall andÂ creatindÂ an island kitchen.Â Â Common Bathroom will beÂ store room.Â Â DisconnectingÂ all plumbing points.Â Â MBR- BedÂ (existing ), wardrobe with Lofts, study unit with above storage and sofa seating with coffee table.Â Kids bedroomÂ Bed, Wardrobe with Lofts, Study unit with above storage and seating chair to enjoy the view.Â Â UNIT 2 2 BHK.Â Â Kitchen will beÂ multi purposeÂ room-Â entrance to be shifted towards left.Â Mandir on the adjacent wall ofÂ entrance.Â Â Common bedroom will be Guest Bedroom-Â Sofa cum bed, Existing Godrej wardrobe, one tale to keep bags,Â Work spaceÂ with Minimum storage.Â Storage in the passage.Â Â MBR will be Parents Bedroom-Â Wardrobe w/o lofts, Bed cum bedÂ or Queen Size bed,Â TV needed.Â FC, painting, electricalsÂ BudgetÂ suggestedÂ -Â 40- 45 lakhs.Â Â CDPÂ 8thÂ march. 11 am.Â Â | [6 empty] | 2026-03-22 |  | 2026-03-29
18623 | Turnkey | 2026-01-01 | Kuranjay Janardan Dhasade kurnjaya dhasade | ananta residency | MUM - GOR | Yes | Mandar Ambre | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Mrunali Mitkari |  | Hold | Design | 20% Payment | 1224963 | 148728 | 1487280 | 0 | 0 | 12 | 41 | 0 | 96265 | 537633 | 442337.6 |  |  | 2026-02-28 | 2026-03-04 12:25 | 2026-03-25 | 2026-03-25 15:51 | 2026-03-28 | 2026-03-28 12:40 | 2026-05-23 | 2026-05-23 20:41 | 2026-10-24 |  | 2026-10-31 |  | 2026-03-28 | 2026-03-31 00:37 | 2026-03-29 | 2026-03-31 12:32 | 2026-03-31 | 2026-03-31 17:54 | 2026-04-10 | 2026-04-10 17:09 |  |  |  |  | 2026-05-23 |  | 2026-10-26 |  | 2026-10-27 |  |  |  | 2026-11-03 |  | 2026-11-04 |  | 2026-11-05 |  | 2026-11-06 | [6 empty] | 2026-11-24 |  | 2026-12-03 |  | 2026-12-02 |  | 2026-12-03 |  | 2026-12-04 |  | 2026-12-06 |  |  |  | 2026-12-28 |  | 2026-12-30 |  | 2026-12-31 | [5 empty] | 2026-11-04 |  | 2026-04-11 | 2026-05-23 20:34 | Site is RTMI | 2026-02-28 | 2026-03-04 12:25 | 1260407 | 226873 | 0 | 0 | 0 | 0 | 1252655.3881 | 211265 | 2026-06-17 14:24:47 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-26 18:49:41 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-24 10:47:51 +0530 | Mandar Ambre | DDM1: Hi MOM DEM1 23/06/26Â Living RoomÂ 1. breaking of the shaft wall is in cx scope 2. Mandir unit is in Cx scope 3. Living room used Minar idea and right hand side of Living room.Â 4.Living tv unit to redesign as per referenceÂ images shared in groupÂ Kitchen.Â 1. To make changes as per the site condition like shift on drawer in center and shutter unit. 2. Wall unit to make in glass shutter unitÂ 3. Loft unit inventor will be kept , need to know capacityÂ and size of batteryÂ Master bedroomÂ 1. To add unit behind the mirror for storageÂ 2. To remove the book storage unitÂ 3. To add foldable study tableÂ Kids Bedroom 1. The bed position is changesÂ 2. WardrobeÂ is shifted front to front 3. Study unit to make, wall unit and loft unitÂ 4. Mirror unit, to shifted on wall The Following were observation during the meeting the False ceiling qty is less, informed cx it is a only peripheral False is considerthe out door pvc is not in our scope , informed the cx electrical work will change as per the site conditioncx has budget constraint , which increased risk factor Cab service confusion , that can will be provide for every meeting | 2026-05-24 | 2026-05-23 20:49 | 2026-10-25 |  | Under Construction | 2026-06-30
18625 | Turnkey | 2026-01-01 | Swaditya Karunakaran | Assetz Marq | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 2122832 | 9999 | 0 | 0 | 0 | 137 | 0 | 202284 | 212283 | 886830 | 811436 |  |  | 2026-02-28 | 2026-02-28 21:05 | 2026-03-01 | 2026-03-27 11:38 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-02-28 | 2026-02-28 21:04 | 0 | 0 | 0 | 0 | 0 | 0 | 1799010 | 323821 | 2026-03-01 16:18:56 +0530 | Saranya Thiyagarajan | DCM: Orientation: North-Facing Floor Level: 21st Floor 1. Design Style and Overall ConceptThe residence will follow a minimalistic Scandinavian and Japandi design approach.The color palette will primarily consist of warm beige tones with light wood finishes.The overall aesthetic will be subtle, non-flashy, and fully maintained, focusing on minimal yet functional interiors.2. FoyerProvision for a tall storage unit for shoes and accessories.Seating bench for convenience.Full-height mirror to enhance functionality and spatial perception.3. Living AreaMinimal TV wall design with floating wall drawers only.Avoidance of bulky storage units to maintain a clean and uncluttered appearance.4. Dining AreaLower crockery storage unit.Raised counter unit with bar stools for casual dining.Upper countertop designated for placing a coffee machine.A small wash basin to be incorporated in the corner of the dining area.5. Pooja UnitPooja area to be designed as a sleek cupboard-style unit.Accommodation for 45 small idols.Design to remain minimal and discreet, not resembling a traditional pooja unit.6. KitchenMonotone beige and wood palette for the kitchen.Appliances to include:Built-in ovenDishwasherWashing machine (under-counter placement)Storage provisions to include:Janitor unitTall storage unitRice storage unitWicker basket storageSingle-door refrigerator to be provided.No gas cylinder storage required.7. Master BedroomBed placement on the east wall.Opposite wall to include TV with a small ledge unit for essential items.Workstation to be incorporated.Mirror options:Tall mirror with ledge, orL-shaped mirror with closed storage on one side.Hinged wardrobe with loft storage.8. Master BathroomGlass shower partition.Vanity unit with storage.9. Guest Bedroom (Bedroom 3)Murphy bed to optimize space.Wardrobe unit.Height-adjustable study table.Overhead storage units.Sleek mirror with drawer storage.No TV near the window.10. Guest BathroomShower partition.Vanity storage unit.11. Kids Bedroom (Bedroom 2)Subtle car-themed design.Car display unit opposite the bed.Sliding wardrobe.Study table.Bay window seating near the window.No television unit.Long mirror to be positioned near the bathroom wall.12. Kids BathroomShower partition.Vanity unit with storage.13. Passage AreaPassage wall near the guest bedroom to feature a picture gallery wall.14. BalconyBalcony to be fully covered.Foldable table to be provided.Storage unit for clothes and utility items.15. Ceiling DesignMinimal false ceiling with pelmet detailing to maintain a clean and subtle ceiling profile.16. BudgetEstimated Interior Budget: 1517 Lakhs. | [6 empty] | 2026-04-05 |  | 2026-04-12
18626 | Turnkey | 2026-01-01 | Amit Ganwani | 72 West | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Active | Preproduction | DEM2 | 2305109 | 461022 | 2843713 | 0 | 0 | 24 | 20 | 0 | 0 | 991156 | 852931.2 |  |  | 2026-02-28 | 2026-03-05 15:16 | 2026-03-04 | 2026-03-06 16:08 | 2026-03-14 | 2026-03-14 21:14 | 2026-05-12 | 2026-05-12 20:53 | 2026-06-16 |  | 2026-06-23 |  | 2026-03-14 | 2026-03-16 18:55 | 2026-03-15 | 2026-03-18 19:39 | 2026-03-18 | 2026-03-20 15:25 | 2026-03-31 | 2026-03-31 16:05 |  |  |  |  | 2026-05-12 | 2026-06-21 12:22 | 2026-06-18 |  | 2026-06-19 |  |  |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-29 | [6 empty] | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-06-27 |  | 2026-04-01 | 2026-05-12 19:24 | Site is RTMI | 2026-02-28 | 2026-03-04 11:46 | 2409926 | 433786 | 0 | 0 | 0 | 0 | 2391341.6745 | 412643 | 2026-06-16 16:46:31 +0530 | Vishakha Vaishnav | tried connecting cx , didn't answered | 2026-05-27 12:01:18 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-09 12:11:15 +0530 | Reshma Melanta | DEM - 1 MEETING TODAY 9th May 2026 | 2026-05-13 | 2026-05-12 20:55 | 2026-06-17 |  | RTMI
18627 | Turnkey | 2026-01-01 | dhairya Gala | partap harmony | MUM - GOR | Yes | Rahul Agrawal |  | Shahid Chougley | [5 empty] | Nivesh Gupta |  | Active | Prospect | DCM Due | 1044671 | 9999 | 1044671 | 0 | 0 | 137 | 0 | 94468 | 104467 | 453725 | 382012 |  |  | 2026-02-28 | 2026-02-28 21:15 | 2026-03-05 | 2026-03-13 10:40 | 2026-03-13 | 2026-03-23 12:55 | 2026-03-30 |  | 2026-04-06 |  | 2026-04-13 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-25 | [5 empty] | 2026-03-31 |  | 2026-04-08 |  | 2026-04-09 |  |  |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 | [6 empty] | 2026-05-07 |  | 2026-05-16 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-19 |  |  |  | 2026-06-10 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-04-17 |  | 2026-03-26 |  | Unknown | 2026-02-28 | 2026-02-28 21:14 | 885315 | 159356 | 0 | 0 | 0 | 0 | 885315 | 159356 | 2026-03-08 13:59:14 +0530 | Rahul Agrawal | DCM: Dhairya Gala Dcm 7th March A couple fiance both working office Living RoomTV unit3 + 2 sofaDining 4 seater KitchenL-shape platformSouth wall to West wallFridge on west wallBase + wall + loft cabinets Master BedroomBed 7 ft 5/6 ft (Client will get it customised)WardrobeDressing Notes ElectricalPaint / false ceilings (not much requirement of this) painting not on all walls BUDGET 8-9LAKHS | [6 empty] | 2026-03-31 |  | 2026-04-07
18628 | Turnkey | 2026-01-01 | Rajesh Kumar Shukla | Arihant Aspire | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-02-28 22:34 | 2026-03-01 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-15 |  | 2026-03-16 | [5 empty] | 2026-03-22 |  | 2026-03-30 |  | 2026-03-31 |  |  |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 | [6 empty] | 2026-04-28 |  | 2026-05-07 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-10 |  |  |  | 2026-06-01 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-04-08 |  | 2026-03-17 |  | Unknown | 2026-02-28 | 2026-02-28 21:33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-02-28 22:42:37 +0530 | Aryan Singh | Investment Under 10L For Rent Purpose | [6 empty] | 2026-03-22 |  | 2026-03-29
18634 | Turnkey | 2026-01-01 | Raktim Uttamkumar Saha | Mahavir Spring | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Faraz Soudagar | Akshat Shrivastava | Murali S | Aryan Singh | Shailendra Mishra | Active | Installation | Execution | 1328179 | 1330179 | 1632989 | 0 | 1328179 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-02-28 23:23 | 2026-03-04 | 2026-03-04 14:41 | 2026-03-04 | 2026-03-05 17:37 | 2026-03-31 | 2026-03-31 10:50 | 2026-04-04 | 2026-04-03 15:21 | 2026-04-23 | 2026-04-23 13:32 | 2026-03-05 | 2026-02-28 | 2026-03-06 | 2026-03-06 17:30 | 2026-03-06 | 2026-03-09 15:10 | 2026-03-15 | 2026-03-15 16:55 |  |  |  |  | 2026-04-07 | 2026-03-31 12:33 | 2026-04-12 | 2026-04-13 18:12 | 2026-04-14 | 2026-04-13 18:12 |  |  | 2026-04-24 | 2026-04-29 11:21 | 2026-04-29 | 2026-04-29 18:55 | 2026-05-02 | 2026-05-03 16:14 | 2026-05-11 | 2026-05-09 12:55 |  |  |  |  | 2026-05-09 14:32 | 2026-05-21 | 2026-05-28 18:19 | 2026-06-01 | 2026-05-30 18:52 | 2026-05-31 | 2026-06-04 16:22 | 2026-05-30 | 2026-06-16 11:53 | 2026-06-15 | 2026-06-16 16:12 | 2026-06-18 | 2026-07-03 13:32 |  |  | 2026-07-22 |  | 2026-07-24 |  | 2026-07-25 | [5 empty] | 2026-04-29 | 2026-05-09 11:13 | 2026-03-16 | 2026-03-27 11:29 | Site is RTMI | 2026-02-28 | 2026-02-28 22:26 | 1383889 | 249100 | 0 | 0 | 1481106.3056 | 244552 | 1481106.3056 | 244552 | 2026-07-12 14:30:53 +0530 | Faraz Soudagar | Execution: Modular installation done as per available material Beading installation ETA - 14th July POP punning ETa - 13th July Final coat of paint ETA - 17th July Deep cleaning - 18th July Qc - 20th July | 2026-07-01 23:11:05 +0530 | Faraz Soudagar | Execution: Modular is in progress. Delayed due to team issue | 2026-06-23 22:38:40 +0530 | Faraz Soudagar | Execution: Modular delivery done - 16th June Installation start date - 20th June | 2026-04-01 | 2026-03-31 16:01 | 2026-04-04 | 2026-04-03 15:23
18636 | Turnkey | 2026-01-01 | Shambhavi kamat | DOSTI WEST COUNTY | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Tanveer Patel | Akshat Shrivastava | Murali S | Aryan Singh | Shailendra Mishra | Active | Installation | Execution | 1231179 | 1231179 | 1362138 | 0 | 1231179 | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-02-28 22:30 | 2026-03-15 | 2026-03-15 20:05 | 2026-03-18 | 2026-03-15 21:17 | 2026-04-08 | 2026-04-22 15:51 | 2026-05-07 | 2026-05-06 14:48 | 2026-05-26 | 2026-05-26 10:57 | 2026-03-15 | 2026-03-17 18:11 | 2026-03-16 | 2026-03-19 13:57 | 2026-03-19 | 2026-03-20 11:51 | 2026-03-26 | 2026-03-26 15:24 |  |  |  |  | 2026-03-23 | 2026-03-17 18:11 | 2026-05-09 | 2026-05-23 20:56 | 2026-05-24 | 2026-05-24 12:24 |  |  | 2026-05-27 | 2026-05-28 10:52 | 2026-05-28 | 2026-05-28 12:52 | 2026-05-29 | 2026-05-28 15:15 | 2026-05-29 | 2026-05-28 21:25 |  |  |  |  | 2026-05-30 11:03 | 2026-06-06 | 2026-06-05 21:30 | 2026-06-18 | 2026-06-18 19:14 | 2026-06-17 | 2026-06-25 18:17 | 2026-06-18 | 2026-07-04 11:46 | 2026-07-07 | 2026-07-08 12:33 | 2026-07-09 |  |  |  | 2026-07-08 |  | 2026-07-10 |  | 2026-07-30 | [5 empty] | 2026-05-28 | 2026-05-30 11:02 | 2026-04-20 | 2026-04-07 13:01 | Site is RTMI | 2026-02-28 | 2026-02-28 22:26 | 1154354 | 207783 | 0 | 0 | 1240259.5895 | 214021 | 1240259.5895 | 214021 | 2026-07-13 14:33:35 +0530 | Tanveer Patel | Execution: 80% modular work completed Libra not received | 2026-07-13 14:32:55 +0530 | Tanveer Patel | Execution: Libra | 2026-06-22 23:51:53 +0530 | Tanveer Patel | Procurement: Furniture is ready for dispatchFloor Covering not required as per cx | 2026-04-25 | 2026-04-22 15:54 | 2026-05-07 | 2026-05-06 18:12
18638 | Turnkey | 2026-01-01 | Rahul Lanka | * | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Saloni Chawan |  | Active | Prospect | 10% Payment | 1342486 | 9999 | 0 | 0 | 0 | 130 | 0 | 124250 | 134249 | 621066 | 452923.2 |  |  | 2026-02-28 | 2026-03-02 19:55 | 2026-03-05 | 2026-03-05 16:45 | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-08 |  | 2026-03-09 | [5 empty] | 2026-03-15 |  | 2026-03-23 |  | 2026-03-24 |  |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 | [6 empty] | 2026-04-21 |  | 2026-04-30 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-03 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-04-01 |  | 2026-03-10 |  | Unknown | 2026-02-28 | 2026-03-02 19:52 | 0 | 0 | 0 | 0 | 0 | 0 | 1137700 | 204786 | 2026-03-05 16:38:16 +0530 | Moksh Mehta | DCM: Client Name: - Rahul Lalka Property: - Runwal Sanctury Possession Date: - T5 3002 Sq Ft: - 981+ 40 sqft No of Members: - Rental Purpose Budget:- 8-9L Living Room: - TV Unit 50" inch. Kitchen: - Semi Modular KitchenBase - 2 no's , Wall - 2nos Bedroom's Wardrobes in 2 BedroomsCurtain rod's as a possibility Bathroom's Base Vanity Unit's for allGrill Fabrication work Misc:- False Ceiling (Optional)PaintingElectrification | [6 empty] | 2026-03-15 |  | 2026-03-22
18639 | Turnkey | 2026-01-01 | Prasanna Deshmukh PrasannaDeshmukh | 24 East Sanpada Navi Mumbai | MUM - Thane | Yes | Maasoumeh Raza | [7 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 2058152 | 9999 | 0 | 0 | 0 | 135 | 0 | 195816 | 205815 | 906456 | 740065.2 |  |  | 2026-02-28 | 2026-03-02 19:56 | 2026-03-05 | 2026-03-06 14:06 | 2026-03-14 |  | 2026-03-16 |  | 2026-03-23 |  | 2026-03-30 |  | 2026-03-09 |  | 2026-03-10 |  | 2026-03-10 |  | 2026-03-11 | [5 empty] | 2026-03-17 |  | 2026-03-25 |  | 2026-03-26 |  |  |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-05 | [6 empty] | 2026-04-23 |  | 2026-05-02 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-05 |  |  |  | 2026-05-27 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-04-03 |  | 2026-03-12 |  | Unknown | 2026-02-28 | 2026-03-02 19:55 | 0 | 0 | 0 | 0 | 0 | 0 | 1744197 | 313955 | 2026-03-06 14:07:35 +0530 | Maasoumeh Raza | DCM: | 2026-03-05 18:08:41 +0530 | Maasoumeh Raza | Name:Â 18639 - Prasanna Deshmukh PrasannaDeshmukhÂ Â Property Name: Malhar 24 East Property type: 2BHK Possession: March Move in: JulyÂ Member: 2 Member Budget: 12L TO 15L Theme : Scandinavian interior Requirements: Living room: Shoe Rack with seating [20 pairs] Safety door with panelling, main entrance to be refurbishÂ Tv Unit with back panel [55 inch] 3 seater sofaÂ 4 Seater dining [circular] Mirror panelling in dining area wall Coffee tableÂ Kitchen : Base unit Wall unit Loft unit Wicker basket Appliance unit Service platform with storageÂ Â Guest bedroom :Â Queen size bed Wardrobe with loft side table TV Unit with study table Master bedroom:Â Queen size bed Wardrobe with loft Dressing Unit side table TV unit Bathroom: 2 Below vanity unit Additional scope: Full home False ceiling Painting Electrical |  |  |  | 2026-03-17 |  | 2026-03-24
18640 | Turnkey | 2026-01-01 | Sagar patil | DOSTI WEST COUNTY | MUM - Thane | Yes | Hemant Sonar | Anamika Dolai | Anil Kuwar | [5 empty] | Nishtha Valawalkar |  | Hold | Preproduction | DEM2 | 905250 | 215998 | 1030000 | 0 | 0 | 0 | 119 | 0 | 0 | 343139 | 346112.8 |  |  | 2026-02-28 | 2026-02-28 23:28 | 2026-03-02 | 2026-03-02 12:34 | 2026-03-07 | 2026-03-07 21:17 | 2026-03-23 | 2026-03-19 14:17 | 2027-04-01 |  | 2027-04-08 |  | 2026-03-07 | 2026-03-09 19:02 | 2026-03-08 | 2026-03-09 20:46 | 2026-03-09 | 2026-03-12 11:21 | 2026-03-18 | 2026-03-18 18:28 |  |  |  |  | 2026-03-15 | 2026-03-09 19:02 | 2027-04-03 |  | 2027-04-04 |  |  |  | 2027-04-11 |  | 2027-04-12 |  | 2027-04-13 |  | 2027-04-14 | [6 empty] | 2027-05-02 |  | 2027-05-11 |  | 2027-05-10 |  | 2027-05-11 |  | 2027-05-12 |  | 2027-05-14 |  |  |  | 2027-06-05 |  | 2027-06-07 |  | 2027-06-08 | [5 empty] | 2027-04-12 |  | 2027-04-10 | 2026-03-19 14:13 | Site is RTMI | 2026-02-28 | 2026-02-28 23:27 | 872882 | 157118 | 0 | 0 | 0 | 0 | 852419.297 | 138089 | 2026-07-14 14:02:15 +0530 | Anamika Dolai | possession- February'27 | 2026-03-19 14:18:17 +0530 | Hemant Sonar | DDM1: Initial measurement has not been done, as possession is scheduled in December. Design meetings will be planned after possession. | 2026-03-12 11:21:28 +0530 | Royden Henriques |  | 2026-03-20 | 2026-03-19 14:17 | 2027-04-02
18642 | Turnkey | 2026-01-01 | Sanket Deshpande | Godrej exquisite | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Nishtha Valawalkar | Prasad Bhivaji Hande | Hold | Design | DEM1 | 902702 | 118999 | 1191196 | 0 | 0 | 35 | 92 | 0 | 61541 | 368046 | 354116 |  |  | 2026-02-28 | 2026-03-02 18:27 | 2026-03-05 | 2026-03-07 21:16 | 2026-03-10 | 2026-03-07 22:22 | 2026-08-05 |  | 2026-08-12 |  | 2026-08-19 |  | 2026-03-07 | 2026-03-09 19:12 | 2026-03-08 | 2026-03-09 20:45 | 2026-03-09 | 2026-03-10 18:06 | 2026-03-18 | 2026-03-18 18:36 |  |  |  |  | 2026-08-06 |  | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-08-01 |  | Unknown | 2026-02-28 | 2026-03-02 11:55 | 1009488 | 181707 | 0 | 0 | 0 | 0 | 972976.6812 | 162107 | 2026-07-14 14:04:06 +0530 | Anamika Dolai | Possession- October'26 | 2026-04-28 13:12:54 +0530 | Anamika Dolai | Done, milestones explained, june end will receive possession. | 2026-04-08 18:36:01 +0530 | Nazneen Chovvakkaran | Some Image was uploaded | 2026-08-06 |  | 2026-08-13 |  | Under Construction | 2026-06-01
18644 | Turnkey | 2026-01-01 | Michelle Dsouza | Centrico | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Ashish Jha |  | Active | Preproduction | DEM2 | 1753227 | 350645 | 2294457 | 0 | 0 | 26 | 0 | 0 | 0 | 722587 | 679995.2 |  |  | 2026-03-01 | 2026-03-01 13:21 | 2026-03-01 | 2026-03-01 18:21 | 2026-03-15 | 2026-03-25 13:01 | 2026-06-14 | 2026-06-14 19:59 | 2026-08-12 |  | 2026-08-19 |  | 2026-03-25 | 2026-03-31 20:40 | 2026-03-26 | 2026-04-01 15:09 | 2026-04-01 | 2026-04-02 13:30 | 2026-04-04 | 2026-04-04 18:39 |  |  |  |  | 2026-06-14 | 2026-06-19 18:54 | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-04-05 | 2026-06-14 19:52 | Site is RTMI | 2026-03-01 | 2026-03-01 13:08 | 1944455 | 350002 | 0 | 0 | 0 | 0 | 1919918.841 | 317017 | 2026-06-14 19:13:51 +0530 | Riddhi Deshpande | DDM1: cx will pay in 2-3 days | 2026-06-14 15:45:27 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-28 19:30:52 +0530 | Riddhi Deshpande | DDM1: client not available doe a design discussion until june 1st week | 2026-06-15 | 2026-06-14 20:02 | 2026-08-13 |  | Under Construction | 2026-08-31
18645 | Turnkey | 2026-01-01 | Sixguards safety solutions Private Limited | independent house | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S | Mohammed Rasick | Vishwa Hiremath | Active | Production | Dispatch Due | 1593616 | 1593616 | 1677787 | 1444906 | 1593616 | 1 | 7 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-03-01 13:10 | 2026-04-02 | 2026-04-02 12:43 | 2026-04-05 | 2026-04-02 14:36 | 2026-04-27 | 2026-04-27 19:49 | 2026-05-11 | 2026-05-10 19:06 | 2026-06-07 | 2026-06-07 11:54 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-07 18:23 | 2026-04-07 | 2026-04-10 22:00 | 2026-04-15 | 2026-04-15 11:10 |  |  |  |  | 2026-04-27 | 2026-05-10 18:57 | 2026-06-01 | 2026-05-28 00:02 | 2026-05-29 | 2026-05-29 01:41 |  |  | 2026-06-10 | 2026-06-18 14:13 | 2026-06-18 | 2026-06-18 16:35 | 2026-06-18 | 2026-06-18 19:51 | 2026-06-19 | 2026-06-22 17:55 |  |  |  |  | 2026-06-23 20:00 | 2026-07-01 | 2026-06-30 19:57 | 2026-07-09 | 2026-07-07 17:47 | 2026-07-08 | 2026-07-14 18:24 | 2026-07-07 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-18 | 2026-06-23 19:59 | 2026-04-16 | 2026-04-27 19:39 | Site is RTMI | 2026-02-28 | 2026-03-01 12:42 | 1421854 | 255933 | 1601545.257 | 264447 | 1848795.2108 | 305255 | 1848795.2108 | 305255 | 2026-05-26 19:05:35 +0530 | Shivani Shet | DDM1: MOMGROUND FLOOR GF Living Room / TV Unit Â Â Â Â Â Â Â TV unit with rafters Â Â Â Â Â Â Â One glass flap-down unit for set-top box Â Â Â Â Â Â Â Additional 2 flap-down units in TV unit GF Alter UnitÂ Â Â Â Â Â Rafters and base storage and paneling with light Â Â Â Â Â Â Â Partition designed with some storage GF Parents Bedroom (PBR) Â Â Â Â Â Â Â Wardrobe Â Â Â Â Â Â Â Loft removed Â Â Â Â Â Â Â Dresser unit with ledges with panel with light GF Guest Bedroom (GBR)Â Â Â Â Â Â Â Wardrobe with loft Â Â Â Â Â Â Â Dresser unit with mirror panel with light and drawer Â Â FIRSTÂ FLOOR FF Living Room / TV UnitÂ Â Â Â Â Â Tv unit with rafters and flat pattis Â Â Â Â Â Â Â 2 flap down and 1 glass flap down FF Alter UnitÂ Â Â Â Â Â Â Rafters with 2 drawers Â Â Â Â Â Â Â Added 2 shelves and light behind the paneling and behind the photo frame also Â Â Â Â Â Â Â Pebbles will be in client scope Â FF Foyer unit Â Â Â Â Â Â Â Â Flat golden pattis with wallpaper and paint design Â Â Â Â Â Â Â Rafters with ledges with light Â Â Â Â Â Â Â Study table with open unit and one down storage drawer and shutter with lock FF Master Bedroom (MBR) Â Â Â Â Â Â Â Wardrobe with loft with drawers added at the bottom Â Â Â Â Â Â Â Dresser unit with ledges with double paneling Â Â Â Â Â Â Â Added 2 drawers in front of bed Â Â Â Â Â Â Â Design wall rafters on either side FF Guest Bedroom (GBR)Â Â Â Â Â Â Â Wardrobe with loft Â Â Â Â Â Â Â Study and dresser unit Â FF Kids Bedroom (KBR) Balcony Â Â Â Â Â Â Â Wardrobe without loft Â Â Â Â Â Â Â dresser considered with shelf with paneling and mirror Â Â Â Â Â Â Â Wall design- rafters and beading Â Â Â Â Â Â Â KBR balcony Wardrobe with drawer and single wardrobe Â DiningÂ Â Â Â Â Â Â Crockery unit Â Â Â Â Â Â Â False ceiling with 4 lights and 2 hanging lights Â Â Â Â Â Â | 2026-04-23 16:28:19 +0530 | Rhea Rathod | CDP: Renovation project Ground floor- -Vanity unit in the dining area was removed -Kitchen was descoped -Partition to be designed as per client requirement -TV unit and Altar unit - Rafters to be added as per the design -No mirrors - as the clients wants mirrors with wooden frames -Vanity units added - in the bathrooms -Tv unit and wardrobes with loft and dresser unit were made in pre-lam First floor -Beadings have been considered - solid wooden beadings -Rafters to be added -Wallpapers added - 2 in numbers -Living area - -Tv unit, Altar unit Dining area - -Crockery unit with glass shutters -False ceiling has to be designed Kitchen - -Units need to be adjusted as per the existing kitchen -Vanity unit added in the dining area -Breakfast counter- top units considered Master bedroom - -New wall concept to be proposed with beadings -Wardrobe with loft and dresser - PL Daughter's bedroom - 01 - -Wardrobe is added without loft in Balcony area - PL -Dresser added - PL -Wall concept needs to be proposed Daughter's bedroom -02 - -Wardrobe with loft - PL -Study unit needs to be planned as per existing sill level -Wall concept needs to be proposed Vanities in all bathrooms No mirrors - as the clients wants mirrors with wooden frames in bathrooms and bedrooms | 2026-04-15 11:09:31 +0530 | Parasa Sri | Welcome call done. The site is ready for initial measurements. The client is not in the station until 20th April. | 2026-04-28 | 2026-04-27 20:11 | 2026-05-11 | 2026-05-10 19:19 | RTMI
18646 | Turnkey | 2026-01-01 | Khushi shah | Divya Darpan | MUM - GOR | Yes | Zoya Ansari | Reshma Melanta | Safalta Karkera | [5 empty] | Umang Shah |  | Lost | Design | 20% Payment | 800690 | 109999 | 1097465 | 0 | 0 | 49 | 48 | 0 | 50139 | 364395 | 276156.8 |  |  | 2026-03-01 | 2026-03-01 12:58 | 2026-03-05 | 2026-03-05 16:35 | 2026-03-11 | 2026-03-11 12:00 | 2026-04-09 | 2026-04-09 16:20 | 2026-06-01 |  | 2026-06-08 |  | 2026-03-11 | 2026-03-20 14:18 | 2026-03-12 | 2026-03-20 14:25 | 2026-03-20 | 2026-03-20 17:11 | 2026-03-24 | 2026-03-24 19:14 |  |  |  |  | 2026-04-09 |  | 2026-06-03 |  | 2026-06-04 |  |  |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 | [6 empty] | 2026-07-02 |  | 2026-07-11 |  | 2026-04-30 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-14 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-12 |  | 2026-03-25 | 2026-04-09 16:11 | Site is RTMI | 2026-03-01 | 2026-03-01 12:57 | 930055 | 167410 | 0 | 0 | 0 | 0 | 913177.3965 | 154173 | 2026-07-05 16:05:44 +0530 | Reshma Melanta | Others: | 2026-07-02 15:10:22 +0530 | Reshma Melanta | Others: | 2026-06-14 18:22:51 +0530 | Shahid Chougley | CX Khushi Shah (18646) is currently not responding to our calls. A text message has also been sent; however, no response has been received as of now. The NET for this project was completed on 18 March 2026, with an estimated project value of 8,00,691. As per the standard process, clients are informed during the NET stage that the quoted value is indicative and not the final project cost. Clients are also advised to maintain a contingency buffer of 710%, as the final costing is determined during the PKO stage based on finalized designs, specifications, and project requirements. During the first DEM meeting, the client requested design modifications that resulted in an estimated cost escalation of approximately 1,02,665 over the NET value. The increase is directly attributable to the changes incorporated into the design during the post-NET stage. | 2026-04-10 | 2026-04-09 16:28 | 2026-06-02 |  | RTMI
18647 | Turnkey | 2026-01-01 | Deepak peswani | New Brindavan CHSL | MUM - GOR | Yes | Preeti Agarwal | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh |  |  |  | Moni Sahani | Aakash Gaikwad | Active | Preproduction | Site Readiness 2 | 2177279 | 1378531 | 1927835 | 0 | 2177279 | 4 | 0 | 0 | 0 | 0 | 798748 |  |  | 2026-03-01 | 2026-03-05 15:17 | 2026-03-05 | 2026-03-05 17:50 | 2026-03-05 | 2026-03-05 18:18 | 2026-03-18 | 2026-03-14 21:46 | 2026-03-27 | 2026-04-02 15:00 | 2026-06-12 | 2026-06-12 17:33 | 2026-03-05 | 2026-03-06 14:30 | 2026-03-06 | 2026-03-06 14:40 | 2026-03-06 | 2026-03-07 11:55 | 2026-03-11 | 2026-03-11 17:17 |  |  |  |  | 2026-03-25 | 2026-03-23 14:56 | 2026-05-09 | 2026-05-09 15:39 | 2026-05-10 | 2026-05-09 15:40 |  |  | 2026-06-14 | 2026-06-23 13:29 | 2026-07-08 | 2026-07-08 18:59 | 2026-07-09 | 2026-07-10 11:38 | 2026-07-11 | 2026-07-11 16:31 | [5 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-08 |  | 2026-03-12 | 2026-03-14 21:31 | Site is RTMI | 2026-03-01 | 2026-03-01 13:24 | 2309414.4392 | 381788 | 0 | 0 | 2745958.78 | 463618 | 2745958.78 | 463618 | 2026-06-30 13:54:41 +0530 | Avinash Jaiswal | Added DF 5% as retention effort. This discussed with Nimish and Mahimn | 2026-06-21 15:51:34 +0530 | Avinash Jaiswal | Some Image was uploaded | 2026-06-20 21:11:43 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-03-15 | 2026-03-14 21:48 | 2026-04-03 | 2026-04-04 17:15
18648 | Turnkey | 2026-01-01 | Sagar Dilip Dhake Rashmi Sagar Dhake | Mahavir Spring | MUM - Thane | No Estimate | Rinisha Masurkar | [7 empty] | Subhan Khan |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-01 13:40 | 2026-03-02 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-08 | [5 empty] | 2026-03-14 |  | 2026-03-22 |  | 2026-03-23 |  |  |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 | [6 empty] | 2026-04-20 |  | 2026-04-29 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-02 |  |  |  | 2026-05-24 |  | 2026-05-26 |  | 2026-05-27 | [5 empty] | 2026-03-31 |  | 2026-03-09 |  | Unknown | 2026-03-01 | 2026-03-01 13:38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-01 13:42:02 +0530 | Mustufa Sohagpurwala | Some Image was uploaded | [6 empty] | 2026-03-14 |  | 2026-03-21
18649 | Turnkey | 2026-01-01 | Soumyabrata pal | SOBHA Neopolis | BNG - HRBR | Yes | Priyanka Gs | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 2672840 | 9999 | 2672840 | 0 | 0 | 129 | 0 | 257285 | 267284 | 1135028 | 1003243.6 |  |  | 2026-02-28 | 2026-03-01 15:11 | 2026-03-03 | 2026-03-07 18:27 | 2026-03-10 | 2026-03-22 12:07 | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-11 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-05 |  | 2026-06-10 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-02-28 | 2026-03-01 13:50 | 2265119 | 407721 | 0 | 0 | 0 | 0 | 2265119 | 407721 | 2026-03-07 18:26:40 +0530 | Priyanka Gs | Some Image was uploaded | 2026-03-07 18:25:59 +0530 | Priyanka Gs | Some Image was uploaded |  |  |  | 2026-03-30 |  | 2026-04-06
18650 | Turnkey | 2026-01-01 | Sharath Kumar Gone Sharath Kumar Gone | independent house | BNG - HRBR | Yes | Palak Thakur | Rajeshwari S | [6 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 912284 | 9999 | 912284 | 0 | 0 | 109 | 0 | 81229 | 91228 | 374045 | 355782 |  |  | 2026-03-01 | 2026-03-01 15:13 | 2026-03-25 | 2026-03-25 19:08 | 2026-03-28 | 2026-03-30 12:11 | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Unknown | 2026-03-01 | 2026-03-01 13:50 | 773122 | 139161 | 0 | 0 | 0 | 0 | 773122 | 139161 | 2026-04-14 15:58:05 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-03-29 15:05:58 +0530 | Palak Thakur | CDP: Hello Mam and sirÂ Â , the mom are as follows-Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â the MOM 18650 - Sharath Kumar Gone Subject: Design and Quote Changes Design Phase MOM - 29/03/26-18650 - Sharath Kumar GoneÂ CHANGES IN CDP MEETING FOR DESIGN PHASEÂ kitchenÂ wall till 2 feet in kitchen ( will be removed entirely) more design options for kitchen arch to be more curved in kitchen entrance move the sink to outer side slightlyÂ Â cylinder might go outside the house bar cum breakfast counter to be towards sinkÂ master bedroom wardrobe placement can be discussed in masterÂ wardrobe to be shifted to the side of study and study in wardrobe wallÂ dresser to be added in masterÂ pergola design to be starting from door itself to cover from top only design to provide wallpaper for living room is considered in scopeÂ other all areas paint is done ( not in scope )Â exposed brick wall ( can be discussed )Â Â pooja design options needed [pooja optionÂ bonito store offeringÂ or kitchen counter to extend and as a wall unitÂ | 2026-03-25 19:07:40 +0530 | Palak Thakur | DCM: Minutes of Meeting held on Date: <25-03/2026> Attendees:palak Discussion:rgm Based on <25-03/2026> meeting, below is a list of all the requirements that were discussed during the meeting: FINAL MOMÂ 25-03/2026 Â 18650 - Sharath Kumar Client Name: Â SHARAD KUMAR and swetha mam Â Property: INDEPENDENT HOUSE Â LOCATIONr: KALANAHALLI YELANKA Main Door Facing: east TOWARDS OUTSIDE Possession:IN HAND AS SOON AS POSSIBLE Current residence YELANKA TO BE CHECKED FROM DOC sqft TYPE OF CONSTRUCTION BUILDER CONSTRUCTION Family Details 4 PEOPLE ( COUPLE +1 SON 17 AND 1 DAUGHTERÂ 10 )HYDERBAD HOMETOWN 15 YEARS IN BNG Mam it us based company EPG Budget Client Budget: 7 Lakhs ALL MODULAR DESIGNRecommended Budget (as per requirements): LakhsTheme Simple design Design Preferences Colors, Finishes & Lighting Kitchen: whiteLiving Area: white color paletteOverall Preference:white tones to be incorporated across the houseKitchen Countertop: quartz in cx scope Lighting: Good functional and ambient lighting to be planned throughout the houseCeiling:height 11feet no false ceiling Design Requirements & Discussion Points EXISTING FURNITURE na Might be changes in kitchen afyter concrete slab formation Bedroom top MASTER BEDROOM King bedWardrobe 1'4+ loft 2'Study unit1 shutter as mirror Hinged wardrobe bedroom 2Â kids centre WARDROBE +LOFTQueen bedStudy unit + wall storageLIVING ROOMTV 65"Fixed sofa with storageSofa cum diwan in cornerCover pillar with designWashroom base unit x master bedroomTv wall can be highlightedArch design woodenPargola design for outside (execution not in scope ) Some painting above beam KITCHENÂ Quartz by cxÂ 2 cylinderÂ spaceÂ FRIDEÂ 1 DOORÂ Double sinkÂ MICROVAVE in wall unitÂ Electrical items HANDLESS KITCHENÂ Â BASE + WALLÂ Open close glass conceptsÂ Add breakfast tableÂ DININGÂ 6 seaterÂ diningÂ Roof lights Foyer storageÂ Pooja unitÂ 2 depth standing poojaÂ With 2 doors + pocket doorsÂ Mid Seating poojaÂ HtÂ 6Â feet | 2026-04-07 |  | 2026-04-14
18651 | Turnkey | 2026-01-01 | Santosh Lokare | Mhada | MUM - GOR | Yes | Sweta Bhise |  | Shahid Chougley | [5 empty] | Rashmita Das |  | Lost | Prospect | Onboarding Due | 1130661 | 151979 | 1453341 | 0 | 0 | 126 | 0 | 0 | 74153 | 467004 | 437525.2 |  |  | 2026-03-01 | 2026-03-05 16:00 | 2026-03-05 | 2026-03-05 16:40 | 2026-03-11 | 2026-03-12 00:21 | 2026-03-19 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-03-07 | 2026-03-09 19:16 | 2026-03-08 | 2026-03-11 19:50 | 2026-03-13 |  | 2026-03-14 | [5 empty] | 2026-03-20 |  | 2026-03-28 |  | 2026-03-29 |  |  |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-08 | [6 empty] | 2026-04-26 |  | 2026-05-05 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-08 |  |  |  | 2026-05-30 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-04-06 |  | 2026-03-15 |  | Unknown | 2026-03-01 | 2026-03-01 13:53 | 1549442 | 278899 | 0 | 0 | 0 | 0 | 1275492.345 | 202774 | 2026-04-21 16:28:40 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-20 12:14:06 +0530 | Bency Chacko |  | 2026-04-15 18:50:15 +0530 | Bency Chacko | Customer Voice of Customer (VOC) The customer stated that he made an initial payment of 10% on 8th March. However, despite multiple follow-ups, he did not receive an accurate quotation until much later. Between 8th March and 27th March, the customer was reportedly shown around 10 different quotations, all of which contained incorrect pricing or details. On 11th March, a revised quotation was shared, but it was still inaccurate. Although Nimish later connected with the customer and a correct quotation was finally shared post 27th March, the delay had already impacted the customers decision. Due to the prolonged inaccuracies and lack of timely resolution, the customer proceeded with a local vendor and completed the required work independently. The customer has clearly stated that: He does not consider the booking as valid due to incorrect deliverables.The services provided did not meet his requirements.He does not wish to proceed further with the project.He is now requesting a full refund of the amount paid. Additionally, the customer has expressed strong dissatisfaction and has indicated that if the issue is not resolved promptly, he may escalate the matter publicly on social media platforms, citing his association with Times Now. | 2026-03-20 |  | 2026-03-27
18652 | Turnkey | 2026-01-01 | Gauri Sawant | Runwal Sanctuary | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | suraj kumar | Aditya Vikram | Murali S | Foram Joshi | Shailendra Mishra | Active | Production | Dispatch Due | 2021049 | 2021049 | 1877834 | 0 | 2021049 | 2 | 17 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-01 14:14 | 2026-03-01 | 2026-03-01 22:10 | 2026-03-04 | 2026-03-02 12:45 | 2026-03-29 | 2026-03-29 15:18 | 2026-04-08 | 2026-04-08 10:52 | 2026-06-04 | 2026-06-04 10:51 | 2026-03-02 | 2026-03-04 18:53 | 2026-03-03 | 2026-03-04 19:22 | 2026-03-04 | 2026-03-06 11:56 | 2026-03-11 | 2026-03-11 11:06 |  |  |  |  | 2026-03-17 | 2026-03-25 16:15 | 2026-05-31 | 2026-05-14 17:12 | 2026-05-15 | 2026-05-14 17:12 |  |  | 2026-06-04 | 2026-06-09 11:15 | 2026-06-14 | 2026-06-14 16:26 | 2026-06-17 | 2026-06-18 22:35 | 2026-06-18 | 2026-06-26 13:02 |  |  |  |  | 2026-06-28 16:21 | 2026-07-04 | 2026-07-04 17:30 | 2026-07-13 | 2026-07-11 19:10 | 2026-07-12 | 2026-07-13 16:07 | 2026-07-11 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-28 |  | 2026-07-29 | [5 empty] | 2026-06-14 | 2026-06-27 13:29 | 2026-03-12 | 2026-03-29 14:58 | Site is RTMI | 2026-03-01 | 2026-03-01 14:06 | 1591385 | 286449 | 0 | 0 | 2097045.7057 | 361862 | 2097045.7057 | 361862 | 2026-07-08 11:46:01 +0530 | suraj kumar | Project status: Currently, Modular material is in progress. Floor covering and Deep cleaning not in our scope.. | 2026-06-23 13:26:54 +0530 | Anil Jagtap | CX has informed that she is travelling at the moment and will process the PKO payment on Friday. | 2026-06-18 21:16:55 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-03-30 | 2026-04-02 17:12 | 2026-05-08 | 2026-05-07 20:07
18653 | Turnkey | 2026-01-01 | Priyam Tiwari | Vista | MUM - GOR | Yes | Khyati Bandi | Reshma Melanta | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Hold | Design | 20% Payment | 1617160 | 219281 | 2192799 | 0 | 0 | 1 | 77 | 0 | 104151 | 681420 | 612308 |  |  | 2026-02-28 | 2026-03-04 12:53 | 2026-03-09 | 2026-03-09 12:55 | 2026-03-12 | 2026-03-10 13:05 | 2026-04-18 | 2026-04-18 20:22 | 2026-08-02 |  | 2026-08-09 |  | 2026-03-10 | 2026-03-11 13:04 | 2026-03-11 | 2026-03-11 13:12 | 2026-03-11 | 2026-03-12 14:20 | 2026-03-20 | 2026-03-20 19:01 |  |  |  |  | 2026-04-28 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-04-09 | 2026-04-18 20:13 | Site is RTMI | 2026-02-28 | 2026-03-04 12:52 | 1858304 | 334494 | 0 | 0 | 0 | 0 | 1836018.6793 | 309990 | 2026-07-02 16:56:12 +0530 | Reshma Melanta | Others: | 2026-05-27 12:50:09 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-09 18:34:19 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-19 | 2026-04-28 20:13 | 2026-08-03 |  | Under Construction | 2026-06-01
18654 | Turnkey | 2026-01-01 | Anne Rajesh Anthony | 100 Trees | MUM - GOR | Yes | Priyanka Murarka | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1077760 | 215552 | 1373468 | 0 | 0 | 55 | 0 | 0 | 0 | 442969 | 419239.2 |  |  | 2026-02-28 | 2026-03-10 20:08 | 2026-03-26 | 2026-03-26 16:22 | 2026-03-27 | 2026-03-27 14:48 | 2026-04-29 | 2026-04-29 19:09 | 2027-01-16 |  | 2027-01-23 |  | 2026-03-26 | 2026-03-26 19:56 | 2026-03-28 | 2026-03-27 15:50 | 2026-03-27 | 2026-03-30 14:51 | 2026-04-10 | 2026-04-10 17:59 |  |  |  |  | 2026-04-29 | 2026-05-21 18:29 | 2027-01-18 |  | 2027-01-19 |  |  |  | 2027-01-26 |  | 2027-01-27 |  | 2027-01-28 |  | 2027-01-29 | [6 empty] | 2027-02-16 |  | 2027-02-25 |  | 2027-02-24 |  | 2027-02-25 |  | 2027-02-26 |  | 2027-02-28 |  |  |  | 2027-03-22 |  | 2027-03-24 |  | 2027-03-25 | [5 empty] | 2027-01-27 |  | 2026-04-11 | 2026-04-29 14:33 | Site is RTMI | 2026-02-28 | 2026-03-10 20:07 | 1163955 | 209512 | 0 | 0 | 0 | 0 | 1142811.6032 | 188810 | 2026-06-06 13:47:22 +0530 | Priyanka Murarka | Some Image was uploaded | 2026-06-04 13:33:29 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-13 16:35:54 +0530 | Vishakha Vaishnav | Tried calling the cx for the 10% due , however the cx didn't answered the call | 2026-04-30 | 2026-04-29 19:12 | 2027-01-17 |  | RTMI
18656 | Turnkey | 2026-01-01 | Neville Dubash | Ajmera Manhatan | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Saloni Chawan |  | Hold | Preproduction | DEM2 | 3574122 | 1414825 | 4692115 | 0 | 0 | 11 | 68 | 0 | 0 | 861814 | 1297482.8 |  |  | 2026-03-01 | 2026-03-02 20:08 | 2026-03-10 | 2026-03-10 01:35 | 2026-03-15 | 2026-03-15 20:00 | 2026-05-22 | 2026-05-22 13:29 | 2027-01-01 |  | 2027-01-08 |  | 2026-03-15 | 2026-03-17 18:22 | 2026-03-16 | 2026-03-19 14:28 | 2026-03-19 | 2026-03-20 14:29 | 2026-03-26 | 2026-04-05 13:45 |  |  |  |  | 2026-05-22 | 2026-05-22 14:27 | 2027-01-03 |  | 2027-01-04 |  |  |  | 2027-01-11 |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 | [6 empty] | 2027-02-01 |  | 2027-02-10 |  | 2027-02-09 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-13 |  |  |  | 2027-03-07 |  | 2027-03-09 |  | 2027-03-10 | [5 empty] | 2027-01-12 |  | 2026-08-31 | 2026-05-09 15:35 | Site is RTMI | 2026-03-01 | 2026-03-02 20:07 | 3976368 | 715746 | 0 | 0 | 0 | 0 | 3902519.803 | 644357 | 2026-07-10 13:56:46 +0530 | Anil Jagtap | cx will receive the possession by end of December*26 | 2026-06-02 14:53:23 +0530 | Anamika Dolai | Some Image was uploaded | 2026-05-13 15:21:36 +0530 | Saloni Chawan | Some Image was uploaded | 2026-05-23 | 2026-05-22 13:30 | 2027-01-02
18657 | Turnkey | 2026-01-01 | Yasir Shafi Reshi | Keya The Lake Terraces | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  | Sethuragavan R | Yogeshwaran | Ranjith Kumar | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Active | Installation | Execution | 907332 | 907332 | 1291918 | 0 | 954832 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-01 16:03 | 2026-03-18 | 2026-03-18 15:10 | 2026-03-31 | 2026-04-04 10:31 | 2026-05-26 | 2026-05-26 19:49 | 2026-06-05 | 2026-06-04 13:07 | 2026-06-15 | 2026-06-14 12:52 | 2026-04-04 | 2026-03-31 | 2026-04-05 | 2026-04-08 11:15 | 2026-04-08 | 2026-04-08 16:11 | 2026-04-15 | 2026-04-15 18:39 |  |  |  |  | 2026-06-11 | 2026-05-26 19:15 | 2026-06-10 | 2026-06-11 11:58 | 2026-06-12 | 2026-06-11 12:05 |  |  | 2026-06-15 | 2026-06-16 16:21 | 2026-06-16 | 2026-06-16 21:31 | 2026-06-17 | 2026-06-16 22:30 | 2026-06-17 | 2026-06-19 18:30 |  |  |  |  | 2026-06-23 11:30 | 2026-06-27 | 2026-06-26 20:54 | 2026-07-04 | 2026-07-02 14:14 | 2026-05-25 | 2026-04-03 12:30 | 2026-07-02 | 2026-07-13 14:47 | 2026-07-13 | 2026-07-13 22:43 | 2026-07-15 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-16 | 2026-06-23 11:29 | 2026-06-06 | 2026-05-26 19:31 | Site is RTMI | 2026-03-01 | 2026-03-01 16:02 | 1094846 | 197072 | 0 | 0 | 1157611.0074 | 186838 | 1157611.0074 | 186838 | 2026-07-08 08:24:11 +0530 | Ranjith Kumar | Dispatch Due: | 2026-07-07 10:20:47 +0530 | Ranjith Kumar | Dispatch Due: | 2026-07-04 10:10:15 +0530 | Ranjith Kumar | Dispatch Due: | 2026-05-27 | 2026-05-26 19:52 | 2026-06-05 | 2026-06-09 16:19 | Under Construction | 2026-04-30
18659 | Turnkey | 2026-01-01 | Pallavi Chhipa | GTT | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 2643002 | 9999 | 0 | 0 | 0 | 126 | 0 | 254301 | 264300 | 1073853 | 1040548.4 |  |  | 2026-03-01 | 2026-03-01 19:32 | 2026-03-05 | 2026-03-05 11:12 | 2026-03-11 |  | 2026-03-18 |  | 2026-03-25 |  | 2026-04-01 |  | 2026-03-11 |  | 2026-03-12 |  | 2026-03-12 |  | 2026-03-13 | [5 empty] | 2026-03-19 |  | 2026-03-27 |  | 2026-03-28 |  |  |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 | [6 empty] | 2026-04-25 |  | 2026-05-04 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-07 |  |  |  | 2026-05-29 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-04-05 |  | 2026-03-14 |  | Unknown | 2026-03-01 | 2026-03-01 16:15 | 0 | 0 | 0 | 0 | 0 | 0 | 2239832 | 403169 | 2026-03-05 11:09:03 +0530 | Swati Rathod | Based on 01-03-2026 meeting, below is a list of all the requirements that were discussed during the meeting: PID: 18659Â Property - 3BHK possession - 01-03-2026 Budget - 10L- 12L Members - 4ppl(2kids)(vriha(8.5yrs)-prashi(6mont) - east facing - king, queen bed, chest of drawers(with 6 drawer) is already there. - west wall near dinning nice wall concept above chest of drawers to be done. FOYER : - shoe rack(40-50 pairs) - tall unit - wash basin on M. bedroom toilet wall(east wall) - full length mirror on south ALLÂ LIVING: - tv unit with ledges - l shaped sofa DINNING: - 6 seater - pooja(sanding)(closed with ledges) with crockery unit(more ht) KITCHEN: - OTG(not modular) with roller shutter - bottom unit - top units - loft - quartz - pantry unit - tall unit(glass shutter) - single sink - 3-4 burner - try D.W near single bowl - mob space to be provided UTILITY: - 2 bowl sink,Â - W.M, D.W -top storage for planter elements with less depth 9top unit with ledges) TOILETS: - vanity - storage on commode topÂ M.BEDROOM:(kids bedroom) - glass partition in toilet - bunk bed(q size bed in bottom) - openable wardrobe on west wall - study unit - dresser - wardrobe with bed as reff.(1 with glass shutter) - study unit small for 2 kids - (bottom bag storage top used cloths storage) BEDROOM(11'x14'6"):(M bedroom) - west all king size bed(6'x6'6") - openable wardroveÂ - window seating - east wall (dresser with tv (bottom storage) and wardrobe) - side table near window wallÂ - glass partition in toilet - used cloth wardrobe BEDROOM(11'x11'6"): - king size bed - wardrobe with small study unit Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements | 2026-03-01 19:50:24 +0530 | Pulivarthi Nirosha | Some Image was uploaded |  |  |  | 2026-03-19 |  | 2026-03-26
18660 | Turnkey | 2026-01-01 | Vinamra Vinod | Runwal Greens | MUM - Thane | Yes | Mayuri Patil | [7 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 2821502 | 9999 | 0 | 0 | 0 | 136 | 0 | 272151 | 282150 | 1154841 | 1102360.8 |  |  | 2026-03-01 | 2026-03-01 23:02 | 2026-03-04 | 2026-03-10 12:07 | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-03-01 | 2026-03-01 22:44 | 0 | 0 | 0 | 0 | 0 | 0 | 2391104 | 430398 | 2026-03-10 11:53:28 +0530 | Maasoumeh Raza | Name:Â 18660 - Vinamra Vinod Property Name: Runwal Greens Property type: 3BHK Possession: March Move in: JulyÂ Member: 5 member [couple,2 kids & grand mother] Budget: 15L TO 20L Requirements: Living room: Shoe Rack InsideÂ Safety doorÂ Tv Unit with Mandir 3 + 2seater sofaÂ 6 Seater dining [Option needed] Crockery unit Balcony design option needed.Â Mirror panelling in anyone wallÂ Kitchen : Base unit Wall unit Loft unit Appliance unit Storage for broom & mop Â Sliding door Demolish the existing kitchen wall. If structurally feasible, create a niche/space that can be used either for a mandir or a crockery cabinet, depending on the clients preference. Washing machine top storage Â Guest bedroom :Â Â Queen size bed Wardrobe with loft Kids bedroom:Â King size bed Wardrobe with loft Dressing Unit[long mirror] Study table storage in niche bay seating Master bedroom:Â King size bed side table Dressing Unit Study table Demolishing of the existing wardrobe wall and redesigning the space as per the new wall layout after demolition. Bathroom: 3 Below vanity unit Glass partitionÂ Additional scope: Full home False ceiling Painting Electrical | 2026-03-04 13:08:03 +0530 | Aryan Singh | Some Image was uploaded |  |  |  | 2026-03-23 |  | 2026-03-30
18661 | Turnkey | 2026-01-01 | Shubhlaxmi Jena | The Baya Midtown | MUM - GOR | Yes | Preeti Agarwal | Manzoor Shaikh | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Nilesh Patel | Rizwan Mistry | Murali S | Rashmita Das | Vinay Surve | Active | Installation | Execution | 1116219 | 1116219 | 1678013 | 0 | 1134219 | 19 | 11 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-05 12:20 | 2026-03-05 | 2026-03-05 12:30 | 2026-03-05 | 2026-03-05 14:26 | 2026-03-12 | 2026-03-12 12:28 | 2026-03-22 | 2026-03-22 14:40 | 2026-04-10 | 2026-04-10 19:37 | 2026-03-05 | 2026-03-06 20:35 | 2026-03-06 | 2026-03-07 10:52 | 2026-03-07 | 2026-03-08 12:04 | 2026-03-08 | 2026-03-08 17:21 |  |  |  |  | 2026-03-19 | 2026-03-20 22:23 | 2026-04-04 | 2026-04-07 14:22 | 2026-04-08 | 2026-04-07 14:23 |  |  | 2026-04-16 | 2026-05-05 15:45 | 2026-05-09 | 2026-05-09 22:21 | 2026-05-10 | 2026-05-10 22:44 | 2026-05-11 | 2026-05-14 16:50 |  |  |  |  | 2026-06-06 10:16 | 2026-06-16 | 2026-06-17 19:52 | 2026-06-21 | 2026-06-19 19:07 | 2026-06-20 | 2026-06-19 20:28 | 2026-06-19 | 2026-06-23 18:53 | 2026-06-23 | 2026-06-26 19:36 | 2026-06-28 | 2026-07-11 12:54 |  |  | 2026-07-08 |  | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-05-09 | 2026-06-06 10:15 | 2026-03-09 | 2026-03-11 16:40 | Site is RTMI | 2026-03-01 | 2026-03-04 11:31 | 1422045 | 255968 | 0 | 0 | 1231727.0613 | 198948 | 1231727.0613 | 198948 | 2026-07-13 11:30:26 +0530 | Nilesh Patel | PI works has been completed Modulars Installation works has been completed (Except Living Room Loft storage, TV unit and Profile Shutter Installation) Blocker - Invisible bed is delayed by Vendor PVC beading is yet not delivered at site Mirrors Delivery and Installation pending Handles Order Raising is missed in BOM | 2026-06-23 15:43:01 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-16 12:03:15 +0530 | Nilesh Patel | Execution: Floor Covering has been completed a site False ceiling frame works and Gypsm sheet installation has been done at site Cornice for both the bedroom is in progress | 2026-03-13 | 2026-03-12 12:47 | 2026-03-23 | 2026-03-22 14:43
18662 | Turnkey | 2026-01-01 | Bipin Das | mvn aero one | BNG - HRBR | Yes | Sreelakshmi M | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Active | Preproduction | DEM2 | 1697754 | 237749 | 1518446 | 0 | 0 | 92 | 0 | 0 | 0 | 820755 | 639250 |  |  | 2026-03-01 | 2026-03-01 17:21 | 2026-03-08 | 2026-03-08 15:04 | 2026-03-13 | 2026-03-17 16:33 | 2026-03-30 | 2026-03-30 12:52 | 2026-07-01 | 2026-06-30 17:54 | 2026-07-24 |  | 2026-03-17 | 2026-03-17 16:44 | 2026-03-18 | 2026-03-17 16:46 | 2026-03-17 | 2026-03-18 12:21 | 2026-03-20 | 2026-03-20 18:45 |  |  |  |  | 2026-03-30 | 2026-04-14 18:28 | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-09-11 |  | 2026-09-12 | [6 empty] | 2026-09-30 |  | 2026-10-09 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-12 |  |  |  | 2026-11-03 |  | 2026-11-05 |  | 2026-11-06 | [5 empty] | 2026-07-28 |  | 2026-03-21 | 2026-03-30 12:42 | Site is RTMI | 2026-03-01 | 2026-03-01 17:15 | 1286818 | 231627 | 0 | 0 | 0 | 0 | 1754638.0143 | 300165 | 2026-06-29 10:40:16 +0530 | Sreelakshmi M | Minutes of Meeting (MOM) Date: 28/07/2026 Discussion Summary * Wallpaper, material selection, and paint codes have been finalized. * Pooja to check the outside. Kitchen * Replace the existing golden strip with rose gold. * Add a new switch point inside the roller shutter. * Share the kitchen accessories reference images with the client. * Share the dado tile reference images with the client. * Share the paint codes for: Â Â * Full house painting Â Â * Highlight walls * Share the charcoal beading paint code. Master Bedroom * Add a false ceiling. * Provide one additional option with sprinkler boxing.and renders Conclusion * The overall design has been finalized. | 2026-06-13 17:00:21 +0530 | Sreelakshmi M | MOM 13 June 2026 ¦ 10:35 AM * Laminate selections are confirmed except for the TV unit. * Memory wall painting in Silver Moon is finalized. The same finish is fixed for the master bedroom bed-back wall. * Breakfast counter rafters to match the wooden laminate used on the breakfast counter side panel and ceiling. * No changes in the kitchen; only the dado tile selection needs to be checked. * Living room HDHMR grooving is finalized. * Duco painting costing to be checked. * Designs are finalized; only the wallpaper and TV bottom laminate need to be changed as per the wallpaper selection. * Beading paint color to be finalized after wallpaper and TV unit laminate selection. * False ceiling design to be checked and confirmed from the client side. * Wardrobe internal layout to be finalized. * Internal wardrobe layout PDF to be shared for reference. | 2026-06-02 10:52:29 +0530 | Sreelakshmi M | MOM Living room material selection and design has been finalized. Quotation to include the following options: 1. Rafters finish option with complete costing. 2. HDHMR grooving with paint finish option with complete costing. Pooja options need to be checked outside. Dado tile options need to be checked outside. Material selection for the Master Bedroom and Guest Bedroom is pending. | 2026-03-31 | 2026-03-30 12:56 | 2026-07-01 | 2026-06-30 18:10 | Under Construction | 2026-03-31
18663 | Turnkey | 2026-01-01 | Jatin Kumar Patro | SV Polaris | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP |  | Sethuragavan R | Yogeshwaran | Ranjith Kumar | Murali S | Chanakya Panigrahi | Sunil Kumar S M | Active | Preproduction | Procurement | 1079603 | 658038 | 1699856 | 0 | 1079603 | 5 | 49 | 0 | 0 | 0 | 421565 |  |  | 2026-03-01 | 2026-03-07 11:03 | 2026-03-08 | 2026-03-08 11:13 | 2026-03-08 | 2026-03-08 11:16 | 2026-04-09 | 2026-04-09 12:07 | 2026-06-17 | 2026-06-16 13:46 | 2026-06-26 | 2026-06-25 08:26 | 2026-03-08 | 2026-03-12 17:14 | 2026-03-09 | 2026-03-12 17:39 | 2026-03-12 | 2026-03-13 18:35 | 2026-03-20 | 2026-03-20 19:47 |  |  |  |  | 2026-04-09 | 2026-04-06 22:02 | 2026-06-19 | 2026-06-20 14:58 | 2026-06-21 | 2026-06-23 10:51 |  |  | 2026-06-27 | 2026-06-28 12:04 | 2026-06-30 | 2026-06-30 23:30 | 2026-07-01 | 2026-06-30 23:48 | 2026-07-01 | 2026-07-08 17:24 |  |  |  |  | 2026-07-10 18:51 | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-30 | 2026-07-10 18:50 | 2026-04-04 | 2026-04-09 11:21 | Site is RTMI | 2026-03-01 | 2026-03-06 20:21 | 1440556 | 259300 | 0 | 0 | 1219077.961 | 201295 | 1219077.961 | 201295 | 2026-07-10 18:58:28 +0530 | Ranjith Kumar | Some Image was uploaded | 2026-06-29 12:15:34 +0530 | Aishwarya C | Some Image was uploaded | 2026-06-27 19:46:43 +0530 | Aishwarya C | Some Image was uploaded | 2026-04-10 | 2026-05-29 19:53 | 2026-06-17 | 2026-06-18 16:18
18664 | Turnkey | 2026-01-01 | K.PRASANNA | SSVR NIYAARA | BNG - HSR | No Estimate | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-01 17:38 | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-15 |  | 2026-03-16 | [5 empty] | 2026-03-22 |  | 2026-03-30 |  | 2026-03-31 |  |  |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 | [6 empty] | 2026-04-28 |  | 2026-05-07 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-10 |  |  |  | 2026-06-01 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-04-08 |  | 2026-03-17 |  | Unknown | 2026-03-01 | 2026-03-01 17:32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-22 |  | 2026-03-29
18665 | Turnkey | 2026-01-01 | khushi prajapati | Kalpataru Immensa | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [7 empty] | Lost | Design | DEM1 | 1971769 | 252999 | 2537402 | 0 | 0 | 117 | 0 | 0 | 141355 | 854552 | 722863.2 |  |  | 2026-02-28 | 2026-03-06 18:03 | 2026-03-08 | 2026-03-08 21:09 | 2026-03-11 | 2026-03-09 22:30 | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-03-09 | 2026-03-10 18:59 | 2026-03-10 | 2026-03-11 11:11 | 2026-03-11 | 2026-03-20 13:35 | 2026-03-22 | 2026-03-22 12:20 |  |  |  |  | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-03-23 | 2026-03-22 16:36 | Site is RTMI | 2026-02-28 | 2026-03-06 18:02 | 2150341 | 387061 | 0 | 0 | 0 | 0 | 2079102.9008 | 346383 | 2026-05-07 18:05:55 +0530 | Anil Kuwar | Some Image was uploaded | 2026-04-22 17:43:36 +0530 | Anil Jagtap | Some Image was uploaded | 2026-04-18 14:49:56 +0530 | Sarita Jangid | Some Image was uploaded | 2026-06-03 |  | 2026-06-10 |  | Under Construction | 2026-03-01
18667 | Turnkey | 2026-01-01 | Mahendra Parmar | Runwal Sanctuary | MUM - Thane | No Estimate | [8 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-02 20:02 | 2026-03-02 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-03-01 | 2026-03-02 20:01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-08 |  | 2026-04-15
18668 | Turnkey | 2026-01-01 | Ramya | Infinity green woods | BNG - HSR | Yes | Nayan Reddy | Abhinandan K S | Kowshik | [5 empty] | Varun Mandana |  | Active | Prospect | DCM Due | 1003182 | 9999 | 0 | 0 | 0 | 136 | 0 | 90319 | 100318 | 407992 | 394553.6 |  |  | 2026-03-01 | 2026-03-01 18:47 | 2026-03-13 | 2026-03-13 11:54 | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-15 |  | 2026-03-16 | [5 empty] | 2026-03-22 |  | 2026-03-30 |  | 2026-03-31 |  |  |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 | [6 empty] | 2026-04-28 |  | 2026-05-07 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-10 |  |  |  | 2026-06-01 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-04-08 |  | 2026-03-17 |  | Unknown | 2026-03-01 | 2026-03-01 18:35 | 0 | 0 | 0 | 0 | 0 | 0 | 850155 | 153027 | 2026-03-13 15:44:27 +0530 | Nayan Reddy | DCM: Cx NameÂ -Â Â RamyaÂ crm - VarunÂ Â 01/03/26 Move in date - July Budget -10-8L Property name -Â Infinity Green woodsÂ direction - e facingÂ f to cÂ - 10'Â Modular kitchenÂ Kitchen entry wall need to be removed from model 1 sink unit near corner areaÂ crockery concpet in kitchenÂ tall unitÂ base unitÂ wall unitÂ loftÂ UtilityÂ sink cabinetÂ wall cabinetÂ janitor unitÂ Living roomÂ tv unit -Â suspended drawers and dispaly unitÂ Fc in living and dinningÂ dinning crockery unit and pooja unitÂ MBRÂ Study unitÂ closed cabinetÂ dressing unitÂ 9' wardrobeÂ Bedroom (GBR) WardrobeÂ | 2026-03-01 19:31:03 +0530 | Varun Mandana | Some Image was uploaded |  |  |  | 2026-03-22 |  | 2026-03-29
18669 | Turnkey | 2026-01-01 | Amogh sivekar | Paranjape Aspire | MUM - GOR | Yes | Rajnish Mishra | Reshma Melanta | Safalta Karkera | [5 empty] | Moni Sahani |  | Hold | Preproduction | DEM2 | 1096271 | 219253 | 1576931 | 0 | 0 | 12 | 72 | 0 | 0 | 500478 | 376539.6 |  |  | 2026-03-01 | 2026-03-05 15:13 | 2026-03-03 | 2026-03-05 16:42 | 2026-03-08 | 2026-03-08 14:09 | 2026-03-31 | 2026-03-31 14:35 | 2026-08-02 |  | 2026-08-09 |  | 2026-03-08 | 2026-03-09 19:22 | 2026-03-09 | 2026-03-11 14:16 | 2026-03-11 | 2026-03-12 18:09 | 2026-03-20 | 2026-03-20 18:48 |  |  |  |  | 2026-03-31 | 2026-05-18 18:52 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-09-14 |  | 2026-09-15 | [6 empty] | 2026-10-03 |  | 2026-10-12 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-15 |  |  |  | 2026-11-06 |  | 2026-11-08 |  | 2026-11-09 | [5 empty] | 2026-08-13 |  | 2026-03-21 | 2026-03-31 14:30 | Site is RTMI | 2026-03-01 | 2026-03-01 18:38 | 1336382 | 240548 | 0 | 0 | 0 | 0 | 1282405.0789 | 206126 | 2026-06-02 17:12:51 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-17 19:56:46 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-15 13:49:27 +0530 | Moni Sahani | Some Image was uploaded | 2026-04-01 | 2026-03-31 14:37 | 2026-08-03 |  | Under Construction | 2026-08-01
18672 | Turnkey | 2026-01-01 | Hemanthkumar | Nava vajra | BNG - HRBR | Yes | Chandini Nj | Parasa Sri | Shibin Lal | [5 empty] | Raghavendra S |  | Hold | Preproduction | DEM2 | 1222187 | 253999 | 1570266 | 0 | 0 | 59 | 7 | 0 | 0 | 498699 | 469489.2 |  |  | 2026-03-01 | 2026-03-30 13:22 | 2026-03-30 | 2026-03-30 13:38 | 2026-04-02 | 2026-03-30 14:09 | 2026-05-10 | 2026-05-09 12:15 | 2026-08-21 |  | 2026-08-28 |  | 2026-03-30 | 2026-03-30 19:09 | 2026-03-31 | 2026-03-31 12:54 | 2026-03-31 | 2026-03-31 15:25 | 2026-04-05 | 2026-04-12 20:04 |  |  |  |  | 2026-05-09 | 2026-05-10 18:41 | 2026-08-23 |  | 2026-08-24 |  |  |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 | [6 empty] | 2026-09-21 |  | 2026-09-30 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-03 |  |  |  | 2026-10-25 |  | 2026-10-27 |  | 2026-10-28 | [5 empty] | 2026-09-01 |  | 2026-05-22 | 2026-05-09 12:12 | Site is RTMI | 2026-03-01 | 2026-03-01 19:53 | 1330733 | 239532 | 0 | 0 | 0 | 0 | 1276909.802 | 210842 | 2026-05-14 14:37:08 +0530 | Chandini Nj | False ceiling - living, dining and KBR, MBR Living and dining - membrane finish living area - radha krishna pattern and using marbleÂ kitchen - island unit, tall unit oven provision, small sink in the corner (hob side) MBR - hinged wardrobe, but need to provide bottom storage without loft. Dresser unit with mirror and side storage KBR - as per the video we need to plan GBR -Â SAME DESIGN BUT NEED TO consider sofa comes bedÂ Pooja unit - reference images | 2026-05-09 12:11:43 +0530 | Parasa Sri | DEM-1 Done. Initial measurement is planned on 17th May. | 2026-04-23 12:21:29 +0530 | Parasa Sri | Some Image was uploaded | 2026-05-10 | 2026-05-09 12:15 | 2026-08-22 |  | Under Construction | 2026-04-15
18675 | Turnkey | 2026-01-01 | Laxmi Chand Jaiswal | Desire Tree | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  | RaviKumar Battala | Suchendra Shetty | Jairam Joshi |  | Aman Kumar | Affaan Abdulla | Lost | Preproduction | 2D | 1492918 | 235604 | 1643970 | 1855148 | 1492918 | 27 | 0 | 0 | 0 | 701528 | 555785.6 |  |  | 2026-03-01 | 2026-03-01 20:12 | 2026-03-07 | 2026-03-14 18:31 | 2026-03-15 | 2026-03-16 17:47 | 2026-05-11 | 2026-05-07 10:58 | 2026-05-21 | 2026-05-20 10:54 | 2026-05-31 | 2026-05-30 09:58 | 2026-03-16 | 2026-03-20 10:44 | 2026-03-17 | 2026-03-20 10:50 | 2026-03-20 | 2026-03-24 12:06 | 2026-03-27 | 2026-03-27 19:08 |  |  |  |  | 2026-05-09 | 2026-05-06 18:22 | 2026-05-21 | 2026-05-21 14:15 | 2026-05-22 | 2026-05-21 14:21 |  |  | 2026-05-31 | 2026-06-18 16:22 | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 | [6 empty] | 2026-10-21 |  | 2026-10-30 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-02 |  |  |  | 2026-11-24 |  | 2026-11-26 |  | 2026-11-27 | [5 empty] | 2026-10-01 |  | 2026-05-04 | 2026-05-07 10:31 | Site is RTMI | 2026-03-01 | 2026-03-01 20:10 | 1393195 | 250775 | 1944823.4058 | 321124 | 1684101.8043 | 278072 | 1684101.8043 | 278072 | 2026-07-09 16:05:24 +0530 | Akshay Ds |  | 2026-07-09 14:27:08 +0530 | Akshay Ds |  | 2026-07-09 14:25:38 +0530 | Akshay Ds |  | 2026-05-08 | 2026-05-09 18:25 | 2026-05-21 | 2026-05-20 10:54 | Under Construction | 2026-04-30
18676 | Turnkey | 2026-01-01 | Mukesh Nisar | Pratap Harmony | MUM - GOR | Yes |  |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 1654430 | 9999 | 1654430 | 0 | 0 | 103 | 0 | 155444 | 165443 | 661772 | 661772 |  |  | 2026-03-01 | 2026-03-01 20:35 | 2026-03-05 | 2026-03-19 12:35 | 2026-03-22 | 2026-04-03 16:03 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-01 | 2026-03-01 20:34 | 1402060 | 252370 | 0 | 0 | 0 | 0 | 1402060 | 252370 | [9 empty] | 2026-04-11 |  | 2026-04-18
18677 | Turnkey | 2026-01-01 | Ankita Pandey | MEADOWS SONG VILLA 117 | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Kowshik |  | RaviKumar Battala | Sachin I Betageri | Ranjith Kumar | Murali S | Nidhi Shaw | Sunil Kumar S M | Completed | Complete | Completed | 1386162 | 1386162 | 1744923 | 0 | 1386162 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-01 20:36 | 2026-03-04 | 2026-03-04 15:38 | 2026-03-07 | 2026-03-07 21:22 | 2026-04-03 | 2026-03-30 16:44 | 2026-04-08 | 2026-04-07 10:41 | 2026-04-15 | 2026-04-15 16:31 | 2026-03-07 | 2026-03-09 14:09 | 2026-03-08 | 2026-03-11 10:54 | 2026-03-11 | 2026-03-11 16:11 | 2026-03-14 | 2026-03-14 19:18 |  |  |  |  | 2026-03-30 | 2026-03-31 01:06 | 2026-04-08 | 2026-04-09 22:28 | 2026-04-10 | 2026-04-09 22:29 |  |  | 2026-04-22 | 2026-04-25 17:56 | 2026-04-25 | 2026-04-25 20:43 | 2026-04-27 | 2026-04-25 20:50 | 2026-05-02 | 2026-04-30 19:13 |  |  |  |  | 2026-05-02 17:08 | 2026-05-08 | 2026-05-08 13:32 | 2026-06-01 | 2026-05-30 19:06 | 2026-05-30 | 2026-05-30 18:55 | 2026-05-30 | 2026-05-30 19:54 | 2026-05-30 | 2026-05-30 19:55 | 2026-06-01 | 2026-06-03 12:33 |  |  | 2026-06-19 | 2026-06-20 19:12 | 2026-06-21 | 2026-06-20 20:41 | 2026-06-22 | 2026-06-20 22:25 |  |  |  |  | 2026-04-25 | 2026-04-30 15:35 | 2026-03-15 | 2026-03-30 16:05 | Site is RTMI | 2026-03-01 | 2026-03-01 20:35 | 1478748 | 266174 | 0 | 0 | 1539254.096 | 254160 | 1539254.096 | 254160 | 2026-07-01 18:16:08 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-06-20 22:27:29 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-06-18 18:18:07 +0530 | Ranjith Kumar | Execution: | 2026-03-31 | 2026-03-30 16:46 | 2026-04-08 | 2026-04-07 10:42
18678 | Turnkey | 2026-01-01 | Jijesh Chandran | Kalpatru elitus | MUM - Thane | Yes | Maasoumeh Raza | [7 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 2456177 | 9999 | 0 | 0 | 0 | 136 | 0 | 235619 | 245618 | 1041165 | 923776.8 |  |  | 2026-03-01 | 2026-03-01 20:48 | 2026-03-04 | 2026-03-04 14:17 | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 | [5 empty] | 2026-03-28 |  | 2026-04-05 |  | 2026-04-06 |  |  |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 | [6 empty] | 2026-05-04 |  | 2026-05-13 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-16 |  |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-04-14 |  | 2026-03-23 |  | Unknown | 2026-03-01 | 2026-03-01 20:45 | 0 | 0 | 0 | 0 | 0 | 0 | 2084307 | 371869 | 2026-03-04 14:12:54 +0530 | Maasoumeh Raza | Name:Â 18678 - Jijesh ChandranÂ Property Name: Kalpatru elitus Property type: 2BHK Possession: March Move in: SeptemberÂ Member: 3 member [couple & 1 boy] Budget: 15L Theme : White wall with tinted of colour in loose furniture or wall White light only Requirements: Living room: Shoe Rack Safety door Console unitÂ Tv Unit with back panel, one unit will be in glass [55 inch] 3 seater sofa 4 Seater dining Mandir unit full height [open mandir] Kitchen : Base unit Wall unit Loft unit Wicker basket Appliance unit Storage for broom & mop beautification in Utility areaÂ Â Â Son bedroom :Â Queen size Bed with storage Wardrobe with loft Side table Study table Master bedroom:Â King size bed Wardrobe with loft Dressing Unit Study table Bookshelf with storage Bathroom: 2 Below vanity unit Glass partitionÂ Additional scope: Full home False ceiling Painting Electrical | [6 empty] | 2026-03-28 |  | 2026-04-04
18679 | Turnkey | 2026-01-01 | Gaurav | Pelican Square | BNG - HSR | Yes | Saranya Thiyagarajan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1937054 | 9999 | 1937054 | 0 | 0 | 123 | 0 | 183706 | 193705 | 817224 | 732418.8 |  |  | 2026-03-01 | 2026-03-01 20:42 | 2026-03-13 | 2026-03-13 11:50 | 2026-03-16 |  | 2026-03-23 |  | 2026-03-30 |  | 2026-04-06 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-18 | [5 empty] | 2026-03-24 |  | 2026-04-01 |  | 2026-04-02 |  |  |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 | [6 empty] | 2026-04-30 |  | 2026-05-09 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-12 |  |  |  | 2026-06-03 |  | 2026-06-05 |  | 2026-06-06 | [5 empty] | 2026-04-10 |  | 2026-03-19 |  | Unknown | 2026-03-01 | 2026-03-01 20:41 | 1641571 | 295482 | 0 | 0 | 0 | 0 | 1641571 | 295482 | 2026-03-13 11:41:13 +0530 | Saranya Thiyagarajan | DCM: Move in date - may end Â Budget - Property name -Â pelican Square direction - W facingÂ Â f to c = 9.6 Wooden shadesÂ +light colorsÂ yellow and green cx likes you use in wall conceptsÂ not looking for any beading designe Â GFÂ KITCHEN - LAMINATE FINSHÂ wooden texture laminateÂ dado tilesÂ 1000mm for fridgeÂ island kitchen concpetÂ 2w *3l loft + wall unitÂ L shapeÂ base unit - uÂ shapeÂ tall unit - optional Â crockery unitÂ - 750w * 1200h in kitchen Â Dinning areaÂ handwasg cabinet Â Living roomÂ Glass shutter for booksÂ Â bottom cabinet storageÂ 55" tvÂ book shelf with glass shutter no open cabinet 3 + 1 loung chair Â Â double height ceiling looking for traditional theme for big wallÂ mix of light color and brigt colorÂ option 2 -Â wall cladding bricks option 1 - paint + wallpaper Â Â BEDROOM 1 (GBR) Bay window seating with wardrobe and integrated study unitÂ Â Â Vanity cabinetÂ only bottom cabinet Â Â Bedroom 2 (MBR)Â l shape wardrobeÂ in dresser areaÂ dressing unitÂ - bottom storage 2ftÂ wall concept for bed opp wall Â Bedroom 1Â mostly for studyÂ f to 14ftÂ 8.6H Wooden Stair case with wardrobe Â Â Store roomÂ pooja unitÂ white laminateÂ marble slabeÂ suspended drawers Â Family/studyÂ any wall concpets ideasÂ | [6 empty] | 2026-03-24 |  | 2026-03-31
18680 | Turnkey | 2026-01-01 | Rajesh shah | kanchan Giri | MUM - GOR | Yes | Priyanka Patel |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1305715 | 9999 | 1305715 | 0 | 0 | 112 | 0 | 120573 | 130572 | 522286 | 522286 |  |  | 2026-03-01 | 2026-03-19 18:29 | 2026-03-22 | 2026-03-22 12:30 | 2026-04-02 | 2026-04-02 15:40 | 2026-04-09 |  | 2026-04-16 |  | 2026-04-23 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-03 |  | 2026-04-04 | [5 empty] | 2026-04-10 |  | 2026-04-18 |  | 2026-04-19 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 | [6 empty] | 2026-05-17 |  | 2026-05-26 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-29 |  |  |  | 2026-06-20 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-04-27 |  | 2026-04-05 |  | Unknown | 2026-03-01 | 2026-03-04 18:44 | 1106538 | 199176 | 0 | 0 | 0 | 0 | 1106538 | 199176 | [9 empty] | 2026-04-10 |  | 2026-04-17
18682 | Turnkey | 2026-01-01 | Neha Rajan | Lodha Bellagio | MUM - GOR | Yes | Sakshi Hire |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 2571062 | 9999 | 2571062 | 0 | 0 | 103 | 0 | 247107 | 257106 | 1115934 | 940915.2 |  |  | 2026-02-28 | 2026-03-04 11:27 | 2026-03-04 | 2026-03-04 11:38 | 2026-04-03 | 2026-04-03 17:36 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-02-28 | 2026-03-02 11:48 | 2187438 | 383623 | 0 | 0 | 0 | 0 | 2187438 | 383623 | 2026-03-04 11:30:05 +0530 | Sakshi Hire | powai property cx is banker and wife is in IT 6 peaople 3 adults 1 maid 1 special kid 1205 carpet area shoe rack near entry 20 pairs 6 seating dining with bench/ chairs tv unit 60" with sleek drw centre tableÂ windoq shifting in deck area deck area right side barÂ left workstation foldableÂ cook top flat double door fridgeÂ microwave & otg tall unit large sink in utility inside smaller utility and kitchn merged wm an ddryer 1 above one dish washer opp side on wm ac compre shifting towards living duct area hob on opp sideÂ chimney panel modular kitchen bed 2 son bed wardrobe loft bed 3 parents queen side bed puja wall mounted with seater in NE corner tv unit with ledge arm chair front to window MBR office table & chair in wb one corner for shoes king size bed with side table wb 1 shutter mirrorÂ shelf front on bed like book rack closed Â chair if possible mbr wc *door shifting towards leftÂ sink infront of door* living and dining fc opt wc 3 shower from ceiling janiter unit art deco & abstrct luxe moulding sofa wall texture paint dining area mbrÂ natural light bright and airy calm serene no wallpaper no prints memory wall in passage | [6 empty] | 2026-04-11 |  | 2026-04-18
18683 | Turnkey | 2026-01-01 | Skilled Fabricators (Prasad Vishwakarma) | Unique Vistas | MUM - Thane | Yes | Pragati Devasani | Anil Jagtap | Rachna Abhyankar | [5 empty] | Mustufa Sohagpurwala |  | Hold | Preproduction | Site Readiness 1 | 2101794 | 420359 | 2871348 | 0 | 0 | 2 | 87 | 0 | 0 | 892366 | 789069.2 |  |  | 2026-03-01 | 2026-03-05 12:16 | 2026-03-05 | 2026-03-05 13:18 | 2026-03-28 | 2026-03-31 11:09 | 2026-05-18 | 2026-05-19 13:22 | 2026-07-14 |  | 2026-07-21 |  | 2026-03-28 | 2026-03-30 16:41 | 2026-04-01 | 2026-04-06 19:53 | 2026-04-06 | 2026-04-08 11:09 | 2026-04-12 | 2026-04-12 12:51 |  |  |  |  | 2026-05-18 | 2026-05-18 19:01 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-07-25 |  | 2026-05-30 | 2026-05-17 19:17 | Site is Non-RTMI | 2026-03-01 | 2026-03-02 19:56 | 2433346 | 438002 | 0 | 0 | 0 | 0 | 2363457.2948 | 388875 | 2026-07-09 17:16:55 +0530 | Anil Jagtap | cx will receive the possession by July end (tentatively) | 2026-06-27 14:47:04 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-25 16:09:30 +0530 | Siddhi Chaphekar | Some Image was uploaded | 2026-05-20 | 2026-05-19 13:25 | 2026-07-15
18684 | Turnkey | 2026-01-01 | Rohit Goyal | mahavir spring | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | Asif Shaikh | Aditya Vikram | Murali S | Aryan Singh | Shailendra Mishra | Completed | Complete | Completed | 851036 | 851037 | 1242652 | 854693 | 851036 | 43 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-01 22:55 | 2026-03-08 | 2026-03-08 18:07 | 2026-03-11 | 2026-03-08 21:23 | 2026-03-14 | 2026-03-14 19:50 | 2026-03-19 | 2026-03-18 14:24 | 2026-03-24 | 2026-03-24 12:08 | 2026-03-08 | 2026-03-09 19:29 | 2026-03-09 | 2026-03-09 21:45 | 2026-03-09 | 2026-03-10 16:49 | 2026-03-14 | 2026-03-14 19:44 |  |  |  |  | 2026-03-17 | 2026-03-09 19:36 | 2026-03-19 | 2026-03-20 19:29 | 2026-03-21 | 2026-03-21 11:57 |  |  | 2026-03-25 | 2026-03-30 12:32 | 2026-03-29 | 2026-03-30 11:50 | 2026-03-31 | 2026-03-30 14:44 | 2026-03-31 | 2026-04-01 17:18 |  |  |  |  | 2026-04-08 18:06 | 2026-05-04 | 2026-04-30 22:18 | 2026-05-14 | 2026-05-12 22:41 | 2026-05-08 | 2026-05-01 17:28 | 2026-05-12 | 2026-05-14 12:35 | 2026-05-13 | 2026-05-16 12:45 | 2026-06-01 | 2026-05-31 15:07 |  |  | 2026-06-08 | 2026-06-02 20:43 | 2026-06-08 | 2026-06-02 20:45 | 2026-06-14 | 2026-06-02 20:51 |  |  |  |  | 2026-03-30 | 2026-04-01 18:56 | 2026-03-15 | 2026-03-14 19:47 | Site is RTMI | 2026-03-01 | 2026-03-01 22:38 | 1053095 | 189557 | 929009.805 | 154783 | 919306.8774 | 153167 | 919306.8774 | 153167 | 2026-05-31 14:58:57 +0530 | Asif Shaikh | Execution: Modular Completed .Debris Removed.DC -- 1st June.Pre Qc - 2nd June.Qc - 3rd June | 2026-05-24 18:26:09 +0530 | Asif Shaikh | Execution: Modular Start date -- 21st May.Modular end date - 5th juneDebris cleaning - 6th June.DC - 7th June.QC - 8th June | 2026-05-10 17:23:31 +0530 | Asif Shaikh | Dispatch Due: Site Is ready for dispatched. | 2026-03-15 | 2026-03-14 20:05 | 2026-03-19 | 2026-03-18 16:27
18685 | Turnkey | 2026-01-01 | Parikshit Betharia | Nms One 27 | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Foram Joshi |  | Hold | Preproduction | DEM2 | 1800183 | 360037 | 2432927 | 0 | 0 | 35 | 72 | 0 | 0 | 758303 | 681843.2 |  |  | 2026-03-01 | 2026-03-01 22:45 | 2026-03-06 | 2026-03-06 20:33 | 2026-03-09 | 2026-03-07 21:38 | 2026-03-30 | 2026-03-26 18:40 | 2027-08-01 |  | 2027-08-08 |  | 2026-03-07 | 2026-03-09 19:05 | 2026-03-08 | 2026-03-11 11:00 | 2026-03-11 | 2026-03-14 13:09 | 2026-03-18 | 2026-03-18 16:15 |  |  |  |  | 2026-03-26 | 2026-03-30 18:59 | 2027-08-03 |  | 2027-08-04 |  |  |  | 2027-08-11 |  | 2027-08-12 |  | 2027-08-13 |  | 2027-08-14 | [6 empty] | 2027-09-01 |  | 2027-09-10 |  | 2027-09-09 |  | 2027-09-10 |  | 2027-09-11 |  | 2027-09-13 |  |  |  | 2027-10-05 |  | 2027-10-07 |  | 2027-10-08 | [5 empty] | 2027-08-12 |  | 2026-03-19 | 2026-03-26 18:08 | Site is RTMI | 2026-03-01 | 2026-03-01 22:43 | 2061802 | 371124 | 0 | 0 | 0 | 0 | 1956155.4024 | 324180 | 2026-07-14 12:49:51 +0530 | Divya Rahangdale | The client will receive possession by August. | 2026-07-02 16:36:11 +0530 | Divya Rahangdale | Hold | 2026-06-11 16:32:37 +0530 | Shraddha Pansare | Possession delayed- expected July 1st week. | 2026-03-27 | 2026-03-26 18:44 | 2027-08-02 |  | Under Construction | 2026-04-01
18686 | Turnkey | 2026-01-01 | Uday Laxmanrao Durge | Mahavir Spring | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Faraz Soudagar | Aditya Vikram | Murali S | Saloni Chawan | Shailendra Mishra | Active | Preproduction | Procurement | 889749 | 553141 | 1617536 | 0 | 889749 | 5 | 53 | 0 | 0 | 0 | 336608 |  |  | 2026-03-01 | 2026-03-02 20:11 | 2026-03-05 | 2026-03-30 15:40 | 2026-04-02 | 2026-03-30 15:46 | 2026-05-07 | 2026-05-07 16:49 | 2026-06-11 | 2026-06-14 15:33 | 2026-06-20 | 2026-06-20 15:40 | 2026-03-30 | 2026-03-30 19:22 | 2026-03-31 | 2026-03-31 16:44 | 2026-03-31 | 2026-03-31 17:51 | 2026-04-09 | 2026-04-09 12:22 |  |  |  |  | 2026-06-20 | 2026-04-22 16:51 | 2026-06-18 | 2026-06-19 11:16 | 2026-06-20 | 2026-06-19 17:11 |  |  | 2026-06-25 | 2026-06-26 18:23 | 2026-06-27 | 2026-06-27 15:21 | 2026-06-28 | 2026-06-27 19:18 | 2026-06-28 | 2026-06-28 12:23 |  |  |  |  | 2026-07-10 14:26 | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-27 | 2026-07-03 18:16 | 2026-06-15 | 2026-05-07 16:28 | Site is Non-RTMI | 2026-03-01 | 2026-03-02 20:09 | 1370794 | 246742 | 0 | 0 | 1007470.1308 | 177517 | 1007470.1308 | 177517 | 2026-07-12 13:47:16 +0530 | Faraz Soudagar | Procurement: PI work - Only Floor covering | 2026-06-27 19:24:15 +0530 | Asavari Vare | Some Image was uploaded | 2026-04-16 12:45:22 +0530 | Anil Jagtap | cx will receive the possession by Mid of June | 2026-05-08 | 2026-05-07 18:36 | 2026-06-15 | 2026-06-17 19:37
18689 | Turnkey | 2026-01-01 | Anushree Gupta Kesari | Mahavir Spring | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Faraz Soudagar | Aditya Vikram | Murali S | Prashant Panigrahi | Shailendra Mishra | Active | Handover | Project Closure Pending | 1324705 | 1324705 | 1826392 | 1492008 | 1324705 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-04 11:01 | 2026-03-05 | 2026-03-06 11:31 | 2026-03-09 | 2026-03-06 15:08 | 2026-03-17 | 2026-03-17 17:22 | 2026-03-19 | 2026-03-22 16:52 | 2026-04-14 | 2026-04-14 21:15 | 2026-03-06 | 2026-03-06 20:38 | 2026-03-07 | 2026-03-06 22:48 | 2026-03-06 | 2026-03-09 13:50 | 2026-03-10 | 2026-03-10 19:15 |  |  |  |  | 2026-03-18 | 2026-03-16 18:25 | 2026-04-02 | 2026-04-04 20:30 | 2026-04-05 | 2026-04-06 11:42 |  |  | 2026-04-16 | 2026-04-21 17:18 | 2026-04-21 | 2026-04-21 18:00 | 2026-04-22 | 2026-04-21 19:15 | 2026-04-23 | 2026-04-23 19:46 |  |  |  |  | 2026-04-25 12:26 | 2026-05-01 | 2026-04-30 22:28 | 2026-05-18 | 2026-05-16 18:18 | 2026-05-17 | 2026-05-19 17:40 | 2026-05-16 | 2026-05-22 11:20 | 2026-05-22 | 2026-05-28 13:55 | 2026-05-30 | 2026-06-16 13:37 |  |  | 2026-07-05 | 2026-06-30 09:33 | 2026-07-07 | 2026-06-30 09:36 | 2026-07-08 | 2026-06-30 09:43 |  |  |  |  | 2026-04-21 | 2026-04-21 19:43 | 2026-03-11 | 2026-03-13 13:15 | Site is RTMI | 2026-03-01 | 2026-03-04 11:01 | 1547790 | 278602 | 1546807.473 | 261153 | 1440770.1952 | 243260 | 1440770.1952 | 243260 | 2026-07-13 13:58:48 +0530 | Faraz Soudagar | Project Closure Pending: Initial ETA 11th July Aristo shutte not ready Aristo shutter revised ETA - 16th July Project closure - 16th July | 2026-06-23 22:42:08 +0530 | Faraz Soudagar | Execution: Modular installation done, profile shutter delayed. Installation ETA - 24th June deep cleaning ETA - 24th June QC - 25th June HO - 25th June | 2026-06-01 14:48:29 +0530 | Faraz Soudagar | Execution: Modular delivery done - 29th May installation start date - 1st June | 2026-03-18 | 2026-03-17 17:24 | 2026-03-23 | 2026-03-22 16:55
18690 | Turnkey | 2026-01-01 | Sajan Thomas Mathew mathew | Lodha Amara | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Tanveer Patel | Akshat Shrivastava | Murali S | Prashant Panigrahi | Shailendra Mishra | Active | Installation | Execution | 1082299 | 1082299 | 1430025 | 0 | 1082299 | 15 | 30 | 0 | 0 | 0 | 0 |  |  | 2026-02-28 | 2026-03-11 14:37 | 2026-03-13 | 2026-03-13 20:14 | 2026-03-16 | 2026-03-14 20:09 | 2026-04-04 | 2026-04-03 12:47 | 2026-05-11 | 2026-05-10 11:51 | 2026-05-11 | 2026-05-11 21:13 | 2026-03-14 | 2026-03-17 18:38 | 2026-03-15 | 2026-03-18 22:10 | 2026-03-18 | 2026-03-20 11:13 | 2026-03-25 | 2026-03-25 13:09 |  |  |  |  | 2026-03-31 | 2026-03-31 12:12 | 2026-05-16 | 2026-05-11 09:56 | 2026-05-12 | 2026-05-11 09:56 |  |  | 2026-05-13 | 2026-05-17 18:36 | 2026-05-19 | 2026-05-19 12:24 | 2026-05-20 | 2026-05-19 20:22 | 2026-05-20 | 2026-05-21 18:55 |  |  |  |  | 2026-05-25 12:46 | 2026-06-03 | 2026-06-03 22:00 | 2026-06-26 | 2026-06-24 21:25 | 2026-06-25 | 2026-06-25 18:17 | 2026-06-24 | 2026-06-27 12:33 | 2026-06-29 | 2026-06-30 00:32 | 2026-06-30 | 2026-07-11 13:34 |  |  | 2026-06-25 |  | 2026-07-09 |  | 2026-07-21 | [5 empty] | 2026-05-19 | 2026-05-25 12:45 | 2026-04-15 | 2026-04-02 13:45 | Site is Non-RTMI | 2026-02-28 | 2026-03-04 18:26 | 1211886 | 218139 | 0 | 0 | 1199858.495 | 198125 | 1199858.495 | 198125 | 2026-07-13 14:17:44 +0530 | Tanveer Patel | Execution: Libra pending Knobs pending Profile shutter | 2026-07-01 23:50:48 +0530 | Tanveer Patel | DDM1:Material delivered on 29th June Team is not yet aligned | 2026-06-22 23:25:35 +0530 | Tanveer Patel | Procurement: Floor protection done on 13 JuneMaterial ready for dispatch on 25th June | 2026-04-04 | 2026-04-03 12:53 | 2026-05-11 | 2026-05-10 12:03
18691 | Turnkey | 2026-01-01 | Anila Nair |  | MUM - Thane | No Estimate | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-02 | 2026-03-02 14:49 | 2026-03-03 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-08 | [5 empty] | 2026-03-14 |  | 2026-03-22 |  | 2026-03-23 |  |  |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 | [6 empty] | 2026-04-20 |  | 2026-04-29 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-02 |  |  |  | 2026-05-24 |  | 2026-05-26 |  | 2026-05-27 | [5 empty] | 2026-03-31 |  | 2026-03-09 |  | Unknown | 2026-03-02 | 2026-03-02 14:47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-02 14:50:23 +0530 | Anant Giri | Some Image was uploaded | [6 empty] | 2026-03-14 |  | 2026-03-21
18692 | Turnkey | 2026-01-01 | Akshay Gothi | Regency Luxuria | MUM - Thane | Yes | Moksh Mehta | [7 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 925988 | 9999 | 0 | 0 | 0 | 131 | 0 | 82600 | 92599 | 370395 | 370395.2 |  |  | 2026-03-01 | 2026-03-06 11:16 | 2026-03-04 | 2026-03-06 17:17 | 2026-03-08 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-03-08 |  | 2026-03-09 |  | 2026-03-09 |  | 2026-03-10 | [5 empty] | 2026-03-16 |  | 2026-03-24 |  | 2026-03-25 |  |  |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-04 | [6 empty] | 2026-04-22 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-19 |  | 2026-06-21 |  | 2026-06-23 | [5 empty] | 2026-04-02 |  | 2026-03-11 |  | Unknown | 2026-03-01 | 2026-03-05 20:42 | 0 | 0 | 0 | 0 | 0 | 0 | 784736 | 141252 | 2026-03-04 21:14:18 +0530 | Moksh Mehta | DCM: Client Name:- Akshay Gothi Property:- Regency Luxuria Possesion Date:- Mar 26 Sq Ft:- 2147 sqft No of Members: - 3 couple (35+) + Uncle & Aunt (55+) + Mother (58+) + Grand Parents (80+) + Daughter (4 & 2) + Son (newborn) Budget: - 40-45L End to End Stretched budget. Ent: Shoe Rack (40 - 35 Pairs) Wall Concepts.Safety Door. Living Room :- TV Unit (55") with Display unit3 Seater Sofa + 1 Chair + 2 Seater (8 - 10 people)Wall concepts.Mandir Unit 3'x6'Seating area near informal seating in L-shape if possible Dining Area :- Crockery Unit.8 Seater Dining Table.Wall Concepts. Kitchen :- Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos.All generic appliances.Main Sink outside the kitchen Sink change possibilities to be checked in main kitchen Bedroom 2 :- Pranay Queen size Bed with StorageWardrobe with Loft & Utility Unit Side tale Some space for extra shoes racksMiscellaneous storage like Bags, books, etcSpace for TV Minimalistic Neutral Shades Bedroom 1:- Mother's & for Both the daughter's Queen Size Bed with StorageWardrobe with Loft & Utility Unit Side Table Folding Study Table / Fixed Study Table Bedroom 3 :- Sanchay Queen Size Bed with StorageWardrobe with loft & Utility UnitSide TableDresser Place for TV Design preference to play with rafter & Lighting to be given Bedroom 4 :- Uncle & Aunt Queen size Bed with storageWardrobe with LoftDresser with Side Table Bedroom 5:- Akshay Queen Size BedWardrobe with LoftAdditional Storage space for Dresser Study Room:- Grand Parents Single bed Wardrobe with Loft Bathroom's Base Vanity Unit's for allGlass Partition for all Master Bedroom's Passage:- Storage units in both the passage area units Misc:- False CeilingPaintingElectrification | [6 empty] | 2026-03-16 |  | 2026-03-23
18693 | Turnkey | 2026-01-01 | Shrutika Mane | swastik platinum | MUM - GOR | Yes | Anjali Jain | Manzoor Shaikh | Kashmira Nerurkar |  |  | suraj kumar | Aditya Vikram |  | Harshaan Tiku | Aakash Gaikwad | Active | Design | DEM3 | 825757 | 165152 | 1203571 | 0 | 0 | 1 | 64 | 0 | 0 | 351034 | 309571.2 |  |  | 2026-03-01 | 2026-03-04 18:37 | 2026-03-04 | 2026-03-04 18:40 | 2026-03-07 | 2026-03-04 19:08 | 2026-03-25 | 2026-03-25 16:39 | 2026-04-18 | 2026-04-18 15:57 | 2026-07-18 |  | 2026-03-04 | 2026-03-04 19:10 | 2026-03-05 | 2026-03-06 13:41 | 2026-03-06 | 2026-03-06 14:18 | 2026-03-08 | 2026-03-08 12:04 |  |  |  |  | 2026-03-25 | 2026-03-31 20:42 | 2026-07-15 | 2026-07-14 18:44 | 2026-07-15 | 2026-07-14 18:44 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-03-09 | 2026-03-25 16:12 | Site is RTMI | 2026-03-01 | 2026-03-04 18:36 | 1019976 | 183595 | 0 | 0 | 0 | 0 | 1004630.1736 | 169619 | 2026-05-03 12:14:13 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-28 13:01:12 +0530 | Anjali Jain | Some Image was uploaded | 2026-04-15 15:03:01 +0530 | Harshaan Tiku | Some Image was uploaded | 2026-03-26 | 2026-03-25 16:44 | 2026-04-19 | 2026-04-18 16:23 | Under Construction | 2026-05-01
18694 | Turnkey | 2026-01-01 | Shuaeb R. Khan | Pearl Castle | MUM - GOR | Yes | Khushi Khandelwal |  | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 1513777 | 9999 | 1513777 | 0 | 0 | 103 | 0 | 141379 | 151378 | 637995 | 573026.4 |  |  | 2026-03-02 | 2026-03-02 19:00 | 2026-03-02 | 2026-03-02 19:43 | 2026-03-11 | 2026-04-03 15:47 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-02 | 2026-03-02 18:54 | 1282862 | 230915 | 0 | 0 | 0 | 0 | 1282862 | 230915 | 2026-03-02 19:41:57 +0530 | Khushi Khandelwal | Some Image was uploaded | [6 empty] | 2026-04-11 |  | 2026-04-18
18698 | Turnkey | 2026-01-01 | Rajesh Srinivasan | Pelican square | BNG - HSR | No Estimate | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 133 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-01 | 2026-03-04 12:54 | 2026-03-02 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-03-01 | 2026-03-04 11:54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-23 |  | 2026-03-30
18699 | Turnkey | 2026-01-01 | Varsha | Walchand Paradise | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | Akash Jadhav | Sandeep Tiwari | Murali S | Nishtha Valawalkar | Shailendra Mishra | Active | Handover | Project Closure Pending | 1263358 | 1204788 | 1301993 | 0 | 1263358 | 18 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-04 | 2026-03-04 13:14 | 2026-03-05 | 2026-03-05 17:34 | 2026-03-08 | 2026-03-07 22:31 | 2026-03-19 | 2026-03-19 18:16 | 2026-03-26 | 2026-03-29 15:53 | 2026-04-09 | 2026-04-09 11:58 | 2026-03-07 | 2026-03-09 19:17 | 2026-03-08 | 2026-03-10 10:54 | 2026-03-10 | 2026-03-12 12:01 | 2026-03-17 | 2026-03-17 17:58 |  |  |  |  | 2026-03-19 | 2026-03-20 22:20 | 2026-03-28 | 2026-03-27 11:51 | 2026-03-28 | 2026-03-27 17:47 |  |  | 2026-04-15 | 2026-04-18 15:46 | 2026-04-19 | 2026-04-19 18:13 | 2026-04-20 | 2026-04-19 19:24 | 2026-04-23 | 2026-04-21 19:16 |  |  |  |  | 2026-04-22 13:20 | 2026-05-04 | 2026-05-05 21:04 | 2026-05-22 | 2026-05-16 19:39 | 2026-05-17 | 2026-05-21 18:33 | 2026-05-16 | 2026-05-26 16:48 | 2026-05-27 | 2026-05-29 18:15 | 2026-06-15 | 2026-06-15 10:45 |  |  | 2026-06-24 | 2026-06-27 22:30 | 2026-06-26 | 2026-06-27 22:40 | 2026-06-27 | 2026-06-27 22:51 |  |  |  |  | 2026-04-19 | 2026-04-21 18:30 | 2026-03-18 | 2026-03-18 20:58 | Site is RTMI | 2026-03-04 | 2026-03-04 13:11 | 1438022.2888 | 232168 | 0 | 0 | 1430069.5629 | 230851 | 1430069.5629 | 230851 | 2026-06-15 13:30:02 +0530 | Akash Jadhav | Execution: Per QC : 14th June QC : 15th June Site handover : 16th June Blocker : glass and hardware not received | 2026-06-07 23:59:15 +0530 | Akash Jadhav | Execution: Main load recived at site 29th may Modular installation done till 8th June Final Painting In progress 7th June to 10th June Cleaning : 11th June Per Qc : 11th June Qc : 12th June Site handover : 16th June Blocker : Day 4 Profile shutter | 2026-06-02 23:08:59 +0530 | Akash Jadhav | Execution: Main load deliver on site at 30th may Modular installation work in progress | 2026-03-20 | 2026-03-19 18:24 | 2026-03-30 | 2026-03-29 15:54
18702 | Turnkey | 2026-01-01 | Harindranath k | independent house | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Raghavendra S |  | Active | Design | DEM1 | 725859 | 79999 | 725859 | 0 | 0 | 99 | 0 | 0 | 65173 | 290344 | 290343.6 |  |  | 2026-03-04 | 2026-03-15 11:18 | 2026-03-27 | 2026-03-27 14:39 | 2026-03-30 | 2026-03-27 14:53 | 2026-08-05 |  | 2026-08-12 |  | 2026-08-19 |  | 2026-03-27 | 2026-03-31 | 2026-03-28 | 2026-04-07 12:28 | 2026-04-07 | 2026-04-07 15:00 | 2026-04-13 | 2026-04-13 09:07 |  |  |  |  | 2026-08-06 |  | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-08-01 |  | Unknown | 2026-03-04 | 2026-03-13 12:51 | 734468.0875 | 126741 | 0 | 0 | 0 | 0 | 734468.0875 | 126741 | 2026-07-14 23:08:08 +0530 | Rajeshwari S | Its a renovation project Client budget was coming below 7 lacs as his architect informed him not to demolish the kitchen as the building condition is not strong. Client wanted to cancel and get the work done only for what he paid. But informed about cancellation policy and convince him to get the work done as per his initial requirement. Client agreed and wanted to schedule the meeting. Post that client not responding to calls and wats app messages to schedule the meeting. | 2026-07-14 17:23:48 +0530 | Rajeshwari S | Client not paid 10% yet. not visiting office for 1st Design meeting. Renovation project.Â Client scope of work reduced below 7 lacs as client Architect has instructed not to demolish the internals now.Â Client agreed for going ahead with present price - not responding to calls as he is not in country.Â Could not place on hold as 10% not received.Â | 2026-06-24 16:04:00 +0530 | Priyanka R | Some Image was uploaded | 2026-08-06 |  | 2026-08-13 |  | RTMI
18703 | Turnkey | 2026-01-01 | Praveen | BUILDER FLOOR | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Ruthwik S K | Ranjith Kumar | Murali S | Kushal S | Vishwa Hiremath | Active | Production | 100% Payment | 1117661 | 670597 | 1287651 | 0 | 1117661 | 2 | 5 | 0 | 0 | 0 | 447064 |  |  | 2026-03-04 | 2026-03-10 11:38 | 2026-03-10 | 2026-03-10 11:46 | 2026-03-10 | 2026-03-10 12:01 | 2026-04-29 | 2026-04-28 19:09 | 2026-05-23 | 2026-05-26 10:51 | 2026-06-13 | 2026-06-12 14:31 | 2026-03-10 | 2026-03-11 18:26 | 2026-03-11 | 2026-03-12 10:44 | 2026-03-12 | 2026-03-12 16:07 | 2026-03-20 | 2026-03-20 22:51 |  |  |  |  | 2026-05-10 | 2026-05-20 11:27 | 2026-05-27 | 2026-05-29 01:52 | 2026-05-30 | 2026-05-29 19:04 |  |  | 2026-06-16 | 2026-06-17 18:35 | 2026-06-18 | 2026-06-18 18:04 | 2026-06-19 | 2026-06-22 06:43 | 2026-06-23 | 2026-07-03 16:43 |  |  |  |  | 2026-07-05 14:13 | 2026-07-10 | 2026-07-09 20:44 | 2026-07-13 | 2026-07-13 14:14 | 2026-07-12 |  | 2026-07-13 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-18 | 2026-07-03 18:07 | 2026-03-21 | 2026-04-28 18:59 | Site is RTMI | 2026-03-04 | 2026-03-10 11:35 | 1091230 | 196421 | 0 | 0 | 1217321.5761 | 200999 | 1217321.5761 | 200999 | 2026-07-06 15:05:54 +0530 | Ranjith Kumar | Bonito Side Floor Covering only Cx Side - Electrical, False Ceiling | 2026-04-28 18:55:39 +0530 | Rhea Rathod | DDM1: Minutes of Meeting held on Date: 25/04/2026 Attendees: Rhea, Praveen, Geetha Discussion: LIVING AREA- -Rafters added -Open Tall unit forÂ TV unit KITCHEN- -Loft removed -Tall unit to incorporate Microwave -Top unit to be added in the utility DINING AREA- -Crockery unit - to be removed -Wall concept to be designed as per shared reference MASTER BEDROOM- -Bed to be positioned in the niche areaÂ - Existing bed -Wall concept yet to be decided -Wardrobe - sliding wardrobe in place of the study unit -Study unit - Foldable along with fixed ledge for tv unit MASTER BEDROOM - BATHROOM- -Vanity unit added DAUGHTER'S BEDROOM- -Loft to be added DAUGHTER'S BEDROOM - BATHROOM- -Vanity Unit added SON'S BEDROOM- -One doubleÂ door wardrobe and one single door wardrobe with loft -Mirror and ledge to be added for dresser COMMON BATHROOM -Vanity unit added Note - Wall concepts need to be finalised as per shared references | 2026-04-22 18:59:53 +0530 | Rajeshwari S | Client is visiting on 25th April for DEM and layout finalization Payment will be done on closure. | 2026-04-29 | 2026-04-28 19:21 | 2026-05-27 | 2026-05-26 10:52 | Under Construction | 2026-06-30
18705 | Turnkey | 2026-01-01 | Divya shah | Mesacon Greens | MUM - GOR | Yes | Yash Jain |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1326741 | 9999 | 1326741 | 0 | 0 | 103 | 0 | 122675 | 132674 | 561753 | 499639.6 |  |  | 2026-03-04 | 2026-03-26 14:04 | 2026-03-05 | 2026-04-03 12:05 | 2026-04-03 | 2026-04-03 16:01 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-04 | 2026-03-05 13:25 | 1124356 | 202384 | 0 | 0 | 0 | 0 | 1124356 | 202384 | 2026-04-15 13:59:51 +0530 | Sahil Sethi | Some Image was uploaded | 2026-04-03 12:05:24 +0530 | Priyanka Patel | DCM: 1. Name of the customer 2. Profession 3. Project Name/Tower Name/Flat Number 4. Typology (1BHK, 2BHK, 3BHK, etc) 2 BHK 5. Site Access Date 6. Possession Date 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 8 Customer Preferences8. Who will be living in the house? 9. What activities do you usually prefer at your home ? 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials 15. Do you have any existing furniture that must be accommodated? 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? 2. Must-have furniture or features? 3. Choose your decor inspirations 4. False ceiling required Dining & Kitchen1. Any special furniture? 2. Must-have appliances? 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type 2. Master Bedroom - Wardrobe style 3. Master Bedroom - Additional units 4. False Ceiling Required - Master Bedroom 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 800000 |  |  |  | 2026-04-11 |  | 2026-04-18
18706 | Turnkey | 2026-01-01 | Rajat Dey | Samhita Serene Mtb | BNG - HRBR | Yes |  | Rajeshwari S | Shibin Lal | [7 empty] | Hold | Design | 20% Payment | 921265 | 102599 | 1026114 | 0 | 0 | 29 | 70 | 0 | 81654 | 377610 | 359402.4 |  |  | 2026-03-01 | 2026-03-10 11:57 | 2026-03-08 | 2026-03-10 12:02 | 2026-03-13 | 2026-03-10 12:11 | 2026-04-11 | 2026-04-07 13:46 | 2027-02-05 |  | 2027-02-12 |  | 2026-03-10 | 2026-03-12 12:14 | 2026-03-11 | 2026-03-20 11:18 | 2026-03-20 | 2026-03-20 16:47 | 2026-03-22 | 2026-03-22 12:58 |  |  |  |  | 2026-09-30 |  | 2027-02-07 |  | 2027-02-08 |  |  |  | 2027-02-15 |  | 2027-02-16 |  | 2027-02-17 |  | 2027-02-18 | [6 empty] | 2027-03-08 |  | 2027-03-17 |  | 2027-03-16 |  | 2027-03-17 |  | 2027-03-18 |  | 2027-03-20 |  |  |  | 2027-04-11 |  | 2027-04-13 |  | 2027-04-14 | [5 empty] | 2027-02-16 |  | 2026-03-23 | 2026-04-07 13:42 | Site is RTMI | 2026-03-01 | 2026-03-08 12:58 | 869588 | 156525 | 0 | 0 | 0 | 0 | 1017579.7489 | 172565 | 2026-03-22 13:02:07 +0530 | Rajeshwari S | Call done along with designer Possession - March end 2026 Has permission for IM. Will schedule the same and confirm to client. 1 DD is schedule on 23rd March 2026 Payment will be done after layout fialization. (After 1st meeting) Estimation finalized for Rs.7,83,393/- Post offers | 2026-03-20 16:46:38 +0530 | Bency Chacko | Possession - March end 2026 IMs can be taken Design fees - 30th March 2026 No on-site work is planned B2C - Self-funded Agreement terms are cleared Checklist cleared The scope of work is clear Timelines are cleared | 2026-03-20 14:44:39 +0530 | Bency Chacko |  | 2026-04-08 | 2026-04-07 13:48 | 2027-02-06 |  | Under Construction | 2026-03-31
18709 | Turnkey | 2026-01-01 | Mukesh Kurlawala care | Nice | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Avi Thakkar |  | Hold | Preproduction | Site Readiness 1 | 1211812 | 242362 | 2004351 | 0 | 0 | 1 | 88 | 0 | 0 | 528090 | 441360.4 |  |  | 2026-03-04 | 2026-03-11 11:23 | 2026-03-08 | 2026-03-11 15:53 | 2026-03-11 | 2026-03-11 15:58 | 2026-04-07 | 2026-04-07 16:46 | 2026-07-06 |  | 2026-07-13 |  | 2026-03-11 | 2026-03-17 19:44 | 2026-03-12 | 2026-03-18 11:35 | 2026-03-18 | 2026-03-18 17:02 | 2026-03-31 | 2026-03-31 17:32 |  |  |  |  | 2026-04-22 | 2026-04-22 21:06 | 2026-07-08 |  | 2026-07-09 |  |  |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 | [6 empty] | 2026-08-06 |  | 2026-08-15 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-12 | [5 empty] | 2026-07-17 |  | 2026-04-01 | 2026-04-07 16:11 | Site is Non-RTMI | 2026-03-04 | 2026-03-08 13:50 | 1698602 | 305748 | 0 | 0 | 0 | 0 | 1367019.6737 | 230615 | 2026-06-03 18:40:30 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-23 11:28:45 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-21 16:33:18 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-08 | 2026-04-07 16:57 | 2026-07-07
18710 | Turnkey | 2026-01-01 | Pranav Ghate | Rohan Ekanta | BNG - HSR | Yes | Nayan Reddy | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 1529054 | 9999 | 0 | 0 | 0 | 132 | 0 | 142906 | 152905 | 611622 | 611621.6 |  |  | 2026-03-05 | 2026-03-05 13:25 | 2026-03-06 |  | 2026-03-06 |  | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-03-06 |  | 2026-03-07 |  | 2026-03-07 |  | 2026-03-08 | [5 empty] | 2026-03-14 |  | 2026-03-22 |  | 2026-03-23 |  |  |  | 2026-03-30 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 | [6 empty] | 2026-04-20 |  | 2026-04-29 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-02 |  |  |  | 2026-05-24 |  | 2026-05-26 |  | 2026-05-27 | [5 empty] | 2026-03-31 |  | 2026-03-09 |  | Unknown | 2026-03-05 | 2026-03-05 13:24 | 0 | 0 | 0 | 0 | 0 | 0 | 1295809 | 233245 | [9 empty] | 2026-03-14 |  | 2026-03-21
18711 | Sub Project |  | Rahul Jiwane | piramal vaikunth | MUM - Thane |  | Naved Malik | Divya Rahangdale | Sneha Kadam |  |  | Vinay Bulani | Aditya Vikram | Murali S |  | Aakash Gaikwad | Active | Installation | Execution | 4964 | 5000 | 0 | 0 | 20964 | 90 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-05 | 2026-03-06 12:12 | 2026-03-06 | 2026-03-06 12:12 | 2026-03-06 | 2026-03-06 12:13 | 2026-03-07 | 2026-03-06 12:14 | 2026-03-07 | 2026-03-06 12:15 | 2026-03-07 | 2026-03-06 12:16 | 2026-03-06 | 2026-03-06 12:13 | 2026-03-07 | 2026-03-06 12:13 | 2026-03-06 | 2026-03-06 12:13 | 2026-03-07 | 2026-03-06 12:13 |  |  |  |  | 2026-03-06 | 2026-03-06 12:14 | 2026-03-07 | 2026-03-06 12:15 | 2026-03-07 | 2026-03-06 12:16 |  |  | 2026-03-07 | 2026-03-07 17:22 | 2026-03-08 | 2026-03-10 12:44 | 2026-03-11 | 2026-03-10 18:13 | 2026-03-11 | 2026-03-10 18:13 |  |  |  |  | 2026-03-12 19:05 | 2026-03-15 | 2026-03-14 22:34 | 2026-03-18 | 2026-03-16 16:22 | 2026-03-17 | 2026-04-11 19:10 | 2026-03-16 | 2026-04-14 22:03 | 2026-04-14 | 2026-04-16 13:04 | 2026-04-18 | 2026-05-23 19:13 |  |  | 2026-04-06 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-03-10 | 2026-03-12 19:04 | 2026-03-07 | 2026-03-06 12:13 | Unknown | 2026-03-05 | 2026-03-06 12:12 | 0 | 0 | 0 | 0 | 17766 | 3197 | 17766 | 3197 | [9 empty] | 2026-03-07 | 2026-03-06 12:14 | 2026-03-07 | 2026-03-06 12:15
18714 | Turnkey | 2026-01-01 | ASHOK pariawala | Ekta medaw | MUM - GOR | Yes | Neha Yadav | Reshma Melanta | Safalta Karkera | [6 empty] | Vinay Surve | Hold | Design | DEM3 | 2171875 | 335619 | 2116078 | 0 | 0 | 0 | 85 | 0 | 0 | 1080311 | 755944.8 |  |  | 2026-03-05 | 2026-03-05 17:30 | 2026-03-07 | 2026-03-07 15:29 | 2026-03-12 | 2026-03-12 20:06 | 2026-03-31 | 2026-03-31 14:52 | 2026-04-18 | 2026-04-17 12:38 | 2026-10-02 |  | 2026-03-12 | 2026-03-13 12:54 | 2026-03-13 | 2026-03-13 13:48 | 2026-03-13 | 2026-03-14 10:53 | 2026-03-18 | 2026-03-18 16:23 |  |  |  |  | 2026-03-31 | 2026-04-15 18:52 | 2026-08-01 | 2026-04-30 12:39 | 2026-05-01 | 2026-04-30 12:39 |  |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-08 | [6 empty] | 2026-10-26 |  | 2026-11-04 |  | 2026-11-03 |  | 2026-11-04 |  | 2026-11-05 |  | 2026-11-07 |  |  |  | 2026-11-29 |  | 2026-12-01 |  | 2026-12-02 | [5 empty] | 2026-10-06 |  | 2026-03-19 | 2026-03-30 15:30 | Site is RTMI | 2026-03-05 | 2026-03-05 17:12 | 1793286 | 322791 | 0 | 0 | 0 | 0 | 2273604.6311 | 392320 | 2026-05-24 11:41:35 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-21 17:34:50 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-14 17:55:49 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-01 | 2026-03-31 14:54 | 2026-04-18 | 2026-04-17 12:40 | RTMI
18715 | Turnkey | 2026-01-01 | keyur Gandhi | labh sapphire | MUM - GOR | Yes | Sweta Bhise |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | DCM Due | 3092430 | 9999 | 0 | 0 | 0 | 132 | 0 | 299244 | 309243 | 1309969 | 1163974.8 |  |  | 2026-03-05 | 2026-03-05 17:34 | 2026-03-06 | 2026-03-07 11:52 | 2026-03-18 |  | 2026-03-17 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-03-10 |  | 2026-03-11 |  | 2026-03-11 |  | 2026-03-12 | [5 empty] | 2026-03-18 |  | 2026-03-26 |  | 2026-03-27 |  |  |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-06 | [6 empty] | 2026-04-24 |  | 2026-05-03 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-06 |  |  |  | 2026-05-28 |  | 2026-05-30 |  | 2026-05-31 | [5 empty] | 2026-04-04 |  | 2026-03-13 |  | Unknown | 2026-03-05 | 2026-03-05 17:33 | 0 | 0 | 0 | 0 | 0 | 0 | 2622990 | 469439 | 2026-04-15 16:59:56 +0530 | Umang Shah | Some Image was uploaded | 2026-04-08 11:12:59 +0530 | Meet Shah | Some Image was uploaded | 2026-04-08 11:05:29 +0530 | Meet Shah | Some Image was uploaded | 2026-03-18 |  | 2026-03-25
18716 | Turnkey | 2026-01-01 | Shekar | SPN Pride | BNG - HRBR | Yes | Sanjay Kulkarni | Rajeshwari S | Surabhi Ravichandran | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Harshit Choudhary | Saddam Hussain Z M | Murali S | Mohammed Rasick | Vishwa Hiremath | Active | Handover | Project Closure Pending | 1366223 | 1366227 | 1546969 | 1366135 | 1366223 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-05 | 2026-03-05 19:07 | 2026-03-17 | 2026-03-17 16:42 | 2026-03-18 | 2026-03-19 11:37 | 2026-04-11 | 2026-04-07 16:26 | 2026-04-15 | 2026-04-14 12:04 | 2026-04-27 | 2026-04-25 11:30 | 2026-03-15 | 2026-03-17 18:20 | 2026-03-21 | 2026-03-17 18:52 | 2026-03-19 | 2026-03-18 17:49 | 2026-03-21 | 2026-03-20 23:02 |  |  |  |  | 2026-04-07 | 2026-04-11 13:59 | 2026-04-15 | 2026-04-22 02:22 | 2026-04-23 | 2026-04-22 02:22 |  |  | 2026-04-26 | 2026-04-26 18:55 | 2026-04-27 | 2026-04-27 19:54 | 2026-04-28 | 2026-04-28 18:50 | 2026-04-29 | 2026-04-30 19:11 |  |  |  |  | 2026-05-02 12:11 | 2026-05-14 | 2026-05-13 21:32 | 2026-05-28 | 2026-05-25 18:38 | 2026-05-25 | 2026-05-25 18:36 | 2026-05-25 | 2026-05-26 16:38 | 2026-05-26 | 2026-05-26 17:38 | 2026-05-31 | 2026-05-31 11:16 |  |  | 2026-06-30 | 2026-06-30 20:20 | 2026-07-05 | 2026-06-30 21:30 | 2026-07-06 | 2026-06-30 23:24 |  |  |  |  | 2026-04-27 | 2026-05-02 11:20 | 2026-03-21 | 2026-04-07 11:01 | Site is RTMI | 2026-03-05 | 2026-03-05 18:59 | 1310991 | 235978 | 1402140.639 | 241952 | 1402217.8625 | 241966 | 1402217.8625 | 241966 | 2026-07-07 00:52:24 +0530 | Saddam Hussain Z M | Execution: Wallpaper installation pending due to client dependency work, ETA 21st July | 2026-07-05 22:41:36 +0530 | Saddam Hussain Z M | Execution: Wallpaper installation pending due to client dependency work, ETA 21st July | 2026-06-15 11:43:35 +0530 | Saddam Hussain Z M | Some Image was uploaded | 2026-04-08 | 2026-04-07 16:28 | 2026-04-15 | 2026-04-14 12:05 | RTMI
18717 | Turnkey | 2026-01-01 | Nawin Kumar Singh | Warrior Central Bay | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar |  |  |  | Shashank Singh | Vishwa Hiremath | Active | Design | 60% Payment | 1097601 | 208667 | 1321526 | 1340049 | 1097601 | 15 | 12 | 0 | 0 | 451883 | 437050.8 |  |  | 2026-02-28 | 2026-03-23 15:48 | 2026-03-10 | 2026-03-24 12:45 | 2026-03-27 | 2026-03-25 10:45 | 2026-07-29 | 2026-05-10 18:27 | 2026-06-21 | 2026-06-20 18:53 | 2026-06-25 | 2026-06-25 15:36 | 2026-03-25 | 2026-03-26 19:55 | 2026-03-26 | 2026-03-26 20:14 | 2026-03-26 | 2026-03-27 16:50 | 2026-03-31 | 2026-03-31 20:02 |  |  |  |  | 2026-06-05 | 2026-06-13 17:18 | 2026-06-21 | 2026-06-23 20:52 | 2026-06-24 | 2026-06-23 23:36 |  |  | 2026-06-26 | 2026-06-29 17:12 | 2026-06-29 | 2026-06-29 19:44 | 2026-06-30 | 2026-06-30 12:01 | 2026-07-01 | [6 empty] | 2026-07-19 |  | 2026-07-28 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-31 |  |  |  | 2026-08-22 |  | 2026-08-24 |  | 2026-08-25 | [5 empty] | 2026-06-29 |  | 2026-07-25 | 2026-05-10 18:23 | Site is RTMI | 2026-02-28 | 2026-03-13 17:54 | 1119937 | 201588 | 1385787.94 | 228821 | 1124831.947 | 185735 | 1124831.947 | 185735 | 2026-06-02 19:34:35 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-26 17:12:52 +0530 | Shivani Shet | DDM2: 24 May 18717 - Nawin Kumar Singh MOM Living Room / TV UnitÂ Â Â Â Â Â Plan a Sitting Pooja unit on east wall Â Â Â Â Â Â Tv unit Â with tall unit for storage Â Â Â Â Â Â Crockery unit with vanity add glass wall units and mirror KitchenÂ Â Â Â Â Â No changes Master Bedroom (MBR)Â Â Â Â Â Â No changes Son s Bedroom (SBR)Â Â Â Â Â Â Plan for study table5 Â Â Â Â Â Â Wardrobe and dresser unit Daughter s Bedroom (DBR)Â Â Â Â Â Â Plan for D shape mirror Â Â Â Â Â Â Remaining all Wardrobe with end to end wall Â Â Â Â Â Â Â | 2026-05-26 17:05:45 +0530 | Shivani Shet | DDM1: First meeting - 10 May 18717 - Nawin Kumar Singh MOM Living Room / TV UnitÂ Â Â Â Â Â Plan a Sitting Pooja unit on east wall with sofa on left Â Â Â Â Â Â Tv unit Â Â Â Â Â Â Balcony design Â Â Â Â Â Â Place for designing for Talwar Â Â Â Â Â Â Crockery unit with vanity KitchenÂ Â Â Â Â Â L shape kitchen to be considered Â Â Â Â Â Â Loft end to end Â Â Â Â Â Â Â Cylinder space is considered blind corner Â Â Â Â Â Â Existing ro new Â Â Â Â Â Â As per site condition either L shape or U shape Master Bedroom (MBR)Â Â Â Â Â Â Wardrobe and dresser unit Son s Bedroom (SBR)Â Â Â Â Â Â Plan for study table Â Â Â Â Â Â Wardrobe and dresser unit Daughter s Bedroom (DBR)Â Â Â Â Â Â Plan for study table Â Â Â Â Â Â Wardrobe and dresser unit Â Â Â Â Â Â Â | 2026-05-11 | 2026-05-10 18:30 | 2026-06-21 | 2026-06-20 19:50 | RTMI
18719 | Turnkey | 2026-01-01 | Vijay | Samhita Serene Mtb | BNG - HRBR | Yes | Alekhya Korada | Rajeshwari S | Yogesh Patidar | [5 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1645697 | 9999 | 1645697 | 0 | 0 | 84 | 0 | 154571 | 164570 | 658279 | 658278.8 |  |  | 2026-03-06 | 2026-03-06 21:25 | 2026-03-20 | 2026-03-20 19:17 | 2026-03-23 | 2026-04-22 12:43 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-06 | 2026-03-06 12:34 | 1749439.4423 | 288874 | 0 | 0 | 0 | 0 | 1749439.4423 | 288874 | 2026-03-20 19:50:24 +0530 | Alekhya Korada | Some Image was uploaded | [6 empty] | 2026-04-30 |  | 2026-05-07
18722 | Turnkey | 2026-01-01 | Srinivasa Deshikan | Adarsh Palm Retreat | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  | Sethuragavan R | Affaan Abdulla | Jairam Joshi | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Active | Production | Production | 1386176 | 870196 | 1453835 | 0 | 1386176 | 6 | 0 | 0 | 0 | 0 | 515980 |  |  | 2026-03-06 | 2026-03-06 13:34 | 2026-03-13 | 2026-03-13 13:50 | 2026-03-17 | 2026-03-17 11:34 | 2026-05-10 | 2026-05-10 16:13 | 2026-06-17 | 2026-06-16 16:24 | 2026-06-28 | 2026-06-28 12:41 | 2026-03-17 | 2026-03-17 19:03 | 2026-03-18 | 2026-03-18 12:49 | 2026-03-18 | 2026-03-18 13:45 | 2026-03-25 | 2026-03-25 17:26 |  |  |  |  | 2026-05-10 | 2026-05-11 13:53 | 2026-06-25 | 2026-06-25 13:37 | 2026-06-26 | 2026-06-25 13:38 |  |  | 2026-06-29 | 2026-06-30 18:17 | 2026-06-30 | 2026-06-30 19:12 | 2026-07-01 | 2026-06-30 19:34 | 2026-07-01 | 2026-07-02 11:16 |  |  |  |  | 2026-07-04 17:58 | 2026-07-10 | 2026-07-09 20:43 | 2026-07-18 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-30 | 2026-07-04 01:45 | 2026-04-06 | 2026-04-23 16:44 | Site is RTMI | 2026-03-06 | 2026-03-06 13:33 | 1232064 | 221771 | 0 | 0 | 1520821.992 | 251111 | 1520821.992 | 251111 | 2026-07-13 15:27:03 +0530 | Jairam Joshi | Procurement: Key - 13th FC- 14th False cieling and ele work - 21st SRD 22nd July | 2026-07-08 19:06:41 +0530 | Jairam Joshi | Procurement: Key - 9th July FC- 10th False cieling and ele work - 20th SRD 21st July | 2026-06-04 15:52:32 +0530 | Manoj Kumar R | MOM - 22-05-2026 FoyerÂ wallpaper retain same, Base unit & seater to be redesign. Tv unit Console tv unit to be plan Beading with wallpaper to be plan for tv unit wall check for tall unit Pooja unit 3' Pocket door with cnc shutter internal ledges to be considered crockery aluminium frame glass shutterto be considered ,Â pullout tray to be considered wooden finish &Â creame color combination. KitchenÂ spacing to be provide for 2.5' chimney & hob Ledge to be extended till tall unit Undersink Ro to be plan. MBR Dresser will be under client scope. Bedwall design as per reference . Wardrobe wooden membrane finish with ratten finish (curved design ). False ceiling withÂ boarder paint. KBR dual color combination wardrobe(Green & white),Â study table white color, Side tall unit to be mirror glass shutter & drawers Bed wall to be plan as per existing unit Study top unit to be considered as closed & open unit False ceiling Living false ceiling to be designed as per sprinkler point . | 2026-05-11 | 2026-05-10 16:32 | 2026-06-17 | 2026-06-16 17:19 | Under Construction | 2026-03-31
18724 | Turnkey | 2026-01-01 | Ankur Jain | Prestige Green Gables | BNG - HSR | Yes | Nayan Reddy |  | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 2068617 | 9999 | 0 | 0 | 0 | 131 | 0 | 196863 | 206862 | 864690 | 790203.2 |  |  | 2026-03-06 | 2026-03-06 16:14 | 2026-03-13 | 2026-03-13 11:46 | 2026-03-10 |  | 2026-03-23 |  | 2026-03-30 |  | 2026-04-06 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-18 | [5 empty] | 2026-03-24 |  | 2026-04-01 |  | 2026-04-02 |  |  |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 | [6 empty] | 2026-04-30 |  | 2026-05-09 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-12 |  |  |  | 2026-06-03 |  | 2026-06-05 |  | 2026-06-06 | [5 empty] | 2026-04-10 |  | 2026-03-19 |  | Unknown | 2026-03-06 | 2026-03-06 16:12 | 0 | 0 | 0 | 0 | 0 | 0 | 1753066 | 315551 | [9 empty] | 2026-03-24 |  | 2026-03-31
18728 | Turnkey | 2026-01-01 | Arnab Banerjee | SNN Serenity Gardens | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw | Vishwa Hiremath | Active | Preproduction | CM | 1714597 | 313588 | 2209862 | 0 | 0 | 5 | 0 | 0 | 0 | 749896 | 651113.2 |  |  | 2026-03-06 | 2026-03-07 15:13 | 2026-04-02 | 2026-04-02 18:06 | 2026-04-05 | 2026-04-21 14:28 | 2026-05-16 | 2026-05-16 19:28 | 2026-07-08 |  | 2026-07-28 |  | 2026-04-05 | 2026-04-20 16:50 | 2026-04-22 | 2026-04-21 19:28 | 2026-04-21 | 2026-04-22 13:02 | 2026-04-25 | 2026-04-25 12:57 |  |  |  |  | 2026-05-25 | 2026-05-16 18:48 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-09 |  | 2026-08-10 | [6 empty] | 2026-08-28 |  | 2026-09-06 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-09 |  |  |  | 2026-10-01 |  | 2026-10-03 |  | 2026-10-04 | [5 empty] | 2026-08-08 |  | 2026-05-20 | 2026-05-16 19:24 | Site is RTMI | 2026-03-06 | 2026-03-06 20:22 | 1875260 | 334601 | 0 | 0 | 0 | 0 | 1984245.8893 | 327696 | 2026-05-20 18:26:59 +0530 | Prathyusha Elangovan | Mr.Arnab-Material Selection(MOM) FOYER FAIRFIELD WALNUT 2309 FOR ENTIRE SHOE RACK AND SEATER 1587 LUV-HARLEY MARBLE-FOR THE CENTRE KNOBS-ROSE GOLD KNOB 7066 TV UNIT MERAKI WALNUT-FOR THE SIDE PANEL WITH BLACK METAL STRIP TV BACK PANEL-CRYSTAL MATTY-1249 FLAVA RAFTERS FLPB 9619 CROCKERY CARNATION 8151 -INTERNAL BOTTOM SHUTTERS-CLOUD CONCRETE 1560 ANTRACITE GREY-1713 Black and gold knob-3269 KITCHEN Â PT -DAISY (SM-2) ESM BLUE (SM-1) MBR MERAKI WALNUT-2292 LUV PREMIUM GREEN-1722 AFP LONG HANDLES-ROSE HANDLE MACAW(G H)ROSE HANDLE -596 KNOB FOR MBR DRESSER-DIA-45 V 1437 BIG(K.H) KBR PURPLE 1159-LOFT LIGHT RED-165 SUD-MIDDLE MYSRORE IVORY 124 SGL-BOTTOM KBR HANDLE-P 36 ROSE GOLD HANDLE -305 OFFICE ROOM PEARL WHITE-1589 HG AVIO BLUE 1709 VANITY UNIT COMMON VANITY PLATINUM LUV 1703 SCRAT PINK MBR VANITY BLACK MARMOR 5575 SGL KNOB-ANTIQUE KNOB -50MM V-3279(K.H) | 2026-05-20 18:25:58 +0530 | Prathyusha Elangovan | Mr.Arnab (MOM) 9/05/26 FOYER 1350MM DOUBLE+SINGLE INTERNALS AS PER THE PREVIOUS DESIGN ENHANCEMENT NEEDS TO BE DONE TV PANEL NEEDS TO BE ADDED ADJ WALL-TEXTURE PAINT(GOD FRAME) COMPLETE WALL WILLL BE PAINTE POP CEILING CENTRE OF HE LIVING DINING AREA SAME DESIGN CORNER SHELEVSÂ KITCHEN PULL OUT TRAY ROLLER SHUTTER IN THE CENTRE UNITS ON TOP AND BOTTOM OF TALL UNIT NO LOFTS KIDSBEDROOM SAME DESIGN WALLPAPER ON BOTH THE WALLS PLAY AREA POOJA UNIT LOOSE FURNITURE BOTH BEDROOMS USED CLOTHES STORAGE COMMON WASHROOM(NEEDS TO BE CHECKED DURING CROSS MEASURMENTS(DIM IS INCORRECT) | 2026-04-29 15:19:37 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-17 | 2026-05-16 19:30 | 2026-07-09 |  | Under Construction | 2026-06-03
18731 | Turnkey | 2026-01-01 | Grace Johnson | independent house | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S | Kushal S | Vishwa Hiremath | Active | Handover | Project Closure Pending | 880733 | 880733 | 983027 | 0 | 880733 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-06 | 2026-03-06 21:24 | 2026-03-14 | 2026-03-14 11:54 | 2026-03-18 | 2026-03-19 18:02 | 2026-04-14 | 2026-04-14 12:05 | 2026-04-25 | 2026-04-24 11:54 | 2026-04-27 | 2026-04-27 16:33 | 2026-03-19 | 2026-03-26 19:09 | 2026-03-20 | 2026-03-27 13:07 | 2026-03-27 | 2026-03-28 17:51 | 2026-04-03 | 2026-04-03 13:26 |  |  |  |  | 2026-04-14 | 2026-04-14 18:59 | 2026-04-25 | 2026-04-24 12:01 | 2026-04-25 | 2026-04-27 13:50 |  |  | 2026-05-16 | 2026-05-20 15:00 | 2026-05-21 | 2026-05-21 18:39 | 2026-05-25 | 2026-05-23 16:10 | 2026-05-24 | 2026-05-25 18:40 |  |  |  |  | 2026-05-26 16:51 | 2026-06-06 | 2026-06-05 21:25 | 2026-06-15 | 2026-06-13 22:23 | 2026-06-14 | 2026-06-15 17:11 | 2026-06-13 | 2026-06-17 16:06 | 2026-06-17 | 2026-06-17 19:47 | 2026-07-02 | 2026-07-01 11:48 |  |  | 2026-07-05 | 2026-07-06 09:03 | 2026-07-07 | 2026-07-06 11:17 | 2026-07-08 | 2026-07-06 17:54 |  |  |  |  | 2026-05-24 | 2026-05-26 16:50 | 2026-04-04 | 2026-04-14 11:51 | Site is RTMI | 2026-03-06 | 2026-03-06 20:41 | 833074 | 149953 | 0 | 0 | 985697.807 | 162762 | 985697.807 | 162762 | 2026-07-07 00:45:24 +0530 | Saddam Hussain Z M | Execution: Observation Points - 22nd July | 2026-07-06 18:03:01 +0530 | Saddam Hussain Z M | Execution: Observation Points - 22nd July | 2026-04-14 12:14:29 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 12/04/2026 Title: DEM 1 Project: 18731 Client: Grace Johnson Attendees: Vishal Objective: DEM 1 Discussion Based on 12/04/2026 meeting, below is a list of all the requirements that were discussed during the meeting: DEM-1 MOM PID-18731 Customer name: Grace Johnson Date & time: 12/04/2025 @5.30pm Designer name: Vishal Kitchen: * as discussed existing granite going to remove and placing new one * kitchen cabinet placements are finalized. * Spice rack has to consider below the wall cabinets * As mentioned, Sink can we move little Towards wall side * Above the Sink , need to plan for GTPT tray (for keeping Plates) * RO will be Under the sink (as discussed, Electrical and Plumbing Point has to be create for the RO) TV Unit: * Base unit with 2 drawers and 1 Glass shutter at the center * Need to give design with Beading for the back wall MBR: * Dresser unit has to place next to the wardrobe and mirror on top of shutter * need to consider loftÂ above the wardrobe ( not finalized) * need to create one more wardrobe outside the room ( common area) DBR: * Need To plan for dresser Pullout towards wall side * Bed size are not confirmed ( as mentioned, once the initial Measurement file received, we will get to know the exact space availability) SBR: * as mentioned, need to plan for wardrobe, bed and the study table in a room (as there is confusion in dimension ) | 2026-04-15 | 2026-04-14 12:12 | 2026-04-25 | 2026-04-24 12:00 | RTMI
18732 | Turnkey | 2026-01-01 | Vyom Bhardwaj | SOBHA Dream Acres | BNG - HSR | Yes | Shefali | Abhinandan K S | Priyanka Mathur |  | RaviKumar Battala | Suchendra Shetty | Jairam Joshi | Murali S | Chanakya Panigrahi | Sunil Kumar S M | Active | Handover | Project Closure Pending | 1058190 | 1058191 | 1432237 | 1084811 | 1058190 | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-07 | 2026-03-07 11:56 | 2026-03-08 | 2026-03-10 11:57 | 2026-03-13 | 2026-03-10 12:04 | 2026-04-04 | 2026-03-31 16:36 | 2026-04-21 | 2026-04-20 19:27 | 2026-04-24 | 2026-04-24 19:45 | 2026-03-10 | 2026-03-11 12:20 | 2026-03-11 | 2026-03-12 10:25 | 2026-03-12 | 2026-03-12 17:21 | 2026-03-13 | 2026-03-13 18:54 |  |  |  |  | 2026-03-31 | 2026-04-01 17:26 | 2026-04-22 | 2026-04-21 20:01 | 2026-04-22 | 2026-04-21 20:01 |  |  | 2026-04-26 | 2026-04-27 19:10 | 2026-04-28 | 2026-04-28 18:51 | 2026-04-29 | 2026-04-28 22:07 | 2026-04-29 | 2026-04-29 16:52 |  |  |  |  | 2026-05-05 11:36 | 2026-05-12 | 2026-05-12 21:02 | 2026-06-03 | 2026-05-30 23:31 | 2026-05-31 | 2026-05-31 15:45 | 2026-05-30 | 2026-06-02 17:08 | 2026-06-02 | 2026-06-03 13:05 | 2026-06-16 | 2026-06-15 18:46 |  |  | 2026-07-07 | 2026-07-07 19:48 | 2026-07-18 | 2026-07-08 13:33 | 2026-07-19 | 2026-07-08 15:30 |  |  |  |  | 2026-04-28 | 2026-05-02 15:34 | 2026-03-14 | 2026-03-31 11:01 | Site is RTMI | 2026-03-07 | 2026-03-07 11:55 | 1213760 | 218476 | 1191569.768 | 196750 | 1166980.87 | 192690 | 1166980.87 | 192690 | 2026-07-08 15:32:26 +0530 | Jairam Joshi | Project Closure Pending: Wallpaper pending CX depending - 15th July Observation points - 23rd July Closure - 23rd July | 2026-07-06 18:58:07 +0530 | Jairam Joshi | Execution: QC- 7th July HO -8th July | 2026-06-16 18:32:12 +0530 | Jairam Joshi | Some Image was uploaded | 2026-04-01 | 2026-03-31 16:47 | 2026-04-21 | 2026-04-21 01:14 | RTMI
18733 | Turnkey | 2026-01-01 | Mrs. Nancy Chaudhary | Pavani Mariabilia | BNG - HSR | Yes | Shefali | Akshay Ds | Soumya KP |  | RaviKumar Battala | Deekshith P | Jairam Joshi | Murali S | Ramesh Nayak | Affaan Abdulla | Active | Production | Production | 1285352 | 785416 | 1343677 | 0 | 1285352 | 15 | 0 | 0 | 0 | 0 | 499936 |  |  | 2026-03-07 | 2026-03-08 20:20 | 2026-03-19 | 2026-04-03 14:52 | 2026-04-04 | 2026-04-04 18:58 | 2026-05-11 | 2026-05-11 18:35 | 2026-05-24 | 2026-05-23 17:28 | 2026-05-31 | 2026-05-31 10:55 | 2026-04-04 | 2026-04-06 19:23 | 2026-04-05 | 2026-04-07 10:35 | 2026-04-07 | 2026-04-07 16:59 | 2026-04-15 | 2026-04-15 18:41 |  |  |  |  | 2026-05-01 | 2026-05-09 18:03 | 2026-05-25 | 2026-05-24 01:41 | 2026-05-25 | 2026-05-24 01:42 |  |  | 2026-06-02 | 2026-06-05 16:41 | 2026-06-05 | 2026-06-05 20:46 | 2026-06-06 | 2026-06-05 20:59 | 2026-06-06 | 2026-06-09 18:03 |  |  |  |  | 2026-06-12 10:04 | 2026-07-01 | 2026-06-30 19:59 | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-05 | 2026-06-12 10:03 | 2026-04-16 | 2026-04-26 12:29 | Site is RTMI | 2026-03-07 | 2026-03-07 16:32 | 1138709 | 204967 | 0 | 0 | 1433174.2805 | 236647 | 1433174.2805 | 236647 | 2026-07-04 15:33:35 +0530 | Jairam Joshi | Procurement: SRD task closed | 2026-06-26 17:00:56 +0530 | Jairam Joshi | Procurement: PI tasks completed from bonito scope CX side ele WIP - 29th June SRD - 30th June | 2026-06-22 17:44:14 +0530 | Jairam Joshi | Procurement: CX side WIP - 22nd Key -23rd FC- 24th SRD 25th | 2026-05-12 | 2026-05-11 22:36 | 2026-05-24 | 2026-05-31 10:57 | Under Construction | 2026-04-27
18735 | Turnkey | 2026-01-01 | Palak Desai | Krishna Heights | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anant Giri |  | Hold | Preproduction | Site Readiness 1 | 1040144 | 210999 | 1561313 | 0 | 0 | 4 | 88 | 0 | 0 | 447724 | 381420.8 |  |  | 2026-03-07 | 2026-03-07 14:11 | 2026-03-09 | 2026-03-27 12:37 | 2026-03-29 | 2026-03-29 22:48 | 2026-04-19 | 2026-04-19 20:21 | 2026-10-05 |  | 2026-10-12 |  | 2026-03-29 | 2026-03-30 18:00 | 2026-03-30 | 2026-03-30 21:28 | 2026-03-30 | 2026-04-01 13:07 | 2026-04-05 | 2026-04-05 13:33 |  |  |  |  | 2026-07-05 | 2026-04-19 17:22 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-22 |  | 2026-10-23 | [6 empty] | 2026-11-10 |  | 2026-11-19 |  | 2026-05-19 |  | 2026-11-19 |  | 2026-11-20 |  | 2026-11-22 |  |  |  | 2026-12-14 |  | 2026-12-16 |  | 2026-12-17 | [5 empty] | 2026-10-16 |  | 2026-06-30 | 2026-04-19 20:12 | Site is Non-RTMI | 2026-03-07 | 2026-03-07 14:10 | 1325948 | 235364 | 0 | 0 | 0 | 0 | 1294824.87 | 192474 | 2026-07-08 12:04:22 +0530 | Anil Jagtap | Possession - September *26 | 2026-06-30 11:40:25 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-27 18:59:37 +0530 | Rachna Abhyankar | cx will get the possession post 2-3 months approximately | 2026-04-20 | 2026-04-19 20:26 | 2026-10-06
18736 | Turnkey | 2026-01-01 | Jyotsna | Assetz Marq 3.0 | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1406869 | 281374 | 1885816 | 0 | 0 | 2 | 90 | 0 | 0 | 616955 | 508540 |  |  | 2026-03-07 | 2026-03-07 14:02 | 2026-03-13 | 2026-03-13 16:04 | 2026-03-14 | 2026-03-16 17:40 | 2026-04-18 | 2026-04-14 12:49 | 2026-09-20 |  | 2026-09-27 |  | 2026-03-16 | 2026-03-17 14:11 | 2026-03-17 | 2026-03-24 12:11 | 2026-03-24 | 2026-03-25 14:13 | 2026-03-27 | 2026-03-27 19:49 |  |  |  |  | 2026-04-14 | 2026-04-14 13:13 | 2026-09-22 |  | 2026-09-23 |  |  |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 | [6 empty] | 2026-10-21 |  | 2026-10-30 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-02 |  |  |  | 2026-11-24 |  | 2026-11-26 |  | 2026-11-27 | [5 empty] | 2026-10-01 |  | 2026-04-03 | 2026-04-14 11:36 | Site is RTMI | 2026-03-07 | 2026-03-07 14:01 | 1598149 | 287666 | 0 | 0 | 0 | 0 | 1590775.2553 | 262658 | 2026-04-16 15:19:18 +0530 | Lalitha Ajay Kumar | Some Image was uploaded | 2026-04-16 13:51:17 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-03-27 19:48:43 +0530 | Abhinandan K S | Posssesion- May or June 2026 Customer is ok with the Offers. timeline and Net quote. 15th April 2026- 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer | 2026-04-15 | 2026-04-14 12:49 | 2026-09-21 |  | Under Construction | 2026-04-30
18738 | Turnkey | 2026-01-01 | Chandan Kumar | Prestige Merdian Park | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 3367454 | 9999 | 0 | 0 | 0 | 130 | 0 | 326746 | 336745 | 1427138 | 1266824.8 |  |  | 2026-03-07 | 2026-03-07 14:58 | 2026-03-10 | 2026-03-10 15:09 | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-15 | [5 empty] | 2026-03-21 |  | 2026-03-29 |  | 2026-03-30 |  |  |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 | [6 empty] | 2026-04-27 |  | 2026-05-06 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-09 |  |  |  | 2026-05-31 |  | 2026-06-02 |  | 2026-06-03 | [5 empty] | 2026-04-07 |  | 2026-03-16 |  | Unknown | 2026-03-07 | 2026-03-07 14:57 | 0 | 0 | 0 | 0 | 0 | 0 | 2853775 | 513679 | 2026-03-10 14:58:18 +0530 | Ankita Agarwal | DCM: Client Brief Chandan CXProperty: Prestige City Configuration: 3 BHK Theme: Modern & Abstract Luxury Budget: 25L 30L Meeting: Thursday TL: Varun FP: Page 21 Client RequirementsEntrance / FoyerShoe rack with seatingWall treatmentElectrical board to be concealedDesign to blend with entrance aestheticsSpace Next to FoyerInformal cozy seating areaLiving RoomTV Unit Base suspended unitWall panellingNo wall storage unit requiredSofa Wall Wall panellingFurniture Sofa: 3 + 2 seatingDining Area6 seater dining tablePuja unit integrated with crockery unit (as per layout)KitchenFinish Membrane finishUnits Required Appliance unitCylinder unitTambour unitRustic handlesAppliances DishwasherAquaguard under sinkUtilityJanitor unitWashing machineDryer spaceMaster Bedroom (2 People)Wardrobe with loftDresser integrated with wardrobeCozy seating opposite bedBed back wall panellingMaster BathroomVanity unitMirrorGrid ceilingGlass partition (as per site condition)Passage AreaWall paintingMirror dcorBedroom 3User: 21 year old girl (MBA student) Requirements Wardrobe (Swing or Sliding client not sure yet) with loftDresser with drawersStudy table with wall unitBed back wall panellingBedroom 2User: 20 year old (BBA student) Theme Dark shade themeGrey and navy blue paletteRequirements Sliding wardrobe with loftTV unit with study table and wall unitBed back wall panellingFull length mirrorBathroomVanity and mirrorClient planning to change tilesFalse CeilingFull house ceiling design3D panel ceiling design elementsMain DoorEntrance door to be replacedEntrance wall panellingFlooringClient planning to change tiles for entire houseWooden flooring in all bedroomsTo Be Discussed LaterFurniture detailingLighting planAC provisionMaid room design | [6 empty] | 2026-03-21 |  | 2026-03-28
18739 | Turnkey | 2026-01-01 | MINANATH MANABHAU MHASKE | Casa Supremo | MUM - Thane | No Estimate | [10 empty] | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 127 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-07 | 2026-03-10 13:19 | 2026-03-08 |  | 2026-03-07 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-03-07 |  | 2026-03-08 |  | 2026-03-08 |  | 2026-03-09 | [5 empty] | 2026-03-15 |  | 2026-03-23 |  | 2026-03-24 |  |  |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-03 | [6 empty] | 2026-04-21 |  | 2026-04-30 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-03 |  |  |  | 2026-05-25 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-04-01 |  | 2026-03-10 |  | Unknown | 2026-03-07 | 2026-03-10 13:18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-15 |  | 2026-03-22
18740 | Turnkey | 2026-01-01 | PRASHANSA RAKESH AND BALDEV NAGPAL | SSVR Niyaraa | BNG - HSR | Yes | Swati Rathod | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1727205 | 9999 | 0 | 0 | 0 | 130 | 0 | 162722 | 172721 | 690882 | 690882 |  |  | 2026-03-07 | 2026-03-07 15:02 | 2026-03-21 | 2026-05-05 11:13 | 2026-03-20 |  | 2026-05-15 |  | 2026-05-22 |  | 2026-05-29 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-05-16 |  | 2026-05-24 |  | 2026-05-25 |  |  |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 | [6 empty] | 2026-06-22 |  | 2026-07-01 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-04 |  |  |  | 2026-07-26 |  | 2026-07-28 |  | 2026-07-29 | [5 empty] | 2026-06-02 |  | 2026-05-11 |  | Unknown | 2026-03-07 | 2026-03-07 15:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1463733 | 263472 | 2026-03-26 19:33:38 +0530 | Swati Rathod | East facing Living- MBR- Sliding wardrobe with loft on opp wall as well., Dresser. BR 1-Next to balcony- Study office- Swing wardrobe,existing study table- 2 table- 5*2.5 ft- floor mounted storage, open shelves opp to wardrobe wall- for small plants BR2- Swing Wardrobe, Dresser MBR & BR2- side table if possible Toilets- Vanity unit /storage on top Kitchen- No utility wall b/w only beam passing through Fridge , WM, DW, sink work out- U kitchen Tall unit - outside kitchen Â Opt 1- U kitchen- Fridge inbtw 2 windows , After fridge area, RO top, Hob on East wall. Sofa side wall- SInk, Tall unit Outside kitchen along with crockery unit, Base, Top and loft Opt 2- try working out as per vastu Â Pooja- In Living area Dining and living as per plan No texture paint, beading no fluted panels Â LOW MAINTANCE AND MINIMAL WARM TONES LIKE TAN YELLOW AND SUBTLE GREEN Budget -12 Lakhs Soft possession- july | [6 empty] | 2026-05-16 |  | 2026-05-23
18741 | Turnkey | 2026-01-01 | Max Flow Industries (MAAZ ABDUL HAMID SALEMA) HAMID SALEMA | Roswalt Zaiden | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Hold | Design | DEM1 | 3060818 | 398250 | 3982500 | 0 | 0 | 46 | 35 | 0 | 213914 | 1275844 | 1172810 |  |  | 2026-03-07 | 2026-04-12 13:34 | 2026-04-04 | 2026-04-12 19:00 | 2026-04-15 | 2026-04-15 11:58 | 2027-01-19 |  | 2027-01-26 |  | 2027-02-02 |  | 2026-04-15 | 2026-04-15 15:15 | 2026-04-16 | 2026-04-15 15:17 | 2026-04-15 | 2026-04-25 10:05 | 2026-04-28 | 2026-04-28 19:05 |  |  |  |  | 2027-01-20 |  | 2027-01-28 |  | 2027-01-29 |  |  |  | 2027-02-05 |  | 2027-02-06 |  | 2027-02-07 |  | 2027-02-08 | [6 empty] | 2027-02-26 |  | 2027-03-07 |  | 2026-06-07 |  | 2027-03-07 |  | 2027-03-08 |  | 2027-03-10 |  |  |  | 2027-04-01 |  | 2027-04-03 |  | 2027-04-04 | [5 empty] | 2027-02-06 |  | 2027-01-15 |  | Unknown | 2026-03-07 | 2026-04-10 13:58 | 3375000 | 607500 | 0 | 0 | 0 | 0 | 3338426.2911 | 558048 | 2026-06-10 14:56:53 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-21 12:03:36 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-30 19:27:30 +0530 | Meet Shah | Some Image was uploaded | 2027-01-20 |  | 2027-01-27 |  | Under Construction | 2026-12-31
18743 | Turnkey | 2026-01-01 | Manjunatha Poojari | DOSTI WEST COUNTY | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [6 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 1591619 | 9999 | 0 | 0 | 0 | 130 | 0 | 149163 | 159162 | 657986 | 615309.6 |  |  | 2026-03-07 | 2026-03-07 21:51 | 2026-03-10 | 2026-03-10 18:46 | 2026-03-19 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-20 |  | 2026-03-21 | [5 empty] | 2026-03-27 |  | 2026-04-04 |  | 2026-04-05 |  |  |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 | [6 empty] | 2026-05-03 |  | 2026-05-12 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-15 |  |  |  | 2026-06-06 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-04-13 |  | 2026-03-22 |  | Unknown | 2026-03-07 | 2026-03-07 21:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1351117 | 240502 | 2026-03-31 19:35:45 +0530 | Aryan Singh | Some Image was uploaded | 2026-03-24 15:13:11 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-08 17:23:59 +0530 | Rutuja Kotwal | DCM: Mr. Manjunatha Poojari 2BHK. 611 +33+18 sq.ft. Move in 5 people - husband, wife, 2 kids son - 18 yrs. girl - 12 yrs. Mother - 76 yrs. profession - IT professionals. Direction - Exiting Northeast Design as per basic Vastu. Possession - June 2026. budget - 8-10 lakhs. Living Room - Safety door, partition in the entrance, Sofa cum bed, TV unit with Mandir, Folding dining table, approx. rate to be added, sound bar and woofer and speakers, shoe rack, swing if possible, Chest of drawers besides sofa for keeping medicines. Kitchen - parallel platform, Base units, wall units and Lofts, machine and Dishwasher in the utility area., wicker baskets, Rolling shutters, built in hob and chimney, spice rack, Bedroom 1 - Bed, wardrobe with lofts, bed for 3 people, 2 Study unit with book storage, smart board dressing table with Storage. major Storage in this bedroom. canopy area for daughter. TV unit MBR- murphy bed with sofa with side table loose, work space, wardrobe with lofts, side table, dressing unit with Storage, Accent Chair. CDP- 19th at 11am. not confirmed. Budget suggested - 18 - 20 lakhs. | 2026-03-27 |  | 2026-04-03
18745 | Turnkey | 2026-01-01 | Suresh Vora | sankeshwar heights | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 1261635 | 9999 | 0 | 0 | 0 | 120 | 0 | 116165 | 126164 | 504654 | 504654 |  |  | 2026-03-07 | 2026-03-17 18:13 | 2026-03-08 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-03-07 | 2026-03-17 18:12 | 0 | 0 | 0 | 0 | 0 | 0 | 1069182 | 192452 | [9 empty] | 2026-03-30 |  | 2026-04-06
18746 | Turnkey | 2026-01-01 | Sachin Kashyap | Adarsh Park Height | BNG - HSR | Yes | Chittipireddy Sriharish | Abhinandan K S | Kowshik |  | Sethuragavan R | Suchendra Shetty | Jairam Joshi | Murali S | Ramesh Nayak | Affaan Abdulla | Active | Production | Production | 1684919 | 1020664 | 1872898 | 0 | 1684919 | 7 | 0 | 0 | 0 | 0 | 664255 |  |  | 2026-03-07 | 2026-03-08 20:19 | 2026-03-25 | 2026-03-25 12:41 | 2026-03-28 | 2026-03-26 12:45 | 2026-03-27 | 2026-03-27 16:13 | 2026-05-22 | 2026-05-21 18:54 | 2026-06-24 | 2026-06-24 10:46 | 2026-03-08 | 2026-03-09 19:24 | 2026-03-09 | 2026-03-10 10:01 | 2026-03-10 | 2026-03-13 18:44 | 2026-03-15 | 2026-03-15 08:22 |  |  |  |  | 2026-03-21 | 2026-03-20 19:22 | 2026-05-22 | 2026-05-24 01:03 | 2026-05-25 | 2026-05-24 01:04 |  |  | 2026-06-29 | 2026-06-29 18:37 | 2026-06-29 | 2026-06-29 21:09 | 2026-06-30 | 2026-06-29 21:36 | 2026-06-30 | 2026-07-02 12:25 |  |  |  |  | 2026-07-03 18:50 | 2026-07-09 | 2026-07-08 22:14 | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-30 | 2026-07-03 18:49 | 2026-03-29 | 2026-03-27 16:08 | Site is RTMI | 2026-03-07 | 2026-03-07 19:04 | 1587202 | 285696 | 0 | 0 | 1630892.0745 | 281428 | 1630892.0745 | 281428 | 2026-07-13 18:40:05 +0530 | Jairam Joshi | Procurement: CX side Ele work in progress - 2days work key - TBD FC -TBD SRD -TBD CX will provide keys 3days before dispatch | 2026-07-06 18:13:45 +0530 | Jairam Joshi | Procurement: CX side Ele work in progress - 12th key - 13th FC -14th SRD -15th | 2026-06-29 14:59:45 +0530 | Chittipireddy Sriharish | Some Image was uploaded | 2026-03-28 | 2026-03-27 16:16 | 2026-05-22 | 2026-05-21 19:01 | RTMI
18747 | Turnkey | 2026-01-01 | D Mukherjee / S Bhattacharya | GR Sitara | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Aman Kumar |  | Active | Design | DEM1 | 1609995 | 219108 | 2228286 | 0 | 0 | 55 | 0 | 0 | 102891 | 643998 | 643998 |  |  | 2026-03-07 | 2026-03-07 19:15 | 2026-04-10 | 2026-04-10 11:14 | 2026-05-10 | 2026-05-10 20:54 | 2026-07-08 |  | 2026-10-01 |  | 2026-10-08 |  | 2026-05-10 | 2026-05-12 11:26 | 2026-05-11 | 2026-05-19 10:38 | 2026-05-19 | 2026-05-21 10:37 | 2026-05-26 | 2026-05-26 13:12 |  |  |  |  | 2026-07-09 |  | 2026-10-03 |  | 2026-10-04 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-14 | [6 empty] | 2026-11-01 |  | 2026-11-10 |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-13 |  |  |  | 2026-12-05 |  | 2026-12-07 |  | 2026-12-08 | [5 empty] | 2026-10-12 |  | 2026-05-27 | 2026-06-27 11:26 | Site is RTMI | 2026-03-07 | 2026-03-07 19:14 | 1888378 | 339908 | 0 | 0 | 0 | 0 | 1856843.1936 | 306609 | 2026-07-04 11:11:28 +0530 | Muskan Agarwal | ðŸ“ŒMinutes of Meeting - Points Discussed & Agreed Corrections Living Room 1. TV back panel to be added with provision for a TV size greater than 56 inches. 2. Pelmet to be added for double curtains near the balcony door. Note: The balcony door will be covered from the top due to the pelmet. 3. Foyer partition to be designed as per reference: Depth: 6 inches Width: 2 feet 4. Shoe rack to be positioned after the door space. 5. A small seating provision to be incorporated near the shoe rack. 6. Punning feature to be developed in an L-shape behind TV. Dining Area 1. Pelmet to be added for double curtains near the balcony door. Note: The balcony door will be covered from the top due to the pelmet. 2. Crockery unit to be covered from the top with a dead panel. 3. Crockery unit design to be revised: Combination of open shelves and wall-mounted cabinets. Back panel to be provided. No tall unit to be included in the crockery design. Kitchen 1. Glass partitions to be added on both walls. 2. Pantry unit to be added adjacent to the appliance unit. 3. Blind corner storage unit to be provided for two-cylinder storage. 4. Aquaguard dimensions to be confirmed by the client. 5. Client has opted for a filter chimney. 6. Utility sink to be swapped to the opposite wall with the wall storage arrangement revised accordingly. Important Note 1. The module sizes mentioned/discussed are tentative and may vary based on the final site measurements. 2. The client has been informed and acknowledges that any changes arising from the final site measurements may impact quantities, module dimensions, and design details. | 2026-05-26 14:12:49 +0530 | Maspi Das | Client name- D Bhattacharya Date- 05.04.2026 Property- G R Sitara Possession- Done Facing - EAST Members- 4 Kids - NO Theme - Minimal, Aesthetic (refers Tropical/Floral touch) Budget- 11L Next Design meeting - 12/04/2026 **FALSE CEILING for Living, Dining, Entrance & Common space** **Both the balcony- Ledges for plants** *hanging props* *A space for SOFT TOYS display/storage* Foyer- Entrance wall shoe rack with minimal wall design and space for pictures (Picture wall) Partition Kitchen- Utility- Sink unit one side, Wall & Lofts (Both side) *Rolling curtains on the Utility window* *Need a pocket door in between the utility and Kitchen* **Between kitchen & Utility the half wall is there need to have something to give little light, air circulation & opacity** Granite Left side little extension of Slab- below dishwasher & one cabinet L- shaped Kitchen with Base, Wall & Loft units *Pantry unit* *OTG Unit with wicker basket* Add WIKER BASKET *Combination of Profile glass door & lam* Dining area- Crockery unit with double door refrigerator Common sink area- Vanity unit with open storage and mirror with glass partition BR2 - Study unit with Storage for books (Displayed storage) Puja unit- BD-VRM-2025-0680 (from studio) 2-door wardrobe with a C-shaped table and ledges for small accessories - Loft with Wardrobe Â All the bathrooms -Vanity units, Mirrors, Partition & Storage on top of WC BR1- Bay window sitting with shutter storage (LAVENDER color pop up) Wall design for Bedrest wall Minimal design for Bay window sitting area (based on the wall design) Wardrobe with Loft (if possible 5door or increase the length of the wall) Mirror on the wall blend with the wall design 2 DOOR WARDROBE (behind the entry door) MBR (Wooden floor)- One wardrobe with Tv ledge One wardrobe behind the door Dressing table Photo frame- 2'6"x2' (not exact for ref) **door need to change into window & door**7 | 2026-05-26 13:15:52 +0530 | Abhinandan K S | RTMI project. Initial measurement to aligned either on 29th 0r 30th May 2026 as per the Cx's availability. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. Customer wants revised estimate as per the changes requested in the CDP meeting. | 2026-07-09 |  | 2026-10-02 |  | RTMI
18749 | Turnkey | 2026-01-01 | Pradeep Patidar | Adarsh Tropica | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 1280435 | 9999 | 1280435 | 0 | 0 | 120 | 0 | 118045 | 128044 | 514713 | 509634.8 |  |  | 2026-03-07 | 2026-03-07 20:19 | 2026-03-17 | 2026-03-17 13:38 | 2026-03-17 | 2026-03-17 14:42 | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-03-07 | 2026-03-07 20:17 | 1085114 | 195320 | 0 | 0 | 0 | 0 | 1085114 | 195320 | 2026-03-13 13:16:48 +0530 | Swati Rathod | Pradeep cx :Â 2bhkÂ 2people +2kidsÂ parentsÂ Budget : 7-8L theme :Minimal with pattern. Direction the north-westÂ outside shoe rack in L shapeÂ just opp to main door , we need to plan seater with design Foyer: wall design and console table. Living : suspended tv unit with wall design , minimal design.Â 3 and accent chair or L shape we can also we dining chair with 3seater sofa dining:6ft H puja unit on the next to dining table facing balcony along crockery.Â we need to arrangement of dining tableÂ 4seaterÂ dining tableÂ False ceiling for living and dinning Kitchen :Â Hob & chimney sinkÂ microwaveÂ mixerÂ aqua guard galÂ washing machineÂ over theÂ dishwasher tall unit for veg and extra storage next to washing machine. base , wall and loftÂ MBR :7ft wardrobe with loft . dresser next to bedÂ king bed and side tableÂ Work station (4ft w) KBR :6year girl and 5month boy 7ft wardrobe with loft . Mirror on the wallÂ study with wall storage ( 3ft w) Play area or wall play (kids theme ) No bedÂ Both Bathroom : vanity and janitor unit in balcony. | 2026-03-10 12:00:31 +0530 | Chanakya Panigrahi | RGM Sheet 1. Budget - 7-9L 2. Property Name & Possession - Adarsh Tropoca 3. Carpet Area - 750 4. BHK - 2 BHK 5. Family Size - 2 + 2 Name - Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer - Yes 4. Living/Dining Room Inclusions - TV Unit 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Yes Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz -Â |  |  |  | 2026-03-25 |  | 2026-04-01
18750 | Turnkey | 2026-01-01 | Nitesh mestry | Runwal Forests | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 1418033 | 9999 | 0 | 0 | 0 | 130 | 0 | 131804 | 141803 | 633358 | 501068.4 |  |  | 2026-03-07 | 2026-03-07 21:44 | 2026-03-10 | 2026-03-10 18:32 | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-03-07 | 2026-03-07 21:44 | 0 | 0 | 0 | 0 | 0 | 0 | 1201723 | 216310 | 2026-03-10 13:09:06 +0530 | Rutuja Kotwal | DCM: Mr. Nitesh Mestry. Runwal Forest kanjurmarg. 615.59 sq. ft. 2 BHK. Move in - 4.5 People- Husband, wife, parents, daughter - 5 yrs. Design As per basic Vastu. Direction- North east. entrance. Budget- 8 - 10 lakhs. Living Room - Shoe rack, 4 seater dining table, TV unit with back panel, Sofa, Mandir- Suspended. Kitchen - Semi modular kitchen. Base units, wall units and Lofts one side. Parent's Bedroom - NO TV, Wardrobe with Lofts and tall unit, Side table with Mirror, Study unit with above storage, Sofa cum Bed. Master Bedroom- Bed, wardrobe with Lofts, Study unit with above storage to keep laptop. CDP- 15th March at 11 am. Budget suggested - 15 lakhs. | [6 empty] | 2026-03-23 |  | 2026-03-30
18751 | Turnkey | 2026-01-01 | Pravin Shejwal | Gami ved | MUM - Thane | Yes | Pooja Nakul Sharma | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 2047004 | 9999 | 0 | 0 | 0 | 126 | 0 | 194701 | 204700 | 850669 | 786934 |  |  | 2026-03-07 | 2026-03-11 17:37 | 2026-03-10 |  | 2026-03-12 |  | 2026-03-19 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-03-12 |  | 2026-03-13 |  | 2026-03-13 |  | 2026-03-14 | [5 empty] | 2026-03-20 |  | 2026-03-28 |  | 2026-03-29 |  |  |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-08 | [6 empty] | 2026-04-26 |  | 2026-05-05 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-08 |  |  |  | 2026-05-30 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-04-06 |  | 2026-03-15 |  | Unknown | 2026-03-07 | 2026-03-10 18:56 | 0 | 0 | 0 | 0 | 0 | 0 | 1734749 | 312254 | [9 empty] | 2026-03-20 |  | 2026-03-27
18753 | Turnkey | 2026-01-01 | Tejas Galani | humlog chs | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | Anamika Ghate | Anamika Ghate | Savita Parab | Rizwan Mistry | Murali S | Ashish Jha | Aakash Gaikwad | Active | Installation | Execution | 1499649 | 1499649 | 2064225 | 0 | 1539649 | 18 | 6 | 0 | 0 | 0 | 0 |  |  | 2026-03-08 | 2026-03-08 11:55 | 2026-03-11 | 2026-03-15 13:43 | 2026-04-01 | 2026-04-09 12:17 | 2026-04-17 | 2026-04-17 15:41 | 2026-05-11 | 2026-05-10 11:52 | 2026-05-12 | 2026-05-12 20:40 | 2026-04-09 | 2026-03-31 | 2026-04-10 | 2026-04-09 17:44 | 2026-04-09 | 2026-04-10 13:01 | 2026-04-12 | 2026-04-12 11:43 |  |  |  |  | 2026-04-17 | 2026-04-28 19:49 | 2026-05-11 | 2026-05-10 12:06 | 2026-05-11 | 2026-05-10 13:42 |  |  | 2026-05-14 | 2026-05-16 13:20 | 2026-05-20 | 2026-05-20 19:42 | 2026-05-21 | 2026-05-20 21:05 | 2026-05-25 | 2026-05-23 13:40 |  |  |  |  | 2026-05-23 19:26 | 2026-05-30 | 2026-05-30 20:53 | 2026-06-11 | 2026-06-09 18:34 | 2026-06-10 | 2026-06-18 13:34 | 2026-06-09 | 2026-06-23 14:28 | 2026-06-22 | 2026-06-27 09:53 | 2026-06-28 | 2026-07-11 13:01 |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-05-20 | 2026-05-23 09:55 | 2026-04-13 | 2026-04-16 11:19 | Site is RTMI | 2026-03-08 | 2026-03-08 11:38 | 1752144 | 312080 | 0 | 0 | 1800858.2803 | 290921 | 1800858.2803 | 290921 | 2026-07-08 23:43:31 +0530 | Savita Parab | Execution: floor covering done carpentry in progress false ceiling done electrical in cx scope painting in progress modular delivered modular in progress bed eta is 12th july deep cleaning planned on 9th july only 3 bedroom kitchen handover planned on 9th july rest living and passage handover planned on 15th july | 2026-06-29 14:44:50 +0530 | Avinash Jaiswal | Some Image was uploaded | 2026-06-23 13:34:53 +0530 | Avinash Jaiswal | Some Image was uploaded | 2026-04-18 | 2026-04-17 15:41 | 2026-05-11 | 2026-05-10 11:52
18754 | Turnkey | 2026-01-01 | Bhawna Merchant | 10 bkc | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Nilesh Patel | Rizwan Mistry |  | Mrunali Mitkari | Aakash Gaikwad | Active | Preproduction | 2D | 8269774 | 946063 | 6000767 | 0 | 1499926 | 11 | 0 | 0 | 0 | 4098492 | 3225219.2 |  |  | 2026-03-07 | 2026-04-23 15:39 | 2026-04-16 | 2026-04-23 19:54 | 2026-04-26 | 2026-04-24 12:38 | 2026-05-23 | 2026-05-23 19:50 | 2026-06-24 | 2026-06-24 11:08 | 2026-06-24 | 2026-06-24 19:26 | 2026-04-24 | 2026-04-24 12:38 | 2026-04-25 | 2026-04-27 13:04 | 2026-04-27 | 2026-05-07 16:29 | 2026-05-09 | 2026-05-09 16:12 |  |  |  |  | 2026-05-23 | 2026-06-09 18:05 | 2026-06-25 | 2026-06-24 19:19 | 2026-06-25 | 2026-06-24 19:19 |  |  | 2026-06-26 | 2026-07-04 17:07 | 2026-06-30 |  | 2026-07-01 |  | 2026-07-15 | [6 empty] | 2026-07-25 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-23 |  | 2026-08-27 |  |  |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-20 | [5 empty] | 2026-06-30 |  | 2026-05-10 | 2026-05-23 19:41 | Site is RTMI | 2026-03-07 | 2026-03-08 11:41 | 5085396 | 915371 | 0 | 0 | 1590070.109 | 262361 | 8338774.1407 | 1375897 | 2026-06-09 11:44:47 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-09 16:11:50 +0530 | Reshma Melanta | CX HAS VISTED THE ANDHERI EC MET THE CX PERSONALLY RTMI PROJECT HO VP ADDED MY SELF TO THE GROUP THE CX HAS CIVIL WORK AND NEEDS THE POSSESSION OF THE HOUSE BY JANU 2027 WILL BE HAPPY IF WE GIVE THE SAME BY DECEMBER 2027 | 2026-05-07 16:28:34 +0530 | Bency Chacko | Handholding done RTMI Need to move in by the first week of December The customer has her civil work with us. Clear with the process, checklist, and timelines. Need to start as quickly as possible. The customer has no issues. Clear with PV, offers and checklist | 2026-05-24 | 2026-05-23 19:59 | 2026-06-25 | 2026-06-24 11:09 | RTMI
18755 | Turnkey | 2026-01-01 | Satish | SSVR Niyaara | BNG - HSR | Yes | Preethi Shetty | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2212035 | 9999 | 0 | 0 | 0 | 119 | 0 | 211205 | 221204 | 942236 | 827391.6 |  |  | 2026-03-08 | 2026-03-08 12:13 | 2026-03-17 | 2026-03-17 18:07 | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-04-15 |  | 2026-04-23 |  | 2026-04-24 |  |  |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-04 | [6 empty] | 2026-05-22 |  | 2026-05-31 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-03 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-05-02 |  | 2026-04-10 |  | Unknown | 2026-03-08 | 2026-03-08 12:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1874606 | 337429 | 2026-03-14 19:20:08 +0530 | Preksha Sajjanshettar | RGM 3bhkÂ 1540sqft property name : SS VR niyara west facing entranceÂ currently 4people , 2+ later budget : 7-10L Foyer : there is 11" area on the behind the entrance , there we have to plan shoe rackÂ Living :Â suspended tv unitÂ Â Entrance switch board should be coveredÂ sofa should be as per design , no preferenceÂ plan wardrobe with hidden door for bedroom 1 dining:Â there is a beam , cx want to beautify it with wooden design or hanging lightÂ Puja : tall puja 3ft w , with seating arrangement for old age people . wash areaÂ Balcony : washingÂ machine front load on the top , and bottom granite .Â gardening .Â Kitchen :-Â dishwasherÂ mixerÂ wet grinderÂ sinkÂ cook top and chimneyÂ aquagaurdÂ Handleless base , wall , loftÂ tall unit , breakfast counter granite UtilityÂ 3 cylinder, big sink ladder spaceÂ MBR : parents - age 50+ 11ft SwingÂ wardrobe with loft,Â cx want loft space on the bottom and wardrobe upper sideÂ hidden mirrorÂ tv panel only KBR :25age boyÂ SWING wardrobe with loft , tv unit cum studyÂ Guest bedroom :Â Â 2 studyÂ window wall we need bed with way window seater wardrobe with loftÂ Bathroom : vanity and mirrorÂ false ceiling : living and dining . | [6 empty] | 2026-04-15 |  | 2026-04-22
18756 | Turnkey | 2026-01-01 | Mr Prakash Parui | Lodha Casa Supremo | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Lost | Design | DEM1 | 1039738 | 89999 | 1319831 | 0 | 0 | 24 | 72 | 0 | 117949 | 454328 | 377462.4 |  |  | 2026-03-08 | 2026-03-13 14:37 | 2026-03-08 | 2026-03-13 16:38 | 2026-03-18 | 2026-03-18 19:43 | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-03-18 | 2026-03-31 | 2026-03-19 | 2026-04-04 14:20 | 2026-04-04 | 2026-04-10 10:46 | 2026-04-21 | 2026-04-21 11:01 |  |  |  |  | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-03-08 | 2026-03-08 12:19 | 1118501 | 201330 | 0 | 0 | 0 | 0 | 1088910.742 | 183010 | 2026-07-02 16:28:04 +0530 | Reshma Melanta | Others: | 2026-06-19 20:12:42 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-19 18:11:59 +0530 | Reshma Melanta | Some Image was uploaded | 2026-07-06 |  | 2026-07-13
18757 | Turnkey | 2026-01-01 | John Dev | Shriram sameeksha | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Mohammed Rasick |  | Hold | Design | 20% Payment | 700344 | 78999 | 794366 | 0 | 0 | 30 | 82 | 0 | 61070 | 367522 | 192753.6 |  |  | 2026-03-07 | 2026-03-09 12:48 | 2026-03-10 | 2026-03-10 13:16 | 2026-03-10 | 2026-03-10 15:08 | 2026-03-25 | 2026-03-25 11:09 | 2026-11-01 |  | 2026-11-08 |  | 2026-03-21 | 2026-03-09 19:27 | 2026-03-14 | 2026-03-10 14:41 | 2026-03-11 | 2026-03-10 17:05 | 2026-03-12 | 2026-03-12 19:00 |  |  |  |  | 2026-11-30 |  | 2026-11-03 |  | 2026-11-04 |  |  |  | 2026-11-11 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-14 | [6 empty] | 2026-12-02 |  | 2026-12-11 |  | 2026-12-10 |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-14 |  |  |  | 2027-01-05 |  | 2027-01-07 |  | 2027-01-08 | [5 empty] | 2026-11-12 |  | 2026-03-13 | 2026-03-22 19:00 | Site is RTMI | 2026-03-07 | 2026-03-09 12:08 | 673191 | 121174 | 0 | 0 | 0 | 0 | 670945.447 | 118272 | 2026-05-19 18:23:08 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-19 15:28:38 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-11 07:32:42 +0530 | Rajeshwari S | Some Image was uploaded | 2026-03-26 | 2026-03-25 11:12 | 2026-11-02
18758 | Turnkey | 2026-01-01 | Ketan Karekar | LODHA AMARA | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Nishtha Valawalkar |  | Lost | Design | DEM1 | 1559852 | 215999 | 2160246 | 0 | 0 | 106 | 0 | 0 | 95971 | 658579 | 589302.8 |  |  | 2026-03-08 | 2026-03-08 13:05 | 2026-03-08 | 2026-03-08 14:05 | 2026-03-22 | 2026-03-24 11:09 | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-03-24 | 2026-03-25 16:45 | 2026-03-25 | 2026-03-25 18:23 | 2026-03-25 | 2026-03-31 14:02 | 2026-04-10 | 2026-04-10 15:15 |  |  |  |  | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2027-12-30 |  | 2027-12-31 | [6 empty] | 2028-01-18 |  | 2028-01-27 |  | 2028-01-26 |  | 2028-01-27 |  | 2028-01-28 |  | 2028-01-30 |  |  |  | 2028-02-21 |  | 2028-02-23 |  | 2028-02-24 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-03-08 | 2026-03-08 12:53 | 1830717 | 329529 | 0 | 0 | 0 | 0 | 1797494.868 | 282180 | 2026-05-08 14:10:44 +0530 | Sarita Jangid | Some Image was uploaded | 2026-05-07 18:08:58 +0530 | Anil Kuwar | Others:we have provided cx 3 to 4 options in designing,but cx is asking for the cacnellation and cx is not stating the reason for it. | 2026-04-30 16:51:11 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-07-05 |  | 2026-07-12
18760 | Turnkey | 2026-01-01 | Vignesh Nair nair | Andheri East | MUM - GOR | Yes | Khushi Khandelwal |  | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 1151103 | 9999 | 1151103 | 0 | 0 | 103 | 0 | 105111 | 115110 | 503772 | 417110 |  |  | 2026-03-08 | 2026-03-08 17:21 | 2026-03-08 | 2026-03-22 13:28 | 2026-03-25 | 2026-04-03 15:52 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-08 | 2026-03-08 13:37 | 1161423.6045 | 197711 | 0 | 0 | 0 | 0 | 1161423.6045 | 197711 | 2026-04-15 13:53:28 +0530 | Moni Sahani | Some Image was uploaded | 2026-03-08 15:20:18 +0530 | Khushi Khandelwal | Some Image was uploaded |  |  |  | 2026-04-11 |  | 2026-04-18
18761 | Turnkey | 2026-01-01 | Nitesh Ghosalkar | Puranik Elito | MUM - Thane | Yes | Maasoumeh Raza | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 1011532 | 9999 | 0 | 0 | 0 | 129 | 0 | 91154 | 101153 | 429642 | 379584 |  |  | 2026-03-08 | 2026-03-08 13:54 | 2026-03-10 | 2026-03-10 18:20 | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-15 |  | 2026-03-16 | [5 empty] | 2026-03-22 |  | 2026-03-30 |  | 2026-03-31 |  |  |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 | [6 empty] | 2026-04-28 |  | 2026-05-07 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-10 |  |  |  | 2026-06-01 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-04-08 |  | 2026-03-17 |  | Unknown | 2026-03-08 | 2026-03-08 13:48 | 0 | 0 | 0 | 0 | 0 | 0 | 857230 | 154301 | 2026-03-08 15:04:05 +0530 | Rutuja Kotwal | DCM: Mr. Nitesh Ghosalkar. Puranik Elito vartak nagar thane west 360 sq.ft. Move in - 4 people Husband, wife and parents. - 70 yrs. Profession - Accounts wife - Hema Iyer - CA. Direction - Entering west Design as per basic vastu. Budget- 4 - 5 lakhs Living Room - Sofa cum bed , TV unit, Folding dining table ( cost will be understood in the later stage), Kitchen- Base Units, Wall Units and lofts. Service platform to be made with below storage. MBR- Sofa cum bed, Wardrobe with Lofts, side table with Mirror, Folding Study with shelves.. CDP- 14th March at 3pm. Budget suggested- 10 lakhs | [6 empty] | 2026-03-22 |  | 2026-03-29
18762 | Turnkey | 2026-01-01 | Pushpender nandel | Guru Krupa | MUM - GOR | No Estimate | Rishika Malviya |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-08 | 2026-03-11 19:38 | 2026-03-12 | 2026-03-13 17:05 | 2026-03-11 |  | 2026-03-23 |  | 2026-03-30 |  | 2026-04-06 |  | 2026-03-16 |  | 2026-03-17 |  | 2026-03-17 |  | 2026-03-18 | [5 empty] | 2026-03-24 |  | 2026-04-01 |  | 2026-04-02 |  |  |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 | [6 empty] | 2026-04-30 |  | 2026-05-09 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-12 |  |  |  | 2026-06-03 |  | 2026-06-05 |  | 2026-06-06 | [5 empty] | 2026-04-10 |  | 2026-03-19 |  | Unknown | 2026-03-08 | 2026-03-08 13:58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-15 16:58:13 +0530 | Umang Shah | Some Image was uploaded | 2026-03-13 17:37:08 +0530 | Rishika Malviya | DCM: Customer and Project Profile1. Name of the customer Pushpender Nandel 2. Profession Job 3. Project Name/Tower Name/Flat Number Gurukrupa 4. Typology (1BHK, 2BHK, 3BHK, etc) 2.5BHK 5. Site Access Date 2026-03-20 6. Possession Date 2026-05-30 7. Please mention the budget for interior designing (In INR Lakhs) Customer Preferences8. Who will be living in the house? Nuclear Family 9. What activities do you usually prefer at your home ? 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] Civil 11. Mention basic vastu principles agreed for integration in design, if any Yes 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) NA Upload reference images 14. Any absolute no-go styles colours or materials Dark colors 15. Do you have any existing furniture that must be accommodated? NA 13. Do you want the design to reflect any personal story, cultural influence, or special memory NA ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required No Dcor & Living Room1. Whats the primary use of your living room? TV Focus 2. Must-have furniture or features? Sofa, Display unit , Puja unit, TV unit 3. Choose your decor inspirations Artwork, Plants 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Parents 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Dresser 9. False Ceiling Required - Bedroom 1 No 10. Bedroom 2 - Utility Parents 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units Dresser 14. False Ceiling Required - Bedroom 2 No 15. Bedroom 3 - Utility Guests 16. Bedroom 3 - Bed Type Storage 17. Bedroom 3 - Wardrobe Style Swing 18. Bedroom 3 - Additional Units Dresser 19. False Ceiling Required - Bedroom 3 No Bathrooms1. Preferred vanity style 2. What do you prefer? NA 3. What are your requirements for Utility Area? NA Balcony & Outdoor1. How do you intend to use your balcony? Utility 2. Outdoor Mood How do you intend to use the utility Storage Miscellaneous1. Timeline related commitment made by Bonito, if any NA 2. Other commitments made by Bonito to customer, if any NA 3. What are offers committed to customers? NA 4. Move-in date confirmed with customer 2026-05-30 5. Any special occasion mentioned by the customer wrt handover date NA 6. Additional Requirements (Mention any requirements from customer not covered in the form) NA | 2026-03-08 15:45:00 +0530 | Rishika Malviya | Some Image was uploaded | 2026-03-24 |  | 2026-03-31
18763 | Turnkey | 2026-01-01 | Sneha dhimate | RustomjeeLaVie | MUM - GOR | Yes | Sakshi Hire |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1497456 | 9999 | 1497456 | 0 | 0 | 103 | 0 | 139747 | 149746 | 666950 | 531014.4 |  |  | 2026-03-08 | 2026-03-13 14:41 | 2026-03-08 | 2026-04-03 17:13 | 2026-04-06 | 2026-04-03 17:21 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-08 | 2026-03-08 14:51 | 1272051 | 225404 | 0 | 0 | 0 | 0 | 1272051 | 225404 | 2026-03-08 19:06:15 +0530 | Sakshi Hire | DCM: Thane west 2 adults husband in IT wife is in garment export may end possesion 3 ac granite has givenÂ shoe rack 20 pairs inside with partition safety door foldable dining with seating arrangement with storage mirror behind tall unit in soft wall right side foldableÂ partition window in balcony option mosquito net and invisible grill 3 +1 seater sofa with legs 65 tvÂ sleek drwer supspended double door vertically detergent unit aboveÂ pvc paneling for pipe opp side microwave unitÂ GBR mirror inside wardrobeÂ foldable study opp wall sofa cum bedÂ mandir seating level MBR queen size bed side tables dresser with storage tv unit with storage with decorÂ plain FC in Mbr and Livng Â sliding door on kitchen entry | [6 empty] | 2026-04-11 |  | 2026-04-18
18764 | Turnkey | 2026-01-01 | Chirag Mota | Mahavir Pride | MUM - Thane | Yes | Pooja Nakul Sharma | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 2105176 | 9999 | 0 | 0 | 0 | 129 | 0 | 200519 | 210518 | 851084 | 833056.8 |  |  | 2026-03-08 | 2026-03-08 15:36 | 2026-03-08 | 2026-03-10 10:54 | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-03-08 | 2026-03-08 15:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1784048 | 321128 | 2026-03-10 11:08:55 +0530 | Pooja Nakul Sharma | DCM: Mr MotaÂ 1+1 Bhk Mahavir (Dombivali) Soft poss- April 2026Â 1. Common wall is broken, 03 main door will be usable, 03 common bathroom brokedn and taken into the LR. 2. Outside area to be used for safety door, seating and shoe storage.Â 3. 03 kitchen- utility to be taken inside. 4. Tv unit, wall mount dining table (6 seater), Puja unit (standing with storage and door), Crockery unit on Com. bathroom wall (window is covered). (100 kg dabba's to be kept under console), 3+2 seater sofa, common beam design to be done.Â 5. MBR- King bed with storage (7*7 ft), wardrobe, foldable study, full mirror with storage behind.Â 6. 03 MBR- 6ft bed, 04 MBR- 7ft bed. 7. PBR- wardrobe with loft, king bed. 8. 04 MBR- L shape wardrobe with dresser.Â 9. PBR- Sofa cum bed/ Murphy, study unit with storage.Â 10. 03 kitchen- is opp as per the plan. Base, wall, loft unit 11. Base vanity storage in all bathrooms.Â 12. All balconies are 1.5ft deep. 13. Civil work- both kitchen utility to be taken inside (flooring+wall demolition).Â 14. False ceiling only in LR, minimal wall concepts, neutral colors+pastel colours.Â 15. CDP- 15th march at 3 pm.Â | 2026-03-08 15:21:13 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded |  |  |  | 2026-03-23 |  | 2026-03-30
18765 | Turnkey | 2026-01-01 | Arup | Pelican Square | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik | [5 empty] | Aman Kumar |  | Hold | Preproduction | DEM2 | 1810494 | 362099 | 2483711 | 0 | 0 | 47 | 22 | 0 | 0 | 815997 | 632397.6 |  |  | 2026-03-08 | 2026-03-08 16:43 | 2026-04-07 | 2026-04-07 16:40 | 2026-04-10 | 2026-04-09 11:30 | 2026-05-07 | 2026-05-10 18:42 | 2026-07-21 |  | 2026-07-28 |  | 2026-04-09 | 2026-04-14 10:26 | 2026-04-10 | 2026-04-17 11:41 | 2026-04-17 | 2026-04-20 15:36 | 2026-04-24 | 2026-04-24 12:31 |  |  |  |  | 2026-04-30 | 2026-05-06 18:22 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-04-25 | 2026-05-07 17:01 | Site is RTMI | 2026-03-08 | 2026-03-08 16:40 | 2104840 | 378871 | 0 | 0 | 0 | 0 | 2069956.6977 | 341770 | 2026-06-23 16:13:27 +0530 | Akshay Ds | Some Image was uploaded | 2026-04-24 12:20:33 +0530 | Akshay Ds | The customer is clear on the overall process. The site is currently not ready for initial measurements, as the flooring work is yet to be completed. The customer has confirmed that DEM1 will be conducted based on the floor plan. The 10% payment will be made post DEM1 (tentatively in the first week of May). Post DEM1, the project will be placed on hold until June. DEM1 is tentatively planned for the first week of May. | 2026-04-20 15:35:38 +0530 | Sanjana Swami | Possession expected by June 2026 IMs can be taken as the site is accessible next week Customer is available towards the weekends for designs. No concern was raised on the quotation and offers. Offers and the scope of work have been cleared. No onsite work has been planned by the customer. Customer will be opting for B2C self-funding. Customer will be paying 10% after the layouts are closed (DM 1 closure) | 2026-05-11 | 2026-05-10 18:43 | 2026-07-22 |  | Under Construction | 2026-06-30
18766 | Turnkey | 2026-01-01 | Abhishek Anand K | Bren Soho | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Hold | Design | DEM1 | 1634601 | 221790 | 2217901 | 0 | 0 | 32 | 80 | 0 | 105130 | 653840 | 653840.4 |  |  | 2026-03-08 | 2026-03-08 16:04 | 2026-03-15 | 2026-03-15 19:35 | 2026-03-15 | 2026-03-15 19:39 | 2027-06-09 |  | 2027-06-16 |  | 2027-06-23 |  | 2026-03-15 | 2026-03-18 19:00 | 2026-03-16 | 2026-03-18 19:01 | 2026-03-18 | 2026-03-25 15:39 | 2026-04-03 | 2026-04-03 19:46 |  |  |  |  | 2027-06-10 |  | 2027-06-18 |  | 2027-06-19 |  |  |  | 2027-06-26 |  | 2027-06-27 |  | 2027-06-28 |  | 2027-06-29 | [6 empty] | 2027-07-17 |  | 2027-07-26 |  | 2027-07-25 |  | 2027-07-26 |  | 2027-07-27 |  | 2027-07-29 |  |  |  | 2027-08-20 |  | 2027-08-22 |  | 2027-08-23 | [5 empty] | 2027-06-27 |  | 2027-06-05 |  | Unknown | 2026-03-08 | 2026-03-08 16:03 | 1879577 | 338323 | 0 | 0 | 0 | 0 | 1879576.87 | 310362 | 2026-06-20 12:41:39 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-22 18:25:18 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-11 16:38:35 +0530 | Abhinandan K S | Some Image was uploaded | 2027-06-10 |  | 2027-06-17 |  | Under Construction | 2027-05-31
18767 | Turnkey | 2026-01-01 | Gaurav Sharma | Kalpataru | MUM - Thane | Yes | Pooja Nakul Sharma | Anamika Dolai | [6 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 4786117 | 9999 | 0 | 0 | 0 | 129 | 0 | 468613 | 478612 | 1943804 | 1885089.6 |  |  | 2026-03-08 | 2026-03-08 22:13 | 2026-03-20 | 2026-04-28 12:02 | 2026-05-01 |  | 2026-05-08 |  | 2026-05-15 |  | 2026-05-22 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-02 |  | 2026-05-03 | [5 empty] | 2026-05-09 |  | 2026-05-17 |  | 2026-05-18 |  |  |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 | [6 empty] | 2026-06-15 |  | 2026-06-24 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-05-26 |  | 2026-05-04 |  | Unknown | 2026-03-08 | 2026-03-08 16:35 | 0 | 0 | 0 | 0 | 0 | 0 | 4056031 | 730085 | 2026-03-20 19:29:20 +0530 | Aryan Singh | Some Image was uploaded | 2026-03-20 12:30:10 +0530 | Pooja Nakul Sharma | DCM: Mr SharmaÂ Kalpataru ImmensaÂ 4BHKÂ Poss- Mid April 2026Â Family of 4 Social gatheringsÂ basic vastu to be followed 34th floor, 04 seriesÂ 1. Shoerack outside along with seating, safety door 2. Foyer storage with wall concept. 3. Sofa seating, TV unit/ projector screen, dining 6 seater, crockery unit/ concealed storage in the niche.Â 4. Puja unit as per vastu, with storage.Â 5. Kitchen- Option open for countertop replacement (to be checked as per actual site). 6. Utility area- DW, WM, additional sinkÂ 7. Kitchen- Base, wall, loft units.Â 8. Store room- Puja unit/ washing machine.Â 9. Passage niche- full height storage 10. Bedroom 1 - Daughter's bedroom (Parents might also use it). King bed with storage, Wardrobe, Walk in wardrobe with bathroom civil. Study unit, dresser, Tv wall to be planned.Â 11. Bathroom vanity. 12. Guest room- Entertainment room with sofa cum bed. Storage to be planned if possible.Â 13. Bedroom 2- Son's room (studying 11th std). Queen bed (5.5x6.5), wardrobe, study unit with storage, Full mirror with storage.Â 14. MBR - King bed, TV wall, dresser with storage, Walk in wardrobe with dresser, study, vanity units to be planned.Â 15. Bathroom civil- tiles to be changed, wc to be changed to wall mount one.Â 16. FLooring to be chnaged as well, 6x8 ft tiles.Â 17. Balcony - seating, wall concept. 18. No dark bright colours.Â 19. Budget- 30-40L 20. CDP planned- 26th March | 2026-03-08 16:32:50 +0530 | Aryan Singh | Some Image was uploaded | 2026-05-09 |  | 2026-05-16
18768 | Turnkey | 2026-01-01 | Akshay Sriram | Casagrand flamingo | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik |  |  | Yogeshwaran | Ranjith Kumar |  | Fuzail Girach |  | Active | Preproduction | DEM2 | 1364183 | 273333 | 1673333 | 0 | 0 | 72 | 0 | 0 | 0 | 548562 | 542287.6 |  |  | 2026-03-08 | 2026-03-14 16:35 | 2026-03-15 | 2026-03-15 13:35 | 2026-03-15 | 2026-03-15 13:45 | 2026-05-04 | 2026-05-04 12:08 | 2026-07-26 |  | 2026-08-02 |  | 2026-03-15 | 2026-03-24 13:25 | 2026-03-16 | 2026-04-04 14:41 | 2026-04-04 | 2026-04-09 17:10 | 2026-04-14 | 2026-04-14 16:05 |  |  |  |  | 2026-05-04 | 2026-05-04 12:55 | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-04-15 | 2026-05-04 12:04 | Site is RTMI | 2026-03-08 | 2026-03-08 16:28 | 1418079 | 255254 | 0 | 0 | 0 | 0 | 1418078.818 | 244706 | 2026-07-10 11:52:19 +0530 | Chittipireddy Sriharish | DDM2: Living room Wall accent - sofa wall (charcoal beadings) TV wall - charcoal beadings Crockery unit wall - existing puja unit need to be placed wall mounted Kitchen No changes Master bedroom Wall accents need to be added Kids bedroom Wall accents need to be added - minimalistic & simple Guest bedroom Wall accents need to be added - minimalistic & simple Wardrobe internals need to be cross checked with client once | 2026-05-01 11:58:48 +0530 | Chittipireddy Sriharish | DDM1: Kitchen Counter top - installation Master bedroom Dresser unit | 2026-04-09 17:08:37 +0530 | Bency Chacko | Some Image was uploaded | 2026-05-05 | 2026-05-04 12:09 | 2026-07-27 |  | Under Construction | 2026-04-30
18769 | Turnkey | 2026-01-01 | Jawahar B. Goradia | Sky rise | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Design | DEM1 | 1081342 | 216269 | 1369989 | 0 | 0 | 112 | 0 | 0 | 0 | 445347 | 419726 |  |  | 2026-03-08 | 2026-03-10 11:07 | 2026-03-09 | 2026-03-15 22:28 | 2026-03-18 | 2026-03-19 15:27 | 2026-11-26 |  | 2027-02-24 |  | 2027-03-03 |  | 2026-03-19 | 2026-03-21 12:24 | 2026-03-20 | 2026-03-21 18:57 | 2026-03-21 | 2026-03-25 15:34 | 2026-04-10 | 2026-04-10 12:32 |  |  |  |  | 2026-05-22 | 2026-05-07 19:03 | 2027-02-26 |  | 2027-02-27 |  |  |  | 2027-03-06 |  | 2027-03-07 |  | 2027-03-08 |  | 2027-03-09 | [6 empty] | 2027-03-27 |  | 2027-04-05 |  | 2027-04-04 |  | 2027-04-05 |  | 2027-04-06 |  | 2027-04-08 |  |  |  | 2027-04-30 |  | 2027-05-02 |  | 2027-05-03 | [5 empty] | 2027-03-07 |  | 2027-01-07 |  | Site is RTMI | 2026-03-08 | 2026-03-08 16:30 | 1161008 | 208981 | 0 | 0 | 0 | 0 | 1150472.625 | 189357 | 2026-04-30 19:13:35 +0530 | Meet Shah | Some Image was uploaded | 2026-04-15 12:21:05 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-10 12:35:11 +0530 | Manzoor Shaikh | "Welcome call done. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : December 2026 Customer will make 10% on 15th April FDM dates: TBD Price protection for 150 days from the NET date." | 2026-11-27 |  | 2027-02-25 |  | Under Construction | 2026-12-31
18770 | Turnkey | 2026-01-01 | Priya Shalini | Adarsh Park Heights | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Fuzail Girach |  | Active | Prospect | DCM Due | 1086490 | 9999 | 0 | 0 | 0 | 118 | 0 | 98650 | 108649 | 434596 | 434596 |  |  | 2026-03-08 | 2026-03-19 12:05 | 2026-03-19 | 2026-03-19 12:11 | 2026-03-14 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-03-08 | 2026-03-08 16:28 | 0 | 0 | 0 | 0 | 0 | 0 | 920754 | 165735 | 2026-03-19 12:06:12 +0530 | Rajasekar Ranganathan | PRIYA SHALINI 18770 RGM 9/03/2026 ENTRANCE FOYER AREA Shoe rack outside 20 pairs Miscellaneous unitWall finish in glassLIVING AREA TV unit, Key holder provision AC partition, Track lightsDecor for sofa wall, PujaDINING Crockery unit, Appliances pullout Simple decor, Puja items partKITCHEN Fridge, Tall unit open for Applua, Granite from builder, Cylinder, Full kitchen, Existing dishwasher, RO existing. UTILITY Washing machine, Cabinet for dishwasher. BALCONY Janitor rod BEDROOM 1 (Kids Room) Wardrobe sliding, Study table, Dresser, Side table, No loft. Toys unit, Hanging optionBEDROOM 2 (MBR) Walk-in closet, Dresser, Study table with library, Wall decor, Bed with headboard, Hanging optionBATHROOMS (BOTH) Vanity unit with mirror, Open storage on WC. | [6 empty] | 2026-03-30 |  | 2026-04-06
18772 | Turnkey | 2026-01-01 | Srinivas Laishetty | Ayodhya | MUM - Thane | Yes | Moksh Mehta | Anamika Dolai | [6 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 1691608 | 9999 | 0 | 0 | 0 | 129 | 0 | 159162 | 169161 | 713379 | 639907.2 |  |  | 2026-03-08 | 2026-03-08 16:55 | 2026-03-11 | 2026-03-11 17:02 | 2026-03-13 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-03-13 |  | 2026-03-14 |  | 2026-03-14 |  | 2026-03-15 | [5 empty] | 2026-03-21 |  | 2026-03-29 |  | 2026-03-30 |  |  |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 | [6 empty] | 2026-04-27 |  | 2026-05-06 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-09 |  |  |  | 2026-05-31 |  | 2026-06-02 |  | 2026-06-03 | [5 empty] | 2026-04-07 |  | 2026-03-16 |  | Unknown | 2026-03-08 | 2026-03-08 16:50 | 0 | 0 | 0 | 0 | 0 | 0 | 1433566 | 258041 | 2026-03-11 16:57:38 +0530 | Moksh Mehta | DCM: Client Name:- Srinivas Lai Shetty Property:- Ahyodya Possesion Date:- Mar 26 Sq Ft:- 1016 sqft No of Members: - 4 Couple 45 & 40 + Boys 21 & 18. Budget:- 10L-15L exp set for 15L - 20L. Ent: Shoe Rack (15 - 20 Pairs).Wall Concepts. Living Room :- TV Unit (55") with Mandir.3 Seater Sofa + 1 Chair (6 Peoples).Wall concepts.Mandir Unit.Swing if possible. Dining Area :- 6 Seater Dining Table.Wall Concepts. Kitchen :- Semi Modular Kitchen.Base - 1 nos , Wall - 1nos & Loft - 1 nos.All generic appliances Master Bedroom:- 080 Queen size Bed with StorageWardrobe with LoftSide tale Bedroom 3:- Getting converted to master with kitchen of 07 Queen Size Bed with StorageWardrobe with LoftSide Table (Optional)Folding Study Table. Bedroom :- 07 Queen Size Bed with StorageWardrobe with loftSide TableFolding Study Table Bathroom's Base Vanity Unit's for allStorages in balconies Misc:- False Ceiling Painting Electrification. | [6 empty] | 2026-03-21 |  | 2026-03-28
18774 | Turnkey | 2026-01-01 | Kishor | Aadarsh park height | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 1406485 | 9999 | 0 | 0 | 0 | 120 | 0 | 130650 | 140649 | 595406 | 529782.4 |  |  | 2026-03-08 | 2026-03-08 18:27 | 2026-03-10 | 2026-03-10 22:30 | 2026-03-17 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-03-08 | 2026-03-08 18:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1191936 | 214548 | 2026-03-17 14:49:58 +0530 | Preksha Sajjanshettar | RGM Client - KishorÂ RGMÂ 2 persons (with 2year old daughter) West facing 2BHK Design Engineer May - 2026 Foyer AreaÂ Tall unitÂ and Shoe rack with seating - 10-12 pairs Wall TreatmentsÂ Living AreaÂ L - Shape SofaÂ TV unit Tall with base unitÂ wallpaper (avoid mirror) 50" TVÂ Wall treatment on sofa back wall and tv back wallÂ Dining areaÂ 6-SeaterÂ Crockery unit with pantry unitÂ Pooja Unit to be consideredÂ KitchenÂ double door fridge - top-bottom doorÂ OTG Unit provision for appliance unit BASE-TOP-LOFT unit Smaller SinkÂ RO - top mount outside (Utility) HOB-4Burner Loft to be considered UtilityÂ Bigger SinkÂ Washing machineÂ Top cabinetÂ Granite from Bonito Master bedroomÂ W-I-W - L shapeÂ Wardrobe (openable) Dresser unit next to w-i-w next to Dresser side table needed King size BED Center false ceilingÂ Bay seating with tall unit continued by Study unitÂ simple TV unit provision with wall ledgeÂ Wall treatment for bed headboardÂ MBR and GBR Toilet VanityÂ Guest bedroomÂ Queen sizeÂ Sliding wardrobe (consider according to space) side tableÂ Dresser unitÂ Study unit with top storageÂ Wall treatment for bed headboardÂ Center false ceilingÂ BalconyÂ TOP storage - open Budget - 15Lac | [6 empty] | 2026-03-25 |  | 2026-04-01
18775 | Turnkey | 2026-01-01 | Abinash Padhi | SNN RAJ Serenity | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Priyanka Mathur | [5 empty] | Chanakya Panigrahi |  | Lost | Design | DEM1 | 1269099 | 139999 | 1695340 | 0 | 0 | 111 | 0 | 0 | 113821 | 553350 | 461928.8 |  |  | 2026-03-08 | 2026-03-08 18:49 | 2026-03-15 | 2026-03-15 10:41 | 2026-03-18 | 2026-03-17 11:58 | 2026-07-22 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-03-17 | 2026-03-20 13:29 | 2026-03-18 | 2026-03-24 14:55 | 2026-03-24 | 2026-03-26 12:19 | 2026-04-03 | 2026-04-03 19:48 |  |  |  |  | 2026-07-23 |  | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-07-18 |  | Site is Non-RTMI | 2026-03-08 | 2026-03-08 18:48 | 1436729 | 258611 | 0 | 0 | 0 | 0 | 1431152.0986 | 236303 | 2026-05-08 12:00:40 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-23 18:12:07 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-03-26 12:18:40 +0530 | Bency Chacko | Design meetings - After the 2nd week of April 2026 Site access - No idea Possession - Towards May The customer will close the 10% payments in May. Timelines cleared, checklist cleared No on-site scope is planned Quotes and Offers are cleared B2C - Self-funding | 2026-07-23 |  | 2026-07-30 |  | Under Construction | 2026-05-13
18776 | Turnkey | 2026-01-01 | MR. SUMEET SINGH GHAI | Veena Synergy | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  |  | Uday Yadruk | Rizwan Mistry |  | Manasi Patil | Siddhesh Gujrathi | Active | Design | DEM3 | 1104857 | 220972 | 1415456 | 0 | 0 | 1 | 0 | 0 | 0 | 486686 | 397199.2 |  |  | 2026-03-08 | 2026-03-13 17:10 | 2026-03-13 | 2026-03-13 17:35 | 2026-03-15 | 2026-03-15 11:28 | 2026-04-18 | 2026-04-18 18:13 | 2026-06-20 |  | 2026-07-18 |  | 2026-03-15 | 2026-03-25 16:52 | 2026-03-16 | 2026-03-25 16:55 | 2026-03-25 | 2026-03-28 13:00 | 2026-04-09 | 2026-04-09 14:06 |  |  |  |  | 2026-04-19 | 2026-04-24 19:00 | 2026-07-12 | 2026-07-14 10:36 | 2026-07-15 | 2026-07-14 10:37 |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-04-10 | 2026-04-18 16:16 | Site is Non-RTMI | 2026-03-08 | 2026-03-13 17:08 | 1199539 | 215917 | 0 | 0 | 0 | 0 | 1174809.2962 | 192944 | 2026-05-06 17:59:27 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-06 17:58:37 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-14 11:01:52 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-19 | 2026-04-19 18:12 | 2026-06-21 |  | Under Construction | 2026-06-30
18777 | Turnkey | 2026-01-01 | Suhas Deshmukh | Godrej ascend | MUM - Thane | Yes | Garv Sharma | Sarita Jangid | [6 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 1741882 | 9999 | 0 | 0 | 0 | 129 | 0 | 164189 | 174188 | 753210 | 640295.6 |  |  | 2026-03-08 | 2026-03-08 19:41 | 2026-03-19 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-03-08 | 2026-03-08 19:39 | 0 | 0 | 0 | 0 | 0 | 0 | 1476172 | 265710 | [9 empty] | 2026-03-30 |  | 2026-04-06
18778 | Turnkey | 2026-01-01 | Tejas shah | Everest World | MUM - GOR | Yes | Sakshi Hire |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | DCM Due | 2798732 | 9999 | 2798732 | 0 | 0 | 103 | 0 | 269874 | 279873 | 1198553 | 1040432.4 |  |  | 2026-03-08 | 2026-04-03 16:57 | 2026-03-11 | 2026-04-03 17:53 | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-08 | 2026-03-08 19:44 | 2371807 | 426925 | 0 | 0 | 0 | 0 | 2371807 | 426925 | 2026-04-15 16:59:23 +0530 | Umang Shah | Some Image was uploaded | 2026-03-11 19:28:52 +0530 | Sakshi Hire | DCM: vile parle eastÂ already got possesion 5 adults 1 child 11' height sons bedroom study bed with storage side tableÂ wardrobe loft dresser master bedroom workstationÂ king bed side tables dresser window seating front side half window wardrobe & loft daughter plus motherbedroomÂ study bed with storage side tableÂ wardrobe loft dresser 2 kitchen breakfast counter counter storage 50kg or more pantryÂ dishwasher washing machine & dryer cleaning robeÂ microwave airfryer toaster mixer quartz look diningÂ 6 dining set pooja room in dining with glass partition crockery below storage living 55" jhula tv unit below storage floatingÂ safety doorÂ shoe rack in lobby false ceiling in living & dining |  |  |  | 2026-04-11 |  | 2026-04-18
18779 | Turnkey | 2026-01-01 | Vaishali Jadhav | Shreeji paraiso | MUM - Thane | Yes | Moksh Mehta | Anamika Dolai | [6 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1747272 | 9999 | 0 | 0 | 0 | 125 | 0 | 164728 | 174727 | 764767 | 633050.4 |  |  | 2026-03-08 | 2026-03-11 14:36 | 2026-03-10 | 2026-03-12 11:51 | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-03-08 | 2026-03-11 14:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1480739 | 266533 | 2026-03-10 18:46:06 +0530 | Karuna Shinde | Some Image was uploaded | [6 empty] | 2026-03-23 |  | 2026-03-30
18780 | Turnkey | 2026-01-01 | Rajesh Mehta | anand mangal | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [7 empty] | Active | Design | DEM1 | 1699205 | 224999 | 2214062 | 0 | 0 | 38 | 73 | 0 | 114842 | 735123 | 624241.2 |  |  | 2026-03-08 | 2026-03-14 11:30 | 2026-03-14 | 2026-03-24 15:01 | 2026-03-24 | 2026-03-24 15:46 | 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-03-24 | 2026-03-25 12:46 | 2026-03-25 | 2026-03-25 20:35 | 2026-03-25 | 2026-03-26 11:54 | 2026-03-30 | 2026-03-30 15:17 |  |  |  |  | 2026-08-09 |  | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-05-11 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-08-04 |  | Unknown | 2026-03-08 | 2026-03-14 11:29 | 1878611 | 335451 | 0 | 0 | 0 | 0 | 1843982.4605 | 306489 | 2026-05-16 15:56:20 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-15 17:06:13 +0530 | Vishakha Vaishnav | Tried connecting the customer , cx disconnected the call | 2026-03-31 17:13:02 +0530 | Reshma Melanta | ADDED MYSELF TO THE GROUP | 2026-08-09 |  | 2026-08-16
18781 | Turnkey | 2026-01-01 | Sonal Shekhar | Prestige Merdian | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Priyanka Mathur |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Varun Mandana | Sunil Kumar S M | Active | Installation | Execution | 1238465 | 1238466 | 1796634 | 0 | 1238465 | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-08 | 2026-03-18 17:23 | 2026-03-18 | 2026-03-18 19:04 | 2026-03-18 | 2026-03-20 15:48 | 2026-04-23 | 2026-04-23 18:05 | 2026-05-15 | 2026-05-14 10:26 | 2026-05-24 | 2026-05-24 20:15 | 2026-03-20 | 2026-03-24 13:29 | 2026-03-21 | 2026-04-04 11:08 | 2026-04-04 | 2026-04-04 12:32 | 2026-04-11 | 2026-04-11 19:23 |  |  |  |  | 2026-04-23 | 2026-05-10 16:22 | 2026-05-15 | 2026-05-14 18:07 | 2026-05-15 | 2026-05-14 18:09 |  |  | 2026-05-25 | 2026-05-25 17:50 | 2026-05-25 | 2026-05-25 19:57 | 2026-05-26 | 2026-05-25 20:12 | 2026-05-26 | 2026-05-27 20:02 |  |  |  |  | 2026-05-29 16:07 | 2026-06-06 | 2026-06-05 21:32 | 2026-06-21 | 2026-06-20 13:02 | 2026-06-20 | 2026-06-21 12:57 | 2026-06-20 | 2026-07-03 16:11 | 2026-07-03 | 2026-07-04 11:40 | 2026-07-14 | 2026-07-13 16:04 |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-05-25 | 2026-05-28 19:04 | 2026-04-12 | 2026-04-23 15:49 | Site is RTMI | 2026-03-08 | 2026-03-10 14:46 | 1522572 | 274062 | 0 | 0 | 1481336.8825 | 236206 | 1481336.8825 | 236206 | 2026-07-06 15:47:27 +0530 | Ranjith Kumar | Execution: | 2026-06-29 10:45:02 +0530 | Ranjith Kumar | Dispatch Due: | 2026-06-22 13:14:57 +0530 | Ranjith Kumar | Cx Side - Demolition, Electrical Bonito Side - False Ceiling - WIP Cx Dependency & Floor Covering Done | 2026-04-24 | 2026-04-23 18:06 | 2026-05-15 | 2026-05-14 10:26 | RTMI
18783 | Turnkey | 2026-01-01 | Ina Mehta | Ajmera Manhattan | MUM - GOR | No Estimate | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-09 | 2026-03-09 16:24 | 2026-03-10 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-04-16 |  | 2026-04-23 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-03 |  | 2026-04-04 | [5 empty] | 2026-04-10 |  | 2026-04-18 |  | 2026-04-19 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 | [6 empty] | 2026-05-17 |  | 2026-05-26 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-29 |  |  |  | 2026-06-20 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-04-27 |  | 2026-04-05 |  | Unknown | 2026-03-09 | 2026-03-09 16:19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-10 |  | 2026-04-17
18784 | Turnkey | 2026-01-01 | Mandar Vaidya | Rustomjee crown | MUM - GOR | Yes | Priyanka Patel |  | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 2646587 | 10000 | 0 | 0 | 0 | 103 | 0 | 254659 | 264659 | 1058635 | 1058634.8 |  |  | 2026-03-09 | 2026-03-17 19:34 | 2026-03-23 | 2026-03-23 15:33 | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-05 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-09 | 2026-03-10 11:29 | 0 | 0 | 0 | 0 | 0 | 0 | 2242871 | 403716 | 2026-04-15 17:08:03 +0530 | Umang Shah | Some Image was uploaded | [6 empty] | 2026-04-11 |  | 2026-04-18
18785 | Turnkey | 2026-01-01 | Ambiti Chinmayi | Sai Orchid | BNG - HSR | Yes | Chittipireddy Sriharish | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 1695985 | 9999 | 0 | 0 | 0 | 128 | 0 | 159600 | 169599 | 687662 | 669125.6 |  |  | 2026-03-08 | 2026-03-09 18:58 | 2026-03-09 |  | 2026-03-14 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-03-14 |  | 2026-03-15 |  | 2026-03-15 |  | 2026-03-16 | [5 empty] | 2026-03-22 |  | 2026-03-30 |  | 2026-03-31 |  |  |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 | [6 empty] | 2026-04-28 |  | 2026-05-07 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-10 |  |  |  | 2026-06-01 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-04-08 |  | 2026-03-17 |  | Unknown | 2026-03-08 | 2026-03-09 18:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1437276 | 258709 | 2026-03-14 16:59:13 +0530 | Chittipireddy Sriharish | CDP: Kitchen wall ledges need to be added below the wall unit s Master bedroom Bed placement need to be confirmed by client accordingly, wardrobe will be decided Guest bedroom study unit - need to be designed as per reference Kids bedroom Wall ledges need to be added | 2026-03-14 16:53:51 +0530 | Chittipireddy Sriharish | CDP: Living room TV unit Tall unit need to be replaced with wall ledges Puja unit need to discussed in detail (placement need to be finalized) Kitchen | 2026-03-11 19:34:50 +0530 | Chittipireddy Sriharish | DCM: Foyer Shoe rack with sitting space (7 members) Living room Tv unit with tall unit Puja unit next to the tv unit False ceiling Wall accents Dining Area Crockery unit Kitchen 2 feet sink need to be considered Granite - need to be considered Utility 3 feet sink need to be considered MBR Wardrobe - 7 feet Dresser study GBR - Bedroom 1 wardrobe study unit Dresser unit KBR - Bedroom 2 Wardrobe Study unit | 2026-03-22 |  | 2026-03-29
18786 | Turnkey | 2026-01-01 | Narayan Chavan | Hiranandani castalia | MUM - GOR | Yes | Anjali Jain | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Umang Shah |  | Hold | Preproduction | DEM2 | 1098857 | 219722 | 1385051 | 0 | 0 | 0 | 73 | 0 | 0 | 444816 | 434319.2 |  |  | 2026-03-09 | 2026-03-13 11:41 | 2026-03-13 | 2026-03-13 20:34 | 2026-03-14 | 2026-03-14 21:06 | 2026-04-30 | 2026-04-30 19:17 | 2027-01-01 |  | 2027-01-08 |  | 2026-03-14 | 2026-03-14 21:14 | 2026-03-15 | 2026-03-14 21:15 | 2026-03-14 | 2026-03-24 12:48 | 2026-03-31 | 2026-03-31 14:31 |  |  |  |  | 2026-04-30 | 2026-05-08 19:34 | 2027-01-03 |  | 2027-01-04 |  |  |  | 2027-01-11 |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 | [6 empty] | 2027-02-01 |  | 2027-02-10 |  | 2026-05-06 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-13 |  |  |  | 2027-03-07 |  | 2027-03-09 |  | 2027-03-10 | [5 empty] | 2027-01-12 |  | 2027-01-15 | 2026-04-30 17:17 | Site is RTMI | 2026-03-09 | 2026-03-10 11:20 | 1173772 | 211278 | 0 | 0 | 0 | 0 | 1168570.7212 | 192029 | 2026-05-03 20:38:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-30 19:21:42 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-30 19:17:44 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-01 | 2026-04-30 19:17 | 2027-01-02
18789 | Turnkey | 2026-01-01 | Keerthi Kumar S R | Purvi arvindam | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Hold | Preproduction | Site Readiness 1 | 1502212 | 300442 | 1978494 | 0 | 0 | 22 | 69 | 0 | 0 | 625457 | 576313.2 |  |  | 2026-03-08 | 2026-03-24 13:20 | 2026-03-11 | 2026-03-25 09:39 | 2026-03-28 | 2026-03-25 17:06 | 2026-04-07 | 2026-04-07 13:51 | 2026-08-29 |  | 2026-09-05 |  | 2026-03-25 | 2026-03-26 12:23 | 2026-03-26 | 2026-03-26 14:16 | 2026-03-26 | 2026-03-27 14:48 | 2026-03-31 | 2026-03-31 18:47 |  |  |  |  | 2026-04-07 | 2026-04-15 18:29 | 2026-08-31 |  | 2026-09-01 |  |  |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 | [6 empty] | 2026-09-29 |  | 2026-10-08 |  | 2026-10-07 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-11 |  |  |  | 2026-11-02 |  | 2026-11-04 |  | 2026-11-05 | [5 empty] | 2026-09-09 |  | 2026-04-01 | 2026-04-07 12:51 | Site is Non-RTMI | 2026-03-08 | 2026-03-10 11:58 | 1676690 | 301804 | 0 | 0 | 0 | 0 | 1615428.1758 | 266738 | 2026-06-16 22:59:41 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-02 01:43:18 +0530 | Ashiya Sanam | Minutes of Meeting held on Date: Title:design discussion Project:18789 Client: Attendees:ashiya Objective: Discussion Based on the meeting, below is a list of all the requirements that were discussed during the meeting: Living Room: 1.Pooja unit-GOPURAM on top with three steps 2.cnc door and drawers to be outsideÂ 3.Internals same as per design 4.Partition as per reference image 5.Fridge wall to be addedÂ 6.Arch design to end till the sofa wall 7.fan and chandeliers position to be given 8.strip designs on tv back panel 9.breakfast counter base unit with louvers behind 10.Breakfast top shelf to be in curve and bottom in rectangle with louvers below covering the whole unit 11.FRIDGE back wall design to be suggested Kitchen: 1.units as per cdp design to cover the whole kitchen Utility: 1.Sink unit half area to be provided for cylinder provision Study Room: 1.study table to be removed as L shape consider 4ftÂ 2.Dresser drawer to be removed 3.Mirror to have border lighting 4.L corner shutter to be as per reference Guest bedroom: 1.Loft on top of study to be covered 2.Wardrobe colour patterns with DC pattern to be suggested Master bedroom: 1.Wall designs as per reference image 2.Sliding wardrobe to be added instead of openable wardrobe 3.Used clothes provision wardrobe to be less than 2 ft-provide grill cut out | 2026-04-20 11:08:25 +0530 | Ashiya Sanam | Minutes of Meeting held on Date: 07-04-26 Title:DEM-1 Project:18789 Client:Keerthi Kumar Attendees: Ashiya Objective: Discussion Based on07-04-26 at meeting, below is a list of all the requirements that were discussed during the meeting: FoyerThe shoe rack is not included in the current quotation, as discussed.to be added as per offer Living AreaThe overall living area layout was finalisedA partition next to the pooja unit to be added as pillars on both sides and ledges and hanging lamp space to be providedThis partition is not included in the current quote. Dining AreaCrockery unit was finalisedPanelling / punning work above the beam will be required to achieve a finished look.and a arch to added with a step up for the breakfast counter towards the counter KitchenThe overall kitchen layout was reviewed As per site readiness need to re discuss on the kitchen layout and alignment of cabinetsThis tall unit is included in the current quotation.Utilityutility two cylinders provision to be givencheck space for washing machine and dishwasher Master BedroomDresser storage has been modified as per the clients requirement.The revised dresser storage is included in the current quote.wardrobe to go with sliding with drawers below the wardrobe Guest Bedroom:1.Layout is finalised, changes as per the IM File Bedroom 2: 1.Study unit to be changed as er vastu constraints 2.Layout is finalised *To Add a wall unit in balcony and a foldable ledge *Closed units to be added in the dining area sink Scope ExclusionsThe following items are not included in the current quotation, as discussed and acknowledged:False ceiling worksElectrical worksPainting worksElectrical points and wiring requirements will be discussed and finalised during the crossmeasurement stage, based on finalised designs. Wardrobe Internals All product internals were reviewed and explained during the meeting.Additional drawerswill have a cost impact on the final quotation. | 2026-04-08 | 2026-04-07 13:54 | 2026-08-30 |  | Under Construction | 2026-07-31
18790 | Turnkey | 2026-01-01 | Mrs. Manju Jain | Lodha Bellagio | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Active | Preproduction | DEM2 | 1770479 | 354096 | 2173474 | 0 | 0 | 26 | 21 | 0 | 0 | 726060 | 690322.8 |  |  | 2026-03-07 | 2026-03-17 15:02 | 2026-04-19 | 2026-04-19 19:52 | 2026-04-22 | 2026-04-19 20:04 | 2026-05-17 | 2026-05-17 18:52 | 2026-07-09 |  | 2026-07-16 |  | 2026-04-19 | 2026-04-20 12:34 | 2026-04-20 | 2026-04-21 12:46 | 2026-04-21 | 2026-04-29 09:39 | 2026-05-08 | 2026-05-08 13:39 |  |  |  |  | 2026-05-17 | 2026-06-19 14:14 | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-05-09 | 2026-05-17 14:05 | Site is RTMI | 2026-03-07 | 2026-03-10 12:11 | 1845052 | 328421 | 0 | 0 | 0 | 0 | 1932752.7255 | 322625 | 2026-06-19 14:17:15 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-16 16:59:09 +0530 | Vishakha Vaishnav | CX said that she will connect tommo by 12pm | 2026-05-29 18:48:28 +0530 | Reshma Melanta | Minutes of Meeting (MOM)Project ID: 18790 Client Name: Mrs. Manju Jain Date of Call: 29th May 2026 Background & Key EscalationsSales vs. Design Alignment: The client highlighted an issue regarding commitments made during the sales phase. They were initially informed that the Bonito team would handle the entire scope of work. However, during the Design Execution Meeting (DEM-1) at the transition milestone, the Designer indicated certain requirements were not feasible. This discrepancy triggered the client's escalation.Follow-up Alignment Meeting: A meeting was scheduled for the subsequent day to resolve these pointers. When the 10% milestone payment was requested, the client stated they attended the meeting with a mindset focused on seeking a refund.Discussion Points (Call on 29th May 2026)Communication Gaps: The client's husband joined the discussion and noted he was completely unaware of both the 10% payment milestone requirement and the Onboarding Call process.Client's Current Stance: The client explicitly stated that they need to see the requested changes/rectifications implemented before committing to move forward with Bonito Designs. | 2026-05-18 | 2026-05-17 19:38 | 2026-07-10
18795 | Turnkey | 2026-01-01 | Anandamayee sahoo & Shashank Kumar | Samhita Serene Mtb | BNG - HRBR | Yes | Salpriyan Pm | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Hold | Preproduction | Site Readiness 1 | 1387702 | 215691 | 1423025 | 0 | 0 | 5 | 60 | 0 | 0 | 642936 | 529075.2 |  |  | 2026-02-28 | 2026-04-03 18:49 | 2026-03-01 | 2026-04-03 18:54 | 2026-04-03 | 2026-04-03 19:06 | 2026-05-04 | 2026-05-03 13:59 | 2026-07-14 |  | 2026-08-20 |  | 2026-04-03 | 2026-03-31 | 2026-04-04 | 2026-04-04 18:29 | 2026-04-04 | 2026-04-06 13:30 | 2026-04-10 | 2026-04-10 18:54 |  |  |  |  | 2026-05-30 | 2026-05-29 18:33 | 2026-08-15 |  | 2026-08-16 |  |  |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 | [6 empty] | 2026-09-13 |  | 2026-09-22 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-25 |  |  |  | 2026-10-17 |  | 2026-10-19 |  | 2026-10-20 | [5 empty] | 2026-08-24 |  | 2026-04-11 | 2026-05-03 13:53 | Site is Non-RTMI | 2026-02-28 | 2026-04-03 17:57 | 1205953 | 217071 | 0 | 0 | 0 | 0 | 1528801.879 | 252488 | 2026-06-25 11:29:18 +0530 | Arjun M V | Some Image was uploaded | 2026-04-24 16:01:52 +0530 | Alekhya Korada | Some Image was uploaded | 2026-04-24 15:58:13 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-04 | 2026-05-03 13:59 | 2026-07-15 |  | Under Construction | 2026-05-31
18796 | Turnkey | 2026-01-01 | Hemant shah | pratap adinath | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera |  |  | Rajkumar Suthar | Sandeep Tiwari | Murali S | Avi Thakkar | Abdul Shafeen | Active | Production | 100% Payment | 917979 | 595351 | 1798232 | 0 | 917979 | 2 | 0 | 0 | 0 | 0 | 322628 |  |  | 2026-03-10 | 2026-03-19 14:47 | 2026-03-23 | 2026-03-23 15:40 | 2026-03-28 | 2026-03-28 22:42 | 2026-05-01 | 2026-04-27 15:31 | 2026-05-21 | 2026-05-20 20:14 | 2026-06-20 | 2026-06-20 00:59 | 2026-03-28 | 2026-03-30 17:10 | 2026-03-29 | 2026-03-31 10:59 | 2026-03-31 | 2026-03-31 17:04 | 2026-04-04 | 2026-04-04 19:18 |  |  |  |  | 2026-04-27 | 2026-04-28 20:06 | 2026-05-24 | 2026-05-24 18:10 | 2026-05-25 | 2026-05-24 18:37 |  |  | 2026-06-24 | 2026-06-28 19:28 | 2026-06-28 | 2026-06-28 22:19 | 2026-06-29 | 2026-06-28 22:43 | 2026-06-29 | 2026-06-29 13:44 |  |  |  |  | 2026-07-03 14:53 | 2026-07-10 | 2026-07-09 20:43 | 2026-07-15 | 2026-07-13 13:59 | 2026-07-14 |  | 2026-07-13 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-28 | 2026-07-03 14:52 | 2026-04-25 | 2026-04-27 15:25 | Site is RTMI | 2026-03-10 | 2026-03-10 19:04 | 1523926 | 274306 | 0 | 0 | 1118041.755 | 178166 | 1118041.755 | 178166 | 2026-07-12 09:46:36 +0530 | Rajkumar Suthar | Execution: Floor covering : 13th July 1st coat paint : 14th-18th July Site readiness : 18th July | 2026-06-24 15:52:06 +0530 | Abdul Shafeen | HOTO: need to clear below points before QC closure 1) bedroom1 bathroom is descope which needs to remove from the drawings and from the renders as well. 2) house video calling location needs to change according to the foyer unit which needs to take a mail acknowledgement from cx and need to attach on annexure. | 2026-06-19 17:49:57 +0530 | Swapnali Shedekar | Some Image was uploaded | 2026-04-28 | 2026-04-27 15:34 | 2026-05-21 | 2026-05-20 20:20 | Under Construction | 2026-05-08
18797 | Sub Project |  | Sayed iffat Riyaz | Lodha Bel Air | MUM - Thane | Yes | Naved Malik | Anamika Dolai | Sneha Kadam | [7 empty] | Active | Preproduction | CM | 193304 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 115982 | 77321.6 |  |  | 2026-03-10 | 2026-04-28 18:33 | 2026-03-11 | 2026-04-28 18:33 | 2026-04-28 | 2026-04-28 18:33 | 2026-05-06 | 2026-05-06 14:48 | 2026-05-07 | 2026-05-06 16:23 | 2026-05-12 |  | 2026-04-28 | 2026-04-28 18:33 | 2026-04-29 | 2026-04-28 18:33 | 2026-04-28 | 2026-04-28 18:33 | 2026-04-29 | 2026-04-28 18:34 |  |  |  |  | 2026-05-06 | 2026-05-06 15:22 | 2026-05-07 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-29 | 2026-04-28 18:34 | Unknown | 2026-03-10 | 2026-04-28 18:33 | 0 | 0 | 0 | 0 | 0 | 0 | 163817 | 29487 | [9 empty] | 2026-05-07 | 2026-05-06 14:49 | 2026-05-07 | 2026-05-06 16:26
18799 | Turnkey | 2026-01-01 | Sairaj Sakpal | raj reality | MUM - GOR | Yes |  |  | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1055000 | 9999 | 0 | 0 | 0 | 103 | 0 | 95501 | 105500 | 469392 | 374607.6 |  |  | 2026-03-10 | 2026-04-03 15:54 | 2026-03-11 | 2026-04-03 15:57 | 2026-03-17 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Unknown | 2026-03-10 | 2026-04-03 15:54 | 0 | 0 | 0 | 0 | 0 | 0 | 895620 | 159380 | 2026-04-30 20:09:07 +0530 | Meet Shah | Some Image was uploaded | 2026-04-08 11:10:52 +0530 | Meet Shah | Some Image was uploaded | 2026-03-11 16:56:10 +0530 | akansha arora | DCM: Minutes of Meeting held on Date: 11-03-2026 Attendees: Akansha Arora Harshaan Discussion: DCM Configuration - 2BHK Possession - End of March Site Access - Yes (After taking Permission) Living & Dining- 1 foldable dining table or Bench with 2 chairs 1 L shape sofa 1 TV unit for 50"- 55" TV 1 tall Mandir 1 shoe Rack (If placed inside) Kitchen - Base units have been provided by the builder. (cx may change it as he does not want too much shelf units) Wall & loft units are required. Parallel kitchen - 1 side Refrigerator and other side Washing machine space provided. Bedroom 1- 1 wardrobe with loft 1 queen sized bed. 1 bed side table. Bedroom 2- 1 wardrobe with loft 1 queen sized bed. 1 bed side table. 1 existing study unit needs to be placed. Washrooms- cx requires glass partitions but have asked to go for Curtains as it gets dried easily. On Site - False ceiling required as there are fire pipes in bedrooms. Painting Few electrical point shifting as per site condition. | 2026-04-14 |  | 2026-04-21
18803 | Turnkey | 2026-01-01 | Ayush | DSR highland greenz | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Kowshik |  | Sethuragavan R | Yogeshwaran | Ranjith Kumar | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Active | Handover | Project Closure Pending | 1095857 | 1095857 | 1490355 | 0 | 1095857 | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-09 | 2026-03-11 13:04 | 2026-03-17 | 2026-03-17 11:58 | 2026-03-17 | 2026-03-17 11:59 | 2026-04-11 | 2026-04-02 18:34 | 2026-04-09 | 2026-04-08 16:56 | 2026-04-22 | 2026-04-22 14:02 | 2026-03-17 | 2026-03-17 18:30 | 2026-03-18 | 2026-03-18 12:39 | 2026-03-18 | 2026-03-18 18:16 | 2026-03-20 | 2026-03-20 19:46 |  |  |  |  | 2026-04-02 | 2026-04-08 16:02 | 2026-04-09 | 2026-04-14 18:09 | 2026-04-15 | 2026-04-14 18:10 |  |  | 2026-04-27 | 2026-04-29 19:48 | 2026-04-30 | 2026-04-30 14:46 | 2026-05-01 | 2026-04-30 15:44 | 2026-05-01 | 2026-05-06 11:08 |  |  |  |  | 2026-05-07 15:21 | 2026-05-15 | 2026-05-14 21:24 | 2026-06-02 | 2026-05-28 19:05 | 2026-05-29 | 2026-05-30 15:55 | 2026-05-28 | 2026-06-01 17:33 | 2026-06-01 | 2026-06-01 17:43 | 2026-06-06 | 2026-06-05 17:56 |  |  | 2026-06-30 | 2026-06-25 15:15 | 2026-07-02 | 2026-06-25 19:07 | 2026-07-03 | 2026-06-25 20:19 |  |  |  |  | 2026-05-07 | 2026-05-07 15:20 | 2026-03-21 | 2026-03-29 16:45 | Site is RTMI | 2026-03-09 | 2026-03-11 13:02 | 1266138 | 224216 | 0 | 0 | 1257168.903 | 207588 | 1257168.903 | 207588 | 2026-06-25 20:20:14 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-06-17 12:40:54 +0530 | Ranjith Kumar | Execution: | 2026-05-29 10:56:29 +0530 | Ranjith Kumar | 100% Payment: | 2026-04-03 | 2026-04-02 18:44 | 2026-04-09 | 2026-04-08 17:29 | Under Construction | 2026-03-28
18805 | Turnkey | 2026-01-01 | bharat Purohit | adarsh bagh | MUM - GOR | Yes | Pratima Kajwe |  | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1201683 | 9999 | 0 | 0 | 0 | 126 | 0 | 110169 | 120168 | 480673 | 480673.2 |  |  | 2026-03-11 | 2026-03-11 15:01 | 2026-04-03 | 2026-04-03 15:30 | 2026-03-11 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Unknown | 2026-03-11 | 2026-03-11 15:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1018376 | 183307 | 2026-03-11 17:54:16 +0530 | Pratima Kajwe | DCM: MOM Living room Informal living with indian seating with glass facade on the back as background. Formal living room 3 seater sofa and 2 chairs Curtain for formal need to think on. Dining area 6-8 seater dining with crockery unit near window and mandir placement on the left. half on the top side above crockery. Slider near common wall of dining and kitchen for service counter to access Kitchen service counter space can be made as open kitchen with breakfast counter. Storage area access from passage Common bathroom Change in opening with dryer and washing machine space also to be accessed by Care taker. Parent's bedroom (bedroom 5) Helper sleeping space, Foldable partition to divide the room as care taker and parent's room Tv room to be placed on servant's room. Window AC in this rooms Master bedroom 1 (sir's room) L shaped wardrobe with dressing besides bed and low heighted storage near window (wardrobe) so it doesn't get blocked. Split AC for all rooms. Master bedroom 2 (ma'am's room ) Full wardrobe with dresser and study position to be flipped or kept as it is would be open to dicussion Master bedroom 4 (younger son Dhananjay ) Full white theme concept Flip bed position and TV on opposite side. Dressing and study position to be worked upon. 40 pairs for shoes and 40 bottles of perfumes. Master bedroom 3 (Older son Digvijay singh) Replanning of bathrooms to be considered for walk-in wardrobe and Jacuzzi with shower and WC with wash basin on the same bathroom , Study table with storage and placed near wardrobe (walk-in wardrobe) Train partition for lounger area will rest near fire duct shutter. All furniture to be considered in BWP ply no HDHMR Budget - 35-40L Lift size is small need to check feasibility of taking materials | [6 empty] | 2026-04-14 |  | 2026-04-21
18806 | Turnkey | 2026-01-01 | Rashmi r | Independent House | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 1162149 | 9999 | 0 | 0 | 0 | 120 | 0 | 106216 | 116215 | 476259 | 453460 |  |  | 2026-03-07 | 2026-03-17 13:54 | 2026-03-08 |  | 2026-03-18 |  | 2026-03-25 |  | 2026-04-01 |  | 2026-04-08 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-03-20 | [5 empty] | 2026-03-26 |  | 2026-04-03 |  | 2026-04-04 |  |  |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 | [6 empty] | 2026-05-02 |  | 2026-05-11 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-14 |  |  |  | 2026-06-05 |  | 2026-06-07 |  | 2026-06-08 | [5 empty] | 2026-04-12 |  | 2026-03-21 |  | Unknown | 2026-03-07 | 2026-03-11 16:29 | 0 | 0 | 0 | 0 | 0 | 0 | 984872 | 177277 | [9 empty] | 2026-03-26 |  | 2026-04-02
18807 | Turnkey | 2026-01-01 | Ardhana Sandy | Independent house | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 2034998 | 9999 | 0 | 0 | 0 | 90 | 0 | 193501 | 203500 | 844451 | 783547.2 |  |  | 2026-03-11 | 2026-04-16 17:58 | 2026-03-11 |  | 2026-03-17 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [6 empty] | 2026-05-01 |  | 2026-05-10 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-13 |  |  |  | 2026-06-04 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-03-11 | 2026-03-11 18:35 | 0 | 0 | 0 | 0 | 0 | 0 | 1724575 | 310423 | 2026-03-16 11:12:15 +0530 | Ankita Agarwal | DCM: Minutes of Meeting (MOM)Client Name: Mr. Sandeep Project: Residential Interior RGM Family Members: 3 Kid: 1 (5-year-old girl Aru) Estimated Budget: 10 Lakhs 1. Living RoomEntrance / Foyer Shoe unit outside the apartment (Approx. 3040K budget)Entrance base unit with seatingDesign Theme Rajasthan theme wall designSofa back wall with Rajasthan theme conceptPooja Area Pooja unit combined with crockery storageSeating setup for poojaStep with drawer and shutter storageWallpaper behind pooja unitTV Unit TV unit with wallpaper backgroundT-strip lightingTall unit (Optional depending on budget)2. KitchenBase unit with internal drawersWall unitsLoft storageTall unit for microwave & standalone appliancesNo roll-up shutterUnder-hob unit for pots and pans storage3. Master BedroomWardrobe with loft (Sliding shutters) 8 ftDresser with storage near the windowSeating space near window (if feasible)Bed back wall with wallpaperFlap table4. Bedroom 2 (Study / Guest Bedroom)Wardrobe with loft 9 ftOttoman near the windowStudy table for office workAdditional adjustable table / top cabinetPink wallpaper themeOptional Window seating (if budget permits)BudgetTotal Interior Budget: 10 Lakhs | [6 empty] | 2026-03-25 |  | 2026-04-01
18808 | Turnkey | 2026-01-01 | Deepak Das | Ruchira Park East | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1630757 | 241072.45 | 1701037 | 0 | 0 | 114 | 0 | 0 | 0 | 779879 | 609806 |  |  | 2026-03-11 | 2026-03-14 11:46 | 2026-03-13 | 2026-03-14 11:47 | 2026-03-17 | 2026-03-15 17:33 | 2026-03-22 | 2026-03-22 19:52 | 2026-06-21 |  | 2026-07-27 |  | 2026-03-15 | 2026-03-18 10:27 | 2026-03-16 | 2026-03-18 10:27 | 2026-03-18 | 2026-03-18 15:33 | 2026-03-22 | 2026-03-22 19:21 |  |  |  |  | 2026-03-22 | 2026-03-23 18:11 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-07-31 |  | 2026-03-23 | 2026-03-22 19:48 | Site is RTMI | 2026-03-11 | 2026-03-11 16:33 | 1441557 | 259480 | 0 | 0 | 0 | 0 | 1735982.7266 | 278987 | 2026-04-30 14:57:04 +0530 | Patil Madhavi | Some Image was uploaded | 2026-03-18 15:32:34 +0530 | Bency Chacko | Possession - July - 2026 SP - April 15th 2026 No permission for IMs Design meetings - Sunday The customer will be closing the Design payments by 31st March if the layouts are finalised. B2C - Self-funding No on-site work is planned Checklist is cleared Offers and quotes are cleared Timelines are cleared | 2026-03-18 11:44:35 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-03-23 | 2026-03-22 19:53 | 2026-06-22 |  | Under Construction | 2026-04-15
18810 | Sub Project |  | Ryan Choudhary | bharathiya nikoo homes | BNG - HRBR |  | Priyanka Gs | Parasa Sri | Shibin Lal |  |  | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-11 | 2026-03-13 13:27 | 2026-03-12 | 2026-03-13 13:27 | 2026-03-13 | 2026-03-13 13:27 | 2026-03-14 | 2026-03-13 13:29 | 2026-03-14 | 2026-03-13 13:30 | 2026-03-14 | 2026-03-13 13:34 | 2026-03-13 | 2026-03-13 13:27 | 2026-03-14 | 2026-03-13 13:28 | 2026-03-13 | 2026-03-13 13:28 | 2026-03-14 | 2026-03-13 13:28 |  |  |  |  | 2026-03-13 | 2026-03-13 13:29 | 2026-03-14 | 2026-03-13 13:33 | 2026-03-14 | 2026-03-13 13:33 |  |  | 2026-03-14 | 2026-03-13 18:02 | 2026-03-14 | 2026-03-13 18:31 | 2026-03-14 | 2026-03-13 20:24 | 2026-03-14 | 2026-03-13 20:24 |  |  |  |  | 2026-03-31 12:06 | 2026-04-01 | 2026-03-31 12:10 | 2026-04-02 | 2026-03-31 15:05 | 2026-04-08 | 2026-03-31 13:05 | 2026-03-31 | 2026-03-31 15:55 | 2026-03-31 | 2026-03-31 16:04 | 2026-04-01 | 2026-03-31 17:03 |  |  | 2026-04-02 | 2026-03-31 17:32 | 2026-04-02 | 2026-03-31 17:33 | 2026-03-31 | 2026-03-31 20:09 |  |  |  |  | 2026-03-13 | 2026-03-13 18:37 | 2026-03-14 | 2026-03-13 13:28 | Unknown | 2026-03-11 | 2026-03-13 13:27 | 0 | 0 | 0 | 0 | 42372.8814 | 0 | 42372.8814 | 0 | [9 empty] | 2026-03-14 | 2026-03-13 13:29 | 2026-03-14 | 2026-03-13 13:30
18814 | Turnkey | 2026-01-01 | Shubhangi Sawant Nawale | Raymond Tenx Habitat | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | Tanveer Patel | Akshat Shrivastava | Murali S | Foram Joshi | Shailendra Mishra | Active | Installation | Execution | 1205344 | 1205344 | 999937 | 0 | 1205344 | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-12 | 2026-03-12 12:21 | 2026-03-15 | 2026-03-15 19:59 | 2026-03-18 | 2026-03-15 20:03 | 2026-04-14 | 2026-04-14 19:23 | 2026-04-19 | 2026-04-18 19:01 | 2026-05-05 | 2026-05-05 18:38 | 2026-03-15 | 2026-03-17 13:08 | 2026-03-16 | 2026-03-20 15:12 | 2026-03-20 | 2026-03-20 17:46 | 2026-03-25 | 2026-03-25 14:06 |  |  |  |  | 2026-04-07 | 2026-04-08 21:01 | 2026-04-17 | 2026-04-17 18:39 | 2026-04-20 | 2026-04-18 20:26 |  |  | 2026-05-08 | 2026-05-09 18:52 | 2026-05-17 | 2026-05-17 20:14 | 2026-05-19 | 2026-05-17 20:27 | 2026-05-18 | 2026-05-18 22:02 |  |  |  |  | 2026-05-21 16:24 | 2026-06-03 | 2026-06-03 20:06 | 2026-06-27 | 2026-06-25 18:55 | 2026-06-11 | 2026-06-11 12:32 | 2026-06-25 | 2026-07-01 16:26 | 2026-06-30 | 2026-07-03 13:57 | 2026-07-05 | 2026-07-11 13:51 |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-07-27 | [5 empty] | 2026-05-18 | 2026-05-20 17:19 | 2026-04-03 | 2026-04-03 15:17 | Site is RTMI | 2026-03-12 | 2026-03-12 12:20 | 1071584.8274 | 176939 | 0 | 0 | 1261329.5715 | 208272 | 1261329.5715 | 208272 | 2026-07-13 13:59:25 +0530 | Tanveer Patel | Execution: Libra bracket 3 set Tandem chennal 1set Wardrobe drawer missing Kitchen loft Patta 900mm 6p Hanger road 800p/300 p Kitchen side panel 650x325 Chimney penal 800x480mm | 2026-07-01 23:48:51 +0530 | Tanveer Patel | DDM1: Material delivered on 30th june Team is not yet aligned | 2026-07-01 23:41:07 +0530 | Tanveer Patel | DDM1:Material delivered on 30 june Team is not planned yet | 2026-04-15 | 2026-04-14 19:28 | 2026-04-19 | 2026-04-18 19:02
18819 | Turnkey | 2026-01-01 | Mr Ganesh Chauhan | Godrej Upvan | MUM - Thane | Yes | Hemant Sonar |  | Anil Kuwar | [5 empty] | Aryan Singh |  | Active | Prospect | Onboarding Due | 820008 | 229999 | 1093111 | 0 | 0 | 124 | 0 | 0 | 0 | 268364 | 321644.8 |  |  | 2026-03-12 | 2026-03-12 18:46 | 2026-03-12 | 2026-03-12 21:18 | 2026-03-12 | 2026-03-12 21:21 | 2026-03-19 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-03-12 | 2026-03-13 12:57 | 2026-03-13 | 2026-03-13 16:38 | 2026-03-13 |  | 2026-03-14 | [5 empty] | 2026-03-20 | 2026-03-13 12:58 | 2026-03-28 |  | 2026-03-29 |  |  |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-08 | [6 empty] | 2026-04-26 |  | 2026-05-05 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-08 |  |  |  | 2026-05-30 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-04-06 |  | 2026-03-15 |  | Unknown | 2026-03-12 | 2026-03-12 14:58 | 926365 | 166745 | 0 | 0 | 0 | 0 | 900435.5165 | 141102 | 2026-04-20 12:14:40 +0530 | Bency Chacko |  | 2026-04-02 13:06:50 +0530 | Christopher Macwan | Some Image was uploaded | 2026-03-18 16:59:04 +0530 | Aryan Singh | CX visited the office on Tuesday, have re informed him regarding the No refund policy. CX mentioned he will get back to us for the same after few days. Will update as soon as CX inform us the same. | 2026-03-20 |  | 2026-03-27
18821 | Sub Project |  | Jadhav Pankaj | 34 park estate | MUM - GOR |  | Rahul Agrawal | Manzoor Shaikh | Safalta Karkera |  |  | Shashwat Joshi | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Active | Production | Dispatch Due | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-13 | 2026-05-27 10:52 | 2026-03-14 | 2026-05-27 10:52 | 2026-05-27 | 2026-05-27 10:52 | 2026-05-28 | 2026-05-27 10:54 | 2026-05-28 | 2026-05-27 10:55 | 2026-05-28 | 2026-05-27 10:57 | 2026-05-27 | 2026-05-27 10:53 | 2026-05-28 | 2026-05-27 10:53 | 2026-05-27 | 2026-05-27 10:53 | 2026-05-28 | 2026-05-27 10:53 |  |  |  |  | 2026-05-27 | 2026-05-27 10:54 | 2026-05-28 | 2026-05-27 10:56 | 2026-05-28 | 2026-05-27 10:56 |  |  | 2026-05-28 | 2026-05-27 15:14 | 2026-05-28 | 2026-05-27 17:51 | 2026-06-12 | 2026-06-23 15:50 | 2026-06-24 | 2026-06-23 15:50 |  |  |  |  | 2026-06-23 18:31 | 2026-06-28 | 2026-06-27 21:18 | 2026-07-01 | 2026-06-29 09:57 | 2026-06-30 | 2026-07-08 11:23 | 2026-06-29 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-05-27 | 2026-06-11 14:01 | 2026-05-28 | 2026-05-27 10:53 | Unknown | 2026-03-13 | 2026-05-27 10:52 | 0 | 0 | 0 | 0 | 35720.34 | 0 | 35720.34 | 0 | [9 empty] | 2026-05-28 | 2026-05-27 10:54 | 2026-05-28 | 2026-05-27 10:56
18822 | Turnkey | 2026-01-01 | Manoj Nandu | meru shikhar | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 1053763 | 9999 | 0 | 0 | 0 | 124 | 0 | 95377 | 105376 | 466164 | 376846.4 |  |  | 2026-03-13 | 2026-03-13 14:48 | 2026-03-29 | 2026-03-29 08:19 | 2026-03-28 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-04-22 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-04-09 |  | 2026-04-17 |  | 2026-04-18 |  |  |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 | [6 empty] | 2026-05-16 |  | 2026-05-25 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-28 |  |  |  | 2026-06-19 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-04-26 |  | 2026-04-04 |  | Unknown | 2026-03-13 | 2026-03-13 14:46 | 0 | 0 | 0 | 0 | 0 | 0 | 1171175.7019 | 189900 | 2026-03-29 08:20:24 +0530 | Sweta Bhise | DCM: 1. Name of the customer manoj nandu 2. Profession Service 3. Project Name/Tower Name/Flat Number meru shikhar 4. Typology (1BHK, 2BHK, 3BHK, etc) 2bhk 5. Site Access Date 2026-03-15 6. Possession Date 2026-03-15 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 900000 Customer Preferences8. Who will be living in the house? Couple 9. What activities do you usually prefer at your home ? Family Bonding, Prayer 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials 15. Do you have any existing furniture that must be accommodated? 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? Multipurpose 2. Must-have furniture or features? Display unit , Puja unit, Coffee table, TV unit 3. Choose your decor inspirations NA 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Washing machine, Chimney, Hob, Fridge 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units TV unit, Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Dresser , Study table 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? 2. Outdoor Mood How do you intend to use the utility Cloths Drying Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) | [6 empty] | 2026-04-09 |  | 2026-04-16
18824 | Turnkey | 2026-01-01 | Gopal Krishna Parmeswar b | park West | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1636184 | 163619 | 2219696 | 0 | 0 | 107 | 0 | 0 | 163618 | 685915 | 623032 |  |  | 2026-03-13 | 2026-03-13 18:44 | 2026-03-15 | 2026-03-21 18:30 | 2026-03-26 | 2026-03-26 20:28 | 2026-08-08 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-03-26 | 2026-03-28 11:51 | 2026-03-27 | 2026-03-28 11:51 | 2026-03-28 | 2026-03-30 18:50 | 2026-04-03 | 2026-04-03 19:52 |  |  |  |  | 2026-08-09 |  | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-08-04 |  | Site is RTMI | 2026-03-13 | 2026-03-13 18:42 | 1881098 | 338597 | 0 | 0 | 0 | 0 | 1881098.7267 | 310604 | 2026-06-03 16:15:27 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-12 23:06:09 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-12 23:05:37 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-08-09 |  | 2026-08-16 |  | Under Construction | 2026-04-16
18825 | Turnkey | 2026-01-01 | Anurag Sharma | Swaroop residency | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 898426 | 9999 | 898426 | 0 | 0 | 103 | 0 | 79844 | 89843 | 384383 | 334357.6 |  |  | 2026-03-13 | 2026-03-17 15:03 | 2026-04-03 | 2026-04-03 15:24 | 2026-04-03 | 2026-04-03 15:27 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-13 | 2026-03-15 17:02 | 1030586.4113 | 166413 | 0 | 0 | 0 | 0 | 1030586.4113 | 166413 | 2026-03-22 12:50:30 +0530 | Sahil Sethi | User ResponseCustomer and Project Profile1. Name of the customer Anurag 2. Profession working 3. Project Name/Tower Name/Flat Number Swaroop residency 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK 5. Site Access Date 2026-03-31 6. Possession Date 2026-04-15 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 10 Customer Preferences8. Who will be living in the house? Nuclear Family 9. What activities do you usually prefer at your home ? Relaxing and Unwinding, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any NA 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) NA Upload reference images 14. Any absolute no-go styles colours or materials NA 15. Do you have any existing furniture that must be accommodated? NA 13. Do you want the design to reflect any personal story, cultural influence, or special memory NA ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? Multipurpose 2. Must-have furniture or features? TV unit, Puja unit 3. Choose your decor inspirations NA 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? NA 2. Must-have appliances? Microwave, Fridge, Chimney, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining No 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Study table 9. False Ceiling Required - Bedroom 1 No 10. Bedroom 2 - Utility Other 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units Study Table 14. False Ceiling Required - Bedroom 2 No 15. Bedroom 3 - Utility Others 16. Bedroom 3 - Bed Type Storage 17. Bedroom 3 - Wardrobe Style Swing 18. Bedroom 3 - Additional Units Dresser 19. False Ceiling Required - Bedroom 3 No Bathrooms1. Preferred vanity style 2. What do you prefer? NA 3. What are your requirements for Utility Area? NA Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Any other Miscellaneous1. Timeline related commitment made by Bonito, if any NA 2. Other commitments made by Bonito to customer, if any NA 3. What are offers committed to customers? NA 4. Move-in date confirmed with customer 2026-08-15 5. Any special occasion mentioned by the customer wrt handover date NA 6. Additional Requirements (Mention any requirements from customer not covered in the form) room extension work shifting of window which will be in cliwent's scopes 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (in INR Lakhs) 12 | [6 empty] | 2026-04-11 |  | 2026-04-18
18826 | Turnkey | 2026-01-01 | Smita Berde | Ashar Arise | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Hold | Preproduction | CM | 1198096 | 240999 | 1684645 | 0 | 0 | 0 | 68 | 0 | 0 | 514178 | 442918.8 |  |  | 2026-03-13 | 2026-03-13 20:57 | 2026-03-15 | 2026-03-15 20:06 | 2026-03-15 | 2026-03-15 20:07 | 2026-09-04 | 2026-05-22 13:35 | 2026-06-10 | 2026-06-10 16:17 | 2026-07-11 |  | 2026-03-15 | 2026-03-17 19:23 | 2026-03-16 | 2026-03-20 19:18 | 2026-03-20 | 2026-03-24 14:44 | 2026-03-26 | 2026-03-26 15:39 |  |  |  |  | 2026-05-06 | 2026-04-09 18:34 | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-08-31 | 2026-05-22 13:34 | Site is Non-RTMI | 2026-03-13 | 2026-03-13 20:56 | 1427666 | 256979 | 0 | 0 | 0 | 0 | 1364662.097 | 216319 | 2026-07-09 15:35:55 +0530 | Anant Giri | Others: | 2026-07-03 13:11:37 +0530 | Monika Pal | Minutes of Meeting held on Date: 03-07-2026 | 2026-06-18 11:25:36 +0530 | Monika Pal | Some Image was uploaded | 2026-05-23 | 2026-05-22 18:40 | 2026-06-10 | 2026-06-10 16:24
18827 | Turnkey | 2026-01-01 | Aarti | Adarsh Park Heights | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Fuzail Girach |  | Active | Design | DEM1 | 2204128 | 191981 | 1868617 | 0 | 0 | 95 | 0 | 0 | 248845 | 961655 | 801647.6 |  |  | 2026-03-13 | 2026-03-27 12:16 | 2026-03-30 | 2026-03-30 11:44 | 2026-03-30 | 2026-03-30 16:01 | 2026-10-01 | 2026-07-14 19:54 | 2026-07-21 |  | 2026-10-15 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-09 16:47 | 2026-04-09 | 2026-04-11 15:25 | 2026-04-14 | 2026-04-14 14:37 |  |  |  |  | 2026-07-15 |  | 2026-10-10 |  | 2026-10-11 |  |  |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 | [6 empty] | 2026-11-08 |  | 2026-11-17 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 |  | 2026-11-20 |  |  |  | 2026-12-12 |  | 2026-12-14 |  | 2026-12-15 | [5 empty] | 2026-10-19 |  | 2026-06-06 | 2026-06-19 17:42 | Site is Non-RTMI | 2026-03-13 | 2026-03-14 12:27 | 1583574 | 285043 | 0 | 0 | 0 | 0 | 2787919 | 501825 | 2026-04-11 15:25:02 +0530 | Bency Chacko | Possession - July end IMs can be done on 20th April 2026 Can close the LFM in 10 days and close the 10% payments by 21st April 2026 Checklist, timelines, and scope of work are closed No on-site work is planned No civil scope is planned B2C - Self-funding Agreements terms cleared | 2026-04-11 11:53:57 +0530 | Bency Chacko |  | 2026-04-10 18:59:08 +0530 | Bency Chacko |  | 2026-07-15 |  | 2026-07-22 |  | Under Construction | 2026-07-31
18829 | Turnkey | 2026-01-01 | Madhuri Vinayak Nyayadhish | Mahindra Alcove | MUM - GOR | Yes | Sakshi Hire |  | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1552935 | 9999 | 1552935 | 0 | 0 | 103 | 0 | 145295 | 155294 | 689426 | 552922.4 |  |  | 2026-03-13 | 2026-03-13 18:48 | 2026-04-03 | 2026-04-03 16:43 | 2026-04-03 | 2026-04-03 16:50 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-13 | 2026-03-13 18:33 | 1567312.3465 | 270447 | 0 | 0 | 0 | 0 | 1567312.3465 | 270447 | 2026-04-14 17:16:29 +0530 | Saloni Sagwekar | Some Image was uploaded | 2026-03-13 19:37:35 +0530 | Sakshi Hire | DCM: vile parle east existingÂ 20th march 3pm 960 carpetÂ 703 falt no 10-12 pairs footwears inside house 6 seater diningÂ Â bed 1 bed queen size side tables wardrobe and loft tv unit bed 2 sofa cum bed small wardrobe 1'6" 5'tableÂ overhead storage with close and open cabinet sound proofing panels master bedroom bed king size side tables wardrobe tables workstation with storage dresser above left side table false ceiling for overall area morden traditional warm & cozy small mandir next to tv unit |  |  |  | 2026-04-11 |  | 2026-04-18
18830 | Turnkey | 2026-01-01 | Mrinal Bharti | Bhavya Dazzel | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 995790 | 9999 | 0 | 0 | 0 | 123 | 0 | 89580 | 99579 | 398316 | 398316 |  |  | 2026-03-13 | 2026-03-14 16:01 | 2026-03-14 |  | 2026-03-17 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-03-17 |  | 2026-03-18 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | 2026-03-25 |  | 2026-04-02 |  | 2026-04-03 |  |  |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 | [30 empty] | 2026-04-11 |  | 2026-03-20 |  | Unknown | 2026-03-13 | 2026-03-14 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 843890 | 151900 | [9 empty] | 2026-03-25 |  | 2026-04-01
18831 | Turnkey | 2026-01-01 | Elegant Cranes C | Runwal SANCTUARY | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar |  |  | suraj kumar | Aditya Vikram |  | Saloni Chawan | Shailendra Mishra | Active | Preproduction | CM | 2484350 | 497532 | 3225333 | 0 | 0 | 1 | 85 | 0 | 0 | 1121437 | 865381.2 |  |  | 2026-03-13 | 2026-03-15 21:41 | 2026-03-21 | 2026-03-21 11:24 | 2026-03-21 | 2026-03-21 11:27 | 2026-04-08 | 2026-04-08 12:20 | 2026-07-15 | 2026-07-14 11:18 | 2026-07-20 |  | 2026-03-21 | 2026-03-26 16:32 | 2026-03-22 | 2026-03-26 16:36 | 2026-03-26 | 2026-03-27 16:03 | 2026-04-05 | 2026-04-05 16:41 |  |  |  |  | 2026-04-20 | 2026-04-06 22:55 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-07-24 |  | 2026-04-15 | 2026-04-08 10:40 | Site is RTMI | 2026-03-13 | 2026-03-15 21:40 | 2733333 | 492000 | 0 | 0 | 0 | 0 | 2733333.4628 | 466375 | 2026-06-27 19:02:09 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-06-27 19:01:51 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-06-27 19:01:09 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-04-09 | 2026-04-08 12:29 | 2026-07-15 | 2026-07-14 11:22
18833 | Turnkey | 2026-01-01 | Jitin Bhatia | others | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 2872078 | 9999 | 0 | 0 | 0 | 103 | 0 | 277209 | 287208 | 1328946 | 968716 |  |  | 2026-03-13 | 2026-04-03 15:31 | 2026-03-21 | 2026-04-03 15:33 | 2026-03-14 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Unknown | 2026-03-13 | 2026-04-03 15:30 | 0 | 0 | 0 | 0 | 0 | 0 | 2433964 | 438113 | 2026-04-24 16:13:57 +0530 | Meet Shah | Some Image was uploaded | 2026-04-15 15:37:13 +0530 | Manasi Patil | Some Image was uploaded | 2026-03-21 17:39:22 +0530 | Rishika Malviya | Some Image was uploaded | 2026-04-14 |  | 2026-04-21
18834 | Turnkey | 2026-01-01 | Prakash Tiwari ( GEM FASHION STUDIO ) | L&T elixir | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Kashmira Nerurkar |  | Mohammed Lal | Savita Parab | Rizwan Mistry |  | Umang Shah | Vinay Surve | Active | Preproduction | 2D | 1706556 | 245074 | 1642275 | 0 | 0 | 51 | 14 | 0 | 0 | 848201 | 613281.2 |  |  | 2026-03-14 | 2026-03-14 12:47 | 2026-03-22 | 2026-03-22 12:06 | 2026-03-25 | 2026-03-23 22:15 | 2026-04-09 | 2026-04-09 12:08 | 2026-05-03 | 2026-05-02 18:52 | 2026-05-21 | 2026-05-21 16:32 | 2026-03-23 | 2026-03-24 15:46 | 2026-03-24 | 2026-03-29 22:52 | 2026-03-29 | 2026-03-30 16:58 | 2026-04-03 | 2026-04-03 19:09 |  |  |  |  | 2026-04-09 | 2026-04-29 17:10 | 2026-05-04 | 2026-05-03 21:31 | 2026-05-04 | 2026-05-03 21:31 |  |  | 2026-05-23 | 2026-05-25 18:27 | 2026-05-24 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-05-25 |  | 2026-04-04 | 2026-04-09 12:02 | Site is RTMI | 2026-03-14 | 2026-03-14 12:46 | 1394884 | 247390 | 0 | 0 | 0 | 0 | 1890711.1224 | 319050 | 2026-06-26 18:53:31 +0530 | Zoya Ansari | Minutes of Meeting held on Date: 23/06/2026 Title: price escalation Project: Client: Rohan Tiwari Attendees: Prakash Tiwari, Rohan Tiwari, kashmira, manzur , zoya , shraddha, rishika Objective: Refund for the project Discussion As discussed in the meeting , the client has asked for refund and we stated that no refund will be given to the client , still asked for settlement and continuing the project, but the client has deneid completely | 2026-05-30 13:35:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-23 13:39:24 +0530 | Mohammed Lal | Some Image was uploaded | 2026-04-10 | 2026-04-09 12:13 | 2026-05-03 | 2026-05-02 18:55 | RTMI
18839 | Turnkey | 2026-01-01 | Vishal Korgaonkar | Vihang luxuria | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Design | DEM1 | 800716 | 79999 | 1393809 | 0 | 0 | 22 | 85 | 0 | 80144 | 322028 | 318545.2 |  |  | 2026-03-14 | 2026-03-19 14:30 | 2026-03-19 | 2026-03-19 14:35 | 2026-03-25 | 2026-03-25 18:57 | 2027-01-14 |  | 2027-01-21 |  | 2027-01-28 |  | 2026-03-26 | 2026-03-27 12:08 | 2026-03-27 | 2026-03-27 12:57 | 2026-03-27 | 2026-03-30 10:01 | 2026-04-04 | 2026-04-04 19:30 |  |  |  |  | 2027-01-15 |  | 2027-01-23 |  | 2027-01-24 |  |  |  | 2027-01-31 |  | 2027-02-01 |  | 2027-02-02 |  | 2027-02-03 | [6 empty] | 2027-02-21 |  | 2027-03-02 |  | 2026-05-14 |  | 2027-03-02 |  | 2027-03-03 |  | 2027-03-05 |  |  |  | 2027-03-27 |  | 2027-03-29 |  | 2027-03-30 | [5 empty] | 2027-02-01 |  | 2027-01-10 |  | Unknown | 2026-03-14 | 2026-03-14 14:16 | 1181194 | 212615 | 0 | 0 | 0 | 0 | 861193.9225 | 145405 | 2026-04-21 10:32:19 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-14 17:10:54 +0530 | Saloni Sagwekar | Some Image was uploaded | 2026-04-12 16:22:41 +0530 | Zoya Bhatkar | Designer Update : Transition Notes PID 18839 : Vishal Korgaonkar : 2BHK Cx has done the booking on Minimum value of 8 lakh actual value is around 13.93 Living RoomTV Unit Only base unit considered mandir - Only base unit considered Storage near sofaÂ KitchenSemi Modular Loft on both sides Master BedroomWardrobe with LoftÂ 2 Side TablesÂ Side Table cum dresser with Wall StorageÂ Study with wall Storage BedroomÂ Wardrobe with LoftÂ 1 Side TablesÂ foldable study Additional Scope of workÂ Single Drop Considered for Living Room Only 150 Sqft consideredÂ Living area is 184 sqft according to CDP LayoutÂ | 2027-01-15 |  | 2027-01-22
18840 | Turnkey | 2026-01-01 | Gourav Bhama | Pallate | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 3614488 | 9999 | 3614488 | 0 | 0 | 110 | 0 | 351450 | 361449 | 1566168 | 1325422.4 |  |  | 2026-03-13 | 2026-03-14 14:23 | 2026-03-14 | 2026-03-27 15:15 | 2026-03-30 | 2026-04-03 15:38 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-13 | 2026-03-14 14:22 | 3063125 | 551362 | 0 | 0 | 0 | 0 | 3063125 | 551362 | 2026-03-27 15:15:04 +0530 | Khushi Khandelwal | DCM: CIVIL SCOPE flooring washroom tiling wall demolition making of wall Interior of every bedroom | [6 empty] | 2026-04-11 |  | 2026-04-18
18841 | Turnkey | 2026-01-01 | Lalita Tripathi | Mahindra Eden | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 805522 | 194555 | 1118468 | 0 | 0 | 2 | 47 | 0 | 0 | 288758 | 322208.8 |  |  | 2026-03-14 | 2026-03-14 15:22 | 2026-03-18 | 2026-03-18 16:33 | 2026-03-19 | 2026-03-20 12:01 | 2026-05-23 | 2026-05-26 20:16 | 2026-08-06 |  | 2026-08-13 |  | 2026-03-20 | 2026-03-22 11:33 | 2026-03-21 | 2026-03-22 11:57 | 2026-03-22 | 2026-03-26 15:48 | 2026-03-30 | 2026-03-30 12:16 |  |  |  |  | 2026-05-27 | 2026-05-27 13:38 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-04-14 | 2026-04-11 18:46 | Site is Non-RTMI | 2026-03-14 | 2026-03-14 15:12 | 947855 | 170613 | 0 | 0 | 0 | 0 | 928906.1 | 153384 | 2026-05-29 14:38:06 +0530 | Akshay Ds | Some Image was uploaded | 2026-05-24 15:30:59 +0530 | Sayed Byahatti | DDM1: 11-04-26 (18841 - Lalita Tripathi) Foyer -1 : LIMITED MAINTANCE FREE CONCEPT FOR wall THEMES AND WALL LAMPS ETC. MAIN Foyer - 2 : NATURE FAME LIKE WALL PAPER,AND CORNER CONCEPT TO BE DESIGN HANDLES TO BE CHANGE G-PROFILE TO EDGE PROFILE. TV UNIT : AS SHARE PICTURE REFRENCE, WALL LEDGE WITH METAL FABRICATION . DINIG AREA : CROCKERY UNIT TO BE PLACED IT IN CENTER, REMOVE THE WALL CONCEPTS SUGGEST NEW ONE. Â Â KITCHEN ENTRANCE WALL TO BE DESIGN SUGGEST AND STORAGE ALSO TO BE SUGGEST. KITCHEN : BOTTOM BASE UNIT STORAGE SKIRTING DEPTH TO BE CHECK. VANITY AREA : TO DISCUSS AS PER INITTAIL MEASUREMENTS.( AFTER INITIAL MEASUREMENT DONE ) KIDS ROOM : WALL PANELS TO BE SUGGEST, STUDY UNIT ALSO TO BE , AND WALLPAPER TO BE SUGEST. MASTER BR : SLIDING WARDRPBE IF POSSILE AS PER SITE SPACE , BOTTOM STORAGE DRAWARS.HEADREST SIDE WALL PANELS TO BE SUGGEST. BEDROOM 2: WARDROBE AS PER MASTER BEDROOM WARDROBE, SIGNUTURE WALL THEMES WALL PAPER TO BE DESIGN AND SUGGEST. ALL 3 BATHROOMS VANITYN UNIT TO BE DISCUS AFTER INITIAL MEASUREMENT. INITIAL MEASUREMENTS TO BE DISCUSS. | 2026-05-14 17:31:10 +0530 | Akshay Ds | Some Image was uploaded | 2026-05-27 | 2026-05-26 20:20 | 2026-08-07 |  | Under Construction | 2026-04-30
18842 | Turnkey | 2026-01-01 | Arun Agrawal | Sadgur Avenue | MUM - GOR | Yes | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Akash Jadhav | Sandeep Tiwari | Murali S | Umang Shah | Abdul Shafeen | Hold | Preproduction | Site Readiness 2 | 1730693 | 1145147 | 1418139 | 0 | 1778183 | 5 | 8 | 0 | 0 | 0 | 585546 |  |  | 2026-03-14 | 2026-03-14 15:14 | 2026-03-14 | 2026-03-15 22:34 | 2026-03-15 | 2026-03-15 22:37 | 2026-04-19 | 2026-04-19 20:39 | 2026-05-08 | 2026-05-07 13:39 | 2026-06-16 | 2026-06-16 22:36 | 2026-03-15 | 2026-03-17 18:56 | 2026-03-16 | 2026-03-17 19:10 | 2026-03-17 | 2026-03-18 13:13 | 2026-03-25 | 2026-03-25 15:48 |  |  |  |  | 2026-04-19 | 2026-04-22 21:02 | 2026-04-28 | 2026-04-27 19:31 | 2026-04-28 | 2026-04-27 19:32 |  |  | 2026-06-18 | 2026-06-29 18:21 | 2026-06-29 | 2026-06-29 21:16 | 2026-06-30 | 2026-06-29 21:41 | 2026-06-30 | 2026-07-02 11:17 | [5 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-06-29 |  | 2026-04-08 | 2026-04-19 15:16 | Site is RTMI | 2026-03-14 | 2026-03-14 15:14 | 1204100 | 214039 | 0 | 0 | 1945632.8619 | 318537 | 1945633.1464 | 311293 | 2026-07-07 12:18:49 +0530 | Manzoor Shaikh | Others: Seepage work will be done by the Builder needs a week time. | 2026-06-24 18:21:14 +0530 | Rajnish Mishra | Some Image was uploaded | 2026-06-23 17:20:14 +0530 | Rajnish Mishra | Some Image was uploaded | 2026-04-20 | 2026-04-19 20:41 | 2026-05-08 | 2026-05-07 13:40
18843 | Turnkey | 2026-01-01 | shilpa waza | Vijay Park | MUM - Thane | No Estimate | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-15 21:01 | 2026-03-24 |  | 2026-03-19 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-05-20 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-23 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-03-14 | 2026-03-15 21:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-15 21:02:37 +0530 | Anant Giri | Some Image was uploaded | [6 empty] | 2026-04-04 |  | 2026-04-11
18844 | Turnkey | 2026-01-01 | Deeptha Jeganathan | konig Orange County | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Shivakumar Ms | Jairam Joshi | Murali S |  | Abdul Shafeen | Active | Installation | Execution | 1091472 | 1091472 | 1083158 | 0 | 1091472 | 8 | 12 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-19 11:55 | 2026-03-20 | 2026-03-20 20:18 | 2026-03-23 | 2026-03-20 20:19 | 2026-04-09 | 2026-04-05 16:20 | 2026-04-21 | 2026-04-22 16:52 | 2026-05-28 | 2026-05-28 13:08 | 2026-03-20 | 2026-03-20 22:37 | 2026-03-21 | 2026-03-25 15:26 | 2026-03-25 | 2026-03-27 18:30 | 2026-03-31 | 2026-03-31 18:44 |  |  |  |  | 2026-04-10 | 2026-04-14 19:08 | 2026-05-03 | 2026-05-03 15:31 | 2026-05-04 | 2026-05-03 15:52 |  |  | 2026-05-30 | 2026-05-31 20:49 | 2026-05-31 | 2026-05-31 22:15 | 2026-06-01 | 2026-05-31 22:58 | 2026-06-01 | 2026-05-31 23:18 |  |  |  |  | 2026-06-02 19:02 | 2026-06-10 | 2026-06-11 21:01 | 2026-06-20 | 2026-06-18 14:09 | 2026-06-19 | 2026-06-18 15:14 | 2026-06-30 | 2026-07-07 11:32 | 2026-07-07 | 2026-07-07 11:42 | 2026-07-11 | 2026-07-10 18:53 |  |  | 2026-08-08 |  | 2026-08-10 |  | 2026-08-11 | [5 empty] | 2026-05-31 | 2026-06-02 14:23 | 2026-04-01 | 2026-04-05 15:14 | Site is RTMI | 2026-03-14 | 2026-03-18 20:04 | 917931 | 165227 | 0 | 0 | 1201346.7486 | 207300 | 1201346.7486 | 207300 | 2026-07-03 16:33:49 +0530 | Jairam Joshi | Dispatch Due: Key - 4th FC-6th SRD 6th | 2026-06-19 14:24:20 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-18 13:36:04 +0530 | Jairam Joshi | Procurement: CX side PI WIP - 19th a week delay - ETA 24t Key 25th FC - 26th SRD -26th june | 2026-04-06 | 2026-04-05 16:25 | 2026-04-23 | 2026-04-22 16:57 | RTMI
18845 | Turnkey | 2026-01-01 | Tanvi Joshi | Raymond GS | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Aryan Singh |  | Active | Design | DEM1 | 1776892 | 259999 | 2441454 | 0 | 0 | 18 | 93 | 0 | 95379 | 729439 | 692074.8 |  |  | 2026-03-14 | 2026-03-14 16:20 | 2026-03-18 | 2026-03-19 14:04 | 2026-03-20 | 2026-03-20 15:47 | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-03-20 | 2026-03-20 19:18 | 2026-03-21 | 2026-03-20 19:20 | 2026-03-20 | 2026-03-26 14:05 | 2026-03-27 | 2026-03-27 14:44 |  |  |  |  | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-03-14 | 2026-03-14 16:12 | 2069029 | 372425 | 0 | 0 | 0 | 0 | 1997204.8703 | 329780 | 2026-07-02 19:23:00 +0530 | Anamika Dolai | Tried connecting with the client , client is not responding. | 2026-03-30 18:01:45 +0530 | Pooja Metre | Some Image was uploaded | 2026-03-26 14:05:29 +0530 | Royden Henriques |  | 2026-07-05 |  | 2026-07-12
18846 | Turnkey | 2026-01-01 | Abhishek Shetty | Casa Supremo | MUM - GOR | No Estimate | [8 empty] | Rashmita Das |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 117 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-20 11:49 | 2026-03-15 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-14 | 2026-03-14 17:47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-05 |  | 2026-04-12
18847 | Turnkey | 2026-01-01 | vijay K | other | BNG - HSR | Yes | Swati Rathod |  | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1269669 | 9999 | 0 | 0 | 0 | 123 | 0 | 116968 | 126967 | 511293 | 504442 |  |  | 2026-03-14 | 2026-03-14 18:16 | 2026-03-21 | 2026-03-21 11:31 | 2026-03-14 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-25 |  | 2026-03-26 | [5 empty] | 2026-04-01 |  | 2026-04-09 |  | 2026-04-10 |  |  |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 | [6 empty] | 2026-05-08 |  | 2026-05-17 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-20 |  |  |  | 2026-06-11 |  | 2026-06-13 |  | 2026-06-14 | [5 empty] | 2026-04-18 |  | 2026-03-27 |  | Unknown | 2026-03-14 | 2026-03-14 18:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1075991 | 193678 | 2026-03-15 10:59:29 +0530 | Aparna | MOM : 14.03.26 Apartment - Udbhav Gokulam, balagere road Possession - june'26 Budget : 8L North facing mainÂ door Family - 2 adults + 1 Son(Viransh 6 yrs) ceiling 9.3 feet Height Foyer -Â 1. Shoe rack upto half wall height 1. metal gate for outside entrance (need to check) Living room 1. wall mounted TV unit on pooja wall, with tall unit, back panel 2. 65" TV size 3. 3 + 1 + 1 existing sofa 4. pooja doors to merge with TV unit design which will have external drawers on the entry door 5. platform built with countertop, bottom depth is 1 feet depth, step in marble 6. False ceiling peripheral for living Dining -Â 1. 4 seater squareÂ 2. crockery on kids wall 3. wall design for MBR vanity wall which will have robo cleaner, opp to living entry Kitchen - 1. u shape kitchenÂ 2. Base, wall & loft 3. Sink point & hob on right wall 4. appliancesÂ - double door fridge, microwave, mixer 5. tall appliances unit, tall unit for pantry 6. single bowl sink inside kitchen Utility -Â 1. main sink unit 2. Washing machine with DW above as plumbing on 1 single wall 3. wall unit above sink 4. Grills for entire balcony (need to check) MBR 1. Opt 1 - preferred to have WR on 12.4 full wall with fixed studyÂ Opt 2 1. 8' WR opp to entrance with dresse, 6' WR on opp with study, dresser KBR 1.Balcony merged together, end to end window on right 2. L shape study, seating, hinged wardrobe 3. wall design with writing wall 4. tall unit with bookshelf on opp of entrance wall, cot, dresser to plan on the entrance opp wall 6. 5' x 12'W UPVC window (need to check) | [6 empty] | 2026-04-01 |  | 2026-04-08
18848 | Turnkey | 2026-01-01 | Ajit Sahoo | Sumadhura Folium | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik |  | RaviKumar Battala | Deekshith P | Jairam Joshi |  | Chanakya Panigrahi | Sunil Kumar S M | Hold | Design | 60% Payment | 2173836 | 321207 | 2296722 | 0 | 2163373 | 15 | 29 | 0 | 0 | 996336 | 856292.8 |  |  | 2026-03-14 | 2026-03-14 18:42 | 2026-03-18 | 2026-03-18 18:25 | 2026-03-30 | 2026-03-30 18:06 | 2026-04-26 | 2026-04-22 15:30 | 2026-05-21 | 2026-05-20 19:26 | 2026-05-29 | 2026-05-29 12:59 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-07 13:00 | 2026-04-07 | 2026-04-08 16:20 | 2026-04-11 | 2026-04-11 19:14 |  |  |  |  | 2026-04-22 | 2026-04-23 12:08 | 2026-05-21 | 2026-05-22 16:08 | 2026-05-23 | 2026-05-22 16:10 |  |  | 2026-05-30 | 2026-05-31 23:00 | 2026-05-31 | 2026-05-31 23:55 | 2026-06-01 | 2026-06-01 00:09 | 2026-10-02 | [6 empty] | 2026-10-20 |  | 2026-10-29 |  | 2026-10-28 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-11-01 |  |  |  | 2026-11-23 |  | 2026-11-25 |  | 2026-11-26 | [5 empty] | 2026-09-30 |  | 2026-04-12 | 2026-04-22 11:07 | Site is RTMI | 2026-03-14 | 2026-03-14 18:36 | 1946374 | 350347 | 0 | 0 | 2506695.791 | 405514 | 2523627.491 | 407110 | 2026-06-16 19:13:48 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-30 16:07:41 +0530 | Preksha Sajjanshettar | Some Image was uploaded | 2026-05-20 18:00:17 +0530 | Preksha Sajjanshettar | DDM - 17-05-2026 KidsÂ Replace as per early design(drawer- in wardrobe units) top filler - can be 100mm or not since false is also coming foot rest - remove OfficeÂ tray to be considered - for keyboard Increase the depth of pencil drawer(500mm) Foot rest - increase the depth by 450mm - movableÂ GuestÂ foot rest - movable top filler - can be 100mm or not since Master bedroom -Â Toilet wall loft open issue need to check with QCÂ Crockery unit make all the internal shelf as loose shelf - tall unit UtilityÂ Top cabinet - internal partition need to loose FoyerÂ make 5 partition (try to get 120mm)(shoe rack middle units) add light on bottom Pooja unit is removed | 2026-04-23 | 2026-04-22 15:39 | 2026-05-21 | 2026-05-20 19:29 | Under Construction | 2026-04-29
18849 | Turnkey | 2026-01-01 | Maulik Nikhil Vyas | Navrang Oasis | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Kashmira Nerurkar |  |  | Shashwat Joshi | Rizwan Mistry |  | Harshaan Tiku | Vinay Surve | Active | Preproduction | 2D | 880676 | 210484 | 1375444 | 0 | 0 | 71 | 0 | 0 | 0 | 348640 | 321552.4 |  |  | 2026-03-14 | 2026-03-14 18:42 | 2026-03-16 | 2026-03-20 13:28 | 2026-03-20 | 2026-03-20 16:57 | 2026-03-29 | 2026-03-29 13:19 | 2026-04-12 | 2026-04-11 17:20 | 2026-05-03 | 2026-05-03 16:51 | 2026-03-20 | 2026-03-21 12:38 | 2026-03-21 | 2026-03-21 12:39 | 2026-03-21 | 2026-03-23 13:03 | 2026-03-25 | 2026-03-25 19:11 |  |  |  |  | 2026-03-29 | 2026-04-09 16:42 | 2026-04-18 | 2026-04-23 18:40 | 2026-04-24 | 2026-04-23 18:41 |  |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 | [6 empty] | 2026-09-25 |  | 2026-10-04 |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-07 |  |  |  | 2026-10-29 |  | 2026-10-31 |  | 2026-11-01 | [5 empty] | 2026-09-05 |  | 2026-03-26 | 2026-03-29 12:29 | Site is RTMI | 2026-03-14 | 2026-03-14 18:41 | 1167918 | 207526 | 0 | 0 | 0 | 0 | 971869.6833 | 164086 | 2026-06-06 18:35:20 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-09 19:22:06 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-09 19:21:41 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-03-30 | 2026-03-29 13:22 | 2026-04-12 | 2026-04-11 17:24
18852 | Turnkey | 2026-01-01 | SARIKA BANKAR | Aikya Roots | MUM - GOR | Yes | Saif Shaikh | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | suraj kumar | Aditya Vikram | Murali S | Nivesh Gupta | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 1217948 | 1217948 | 1415750 | 0 | 1217948 | 6 | 4 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-14 19:13 | 2026-03-20 | 2026-03-20 11:48 | 2026-03-23 | 2026-03-21 20:23 | 2026-05-09 | 2026-04-12 21:08 | 2026-04-25 | 2026-04-24 17:54 | 2026-05-05 | 2026-05-05 12:00 | 2026-03-23 | 2026-03-21 15:22 | 2026-03-22 | 2026-03-21 20:37 | 2026-03-21 | 2026-03-23 15:02 | 2026-03-31 | 2026-03-31 14:55 |  |  |  |  | 2026-04-12 | 2026-04-14 19:02 | 2026-04-26 | 2026-04-27 19:57 | 2026-04-28 | 2026-04-28 13:53 |  |  | 2026-05-08 | 2026-05-23 11:34 | 2026-05-23 | 2026-05-23 18:40 | 2026-05-24 | 2026-05-23 19:47 | 2026-05-24 | 2026-05-25 18:46 |  |  |  |  | 2026-06-04 19:42 | 2026-07-01 | 2026-06-30 20:07 | 2026-07-11 | 2026-07-09 19:45 | 2026-07-08 | 2026-07-06 19:19 | 2026-07-09 | 2026-07-13 17:20 | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-08-08 | [5 empty] | 2026-06-26 | 2026-06-04 19:41 | 2026-05-05 | 2026-04-12 21:04 | Site is RTMI | 2026-03-14 | 2026-03-14 19:08 | 1202075 | 213674 | 0 | 0 | 1364668.3972 | 230407 | 1364668.3972 | 230407 | 2026-07-13 14:42:20 +0530 | suraj kumar | Project Status: Floor covering installation work completed. False ceiling looping work has been completed. Wall base looping work is in progress.. Carpentry work has been completed. False ceiling farming & Board fixing work has been completed. Punning grooving work has been completed. Wall base preparation work has been completed. Modular material will be delivered to the site today. | 2026-07-08 11:43:58 +0530 | suraj kumar | Project Status: Floor covering installation work completed. False ceiling looping work has been completed. Wall base looping work is in progress.. Carpentry work has been completed. False ceiling farming & Board fixing work has been completed. Punning grooving work has been completed. Wall base preparation work is in progress. Site is ready for modular delivery. | 2026-07-08 11:42:45 +0530 | suraj kumar | Project Status: Floor covering installation work completed. False ceiling looping work has been completed. Wall base looping work is in progress.. Carpentry work has been completed. False ceiling farming & Board fixing work has been completed. Punning grooving work has been completed. Wall base preparation work is in progress. Site will ready for modular delivery by 10th july. | 2026-04-13 | 2026-04-12 21:10 | 2026-04-25 | 2026-04-24 18:02
18854 | Turnkey | 2026-01-01 | Mohan Kamath | Runwal Sanctuary | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 2576212 | 9999 | 0 | 0 | 0 | 123 | 0 | 247622 | 257621 | 1123184 | 937786 |  |  | 2026-03-14 | 2026-03-14 19:53 | 2026-03-14 | 2026-04-10 12:17 | 2026-03-14 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-05-04 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-04-21 |  | 2026-04-29 |  | 2026-04-30 |  |  |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 | [6 empty] | 2026-05-28 |  | 2026-06-06 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-09 |  |  |  | 2026-07-01 |  | 2026-07-03 |  | 2026-07-04 | [5 empty] | 2026-05-08 |  | 2026-04-16 |  | Unknown | 2026-03-14 | 2026-03-14 19:43 | 0 | 0 | 0 | 0 | 0 | 0 | 2183231 | 392981 | 2026-03-15 17:38:33 +0530 | Karuna Shinde | Some Image was uploaded | 2026-03-14 19:44:03 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded |  |  |  | 2026-04-21 |  | 2026-04-28
18857 | Turnkey | 2026-01-01 | Sharada Kenkare | Courtyard | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 1865763 | 9999 | 1865763 | 0 | 0 | 103 | 0 | 176577 | 186576 | 843541 | 649069.2 |  |  | 2026-03-14 | 2026-03-17 15:01 | 2026-03-22 | 2026-03-22 18:45 | 2026-03-25 | 2026-04-03 15:41 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-14 | 2026-03-15 16:58 | 1581155 | 284607 | 0 | 0 | 0 | 0 | 1581155 | 284607 | 2026-04-30 16:13:04 +0530 | Meet Shah | Some Image was uploaded | [6 empty] | 2026-04-11 |  | 2026-04-18
18858 | Turnkey | 2026-01-01 | Ashok Agrawal | The courtyard | MUM - Thane | Yes | Pooja Nakul Sharma | Anamika Dolai | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 6679500 | 9999 | 0 | 0 | 0 | 95 | 0 | 657951 | 667950 | 2815148 | 2528452.4 |  |  | 2026-03-14 | 2026-03-14 22:23 | 2026-03-15 | 2026-04-11 15:39 | 2026-04-14 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-04-22 |  | 2026-04-30 |  | 2026-05-01 |  |  |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 | [6 empty] | 2026-05-29 |  | 2026-06-07 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-10 |  |  |  | 2026-07-02 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-05-09 |  | 2026-04-17 |  | Unknown | 2026-03-14 | 2026-03-14 22:17 | 0 | 0 | 0 | 0 | 0 | 0 | 5660593 | 1018906 | 2026-04-07 17:37:00 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-17 11:24:37 +0530 | Pooja Nakul Sharma | CDP date- 20th March | 2026-03-17 11:23:14 +0530 | Pooja Nakul Sharma | Some Image was uploaded | 2026-04-22 |  | 2026-04-29
18860 | Turnkey | 2026-01-01 | Mr Rajan Raje | Raymond | MUM - Thane | No Estimate | Karuna Shinde | Anamika Dolai | [6 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-15 21:44 | 2026-03-15 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-03-14 | 2026-03-15 21:44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-11 13:20:47 +0530 | Saloni Chawan | The client owns a 3 BHK apartment in Raymond by GS and has allocated a budget of 80 lakhs to 1 crore for the project. They intend to commence the work when the property is either nearing possession or ready for handover. The client has an in-house designer who will actively participate in the project. This designer will contribute to the design process and coordinate with our design team to ensure seamless collaboration. The overall execution and implementation of the project will be managed by us. I conducted a detailed discussion with the client and their in-house designer, during which I explained our services, capabilities, and scope of work. Both parties are aligned with our offerings and have expressed their willingness to proceed under these terms. However, their decision is contingent upon satisfaction with our material offerings. They have expressed concern that our material library may have limited selections. As they wish to create a unique and personalized home, they want assurance that the available options will not restrict their vision or result in a design similar to others. This remains their only blocker, and they seek confirmation that they will have adequate flexibility and access to a diverse range of materials throughout the project. | [6 empty] | 2026-07-08 |  | 2026-07-15
18861 | Turnkey | 2026-01-01 | kinnari kamat | 100 Trees | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 3437878 | 9999 | 0 | 0 | 0 | 123 | 0 | 333789 | 343788 | 1422242 | 1328060.8 |  |  | 2026-03-14 | 2026-03-14 22:14 | 2026-03-17 |  | 2026-03-14 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 | [5 empty] | 2026-03-28 |  | 2026-04-05 |  | 2026-04-06 |  |  |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 | [6 empty] | 2026-05-04 |  | 2026-05-13 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-16 |  |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-04-14 |  | 2026-03-23 |  | Unknown | 2026-03-14 | 2026-03-14 21:59 | 0 | 0 | 0 | 0 | 0 | 0 | 2913456 | 524422 | 2026-03-15 18:00:38 +0530 | Karuna Shinde | Some Image was uploaded | [6 empty] | 2026-03-28 |  | 2026-04-04
18862 | Turnkey | 2026-01-01 | Rahul Pawar | Raymond Tenex | MUM - Thane | Yes | Garv Sharma | Divya Rahangdale | [6 empty] | Mustufa Sohagpurwala |  | Active | Prospect | 10% Payment | 1496784 | 9999 | 0 | 0 | 0 | 116 | 0 | 139679 | 149678 | 610433 | 586994 |  |  | 2026-03-14 | 2026-03-14 22:55 | 2026-03-15 | 2026-03-21 11:53 | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-22 |  | 2026-03-23 | [5 empty] | 2026-03-29 |  | 2026-04-06 |  | 2026-04-07 |  |  |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 | [6 empty] | 2026-05-05 |  | 2026-05-14 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-08 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-04-15 |  | 2026-03-24 |  | Unknown | 2026-03-14 | 2026-03-14 22:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1268461 | 228323 | 2026-03-14 22:57:10 +0530 | Mustufa Sohagpurwala | Some Image was uploaded | [6 empty] | 2026-03-29 |  | 2026-04-05
18863 | Turnkey | 2026-01-01 | Madhav Ram Nimishakavi | Ajmera Lakeside | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Installation | Execution | 1016023 | 1016023 | 1022937 | 1011462 | 1016023 | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-18 19:27 | 2026-03-20 | 2026-03-20 18:59 | 2026-03-20 | 2026-03-20 20:17 | 2026-04-27 | 2026-04-26 15:48 | 2026-06-04 | 2026-06-04 12:33 | 2026-06-09 | 2026-06-07 13:48 | 2026-03-20 | 2026-03-20 20:18 | 2026-03-21 | 2026-03-20 20:53 | 2026-03-20 | 2026-03-23 15:06 | 2026-04-12 | 2026-04-12 20:02 |  |  |  |  | 2026-04-26 | 2026-04-29 13:39 | 2026-06-05 | 2026-06-06 14:22 | 2026-06-07 | 2026-06-06 20:11 |  |  | 2026-06-10 | 2026-06-10 18:49 | 2026-06-11 | 2026-06-11 15:27 | 2026-06-12 | 2026-06-11 19:12 | 2026-06-12 | 2026-06-12 15:00 |  |  |  |  | 2026-06-13 16:58 | 2026-06-19 | 2026-06-18 19:58 | 2026-06-27 | 2026-06-26 10:45 | 2026-06-27 | 2026-06-25 18:19 | 2026-06-26 | 2026-06-30 17:40 | 2026-06-30 | 2026-07-01 08:29 | 2026-07-07 | 2026-07-06 17:12 |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-06-11 | 2026-06-13 16:57 | 2026-04-13 | 2026-04-26 15:42 | Site is RTMI | 2026-03-14 | 2026-03-18 19:15 | 866896 | 156041 | 1000203.799 | 172595 | 1039603.5205 | 179393 | 1039603.5205 | 179393 | 2026-06-11 11:16:28 +0530 | Hemalatha D | Some Image was uploaded | 2026-06-09 13:39:42 +0530 | Hemalatha D | Some Image was uploaded | 2026-05-12 17:26:58 +0530 | Parasa Sri | Some Image was uploaded | 2026-04-27 | 2026-04-26 15:51 | 2026-06-05 | 2026-06-04 12:36 | Under Construction | 2026-03-31
18864 | Turnkey | 2026-01-01 | Vidyesh Tikam | Piramal Vaikunth | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Nishtha Valawalkar |  | Hold | Preproduction | Site Readiness 1 | 1123657 | 224749 | 1350684 | 0 | 0 | 0 | 88 | 0 | 0 | 504968 | 393940 |  |  | 2026-03-14 | 2026-03-15 11:10 | 2026-03-15 | 2026-03-19 19:10 | 2026-03-22 | 2026-03-20 14:11 | 2026-04-18 | 2026-04-18 14:34 | 2026-08-17 |  | 2026-08-24 |  | 2026-03-20 | 2026-03-21 15:32 | 2026-03-21 | 2026-03-21 15:34 | 2026-03-21 | 2026-03-23 13:38 | 2026-03-25 | 2026-03-25 13:01 |  |  |  |  | 2026-06-05 | 2026-03-31 18:52 | 2026-08-19 |  | 2026-08-20 |  |  |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 | [6 empty] | 2026-09-17 |  | 2026-09-26 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-29 |  |  |  | 2026-10-21 |  | 2026-10-23 |  | 2026-10-24 | [5 empty] | 2026-08-28 |  | 2026-06-30 | 2026-04-18 14:24 | Site is Non-RTMI | 2026-03-14 | 2026-03-15 11:09 | 1147449 | 203235 | 0 | 0 | 0 | 0 | 1154525.892 | 186908 | 2026-07-10 19:00:43 +0530 | Divya Rahangdale | CX will receive possession by the first week of August. | 2026-05-07 19:44:46 +0530 | Sneha Kadam | Possession expected in July | 2026-03-27 13:13:13 +0530 | Anamika Dolai | Done | 2026-04-19 | 2026-04-18 14:37 | 2026-08-18
18865 | Turnkey | 2026-01-01 | Gautam Pandya | farmhouse | MUM - GOR | Yes | Rishika Malviya |  | Safalta Karkera | [5 empty] | Ashish Jha |  | Active | Prospect | 10% Payment | 2588243 | 9999 | 2588243 | 0 | 0 | 112 | 0 | 248825 | 258824 | 1109180 | 961414.4 |  |  | 2026-03-15 | 2026-03-15 14:28 | 2026-03-17 | 2026-03-17 12:48 | 2026-03-18 | 2026-03-25 12:59 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-03-15 | 2026-03-15 11:40 | 2193426 | 394816 | 0 | 0 | 0 | 0 | 2193426 | 394816 | 2026-04-15 13:46:41 +0530 | Ashish Jha | Some Image was uploaded | [6 empty] | 2026-04-02 |  | 2026-04-09
18866 | Sub Project |  | Kajal tayal | JP Barcelona | MUM - GOR |  | Neha Yadav |  | Safalta Karkera |  |  | Faraz Soudagar | Aditya Vikram | Murali S |  |  | Completed | Complete | Completed | 44 | 0 | 0 | 0 | 44 | 89 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-17 20:02 | 2026-03-16 | 2026-03-17 20:03 | 2026-03-17 | 2026-03-17 20:03 | 2026-03-18 | 2026-03-17 20:05 | 2026-03-18 | 2026-03-17 20:07 | 2026-03-18 | 2026-03-17 20:08 | 2026-03-17 | 2026-03-17 20:04 | 2026-03-18 | 2026-03-17 20:04 | 2026-03-17 | 2026-03-17 20:04 | 2026-03-18 | 2026-03-17 20:04 |  |  |  |  | 2026-03-17 | 2026-03-17 20:06 | 2026-03-18 | 2026-03-17 20:07 | 2026-03-18 | 2026-03-17 20:07 |  |  | 2026-03-18 | 2026-03-17 20:10 | 2026-03-18 | 2026-03-17 20:11 | 2026-04-02 | 2026-03-17 20:12 | 2026-03-18 | 2026-03-17 20:12 |  |  |  |  | 2026-03-18 12:17 | 2026-03-26 | 2026-03-25 20:07 | 2026-03-28 | 2026-03-26 20:54 | 2026-04-14 | 2026-03-17 20:14 | 2026-03-26 | 2026-04-10 15:12 | 2026-04-10 | 2026-04-10 15:14 | 2026-04-17 | 2026-04-16 14:02 |  |  | 2026-04-18 | 2026-04-17 15:02 | 2026-04-19 | 2026-04-17 15:02 | 2026-04-17 | 2026-04-17 15:04 |  |  |  |  | 2026-04-01 | 2026-03-17 20:14 | 2026-03-18 | 2026-03-17 20:04 | Unknown | 2026-03-15 | 2026-03-17 20:02 | 0 | 0 | 0 | 0 | 57665 | 10379 | 57665 | 10379 | 2026-03-17 18:47:29 +0530 | Reshma Melanta | Some Image was uploaded | [6 empty] | 2026-03-18 | 2026-03-17 20:05 | 2026-03-18 | 2026-03-17 20:07
18867 | Turnkey | 2026-01-01 | Abhijit Kar | Godrej Ananda | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Hold | Preproduction | Site Readiness 1 | 1156508 | 231302 | 1346664 | 0 | 0 | 5 | 55 | 0 | 0 | 480447 | 444758.8 |  |  | 2026-03-14 | 2026-03-17 13:06 | 2026-03-19 | 2026-03-19 16:17 | 2026-03-30 | 2026-03-30 12:49 | 2026-04-26 | 2026-04-26 18:24 | 2026-09-07 |  | 2026-09-14 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-02 11:24 | 2026-04-02 | 2026-04-02 17:59 | 2026-04-05 | 2026-04-05 15:35 |  |  |  |  | 2026-05-15 | 2026-05-29 18:42 | 2026-09-09 |  | 2026-09-10 |  |  |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 | [6 empty] | 2026-10-08 |  | 2026-10-17 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-20 |  |  |  | 2026-11-11 |  | 2026-11-13 |  | 2026-11-14 | [5 empty] | 2026-09-18 |  | 2026-04-06 | 2026-04-25 14:22 | Site is Non-RTMI | 2026-03-14 | 2026-03-15 12:16 | 1141241 | 205423 | 0 | 0 | 0 | 0 | 1265416.3605 | 218359 | 2026-05-28 12:01:12 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-25 10:20:40 +0530 | Vishnu S | Some Image was uploaded | 2026-04-26 13:06:19 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-27 | 2026-04-26 18:30 | 2026-09-08 |  | Under Construction | 2026-10-31
18868 | Turnkey | 2026-01-01 | Shairi Paul | Genurise North Park | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Janvi Nagdeo |  | Hold | Preproduction | Site Readiness 1 | 1104624 | 248999 | 1248014 | 0 | 0 | 18 | 69 | 0 | 0 | 426874 | 428751.2 |  |  | 2026-03-14 | 2026-03-17 13:07 | 2026-03-20 | 2026-03-20 19:03 | 2026-03-24 | 2026-03-24 13:51 | 2026-04-14 | 2026-04-14 16:36 | 2026-07-23 |  | 2026-07-24 |  | 2026-03-24 | 2026-03-24 16:35 | 2026-03-25 | 2026-03-25 13:00 | 2026-03-25 | 2026-03-25 17:45 | 2026-04-02 | 2026-04-02 13:24 |  |  |  |  | 2026-04-19 | 2026-04-19 12:03 | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-04-03 | 2026-04-14 16:13 | Site is RTMI | 2026-03-14 | 2026-03-15 12:21 | 1057639 | 190375 | 0 | 0 | 0 | 0 | 1156090.0818 | 199554 | 2026-07-05 15:06:21 +0530 | Priyanka R |  | 2026-04-24 12:20:29 +0530 | Yogesh B | Some Image was uploaded | 2026-04-20 10:24:54 +0530 | Priyanka R | Some Image was uploaded | 2026-04-15 | 2026-04-14 16:37 | 2026-07-24 |  | Under Construction | 2026-06-30
18869 | Turnkey | 2026-01-01 | Sakshi kondurkar Kondurkar | HUBTOWN PREMIER RESIDENCES | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | [5 empty] | Rashmita Das |  | Hold | Design | DEM1 | 807185 | 109999 | 982798 | 0 | 0 | 14 | 83 | 0 | 51438 | 353372 | 292375.6 |  |  | 2026-03-15 | 2026-03-20 11:52 | 2026-03-31 | 2026-03-31 22:25 | 2026-03-31 | 2026-03-31 22:57 | 2027-01-04 |  | 2027-01-11 |  | 2027-01-18 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-04 11:58 | 2026-04-04 | 2026-04-09 18:34 | 2026-04-23 | 2026-04-23 18:37 |  |  |  |  | 2027-01-05 |  | 2027-01-13 |  | 2027-01-14 |  |  |  | 2027-01-21 |  | 2027-01-22 |  | 2027-01-23 |  | 2027-01-24 | [6 empty] | 2027-02-11 |  | 2027-02-20 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-21 |  | 2027-02-23 |  |  |  | 2027-03-17 |  | 2027-03-19 |  | 2027-03-20 | [5 empty] | 2027-01-22 |  | 2026-12-31 |  | Unknown | 2026-03-15 | 2026-03-17 11:10 | 832879 | 149918 | 0 | 0 | 0 | 0 | 806387.415 | 139146 | 2026-04-23 18:34:56 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-23 18:20:15 +0530 | Reshma Melanta | NOT ANSWERING THE CALL | 2026-04-21 16:53:00 +0530 | Reshma Melanta | NOT ANSWERING THE CALL | 2027-01-05 |  | 2027-01-12 |  | Under Construction | 2026-04-09
18870 | Turnkey | 2026-01-01 | Chetan Vasrani | Birla Tisya | BNG - HRBR | Yes |  | Rajeshwari S | [6 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1029164 | 9999 | 1029164 | 0 | 0 | 110 | 0 | 92917 | 102916 | 411666 | 411665.6 |  |  | 2026-03-14 | 2026-03-17 13:52 | 2026-03-18 | 2026-03-26 23:16 | 2026-04-22 | 2026-04-22 11:45 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-14 | 2026-03-15 12:30 | 872173 | 156991 | 0 | 0 | 0 | 0 | 872173 | 156991 | 2026-03-18 10:25:37 +0530 | Rhea Rathod | DCM: Possession - April 15th East facing Family of 5 Pastel colours, bright and light house FoyerÂ - Shoe rack with partition - 20-25 pairs Dining area - Crockery unit with pooja unit - 6/4 seater dining as per the space available Living areaÂ - Wall mounted tv unit - tall unit - wall concept - sofa back wallÂ KitchenÂ - Storage in the utility space - wall, washing machine - Wall storage and loft - Ro unit - Single door fridge Master bedroom - 2 wardrobes with loft - Sleek wardrobe for used clothes - Foldable studyÂ - Small dresserÂ - Wall concept - King size bed - Vanity Bedroom 1 - Mother in law - Queen bed - Wardrobe with loft - Vanity Bedroom - 2 - Kids bedroom - Wardrobe with loft-Â 2 - study table for 2 - 2 single beds | [6 empty] | 2026-04-30 |  | 2026-05-07
18871 | Turnkey | 2026-01-01 | Altaf Shaik | Shriram solaitire | BNG - HRBR | Yes | Chandini Nj | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S | Shashank Singh | Abdul Shafeen | Active | Installation | Execution | 741488 | 741488 | 983028 | 770277 | 781488 | 7 | 11 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-17 13:51 | 2026-03-26 | 2026-03-26 05:31 | 2026-03-29 | 2026-03-30 14:23 | 2026-04-19 | 2026-04-19 18:21 | 2026-04-25 | 2026-04-24 11:22 | 2026-04-29 | 2026-04-27 10:46 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-04 18:31 | 2026-04-04 | 2026-04-10 15:04 | 2026-04-12 | 2026-04-12 20:14 |  |  |  |  | 2026-04-19 | 2026-04-24 10:27 | 2026-04-25 | 2026-04-26 15:40 | 2026-04-27 | 2026-04-26 15:53 |  |  | 2026-05-19 | 2026-05-23 12:26 | 2026-05-23 | 2026-05-23 13:19 | 2026-05-23 | 2026-05-23 13:40 | 2026-05-24 | 2026-05-27 17:38 |  |  |  |  | 2026-05-29 19:47 | 2026-06-06 | 2026-06-05 21:33 | 2026-06-21 | 2026-06-17 18:51 | 2026-06-18 | 2026-07-02 16:23 | 2026-07-02 | 2026-07-06 11:45 | 2026-07-04 | 2026-07-08 01:31 | 2026-07-11 | 2026-07-10 14:50 |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-05-23 | 2026-05-29 19:46 | 2026-04-13 | 2026-04-19 14:12 | Site is RTMI | 2026-03-14 | 2026-03-15 12:30 | 833075 | 149953 | 801254.002 | 129322 | 878813.9422 | 141838 | 878813.9422 | 141838 | 2026-05-24 12:41:12 +0530 | Yogesh B | Some Image was uploaded | 2026-05-19 18:37:34 +0530 | Chandini Nj | Some Image was uploaded | 2026-05-17 17:33:39 +0530 | Chandini Nj | Kitchen - double door fridge, oven,Â MBR - HEADREST WALL need to be changed, no rafters. Used cloth storage provision KBR - CIRCLE WITH DECOR, Instead tall unit some designs Locker provision as per the Vastu False ceiling with profile lightingÂ Vanities need to be provided with some storage in MBR vanity Store room - looking for shoe rack. 50pair of shoes, kitchen setup foldable table outdoor unit. Living area - speakers 4 provision. | 2026-04-20 | 2026-04-19 18:48 | 2026-04-25 | 2026-04-24 11:23 | RTMI
18872 | Turnkey | 2026-01-01 | Swaty Acharya | Devagiri opal | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Hold | Preproduction | Site Readiness 1 | 941281 | 255099 | 1589019 | 0 | 0 | 17 | 69 | 0 | 0 | 309670 | 376512.4 |  |  | 2026-03-14 | 2026-03-18 19:40 | 2026-03-15 | 2026-03-19 11:36 | 2026-03-22 | 2026-03-25 19:50 | 2026-04-22 | 2026-04-18 19:15 | 2026-07-16 |  | 2026-07-17 |  | 2026-03-22 | 2026-03-21 15:29 | 2026-03-23 | 2026-03-25 12:04 | 2026-03-26 | 2026-03-27 18:26 | 2026-04-02 | 2026-04-05 16:10 |  |  |  |  | 2026-04-18 | 2026-04-20 14:58 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-04-06 | 2026-04-18 19:12 | Site is Non-RTMI | 2026-03-14 | 2026-03-15 12:38 | 1346626 | 242392 | 0 | 0 | 0 | 0 | 1010389.8 | 174382 | 2026-06-08 22:02:31 +0530 | Priyanka R | Minutes of meeting ( 07-06-2026)Â Tv unit 1. Floor mounted base - middle flip down with al. frame glass shutter 2. TV panel from base to ceiling level with strip 3. Open tall unit Â Crockery + pooja unit 1. Pooja glass shutter- flutted 2. Lights inside 3. Extra panel at end Dinining washbasin cabinet should be add Passage area wall decor -yet to decide Kitchen 1. Tandem drawer 600mm 2. Cooktop and chimney -75 cm Â Â 3.Â Water purifier placement at wallÂ 4. Tall unit with oven provision 5. Wicker basket- Cx scope 5. Fridge moves to dining Utility 1. Base- Frame & shutter 2. Add janitor unitÂ MBR 1. Wardrobe placement changed- side by side wardrobe with bay window seaterÂ 2. Wardrobe inside -add organizer on top of drawer 3. Mirror with drawer at left end- Add light below loft 4. Loft make allignemnet 5. Beading design on bed back 6. Tv unit design as per reference sharedÂ 7. Wallpaper on seater wallÂ Â KBR 1. Loft right end single shutter will be dummy for AC outlet 2. Study unit -No changes 3. Wardrobe inside pull out iron boardÂ GBR 1. Wardrobe placement Changed 2. Loft end to endÂ 3. Add used clothes hanger cabinet with ventilator on shutter All washrooms - Remove vanity unit | 2026-04-19 19:27:06 +0530 | Priyanka R | DDM1: 18/04/2026 Living 1. TV size provision- 50" 2. bottom legs 3. Cx need 3 TV unit OptionsÂ 4. Wall concept options 5. No wall lightsÂ 6. Crockery +pooja unit move to opposite wall 7. add glass tall unit 8. glass wall cabinetsÂ 9. Pooja inside cnc optionsÂ 10. Spot light inside pooja Kitchen 1. Tall unit is oven + wicker basket in bottomÂ 2. add tandem drawer beside tall unit 3. right end corner unit 4. Add bottle pull out beside hob 5. above sink consider as ro unit 6. hob side wall cabinet -add al.frame glassÂ UtilityÂ 1. Add wall cabinet above washing mechine MBR 1. Need options for bed back wall 2. remove bay window seater 3. add study unit with side cabinets 4. tv unit -No changes KBR 1. Queen size bed 2. Remove study unit add bay window seater instead GBR 1. Replace swing wardrobe with Sliding wardrobe Project will be in Hold, Next meeting will be after IM | 2026-04-10 17:31:39 +0530 | Priyanka R | Some Image was uploaded | 2026-04-19 | 2026-04-18 19:15 | 2026-07-17 |  | Under Construction | 2026-04-16
18873 | Turnkey | 2026-01-01 | indra jana | antariksh ace | MUM - GOR | Yes |  |  | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 1248398 | 9999 | 1248398 | 0 | 0 | 103 | 0 | 114841 | 124840 | 540525 | 458193.2 |  |  | 2026-03-15 | 2026-03-15 19:29 | 2026-03-15 | 2026-04-03 15:47 | 2026-04-03 | 2026-04-03 15:52 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-15 | 2026-03-15 12:38 | 1060766 | 187632 | 0 | 0 | 0 | 0 | 1060766 | 187632 | 2026-04-30 19:07:32 +0530 | Meet Shah | Some Image was uploaded | 2026-04-14 14:57:58 +0530 | Sanskruti Yadav | Some Image was uploaded |  |  |  | 2026-04-11 |  | 2026-04-18
18874 | Turnkey | 2026-01-01 | Shweta | Abhee Riviera Royale | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Preproduction | DEM2 | 1003738 | 200748 | 1272331 | 0 | 0 | 32 | 0 | 0 | 0 | 420467 | 382522.8 |  |  | 2026-03-14 | 2026-03-18 16:06 | 2026-03-15 | 2026-03-18 17:00 | 2026-03-21 | 2026-03-21 19:56 | 2026-06-13 | 2026-06-13 17:09 | 2026-07-14 |  | 2026-08-17 |  | 2026-03-21 | 2026-03-25 12:40 | 2026-03-22 | 2026-03-25 12:43 | 2026-03-25 | 2026-03-27 12:55 | 2026-04-01 | 2026-04-01 12:17 |  |  |  |  | 2026-06-17 | 2026-06-13 14:24 | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-05-12 | 2026-06-13 16:24 | Site is RTMI | 2026-03-14 | 2026-03-15 12:39 | 1078247 | 194084 | 0 | 0 | 0 | 0 | 1070734.1454 | 184765 | 2026-05-14 15:18:51 +0530 | Parasa Sri | Some Image was uploaded | 2026-04-23 12:25:52 +0530 | Parasa Sri | Some Image was uploaded | 2026-04-01 12:19:38 +0530 | Parasa Sri | Welcome call is done Possession - July 2026 Initial measurement can be planned on mid April Available on weekends for DD | 2026-06-14 | 2026-06-13 17:13 | 2026-07-15 |  | Under Construction | 2026-07-31
18876 | Turnkey | 2026-01-01 | Sanjeev Sharma | Dombivli Lodha palava | MUM - Thane | No Estimate | Pooja Nakul Sharma | Anamika Dolai | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-15 13:52 | 2026-03-18 |  | 2026-03-15 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-22 |  | 2026-03-23 | [5 empty] | 2026-03-29 |  | 2026-04-06 |  | 2026-04-07 |  |  |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 | [6 empty] | 2026-05-05 |  | 2026-05-14 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-08 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-04-15 |  | 2026-03-24 |  | Unknown | 2026-03-15 | 2026-03-15 13:51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-15 13:55:07 +0530 | Nishtha Valawalkar | CX having vila in Lodha Royal Vila 4 BHK 1600 Sq.ft in Dombiwali. Budget set expectation - 40L Marwadi CX Explored the market and having quotes. Already informed that plumbing and core civil will not be done by Bonito. Given written over the paper. | 2026-03-15 13:53:19 +0530 | Nishtha Valawalkar | Some Image was uploaded |  |  |  | 2026-03-29 |  | 2026-04-05
18877 | Turnkey | 2026-01-01 | Elsa Hill | sandu ShilpaDatta | MUM - GOR | Yes | Priyanka Murarka | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Manasi Patil |  | Hold | Preproduction | DEM2 | 1497761 | 220634 | 1442541 | 0 | 0 | 39 | 47 | 0 | 0 | 694392 | 582734.8 |  |  | 2026-03-15 | 2026-03-21 17:31 | 2026-03-23 | 2026-03-22 23:24 | 2026-03-25 | 2026-03-23 15:21 | 2026-04-18 | 2026-04-18 14:08 | 2026-05-30 | 2026-05-29 12:05 | 2027-03-04 |  | 2026-03-23 | 2026-03-25 16:43 | 2026-03-24 | 2026-03-25 16:54 | 2026-03-25 | 2026-03-28 13:19 | 2026-04-05 | 2026-04-05 12:51 |  |  |  |  | 2026-04-18 | 2026-04-20 15:06 | 2027-02-27 |  | 2027-02-28 |  |  |  | 2027-03-07 |  | 2027-03-08 |  | 2027-03-09 |  | 2027-03-10 | [6 empty] | 2027-03-28 |  | 2027-04-06 |  | 2027-04-05 |  | 2027-04-06 |  | 2027-04-07 |  | 2027-04-09 |  |  |  | 2027-05-01 |  | 2027-05-03 |  | 2027-05-04 | [5 empty] | 2027-03-08 |  | 2026-08-05 | 2026-04-18 13:50 | Site is RTMI | 2026-03-15 | 2026-03-20 16:28 | 1222492 | 220048 | 0 | 0 | 0 | 0 | 1531480.4745 | 252878 | 2026-05-29 13:17:22 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-24 15:23:49 +0530 | Priyanka Murarka | DDM2: 24/05 Living room All cabinets in push to open Laminate on alter panel - STS Paladine Marble 1449 with lights from all sides. Paint - Tear drop - 9244 - pg 184 Wallpaper - 4040-2 Aurora - behind sofa Laminate for shoe cabinet & window seating - Platinum-BD-LAM-2023-0016 - Grey HG Vertical moulding - 22mm - behind tv Behind tall pantry unit - Laminate - 120 LUV Alumnina Grey and wallpaper on right side same as sofa wall. Peripheral drop on sides to cover sprinkler pipes & cove light. KITCHEN Laminate in full kitchen - platinum- BD-LAM-2023-0016 - GREY paint - ice grey - 8259 - pg 20 G profile - black - base Extended handle for wall unit Push to open for loft MBR & BEDROOM 1 Laminate - carolina rovere - 2289 SD handle - Sujin SI-072 - size 488mm Paint - White sugar - L181 pg. 22 MBR - wallpaper - 4032-2 aurora Vanities same as kitchen laminate There is no possession received can't align for cross measurements. Need to keep the project on hold till June end. | 2026-05-20 18:03:51 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-19 | 2026-04-18 14:11 | 2026-05-30 | 2026-05-29 12:47 | Under Construction | 2026-07-31
18878 | Turnkey | 2026-01-01 | Subramanian | Radiance Gardenia | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Installation | Execution | 2172303 | 2172303 | 2567668 | 0 | 2279803 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-19 12:01 | 2026-03-15 | 2026-03-22 02:42 | 2026-03-25 | 2026-04-04 18:48 | 2026-05-03 | 2026-05-03 19:19 | 2026-05-08 | 2026-05-07 13:35 | 2026-05-17 | 2026-05-17 19:09 | 2026-04-04 | 2026-04-08 19:57 | 2026-04-05 | 2026-04-10 13:26 | 2026-04-10 | 2026-04-11 14:00 | 2026-04-15 | 2026-04-15 15:12 |  |  |  |  | 2026-05-03 | 2026-05-05 14:29 | 2026-05-13 | 2026-05-16 17:12 | 2026-05-17 | 2026-05-17 01:48 |  |  | 2026-05-26 | 2026-05-27 11:32 | 2026-05-27 | 2026-05-27 17:46 | 2026-05-28 | 2026-05-27 17:57 | 2026-05-28 | 2026-05-28 19:16 |  |  |  |  | 2026-05-29 15:30 | 2026-06-12 | 2026-06-11 21:03 | 2026-06-29 | 2026-06-27 18:28 | 2026-06-28 | 2026-06-26 15:50 | 2026-06-27 | 2026-06-29 16:34 | 2026-06-29 | 2026-06-29 19:31 | 2026-07-07 | 2026-07-07 10:21 |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-05-27 | 2026-05-29 15:29 | 2026-04-16 | 2026-05-02 17:51 | Site is RTMI | 2026-03-15 | 2026-03-19 11:57 | 2175989 | 391678 | 0 | 0 | 2421188.1496 | 408783 | 2421188.1496 | 408783 | 2026-05-07 19:38:25 +0530 | Yogesh B | Some Image was uploaded | 2026-04-24 12:23:59 +0530 | Yogesh B | Some Image was uploaded | 2026-04-11 13:53:52 +0530 | Bency Chacko | Possession - RTMI - Awaiting registration, which will be done soon IMs can be taken, and they want to close designs immediately No on-site work is planned No civil work is planned agreements are cleared Checklists are closed B2C - self-funding Timelines are cleared Will close 10% after closing LFM. | 2026-05-04 | 2026-05-03 19:25 | 2026-05-08 | 2026-05-07 13:39 | RTMI
18879 | Turnkey | 2026-01-01 | Pallavi Bijutkar | akiya roots | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Lost | Design | DEM1 | 804663 | 84999 | 1108055 | 0 | 0 | 110 | 0 | 0 | 75934 | 342451 | 301279.2 |  |  | 2026-03-15 | 2026-03-21 12:47 | 2026-03-22 | 2026-03-22 23:26 | 2026-03-25 | 2026-03-23 15:21 | 2026-05-04 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-03-23 | 2026-03-24 21:08 | 2026-03-24 | 2026-03-25 13:17 | 2026-03-25 | 2026-03-27 11:09 | 2026-04-09 | [5 empty] | 2026-05-05 |  | 2026-05-13 |  | 2026-05-14 |  |  |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 | [6 empty] | 2026-06-11 |  | 2026-06-20 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-23 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-05-22 |  | 2026-04-30 |  | Unknown | 2026-03-15 | 2026-03-21 12:47 | 941316 | 166738 | 0 | 0 | 0 | 0 | 918716 | 143720 | 2026-04-28 12:17:16 +0530 | Manzoor Shaikh | Tried calling the customer, however, the call went unanswered, the store credit 0f 84,999 is issued. | 2026-04-28 12:08:05 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-17 18:40:31 +0530 | Manzoor Shaikh | The customer wishes to cancel the project after signing the agreement. She stated that she was not informed about the cancellation policy or refund terms. Due to a financial crunch, she is seeking a refund. Additionally, the customer mentioned that Harshaan advised her to respond Yes during the onboarding call and assured her that he would later inform her about possible options. | 2026-05-05 |  | 2026-05-12 |  | Under Construction | 2026-04-19
18880 | Turnkey | 2026-01-01 | Geethu | Nava Vajra | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Hold | Preproduction | DEM2 | 1610545 | 322109 | 1610545 | 0 | 0 | 40 | 5 | 0 | 0 | 659565 | 628870.8 |  |  | 2026-03-14 | 2026-03-24 17:46 | 2026-03-15 | 2026-03-25 09:35 | 2026-03-28 | 2026-03-25 12:05 | 2026-05-17 | 2026-05-17 18:55 | 2026-11-16 |  | 2026-12-08 |  | 2026-03-22 | 2026-03-24 17:20 | 2026-03-23 | 2026-03-24 19:27 | 2026-03-26 | 2026-03-26 14:15 | 2026-04-01 | 2026-04-01 11:46 |  |  |  |  | 2026-05-17 | 2026-05-31 13:18 | 2026-12-03 |  | 2026-12-04 |  |  |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-13 |  | 2026-12-14 | [6 empty] | 2027-01-01 |  | 2027-01-10 |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-11 |  | 2027-01-13 |  |  |  | 2027-02-04 |  | 2027-02-06 |  | 2027-02-07 | [5 empty] | 2026-12-12 |  | 2026-04-02 | 2026-05-02 16:44 | Site is RTMI | 2026-03-14 | 2026-03-15 15:14 | 1364868 | 245676 | 0 | 0 | 0 | 0 | 1364868 | 245676 | 2026-04-23 12:27:06 +0530 | Parasa Sri | Some Image was uploaded | 2026-04-01 11:54:08 +0530 | Parasa Sri | Welcome call is done. Key is available for Initial measurement. Client is not available for meetings till may. | 2026-03-26 14:12:29 +0530 | Bency Chacko | Dec 2026 - Possession Aug - On-site work can begin - Soft Possession IMs can be taken Design fees - 11th April 2026 No on-site work is planned No civil work is planned Checklist is cleared Agreements are cleared Timelines are cleared B2C - self funded | 2026-05-18 | 2026-05-17 18:56 | 2026-11-17 |  | Under Construction | 2026-08-04
18882 | Turnkey | 2026-01-01 | Manoj Mistry | Piramal Mahalaxmi | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Design | DEM1 | 1095519 | 139999 | 1393157 | 0 | 0 | 100 | 0 | 0 | 79105 | 477896 | 398519.6 |  |  | 2026-03-15 | 2026-03-28 20:51 | 2026-03-15 | 2026-03-30 18:49 | 2026-03-30 | 2026-03-30 19:05 | 2026-08-20 |  | 2026-08-27 |  | 2026-09-03 |  | 2026-03-30 | 2026-03-31 20:58 | 2026-03-31 | 2026-04-02 12:16 | 2026-04-02 | 2026-04-06 14:42 | 2026-04-11 | 2026-04-11 18:18 |  |  |  |  | 2026-08-21 |  | 2026-08-29 |  | 2026-08-30 |  |  |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 | [6 empty] | 2026-09-27 |  | 2026-10-06 |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-09 |  |  |  | 2026-10-31 |  | 2026-11-02 |  | 2026-11-03 | [5 empty] | 2026-09-07 |  | 2026-08-16 |  | Unknown | 2026-03-15 | 2026-03-28 20:50 | 1183443 | 209714 | 0 | 0 | 0 | 0 | 1180266.3322 | 195964 | 2026-04-17 17:46:44 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-15 17:04:29 +0530 | Manasi Patil | Some Image was uploaded | 2026-04-11 18:15:59 +0530 | Manzoor Shaikh | "Welcome call done. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : July End Customer will make 10% on 15th April as per Manasi's acknowledgement. FDM dates: TBD Price protection for 150 days from the NET date." | 2026-08-21 |  | 2026-08-28
18883 | Turnkey | 2026-01-01 | Rakesh Rakesh | karle vario homes | BNG - HRBR | Yes | Sagarika Venkatesh | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Banka H Suthar | Saddam Hussain Z M |  | Mohammed Rasick | Vishwa Hiremath | Active | Production | Dispatch Due | 1702146 | 1702146 | 2080260 | 0 | 1702146 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-25 18:24 | 2026-03-15 | 2026-03-25 18:42 | 2026-03-28 | 2026-03-25 19:48 | 2026-04-24 | 2026-04-20 15:51 | 2026-05-18 | 2026-05-17 13:34 | 2026-05-30 | 2026-05-30 13:58 | 2026-03-25 | 2026-03-31 | 2026-03-26 | 2026-04-03 08:32 | 2026-04-03 | 2026-04-04 14:37 | 2026-04-05 | 2026-04-05 13:11 |  |  |  |  | 2026-04-20 | 2026-04-24 18:06 | 2026-05-24 | 2026-05-24 20:18 | 2026-05-25 | 2026-05-26 20:00 |  |  | 2026-06-04 | 2026-06-06 17:26 | 2026-06-09 | 2026-06-09 13:44 | 2026-06-10 | 2026-06-09 15:30 | 2026-06-10 | 2026-06-11 18:44 |  |  |  |  | 2026-06-12 18:59 | 2026-06-23 | 2026-06-22 21:21 | 2026-07-01 | 2026-06-29 19:17 | 2026-06-30 | 2026-07-09 19:39 | 2026-06-29 | 2026-07-14 20:07 | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-06-09 | 2026-06-12 18:58 | 2026-04-06 | 2026-04-20 15:50 | Site is RTMI | 2026-03-15 | 2026-03-15 16:41 | 1762932 | 317327 | 0 | 0 | 1816734.5638 | 293208 | 1816734.5638 | 293208 | 2026-06-07 10:40:20 +0530 | Arjun M V | Some Image was uploaded | 2026-06-05 19:40:58 +0530 | Arjun M V | Some Image was uploaded | 2026-04-05 13:13:47 +0530 | Rajeshwari S | Called Mr. Rakesh. Client is available in Bangalore only till 7th April post that he is not available for 2 weeks. Wants to have 1st meeting online. IM has to be scheduled and inform to client. Tuesday we have to call client along with designer. will confirm on key available for IM Confirmed that Estimation was closed for Rs.16,10,646/- Informed on 10% to be paid on 17th. April | 2026-04-21 | 2026-04-20 15:52 | 2026-05-18 | 2026-05-17 13:34 | RTMI
18884 | Turnkey | 2026-01-01 | Dhawal Rathore | Tigon Elite | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 907863 | 9999 | 0 | 0 | 0 | 122 | 0 | 80787 | 90786 | 377305 | 348985.2 |  |  | 2026-03-15 | 2026-03-15 20:57 | 2026-03-16 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-15 | 2026-03-15 20:56 | 0 | 0 | 0 | 0 | 0 | 0 | 1087177.39 | 170140 | 2026-03-15 20:59:30 +0530 | Anant Giri | Some Image was uploaded | [6 empty] | 2026-04-05 |  | 2026-04-12
18885 | Turnkey | 2026-01-01 | Vishwanth Kenkre | Courtyard | MUM - GOR | No Estimate | [8 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-17 15:00 | 2026-03-19 |  | 2026-03-19 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-03-14 | 2026-03-15 17:05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-08 11:04:44 +0530 | Meet Shah | Some Image was uploaded | 2026-03-16 18:41:22 +0530 | Khushi Khandelwal | DCM: Living & dining spaceÂ 3+ 2 seater sofaÂ tv unitÂ 4 seater or foldable table with 2 chairs Kitchen Ref.Â mixer juicer blenderÂ hob & chimneyÂ Bedroom-01 Master bedroomÂ BedÂ wardrobeÂ side tableÂ Study areaÂ Bedroom-02 Elderly people Dresser & mandirÂ No wardrobeÂ Bedroom-03 Murphy bedÂ storageÂ study deskÂ |  |  |  | 2026-03-30 |  | 2026-04-06
18886 | Turnkey | 2026-01-01 | Mrs Shroff | beaupride | MUM - GOR | No Estimate | [8 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-17 15:00 | 2026-03-25 | 2026-03-25 14:02 | 2026-03-18 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-14 | 2026-03-17 14:59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-15 13:51:38 +0530 | Moni Sahani | Some Image was uploaded | 2026-03-25 13:58:18 +0530 | Priyanka Patel | DCM: Customer and Project Profile1. Name of the customer Mr Shroff 2. Profession NA 3. Project Name/Tower Name/Flat Number VERSOVA 4. Typology (1BHK, 2BHK, 3BHK, etc) 5BHK 5. Site Access Date 2026-03-25 6. Possession Date 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 500000 Customer Preferences8. Who will be living in the house? Single, Nuclear Family, Joint Family, Elderly Members, Live-In Help 9. What activities do you usually prefer at your home ? Working From Home, Hosting Guests, Family Bonding, Relaxing and Unwinding, Pursuing Hobbies 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any NA 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) NA Upload reference images 14. Any absolute no-go styles colours or materials NA 15. Do you have any existing furniture that must be accommodated? NA 13. Do you want the design to reflect any personal story, cultural influence, or special memory NA ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? TV Focus, Multipurpose, Entertaining guests 2. Must-have furniture or features? Sofa, Statement Wall/ Feature, Display unit , Puja unit, Bookshelves, Coffee table, Speakers, Home speakers, TV unit 3. Choose your decor inspirations Artwork, Travel souvenirs 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Partitions, Crockery unit 2. Must-have appliances? Washing machine, Built-in Oven, Dishwasher, Chimney, Hob, Fridge, Microwave 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Study Table, TV unit, Dresser, Bookshelf 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Guest 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units TV unit, Dresser , Bookshelf , Study table 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Other 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units TV Unit, Dresser, Bookshelf, Study Table 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility Guests 16. Bedroom 3 - Bed Type Storage 17. Bedroom 3 - Wardrobe Style Sliding 18. Bedroom 3 - Additional Units TV Unit, Dresser, Study Table 19. False Ceiling Required - Bedroom 3 Yes Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Top Storage, Extra sink, Tall Storage Balcony & Outdoor1. How do you intend to use your balcony? Utility, Furniture 2. Outdoor Mood How do you intend to use the utility Appliances Miscellaneous1. Timeline related commitment made by Bonito, if any NA 2. Other commitments made by Bonito to customer, if any NA 3. What are offers committed to customers? NA 4. Move-in date confirmed with customer 2026-03-25 5. Any special occasion mentioned by the customer wrt handover date NA 6. Additional Requirements (Mention any requirements from customer not covered in the form) NA 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 500000 |  |  |  | 2026-04-05 |  | 2026-04-12
18887 | Turnkey | 2026-01-01 | Akshay | 3 bedroom independent home | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik |  | Parvez Syed | Yogeshwaran | Ranjith Kumar | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Active | Production | Production | 712678 | 430670 | 1181358 | 0 | 759330 | 2 | 0 | 0 | 0 | 0 | 282008 |  |  | 2026-03-15 | 2026-03-15 17:18 | 2026-03-18 | 2026-03-18 18:36 | 2026-03-22 | 2026-03-22 11:45 | 2026-05-05 | 2026-06-14 19:49 | 2026-06-19 | 2026-06-18 17:19 | 2026-06-29 | 2026-06-28 12:55 | 2026-03-22 | 2026-03-25 12:33 | 2026-03-23 | 2026-03-25 15:20 | 2026-03-25 | 2026-03-25 17:21 | 2026-04-03 | 2026-04-03 19:49 |  |  |  |  | 2026-05-06 | 2026-06-14 17:45 | 2026-06-23 | 2026-06-23 10:25 | 2026-06-24 | 2026-06-23 10:25 |  |  | 2026-06-28 | 2026-06-30 20:28 | 2026-06-30 | 2026-06-30 21:09 | 2026-07-01 | 2026-06-30 21:28 | 2026-07-01 | 2026-06-30 22:05 |  |  |  |  | 2026-07-03 21:04 | 2026-07-14 | 2026-07-13 20:11 | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-30 | 2026-07-03 21:03 | 2026-05-15 | 2026-05-04 12:00 | Site is RTMI | 2026-03-15 | 2026-03-15 17:17 | 1001151 | 180207 | 0 | 0 | 853615.0315 | 140999 | 854690.1315 | 141128 | 2026-07-07 10:34:19 +0530 | Ranjith Kumar | Bonito Side - Floor Covering only Cx Side - Electrical, Civil & Corecutting | 2026-06-30 11:09:25 +0530 | Chittipireddy Sriharish | Some Image was uploaded | 2026-06-28 19:20:15 +0530 | Chittipireddy Sriharish | Some Image was uploaded | 2026-06-15 | 2026-06-14 19:57 | 2026-06-19 | 2026-06-22 18:27 | RTMI
18889 | Turnkey | 2026-01-01 | Anup kumar | Ecolife Akash | BNG - HSR | Yes | Vishal Haridas | Akshay Ds | Soumya KP | [5 empty] | Fuzail Girach |  | Active | Preproduction | DEM2 | 1588288 | 317658 | 1844227 | 0 | 0 | 21 | 7 | 0 | 0 | 662570 | 608059.6 |  |  | 2026-03-15 | 2026-03-18 11:56 | 2026-03-18 | 2026-03-18 18:05 | 2026-03-20 | 2026-03-20 13:25 | 2026-06-18 | 2026-06-17 16:47 | 2026-08-05 |  | 2026-08-12 |  | 2026-03-20 | 2026-03-20 22:34 | 2026-03-21 | 2026-04-04 14:41 | 2026-04-04 | 2026-04-07 11:04 | 2026-04-12 | 2026-04-12 18:46 |  |  |  |  | 2026-06-22 | 2026-06-24 17:50 | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-06-12 | 2026-06-17 01:23 | Site is RTMI | 2026-03-15 | 2026-03-15 17:56 | 1562904 | 281322 | 0 | 0 | 0 | 0 | 1707511 | 281942 | 2026-05-30 16:23:43 +0530 | Akshay Ds | Some Image was uploaded | 2026-05-23 17:32:51 +0530 | Preethi Shetty | 23/05/2026 cx - Anup KumarÂ TV unit - 2 tall unit with one glass shutter, one solid shutter Acc to unit check for FC as per ref. Partition with storage as per ref. Pooja unit to be confirmed- incase if cx need add bottom storage of 1 ft htÂ Kitchen - MBR entrance : Gypsum panel with wallpaper - to be confirmed ,Â Maindoor wall - sleek mirror panelling , with sofa wall design to be changed GBR -Â Sliding wardrobe , Dresser : draw + mirror with storage wall design as per the unit placement KBR - Study wall unit add one more open unitÂ MBR - 5 shutter storage, with dresser - with mirror storage , bottom storageÂ | 2026-05-19 19:18:09 +0530 | Preethi Shetty | Need to work on the design changes as per client, client is available during weekend, need to schedule the meeting as per his availability | 2026-06-18 | 2026-06-17 16:51 | 2026-08-06 |  | Under Construction | 2026-06-01
18890 | Turnkey | 2026-01-01 | Ashutosh Kumar | Shriram WYTField | BNG - HSR | Yes | Kiran Agarampalli | Abhinandan K S | Kowshik |  | Parvez Syed | Shivakumar Ms | Jairam Joshi | Murali S | Muralikrishna Udupi | Affaan Abdulla | Active | Installation | Execution | 1130722 | 1130722 | 1141966 | 0 | 1130722 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-15 18:13 | 2026-03-17 | 2026-03-24 15:48 | 2026-03-27 | 2026-03-24 15:54 | 2026-04-19 | 2026-04-19 21:04 | 2026-05-31 | 2026-05-30 09:29 | 2026-06-10 | 2026-06-09 19:14 | 2026-03-24 | 2026-03-24 17:10 | 2026-03-25 | 2026-03-25 15:48 | 2026-03-25 | 2026-03-26 16:19 | 2026-03-27 | 2026-03-27 19:45 |  |  |  |  | 2026-04-19 | 2026-04-20 12:25 | 2026-05-31 | 2026-05-31 20:36 | 2026-06-01 | 2026-05-31 20:36 |  |  | 2026-06-11 | 2026-06-13 18:36 | 2026-06-13 | 2026-06-13 20:08 | 2026-06-26 | 2026-06-14 19:18 | 2026-06-27 | 2026-06-14 19:16 |  |  |  |  | 2026-06-20 14:55 | 2026-07-01 | 2026-06-30 20:00 | 2026-07-09 | 2026-07-07 18:59 | 2026-07-08 | 2026-07-08 15:39 | 2026-07-07 | 2026-07-10 14:46 | 2026-07-11 | 2026-07-11 08:58 | 2026-07-15 | 2026-07-14 13:05 |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-13 | 2026-06-20 14:54 | 2026-04-03 | 2026-04-19 21:00 | Site is RTMI | 2026-03-15 | 2026-03-15 18:11 | 967768 | 174198 | 0 | 0 | 1255378.8737 | 199177 | 1255378.8737 | 199177 | 2026-07-03 16:35:29 +0530 | Jairam Joshi | Procurement: All PI works completed SRD task closed | 2026-06-20 14:53:24 +0530 | Jairam Joshi | Procurement: CX side PI works in progress Key - 25th June FC- 26th Ele and false cieling works - 6th July SRD - 7th July | 2026-06-11 17:18:37 +0530 | Kiran Agarampalli | Some Image was uploaded | 2026-04-20 | 2026-04-19 21:08 | 2026-05-31 | 2026-05-30 09:30 | RTMI
18891 | Turnkey |  | Aditya P Raut |  | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Savita Parab | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Active | Production | Dispatch Due | 434005 | 434006 | 378268 | 0 | 434005 | 5 | 1 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-21 11:26 | 2026-03-16 | 2026-04-07 13:02 | 2026-04-07 | 2026-04-07 13:29 | 2026-04-07 | 2026-04-07 14:18 | 2026-05-07 | 2026-05-06 19:16 | 2026-05-08 | 2026-05-08 19:28 | 2026-03-19 | 2026-04-06 22:04 | 2026-04-08 | 2026-04-07 13:29 | 2026-04-07 | 2026-04-07 13:29 | 2026-04-08 | 2026-04-07 13:30 |  |  |  |  | 2026-03-27 | 2026-04-06 22:04 | 2026-05-07 | 2026-05-06 21:42 | 2026-05-07 | 2026-05-06 21:42 |  |  | 2026-05-19 | 2026-05-20 15:21 | 2026-05-23 | 2026-05-23 15:18 | 2026-05-24 | 2026-05-23 16:04 | 2026-06-10 | 2026-06-04 17:40 |  |  |  |  | 2026-06-15 23:55 | 2026-06-21 | 2026-06-20 22:13 | 2026-06-25 | 2026-06-24 13:09 | 2026-06-24 | 2026-07-10 12:01 | 2026-07-02 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-08-21 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-05-23 | 2026-06-15 23:54 | 2026-04-08 | 2026-04-07 13:30 | Unknown | 2026-03-15 | 2026-03-21 11:26 | 478684.332 | 79057 | 0 | 0 | 530213.2283 | 87560 | 530213.2283 | 87560 | 2026-07-08 23:50:25 +0530 | Savita Parab | Execution: floor covering dne site is on hold due to no water and electric supply inside the flat and no lift for material loading | 2026-07-08 23:45:32 +0530 | Savita Parab | Execution: floor covering done site is on hold due to no water and electric supply inside the flat and there is no lift for material loading | 2026-06-30 17:46:25 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-08 | 2026-04-07 14:20 | 2026-05-07 | 2026-05-06 19:18
18892 | Turnkey | 2026-01-01 | Umesh kasle | Satelite Eligance | MUM - GOR | No Estimate | Khushi Khandelwal |  | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-17 14:59 | 2026-03-15 | 2026-03-17 20:11 | 2026-03-21 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 | [5 empty] | 2026-03-28 |  | 2026-04-05 |  | 2026-04-06 |  |  |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 | [6 empty] | 2026-05-04 |  | 2026-05-13 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-16 |  |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-04-14 |  | 2026-03-23 |  | Unknown | 2026-03-15 | 2026-03-15 18:25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-15 13:47:40 +0530 | Moni Sahani | Some Image was uploaded | 2026-03-15 19:11:03 +0530 | Khushi Khandelwal | DCM: 1BHK+2BHKÂ June posessionÂ 5 people+ pet dog 1063 Sqft 1bhk common washroom can be used as home office & study room 1bhk kitchen- can be used as pooja roomÂ MASTER BEDROOM (1BHK) WardrobeÂ Queen size bed (acc. to the room size) Side tableÂ TV on wall LIVING ROOMÂ Sofa 3+2 SEATERÂ Dining table- Low height seatingÂ TV unitÂ BEDROOM-01 Wardrobe & modular bedÂ Cozy space for pet (funky theme)OR GALAXY THEME Bedroom-02 (master bed) walkin-WardrobeÂ Queen bedÂ Dresser |  |  |  | 2026-03-28 |  | 2026-04-04
18893 | Sub Project |  | Kiran Uttekar | Shraddha Pearl | MUM - GOR |  | Riddhi Deshpande |  | Safalta Karkera |  |  | suraj kumar | Aditya Vikram | Murali S |  | Aakash Gaikwad | Active | Production | 100% Payment | 36669 | 36886 | 0 | 0 | 41669 | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-05-27 12:03 | 2026-03-16 | 2026-05-27 12:03 | 2026-05-27 | 2026-05-27 12:03 | 2026-05-28 | 2026-05-27 12:04 | 2026-05-28 | 2026-05-27 12:05 | 2026-05-28 | 2026-05-27 12:06 | 2026-05-27 | 2026-05-27 12:03 | 2026-05-28 | 2026-05-27 12:03 | 2026-05-27 | 2026-05-27 12:03 | 2026-05-28 | 2026-05-27 12:04 |  |  |  |  | 2026-05-27 | 2026-05-27 12:04 | 2026-05-28 | 2026-05-27 12:06 | 2026-05-28 | 2026-05-27 12:06 |  |  | 2026-05-28 | 2026-05-27 15:49 | 2026-05-28 | 2026-05-28 14:50 | 2026-05-29 | 2026-05-28 15:09 | 2026-05-29 | 2026-05-28 15:09 |  |  |  |  | 2026-05-29 12:27 | 2026-06-03 | 2026-06-03 23:33 | 2026-06-08 | 2026-06-06 11:09 | 2026-06-07 |  | 2026-06-06 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-05-28 | 2026-05-28 15:09 | 2026-05-28 | 2026-05-27 12:04 | Unknown | 2026-03-15 | 2026-05-23 22:10 | 0 | 0 | 0 | 0 | 62770.6271 | 6356 | 62770.6271 | 6356 | 2026-05-14 18:17:29 +0530 | Reshma Melanta | Some Image was uploaded | [6 empty] | 2026-05-28 | 2026-05-27 12:04 | 2026-05-28 | 2026-05-27 12:05
18894 | Turnkey | 2026-01-01 | Jignesh Bhinde | Runwal SANCTUARY | MUM - Thane | Yes | Moksh Mehta | Anamika Dolai | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1942380 | 9999 | 0 | 0 | 0 | 122 | 0 | 184239 | 194238 | 846890 | 707014.4 |  |  | 2026-03-15 | 2026-03-15 20:33 | 2026-03-15 |  | 2026-03-15 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-03-15 |  | 2026-03-16 |  | 2026-03-16 |  | 2026-03-17 | [5 empty] | 2026-03-23 |  | 2026-03-31 |  | 2026-04-01 |  |  |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-10 |  | 2026-04-11 | [6 empty] | 2026-04-29 |  | 2026-05-08 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-11 |  |  |  | 2026-06-02 |  | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-04-09 |  | 2026-03-18 |  | Unknown | 2026-03-15 | 2026-03-15 20:16 | 0 | 0 | 0 | 0 | 0 | 0 | 1646085 | 296295 | 2026-03-15 20:36:37 +0530 | Nishtha Valawalkar | 2 BHK Runwal Sanctuary 12 to 14L 720 SQ.FT DCM done by Garv As of now cdp planned for 24th March at 3 PM | 2026-03-15 20:35:10 +0530 | Nishtha Valawalkar | Some Image was uploaded |  |  |  | 2026-03-23 |  | 2026-03-30
18895 | Turnkey | 2026-01-01 | Deepa Kunder | Lodha Woods | MUM - GOR | Yes | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera |  |  | Nishant Jadhav | Sandeep Tiwari |  | Rashmita Das | Siddhesh Gujrathi | Active | Preproduction | DEM2 | 1554234 | 257594 | 1661631 | 0 | 0 | 4 | 0 | 0 | 0 | 688552 | 608087.6 |  |  | 2026-03-15 | 2026-03-20 11:50 | 2026-03-28 | 2026-03-28 15:22 | 2026-03-30 | 2026-03-30 14:03 | 2026-06-17 | 2026-06-17 18:42 | 2026-07-12 | 2026-07-11 16:44 | 2026-07-18 |  | 2026-03-30 | 2026-03-30 16:58 | 2026-03-31 | 2026-04-02 11:17 | 2026-04-02 | 2026-04-02 16:14 | 2026-04-04 | 2026-04-04 18:53 |  |  |  |  | 2026-06-07 | 2026-06-17 17:29 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-04-05 | 2026-06-06 15:19 | Site is RTMI | 2026-03-15 | 2026-03-15 19:05 | 1408162 | 253469 | 0 | 0 | 0 | 0 | 1566825.7218 | 264544 | 2026-06-09 17:23:36 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-07 17:56:08 +0530 | Safalta Karkera | DDM1: Hi, Minutes of Meeting held on Date: 06/06/26 Attendees: Rajnish, Shreya and Client Discussion: DEM-1 layout Finalization Based on 06/06/26 meeting, below is a list of all the requirements that were discussed during the meeting: Living Room Tv unit to be floor mounted Tv unit back wall to be design in 2 options- Marble tile finish and Plain wall with louvers and texture paint/ wallpaper Sofa wall to be design as per refrence Dinning wall to be design as per CDP Pencil Drawer and Steps to be added in mandir unit CX might selected mandir unit from store (update is pending) Plain False ceiling with profile lights Colour theme brown and Beige Kitchen Base, Wall and Loft unit as per discussion in meeting Wicker Basket to be added in kitchen base unit Storoge/decor above Refrigerator Dustbin and Detergent holder to be added Cx might change counter top stone (CX scope) Cx wants to change Dado tiles (CX scope) Utility Area is in Cx scope as disccued in meeting Master Bedroom Wardrobe Layout Possition and Internal of Wardrobe as disccued in meeting One side table No TV and TV Unit on wall Pelmet to be added Wall to be disgned as per reference Mirror to be added above Side table False ceiling discussion is pending Kids Bedroom, Bathrooms, Balcony and False Ceiling Design to be discussed in next Meeting. | 2026-06-06 16:10:13 +0530 | Manzoor Shaikh | The customer has received the possession on 28th May IM done on 30th May. | 2026-06-18 | 2026-06-17 18:43 | 2026-07-12
18896 | Turnkey | 2026-01-01 | Nikita Dandekar Singh | micl parkwood | MUM - GOR | Yes | Swapnali Shedekar | Reshma Melanta | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Preproduction | DEM2 | 1692537 | 338504 | 2048968 | 0 | 0 | 44 | 43 | 0 | 0 | 812289 | 541744.4 |  |  | 2026-03-15 | 2026-03-15 19:39 | 2026-03-15 | 2026-03-20 15:29 | 2026-03-20 | 2026-03-20 20:05 | 2026-04-01 | 2026-03-31 15:04 | 2026-06-25 |  | 2026-07-02 |  | 2026-03-20 | 2026-03-24 12:55 | 2026-03-21 | 2026-03-24 13:24 | 2026-03-24 | 2026-03-24 16:44 | 2026-03-27 | 2026-03-27 19:01 |  |  |  |  | 2026-04-15 | 2026-05-08 18:57 | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-03-28 | 2026-03-31 14:53 | Site is RTMI | 2026-03-15 | 2026-03-15 19:38 | 1739215 | 309753 | 0 | 0 | 0 | 0 | 1731577.9535 | 288941 | 2026-05-07 17:43:47 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-27 16:16:51 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-27 16:05:44 +0530 | Reshma Melanta | CALLED THE CX DID NOT ANSWER | 2026-05-31 | 2026-04-05 18:50 | 2026-06-26
18897 | Turnkey | 2026-01-01 | Prateek Somani | prestige city meridian park | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 2213230 | 9999 | 0 | 0 | 0 | 122 | 0 | 211324 | 221323 | 885292 | 885292 |  |  | 2026-03-15 | 2026-03-15 20:11 | 2026-04-25 | 2026-04-27 12:15 | 2026-04-27 |  | 2026-05-04 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-28 |  | 2026-04-29 | [5 empty] | 2026-05-05 |  | 2026-05-13 |  | 2026-05-14 |  |  |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 | [6 empty] | 2026-06-11 |  | 2026-06-20 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-23 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-05-22 |  | 2026-04-30 |  | Unknown | 2026-03-15 | 2026-03-15 20:10 | 0 | 0 | 0 | 0 | 0 | 0 | 1875619 | 337611 | 2026-04-25 21:25:42 +0530 | Priyamvada PV | Cx : Prateek Somani RGM dated : 25.04.26 Property :Â Prestige city meridian park site access date : June/july' 26 Possession date : Aug'26 last week MDÂ : East facingÂ Family members : 2 adults, 2 kidsÂ Kids : 5.5 & 1.5 girls Rutvi & Kashvi F2C : 9.5' height Budget - 10-15LÂ minimal and modern spacious designs lighter tone warm feeling, pop up colors minimallyÂ Scope of work :Â Foyer storage with seating (30-40 pairs) keys umbrella etc storage along with shoe rack Wall design to be done Dining :Â 6 seater Dining table Crockery unit - base unit with granite, wall unit mirror not reflecting door, mirror with family photo wall on left of Dining table family photo wall to be highlighted TV unit :Â wall mounted TV unit with pooja No tall unit back wall to be designed Pooja - No CNC doors, modern with glass shutters to merge with tv design sofa : L shape sofa towards balcony Kitchen :Â AppliancesÂ mixer, microwave, fryer, dishwasher, wet grinder DW next to kitchen sink Utility will have main sink and washing machine wall storage gas cylinder unit, extra cylinder in utility Fridge - single door mix of glass units and laminate spice rack to be planned Granite - Bonito Designs scope mop unit to be checked as per space in utility BR-1 (MBR) King size bed L shaped wardrobe No TV unit, study unit storage near bedroom entry Dressing - not rectangular mirror (diff stand out) L Glass wardrobe and laminate wardrobe Vanity base storage all vanitiesÂ BR-2 (KBR) Queen size bed Hinged wardrobe for both kids dressing study separate for kids bay window seating BR-3 (GBR) Queen size bed space mirror on the wallÂ study cum iron space (aesthetically better) Hinged wardrobe Printer space in either KBR/GBR False ceiling :Â Plain FC in Foyer, living , dining , MBR | [6 empty] | 2026-05-05 |  | 2026-05-12
18898 | Turnkey | 2026-01-01 | amit soni | Natasha Atlantis | MUM - Thane | Yes | [8 empty] | Anjan Kumar |  | Active | Prospect | 10% Payment | 691696 | 9999 | 0 | 0 | 0 | 73 | 0 | 59171 | 69170 | 325644 | 227712.4 |  |  | 2026-03-15 | 2026-03-15 21:20 | 2026-04-30 | 2026-04-30 14:55 | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-04 |  | 2026-05-05 | [5 empty] | 2026-05-11 |  | 2026-05-19 |  | 2026-05-20 |  |  |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 | [6 empty] | 2026-06-17 |  | 2026-06-26 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-29 |  |  |  | 2026-07-21 |  | 2026-07-23 |  | 2026-07-24 | [5 empty] | 2026-05-28 |  | 2026-05-06 |  | Unknown | 2026-03-15 | 2026-03-15 20:55 | 0 | 0 | 0 | 0 | 0 | 0 | 784913 | 141284 | 2026-04-30 14:56:05 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-04-10 16:42:48 +0530 | Archita Loya | DCM: Name: Amit Soni Property Name: Natasha Atlantis Property type: 1BHK 402 Property Location:Â Possession: JULYÂ Move in: Member: 4 MEMBER COUPLE AND KIDS GIRL 6, BOY 1 Profession: BUISNESSMANÂ Â North direction: Â Â Existing Furniture:Â Requirements: Â Living room: TV UNIT WITH ONE OPEN DRAWER AND OTHER CLOSED, SOFA CUM BED, 4 SEATER DINING FOLDABLE, CROCKERY UNIT, MIRROR DESIGNING ON DINING WALL, SOFA NOT TYPCAL RECTANGULAR,MANDIR IN LIVING FULL LENGTH, SHOE RACK 10 TO 12 PAIR. Kitchen : L SHAPE COUNTER TOP WITH FRIDGE AND WASHING MACHINE SPACE ON SIDES, DUCTLESS CHIMNEY, BASE UNIT, WALL UNIT , LOFT AND ABOVE FRIDGE AND WASHING MACHINE AS WELL.Â Â Â Bedroom: WARDROBE WITH LOFT, LOW HEIGHT QUEEN SIZE BED OR NORMAL HEIGHT, DRESSING TABLE, MIRROR INSIDE WITH FULL HEIGH, LOOSE SIDE TABLE.Â Â Bathroom: VANITY IN BOTH BATHROOMS AND MIRROR ABOVE. Theme: MODERN MINIMALISTIC LOOK, LIGHTER SHADESÂ Â Additional scope: FALSE CEILING IN LIVING ROOM AND PROFILE LIGHT IN BEDROOM Â Â Â Â Â Â Â Â Â PAINTING Â Â Â Â Â Â Â Â Â ELCETRICAL.Â Â Budget:8Â Â Budget Suggested: 10 | 2026-04-07 16:13:29 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-05-11 |  | 2026-05-18
18899 | Turnkey | 2026-01-01 | Vijayant panda | Abhee Riviera Royale | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1644225 | 9999 | 1644225 | 0 | 0 | 107 | 0 | 154424 | 164423 | 657690 | 657690 |  |  | 2026-03-15 | 2026-03-20 14:34 | 2026-03-25 | 2026-03-26 12:01 | 2026-03-30 | 2026-03-30 13:29 | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Unknown | 2026-03-15 | 2026-03-20 10:48 | 1393411 | 250814 | 0 | 0 | 0 | 0 | 1393411 | 250814 | 2026-03-26 12:05:37 +0530 | Preksha Sajjanshettar | Some Image was uploaded | 2026-03-26 12:04:37 +0530 | Preksha Sajjanshettar |  | 2026-03-26 12:02:30 +0530 | Preksha Sajjanshettar | RGM Vijayanth Panda BHK-3 BHK Property - Riviera Royale Possession-JULY Facing -EAST Members-3 Kids -1 GIRL(1 YEAR OLD) NEXT VISIT-NEXT WEEK SATURDAY-6PM Budget -13+2L CAN BE STRETCHED THEME-80% CONTEMPORARY +20% MODERN EUROPEAN WITH NEUTRAL COLOURS) ALL LOOSE FURNITURES-CX SCOPE BATHROOM GLASS PARTITION,FITTINGS-CX SCOPE 1 QUEEN SIZE BED-NEEDED FOR KIDS BEDROOM(ENTRANCE BEDROOM) FOYER PARTITION+CONSOLE UNIT/TABLE FROM BONITO STUDIO(SLEEK PARTITION 2'.5" WITH POOJA UNIT ON THE ADJ WALL-3' POOJA UNIT) CROCKERY+POOJA UNIT(WHITE LAMINATE)TILL THE CEILING LEAVE THE DEPTH OF THE CROCKERY AND THEN BREAK THE WALL FOR BREAKFAST COUNTER BREAKFAST COUNTER-KITCHEN(WALL HAS TO BE DEMOLISHED AND SEATING , WITH STORAGE INSIDE THE KITCHEN)-UNDER THE COUNTER TO BE HIGHLIGHTED COLUMN SHOULD BE HIGHLIGHTED (BREAKFAST COUNTER WALL) QUARTZ COUNTERTOP(BONITO SCOPE) DINING TABLE-(5'/3'-6 SEATER) ADDITIONAL CROCKERY OR WALL DISPLAY UNIT WITH LESSER DEPTH AND 3' WIDTH ON TV WALL WASHBASIN WALL ONLY TO BE HIGHLIGTED WITH NO UNITS ON THE WALL BALCONY STORAGE ON ONE WALL(BASE+WALL+LOFT) KITCHEN+LOFT -ENTRANCE WALL TO BE PLANNED FOR BREAKFAST COUNTER TALL UNIT ON THE FRIDGE SPACE UTILITY WALL/PASSAGE WILL BE DEMOLISHED AND FRIDGE WILL BE PLACED THERE QUARTZ COUNTERTOP(BONITO SCOPE) CYLINDER IN THE L-CORNERUNIT APPLIANCES-MICROWAVE,AIR FRYER,TOASTER,GRINDER,INDUCTION,RO) SPICE RACK TO BE CLOSED GREY/BLACK TINTED GLASS BEIGE COLOUR OR SIMILAR SHADE WITH BLACK TINTED GLASS SHUTTERS HERE AND THERE -WALL UNITS LIGHTS BELOW THE WALL UNITS GTPT(IF SPACE IS THERE)BUT THERE IS A WINDOW ABOVE THE SINK )RO HAS TO BE PLACED ON THE WALL DUSTBIN/DETERGENT HOLDER BPO WICKER BASKET-CLOSED COOKTOP+CHIMNEY UTILITY SMALL SINK+WASHING MACHINE+WALL+LOFT JANITOR UNIT MBR L SHAPE HINGED WARDROBE+DRESSER IN HE CORNER AS PER REFERENCE+LOFT SLIDING WARDROBE+SEATER(TOWARDS BALCONY)+HANGING LIGHTS+LOFT ARISTO/HINGED WARDROBE TILL CEILING WITH BOTTOM STORAGE BED BACK WALL TO BE HIGHLIGHTEDÂ EXSITING BED DARK GREY HEADBOARD KING SIZE BED EXISTING FLOOR-WOODEN FINISH TILE(LIGHT WALNUT) BALCONY STORAGE ON ONE WALL(BASE+WALL+LOFT) GBR FLOATING SIDE TABLE TV WALL-HINGED/SLIDING WARDROBE EXISTING STUDY TABLE(4'/2') L SHAPE WARDROBE+BOOK SHELF+STUDY TABLE SIMPLE BED BACK HIGHLIGHT KBR QUEEN SIZE BED(FROM BONITO BASED ON THE BUDGET)/OR CX WILL PROCURE HINGED WARDROBE+LOFT STUDY TABLE ON THE TV WALL+BOOK SHELF NOT TO BE CARTOON THEMED FLOATING SIDE TABLE NEAR BALCONY DOOR PASTEL THEME WALLPAPER VANITY UNITS-ALL 3 TOILETS+MIRROR(OPTIONAL) COUNTERTOP WILL BE CONFIRMED BY THE CX FALSE CEILING IN ALL BEDROOMS ,LIVING DINING(PERIPHERAL ) FLOOR TO CEILING CURTAIN PROVISION NEAR ALL THE BALCONY DOORS | 2026-04-07 |  | 2026-04-14
18900 | Turnkey | 2026-01-01 | Rakesh Koli | Natasha Atlantis | MUM - Thane | No Estimate | [8 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-15 21:28 | 2026-03-16 |  | 2026-03-31 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-20 |  | 2026-03-21 | [5 empty] | 2026-03-27 |  | 2026-04-04 |  | 2026-04-05 |  |  |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 | [6 empty] | 2026-05-03 |  | 2026-05-12 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-15 |  |  |  | 2026-06-06 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-04-13 |  | 2026-03-22 |  | Unknown | 2026-03-15 | 2026-03-15 21:25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-03-27 |  | 2026-04-03
18901 | Turnkey | 2026-01-01 | Neha | Aadarsh park height | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 1878438 | 9999 | 0 | 0 | 0 | 120 | 0 | 177845 | 187844 | 751375 | 751375.2 |  |  | 2026-03-15 | 2026-03-17 16:38 | 2026-07-03 | 2026-07-08 11:32 | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-07-19 |  | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-14 |  | Unknown | 2026-03-15 | 2026-03-17 16:19 | 0 | 0 | 0 | 0 | 0 | 0 | 1591897 | 286541 | 2026-07-08 11:31:25 +0530 | Maspi Das | RGM Date : 03.07.2026 PID: 18901 Name : Neha Typology : 3BHK From : Profession : Property : Folium By Samudra Location : Site Access Date : July Main door facing : North-East Total Members : 6 Kids - 2 4 years girl, 6months Theme : CDP date : Budget- 10-12L Interior Design Requirements FALSE CEILING THROGHOUT THE HOUSE/ALSO WITHOUT Foyer - With mirrors and glass (Open to ideas) 1. Design a shoe rack with a seating bench near the mandir. 2. Explore adding overhead storage cabinets above the shoe rack. 3. Leave space for either:A decorative mirror, or An architectural feature wall. 4. Conceal the MCB/electrical panel with a seamless cabinet. 5. Plan decorative lighting with spotlights. 6. Since the entrance is north-facing, explore incorporating a flowing water element (as per Vastu, if feasible). 7. Include hidden storage for keys. Mandir - Movable one (IT has to be the Best part of the house, so need to design accordingly) follow as much as vastu possible 1. Position the mandir outside the kitchen. 2. Incorporate Krishna/Shyam Ji-inspired elements, such as:Peacock feather designKrishna artwork or motif 3. Use a white color theme with warm ambient lighting. 4. Design shutters that can be completely hidden when opened. 5. Provide a small seating arrangement if space permits. 6. Include sufficient storage cabinets. Kitchen 1. Pantry unit with drawers 2. Wicker basket (Instead of WB, what can be suggested) 3. Install a 4-burner hob cooktop. 4. Use a T-shaped chimney. 5. Create a dedicated appliance unit for: Microwave Oven Other kitchen appliances (suggestion) 6. Provide overhead loft storage. 7. Install the RO unit below the counter 9. Check the feasibility of installing a ceiling or wall-mounted fan. 10. Add internal cabinet lighting and also below the wall cabinets. 11. Include a few glass-front display cabinets(Mix of laminate and glass shutters) 12. Design a breakfast counter (Show with breakfast counter and without) 13. Explore a hidden transparent partition/door for the kitchen. 14. Add wooden paneling on the kitchen exterior. 17. Finalize premium tiles and granite selection. 18. Sink is preferred to be black Utility Area 1. Install sliding windows with invisible mosquito mesh. 2. Provide a sink dedicated to utensil cleaning. 3. Allocate space for: Dishwasher, Washing machine 4. Include cabinets and loft storage. 5. Plan a clothes drying provision. Dining Area 1. Design a crockery/display unit. 2. Install a chandelier above the dining area. 3. Provide a wash basin near the crockery unit, separated with a glass partition. 4. Accommodate a 4-seater dining table. 5. Consider a mirror in the dining area - MUST (as related to vastu and also makes the place looks bigger) Living Room 55" TV Sofa L-shaped 2. Include a center table. 3. Add a transparent half-height partition between the living and dining areas near the sofa. 4. Design a full-wall TV unit with: Display unit (nothing open), Decorative lighting and panel should be in Curve shape (with lights) 5. Provide double curtain tracks (sheer + blackout curtains). Balcony (Living Room) 1. Install invisible sliding mosquito mesh or safety grill. 2. Provide comfortable seating. 3. Create a vertical/hanging garden on one wall. 4. Explore storage options if feasible. DO CHECK WHAT CAN BE DONE REGARDING ATTATCHED BED FOR THE BEDROOMS Bedroom 3 (Small Bedroom) 1. Place a sliding wardrobe near the entrance. 2. Position a queen-size bed along the window wall. Include dedicated hanging space for daily-use clothes- NEED TO CHECK 5. Integrate a hidden dressing mirror Show rolling curtains 7. Design a Peripheral false ceiling Bedroom2 (Kids' Bedroom) 1. Provide a queen-size bed. --ACCENT WALL FOR THE BED REST WALL AS PER KBR THEME-- 2. Design a bay window with a study table beside it. 3. Create an accent wall using: Architectural elements, or A photo gallery wall 4. Position the wardrobe near the entrance. 5. Include a hidden dressing mirror within or beside the wardrobe. 6. Provide bedside tables. 7. Include hanging space for everyday clothing. 8. Install curtains. 9. Design a false ceiling with lighting. 10.Plan ledges or book storage for books or display (CAN STORE OR DISPLAY ARTIFACTS OR OTHER STUFFS AS WELL) 11. Mirror on the wall beside the bed with a bed side table Master Bedroom 1. Provide a king-size bed with an ottoman 2. Place the dressing unit on one side. 3. Provide a study table on TV wall towards the corner. 4. Wardrobe on the Entry wall with study table of 2'6" not more thn that 5. Add another wardrobe beside the attached washroom if space permits. 6. Install floor-to-ceiling curtains. 7. Design a false ceiling with lighting. 8. Include a concealed locker - MUSTT 9. Plan a cozy corner with proper book shelf and miniature sofa for two Master Bedroom Balcony 1. Provide a clothes drying provision. 2. Design seating space. 3. Install invisible sliding mosquito mesh/grill. 4. Add a hanging garden or decorative greenery. 5. Explore storage options. Common Washroom 1. Install a sliding glass shower partition. 2. Provide a vanity cabinet below the wash basin. 6. Check feasibility of installing a compact ceiling exhaust fan/light combination- NEED TO CHECK WHILE VISITING THE SITE MBR Check feasibility of installing a compact ceiling exhaust fan/light combination- NEED TO CHECK WHILE VISITING THE SITE Passage 1. Design decorative lighting. 2. Explore wall treatments or architectural features to enhance the corridor. | 2026-04-22 18:06:19 +0530 | Patil Madhavi | Some Image was uploaded |  |  |  | 2026-07-19 |  | 2026-07-26
18902 | Turnkey | 2026-01-01 | Mandar Idekar | The ICON | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Nishtha Valawalkar |  | Hold | Design | DEM1 | 912040 | 89999 | 912040 | 0 | 0 | 4 | 107 | 0 | 92409 | 368648 | 360984.4 |  |  | 2026-03-15 | 2026-03-15 21:30 | 2026-03-22 | 2026-03-22 11:29 | 2026-03-25 | 2026-03-24 12:12 | 2026-09-05 |  | 2026-09-12 |  | 2026-09-19 |  | 2026-03-24 | 2026-03-25 13:44 | 2026-03-25 | 2026-03-25 13:49 | 2026-03-25 | 2026-03-26 13:37 | 2026-07-05 | 2026-07-05 12:18 |  |  |  |  | 2026-09-06 |  | 2026-09-14 |  | 2026-09-15 |  |  |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 | [6 empty] | 2026-10-13 |  | 2026-10-22 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-25 |  |  |  | 2026-11-16 |  | 2026-11-18 |  | 2026-11-19 | [5 empty] | 2026-09-23 |  | 2026-08-20 |  | Unknown | 2026-03-15 | 2026-03-15 21:23 | 772915 | 139124 | 0 | 0 | 0 | 0 | 772915 | 139124 | 2026-07-05 12:16:10 +0530 | Divya Rahangdale | Welcome call done : Possession date : July End 10% payment aligned : As per Dipen's approval, the client will pay the 10% once they receive possession of the property. Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-07-02 19:11:17 +0530 | Divya Rahangdale | Hold till July end | 2026-06-29 13:43:41 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-09-06 |  | 2026-09-13
18903 | Turnkey | 2026-01-01 | Nelson Eric Williams | Piramal Vaikunth | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Foram Joshi |  | Hold | Preproduction | Site Readiness 1 | 898402 | 191199 | 1185348 | 0 | 0 | 3 | 92 | 0 | 0 | 356145 | 351058.4 |  |  | 2026-03-15 | 2026-03-15 21:42 | 2026-03-21 | 2026-03-24 12:22 | 2026-03-27 | 2026-03-27 16:02 | 2026-04-11 | 2026-04-10 15:34 | 2026-07-20 |  | 2026-07-27 |  | 2026-03-27 | 2026-03-28 15:00 | 2026-03-28 | 2026-03-30 11:51 | 2026-03-30 | 2026-03-30 14:41 | 2026-04-05 | 2026-04-05 12:54 |  |  |  |  | 2026-04-10 | 2026-04-11 14:23 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-07-31 |  | 2026-04-06 | 2026-04-10 15:33 | Site is Non-RTMI | 2026-03-15 | 2026-03-15 21:38 | 1004532 | 180815 | 0 | 0 | 0 | 0 | 997411.5549 | 163129 | 2026-07-14 14:10:00 +0530 | Anamika Dolai | Possession- July'26 | 2026-04-05 12:57:38 +0530 | Anamika Dolai | Done, explained about the payment milestones, client will visit EC on 10'april, nd proceed with 10% of the payment. | 2026-03-30 14:42:31 +0530 | Foram Joshi | mail updated | 2026-04-11 | 2026-04-10 15:48 | 2026-07-21
18904 | Turnkey | 2026-01-01 | upesh anchan |  | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Asif Shaikh | Aditya Vikram |  | Saloni Chawan | Prasad Bhivaji Hande | Active | Preproduction | 2D | 969978 | 179999 | 1737788 | 969978 | 0 | 18 | 23 | 0 | 0 | 404994 | 384984.8 |  |  | 2026-03-15 | 2026-03-15 21:38 | 2026-03-20 | 2026-03-20 16:07 | 2026-03-21 | 2026-03-24 11:09 | 2026-04-08 | 2026-04-07 12:48 | 2026-04-23 | 2026-04-22 16:17 | 2026-06-15 | 2026-06-14 15:58 | 2026-03-24 | 2026-03-24 16:25 | 2026-03-25 | 2026-03-25 12:43 | 2026-03-25 | 2026-03-25 13:17 | 2026-04-03 | 2026-04-03 15:40 |  |  |  |  | 2026-04-08 | 2026-04-15 12:21 | 2026-06-15 | 2026-06-14 11:33 | 2026-06-15 | 2026-06-14 11:53 |  |  | 2026-06-16 | 2026-06-27 19:50 | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-04-04 | 2026-04-07 12:11 | Site is RTMI | 2026-03-15 | 2026-03-15 21:37 | 1472702 | 265086 | 1080838.339 | 178471 | 0 | 0 | 1080838.339 | 178471 | 2026-06-20 15:15:38 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-04-30 17:32:08 +0530 | Harshali Bhuyar | CIVIL WORK DEPENDENCY , PROJECT ON HOLD TILL MID MAY. | 2026-04-17 10:43:29 +0530 | Harshali Bhuyar | Others: DEM 2 on sunday . | 2026-04-08 | 2026-04-15 14:54 | 2026-04-24 | 2026-04-22 16:18
18905 | Turnkey | 2026-01-01 | Priti Pol | L&T Rejevue | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [6 empty] | Saloni Chawan |  | Active | Prospect | 10% Payment | 2759937 | 9999 | 0 | 0 | 0 | 110 | 0 | 265995 | 275994 | 1212284 | 995666 |  |  | 2026-03-15 | 2026-03-15 21:46 | 2026-03-21 | 2026-03-27 21:29 | 2026-12-31 |  | 2027-01-07 |  | 2027-01-14 |  | 2027-01-21 |  | 2026-12-31 |  | 2027-01-01 |  | 2027-01-01 |  | 2027-01-02 | [5 empty] | 2027-01-08 |  | 2027-01-16 |  | 2027-01-17 |  |  |  | 2027-01-24 |  | 2027-01-25 |  | 2027-01-26 |  | 2027-01-27 | [6 empty] | 2027-02-14 |  | 2027-02-23 |  | 2027-02-22 |  | 2027-02-23 |  | 2027-02-24 |  | 2027-02-26 |  |  |  | 2027-03-20 |  | 2027-03-22 |  | 2027-03-23 | [5 empty] | 2027-01-25 |  | 2027-01-03 |  | Unknown | 2026-03-15 | 2026-03-15 21:45 | 0 | 0 | 0 | 0 | 0 | 0 | 2341217 | 418720 | 2026-04-10 20:40:23 +0530 | Moksh Mehta | DCM: Mr. Harshal VyasÂ Â Mrs.: PritiÂ PolÂ 3 BHK.Â Â LNT Rejuve 360Â Â PossessionÂ AprilÂ end.Â Â Move in 3 people- Husband, wife ( 35+) and 2 yr.Â OldÂ daughter.Â Â 1024sq. MBA- Husband.Â Â Budget 20-25 lakhsÂ Â Living Room-Â Shoe Rack with seating area (30 Pairs) Shoe Size 10 for men4 seaterÂ dining table,Â with 2 extra Chairs for getting it converted to 6 seaterconsole unit with water or time flowing elementsL shape sofa cum Bed with Storage +1 Chair TV unit, TV size 55Â CrockeryÂ Unit (One dinner set)Modern & Minimalistic KitchenÂ Base UnitsWall UnitsLoft Unit Janitor unit if Possible Bedroom 2 Guest-Â Color blocking for the Bed back Sofa cum bedWardrobe with LoftsWorkstation for PC SetupMandirÂ Idol Size 3" Bedroom 1 Kids Room - Tropical, Pinkish Shades Wardrobe with LoftsSingle Size BedWhite BoardChild roomStudy Table with wall storageDresser MBR-Â Bed placement to change on other sideKing Size Bed with Side tables SideÂ tableÂ and Dressing tableWardrobeÂ with Lofts.Â Â Vanity units in all Bathrooms.Â Â FC, Painting, Electricals.Â Â | 2026-03-27 16:46:26 +0530 | Rutuja Kotwal | DCM: Mr. Harshal VyasÂ Â Mrs.: PritiÂ PolÂ 3 BHK.Â Â LNT Rejuve 360Â Â Possession Â AprilÂ end.Â Â Move in 3 people- Husband, wife and 2 yr.Â OldÂ daughter.Â Â 1024sq. Ft.Â Â Direction Entering East.Â Â Design as per Basic VastuÂ Â Profession CA WifeÂ Â MBA- Husband.Â Â Budget 20-25 lakhsÂ Â Living Room-Â Shoe Rack withÂ full ht.Â storage,Â 6 seaterÂ dining table,Â console unitÂ ready made,Â Â L shape sofa with Ottoman, TV unit TV size 55Â Â KitchenÂ BaseÂ units, Wall Units and Lofts.Â Wall Ledge near machine.Â Â Bedroom 2 Guest-Â Sofa cum bed, Wardrobe with Lofts,Â Workstation minimal, MandirÂ Bedroom 1 Kids Room - Wardrobe with Lofts, Sofa Cum Bed,Â White Board, Child room, Study Table,Â Â MBR-Â Bed placement to change on other side,Â SideÂ tableÂ and Dressing table near WardrobeÂ with Lofts.Â Â Vanity units in all Bathrooms.Â Â FC, Painting, Electricals.Â Â CDPÂ -Â Â 28thÂ March atÂ 11am.Â Â Budget Suggestion 30 lakhs.Â |  |  |  | 2027-01-08 |  | 2027-01-15
18906 | Turnkey | 2026-01-01 | Anand Dusane | Runwal SANCTUARY | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | suraj kumar | Akshat Shrivastava | Murali S | Foram Joshi | Shailendra Mishra | Active | Production | Dispatch Due | 1467487 | 1467487 | 1988368 | 0 | 1467487 | 6 | 6 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-15 21:37 | 2026-03-19 | 2026-03-24 11:12 | 2026-03-27 | 2026-03-24 12:00 | 2026-04-14 | 2026-04-14 16:43 | 2026-04-23 | 2026-04-22 15:57 | 2026-04-28 | 2026-04-28 19:03 | 2026-03-24 | 2026-03-24 16:59 | 2026-03-25 | 2026-03-26 16:15 | 2026-03-26 | 2026-03-27 09:58 | 2026-04-03 | 2026-04-03 15:49 |  |  |  |  | 2026-04-14 | 2026-04-15 18:26 | 2026-04-25 | 2026-04-28 18:48 | 2026-04-29 | 2026-04-28 18:48 |  |  | 2026-04-29 | 2026-05-22 19:30 | 2026-05-31 | 2026-05-31 13:56 | 2026-06-01 | 2026-05-31 14:07 | 2026-06-01 | 2026-06-01 16:51 |  |  |  |  | 2026-06-04 18:50 | 2026-06-12 | 2026-06-17 19:51 | 2026-06-25 | 2026-06-23 13:14 | 2026-06-24 | 2026-07-09 13:04 | 2026-07-03 | 2026-07-14 16:23 | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-06 |  | 2026-08-07 | [5 empty] | 2026-05-31 | 2026-06-03 18:37 | 2026-04-15 | 2026-04-12 11:07 | Site is RTMI | 2026-03-15 | 2026-03-15 21:34 | 1687344 | 301023 | 0 | 0 | 1792757.9203 | 278006 | 1792757.9203 | 278006 | 2026-07-08 11:54:27 +0530 | suraj kumar | Project Status: Floor covering installation work completed. False ceiling framing work has been completed. False ceiling looping work has been completed. Wall base looping work completed. False ceiling board fixing work has been completed. Wall base preparation work has been completed. Upcoming work plan: Modular delivery & Installation work. | 2026-06-24 01:52:50 +0530 | suraj kumar | Project Status: Floor covering installation work completed.False ceiling framing work has been completed.False ceiling looping work has been completed.Wall base looping work completed.False ceiling board fixing work is in progress. ( 90% Completed.)Wall base preparation work is in progress ( ETA- 30th May)Upcoming work plan: Modular delivery & Installation. ( Currently, modular material is in manufactring) | 2026-05-22 00:00:37 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-04-15 | 2026-04-14 16:44 | 2026-04-23 | 2026-04-22 16:02
18907 | Turnkey | 2026-01-01 | Rajendra Namdeo Vichare | Lodha Casa Supremo | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Akash Jadhav | Sandeep Tiwari | Murali S | Saloni Chawan | Shailendra Mishra | Active | Installation | Execution | 971531 | 971531 | 1357424 | 0 | 971531 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-19 20:52 | 2026-03-17 | 2026-03-19 20:54 | 2026-03-19 | 2026-03-19 20:56 | 2026-04-08 | 2026-04-07 19:45 | 2026-04-24 | 2026-05-01 23:51 | 2026-05-13 | 2026-05-13 11:26 | 2026-03-19 | 2026-03-20 22:26 | 2026-03-20 | 2026-03-22 12:17 | 2026-03-22 | 2026-03-24 12:11 | 2026-03-25 | 2026-03-25 12:59 |  |  |  |  | 2026-04-07 | 2026-04-11 14:36 | 2026-05-02 | 2026-05-04 21:51 | 2026-05-05 | 2026-05-04 21:51 |  |  | 2026-05-22 | 2026-05-23 19:17 | 2026-05-26 | 2026-05-26 15:37 | 2026-05-27 | 2026-05-26 19:04 | 2026-05-27 | 2026-05-28 18:53 |  |  |  |  | 2026-05-31 12:57 | 2026-06-07 | 2026-06-06 20:32 | 2026-06-28 | 2026-06-26 20:36 | 2026-06-27 | 2026-06-30 16:59 | 2026-06-26 | 2026-07-08 10:05 | 2026-07-07 | 2026-07-09 13:26 | 2026-07-11 |  |  |  | 2026-06-29 |  | 2026-07-01 |  | 2026-07-31 | [5 empty] | 2026-05-26 | 2026-05-31 12:56 | 2026-04-10 | 2026-04-05 11:22 | Site is Non-RTMI | 2026-03-15 | 2026-03-15 21:46 | 1153485 | 203939 | 0 | 0 | 1101910.0755 | 166504 | 1101910.0755 | 166504 | 2026-06-15 13:27:44 +0530 | Akash Jadhav | Execution: Execution: Key task close on 31st may PI Work In cx Scope work Site readiness : 29th June | 2026-06-07 23:51:30 +0530 | Akash Jadhav | Execution: Key task close on 31st may PI Work In cx Scope work Site readiness : 29th June | 2026-06-02 23:05:36 +0530 | Akash Jadhav | Procurement: Key task close on 31st may | 2026-04-08 | 2026-04-07 19:48 | 2026-05-02 | 2026-05-01 23:52
18908 | Turnkey | 2026-01-01 | Ritesh Suryavanshi | kalpataru shrishti namah | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Mrunali Mitkari |  | Hold | Preproduction | DEM2 | 1233159 | 246632 | 1633913 | 0 | 0 | 24 | 19 | 0 | 0 | 512926 | 473600.8 |  |  | 2026-03-15 | 2026-03-22 12:30 | 2026-03-22 | 2026-03-22 21:43 | 2026-03-23 | 2026-03-23 16:07 | 2026-05-21 | 2026-05-20 19:25 | 2026-10-01 |  | 2026-10-08 |  | 2026-03-23 | 2026-03-25 12:06 | 2026-03-24 | 2026-03-26 15:02 | 2026-03-26 | 2026-03-27 14:15 | 2026-04-09 | 2026-04-09 17:10 |  |  |  |  | 2026-05-20 | 2026-06-08 19:17 | 2026-10-03 |  | 2026-10-04 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-14 | [6 empty] | 2026-11-01 |  | 2026-11-10 |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-13 |  |  |  | 2026-12-05 |  | 2026-12-07 |  | 2026-12-08 | [5 empty] | 2026-10-12 |  | 2026-06-30 | 2026-05-20 18:49 | Site is RTMI | 2026-03-15 | 2026-03-17 18:53 | 1387168 | 246744 | 0 | 0 | 0 | 0 | 1259874.647 | 212515 | 2026-07-02 17:34:12 +0530 | Vishakha Vaishnav | Others: cx will get the possession in month by july end | 2026-06-14 16:01:39 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-14 15:59:49 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-21 | 2026-05-20 19:27 | 2026-10-02 |  | Under Construction | 2026-04-30
18910 | Turnkey | 2026-01-01 | Prasanta kumar parida | Regency luxria | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [6 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 3079272 | 9999 | 0 | 0 | 0 | 119 | 0 | 297928 | 307927 | 1381027 | 1082390.8 |  |  | 2026-03-15 | 2026-03-18 12:30 | 2026-03-18 |  | 2026-03-18 |  | 2026-03-25 |  | 2026-04-01 |  | 2026-04-08 |  | 2026-03-18 |  | 2026-03-19 |  | 2026-03-19 |  | 2026-03-20 | [5 empty] | 2026-03-26 |  | 2026-04-03 |  | 2026-04-04 |  |  |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 | [6 empty] | 2026-05-02 |  | 2026-05-11 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-14 |  |  |  | 2026-06-05 |  | 2026-06-07 |  | 2026-06-08 | [5 empty] | 2026-04-12 |  | 2026-03-21 |  | Unknown | 2026-03-15 | 2026-03-18 12:20 | 0 | 0 | 0 | 0 | 0 | 0 | 2611839 | 467432 | 2026-03-17 11:23:45 +0530 | Rutuja Kotwal | DCM: Mr.Â Prasanta ParidaÂ 3 BHK.Â Â Regency LuxuriaÂ DombivliÂ East.Â Â Direction Â North EastÂ Â Design as per basic Vastu.Â Â Move in 4 people Husband, wife and 2 kids 30 yrs. And 27 yrs. RespectivelyÂ Â Area 1248Â sq.ft.Â Living room Shoe rack, Safety door, wall paneling,Â decorating insideÂ entranceÂ wall,Â 6 seaterÂ dining table,Â mandir on dining wallÂ with crockery unit, sofa, TV unitÂ without display unitÂ KitchenÂ -Â BaseÂ unit, WallÂ unitsÂ and Lofts.Â Stove placement to change in the opp.Â SideÂ Â Bathrooms PVCÂ ceiling,Â GlassÂ partition to check on site whether it is possible or not, Vanity units in all bathrooms.Â No storage in the passage.Â Parent BedroomÂ -Â WardrobeÂ with Lofts, Bed,Â mirror to hide inside, Side table.Â Â SonsÂ BedroomÂ storage behind door,Â Wardrobe with Lofts, Bed, side table,Â Â Master bedroom- Add. Wardrobe in the niche with lofts,Â Wardrobe with Lofts, Bed,Â side table.Â Â Include lights. In the estimateÂ Budget 15- 20 lakhsÂ Â Budget suggested 25-Â 30 lakhsÂ Â CDPÂ 18thÂ March 2026 at 3pm.Â Â | [6 empty] | 2026-03-26 |  | 2026-04-02
18911 | Turnkey | 2026-01-01 | Priyanka Gopalkar | akiya roots | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Kashmira Nerurkar |  | Priyanka Kamble | suraj kumar | Aditya Vikram | Murali S | Umang Shah | Abdul Shafeen | Active | Production | Production | 1251987 | 812017 | 1196674 | 0 | 1251987 | 1 | 6 | 0 | 0 | 0 | 439970 |  |  | 2026-03-15 | 2026-03-15 22:53 | 2026-03-17 | 2026-03-18 10:56 | 2026-03-20 | 2026-03-20 13:20 | 2026-04-09 | 2026-04-09 13:40 | 2026-05-08 | 2026-05-09 17:17 | 2026-06-09 | 2026-06-09 12:32 | 2026-03-20 | 2026-03-22 11:20 | 2026-03-21 | 2026-03-22 11:20 | 2026-03-22 | 2026-03-23 16:10 | 2026-03-28 | 2026-03-28 15:18 |  |  |  |  | 2026-04-09 | 2026-04-20 12:25 | 2026-05-24 | 2026-05-23 23:56 | 2026-05-24 | 2026-05-23 23:57 |  |  | 2026-06-14 | 2026-06-17 17:09 | 2026-06-21 | 2026-06-21 16:49 | 2026-06-24 | 2026-06-21 18:01 | 2026-06-22 | 2026-06-25 18:03 |  |  |  |  | 2026-06-29 16:34 | 2026-07-14 | 2026-07-14 16:49 | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-21 | 2026-06-29 16:33 | 2026-04-08 | 2026-04-09 13:08 | Site is RTMI | 2026-03-15 | 2026-03-15 22:49 | 1014130 | 182543 | 0 | 0 | 1497344.5789 | 235218 | 1497344.5789 | 235218 | 2026-07-08 11:24:50 +0530 | suraj kumar | Site report: - On site KOM meeting has been completed. - The floor covering work has been completed. - The False ceiling framing work is in progress. ( Board material will be dumped by today 8th july) | 2026-06-25 15:48:59 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-18 19:21:17 +0530 | Priyanka Kamble | Some Image was uploaded | 2026-04-10 | 2026-04-09 13:43 | 2026-05-10 | 2026-05-09 17:18
18912 | Turnkey | 2026-01-01 | Mr.Aditya nahata | sindya sun shine | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 2463631 | 9999 | 0 | 0 | 0 | 121 | 0 | 236364 | 246363 | 1003325 | 967580 |  |  | 2026-03-15 | 2026-03-16 00:10 | 2026-03-18 | 2026-03-18 21:09 | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-22 |  | 2026-03-23 | [5 empty] | 2026-03-29 |  | 2026-04-06 |  | 2026-04-07 |  |  |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 | [6 empty] | 2026-05-05 |  | 2026-05-14 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-08 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-04-15 |  | 2026-03-24 |  | Unknown | 2026-03-15 | 2026-03-16 00:09 | 0 | 0 | 0 | 0 | 0 | 0 | 2087822 | 375808 | 2026-03-17 12:01:22 +0530 | Aparna | CX name : Aditya Property : Vijayanagar , sindhya Sunshine apts Possession : May'26 Facing : North facing MD OccupationÂ : Business Family members : 2 couple + 1 baby ( age of kid 3 mnths boy) F 2 C: 9'H CDD date : 19.03.26 Budget : 15-20L Customer looking for maximum storage but aesthetically good looking Civil :Â 1. Entire flooring tiles change 2. Kitchen left wall to be demolished to place pooja 3.Kitchen plumbing to be shifted to op of entry, utiity will have DW, WM, DD sink 4. All 3 balconies door + window to be converted to sliding doors 5. All WCS to be shifted to north/south wall as per FP (outlets&inlet) 6. BR 3700x3100 (KBR) window to be changed to sliding & fixed towards the outer wall to have bay window space 7. Hand wash right wall to be demolished to half height + partition above (design perspective) 8. BR (38=900x3650) MBR vanity entrance to be shifted to MBR entry opp 9. Existing cabinets in kitchen, rooms wR all to be removed/debris removal 10. All doors finishing to be changed 11. Repainting of full house (Premium durable finish) 12. utility fixed window to change to sliding 13. all vanity fixtures including WC, shower partitionÂ ModularÂ : 3 cots with storage Foyer :Â 1. Shoe rack outside 2. Foyer console with wall design (No mirror) LivingÂ 1. L shape wall with wall concept, TV on BR-2 wall 2. TV with panel, rafters, tall unit with glassÂ 3.Â Pooja facing living balcony, pooja at left of kitchen entry (2'W) without wall behind 4. standing poojaÂ ( 5 frames approx.) 5. crockery on right of kitchen entrance (tall unit, base + wall)Â 6. Check for False ceiling only in living (Peripheral) Kitchen 1. Matka on left wall, double door fridge, tal unit with appliances 2. hob on opp of kit entry 3. glass shutters or wall unit with spice unit UtilityÂ : 1. DD sink, mop unit, DW, WMÂ 2. iron table optionÂ MBR 1. Hinged wR, loft 2. side table for locker storageÂ 3. WR in balcony (5.5'W) 4. TV unit with dressingÂ KBR / GBR 1. Hinged wardrobe +Â study on opp (platform bed+WR)Â 2. storage is main purpose Aditya room 1. WFO / no WFH 2. WR on left of balcony entry (1.5') 3. Hidden mirror dresser cum tv unit on opp of cot 4. L shape WR on vanity wall 5. balcony seating with wall ledges as per ref VanityÂ all vanity storage in base mirror with storage (full wall preferably for aesthetics) | [6 empty] | 2026-03-29 |  | 2026-04-05
18913 | Turnkey | 2026-01-01 | Mr.Pavan Kumar Ramayanam | Pavani Mariabilia | BNG - HSR | Yes | Priyamvada PV |  | Kowshik | [5 empty] | Nidhi Shaw |  | Lost | Prospect | 10% Payment | 1878044 | 9999 | 1878044 | 0 | 0 | 107 | 0 | 177805 | 187804 | 762498 | 739937.2 |  |  | 2026-03-15 | 2026-03-20 14:57 | 2026-03-30 | 2026-03-30 15:32 | 2026-04-02 | 2026-03-30 16:15 | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Unknown | 2026-03-15 | 2026-03-16 00:14 | 1591563 | 286481 | 0 | 0 | 0 | 0 | 1591563 | 286481 | 2026-04-14 11:06:40 +0530 | Sanjeev Jha | Some Image was uploaded | 2026-03-26 13:09:42 +0530 | Aparna | RGM Project DetailsClient Name: PawanProject: 3BHK Interior DesignProperty: Pavani MirabiliaFacing: WestFamily Members: 5 (Including 1 Kid)Possession Timeline: April 1st Week Meeting DetailsMeeting Purpose: Requirement Discussion & Design Brief FinalizationNext Meeting: 27.03.2026 (Second Half) Design OverviewTheme Finalized: Neutral with Pastel ColorsDesign Approach:Living & Dining Elegant & Premium LookKitchen & Bedrooms Functional & MinimalBudget Range: 11L 16L Entrance / Common AreaShoe rack with seating provisionWall lights for name plateDoor paneling To be checkedSafety grill door To be implemented Living AreaTV unit As per client referenceSofa wall As per reference imagePartition for TV wallFalse ceiling requiredDining AreaCrockery unit with integrated puja unit (with doors)Seating with drawers and tray storageProvision for sinkInternal puja design Reference takenLighting inside crockery unit KitchenTall unit for microwave & ovenRolling shutter unit with one wicker basketGranite countertopUnder-cabinet lightingKitchen entrance panelingPull-out accessoriesDado tiles Utility AreaBase unit & wall unit with GTPT trayJanitor unit near washing machineAdditional wall storageDado tilesSafety grills & cloth drying provision Master Bedroom (MBR)Wardrobes on both sides with seating in betweenDresser behind doorWall design requiredFalse ceilingKids Bedroom (KBR)Wardrobe with dresser & study unitMirror with storage (PU finish)Bed back cushioningWall design Guest Bedroom (GBR)Wardrobe with study unitMirror storage (reference shared)Wall design WashroomsVanity units with mirrorsBathroom partitions (glass) BalconyWooden ceiling with spotlightsStorage to cover duct spaceSafety grillsCloth drying systemÂ | 2026-03-26 12:52:22 +0530 | Aparna | RGM | 2026-04-07 |  | 2026-04-14
18914 | Turnkey | 2026-01-01 | Hiya Datta | Godrej Ananda | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1078750 | 9999 | 1078750 | 0 | 0 | 112 | 0 | 97876 | 107875 | 431500 | 431500 |  |  | 2026-03-15 | 2026-03-17 13:50 | 2026-03-17 | 2026-03-17 14:58 | 2026-03-22 | 2026-04-22 12:36 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-15 | 2026-03-16 12:05 | 914195 | 164555 | 0 | 0 | 0 | 0 | 914195 | 164555 | 2026-04-22 17:51:44 +0530 | Alekhya Korada | CDP MOM MOM of Mrs.. Hiya duttaÂ * near bar unit require glass storage as Crockery unitÂ *wicker basket in kitchen *Need place for dishwasher EITHER OR IN UTILITY * 280 ltr fridge top and bottom double door - 2' width *Next to tv unit, require either open storageÂ *Need some handbag storge space i any of the bedrooms *RequireÂ slim organiser in one of the room *In pooja room, above study glass storage unit.Bootm, study flapdown unit *In master bedroom - dressing storage requiredÂ | 2026-03-17 14:56:56 +0530 | Alekhya Korada | Some Image was uploaded | 2026-03-17 14:36:49 +0530 | Alekhya Korada | RGM Recording an requirement screen shots | 2026-04-30 |  | 2026-05-07
18915 | Turnkey | 2026-01-01 | Savitha CA | independent house | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Ruthwik S K | Ranjith Kumar | Murali S | Kushal S | Vishwa Hiremath | Active | Handover | Project Closure Pending | 1042008 | 1042008 | 1196799 | 0 | 1042008 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-17 13:48 | 2026-03-25 | 2026-03-25 09:31 | 2026-03-28 | 2026-03-25 17:06 | 2026-04-21 | 2026-04-17 20:04 | 2026-04-26 | 2026-04-25 10:59 | 2026-05-07 | 2026-05-06 11:24 | 2026-03-22 | 2026-03-24 15:41 | 2026-03-26 | 2026-03-26 14:13 | 2026-03-26 | 2026-03-27 17:26 | 2026-04-02 | 2026-04-02 17:13 |  |  |  |  | 2026-04-17 | 2026-04-20 12:44 | 2026-04-26 | 2026-04-27 22:41 | 2026-04-28 | 2026-04-27 23:18 |  |  | 2026-05-08 | 2026-05-12 14:45 | 2026-05-12 | 2026-05-13 17:00 | 2026-05-14 | 2026-05-13 17:31 | 2026-05-14 | 2026-05-14 18:58 |  |  |  |  | 2026-05-18 17:23 | 2026-05-29 | 2026-05-28 19:23 | 2026-06-06 | 2026-06-04 19:45 | 2026-06-05 | 2026-06-05 12:09 | 2026-06-04 | 2026-06-10 19:07 | 2026-06-10 | 2026-06-11 08:51 | 2026-06-16 | 2026-06-16 13:50 |  |  | 2026-07-13 | 2026-07-13 17:28 | 2026-07-24 | 2026-07-14 16:00 | 2026-07-25 | 2026-07-14 19:22 |  |  |  |  | 2026-05-13 | 2026-05-18 17:22 | 2026-04-03 | 2026-04-17 20:00 | Site is Non-RTMI | 2026-03-15 | 2026-03-16 12:36 | 1014236 | 182562 | 0 | 0 | 1154396.494 | 190603 | 1154396.494 | 190603 | 2026-07-14 19:24:29 +0530 | Ranjith Kumar | Project Closure Pending: | 2026-07-06 15:07:57 +0530 | Ranjith Kumar | Carp Work - 4 to 8 Jul Cleaning -9/Jul Cx Side 3 Electrical points third party engaged | 2026-05-25 22:00:18 +0530 | Ruthwik S K | Cx Side Polishing Done Key HO - 25/May Bonito Side - Electrical Floor Covering Cx Informing that he is going to get False Ceiling Done. Which is not discussed. | 2026-04-18 | 2026-04-17 20:04 | 2026-04-26 | 2026-04-25 10:59 | RTMI
18916 | Turnkey | 2026-01-01 | Sivareena | SNN RAJ Serenity | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik |  |  | Sachin I Betageri | Ranjith Kumar |  | Nidhi Shaw | Raghavendra Gowda | Active | Design | DEM3 | 1027614 | 144109 | 1097319 | 0 | 0 | 11 | 0 | 0 | 0 | 511196 | 372309.2 |  |  | 2026-03-15 | 2026-03-20 14:33 | 2026-03-20 | 2026-03-20 23:02 | 2026-03-25 | 2026-03-25 14:13 | 2026-05-30 | 2026-05-30 19:25 | 2026-07-04 | 2026-07-03 19:01 | 2026-07-08 |  | 2026-03-25 | 2026-03-25 15:03 | 2026-03-26 | 2026-03-27 13:48 | 2026-03-27 | 2026-03-30 20:09 | 2026-04-03 | 2026-04-03 19:45 |  |  |  |  | 2026-05-30 | 2026-06-13 11:26 | 2026-07-13 | 2026-07-04 21:13 | 2026-07-05 | 2026-07-04 21:14 |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-22 |  | 2026-05-16 | 2026-05-26 11:54 | Site is RTMI | 2026-03-15 | 2026-03-20 14:29 | 929931 | 167387 | 0 | 0 | 0 | 0 | 1201557.2306 | 198393 | 2026-06-10 12:51:05 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-20 18:23:07 +0530 | Prathyusha Elangovan | SIVAREENA (MOM-09/05/26)WITH EXISTING FALSE CEILING IS THER NEED LIGHTS TO BE SUGGESTED BRIGHT PASTEL SHADES MAUVE,PINKS ALONG WITH POOJA UNIT,WALL MOUNTED CROCKERY UNIT SAME REQUIREMENTS AS SHUBHADEEP PLACEMENT FOR AC IN LIVING AND BEDROOMS | 2026-05-20 18:22:28 +0530 | Prathyusha Elangovan | SHUBHADEEP(GREENS/BLUES/TEAL)PARENT'S (MOM-09/05/26) FOYER AREA DESIGN NEEDS TO BE SUGGESTED CONSOLE TABLE FOYER SHOW RACK-CX PROCURING FROM OUTSIDE(SUGGEST THE DESIGN) COMMON WALL(PASSAGE AREA)NEEDS TO BE HIGHLIGHTED) TV UNIT- END TO END FLOOR MOUNTED TALL UNIT ON LEFT SIDE TV BACK PANEL ONLY TO HIDE WIRES 43"TV DINING WALL-HIGHLIGHTED(WALLPAPER/MIRROR/BEADING) TINTED GLASS KITCHEN GRANITE INSTALLATION HANDLES UTILITY SAME AS THE INITIAL DESIGN BELOW THE SINK DUSTBIN/DETERGENT HOLDER MBR-1 EXISTING WARDROBE-7 FEET SLEEK UNIT NEXT TO THE WARDROBE BED BACK WALL NEEDS TO BE HIGHLIGHTED EXISTING QUEEN SIZE BED VANITY BASE UNIT DRESSER NEXT TO THE BED-ONLY MIRROR WITHOUT STORAGE MBR-2(WITH BAY WINDOW) SLIDING WARDROBE (IF SACE PERMITS PUT HINGED WARDROBE) EXISTING QUEEN SIZE BED DRESSER WIHTOUT SPACE IN THE BOTTOM L SHAPE WINDOW-CUSION ON THE SETAER AND ALSO FOR BACK WALL NO FALSE CEILING FOR THIS FLAT STUDY ROOM DESIGN NEEDS TO BE SUGGESTED,RELAXING SPACE WITH SEATER AND STORAGE BALCONY LOOSE FURNITURE NEEDS TO BE SUGESTED LIGHTS HAS TO BE SIGGESTED DINING,FOYER,LIVING NEEDS TO BE WELL LIT PLACEMENT FOR AC IN LIVING AND BEDROOMS FANS PLACEMENT H | 2026-05-31 | 2026-05-30 19:28 | 2026-07-04 | 2026-07-03 19:15 | Under Construction | 2026-07-31
18917 | Turnkey | 2026-01-01 | Pavan Kumar | Nava Vajra | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 1235289 | 9999 | 0 | 0 | 0 | 120 | 0 | 113530 | 123529 | 510875 | 477356.4 |  |  | 2026-03-15 | 2026-03-17 13:49 | 2026-03-25 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-04-06 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 | [6 empty] | 2026-05-13 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-25 |  |  |  | 2026-06-16 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-04-23 |  | 2026-04-01 |  | Unknown | 2026-03-15 | 2026-03-17 13:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1326646.1763 | 228926 | [9 empty] | 2026-04-06 |  | 2026-04-13
18920 | Turnkey | 2026-01-01 | Sakshi Sharma | Sakar Swapna | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Uday Yadruk | Rizwan Mistry | Murali S | Umang Shah | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 1222942 | 1222942 | 1247982 | 0 | 1222942 | 5 | 17 | 0 | 0 | 0 | 0 |  |  | 2026-03-16 | 2026-03-17 18:12 | 2026-03-16 | 2026-03-23 22:17 | 2026-03-20 | 2026-03-23 22:18 | 2026-04-19 | 2026-04-19 17:51 | 2026-04-25 | 2026-04-24 18:13 | 2026-05-03 | 2026-05-03 18:50 | 2026-03-25 | 2026-03-25 18:37 | 2026-03-26 | 2026-03-26 12:11 | 2026-03-26 | 2026-03-26 18:14 | 2026-03-30 | 2026-03-30 14:44 |  |  |  |  | 2026-04-24 | 2026-04-24 18:09 | 2026-04-26 | 2026-04-26 20:25 | 2026-04-27 | 2026-04-28 14:08 |  |  | 2026-05-09 | 2026-05-23 19:31 | 2026-05-23 | 2026-05-23 20:37 | 2026-05-23 | 2026-05-23 21:15 | 2026-05-24 | 2026-05-26 18:51 |  |  |  |  | 2026-05-27 19:18 | 2026-06-05 | 2026-06-04 21:17 | 2026-06-21 | 2026-06-19 13:42 | 2026-06-20 | 2026-07-10 12:00 | 2026-07-04 |  | 2026-06-18 |  | 2026-06-20 |  |  |  | 2026-06-27 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-05-23 | 2026-05-27 19:17 | 2026-03-31 | 2026-04-19 17:43 | Site is RTMI | 2026-03-16 | 2026-03-17 18:06 | 1057612 | 190370 | 0 | 0 | 1699158.2545 | 274245 | 1699158.2545 | 274245 | 2026-07-03 16:28:51 +0530 | Meet Shah | Others: | 2026-07-02 14:40:10 +0530 | Reshma Melanta | 100% Payment: | 2026-06-23 15:54:33 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-20 | 2026-04-19 17:53 | 2026-04-25 | 2026-04-24 18:13
18921 | Turnkey | 2026-01-01 | vijay Atmaram Thorat | athtna | MUM - GOR | Yes | Manisha Dubey | Reshma Melanta | Shantanu Parakh | [5 empty] | Ashish Jha |  | Hold | Design | 20% Payment | 1000110 | 120941 | 1309403 | 0 | 0 | 3 | 75 | 0 | 79081 | 430130 | 369957.6 |  |  | 2026-03-16 | 2026-03-16 20:47 | 2026-03-26 | 2026-03-26 11:58 | 2026-03-28 | 2026-03-28 15:05 | 2026-04-28 | 2026-04-28 19:21 | 2026-08-06 |  | 2026-08-13 |  | 2026-03-28 | 2026-03-31 21:04 | 2026-03-29 | 2026-04-02 15:54 | 2026-04-02 | 2026-04-02 17:17 | 2026-04-09 | 2026-04-09 18:54 |  |  |  |  | 2026-08-05 |  | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-04-10 | 2026-04-28 19:17 | Site is RTMI | 2026-03-16 | 2026-03-16 20:41 | 1112159 | 197243 | 0 | 0 | 0 | 0 | 1104108.325 | 174469 | 2026-07-02 16:52:32 +0530 | Reshma Melanta | Others: | 2026-06-02 16:51:50 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-08 13:47:44 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-29 | 2026-04-28 19:33 | 2026-08-07 |  | Under Construction | 2026-07-31
18923 | Turnkey | 2026-01-01 | Saurabh Shekhar | Assetz Marq | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 1309588 | 9999 | 0 | 0 | 0 | 112 | 0 | 120960 | 130959 | 523835 | 523835.2 |  |  | 2026-03-15 | 2026-03-18 16:22 | 2026-03-18 | 2026-03-18 16:57 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-15 | 2026-03-17 12:34 | 0 | 0 | 0 | 0 | 0 | 0 | 1456922.1 | 240572 | 2026-03-18 17:49:23 +0530 | Janvi Nagdeo | Some Image was uploaded | [6 empty] | 2026-04-05 |  | 2026-04-12
18924 | Turnkey | 2026-01-01 | Abrar Khan | Crescent | MUM - GOR | Yes | Manisha Dubey | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Savita Parab | Rizwan Mistry | Murali S | Sanskruti Yadav | Aakash Gaikwad | Active | Production | Production | 1309106 | 1309106 | 1398403 | 1362994 | 1309106 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-15 | 2026-03-19 12:43 | 2026-04-12 | 2026-04-12 21:13 | 2026-04-12 | 2026-04-12 21:22 | 2026-05-02 | 2026-04-28 19:11 | 2026-05-10 | 2026-05-17 17:50 | 2026-05-20 | 2026-05-20 21:07 | 2026-04-12 | 2026-04-15 15:21 | 2026-04-13 | 2026-04-15 15:25 | 2026-04-15 | 2026-04-20 10:20 | 2026-04-21 | 2026-04-21 17:04 |  |  |  |  | 2026-04-28 | 2026-04-30 19:29 | 2026-05-18 | 2026-05-17 15:16 | 2026-05-18 | 2026-05-17 15:17 |  |  | 2026-05-23 | 2026-05-31 20:08 | 2026-05-31 | 2026-05-31 21:02 | 2026-06-01 | 2026-05-31 21:08 | 2026-06-02 | 2026-06-03 19:03 |  |  |  |  | 2026-06-15 23:54 | 2026-07-01 | 2026-06-30 20:05 | 2026-07-18 |  | 2026-07-17 | 2026-07-11 16:36 | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-05-31 | 2026-06-15 23:53 | 2026-04-22 | 2026-04-28 19:09 | Site is RTMI | 2026-03-15 | 2026-03-19 12:42 | 1185087 | 213315 | 1511310.4614 | 248719 | 1495605.3497 | 240499 | 1495605.3497 | 240499 | 2026-07-11 15:45:22 +0530 | Reshma Melanta | Others: | 2026-07-08 23:53:39 +0530 | Savita Parab | Execution: floor covering done false ceiling done electrical wiring done paint work start from 9th july | 2026-06-15 23:59:29 +0530 | Savita Parab | Execution: Floor covering done false ceiling demolition started from 15th June ac pipe and ac pelmet not done from cx side | 2026-04-29 | 2026-04-28 19:11 | 2026-05-18 | 2026-05-17 17:51
18925 | Turnkey | 2026-01-01 | Karishma R | Stone bridge alpha | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Janvi Nagdeo |  | Lost | Design | 20% Payment | 985352 | 127999 | 1288624 | 0 | 0 | 86 | 8 | 0 | 69071 | 406189 | 382092.4 |  |  | 2026-03-15 | 2026-03-18 16:11 | 2026-03-19 | 2026-03-19 18:01 | 2026-03-24 | 2026-03-24 15:26 | 2026-04-13 | 2026-04-12 13:03 | 2027-07-31 |  | 2027-08-07 |  | 2026-03-24 | 2026-03-24 17:18 | 2026-03-25 | 2026-03-26 12:07 | 2026-03-26 | 2026-03-26 17:18 | 2026-04-03 | 2026-04-03 12:19 |  |  |  |  | 2026-04-12 |  | 2027-08-02 |  | 2027-08-03 |  |  |  | 2027-08-10 |  | 2027-08-11 |  | 2027-08-12 |  | 2027-08-13 | [6 empty] | 2027-08-31 |  | 2027-09-09 |  | 2027-09-08 |  | 2027-09-09 |  | 2027-09-10 |  | 2027-09-12 |  |  |  | 2027-10-04 |  | 2027-10-06 |  | 2027-10-07 | [5 empty] | 2027-08-11 |  | 2026-04-04 | 2026-04-12 11:14 | Site is RTMI | 2026-03-15 | 2026-03-18 16:09 | 1092054 | 196569 | 0 | 0 | 0 | 0 | 1073484.5884 | 181247 | 2026-05-13 10:57:29 +0530 | Parasa Sri | Some Image was uploaded | 2026-05-12 16:02:50 +0530 | Parasa Sri | Some Image was uploaded | 2026-04-12 12:21:15 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 11/04/2026 Title: DEM 1 Project: 18925 Client: Karishma R Attendees: Vishal Objective: DEM 1 Discussion Based on 11/04/2026 meeting, below is a list of all the requirements that were discussed during the meeting: Tv unit: as discussed, need confirmation on Inverter Point which is near tv unit base cabinet, if CX is placing the Invertor need to give provision for that and cabinet size will be change, accordingly Cost will be changestv back panel design will be remained same as of now, as discussed if u like any other Design, share the reference, i will add it to the design (as of now tv back wall will be with Metal strips and mirrors- No back panel is considered)pooja unit- as you mentioned, CX is selected from Studio Product so it not a part of EstimationFalse Ceiling and Partitions are not included in the estimation- its CX scopeneed to give some option for Pooja unit wall with some wall paper (preferably wallpaper with Indian Traditional touch)as discussed, electrical charges and fixtures are not included in the estimation, once we come for the Cross-measurement Validation team will be suggesting and give the costing is any changes are required.Tv unit tall unit, with alu shutter and Tinted glassas discussed, photo frame wall will be keeping plain, as you mention ed you are going to keep bigger photo frame and the smaller one around it. KITCHEN: Left side of HOb/Chimney, has to plan for microvan unit in the wall unitas discussed, kitchen wall L corner unit - glass shutter is not possible (there is a more chances of getting/ break glass easily)For sink unit and the corner unit required Ventilation f=grill on it- has to be consideredneed to plan for wicker basket in kitchenUnder the breakfast counter, has placed the cabinet which is lesser in depth (250mm)spice rack is required under the wall cabinet Crockery Unit: Crockery wall unit height has to change to 750mm as of now its 600mm, according to the cost may varyunder the breakfast counter need to give design with the combination of rafters, panel and the lightsbetween the base and top cabinet has to plan for bronze mirror (ad on)wine glass holder has to place in the designcrockery unit has to reduce to 4 shutters to 3 shutter and rest space need to plan for wall design with beadingNo change inÂ common vanity area (tile is not part of estimation) MBR: No changes in Wardrobe placementbed back wall paneling is not included in estimation (closed estimate)as discussed, if you are planning to keep locker then the dimension has to be shared, accordingly we can plan for itas CX mention, they will be sharing the reference for the dresser unit, accordingly design will changewardrobe has design with used cloth cabinetwardrobe internal design has not been finalised- we can discuss in the next meeting PBR: (layout has been changes) as per CPD discussion we have changes theÂ study room to Parents room as of nowwardrobe has moved to the main door wallÂ wardrobe with side storage for used cloth and mirror on the shutterbed we moved to the window wall side and need to give design for the bed wall (as discussed preferably with wall paint or the beading)Corner has to plan for some ledgesÂ for open storageas mentioned there might be an electrical point where we are planning foe the wardrobe- that has to be shifted to another wallÂ Study room: wardrobe with bay window seater is plannedstudy table has placed towards south- west corner, according to wall cabinet has to be planned - preferably with combination of glass and normal shuttercorner has to plan for cozy corner with single seater / Swing which CX is having already Note:Â as discussed, will be giving the updated estimation (with the combination of prelam and post lam)Â electrical and plumbing costs are not consideredFalse ceiling and Partition costs are not added in cost | 2026-04-13 | 2026-04-12 13:03 | 2027-08-01 |  | RTMI
18926 | Sub Project |  | Saravanan | JRC Palladio | BNG - HRBR |  | Arjun M V | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Nanda Kumar | Ranjith Kumar | Murali S |  | Vishwa Hiremath | Active | Production | 100% Payment | -1913 | 0 | 0 | 0 | -1913 | 84 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-17 | 2026-04-08 19:03 | 2026-03-18 | 2026-04-08 19:03 | 2026-04-08 | 2026-04-08 19:03 | 2026-04-09 | 2026-04-08 19:04 | 2026-04-09 | 2026-04-08 19:05 | 2026-04-09 | 2026-04-08 19:06 | 2026-04-08 | 2026-04-08 19:03 | 2026-04-09 | 2026-04-08 19:03 | 2026-04-08 | 2026-04-08 19:04 | 2026-04-09 | 2026-04-08 19:04 |  |  |  |  | 2026-04-08 | 2026-04-08 19:04 | 2026-04-09 | 2026-04-08 19:06 | 2026-04-09 | 2026-04-08 19:06 |  |  | 2026-04-09 | 2026-04-17 15:12 | 2026-04-18 | 2026-04-18 15:10 | 2026-04-19 | 2026-04-18 18:02 | 2026-04-19 | 2026-04-18 18:02 |  |  |  |  | 2026-04-18 18:05 | 2026-04-23 | 2026-04-22 19:20 | 2026-04-24 | 2026-04-22 20:08 | 2026-04-23 |  | 2026-04-22 |  | 2026-05-06 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-04-18 | 2026-04-18 18:02 | 2026-04-09 | 2026-04-08 19:04 | Unknown | 2026-03-17 | 2026-04-08 19:03 | 0 | 0 | 0 | 0 | 70073.0339 | 7335 | 70073.0339 | 7335 | 2026-06-10 15:32:50 +0530 | Ranjith Kumar | Execution: | [6 empty] | 2026-04-09 | 2026-04-08 19:04 | 2026-04-09 | 2026-04-08 19:05
18927 | Sub Project |  | Manikantan tk | Prestige Eden Park | BNG - HRBR |  | Sanjay Kulkarni |  | Shibin Lal |  |  | Sachin I Betageri | Ranjith Kumar | Murali S |  |  | Active | Handover | Project Closure Pending | -711 | 0 | 0 | 0 | -711 | 103 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-17 | 2026-03-17 18:00 | 2026-03-18 | 2026-03-17 18:00 | 2026-03-17 | 2026-03-17 18:00 | 2026-03-18 | 2026-03-17 18:01 | 2026-03-18 | 2026-03-17 18:03 | 2026-03-18 | 2026-03-17 18:05 | 2026-03-17 | 2026-03-17 18:01 | 2026-03-18 | 2026-03-17 18:01 | 2026-03-17 | 2026-03-17 18:01 | 2026-03-18 | 2026-03-17 18:01 |  |  |  |  | 2026-03-17 | 2026-03-17 18:02 | 2026-03-18 | 2026-03-17 18:03 | 2026-03-18 | 2026-03-17 18:04 |  |  | 2026-03-18 | 2026-03-25 | 2026-03-19 | 2026-03-25 19:25 | 2026-03-28 | 2026-03-27 11:06 | 2026-03-28 | 2026-03-27 11:07 |  |  |  |  | 2026-03-27 15:54 | 2026-04-01 | 2026-03-31 20:39 | 2026-04-02 | 2026-03-31 20:50 | 2026-04-01 | 2026-03-31 22:10 | 2026-03-31 | 2026-04-01 16:33 | 2026-04-01 | 2026-04-03 12:39 | 2026-04-13 | 2026-03-31 20:36 |  |  | 2026-04-02 | 2026-03-31 20:59 | 2026-04-02 | 2026-03-31 21:00 | 2026-04-03 | 2026-04-03 18:25 |  |  |  |  | 2026-03-25 | 2026-03-27 11:06 | 2026-03-18 | 2026-03-17 18:01 | Unknown | 2026-03-17 | 2026-03-17 18:00 | 0 | 0 | 0 | 0 | 33295 | 5993 | 33295 | 5993 | [9 empty] | 2026-03-18 | 2026-03-17 18:01 | 2026-03-18 | 2026-03-17 18:03
18928 | Sub Project |  | Sivaprasad Tummala | Coco villa | BNG - HRBR |  | Vishnu S | Rajeshwari S | Shibin Lal | [7 empty] | Active | Design | 60% Payment | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-17 | 2026-06-06 14:06 | 2026-03-18 | 2026-06-06 14:06 | 2026-03-21 | 2026-06-06 14:06 | 2026-06-07 | 2026-06-06 14:07 | 2026-06-07 | 2026-06-06 14:07 | 2026-06-07 | 2026-06-06 14:08 | 2026-06-09 | 2026-06-06 14:06 | 2026-06-07 | 2026-06-06 14:06 | 2026-06-06 | 2026-06-06 14:06 | 2026-06-07 | 2026-06-06 14:07 |  |  |  |  | 2026-06-06 | 2026-06-06 14:07 | 2026-06-07 | 2026-06-06 14:08 | 2026-06-07 | 2026-06-06 14:08 |  |  | 2026-06-07 | 2026-06-06 14:08 | 2026-06-07 | 2026-06-06 14:52 | 2026-06-07 | 2026-06-06 17:04 | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-06 |  | 2026-06-07 | 2026-06-06 14:07 | Unknown | 2026-03-17 | 2026-06-06 14:06 | 0 | 0 | 0 | 0 | 16222.5 | 0 | 16222.5 | 0 | [9 empty] | 2026-06-07 | 2026-06-06 14:07 | 2026-06-07 | 2026-06-06 14:08
18930 | Sub Project |  | Mr.Mani | INDEPENDENT HOUSE | BNG - HRBR |  | Salpriyan Pm | Rajeshwari S | Shibin Lal |  |  | Shivakumar Ms | Jairam Joshi | Murali S |  |  | Completed | Complete | Completed | 7490 | 7491 | 0 | 0 | 7490 | 43 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-17 | 2026-03-19 17:12 | 2026-03-18 | 2026-03-19 17:12 | 2026-03-19 | 2026-03-19 17:12 | 2026-03-20 | 2026-03-19 17:13 | 2026-03-20 | 2026-03-19 17:15 | 2026-03-20 | 2026-03-19 17:16 | 2026-03-19 | 2026-03-19 17:12 | 2026-03-20 | 2026-03-19 17:12 | 2026-03-19 | 2026-03-19 17:12 | 2026-03-20 | 2026-03-19 17:12 |  |  |  |  | 2026-03-19 | 2026-03-19 17:13 | 2026-03-20 | 2026-03-19 17:15 | 2026-03-20 | 2026-03-19 17:15 |  |  | 2026-03-20 | 2026-03-19 17:17 | 2026-03-20 | 2026-04-17 20:09 | 2026-04-18 | 2026-04-17 20:33 | 2026-04-18 | 2026-04-17 20:34 |  |  |  |  | 2026-04-18 15:20 | 2026-04-23 | 2026-04-22 19:23 | 2026-04-24 | 2026-04-22 20:10 | 2026-04-23 | 2026-04-23 19:49 | 2026-04-22 | 2026-05-15 14:06 | 2026-05-15 | 2026-05-15 15:20 | 2026-05-16 | 2026-05-15 17:42 |  |  | 2026-05-16 | 2026-05-16 12:05 | 2026-05-19 | 2026-05-16 12:06 | 2026-05-20 | 2026-05-16 12:14 |  |  |  |  | 2026-04-17 | 2026-04-17 20:34 | 2026-03-20 | 2026-03-19 17:12 | Unknown | 2026-03-17 | 2026-03-19 17:12 | 0 | 0 | 0 | 0 | 48721 | 8769 | 48721 | 8769 | [9 empty] | 2026-03-20 | 2026-03-19 17:13 | 2026-03-20 | 2026-03-19 17:15
18931 | Sub Project |  | GURU BASAVARAJ | Tree by provident | BNG - HRBR |  | Sanjay Kulkarni | Parasa Sri | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Shijin C C | Jairam Joshi | Murali S |  | Vishwa Hiremath | Completed | Complete | Completed | 46086 | 46000 | 0 | 0 | 46086 | 58 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-17 | 2026-03-26 12:15 | 2026-03-18 | 2026-03-26 12:15 | 2026-03-26 | 2026-03-26 12:15 | 2026-03-27 | 2026-03-26 12:16 | 2026-03-27 | 2026-03-26 12:17 | 2026-03-27 | 2026-03-26 12:19 | 2026-03-26 | 2026-03-26 12:15 | 2026-03-27 | 2026-03-26 12:15 | 2026-03-26 | 2026-03-26 12:16 | 2026-03-27 | 2026-03-26 12:16 |  |  |  |  | 2026-03-26 | 2026-03-26 12:17 | 2026-03-27 | 2026-03-26 12:18 | 2026-03-27 | 2026-03-26 12:18 |  |  | 2026-03-28 | 2026-04-05 11:29 | 2026-04-05 | 2026-04-21 20:16 | 2026-04-22 | 2026-04-22 15:45 | 2026-04-23 | 2026-04-23 19:48 |  |  |  |  | 2026-04-24 15:53 | 2026-04-30 | 2026-04-29 18:49 | 2026-05-01 | 2026-04-29 22:20 | 2026-04-30 | 2026-04-30 11:54 | 2026-04-29 | 2026-04-30 12:47 | 2026-04-30 | 2026-04-30 12:54 | 2026-05-01 | 2026-04-30 13:07 |  |  | 2026-05-02 | 2026-04-30 13:11 | 2026-05-02 | 2026-04-30 13:12 | 2026-04-30 | 2026-04-30 13:19 |  |  |  |  | 2026-04-21 | 2026-04-24 14:36 | 2026-03-27 | 2026-03-26 12:16 | Unknown | 2026-03-17 | 2026-03-26 12:14 | 0 | 0 | 0 | 0 | 39056 | 7030 | 39056 | 7030 | [9 empty] | 2026-03-27 | 2026-03-26 12:16 | 2026-03-27 | 2026-03-26 12:17
18932 | Sub Project |  | kiran ivaturi | Piramal Revanta | MUM - Thane |  | Chaitali Sawant |  | Sneha Kadam |  |  |  |  | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-17 | 2026-03-28 18:26 | 2026-03-18 | 2026-03-28 18:26 | 2026-03-28 | 2026-03-28 18:26 | 2026-03-29 | 2026-03-28 18:27 | 2026-03-29 | 2026-03-28 18:28 | 2026-03-29 | 2026-03-28 18:29 | 2026-03-28 | 2026-03-28 18:26 | 2026-03-29 | 2026-03-28 18:26 | 2026-03-28 | 2026-03-28 18:26 | 2026-03-29 | 2026-03-28 18:26 |  |  |  |  | 2026-03-28 | 2026-03-28 18:27 | 2026-03-29 | 2026-03-28 18:28 | 2026-03-29 | 2026-03-28 18:28 |  |  | 2026-03-29 | 2026-03-28 18:33 | 2026-03-29 | 2026-03-28 18:34 | 2026-03-29 | 2026-03-28 18:35 | 2026-03-29 | 2026-03-28 18:35 |  |  |  |  | 2026-03-28 18:41 | 2026-04-12 | 2026-04-13 17:11 | 2026-04-15 | 2026-04-13 17:23 | 2026-04-14 |  | 2026-04-13 |  | 2026-05-10 |  | 2026-05-15 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [5 empty] | 2026-03-28 | 2026-03-28 18:34 | 2026-03-29 | 2026-03-28 18:26 | Unknown | 2026-03-17 | 2026-03-28 18:26 | 0 | 0 | 0 | 0 | 16222.5 | 0 | 16222.5 | 0 | [9 empty] | 2026-03-29 | 2026-03-28 18:27 | 2026-03-29 | 2026-03-28 18:28
18933 | Turnkey | 2026-01-01 | Mr. Kamlesh | Bhavya Elite | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1295311 | 9999 | 0 | 0 | 0 | 118 | 0 | 119532 | 129531 | 518124 | 518124.4 |  |  | 2026-03-17 | 2026-03-19 13:35 | 2026-03-18 |  | 2026-03-30 |  | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Site is RTMI | 2026-03-17 | 2026-03-17 19:27 | 0 | 0 | 0 | 0 | 0 | 0 | 1097722 | 197589 | 2026-04-15 17:02:16 +0530 | Anant Giri | Some Image was uploaded | 2026-03-24 12:05:09 +0530 | Karuna Shinde | Some Image was uploaded |  |  |  | 2026-04-07 |  | 2026-04-14
18934 | Turnkey | 2026-01-01 | Franklin Rodricks | Aikya Roots | MUM - GOR | Yes | Batskhem Marpna | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Hold | Design | DEM1 | 806401 | 109936 | 1099358 | 0 | 0 | 3 | 107 | 0 | 51344 | 350374 | 294746.4 |  |  | 2026-03-17 | 2026-03-24 13:16 | 2026-03-17 | 2026-03-24 13:31 | 2026-03-25 | 2026-03-25 18:49 | 2026-08-03 |  | 2026-08-10 |  | 2026-08-17 |  | 2026-03-26 | 2026-03-26 19:14 | 2026-03-27 | 2026-03-26 19:33 | 2026-03-26 | 2026-03-27 12:46 | 2026-03-30 | 2026-03-30 14:54 |  |  |  |  | 2026-08-04 |  | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-07-30 |  | Unknown | 2026-03-17 | 2026-03-18 11:38 | 931659 | 167698 | 0 | 0 | 0 | 0 | 931658.5315 | 160764 | 2026-05-15 19:07:59 +0530 | Vishakha Vaishnav | Spoke to cx he said that he will get the possession in Dec 2026 | 2026-05-15 17:20:30 +0530 | Vishakha Vaishnav | Tried connecting cx, didn't respond | 2026-04-27 18:37:45 +0530 | Reshma Melanta | Some Image was uploaded | 2026-08-04 |  | 2026-08-11
18936 | Sub Project |  | Krutika Kanal | east side | MUM - GOR | Yes | Saif Shaikh | Manzoor Shaikh | Shantanu Parakh |  |  | suraj kumar | Aditya Vikram | Murali S |  |  | Active | Production | 100% Payment | 398112 | 63978 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 334134 |  |  | 2026-03-17 | 2026-03-27 16:00 | 2026-03-18 | 2026-03-27 16:00 | 2026-03-27 | 2026-03-27 16:01 | 2026-03-28 | 2026-03-29 20:20 | 2026-04-22 | 2026-04-21 15:02 | 2026-04-22 | 2026-04-21 15:06 | 2026-03-27 | 2026-03-27 16:01 | 2026-03-28 | 2026-03-27 16:01 | 2026-03-27 | 2026-03-27 16:01 | 2026-03-28 | 2026-03-27 16:02 |  |  |  |  | 2026-03-29 | 2026-04-14 14:39 | 2026-04-22 | 2026-04-21 15:03 | 2026-04-22 | 2026-04-21 15:03 |  |  | 2026-04-24 | 2026-04-23 13:07 | 2026-04-24 | 2026-04-23 13:08 | 2026-04-24 | 2026-04-23 13:08 | 2026-04-24 | 2026-04-23 13:08 |  |  |  |  | 2026-04-23 13:09 | 2026-04-30 | 2026-04-29 19:27 | 2026-05-30 | 2026-05-25 10:54 | 2026-05-26 |  | 2026-05-25 |  | 2026-05-13 |  | 2026-05-15 |  |  |  | 2026-05-22 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-04-23 | 2026-04-23 13:08 | 2026-03-28 | 2026-03-27 16:02 | Unknown | 2026-03-17 | 2026-03-27 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 337383 | 60729 | 2026-04-21 12:56:44 +0530 | Manzoor Shaikh | Some Image was uploaded | [6 empty] | 2026-03-30 | 2026-03-29 20:21 | 2026-04-22 | 2026-04-21 15:02
18941 | Turnkey | 2026-01-01 | Deepak Ghotekar | Balaram Complex | MUM - Thane | Yes | Mayuri Patil |  | Safalta Karkera | [5 empty] | Anjan Kumar |  | Active | Prospect | 10% Payment | 1421286 | 34999 | 1421286 | 0 | 0 | 115 | 0 | 107130 | 142129 | 595934 | 541094.4 |  |  | 2026-03-18 | 2026-03-18 15:41 | 2026-03-22 | 2026-03-22 11:28 | 2026-03-22 | 2026-06-29 14:19 | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-07-07 |  | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-07-02 |  | Unknown | 2026-03-18 | 2026-03-18 15:26 | 1207281 | 214004 | 0 | 0 | 0 | 0 | 1207281 | 214004 | 2026-03-22 10:53:51 +0530 | Mayuri Patil | DCName: DeepakÂ Property Name: Balaram complex Property type: 2BHK 650 Property Location: Kalyan Possession: 31 March Tentative Move in:Â Member: 5 couple, mother, 2 children, boy 12, girl 9. Profession: mechanical engineer.Â North direction: entrance Existing Furniture: Â Requirements: Living room: TV UNIT, L SHAPE SOFA, 4 SEATER DINING, SHOE RACK ON RIGHT SIDE NICHE AND WALL DECOR ON LEFT SIDE, MANDIR ON WC SIDE WITH GAP FACING LIVING ROOM, WALL DECOR IN THE BALCONY WALLS, LIVING ROOM DINING AREA WITH TROPHY SHOWING CLOSED AND OPEN UNITSÂ AND SHOE AREA WITH SHIVAJI MAHARAJ 3D WALL ART, VITHAL BHAGWAN DECOR NEAR MANDIR. Â Kitchen :LEFT SIDE PLATFORM LENGTH SMALL AND WIDTH, RIGHT SIDE PLATFORM HOB AND SINK, CHANGE IN PLATFORM, BOTH SIDE BASE UNIT, WALL UNIT, LOFT.Â Master bedroom: WARDROBE WITH LOFT ON DUCT SIDE AND DRESSING CONNECTED TO WARDROBE, BED, DISPLAY FOR BOOKS IN FRONT OF BED. Â Bedroom 1: WARDROBE, BED, STUDY TABLE, SIDE TABLE, EITHER 2 SINGLE BED OR SOFA CUM BED OR WHATEVER SUITS, STORAGE IN BALCONY TILL CEILING ONE SIDE. Â Bathroom: MASTER BEDROOM GLASS PARTITION AND VANITY. Â Â Â Â Â Â Â Â Â COMMON BATHROOM LOFT FOR HIDING TOP TANK. Â Â Â Â Â Â Â Â Â COMMON WC VANITY. Â Theme: MINIMAL TOUCH OF TRADITIONAL. Additional scope: FALSE CEILING IN BOTH ROOMS AND LIVING ROOM Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â PAINTING Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â ELCECTRICALSÂ Â Â Budget: 10 Â Budget Suggested:13 TO 15Â Â Â Â CDP: 22 MARCH | 2026-03-18 15:45:29 +0530 | vinaya thakur | Some Image was uploaded |  |  |  | 2026-07-07 |  | 2026-07-14
18942 | Turnkey | 2026-01-01 | Sobi Wilson | Independent house | BNG - HRBR | Yes | Sagarika Venkatesh | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Deekshith P | Jairam Joshi |  | Mohammed Rasick | Vishwa Hiremath | Active | Preproduction | 2D | 2575627 | 452461 | 3065276 | 2575627 | 0 | 1 | 13 | 0 | 0 | 1243419 | 879747.2 |  |  | 2026-03-17 | 2026-04-02 18:17 | 2026-03-19 | 2026-04-02 18:19 | 2026-04-05 | 2026-04-02 18:26 | 2026-04-29 | 2026-04-25 11:24 | 2026-06-21 | 2026-06-20 13:12 | 2026-07-05 | 2026-07-05 12:31 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-04 18:29 | 2026-04-04 | 2026-04-06 16:01 | 2026-04-13 | 2026-04-13 09:11 |  |  |  |  | 2026-04-25 | 2026-05-30 18:54 | 2026-06-24 | 2026-06-27 14:16 | 2026-06-28 | 2026-06-27 14:56 |  |  | 2026-07-11 | 2026-07-14 17:29 | 2026-07-13 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-14 |  | 2026-04-14 | 2026-04-25 11:21 | Site is RTMI | 2026-03-17 | 2026-03-18 16:23 | 2597691 | 467584 | 3072493.7117 | 484417 | 0 | 0 | 3072493.7117 | 484417 | 2026-07-10 19:49:03 +0530 | Sagarika Venkatesh | HOTO: | 2026-07-10 10:32:59 +0530 | Sagarika Venkatesh | HOTO: | 2026-06-02 11:42:26 +0530 | Arjun M V | Some Image was uploaded | 2026-04-26 | 2026-04-25 11:24 | 2026-06-21 | 2026-06-20 17:41 | RTMI
18944 | Turnkey | 2026-01-01 | Sudhakar Mahadeo Mhatre | Arihant Aspire | MUM - Thane | No Estimate | Maasoumeh Raza | Anamika Dolai | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-18 | 2026-03-18 18:53 | 2026-03-18 | 2026-03-18 19:56 | 2026-03-22 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-22 |  | 2026-03-23 | [5 empty] | 2026-03-29 |  | 2026-04-06 |  | 2026-04-07 |  |  |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 | [6 empty] | 2026-05-05 |  | 2026-05-14 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-08 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-04-15 |  | 2026-03-24 |  | Unknown | 2026-03-18 | 2026-03-18 18:49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-24 13:24:52 +0530 | Maasoumeh Raza | DCM: Name: 18944 - Sudhakar Mahadeo Mhatre Property Name: Arihant Aspire Property type: 2bhk [732sqft] Possession: May End Move in: AugustÂ Member: 4 member Budget: 12L to 15L Theme - EuropeanÂ Requirements:Â Living room:Â Shoe rack [40 pairs] L-Sofa TV unit with display [55 Inch] MandirÂ Â Master Bedroom: Queen size BedÂ Wardrobe with loft side table Dressing unit Study table Master bathroom vanity below Parent's Bedroom: Queen size BedÂ Wardrobe with loft side table Dressing unit Study table Common bathroom vanity below Utility: Washing machine above storage wash basin base unit Kitchen : Base unitÂ Wall unit Loft unit [1 side option] Appliance unit Balcony: Planter Additional Work: False ceiling only in living room & bedroom peripheral ElectrificationÂ Painting | 2026-03-19 13:29:15 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-18 18:55:46 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-29 |  | 2026-04-05
18946 | Turnkey | 2026-01-01 | Anil Lobo |  | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | [5 empty] | Umang Shah |  | Hold | Design | 20% Payment | 1401752 | 179999 | 1721721 | 0 | 0 | 14 | 35 | 0 | 100351 | 609802 | 511599.6 |  |  | 2026-03-18 | 2026-03-18 19:39 | 2026-03-23 | 2026-03-23 12:38 | 2026-03-22 | 2026-03-23 12:41 | 2026-05-28 | 2026-05-27 18:02 | 2026-08-02 |  | 2026-08-09 |  | 2026-03-23 | 2026-03-24 14:52 | 2026-03-24 | 2026-03-24 16:16 | 2026-03-24 | 2026-03-26 12:05 | 2026-03-30 | 2026-03-30 13:32 |  |  |  |  | 2026-05-27 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-04-07 | 2026-05-27 18:01 | Site is RTMI | 2026-03-18 | 2026-03-18 19:37 | 1459085 | 262635 | 0 | 0 | 0 | 0 | 1433651.4027 | 247385 | 2026-07-07 12:20:42 +0530 | Reshma Melanta | Others: | 2026-06-09 15:27:51 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-17 11:45:13 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-28 | 2026-05-27 18:05 | 2026-08-03
18947 | Turnkey | 2026-01-01 | Mitesh Dani | Veena Suyog | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 2537123 | 9999 | 2141915 | 0 | 0 | 103 | 0 | 243713 | 253712 | 1110204 | 919494 |  |  | 2026-03-18 | 2026-03-20 11:51 | 2026-03-25 | 2026-03-25 18:37 | 2026-04-03 | 2026-04-03 15:42 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-18 | 2026-03-19 12:34 | 1818727 | 323187 | 0 | 0 | 0 | 0 | 2153649 | 383473 | [9 empty] | 2026-04-11 |  | 2026-04-18
18948 | Turnkey | 2026-01-01 | Faalgun Mehta | * | MUM - GOR | Yes | Manisha Dubey | Reshma Melanta | Shantanu Parakh | [5 empty] | Avi Thakkar |  | Lost | Design | 20% Payment | 1513604 | 89999 | 1102634 | 0 | 0 | 58 | 18 | 0 | 212722 | 650158 | 560725.2 |  |  | 2026-03-18 | 2026-03-31 11:30 | 2026-03-31 | 2026-03-31 11:53 | 2026-04-03 | 2026-03-31 23:50 | 2026-04-28 | 2026-04-28 20:42 | 2026-07-02 |  | 2026-07-09 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-02 13:34 | 2026-04-02 | 2026-04-02 18:45 | 2026-04-10 | 2026-04-10 19:53 |  |  |  |  | 2026-06-15 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-04-11 | 2026-04-28 20:35 | Site is RTMI | 2026-03-18 | 2026-03-19 12:04 | 936723 | 165911 | 0 | 0 | 0 | 0 | 1609872.4672 | 277795 | 2026-06-09 12:42:57 +0530 | Christopher Macwan | Some Image was uploaded | 2026-06-06 18:58:37 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-15 12:37:55 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-29 | 2026-04-30 22:07 | 2026-07-03 |  | RTMI
18954 | Turnkey | 2026-01-01 | Mehul Patel | Kalpataru ELlitus | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [8 empty] | Active | Prospect | 10% Payment | 2746868 | 9999 | 0 | 0 | 0 | 110 | 0 | 264688 | 274687 | 1109490 | 1088004 |  |  | 2026-03-19 | 2026-03-19 12:00 | 2026-03-27 | 2026-03-27 21:34 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-19 | 2026-03-19 11:57 | 0 | 0 | 0 | 0 | 0 | 0 | 2327854 | 419013 | 2026-03-21 19:06:27 +0530 | Rutuja Kotwal | DCM: Mr. Mehul Patel 3BHK. 1222 sq.ft. Move in - 4 people - Husband, wife, Son - 21 yrs. and Father - 80 yrs. Profession - Banker. Wife - Home maker. Possession - July or August. Direction - Entering East. Design as per Basic Vastu. NO WALLPAPER AT ALL IN THE ENTIRE HOUSE. Living Room - Shoe rack , 6 seater dining Table, Swing 2 seater , TV unit with vertical cabinet, Sofa, Passage- Creating a niche and making another wash basin. storage in the passage. Kitchen - Separating kitchen and Utility Area by a sliding door. Making a window for Ventilation in kitchen. Dishwasher and Dryer to be placed. Base units, wall units and Lofts. Parent's Bedroom - Bed, Wardrobe with Lofts, small Mandir besides bed near window, chest of drawers. MBR- Existing Bed, Wardrobe with Lofts, Dressing unit, 2 side tables, Study table with above cabinet, TV unit. Son's Bedroom - Existing Bed, Wardrobe with Lofts, dressing Unit, 1 side table, Study table with above cabinet, TV unit. Vanity Units in all bathrooms. CDP - 28th March 2026 at 3pm. Budget - 20 lakhs. Budget suggested - 30 lakhs | 2026-03-19 12:01:13 +0530 | Kuldeepsingh Shekhawat | Some Image was uploaded |  |  |  | 2026-04-05 |  | 2026-04-12
18955 | Turnkey | 2026-01-01 | Ekta Shah | RUNWAL FOREST | MUM - Thane | Yes | Moksh Mehta | Anamika Dolai | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1610260 | 9999 | 0 | 0 | 0 | 118 | 0 | 151027 | 161026 | 693962 | 594246.4 |  |  | 2026-03-19 | 2026-03-19 21:30 | 2026-03-20 |  | 2026-03-19 |  | 2026-03-26 |  | 2026-04-02 |  | 2026-04-09 |  | 2026-03-19 |  | 2026-03-20 |  | 2026-03-20 |  | 2026-03-21 | [5 empty] | 2026-03-27 |  | 2026-04-04 |  | 2026-04-05 |  |  |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 | [6 empty] | 2026-05-03 |  | 2026-05-12 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-15 |  |  |  | 2026-06-06 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-04-13 |  | 2026-03-22 |  | Unknown | 2026-03-19 | 2026-03-19 21:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1364627 | 245632 | 2026-03-28 08:37:58 +0530 | Mayuri Patil | Name: RUSHABH CHHEDAÂ Property Name: RUNWAL FOREST T11 Property type: 2BHK Possession: JULYÂ Member: 3 , COUPLE (35YRS) + DAUGHTER (6 YEARS) Requirements: Living room:Â SHOERACK+ STORAGE FOR MISCELLANIOUS ITEMS (22-25 PAIRS) , 4 SEATER DINING TABLE , 3 SEATER SOFA CUM BED + 1 CHAIR, TV UNIT -(45-50)INCH, TV+MANDIR. Â Â Kitchen : BOTH SIDE BASE & WALL,LOFT ON ONE SIDE,ADDITIONAL WASH BASIN SPACE (IF POSSIBLE), Â Â DAUGHTER'S bedroom : TYPE OF BED TO BE CONFIRM BY CX , WARDROBE WITH LOFT , LIST OF APARATES TO BE SHARED BY CX. Â Â Master bedroom: QUEEN SIZE PLATFORM BED, WARDROBE WITH LOFT,PROJECTER PLACEMENT,DRESSER, SIDE TABLE. Â Â Bathroom: VANITY UNIT. Â Â Additional scope: FALSE CELING,PAINTING,ELECTRICAL. Â TRADITIONAL THEME FOR LIVING ROOM , MODERN THEME FOR BEDROOMS, LIGHTS COLOURS Â BUDGET:10-12 LAKHS | 2026-03-19 21:31:17 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-19 13:30:37 +0530 | Nishtha Valawalkar | 2 BHK Runwal Forest 617 Sq.ft. Budget - 10 to 12 (Can be made in SMART) LF descoped OR pitched Kashedi Market | 2026-03-27 |  | 2026-04-03
18956 | Turnkey | 2026-01-01 | Rahul Gupta | Snn Estates Felicity | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Preproduction | DEM2 | 1606775 | 321355 | 2181824 | 0 | 0 | 8 | 0 | 0 | 0 | 672298 | 613121.6 |  |  | 2026-03-19 | 2026-03-19 13:39 | 2026-03-19 | 2026-03-21 18:23 | 2026-03-25 | 2026-03-25 18:14 | 2026-06-25 | 2026-06-25 20:02 | 2026-07-16 |  | 2026-08-21 |  | 2026-03-25 | 2026-03-25 18:15 | 2026-03-26 | 2026-03-25 18:15 | 2026-03-25 | 2026-03-30 17:29 | 2026-04-03 | 2026-04-03 19:46 |  |  |  |  | 2026-07-05 | 2026-07-07 11:45 | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-06-06 | 2026-05-26 19:40 | Site is RTMI | 2026-03-19 | 2026-03-19 13:30 | 1849003 | 332820 | 0 | 0 | 0 | 0 | 1815850.7725 | 306118 | 2026-06-04 15:21:40 +0530 | Avishkar Sargam | MOM 31st May Kitchen Add lighting to the crockery wall unit. No other changes required on the hob side. Increase the counter depth to conceal the existing plumbing slab. Extend the width of the sink unit. Add a 2-drawer unit next to the sink unit. Remove the tambour unit. Revise the wall and loft units to align with the changes made to the base units. Living Room Revise the shoe rack design. Redesign the pooja unit as per the shared reference and provide multiple design options. Continue the wall moulding design on the sofa wall. Revise the TV unit design as per the shared reference. Master Bedroom Restrict the wardrobe width to 5 feet. Revise the bed-back wall design as per the requirement. Remove the study unit. Extend the wall moulding design across the room as required. Bedroom 2 Continue with the bay window seating design. Add a dresser unit. Add wallpaper on the adjacent wall. Bedroom 3 No changes required in the bedroom. No study unit to be provided. Bedroom 4 No changes required in the bedroom. | 2026-05-24 14:42:34 +0530 | Avishkar Sargam | DDM1: MOM 23rd May Kitchen Hob Side * Remove the open unit and replace it with a shelf unit. * Add 3 drawers next to the hob. * Check loft design with Saranya. Utility Side * Add tinted glass shutter on the utility side next to the RO. * Remaining layout to stay the same. Additional * One more kitchen layout option to be created. Master Bedroom * Bed position changed towards the East. * New side table and dresser design next to the bed. * Add foldable study table. * Wardrobe position shifted next to the bay window seating. Bedroom 4 * Add bay window seating near the window. * Shift wardrobe position next to the window. * Need a dedicated space for sewing machine and ironing board. Next Meeting Agenda * Sons Bedroom * Living Room | 2026-03-30 17:28:36 +0530 | Bency Chacko |  | 2026-06-26 | 2026-06-25 20:43 | 2026-07-17 |  | Under Construction | 2026-07-31
18957 | Turnkey | 2026-01-01 | Shiva Apparels ( Abinesh Selvaraj ) | Dosti mezzo | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1204787 | 150730 | 1507295 | 0 | 0 | 97 | 0 | 0 | 90227 | 512499 | 451330.4 |  |  | 2026-03-15 | 2026-04-02 11:08 | 2026-04-02 | 2026-04-02 16:32 | 2026-04-02 | 2026-04-02 16:58 | 2026-06-25 |  | 2026-08-21 |  | 2026-08-28 |  | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-07 18:15 | 2026-04-07 | 2026-04-09 12:59 | 2026-04-18 | 2026-04-18 17:57 |  |  |  |  | 2026-06-26 |  | 2026-08-23 |  | 2026-08-24 |  |  |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 | [6 empty] | 2026-09-21 |  | 2026-09-30 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-03 |  |  |  | 2026-10-25 |  | 2026-10-27 |  | 2026-10-28 | [5 empty] | 2026-09-01 |  | 2026-04-19 |  | Unknown | 2026-03-15 | 2026-04-01 11:20 | 1277369 | 229926 | 0 | 0 | 0 | 0 | 1266290.0892 | 208187 | 2026-07-02 14:01:21 +0530 | Manzoor Shaikh | The client is not responding for the DEM1 meeting, have also asked about the possession | 2026-06-26 16:04:15 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-21 15:09:23 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-26 |  | 2026-08-22 |  | Under Construction | 2026-06-30
18958 | Turnkey | 2026-01-01 | Padmini Ravindran | PURVA ATMOSPHERE | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Harshit Choudhary | Saddam Hussain Z M | Murali S | Mohammed Rasick | Abdul Shafeen | Active | Installation | Execution | 1433419 | 1433419 | 1507074 | 1677560 | 1433419 | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-19 | 2026-03-24 18:09 | 2026-03-25 | 2026-03-25 09:14 | 2026-03-25 | 2026-03-25 12:12 | 2026-04-05 | 2026-04-05 20:06 | 2026-05-07 | 2026-05-06 17:53 | 2026-05-13 | 2026-05-13 19:42 | 2026-03-25 | 2026-03-25 12:41 | 2026-03-26 | 2026-03-25 19:04 | 2026-03-25 | 2026-03-26 12:51 | 2026-03-31 | 2026-03-31 17:54 |  |  |  |  | 2026-04-05 | 2026-04-23 14:59 | 2026-05-12 | 2026-05-10 17:25 | 2026-05-11 | 2026-05-10 18:07 |  |  | 2026-05-19 | 2026-05-22 22:33 | 2026-05-23 | 2026-05-23 10:46 | 2026-05-29 | 2026-05-23 11:11 | 2026-05-24 | 2026-05-25 18:39 |  |  |  |  | 2026-05-27 18:21 | 2026-06-05 | 2026-06-04 21:18 | 2026-06-19 | 2026-06-17 18:49 | 2026-06-18 | 2026-06-26 13:18 | 2026-06-17 | 2026-06-26 17:10 | 2026-06-20 | 2026-06-26 17:13 | 2026-06-27 | 2026-06-26 17:25 |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-23 | 2026-05-27 18:20 | 2026-04-01 | 2026-04-05 19:02 | Site is RTMI | 2026-03-19 | 2026-03-23 18:13 | 1277181 | 229892 | 1781349.43 | 307387 | 1487026.6298 | 256600 | 1487026.6298 | 256600 | 2026-05-22 18:55:37 +0530 | Hemalatha D | Some Image was uploaded | 2026-05-22 17:22:02 +0530 | Hemalatha D | Some Image was uploaded | 2026-05-22 12:52:51 +0530 | Hemalatha D | Some Image was uploaded | 2026-04-06 | 2026-04-05 20:07 | 2026-05-07 | 2026-05-06 19:13 | RTMI
18959 | Turnkey | 2026-01-01 | Nandan | PURVA ATMOSPHERE | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Harshit Choudhary | Saddam Hussain Z M | Murali S | Mohammed Rasick | Abdul Shafeen | Active | Installation | Execution | 1510575 | 1510575 | 1545931 | 1690833 | 1510575 | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-19 | 2026-03-24 18:07 | 2026-03-25 | 2026-03-25 09:21 | 2026-03-28 | 2026-03-25 12:07 | 2026-04-05 | 2026-04-05 20:07 | 2026-05-07 | 2026-05-06 14:47 | 2026-05-13 | 2026-05-13 14:52 | 2026-03-25 | 2026-03-25 12:35 | 2026-03-26 | 2026-03-25 19:04 | 2026-03-25 | 2026-03-26 12:52 | 2026-03-31 | 2026-03-31 17:53 |  |  |  |  | 2026-04-05 | 2026-04-20 12:22 | 2026-05-12 | 2026-05-10 18:07 | 2026-05-11 | 2026-05-10 18:33 |  |  | 2026-05-19 | 2026-05-21 20:59 | 2026-05-23 | 2026-05-23 14:27 | 2026-05-29 | 2026-05-23 19:44 | 2026-05-24 | 2026-05-25 18:59 |  |  |  |  | 2026-05-27 18:21 | 2026-06-05 | 2026-06-05 21:31 | 2026-06-23 | 2026-06-18 19:03 | 2026-06-19 | 2026-06-19 18:25 | 2026-06-18 | 2026-06-20 15:50 | 2026-06-20 | 2026-06-20 21:02 | 2026-06-25 | 2026-06-25 18:31 |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-23 | 2026-05-27 18:20 | 2026-04-01 | 2026-04-05 18:55 | Site is RTMI | 2026-03-19 | 2026-03-23 18:20 | 1310111 | 235820 | 1713103.3655 | 295611 | 1556677.2185 | 268618 | 1556677.2185 | 268618 | 2026-05-23 11:59:05 +0530 | Hemalatha D | Some Image was uploaded | 2026-05-22 16:16:35 +0530 | Hemalatha D | Some Image was uploaded | 2026-05-20 13:30:57 +0530 | Hemalatha D | Some Image was uploaded | 2026-04-06 | 2026-04-05 20:18 | 2026-05-07 | 2026-05-06 14:49 | RTMI
18960 | Turnkey | 2026-01-01 | madhabananda Acharya | Rohan Ekanta | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Hold | Preproduction | DEM2 | 1236404 | 247281 | 1658510 | 0 | 0 | 34 | 52 | 0 | 0 | 496254 | 492868.8 |  |  | 2026-03-19 | 2026-03-19 14:38 | 2026-03-20 | 2026-03-23 11:23 | 2026-03-23 | 2026-03-23 12:12 | 2026-04-23 | 2026-04-19 17:53 | 2026-09-01 |  | 2026-09-08 |  | 2026-03-23 | 2026-03-26 10:45 | 2026-03-24 | 2026-03-26 10:46 | 2026-03-26 | 2026-03-28 16:03 | 2026-04-03 | 2026-04-03 19:51 |  |  |  |  | 2026-04-19 | 2026-04-20 15:07 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-04-04 | 2026-04-19 12:42 | Site is RTMI | 2026-03-19 | 2026-03-19 14:33 | 1405517 | 252993 | 0 | 0 | 0 | 0 | 1400866.891 | 231315 | 2026-05-24 11:56:43 +0530 | Abhinandan K S | Some Image was uploaded | 2026-04-23 18:33:46 +0530 | Janush Bojamma C T | Project to be kept hold | 2026-03-28 16:03:01 +0530 | Bency Chacko |  | 2026-04-20 | 2026-04-19 17:54 | 2026-09-02 |  | Under Construction | 2026-07-31
18961 | Turnkey | 2026-01-01 | Gurpreet Singh | Bhavya Elite | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 1419283 | 9999 | 1419283 | 0 | 0 | 117 | 0 | 131929 | 141928 | 595405 | 540021.2 |  |  | 2026-03-19 | 2026-03-20 19:40 | 2026-03-23 | 2026-03-23 12:42 | 2026-03-21 | 2026-03-23 12:44 | 2026-03-30 |  | 2026-04-06 |  | 2026-04-13 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-25 | [5 empty] | 2026-03-31 |  | 2026-04-08 |  | 2026-04-09 |  |  |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 | [6 empty] | 2026-05-07 |  | 2026-05-16 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-19 |  |  |  | 2026-06-10 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-04-17 |  | 2026-03-26 |  | Unknown | 2026-03-19 | 2026-03-20 19:39 | 1202782 | 216500 | 0 | 0 | 0 | 0 | 1202782 | 216500 | 2026-04-08 11:07:44 +0530 | Meet Shah | Some Image was uploaded | 2026-03-24 12:17:54 +0530 | Sanskruti Yadav | Some Image was uploaded |  |  |  | 2026-03-31 |  | 2026-04-07
18962 | Turnkey | 2026-01-01 | Utpal Sharma | Ecolife eon | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP |  | Sethuragavan R |  |  |  | Ramesh Nayak | Sunil Kumar S M | Active | Preproduction | Hoto | 1344843 | 218757.9 | 1429050 | 1344843 | 0 | 1 | 64 | 0 | 0 | 602631 | 523454 |  |  | 2026-03-19 | 2026-03-19 17:14 | 2026-03-29 | 2026-03-29 15:25 | 2026-03-29 | 2026-03-29 21:46 | 2026-04-15 | 2026-04-15 18:56 | 2026-07-09 | 2026-07-08 12:55 | 2026-07-15 | 2026-07-14 19:20 | 2026-03-29 | 2026-03-29 23:00 | 2026-03-30 | 2026-04-02 10:42 | 2026-04-02 | 2026-04-02 16:05 | 2026-04-03 | 2026-04-03 19:39 |  |  |  |  | 2026-04-15 | 2026-04-16 18:58 | 2026-07-09 | 2026-07-09 09:59 | 2026-07-10 | 2026-07-09 10:01 |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-07-17 | 2026-04-15 18:50 | Site is Non-RTMI | 2026-03-19 | 2026-03-19 17:12 | 1216389 | 212661 | 1487209.089 | 245569 | 0 | 0 | 1487209.089 | 245569 | 2026-05-16 17:48:41 +0530 | Aishwarya C | Mr utpalÂ MOM base cabinetÂ for wires inside the wallÂ plain wallpaper on the back wall tv unit 450 mm for a plantÂ 1800for the tv unit cabinet sofa back wallÂ Â crockery unit tall unit need glass shutterÂ pooja unit with no shutter curtain option instead of shutterÂ tall unit with bottom storageÂ simple back deignÂ only rafters no mirror mbr add a single door cabinet wardrobe need option for dressing unit laundry basketand bag storageÂ bedroom 2Â bay seating need to addÂ kitchenÂ under sink ROÂ need all appliance dimensions need to discuss after the initial measurementÂ blind for pooja unit need to buy ouside | 2026-05-05 12:34:57 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-04-22 18:25:42 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-16 | 2026-04-15 19:10 | 2026-07-09 | 2026-07-08 12:58 | Under Construction | 2026-06-30
18964 | Turnkey | 2026-01-01 | vivek | JP Barcelona | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | Akash Jadhav | Sandeep Tiwari | Murali S | Aryan Singh | Prasad Bhivaji Hande | Active | Installation | Execution | 1494858 | 537589 | 0 | 0 | 1494858 | 41 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-19 | 2026-04-09 19:15 | 2026-03-20 | 2026-04-09 19:15 | 2026-04-09 | 2026-04-09 19:15 | 2026-04-10 | 2026-04-09 19:16 | 2026-04-10 | 2026-04-09 19:17 | 2026-04-12 | 2026-04-12 15:39 | 2026-04-09 | 2026-04-09 19:15 | 2026-04-10 | 2026-04-09 19:15 | 2026-04-09 | 2026-04-09 19:16 | 2026-04-10 | 2026-04-09 19:16 |  |  |  |  | 2026-04-09 | 2026-04-09 19:17 | 2026-04-10 | 2026-04-11 11:12 | 2026-04-12 | 2026-04-11 14:40 |  |  | 2026-04-15 | 2026-04-18 17:01 | 2026-04-18 | 2026-04-18 21:22 | 2026-04-19 | 2026-04-22 14:25 | 2026-04-23 | 2026-04-23 12:27 |  |  |  |  | 2026-04-23 18:11 | 2026-05-15 | 2026-05-14 21:23 | 2026-05-25 | 2026-05-23 18:30 | 2026-05-24 | 2026-05-29 16:50 | 2026-05-23 | 2026-06-04 16:24 | 2026-06-02 | 2026-06-04 17:10 | 2026-07-03 | 2026-07-03 11:00 |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-04-18 | 2026-04-23 13:53 | 2026-04-10 | 2026-04-09 19:16 | Unknown | 2026-03-19 | 2026-04-09 19:15 | 0 | 0 | 0 | 0 | 1266829 | 228029 | 1266829 | 228029 | 2026-06-15 13:26:29 +0530 | Akash Jadhav | Execution: Modular installation work done till 18th June Final painting start from 20th to 24th June Debris Removal at 25th June Cleaning 26th June Per qc : 26th June QC : 27th June Blocker Hard wear missing not received | 2026-06-07 23:45:41 +0530 | Akash Jadhav | Execution: Main load received at by 1st June Per Qc : 26th June QC : 27th June Blocker : Na | 2026-06-02 23:03:14 +0530 | Akash Jadhav | Procurement: PI work completed As per the docket Modular Will deliver on site at 5th June | 2026-04-10 | 2026-04-09 19:16 | 2026-04-10 | 2026-04-09 19:17
18966 | Turnkey | 2026-01-01 | Santosh Shinde | Srishti Namah | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Vandana Preet |  | Active | Preproduction | DEM2 | 1657874 | 331575 | 2218650 | 0 | 0 | 52 | 11 | 0 | 0 | 706859 | 619440 |  |  | 2026-03-19 | 2026-03-19 21:59 | 2026-03-21 | 2026-03-29 10:22 | 2026-04-01 | 2026-03-31 16:09 | 2026-04-19 | 2026-04-16 20:14 | 2026-07-04 |  | 2026-07-11 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 17:28 | 2026-04-03 | 2026-04-04 15:19 | 2026-04-09 | 2026-04-09 12:32 |  |  |  |  | 2026-04-20 | 2026-04-16 19:00 | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-04-10 | 2026-04-15 20:24 | Site is Non-RTMI | 2026-03-19 | 2026-03-19 19:17 | 1883014 | 335636 | 0 | 0 | 0 | 0 | 1856212.9453 | 302721 | 2026-07-02 13:47:37 +0530 | Anamika Dolai | Client needs handover by dec. | 2026-06-30 11:21:44 +0530 | Swami Vadnere | Some Image was uploaded | 2026-05-24 11:34:55 +0530 | Swami Vadnere | DDM1: MOM 23/05/2026 Entrance Area * 23 design options for entrance area. * Safety door design options. Living Room * TV unit options for 52-inch TV. * Check feasibility of pull-out seating in mandir unit. * Add light points near crockery unit. * 23 sofa back wall options as per shared references. * Add bench seating in dining area along with 2 chairs. * Ceiling design options with profile lights and track lights. Kitchen * Add glass wall units. * Change appliance unit to tall pantry unit * Internals: 2 drawers and remaining shelves. * Kitchen colour options. Kids Room * Add loft above existing wardrobe. * Marvel-themed bedroom design. * Decorative wall design for displaying Hot Wheels cars and Marvel miniatures. * Study table wall unit with one foldable study table. * Ceiling design as per room theme with profile lights and track lights. Parents Room * Existing queen-size bed to remain. * Add new single bed. * Design theme to be simple and subtle. Master Bedroom * Change sliding wardrobe to openable wardrobe unit. * TV unit cum study table options. * Bed back wall design options. * Add dressing unit near bed. * Convert existing dressing unit space into cloth storage. * Ceiling design as per room theme. | 2026-04-11 | 2026-04-16 20:37 | 2026-07-05
18967 | Turnkey | 2026-01-01 | Abhishek Mishra Mishra | Telenque square | BNG - HSR | Yes |  | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 3040318 | 9999 | 0 | 0 | 0 | 117 | 0 | 294033 | 304032 | 1309639 | 1122615.6 |  |  | 2026-03-19 | 2026-03-20 14:29 | 2026-03-19 | 2026-04-12 06:53 | 2026-04-11 |  | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-04-23 |  | 2026-05-01 |  | 2026-05-02 |  |  |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 | [6 empty] | 2026-05-30 |  | 2026-06-08 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-11 |  |  |  | 2026-07-03 |  | 2026-07-05 |  | 2026-07-06 | [5 empty] | 2026-05-10 |  | 2026-04-18 |  | Unknown | 2026-03-19 | 2026-03-20 14:19 | 0 | 0 | 0 | 0 | 0 | 0 | 2576541 | 463777 | 2026-03-27 17:08:44 +0530 | Aparna | RGM MOM Interior Design DiscussionProject Type: Type A East Facing Possession Timeline: June Budget: 15 16 Lakhs Family Details: 5 Members (3 Kids) Overall ThemeStyle: Traditional + ClassyElegant finishes with subtle detailingBalanced mix of functional + aesthetic designEntrance / FoyerShoe rack with capacity for 30 pairsClean, organized storage with traditional touchLiving RoomTV Unit Design:Designed for 65-inch TVBack panel with premium finishProvision for sound bar & speakersIntegrated glass display unitMaster Bedroom (Ground Floor)Theme: Hotel-style luxury design Option 1: Bed with side tablesWardrobe on south wall with loft storageOption 2: L-shaped layout (bed near window side)Wardrobe + study ledge integrationCurtainsCurtain pelmet provided in all rooms for a clean finishKitchen & UtilityKitchen with utility separationDining-side wash basin area:Partition using dummy wall for visual separationHome Office + Dining + PoojaCombined space planning:6-seater dining tableDedicated pooja unitFunctional home office areaSecond Floor Bedroom 1 (BR1)Wardrobe with integrated dresserStudy table with:Pencil drawerCurved edges for safetyTV unit above study tableBR1 Study DesignStudy table with soft cornersL-shaped top cabinets for storageStaircaseInvisible grill design for safety + modern aestheticÂ | [6 empty] | 2026-04-23 |  | 2026-04-30
18968 | Turnkey | 2026-01-01 | Alfateh Mustafa | Nikoo Homes | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M | Murali S | Shashank Singh | Abdul Shafeen | Active | Installation | Execution | 972792 | 972791 | 1261288 | 1184512 | 1170292 | 11 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-14 | 2026-03-26 19:33 | 2026-03-14 | 2026-03-27 17:00 | 2026-03-27 | 2026-03-27 19:49 | 2026-04-15 | 2026-04-11 18:47 | 2026-04-23 | 2026-04-22 18:37 | 2026-05-11 | 2026-05-10 17:07 | 2026-03-27 | 2026-03-31 | 2026-03-28 | 2026-04-03 17:07 | 2026-04-03 | 2026-04-04 15:20 | 2026-04-05 | 2026-04-07 19:39 |  |  |  |  | 2026-04-11 | 2026-04-20 19:36 | 2026-04-25 | 2026-04-26 15:55 | 2026-04-27 | 2026-04-26 16:12 |  |  | 2026-05-15 | 2026-05-15 20:25 | 2026-05-15 | 2026-05-15 22:18 | 2026-05-23 | 2026-05-16 14:46 | 2026-05-17 | 2026-05-31 13:50 |  |  |  |  | 2026-06-02 14:41 | 2026-06-20 | 2026-06-19 20:17 | 2026-06-26 | 2026-06-24 19:51 | 2026-06-25 | 2026-07-03 15:34 | 2026-06-24 | 2026-07-03 16:01 | 2026-07-03 | 2026-07-04 08:27 | 2026-07-10 | 2026-07-09 19:27 |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-05-22 | 2026-06-02 14:40 | 2026-04-08 | 2026-04-11 18:33 | Site is RTMI | 2026-03-14 | 2026-03-26 18:27 | 1068888 | 192399 | 1242140.4731 | 205095 | 1192061.4395 | 196824 | 1192061.4395 | 196824 | 2026-07-14 09:04:03 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 7-07-2026 to 14-07-2026 for your kind perusal. Project Status: Execution work Floor covering - bonito scope Key Dates: Modular materials dispatched - 3/07/26 Handover as per TAT- 9/08/26 36working days required to complete project post material dispatch to site Key Risk [ Client ] No third party vendors are allowed to site until completion of bonito work No designs changes will be done at the time of execution Note As its priority project we are trying to complete the project as soon as possible | 2026-06-23 11:52:53 +0530 | Nikhil Mogeraya | Hi, Please find theÂ WeeklyÂ ReportÂ for theÂ reportingÂ period. 0 15-06-2026 to 23-06-2026 for your kind perusal. Project Status: Pre Execution workFloor covering - bonito scopeKey Dates: Modular materials dispatched - PH will update youHandover as per TAT- TBD36working days required to complete project post material dispatch to siteKey Risk [ Client ] No third party vendors are allowed to site until completion of bonito workNo designs changes will be done at the time of executionNote Hi sir kindly let me know when will be the site ready.And when we can plan for floor covering | 2026-06-05 19:14:08 +0530 | Yogesh B | Some Image was uploaded | 2026-04-12 | 2026-04-11 19:00 | 2026-04-23 | 2026-04-22 18:37 | RTMI
18969 | Turnkey | 2026-01-01 | Manisha Sahu | Godrej Park Retreat | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 1189857 | 9999 | 0 | 0 | 0 | 118 | 0 | 108987 | 118986 | 475943 | 475942.8 |  |  | 2026-03-19 | 2026-03-19 19:36 | 2026-03-20 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-03-19 | 2026-03-19 19:33 | 0 | 0 | 0 | 0 | 0 | 0 | 1008354 | 181503 | 2026-03-28 10:54:40 +0530 | Rajasekar Ranganathan | CLIENT REQUIREMENT BRIEF Mr. Rahul SahuProject OverviewClient Name: Mr. Rahul SahuPossession Timeline: Within 3 monthsProject Budget: 15 LakhsScope: Full home interior (all new furniture & modular work)FOYER AREA 4 Shoe rack with 30-pair capacityIntegrated seating provisionDecorative wall panel design / wallpaper conceptLIVING AREA 4 Sofa: 35 seater configurationTV Unit with integrated pooja unitFeature TV wall panel designDining: 6-seater dining setupWall design concept for dining areaCrockery unit with storageKITCHEN 4 Base + Wall + Loft cabinetsTall pantry / appliance unitProvision for:RO (below sink)Built-in appliancesLockable storage optionsMinimum 2 wicker basketsUTILITY AREA 4 Sink storage unitOverhead wall storage cabinetsLarder / tall storage unitsCOMMON & OTHER WASHROOM 4 Glass partition (shower area)Vanity unit with mirrorFluted panel design elementsMASTER BEDROOM 4 King-size bedFeature wall panel designL-shaped wardrobeInternal drawer organizersPremium dresser unitWall-mounted bedside lightsBEDROOM 2 4 Queen-size bedWardrobe cabinetFolding study/work tableSide tableWall design elementsBEDROOM 1 4 Sofa-cum-bedStudy tableWardrobe with lock provisionWall design conceptsKEY DESIGN NOTES | 2026-03-20 10:35:25 +0530 | Chanakya Panigrahi | Â RGM Sheet 1. Budget - 13L-15LÂ 2. Property Name & Possession -Godrej Park Retreat 3. Carpet Area - 1050 4. BHK - 3BHK 5. Family Size - 2 + 1 Name -Â Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer - Yes 4. Living/Dining Room Inclusions - TV Unit 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Yes Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz -Â Service Scope -Â False Ceiling - No Painting - Yes Electricity - No 8. Utility/Janitor Unit -Â 9. Timeline - June |  |  |  | 2026-03-30 |  | 2026-04-06
18970 | Turnkey | 2026-01-01 | Hemant Mahabal | Bhoomi Icon | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | vinaya thakur |  | Hold | Preproduction | Site Readiness 1 | 867229 | 174999 | 1042948 | 0 | 0 | 0 | 79 | 0 | 0 | 430937 | 261292.8 |  |  | 2026-03-19 | 2026-03-19 20:33 | 2026-03-21 | 2026-03-21 23:04 | 2026-03-22 | 2026-03-21 23:05 | 2026-04-14 | 2026-04-14 14:18 | 2026-11-27 |  | 2026-12-04 |  | 2026-03-22 | 2026-03-25 18:14 | 2026-03-23 | 2026-03-29 13:06 | 2026-03-29 | 2026-03-30 16:21 | 2026-04-07 | 2026-04-07 14:01 |  |  |  |  | 2026-04-22 | 2026-04-27 17:37 | 2026-11-29 |  | 2026-11-30 |  |  |  | 2026-12-07 |  | 2026-12-08 |  | 2026-12-09 |  | 2026-12-10 | [6 empty] | 2026-12-28 |  | 2027-01-06 |  | 2027-01-05 |  | 2027-01-06 |  | 2027-01-07 |  | 2027-01-09 |  |  |  | 2027-01-31 |  | 2027-02-02 |  | 2027-02-03 | [5 empty] | 2026-12-08 |  | 2026-04-08 | 2026-04-14 14:10 | Site is Non-RTMI | 2026-03-19 | 2026-03-19 20:32 | 883854 | 159093 | 0 | 0 | 0 | 0 | 898363.9882 | 151662 | 2026-07-14 17:35:54 +0530 | Divya Rahangdale | Client will receive possession by the end of October. | 2026-06-29 13:59:40 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: Possession was expected in december end | 2026-04-22 15:41:57 +0530 | Asavari Vare | Minutes of Meeting held on Date: 14/04/26 Based on meeting, below is a list of all the requirements that were discussed during the meeting: Minutes of Meeting held on Date: 19-04-26 Attendees: Clients Discussion: meeting Based on meeting, below is a list of all the requirements that were discussed during the meeting: AÂ 4-seater dining tableÂ has been finalized for the living room.Modular seatingÂ has been incorporated into the living room layout.Kitchen wall storageÂ has been enhanced, including aÂ glass unit on the sink side. Client will visit on 25/04/26 for 10% payment | 2026-04-15 | 2026-04-22 15:35 | 2026-11-28
18971 | Turnkey | 2026-01-01 | Kamal kumar | DOSTI WEST COUNTY | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Shreyash Kotecha |  | Hold | Design | 20% Payment | 1485280 | 205999 | 2069538 | 0 | 0 | 30 | 60 | 0 | 91057 | 624347 | 563876.8 |  |  | 2026-03-19 | 2026-03-20 19:29 | 2026-03-26 | 2026-03-27 11:48 | 2026-03-30 | 2026-03-27 15:08 | 2026-05-11 | 2026-04-15 18:47 | 2026-06-11 |  | 2026-06-18 |  | 2026-03-27 | 2026-03-30 15:41 | 2026-03-28 | 2026-03-30 15:41 | 2026-03-30 | 2026-03-31 15:01 | 2026-06-06 | 2026-04-09 13:35 |  |  |  |  | 2026-07-15 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-04-10 | 2026-04-14 14:22 | Site is Non-RTMI | 2026-03-19 | 2026-03-20 19:26 | 1756648 | 312890 | 0 | 0 | 0 | 0 | 1701817.9863 | 278417 | 2026-06-19 13:25:19 +0530 | Anamika Dolai | Some Image was uploaded | 2026-06-12 18:45:06 +0530 | Anamika Dolai | Client is not willing to pay DEM1 as possession is delayed to July . Client relative of Ishan- closing TL .Hence, wanted the same to be communicated over the milestones. | 2026-06-05 18:26:13 +0530 | Anamika Dolai | client will visit on 9th and pay the 10%. | 2026-04-08 | 2026-04-16 20:22 | 2026-06-12
18972 | Turnkey | 2026-01-01 | Priya | Goderaj Park Retreat | BNG - HSR | Yes | Manoj Kumar R | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Hold | Preproduction | Site Readiness 1 | 1217288 | 188420 | 1235025 | 0 | 0 | 6 | 90 | 0 | 0 | 565600 | 463267.6 |  |  | 2026-03-19 | 2026-03-20 14:37 | 2026-03-20 | 2026-03-20 18:04 | 2026-03-25 | 2026-03-25 12:27 | 2026-04-10 | 2026-04-10 10:56 | 2026-09-05 |  | 2026-09-12 |  | 2026-03-25 | 2026-03-25 17:29 | 2026-03-26 | 2026-03-26 12:51 | 2026-03-26 | 2026-03-27 15:32 | 2026-04-03 | 2026-04-03 19:50 |  |  |  |  | 2026-04-10 | 2026-04-10 15:18 | 2026-09-07 |  | 2026-09-08 |  |  |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 | [6 empty] | 2026-10-06 |  | 2026-10-15 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-18 |  |  |  | 2026-11-09 |  | 2026-11-11 |  | 2026-11-12 | [5 empty] | 2026-09-16 |  | 2026-04-04 | 2026-04-10 10:45 | Site is Non-RTMI | 2026-03-19 | 2026-03-19 20:54 | 1046631 | 188393 | 0 | 0 | 0 | 0 | 1401724.8811 | 231450 | 2026-07-14 18:49:34 +0530 | Manoj Kumar R | Foyer Ledge removed, storage unit added pop design with wallpaper to be add. Tv unit Backpanel(Curved edges) & Tall unit added Flapdown changed to drawers & glass flapdown unit. Pooja unit added with cnc door. & 3 step gopuram box. Next to the pooja beading & flatstrio added. Kitchen Base unit Cylinder unit considered, Blind corner with Half shelf considered, Tall unit shutter sizes changed, Microwave(free standing) to be considered in the design. Loft to be considered in hob elevation. wall unit Open ledge removed l corner closed unit considered. Glass shutter considered in the tall unit side, open unit changed to closed unit. Granite nosing to be conisdered. kitchen entrance panelling to be add. Granite nosing to be conisdered. Utility Sink unit with granite added. Wall unit removed Granite nosing to be conisdered. GBR Loft to be considered adjacent to the wardrobe wall. study unit only tall unit with glass shutter considered in the design, Study stoarge unit removed . KBR wallpaper added single wardrobe with loft added next to the wardrobe, study(Foldable table) shifted to left side wall. MBR Openable wardrobe changed to sliding wardrobe, hidden drawer considered . metal strip considered on wardrobe shutter. Dreseer ledge removed & storage unit , mirror considered Bedwall - wallpaper with beading added. all bathroom vanities removed. Fase ceiling considered in the living, Master & kids room. All actual material samples shared in the whatsapp group. | 2026-04-22 18:19:14 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-16 15:16:04 +0530 | Lalitha Ajay Kumar | Some Image was uploaded | 2026-04-11 | 2026-04-10 11:00 | 2026-09-06 |  | Under Construction | 2026-05-31
18973 | Turnkey | 2026-01-01 | pyaali Ghosh |  | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Active | Preproduction | DEM2 | 931472 | 169958 | 1146555 | 0 | 0 | 8 | 0 | 0 | 0 | 397485 | 364028.8 |  |  | 2026-03-19 | 2026-06-29 13:52 | 2026-03-20 | 2026-06-29 16:00 | 2026-07-02 | 2026-06-29 17:07 | 2026-07-07 | 2026-07-07 16:51 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 | 2026-06-30 11:45 | 2026-06-30 | 2026-06-30 11:50 | 2026-06-30 | 2026-06-30 15:35 | 2026-07-03 | 2026-07-03 15:41 |  |  |  |  | 2026-07-09 | 2026-07-04 20:09 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-08-30 |  | 2026-08-31 | [6 empty] | 2026-09-18 |  | 2026-09-27 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-28 |  | 2026-09-30 |  |  |  | 2026-10-22 |  | 2026-10-24 |  | 2026-10-25 | [5 empty] | 2026-07-24 |  | 2026-09-01 | 2026-07-07 15:06 | Site is RTMI | 2026-03-19 | 2026-06-29 13:50 | 973902 | 172652 | 0 | 0 | 0 | 0 | 1060981.7463 | 173565 | 2026-07-11 17:59:00 +0530 | Mehnaz Ashraf | I will visit on site tomorrow at 11 AM for civil discussion. | 2026-07-07 17:22:28 +0530 | Mehnaz Ashraf | The MoM has been shared with the client. The civil scope is under the client's scope. We will take CM once the flooring work is completed at the site. | 2026-07-04 19:58:42 +0530 | Anil Jagtap | civil work will completed by Mid August | 2026-07-08 | 2026-07-07 16:53 | 2026-07-14 |  | Under Construction | 2026-07-31 | 2026-06-27 | 122091 | Ravi Roy
18974 | Turnkey | 2026-01-01 | Ashish Sahu | prestige city | BNG - HSR | Yes | Nayan Reddy | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 1344600 | 9999 | 0 | 0 | 0 | 117 | 0 | 124461 | 134460 | 537840 | 537840 |  |  | 2026-03-19 | 2026-03-20 10:18 | 2026-03-24 | 2026-03-24 12:39 | 2026-03-26 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-05-20 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-23 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-03-19 | 2026-03-19 22:17 | 0 | 0 | 0 | 0 | 0 | 0 | 1139492 | 205108 | 2026-04-30 14:56:34 +0530 | Patil Madhavi | Some Image was uploaded | 2026-03-24 11:59:03 +0530 | Nayan Reddy | DCM: MINUTES OF MEETING (MOM)Project DetailsClient Name: AshishCRM: RameshProject: Prestige City Meridian ParkFacing: EastConstruction Type: MivanFloor to Ceiling Height: 96Budget: 1012 LakhsMove-in Date: 15/05/2026Meeting Date (RGM): 20/03/2026 Scope of Work1. KitchenMint-themed modular kitchenTall unit with oven + OTGProvision for mixer & toaster800mm single door fridge spaceBase unit + wall unit + loftPantry unit includedSink 600mmDishwasher inside kitchenCountertop: Bonito Granite 2. UtilityWashing machine provisionSink area 900mm 3. FoyerShoe rackPartition between foyer & dining 4. Dining Area6-seater dining setupCrockery unitHandwash cabinet 5. Living RoomTV unitDisplay unitSuspended drawersTall unit (design suggestion required)False ceiling in living & diningSofa: 3-seater + 1 + 1Partition between sofa & pooja unit 6. Pooja UnitLocated near kitchenSize: 2.8 x 6Pocket door mechanism 7. Master Bedroom (Bedroom 1)King size bedWardrobe with loftDressing unit (separate from wardrobe)Study unit 900mmWall storage (open ledges with lighting)False ceiling 8. Kids Bedroom (Bedroom 2)Wardrobe with loftDresserBay window with storageWorkstationNote: 1 child expected 9. Guest Bedroom (Bedroom 3)Wardrobe with loftDresser 10. BathroomsVanity cabinet in all washroomsGlass partition in master bathroom Key Design Notes / DecisionsSeparate dresser & wardrobe in MBR (mandatory)Functional + minimal luxury approach within budgetSmart storage optimization required across roomsDesigner to propose unique tall unit design in living room |  |  |  | 2026-04-04 |  | 2026-04-11
18975 | Turnkey | 2026-01-01 | Rudraksh jewellers(Aman Gandhi) | Seema Rajdhani | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Lost | Design | 20% Payment | 942295 | 0 | 967338 | 0 | 0 | 74 | 14 | 0 | 188459 | 376918 | 376918 |  |  | 2026-03-19 | 2026-03-28 13:33 | 2026-03-19 | 2026-03-28 18:14 | 2026-03-30 | 2026-03-30 13:31 | 2026-04-18 | 2026-04-18 17:04 | 2026-07-01 |  | 2026-07-08 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-05 15:35 | 2026-04-05 | 2026-04-08 10:36 | 2026-04-11 | 2026-04-11 15:07 |  |  |  |  | 2026-04-18 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-04-12 | 2026-04-18 16:40 | Site is RTMI | 2026-03-19 | 2026-03-19 21:24 | 1104091.433 | 179594 | 0 | 0 | 0 | 0 | 1078354.695 | 178062 | 2026-05-14 17:13:35 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-12 14:41:45 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-11 18:20:13 +0530 | Christopher Macwan | Some Image was uploaded | 2026-04-19 | 2026-04-18 17:52 | 2026-07-02
18976 | Turnkey | 2026-01-01 | Amol Bhandare | RUNWAL FOREST | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Design | DEM1 | 2121947 | 284999 | 2738241 | 0 | 0 | 91 | 13 | 0 | 139390 | 875293 | 822264.8 |  |  | 2026-03-19 | 2026-03-19 21:57 | 2026-03-30 | 2026-03-30 21:47 | 2026-04-02 | 2026-03-30 21:51 | 2026-12-04 |  | 2026-12-11 |  | 2026-12-18 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-02 12:15 | 2026-04-02 | 2026-04-02 14:26 | 2026-04-03 | 2026-04-03 18:12 |  |  |  |  | 2026-12-05 |  | 2026-12-13 |  | 2026-12-14 |  |  |  | 2026-12-21 |  | 2026-12-22 |  | 2026-12-23 |  | 2026-12-24 | [6 empty] | 2027-01-11 |  | 2027-01-20 |  | 2027-01-19 |  | 2027-01-20 |  | 2027-01-21 |  | 2027-01-23 |  |  |  | 2027-02-14 |  | 2027-02-16 |  | 2027-02-17 | [5 empty] | 2026-12-22 |  | 2026-11-30 |  | Unknown | 2026-03-19 | 2026-03-19 21:57 | 2323345 | 414896 | 0 | 0 | 0 | 0 | 2323344.644 | 380325 | 2026-07-02 17:05:00 +0530 | Divya Rahangdale | Hold | 2026-06-26 13:36:26 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-06-17 17:48:07 +0530 | Anil Jagtap | The customer informed that he is expected to receive possession by mid-July and want to start the DDM process . | 2026-12-05 |  | 2026-12-12
18977 | Turnkey | 2026-01-01 | Mrs Neeti Singh | Kalpataru Vivant | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  |  | Uday Yadruk | Rizwan Mistry |  | Umang Shah | Siddhesh Gujrathi | Active | Design | DEM3 | 1103003 | 225967 | 1452880 | 0 | 0 | 12 | 0 | 0 | 0 | 456421 | 420615.2 |  |  | 2026-03-19 | 2026-03-19 22:44 | 2026-04-03 | 2026-04-03 12:11 | 2026-04-04 | 2026-04-04 19:29 | 2026-04-22 | 2026-04-19 17:03 | 2026-07-13 | 2026-07-14 12:31 | 2026-07-16 |  | 2026-04-04 | 2026-04-06 22:33 | 2026-04-05 | 2026-04-07 13:33 | 2026-04-07 | 2026-04-07 15:57 | 2026-04-17 | 2026-04-17 17:03 |  |  |  |  | 2026-04-19 | 2026-04-28 20:06 | 2026-07-02 | 2026-07-03 09:38 | 2026-07-04 | 2026-07-03 09:38 |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-04-18 | 2026-04-18 20:14 | Site is RTMI | 2026-03-19 | 2026-03-19 22:36 | 1233541 | 219338 | 0 | 0 | 0 | 0 | 1211049.6015 | 200670 | 2026-07-05 11:35:46 +0530 | Khyati Bandi | LIVING AREA - 1. Book shelf height - 72" 2. Mandir below drawers 11" (2 drawers) 3. Full rectangular mirror with bevelling 4. U shape peripheral ceiling KITCHEN - 1. Sink granite 2. Microwave to be in utility MBR - 1. Rectangular beveled Mirror 2. No shutter for locker in wardrobe COMMON WASHROOM - 1. Brown tinted glass shutter 2. Mirror height 2'6" SONS ROOM - 1. Study height 30" + book shelf as per last 3d 2. add shelves on window wall with half paneling 3. Remove cloth hanging unit, increase width of wardrobe | 2026-06-04 17:36:53 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-27 10:52:46 +0530 | Khyati Bandi | KITCHEN -Â 1. Add one wicker basket 600mm height 200mm 2. Add dustbin unit near sink, Add one shelf if possible. SONS ROOM -Â 1. Add shoe accessoriesÂ 2. Queen size bedÂ MBR -Â 1. Remove dressing unitÂ 2. wardrobe 900mm 3. Locker will be placed in base shelf above skirtingÂ | 2026-04-20 | 2026-04-19 17:05 | 2026-07-15 | 2026-07-14 12:31 | Under Construction | 2026-05-01
18978 | Turnkey | 2026-01-01 | Shashank Sanjay Lad | Piramal Vaikunth | MUM - Thane | Yes | Maasoumeh Raza | Anamika Dolai | [8 empty] | Active | Prospect | DCM Due | 959676 | 9999 | 0 | 0 | 0 | 118 | 0 | 85969 | 95968 | 424330 | 343411.2 |  |  | 2026-03-19 | 2026-03-19 23:23 | 2026-03-20 | 2026-04-02 11:26 | 2026-03-19 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-04-13 |  | 2026-04-21 |  | 2026-04-22 |  |  |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 | [6 empty] | 2026-05-20 |  | 2026-05-29 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-06-01 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-04-30 |  | 2026-04-08 |  | Unknown | 2026-03-19 | 2026-03-19 23:02 | 0 | 0 | 0 | 0 | 0 | 0 | 813285 | 146391 | 2026-05-27 16:04:15 +0530 | Maasoumeh Raza | DCM: Project No: 18978 Client: Shashank Sanjay Lad Hi, Name: 18978 - Shashank Sanjay LadÂ Property Name: Piramal Vaikunth Property type: 1bhkÂ Possession: June Move in: September Member: 3 memberÂ Budget: 8LÂ Requirements:Â Living room:Â Shoe rack [40 pairs] in bedroom TV unit [43 Inch] MandirÂ Â Master Bedroom: Queen size BedÂ Wardrobe with loft side table Dressing unit Study table Master bathroom vanity below Kitchen : Base unitÂ Wall unit Loft unit [1 side option] Appliance unit Additional Work: False ceilingÂ ElectrificationÂ Painting Based on meeting, below is a list of all the requirements that were discussed during the meeting: | 2026-04-07 17:30:38 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-24 15:37:27 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-04-13 |  | 2026-04-20
18979 | Turnkey | 2026-01-01 | Sushma survase | new prathamesh | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar | [7 empty] | Hold | Preproduction | Site Readiness 1 | 922686 | 184537 | 1242877 | 0 | 0 | 2 | 60 | 0 | 0 | 430206 | 307942.8 |  |  | 2026-03-19 | 2026-03-20 16:16 | 2026-03-26 | 2026-03-26 15:19 | 2026-03-26 | 2026-03-26 15:26 | 2026-05-10 | 2026-05-10 18:49 | 2026-07-22 |  | 2026-07-29 |  | 2026-03-26 | 2026-03-26 19:27 | 2026-03-27 | 2026-03-27 15:32 | 2026-03-27 | 2026-04-04 12:32 | 2026-04-17 | 2026-04-17 18:47 |  |  |  |  | 2026-05-10 | 2026-05-14 18:51 | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-04-18 | 2026-05-10 18:42 | Site is Non-RTMI | 2026-03-19 | 2026-03-20 16:07 | 1053285 | 189591 | 0 | 0 | 0 | 0 | 1052885.4152 | 166680 | 2026-05-28 13:07:33 +0530 | Reshma Melanta | THE SITE IS NOT READY FOR IM THE BUILDER IS NOT ALLOWING THE SAME. HAVE KEPT THE PROJECT ON HOLD ONCE IM IS APPORVED WILL UN HOLD THE PROJECT | 2026-05-13 15:47:04 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-26 15:43:49 +0530 | Sonal Singh | DDM1: 26-04-26 The DDM 1 agenda could not be completed as the net designer provided an incorrect SKP file. Additionally, during the CDP, the client requested the same design input; however, this has also not yet been completed. | 2026-05-11 | 2026-05-10 18:52 | 2026-07-23
18980 | Sub Project |  | Shashank Singh | Courtyard asteria | MUM - Thane | Yes | Hemant Sonar |  | Anil Kuwar |  | Vaishali G | [5 empty] | Active | Design | 20% Payment | 452337 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 135701 | 135701 | 180934.8 |  |  | 2026-03-20 | 2026-03-27 16:07 | 2026-03-21 | 2026-03-27 16:08 | 2026-03-27 | 2026-03-27 16:08 | 2026-03-27 | 2026-03-27 16:36 | 2026-04-02 |  | 2026-04-09 |  | 2026-03-27 | 2026-03-27 16:12 | 2026-03-28 | 2026-03-27 16:12 | 2026-03-27 | 2026-03-27 16:12 | 2026-03-28 | 2026-03-27 16:12 |  |  |  |  | 2026-03-27 |  | 2026-04-04 |  | 2026-04-05 |  |  |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 | [30 empty] | 2026-04-13 |  | 2026-03-28 | 2026-03-27 16:12 | Unknown | 2026-03-20 | 2026-03-27 16:07 | 0 | 0 | 0 | 0 | 0 | 0 | 417731.7742 | 69000 | [9 empty] | 2026-03-28 | 2026-03-27 16:36 | 2026-04-03
18981 | Turnkey | 2026-01-01 | Bhavna vora | Integrated ramicon | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Design | DEM1 | 2385784 | 297487 | 2974876 | 0 | 0 | 96 | 0 | 0 | 179670 | 1048329 | 860298 |  |  | 2026-03-19 | 2026-03-30 12:30 | 2026-03-30 | 2026-03-30 12:50 | 2026-04-02 | 2026-03-30 12:58 | 2026-07-03 |  | 2026-08-21 |  | 2026-08-28 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-08 22:57 | 2026-04-08 | 2026-04-10 11:57 | 2026-04-12 | 2026-04-12 11:23 |  |  |  |  | 2026-07-04 |  | 2026-08-23 |  | 2026-08-24 |  |  |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 | [6 empty] | 2026-09-21 |  | 2026-09-30 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-03 |  |  |  | 2026-10-25 |  | 2026-10-27 |  | 2026-10-28 | [5 empty] | 2026-09-01 |  | 2026-08-15 |  | Unknown | 2026-03-19 | 2026-03-20 12:55 | 2521082 | 453794 | 0 | 0 | 0 | 0 | 2504669.795 | 432195 | 2026-04-12 11:22:44 +0530 | Manzoor Shaikh | "Welcome call done along with the Designer. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : July End Customer will make 10% as per deviation approval from dipen post 45 days, however, the client said she already informed Moni that she will pay after possession only. FDM dates: TBD Price protection for 150 days from the NET date." | 2026-04-10 11:56:25 +0530 | Royden Henriques | Some Image was uploaded | 2026-04-09 22:10:26 +0530 | Sahil Sethi | Some Image was uploaded | 2026-07-04 |  | 2026-08-22
18983 | Turnkey | 2026-01-01 | Hemant Shendre | Atharv Aaradhyam | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-20 | 2026-03-21 12:22 | 2026-03-21 |  | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-03-20 |  | 2026-03-21 |  | 2026-03-21 |  | 2026-03-22 | [5 empty] | 2026-03-28 |  | 2026-04-05 |  | 2026-04-06 |  |  |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 | [6 empty] | 2026-05-04 |  | 2026-05-13 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-16 |  |  |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-10 | [5 empty] | 2026-04-14 |  | 2026-03-23 |  | Unknown | 2026-03-20 | 2026-03-21 12:14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-24 17:20:35 +0530 | Aryan Singh | Some Image was uploaded | 2026-03-24 15:11:39 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-20 17:31:04 +0530 | Aryan Singh | Some Image was uploaded | 2026-03-28 |  | 2026-04-04
18984 | Sub Project |  | Sheena Basnal | Purva atmospher | BNG - HRBR |  | Chandini Nj | Rajeshwari S | Shibin Lal |  |  | Harshit Choudhary | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-20 | 2026-03-27 11:18 | 2026-03-21 | 2026-03-27 11:18 | 2026-03-27 | 2026-03-27 11:18 | 2026-03-28 | 2026-03-27 11:19 | 2026-03-28 | 2026-03-27 11:21 | 2026-03-28 | 2026-03-27 11:22 | 2026-03-27 | 2026-03-27 11:18 | 2026-03-28 | 2026-03-27 11:18 | 2026-03-27 | 2026-03-27 11:18 | 2026-03-28 | 2026-03-27 11:19 |  |  |  |  | 2026-03-27 | 2026-03-27 11:19 | 2026-03-28 | 2026-03-27 11:21 | 2026-03-28 | 2026-03-27 11:21 |  |  | 2026-03-28 | 2026-03-27 16:12 | 2026-03-28 | 2026-03-27 16:23 | 2026-04-05 | 2026-04-05 12:19 | 2026-04-06 | 2026-04-05 12:19 |  |  |  |  | 2026-04-05 13:34 | 2026-04-12 | 2026-04-13 17:07 | 2026-04-15 | 2026-04-13 17:24 | 2026-04-14 | 2026-04-28 12:09 | 2026-04-13 | 2026-04-28 16:00 | 2026-04-28 | 2026-04-28 16:01 | 2026-04-29 | 2026-04-28 18:06 |  |  | 2026-04-30 | 2026-04-28 18:12 | 2026-04-30 | 2026-04-28 18:15 | 2026-05-08 | 2026-04-29 20:39 |  |  |  |  | 2026-03-27 | 2026-04-04 11:07 | 2026-03-28 | 2026-03-27 11:19 | Unknown | 2026-03-20 | 2026-03-27 11:18 | 0 | 0 | 0 | 0 | 42372.8814 | 0 | 42372.8814 | 0 | [9 empty] | 2026-03-28 | 2026-03-27 11:19 | 2026-03-28 | 2026-03-27 11:21
18986 | Turnkey | 2026-01-01 | Anand Kabra | SNN RAJ SERENITY | BNG - HSR | Yes | Rajasekar Ranganathan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 6262032 | 9999 | 0 | 0 | 0 | 110 | 0 | 616204 | 626203 | 2601387 | 2408238.4 |  |  | 2026-03-18 | 2026-03-27 18:11 | 2026-03-20 |  | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-06-03 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-03 |  | 2026-06-05 |  |  |  | 2026-07-08 |  | 2026-07-10 |  | 2026-07-12 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-03-18 | 2026-03-20 18:42 | 0 | 0 | 0 | 0 | 0 | 0 | 5323951 | 938080 | 2026-03-26 16:05:22 +0530 | Aparna | RGM Client Name: Anand Kabra Project Type: 4.5 BHK Property: SNN Serenity Gardens Possession Timeline: End of April Facing: West Facing Family Members: 4 Kids: 2 Sons Next Site Visit: After 28th Budget: 15L Note: All loose furniture in client scopeAristo wardrobes to be provided for all bedroomsOverall Design BriefDesign to be minimalistic, unique, and elegantFalse ceiling required in Living, Dining, and all Bedrooms (lighter shades)Functional planning with aesthetic detailing across all spacesEntrance / FoyerAdditional foyer space to be utilizedWooden door with partitionReference images shared for design directionExisting console with rattan finish to be retainedOpposite side unit to match same finishFoyer WallDesign as per reference (can be modified)Opposite Entry WallArch-shaped POP nicheHighlight with texture paint / Pichwai paintingIntegrated lighting as per referenceLiving Area (Bedroom 4 Converted Space)No TV unit in living roomTV to be placed in Bedroom 4Highlight wall with painting (6 x 5)3-seater low seating sofaOpposite wall: 5-seater sofa with rectangular mirror aboveFeature wall treatment requiredPooja UnitSize: 5 x 2.5Sitting pooja conceptPocket doors with glass shuttersInternal finish: Onyx stone at bottomInternal lightingConcealed seating with storage2 shelvesDining Area8-seater diningDining table (Onyx) Client scopeKitchenExtended breakfast counter / island (preferred)Tall unit for microwave, OTGHob & chimney (to be included from our end)Loft storage2 tall unitsUtility AreaWall storageSink unitDishwasher provisionNo washing machine hereJanitor unitBalcony (Extended)Washing machine (BR1 wall)Dryer, laundry baskets, ironing board, storageOpposite side seating (client scope)Aesthetic storage unitBedroom 1 (Master Bedroom)Shift door opening near balconyWooden partition to create walk-in closet with dresserDecorative corner in partitionFloor-mounted TV unit with storageBay window seatingBed back wall with wooden paneling (as per reference)Bedside tables includedBedroom 3 (Son 20 yrs)Aristo wardrobeDresser + TV + Study table on same wallBay window seatingBed design as per reference (similar look & feel)Bathroom: End-to-end vanity, WC opposite toilet doorLED mirror + vanity unitBedroom 2 (Son 15 yrs)Entrance wall construction & door repositioningDresser room (5 x 3.5) with sliding door for washroomWardrobe on dining wallTV unit + bedTheme to be proposedBedroom 4 (Guest Bedroom)Entry shifted to opposite sideBed design to be suggested as per themeTV unitDresser on right sideToilet with end-to-end wash basinShower glass partition (client scope)Aristo wardrobeStudy RoomU-shaped study unitTall toy storageLoft storageSeating for 2 peopleBookshelf with glass shutters and lightingBalcony (Landscape Area)SeatingWater fountainExterior landscapingKey Discussion SummaryStrong focus on functional luxury with minimal aestheticsUse of highlight elements like Pichwai, Onyx, mirrors, texturesBedrooms customized as per individual needsStorage planning is a priority across all areasAction ItemsFinalize foyer design with partition and console matchingDevelop POP niche with lighting + Pichwai conceptPlan Bedroom 4 as semi-living/TV spaceDesign walk-in wardrobe for Master BedroomSuggest theme for Bedroom 2Finalize kitchen layout with island/breakfast counterPlan utility and balcony functionalityDesign study unit and storageProvide false ceiling concepts for all spacesPrepare design for next visit after 28thÂ | [6 empty] | 2026-04-04 |  | 2026-04-11
18987 | Turnkey | 2026-01-01 | Dhiren Dedhia | kalpataru shrishti namah | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Design | DEM1 | 802497 | 79999 | 1120884 | 0 | 0 | 7 | 96 | 0 | 80500 | 320999 | 320998.8 |  |  | 2026-03-20 | 2026-03-26 13:38 | 2026-03-29 | 2026-03-29 11:05 | 2026-03-29 | 2026-03-30 13:08 | 2026-08-02 |  | 2026-08-09 |  | 2026-08-16 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-02 10:35 | 2026-04-02 | 2026-04-03 12:47 | 2026-04-10 | 2026-04-10 13:35 |  |  |  |  | 2026-08-03 |  | 2026-08-11 |  | 2026-08-12 |  |  |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-08-20 |  | 2026-08-01 |  | Unknown | 2026-03-20 | 2026-03-20 13:48 | 949901 | 170982 | 0 | 0 | 0 | 0 | 934766.204 | 154067 | 2026-04-10 13:37:04 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-10 13:30:19 +0530 | Reshma Melanta | SPOKE TO THE CX POSSESSION - JUNE/JULY 2026 NOT SURE CX - WILL PAY ONLY POST THE POSSESSION APPROVAL FROM DIPEN FOR THE SAME HAVE ADDED MY SELF TO THE GROUP HAVE SEND ACROSS ON HOLD REQUEST TO THE CLEITN FOR APPROVAL. | 2026-04-03 12:47:05 +0530 | Royden Henriques | ___________________________________________ Possession : june/july'26 Payment Mode : B2C Self funding - Yes CX will pay the next milestone in September when he receives Possession and price protection until Sep - As per Approval from Dipen. Designs also will start once he gets possession. Tower H, 2307-2308, Kalpataru Shrishti Namaha,, Sector 1, Shrishti Complex, Mira Road- East, Mira Bhyandar Road, Thane -401107 Post offers the amount is 8,02,497/- as per the offer email. 90+15=105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays | 2026-08-03 |  | 2026-08-10
18989 | Turnkey | 2026-01-01 | Mr. Indrapratap Vishwakarma | SK Heights | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [7 empty] | Hold | Design | DEM1 | 808324 | 101999 | 1033385 | 0 | 0 | 5 | 92 | 0 | 59666 | 357203 | 289456.4 |  |  | 2026-03-20 | 2026-03-30 17:19 | 2026-03-30 | 2026-03-30 21:22 | 2026-04-02 | 2026-03-30 21:29 | 2026-08-03 |  | 2026-08-10 |  | 2026-08-17 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-04 11:27 | 2026-04-04 | 2026-04-09 09:22 | 2026-04-11 | 2026-04-11 11:35 |  |  |  |  | 2026-08-04 |  | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-07-30 |  | Unknown | 2026-03-20 | 2026-03-30 17:15 | 875750 | 157635 | 0 | 0 | 0 | 0 | 875749.986 | 139320 | 2026-07-10 13:17:32 +0530 | Anil Jagtap | cx will receive the possession by September *26 | 2026-04-11 11:33:47 +0530 | Anil Jagtap | welcome call done. Possession will received around June or july | 2026-04-09 09:22:12 +0530 | Royden Henriques |  | 2026-08-04 |  | 2026-08-11
18990 | Turnkey | 2026-01-01 | Prakash pawar | Purva Zenium | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 1993350 | 202999 | 1247966 | 0 | 0 | 84 | 0 | 0 | 195671 | 822554 | 772126.4 |  |  | 2026-03-19 | 2026-03-29 16:19 | 2026-04-22 | 2026-04-22 12:45 | 2026-04-25 | 2026-04-22 13:08 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 | 2026-07-11 17:58 | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-19 | 2026-03-27 19:17 | 1057599 | 190367 | 0 | 0 | 0 | 0 | 1689280 | 304070 | 2026-04-24 11:33:24 +0530 | Yogesh B | Some Image was uploaded | 2026-04-14 16:56:40 +0530 | Shashank Singh | Some Image was uploaded | 2026-04-14 16:56:05 +0530 | Shashank Singh | Some Image was uploaded | 2026-04-30 |  | 2026-05-07
18991 | Turnkey | 2026-01-01 | Srishti / Tayendra Kumar | null | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Shashank Singh |  | Active | Design | DEM1 | 1201043 | 128749 | 1553000 | 0 | 0 | 55 | 0 | 0 | 111460 | 505127 | 455707.6 |  |  | 2026-03-20 | 2026-04-17 18:38 | 2026-04-22 | 2026-04-22 12:58 | 2026-04-25 | 2026-04-27 14:41 | 2026-07-05 |  | 2026-08-03 |  | 2026-08-10 |  | 2026-04-27 | 2026-04-30 | 2026-04-28 | 2026-05-20 17:16 | 2026-05-20 | 2026-05-21 13:04 | 2026-05-24 | 2026-05-24 18:57 |  |  |  |  | 2026-07-06 |  | 2026-08-05 |  | 2026-08-06 |  |  |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 | [6 empty] | 2026-09-03 |  | 2026-09-12 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-15 |  |  |  | 2026-10-07 |  | 2026-10-09 |  | 2026-10-10 | [5 empty] | 2026-08-14 |  | 2026-05-25 |  | Unknown | 2026-03-20 | 2026-03-26 19:53 | 1316101 | 236898 | 0 | 0 | 0 | 0 | 1301267.4271 | 214862 | 2026-07-12 15:00:31 +0530 | Parasa Sri | IM on 18th | 2026-06-23 16:20:43 +0530 | Parasa Sri | Some Image was uploaded | 2026-06-06 17:29:32 +0530 | Parasa Sri | Some Image was uploaded | 2026-07-06 |  | 2026-08-04 |  | Under Construction | 2026-07-31
18992 | Turnkey | 2026-01-01 | Prabhat Keni | Ladha Pallava | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Shreyash Kotecha |  | Active | Preproduction | DEM2 | 3399995 | 679999 | 4468149 | 0 | 0 | 23 | 0 | 0 | 0 | 1673891 | 1046105.2 |  |  | 2026-03-20 | 2026-03-21 18:44 | 2026-03-28 | 2026-05-12 14:54 | 2026-05-15 | 2026-05-14 19:43 | 2026-06-15 | 2026-06-11 17:19 | 2026-07-26 |  | 2026-08-02 |  | 2026-05-14 | 2026-05-15 12:24 | 2026-05-15 | 2026-05-15 21:02 | 2026-05-15 | 2026-05-18 10:32 | 2026-06-10 | 2026-06-10 13:20 |  |  |  |  | 2026-06-16 | 2026-06-22 19:07 | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-23 |  | 2026-10-25 |  | 2026-10-27 | [5 empty] | 2026-08-06 |  | 2026-06-11 | 2026-06-11 17:16 | Site is RTMI | 2026-03-20 | 2026-03-21 11:58 | 3788855 | 679294 | 0 | 0 | 0 | 0 | 3750506.5025 | 616500 | 2026-06-26 11:34:28 +0530 | Naved Malik | Planning one virtual meeting on 27th June with client as he lives in US. | 2026-06-21 11:47:28 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-13 19:35:14 +0530 | Naved Malik | Some Image was uploaded | 2026-06-12 | 2026-06-11 18:14 | 2026-07-27
18993 | Turnkey | 2026-01-01 | Mr. Viren P Pandya | Mahindra Alcove | MUM - GOR | Yes | Khyati Bandi | Reshma Melanta | Safalta Karkera |  | Mohammed Lal | Savita Parab | Rizwan Mistry | Murali S | Moni Sahani | Aakash Gaikwad | Active | Production | 100% Payment | 1239190 | 769093 | 1219303 | 1255713 | 1286690 | 2 | 0 | 0 | 0 | 0 | 470097 |  |  | 2026-03-20 | 2026-03-27 13:49 | 2026-03-22 | 2026-03-27 18:32 | 2026-03-30 | 2026-03-30 12:10 | 2026-04-22 | 2026-04-19 17:36 | 2026-06-01 | 2026-05-31 12:57 | 2026-05-31 | 2026-05-31 15:34 | 2026-03-30 | 2026-03-28 15:58 | 2026-03-31 | 2026-04-02 13:19 | 2026-04-02 | 2026-04-02 15:47 | 2026-04-10 | 2026-04-10 12:01 |  |  |  |  | 2026-04-19 | 2026-05-08 15:08 | 2026-05-18 | 2026-05-17 17:08 | 2026-05-18 | 2026-05-17 17:09 |  |  | 2026-06-04 | 2026-06-06 16:11 | 2026-06-06 | 2026-06-06 20:47 | 2026-06-07 | 2026-06-17 17:52 | 2026-06-18 | 2026-06-24 17:50 |  |  |  |  | 2026-06-27 09:53 | 2026-07-05 | 2026-07-04 18:51 | 2026-07-15 | 2026-07-13 18:44 | 2026-07-14 |  | 2026-07-13 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-06-06 | 2026-06-27 09:52 | 2026-04-11 | 2026-04-18 20:14 | Site is RTMI | 2026-03-20 | 2026-03-20 19:03 | 1033307 | 185995 | 1286523.558 | 215569 | 1321291.2115 | 218098 | 1321291.2115 | 218098 | 2026-07-08 23:55:53 +0530 | Savita Parab | Execution: cx scope work is going on we received key on 24th july as confirmed by PH | 2026-06-25 11:55:56 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-24 14:18:48 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-20 | 2026-04-19 17:38 | 2026-06-01 | 2026-05-31 12:58
18994 | Turnkey | 2026-01-01 | Satish Raju Shetty | Lodha Woods | MUM - GOR | Yes | Batskhem Marpna | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Moni Sahani |  | Hold | Design | DEM1 | 1293946 | 129394 | 1293946 | 0 | 0 | 40 | 51 | 0 | 129395 | 559875 | 475282 |  |  | 2026-03-19 | 2026-04-10 13:13 | 2026-04-11 | 2026-04-11 10:10 | 2026-04-14 | 2026-04-14 13:38 | 2026-08-09 |  | 2026-08-16 |  | 2026-08-23 |  | 2026-04-02 | 2026-04-10 17:42 | 2026-04-03 | 2026-04-10 19:27 | 2026-04-15 | 2026-04-15 16:02 | 2026-04-23 | 2026-04-23 18:17 |  |  |  |  | 2026-08-10 |  | 2026-08-18 |  | 2026-08-19 |  |  |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 | [6 empty] | 2026-09-16 |  | 2026-09-25 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-28 |  |  |  | 2026-10-20 |  | 2026-10-22 |  | 2026-10-23 | [5 empty] | 2026-08-27 |  | 2026-08-05 |  | Unknown | 2026-03-19 | 2026-03-20 19:13 | 1098663 | 195283 | 0 | 0 | 0 | 0 | 1098663 | 195283 | 2026-07-02 16:40:25 +0530 | Reshma Melanta | Others: | 2026-04-25 19:11:13 +0530 | Reshma Melanta | Minutes of Meeting: Client Call SummaryProject Status & Timeline Update 1. Possession and Scheduling Site Possession: Currently estimated for late July 2026, though this remains tentative and subject to confirmation.Client Availability: Please note that you will be unavailable from May 1st to May 22nd, 2026, due to your daughters exams and upcoming travel.Meeting Preferences: Moving forward, meetings should ideally be scheduled on Saturdays or Sundays to accommodate your schedule.2. Project Status & Design Team Designer Update: The assigned designer, Sweta, is currently on leave.Price Protection: As discussed, to secure current commercial terms and prevent price escalations, the project will be placed on formal hold.Next Steps: A formal email will be shared shortly to document this hold period for our records.3. Post-Break Alignment DEM-1 Meeting: A Design Evaluation Meeting (DEM-1) is required to realign the project once you return. This will be scheduled after May 22nd, 2026.Communication: You will provide an update in the WhatsApp group to confirm the exact dates for this meeting once you are ready to resume. | 2026-04-23 18:12:16 +0530 | Reshma Melanta | THE CX IS OUTSIDE TOWN THE CX WILL CALL TOMORROW INTRODUCED MYSELF IN THE GROUP | 2026-08-10 |  | 2026-08-17 |  | Under Construction | 2026-07-31
18997 | Turnkey | 2026-01-01 | Sambhav Jaiswal | Sobha Royal Pavilion | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP |  | RaviKumar Battala | Yogeshwaran | Ranjith Kumar | Murali S | Ramesh Nayak | Affaan Abdulla | Active | Installation | Execution | 1572886 | 1572886 | 1862728 | 0 | 1572886 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-21 | 2026-03-21 12:39 | 2026-03-30 | 2026-03-31 18:26 | 2026-03-31 | 2026-03-31 22:13 | 2026-04-25 | 2026-05-09 17:03 | 2026-05-11 | 2026-05-10 10:37 | 2026-05-26 | 2026-05-26 12:49 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 13:26 | 2026-04-03 | 2026-04-04 17:01 | 2026-04-11 | 2026-04-11 19:20 |  |  |  |  | 2026-04-26 | 2026-05-09 14:41 | 2026-05-11 | 2026-05-13 23:47 | 2026-05-14 | 2026-05-13 23:48 |  |  | 2026-05-30 | 2026-06-03 19:27 | 2026-06-11 | 2026-06-11 16:32 | 2026-06-12 | 2026-06-13 07:02 | 2026-06-14 | 2026-06-18 13:18 |  |  |  |  | 2026-06-22 11:00 | 2026-06-28 | 2026-06-27 21:00 | 2026-07-08 | 2026-07-06 21:12 | 2026-07-07 | 2026-07-10 12:59 | 2026-07-19 | 2026-07-13 18:50 | 2026-07-13 | 2026-07-13 22:43 | 2026-07-15 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-06-11 | 2026-06-22 10:59 | 2026-04-12 | 2026-04-25 16:46 | Site is RTMI | 2026-03-21 | 2026-03-21 12:35 | 1578583 | 284145 | 0 | 0 | 1821431.3266 | 305906 | 1821431.3266 | 305906 | 2026-07-07 10:30:46 +0530 | Ranjith Kumar | 100% Payment: | 2026-06-18 18:35:00 +0530 | Ranjith Kumar | Site Readiness 2: | 2026-06-04 12:54:19 +0530 | Aishwarya C | just for the offer client needs electrical also part of the project he rejected in the final stage of the project right before pushing to production | 2026-05-10 | 2026-05-09 17:07 | 2026-05-11 | 2026-05-10 10:38 | RTMI
18998 | Turnkey | 2026-01-01 | Sanjivani Desai | Silver Serene | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Nishant Jadhav | Sandeep Tiwari | Murali S | Rashmita Das | Siddhesh Gujrathi | Active | Preproduction | Procurement | 1533073 | 951391 | 1379392 | 0 | 1533073 | 10 | 18 | 0 | 0 | 0 | 581682 |  |  | 2026-03-21 | 2026-03-21 21:07 | 2026-03-22 | 2026-03-22 21:45 | 2026-03-25 | 2026-03-25 13:20 | 2026-04-22 | 2026-04-22 19:26 | 2026-06-22 | 2026-06-21 19:02 | 2026-06-21 | 2026-06-21 19:10 | 2026-03-25 | 2026-03-26 12:19 | 2026-03-26 | 2026-03-26 12:20 | 2026-03-26 | 2026-03-30 11:09 | 2026-04-10 | 2026-04-10 18:40 |  |  |  |  | 2026-04-23 | 2026-05-14 18:58 | 2026-06-05 | 2026-06-06 11:31 | 2026-06-07 | 2026-06-08 13:26 |  |  | 2026-06-25 | 2026-06-27 18:13 | 2026-06-30 | 2026-06-30 18:34 | 2026-07-01 | 2026-06-30 21:01 | 2026-07-01 | 2026-07-04 14:39 |  |  |  |  | 2026-07-05 18:38 | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-30 | 2026-07-05 15:53 | 2026-06-30 | 2026-04-22 19:14 | Site is RTMI | 2026-03-21 | 2026-03-21 12:45 | 1168976 | 210415 | 0 | 0 | 1619559.7937 | 267417 | 1619559.7937 | 267417 | 2026-05-22 12:27:56 +0530 | Manzoor Shaikh | Dear Ms. Sanjivani Desai, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 24th May at 04:00 PM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Shweta will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-05-12 16:50:08 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-30 16:20:30 +0530 | Meet Shah | Some Image was uploaded | 2026-04-23 | 2026-04-23 19:09 | 2026-06-22 | 2026-06-21 19:03
18999 | Turnkey | 2026-01-01 | Kashyap M | Nishad Building | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2293982 | 9999 | 2293982 | 0 | 0 | 109 | 0 | 219399 | 229398 | 1004821 | 830364.8 |  |  | 2026-03-21 | 2026-03-25 23:51 | 2026-03-21 | 2026-03-25 23:53 | 2026-03-28 | 2026-03-28 15:14 | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-21 | 2026-03-25 23:50 | 1944053 | 349929 | 0 | 0 | 0 | 0 | 1944053 | 349929 | [9 empty] | 2026-04-05 |  | 2026-04-12
19000 | Turnkey | 2026-01-01 | CONCRETE ARTS INDIA (Ruchi Kokate) | Dev Datta | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Snehankit Agre | Akshat Shrivastava | Murali S | Mustufa Sohagpurwala | Shailendra Mishra | Active | Production | Dispatch Due | 1499862 | 1499862 | 1709196 | 0 | 1499862 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-21 | 2026-03-21 13:31 | 2026-03-25 | 2026-03-26 21:16 | 2026-03-29 | 2026-03-27 14:25 | 2026-04-08 | 2026-04-08 19:24 | 2026-04-25 | 2026-04-24 18:22 | 2026-05-06 | 2026-05-06 19:51 | 2026-03-27 | 2026-03-27 19:10 | 2026-03-28 | 2026-03-30 11:26 | 2026-03-30 | 2026-03-30 16:30 | 2026-04-04 | 2026-04-04 13:03 |  |  |  |  | 2026-04-08 | 2026-04-09 19:14 | 2026-04-25 | 2026-04-24 19:12 | 2026-04-25 | 2026-04-24 19:13 |  |  | 2026-05-09 | 2026-05-10 11:59 | 2026-05-14 | 2026-05-14 16:21 | 2026-05-15 | 2026-05-14 18:05 | 2026-05-15 | 2026-05-18 19:06 |  |  |  |  | 2026-05-20 16:40 | 2026-06-01 | 2026-05-31 18:33 | 2026-06-25 | 2026-06-23 20:25 | 2026-06-24 | 2026-06-24 17:51 | 2026-06-23 | 2026-07-09 11:24 | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-05-14 | 2026-05-20 16:39 | 2026-04-10 | 2026-04-08 18:25 | Site is Non-RTMI | 2026-03-21 | 2026-03-21 13:30 | 1448471 | 260724 | 0 | 0 | 1491408 | 268453 | 1491408 | 268453 | 2026-07-13 11:02:25 +0530 | Snehankit Agre | Execution: 13th Modular work started today. | 2026-07-06 23:58:16 +0530 | Snehankit Agre | Execution: First coat of paint completed on Saturday 4th july Carpentry work pending, depend on modular storage | 2026-07-02 00:22:47 +0530 | Snehankit Agre | Execution: Electrical work completed 8 june to 14 june Ceiling work completed 15 june to 20 june First coat painting in progress | 2026-04-09 | 2026-04-08 19:28 | 2026-04-25 | 2026-04-24 18:24
19002 | Turnkey | 2026-01-01 | Swati Jadhav | Mahavir Spring | MUM - Thane | Yes | Moksh Mehta | Anamika Dolai | [6 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1622724 | 9999 | 0 | 0 | 0 | 116 | 0 | 152273 | 162272 | 711914 | 586265.2 |  |  | 2026-03-21 | 2026-03-21 15:07 | 2026-03-22 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-22 |  | 2026-03-23 | [5 empty] | 2026-03-29 |  | 2026-04-06 |  | 2026-04-07 |  |  |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 | [6 empty] | 2026-05-05 |  | 2026-05-14 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-08 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-04-15 |  | 2026-03-24 |  | Unknown | 2026-03-21 | 2026-03-21 14:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1377686 | 245038 | [9 empty] | 2026-03-29 |  | 2026-04-05
19003 | Turnkey | 2026-01-01 | Dhanraj Mohan Jadhav | DEM Pheonix | MUM - GOR | Yes | Anjali Jain | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 878822 | 175764 | 1146739 | 0 | 0 | 15 | 0 | 0 | 0 | 364340 | 338718 |  |  | 2026-03-21 | 2026-03-24 19:28 | 2026-03-26 | 2026-03-26 18:59 | 2026-03-29 | 2026-03-26 19:48 | 2026-06-21 | 2026-06-18 19:33 | 2026-06-24 |  | 2026-07-01 |  | 2026-03-26 | 2026-03-28 14:53 | 2026-03-27 | 2026-03-30 13:46 | 2026-03-30 | 2026-03-30 18:24 | 2026-04-04 | 2026-04-04 19:25 |  |  |  |  | 2026-06-18 | 2026-06-30 12:58 | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-06-05 | 2026-06-18 19:07 | Site is RTMI | 2026-03-21 | 2026-03-24 19:28 | 971812 | 174926 | 0 | 0 | 0 | 0 | 946640.4585 | 158464 | 2026-07-07 13:38:41 +0530 | Manzoor Shaikh | Dear Mr. Dhanraj Mohan Jadhav, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 08th July at 11:00 AM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Anjali will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic â€¢ Material â€¢ Finishes â€¢ Selection of light fittings â€¢ Finalize kitchen accessories â€¢ Finalize appliances â€¢ Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-06-18 19:05:51 +0530 | Anjali Jain | DDM1 Transition Download As discussed with Pratima, A. Living Room Modular Unit are (Pre laminate) Â 1. Display unit Â 2. TV unit (Drawer is consider) B. Kitchen Semi Modular units are 1.Loft Cabinet -Â Â (laminate) 2.Base Unit 3 Drawers qty 1 (Wire basket), Bottel pull out qty 1,Â shutter (Semi modular units) (laminate) 3.Â Top cabinetÂ (6 units laminate) C. Kids Bedroom Modular unit are (Pre laminate) 1.Wardrobe with Loft (internals given basic) 2.Bed (Free box storage) D. Master Bedroom Modular unit are (Pre laminate) 1.Wardrobe with Loft (internals given basic) 2.Bed Bathroom & Toilet Additional Scope of Work 1.Electrical (25 NOS added in quotation- 26800) 2.False ceiling (200 sq.ft added in quotation) 3.Premium Emulsion (1000 sqft added in quotation which is wrong acc. to sqft) 4.Tractor Emulsion(538 sq.ft added in quotation) 5. Beading 10 nos.Â Others Cleaning Charges, Thinner Cleaning and Floor Cleaning - 2 BHK 6 to 10 Project Management feesÂ Celebrity Design feesÂ Transportation & Lifting ChargesÂ Floor Covering - 5 sqft DEM 1 Sofa is not added in the quotation (Offer from CRM free) Kids bedroom need to add study table Mirror needs to add in quotationmaster bedroom need to add mirror and dressing mandir need to add in the quotation False ceiling need to add in bedrooms also painting quantity need to update Decor parts need to add only moulding is consider in quotation for now | 2026-06-17 11:44:48 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-19 | 2026-06-18 19:43 | 2026-06-25 |  | Under Construction | 2026-05-31
19004 | Turnkey | 2026-01-01 | Komal Mahajan | Raymond GS | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Hold | Preproduction | Site Readiness 1 | 4121446 | 959999 | 4744716 | 0 | 0 | 8 | 71 | 0 | 0 | 1579310 | 1582136.8 |  |  | 2026-03-21 | 2026-03-21 21:52 | 2026-03-25 | 2026-03-26 13:58 | 2026-03-26 | 2026-03-26 22:51 | 2026-04-27 | 2026-04-27 15:38 | 2026-11-17 |  | 2026-11-24 |  | 2026-03-26 | 2026-03-28 15:39 | 2026-03-27 | 2026-03-28 19:13 | 2026-03-28 | 2026-03-30 12:28 | 2026-04-07 | 2026-04-07 15:01 |  |  |  |  | 2026-04-03 | 2026-03-28 15:39 | 2026-11-19 |  | 2026-11-20 |  |  |  | 2026-11-27 |  | 2026-11-28 |  | 2026-11-29 |  | 2026-11-30 | [6 empty] | 2026-12-18 |  | 2026-12-27 |  | 2026-12-26 |  | 2026-12-27 |  | 2026-12-28 |  | 2026-12-30 |  |  |  | 2027-01-21 |  | 2027-01-23 |  | 2027-01-24 | [5 empty] | 2026-11-28 |  | 2026-05-15 | 2026-04-27 13:48 | Site is Non-RTMI | 2026-03-21 | 2026-03-21 21:52 | 4020945 | 723770 | 0 | 0 | 0 | 0 | 3831733 | 689712 | 2026-07-10 19:05:24 +0530 | Divya Rahangdale | CX will receive the possession by October. | 2026-06-29 14:00:59 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: Possession is expected by Oct end | 2026-05-06 15:31:30 +0530 | Asavari Vare | Some Image was uploaded | 2026-04-28 | 2026-04-27 17:39 | 2026-11-18
19006 | Turnkey | 2026-01-01 | Ashutosh agarwal | 100 Trees | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Soumya KP | [5 empty] | Aman Kumar |  | Active | Preproduction | DEM2 | 1108637 | 221726 | 1254413 | 0 | 0 | 6 | 0 | 0 | 0 | 469533 | 417378.4 |  |  | 2026-03-21 | 2026-03-21 15:19 | 2026-03-30 | 2026-03-30 12:02 | 2026-04-02 | 2026-03-30 12:37 | 2026-05-14 | 2026-06-28 16:31 | 2026-07-11 |  | 2026-08-10 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-03 14:59 | 2026-04-03 | 2026-04-04 12:50 | 2026-04-12 | 2026-04-12 18:48 |  |  |  |  | 2026-07-05 | 2026-07-09 11:30 | 2026-08-05 |  | 2026-08-06 |  |  |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 | [6 empty] | 2026-09-03 |  | 2026-09-12 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-15 |  |  |  | 2026-10-07 |  | 2026-10-09 |  | 2026-10-10 | [5 empty] | 2026-08-14 |  | 2026-04-13 | 2026-05-10 19:18 | Site is RTMI | 2026-03-21 | 2026-03-21 15:19 | 1063062 | 191351 | 0 | 0 | 0 | 0 | 1218214.5128 | 201148 | 2026-05-25 11:08:57 +0530 | Priyanka Inchoor | Based on meeting, below is a list of all the requirements that were discussed during the meeting: Ashutosh DDM-2 Foyer unit Gypsum paneling with lighting, inside wallpaper and rafters with hanging light. Movable shoe rack will come here Entry left wall texture paint with golden strip option Tv unit design with rafter and lighting inside wallpaper beading design is sameÂ with 2 wall lights pooja unit- storage 1 drawer and one trayÂ No change in the ledge design false ceiling peripheral with curve edges Kitchen Tall unit design with oven option and wicker basket and at the bottom tandem box above sink dish drainer to be consider sink size is 30" in width, add wet and dry dustbin dining panel remains same need support from the floor (metal fabrication) next to hob unit change from shutter to single lift-up Guest bedroom Wardrobe internals pending Headboard design is finalized with wallpaper and paint option corner ledge as per the reff image need to be consider Electrical point need to be shift near to the ledges in the corner MBR Wardrobe internals are pending need safety locker headboard design remains same- beading Thank you | 2026-05-12 14:22:25 +0530 | Priyanka Inchoor | As discussed over the meeting, find the attached MOM Foyer area Foyer area with shoe rack provision with wall conceptÂ (Hanging light needed here) Living Room TV base cabinet with glass shutter (middle cabinet) No paneling required Provide wallpaper option instead for tv wall Wall Lights for TV wall consider False ceiling in living area Pooja design to be done as per the reference with curtain provision No changes in the display unit Guest Bedroom (GBR) Corner ledges with some storage Balcony design required need to provide some wall concept designs for Headboard wall Queen size cot needs to be consideredÂ Master Bedroom (MBR) Consider Folding study table opposite to bed wall L-shape dressing unit as well as wardrobe as per the reference image Queen size cot needs to be consideredÂ Kitchen Wicker basket is added in tall unit We had fixed meeting on 15th at 5.30pm | 2026-04-24 10:59:50 +0530 | Priyanka Inchoor | Some Image was uploaded | 2026-06-29 | 2026-06-28 16:36 | 2026-07-12 |  | Under Construction | 2026-06-30
19010 | Turnkey | 2026-01-01 | Aakash Gupta | RUNWAL FOREST | MUM - Thane | Yes | Rachna Abhyankar |  | Rushika More | [5 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 1981871 | 9999 | 0 | 0 | 0 | 115 | 0 | 188188 | 198187 | 847689 | 737807.6 |  |  | 2026-03-21 | 2026-03-22 03:35 | 2026-03-25 | 2026-03-27 19:15 | 2026-03-27 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-05-20 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-23 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-03-21 | 2026-03-21 16:09 | 0 | 0 | 0 | 0 | 0 | 0 | 1682678 | 299193 | 2026-03-22 21:25:17 +0530 | Rachna Abhyankar | Client Name - Mr Aakash GuptaÂ Property Type - New - 2BHKÂ - Runwal ForestÂ Possession - August 2026 Family - 2 Adults (Marries couple) Budget - 10-14L Theme - Modern GenÂ Foyer :-Â 1-Shoe rack + Safety DoorÂ 2- Less panelling Living Room:- 1- TV Unit - 65"Â 2- 2 Seater recliner sofa + 1 OttomanÂ 3- Mandir ( blinds as a shutter ) 4- Crockery Unit + Bar UnitÂ 5- Dining Table ( Bench + 2 chair ) 6- Sofa wall conceptsÂ 7- Decor wall at dining areaÂ Kitchen:- 1- Full Modular Kitchen (Base + Loft + Wall) option ( as kitchen counter they want to be in White - if cost is okay they will proceed with civil work) 2- Panelling to hide the shaft doorÂ Â Bedroom 01(Guest Bedroom):- 1- Compact Queen Bed with storage 2- Study + storage unitÂ 3- Full length mirrorÂ 4- wardrobe + Loft + Study Unit Master Bedroom:- 1- Wardrobe + LoftÂ 2- Queen size bed with storageÂ 3- Dressing Unit = Side tableÂ 4- Foldable study table Bathrooms:- 1-Both vanities will have upper cabinets 2- Shower partition Civil Requirements:- 1-False ceilingÂ 2-ElectricalÂ 3-PaintingÂ 4-Demolishing of kitchen Counter top ( if they select white countertop) DCM - Thursday 26th March ,2026 - 11 am | 2026-03-22 21:24:47 +0530 | Rachna Abhyankar | Client Name - Mr Aakash GuptaÂ Property Type - New - 2BHKÂ - Runwal ForestÂ Possession - August 2026 Family - 2 Adults (Marries couple) Budget - 10-14L Theme - Modern GenÂ Foyer :-Â 1-Shoe rack + Safety DoorÂ 2- Less panelling Living Room:- 1- TV Unit - 65"Â 2- 2 Seater recliner sofa + 1 OttomanÂ 3- Mandir ( blinds as a shutter ) 4- Crockery Unit + Bar UnitÂ 5- Dining Table ( Bench + 2 chair ) 6- Sofa wall conceptsÂ 7- Decor wall at dining areaÂ Kitchen:- 1- Full Modular Kitchen (Base + Loft + Wall) option ( as kitchen counter they want to be in White - if cost is okay they will proceed with civil work) 2- Panelling to hide the shaft doorÂ Â Bedroom 01(Guest Bedroom):- 1- Compact Queen Bed with storage 2- Study + storage unitÂ 3- Full length mirrorÂ 4- wardrobe + Loft + Study Unit Master Bedroom:- 1- Wardrobe + LoftÂ 2- Queen size bed with storageÂ 3- Dressing Unit = Side tableÂ 4- Foldable study table Bathrooms:- 1-Both vanities will have upper cabinets 2- Shower partition Civil Requirements:- 1-False ceilingÂ 2-ElectricalÂ 3-PaintingÂ 4-Demolishing of kitchen Counter top ( if they select white countertop) | 2026-03-21 23:35:23 +0530 | Aryan Singh | Some Image was uploaded | 2026-04-04 |  | 2026-04-11
19011 | Turnkey | 2026-01-01 | Balamurugan Akshayalakshmi | Priyanka Residency | BNG - HSR | Yes | Swati Rathod | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 1170002 | 9999 | 1170002 | 0 | 0 | 110 | 0 | 107001 | 117000 | 483402 | 452600 |  |  | 2026-03-21 | 2026-03-21 16:32 | 2026-03-25 | 2026-03-25 17:59 | 2026-03-27 | 2026-03-27 12:08 | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-05-20 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-23 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-03-21 | 2026-03-21 16:31 | 991527 | 178475 | 0 | 0 | 0 | 0 | 991527 | 178475 | 2026-03-25 17:26:54 +0530 | Ankita Agarwal | DCM: MOM Interior Design MeetingDate: 21.03.2026 Client Name: Mr. Balamurugan & Mrs. Akshaya Lakshmi Overall RequirementsTheme: NeutralBudget: 810 LakhsNext Design Meeting: To be scheduledLiving AreaTV unit with sliding shutters + tall storage (client reference shared)Rafters on one side with TV in niche areaStrip lighting around nichePuja unit beside TV unit on dining wall (reference shared)Requirement:Simple design solutions to conceal beam between Living & DiningKitchenLayout: Parallel kitchen (as per floor plan)OTG unit + wicker basketsTall unit with fixed shelves beside hobGranite countertopProvision for appliance socket pointsUtility AreaJanitor unit (cleaning storage)Master Bedroom (MBR)Wardrobes on both sides of bedWardrobe with hidden storageOverhead shelf above bed integrated with wall panelingWardrobe shutters in dual shade/texture finishInternal: Adjustable shelvesDresser unit with mirror inside shutterMBR BathroomMirror with storage behindMBR Washroom WallVanity unit + mirror with storageBedroom 2 (Parents Bedroom PBR)Wardrobe with grooved shuttersInternal: 12 adjustable shelvesBudget - 8-10LKH | [6 empty] | 2026-04-04 |  | 2026-04-11
19012 | Turnkey | 2026-01-01 | Jayita Roy | Karle Vario Homes | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Banka H Suthar | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Production | Dispatch Due | 1693548 | 1693548 | 2050776 | 0 | 1693548 | 5 | 6 | 0 | 0 | 0 | 0 |  |  | 2026-03-21 | 2026-03-31 18:17 | 2026-04-02 | 2026-04-02 11:41 | 2026-04-02 | 2026-04-02 12:31 | 2026-04-21 | 2026-04-21 18:39 | 2026-05-24 | 2026-05-23 12:36 | 2026-05-24 | 2026-05-24 10:48 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-06 11:30 | 2026-04-06 | 2026-04-07 12:05 | 2026-04-13 | 2026-04-13 09:13 |  |  |  |  | 2026-05-08 | 2026-05-23 12:23 | 2026-06-01 | 2026-05-23 13:46 | 2026-05-24 | 2026-05-23 13:47 |  |  | 2026-06-10 | 2026-06-11 14:45 | 2026-06-12 | 2026-06-13 12:11 | 2026-06-13 | 2026-06-16 19:40 | 2026-06-25 | 2026-06-26 15:47 |  |  |  |  | 2026-06-29 12:49 | 2026-07-07 | 2026-07-06 12:49 | 2026-07-09 | 2026-07-08 14:27 | 2026-07-08 | 2026-07-10 14:29 | 2026-07-08 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-13 | 2026-06-29 12:48 | 2026-04-22 | 2026-04-21 12:11 | Site is RTMI | 2026-03-21 | 2026-03-23 12:48 | 1737945 | 312830 | 0 | 0 | 1908694.7046 | 315159 | 1908694.7046 | 315159 | 2026-04-11 15:17:59 +0530 | Rhea Rathod | CDP: Living - TV unit with wall concept. The wall to be extended as a part of carpentry to accommodate dishwasher in the kitchen Kitchen - Full modular kitchen added Double door fridge- existing, hence the kitchen needs to be space planned accordingly. Granite added Dining - Wall concept Master bedroom - Wall concept Wardrobe with loft mirror bay window seater and l shaped study unit Master bedroom Bathroom - Vanity with mirror and shower partition added Common bathroom - Vanity with mirror and shower partition added Guest bedroom - Invisible bed - costing is added in the estimate. Custom work to be checked with the sourcing team. Full house false ceiling - Living, dining and bedrooms- added | 2026-04-07 12:05:06 +0530 | Bency Chacko | Possession - RTMI keys available and IMs can be done. The keys are given to a customer's friend. It should be collected from her The next meeting can be planned on the 19th, and the customer will be flying to Bangalore.(DEM 1) No on-site work or civil work is planned Clear with Quote, Offers and Timelines Clear with checklist and scope of work After DEM 1 closure, she can close the payments of 10% - 20-21st April | 2026-04-07 10:50:21 +0530 | Bency Chacko |  | 2026-04-22 | 2026-04-21 18:46 | 2026-05-24 | 2026-05-23 12:37 | RTMI
19013 | Turnkey | 2026-01-01 | Preetesh (Preeti) Shetty | Mahavir Spring | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1208209 | 9999 | 0 | 0 | 0 | 116 | 0 | 110822 | 120821 | 508906 | 457661.6 |  |  | 2026-03-21 | 2026-03-21 18:46 | 2026-03-21 |  | 2026-03-21 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-03-21 |  | 2026-03-22 |  | 2026-03-22 |  | 2026-03-23 | [5 empty] | 2026-03-29 |  | 2026-04-06 |  | 2026-04-07 |  |  |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 | [6 empty] | 2026-05-05 |  | 2026-05-14 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-17 |  |  |  | 2026-06-08 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-04-15 |  | 2026-03-24 |  | Unknown | 2026-03-21 | 2026-03-21 18:45 | 0 | 0 | 0 | 0 | 0 | 0 | 1023906 | 184303 | 2026-03-21 18:48:48 +0530 | Nishtha Valawalkar | 2 BHK Mahaveer Springs As per cx 10 t0 12L 13 to 14L expectation set by me on the gross table (Smart/select) Parents and son is going o stay. (Son's name is Preetesh Shety stays in Belgium who will connect online during CDP) | 2026-03-21 18:46:50 +0530 | Nishtha Valawalkar | Some Image was uploaded |  |  |  | 2026-03-29 |  | 2026-04-05
19014 | Turnkey | 2026-01-01 | Rahul Abhishek | Woodsvale (Villas) | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  | RaviKumar Battala | Nanda Kumar | Ranjith Kumar |  | Aman Kumar | Sunil Kumar S M | Active | Preproduction | 3D Sign off | 1776787 | 355357 | 2371042 | 1776787 | 0 | 1 | 18 | 0 | 0 | 768367 | 653063.2 |  |  | 2026-03-21 | 2026-03-21 17:46 | 2026-03-30 | 2026-03-30 13:55 | 2026-04-02 | 2026-03-30 14:20 | 2026-04-30 | 2026-04-26 17:56 | 2026-07-11 | 2026-07-10 19:50 | 2026-07-13 | 2026-07-11 12:02 | 2026-03-30 | 2026-03-31 10:19 | 2026-03-31 | 2026-04-03 19:37 | 2026-04-03 | 2026-04-06 16:26 | 2026-04-12 | 2026-04-12 19:00 |  |  |  |  | 2026-06-13 | 2026-06-13 16:02 | 2026-07-06 | 2026-07-07 13:56 | 2026-07-08 | 2026-07-07 13:59 |  |  | 2026-07-14 | 2026-07-14 19:29 | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-04-13 | 2026-04-26 17:51 | Site is Non-RTMI | 2026-03-21 | 2026-03-21 17:46 | 2009358 | 361684 | 2011038.71 | 332052 | 0 | 0 | 2011038.71 | 332052 | 2026-07-14 13:06:44 +0530 | Kiran Agarampalli |  | 2026-07-13 19:16:41 +0530 | Kiran Agarampalli |  | 2026-07-13 18:52:55 +0530 | Kiran Agarampalli |  | 2026-06-13 | 2026-06-13 15:55 | 2026-07-11 | 2026-07-10 20:01 | Under Construction | 2026-06-13
19015 | Turnkey | 2026-01-01 | Khushboo Kripashankar Pandey | DEM Pheonix | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 927934 | 9999 | 0 | 0 | 0 | 110 | 0 | 82794 | 92793 | 375005 | 367342 |  |  | 2026-03-21 | 2026-03-27 12:48 | 2026-06-30 | 2026-06-30 16:35 | 2026-05-05 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-03-21 | 2026-03-24 13:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1063319.9767 | 175578 | 2026-06-30 16:35:05 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-06-30 01:35:49 +0530 | Pratima Kajwe | CDP: SPOT CDP Mirror - 35k Wall Clock - 3k 2 Beds - 80k Side tables - 4k 2 Mattress - 25k Sofa Cum Bed - 40k Center Table - 5k Dining Table - 50k Mandir - 20k Shoe-rack - 15k Curtains - 30k Accessories - 5k Lights - 30k | 2026-04-14 16:50:44 +0530 | Saloni Sagwekar | Some Image was uploaded | 2026-07-11 |  | 2026-07-18
19016 | Turnkey | 2026-01-01 | smraddhi KHARE khare | Lodha Woods | MUM - GOR | Yes | Neha Yadav | Reshma Melanta | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Preproduction | DEM2 | 1195046 | 239009 | 1568457 | 0 | 0 | 37 | 10 | 0 | 0 | 536473 | 419564.4 |  |  | 2026-03-21 | 2026-03-21 21:05 | 2026-03-21 | 2026-03-22 12:17 | 2026-04-05 | 2026-04-08 14:55 | 2026-05-28 | 2026-05-28 14:03 | 2026-06-08 |  | 2026-06-15 |  | 2026-04-08 | 2026-04-17 11:32 | 2026-04-09 | 2026-04-24 12:22 | 2026-04-24 | 2026-04-25 17:00 | 2026-04-30 | 2026-04-30 14:21 |  |  |  |  | 2026-05-28 | 2026-06-08 18:45 | 2026-06-10 |  | 2026-06-11 |  |  |  | 2026-06-18 |  | 2026-06-19 |  | 2026-07-05 |  | 2026-08-08 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-06-19 |  | 2026-05-01 | 2026-05-28 13:58 | Site is RTMI | 2026-03-21 | 2026-03-21 18:48 | 1329200 | 239256 | 0 | 0 | 0 | 0 | 1327741.403 | 213947 | 2026-07-14 15:39:35 +0530 | Reshma Melanta | Others: CX IS WORKING IN TELEVISION INDUSTRY - WE SUPPOSE SHE HAS GOT A SPONCERSHIP FROM THE BRAND BUT THE SAME IS NOT SURE. THE QUOTATION OF THE CX INCREASED FROM NET TO DEM 1 AND THE CX IS NOT ALIGNED FOR THE SAME, SPOKE TO THE SISTER HAS WELL BUT NO ON IS ALIGN TO GO AHEAD WITH THE SAME AND IS ASKING FOR A REFUND, HAVE CLEALRY MENTIONED WE DONT HAVE REFUND HAS PER THE AGREEMENT NEEDED A AGREEMENT COPY WHICH IS SHARED IN THE GROUP TO THE CLIENT. MENTIONED THE CLIENT TO AVE A CALL WITH THE DESIGNER MANAGER TO CLEAR THE ISSUE BUT NO REVERT AND CX IS MENTIONED THAT THEIR WANT A REFUND AND DONT WANT TO GO AHEAD WITH BONITO. | 2026-06-21 15:34:45 +0530 | Neha Yadav | DDM 2 & 3 Meeting Discussion: Living : 1)Dining need to remove there will be seating instead & book storage with flutted glass shutterÂ 2)Tv open unit will be drawer & and need to add tv panelÂ 3)In ceiling there will be 2 fan & chendilear in center.Â 4)Kitchen wall cabinets will be in glass shutter 5)storage need to add in utility areaÂ 6)Bedroom 1 will have cane & wallpaper shutterÂ Feel free to add pointers if missed any. | 2026-06-07 11:19:56 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-29 | 2026-05-28 14:07 | 2026-06-09 |  | Under Construction | 2026-05-31
19017 | Turnkey | 2026-01-01 | Avinash | Ajmera Iris | BNG - HSR | Yes | Nayan Reddy |  | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 1469703 | 9999 | 0 | 0 | 0 | 116 | 0 | 136971 | 146970 | 590420 | 585342 |  |  | 2026-03-21 | 2026-03-21 18:39 | 2026-03-22 |  | 2026-03-25 |  | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-03-25 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-03-21 | 2026-03-21 18:37 | 0 | 0 | 0 | 0 | 0 | 0 | 1245511 | 224192 | 2026-04-22 18:37:11 +0530 | Patil Madhavi | Some Image was uploaded | 2026-03-26 14:52:14 +0530 | Nayan Reddy | DCM: Avinash(IT)/ Geetha(Homemaker) / Richie Reddy and Rinie Reddy 3BHK EAST FACINGÂ Shoe unit - in the entrance (Outside) Foyer - 3ft storage unit for 2cylinders space unit - gas piping will be taken from foyer Adj wall mirror wallpaper / texture paint Living TV wall - 1.5*7 ft tall unit, wallpaper/texture paint finish no base unit One shelf unit at 7ft height with tall unitÂ 3+2 existing sofa, in future planning for recliner sofa 3+2 sofa back wall - trims with wallpaper/texture paint / paintingsÂ 5ft jula provision if possible Dining - no crockery unit, only a seating storage of 5*2ft height, on wall planning for photo frames 6 seater dining table - full height tinted mirror on wallÂ Kitchen - L shape extend base unit till utility area 35inches wide fridge, microwave, mixer, single bowl sink In Utility 4ft long sink bowl in wall unit dish drainer req.and on opp wall dishwasher and washing machine one ledge and wall unit abv wall unit and loft in L shape including abv fridge Chimney hole need to check as there's a BM provision abv utility wall, under sink RO in utility NEED GROOVING IN GRANITE FOR WATER DRAIN Stand alone hob, 3ft MBR - Wardrobe swing / Aristo, Queen size bed facing towards south/headboard, Pooja unit 3ft in the corner, Dresser unit, concealed curtains are req.Janitor unit unit in balconyÂ BR1 - swing / Aristo wardrobe on adj wall of door, Queen size bed headboard on south Living Balcony - Pipes to be concealed - wooden lights as per ref. KBR - full length wardrobe bottom draws, full ht shutters no loft, TV unit space for dresser with storage, on the sides of bed need book shelf storage Architrave - near kitchen and foyer entrance to be curved if possibleÂ FC not req. only surface lights/track light full home, FC to be done only if req. Budget - 15lk Beige, white, grey, wood tones AJMERA IRIS - ELECTRONIC CITY JULY - soft handover/ dec |  |  |  | 2026-04-02 |  | 2026-04-09
19018 | Turnkey | 2026-01-01 | Monal Jain | Mahavir Spring | MUM - Thane | No Estimate | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 0 | 10000 | 0 | 0 | 0 | 113 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-21 | 2026-03-24 17:57 | 2026-03-22 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-04-29 |  | 2026-05-07 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-05-17 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-24 |  | Unknown | 2026-03-21 | 2026-03-24 16:38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-25 11:13:23 +0530 | Mustufa Sohagpurwala | Some Image was uploaded | 2026-03-24 11:08:42 +0530 | Mustufa Sohagpurwala | Some Image was uploaded |  |  |  | 2026-04-29 |  | 2026-05-06
19019 | Turnkey | 2026-01-01 | Hrishikesh V Belavadi | Independent Duplex | BNG - HRBR | Yes | Chandini Nj | Parasa Sri | Shibin Lal | [7 empty] | Hold | Preproduction | DEM2 | 2513763 | 641999 | 3214835 | 0 | 0 | 56 | 24 | 0 | 0 | 899118 | 972645.6 |  |  | 2026-03-21 | 2026-04-08 16:34 | 2026-04-08 | 2026-04-08 18:32 | 2026-04-11 | 2026-04-08 19:03 | 2026-04-26 | 2026-04-26 10:56 | 2026-08-05 |  | 2026-08-12 |  | 2026-04-08 | 2026-04-08 19:54 | 2026-04-09 | 2026-04-08 20:06 | 2026-04-08 | 2026-04-09 16:22 | 2026-04-12 | 2026-04-12 20:17 |  |  |  |  | 2026-04-13 | 2026-04-08 19:55 | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-04-13 | 2026-04-26 10:51 | Site is RTMI | 2026-03-21 | 2026-04-06 11:40 | 2724437 | 490398 | 0 | 0 | 0 | 0 | 2659614.8491 | 458943 | 2026-05-02 13:09:45 +0530 | Chandini Nj | Ground floorÂ UPS provision shoe rack key chain holder,Â newspaper helmets seater, cylinder provision accent wallÂ Kitchen - gas, chimney, sink, ro unit, crockery, fridge double door,Â pantry unit, microwave ovenÂ small appliances place, bar unit, Utility washing machine, dishwasher, double sink unit with drain board, broom cupboard,Â dustbin Invisible door for washroom common washroom vanity (optional) 2nd floor master bedroom walk in wardrobe Invisible door Dresser unit bed position lockerÂ study unit first floorÂ swing libraryÂ third floorÂ Study unitÂ swingÂ bedÂ bay seating storage media room Wradrobe tv unit study unit as per the final designs electrical points will be changed | 2026-04-23 12:29:02 +0530 | Parasa Sri | Some Image was uploaded | 2026-04-21 17:38:48 +0530 | Priyanka Gs | CDP: Recap: 19019 - Celebrity Design Presentation (CDP) with the customer 05 April ¦ Meeting ¦ Microsoft Teams CDP Recording | 2026-04-27 | 2026-04-26 10:58 | 2026-08-06 |  | Under Construction | 2026-10-21
19021 | Turnkey | 2026-01-01 | Aman Collection And Aman Enterprises ( Nitin Garg ) | Lodha Suprimo | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | Viraj Chavan | Viraj Chavan |  |  |  | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1342531 | 246962 | 1693502 | 0 | 0 | 30 | 10 | 0 | 0 | 577761 | 517808 |  |  | 2026-03-21 | 2026-03-24 18:34 | 2026-03-30 | 2026-03-30 14:06 | 2026-03-31 | 2026-03-31 22:31 | 2026-05-09 | 2026-05-09 20:15 | 2026-06-09 |  | 2026-07-08 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-04 02:23 | 2026-04-04 | 2026-04-04 15:44 | 2026-04-12 | 2026-04-12 14:55 |  |  |  |  | 2026-06-08 | 2026-06-15 18:01 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-04-13 | 2026-05-09 20:12 | Site is RTMI | 2026-03-21 | 2026-03-24 18:34 | 1435171 | 258330 | 0 | 0 | 0 | 0 | 1475438.8377 | 245598 | 2026-07-05 11:57:13 +0530 | Saif Shaikh |  | 2026-07-04 13:38:52 +0530 | Reshma Melanta | Others: | 2026-06-18 12:24:49 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-10 | 2026-05-09 20:15 | 2026-06-10
19022 | Turnkey | 2026-01-01 | Prajwal Shetty | Lodha Suprimo | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1334911 | 266982 | 1773301 | 0 | 0 | 39 | 0 | 0 | 0 | 581912 | 486016.8 |  |  | 2026-03-21 | 2026-03-24 18:33 | 2026-03-30 | 2026-03-30 13:32 | 2026-04-02 | 2026-04-02 11:45 | 2026-05-12 | 2026-05-12 19:18 | 2026-07-16 |  | 2026-07-23 |  | 2026-04-02 | 2026-03-30 18:52 | 2026-04-03 | 2026-03-31 17:11 | 2026-04-03 | 2026-04-02 11:19 | 2026-04-09 | 2026-04-09 12:47 |  |  |  |  | 2026-05-12 | 2026-06-06 13:17 | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 | [6 empty] | 2026-09-20 |  | 2026-09-29 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-02 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-27 | [5 empty] | 2026-08-31 |  | 2026-08-15 | 2026-05-12 19:14 | Site is RTMI | 2026-03-21 | 2026-03-24 18:33 | 1505084 | 268216 | 0 | 0 | 0 | 0 | 1503552.0756 | 242148 | 2026-05-26 11:22:30 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-20 13:50:22 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-13 16:23:06 +0530 | Vishakha Vaishnav | Tried calling the cx for the 10% due , however the cx didn't answered the call | 2026-05-13 | 2026-05-12 19:20 | 2026-07-17
19023 | Turnkey | 2026-01-01 | Risikesh Dubey | kalpatru vivant | MUM - GOR | Yes | Anjali Jain | Manzoor Shaikh | Kashmira Nerurkar |  |  | Nishant Jadhav | Sandeep Tiwari |  | Saloni Sagwekar | Siddhesh Gujrathi | Active | Preproduction | DEM2 | 1531411 | 219749 | 1427790 | 0 | 0 | 25 | 0 | 0 | 0 | 722828 | 588833.6 |  |  | 2026-03-21 | 2026-03-24 13:13 | 2026-03-22 | 2026-03-25 11:37 | 2026-03-22 | 2026-03-25 11:51 | 2026-04-27 | 2026-04-27 16:15 | 2026-06-19 | 2026-06-19 00:42 | 2026-07-21 |  | 2026-03-26 | 2026-03-26 18:37 | 2026-03-27 | 2026-03-26 19:32 | 2026-03-26 | 2026-04-01 11:13 | 2026-04-04 | 2026-04-04 19:11 |  |  |  |  | 2026-04-27 | 2026-05-08 19:09 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 | [6 empty] | 2026-09-07 |  | 2026-09-16 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-19 |  |  |  | 2026-10-11 |  | 2026-10-13 |  | 2026-10-14 | [5 empty] | 2026-08-18 |  | 2026-04-05 | 2026-04-27 12:57 | Site is RTMI | 2026-03-21 | 2026-03-21 20:12 | 1212278 | 215511 | 0 | 0 | 0 | 0 | 1606460.275 | 265257 | 2026-05-30 15:52:21 +0530 | Manzoor Shaikh | Dear Mr. Risikesh Dubey, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 1 meeting for 31st May at 10:30 AM at Andheri EC. The agenda for this meeting will be to discuss the DEM 2 with our designer, Anjali will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-05-07 13:13:49 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-30 16:22:23 +0530 | Meet Shah | Some Image was uploaded | 2026-04-28 | 2026-04-27 16:24 | 2026-06-20 | 2026-07-05 11:36
19024 | Turnkey | 2026-01-01 | Sudipto Paul chowdhury | Lodha Woods | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera | [5 empty] | Umang Shah |  | Hold | Preproduction | DEM2 | 1066664 | 213333 | 1287759 | 0 | 0 | 12 | 13 | 0 | 0 | 426665 | 426665.6 |  |  | 2026-03-21 | 2026-03-21 20:04 | 2026-03-26 | 2026-03-31 20:12 | 2026-04-02 | 2026-04-02 14:16 | 2026-06-12 | 2026-06-12 17:00 | 2026-09-19 |  | 2026-09-26 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 18:12 | 2026-04-03 | 2026-04-03 11:55 | 2026-04-11 | 2026-04-11 14:19 |  |  |  |  | 2026-06-12 | 2026-06-20 18:00 | 2026-09-21 |  | 2026-09-22 |  |  |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-02 | [6 empty] | 2026-10-20 |  | 2026-10-29 |  | 2026-10-28 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-11-01 |  |  |  | 2026-11-23 |  | 2026-11-25 |  | 2026-11-26 | [5 empty] | 2026-09-30 |  | 2026-04-12 | 2026-06-12 16:46 | Site is RTMI | 2026-03-21 | 2026-03-21 20:04 | 1091321 | 196437 | 0 | 0 | 0 | 0 | 1084354.925 | 187118 | 2026-07-02 17:41:03 +0530 | Vishakha Vaishnav | Others: CX WILL GET POSSESSION BY SEPTEMBER END | 2026-06-17 16:07:19 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-12 16:15:06 +0530 | Karan Chavda | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion Based on meeting, below is a list of all the requirements that were discussed during the meeting: Mr. Sudipto paul Minutes of MeetingÂ Â Â Living roomÂ 1. Double shutter tallÂ Â 2. 6" gap between shoe rack and crockeryÂ 3. Shoe rack outsideÂ 4. Tv side unit full glass (custom) or only shutter glass (modular) to be decidedÂ 5. Existing dining 4x2.5.Â 8. Use colour blocking in living roomÂ 9. Only panelling in tv unitÂ 10. Cx asked for glass tall unitsÂ 11. Ask for lock in glass shuttersÂ 12. Use drawers as steps for mandirÂ 13. Mor pankh sticker on mandir side panel near diningÂ 14. Peripheral with track light ceilingÂ 15. Ac pelmet neededÂ KitchenÂ 1. Loft on stove sideÂ 2. No false ceilingÂ Master bedroomÂ Â 1. Used clothes tall unit beside glass tall unitÂ 2. No false ceilingÂ Guest bedroomÂ 1. Double shutter glass tall unitÂ 2. No false ceilingÂ Â * Glass partitions were discussed but not in quotation.Â * Mandir partitions not included in quote.Â * Glass Tall unit were asked during first meeting.Â Â Â For net designerÂ Living RoomÂ 1. No top panel and handle for crockeryÂ 2. Glass parttions were discussed but not in quotationÂ 3. Mandir patitions not included in quoteÂ 4. No top panel in mandir unitÂ 5. Sides not coloured for any unitÂ Â Â Master bedroomÂ 1. No fillers givenÂ 2. No handle for lofts givenÂ Â 3. No handle for tall unitÂ Â Â Master bedroom 2Â 1. No fillers givenÂ Â 2. No handle given for tall unitÂ 3. No handle for loft unitsÂ Â Â KitchenÂ Â 1. No internal shelves given for base unit service platformÂ 2. Add loft on stove sideÂ Â Â Glass parttions were discussed but not in quotationÂ Mandir patitions not included in quoteÂ Â Â No handles for vanities | 2026-06-13 | 2026-06-12 17:04 | 2026-09-20
19025 | Turnkey | 2026-01-01 | Neha Singh | Brigade Calista | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 900496 | 9999 | 0 | 0 | 0 | 116 | 0 | 80051 | 90050 | 360198 | 360198.4 |  |  | 2026-03-21 | 2026-03-21 20:59 | 2026-03-22 |  | 2026-03-25 |  | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-07-27 |  | 2026-03-26 |  | 2026-03-26 |  | 2026-03-27 | [5 empty] | 2026-04-02 |  | 2026-04-10 |  | 2026-04-11 |  |  |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-21 | [6 empty] | 2026-05-09 |  | 2026-05-18 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-21 |  |  |  | 2026-06-12 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-04-19 |  | 2026-03-28 |  | Unknown | 2026-03-21 | 2026-03-21 20:58 | 0 | 0 | 0 | 0 | 0 | 0 | 763132 | 137363 | 2026-03-23 14:27:27 +0530 | Preksha Sajjanshettar | Some Image was uploaded | 2026-03-23 14:27:04 +0530 | Preksha Sajjanshettar | Some Image was uploaded | 2026-03-23 14:22:45 +0530 | Preksha Sajjanshettar | RGM Interior Design BriefClient: Neha Singh PID: 19025 Date: 22-03-2026 Possession: September 2026 Family: 2 Adults + 11-month-old child Occupation: IT Facing: East Budget: 10 Lakhs Design Preference: Soft, muted tonesAvoid bright & neon colorsFunctional + minimal + warmLIVING ROOMLayout: Sofa: 3+1+1 OR Recliner setupMaintain circulation space (baby-friendly)Key Elements: TV Unit: Base cabinet + ledge + wallpaper backdropSofa Wall:Option 1: Subtle wallpaperOption 2: Panel moulding / fluted panelSoft furnishings in muted tonesDINING AREADesign Plan: Toilet Wall: Family photo collage (grid layout)Bedroom 1 Wall:Crockery unit + integrated pooja unit with seatingDining Table: 6-seater (future consideration)Jhula (Swing):Position near window/living-dining transitionEnsure ceiling support feasibilityKITCHEN + UTILITYKitchen Plan: Simple, highly functional layoutNeutral laminates (no glossy bright finishes)Must-Haves: Pantry tall unitUnder-mount ROStandard fridge spaceEfficient drawer storageUtility: Sink + washing machineCheck partition option (glass/sliding) between kitchen & utilityMASTER BEDROOMDesign Plan: Existing King size bed retainedKey Elements: Wardrobe: Openable shuttersStudy: At window (natural light)Dresser: Beside bedFeature Walls:Bed back: Upholstered / panel designOpposite wall: Wallpaper / textureBEDROOM 1 KIDS ROOMDesign Plan: Queen size bedFoldable study unit (space-saving)Openable wardrobeWall Treatments: Bedhead wall: Soft playful panel/wallpaperStudy wall: Functional + pinboard / writable surfaceSafety Focus: Rounded edgesSoft finishesNo sharp projections | 2026-04-02 |  | 2026-04-09
19026 | Turnkey | 2026-01-01 | Mr.Prashant Kuckian | DEM Pheonix | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1206957 | 9999 | 0 | 0 | 0 | 116 | 0 | 110697 | 120696 | 536305 | 429260.4 |  |  | 2026-03-21 | 2026-03-21 21:53 | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-04-06 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 | [6 empty] | 2026-05-13 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-25 |  |  |  | 2026-06-16 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-04-23 |  | 2026-04-01 |  | Unknown | 2026-03-21 | 2026-03-21 21:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1025132 | 181824 | 2026-03-27 15:00:08 +0530 | Karuna Shinde | Some Image was uploaded | 2026-03-27 14:58:18 +0530 | Karuna Shinde | DCM: Client Name: Prashant Kuckian Property: Piramal Vaikunth Configuration: 467 sq.ft Possession: July Profession: Service Family Size: 3 Members Couple Baby (1 year old) SCOPE OF WORK Modular furniture Painting Decor False ceiling (Living Room only) Vastu Consideration: Yes Theme Preference: Modern Luxury Budget Planned: 8 12 Lakhs CDP Meeting: 29th March, 3 PM (Sunday) AREA-WISE REQUIREMENTSLiving Room Shoe rack in niche TV unit with mandir integration 2-seater sofa-cum-bed Puffy seating Foldable dining option Standing lamp Indoor plants Kitchen Base unit Tall unit (pantry) Appliances: Microwave Mixer Chimney RO Master Bedroom Wardrobe with loft Bed Dresser Wallpaper Study / Multi-purpose Room Platform bed or single bed (as per space) Storage for baby essentials | 2026-03-21 21:54:23 +0530 | Anant Giri | Some Image was uploaded | 2026-04-06 |  | 2026-04-13
19027 | Turnkey | 2026-01-01 | Mr.Jitendra Sahoo | Park East by Ruchira | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Design | 20% Payment | 1398027 | 189999 | 1801935 | 0 | 0 | 35 | 12 | 0 | 89606 | 594095 | 524326.4 |  |  | 2026-03-21 | 2026-03-25 19:12 | 2026-03-22 | 2026-03-26 11:21 | 2026-03-27 | 2026-03-27 20:05 | 2026-05-29 | 2026-05-29 21:58 | 2026-08-06 |  | 2026-08-13 |  | 2026-03-27 | 2026-03-28 15:55 | 2026-03-28 | 2026-03-29 13:33 | 2026-03-29 | 2026-03-30 18:10 | 2026-04-03 | 2026-04-03 22:48 |  |  |  |  | 2026-06-10 |  | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-17 |  | 2026-04-04 | 2026-05-29 21:52 | Site is RTMI | 2026-03-21 | 2026-03-21 21:10 | 1527064 | 274871 | 0 | 0 | 0 | 0 | 1484556.845 | 250648 | 2026-05-29 22:25:43 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 24/05/2026 Title: DEM 1 Project: 19027 Client: Jitendra Sahoo Attendees: Designer Objective: DEm1 Discussion Based on 24/05/2026 meeting, below is a list of all the requirements that were discussed during the meeting: 1. Shoe size has to be change (5feet height unit + one seater) 2. Entrance partition has to give with combination of Metal and glass (design not yet finalized) 3. Pooja unit width has to be increase to 2 feet to 3 feet 4. Inside the pooja unit has to give provision for keeping Idol , both side 3 ledges has to provide 5. as we discussed, has to provide option for seater in pooja unit ( designs are not yetÂ finalized) 6. Tv Unit has to design with storage for keeping books and decor 7. Tv unit base cabinet has to plan as per the site condition- as per electrical points 8. False ceiling design has to be consider 9. as discussed, wall concepts will be discussing once the Initial measurement are taken - as its Mivan construction, need to check electrical pointsÂ 10. Crockery and vanity unit has to be design with storage and bevelled mirror has to place for the back splash 11. Need to check about the plumbing point at site and need to design accordingly 12. Kitchen Appliances placements are same- need to discuss in detail once the measurements are takenÂ 13. KBR- Has to re design ( need to include queen size bed, study table 4 feet width , wardrobe and one more storage, and false ceiling) 14. MBR- as per discussion , dresser has to be changed 15. King size bed has to consider in MBR 16. study table in MBR is CX scope 17. Wall concept for the MBR are not yet discussedÂ 18. False ceiling has to be consider in MBR ( Lighting Purpose) 19. PBR- Wardrobe placements are sameÂ 20. Long mirror has to place with minimal storage 21. Study table has to place opposite to bed wall 22. Queen size bed has to consider in PBR 23. Passage area - has to give bottom storage up to 4 feet and above that need to plan for family photo frame wall 24. opposite to photo frame wall- need to design with modern photo frame note: Wall concepts are not yet finalized as its mivan constructionÂ styleÂ cant able to move any electrical points | 2026-05-24 19:43:32 +0530 | Vishal Bandi | Silver coin received | 2026-05-08 11:19:43 +0530 | Parasa Sri | Client will be visiting for DEM-1 on 15th may | 2026-05-30 | 2026-05-29 22:23 | 2026-08-07 |  | Under Construction | 2026-07-31
19028 | Turnkey | 2026-01-01 | Kumar Love | Abhee Riviera Royale | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1640223 | 169999 | 2370383 | 0 | 0 | 71 | 0 | 0 | 158046 | 716080 | 596098 |  |  | 2026-03-21 | 2026-03-21 21:43 | 2026-04-30 | 2026-04-30 15:06 | 2026-05-03 | 2026-04-30 16:00 | 2026-08-09 |  | 2026-09-10 |  | 2026-09-17 |  | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-01 21:01 | 2026-05-01 | 2026-05-05 17:56 | 2026-05-15 | 2026-05-15 19:02 |  |  |  |  | 2026-08-10 |  | 2026-09-12 |  | 2026-09-13 |  |  |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 | [6 empty] | 2026-10-11 |  | 2026-10-20 |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-23 |  |  |  | 2026-11-14 |  | 2026-11-16 |  | 2026-11-17 | [5 empty] | 2026-09-21 |  | 2026-08-05 |  | Unknown | 2026-03-21 | 2026-03-21 21:38 | 2008799 | 361583 | 0 | 0 | 0 | 0 | 1974955.4089 | 326093 | 2026-05-15 19:01:10 +0530 | Abhinandan K S | Possession- August 2026 Initial measurements can be taken once the Builder allows us. Customer has agreed to make the payment of DEM 1 - 10% only if we show significant progress. Customer is informed about the process, terms and conditions. Customer is ok with the Offers and the Net quote. DD1 is planned on 16th May 2026. DD2 to be planned once the DD1 is completed. Customer personally knows our Chairman Mr. Abhinandan Lodha and we will have take utmost care during the course of the project. | 2026-05-05 17:56:15 +0530 | Bency Chacko |  | 2026-05-05 17:02:37 +0530 | Bency Chacko |  | 2026-08-10 |  | 2026-09-11 |  | Under Construction | 2026-09-30
19029 | Turnkey | 2026-01-01 | Mrs. Prabhavathi | MJR Divine Meadows | BNG - HSR | Yes | Priyamvada PV |  | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1605875 | 9999 | 1605875 | 0 | 0 | 116 | 0 | 150589 | 160588 | 642350 | 642350 |  |  | 2026-03-21 | 2026-03-21 21:38 | 2026-04-05 | 2026-04-21 15:31 | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-04-29 |  | 2026-05-07 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-24 |  | Unknown | 2026-03-21 | 2026-03-21 21:36 | 1360911 | 244964 | 0 | 0 | 0 | 0 | 1360911 | 244964 | 2026-04-29 18:08:20 +0530 | Priyamvada PV | Prabhavathi - 4ppl (parents might stay sometimes) Â G+2:Villa ,MJR Divine meadows, sarjapura chikkatirupati main road Possesion-by april end (tentative) Movin-Once the interiors are done Prof. - IT/Mam artistÂ Indo western theme / earthy tones Budget : 12-15LK Ground floor : Main Door - West FacingÂ Deck area- sitout space for livingÂ Living room: wall mounted tv unit , back panelling with ply backing or wallpaper(traditional theme) or trims Sofa back wall trims and wall paintings (frames) FC in living & Dining area to be considered Dining area - One fixed glass & one door provision is givenÂ 6 or 4 seater as per the space Lift space - crockery unit , (can plan for a small tall unit) Pooja unit req, on adj to TV wall Kitchen- Kitchen entrance wall to be demolished for breakfast counter , Arch panelling to be provided with hanging lights one panty unit , tall unit for appliances, u shaped Counter , parallel liner counter Electrical Appliances ; Fridge, microwave, RO unit, mixer, Dish washer-not yet confirmed Utility area - Tall unit for mop storage GBR- Left side Granite with vanity unit Under staircase need to plan for dcor space, water fountain Dining area bathroom wall - wall panellingÂ GBR - wardrobe & loft, Queen size bed, Study table in the corner - reading desk , Bed back wall - textured wallpaper finish Bathroom - Glass partition with door, vanity unit , mirror Stairs - wall designs, wall lights First Floor Living area - No TV unit , wall designs to be done, just a common area Bedroom - 1 , Queen size bed, bed back wall with texture paint / wallpaper, wardrobe & loft, Mirror on side panel of wardrobe , study space in the corner Bathroom - Glass partition with door, vanity unit , mirror Study Room / Work Space : Opp to door - Tall unit with study table, 2 drawersÂ MBR - King size bed, wall panelling with lighting, gypsum panelling Walk In wardrobe , other wardrobe to be planed & loft, TV unit/PartitionÂ Bathroom - Glass partition with door, vanity unit , mirror Balcony - wall planting ....sit outÂ FC IN MBR Second floor- HOME THEARE / ART STUDIO ROOMÂ : either give a partition for bothÂ Wallpaper / texture - frames Â Lounge Area - Storage space , sit out | [6 empty] | 2026-04-29 |  | 2026-05-06
19030 | Turnkey | 2026-01-01 | Swetha Priya | Engrace 4 | BNG - HSR | Yes | Ankita Agarwal | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1953172 | 9999 | 0 | 0 | 0 | 116 | 0 | 185318 | 195317 | 781269 | 781268.8 |  |  | 2026-03-21 | 2026-03-21 21:36 | 2026-03-22 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-21 | 2026-03-21 21:35 | 0 | 0 | 0 | 0 | 0 | 0 | 1655230 | 297941 | 2026-04-11 13:05:34 +0530 | Ankita Agarwal | DCM: BUDGET - 18LKH | 2026-03-26 15:52:16 +0530 | Ankita Agarwal | DCM: MOM Interior Design MeetingDate: 26.03.2026 Client Name: Swetha Priya / Abhishek Project: Engrace 4 by Modern Spaaces Flat No.: 216, Second Floor Configuration: 3BHK Profession: IT Family Members: 2 Facing: North-facing entrance Budget: 1213 Lakhs Possession Timeline: Flooring Completion: 01.06.2026Expected Possession: September 2026 (Tentative)Design ThemeModern Indian / MinimalistColor Palette: Walnut Brown with subtle neutral tonesEntrance AreaShoe storage unit outside entranceFoyer Area3 ft storage unit (footwear, helmets, dcor like Buddha idol)Seating storage: 23 ftWall Design Options:Texture paint / wallpaperWall paintingsTrack lightingLiving RoomSofa Area3+2 seater sofaPlacement: Centered, ~12 ft from TV unitWall Behind Sofa:Existing pooja unit to be redesignedTextured wall finishOption for reading corner / workstationTV Unit WallWall-mounted TV unitTall unit with glass shuttersFull-height plain wall paneling (matte finish)No louvers / no fluted panelsFinish: Plain FCBalcony (Living)Wall dcor elementsDining Area6-seater dining tableCrockery Unit:Base + wall unitsGlass shutters (with wine glass holders)7 ft tall unitLoft aboveKitchenLayout: U-shaped kitchenAppliances to AccommodateDouble door fridgeMicrowaveAir fryerSandwich makerMixerInductionDishwasherWashing machineChimneyRO systemGas cylinder storageDesign RequirementsHob unit on east wall (right side)Linear wall unitsPantry unit + tall unit (to be checked)RO unit integrationU-shaped loftsDishwasher + sink placement to be finalizedNon-standard countertopUtility AreaGranite counter with storageSeparate top-load washing machine provisionOverhead wall storage unitsBedroom 1 (Master Bedroom)Wardrobe behind door with loft + internal lockerKing-size bedBed-back wall:Highlight with stencil art / block paintDresser on right side of bedL-shaped wardrobe with workspaceBalcony storage (if wall permitted)Bedroom 2Wardrobe with loftL-shaped dresser unitOpposite wall: Study unit with wall storageBathroomMirror cabinet with storageFixed shower partitionBedroom 3Wardrobe with loftDresser on left side of bedCommon BathroomCorner storage unit (right wall)Fixed shower partitionBalcony (Bedroom 3 - B3)Janitor/storage space on bedroom wallFlooringMosaic tiles in living room & balconyGeneral SpecificationsPlain FC finish across home4-inch skirtingCeiling fan in kitchenÂ |  |  |  | 2026-04-05 |  | 2026-04-12
19031 | Turnkey | 2026-01-01 | Darshit Jain | Regency Luxuria | MUM - Thane | No Estimate | Moksh Mehta | Anamika Dolai | [6 empty] | Anjan Kumar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-21 | 2026-03-22 11:11 | 2026-03-22 |  | 2026-03-24 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-03-24 |  | 2026-03-25 |  | 2026-03-25 |  | 2026-03-26 | [5 empty] | 2026-04-01 |  | 2026-04-09 |  | 2026-04-10 |  |  |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-20 | [6 empty] | 2026-05-08 |  | 2026-05-17 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-20 |  |  |  | 2026-06-11 |  | 2026-06-13 |  | 2026-06-14 | [5 empty] | 2026-04-18 |  | 2026-03-27 |  | Unknown | 2026-03-21 | 2026-03-22 11:08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-22 12:29:39 +0530 | Anant Giri | Some Image was uploaded | [6 empty] | 2026-04-01 |  | 2026-04-08
19032 | Turnkey | 2026-01-01 | Sanjeev mishra | Raymond Address Season 1 | MUM - Thane | Yes | Pooja Nakul Sharma | Anamika Dolai | [6 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 11315269 | 9999 | 0 | 0 | 0 | 115 | 0 | 1121528 | 1131527 | 4946615 | 4105600 |  |  | 2026-03-21 | 2026-03-22 03:34 | 2026-04-02 |  | 2026-04-16 |  | 2026-04-23 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-17 |  | 2026-04-18 | [5 empty] | 2026-04-24 |  | 2026-05-02 |  | 2026-05-03 |  |  |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 | [6 empty] | 2026-05-31 |  | 2026-06-09 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-12 |  |  |  | 2026-07-04 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-05-11 |  | 2026-04-19 |  | Site is RTMI | 2026-03-21 | 2026-03-21 23:51 | 0 | 0 | 0 | 0 | 0 | 0 | 9589211 | 1726058 | 2026-04-17 15:51:04 +0530 | Pooja Nakul Sharma | DCM: PID 19032 Sanjeev MishraÂ Mr Rahul and Neha MishraÂ Penthouse : 5500 sq ft approxÂ Property name : Address by GS (Raymond Realty) Floor/flat no : Tower : BÂ Possession: May/ June 2026 Family : Couple (Rahul and Neha), Parents (Sanjeev and his wife), 1.5 yr/o daughterÂ Profession: Husband- Advocate, Wife- YoutuberÂ Theme preference: European countryside vintage/ Hollywood modern luxury (Dark wood, dark grey colour preference) Requirements :Â 1. Foyer area - To be grand/ luxuryÂ - Lion/ Elephant statue can be planned as per vastuÂ - Main/ Safety door will be double door - No shoerack at the entrance - Mirrors can be used - Need a console table at the entrance - Need a diffrential flooring, B/W with inlay 2. Living Room - Piano can be planned in family areaÂ - One common bathroom can be demolished and taken into the living room - Need to have a space dedicated to bike display (BMW model, one of a kind in India) - Need to plan work area for husband (Rahul), which is also near the bike display area - Need a grand TV wallÂ - Crockery can be accomodated if space permits, or a console can also be planned near dining.Â - Dining to be 8-10 seater - Puja area/ room to be planned in lower floor itself along will different type of flooring (Can have kamdhenu pictures on wall)Â 3. Servant roomÂ - Need to have dedicated servant room for 24/7 househelp and for 2 persons. Bunk bed can also be planned.Â - Basic requirements like wardrobe and bed for 2 people can be accomodated.Â 4. Kitchen - All standard appilances will be used (Dishwasher, washing machine, refrigerator (double door), Microwave oven/ OTG, mixer, etc.) - Need to plan proper groceries storage. - One sink in main kitchen (to wash vegetables) and one will be in utility area (For washing utensils).Â - Store room attached with kitchen will be used for groceries storage - Island is already given by the builder.Â 5. Guest bedroom (left of the entry) _Lower level - Door can be modified accordingly. - Basic storage and furniture to be planned.Â 6. Guest bedroom 2 (Daughter in law's bedroom) _Lower level - Will be visiting occasionally - Bed, wardrobe, Tv unit, dresser to be planned.Â - Bathroom vanity to be planned. 7. Below, near staircase can be highlighted, (planters reference was showed) 8. Client wants to plan a play area for kidsÂ 9. Parents bedroom (left of the staircase)- Upper level - King bed, walk in wardrobe with dresser, study/ work area, Tv unit/ provision.Â - Father (Mr Sanjeev) is also a lawyer/ advocate by profession. 10. Guest bedroom 3 - Upper level - Basic storage and furniture to be planned.Â - Client wants to keep it as a normal additional bedroom only. 11. Gym area - Can be planned efficiently with steam room attached. 12. Daughter's bedroom (1.5 yr/o) - Bunk bed is preferred by client for a playful, interactive design. Can also plan an activity wall like climbing ropes, pull bars etc.Â - Bunk bed is also asked as per future second baby planning so client wants to have same bedroom for them.Â - Dresser/ study/ wardrobe to be planned as per future use.Â 13. MBRÂ - To have a walk in wardrobe with big dresser and space for bags and shoes.Â - King bed, wardrobes, Tv wall to be planned.Â - To have a luxury/ grand vibe.Â - Bathtub to be planned in bathroom, hence bathroom can be modified accordingly.Â 14. Budget- 1.5 CrÂ | 2026-03-25 14:01:36 +0530 | Aryan Singh | Some Image was uploaded |  |  |  | 2026-04-24 |  | 2026-05-01
19033 | Turnkey | 2026-01-01 | Gautam Pawar | The Icon | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-21 | 2026-03-22 03:34 | 2026-03-22 |  | 2026-03-30 |  | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Unknown | 2026-03-21 | 2026-03-22 01:03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-07 |  | 2026-04-14
19035 | Sub Project |  | Manoj Kanathe | MXOthers | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Shibin Lal | [7 empty] | Active | Preproduction | DEM2 | 99348 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 59609 | 39739.2 |  |  | 2026-03-22 | 2026-03-28 16:02 | 2026-03-23 | 2026-03-28 16:03 | 2026-03-28 | 2026-03-28 16:03 | 2026-03-29 | 2026-03-28 16:04 | 2026-04-01 |  | 2026-04-08 |  | 2026-03-28 | 2026-03-28 16:03 | 2026-03-29 | 2026-03-28 16:03 | 2026-03-28 | 2026-03-28 16:03 | 2026-03-29 | 2026-03-28 16:03 |  |  |  |  | 2026-03-28 | 2026-03-28 16:06 | 2026-04-03 |  | 2026-04-04 |  |  |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-14 | [6 empty] | 2026-05-02 |  | 2026-05-11 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-14 |  |  |  | 2026-06-05 |  | 2026-06-07 |  | 2026-06-08 | [5 empty] | 2026-04-12 |  | 2026-03-29 | 2026-03-28 16:03 | Unknown | 2026-03-22 | 2026-03-28 16:02 | 0 | 0 | 0 | 0 | 0 | 0 | 84193 | 15154 | [9 empty] | 2026-03-29 | 2026-03-28 16:04 | 2026-04-02
19036 | Turnkey | 2026-01-01 | Rahul Valmiki | Kalpatru shrishti namah | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 820820 | 9999 | 0 | 0 | 0 | 96 | 0 | 72083 | 82082 | 369565 | 287091.2 |  |  | 2026-03-21 | 2026-04-10 13:57 | 2026-03-22 |  | 2026-04-01 |  | 2026-04-08 |  | 2026-04-15 |  | 2026-04-22 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-04-09 |  | 2026-04-17 |  | 2026-04-18 |  |  |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 | [6 empty] | 2026-05-16 |  | 2026-05-25 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-28 |  |  |  | 2026-06-19 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-04-26 |  | 2026-04-04 |  | Unknown | 2026-03-21 | 2026-03-22 12:14 | 0 | 0 | 0 | 0 | 0 | 0 | 989417.731 | 154061 | 2026-04-15 13:53:56 +0530 | Moni Sahani | Some Image was uploaded | 2026-03-27 13:03:39 +0530 | Sahil Sethi | User ResponseCustomer and Project Profile1. Name of the customer Rahul 2. Profession job 3. Project Name/Tower Name/Flat Number 1bhk 4. Typology (1BHK, 2BHK, 3BHK, etc) 1bhk 5. Site Access Date 2026-04-15 6. Possession Date 2026-04-15 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 8 Customer Preferences8. Who will be living in the house? 9. What activities do you usually prefer at your home ? 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials 15. Do you have any existing furniture that must be accommodated? 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? 2. Must-have furniture or features? 3. Choose your decor inspirations 4. False ceiling required Dining & Kitchen1. Any special furniture? 2. Must-have appliances? 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type 2. Master Bedroom - Wardrobe style 3. Master Bedroom - Additional units 4. False Ceiling Required - Master Bedroom 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? NA 3. What are your requirements for Utility Area? NA Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Sig |  |  |  | 2026-04-09 |  | 2026-04-16
19040 | Turnkey | 2026-01-01 | Ganesh Kadam Kadam | BDD Redevelopment, worli | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Shashwat Joshi | Rizwan Mistry | Murali S | Foram Joshi | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 1541008 | 1541008 | 1877885 | 0 | 1541008 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-22 | 2026-03-31 22:07 | 2026-03-22 | 2026-03-31 22:08 | 2026-04-03 | 2026-03-31 22:09 | 2026-04-18 | 2026-04-15 20:25 | 2026-04-22 | 2026-04-21 11:41 | 2026-05-22 | 2026-05-22 17:10 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 16:29 | 2026-04-03 | 2026-04-07 17:26 | 2026-04-09 | 2026-04-09 12:58 |  |  |  |  | 2026-04-15 | 2026-04-19 15:33 | 2026-05-01 | 2026-04-30 21:01 | 2026-05-07 | 2026-05-08 10:14 |  |  | 2026-05-23 | 2026-06-03 14:03 | 2026-06-04 | 2026-06-04 22:59 | 2026-06-05 | 2026-06-05 13:08 | 2026-06-06 | 2026-06-09 19:21 |  |  |  |  | 2026-06-14 16:06 | 2026-07-13 | 2026-06-26 20:50 | 2026-07-06 | 2026-07-06 19:33 | 2026-07-05 | 2026-07-10 12:02 | 2026-07-06 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-04 | 2026-06-12 10:57 | 2026-04-10 | 2026-04-14 14:27 | Site is RTMI | 2026-03-22 | 2026-03-22 13:28 | 1594229 | 283655 | 0 | 0 | 1615311.7325 | 266721 | 1615311.7325 | 266721 | 2026-06-29 14:11:16 +0530 | Anamika Dolai | Some Image was uploaded | 2026-05-31 15:21:21 +0530 | Viraj Jadhav | Some Image was uploaded | 2026-05-31 13:02:24 +0530 | Viraj Jadhav | Some Image was uploaded | 2026-04-11 | 2026-04-15 20:40 | 2026-04-22 | 2026-04-22 21:28
19041 | Turnkey | 2026-01-01 | Hrshheekesh Alavani | Piramal Vaikunth Vind | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1289999 | 9999 | 0 | 0 | 0 | 112 | 0 | 119001 | 129000 | 538390 | 493609.6 |  |  | 2026-03-22 | 2026-03-25 12:26 | 2026-03-22 | 2026-04-22 12:53 | 2026-03-22 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-03-22 | 2026-03-25 12:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1093219 | 196779 | 2026-04-07 17:32:30 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-25 12:27:28 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-24 11:38:55 +0530 | Karuna Shinde | Some Image was uploaded | 2026-05-03 |  | 2026-05-10
19042 | Turnkey | 2026-01-01 | Avinash Sinha | Century Ethos | BNG - HRBR | Yes | Vijin Venu | Rajeshwari S | Shibin Lal | Vaishali G | Vaishali G | Banka H Suthar | Saddam Hussain Z M | Murali S | Raghavendra S | Abdul Shafeen | Active | Preproduction | Site Readiness 2 | 1928223 | 1176797 | 2061483 | 0 | 1928223 | 6 | 0 | 0 | 0 | 0 | 751426 |  |  | 2026-03-22 | 2026-03-27 11:18 | 2026-03-28 | 2026-03-28 11:26 | 2026-04-02 | 2026-04-02 12:22 | 2026-05-07 | 2026-05-11 23:32 | 2026-06-08 | 2026-06-20 00:29 | 2026-06-20 | 2026-06-20 19:20 | 2026-03-30 | 2026-03-30 23:27 | 2026-04-03 | 2026-04-02 16:29 | 2026-04-02 | 2026-04-02 17:40 | 2026-04-10 | 2026-04-10 15:52 |  |  |  |  | 2026-05-12 | 2026-05-12 12:22 | 2026-06-21 | 2026-06-20 17:08 | 2026-06-21 | 2026-06-20 17:26 |  |  | 2026-06-24 | 2026-07-04 20:28 | 2026-07-05 | 2026-07-05 19:40 | 2026-07-06 | 2026-07-05 22:03 | 2026-07-06 | 2026-07-09 19:37 | [5 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-05 |  | 2026-05-15 | 2026-05-07 13:27 | Site is RTMI | 2026-03-22 | 2026-03-22 13:57 | 1747019 | 314463 | 0 | 0 | 2231148.5223 | 360110 | 2231148.5223 | 360110 | 2026-07-03 17:37:30 +0530 | Vijin Venu |  | 2026-07-03 17:36:06 +0530 | Vijin Venu |  | 2026-07-03 14:58:05 +0530 | Vijin Venu | 1)Convert the TV base open unit into a flap-down unit with a Saint-Gobain glass shutter. 2)Change the right and left flap-down units to drawers. 3)Use the same handle design for both the drawers and the tall unit. 4)Ensure the false ceiling design is the same in both the living and dining areas. 5)Provide strip light provision and a centre point for the chandelier. 6)Provide a PVC conduit for the TV wiring. If possible, share a 2D electrical drawing. 7)Use the same handle design for all bedroom wardrobes and loft units. 8)MBR Walk-in Wardrobe: Increase the right-side filler to 100 mm. The loft should also align accordingly. 9)Check and share the lock options/images that will be provided. Please review the above points and cancel the approval then will go forwardÂ | 2026-05-12 | 2026-05-13 11:03 | 2026-06-21 | 2026-06-20 00:37 | RTMI
19043 | Turnkey | 2026-01-01 | Tony Tones | Joel Villa in KR Puram | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 2308325 | 9999 | 2308325 | 0 | 0 | 102 | 0 | 220834 | 230833 | 963694 | 882965.6 |  |  | 2026-03-21 | 2026-03-22 14:44 | 2026-03-25 | 2026-03-25 17:26 | 2026-04-22 | 2026-04-22 13:20 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-21 | 2026-03-22 14:36 | 1956207 | 352117 | 0 | 0 | 0 | 0 | 1956207 | 352117 | 2026-04-14 18:04:21 +0530 | Mohammed Rasick | Some Image was uploaded | [6 empty] | 2026-04-30 |  | 2026-05-07
19044 | Turnkey | 2026-01-01 | Awadhesh Pal | Shivkrupa | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Nivesh Gupta | Abdul Shafeen | Active | Design | DEM3 | 1544557 | 193979 | 1252936 | 0 | 0 | 56 | 0 | 0 | 0 | 783329 | 567248.8 |  |  | 2026-03-22 | 2026-03-27 17:31 | 2026-03-27 | 2026-03-28 15:01 | 2026-03-30 | 2026-03-30 13:21 | 2026-04-14 | 2026-04-14 19:24 | 2026-05-08 | 2026-05-07 17:56 | 2026-09-03 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-01 19:06 | 2026-04-01 | 2026-04-02 14:53 | 2026-04-04 | 2026-04-04 17:18 |  |  |  |  | 2026-04-14 | 2026-04-16 18:48 | 2026-05-20 | 2026-05-20 12:37 | 2026-05-21 | 2026-05-20 12:59 |  |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 | [6 empty] | 2026-09-27 |  | 2026-10-06 |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-09 |  |  |  | 2026-10-31 |  | 2026-11-02 |  | 2026-11-03 | [5 empty] | 2026-09-07 |  | 2026-04-05 | 2026-04-14 19:17 | Site is RTMI | 2026-03-22 | 2026-03-22 16:41 | 1064097 | 188838 | 0 | 0 | 0 | 0 | 1582736.198 | 260017 | 2026-07-02 17:37:55 +0530 | Manzoor Shaikh | The client has reached out for a cancellation and refund. ----------------------------------------------------------------------------- Good Evening @~Awadhesh Sir, I understand that there has been a delay in the design process. However, as per our agreement, you will be entitled to delay compensation. Please note that, in accordance with the agreement, we do not have a cancellation or refund policy. Thank you for your understanding. | 2026-06-23 19:13:16 +0530 | Kashmira Nerurkar | Some Image was uploaded | 2026-05-27 19:17:01 +0530 | Riddhi Deshpande | Cross Measurement: cx wanted to change design - cx wanted to discuss the changes in design on site options and renders has been sent. cx wants to add more scope. cx also unsure of the wardrobe internals - it was freezed during design discussions. cx has changed the wardrobes to sliding from openable. - still unsure about this as there is no revert on multiple followup. modulars are changed on site during cross measurements after design discussions as well | 2026-04-15 | 2026-04-14 19:27 | 2026-05-08 | 2026-05-07 17:57
19045 | Turnkey | 2026-01-01 | Priya Garg | Alta Monte | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Avi Thakkar | Siddhesh Gujrathi | Active | Design | DEM3 | 2078920 | 336510 | 2222577 | 0 | 0 | 29 | 0 | 0 | 0 | 934809 | 807600.8 |  |  | 2026-03-22 | 2026-04-01 16:49 | 2026-04-01 | 2026-04-01 18:09 | 2026-04-04 | 2026-04-02 11:39 | 2026-05-07 | 2026-05-07 17:55 | 2026-05-13 |  | 2026-06-20 |  | 2026-04-04 | 2026-03-31 | 2026-04-03 | 2026-04-02 11:52 | 2026-04-02 | 2026-04-02 17:46 | 2026-04-04 | 2026-04-04 17:34 |  |  |  |  | 2026-05-07 | 2026-05-09 16:27 | 2026-06-15 | 2026-06-16 01:55 | 2026-06-17 | 2026-06-16 01:56 |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-04-27 | 2026-05-07 16:03 | Site is RTMI | 2026-03-22 | 2026-03-22 17:06 | 1883539 | 339037 | 0 | 0 | 0 | 0 | 2214788.2002 | 373945 | 2026-05-20 18:33:54 +0530 | Manzoor Shaikh | Dear Ms. Priya Garg, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 23rd May at 2:00 PM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Saakshi will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-05-07 17:58:13 +0530 | Saakshi Bhute | DDM1: Need console unit with storage - share ref need to in width of seating - shoe rack storage in bal - storage for wm Wadrobe from the guest bed will be taken to MBÂ Aristo shutters in MB Â Pelmit lightsÂ profile lights ceilingÂ | 2026-05-03 14:22:35 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-08 | 2026-05-07 17:56 | 2026-05-14
19046 | Turnkey | 2026-01-01 | Gayatri Sujeet Gupte | Mahavir Spring | MUM - Thane | No Estimate | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-22 | 2026-03-25 12:29 | 2026-03-23 |  | 2026-03-22 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-03-22 |  | 2026-03-23 |  | 2026-03-23 |  | 2026-03-24 | [5 empty] | 2026-03-30 |  | 2026-04-07 |  | 2026-04-08 |  |  |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 | [6 empty] | 2026-05-06 |  | 2026-05-15 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-18 |  |  |  | 2026-06-09 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-04-16 |  | 2026-03-25 |  | Unknown | 2026-03-22 | 2026-03-25 12:28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-25 12:29:43 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-22 19:06:46 +0530 | Nishtha Valawalkar | Smart or normal wise | 2026-03-22 19:00:42 +0530 | Nishtha Valawalkar | Mahaveer Springs 1 bhk 12 to 13L budget - Civil work in kitchen for platform as per vastu dc, done by Mansi Weekdays or weekend cdp. CX will confirm the date | 2026-03-30 |  | 2026-04-06
19047 | Turnkey | 2026-01-01 | Vaibhav Joshi | DS Max Sky Shubham | BNG - HRBR | Yes |  | Rajeshwari S | [6 empty] | Shashank Singh |  | Active | Prospect | DCM Due | 930640 | 9999 | 0 | 0 | 0 | 110 | 0 | 83065 | 93064 | 372256 | 372256 |  |  | 2026-03-22 | 2026-03-27 20:05 | 2026-03-23 |  | 2026-03-23 |  | 2026-03-30 |  | 2026-04-06 |  | 2026-04-13 |  | 2026-03-23 |  | 2026-03-24 |  | 2026-03-24 |  | 2026-03-25 | [5 empty] | 2026-03-31 |  | 2026-04-08 |  | 2026-04-09 |  |  |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-19 | [6 empty] | 2026-05-07 |  | 2026-05-16 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-19 |  |  |  | 2026-06-10 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-04-17 |  | 2026-03-26 |  | Unknown | 2026-03-22 | 2026-03-27 19:29 | 0 | 0 | 0 | 0 | 0 | 0 | 1051421.807 | 173614 | [9 empty] | 2026-03-31 |  | 2026-04-07
19048 | Turnkey | 2026-01-01 | Subhadeep | Snn Estates Felicity | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik |  |  | Sachin I Betageri | Ranjith Kumar |  | Nidhi Shaw | Raghavendra Gowda | Active | Design | DEM3 | 1206671 | 146109 | 1098705 | 0 | 0 | 11 | 0 | 0 | 0 | 632273 | 428288.8 |  |  | 2026-03-22 | 2026-03-22 20:14 | 2026-03-25 | 2026-03-25 12:02 | 2026-03-25 | 2026-03-25 15:29 | 2026-05-30 | 2026-05-30 19:31 | 2026-07-04 | 2026-07-03 19:22 | 2026-07-08 |  | 2026-03-25 | 2026-03-25 15:44 | 2026-03-26 | 2026-03-27 14:00 | 2026-03-27 | 2026-03-30 20:38 | 2026-04-03 | 2026-04-03 19:48 |  |  |  |  | 2026-05-30 | 2026-06-13 11:27 | 2026-07-10 | 2026-07-04 21:38 | 2026-07-05 | 2026-07-04 21:38 |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-05-18 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-12 |  | 2026-05-09 | 2026-05-26 11:55 | Site is RTMI | 2026-03-22 | 2026-03-22 19:19 | 931106 | 167599 | 0 | 0 | 0 | 0 | 1408033.0049 | 232482 | 2026-06-10 12:50:52 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-20 18:23:48 +0530 | Prathyusha Elangovan | SHUBHADEEP(GREENS/BLUES/TEAL)PARENT'S (MOM-09/05/26) FOYER AREA DESIGN NEEDS TO BE SUGGESTED CONSOLE TABLE FOYER SHOW RACK-CX PROCURING FROM OUTSIDE(SUGGEST THE DESIGN) COMMON WALL(PASSAGE AREA)NEEDS TO BE HIGHLIGHTED) TV UNIT- END TO END FLOOR MOUNTED TALL UNIT ON LEFT SIDE TV BACK PANEL ONLY TO HIDE WIRES 43"TV DINING WALL-HIGHLIGHTED(WALLPAPER/MIRROR/BEADING) TINTED GLASS KITCHEN GRANITE INSTALLATION HANDLES UTILITY SAME AS THE INITIAL DESIGN BELOW THE SINK DUSTBIN/DETERGENT HOLDER MBR-1 EXISTING WARDROBE-7 FEET SLEEK UNIT NEXT TO THE WARDROBE BED BACK WALL NEEDS TO BE HIGHLIGHTED EXISTING QUEEN SIZE BED VANITY BASE UNIT DRESSER NEXT TO THE BED-ONLY MIRROR WITHOUT STORAGE MBR-2(WITH BAY WINDOW) SLIDING WARDROBE (IF SACE PERMITS PUT HINGED WARDROBE) EXISTING QUEEN SIZE BED DRESSER WIHTOUT SPACE IN THE BOTTOM L SHAPE WINDOW-CUSION ON THE SETAER AND ALSO FOR BACK WALL NO FALSE CEILING FOR THIS FLAT STUDY ROOM DESIGN NEEDS TO BE SUGGESTED,RELAXING SPACE WITH SEATER AND STORAGE BALCONY LOOSE FURNITURE NEEDS TO BE SUGESTED LIGHTS HAS TO BE SIGGESTED DINING,FOYER,LIVING NEEDS TO BE WELL LIT PLACEMENT FOR AC IN LIVING AND BEDROOMS FANS PLACEMENT H | 2026-04-22 18:33:18 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-31 | 2026-05-30 19:34 | 2026-07-04 | 2026-07-03 19:24 | Under Construction | 2026-06-30
19051 | Turnkey | 2026-01-01 | Kishor Agarwal | Hiranandani Estate | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 2254791 | 9999 | 0 | 0 | 0 | 112 | 0 | 215480 | 225479 | 912586 | 891247.2 |  |  | 2026-03-22 | 2026-03-25 12:31 | 2026-04-03 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-04-12 |  | 2026-04-20 |  | 2026-04-21 |  |  |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 | [6 empty] | 2026-05-19 |  | 2026-05-28 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-31 |  |  |  | 2026-06-22 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-04-29 |  | 2026-04-07 |  | Unknown | 2026-03-22 | 2026-03-25 12:30 | 0 | 0 | 0 | 0 | 0 | 0 | 1910839 | 343951 | 2026-04-07 17:37:34 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-03-25 12:31:45 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-03-22 19:05:41 +0530 | Nishtha Valawalkar | Hiranandani Estate 3 bhk 1200 sq.ft Req - LR, WADROBES, BEDS, Services, washroom vanities, 15L (Smart or select) RTMI | 2026-04-12 |  | 2026-04-19
19053 | Turnkey | 2026-01-01 | rinki dey | Raymond - Ten X Habitat | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [6 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 1603863 | 9999 | 0 | 0 | 0 | 99 | 0 | 150387 | 160386 | 653265 | 629825.6 |  |  | 2026-03-22 | 2026-03-22 22:24 | 2026-04-04 | 2026-04-04 11:56 | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-04-15 |  | 2026-04-23 |  | 2026-04-24 |  |  |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-04 | [6 empty] | 2026-05-22 |  | 2026-05-31 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-03 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-05-02 |  | 2026-04-10 |  | Unknown | 2026-03-22 | 2026-03-22 22:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1361263 | 242600 | 2026-03-24 17:04:23 +0530 | Aryan Singh | Some Image was uploaded | [6 empty] | 2026-04-15 |  | 2026-04-22
19055 | Turnkey | 2026-01-01 | akshat pagaria | sangeshwar heights | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Nivesh Gupta |  | Active | Design | DEM1 | 1261627 | 164537.95 | 1645379 | 0 | 0 | 76 | 0 | 0 | 87787 | 565452 | 443849.6 |  |  | 2026-03-22 | 2026-03-25 12:32 | 2026-03-22 | 2026-04-26 21:31 | 2026-04-26 | 2026-04-26 21:37 | 2026-07-23 |  | 2026-07-30 |  | 2026-08-06 |  | 2026-04-26 | 2026-04-30 11:11 | 2026-04-27 | 2026-04-30 11:13 | 2026-04-30 | 2026-04-30 15:11 | 2026-05-13 | 2026-05-13 18:21 |  |  |  |  | 2026-07-24 |  | 2026-08-01 |  | 2026-08-02 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-10 |  | 2026-09-10 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-31 |  | 2026-07-19 |  | Unknown | 2026-03-22 | 2026-03-22 19:45 | 1394389 | 250990 | 0 | 0 | 0 | 0 | 1391156.7485 | 235163 | 2026-06-05 13:07:15 +0530 | Meet Shah | Some Image was uploaded | 2026-05-13 18:19:36 +0530 | Reshma Melanta | Possession expectedÂ July 2026 RERA registrationÂ September 2026 CX is OK to proceed with Dem-1 meeting CX will make pament during the Dem-1 meetingÂ Sonal informed to align a Dem-1 meeting and IM for the same. Self added to the group Schedule and conductÂ Dem-1 meetingÂ Â IM - Can be aligned | 2026-05-09 13:15:51 +0530 | Reshma Melanta | NOT ANSWERING THE CALL | 2026-07-24 |  | 2026-07-31 |  | Under Construction | 2026-07-01
19056 | Turnkey | 2026-01-01 | sumedha Ramchandra Sheela | arcade prime | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Mohammed Lal | Naushad Ansari | Rizwan Mistry | Murali S | Avi Thakkar | Siddhesh Gujrathi | Active | Preproduction | Procurement | 1874373 | 1249474 | 2034210 | 1761087 | 1924373 | 7 | 4 | 0 | 0 | 0 | 624899 |  |  | 2026-03-22 | 2026-04-01 16:32 | 2026-03-29 | 2026-04-01 17:00 | 2026-04-04 | 2026-04-02 19:21 | 2026-05-22 | 2026-05-07 10:52 | 2026-06-13 | 2026-06-12 16:38 | 2026-06-26 | 2026-06-21 19:01 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-05 14:39 | 2026-04-05 | 2026-04-08 13:10 | 2026-04-12 | 2026-04-12 12:09 |  |  |  |  | 2026-05-08 | 2026-05-12 18:43 | 2026-06-22 | 2026-06-21 18:52 | 2026-06-22 | 2026-06-21 18:52 |  |  | 2026-06-23 | 2026-06-25 17:45 | 2026-06-27 | 2026-06-27 19:59 | 2026-06-28 | 2026-06-27 20:09 | 2026-07-03 | 2026-07-06 19:12 |  |  |  |  | 2026-07-08 17:50 | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-06-27 | 2026-07-07 19:52 | 2026-04-13 | 2026-05-05 22:09 | Site is RTMI | 2026-03-22 | 2026-03-31 17:37 | 1723907 | 310303 | 1971269.9245 | 325462 | 2177531.9321 | 359523 | 2177531.9321 | 359523 | 2026-06-27 19:55:06 +0530 | Manzoor Shaikh | The client is at the PKO stage, the quote increased and was at the cancellation, as a retention effort offered 2.5% discount. | 2026-06-25 15:31:50 +0530 | Mohammed Lal | Some Image was uploaded | 2026-06-21 22:46:09 +0530 | Mohammed Lal | Some Image was uploaded | 2026-05-08 | 2026-05-13 19:36 | 2026-06-13 | 2026-06-12 16:38
19057 | Turnkey | 2026-01-01 | Lopamudra Bhattacharyya | Raymond 10X Habitat | MUM - Thane | Yes | [8 empty] | Anjan Kumar |  | Active | Prospect | DCM Due | 1568791 | 9999 | 1568791 | 0 | 0 | 115 | 0 | 146880 | 156879 | 669284 | 585748.8 |  |  | 2026-03-22 | 2026-03-22 21:16 | 2026-03-26 |  | 2026-03-30 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-04-06 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 | [6 empty] | 2026-05-13 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-25 |  |  |  | 2026-06-16 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-04-23 |  | 2026-04-01 |  | Unknown | 2026-03-22 | 2026-03-22 21:14 | 1332285 | 236505 | 0 | 0 | 0 | 0 | 1332285 | 236505 | 2026-03-27 14:50:42 +0530 | Karuna Shinde | Some Image was uploaded | 2026-03-22 21:19:18 +0530 | Anjan Kumar | Some Image was uploaded |  |  |  | 2026-04-06 |  | 2026-04-13
19059 | Turnkey | 2026-01-01 | Prashant Sawant | Puraniks Grand Central Glorio | MUM - Thane | Yes | Rachna Abhyankar |  | Rushika More | [5 empty] | Shreyash Kotecha |  | Lost | Prospect | DCM Due | 1635856 | 9999 | 0 | 0 | 0 | 112 | 0 | 153587 | 163586 | 720567 | 588118 |  |  | 2026-03-22 | 2026-03-25 12:28 | 2026-04-08 | 2026-04-08 11:00 | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-03-22 | 2026-03-25 12:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1386318 | 249537 | 2026-03-25 18:06:59 +0530 | Rachna Abhyankar | Client Name - Mr Prashant Sawant Property Type - New - 2BHKÂ - Puranik Grand central- 500 sq ft Possession - August 2026 Family - 4 Adults (couple with parent) Budget - 10-14L Foyer :-Â 1-Shoe rack + Safety DoorÂ Living Room:- 1- TV Unit - 65"Â 2- 3 Seater sofaÂ 3- Mandir bottom unitÂ 4- Dining Table 4 seater 5- Sofa wall conceptsÂ Kitchen:- 1- Semi Modular Kitchen (Base + 1 Loft + 2 Wall) only 1 side counter given by builder Bedroom 01(MB):- 1- Queen Bed with storage 2- wardrobe + LoftÂ Master Bedroom (Parents Room):- 1- Wardrobe + LoftÂ 2- Queen size bed with storageÂ Â 3- Foldable study table 4- TV Unit - 43" Bathrooms:- 1-Both vanities will have bottom cabinets Civil Requirements:- 1-False ceilingÂ 2-ElectricalÂ 3-PaintingÂ | 2026-03-25 16:59:20 +0530 | Rachna Abhyankar | Some Image was uploaded |  |  |  | 2026-04-08 |  | 2026-04-15
19060 | Turnkey | 2026-01-01 | Santosh Sonawane | Raymond GS | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 2795512 | 9999 | 0 | 0 | 0 | 60 | 0 | 269552 | 279551 | 1224083 | 1012326.8 |  |  | 2026-03-22 | 2026-03-22 21:11 | 2026-04-04 | 2026-04-04 11:26 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-03-22 | 2026-03-22 21:10 | 0 | 0 | 0 | 0 | 0 | 0 | 2369078 | 426434 | 2026-04-02 15:31:37 +0530 | Krutika Vernekar | DCM : Client Profile : Doctor Configuration : 4bhk Possession : August 2026 People : 6 ppl Budget : 25L Theme : Minimal Existing Furniture : Na Entry : Shoerack + Safety Door + Panelling + Name plate. Foyer : Bottom Storage + Back Wall Design. Kitchen : 3 feet ref . Parallel kitchen , Semi Mod , Base + Wall + Loft Living Room : Mandir as per Vastu. Marble back wall take care by Cx , Tv unit existing 75", Sofa Cum bed , 2 seater chair , 2 unit + Vertical. . 6 seater Dining Table . Balcony : only jhoola. Bedroom 1 : Raj is 9 yrs old . Wardrobe + Dressing + Loft + Study + Shelf + Bed (single). Bedroom 2 : Sonpari is 16 yrs old . Wardrobe +Dressing + Loft + Study + Shelf + Bed (queen) Bedroom 3 : Parents Wardrobe + Dressing + Loft + Wardobe + Bed + Additional Storage . Bedroom 4 : Husband and Wife Wardrobe + Dressing + Loft + Storage + Bed | [6 empty] | 2026-05-24 |  | 2026-05-31
19061 | Turnkey | 2026-01-01 | Mr.Sachin Bhoravat | Damji Shamji | MUM - Thane | Yes |  | Anil Jagtap | [6 empty] | Shreyash Kotecha |  | Active | Prospect | Onboarding Due | 1186166 | 128599 | 1186166 | 0 | 0 | 91 | 0 | 0 | 108634 | 484046 | 464887.2 |  |  | 2026-03-22 | 2026-03-25 12:24 | 2026-04-05 | 2026-04-05 13:14 | 2026-04-08 | 2026-04-07 11:13 | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-04-07 | 2026-04-10 17:25 | 2026-04-08 | 2026-04-15 16:14 | 2026-04-15 |  | 2026-06-24 | [5 empty] | 2026-06-30 |  | 2026-07-08 |  | 2026-07-09 |  |  |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 | [6 empty] | 2026-08-06 |  | 2026-08-15 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-12 | [5 empty] | 2026-07-17 |  | 2026-06-25 |  | Unknown | 2026-03-22 | 2026-03-25 12:21 | 1005225 | 180940 | 0 | 0 | 0 | 0 | 1005225 | 180940 | 2026-05-26 12:39:59 +0530 | Bency Chacko |  | 2026-04-30 09:26:53 +0530 | Royden Henriques | Some Image was uploaded | 2026-04-16 11:59:39 +0530 | Shreyash Kotecha | Onboarding Due: There are some customer queries that need to be resolved. Once those are addresses i will update you on the onboading process. | 2026-06-30 |  | 2026-07-07
19062 | Turnkey | 2026-01-01 | Gaurav Saitawdekar | L&T Rejuve | MUM - Thane | Yes | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 1732245 | 9999 | 0 | 0 | 0 | 115 | 0 | 163226 | 173225 | 730166 | 655629.6 |  |  | 2026-03-22 | 2026-03-22 21:26 | 2026-03-23 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-22 | 2026-03-22 21:22 | 0 | 0 | 0 | 0 | 0 | 0 | 1470267 | 261978 | 2026-04-03 13:28:20 +0530 | Mayuri Patil | DCM: Name: Saitawdekar Property Name: Property type:Â Property Location:Â Possession: next month mid may Move in: immediately after interiorÂ Â Member: 4 members Profession: IT industry, parents retired father bankingÂ North direction:Â Existing Furniture: 1 almirah size 6.9 by 4.7, beds, sofa 7 by 2.5 Â Requirements: Living room: entry foyer design with lighting, shoe rack outside, 3 seater sofa, tv unit with drawers no display, fish tank in dining 3 feet by 1 n half feet, 4 seater dining, mandir should be either east facing or west facing with 2 n half feet mandir mostly near dining, mirror on dining wall of toilet side, display in front of the dining 1 to 1 n half feet half open half close.Â Â Â Â Â Kitchen : base unit, wall unit, loft, and microwave unit. Bedroom 1 (parents): queen size bed, wardrobe with loft, bed position change on west side, book shelf either in this bedroom or living room. Â Master Bedroom : King size bed, wardrobe with loft, dressing unit with drawer and full size mirror, tv unit, work station folding table. Â Bathroom : vanity in both bathrooms. Â Theme : minimal theme with light and pastel colorsÂ Â Additional scope: false ceiling living room, electricals, paintings.Â Â Â Budget: Â Budget Suggested : 15 to 16 Â CDP: 3 April 11 am. | 2026-03-24 11:10:23 +0530 | Mustufa Sohagpurwala | Some Image was uploaded |  |  |  | 2026-04-11 |  | 2026-04-18
19063 | Turnkey | 2026-01-01 | Shashikanth Manjunatha | independent house | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Pulivarthi Nirosha |  | Active | Design | DEM1 | 751440 | 105976 | 1059761 | 0 | 0 | 53 | 44 | 0 | 44312 | 303822 | 297329.6 |  |  | 2026-03-22 | 2026-03-24 14:13 | 2026-03-31 | 2026-03-31 15:16 | 2026-04-03 | 2026-03-31 15:58 | 2026-09-07 |  | 2026-09-14 |  | 2026-09-21 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 13:15 | 2026-04-03 | 2026-04-09 13:25 | 2026-04-11 | 2026-04-11 19:25 |  |  |  |  | 2026-09-08 |  | 2026-09-16 |  | 2026-09-17 |  |  |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 | [6 empty] | 2026-10-15 |  | 2026-10-24 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-25 |  | 2026-10-27 |  |  |  | 2026-11-18 |  | 2026-11-20 |  | 2026-11-21 | [5 empty] | 2026-09-25 |  | 2026-09-03 |  | Unknown | 2026-03-22 | 2026-03-24 14:12 | 898103 | 161658 | 0 | 0 | 0 | 0 | 893216.945 | 152762 | 2026-05-22 19:16:01 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-17 17:08:53 +0530 | Priyanka Mathur | We had a call with customer he is saying site is not ready and it will take minimum 2.5 month so he want to put on hold | 2026-04-09 13:25:29 +0530 | Bency Chacko |  | 2026-09-08 |  | 2026-09-15 |  | Under Construction | 2026-06-18
19064 | Turnkey | 2026-01-01 | Tushar Nalawade |  | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Active | Preproduction | DEM2 | 1275084 | 255999 | 1805905 | 0 | 0 | 46 | 43 | 0 | 0 | 510744 | 508340.8 |  |  | 2026-03-22 | 2026-03-22 21:45 | 2026-03-29 | 2026-03-29 22:29 | 2026-03-29 | 2026-03-29 22:33 | 2026-04-15 | 2026-04-15 11:37 | 2026-07-12 |  | 2026-08-09 |  | 2026-03-29 | 2026-03-31 15:49 | 2026-03-30 | 2026-03-31 15:57 | 2026-03-31 | 2026-03-31 16:48 | 2026-04-04 | 2026-04-04 18:13 |  |  |  |  | 2026-04-15 | 2026-04-17 18:28 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-05-07 | 2026-04-15 11:13 | Site is RTMI | 2026-03-22 | 2026-03-22 21:35 | 1530428 | 275477 | 0 | 0 | 0 | 0 | 1483528.15 | 235958 | 2026-06-26 17:24:22 +0530 | Shraddha Pansare | Client mentioned in the initial booking meeting that they will require atleast 5meetings during design phase, also only on weekends. Hence considered PKO in the next month. | 2026-06-26 17:13:54 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-06-26 17:07:50 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-04-16 | 2026-04-15 11:53 | 2026-07-13
19065 | Turnkey | 2026-01-01 | Raghav | AJMERA IRIS | BNG - HSR | Yes | Preksha Sajjanshettar | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1673189 | 9999 | 0 | 0 | 0 | 101 | 0 | 157320 | 167319 | 685700 | 652851.6 |  |  | 2026-03-22 | 2026-03-24 14:14 | 2026-04-03 | 2026-04-03 15:11 | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-04-13 |  | 2026-04-21 |  | 2026-04-22 |  |  |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 | [6 empty] | 2026-05-20 |  | 2026-05-29 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-06-01 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-04-30 |  | 2026-04-08 |  | Unknown | 2026-03-22 | 2026-03-24 14:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1417957 | 255232 | 2026-04-22 18:36:49 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-05 11:09:53 +0530 | Preksha Sajjanshettar | Some Image was uploaded | 2026-04-05 11:09:07 +0530 | Preksha Sajjanshettar | RGM PID 19065 Name : Raghav, Sindhu - 2 kids 13& 8yrs old Address : Ajmera, First floor - B102 3BHK Profession : IT Soft Hand over : June/July East Face Entrance Theme : ? Budget : 15LK Entrance Shoe Unit - 7ft Cabinet & loft Foyer : L- shape storage unit for shoes Living Area: TV wall - either sides storage unit - glass door with black frame middle tv provision-70", also need provision for speakers, wall panelling laminate finishÂ Sofa back wall - texture paint and punning Dining Area :Â Crockery unit - one tall unit , base & wall unitÂ 6 seater dining table Pooja unit beside fridge wall west facing Kitchen: Double door fridge, HOB - inbuilt, Chimney, microwave, dish washer, mixer, grinder, RO under sink L- shape kitchen, tall unit for appliances, Panelling for fridge Utility: Base & wall unit MBR : Wardrobe, work desk adj ht, king size bed, tv unit KBR : wardrobe loft , study table , Queen size bed Bedroom : wardrobe & loft study tableÂ Â Bathrooms : vanity units , no granite (need to check ) Both the balconies : base unit FC - Full home-peripheral Granite from our end , utility base unit for dish washer and a sink provision, as of now consider dresser later cx wants to check | 2026-04-13 |  | 2026-04-20
19066 | Turnkey | 2026-01-01 | (Faiyaz Haque) All Sign Technologies Pvt Ltd | Lodha bel air | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Safalta Karkera |  | Ehtesham Bhati | Uday Yadruk | Rizwan Mistry | Murali S | Umang Shah | Aakash Gaikwad | Active | Production | Production | 1618052 | 1078655 | 1764810 | 0 | 1658052 | 5 | 26 | 0 | 0 | 0 | 539397 |  |  | 2026-03-22 | 2026-03-22 21:44 | 2026-03-24 | 2026-03-24 12:30 | 2026-03-26 | 2026-03-25 19:58 | 2026-03-31 | 2026-03-31 19:38 | 2026-04-10 | 2026-04-09 13:56 | 2026-04-26 | 2026-04-26 15:12 | 2026-03-25 | 2026-03-26 18:38 | 2026-03-26 | 2026-03-27 17:26 | 2026-03-27 | 2026-03-28 12:34 | 2026-03-28 | 2026-03-28 19:00 |  |  |  |  | 2026-03-31 | 2026-04-03 17:45 | 2026-04-16 | 2026-04-16 15:59 | 2026-04-17 | 2026-04-16 15:59 |  |  | 2026-04-28 | 2026-05-06 13:49 | 2026-05-17 | 2026-05-17 14:12 | 2026-05-18 | 2026-05-22 15:39 | 2026-06-30 | 2026-07-02 12:21 |  |  |  |  | 2026-07-03 19:28 | 2026-07-11 | 2026-07-10 22:15 | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-04 |  | 2026-08-05 | [5 empty] | 2026-05-17 | 2026-07-02 17:03 | 2026-03-29 | 2026-03-31 19:31 | Site is RTMI | 2026-03-22 | 2026-03-22 21:42 | 1495602 | 269208 | 0 | 0 | 1806105.7878 | 311652 | 1806105.7878 | 311652 | 2026-07-02 11:01:32 +0530 | Manzoor Shaikh | The client is at the PKO stage, and is ready to continue paying the milestone due, hence as a retention effort offered Rs.30,000 discount, approved by Rupali. | 2026-06-14 14:44:04 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-14 13:46:09 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-04-01 | 2026-03-31 19:44 | 2026-04-10 | 2026-04-09 15:19 | RTMI
19067 | Turnkey | 2026-01-01 | Pundlik Kadam | skyrise | MUM - GOR | Yes | Saif Shaikh | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Sanskruti Yadav |  | Hold | Design | DEM1 | 1172833 | 234400 | 1645253 | 0 | 0 | 22 | 13 | 0 | 0 | 472782 | 465650.8 |  |  | 2026-03-22 | 2026-03-23 16:50 | 2026-04-03 | 2026-04-03 15:27 | 2026-06-07 | 2026-06-08 12:27 | 2026-07-24 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-06-07 | 2026-06-07 21:45 | 2026-06-08 | 2026-06-07 22:37 | 2026-06-09 | 2026-06-10 20:07 | 2026-06-16 | 2026-06-16 18:41 |  |  |  |  | 2026-06-22 | 2026-06-19 12:22 | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-07-20 |  | Unknown | 2026-03-22 | 2026-03-23 16:49 | 1394283 | 250970 | 0 | 0 | 0 | 0 | 1384828.298 | 219660 | 2026-07-02 23:59:47 +0530 | Vishakha Vaishnav | Others: | 2026-06-16 18:40:13 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : cx said site is accessible DEM Dates -Â DEM 1 - cx said he will confirm as he is busy for this month probably he will come for the meeting by july 1st week DEM 2 - TBD DEM 3 - TBD Possession date : Rera possession is december 2026 Customer will make 10% : done Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-10 20:07:10 +0530 | Athul Ajaykumar |  | 2026-07-25 |  | 2026-08-01 |  | Under Construction | 2026-10-31 | 2026-06-07 | 164525 | Ravi Roy
19068 | Turnkey | 2026-01-01 | Ankit Chheda | Riveria | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 1647324 | 9999 | 1647324 | 0 | 0 | 113 | 0 | 154733 | 164732 | 674857 | 643002.4 |  |  | 2026-03-22 | 2026-03-24 12:57 | 2026-03-24 | 2026-03-24 15:47 | 2026-04-06 |  | 2026-04-03 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-03-27 |  | 2026-03-28 |  | 2026-03-28 |  | 2026-03-29 | [5 empty] | 2026-04-04 |  | 2026-04-12 |  | 2026-04-13 |  |  |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 | [6 empty] | 2026-05-11 |  | 2026-05-20 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-23 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-21 |  | 2026-03-30 |  | Unknown | 2026-03-22 | 2026-03-24 12:56 | 1396038 | 251286 | 0 | 0 | 0 | 0 | 1396038 | 251286 | 2026-03-24 12:56:50 +0530 | Sanskruti Yadav | Some Image was uploaded | [6 empty] | 2026-04-04 |  | 2026-04-11
19069 | Turnkey | 2026-01-01 | Bijesh menon | Raymond GS | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Foram Joshi |  | Hold | Design | DEM1 | 1998369 | 298869 | 1998369 | 0 | 0 | 24 | 74 | 0 | 100805 | 856072 | 742622.8 |  |  | 2026-03-22 | 2026-03-26 14:19 | 2026-03-29 | 2026-03-31 16:36 | 2026-03-31 | 2026-03-31 21:37 | 2027-01-04 |  | 2027-01-11 |  | 2027-01-18 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 17:20 | 2026-04-03 | 2026-04-08 15:55 | 2026-07-04 | 2026-07-03 18:26 |  |  |  |  | 2027-01-05 |  | 2027-01-13 |  | 2027-01-14 |  |  |  | 2027-01-21 |  | 2027-01-22 |  | 2027-01-23 |  | 2027-01-24 | [6 empty] | 2027-02-11 |  | 2027-02-20 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-21 |  | 2027-02-23 |  |  |  | 2027-03-17 |  | 2027-03-19 |  | 2027-03-20 | [5 empty] | 2027-01-22 |  | 2026-12-31 |  | Unknown | 2026-03-22 | 2026-03-22 22:29 | 2379710.8537 | 392929 | 0 | 0 | 0 | 0 | 2379710.8537 | 392929 | 2026-07-14 12:33:02 +0530 | Divya Rahangdale | The client is expected to receive possession by November. | 2026-07-05 13:38:31 +0530 | Divya Rahangdale | Welcome call done : Possession date : November 10% payment aligned : As per Dipen's approval, the client will pay the 10% once they receive possession of the property. Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-07-03 13:31:32 +0530 | Divya Rahangdale | Hold till December | 2027-01-05 |  | 2027-01-12
19070 | Turnkey | 2026-01-01 | dhawal mhatre | Sonam Indraneel | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Foram Joshi |  | Lost | Prospect | 10% Payment | 1947418 | 9999 | 0 | 0 | 0 | 110 | 0 | 184743 | 194742 | 865343 | 692591.2 |  |  | 2026-03-22 | 2026-03-22 22:26 | 2026-03-27 | 2026-03-27 19:07 | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-22 | 2026-03-22 22:23 | 0 | 0 | 0 | 0 | 0 | 0 | 1650355 | 297063 | 2026-03-24 17:38:14 +0530 | Pooja Nakul Sharma | DCM: Mr Mhatre 2BHKÂ Poss- July 2026Â family- 4 members (son 8 yr/o) Prof- ITÂ Property- Sonam IndraneelÂ Vastu - Basic vastuÂ Existing - Queen bed and mandir (6 ft height) 1. Safety door (panchmukhi hanuman murti to be kept above door), shoerack (10-15 pairs). 2. Ganpati, kitchen wall to be demolished and folding dining can be done.Â 3. No dining table.Â 4. No Tv in living room, Sofa 3 seater + accent chair / Indian seating. Indoor plants.Â 5. Mandir to be kept in living room.Â 6. Kitchen- Builder has given modular kitchen along with chimney. 7. Parents- Queen bed / sofa cum bed. Study unit, wardrobe, dresser with drawer storage. Son has lot of action figures so can be used for wall concepts. Wall mount TV. 8. MBR- Wardrobe in niche, Ex. Queen bed, Wall mount TV, Dresser. Indoor plants.Â 9. False ceiling, painting, electricals.Â 10. Budget- 8-9L | [6 empty] | 2026-04-05 |  | 2026-04-12
19071 | Turnkey | 2026-01-01 | Sushant Shashikant Raorane | Damji shamji mahavir spring | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Aryan Singh |  | Hold | Preproduction | Site Readiness 1 | 2864843 | 572969 | 3797619 | 0 | 0 | 18 | 71 | 0 | 0 | 1307606 | 984267.6 |  |  | 2026-03-22 | 2026-03-22 22:22 | 2026-03-24 | 2026-03-27 19:30 | 2026-03-30 | 2026-03-29 07:57 | 2026-04-18 | 2026-04-17 14:08 | 2026-08-05 |  | 2026-08-12 |  | 2026-03-29 | 2026-03-31 16:59 | 2026-03-30 | 2026-03-31 17:00 | 2026-03-31 | 2026-04-01 12:38 | 2026-04-11 | 2026-04-11 11:57 |  |  |  |  | 2026-04-17 | 2026-04-17 18:22 | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-04-12 | 2026-04-17 13:27 | Site is Non-RTMI | 2026-03-22 | 2026-03-22 22:21 | 3218322 | 579297 | 0 | 0 | 0 | 0 | 3159577.1995 | 521671 | 2026-07-10 19:09:52 +0530 | Divya Rahangdale | CX will receive the possession by August End. | 2026-06-29 13:30:29 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: Site is not ready. Flooring is not done yet, wall installation is also not done. Site will get ready by August end tentative as per clients last communication. | 2026-06-10 17:05:42 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-04-18 | 2026-04-17 14:14 | 2026-08-06
19072 | Turnkey | 2026-01-01 | Neelam Jaiswal | Arihant aspire | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Yash Metha | Akshat Shrivastava | Murali S | Bhagyashree Salunkhe | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 838725 | 839571 | 1562766 | 0 | 838725 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-22 | 2026-03-24 11:34 | 2026-03-24 | 2026-04-03 11:40 | 2026-04-06 | 2026-04-04 11:35 | 2026-04-29 | 2026-04-29 12:42 | 2026-05-17 | 2026-05-17 02:06 | 2026-05-23 | 2026-05-23 16:19 | 2026-04-04 | 2026-04-06 19:00 | 2026-04-05 | 2026-04-07 17:19 | 2026-04-07 | 2026-04-14 11:50 | 2026-04-24 | 2026-04-24 11:47 |  |  |  |  | 2026-04-29 | 2026-04-29 16:10 | 2026-06-23 | 2026-05-20 12:32 | 2026-05-21 | 2026-05-20 12:32 |  |  | 2026-06-11 | 2026-06-12 16:50 | 2026-06-13 | 2026-06-13 17:58 | 2026-06-14 | 2026-06-14 11:29 | 2026-06-15 | 2026-06-14 17:40 |  |  |  |  | 2026-06-17 07:57 | 2026-06-23 | 2026-06-22 21:23 | 2026-06-30 | 2026-06-28 14:21 | 2026-06-29 | 2026-06-30 14:58 | 2026-06-28 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-06-13 | 2026-06-17 07:56 | 2026-04-25 | 2026-04-28 16:12 | Site is RTMI | 2026-03-22 | 2026-03-24 11:14 | 1324378 | 238388 | 0 | 0 | 1021989.037 | 168746 | 1021989.037 | 168746 | 2026-07-10 13:20:25 +0530 | Divya Rahangdale | Approval for Delayed Dispatch Due to Site Unavailability | 2026-06-13 11:43:29 +0530 | Nilofer Shaikh | Some Image was uploaded | 2026-06-12 12:16:43 +0530 | Naved Malik | Some Image was uploaded | 2026-04-30 | 2026-04-29 12:44 | 2026-05-18 | 2026-05-17 02:07
19073 | Turnkey | 2026-01-01 | Aniket Munje | Lodha Splendora | MUM - Thane | No Estimate | Rutuja Kotwal | Anamika Dolai | [6 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-22 | 2026-03-22 23:40 | 2026-04-22 | 2026-04-22 12:51 | 2026-03-29 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-03-22 | 2026-03-22 23:37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-22 12:18:19 +0530 | Rutuja Kotwal | DCM: Mr. AniketÂ Munje.Â Â 3BHK.Â Â 1135sq.ft. AreaÂ Â Move inÂ 4 people Husband, Wife, 2 daughters- 12yrs. And 7 yrs.Â Â Profession Works in Lodha HusbandÂ Â Wife HR.Â Â Direction Entering West.Â Â Design as per Basic Vastu.Â Â LivingÂ room -Â Â Closing of Kitchen wall and making an opening from the Living room ,Â Shoe rack,Â Sofa in the front wall in front of the entry, TV unit on the kitchen wall whichÂ is untouched,Â 6 seater Dining Table, StorageÂ near windowÂ opp. Dining table, where there will be a Mandir. Mandir in cx. Scope.Â Â KitchenÂ -Â BaseÂ Units, Wall Units and Lofts.Â Â Parents Bedroom- Wardrobe w/o lofts and nothing else., Bed existingÂ Â Daughters Bedroom -Â Wardrobe w/o lofts, Bed, Study Table with storage below and Above,Â MBR- Wardrobe w/o Lofts, Bed, Dressing Unit, Workstation with Above storage,Â tall storage near window.Â Â Store roomÂ Only shelves to be provided above 3 ht.Â Â CDP-Â 1stÂ April 2026 at 3 pm.Â Â Budget-Â 10 lakhs.Â Â Budget Suggested-Â 25- 30 lakhs.Â Â | 2026-03-24 17:37:05 +0530 | Aryan Singh | Some Image was uploaded |  |  |  | 2026-05-03 |  | 2026-05-10
19074 | Turnkey | 2026-01-01 | Mr. Priank | DS Max Sky Shubham | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S | Shashank Singh | Abdul Shafeen | Active | Installation | Execution | 812698 | 812698 | 934656 | 812698 | 812698 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-22 | 2026-03-26 19:49 | 2026-03-27 | 2026-03-27 14:20 | 2026-03-27 | 2026-03-27 14:30 | 2026-04-22 | 2026-04-22 18:51 | 2026-05-11 | 2026-05-10 11:28 | 2026-05-18 | 2026-05-19 11:02 | 2026-03-27 | 2026-03-31 | 2026-03-28 | 2026-04-05 15:47 | 2026-04-05 | 2026-04-07 12:48 | 2026-04-09 | 2026-04-13 09:15 |  |  |  |  | 2026-05-05 | 2026-05-10 11:20 | 2026-05-11 | 2026-05-10 17:37 | 2026-05-11 | 2026-05-13 23:45 |  |  | 2026-05-21 | 2026-05-30 12:24 | 2026-05-30 | 2026-05-30 16:10 | 2026-05-31 | 2026-05-30 20:31 | 2026-05-26 | 2026-05-25 15:58 |  |  |  |  | 2026-06-02 13:01 | 2026-06-12 | 2026-06-17 19:51 | 2026-06-29 | 2026-06-27 18:32 | 2026-06-27 | 2026-06-26 17:52 | 2026-06-27 | 2026-06-29 16:21 | 2026-06-29 | 2026-06-29 19:32 | 2026-07-02 | 2026-07-03 18:41 |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-05-30 | 2026-06-02 13:00 | 2026-04-14 | 2026-04-22 11:43 | Site is RTMI | 2026-03-22 | 2026-03-26 19:46 | 792081 | 142574 | 853221.864 | 147233 | 853221.864 | 147233 | 853221.864 | 147233 | 2026-05-19 15:33:37 +0530 | Priyanka R | Some Image was uploaded | 2026-04-27 13:22:17 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-24 13:18:13 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-30 | 2026-04-22 18:54 | 2026-05-11 | 2026-05-10 11:29 | RTMI
19075 | Turnkey | 2026-01-01 | Srinivasan Sethuraman | v classic apartment | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 1347582 | 9999 | 1347582 | 0 | 0 | 102 | 0 | 124759 | 134758 | 563270 | 514795.2 |  |  | 2026-03-20 | 2026-03-29 12:57 | 2026-03-29 | 2026-03-29 13:42 | 2026-04-05 | 2026-04-22 12:33 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-20 | 2026-03-26 19:49 | 1236349.3424 | 205563 | 0 | 0 | 0 | 0 | 1236349.3424 | 205563 | 2026-04-14 16:45:18 +0530 | Shashank Singh | Some Image was uploaded | 2026-03-29 08:29:00 +0530 | Alekhya Korada | Some Image was uploaded |  |  |  | 2026-04-30 |  | 2026-05-07
19076 | Turnkey | 2026-01-01 | Suraj | DNR Parklink | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Kushal S |  | Hold | Preproduction | Site Readiness 1 | 2024933 | 442999 | 2619289 | 0 | 0 | 2 | 49 | 0 | 0 | 839283 | 742651.2 |  |  | 2026-03-22 | 2026-03-23 15:56 | 2026-03-28 | 2026-03-30 12:27 | 2026-03-30 | 2026-03-30 13:32 | 2026-05-22 | 2026-05-22 14:23 | 2026-09-23 |  | 2026-09-30 |  | 2026-03-30 | 2026-03-30 18:47 | 2026-03-31 | 2026-03-31 13:07 | 2026-03-31 | 2026-04-04 18:35 | 2026-04-12 | 2026-04-12 20:20 |  |  |  |  | 2026-05-22 | 2026-05-25 18:52 | 2026-09-25 |  | 2026-09-26 |  |  |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-06 | [6 empty] | 2026-10-24 |  | 2026-11-02 |  | 2026-11-01 |  | 2026-11-02 |  | 2026-11-03 |  | 2026-11-05 |  |  |  | 2026-11-27 |  | 2026-11-29 |  | 2026-11-30 | [5 empty] | 2026-10-04 |  | 2026-04-13 | 2026-05-02 17:42 | Site is Non-RTMI | 2026-03-22 | 2026-03-23 13:05 | 2219736 | 399552 | 0 | 0 | 0 | 0 | 2166072.1528 | 365710 | 2026-05-22 11:28:20 +0530 | Vishnu S | Some Image was uploaded | 2026-04-20 15:51:36 +0530 | Keerthan M | CDP: Living Foyer unit suggest console unit Dining Change MDF beading to Wainscoting Kitchen add wicker basketStorage above fridge need to be addedJanitor unit need to be added in utilitySink to wash clothes need to be suggestedIn built dish washer need to be considered KBR and GBR need to be swapped MBR wall detailing need to be changed | 2026-04-12 20:24:21 +0530 | Parasa Sri | welcome call done. | 2026-05-23 | 2026-05-22 14:27 | 2026-09-24 |  | Under Construction | 2027-03-31
19077 | Turnkey | 2026-01-01 | Balanandan Krishnamurthi | Assetz Soho and Sky | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 1929868 | 9999 | 0 | 0 | 0 | 114 | 0 | 182988 | 192987 | 799044 | 744850.8 |  |  | 2026-03-22 | 2026-03-23 15:53 | 2026-04-19 | 2026-04-22 13:13 | 2026-04-15 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-03-22 | 2026-03-23 13:09 | 0 | 0 | 0 | 0 | 0 | 0 | 1635481 | 294386 | [9 empty] | 2026-05-03 |  | 2026-05-10
19079 | Turnkey | 2026-01-01 | Hriday Industry | Vasathi Avante | BNG - HRBR | Yes |  | Rajeshwari S | [8 empty] | Active | Prospect | 10% Payment | 1266245 | 9999 | 1697886 | 0 | 0 | 91 | 0 | 0 | 243250 | 544922 | 468074.4 |  |  | 2026-03-23 | 2026-03-30 14:31 | 2026-03-30 | 2026-03-30 15:36 | 2026-03-30 | 2026-03-30 16:10 | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-09 16:11 | 2026-04-09 |  | 2026-04-13 | [5 empty] | 2026-04-19 |  | 2026-04-27 |  | 2026-04-28 |  |  |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 | [6 empty] | 2026-05-26 |  | 2026-06-04 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-29 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-05-06 |  | 2026-04-14 |  | Unknown | 2026-03-23 | 2026-03-25 15:13 | 1438886 | 258999 | 0 | 0 | 0 | 0 | 1393535.6 | 230093 | 2026-04-15 15:50:02 +0530 | Bency Chacko | Some Image was uploaded | 2026-04-11 14:07:07 +0530 | Rajavignesh M | Some Image was uploaded | 2026-04-10 18:47:35 +0530 | Bency Chacko |  | 2026-04-19 |  | 2026-04-26 |  | Under Construction | 2026-04-30
19080 | Turnkey | 2026-01-01 | Abhishek Biradar | SSVR Niyaraa | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 1007364 | 9999 | 1007364 | 0 | 0 | 107 | 0 | 90737 | 100736 | 415201 | 390690 |  |  | 2026-03-23 | 2026-03-29 13:37 | 2026-03-29 | 2026-03-30 12:53 | 2026-03-30 | 2026-03-30 13:03 | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Unknown | 2026-03-23 | 2026-03-26 19:58 | 853698 | 153665 | 0 | 0 | 0 | 0 | 853698 | 153665 | 2026-04-14 17:19:34 +0530 | Shashank Singh | Some Image was uploaded | [6 empty] | 2026-04-07 |  | 2026-04-14
19081 | Turnkey | 2026-01-01 | Mrs. Urmila B. Raut B. Raut | Arihant Aspire | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1765349 | 9999 | 0 | 0 | 0 | 81 | 0 | 166536 | 176535 | 789917 | 622362 |  |  | 2026-03-22 | 2026-03-25 12:22 | 2026-04-21 | 2026-04-21 14:32 | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-03-22 | 2026-03-25 12:21 | 0 | 0 | 0 | 0 | 0 | 0 | 1498860 | 266489 | 2026-04-21 14:29:49 +0530 | Maasoumeh Raza | DCM: Name: 19081 - Mrs. Urmila B. Raut B. Raut Property Name: Arihant Aspire Property type: 2bhk Possession: December Move in: Not confirmÂ Member: 5 memberÂ Budget: 12LÂ Requirements: Existing : No Living room: Safety doorÂ Shoe rack Tv UnitÂ MandirÂ 3 + 2seater sofaÂ 6 Seater dining [Option needed] Crockery unit Balcony design option needed.Â Mirror panelling in anyone wallÂ Kitchen : Base unit Wall unit Loft unit Appliance unit Storage above washing machineÂ Kids bedroom: kids room should be spaciousÂ Option for bedÂ Wardrobe with loft side table Study table Master bedroom:Â Queen size bed side table Dressing Unit Study table Bathroom: 2 Below vanity unit Additional scope: Full home False ceiling Painting Electrical | [6 empty] | 2026-05-03 |  | 2026-05-10
19082 | Turnkey | 2026-01-01 | Vidula Pramod Jathar | Damji shamji mahavir spring | MUM - Thane | Yes | Rinisha Masurkar | [7 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1895259 | 9999 | 0 | 0 | 0 | 92 | 0 | 179527 | 189526 | 828330 | 687877.2 |  |  | 2026-03-22 | 2026-03-25 12:20 | 2026-03-24 | 2026-04-09 16:41 | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-04-20 |  | 2026-04-28 |  | 2026-04-29 |  |  |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 | [6 empty] | 2026-05-27 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-08 |  |  |  | 2026-06-30 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-05-07 |  | 2026-04-15 |  | Unknown | 2026-03-22 | 2026-03-25 12:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1606151 | 289107 | [9 empty] | 2026-04-20 |  | 2026-04-27
19083 | Turnkey | 2026-01-01 | Prasad Raut | Mahavir Spring | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Nishtha Valawalkar |  | Active | Design | 20% Payment | 2499443 | 342899 | 3329033 | 0 | 0 | 22 | 40 | 0 | 156990 | 1160000 | 839554 |  |  | 2026-03-22 | 2026-03-25 12:26 | 2026-04-10 | 2026-04-10 12:14 | 2026-04-16 | 2026-04-30 12:52 | 2026-05-15 | 2026-05-14 12:57 | 2026-05-20 |  | 2026-05-27 |  | 2026-04-30 | 2026-04-30 23:37 | 2026-05-01 | 2026-05-02 11:04 | 2026-05-02 | 2026-05-04 14:51 | 2026-05-07 | 2026-05-07 14:12 |  |  |  |  | 2026-06-30 |  | 2026-05-22 |  | 2026-05-23 |  |  |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 | [6 empty] | 2026-06-20 |  | 2026-06-29 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-02 |  |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-31 |  |  |  |  | 2026-03-22 | 2026-03-25 12:24 | 2826543 | 502489 | 0 | 0 | 0 | 0 | 2797973.8909 | 459840 | 2026-06-14 14:54:46 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-22 17:29:09 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-22 14:23:40 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-15 | 2026-05-14 13:00 | 2026-05-21
19088 | Turnkey | 2026-01-01 | Ranjitha Madhan Gowda | Green finch meadows | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1279855 | 9999 | 1279855 | 0 | 0 | 62 | 0 | 117987 | 127986 | 511942 | 511942 |  |  | 2026-03-22 | 2026-03-24 14:16 | 2026-04-26 | 2026-05-14 19:31 | 2026-05-14 | 2026-05-14 19:38 | 2026-05-21 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-15 |  | 2026-05-16 | [5 empty] | 2026-05-22 |  | 2026-05-30 |  | 2026-05-31 |  |  |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 | [6 empty] | 2026-06-28 |  | 2026-07-07 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-08 |  | 2026-05-17 |  | Unknown | 2026-03-22 | 2026-03-24 14:15 | 1084623 | 195232 | 0 | 0 | 0 | 0 | 1084623 | 195232 | 2026-04-29 20:02:59 +0530 | Aparna | RGM Minutes of Meeting (MOM)Client Name: Ranjitha Project: Green Finch Meadows 2BHK Location: Kariyammana Agrahara Meeting Type: CDP Discussion Meeting Date: 30.04.2026 Budget: 8 Lakhs Family Members: 4 (2 Adults + 2 Kids Girl: 5.4 yrs, Boy: 2.6 yrs) Theme: Neutral Entrance Facing: East Design Discussion SummaryEntranceShoe rack to be designed outside the main doorFoyerPOP wall with decorative ledgeBuddha idol placement on ledgeFeature wall design behind Buddha to enhance focal pointLiving RoomSofa Wall Design to be developed based on reference sharedTV Unit Option 1: Stencil design concept (as seen in EC)Option 2: Reference-based designFinal option to be frozen post 3DDining AreaSpace to include aquarium integrationDesign to balance aesthetics + functionalityPooja UnitTo be designed as per Vastu guidelinesPlacement to be finalized in layout stageKitchenInclusion of:Pantry unitWicker basketsMagic corner3 chimneyAppliances to accommodate:MicrowaveMixerAir fryerToasterPopcorn makerSandwich makerKettleAppliance unit to be designed efficiently (Ensure compact planning without consuming excess space)Kids Bedroom (KBR)Study table integrated with wardrobe unitFocus on maximum storageWall design in unisex kids themeMaster Bedroom (MBR)Provision for photo frame (client to share dimensions)Wardrobe with:Extra storage for used clothesAttached dresser unitWashroomsVanity units to be designed (details to be finalized)Â | [6 empty] | 2026-05-22 |  | 2026-05-29
19089 | Turnkey | 2026-01-01 | Mahaveer jain | Mantri blosssom | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 4730575 | 9999 | 0 | 0 | 0 | 103 | 0 | 463059 | 473058 | 1995777 | 1788682.8 |  |  | 2026-03-24 | 2026-04-03 19:23 | 2026-04-03 | 2026-04-03 19:23 | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Unknown | 2026-03-24 | 2026-04-03 11:22 | 0 | 0 | 0 | 0 | 0 | 0 | 4008962 | 721613 | 2026-04-03 11:45:21 +0530 | Aparna | RGM Cx NameÂ - MahaveerÂ Crm - Aman RGM -24/03/26 Move in date -Â Â Budget -Â 30L Property name - Direction - n facingÂ F to c - 11' Modular kitchenÂ Base unitÂ Wall unitÂ LoftÂ Built in hobÂ double door fridgeÂ 1000mm both walls are not thereÂ in kitchen entrance wallsÂ sink on right side wallÂ fridge on left side wallÂ hob on right side wallÂ induction need to be planned near hob unitÂ tall unitÂ oven spaceÂ Counter top from cx end utilityÂ washing machineÂ dishwasherÂ sink unitÂ Dinning areaÂ corckery unitÂ fc in dinning areaÂ centralised acÂ 8 seater dinning tableÂ LIving roomÂ double height ceilingÂ fcÂ wall conecptÂ sofa placementÂ Pooja unit roomÂ Â deapth 2ftÂ Foyer unitÂ consal taunitÂ wall decorÂ Bedroom 1 (GBR) wardrobe and dressers Washroom designeÂ 25th floor Bedrroom 5Â mbrÂ wardrobeÂ air hingsÂ tv unitÂ bed designÂ washroom designÂ washroom Door we are sifting to sink wallÂ sliding door near to kids bedroom - 2Â Wardrobe andÂ next to the main doorÂ bay window + studyÂ fc in all rooms kids bedroomÂ -Â 2Â wardrobeÂ opp to bedwallÂ dresserÂ Â arch sahpe partiton for study unit placeÂ Family roomÂ above foyer areaÂ beige marbleÂ woodern flooring fpr all roomÂ not in gbr | [6 empty] | 2026-04-14 |  | 2026-04-21
19092 | Turnkey | 2026-01-01 | Jinen Maheshwari | Arcade Nest, Mulund | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 6171608 | 9999 | 0 | 0 | 0 | 80 | 0 | 607162 | 617161 | 2763840 | 2173446.4 |  |  | 2026-03-22 | 2026-04-26 13:59 | 2026-04-26 | 2026-05-07 14:11 | 2026-04-26 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-05-18 |  | 2026-05-26 |  | 2026-05-27 |  |  |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 | [6 empty] | 2026-06-24 |  | 2026-07-03 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-06-04 |  | 2026-05-13 |  | Unknown | 2026-03-22 | 2026-04-24 18:55 | 0 | 0 | 0 | 0 | 0 | 0 | 5230176 | 941431 | 2026-04-18 20:00:49 +0530 | Rutuja Kotwal | DCM: Mr. Jinen Maheshwari 4 BHK. Arkade Nest Mulund west. Possession - Dec. 26. Move in - husband, wife, daughter - 10 yrs. and Parents - around 70 yrs. Profession - Invest Banker. Urvi madam - Teacher. Design as per Vastu. Direction - Exiting West Living room - TV unit, Vertico synchro Mandir, swing if possible, 6 seater dining table,. keeping the walls and making a Pantry storage opening from kitchen, crockery unit and Sofa (curved), POP mural art. Kitchen - Base units, Wall units and Lofts, appliances unit. shifting the sink in the place of fridge. Storage in the passage. Daughter's Bedroom - Bed to the window side , Wardrobe with Lofts, Partition, study unit with tall storage. Guest bedroom- Murphy Bed, Wardrobe. Master Bedroom- Bed, Wardrobe w/o lofts, Aristo wardrobe in walk- in space, dresser in walk- in space, Demolition of the center wall, l-shaped Study desk on the window wall, sitting to be provided. Vanity cabinets in all bathrooms. Parents Bedroom - Bed, Aristo Wardrobe, side tables, folding study. CDP - 26th April at 11am. Budget- 50-60 lakhs. | [6 empty] | 2026-05-18 |  | 2026-05-25
19094 | Turnkey | 2026-01-01 | Vijith Shilpa Menon | Sheth Montana | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  | Krutika Date | suraj kumar | Aditya Vikram |  | Ishan Patle | Prasad Bhivaji Hande | Active | Preproduction | Site Readiness 2 | 2444965 | 1578346 | 2979641 | 2181423 | 2474424 | 4 | 0 | 0 | 0 | 0 | 866619 |  |  | 2026-03-21 | 2026-03-30 17:13 | 2026-03-24 | 2026-03-30 21:01 | 2026-04-02 | 2026-03-30 21:02 | 2026-04-15 | 2026-04-14 12:04 | 2026-04-26 | 2026-04-26 11:00 | 2026-06-19 | 2026-06-19 19:59 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-09 11:06 | 2026-04-09 | 2026-04-09 14:04 | 2026-04-11 | 2026-04-11 12:12 |  |  |  |  | 2026-04-14 | 2026-04-15 19:00 | 2026-06-17 | 2026-06-16 18:39 | 2026-06-17 | 2026-06-16 18:40 |  |  | 2026-06-24 | 2026-07-02 18:49 | 2026-07-02 | 2026-07-02 20:53 | 2026-07-03 | 2026-07-03 21:04 | 2026-07-04 | 2026-07-11 13:13 | [5 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-02 |  | 2026-04-12 | 2026-04-14 11:48 | Site is RTMI | 2026-03-21 | 2026-03-30 17:11 | 2525119 | 454521 | 2363654.8976 | 393776 | 2631907.9534 | 438471 | 2604918.0382 | 433977 | 2026-06-28 16:38:11 +0530 | Krutika Date | Some Image was uploaded | 2026-05-07 18:28:11 +0530 | Anil Kuwar | Some Image was uploaded | 2026-04-11 12:14:26 +0530 | Anamika Dolai | Done, explained milestones, DEM1- 12/04/2. | 2026-04-15 | 2026-04-14 12:09 | 2026-05-03 | 2026-05-06 14:19
19098 | Turnkey | 2026-01-01 | Tiss Thomas | sobha dream garden | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | Sushma Hm |  |  |  |  | Mohammed Rasick |  | Lost | Design | 20% Payment | 1111747 | 141999 | 1420244 | 0 | 0 | 76 | 0 | 0 | 80350 | 491201 | 398196.8 |  |  | 2026-03-24 | 2026-03-24 18:40 | 2026-03-25 | 2026-03-25 15:07 | 2026-03-28 | 2026-03-28 15:20 | 2026-05-01 | 2026-04-30 20:00 | 2026-05-09 |  | 2026-05-06 |  | 2026-03-28 | 2026-03-31 00:50 | 2026-03-29 | 2026-03-31 11:08 | 2026-03-31 | 2026-03-31 18:16 | 2026-04-05 | 2026-04-05 12:42 |  |  |  |  | 2026-05-06 |  | 2026-05-20 |  | 2026-05-21 |  |  |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 | [6 empty] | 2026-06-27 |  | 2026-07-06 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-09 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-07 |  | 2026-04-22 | 2026-04-30 18:44 | Site is RTMI | 2026-03-24 | 2026-03-24 15:48 | 1203597 | 216647 | 0 | 0 | 0 | 0 | 1147062.8471 | 193662 | 2026-04-16 11:53:57 +0530 | Ehthisham Durgam | CDP: Minutes of Meeting (MOM) Client Name: Tiss Thomas KitchenAdd gold strip in shutterChange the color of tiles Living RoomChange TV unit colorModify back wall designRemove curve design and replace with straight lightingDining wall design to be confirmedUpdate color shades to lighter tonesCornice cost is not included BedroomRemove seater and relocate it to the balcony (cost not included)Change wardrobe colorWallpaper to be confirmedCheck requirement for study table Master BedroomChange colors and wallpaperProvide loft with glass shuttersBack panel to be done in gypsum (client to be informed that execution may be slightly challenging)Toilet vanity drawers should be checked according to site condition | 2026-04-05 12:41:07 +0530 | Parasa Sri | Welcome call done. Initial measurements can be done. Need priour meeting intimatimation for further meeting | 2026-03-31 18:15:50 +0530 | Bency Chacko | B2C - Self-funding Possession - RTMI IMs can be done design meetings can be done No on-site work is planned No civil work is planned The customer is available on weekends for design meetings, and once closed with LFM, she can close the 10% as per the process (expected by 15th April 2026) Checklist cleared Timelines cleared Agreement terms cleared Offers Quote and Scope are cleared | 2026-05-01 | 2026-04-30 20:03 | 2026-05-10 |  | RTMI
19100 | Turnkey | 2026-01-01 | SHIVANI DURGESH MASUREKAR | om Paras | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  | Mohammed Lal | Uday Yadruk | Sandeep Tiwari | Murali S | Harshaan Tiku | Aakash Gaikwad | Active | Installation | Execution | 1603675 | 1603675 | 1382438 | 0 | 1603675 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-24 | 2026-03-24 20:02 | 2026-03-25 | 2026-03-25 18:20 | 2026-03-24 | 2026-03-25 19:01 | 2026-04-05 | 2026-04-05 20:25 | 2026-04-16 | 2026-04-15 16:17 | 2026-05-16 | 2026-05-16 16:34 | 2026-03-25 | 2026-03-26 19:54 | 2026-03-26 | 2026-03-27 14:27 | 2026-03-27 | 2026-03-30 11:54 | 2026-03-31 | 2026-03-31 20:29 |  |  |  |  | 2026-04-05 | 2026-04-09 19:13 | 2026-04-18 | 2026-04-17 18:04 | 2026-04-18 | 2026-04-17 18:04 |  |  | 2026-05-22 | 2026-05-23 20:21 | 2026-05-25 | 2026-05-25 18:20 | 2026-05-26 | 2026-05-25 18:22 | 2026-05-27 | 2026-05-26 18:53 |  |  |  |  | 2026-05-30 13:12 | 2026-06-12 | 2026-06-11 21:03 | 2026-06-26 | 2026-06-22 19:02 | 2026-06-19 | 2026-06-19 18:54 | 2026-06-22 | 2026-06-24 18:34 | 2026-06-24 | 2026-06-28 00:27 | 2026-06-30 | 2026-07-11 12:58 |  |  | 2026-07-18 |  | 2026-07-21 |  | 2026-07-21 | [5 empty] | 2026-05-25 | 2026-05-27 19:12 | 2026-04-08 | 2026-04-05 20:21 | Site is RTMI | 2026-03-24 | 2026-03-24 20:01 | 1173845 | 208593 | 0 | 0 | 1674956.1507 | 285463 | 1674956.1507 | 285463 | 2026-07-13 18:39:50 +0530 | Uday Yadruk | Execution: Modular installation - completed ( profile shutter installation pending ) Painting work - 1st coat of painting work has been completed Final coat of paint - final coat of painting work is in progress and this will be completed by 16/07/2026 Deep cleaning - 17-07/2026 Site Handover - 18-07-2026 | 2026-06-08 21:16:04 +0530 | Uday Yadruk | Execution: Floor protection work - completed AC pelmet work - completed Electrical point shifting work - completed POP work - in progress ( AC pelmet finishing & Elc zari work finishing ) 1st coat painting work - 10th june ( start date ) site ready for the modular delivery - 18th june 2026 | 2026-06-05 13:21:25 +0530 | Uday Yadruk | Some Image was uploaded | 2026-04-06 | 2026-04-05 20:28 | 2026-04-16 | 2026-04-15 16:18
19102 | Turnkey | 2026-01-01 | Nidhin Raj | Runwal Sanctuary | MUM - Thane | No Estimate | [8 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 113 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-24 | 2026-03-24 19:06 | 2026-03-25 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-04-06 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 | [6 empty] | 2026-05-13 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-25 |  |  |  | 2026-06-16 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-04-23 |  | 2026-04-01 |  | Unknown | 2026-03-24 | 2026-03-24 19:05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-24 19:07:35 +0530 | Saloni Chawan | Some Image was uploaded | [6 empty] | 2026-04-06 |  | 2026-04-13
19107 | Turnkey | 2026-01-01 | Mitesh Dusara | 34 PARK ESTATE | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Kashmira Nerurkar |  |  | Shashwat Joshi | Rizwan Mistry |  | Manasi Patil | Prasad Bhivaji Hande | Active | Preproduction | 2D | 1791611 | 357999 | 2269420 | 0 | 0 | 12 | 0 | 0 | 0 | 785568 | 648044 |  |  | 2026-03-22 | 2026-03-26 13:15 | 2026-03-26 | 2026-03-26 13:26 | 2026-03-31 | 2026-03-31 14:11 | 2026-04-19 | 2026-04-19 14:48 | 2026-05-21 | 2026-05-20 13:04 | 2026-06-21 | 2026-06-21 15:03 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 11:24 | 2026-04-01 | 2026-04-03 10:23 | 2026-04-04 | 2026-04-04 13:58 |  |  |  |  | 2026-04-19 | 2026-04-27 19:16 | 2026-05-23 | 2026-05-25 09:28 | 2026-05-26 | 2026-05-25 11:22 |  |  | 2026-06-27 | 2026-07-03 18:21 | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-16 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-14 |  | 2026-09-18 |  |  |  | 2026-11-07 |  | 2026-11-08 |  | 2026-11-11 | [5 empty] | 2026-07-22 |  | 2026-04-05 | 2026-04-15 19:41 | Site is RTMI | 2026-03-22 | 2026-03-26 13:14 | 1925734 | 343686 | 0 | 0 | 0 | 0 | 1905205.4978 | 320376 | 2026-06-29 13:09:46 +0530 | Zoya Ansari | Some Image was uploaded | 2026-06-10 13:39:35 +0530 | Zoya Ansari | DDM3: Design Discussion with materials June 6th Desoping the civil work completely Finalise the materials and chose membrane | 2026-05-27 16:29:44 +0530 | Safalta Karkera | Some Image was uploaded | 2026-04-20 | 2026-04-19 15:05 | 2026-05-21 | 2026-05-20 13:06
19108 | Turnkey | 2026-01-01 | Dheeraj dave | rajyog society | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 1307818 | 9999 | 1307818 | 0 | 0 | 103 | 0 | 120783 | 130782 | 572710 | 473544 |  |  | 2026-03-24 | 2026-03-25 18:53 | 2026-04-03 | 2026-04-03 17:10 | 2026-04-06 | 2026-04-03 17:12 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-24 | 2026-03-25 16:29 | 1372325.4129 | 222761 | 0 | 0 | 0 | 0 | 1372325.4129 | 222761 | 2026-03-25 18:54:14 +0530 | Mrunali Mitkari | Some Image was uploaded | [6 empty] | 2026-04-11 |  | 2026-04-18
19109 | Turnkey | 2026-01-01 | Hemant Naresh Sawant | LODHA AMARA | MUM - Thane | Yes | Rutuja Kotwal | Anamika Dolai | [6 empty] | vinaya thakur |  | Active | Prospect | DCM Due | 2116145 | 9999 | 0 | 0 | 0 | 112 | 0 | 201616 | 211615 | 868473 | 824442.8 |  |  | 2026-03-21 | 2026-03-25 18:16 | 2026-03-25 | 2026-04-22 12:15 | 2026-03-26 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-03-21 | 2026-03-25 18:11 | 0 | 0 | 0 | 0 | 0 | 0 | 2255185.968 | 372378 | 2026-04-15 16:41:39 +0530 | vinaya thakur | Some Image was uploaded | 2026-03-25 21:02:24 +0530 | Rutuja Kotwal | DCM: Mr. Hemant SawantÂ Â 3 BHK.Â Â Lodha AmaraÂ Area-Â 948 sq. Ft.Â Â Possession In Hand.Â Â Design as perÂ VastuÂ Â CX. Has their own VastuÂ Consultant.Â Â Direction-Â North east.Â Â Profession Banker.Â Â WifeÂ Teacher.Â Â Move in 5 people Husband, wife, 2 Kids 1 daughter and 1 son 21yrs. And 13 respectively andÂ Mother in law.Â Living room Storage in the foyer from ceiling to floor,Â Camouflage of bedroom door, sofa, TV unit- 80"Â with Mandir unit-Â 1'6 wide (suspended),Â 4 seaterÂ dining table, Crockery unit.Â Â KitchenÂ BaseÂ units, Wall Units and Lofts.Â Â Daughters Bedroom -Â ( BedroomÂ 3 )Â - Bed, Wardrobe with Lofts,Â Study unit with Above cabinet, Dressing unit cum side table. Vanity Unit in Bathroom.Â Â Parents Bedroom-Â ( Bedroom) -Â Sofa cum Bed, Wardrobe withÂ Lofts,Â LoftÂ above door,Â Study unit with Above cabinet, Dressing unit cum side table. Vanity Unit in common Bathroom.Â MBR-Â Loft above door,Â Wardrobe with Lofts, Dressing table near window,Â Work stationÂ with above cabinets,Â TV unit withÂ Paneling.,Â Vanity Unit inÂ MasterÂ Bathroom.Â Budget 15 lakhs.Â Â Budget suggested 25- 30 lakhs.Â Â CDP- 26thÂ March at 3 pm.Â Â |  |  |  | 2026-05-03 |  | 2026-05-10
19111 | Sub Project |  | Vishal Bhatia | Asteria courtyard | MUM - Thane |  | Naved Malik | Divya Rahangdale | Sneha Kadam |  |  | Asif Shaikh | Aditya Vikram | Murali S |  | Aakash Gaikwad | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-25 | 2026-03-29 16:06 | 2026-03-26 | 2026-03-29 16:06 | 2026-03-29 | 2026-03-29 16:07 | 2026-03-30 | 2026-03-29 16:08 | 2026-03-30 | 2026-03-29 16:10 | 2026-03-30 | 2026-03-29 16:15 | 2026-03-29 | 2026-03-29 16:07 | 2026-03-30 | 2026-03-29 16:07 | 2026-03-29 | 2026-03-29 16:07 | 2026-03-30 | 2026-03-29 16:07 |  |  |  |  | 2026-03-29 | 2026-03-29 16:08 | 2026-03-30 | 2026-03-29 16:13 | 2026-03-30 | 2026-03-29 16:13 |  |  | 2026-03-30 | 2026-03-30 17:49 | 2026-03-31 | 2026-03-31 11:16 | 2026-04-01 | 2026-04-04 13:13 | 2026-04-05 | 2026-04-04 13:13 |  |  |  |  | 2026-04-04 13:14 | 2026-04-12 | 2026-04-11 14:22 | 2026-04-13 | 2026-04-11 14:49 | 2026-04-12 | 2026-04-28 19:02 | 2026-04-11 | 2026-04-29 13:00 | 2026-04-28 | 2026-04-29 13:05 | 2026-04-30 | 2026-04-29 22:06 |  |  | 2026-05-01 | 2026-04-30 14:09 | 2026-05-02 | 2026-04-30 14:28 | 2026-04-30 | 2026-04-30 17:59 |  |  |  |  | 2026-03-31 | 2026-03-31 19:03 | 2026-03-30 | 2026-03-29 16:07 | Unknown | 2026-03-25 | 2026-03-29 16:06 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | [9 empty] | 2026-03-30 | 2026-03-29 16:08 | 2026-03-30 | 2026-03-29 16:12
19115 | Sub Project |  | WERMORE SOLUTIONS PVT LTD | Raymond | MUM - Thane | Yes | Harshali Bhuyar | Anamika Dolai | Sneha Kadam |  | Nilofer Shaikh |  |  |  |  | Shailendra Mishra | Active | Preproduction | 3D Sign off | 602628 | 0 | 0 | 0 | 642412 | 99 | 0 | 0 | 0 | 372437 | 230191.2 |  |  | 2026-03-26 | 2026-04-02 19:12 | 2026-03-27 | 2026-04-02 19:12 | 2026-04-02 | 2026-04-02 19:12 | 2026-04-03 | 2026-04-02 19:13 | 2026-04-03 | 2026-04-02 19:14 | 2026-04-03 | 2026-04-02 19:15 | 2026-04-02 | 2026-04-02 19:12 | 2026-04-03 | 2026-04-02 19:12 | 2026-04-02 | 2026-04-02 19:12 | 2026-04-03 | 2026-04-02 19:12 |  |  |  |  | 2026-04-02 | 2026-04-02 19:13 | 2026-04-05 | 2026-04-02 19:14 | 2026-04-04 | 2026-04-03 20:10 |  |  | 2026-04-10 | 2026-04-07 15:03 | 2026-04-07 | 2026-04-07 17:50 | 2026-04-08 |  | 2026-04-09 | [6 empty] | 2026-04-27 |  | 2026-05-06 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-09 |  |  |  | 2026-05-31 |  | 2026-06-02 |  | 2026-06-03 | [5 empty] | 2026-04-07 |  | 2026-04-03 | 2026-04-02 19:12 | Unknown | 2026-03-26 | 2026-04-02 19:12 | 0 | 0 | 0 | 0 | 544416 | 97995 | 544416.8788 | 91926 | 2026-04-05 11:13:45 +0530 | Nilofer Shaikh | Some Image was uploaded | [6 empty] | 2026-04-03 | 2026-04-02 19:13 | 2026-04-03 | 2026-04-02 19:14
19118 | Turnkey | 2026-01-01 | Irshad Supariwala | Independent Apartment, | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 829198 | 9999 | 829198 | 0 | 0 | 84 | 0 | 72921 | 82920 | 361513 | 301845.6 |  |  | 2026-03-18 | 2026-04-22 12:06 | 2026-04-22 | 2026-04-22 12:09 | 2026-04-22 | 2026-04-22 12:15 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-18 | 2026-03-31 20:45 | 702710 | 126487 | 0 | 0 | 0 | 0 | 702710 | 126487 | 2026-05-04 15:53:15 +0530 | Rhea Rathod | DCM: Possession - 2 months Family of 4 Profession - real estate Site access - available East facing main door Blue, green, white, beige, golden, black Living - - Passage for wall concept - Reading nook - wall concept TV unit - Optional - Wall mounted - Partition - to divide living and dining Kitchen- - Acrylic kitchen - Glass cabinets - Loft - Double door fridge - Green acrylic, wood, black accents, glass Master bedroom - Aristo carcass - dresser - Wall concept Bedroom 1 - left - Aristo carcass - Dresser unit - Wall concepts Bedroom 2 - Right - Aristo carcass - Dresser unit - Wall concepts MOM - Foyer - seating area - fixed for the foyer place. - Bevelled mirror - rose gold - full wall - Hob position - to be interchanged - crockery unit with bevelled mirror - Fridge position - Bottom drawer - kitchen - with wooden patta as shown in the reel (a kitchen drawer unit) - Partition - at the entrance - Tall unit with drawers as shown | 2026-04-14 16:41:40 +0530 | Shashank Singh | Some Image was uploaded |  |  |  | 2026-04-30 |  | 2026-05-07
19119 | Turnkey | 2026-01-01 | Kavita Kamble | Damji shamji mahavir spring | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar |  |  | Tanveer Patel | Akshat Shrivastava |  | Nishtha Valawalkar | Prasad Bhivaji Hande | Active | Design | DEM3 | 1662233 | 301199 | 1456625 | 0 | 0 | 1 | 43 | 0 | 0 | 766558 | 594475.6 |  |  | 2026-03-26 | 2026-03-26 19:11 | 2026-04-08 | 2026-04-09 11:53 | 2026-04-11 | 2026-04-11 22:58 | 2026-04-24 | 2026-04-24 19:29 | 2026-06-11 | 2026-06-10 16:49 | 2026-07-18 |  | 2026-04-11 | 2026-04-14 18:29 | 2026-04-12 | 2026-04-14 18:49 | 2026-04-14 | 2026-04-15 15:42 | 2026-04-22 | 2026-04-22 18:32 |  |  |  |  | 2026-04-19 | 2026-04-14 18:29 | 2026-07-06 | 2026-07-12 23:17 | 2026-07-13 | 2026-07-14 08:00 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-04-23 | 2026-04-24 19:25 | Site is Non-RTMI | 2026-03-26 | 2026-03-26 19:08 | 1234428 | 222197 | 0 | 0 | 0 | 0 | 1810547.4459 | 298942 | 2026-07-03 13:24:08 +0530 | Monika Pal | 2026-07-03 | 2026-07-03 13:23:29 +0530 | Monika Pal | 2026-07-03 | 2026-07-02 19:41:22 +0530 | Anamika Dolai | Civil work is going on at the site , posession around 10th of july. | 2026-04-25 | 2026-04-24 19:58 | 2026-06-11 | 2026-06-10 16:52
19120 | Turnkey | 2026-01-01 | Mr.Jayant Mallick | Mahindra Alcove | MUM - GOR | No Estimate | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-22 | 2026-03-27 12:53 | 2026-05-20 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-03-22 | 2026-03-26 19:37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-17 18:44:22 +0530 | Saloni Sagwekar | Some Image was uploaded | [6 empty] | 2026-06-08 |  | 2026-06-15
19121 | Turnkey | 2026-01-01 | Shivam Mishra | Kanakia Silicon Future City | MUM - GOR | No Estimate | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-26 | 2026-03-27 13:05 | 2026-03-28 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-03-26 | 2026-03-26 19:37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-14 16:42:16 +0530 | Saloni Sagwekar | Some Image was uploaded | [6 empty] | 2026-04-08 |  | 2026-04-15
19123 | Turnkey | 2026-01-01 | Joseph | Casagrand Amor | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 2060314 | 9999 | 0 | 0 | 0 | 111 | 0 | 196032 | 206031 | 824126 | 824125.6 |  |  | 2026-03-26 | 2026-03-26 20:01 | 2026-04-19 | 2026-04-19 15:12 | 2026-04-19 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-20 |  | 2026-04-21 | [5 empty] | 2026-04-27 |  | 2026-05-05 |  | 2026-05-06 |  |  |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 | [6 empty] | 2026-06-03 |  | 2026-06-12 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-15 |  |  |  | 2026-07-07 |  | 2026-07-09 |  | 2026-07-10 | [5 empty] | 2026-05-14 |  | 2026-04-22 |  | Unknown | 2026-03-26 | 2026-03-26 19:29 | 0 | 0 | 0 | 0 | 0 | 0 | 1746029 | 314285 | 2026-04-10 13:45:03 +0530 | Aparna | RGM Â Minutes of Meeting (MOM)Client DetailsClient Name: JosephProperty: Casagrand AmorConfiguration: 3BHKFacing: EastPossession Timeline: JuneFamily Members: 4Son: Riyan (14 years)Daughter: Jola (11 years)Next Meeting: After 2 weeksBudget: 15 LakhsDesign Theme: Minimalistic & Modern Living RoomTV unit to be wall-mountedBack panel with lightingSleek tall unit with glass shutters (same placement)Sofa wall to be highlighted (feature wall design)Provision for book shelves Dining / CrockeryDedicated crockery unit to be designed KitchenAppliances to be accommodated:MicrowaveRODishwasherLoft storage requiredCountertop: Provided by builderCylinder unit requiredBasic lightingShutter finish: Combination of glass + plain shutters Common AreasCommon wash basin unit to be designed Utility AreaWall storage on East wall Passage AreaPhoto wall concept BalconyJanitor/storage unit requiredAquarium to be accommodated (placement to be suggested) Master Bedroom (MBR)Hinged wardrobe + loftStudy unit opposite to bed + minimal TV unitBed back wall highlightingDresser unit Kids Bedroom (Next to Passage)Sliding wardrobe + loftFull-length mirror on adjacent wallMedium-size bedBed back wall highlighting (wallpaper/design)Open tall storage for toys next to wardrobePhoto wall opposite bed Sons BedroomWardrobe + L-corner study unitSmall TV unit with panel + ledgeWallpaper / wall design WashroomsAll washrooms to include:Vanity base unitMirror False Ceiling DesignLiving & Dining: Peripheral false ceilingMaster Bedroom: False ceiling above bedDaughters Bedroom: False ceiling focusing study areaSons Bedroom: Minimal false ceiling for highlighting | [6 empty] | 2026-04-27 |  | 2026-05-04
19125 | Turnkey | 2026-01-01 | Irisha Gaglani | laabh chs | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1595572 | 9999 | 1595572 | 0 | 0 | 103 | 0 | 149558 | 159557 | 683984 | 592473.2 |  |  | 2026-03-26 | 2026-04-03 15:48 | 2026-04-03 | 2026-04-03 15:49 | 2026-04-03 | 2026-04-03 15:53 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-26 | 2026-04-03 15:48 | 1715452.0777 | 284197 | 0 | 0 | 0 | 0 | 1715452.0777 | 284197 | 2026-04-08 11:13:39 +0530 | Meet Shah | Some Image was uploaded | [6 empty] | 2026-04-11 |  | 2026-04-18
19126 | Turnkey | 2026-01-01 | ramya | goderaj park retreat | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1593013 | 9999 | 0 | 0 | 0 | 111 | 0 | 149302 | 159301 | 670549 | 603861.2 |  |  | 2026-03-26 | 2026-03-26 20:06 | 2026-03-31 |  | 2026-03-30 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-26 | 2026-03-26 20:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1350011 | 243002 | 2026-03-30 14:08:52 +0530 | Aparna | MOM Interior Design DiscussionClient DetailsClient Name: Ramya SProperty: Godrej ParkConfiguration: 2BHKFacing: SouthPossession Status: CompletedMembers: 3Kids: NoDesign OverviewTheme: Gold & IvoryBudget: 15L 18LNext Design Meeting: Yet to be confirmedArea-wise RequirementsFoyerMirror with brushed gold borderConsole tableOne focus lightWall trimsLiving AreaTV Unit (reference image taken)Puja Unit:Wood finish with golden bellsOption: TV + Puja combination (Yet to confirm)Sofa wall: Minimal designColor Theme: Navy BlueFalse Ceiling: PeripheralKitchenColor Theme: Sage Green & IvoryShutters:Mix of normal + fluted glass shuttersHandles: Antique gold finishGranite:Black (Black & white option to be explored)Dado tilesPantry unit + Rolling shutters (for appliances & big vessels)Appliances to accommodate:Mixer, Oven, Air Fryer, KettleUnits:Base, Wall & LoftUtility Area:Base unit + Wall cabinets (Loft if feasible)False Ceiling: PeripheralBedroom 2 (with Study)Wardrobe: Sliding (final type yet to be decided)Study Unit:L-shapedWith glass shuttersWall Design:Tropical wallpaper on bed back wallColor Theme: Sage GreenFalse Ceiling: PeripheralMaster BedroomColor Theme: Rose Pink, Gold & IvoryBed back wall design (reference taken)Wardrobe:Pink & white combinationGolden handlesMirror in one shutterTwo drawers below mirrorWardrobe design & color reference shared in groupFalse Ceiling: IncludedWashrooms (Both)Storage above WCVanity unitsMirrorsPending / To Be ConfirmedTV + Puja unit combinationBedroom 2 wardrobe type (sliding variant selection)Granite option (black vs black & white)Utility loft feasibilityNext meeting schedule | [6 empty] | 2026-04-11 |  | 2026-04-18
19127 | Turnkey | 2026-01-01 | SSVR Constructions | SSVR NIYAARA | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | 20% Payment | 1483782 | 140000 | 2185860 | 0 | 0 | 6 | 0 | 0 | 156756 | 639744 | 547282 |  |  | 2026-03-26 | 2026-03-30 15:18 | 2026-03-30 | 2026-03-30 15:25 | 2026-03-30 | 2026-03-30 15:58 | 2026-07-10 | 2026-07-09 19:19 | 2026-07-31 |  | 2026-08-11 |  | 2026-03-30 | 2026-03-31 | 2026-03-31 | 2026-04-06 21:15 | 2026-04-06 | 2026-04-08 18:41 | 2026-04-11 | 2026-04-11 19:18 |  |  |  |  | 2026-07-21 |  | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-05-22 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-05-16 | 2026-05-20 18:36 | Site is RTMI | 2026-03-26 | 2026-03-28 14:57 | 1852424 | 333436 | 0 | 0 | 0 | 0 | 1958997 | 352619 | 2026-06-05 15:25:08 +0530 | Prathyusha Elangovan | Cx is fine with the layout. No changes in the designs as per today's meeting Needs approval from his MD. Connecting on Tuesday for Layout finalization. | 2026-05-24 13:12:18 +0530 | Prathyusha Elangovan | SSVR CONSTRUCTION(SAI KRISHNA)MOM-DESIGN BRIEF 22/05/26 TV UNIT-WALL MOUNTED GLASS TALL UNIT DESIGN TO BE SUGGESTED AS PER THE COLUMN AND THE BEAM SOFA ADJ WALL -WALLPAPER WITH WALL TRIMS(REFER THE RENDER CROCKERY DESIGN NEEDS TO BE SUGGESTED+WASH BASIN UNIT KITCHEN WITH LOFT GRANITE-BONITO SCOPE KIDS-DRESSER DESIGN BED BACK WALL SAME DESIGN BED PLACEMENT NEEDS TO BE CONFIRMED MBR-SAME DESIGN BAY WINDOW SEATER WITH STORAGE-MBR GBR-SAME DESIGN(DRESSER DESIGN NEEDS TO BE SUGGESTED) BED BACK WALL DESIGN TO BE THE SAME | 2026-04-23 17:31:36 +0530 | Kowshik | Some Image was uploaded | 2026-07-10 | 2026-07-09 19:24 | 2026-08-01 |  | RTMI
19128 | Turnkey | 2026-01-01 | Mehul Thakkar | Runwal Sanctuary | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Aryan Singh |  | Hold | Preproduction | Site Readiness 1 | 1901146 | 380229.2 | 2440232 | 0 | 0 | 0 | 99 | 0 | 0 | 844409 | 676507.6 |  |  | 2026-03-26 | 2026-03-27 12:12 | 2026-03-31 | 2026-03-31 21:25 | 2026-03-31 | 2026-03-31 21:31 | 2026-04-30 | 2026-04-30 18:44 | 2026-07-05 |  | 2026-07-12 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-02 06:54 | 2026-04-02 | 2026-04-03 10:56 | 2026-04-07 | 2026-04-07 15:39 |  |  |  |  | 2026-07-05 | 2026-04-15 18:32 | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-07-16 |  | 2026-06-30 | 2026-04-30 18:33 | Site is Non-RTMI | 2026-03-26 | 2026-03-27 12:12 | 2067994 | 372238 | 0 | 0 | 0 | 0 | 2067993.1659 | 339581 | 2026-07-14 17:19:00 +0530 | Anamika Dolai | Possession- August'26 | 2026-04-07 15:43:43 +0530 | Anamika Dolai | Done, explained the milestones. | 2026-04-03 10:56:25 +0530 | Royden Henriques | ______________________________________ Possession : june'26 Payment Mode : B2C Self funding - Yes CX will pay 10% on 12h April Runwal Sanctuary Tower 2 - 906, L B, Infinity Road, Sambhaji Nagar, Mulund West, Mumbai, Maharashtra 400080 mehulht@gmail.com Post offers the amount is 19,01,147/- as per the offer email. 99+15=115 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays | 2026-05-01 | 2026-04-30 18:46 | 2026-07-06
19130 | Turnkey | 2026-01-01 | Kartavya Jani | DEM Pheonix | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 1130373 | 9999 | 1130373 | 0 | 0 | 107 | 0 | 103038 | 113037 | 466389 | 437909.2 |  |  | 2026-03-22 | 2026-03-28 20:54 | 2026-03-29 | 2026-03-29 21:43 | 2026-03-30 | 2026-03-30 17:22 | 2026-04-06 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-03-30 |  | 2026-03-31 |  | 2026-03-31 |  | 2026-04-01 | [5 empty] | 2026-04-07 |  | 2026-04-15 |  | 2026-04-16 |  |  |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 | [6 empty] | 2026-05-14 |  | 2026-05-23 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-26 |  |  |  | 2026-06-17 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-04-24 |  | 2026-04-02 |  | Unknown | 2026-03-22 | 2026-03-28 20:53 | 957943 | 172429 | 0 | 0 | 0 | 0 | 957943 | 172429 | 2026-04-15 18:23:12 +0530 | Manasi Patil | Some Image was uploaded | [6 empty] | 2026-04-07 |  | 2026-04-14
19131 | Turnkey | 2026-01-01 | Lina Sabnani | rustomjee paramount | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 1862908 | 9999 | 1862908 | 0 | 0 | 96 | 0 | 176292 | 186291 | 800786 | 689540.8 |  |  | 2026-03-26 | 2026-03-28 15:56 | 2026-03-28 | 2026-04-03 12:03 | 2026-04-10 | 2026-04-10 13:00 | 2026-04-17 |  | 2026-04-24 |  | 2026-05-01 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-11 |  | 2026-04-12 | [5 empty] | 2026-04-18 |  | 2026-04-26 |  | 2026-04-27 |  |  |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 | [6 empty] | 2026-05-25 |  | 2026-06-03 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-06 |  |  |  | 2026-06-28 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-05-05 |  | 2026-04-13 |  | Unknown | 2026-03-26 | 2026-03-28 15:44 | 1581023 | 281885 | 0 | 0 | 0 | 0 | 1581023 | 281885 | [9 empty] | 2026-04-18 |  | 2026-04-25
19132 | Turnkey | 2026-01-01 | Mrs. Kalpana Rajpurkar | Hub tower | MUM - GOR | Yes | Riddhi Deshpande | Manzoor Shaikh | Kashmira Nerurkar |  | Urvisha Prajapati | Nilesh Patel | Rizwan Mistry | Murali S | Umang Shah | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 1726513 | 1059398 | 1701343 | 0 | 1726513 | 6 | 5 | 0 | 0 | 0 | 0 |  |  | 2026-03-26 | 2026-03-29 23:29 | 2026-03-30 | 2026-03-30 10:53 | 2026-04-02 | 2026-03-30 13:04 | 2026-04-09 | 2026-04-09 13:16 | 2026-05-08 | 2026-05-07 17:43 | 2026-05-29 | 2026-05-29 16:39 | 2026-03-30 | 2026-03-30 18:28 | 2026-03-31 | 2026-04-01 17:48 | 2026-04-01 | 2026-04-02 13:08 | 2026-04-04 | 2026-04-04 17:52 |  |  |  |  | 2026-04-12 | 2026-04-11 14:12 | 2026-05-13 | 2026-05-16 10:45 | 2026-05-17 | 2026-05-16 10:45 |  |  | 2026-05-31 | 2026-06-04 18:26 | 2026-06-07 | 2026-06-07 19:50 | 2026-06-08 | 2026-06-07 19:55 | 2026-06-08 | 2026-06-15 17:50 |  |  |  |  | 2026-06-23 14:31 | 2026-06-28 | 2026-06-27 21:01 | 2026-07-10 | 2026-07-09 11:51 | 2026-05-22 | 2026-03-27 17:53 | 2026-07-09 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-06-23 | 2026-06-23 14:30 | 2026-04-05 | 2026-04-09 13:13 | Site is RTMI | 2026-03-26 | 2026-03-27 17:53 | 1441816 | 259526 | 0 | 0 | 1796728.1621 | 296925 | 1796728.1621 | 296925 | 2026-06-10 14:10:21 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-31 12:42:23 +0530 | Urvisha Prajapati | Some Image was uploaded | 2026-04-15 17:05:57 +0530 | Umang Shah | Some Image was uploaded | 2026-04-10 | 2026-04-09 13:17 | 2026-05-08 | 2026-05-07 17:43
19133 | Sub Project |  | Snehal Santosh Desai | Raghav Marvel | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | [5 empty] | Active | Design | 60% Payment | 43824 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 13147 | 30676.8 |  |  | 2026-03-27 | 2026-07-03 10:47 | 2026-03-28 | 2026-07-03 10:47 | 2026-07-03 | 2026-07-03 10:47 | 2026-07-04 | 2026-07-03 10:48 | 2026-07-04 | 2026-07-03 10:49 | 2026-07-04 | 2026-07-03 10:51 | 2026-07-03 | 2026-07-03 10:47 | 2026-07-04 | 2026-07-03 10:47 | 2026-07-03 | 2026-07-03 10:48 | 2026-07-04 | 2026-07-03 10:48 |  |  |  |  | 2026-07-03 | 2026-07-03 10:49 | 2026-07-04 | 2026-07-03 10:50 | 2026-07-04 | 2026-07-03 10:50 |  |  | 2026-07-03 | 2026-07-03 13:55 | 2026-07-04 | 2026-07-04 13:11 | 2026-07-05 | 2026-07-04 18:37 | 2026-07-05 | [6 empty] | 2026-07-23 |  | 2026-08-01 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-04 |  |  |  | 2026-08-26 |  | 2026-08-28 |  | 2026-08-29 | [5 empty] | 2026-07-04 |  | 2026-07-04 | 2026-07-03 10:48 | Unknown | 2026-03-27 | 2026-07-03 10:47 | 0 | 0 | 0 | 0 | 0 | 0 | 37139 | 6685 | [9 empty] | 2026-07-04 | 2026-07-03 10:48 | 2026-07-04 | 2026-07-03 10:50
19138 | Turnkey | 2026-01-01 | Jash Kothari | monte south | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 2144294 | 9999 | 2144294 | 0 | 0 | 103 | 0 | 204430 | 214429 | 909165 | 806270.4 |  |  | 2026-03-27 | 2026-03-27 18:17 | 2026-03-30 | 2026-04-03 15:31 | 2026-04-03 | 2026-04-03 15:34 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-27 | 2026-03-27 18:16 | 1817198 | 327095 | 0 | 0 | 0 | 0 | 1817198 | 327095 | 2026-04-15 15:04:55 +0530 | Harshaan Tiku | Some Image was uploaded | 2026-03-28 23:31:20 +0530 | Khushi Khandelwal | CDP: KITCHENÂ Panel in front of openable window Space for flour mill Space for batter bachine BEDROOM-01 Mirror on bed wall (left side of the bed) |  |  |  | 2026-04-11 |  | 2026-04-18
19139 | Turnkey | 2026-01-01 | Zainab Thanewala | Asteria Courtyard | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  | Krutika Date | Faraz Soudagar | Aditya Vikram |  | Foram Joshi | Prasad Bhivaji Hande | Active | Design | 60% Payment | 2735605 | 562999 | 2769280 | 0 | 2811177 | 15 | 2 | 0 | 0 | 1169106 | 1003499.6 |  |  | 2026-03-27 | 2026-03-27 18:46 | 2026-04-03 | 2026-04-03 12:48 | 2026-04-06 | 2026-04-08 11:19 | 2026-04-15 | 2026-04-15 18:32 | 2026-05-06 | 2026-05-05 20:08 | 2026-06-04 | 2026-06-04 17:39 | 2026-04-08 | 2026-04-08 19:43 | 2026-04-09 | 2026-04-09 11:05 | 2026-04-09 | 2026-04-09 14:35 | 2026-04-14 | 2026-04-14 11:55 |  |  |  |  | 2026-04-16 | 2026-04-08 19:43 | 2026-05-07 | 2026-05-09 13:05 | 2026-05-10 | 2026-05-11 16:50 |  |  | 2026-06-11 | 2026-06-25 16:23 | 2026-06-26 | 2026-06-26 12:54 | 2026-06-27 | 2026-06-30 18:05 | 2026-07-01 | [6 empty] | 2026-07-19 |  | 2026-07-28 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-31 |  |  |  | 2026-08-22 |  | 2026-08-24 |  | 2026-08-25 | [5 empty] | 2026-06-26 |  | 2026-04-15 | 2026-04-15 18:22 | Site is RTMI | 2026-03-27 | 2026-03-27 18:45 | 2346847 | 422432 | 0 | 0 | 3097791.2248 | 523018 | 3097791.9798 | 511490 | 2026-07-10 13:21:00 +0530 | Avinash Jaiswal | Client is requesting for cancellation post PKO docket approval due to bad reviews in her society group. Trying to connect with the client on all levels however, client is not responding. Trying to retain | 2026-05-07 17:56:48 +0530 | Anil Kuwar | 2D: Team is working on 2d | 2026-04-14 11:54:02 +0530 | Anil Jagtap | welcome call done cx will receive possession within 10 days | 2026-04-16 | 2026-04-24 13:29 | 2026-05-06 | 2026-05-05 20:14
19141 | Turnkey | 2026-01-01 | Jawahar | INDEPENDENT HOUSE | BNG - HSR | Yes | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 1048607 | 9999 | 0 | 0 | 0 | 110 | 0 | 94862 | 104861 | 419443 | 419442.8 |  |  | 2026-03-27 | 2026-03-27 20:42 | 2026-03-28 | 2026-04-23 14:39 | 2026-04-23 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-05-01 |  | 2026-05-09 |  | 2026-05-10 |  |  |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-20 | [6 empty] | 2026-06-07 |  | 2026-06-16 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-19 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-18 |  | 2026-04-26 |  | Unknown | 2026-03-27 | 2026-03-27 20:41 | 0 | 0 | 0 | 0 | 0 | 0 | 888650 | 159957 | 2026-04-23 14:41:35 +0530 | Priyamvada PV | Family members : 2 adults, 1 4 year old boy & 1 new born Budget : 7L Theme : Basic minimal Changes in site compared to floor plan : Entrance is towards eastdining widow towards north is not presentbedroom windows towards south is not presentvanity entrance from MBRkitchen entrance from living side is closed and access from dining areawall between living & dining - dining entrance is open completelypooja entrance from north to be closed and opened from kitchen side (client scope)chejja opening from common vanity to be closed and opened from GBR bedroom (client scope) existing chejja in kitchen (L shape) Living : 65" TVTV unitstanding pooja unit with storage at base & open concept for topprojector in front of TV from ceiling Kitchen : base units, wall unitt , frame & shutter loftswall mounted microwave unitappliances are microwave, single door fridge, mixer, table top grinder MBR wardrobe with loft, fixed study for WFHdresser GBR separate single cot placementwardrobestudy table | [6 empty] | 2026-05-01 |  | 2026-05-08
19142 | Turnkey | 2026-01-01 | Mithilesh Vishwakarma Vishwakarma | SK Heights | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [7 empty] | Hold | Design | DEM1 | 847890 | 115449 | 1098778 | 0 | 0 | 5 | 92 | 0 | 54129 | 376996 | 301316 |  |  | 2026-03-27 | 2026-03-30 17:20 | 2026-03-30 | 2026-03-30 21:14 | 2026-04-02 | 2026-03-31 12:05 | 2026-08-03 |  | 2026-08-10 |  | 2026-08-17 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 11:16 | 2026-04-03 | 2026-04-09 09:29 | 2026-04-14 | 2026-04-14 14:47 |  |  |  |  | 2026-08-04 |  | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-07-30 |  | Unknown | 2026-03-27 | 2026-03-27 23:20 | 931168 | 167610 | 0 | 0 | 0 | 0 | 931167.7491 | 153746 | 2026-07-10 13:13:13 +0530 | Anil Jagtap | cx will receive the possession by December *26 | 2026-04-14 14:47:42 +0530 | Anil Jagtap | welcome call done Possession - July end | 2026-04-09 09:29:33 +0530 | Royden Henriques |  | 2026-08-04 |  | 2026-08-11
19143 | Turnkey | 2026-01-01 | Swati Lokhande | Skyline heights | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Uday Yadruk | Rizwan Mistry |  | Saloni Sagwekar | Aakash Gaikwad | Active | Preproduction | 2D | 1454823 | 290965 | 1825518 | 1454823 | 0 | 1 | 0 | 0 | 0 | 610708 | 553150 |  |  | 2026-03-27 | 2026-03-28 13:08 | 2026-04-02 | 2026-04-02 12:24 | 2026-04-02 | 2026-04-02 14:14 | 2026-05-03 | 2026-05-02 13:29 | 2026-06-06 | 2026-06-05 19:57 | 2026-07-05 | 2026-07-05 12:30 | 2026-03-31 | 2026-03-31 | 2026-04-03 | 2026-04-03 12:45 | 2026-04-03 | 2026-04-08 10:41 | 2026-04-12 | 2026-04-12 13:06 |  |  |  |  | 2026-05-02 | 2026-05-07 19:03 | 2026-06-13 | 2026-06-12 13:42 | 2026-06-13 | 2026-06-12 13:42 |  |  | 2026-07-12 | 2026-07-14 19:48 | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-04-13 | 2026-05-02 13:25 | Site is RTMI | 2026-03-27 | 2026-03-28 13:06 | 1549336 | 276181 | 1547794.4212 | 253194 | 0 | 0 | 1547794.4212 | 253194 | 2026-07-05 13:16:54 +0530 | Manisha Dubey | appliances size | 2026-07-04 13:04:46 +0530 | Swapnali Shedekar | Minutes of Meeting held on Date: Attendees: Discussion: ï»¿ Transition has been given to Manisha Dubey on 17th June. Meeting with client for final material selection was done on 2nd July with Manisha Dubey, | 2026-06-19 16:24:06 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-03 | 2026-05-02 18:10 | 2026-06-06 | 2026-06-05 19:57
19145 | Turnkey | 2026-01-01 | Bhavesh Jain | Antriksh | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 2048491 | 9999 | 2048491 | 0 | 0 | 107 | 0 | 194850 | 204849 | 870964 | 767828.4 |  |  | 2026-03-28 | 2026-03-28 16:37 | 2026-03-30 | 2026-03-30 18:48 | 2026-04-01 | 2026-04-01 13:16 | 2026-04-08 |  | 2026-04-15 |  | 2026-04-22 |  | 2026-04-01 |  | 2026-04-02 |  | 2026-04-02 |  | 2026-04-03 | [5 empty] | 2026-04-09 |  | 2026-04-17 |  | 2026-04-18 |  |  |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 | [6 empty] | 2026-05-16 |  | 2026-05-25 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-28 |  |  |  | 2026-06-19 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-04-26 |  | 2026-04-04 |  | Unknown | 2026-03-28 | 2026-03-28 16:37 | 1736009 | 312481 | 0 | 0 | 0 | 0 | 1736009 | 312481 | 2026-03-28 17:12:36 +0530 | Yash Jain | DCM: Cx Bhavesh Jain 2bhk 656 sq feet - RTMIÂ Civil already done by cxÂ L shaped sofa cum bed.Â property name - antrisk, kharÂ 2 kid 12, 16yr old son , parents travel, coupleÂ entry -Â FoyerÂ Safety door with name to be in our scopeÂ no wall in foyer unit . Sofa seater 4 shape seater + 1 dining table folding tableÂ tv size - 60-62, tall unit with tv unit storage , Mandir unit, kitchenÂ front walls are already demolisedh and washing machine and kitchen already there, gas top right, full top storages, bedroom 1 - sons bedroomÂ study tablee, bed, headboard,sotrage on both sides of door , bathroom- vanity units on both bathroomsÂ master bedroom - couple room tv unit -Â bed - wardrobe slidingÂ wardrobe , storage , tv unitÂ dresser, loft above sliding wardobe invisible door - setupÂ Doors laminate change -Â | [6 empty] | 2026-04-09 |  | 2026-04-16
19146 | Turnkey | 2026-01-01 | Pawan Mathur | Kalpataru Vivant | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 1503863 | 300476 | 2183869 | 0 | 0 | 21 | 59 | 0 | 0 | 685164 | 518222.8 |  |  | 2026-03-28 | 2026-03-28 13:05 | 2026-03-28 | 2026-03-28 14:45 | 2026-04-01 | 2026-04-01 01:35 | 2026-04-27 | 2026-04-27 15:34 | 2026-08-02 |  | 2026-08-09 |  | 2026-04-01 | 2026-03-31 | 2026-04-02 | 2026-04-05 13:39 | 2026-04-05 | 2026-04-07 15:23 | 2026-04-10 | 2026-04-10 12:53 |  |  |  |  | 2026-04-16 | 2026-04-14 16:42 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-04-11 | 2026-04-26 15:43 | Site is RTMI | 2026-03-28 | 2026-03-28 13:02 | 1853023 | 330845 | 0 | 0 | 0 | 0 | 1851524.831 | 303005 | 2026-05-17 18:45:35 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-26 10:39:23 +0530 | Anjali Jain | DDM1: Kitchen Loft cabinet consider on one side (PL) Wall cabinet (mem) Base cabinet (semi modular) indaux tandemÂ CLIENT CHANGES loft need to extend till wall siNk wall Living room - All the modular unit in PL Crockery unit (PL) TV Unit (PL The Mandir StoreÂ CLIENT CHANGES dining table need to change with bench and 3 chairsÂ crockery unit with bar cabinetÂ sofa with l shape in which sofa cum bed with storage Floor mounted tv unitÂ UtilityÂ Utility storage (mem) Loft cabinet (pl) Parent Bedroom Wardrobe with loft (pl) (Basic storage) Febronic queen bed (Box storage) Parents bedroom (Bathroom & Toilet) Vanity single bottom Son's bedroom Tv & Study unit (PL) side table (PL) Wardrobe with loft (PL) Febronic bed box storageÂ client changes tv unit drawer need to addÂ Â Master bedroom Dressign unit (Pl) Openable wardrobe (Pl) Wardrobe with loftÂ Febronic bed box storageÂ Client changes mirror storage need to add on one side table side tall unit need to cHange in half side table with wall storageÂ Master Bed room (Bathroom & Toilet) Single Wall 2 Drawer Vanity Unit Double Bottom Vanity Unit Bathroom & Toilet Single Bottom Vanity Unit Electrification (55000) Additional Scope of Work HW Gold Flat Strip Gold Finish - 25mm (6 qty) Flava Louvers - Luxury - TL CL 4219 9.5ft X 8 inch (6Qty) POP Punning (Plum) 12-15mm thick (4 qty) Excel - Hot Spots Wallpaper 78198-1 (wallpaper) 4 Charcoal Beading with Type and Designs - Raw - VB-65 (10 qty ) MDF Beading (15 qty) Tractor EmulsionÂ Royale Luxury Emulsion False ceiling (Plain consider) 500 qtyÂ Client changes Need to add false ceiling in entire house Decor part will increase as per design | 2026-04-26 10:36:17 +0530 | Anjali Jain | Others: Kitchen Loft cabinet consider on one side (PL) Wall cabinet (mem) Base cabinet (semi modular) indaux tandemÂ Living room - All the modular unit in PL Crockery unit (PL) TV Unit (PL The Mandir StoreÂ UtilityÂ Utility storage (mem) Loft cabinet (pl) Parent Bedroom Wardrobe with loft (pl) (Basic storage) Febronic queen bed (Box storage) Parents bedroom (Bathroom & Toilet) Vanity single bottom Son's bedroom Tv & Study unit (PL) side table (PL) Wardrobe with loft (PL) Febronic bed box storageÂ Â Master bedroom Dressign unit (Pl) Openable wardrobe (Pl) Wardrobe with loftÂ Febronic bed box storageÂ Master Bed room (Bathroom & Toilet) Single Wall 2 Drawer Vanity Unit Double Bottom Vanity Unit Bathroom & Toilet Single Bottom Vanity Unit Electrification (55000) Additional Scope of Work HW Gold Flat Strip Gold Finish - 25mm (6 qty) Flava Louvers - Luxury - TL CL 4219 9.5ft X 8 inch (6Qty) POP Punning (Plum) 12-15mm thick (4 qty) Excel - Hot Spots Wallpaper 78198-1 (wallpaper) 4 Charcoal Beading with Type and Designs - Raw - VB-65 (10 qty ) MDF Beading (15 qty) Tractor EmulsionÂ Royale Luxury Emulsion False ceiling (Plain consider) 500 qtyÂ | 2026-04-28 | 2026-04-27 16:14 | 2026-08-03 |  | Under Construction | 2026-06-30
19147 | Turnkey | 2026-01-01 | RASHMI PANDEY | TVS Emerald Jardin | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  | RaviKumar Battala | Sachin I Betageri | Ranjith Kumar | Murali S | Muralikrishna Udupi | Sunil Kumar S M | Active | Installation | Execution | 1204930 | 1204931 | 1438030 | 0 | 1201609 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-28 | 2026-03-28 13:16 | 2026-04-03 | 2026-04-03 14:49 | 2026-04-06 | 2026-04-04 18:58 | 2026-05-10 | 2026-05-10 18:35 | 2026-05-27 | 2026-05-26 19:03 | 2026-06-01 | 2026-05-31 07:16 | 2026-04-04 | 2026-04-08 11:50 | 2026-04-05 | 2026-04-08 11:50 | 2026-04-08 | 2026-04-09 13:13 | 2026-04-15 | 2026-04-15 17:03 |  |  |  |  | 2026-05-11 | 2026-05-09 18:24 | 2026-05-27 | 2026-05-29 12:46 | 2026-05-30 | 2026-05-29 13:49 |  |  | 2026-06-01 | 2026-05-31 18:36 | 2026-05-31 | 2026-05-31 22:52 | 2026-06-01 | 2026-06-01 12:28 | 2026-06-02 | 2026-06-04 18:13 |  |  |  |  | 2026-06-05 10:39 | 2026-06-14 | 2026-06-13 20:55 | 2026-07-02 | 2026-06-30 17:07 | 2026-07-01 | 2026-07-03 15:58 | 2026-06-30 | 2026-07-06 11:48 | 2026-07-06 | 2026-07-06 12:27 | 2026-07-08 | 2026-07-10 18:54 |  |  | 2026-08-08 |  | 2026-08-10 |  | 2026-08-11 | [5 empty] | 2026-05-31 | 2026-06-04 20:25 | 2026-04-16 | 2026-04-26 12:22 | Site is RTMI | 2026-03-28 | 2026-03-28 13:14 | 1218669 | 219360 | 0 | 0 | 1352598.6956 | 223338 | 1357978.6956 | 223845 | 2026-07-13 10:38:12 +0530 | Ranjith Kumar | Execution: | 2026-07-01 10:42:08 +0530 | Ranjith Kumar | Some Image was uploaded | 2026-06-10 10:42:34 +0530 | Ranjith Kumar | Bonito Side - Floor Covering & Flase Ceiling qith POP Punning. Cx Side - Electrical | 2026-05-11 | 2026-05-10 18:43 | 2026-05-27 | 2026-05-26 19:29 | RTMI
19148 | Turnkey | 2026-01-01 | Turya Vardhan | Assetz Sun and Sanctum | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1229077 | 245814.95 | 1606972 | 0 | 0 | 5 | 0 | 0 | 0 | 511850 | 471412 |  |  | 2026-03-28 | 2026-03-28 13:21 | 2026-03-28 | 2026-03-31 14:00 | 2026-04-03 | 2026-03-31 22:21 | 2026-06-27 | 2026-06-30 16:06 | 2026-07-21 |  | 2026-08-11 |  | 2026-04-03 | 2026-03-31 19:05 | 2026-04-01 | 2026-04-06 21:18 | 2026-04-06 | 2026-04-08 15:01 | 2026-04-11 | 2026-04-15 18:39 |  |  |  |  | 2026-07-05 | 2026-07-10 15:21 | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-07-04 | 2026-06-27 12:13 | Site is RTMI | 2026-03-28 | 2026-03-28 13:19 | 1361841 | 245131 | 0 | 0 | 0 | 0 | 1372376.4774 | 234774 | 2026-05-07 16:16:01 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-07 16:02:42 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-04-24 11:32:16 +0530 | Shefali | Some Image was uploaded | 2026-07-01 | 2026-06-30 21:46 | 2026-07-22 |  | Under Construction | 2026-04-22
19150 | Turnkey | 2026-01-01 | Rashmi Choudhury | Coevolve Florenza | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 1586126 | 9999 | 0 | 0 | 0 | 108 | 0 | 148614 | 158613 | 634450 | 634450.4 |  |  | 2026-03-28 | 2026-03-29 10:58 | 2026-04-03 |  | 2026-03-31 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Unknown | 2026-03-28 | 2026-03-29 10:56 | 0 | 0 | 0 | 0 | 0 | 0 | 1344175 | 241951 | 2026-03-30 19:00:24 +0530 | Aparna | RGM MOM Interior Design DiscussionClient DetailsClient Name: Harshit / RashmiMembers: 2 PeopleProject: TVS JardinConfiguration: 3BHKFacing: WestPossession: Ready to Move InTheme: Contemporary (Warm color palette)Budget: 10 LakhsEntranceShoe Rack: Not requiredSafety Door: To be checked and finalized with vendorFoyer AreaDesign Concept:Bedroom-facing wall with bottom trims + wallpaper designFinish to match warm contemporary themeLiving RoomTV Unit: Wall-mounted designStorage Options:Option 1: Tall unit (Inverted L shape)Option 2: Open ledges with MS rod supportsSofa Wall:Same design language as foyerTrims + wallpaper finish (as per reference)Dining AreaDining Table: 4-seater round tableWall Unit:Glass shutter unitApprox. 1 ft depthPooja UnitDesign:Base storage unitSize: Approx. 2 ft (D) x 7 ft (H)Placement aligned with overall layoutKitchenLayout: L-shaped counterAppliances Planned:Single door refrigeratorBuilt-in hobMicrowaveAir fryerGrinderStorage:Tall unit for appliancesWall units + loftsPartition:Partition near utility areaUtility AreaUnits:Base cabinetWall cabinet with dish drainerOpposite Side:Washing machineCounter aboveAdditional wall cabinetsMaster Bedroom (MBR)Bed: King size bedWardrobe: With loft + integrated dresserWall Design:Side panelling on both sidesCenter punning (highlight panel)TV Unit: Minimal panelWorkspace:Near window: Work desk / floating ledgeBedroom 2Bed: Queen size bedWardrobe: With loftStorage:Mirror with open storage adjacentStudy Area: Study table + bookshelfWall Design: Minimal panellingBedroom 3Bed: Pull-out bedStorage:Bottom storageWardrobe with loftWindow Area:Corner window with foldable / fixed ledgeBathroomsVanity Unit: Provided in all bathroomsMaster Bathroom:Glass partitionBalconyDesign and utility planning to be discussed | 2026-03-29 11:00:43 +0530 | Chanakya Panigrahi | RGM Sheet 1. Budget - 10l-12lÂ 2. Property Name & Possession - Coevolve Florenza 3. Carpet Area - 1050 4. BHK - 3BHK 5. Family Size - 2 + 1 Name -Â Spouse - Child 1 - Child 2 - Father - Mother - 6. Shoe Rake/Foyer - Yes 4. Living/Dining Room Inclusions - TV Unit 5. Bed Room Inclusions - Yes 6. Kitchen Inclusions - Yes Tall unit - Yes Base unit - Yes Wall unit - Yes Loft - Yes Granite/Quartz -Â Service Scope -Â False Ceiling - No Painting - Yes Electricity - No 8. Utility/Janitor Unit -Â 9. Timeline - June |  |  |  | 2026-04-14 |  | 2026-04-21
19152 | Turnkey | 2026-01-01 | Vikas Gupta | Puraniks | MUM - Thane | Yes | Mehnaz Ashraf | Anamika Dolai | Rushika More | [5 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1732022 | 9999 | 0 | 0 | 0 | 103 | 0 | 163203 | 173202 | 743495 | 642122.8 |  |  | 2026-03-28 | 2026-04-03 17:09 | 2026-04-07 | 2026-04-07 11:34 | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-03-28 | 2026-03-30 17:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1467816 | 264206 | 2026-04-07 11:29:47 +0530 | Maasoumeh Raza | Name: 19152 - Vikas Gupta Property Name: Ruma Bali Property type: 1 + 1 Jodi flat Possession: December Move in: Not confirmÂ Member: 5 memberÂ Budget: 15LÂ Theme : Modern traditional Requirements: Existing : No Living room: Safety door with panellingÂ Shoe rack with seating Tv UnitÂ 3 + 2seater sofaÂ Crockery unit JhulaÂ Semi traditional theme Breaking of common bathroom wall and convert shower area into study room. Diwan window sideÂ Â Kitchen : Base unit Wall unit Loft unit Appliance unit Storage above washing machineÂ Â Parents bedroom :Â Â Queen size bed Wardrobe with loft Side table Kids bedroom: kids room should be spaciousÂ Platform bed with storage Folding Study table Master bedroom:Â King size bed side table Dressing Unit Study table Bathroom: Converting 1 common bathroom into walking closet 2 Vanity unit Additional scope: Full home False ceiling Painting Electrical | [6 empty] | 2026-04-26 |  | 2026-05-03
19154 | Turnkey | 2026-01-01 | Hari Haran | Independent House | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 2901517 | 9999 | 0 | 0 | 0 | 84 | 0 | 280153 | 290152 | 1160607 | 1160606.8 |  |  | 2026-03-28 | 2026-04-22 13:16 | 2026-04-22 | 2026-04-22 13:23 | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-03-28 | 2026-03-28 16:14 | 0 | 0 | 0 | 0 | 0 | 0 | 2458913 | 442604 | [9 empty] | 2026-04-30 |  | 2026-05-07
19155 | Turnkey | 2026-01-01 | Mr.Shravan K | nestcons iris | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S | Raghavendra S | Vishwa Hiremath | Active | Installation | Execution | 1083281 | 1083281 | 1211934 | 0 | 1083281 | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-28 | 2026-03-31 19:39 | 2026-03-31 | 2026-03-31 19:39 | 2026-04-03 | 2026-03-31 19:53 | 2026-04-20 | 2026-04-19 15:43 | 2026-05-24 | 2026-05-23 12:47 | 2026-05-29 | 2026-05-27 18:01 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-02 11:50 | 2026-04-02 | 2026-04-02 14:33 | 2026-04-05 | 2026-04-05 12:31 |  |  |  |  | 2026-04-19 | 2026-04-20 15:00 | 2026-05-26 | 2026-05-23 14:48 | 2026-05-24 | 2026-05-23 14:49 |  |  | 2026-05-30 | 2026-05-30 19:50 | 2026-05-31 | 2026-05-31 19:04 | 2026-06-01 | 2026-05-31 19:34 | 2026-06-01 | 2026-06-01 15:12 |  |  |  |  | 2026-06-02 18:52 | 2026-06-12 | 2026-06-11 21:04 | 2026-06-29 | 2026-06-26 18:44 | 2026-06-27 | 2026-07-06 16:18 | 2026-06-26 | 2026-07-06 16:53 | 2026-07-07 | 2026-07-07 08:53 | 2026-07-14 | 2026-07-13 17:34 |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-05-31 | 2026-06-02 18:46 | 2026-04-06 | 2026-04-19 15:37 | Site is RTMI | 2026-03-28 | 2026-03-30 12:20 | 1027063 | 184871 | 0 | 0 | 1213600.8413 | 195881 | 1213600.8413 | 195881 | 2026-05-27 17:55:58 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 23/05/2026 Title:DEM 3 Project: 19155 Client: Shravan K Attendees: Vishal Bandi Objective: DEM 3 Discussion Based on 23/05/2025 meeting, below is a list of all the requirements that were discussed during the meeting: Tv Unit Tall unit with Solid Shelf Partition with spot light- light Cx scope Tv size has to be confirm partition rafters has to be re aligned ( 3 to 4) Partition tall unit with solid shelf Bonito Edge Profile Shutter - Brown Tinted Glass for Tv unit Bonito Edge Profile Shutter - Clear Glass for Partition glass shutter dummy Wall with laminate finish Granite Black Galaxy- For crockery and kitchen Wash basin and tile CX scope chimney and stove size has to confirmÂ sink cx scope Laminate combination has been changed and loft will be post lam wicker basket size has to confirm to Cx as there is a depth difference mbr STUDY TABLE - has to beam GL - Frosty White - 1113 PGL MBR internal - as discussed dresser ledge -BD-LAM-2023-0239 Loft- MBR+KBR+Kitchen - BD-HNA-2025-0448 | 2026-04-19 17:01:55 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 19/04/2026 @11.30am Title: DEM1 Project: 19155 Client: Mr.Shravan K Attendees: Vishal Objective: DEM 1 Discussion Based on 19/04/2026 meeting, below is a list of all the requirements that were discussed during the meeting: LIVING AREA & DINING AREA: Glass shutter has to place at the center of base cabinet tall unit placement has changed to right to left added extended platform at form No, wall design behind the sofa Partition between Living area and dining area design has changed- cost is not considered for the revised design, it will vary Pooja unit- descoped ( as mentioned- it will be CX scope) Crockery unit-wall cabinet has to be adjusted according to base shutter ( has to make wall cabinet with glass shutter, as of now 2 shutters are with glass andÂ 1 with the solid shutter) False ceiling has to consider for entire dining area( as mentioned need confirmation after estimate is generated) As mentioned, Vanity unit considered preLam and next to that cabinets(crockery) are considered Post lam, so colour will not match with preelam and post lam ( is wants to match the colour then needs to consider post lam only for the crockery base cabinet Tile near the vanity area is not considered in Estimate - Its CX scope as mentioned, for tv unit need conduit piping for to hide wires ( CX scope) KITCHEN: Sink unit has to place left side of the kitchen - only single bowl has to be considered Space has to Given for 90cm chimney and hob i the kitchen HOB/Stove Placement has to move little towards right hand side Cylinder provision is in the utility- copper piping has to be done, its CX scope RO provision has to given above the sink in the kitchen appliances unit has to move towards tall unit tall unit has to be changed to normal tall unit with shelfs inside( not with accessories) as mentioned electrical point is required for Mixer and other appliances- has to be created CX scope Open Ledges has to be consider left hand side of appliances/tall unit Utility Cx ScopeÂ KBR: Loft has to consider above the door also next to wardrobe has to consider used cloth cabinetÂ Cost will vary as per the changes wardrobe internal has to changes as per the discussion No Changes inÂ Study tableÂ as mentioned there is electrical point exactly between the study table - that has to be shift ( as mentioned its CX scope) Mirror has to place above the used cloth cabinet shutter MBR: Loft has to move above the window also next to the dresser unit has to consider ledgesÂ wardrobe internal has to changes as per the discussion No Changes in study Table Common washroom: vanity wall unit has consider, mirror is client scope Note: as per our discussion, Electrical, Plumbing and painting charges are Not included | 2026-04-05 12:29:42 +0530 | Parasa Sri | Welcome call done. The site is ready for initial measurement. The client has informed that it is scheduled on Tuesday at 2 PM. The client prefers physical availability on Sunday. | 2026-04-20 | 2026-04-19 16:58 | 2026-05-24 | 2026-05-23 12:58 | RTMI
19156 | Turnkey | 2026-01-01 | Aparna Keshava Borkar | Runwal Timeless (Own Your Time) | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 3260342 | 9999 | 0 | 0 | 0 | 95 | 0 | 316035 | 326034 | 1541677 | 1066596.4 |  |  | 2026-03-28 | 2026-04-11 11:03 | 2026-03-29 |  | 2026-03-28 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-03-28 |  | 2026-03-29 |  | 2026-03-29 |  | 2026-03-30 | [5 empty] | 2026-04-05 |  | 2026-04-13 |  | 2026-04-14 |  |  |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 | [6 empty] | 2026-05-12 |  | 2026-05-21 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-24 |  |  |  | 2026-06-15 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-04-22 |  | 2026-03-31 |  | Unknown | 2026-03-28 | 2026-03-28 16:45 | 0 | 0 | 0 | 0 | 0 | 0 | 2771574 | 488768 | 2026-04-15 18:18:58 +0530 | Manasi Patil | Some Image was uploaded | [6 empty] | 2026-04-05 |  | 2026-04-12
19157 | Turnkey | 2026-01-01 | Shatrunjay Kumar | Hiranandani Fortune City | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2241367 | 9999 | 2241367 | 0 | 0 | 104 | 0 | 214138 | 224137 | 993696 | 799397.6 |  |  | 2026-03-28 | 2026-03-28 20:55 | 2026-03-28 | 2026-03-28 21:11 | 2026-03-31 | 2026-04-02 13:19 | 2026-04-09 |  | 2026-04-16 |  | 2026-04-23 |  | 2026-04-02 |  | 2026-04-03 |  | 2026-04-03 |  | 2026-04-04 | [5 empty] | 2026-04-10 |  | 2026-04-18 |  | 2026-04-19 |  |  |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 | [6 empty] | 2026-05-17 |  | 2026-05-26 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-29 |  |  |  | 2026-06-20 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-04-27 |  | 2026-04-05 |  | Unknown | 2026-03-28 | 2026-03-28 20:54 | 1899463 | 341903 | 0 | 0 | 0 | 0 | 1899463 | 341903 | 2026-04-15 18:28:25 +0530 | Manasi Patil | Some Image was uploaded | [6 empty] | 2026-04-10 |  | 2026-04-17
19161 | Turnkey | 2026-01-01 | Shibu Thomas | Sai world city Panvel | MUM - Thane | Yes | [8 empty] | Anjan Kumar |  | Lost | Prospect | DCM Due | 4033096 | 9999 | 0 | 0 | 0 | 109 | 0 | 393311 | 403310 | 1757675 | 1468801.6 |  |  | 2026-03-28 | 2026-03-28 21:36 | 2026-03-31 |  | 2026-04-05 |  | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-03 |  | 2026-04-04 |  | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-28 | 2026-03-28 21:30 | 0 | 0 | 0 | 0 | 0 | 0 | 3417878 | 615218 | 2026-04-07 16:14:41 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-03-28 21:38:13 +0530 | Anjan Kumar | Some Image was uploaded |  |  |  | 2026-04-11 |  | 2026-04-18
19162 | Turnkey | 2026-01-01 | Gaurav Bapodia Bapodia | Ruchira Park East | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1548117 | 246295 | 1618519 | 0 | 0 | 81 | 0 | 0 | 0 | 705916 | 595906.4 |  |  | 2026-03-28 | 2026-03-28 18:33 | 2026-04-12 | 2026-04-12 19:38 | 2026-04-13 | 2026-04-13 13:39 | 2026-04-24 | 2026-04-24 20:04 | 2026-08-17 |  | 2026-08-24 |  | 2026-04-13 | 2026-04-14 18:18 | 2026-04-14 | 2026-04-18 13:57 | 2026-04-18 | 2026-04-20 18:16 | 2026-04-22 | 2026-04-22 12:25 |  |  |  |  | 2026-04-24 | 2026-04-25 16:21 | 2026-08-19 |  | 2026-08-20 |  |  |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 | [6 empty] | 2026-09-17 |  | 2026-09-26 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-29 |  |  |  | 2026-10-21 |  | 2026-10-23 |  | 2026-10-24 | [5 empty] | 2026-08-28 |  | 2026-04-23 | 2026-04-24 19:52 | Site is RTMI | 2026-03-28 | 2026-03-28 18:32 | 1371626 | 246892 | 0 | 0 | 0 | 0 | 1668043.7444 | 280390 | 2026-05-19 11:11:18 +0530 | Priyanka Mathur | Hello ma'am & Sir, MOM for the meeting scheduling on 16th May 2026 FoyerÂ - add shoe rack with siting Living roomÂ - Tv unit with open to be in flap down glass unit,Â - mandir standing,Â - add bottom unit in passage for Robo cleaner Master bedroomÂ - Hanging in L shaped wardrobe,Â - wardrobe internals PDF,Â - remove study 2,Â - add dresser unit,Â - study table front panel with white marker laminate,Â Â Kids roomÂ - bottom storage then wardrobe,Â - cloud false ceiling,Â - Add bottom storage unit,Â Guest bedroomÂ - baysiting curved top and 2 wall ledge,Â KitchenÂ - gas pipeline available, ,Â - fridge 3', 3' hob and chimney,Â - undersink RO,Â - left side wall unit to wall ledges,Â - cover chimeny pipe in utility,Â - microwave, 1 wicker basket, 1 tandem drawer,Â # false ceiling in living dining,Â # add wall storage unit in all washrooms | 2026-05-07 15:00:22 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-04-29 15:58:45 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-25 | 2026-04-24 20:07 | 2026-08-18 |  | Under Construction | 2026-06-30
19165 | Turnkey | 2026-01-01 | jayesh bhatt | keval kunj | MUM - GOR | No Estimate | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-28 | 2026-05-01 12:47 | 2026-05-19 |  | 2026-04-02 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Site is RTMI | 2026-03-28 | 2026-04-15 17:06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-01 13:39:34 +0530 | Khushi Khandelwal | DCM: 2BHK 600 sqftÂ 2 members Budget-12-13L Entrance LIVING & DINING AREA 4 seater dining 3+1+1 seaterÂ TV unit Pooja unit on wall near diningÂ Sliding door behind sofa ,next to sofa wall KitchenÂ Parallel kitchenÂ Change platformÂ Appliances-Ref., microwave, mixer, blender, flour mill. BEDROOM-01 Guest bedroomÂ WardrobeÂ BEDROOM-02 MASTER BEDROOM WardrobeÂ Existing bed headboard needs to be changedÂ Side table exisitng or can be changedÂ Niche areaÂ Storage is needed Â NOTE-Cx want to start work after septemberÂ | 2026-04-15 17:06:27 +0530 | Umang Shah | Some Image was uploaded |  |  |  | 2026-05-30 |  | 2026-06-06
19166 | Turnkey | 2026-01-01 | preeti Gupta | nandanvan | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate | Rajkumar Suthar | Sandeep Tiwari | Murali S |  | Vinay Surve | Active | Installation | Execution | 1092041 | 1092041 | 1257723 | 0 | 1163412 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-28 | 2026-03-31 14:33 | 2026-04-02 | 2026-04-02 16:32 | 2026-04-05 | 2026-04-02 17:52 | 2026-04-24 | 2026-04-24 14:23 | 2026-05-07 | 2026-05-06 19:13 | 2026-05-10 | 2026-05-10 21:32 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-07 13:19 | 2026-04-07 | 2026-04-09 18:38 | 2026-04-15 | 2026-04-15 11:54 |  |  |  |  | 2026-04-24 | 2026-04-29 17:27 | 2026-05-05 | 2026-05-05 16:20 | 2026-05-06 | 2026-05-05 16:21 |  |  | 2026-05-14 | 2026-05-16 18:29 | 2026-05-23 | 2026-05-23 21:06 | 2026-05-24 | 2026-05-24 13:13 | 2026-05-25 | 2026-05-27 18:00 |  |  |  |  | 2026-05-30 18:08 | 2026-06-06 | 2026-06-05 21:24 | 2026-06-25 | 2026-06-19 18:55 | 2026-06-20 | 2026-07-02 12:17 | 2026-06-19 | 2026-07-06 15:49 | 2026-07-07 | 2026-07-09 17:59 | 2026-07-11 |  |  |  | 2026-06-28 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-05-23 | 2026-05-30 18:07 | 2026-04-16 | 2026-04-24 14:18 | Site is RTMI | 2026-03-28 | 2026-03-31 14:32 | 1068154 | 189568 | 0 | 0 | 1277600.9577 | 209274 | 1278514.6617 | 199913 | 2026-07-12 10:07:22 +0530 | Rajkumar Suthar | Execution: Day 1 : 10th July Day 4 : 14th July | 2026-06-28 14:26:25 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-28 13:53:47 +0530 | Reshma Melanta | NEED TO CHECK WITH PREETI REGARDING BLINDER FOR BOTH THE BED ROOM. | 2026-04-25 | 2026-04-24 14:28 | 2026-05-07 | 2026-05-06 19:15 | Under Construction | 2026-04-30
19168 | Turnkey | 2026-01-01 | VINOD VAIDYA | Arihant Aspire | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Subhan Khan |  | Active | Preproduction | DEM2 | 1311308 | 266899 | 1769491 | 0 | 0 | 4 | 66 | 0 | 0 | 567945 | 476464 |  |  | 2026-03-28 | 2026-04-03 15:48 | 2026-04-09 | 2026-04-09 17:40 | 2026-04-12 | 2026-04-10 20:56 | 2026-07-10 | 2026-07-10 15:59 | 2026-08-20 |  | 2026-08-27 |  | 2026-04-10 | 2026-04-11 18:21 | 2026-04-11 | 2026-04-14 11:39 | 2026-04-14 | 2026-04-14 13:47 | 2026-04-22 | 2026-04-22 17:09 |  |  |  |  | 2026-07-11 | 2026-07-11 13:25 | 2026-08-22 |  | 2026-08-23 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 | [6 empty] | 2026-09-20 |  | 2026-09-29 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-02 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-27 | [5 empty] | 2026-08-31 |  | 2026-07-31 | 2026-07-10 15:52 | Site is RTMI | 2026-03-28 | 2026-04-03 15:45 | 1502370 | 267120 | 0 | 0 | 0 | 0 | 1491614.7167 | 238033 | 2026-07-14 15:39:44 +0530 | Harshali Bhuyar |  | 2026-07-14 15:38:39 +0530 | Harshali Bhuyar |  | 2026-07-10 19:13:47 +0530 | Divya Rahangdale | CX will receive the possession by August. | 2026-07-11 | 2026-07-11 19:50 | 2026-08-21
19169 | Turnkey | 2026-01-01 | Asmita sorap | BC Corp Arista | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  | Hiba Shaikh | Faizal Shaikh | Rizwan Mistry |  | Nivesh Gupta | Prasad Bhivaji Hande | Active | Preproduction | 2D | 839642 | 167929 | 1442713 | 0 | 0 | 17 | 0 | 0 | 0 | 351136 | 320576.8 |  |  | 2026-03-28 | 2026-03-28 20:38 | 2026-03-31 | 2026-03-31 22:23 | 2026-04-01 | 2026-03-31 23:08 | 2026-04-19 | 2026-04-19 17:34 | 2026-05-03 | 2026-05-02 12:53 | 2026-06-19 | 2026-06-18 11:58 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-02 12:12 | 2026-04-02 | 2026-04-02 17:21 | 2026-04-04 | 2026-04-04 17:38 |  |  |  |  | 2026-04-19 | 2026-04-21 19:27 | 2026-05-25 | 2026-05-26 09:29 | 2026-05-27 | 2026-05-26 09:29 |  |  | 2026-06-26 | 2026-06-28 17:40 | 2026-06-27 |  | 2026-06-29 |  | 2026-06-30 | [6 empty] | 2026-07-18 |  | 2026-07-27 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-30 |  |  |  | 2026-08-21 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-06-28 |  | 2026-04-30 | 2026-04-19 15:23 | Site is RTMI | 2026-03-28 | 2026-03-28 20:37 | 1222638 | 220074 | 0 | 0 | 0 | 0 | 888179.6262 | 144097 | 2026-06-16 18:32:55 +0530 | Manzoor Shaikh | The customer is at the EC for the meeting with Shweta, and wanted to know the handover timelines, as per Shweta, Safalta gave the PKO date 25th June and as per that the handover informed to the client which is 1st week of September 2026. | 2026-04-24 17:56:06 +0530 | Manzoor Shaikh | Dear Mr. Asmita Sorap, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 25th April at 04:00 PM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Shweta will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-04-19 17:53:47 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-20 | 2026-04-19 17:35 | 2026-05-03
19171 | Turnkey | 2026-01-01 | Nitin Shetty | Kalpataru Elitus | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 1915335 | 9999 | 0 | 0 | 0 | 109 | 0 | 181535 | 191534 | 860834 | 671434 |  |  | 2026-03-28 | 2026-03-28 21:58 | 2026-04-09 | 2026-04-09 18:42 | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-04-20 |  | 2026-04-28 |  | 2026-04-29 |  |  |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 | [6 empty] | 2026-05-27 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-08 |  |  |  | 2026-06-30 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-05-07 |  | 2026-04-15 |  | Unknown | 2026-03-28 | 2026-03-28 21:57 | 0 | 0 | 0 | 0 | 0 | 0 | 1625967 | 289368 | 2026-04-07 12:51:59 +0530 | Krutika Vernekar | DCM: Kalpataru ElitusÂ 2bhkÂ 15 L budgetÂ 789 sqftÂ Husband : FinanceÂ Wife : Sales MarketingÂ New born 4 m old , Parents are gonnna come and gooÂ Need 2 shoerack inside and outÂ Safety Door (open to designs) Living Room : TV , mandir , dining , ConsoleÂ Masteroom :Â Wardrobe +Bed + Side tables + Vanity Storage Guest Room : Granite bench for oldage in bathroom + Study + wardobe + Dresser + Storage Need Home Automation , Liked Membrane and Pu Finish + need Safe + place for Woofer in Living + have an existing gym Equipment + Liked Vertico Syncro Cabinet. Cx needs execued images of the building | [6 empty] | 2026-04-20 |  | 2026-04-27
19172 | Turnkey | 2026-01-01 | Mrs. Varsha Mahesh Parte | Damji shamji mahavir spring | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Lost | Prospect | DCM Due | 1941757 | 9999 | 0 | 0 | 0 | 109 | 0 | 184177 | 194176 | 863746 | 689659.6 |  |  | 2026-03-28 | 2026-03-28 21:57 | 2026-03-30 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-03-28 | 2026-03-28 21:55 | 0 | 0 | 0 | 0 | 0 | 0 | 1649775 | 291982 | 2026-04-02 11:19:23 +0530 | Maasoumeh Raza | DCM: Name: 19172 - Mrs. Varsha Mahesh ParteÂ Property Name: Damji shamji mahavir spring Property type: 2BHK Possession: April Move in: September Member:Â 3 memberÂ Â Budget: 12LÂ Requirements:Â Living room:Â Shoe rack [40 pairs] in bedroom TV unit [55 Inch] MandirÂ Â 4 Seater diningÂ Master Bedroom: Queen size BedÂ Wardrobe with loft side table Dressing unit Study table Master bathroom vanity below Kid's Bedroom: Queen size BedÂ Wardrobe with loft Study table Common bathroom vanity below Kitchen : Base unitÂ Wall unit Loft unitÂ Appliance unit Balcony: Planter Additional Work: False ceiling ElectrificationÂ Painting | 2026-03-28 21:58:47 +0530 | Vandana Preet | Some Image was uploaded |  |  |  | 2026-04-08 |  | 2026-04-15
19173 | Turnkey | 2026-01-01 | Parul Mishra | Pelican Square | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik |  | Parvez Syed | Nanda Kumar | Ranjith Kumar |  | Chanakya Panigrahi | Sunil Kumar S M | Active | Preproduction | 2D | 1507805 | 253399 | 1661242 | 1507805 | 0 | 1 | 0 | 0 | 0 | 684170 | 570236.4 |  |  | 2026-03-28 | 2026-03-29 11:02 | 2026-04-02 | 2026-04-02 17:07 | 2026-04-02 | 2026-04-02 21:45 | 2026-06-14 | 2026-06-14 19:49 | 2026-06-21 | 2026-06-20 16:06 | 2026-07-14 | 2026-07-12 18:00 | 2026-04-02 | 2026-04-04 14:01 | 2026-04-03 | 2026-04-04 14:15 | 2026-04-04 | 2026-04-07 14:25 | 2026-04-12 | 2026-04-12 19:12 |  |  |  |  | 2026-06-08 | 2026-06-14 18:03 | 2026-07-01 | 2026-07-04 15:42 | 2026-07-05 | 2026-07-04 15:42 |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-06 | 2026-06-03 18:01 | Site is RTMI | 2026-03-28 | 2026-03-29 11:01 | 1737902.5 | 286969 | 1651647.7596 | 272716 | 0 | 0 | 1651647.7596 | 272716 | 2026-07-12 18:24:47 +0530 | Purva Shiravle |  | 2026-06-16 10:52:39 +0530 | Purva Shiravle | DDM2: A.Living room - 1.Wall concept discussed i.e. with wall punning and mirror , in middle 2 ledges B.Guest bedroom - 1. instead of 3 door wardrobe , 2 door wardrobe required 2. Bed back wall - pink wallpaper is needed C.Master bedroom- 1.bedback wall concept - brick wallpaper 2.wardrobe , dressing placement discussed and finalised 3.study unit - placement & internals discussed and finalised 4. adjacent wall pastel blue required 5.addition of 2 door wardrobe D.Parents Bedroom Bedback full wall , wallpaper needed Wardrobe and dressing unit placement discussed and finalisedÂ | 2026-05-30 11:28:47 +0530 | Purva Shiravle | DDM1: 24-05-2026 Living room - Pooja unit and shoe rack - descoped Guest bedroom - cx wants wardrobe with drawers' shutter combination with pull down hanger accessory as of now they have asked me to add only in guest bedroom to get the rough idea of the quote So basically, addition of drawer cum shutter units and pull-down hanger in guest bedroom Master bedroom tall unit near study unit will be shifted outside of the room and addition of wall unit with ledges in study area Addition of used cloth unit near walk in wardrobe without loft In MBR - adjacent ledge was descoped near studyÂ | 2026-06-15 | 2026-06-14 19:52 | 2026-06-21 | 2026-06-20 16:15 | Under Construction | 2026-07-15
19174 | Turnkey | 2026-01-01 | Arun Murali | Runwal Forest | MUM - Thane | No Estimate | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-28 | 2026-03-29 14:50 | 2026-03-29 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-04-12 |  | 2026-04-20 |  | 2026-04-21 |  |  |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 | [6 empty] | 2026-05-19 |  | 2026-05-28 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-31 |  |  |  | 2026-06-22 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-04-29 |  | 2026-04-07 |  | Unknown | 2026-03-28 | 2026-03-29 14:49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-12 |  | 2026-04-19
19175 | Turnkey | 2026-01-01 | Mr. Gururaj Kulkarni | independent house | BNG - HSR | Yes | Priyanka Inchoor | Akshay Ds | Priyanka Mathur |  | RaviKumar Battala | Shijin C C | Jairam Joshi | Murali S | Ramesh Nayak | Sunil Kumar S M | Active | Installation | Execution | 1628662 | 1628662 | 1310035 | 0 | 1676162 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-28 | 2026-03-29 10:13 | 2026-03-30 | 2026-03-30 12:22 | 2026-04-02 | 2026-03-30 16:46 | 2026-04-25 | 2026-04-21 13:41 | 2026-05-14 | 2026-05-13 12:42 | 2026-05-29 | 2026-05-27 17:54 | 2026-03-30 | 2026-03-31 12:59 | 2026-03-31 | 2026-04-03 14:22 | 2026-04-03 | 2026-04-04 18:37 | 2026-04-12 | 2026-04-12 11:23 |  |  |  |  | 2026-04-21 | 2026-05-07 13:03 | 2026-05-14 | 2026-05-21 10:10 | 2026-05-22 | 2026-05-21 10:11 |  |  | 2026-05-30 | 2026-05-31 14:54 | 2026-05-31 | 2026-05-31 20:38 | 2026-06-01 | 2026-05-31 22:01 | 2026-06-07 | 2026-06-05 18:17 |  |  |  |  | 2026-06-05 19:02 | 2026-07-01 | 2026-06-30 13:33 | 2026-07-02 | 2026-07-01 12:30 | 2026-07-01 | 2026-07-09 12:53 | 2026-07-01 | 2026-07-10 16:19 | 2026-07-11 | 2026-07-11 10:07 | 2026-07-13 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-05-31 | 2026-06-05 12:34 | 2026-04-13 | 2026-04-21 13:07 | Site is RTMI | 2026-03-28 | 2026-03-29 10:12 | 1110199 | 199835 | 0 | 0 | 1918080.1042 | 316702 | 1918080.1042 | 316702 | 2026-07-02 11:35:34 +0530 | Jairam Joshi | 100% Payment: SRD task closed | 2026-06-27 14:51:28 +0530 | Jairam Joshi | 100% Payment: Bonito scope PI works completed CX side work in progress - will give keys 2days before dispach | 2026-06-18 13:10:10 +0530 | Jairam Joshi | Procurement: Bonito scope PI works completed CX side work in progress - will give keys 2days before dispach | 2026-04-22 | 2026-04-21 13:43 | 2026-05-14 | 2026-05-13 12:42 | RTMI
19176 | Turnkey | 2026-01-01 | Madhuri Rajesh Kenny | Puranik glorio | MUM - Thane | Yes | [8 empty] | Bhagyashree Salunkhe |  | Lost | Prospect | DCM Due | 1514211 | 9999 | 0 | 0 | 0 | 109 | 0 | 141422 | 151421 | 630986 | 580382.4 |  |  | 2026-03-28 | 2026-03-28 22:39 | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-04-13 |  | 2026-04-21 |  | 2026-04-22 |  |  |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 | [6 empty] | 2026-05-20 |  | 2026-05-29 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-06-01 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-04-30 |  | 2026-04-08 |  | Unknown | 2026-03-28 | 2026-03-28 22:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1283229 | 230981 | 2026-03-28 22:44:26 +0530 | Bhagyashree Salunkhe | [7 empty] | 2026-04-13 |  | 2026-04-20
19177 | Turnkey | 2026-01-01 | Vikram Kadam | prestige city | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | vinaya thakur |  | Active | Prospect | DCM Due | 906655 | 9999 | 0 | 0 | 0 | 108 | 0 | 80667 | 90666 | 392957 | 332367.2 |  |  | 2026-03-28 | 2026-03-29 20:10 | 2026-04-08 |  | 2026-03-31 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-04-11 |  | 2026-04-12 |  | 2026-04-12 |  | 2026-04-13 | [5 empty] | 2026-04-19 |  | 2026-04-27 |  | 2026-04-28 |  |  |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 | [6 empty] | 2026-05-26 |  | 2026-06-04 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-29 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-05-06 |  | 2026-04-14 |  | Unknown | 2026-03-28 | 2026-03-29 20:07 | 0 | 0 | 0 | 0 | 0 | 0 | 978443.0544 | 156608 | 2026-04-15 16:39:48 +0530 | vinaya thakur | Some Image was uploaded | 2026-04-08 16:27:01 +0530 | Karuna Shinde | DCM: Client Name: Vikram & Prabha Kadam Property: Prestige Siesta (11 ft height) Configuration: 1050 sq.ft Possession: Ready to Move Profession: Service Family Size: 3 Members Couple Son (13 years) SCOPE OF WORK End-to-end interior design False ceiling (Living Room) Integration of existing queen bed & mandir Vastu Consideration: Only mandir placement (facing East) Theme Preference: Overall: Modern Luxury Sons Room: Sporty Theme (Football-inspired) Budget Planned: 10 Lakhs CDP Meeting: 31st March, 3 PM AREA-WISE REQUIREMENTSLiving Room Shoe rack in foyer 6-seater dining setup 3-seater sofa + puffy TV unit with marble finish laminate or Wallpaper Integration of existing mandir Kitchen Base units Wall units Loft (service platform side) Appliances Planning: Fridge Chimney Water purifier Microwave Utility/Dry Balcony: Washing machine Storage above Soap rack Master Bedroom (Couple) King-size bed Wardrobe with loft Dresser Foldable study table Sons Bedroom (13 yrs) Existing bed Wardrobe Fixed study table with storage Theme: Football-inspired sporty look Bathrooms Vanity units Balcony Design options required Swing seating Tulsi placement ideas |  |  |  | 2026-04-19 |  | 2026-04-26
19179 | Turnkey | 2026-01-01 | Rashmi Awasthi | mahavir spring..DamjiShamji | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 2220293 | 9999 | 0 | 0 | 0 | 98 | 0 | 212030 | 222029 | 992162 | 784072.4 |  |  | 2026-03-28 | 2026-04-08 13:29 | 2026-03-29 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-03-28 | 2026-03-29 23:03 | 0 | 0 | 0 | 0 | 0 | 0 | 1884406 | 335887 | 2026-03-31 20:34:24 +0530 | Aryan Singh | Some Image was uploaded | 2026-03-30 12:10:22 +0530 | Aryan Singh | Some Image was uploaded | 2026-03-30 12:09:50 +0530 | Aryan Singh | Some Image was uploaded | 2026-04-08 |  | 2026-04-15
19182 | Turnkey | 2026-01-01 | N. K. Sudha Sudhakaran | Sheth Montana | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  |  | suraj kumar | Aditya Vikram |  |  | Shailendra Mishra | Active | Preproduction | 3D Sign off | 2299547 | 459909 | 2903703 | 2299547 | 0 | 3 | 43 | 0 | 0 | 1027560 | 812077.6 |  |  | 2026-03-29 | 2026-03-30 17:08 | 2026-03-29 | 2026-03-30 20:59 | 2026-04-02 | 2026-03-30 21:00 | 2026-06-07 | 2026-06-07 15:34 | 2026-06-22 | 2026-07-02 11:28 | 2026-07-09 | 2026-07-09 10:57 | 2026-03-30 | 2026-03-31 18:41 | 2026-03-31 | 2026-04-02 09:53 | 2026-04-02 | 2026-04-02 11:14 | 2026-04-04 | 2026-04-04 12:36 |  |  |  |  | 2026-06-09 | 2026-06-13 17:29 | 2026-06-22 | 2026-06-25 20:16 | 2026-06-26 | 2026-06-25 20:16 |  |  | 2026-07-11 | 2026-07-12 11:59 | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-04 | 2026-06-04 16:04 | Site is RTMI | 2026-03-29 | 2026-03-30 16:07 | 2460765 | 442937 | 2409903.0321 | 396541 | 0 | 0 | 2409903.0321 | 396541 | 2026-07-14 13:28:00 +0530 | Nazneen Chovvakkaran | 2D: | 2026-04-14 15:05:22 +0530 | Anil Jagtap | Possession will receive it next week | 2026-04-04 12:33:38 +0530 | Anamika Dolai | Done, explained milestones. | 2026-06-08 | 2026-06-11 10:49 | 2026-07-03
19186 | Turnkey | 2026-01-01 | Vikas | Aadarsh park height | BNG - HSR | Yes | Vishal Haridas | Akshay Ds | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Preproduction | DEM2 | 1748253 | 349650 | 2387511 | 0 | 0 | 7 | 62 | 0 | 0 | 699302 | 699301.2 |  |  | 2026-03-29 | 2026-03-29 14:12 | 2026-03-31 | 2026-03-31 18:06 | 2026-03-31 | 2026-03-31 19:26 | 2026-04-28 | 2026-04-28 16:27 | 2026-07-21 |  | 2026-07-28 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-04 10:46 | 2026-04-04 | 2026-04-04 12:01 | 2026-04-10 | 2026-04-10 19:01 |  |  |  |  | 2026-04-28 | 2026-04-29 17:06 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-04-11 | 2026-04-28 16:21 | Site is RTMI | 2026-03-29 | 2026-03-29 14:05 | 2023315 | 364196 | 0 | 0 | 0 | 0 | 2007663 | 331513 | 2026-06-16 19:10:06 +0530 | Akshay Ds | Some Image was uploaded | 2026-06-11 17:30:13 +0530 | Preethi Shetty | Client is not available as he's out of town, need to check their availability and schedule for next meeting and material selection | 2026-06-04 11:21:10 +0530 | Preethi Shetty | Some Image was uploaded | 2026-04-29 | 2026-04-28 16:33 | 2026-07-22 |  | Under Construction | 2026-04-15
19189 | Turnkey | 2026-01-01 | Ajay Desai | Steller Heights, Marol, Andheri | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Active | Preproduction | DEM2 | 1618235 | 259702 | 1574364 | 0 | 0 | 28 | 0 | 0 | 0 | 735119 | 623413.6 |  |  | 2026-03-29 | 2026-03-29 16:06 | 2026-04-19 | 2026-04-19 10:14 | 2026-04-22 | 2026-04-22 13:50 | 2026-06-14 | 2026-06-14 19:40 | 2026-06-20 |  | 2026-06-27 |  | 2026-04-22 | 2026-04-23 20:28 | 2026-04-23 | 2026-04-28 13:22 | 2026-04-28 | 2026-04-29 18:02 | 2026-04-30 | 2026-04-30 15:43 |  |  |  |  | 2026-06-14 | 2026-06-17 10:49 | 2026-06-22 |  | 2026-06-23 |  |  |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 | [6 empty] | 2026-07-21 |  | 2026-07-30 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-02 |  |  |  | 2026-08-24 |  | 2026-08-26 |  | 2026-08-27 | [5 empty] | 2026-07-01 |  | 2026-05-01 | 2026-06-14 19:28 | Site is RTMI | 2026-03-29 | 2026-03-29 16:05 | 1334206 | 240157 | 0 | 0 | 0 | 0 | 1606592.8845 | 271256 | 2026-06-14 19:12:09 +0530 | Riddhi Deshpande | DDM1: payment is done by cheque, task not ticked off | 2026-06-12 13:33:03 +0530 | Riddhi Deshpande | DDM1: meeting scheduled on 13th june - 5pm | 2026-06-02 17:53:07 +0530 | Reshma Melanta | CURRENTLY CIVIL WORK IS GOING ON POST THAT THE CLEINT WILL ALIGN FOR DEM 1- MEETING | 2026-06-15 | 2026-06-14 19:40 | 2026-06-21 |  | Under Construction | 2026-09-01
19192 | Turnkey | 2026-01-01 | Brajesh Singh | LNT Rejuve 360, Mulund West | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Mustufa Sohagpurwala |  | Lost | Prospect | DCM Due | 2768907 | 9999 | 0 | 0 | 0 | 108 | 0 | 266892 | 276891 | 1142005 | 1073120.8 |  |  | 2026-03-29 | 2026-03-29 16:44 | 2026-03-30 |  | 2026-03-31 |  | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-03-31 |  | 2026-04-01 |  | 2026-04-01 |  | 2026-04-02 | [5 empty] | 2026-04-08 |  | 2026-04-16 |  | 2026-04-17 |  |  |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-27 | [6 empty] | 2026-05-15 |  | 2026-05-24 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-27 |  |  |  | 2026-06-18 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-04-25 |  | 2026-04-03 |  | Unknown | 2026-03-29 | 2026-03-29 16:41 | 0 | 0 | 0 | 0 | 0 | 0 | 2349332 | 419574 | 2026-03-30 12:16:00 +0530 | Siddhi Chaphekar | DCM: Client Requirements(budget-12 to 15lacs) Livingroom- shoe rack with seating+wall paneling,Console unit,Foldable dining(movable),Crockery unit+mirror panelling,L shape sofa,swing in seating area,Tv unit design (bedroom door flushed) Kitchen-Parallel kitchen design with base+wall+loft ,GT PT unit, wicker basket and Serving trolley. Masterbedroom 1- Walkin wardrobe,tv unit,extendable bed(sofa cum bed),dresser Masterbedroom 2- Walkin wardrobe,tv unit,extendable bed(sofa cum bed),dresser Parents bedroom-Sofa cum bed,Wardrobe,Mandir. Note:Vanity units ans shower partition in all the bathrooms. Client believe's in vastu so the placement will be accordingly. Also Cx has mentioned that in next meeting,he wants to see one master bed with walkin wardrobe design and another master bed in normal as per interior designer so he can make decision whether to do walkin or not. | [6 empty] | 2026-04-08 |  | 2026-04-15
19194 | Turnkey | 2026-01-01 | Avinash | Pavani Mirabilia | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Aman Kumar |  | Active | Preproduction | DEM2 | 2066382 | 317420 | 2190118 | 0 | 0 | 58 | 0 | 0 | 0 | 954093 | 794868.8 |  |  | 2026-03-29 | 2026-03-29 17:28 | 2026-04-07 | 2026-04-07 12:58 | 2026-04-13 | 2026-04-13 15:52 | 2026-05-20 | 2026-05-16 19:22 | 2026-07-19 |  | 2026-08-06 |  | 2026-04-13 | 2026-04-17 11:36 | 2026-04-14 | 2026-04-17 19:35 | 2026-04-17 | 2026-04-20 11:47 | 2026-04-27 | 2026-04-27 16:07 |  |  |  |  | 2026-05-16 | 2026-05-18 18:56 | 2026-08-01 |  | 2026-08-02 |  |  |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 | [6 empty] | 2026-08-30 |  | 2026-09-08 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-11 |  |  |  | 2026-10-03 |  | 2026-10-05 |  | 2026-10-06 | [5 empty] | 2026-08-10 |  | 2026-06-13 | 2026-05-16 19:19 | Site is RTMI | 2026-03-29 | 2026-03-29 17:27 | 1856033 | 334085 | 0 | 0 | 0 | 0 | 2370898.677 | 391482 | 2026-06-04 11:48:59 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-06-04 11:47:57 +0530 | Muskan Agarwal | Minutes of Meeting (MOM) 1. Kitchen Tall unit and refrigerator to be repositioned. Loft to be added above the refrigerator. Replace 3 existing drawers with 2 larger drawers on the left side. Add a continuous loft patta. Check feasibility of smaller shutter for corner unit. Microwave to be integrated within the wall unit. Oven to be incorporated within the base unit. 2. Living & Dining Crockery unit to be designed with a total width of 6 ft, incorporating metal fabrication and shelves. Mandir to be positioned near the wall with an 8-inch offset for curtain provision. Mandir width to be 2.5 ft. Include a tray and decorative back panel. Top skirting to be added as per CX scope. TV unit design is finalized and approved. 3. Guest Bedroom (GBR) No TV ledges to be provided. Only wall design concepts to be executed. 4. Master Bedroom (MBR) Overall layout is finalized. Back panel to be added for the seating area. 5. Kids Bedroom (KBR) Provide a dresser layout near the bathroom. Study unit to be designed in L-shape with a maximum size of 3.5 ft. Wardrobe size to be reviewed and finalized. | 2026-05-19 11:14:31 +0530 | Muskan Agarwal | Some Image was uploaded | 2026-05-17 | 2026-05-16 19:24 | 2026-07-20 |  | Under Construction | 2026-05-31
19195 | Turnkey | 2026-01-01 | bhavin mehta | Pavani Mirabilia | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | Arun Kumar | Arun Kumar | Deekshith P | Jairam Joshi | Murali S | Raghavendra S | Abdul Shafeen | Active | Installation | Execution | 1207082 | 1207081 | 1533989 | 0 | 1238244 | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-29 | 2026-03-31 19:37 | 2026-03-31 | 2026-03-31 20:01 | 2026-03-31 | 2026-03-31 20:25 | 2026-04-18 | 2026-04-18 11:08 | 2026-05-14 | 2026-05-13 10:58 | 2026-05-14 | 2026-05-13 14:51 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-03 16:16 | 2026-04-03 | 2026-04-04 14:25 | 2026-04-09 | 2026-04-09 14:42 |  |  |  |  | 2026-04-13 | 2026-04-01 19:01 | 2026-05-09 | 2026-05-12 21:21 | 2026-05-13 | 2026-05-12 21:44 |  |  | 2026-05-19 | 2026-05-23 12:26 | 2026-05-24 | 2026-05-25 18:51 | 2026-05-26 | 2026-05-28 17:54 | 2026-05-29 | 2026-05-29 18:23 |  |  |  |  | 2026-06-02 10:57 | 2026-06-10 | 2026-06-11 21:02 | 2026-06-24 | 2026-06-22 13:34 | 2026-06-23 | 2026-06-24 15:44 | 2026-06-22 | 2026-06-24 15:49 | 2026-06-24 | 2026-06-25 09:39 | 2026-06-30 | 2026-06-30 10:35 |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-29 | [5 empty] | 2026-05-25 | 2026-06-02 10:56 | 2026-04-10 | 2026-04-18 11:06 | Site is RTMI | 2026-03-29 | 2026-03-30 12:18 | 1299990 | 233998 | 0 | 0 | 1278022.6284 | 220537 | 1278023.071 | 215783 | 2026-07-03 02:45:23 +0530 | Jairam Joshi | Execution: | 2026-06-22 17:39:47 +0530 | Jairam Joshi | 100% Payment: Pi works completed SRD task closed | 2026-06-18 17:52:52 +0530 | Jairam Joshi | Procurement: Key - Recieved Builder permission - 15th FC- 16th Ele - 17th - 19th - vendor delayed - 19th - 23rd SRD - 24th | 2026-04-19 | 2026-04-18 11:10 | 2026-05-14 | 2026-05-13 14:13 | Under Construction | 2026-05-01
19196 | Turnkey | 2026-01-01 | Suhas Utekar | kalpatru park | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Design | DEM1 | 1236174 | 247235 | 1569755 | 0 | 0 | 63 | 34 | 0 | 0 | 537354 | 451585.2 |  |  | 2026-03-29 | 2026-03-31 22:24 | 2026-03-31 | 2026-03-31 22:42 | 2026-04-03 | 2026-03-31 23:09 | 2027-02-04 |  | 2027-02-11 |  | 2027-02-18 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-07 11:42 | 2026-04-07 | 2026-04-09 15:02 | 2026-04-12 | 2026-04-12 13:44 |  |  |  |  | 2026-06-04 | 2026-04-14 16:41 | 2027-02-13 |  | 2027-02-14 |  |  |  | 2027-02-21 |  | 2027-02-22 |  | 2027-02-23 |  | 2027-02-24 | [6 empty] | 2027-03-14 |  | 2027-03-23 |  | 2027-03-22 |  | 2027-03-23 |  | 2027-03-24 |  | 2027-03-26 |  |  |  | 2027-04-17 |  | 2027-04-19 |  | 2027-04-20 | [5 empty] | 2027-02-22 |  | 2027-01-31 |  | Unknown | 2026-03-29 | 2026-03-30 11:39 | 1332588 | 237166 | 0 | 0 | 0 | 0 | 1330139.6223 | 210688 | 2026-07-03 17:27:40 +0530 | Manzoor Shaikh | Others: The client was looking for a cancellation, however, convinced the client and he stated that he will not continuing the site at Kalptaru for the Interior work however, in 2027 Ending he will continue at his residential Borivali Flat. | 2026-05-10 11:43:05 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-03 20:53:19 +0530 | Manzoor Shaikh | Some Image was uploaded | 2027-02-05 |  | 2027-02-12
19197 | Turnkey | 2026-01-01 | Jitendra sakhidas | Shivsagar | MUM - GOR | Yes | [8 empty] | Ashish Jha |  | Lost | Prospect | Onboarding Due | 1252990 | 176510 | 1765108 | 0 | 0 | 102 | 0 | 0 | 74088 | 539907 | 462485.2 |  |  | 2026-03-29 | 2026-03-29 19:50 | 2026-04-01 | 2026-04-01 15:02 | 2026-04-01 | 2026-04-01 15:16 | 2026-04-10 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-04-01 | 2026-03-31 | 2026-04-02 | 2026-04-04 12:43 | 2026-04-04 |  | 2026-04-05 | [5 empty] | 2026-04-11 |  | 2026-04-19 |  | 2026-04-20 |  |  |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 | [6 empty] | 2026-05-18 |  | 2026-05-27 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-30 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-04-28 |  | 2026-04-06 |  | Unknown | 2026-03-29 | 2026-03-29 19:48 | 1495854 | 269253 | 0 | 0 | 0 | 0 | 1493055.1722 | 241091 | 2026-04-20 12:15:13 +0530 | Bency Chacko |  | 2026-04-15 15:14:35 +0530 | Ashish Jha | Some Image was uploaded | 2026-04-10 12:03:53 +0530 | Royden Henriques | Some Image was uploaded | 2026-04-11 |  | 2026-04-18
19199 | Turnkey | 2026-01-01 | Vipin Singh | Kalpataru Srishti Namaah | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [5 empty] | Rashmita Das |  | Hold | Design | DEM1 | 801090 | 109999 | 1052109 | 0 | 0 | 39 | 47 | 0 | 50219 | 323918 | 316953.6 |  |  | 2026-03-29 | 2026-04-03 14:45 | 2026-04-02 | 2026-04-03 15:13 | 2026-04-04 | 2026-04-04 22:12 | 2026-12-13 |  | 2026-12-20 |  | 2026-12-27 |  | 2026-04-04 | 2026-04-07 18:53 | 2026-04-05 | 2026-04-08 13:14 | 2026-04-08 | 2026-04-20 10:10 | 2026-04-22 | 2026-04-22 14:07 |  |  |  |  | 2026-12-14 |  | 2026-12-22 |  | 2026-12-23 |  |  |  | 2026-12-30 |  | 2026-12-31 |  | 2027-01-01 |  | 2027-01-02 | [6 empty] | 2027-01-20 |  | 2027-01-29 |  | 2027-01-28 |  | 2027-01-29 |  | 2027-01-30 |  | 2027-02-01 |  |  |  | 2027-02-23 |  | 2027-02-25 |  | 2027-02-26 | [5 empty] | 2026-12-31 |  | 2026-12-09 |  | Site is RTMI | 2026-03-29 | 2026-03-30 11:37 | 891618 | 160491 | 0 | 0 | 0 | 0 | 884953.6185 | 152708 | 2026-05-29 17:25:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-29 17:09:48 +0530 | Manzoor Shaikh | Out called the customer to check if we can start the designing, asked to keep the project on hold for the next 6 months. | 2026-04-29 20:00:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-12-14 |  | 2026-12-21
19200 | Turnkey | 2026-01-01 | Karan Patel | AJMERA ARHAM | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 1822435 | 9999 | 0 | 0 | 0 | 107 | 0 | 172245 | 182244 | 753104 | 704843.6 |  |  | 2026-03-29 | 2026-03-30 12:59 | 2026-04-02 | 2026-04-02 13:20 | 2026-03-31 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-04-13 |  | 2026-04-21 |  | 2026-04-22 |  |  |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 | [6 empty] | 2026-05-20 |  | 2026-05-29 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-06-01 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-04-30 |  | 2026-04-08 |  | Unknown | 2026-03-29 | 2026-03-29 19:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1544436 | 277998 | 2026-04-02 12:26:03 +0530 | Rahul Agrawal | DCM: DCM Karan Patel Date: 01/04/26 PID: 19200 2+2 BHKÂ Family Details: Grandmother, parents, couple, daughter, sister Business family Possession: June Flat will be handed over in bare shell/raw condition Entrance Shoe rack with storage on both sides (but suggested only on one side) Living Plan seating for 810 people (sofa setup) Standing mandir (with option to convert to seating in future; wants foldable) TV unit with storage + crockery 8-seater dining table Mandir near kitchen only Jhula concept (removable) Bedroom 2 (12' x 10'10") Dadi Queen/King size bed with storage Wardrobe with loft Washroom: WC, basin, shower placement Side table cum dressing Same requirements for all bedrooms Kitchen Merge dry balcony with kitchen Storage in dry balcony Fridge: 40 inch Extend one side wall till living Dishwasher Oven, mixer, grinder, chimney Base + wall + loft cabinets Indoor AC unit in kitchen Granite for kitchen top Utility Maximum storage Storage for grains (rice, dal), oil containers Study table Flour mill Ironing space Wardrobe for monsoon clothes Space for trolley bags Include dry balcony in room Soft Civil Painting Electrical False ceiling Tiling installation for full flat (bathroom, kitchen, etc.) Automation in living room and, if possible, in bedrooms 3 Quotes Required Modular work Automation Civil work Next Step CDP Saturday | [6 empty] | 2026-04-13 |  | 2026-04-20
19202 | Turnkey | 2026-01-01 | Mr. Sandeep K Bhangare | Arihant Aspire | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Subhan Khan |  | Hold | Preproduction | DEM2 | 839340 | 167868 | 1211603 | 0 | 0 | 3 | 66 | 0 | 0 | 397993 | 273479.2 |  |  | 2026-03-29 | 2026-04-05 22:14 | 2026-04-03 | 2026-04-06 13:21 | 2026-04-09 | 2026-04-06 13:26 | 2026-05-20 | 2026-05-16 16:21 | 2026-08-06 |  | 2026-08-13 |  | 2026-04-06 | 2026-04-06 19:30 | 2026-04-07 | 2026-04-07 14:26 | 2026-04-07 | 2026-04-16 10:17 | 2026-04-24 | 2026-04-24 16:16 |  |  |  |  | 2026-05-16 | 2026-05-18 18:44 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-07-31 | 2026-05-16 16:19 | Site is RTMI | 2026-03-29 | 2026-04-04 14:02 | 1026782 | 184820 | 0 | 0 | 0 | 0 | 1025727.2674 | 158543 | 2026-07-02 19:52:56 +0530 | Anamika Dolai | Hold till July end | 2026-05-20 11:44:51 +0530 | Anamika Dolai | Some Image was uploaded | 2026-05-16 16:09:30 +0530 | Hemant Sonar | DDM1: Hi @~Sandeep Bhangare Sir, As discussed in todays meeting, please find the Minutes of Meeting (MOM) below: 1. Living room sofa cum bed is planned. 2. Semi-modular kitchen is confirmed. 3. All appliances will be planned as per standard modular sizes. 4. Master bedroom bed size to be revised as per site measurements. 5. Kids bedroom mirror added. 6. Side unit mirror added for used clothes. Please let us know if anything needs to be added or revised. | 2026-05-17 | 2026-05-16 16:23 | 2026-08-07
19203 | Turnkey | 2026-01-01 | Girish Gokhale | Arunkamal | MUM - GOR | Yes | Saif Shaikh | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Preproduction | DEM2 | 1363630 | 272726 | 1720843 | 0 | 0 | 1 | 28 | 0 | 0 | 577557 | 513346.8 |  |  | 2026-03-29 | 2026-05-28 13:23 | 2026-05-29 | 2026-05-29 14:20 | 2026-05-29 | 2026-05-29 17:34 | 2026-06-17 | 2026-06-16 11:33 | 2027-01-02 |  | 2027-01-09 |  | 2026-05-29 | 2026-05-29 18:32 | 2026-05-30 | 2026-05-29 18:34 | 2026-05-29 | 2026-06-03 11:59 | 2026-06-05 | 2026-06-05 17:34 |  |  |  |  | 2026-06-16 | 2026-06-16 18:58 | 2027-01-04 |  | 2027-01-05 |  |  |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 |  | 2027-01-15 | [6 empty] | 2027-02-02 |  | 2027-02-11 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-12 |  | 2027-02-14 |  |  |  | 2027-03-08 |  | 2027-03-10 |  | 2027-03-11 | [5 empty] | 2027-01-13 |  | 2026-06-06 | 2026-06-16 11:04 | Site is RTMI | 2026-03-29 | 2026-04-11 12:00 | 1460440 | 260403 | 0 | 0 | 0 | 0 | 1454198.0403 | 242977 | 2026-06-17 11:49:45 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-05 17:33:12 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement: Site is not accessible DEM Dates -Â DEM 1 - Cx is available for the meeting before 15th June also need to confirm this with designer DEM 2 - TBD DEM 3 - TBD Possession date : December 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-03 11:58:54 +0530 | Sanjana Swami |  | 2026-06-17 | 2026-06-16 11:33 | 2027-01-03 |  | Under Construction | 2026-12-31
19204 | Turnkey | 2026-01-01 | Mrs. Fatema Shiraz Painter | Piramal Aranya | MUM - GOR | No Estimate | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-29 | 2026-04-13 14:51 | 2026-03-30 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-04-06 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 | [6 empty] | 2026-05-13 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-25 |  |  |  | 2026-06-16 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-04-23 |  | 2026-04-01 |  | Unknown | 2026-03-29 | 2026-04-13 14:50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-15 15:01:42 +0530 | Harshaan Tiku | Some Image was uploaded | 2026-04-15 14:58:32 +0530 | Harshaan Tiku | Some Image was uploaded |  |  |  | 2026-04-06 |  | 2026-04-13
19205 | Turnkey | 2026-01-01 | Abhishek A Purwar | BDA apartment Kombalgodu | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1227401 | 9999 | 0 | 0 | 0 | 108 | 0 | 112741 | 122740 | 490960 | 490960.4 |  |  | 2026-03-29 | 2026-03-29 21:25 | 2026-04-15 |  | 2026-04-11 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-03-29 | 2026-03-29 21:23 | 0 | 0 | 0 | 0 | 0 | 0 | 1040171 | 187230 | 2026-04-15 13:31:30 +0530 | Maspi Das | Cx : Abhishek, 5 ppl (parents) Profession :IT , Father into bank Possession: Ready to move in Address:Â 503 phase 4, Block - 3, Kommalguda, chellagatta metro, BDA Flats KAMINIK Theme : looks good , decent colors Budget : 10-12lk South Entrance Entrance - Shoe unitÂ Living : 3+2 sofa, dewan wall mounted base unit, wall panelling - laminate , wallpaper, grooves or louvers Tall glass shutter & open unit on the either sides oh tv unit Pooja unit - (sit and do prefers) Arch panelling btw dining area & li Dining - 6 seater Base & wall cabinets for crockery with a tall unit if possible with double shutter Breakfast counter - kitchen entrance with arch panelling Kitchen - cook top, chimney 3ft , Fridge single door - in dining area, microwave, oven, air frier, mixer, RO unit wall mounted Granite is fixed need check on site L-shape base, wall & loft , one tall unit for appliances Utility - washing machine only wall cabinet Passage - in vanity area need storage space 7ft with loftÂ MBR - King size bed (parents) L- shape wardrobe & loft , dresser with mirror & one side tableÂ Bed back with wallpaper , louvers or laminate as per ref. foldable study unitÂ Bedroom - 1 (Abhishek) Queen size bed Wardrobe with loft, dresser unit , study unit fixed with draws & wall cabinet Bedroom - 2 Younger brother (queen size bed) Wardrobe with loft , dresser, study unit with wall cabinets Bathrooms - mirror with storages FC - No | [6 empty] | 2026-04-26 |  | 2026-05-03
19206 | Turnkey | 2026-01-01 | Dr. Geetanjali Amol Gitte | Mahavir Spring | MUM - GOR | No Estimate | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-29 | 2026-04-03 16:49 | 2026-03-30 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-03-29 | 2026-04-03 16:47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-08 18:38:28 +0530 | Anant Giri | Some Image was uploaded | [6 empty] | 2026-06-07 |  | 2026-06-14
19208 | Turnkey | 2026-01-01 | Jyoti Salunkhe | Atul Horizon | MUM - Thane | No Estimate | [8 empty] | Bhagyashree Salunkhe |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-29 | 2026-03-29 22:34 | 2026-03-30 |  | 2026-05-08 |  | 2026-05-15 |  | 2026-05-22 |  | 2026-05-29 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-05-16 |  | 2026-05-24 |  | 2026-05-25 |  |  |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 | [6 empty] | 2026-06-22 |  | 2026-07-01 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-04 |  |  |  | 2026-07-26 |  | 2026-07-28 |  | 2026-07-29 | [5 empty] | 2026-06-02 |  | 2026-05-11 |  | Unknown | 2026-03-29 | 2026-03-29 22:27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-30 11:52:54 +0530 | Bhagyashree Salunkhe | As discussed with Cx while registration she is fine with DCM by this month of April month but CDP she shall do by May month only due to Financial crisis | 2026-03-29 22:47:13 +0530 | Bhagyashree Salunkhe | Some Image was uploaded |  |  |  | 2026-05-16 |  | 2026-05-23
19209 | Turnkey | 2026-01-01 | MYBSK TECHNOLOGIES PRIVATE LIMITED (Sunil Khetal) | Hill view | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Bhagyashree Salunkhe |  | Hold | Preproduction | DEM2 | 1300690 | 260138 | 1592285 | 0 | 0 | 50 | 4 | 0 | 0 | 537502 | 503050 |  |  | 2026-03-29 | 2026-03-29 22:20 | 2026-04-08 | 2026-04-08 16:27 | 2026-04-18 | 2026-04-18 15:19 | 2026-05-20 | 2026-05-20 20:20 | 2027-01-01 |  | 2027-01-08 |  | 2026-04-18 | 2026-04-21 17:52 | 2026-04-19 | 2026-04-23 14:19 | 2026-04-23 | 2026-04-29 18:10 | 2026-05-07 | 2026-05-07 10:52 |  |  |  |  | 2026-05-20 | 2026-05-22 19:08 | 2027-01-03 |  | 2027-01-04 |  |  |  | 2027-01-11 |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 | [6 empty] | 2027-02-01 |  | 2027-02-10 |  | 2027-02-09 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-13 |  |  |  | 2027-03-07 |  | 2027-03-09 |  | 2027-03-10 | [5 empty] | 2027-01-12 |  | 2026-05-08 | 2026-05-16 15:06 | Site is RTMI | 2026-03-29 | 2026-03-29 22:12 | 1551737.6035 | 264685 | 0 | 0 | 0 | 0 | 1526413.007 | 248958 | 2026-07-11 12:38:41 +0530 | Anil Jagtap |  | 2026-06-24 12:23:31 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-18 21:04:45 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-05-21 | 2026-05-20 20:20 | 2027-01-02
19210 | Turnkey | 2026-01-01 | Shivangi Singh | crystal tower | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1251874 | 9999 | 0 | 0 | 0 | 93 | 0 | 115188 | 125187 | 527589 | 473910.4 |  |  | 2026-03-29 | 2026-04-13 14:50 | 2026-03-30 |  | 2026-03-29 |  | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-03-29 |  | 2026-03-30 |  | 2026-03-30 |  | 2026-03-31 | [5 empty] | 2026-04-06 |  | 2026-04-14 |  | 2026-04-15 |  |  |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-25 | [6 empty] | 2026-05-13 |  | 2026-05-22 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-25 |  |  |  | 2026-06-16 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-04-23 |  | 2026-04-01 |  | Unknown | 2026-03-29 | 2026-04-13 14:49 | 0 | 0 | 0 | 0 | 0 | 0 | 1063197 | 188676 | [9 empty] | 2026-04-06 |  | 2026-04-13
19211 | Turnkey | 2026-01-01 | Mrs. Syeda Umme Asma | SNN RAJ SERENITY | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 2265892 | 457999 | 2699450 | 0 | 0 | 38 | 0 | 0 | 0 | 901536 | 906356.8 |  |  | 2026-03-30 | 2026-03-30 10:53 | 2026-04-04 | 2026-04-04 10:40 | 2026-04-05 | 2026-04-05 15:22 | 2026-05-25 | 2026-05-26 20:12 | 2026-11-06 |  | 2026-11-13 |  | 2026-04-05 | 2026-04-16 13:12 | 2026-04-06 | 2026-04-16 13:12 | 2026-04-16 | 2026-04-17 15:21 | 2026-04-18 | 2026-04-18 17:28 |  |  |  |  | 2026-06-15 | 2026-06-07 19:21 | 2026-11-08 |  | 2026-11-09 |  |  |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 |  | 2026-11-19 | [6 empty] | 2026-12-07 |  | 2026-12-16 |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-19 |  |  |  | 2027-01-10 |  | 2027-01-12 |  | 2027-01-13 | [5 empty] | 2026-11-17 |  | 2026-05-09 | 2026-05-21 15:31 | Site is RTMI | 2026-03-30 | 2026-03-30 10:53 | 2287670 | 411780 | 0 | 0 | 0 | 0 | 2702563.2 | 462339 | 2026-05-21 08:26:27 +0530 | Shefali | DDM3: MOM for both meetings Living room -Â Shoe rack - Change shoe rack to bottom with skirting, change in the unit alignment and number of shelves, add loft, bottom siting storage to drawer, Tv unit As per reference, add 1 display unit for books, Existing 1 painting to be incorporated in design,Â Dining table - 6 seater dining table, crockery unit design as poer reference selcted, removing wall bwading concept. Kitchen - aadding drawer unit instead of shutter unit, add detergent pull out, pull out dustbin, 3 wicker basket, 3 feet fridge, roller unit with bottom unit, add dedo tiles, Add spice rack, Light in bottom unit internals,Â Utlity - full to be modified as per, wall mounted RO, requirement, add 1 tall unit to mop, and 1Â unit for pantry,Â Master bedroom - Dresser unit with tall glass unit, remover side table, try to add day bed space, wall concept on opposite wall concept, increase in the wardrobe size and adding open unit,Â Guest bedroom - L shaped bay window siting with side table, Wardrobe internals freezed,Â Sons room - full arrangement changed, add pencill drawer in study table, 1 tall display unit, white board marker, pinup board and wall concept in front on study table, Wardrobe internal freezed, add side table,Â Study room - shifting of wall units to opposite wall, study table with pencil drawers, place forÂ adjustable height table, l shaped wall ledge, Daughter room - increase in the size of wardrobe, canopy bed, bookshelve with dresser unit | 2026-04-23 18:35:28 +0530 | Shefali | Some Image was uploaded | 2026-04-17 15:21:42 +0530 | Bency Chacko | Possession - OC available - July 2026 IMs can be taken No on-site work is planned No civil work is planned Can close the 10% after closing the LFM Agreements cleared Checklist cleared offers, Quote and timelines are explained The scope of work is explained and clarified | 2026-06-15 | 2026-06-07 19:45 | 2026-11-07 |  | Under Construction | 2026-07-31
19212 | Turnkey | 2026-01-01 | Mamta Ganji | Park east by Ruchira | BNG - HSR | Yes | Preethi Shetty | Akshay Ds | Priyanka Mathur | [5 empty] | Aman Kumar |  | Hold | Preproduction | DEM2 | 1910141 | 380935 | 2849332 | 0 | 0 | 28 | 47 | 0 | 0 | 822787 | 706419.2 |  |  | 2026-03-29 | 2026-03-31 18:49 | 2026-03-31 | 2026-03-31 19:36 | 2026-03-31 | 2026-03-31 19:43 | 2026-04-30 | 2026-04-30 20:31 | 2026-08-01 |  | 2026-08-08 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-06 12:11 | 2026-04-06 | 2026-04-07 17:24 | 2026-04-12 | 2026-04-12 19:01 |  |  |  |  | 2026-04-30 | 2026-05-01 17:32 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-04-13 | 2026-04-30 20:27 | Site is RTMI | 2026-03-29 | 2026-03-31 12:46 | 2414688 | 434643 | 0 | 0 | 0 | 0 | 2251192.0111 | 371080 | 2026-06-16 11:27:42 +0530 | Akshay Ds | Some Image was uploaded | 2026-05-29 15:05:43 +0530 | Akshay Ds | Some Image was uploaded | 2026-05-16 12:10:04 +0530 | Preethi Shetty | Some Image was uploaded | 2026-05-01 | 2026-04-30 20:35 | 2026-08-02 |  | Under Construction | 2026-07-31
19213 | Turnkey | 2026-01-01 | siddhesh Satam | RUNWAL FOREST | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri | Prasad Bhivaji Hande | Active | Preproduction | DEM2 | 999846 | 222319 | 1176577 | 0 | 0 | 7 | 75 | 0 | 0 | 405341 | 372185.6 |  |  | 2026-03-30 | 2026-03-31 10:44 | 2026-03-30 | 2026-03-31 11:02 | 2026-04-03 | 2026-03-31 11:08 | 2026-04-08 | 2026-04-08 14:58 | 2026-04-17 | 2026-04-16 20:35 | 2026-08-15 |  | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-02 10:55 | 2026-04-02 | 2026-04-03 16:39 | 2026-04-08 | 2026-04-08 12:23 |  |  |  |  | 2026-04-11 | 2026-04-15 19:00 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-04-09 | 2026-04-08 14:46 | Site is RTMI | 2026-03-30 | 2026-03-30 17:02 | 997099 | 179477 | 0 | 0 | 0 | 0 | 997098.8066 | 170824 | 2026-07-02 19:45:45 +0530 | Divya Rahangdale | Hold till July end | 2026-04-17 13:51:22 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-04-11 11:59:16 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-04-09 | 2026-04-11 13:21 | 2026-04-17 | 2026-04-16 20:36
19214 | Turnkey | 2026-01-01 | Ravi Mamilla | Sakthi Tranquilis | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | Onboarding Due | 1181643 | 162999 | 1479825 | 0 | 0 | 76 | 0 | 0 | 73330 | 489612 | 455702 |  |  | 2026-03-29 | 2026-03-30 12:27 | 2026-03-31 | 2026-03-31 11:45 | 2026-04-23 | 2026-04-29 14:57 | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 | 2026-04-30 17:31 | 2026-04-30 | 2026-04-30 18:52 | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-03-29 | 2026-03-30 12:22 | 1254089 | 225736 | 0 | 0 | 0 | 0 | 1239245.2425 | 209233 | 2026-05-09 19:24:08 +0530 | Sanjana Swami | Client is highly escalated and is asking for cancellation due to the delay in project timelines. Client stated that as per the application, the project handover was expected in the month of August. However, the timelines are now getting extended from our end, which will impact his planned housewarming ceremony in August. Client mentioned that the delay is from our side and customers projects should not get hampered because of internal delays. He was not ready to listen to the timeline explanation during the call. Additionally, client raised concerns regarding the payment structure and mentioned that 10% payment was already collected at the time of CDP, and now another 10% payment is being requested despite there being no clarity on IMs and 1st DEM timelines. Client also stated that he has been continuously following up for the project initiation but has not received a satisfactory response from our side. Client compared our timelines with other vendors and mentioned that other vendors are committing to project handover within 60 days. Overall, client is extremely unhappy with the current experience and is considering cancellation due to the delays impacting his housewarming plans. | 2026-05-09 18:33:54 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-05-08 16:31:01 +0530 | Sanjana Swami | RTMI property IMs has to be done as soon as possible. Client will be available for 1st DEM next week. No civil work at site Transaction will be B2C self-funding. Notes: Client wants the project to be completed in 2 months. He mentioned that already we have delayed for IMs, and he is clueless as to why we are delaying. Client said that the referral amount of Jyotiraditya will be transferred to him and we can even get the same cleared with Janvi | 2026-05-07 |  | 2026-05-14
19215 | Turnkey | 2026-01-01 | Kushal Doshi | Saint Roof | MUM - Thane | Yes | [8 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 1600621 | 9999 | 0 | 0 | 0 | 106 | 0 | 150063 | 160062 | 640248 | 640248.4 |  |  | 2026-03-29 | 2026-03-31 12:33 | 2026-06-20 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-03-29 | 2026-03-31 12:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1356458 | 244162 | [9 empty] | 2026-07-13 |  | 2026-07-20
19217 | Turnkey | 2026-01-01 | Ushir pankaj | Unaati supreme | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Shreyash Kotecha |  | Hold | Preproduction | Site Readiness 1 | 919988 | 183998 | 1280958 | 0 | 0 | 2 | 79 | 0 | 0 | 394368 | 341622 |  |  | 2026-03-28 | 2026-04-01 11:11 | 2026-04-10 | 2026-04-10 12:11 | 2026-04-13 | 2026-04-12 14:11 | 2026-05-24 | 2026-05-24 20:27 | 2026-09-04 |  | 2026-09-11 |  | 2026-04-12 | 2026-04-13 19:32 | 2026-04-13 | 2026-04-14 12:04 | 2026-04-14 | 2026-04-15 14:52 | 2026-04-23 | 2026-04-23 10:56 |  |  |  |  | 2026-05-18 | 2026-05-24 18:25 | 2026-09-06 |  | 2026-09-07 |  |  |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 | [6 empty] | 2026-10-05 |  | 2026-10-14 |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-17 |  |  |  | 2026-11-08 |  | 2026-11-10 |  | 2026-11-11 | [5 empty] | 2026-09-15 |  | 2026-05-30 | 2026-05-24 20:16 | Site is Non-RTMI | 2026-03-28 | 2026-03-31 20:01 | 1085558 | 195400 | 0 | 0 | 0 | 0 | 1065453.3992 | 170845 | 2026-07-04 17:22:04 +0530 | Anil Jagtap | The client is expected to receive possession by mid-September. | 2026-06-18 18:40:26 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-24 20:22:41 +0530 | Parnavi Joshi | Possession-Aug 2026 (Tentative) Kitchen- -Units below hob counter already provided by builder (not to be in bonito scope) -3 shutters in grey fluted profile glass shutters above service counter next to microwave unit -Space for Air fryer(size needs to be checked ) to be kept in the flap up unit above microwave as rolling shutter not recommended as per space availability -Spice pull out unit added below service counterÂ -Existing window 3' ht, not full length as in model -Storage above w.m in dry balcony space Dry balcony already enclosed (to be checked post IM visit Living room- -Dining -4 seater to be placed leaving space near Buddha's statue -Buddha statue shelf height to be adjustedÂ -Buddha 3d mural/painting to be considered instead of murti Daughters bedroom- -Shivaji maharaj statue to be kept on shelf near window, shelf to be added -Wardrobe internal retained and approved Master bedroom- -Mirror with storage needed -Dresser unit drawer to be wall hung for aÂ pouffy to be kept under it Next meeting- After receiving possession(for material selection) | 2026-05-25 | 2026-05-24 20:32 | 2026-09-05
19218 | Turnkey | 2026-01-01 | Ashish Soni | Builder Floor | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Harshit Choudhary | Saddam Hussain Z M |  |  | Abdul Shafeen | Active | Preproduction | Site Readiness 2 | 678648 | 462557 | 954461 | 709146 | 678648 | 2 | 0 | 0 | 0 | 0 | 216091 |  |  | 2026-03-30 | 2026-03-31 11:12 | 2026-03-31 | 2026-03-31 19:48 | 2026-04-02 | 2026-04-02 13:38 | 2026-04-23 | 2026-04-21 12:21 | 2026-06-11 | 2026-06-10 18:00 | 2026-07-02 | 2026-07-02 12:16 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-04 18:29 | 2026-04-04 | 2026-04-06 18:02 | 2026-04-09 | 2026-04-09 17:50 |  |  |  |  | 2026-04-21 | 2026-05-10 13:28 | 2026-06-19 | 2026-06-24 22:49 | 2026-06-25 | 2026-06-24 23:06 |  |  | 2026-07-04 | 2026-07-07 16:52 | 2026-07-09 | 2026-07-09 19:22 | 2026-07-10 | 2026-07-10 10:57 | 2026-07-14 | 2026-07-13 15:38 | [5 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-09 | 2026-07-12 15:39 | 2026-04-10 | 2026-04-21 12:14 | Site is RTMI | 2026-03-30 | 2026-03-30 18:57 | 808865 | 145595 | 796099.9944 | 131437 | 814504.879 | 134476 | 814504.879 | 134476 | 2026-06-29 11:46:34 +0530 | Shivani Shet | Some Image was uploaded | 2026-06-10 18:40:52 +0530 | Shivani Shet | DDM2: 7 May 2026 Minutes of Meeting (MOM) Foyer Descoped the 2-drawer unit.Added a knob for the shoe rack.Considered a 2-shutter design for the shoe rack.Kitchen & Utility Removed the panel and added laminate finish on the tall unit and end cabinets in the kitchen.Added 2 dustbins in the utility area.Descoped the breakfast counter.All lighting to be warm lights.Provision for an in-built microwave considered in the tall unit.Wicker basket in the tall unit to be under the client's scope.Handles are not included in Bonito's scope for the kitchen and utility cabinets.Removed the Beading Master Bathroom Considered one wall unit shutter and one base unit shutter.Removed the shower cubicle.Removed the open wall unit and open base unit.Handles are not included in Bonito's scope.Guest Bathroom End-to-end cabinetry considered with one open cabinet.Handles are not included in Bonito's scope.Living Bathroom End-to-end cabinetry considered with one open cabinet.Handles are not included in Bonito's scope. | 2026-05-26 19:00:36 +0530 | Shivani Shet | DDM1: Hi Team, Please find below the updated customer requirements and discussion points for the project: 1. Hinges Requirement Customer requires Hettich Sensys hinges for all units in the foyer and kitchen areas.Hettich Veosys hinges to be used specifically for:Sink unitsBathroom unitsAny water-prone areas2. Base Drawer Units Customer requires: Hettich AvanTech YOU drawers with Quadro YOU500/550 mm, 30/40 kg capacityFull extension silent channelSilver finish sidesUnit Details: 780 mm 580 mm 700 mm 2 drawer units (Qty: 2)900 mm 580 mm 700 mm 3 drawer unit (Qty: 1)3. Tall Unit Internal Drawers Inside the tall unit, customer requires: Hettich Inlay internal drawersGlass on 3 sidesÂ Integrated lightingSuggestion required : Recommend either 3 or 4 internal drawer configurations based on usability and available clear internal height.Preferences: First preference: Warm lightSecond preference: Cool white lightPreferred finish: Silver drawer profileTall Unit Size: 450 mm 580 mm 2040 mm4. Pocket Door Pocket door is not required at present.Customer prefers to proceed entirely with Hettich solutions.5. Wicker Basket Replacement Instead of a wicker basket, customer prefers drawer units with: Silver side profileGlass front drawerSuggestion required: 3-drawer setup or 2 drawer to consider in 680mm space approx2 equal-size drawers1 smaller top drawer6. Dustbin Unit Customer is willing to proceed with the Bonito dustbin offering from Ebco.7. Crockery Unit Lighting Clarification required: Ebco is currently offering linear lighting in cool white.Need to check the availability of the same in warm white option. | 2026-04-22 | 2026-04-21 12:23 | 2026-06-11 | 2026-06-10 18:38 | RTMI
19219 | Turnkey | 2026-01-01 | Onkar Jambhale | LODHA AMARA | MUM - Thane | Yes | [8 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 1490595 | 9999 | 0 | 0 | 0 | 107 | 0 | 139061 | 149060 | 603901 | 588574.8 |  |  | 2026-03-29 | 2026-03-30 17:41 | 2026-03-31 | 2026-04-03 17:39 | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-04-12 |  | 2026-04-20 |  | 2026-04-21 |  |  |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 | [6 empty] | 2026-05-19 |  | 2026-05-28 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-31 |  |  |  | 2026-06-22 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-04-29 |  | 2026-04-07 |  | Unknown | 2026-03-29 | 2026-03-30 17:39 | 0 | 0 | 0 | 0 | 0 | 0 | 1263216 | 227378 | 2026-04-03 17:33:35 +0530 | Rutuja Kotwal | DCM: Mr. OnkarÂ JambhaleÂ Â 2 BHK.Â Â 618Â sq.ft.Â Lodha Amara thaneÂ Â Move inÂ -Â 5Â people.Â Â Husband, Wife-Â smita, Son- 6 yrs., and parents. And BrotherÂ Â Profession Finance sector. - Husband.Â Â Smita- HomeÂ maker.Â Â Design as per basicÂ vastu.Â Â DirectionÂ -Â ExitingÂ North west.Â Â Living Room-Â safety door,Â Shoe rack in the niche area,Â 4Â seaterÂ dining table, crockery unit,Â Sofa, TV unitÂ with mandir.Â Kitchen- Base units, wallÂ unitsÂ andÂ lofts .Â Shelves above Machine.Â Â Parents Bedroom / Kids BedroomÂ Bed cum bed, study unit with above storage, MirrorÂ onÂ wall ,Â wardrobe with lofts.Â Master Bedroom Wardrobe withÂ Lofts,Â Work station, Dressing table,Â Bed.Â Below and AboveÂ Vanity unitsÂ in both bathrooms.Â Â False ceiling,Â electricalsÂ and paintings.Â Â Budget 10 12 lakhs.Â Â Budget Suggested 17 18 lakhs.Â Â CDP-Â 4thÂ AprilÂ @Â 3pm.Â | [6 empty] | 2026-04-12 |  | 2026-04-19
19220 | Turnkey | 2026-01-01 | Kasi Kartheek Kiran Araveeti | SLV Classic | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Kushal S |  | Active | Preproduction | DEM2 | 1635605 | 231600 | 1508988 | 0 | 0 | 46 | 13 | 0 | 0 | 779250 | 624754.8 |  |  | 2026-03-30 | 2026-03-31 21:05 | 2026-04-02 | 2026-04-02 10:50 | 2026-04-02 | 2026-04-02 11:15 | 2026-04-29 | 2026-04-29 19:07 | 2026-09-04 |  | 2026-09-11 |  | 2026-04-03 | 2026-03-31 21:12 | 2026-04-03 | 2026-04-02 11:11 | 2026-04-03 | 2026-04-02 14:15 | 2026-04-05 | 2026-04-05 12:21 |  |  |  |  | 2026-04-29 | 2026-05-30 15:29 | 2026-09-06 |  | 2026-09-07 |  |  |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 | [6 empty] | 2026-10-05 |  | 2026-10-14 |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-17 |  |  |  | 2026-11-08 |  | 2026-11-10 |  | 2026-11-11 | [5 empty] | 2026-09-15 |  | 2026-04-06 | 2026-04-29 18:24 | Site is RTMI | 2026-03-30 | 2026-03-31 21:04 | 1278804 | 230184 | 0 | 0 | 0 | 0 | 1814279.5263 | 306321 | 2026-07-12 10:46:36 +0530 | Yogesh B |  | 2026-04-22 19:36:57 +0530 | Rajeshwari S | Some Image was uploaded | 2026-04-10 12:57:59 +0530 | Keerthan M | CDP: Kasi Kartheek Kiran Araveeti (Project No: 19220) Â tv unit tall shutter with Glass crockery base has to change to vanity base kitchen partition has to be discuss with CX Kitchen there is no loft GBR- Foldable accessories has to added GBR- need to discuss on Niche Part at site KBR- wallpaper has to select at the time of material selection bathroom vanity - if there is only granite at site balcony units are not adeed on ODP need to discuss at site for the placement - Cost has been consideredÂ MBR- need to give option with the combination of wallpaper and paintÂ painting cost is not addedÂ False ceiling is consider only for the living area | 2026-04-30 | 2026-04-29 19:46 | 2026-09-05 |  | Under Construction | 2026-04-30
19223 | Turnkey | 2026-01-01 | Sneha Kulkarni | builder floor | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S | Kushal S | Vishwa Hiremath | Active | Installation | Execution | 916663 | 916663 | 1251078 | 0 | 976663 | 25 | 8 | 0 | 0 | 0 | 0 |  |  | 2026-03-30 | 2026-03-31 21:02 | 2026-04-02 | 2026-04-02 11:16 | 2026-04-02 | 2026-04-02 12:11 | 2026-04-30 | 2026-04-26 19:13 | 2026-05-13 | 2026-05-12 11:27 | 2026-05-16 | 2026-05-15 23:24 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-04 18:36 | 2026-04-04 | 2026-04-07 11:26 | 2026-04-10 | 2026-04-10 18:13 |  |  |  |  | 2026-05-10 | 2026-05-11 16:15 | 2026-06-01 | 2026-05-15 22:33 | 2026-05-16 | 2026-05-15 23:13 |  |  | 2026-05-17 | 2026-05-17 11:33 | 2026-05-17 | 2026-05-17 20:59 | 2026-05-20 | 2026-05-21 06:42 | 2026-05-25 | 2026-05-25 18:23 |  |  |  |  | 2026-05-26 16:36 | 2026-06-04 | 2026-06-05 21:30 | 2026-06-14 | 2026-06-12 18:35 | 2026-06-13 | 2026-06-16 17:25 | 2026-06-12 | 2026-06-20 12:40 | 2026-06-19 | 2026-06-20 14:45 | 2026-06-22 | 2026-06-27 08:58 |  |  | 2026-07-16 |  | 2026-07-18 |  | 2026-07-19 | [5 empty] | 2026-05-19 | 2026-05-23 18:59 | 2026-04-11 | 2026-04-26 19:08 | Site is RTMI | 2026-03-30 | 2026-03-31 20:56 | 1060235 | 190842 | 0 | 0 | 1093942.5294 | 180635 | 1093942.5294 | 180635 | 2026-06-18 13:39:03 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-10 15:31:38 +0530 | Yogesh B | Some Image was uploaded | 2026-04-24 11:39:53 +0530 | Yogesh B | Some Image was uploaded | 2026-04-27 | 2026-04-26 19:16 | 2026-05-13 | 2026-05-12 11:27 | Under Construction | 2026-04-15
19225 | Turnkey | 2026-01-01 | Durga Prasad | Samhita serena MTB | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1446844 | 9999 | 0 | 0 | 0 | 31 | 0 | 134685 | 144684 | 624057 | 533418.4 |  |  | 2026-03-29 | 2026-04-03 13:49 | 2026-05-23 | 2026-05-23 13:20 | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-03-29 | 2026-03-30 17:17 | 0 | 0 | 0 | 0 | 0 | 0 | 1226139 | 220705 | 2026-05-23 13:20:25 +0530 | Rhea Rathod | DCM: Possession - Soft handover - June Profession - ITÂ Family of 3 - Daughter 8 yrs old Theme - Open to suggestions Ground floor- Due to constrain in natural lighting, the colours scheme to be kept light/pastel colours East facing Samhita serene Existing furniture - - 2 beds - 1 king. 1 super king - Study table - 5x3.5 - 2 tables Living area - - L shaped sofa - Pooja unit - Loose furniture - North east corner 3' - Tv unit- Suspended unit - Tall unit with ledges - Entrance wall - Radha-Krishna statue with wall concept Kitchen - - Utility wall isn't there - Single door - existing, design to be showed with double door fridgeÂ - Sink - one single bowl, One bigger sink - Hob - east facing - Tall appliance unit - to accommodate induction and microwave - U shaped kitchen - Wall units - Chajja existing - to be checked as per the video - LoftÂ - Granite - to be provided Dining area- - 6 seater - Crockery unit - no glass doors - Vanity unit with top storage and mirror - Washing machine - point outside the common washroom Master bedroom- - Wardrobe wall is straight (no niche) - Wardrobe with loft - Mirror- pull out to be planned inside the wardrobe - Study unit with top shelf, bay window seater, tall unit Bedroom 1- - Wardrobe with loft - Mirror- pull out to be planned inside the wardrobe - Existing study unit Bedroom 2- - Wardrobe with loft - Existing study unit | [6 empty] | 2026-07-04 |  | 2026-07-11
19226 | Turnkey | 2026-01-01 | Shaktidhar Vishal | Assetz Marq | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1656816 | 17784 | 2248077 | 0 | 0 | 2 | 0 | 147898 | 165682 | 721456 | 603996.4 |  |  | 2026-03-30 | 2026-04-17 18:15 | 2026-04-03 | 2026-04-18 12:47 | 2026-04-21 | 2026-05-13 17:50 | 2026-06-10 |  | 2026-06-17 |  | 2026-06-24 |  | 2026-05-13 |  | 2026-05-14 | 2026-06-04 16:10 | 2026-06-04 |  | 2026-06-05 | [5 empty] | 2026-06-11 |  | 2026-06-19 |  | 2026-06-20 |  |  |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 | [6 empty] | 2026-07-18 |  | 2026-07-27 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-30 |  |  |  | 2026-08-21 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-06-28 |  | 2026-06-06 |  | Unknown | 2026-03-30 | 2026-03-30 17:20 | 1905150 | 342927 | 0 | 0 | 0 | 0 | 1848767.9792 | 305257 | 2026-06-23 14:47:48 +0530 | Christopher Macwan | Some Image was uploaded | 2026-06-11 18:06:56 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Scope of Work: Modular + Wallpaper + Membrane (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+ 10+ 31 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible Informed the client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,48,768 Offers Discussed During the Call: Free Shoerack Offer Free Hob & Chimney Offer Design fee waiver (5%) PM fee waiver (5%) Laminate Upgrade - Windows to Wonderful home Services - Windows to Wonderful Home Modular - Windows to Wonderful home Final Closing Value Discussed: 16,56,816 Checklist terms - descoping, delay compensation, agreement terms are not clear. Rejection: Client mentioned that he has not received the updated invoice and the design details.He mentioned that he has not received the agreement soft copy.Client is not aligned with the project completion timeline of 99 business days, which is 99 + 10 + 31 business days (he was told that the project will be completed in 3 months, i.e., 1 month for designs, 1 month for production and 1 month for execution)Client mentioned that there is a possibility that the possession will be delayed beyond November also, so a price protection approval is required Client wants a clarity on the above mentioned pointers and then he will proceed with the OB call | 2026-06-11 17:07:55 +0530 | Sanjana Swami |  | 2026-06-11 |  | 2026-06-18
19227 | Turnkey | 2026-01-01 | Raju Jha | kalpatru vivant | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Hold | Design | 20% Payment | 1474961 | 202443 | 2024433 | 0 | 0 | 11 | 74 | 0 | 92549 | 628387 | 551582 |  |  | 2026-03-30 | 2026-04-02 16:04 | 2026-04-02 | 2026-04-02 16:18 | 2026-04-03 | 2026-04-03 15:19 | 2026-04-21 | 2026-04-21 14:21 | 2026-04-27 |  | 2026-05-04 |  | 2026-04-03 | 2026-03-31 | 2026-04-04 | 2026-04-07 14:55 | 2026-04-07 | 2026-04-07 16:47 | 2026-04-10 | 2026-04-10 16:05 |  |  |  |  | 2026-08-04 |  | 2026-04-29 |  | 2026-04-30 |  |  |  | 2026-05-07 |  | 2026-05-08 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-05-08 |  | 2026-04-11 | 2026-04-21 10:47 | Site is Non-RTMI | 2026-03-30 | 2026-03-30 18:10 | 1715621 | 308811 | 0 | 0 | 0 | 0 | 1665196.64 | 274951 | 2026-07-07 12:22:55 +0530 | Reshma Melanta | Others: | 2026-06-02 17:07:46 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-27 17:48:00 +0530 | Vishakha Vaishnav | as discussed with client he is not sure when he will receive the possession hence keeping the project on hold till August | 2026-04-22 | 2026-04-21 15:50 | 2026-04-28
19229 | Turnkey | 2026-01-01 | Pranay Thakker | Mahavir Spring | MUM - Thane | Yes | [10 empty] | Active | Prospect | DCM Due | 2092359 | 9999 | 0 | 0 | 0 | 104 | 0 | 199237 | 209236 | 865045 | 808842.4 |  |  | 2026-03-29 | 2026-04-02 13:14 | 2026-06-12 | 2026-06-12 17:37 | 2026-04-24 |  | 2026-06-22 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-06-23 |  | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-18 |  | Unknown | 2026-03-29 | 2026-04-02 10:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1773186 | 319173 | 2026-06-12 17:14:09 +0530 | Yerra Bharat | Some Image was uploaded | [6 empty] | 2026-06-23 |  | 2026-06-30
19231 | Turnkey | 2026-01-01 | Sunil Kumar Katariya ll | **************** | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 3857908 | 9999 | 0 | 0 | 0 | 103 | 0 | 375792 | 385791 | 1571858 | 1514468.8 |  |  | 2026-03-30 | 2026-04-03 17:03 | 2026-03-31 | 2026-04-06 14:28 | 2026-04-07 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-04-15 |  | 2026-04-23 |  | 2026-04-24 |  |  |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-04 | [6 empty] | 2026-05-22 |  | 2026-05-31 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-03 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-05-02 |  | 2026-04-10 |  | Unknown | 2026-03-30 | 2026-04-03 16:40 | 0 | 0 | 0 | 0 | 0 | 0 | 3269414 | 588494 | 2026-04-06 14:24:36 +0530 | Ankita Agarwal | DCM: MOM Interior Design DiscussionClient Name: Mr. Sunil Project: Apartment Balaji Park View Facing: East Members: 5 Members 2 Sons (21 yrs & 17 yrs)Ceiling Height: 10.5 ft Budget: 20 Lakhs (Stretch: 2530 Lakhs) Possession Status: No Update 1. Foyer AreaShoe Unit with storage capacity for 5060 pairsModify/reduce entrance wall for better space flowOpposite entrance wall to be designed as a highlight feature wall2. Living RoomNew L / U-shaped sofa setupTV Unit Minimal base unit (no heavy storage/display)3. Pooja UnitMarble pooja setupDedicated ceiling design for pooja space4. Dining AreaProvision for additional storageHighlight wall design6-seater dining table (iron base preferred)Crockery unit with storage5. KitchenClient to share reference imagesWall + loft storage on fridge wallKitchen to be planned as per final layoutBaking setup opposite fridgeStore room: 1 Tall unitGranite countertops6. Master BedroomDresser unitSliding doorWardrobe in walk-in spaceCurved couchMinimal TV unit (55)Sliding partitionBed back wall design7. Siddhs RoomWardrobe + LoftStudy unit with minimal storage (12th standard requirement)Cricket-themed elementsMirror with dresser (Important)Display unit8. Mothers RoomDesign as per referenceQueen size bed9. Elder Sons Room (Varun)Gold accent elementsStudy unit (minimal storage)Wardrobe + LoftSeating spaceDresser near bed10. General RequirementsFalse ceiling in all areasUsed clothes storage provision in every bedroomDresser near mirror (wherever applicable) | [6 empty] | 2026-04-15 |  | 2026-04-22
19233 | Turnkey | 2026-01-01 | RAJESH KUMAR SWAIN & SUBHASMITA NAYAK | SSVR Niyaraa | BNG - HRBR | Yes | Vishal Bandi | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Design | DEM1 | 700564 | 70000 | 700564 | 0 | 0 | 100 | 0 | 0 | 70113 | 280226 | 280225.6 |  |  | 2026-03-30 | 2026-04-02 11:51 | 2026-03-31 | 2026-04-02 11:52 | 2026-04-05 | 2026-04-03 19:10 | 2026-09-26 |  | 2026-10-03 |  | 2026-10-10 |  | 2026-04-03 | 2026-03-31 | 2026-04-04 | 2026-04-03 19:13 | 2026-04-03 | 2026-04-06 11:24 | 2026-04-12 | 2026-04-13 09:20 |  |  |  |  | 2026-09-27 |  | 2026-10-05 |  | 2026-10-06 |  |  |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 | [6 empty] | 2026-11-03 |  | 2026-11-12 |  | 2026-11-11 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-15 |  |  |  | 2026-12-07 |  | 2026-12-09 |  | 2026-12-10 | [5 empty] | 2026-10-14 |  | 2026-04-14 |  | Unknown | 2026-03-30 | 2026-04-01 17:44 | 788065.3985 | 130128 | 0 | 0 | 0 | 0 | 788065.3985 | 130128 | 2026-06-18 13:42:57 +0530 | Rajeshwari S | Discussed with client Client is saying not to call very often, he will get connected to us once he gets the possession He wants to start with the design phase only on getting the possession and make the 10% payment only after layout finalization. | 2026-06-12 16:42:16 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-07 16:59:14 +0530 | Rajeshwari S | Some Image was uploaded | 2026-09-27 |  | 2026-10-04 |  | Under Construction | 2026-05-31
19234 | Turnkey | 2026-01-01 | Razia thanewala |  | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Foram Joshi |  | Hold | Preproduction | Site Readiness 1 | 2578176 | 516999 | 0 | 0 | 0 | 2 | 27 | 0 | 0 | 1220597 | 840580.4 |  |  | 2026-03-30 | 2026-04-17 12:12 | 2026-04-17 | 2026-04-17 16:10 | 2026-04-17 | 2026-04-22 12:12 | 2026-05-15 | 2026-05-15 16:21 | 2026-07-15 |  | 2026-07-22 |  | 2026-04-17 | 2026-04-17 18:24 | 2026-04-23 | 2026-04-22 12:49 | 2026-04-22 | 2026-04-23 10:31 | 2026-05-14 | 2026-05-14 18:12 |  |  |  |  | 2026-07-20 | 2026-06-16 18:56 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-07 |  | 2026-09-09 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-16 | [5 empty] | 2026-07-26 |  |  |  |  | 2026-03-30 | 2026-03-30 20:43 | 0 | 0 | 0 | 0 | 0 | 0 | 2765438.8445 | 477179 | 2026-06-26 12:04:05 +0530 | Naved Malik | Some Image was uploaded | 2026-06-13 19:34:06 +0530 | Naved Malik | Some Image was uploaded | 2026-06-13 13:43:12 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-16 | 2026-05-15 16:22 | 2026-07-16
19235 | Turnkey | 2026-01-01 | Parveen KHAN | Roswalt Zaiden | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Design | DEM1 | 1244513 | 149999 | 1559398 | 0 | 0 | 19 | 81 | 0 | 98904 | 520345 | 475265.2 |  |  | 2026-03-30 | 2026-04-01 16:18 | 2026-03-30 | 2026-04-03 15:39 | 2026-04-03 | 2026-04-03 15:43 | 2026-08-05 |  | 2026-08-12 |  | 2026-08-19 |  | 2026-04-03 | 2026-03-31 | 2026-04-04 | 2026-04-04 14:10 | 2026-04-04 | 2026-04-06 11:41 | 2026-04-09 | 2026-04-09 18:36 |  |  |  |  | 2026-08-06 |  | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-08-01 |  | Unknown | 2026-03-30 | 2026-04-01 16:07 | 1321524 | 237874 | 0 | 0 | 0 | 0 | 1319705.3465 | 221493 | 2026-07-10 13:22:28 +0530 | Reshma Melanta | Others: CX NOT REVERTING TO CALLS OR MESSAGE LAST CONVERSASTION WITH CX WAS HE IS APPLYING FOR LOAN AND THE SAME WAS APPROVED, THE CX ALSO MENTIONED THAT THE POSSESSION IS SHIFTED TO DEC 2026, CURRENTLY HAVE KEPT THE PROJECT ON HOLD ONCE THE CX REVERTS WILL ALIGN THE DEM 1 MEETING. | 2026-05-02 13:08:40 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-17 13:25:44 +0530 | Reshma Melanta | Some Image was uploaded | 2026-08-06 |  | 2026-08-13
19241 | Turnkey | 2026-01-01 | Sujatha | SNN Raj Serenity | BNG - HSR | Yes | Sreenivasulu Reddy | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha | Raghavendra Gowda | Hold | Preproduction | CM | 1885906 | 288133 | 1659106 | 0 | 0 | 0 | 69 | 0 | 0 | 864858 | 732915.2 |  |  | 2026-03-30 | 2026-04-01 00:34 | 2026-04-07 | 2026-04-07 17:43 | 2026-04-10 | 2026-04-14 13:02 | 2026-04-21 | 2026-04-21 16:38 | 2026-07-13 |  | 2026-07-20 |  | 2026-04-14 | 2026-04-14 13:02 | 2026-04-15 | 2026-04-16 13:01 | 2026-04-16 | 2026-04-16 16:10 | 2026-04-18 | 2026-04-18 19:39 |  |  |  |  | 2026-04-21 | 2026-04-22 15:17 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-04-19 | 2026-04-21 15:29 | Site is RTMI | 2026-03-30 | 2026-03-31 20:54 | 1406022 | 253084 | 0 | 0 | 0 | 0 | 1922387.908 | 328867 | 2026-06-11 19:46:50 +0530 | Chittipireddy Sriharish | DDM2: Master bedroom Wardrobe - internals and size need to be as show room set up Bedroom 2 D shape mirror Used cloth storage need to be added Wall ledges need to be provided Bedroom 3 TV unit - flap down with glass shutters Bedroom 4 Study unit along with the wardrobe Puja unit - One step above puja unit | 2026-05-29 16:07:10 +0530 | Akshay Ds | Some Image was uploaded | 2026-04-23 11:32:10 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-22 | 2026-04-21 16:38 | 2026-07-14 |  | Under Construction | 2026-05-11
19244 | Turnkey | 2026-01-01 | Sanjeev Mhatre | luma | MUM - GOR | Yes | Khyati Bandi | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 1001347 | 209999 | 1260756 | 0 | 0 | 20 | 12 | 0 | 0 | 401858 | 389489.6 |  |  | 2026-03-29 | 2026-04-07 13:00 | 2026-05-19 | 2026-05-20 12:09 | 2026-05-23 | 2026-05-27 14:08 | 2026-06-13 | 2026-06-13 11:18 | 2026-08-01 |  | 2026-08-08 |  | 2026-05-23 | 2026-05-23 22:28 | 2026-05-24 | 2026-05-27 12:53 | 2026-05-28 | 2026-06-03 19:55 | 2026-06-05 | 2026-06-05 17:56 |  |  |  |  | 2026-06-17 | 2026-06-13 10:36 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-06-06 | 2026-06-13 11:16 | Site is RTMI | 2026-03-29 | 2026-03-31 22:35 | 1068437 | 192318 | 0 | 0 | 0 | 0 | 1068437.1285 | 180242 | 2026-07-03 11:22:57 +0530 | Vishakha Vaishnav | Others: CX HAS NOT YET RECEVIED THE POSSESSION | 2026-06-13 11:07:11 +0530 | Khyati Bandi | LIVING AREA -Â 1. Blinds in breakfast counterÂ 2. 2 chairs for dining 3. Pleated partition in kitchen entrance 4. Wall and blinds color to be matchedÂ 5. Bottom cabinets to be added with drawers 6. existing mandir to be used, cover up with one unitÂ 7. Three seater sofa cum bed with one chair parallelyÂ 8. Add curve above diningÂ 9. TV back wall to be in curve moldingÂ 10. Add glass shutter near tv unit to keep show piecesÂ KITCHEN 1. Janitor unit as per IM, or else tall unit with shelves to keep broom/mopper 2. Matka provision to be given below RO unitÂ 3. Solid shutters near chimney both sides PARENTS ROOM -Â 1. Extend loft till doorÂ 2. Procurement of book shelf from market 3. Wallpaper+metal strip on bed back wall SONS ROOM -Â 1. Full length mirror in front of the door entranceÂ 2. Sofa murphy bed queen size will be thereÂ 3. Add loft above wardrobe 4. Add glass wall unit above study table to keep books | 2026-06-05 17:54:59 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : SITE IS NOT ACCESIBLE CX WILL LET US KNOW DEM Dates -Â DEM 1 - Cx is available for the meeting need to confirm with designer once DEM 2 - TBD DEM 3 - TBD Possession date : June end Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-14 | 2026-06-13 11:20 | 2026-08-02 |  | Under Construction | 2026-06-30
19245 | Turnkey | 2026-01-01 | Madhur Varma | Nahar amrit shakti | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 2340949 | 9999 | 0 | 0 | 0 | 57 | 0 | 224096 | 234095 | 1029902 | 842856.8 |  |  | 2026-03-29 | 2026-04-07 12:51 | 2026-05-19 | 2026-05-19 19:36 | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-03-29 | 2026-03-31 22:36 | 0 | 0 | 0 | 0 | 0 | 0 | 1983855 | 357093 | 2026-05-19 19:40:11 +0530 | Yash Jain | CDP: kitchen quote has to be sent with the current quote | 2026-04-14 16:25:34 +0530 | Saloni Sagwekar | Some Image was uploaded |  |  |  | 2026-05-27 |  | 2026-06-03
19246 | Turnkey | 2026-01-01 | Kinjal Thakkar | Monte south | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 2156619 | 9999 | 0 | 0 | 0 | 106 | 0 | 205663 | 215662 | 931293 | 794002 |  |  | 2026-03-31 | 2026-03-31 16:39 | 2026-04-01 |  | 2026-04-04 |  | 2026-04-11 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-04-04 |  | 2026-04-05 |  | 2026-04-05 |  | 2026-04-06 | [5 empty] | 2026-04-12 |  | 2026-04-20 |  | 2026-04-21 |  |  |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 | [6 empty] | 2026-05-19 |  | 2026-05-28 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-31 |  |  |  | 2026-06-22 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-04-29 |  | 2026-04-07 |  | Unknown | 2026-03-31 | 2026-03-31 16:38 | 0 | 0 | 0 | 0 | 0 | 0 | 1832879 | 323740 | 2026-04-15 17:03:25 +0530 | Umang Shah | Some Image was uploaded | 2026-04-04 14:00:40 +0530 | Priyanka Patel | DCM: 1. Name of the customer Kinjal Thakkar 2. Profession NA 3. Project Name/Tower Name/Flat Number Monthe 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK 5. Site Access Date 2026-04-04 6. Possession Date 2026-06-04 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 100000 Customer Preferences8. Who will be living in the house? Single, Joint Family 9. What activities do you usually prefer at your home ? Working From Home, Family Bonding, Prayer 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any NA 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) NA Upload reference images 14. Any absolute no-go styles colours or materials NA 15. Do you have any existing furniture that must be accommodated? NA 13. Do you want the design to reflect any personal story, cultural influence, or special memory NA ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Safety Door, Partition, Seating, Console, Shoe rack 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? TV Focus 2. Must-have furniture or features? Sofa, Statement Wall/ Feature, Display unit , Puja unit, Bookshelves, Coffee table, Speakers, Home speakers, TV unit 3. Choose your decor inspirations Plants 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Washing machine, Built-in Oven, Chimney, Hob, Fridge, Microwave 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining No 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Study Table, TV unit, Dresser, Bookshelf 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Parents 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? NA 3. What are your requirements for Utility Area? NA Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Cloths Drying, Any other Miscellaneous1. Timeline related commitment made by Bonito, if any NA 2. Other commitments made by Bonito to customer, if any NA 3. What are offers committed to customers? YES 4. Move-in date confirmed with customer 2026-10-04 5. Any special occasion mentioned by the customer wrt handover date NA 6. Additional Requirements (Mention any requirements from customer not covered in the form) NA 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 800000 |  |  |  | 2026-04-12 |  | 2026-04-19
19248 | Turnkey | 2026-01-01 | Murtaza Shabbir Unjhawala Fatema M Unjhawala | Ajmera Manhattan | MUM - Thane | No Estimate | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-29 | 2026-03-31 17:38 | 2026-03-30 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-03-29 | 2026-03-31 17:37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-05 12:32:40 +0530 | Vandana Preet | 21 gram silver coin is pending to hand over. | [6 empty] | 2026-05-04 |  | 2026-05-11
19249 | Turnkey | 2026-01-01 | Harish Sharma | Runwal Forest | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Hold | Preproduction | DEM2 | 1122296 | 297999 | 1444303 | 0 | 0 | 4 | 76 | 0 | 0 | 416216 | 408080.8 |  |  | 2026-03-31 | 2026-04-03 17:07 | 2026-04-10 | 2026-04-10 12:09 | 2026-04-11 | 2026-04-11 18:53 | 2026-05-10 | 2026-04-26 18:17 | 2026-09-01 |  | 2026-09-11 |  | 2026-04-11 | 2026-04-13 20:09 | 2026-04-12 | 2026-04-14 11:29 | 2026-04-14 | 2026-04-14 12:26 | 2026-04-23 | 2026-04-23 11:36 |  |  |  |  | 2026-04-20 | 2026-04-13 20:09 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 | [6 empty] | 2026-10-05 |  | 2026-10-14 |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-17 |  |  |  | 2026-11-08 |  | 2026-11-10 |  | 2026-11-11 | [5 empty] | 2026-09-15 |  | 2026-05-06 | 2026-04-26 17:29 | Site is RTMI | 2026-03-31 | 2026-04-01 17:33 | 1223985 | 220317 | 0 | 0 | 0 | 0 | 1223985.63 | 201706 | 2026-07-03 14:20:31 +0530 | Divya Rahangdale | Hold till August end | 2026-06-29 13:46:48 +0530 | Sakshi Pokharkar | CX will receive the possession in July end. | 2026-06-26 12:56:02 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-04-27 | 2026-04-26 18:49 | 2026-09-02
19250 | Turnkey | May'26 | HITEN D Chandan | Delta Prestige | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Lost | Prospect | DCM Due | 4352656 | 9999 | 0 | 0 | 0 | 106 | 0 | 425267 | 435266 | 1856902 | 1625222.8 |  |  | 2026-03-31 | 2026-03-31 19:38 | 2026-04-10 |  | 2026-04-04 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-05-04 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-04-21 |  | 2026-04-29 |  | 2026-04-30 |  |  |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 | [6 empty] | 2026-05-28 |  | 2026-06-06 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-09 |  |  |  | 2026-07-01 |  | 2026-07-03 |  | 2026-07-04 | [5 empty] | 2026-05-08 |  | 2026-04-16 |  | Unknown | 2026-03-31 | 2026-03-31 18:41 | 0 | 0 | 0 | 0 | 0 | 0 | 3688692 | 663964 | 2026-04-01 15:17:30 +0530 | Chaitali Sawant | Some Image was uploaded | 2026-04-01 14:46:48 +0530 | Chaitali Sawant | Pooja unit - Proper unit with sitting area. closed shutters with marble pooja unit. But mostly from outside | 2026-04-01 14:45:38 +0530 | Chaitali Sawant | Layout discussed in detail with civil work. Kitchen counter top installation , dado tile installation in bonito scope. 25 to 30 lacs suggested excluding civil work. | 2026-04-21 |  | 2026-04-28
19253 | Turnkey | 2026-01-01 | AAYOJAK EVENTS LLP | kalpatru park | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  |  | Yash Metha | Aditya Vikram |  | Anant Giri | Prasad Bhivaji Hande | Active | Preproduction | 2D | 1503366 | 390399 | 1902889 | 1503366 | 0 | 1 | 0 | 0 | 0 | 598964 | 514002.8 |  |  | 2026-03-31 | 2026-04-12 11:15 | 2026-04-12 | 2026-04-12 20:20 | 2026-04-15 | 2026-04-12 20:29 | 2026-05-15 | 2026-05-14 19:45 | 2026-07-09 | 2026-07-08 20:07 | 2026-07-09 | 2026-07-08 20:18 | 2026-04-12 | 2026-04-13 19:39 | 2026-04-13 | 2026-04-13 20:29 | 2026-04-13 | 2026-04-14 12:02 | 2026-04-22 | 2026-04-22 18:00 |  |  |  |  | 2026-04-20 | 2026-04-13 19:40 | 2026-06-21 | 2026-06-22 22:25 | 2026-06-23 | 2026-06-22 22:26 |  |  | 2026-07-11 | 2026-07-14 15:56 | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-05-08 | 2026-05-09 14:05 | Site is RTMI | 2026-03-31 | 2026-03-31 21:13 | 1615114 | 287775 | 1604976.8813 | 251237 | 0 | 0 | 1604976.8813 | 251237 | 2026-04-22 18:24:23 +0530 | Anamika Dolai | Done, milestones explained, client has requested for Initial Measurement on 26th of April. | 2026-04-14 19:28:55 +0530 | Anant Giri | Some Image was uploaded | 2026-04-14 12:02:44 +0530 | Royden Henriques | ___________________________________________ Possession : RTMI Payment Mode : B2C Self funding - Yes Already paid 27% girijanknair@gmail.com C-23, Aqua Kalpataru Park Riveria Takka Old Panvel, Kalpatru Post offers the amount is 13,95,866/- as per the offer email. 90 + 15 = 105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays. | 2026-05-15 | 2026-05-14 19:50 | 2026-07-09 | 2026-07-08 20:08
19254 | Turnkey | 2026-01-01 | Rajesh Shah | MAVERICK NAMI | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anant Giri |  | Lost | Design | DEM1 | 628691 | 209999 | 1921248 | 0 | 0 | 91 | 0 | 0 | 0 | 181456 | 237236.4 |  |  | 2026-03-29 | 2026-04-03 17:06 | 2026-04-09 | 2026-04-09 11:53 | 2026-04-12 | 2026-04-10 11:03 | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-04-10 | 2026-04-14 17:06 | 2026-04-11 | 2026-04-14 18:05 | 2026-04-14 | 2026-04-15 14:30 | 2026-04-21 | 2026-04-21 20:53 |  |  |  |  | 2026-06-06 |  | 2026-06-14 |  | 2026-06-15 |  |  |  | 2026-06-22 |  | 2026-06-23 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-06-23 |  | 2026-05-15 |  | Unknown | 2026-03-29 | 2026-04-01 17:33 | 1632395 | 288853 | 0 | 0 | 0 | 0 | 762633.55 | 126029 | 2026-06-17 11:47:51 +0530 | Christopher Macwan | Some Image was uploaded | 2026-06-09 11:27:34 +0530 | Christopher Macwan | Some Image was uploaded | 2026-06-05 18:08:29 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-06-06 |  | 2026-06-13
19256 | Turnkey | 2026-01-01 | Sreeram | Surksha | BNG - HSR | Yes | Sreenivasulu Reddy | Akshay Ds | Kowshik | [5 empty] | Fuzail Girach |  | Hold | Preproduction | Site Readiness 1 | 831290 | 166258 | 1190827 | 0 | 0 | 14 | 69 | 0 | 0 | 332516 | 332516 |  |  | 2026-03-31 | 2026-04-09 11:21 | 2026-04-09 | 2026-04-09 15:14 | 2026-04-09 | 2026-04-09 16:09 | 2026-04-25 | 2026-04-22 15:18 | 2026-07-25 |  | 2026-08-01 |  | 2026-04-09 | 2026-03-31 | 2026-04-10 | 2026-04-10 16:56 | 2026-04-10 | 2026-04-10 18:57 | 2026-04-14 | 2026-04-14 17:23 |  |  |  |  | 2026-04-22 | 2026-04-23 19:50 | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-05-28 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-04-15 | 2026-04-21 18:15 | Site is Non-RTMI | 2026-03-31 | 2026-04-08 18:07 | 1009175 | 181651 | 0 | 0 | 0 | 0 | 1002932 | 165608 | 2026-07-09 11:48:47 +0530 | Sreenivasulu Reddy | Site Readiness 1: Property detailsÂ Suraksha Springs Begur - Koppa Rd, Suraksha Nagar, Yelena Halli, Akshaya Nagar, Bengaluru, Karnataka 560114 | 2026-05-29 17:24:08 +0530 | Chittipireddy Sriharish | DDM2: Puja unit - need to be designed as per the references Space need to be provided all round the unit (vastu concerns) | 2026-05-29 17:20:29 +0530 | Chittipireddy Sriharish | DDM2: Kitchen Cylinder provision - need to be confirmed post initial measurements Dish washer - placement need to be confirmed | 2026-04-23 | 2026-04-22 15:19 | 2026-07-26 |  | RTMI
19262 | Turnkey | 2026-01-01 | Mukesh Mulji Parmar | Damji shamji mahavir spring | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Mustufa Sohagpurwala |  | Lost | Prospect | DCM Due | 1742431 | 9999 | 0 | 0 | 0 | 106 | 0 | 164244 | 174243 | 764664 | 629280.4 |  |  | 2026-03-31 | 2026-03-31 22:21 | 2026-04-12 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-05-01 |  | 2026-05-08 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-18 |  | 2026-04-19 | [5 empty] | 2026-04-25 |  | 2026-05-03 |  | 2026-05-04 |  |  |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 | [6 empty] | 2026-06-01 |  | 2026-06-10 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-13 |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-08 | [5 empty] | 2026-05-12 |  | 2026-04-20 |  | Unknown | 2026-03-31 | 2026-03-31 22:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1476636 | 265794 | 2026-05-26 12:53:27 +0530 | Bhagyashree Salunkhe | Cx has not made last payment to the builder yet,it will take more 1 month ,hence asked to call back June end so that he can give clarity about onboarding with us. | 2026-04-14 11:37:02 +0530 | Karuna Shinde | Some Image was uploaded |  |  |  | 2026-04-25 |  | 2026-05-02
19263 | Turnkey | 2026-01-01 | PREMALATHA THUNDY KANDY & VALSARAJAN NADAKKAKATH KALICHETHAN | SSVR Meridian | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Hold | Preproduction | Site Readiness 1 | 1027848 | 205570 | 1342176 | 0 | 0 | 8 | 69 | 0 | 0 | 413678 | 408600 |  |  | 2026-03-31 | 2026-04-06 14:32 | 2026-04-11 | 2026-04-11 22:18 | 2026-04-14 | 2026-04-13 17:38 | 2026-04-26 | 2026-04-26 17:46 | 2026-09-06 |  | 2026-09-13 |  | 2026-04-13 | 2026-04-16 14:03 | 2026-04-14 | 2026-04-16 14:11 | 2026-04-16 | 2026-04-16 17:12 | 2026-04-18 | 2026-04-18 18:02 |  |  |  |  | 2026-04-26 | 2026-04-29 13:46 | 2026-09-08 |  | 2026-09-09 |  |  |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 | [6 empty] | 2026-10-07 |  | 2026-10-16 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-19 |  |  |  | 2026-11-10 |  | 2026-11-12 |  | 2026-11-13 | [5 empty] | 2026-09-17 |  | 2026-04-19 | 2026-04-26 17:39 | Site is Non-RTMI | 2026-03-31 | 2026-04-06 14:27 | 1137437 | 204738 | 0 | 0 | 0 | 0 | 1115821.019 | 184248 | 2026-04-18 17:47:22 +0530 | Akshay Ds | Possession is expected in OCT Layout discussion can be done in floor plan. customer isready to make the payment post DEM1 | 2026-04-16 17:12:07 +0530 | Bency Chacko | Possession - Oct 2026 Floor plan is shared - design needs to be closed on the floor plan Design meeting - Weekends B2C - Self-funded Checklist cleared Timelines cleared Will pay 10% after we close the layouts No on-site work is planned now No civil work is planned Agreements are cleared | 2026-04-16 14:09:52 +0530 | Pulivarthi Nirosha | Some Image was uploaded | 2026-04-27 | 2026-04-26 17:48 | 2026-09-07 |  | Under Construction | 2026-10-31
19265 | Turnkey | 2026-01-01 | Akshat Verma | Sarova Sienna | MUM - GOR | Yes | Rajnish Mishra | Reshma Melanta | Safalta Karkera |  | Mohammed Lal | Nishant Jadhav | Sandeep Tiwari | Murali S | Umang Shah | Siddhesh Gujrathi | Hold | Preproduction | Site Readiness 2 | 1129324 | 605000 | 1075068 | 0 | 1129324 | 8 | 9 | 0 | 0 | 0 | 524324 |  |  | 2026-03-25 | 2026-04-01 17:47 | 2026-04-01 | 2026-04-01 17:52 | 2026-04-02 | 2026-04-02 16:55 | 2026-05-04 | 2026-05-03 17:55 | 2026-06-29 | 2026-06-28 13:51 | 2026-06-24 | 2026-06-24 18:25 | 2026-04-02 | 2026-03-31 | 2026-04-03 | 2026-04-03 14:53 | 2026-04-03 | 2026-04-06 10:07 | 2026-04-14 | 2026-04-14 11:37 |  |  |  |  | 2026-05-03 | 2026-06-26 15:32 | 2026-07-03 | 2026-05-31 21:54 | 2026-06-01 | 2026-05-31 21:54 |  |  | 2026-06-25 | 2026-06-30 13:26 | 2026-06-30 | 2026-06-30 15:41 | 2026-07-01 | 2026-06-30 17:35 | 2026-07-01 | 2026-06-30 17:59 | [5 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-04-15 | 2026-05-03 17:08 | Site is RTMI | 2026-03-25 | 2026-04-01 17:39 | 911074 | 163993 | 0 | 0 | 1276073 | 229693 | 1276073 | 229693 | 2026-07-08 20:43:52 +0530 | Reshma Melanta | Others: | 2026-06-29 20:44:32 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-26 15:42:53 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-04 | 2026-05-03 18:24 | 2026-06-29 | 2026-06-28 13:52
19267 | Turnkey | 2026-01-01 | Shalini | Brigade El Dorado | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M |  | Mohammed Rasick | Vishwa Hiremath | Active | Design | 60% Payment | 1011104 | 140414 | 797278 | 1017483 | 1011104 | 5 | 0 | 0 | 0 | 466248 | 404441.6 |  |  | 2026-03-31 | 2026-04-04 16:46 | 2026-04-03 | 2026-04-04 16:47 | 2026-04-04 | 2026-04-04 18:11 | 2026-06-25 | 2026-06-25 19:06 | 2026-07-01 | 2026-06-30 16:36 | 2026-07-06 | 2026-07-05 18:43 | 2026-04-04 | 2026-03-31 | 2026-04-05 | 2026-04-05 15:02 | 2026-04-05 | 2026-04-06 11:42 | 2026-04-12 | 2026-04-12 19:54 |  |  |  |  | 2026-06-25 | 2026-06-30 16:31 | 2026-07-05 | 2026-07-05 16:59 | 2026-07-06 | 2026-07-05 17:40 |  |  | 2026-07-07 | 2026-07-08 19:15 | 2026-07-09 | 2026-07-09 17:28 | 2026-07-15 | 2026-07-10 12:18 | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-26 | 2026-06-25 17:06 | Site is RTMI | 2026-03-31 | 2026-04-04 12:59 | 675660 | 121618 | 1044227 | 187960 | 1039089 | 187036 | 1039089 | 187036 | 2026-06-28 11:18:16 +0530 | Yogesh B | Some Image was uploaded | 2026-06-14 16:28:09 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-13 18:58:56 +0530 | Vishnu S | Some Image was uploaded | 2026-06-26 | 2026-06-25 19:09 | 2026-07-01 | 2026-06-30 16:37 | RTMI
19268 | Turnkey | 2026-01-01 | Balveer Raj Bhandari | Sakar Swapna | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Uday Yadruk | Rizwan Mistry | Murali S | Umang Shah | Vinay Surve | Active | Installation | Execution | 1117707 | 1117708 | 1599276 | 0 | 1117707 | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-31 | 2026-04-02 12:27 | 2026-04-03 | 2026-04-03 11:33 | 2026-04-03 | 2026-04-03 17:07 | 2026-04-18 | 2026-04-18 18:01 | 2026-04-25 | 2026-04-24 12:38 | 2026-04-26 | 2026-04-26 19:49 | 2026-04-03 | 2026-03-31 | 2026-04-04 | 2026-04-04 16:41 | 2026-04-04 | 2026-04-06 11:55 | 2026-04-10 | 2026-04-10 18:53 |  |  |  |  | 2026-04-16 | 2026-04-14 19:11 | 2026-04-25 | 2026-04-26 18:41 | 2026-04-27 | 2026-04-26 18:44 |  |  | 2026-05-10 | 2026-05-17 17:37 | 2026-05-19 | 2026-05-19 16:02 | 2026-06-24 | 2026-05-20 21:07 | 2026-05-21 | 2026-05-25 18:39 |  |  |  |  | 2026-06-01 13:40 | 2026-06-09 | 2026-06-10 19:39 | 2026-06-22 | 2026-06-20 18:52 | 2026-05-26 | 2026-06-30 12:07 | 2026-06-20 | 2026-06-24 15:55 | 2026-06-24 | 2026-07-08 21:12 | 2026-07-10 | 2026-07-11 13:25 |  |  | 2026-07-01 |  | 2026-07-03 |  | 2026-07-04 | [5 empty] | 2026-05-19 | 2026-06-01 13:39 | 2026-04-11 | 2026-04-18 17:38 | Site is RTMI | 2026-03-31 | 2026-04-02 11:28 | 1355319 | 243957 | 0 | 0 | 1325551.027 | 218929 | 1325551.027 | 218929 | 2026-07-13 18:57:14 +0530 | Uday Yadruk | Execution: Modular - Modular installation work is in progress, we will finish the modular installation work by 15/07/2026 ( with snag ) NOTE : Modular material shifting support required for 3rd floor to 17th floor | 2026-07-03 16:28:25 +0530 | Meet Shah | Others: | 2026-06-14 15:28:09 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-04-19 | 2026-04-18 18:04 | 2026-04-25 | 2026-04-24 12:38
19269 | Turnkey | 2026-01-01 | Mahantesh | Sobha | BNG - HSR | Yes | Avishkar Sargam | Akshay Ds | Soumya KP | [5 empty] | Pulivarthi Nirosha |  | Active | Preproduction | DEM2 | 822067 | 164413 | 1308551 | 0 | 0 | 3 | 14 | 0 | 0 | 330520 | 327134 |  |  | 2026-03-31 | 2026-04-03 18:57 | 2026-04-03 | 2026-04-04 18:59 | 2026-04-07 | 2026-04-04 19:08 | 2026-05-12 | 2026-05-12 12:46 | 2026-07-21 |  | 2026-07-31 |  | 2026-04-04 | 2026-03-31 | 2026-04-05 | 2026-04-08 19:27 | 2026-04-08 | 2026-04-09 15:40 | 2026-04-12 | 2026-04-12 18:04 |  |  |  |  | 2026-07-07 | 2026-07-12 19:53 | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-06-06 | 2026-05-08 16:12 | Site is RTMI | 2026-03-31 | 2026-04-03 17:10 | 1108941 | 199609 | 0 | 0 | 0 | 0 | 1103551.085 | 182222 | 2026-06-04 11:08:14 +0530 | Preethi Shetty | DM1 has been done, need to collect 10% payment from client | 2026-05-16 12:05:18 +0530 | Preethi Shetty | 07/05/2026 3rd or 4th week of May- cross measurements (need to check cx availability) All internals to be fabric finish Handles to be by default - or in cost less handles to be provided TV unit - wood with white same as foyer storage unitÂ Kitchen counter to sink Utility - Granite to be removed for modular installation Granite in kitchen to be added in the quote Wall cabinets- L corner unit with shutters Kitchen - 2.5ft chimney & HOB unit Utility - bottom storage for cylinderÂ No cylinder unit in kitchen Foyer - no FC | 2026-05-16 12:04:44 +0530 | Preethi Shetty | Some Image was uploaded | 2026-05-13 | 2026-05-12 12:50 | 2026-07-22 |  | Under Construction | 2026-05-31
19270 | Turnkey | 2026-01-01 | Vinay pratap | pratap inspria | MUM - GOR | Yes | Priyanka Murarka | Manzoor Shaikh | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Nishant Jadhav | Sandeep Tiwari | Murali S | Sanskruti Yadav | Sunil Poojary | Active | Preproduction | Procurement | 1019284 | 614110 | 1681741 | 0 | 1024284 | 10 | 0 | 0 | 0 | 0 | 405174 |  |  | 2026-03-31 | 2026-04-05 21:33 | 2026-04-01 | 2026-04-05 21:44 | 2026-04-07 | 2026-04-07 13:39 | 2026-05-13 | 2026-05-13 19:54 | 2026-06-15 | 2026-06-14 15:24 | 2026-06-21 | 2026-06-21 13:27 | 2026-04-07 | 2026-04-07 14:05 | 2026-04-08 | 2026-04-07 14:05 | 2026-04-07 | 2026-04-17 16:10 | 2026-04-22 | 2026-04-22 19:33 |  |  |  |  | 2026-05-13 | 2026-05-28 20:17 | 2026-06-17 | 2026-06-20 21:37 | 2026-06-21 | 2026-06-21 03:40 |  |  | 2026-06-23 | 2026-06-26 13:47 | 2026-06-28 | 2026-06-28 21:23 | 2026-06-29 | 2026-06-29 20:47 | 2026-06-30 | 2026-06-29 21:19 |  |  |  |  | 2026-07-05 18:57 | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-28 | 2026-07-03 14:40 | 2026-04-23 | 2026-05-13 13:20 | Site is RTMI | 2026-03-31 | 2026-04-01 12:01 | 1425204 | 256536 | 0 | 0 | 1188148.1455 | 193405 | 1188148.1455 | 193405 | 2026-06-29 18:20:35 +0530 | Avinash Jaiswal | Added 5K due to difference in pre-lam. As approved by Nimish | 2026-06-29 18:13:50 +0530 | Avinash Jaiswal | Added 4K due to difference in pre-lam. As approved by Nimish | 2026-06-25 17:06:41 +0530 | Priyanka Murarka | Some Image was uploaded | 2026-05-14 | 2026-05-13 19:56 | 2026-06-15 | 2026-06-14 15:27
19271 | Sub Project |  | Chaithrika | IndependentHouse | BNG - HRBR |  | Sanjay Kulkarni | Rajeshwari S | Shibin Lal |  |  | Banka H Suthar | Saddam Hussain Z M | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-01 | 2026-04-06 14:53 | 2026-04-02 | 2026-04-06 14:53 | 2026-04-06 | 2026-04-06 14:53 | 2026-04-07 | 2026-04-06 14:54 | 2026-04-07 | 2026-04-06 14:55 | 2026-04-07 | 2026-04-06 14:57 | 2026-04-06 | 2026-04-06 14:54 | 2026-04-07 | 2026-04-06 14:54 | 2026-04-06 | 2026-04-06 14:54 | 2026-04-07 | 2026-04-06 14:54 |  |  |  |  | 2026-04-06 | 2026-04-06 14:55 | 2026-04-07 | 2026-04-06 14:56 | 2026-04-07 | 2026-04-06 14:56 |  |  | 2026-04-07 | 2026-04-06 14:59 | 2026-04-07 | 2026-04-06 15:05 | 2026-04-07 | 2026-04-06 15:05 | 2026-04-07 | 2026-04-06 15:06 |  |  |  |  | 2026-04-06 15:25 | 2026-04-12 | 2026-04-11 14:25 | 2026-04-13 | 2026-04-11 14:54 | 2026-04-12 | 2026-05-22 15:47 | 2026-04-11 | 2026-05-22 16:53 | 2026-05-22 | 2026-05-23 18:18 | 2026-05-24 | 2026-05-23 18:24 |  |  | 2026-05-25 | 2026-05-23 18:29 | 2026-05-25 | 2026-05-23 18:32 | 2026-05-28 | 2026-05-25 20:32 |  |  |  |  | 2026-04-06 | 2026-04-06 15:18 | 2026-04-07 | 2026-04-06 14:54 | Unknown | 2026-04-01 | 2026-04-06 14:53 | 0 | 0 | 0 | 0 | 46609 | 0 | 46609 | 0 | [9 empty] | 2026-04-07 | 2026-04-06 14:54 | 2026-04-07 | 2026-04-06 14:56
19272 | Turnkey | 2026-01-01 | Chandrakala Boggaram | null | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  | Sethuragavan R | Harshit Choudhary | Saddam Hussain Z M |  | Ramesh Nayak | Sunil Kumar S M | Active | Preproduction | 2D | 937084 | 173752.9 | 1177534 | 945992 | 937084 | 1 | 0 | 0 | 0 | 388498 | 374833.6 |  |  | 2026-03-31 | 2026-04-30 11:23 | 2026-04-30 | 2026-04-30 12:27 | 2026-04-30 | 2026-04-30 14:39 | 2026-06-11 | 2026-06-11 22:20 | 2026-07-02 | 2026-07-01 18:37 | 2026-07-09 | 2026-07-09 14:59 | 2026-04-30 | 2026-04-30 18:04 | 2026-05-01 | 2026-04-30 18:07 | 2026-04-30 | 2026-05-04 15:04 | 2026-05-12 | 2026-05-16 19:00 |  |  |  |  | 2026-06-11 | 2026-06-17 19:15 | 2026-07-02 | 2026-07-04 16:18 | 2026-07-05 | 2026-07-04 16:21 |  |  | 2026-07-10 | 2026-07-14 20:35 | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-04 | 2026-06-04 15:58 | Site is RTMI | 2026-03-31 | 2026-04-03 11:59 | 997910 | 179623 | 1102555.6176 | 182058 | 1094326.497 | 180699 | 1094326.497 | 180699 | 2026-07-10 15:48:05 +0530 | Manoj Kumar R |  | 2026-06-11 22:19:40 +0530 | Manoj Kumar R | Ground Floor Wardrobe Wardrobe will start above the existing platform.Shutters will project outward from the platform.Mirror is considered on the shutter.Ceiling curtain provision to be planned.Vanity Area Only Sink unit First Floor Handwash Area Sink unit Loft added above the chajja.Guest Bedroom Wardrobe will start above the existing platform.Wardrobe shutters will extend up to the chajja.Loft shutters will be extended to cover the chajja.Curved ledges are considered on the right side of the door space.Existing mirror can be reused next to the ledges.Kids' Bedroom Wardrobe will start above the existing platform.Wardrobe shutters will extend up to the first platform.Loft shutters will be extended to cover the chajja.Dresser unit with mirror is included.Master Bedroom Wardrobe will start above the existing platform.Wardrobe shutters will extend up to the chajja.Loft shutters will be extended to cover the chajja.Half-open and half-closed units are considered on the right side wall.All wardrobe internal have been modified. | 2026-05-16 19:34:54 +0530 | Akshay Ds | 1.Customer is not clear about the overall process. 2.Customer mentioned that tenants are currently staying in the property and will vacate on 1st July. 3.We have informed the customer that the existing furniture needs to be moved before conducting the CM. 4.Site will be available for us to start work only after the tenants vacate the property. 5.Customer is requesting us to move the existing furniture; however, we have informed them that this needs to be arranged from their end. 6.For IM activities, prior intimation needs to be given to the customer since tenants are staying at the property. 7.Customer is expecting project handover by the end of July. 8.Fast-track approval has already been taken by Naseeda and Rishi; however, customer acknowledgment is still pending. 9.Customer acknowledgment is also pending for the revised timeline. 10.There is a high possibility of the project getting escalated, as the customer is not clear about the project timeline. | 2026-06-12 | 2026-06-11 22:21 | 2026-07-02 | 2026-07-01 18:40 | Under Construction | 2026-07-03
19273 | Turnkey | 2026-01-01 | Betsy Rajgopal | Lodha NCP | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Lost | Design | DEM1 | 2429295 | 324580 | 3245803 | 0 | 0 | 29 | 5 | 0 | 161279 | 1097557 | 845878.8 |  |  | 2026-03-29 | 2026-06-08 18:59 | 2026-06-02 | 2026-06-08 22:13 | 2026-06-11 | 2026-06-08 23:15 | 2026-10-04 |  | 2026-10-11 |  | 2026-10-18 |  | 2026-06-08 | 2026-06-09 16:55 | 2026-06-09 | 2026-06-10 15:32 | 2026-06-09 | 2026-06-11 13:46 | 2026-06-16 | 2026-06-16 17:36 |  |  |  |  | 2026-10-05 |  | 2026-10-13 |  | 2026-10-14 |  |  |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 | [6 empty] | 2026-11-16 |  | 2026-12-11 |  | 2026-12-10 |  | 2026-12-11 |  | 2026-12-11 |  | 2026-12-16 |  |  |  | 2027-01-24 |  | 2027-01-25 |  | 2027-01-26 | [5 empty] | 2026-10-22 |  | 2026-09-30 |  | Unknown | 2026-03-29 | 2026-05-03 12:39 | 2753806 | 491996 | 0 | 0 | 0 | 0 | 2716296.4729 | 458588 | 2026-06-26 15:47:41 +0530 | Bency Chacko | Some Image was uploaded | 2026-06-16 17:35:30 +0530 | Manzoor Shaikh | "Welcome call done. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : 1st week of July as per the customer Customer will make 10% post LFM Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-11 13:45:04 +0530 | Athul Ajaykumar |  | 2026-10-05 |  | 2026-10-12 |  | Under Construction | 2026-07-15
19274 | Sub Project |  | Jack Partners |  | MUM - GOR |  | Priyanka Murarka | Reshma Melanta | Shantanu Parakh |  |  | Rajkumar Suthar | Rizwan Mistry | Murali S |  | Prasad Bhivaji Hande | Active | Handover | Project Closure Pending | 0 | 0 | 0 | 0 | 42641 | 22 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-02 | 2026-04-02 14:34 | 2026-04-03 | 2026-04-02 14:34 | 2026-04-02 | 2026-04-02 14:34 | 2026-04-03 | 2026-04-02 14:35 | 2026-04-03 | 2026-04-02 14:37 | 2026-04-10 | 2026-04-02 14:36 | 2026-04-02 | 2026-04-02 14:34 | 2026-04-03 | 2026-04-02 14:34 | 2026-04-02 | 2026-04-02 14:34 | 2026-04-03 | 2026-04-02 14:34 |  |  |  |  | 2026-04-02 | 2026-04-02 14:35 | 2026-04-03 | 2026-04-02 14:38 | 2026-04-03 | 2026-04-02 14:38 |  |  | 2026-04-06 | 2026-04-16 13:46 | 2026-04-17 | 2026-04-17 18:06 | 2026-04-21 | 2026-04-30 16:03 | 2026-05-01 | 2026-04-30 17:34 |  |  |  |  | 2026-05-13 18:45 | 2026-05-23 | 2026-05-23 18:52 | 2026-05-27 | 2026-05-25 14:57 | 2026-05-26 | 2026-06-20 18:18 | 2026-05-25 | 2026-06-20 21:20 | 2026-06-20 | 2026-06-20 21:48 | 2026-06-07 | 2026-06-20 14:12 |  |  | 2026-06-22 | 2026-06-22 18:13 | 2026-06-24 | 2026-06-22 18:20 | 2026-06-22 | 2026-06-23 11:18 |  |  |  |  | 2026-04-17 | 2026-04-20 12:04 | 2026-04-03 | 2026-04-02 14:34 | Unknown | 2026-04-02 | 2026-04-02 14:34 | 0 | 0 | 0 | 0 | 36137 | 6504 | 36137 | 6504 | [9 empty] | 2026-04-03 | 2026-04-02 14:35 | 2026-04-03 | 2026-04-02 14:37
19275 | Turnkey | 2026-01-01 | Reema Chanda | bitcoin paradise | MUM - GOR | No Estimate | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-02 | 2026-04-07 12:48 | 2026-04-02 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-04-02 | 2026-04-02 13:33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-14 16:24:16 +0530 | Saloni Sagwekar | Some Image was uploaded | [6 empty] | 2026-05-07 |  | 2026-05-14
19276 | Turnkey | 2026-01-01 | josenir Simon | Mahindra Alcove | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Savita Parab | Rizwan Mistry | Murali S | Moni Sahani | Aakash Gaikwad | Active | Production | Dispatch Due | 954497 | 954497 | 1337121 | 0 | 994497 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-02 | 2026-04-03 14:43 | 2026-04-03 | 2026-04-03 15:24 | 2026-04-07 | 2026-04-07 14:52 | 2026-04-22 | 2026-04-18 16:59 | 2026-05-03 | 2026-05-03 18:06 | 2026-05-12 | 2026-05-12 19:56 | 2026-04-07 | 2026-03-31 | 2026-04-08 | 2026-04-08 16:07 | 2026-04-08 | 2026-04-09 09:57 | 2026-04-12 | 2026-04-12 12:14 |  |  |  |  | 2026-04-18 | 2026-04-20 15:05 | 2026-05-06 | 2026-05-08 22:28 | 2026-05-09 | 2026-05-08 22:29 |  |  | 2026-05-14 | 2026-05-21 19:54 | 2026-05-22 | 2026-05-22 14:35 | 2026-05-23 | 2026-05-22 21:01 | 2026-05-23 | 2026-05-27 17:59 |  |  |  |  | 2026-06-01 14:40 | 2026-06-12 | 2026-06-11 21:04 | 2026-06-27 | 2026-06-25 18:19 | 2026-06-26 | 2026-07-06 19:19 | 2026-06-25 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-05-22 | 2026-06-01 14:39 | 2026-04-13 | 2026-04-18 16:33 | Site is RTMI | 2026-04-02 | 2026-04-02 18:43 | 1133153 | 203967 | 0 | 0 | 1110427.3716 | 183355 | 1110427.3716 | 183355 | 2026-07-09 00:01:46 +0530 | Savita Parab | Execution: floor covering done electrical wiring done false ceiling and painting cx scope site is ready to deliver the modular material as confirmation taken from client | 2026-07-05 11:14:38 +0530 | Reshma Melanta | 100% Payment: | 2026-07-03 18:20:31 +0530 | Reshma Melanta | 100% Payment: | 2026-04-19 | 2026-04-18 16:59 | 2026-05-04 | 2026-05-03 18:10
19277 | Turnkey | 2026-01-01 | Yasin Dunge | Lodha casa suprimo | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 3206810 | 9999 | 3206810 | 0 | 0 | 92 | 0 | 310682 | 320681 | 1352652 | 1212795.6 |  |  | 2026-03-19 | 2026-04-04 11:28 | 2026-04-02 | 2026-04-05 18:11 | 2026-04-08 | 2026-04-15 03:16 | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-04-23 |  | 2026-05-01 |  | 2026-05-02 |  |  |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 | [6 empty] | 2026-05-30 |  | 2026-06-08 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-11 |  |  |  | 2026-07-03 |  | 2026-07-05 |  | 2026-07-06 | [5 empty] | 2026-05-10 |  | 2026-04-18 |  | Unknown | 2026-03-19 | 2026-04-03 17:12 | 2717635 | 489174 | 0 | 0 | 0 | 0 | 2717635 | 489174 | 2026-04-02 18:31:47 +0530 | Rishika Malviya | Some Image was uploaded | [6 empty] | 2026-04-23 |  | 2026-04-30
19279 | Turnkey | 2026-01-01 | Moushmi kamat | antariksh ace | MUM - GOR | Yes | Batskhem Marpna | Manzoor Shaikh | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Suraj Jaiswar | Rizwan Mistry | Murali S | Sanskruti Yadav | Aakash Gaikwad | Active | Production | 100% Payment | 755169 | 755169 | 1600238 | 0 | 755169 | 6 | 12 | 0 | 0 | 0 | 0 |  |  | 2026-04-02 | 2026-04-03 11:58 | 2026-04-11 | 2026-04-11 11:42 | 2026-04-14 | 2026-04-11 12:10 | 2026-05-02 | 2026-05-02 12:57 | 2026-05-11 | 2026-05-10 13:02 | 2026-05-21 | 2026-05-21 19:51 | 2026-04-11 | 2026-04-11 18:17 | 2026-04-12 | 2026-04-14 12:33 | 2026-04-14 | 2026-04-14 13:27 | 2026-04-18 | 2026-04-18 16:54 |  |  |  |  | 2026-05-02 | 2026-05-07 19:29 | 2026-05-14 | 2026-05-13 20:33 | 2026-05-14 | 2026-05-13 20:33 |  |  | 2026-05-25 | 2026-06-10 18:31 | 2026-06-13 | 2026-06-14 15:24 | 2026-06-15 | 2026-06-17 12:07 | 2026-05-31 | 2026-05-30 18:38 |  |  |  |  | 2026-06-21 15:48 | 2026-06-26 | 2026-06-25 20:55 | 2026-07-01 | 2026-06-29 12:37 | 2026-06-30 |  | 2026-07-09 |  | 2026-07-09 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-06-14 | 2026-06-21 15:47 | 2026-04-19 | 2026-05-02 12:50 | Site is RTMI | 2026-04-02 | 2026-04-03 11:56 | 1356134 | 244104 | 0 | 0 | 820056.9119 | 141508 | 820056.9119 | 141508 | 2026-07-13 10:55:04 +0530 | Suraj Jaiswar | Execution: Work will start on 13th July. Cx.. work is going on at site. | 2026-07-09 17:23:23 +0530 | Manzoor Shaikh |  | 2026-06-27 18:39:42 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-03 | 2026-05-02 14:18 | 2026-05-11 | 2026-05-10 13:06
19282 | Turnkey | 2026-01-01 | Surabhi srivastava | Godrej Exquisite | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 1199503 | 9999 | 0 | 0 | 0 | 26 | 0 | 109951 | 119950 | 479801 | 479801.2 |  |  | 2026-04-02 | 2026-06-19 12:00 | 2026-06-14 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-02 | 2026-04-05 12:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1016528 | 182975 | 2026-04-05 12:31:33 +0530 | Vandana Preet | Silver coin given to cx Driver on 3/4/26. | [6 empty] | 2026-04-26 |  | 2026-05-03
19283 | Sub Project |  | Nirav P Punjani | kanakia silicon valley | MUM - GOR |  | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Active | Installation | Execution | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-03 | 2026-04-03 12:41 | 2026-04-04 | 2026-04-03 12:41 | 2026-04-03 | 2026-04-03 12:41 | 2026-04-04 | 2026-04-03 12:43 | 2026-04-04 | 2026-04-03 12:44 | 2026-04-04 | 2026-04-03 12:46 | 2026-04-03 | 2026-04-03 12:41 | 2026-04-04 | 2026-04-03 12:42 | 2026-04-03 | 2026-04-03 12:42 | 2026-04-04 | 2026-04-03 12:42 |  |  |  |  | 2026-04-04 | 2026-04-03 12:43 | 2026-04-04 | 2026-04-03 12:45 | 2026-04-04 | 2026-04-03 12:45 |  |  | 2026-04-04 | 2026-04-03 12:47 | 2026-04-04 | 2026-04-12 15:10 | 2026-04-14 | 2026-04-14 18:01 | 2026-04-15 | 2026-04-14 18:01 |  |  |  |  | 2026-04-21 14:09 | 2026-04-23 | 2026-04-22 19:26 | 2026-04-24 | 2026-04-22 20:13 | 2026-04-23 | 2026-05-13 11:21 | 2026-04-22 | 2026-07-02 07:24 | 2026-07-02 | 2026-07-02 07:26 | 2026-07-04 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-04-12 | 2026-04-13 14:49 | 2026-04-05 | 2026-04-03 12:42 | Unknown | 2026-04-03 | 2026-04-03 12:41 | 0 | 0 | 0 | 0 | 30932 | 0 | 30932 | 0 | 2026-06-01 16:40:37 +0530 | Savita Parab | Execution: SITE IS READY TO DISPATCH THE MATERIAL | 2026-05-11 23:10:50 +0530 | Savita Parab | Execution: SITE IS READY TO DISPATCH THE MATERIAL | 2026-05-03 20:43:02 +0530 | Savita Parab | Execution: SITE IS READY TO DISPATCH THE MATERIAL | 2026-04-09 | 2026-04-03 12:42 | 2026-04-04 | 2026-04-03 12:44
19284 | Turnkey | 2026-01-01 | Sudhir Kumar Sah | NAHAR AMRUT SHAKTI | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  |  | suraj kumar | Akshat Shrivastava | Murali S | Anant Giri | Prasad Bhivaji Hande | Active | Installation | Execution | 1165592 | 1165593 | 1359742 | 1520524 | 1165592 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-03 | 2026-04-03 16:46 | 2026-04-15 | 2026-04-15 11:23 | 2026-04-22 | 2026-04-22 10:40 | 2026-05-07 | 2026-05-06 16:59 | 2026-05-15 | 2026-05-14 18:46 | 2026-05-16 | 2026-05-16 19:42 | 2026-04-22 | 2026-04-23 19:36 | 2026-04-23 | 2026-04-23 19:37 | 2026-04-23 | 2026-04-25 09:23 | 2026-04-25 | 2026-04-25 13:04 |  |  |  |  | 2026-05-04 | 2026-05-04 13:13 | 2026-05-15 | 2026-05-14 19:34 | 2026-05-15 | 2026-05-16 10:04 |  |  | 2026-05-17 | 2026-05-20 13:19 | 2026-05-22 | 2026-05-22 11:33 | 2026-05-23 | 2026-05-22 19:00 | 2026-05-23 | 2026-05-29 18:24 |  |  |  |  | 2026-05-31 13:36 | 2026-06-06 | 2026-06-05 21:29 | 2026-06-24 | 2026-06-22 18:50 | 2026-06-13 | 2026-06-06 13:15 | 2026-06-22 | 2026-06-24 19:37 | 2026-06-24 | 2026-06-28 00:26 | 2026-06-30 | 2026-07-11 12:45 |  |  | 2026-06-28 |  | 2026-06-30 |  | 2026-07-25 | [5 empty] | 2026-05-22 | 2026-05-31 13:35 | 2026-05-02 | 2026-04-30 20:06 | Site is RTMI | 2026-04-03 | 2026-04-03 16:46 | 1152324 | 207418 | 1589510.6574 | 262452 | 1305463.079 | 215556 | 1305463.079 | 215556 | 2026-07-13 14:40:37 +0530 | suraj kumar | Our Scope: Services - FC & DC Modular VRM Mirror POP grooving Wallpaper Site report: Modular material has been delivered to the site. ( Vendor delayed align) Modular installation work is in progress, Snag Found Panel missing- we are arranging from another site. Mirror panel will be installed today, Measurement, plan for day after tomorrow. POP Grooving plan for day after tomorrow. Membrane material has been delivered to the site. | 2026-07-08 12:05:44 +0530 | suraj kumar | Our Scope: Services - FC & DC Modular VRM Mirror POP grooving Wallpaper Site report: Modular material has been delivered to the site. Modular installation work is in progress. ( Vendor delayed align) | 2026-06-24 01:39:42 +0530 | suraj kumar | Site report: Site is ready for modular material delivery. | 2026-05-07 | 2026-05-14 16:08 | 2026-05-15 | 2026-05-14 18:46
19286 | Turnkey | 2026-01-01 | Melvin Harry Harry | INDEPENDENT HOUSE | BNG - HRBR | Yes | Vishal Bandi | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kushal S |  | Hold | Preproduction | DEM2 | 957457 | 191999 | 1189275 | 0 | 0 | 50 | 8 | 0 | 0 | 389440 | 376018 |  |  | 2026-04-03 | 2026-04-03 14:48 | 2026-04-03 | 2026-04-18 18:39 | 2026-04-21 | 2026-04-21 12:27 | 2026-05-05 | 2026-05-05 19:59 | 2026-08-02 |  | 2026-08-09 |  | 2026-04-21 | 2026-04-21 18:27 | 2026-04-22 | 2026-04-23 12:30 | 2026-04-23 | 2026-04-23 15:36 | 2026-04-24 | 2026-04-24 19:40 |  |  |  |  | 2026-05-05 | 2026-05-18 17:58 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-04-25 | 2026-05-05 19:53 | Site is RTMI | 2026-04-03 | 2026-04-03 13:44 | 1007860 | 181414 | 0 | 0 | 0 | 0 | 982558.153 | 169551 | 2026-05-07 18:12:21 +0530 | Rajeshwari S | First design meeting done on 5th May 10% payment done. Material selection meeting will be schedule and project will be on hold as site is not ready. Non RTMI Project | 2026-05-05 22:02:15 +0530 | Vishal Bandi | Some Image was uploaded | 2026-04-28 18:06:14 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-06 | 2026-05-05 21:56 | 2026-08-03 |  | Under Construction | 2026-08-31
19289 | Turnkey | 2026-01-01 | Mrs. Yamini Tara | SNN RAJ SERENITY | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 1462701 | 9999 | 1462701 | 0 | 0 | 103 | 0 | 136271 | 146270 | 596674 | 573486.4 |  |  | 2026-04-03 | 2026-04-03 16:41 | 2026-04-03 | 2026-04-05 15:31 | 2026-04-05 |  | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-04-05 |  | 2026-04-06 |  | 2026-04-06 |  | 2026-04-07 | [5 empty] | 2026-04-13 |  | 2026-04-21 |  | 2026-04-22 |  |  |  | 2026-04-29 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 | [6 empty] | 2026-05-20 |  | 2026-05-29 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-06-01 |  |  |  | 2026-06-23 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-04-30 |  | 2026-04-08 |  | Unknown | 2026-04-03 | 2026-04-03 16:40 | 1239577 | 223124 | 0 | 0 | 0 | 0 | 1239577 | 223124 | 2026-04-04 17:02:04 +0530 | Ankita Agarwal | DCM: MINUTES OF MEETING (MOM)Client Name: Mrs. Yamini Tara Project: Residential Interior 2 BHK Location: SNN Raj Serenity, Begur Road Entrance Facing: North Family Members: 4 (Including infant Baby Akshvi, 6 months) Design Theme: Tropical Budget: 10 Lakhs (Stretch: 1213 Lakhs) Decision Timeline: Within 1 Week Date of Meeting: __________ Scope of Work Discussion1. Entrance / Living AreaShoe storage unit with seating (Capacity: 3540 pairs)TV unit with only base cabinet (No overhead storage/display)Sofa back wall design (Tropical theme feature wall)2. Dining AreaFeature wall design requiredPooja unit with seating arrangementProvision for 4 wall frames1 platform space (for decor/pooja utility)Window seating next to pooja unit4-seater dining setup3. KitchenGas pipeline provision (Cylinder in utility area)Tambour unit requiredBuilder-provided countertop to be retainedModular kitchen execution via BonitoOverhead cabinets with glass shutters1 tall glass cabinet at kitchen entrance4. Utility AreaSink unit requiredFunctional layout for washing/cleaning5. Master BedroomWardrobe with Aristo sliding systemWashroom vanity unit6. Bedroom 2 (Kids / Guest Bedroom)Sliding wardrobe opposite bedBed placement on south window wall (6 x 6)Study unit at entranceLoft storage above entranceCouch at entrance7. Ceiling & LightingBasic false ceiling across all roomsBalanced lighting plan (ambient + task + accent lighting)Design ConsiderationsTropical theme with warm, earthy tonesMinimal and functional design approachBaby-safe design (rounded edges, safe materials)Space optimization with clean aesthetics | [6 empty] | 2026-04-13 |  | 2026-04-20
19290 | Turnkey | 2026-01-01 | Ketaki banubakode Rajurkar | Godrej emerald | MUM - Thane | Yes | [8 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 1699852 | 9999 | 0 | 0 | 0 | 103 | 0 | 159986 | 169985 | 773178 | 586703.6 |  |  | 2026-04-01 | 2026-04-03 18:31 | 2026-04-05 | 2026-04-05 11:11 | 2026-04-12 |  | 2026-04-15 |  | 2026-04-22 |  | 2026-04-29 |  | 2026-04-08 |  | 2026-04-09 |  | 2026-04-09 |  | 2026-04-10 | [5 empty] | 2026-04-16 |  | 2026-04-24 |  | 2026-04-25 |  |  |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-05 | [6 empty] | 2026-05-23 |  | 2026-06-01 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-04 |  |  |  | 2026-06-26 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-05-03 |  | 2026-04-11 |  | Unknown | 2026-04-01 | 2026-04-03 18:28 | 0 | 0 | 0 | 0 | 0 | 0 | 1442839 | 257012 | 2026-04-05 09:18:51 +0530 | Rutuja Kotwal | DCM: Mrs. KetakiÂ BanubakodeÂ Â 2BHK.Â Â 805 Sq. Ft.Â Move inÂ 2 people. - Husband and wife.Â Â ProfessionÂ Account managerÂ inÂ amazon.Â Â Mr. Pratik Civil Engineer.Â Â Design as per Basic Vastu.Â Â Direction Exiting East.Â Â Possession MidÂ april.Â Â Living Room - Shoe rack- 20 25 pairs,Â safety door,Â 4 seaterÂ dining Table,Â mandir, Sofa, center table,Â Changing of balcony tiles, vertical unit forÂ coffee.Â Â KitchenÂ Base Units, WallÂ unitsÂ andÂ lofts.Â Â Kitchen Renovation.Â Â Bedroom 1- Bed, Wardrobe w/o lofts, Study unit, VerticalÂ UnitÂ for Athlete storage.Â Â Master Bedroom-Â kingÂ Bed, Wardrobe w/o lofts,Â dressingÂ unit,Â Reading Corner- vertical unit.Â Â False ceiling, wiring, painting.Â Vanity Cabinets in all bathrooms.Â Â Budget 12 lakhs.Â Â Budget SuggestionÂ 17Â lakhs.Â Â With civil- 20 lakhs.Â Â CDP TBD.Â | [6 empty] | 2026-04-16 |  | 2026-04-23
19291 | Turnkey | 2026-01-01 | Rajesh parab | luma | MUM - GOR | No Estimate | [8 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-03-29 | 2026-06-09 12:49 | 2026-03-30 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-05-01 |  | 2026-05-08 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-18 |  | 2026-04-19 | [5 empty] | 2026-04-25 |  | 2026-05-03 |  | 2026-05-04 |  |  |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 | [6 empty] | 2026-06-01 |  | 2026-06-10 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-13 |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-08 | [5 empty] | 2026-05-12 |  | 2026-04-20 |  | Unknown | 2026-03-29 | 2026-04-21 14:22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-15 13:52:29 +0530 | Moni Sahani | Some Image was uploaded | [6 empty] | 2026-04-25 |  | 2026-05-02
19292 | Turnkey | 2026-01-01 | Brijesh ozha | Prescon Midtown Bay | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 2597351 | 9999 | 2597351 | 0 | 0 | 87 | 0 | 249736 | 259735 | 1059850 | 1018031.2 |  |  | 2026-03-29 | 2026-04-10 13:58 | 2026-04-05 | 2026-04-14 11:52 | 2026-04-21 | 2026-04-21 11:36 | 2026-04-28 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-04-29 |  | 2026-05-07 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-24 |  | Unknown | 2026-03-29 | 2026-04-07 12:13 | 2201145 | 396206 | 0 | 0 | 0 | 0 | 2201145 | 396206 | 2026-04-15 13:52:09 +0530 | Moni Sahani | Some Image was uploaded | 2026-04-05 20:12:53 +0530 | Rishika Malviya | Some Image was uploaded | 2026-04-05 20:12:26 +0530 | Rishika Malviya | Some Image was uploaded | 2026-04-29 |  | 2026-05-06
19296 | Turnkey | 2026-01-01 | MANOJ KUMAR CHAURASIYA | Tharwani Vedant Palacia | MUM - Thane | No Estimate | [8 empty] | Bhagyashree Salunkhe |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 102 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-03 | 2026-04-04 15:18 | 2026-04-03 |  | 2026-04-07 |  | 2026-04-13 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-04-06 |  | 2026-04-07 |  | 2026-04-07 |  | 2026-04-08 | [5 empty] | 2026-04-14 |  | 2026-04-22 |  | 2026-04-23 |  |  |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 | [6 empty] | 2026-05-21 |  | 2026-05-30 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-02 |  |  |  | 2026-06-24 |  | 2026-06-26 |  | 2026-06-27 | [5 empty] | 2026-05-01 |  | 2026-04-09 |  | Unknown | 2026-04-03 | 2026-04-04 13:21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-04 15:16:42 +0530 | Bhagyashree Salunkhe | Some Image was uploaded | [6 empty] | 2026-04-14 |  | 2026-04-21
19297 | Turnkey | 2026-01-01 | Dhanush | Pelican Square | BNG - HSR | Yes | Preethi Shetty | Akshay Ds | Priyanka Mathur | [5 empty] | Pulivarthi Nirosha |  | Hold | Preproduction | DEM2 | 2117657 | 423531 | 2809219 | 0 | 0 | 10 | 41 | 0 | 0 | 947717 | 746409.2 |  |  | 2026-04-03 | 2026-04-03 20:19 | 2026-04-24 | 2026-04-24 18:20 | 2026-05-02 | 2026-05-02 14:15 | 2026-05-26 | 2026-05-25 13:22 | 2026-08-01 |  | 2026-08-08 |  | 2026-05-02 | 2026-05-08 10:39 | 2026-05-03 | 2026-05-08 11:39 | 2026-05-08 | 2026-05-09 11:04 | 2026-05-16 | 2026-05-16 18:30 |  |  |  |  | 2026-05-22 | 2026-05-24 16:47 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-05-17 | 2026-05-25 12:58 | Site is RTMI | 2026-04-03 | 2026-04-03 20:16 | 2380694 | 428524 | 0 | 0 | 0 | 0 | 2418397.0226 | 399303 | 2026-06-04 14:05:10 +0530 | Akshay Ds | Some Image was uploaded | 2026-06-04 12:01:05 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-06-04 11:06:09 +0530 | Preethi Shetty | Client Possession is delayed, once the site possession is update will align for initial measurements and further process | 2026-05-26 | 2026-05-25 13:27 | 2026-08-02 |  | Under Construction | 2026-07-08
19298 | Turnkey | 2026-01-01 | Prasanna Maldikar | Aliance Abhimanue , Malad West | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Manasi Patil | Siddhesh Gujrathi | Active | Preproduction | Hoto | 1382064 | 276413 | 1755806 | 1382064 | 0 | 1 | 0 | 0 | 0 | 586978 | 518673.2 |  |  | 2026-04-03 | 2026-04-11 16:17 | 2026-04-05 | 2026-04-11 17:01 | 2026-04-14 | 2026-04-23 17:21 | 2026-05-03 | 2026-05-03 18:21 | 2026-07-12 | 2026-07-11 18:47 | 2026-07-19 | 2026-07-11 19:13 | 2026-04-14 | 2026-04-14 17:32 | 2026-04-15 | 2026-04-15 15:14 | 2026-04-15 | 2026-04-16 12:07 | 2026-04-23 | 2026-04-23 19:22 |  |  |  |  | 2026-05-03 | 2026-05-12 19:05 | 2026-06-18 | 2026-06-18 00:39 | 2026-06-19 | 2026-06-18 01:08 |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-04-24 | 2026-05-03 17:28 | Site is RTMI | 2026-04-03 | 2026-04-11 16:16 | 1487971 | 267834 | 1458255.9542 | 251628 | 0 | 0 | 1458255.9542 | 251628 | 2026-05-12 11:38:08 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-23 19:20:26 +0530 | Reshma Melanta | NOT ANSWERING THE CALL ADDED MYSELF | 2026-04-21 16:51:36 +0530 | Reshma Melanta | TRIED CALLING THE CLEINT DID NOT ANSWER ADDED MYSELF TO THE GROUP | 2026-05-04 | 2026-05-03 18:27 | 2026-07-12 | 2026-07-11 18:49
19301 | Turnkey | 2026-01-01 | Tapan Bhowmik Tapan Bhowmik | Briagde gateway | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik |  |  | Nikhil Mogeraya | Saddam Hussain Z M |  | Ramesh Nayak | Raghavendra Gowda | Active | Design | DEM3 | 867205 | 140122 | 899999 | 0 | 0 | 8 | 0 | 0 | 0 | 402089 | 324994 |  |  | 2026-04-04 | 2026-04-04 16:58 | 2026-04-09 | 2026-04-11 18:41 | 2026-04-11 | 2026-04-11 19:15 | 2026-05-31 | 2026-05-31 19:06 | 2026-07-04 |  | 2026-07-11 |  | 2026-04-11 | 2026-04-13 19:24 | 2026-04-12 | 2026-04-14 11:28 | 2026-04-14 | 2026-04-15 14:05 | 2026-04-16 | 2026-04-16 14:38 |  |  |  |  | 2026-05-31 | 2026-05-31 19:15 | 2026-07-18 | 2026-07-07 08:50 | 2026-07-08 | 2026-07-07 08:50 |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-10 | 2026-05-31 17:09 | Site is RTMI | 2026-04-04 | 2026-04-04 16:01 | 762711 | 137288 | 0 | 0 | 0 | 0 | 916256.6291 | 151353 | 2026-06-07 10:57:00 +0530 | Prathyusha Elangovan | Mr.Tapan(Material Selection) Foyer- Frosty white -1113-PGL Butternut Brown-1508 SUD CROCKERY UNIT Frosty white-1113-PGL GREY TINTED GLASS ROSE GOLD FRAME Folding dining-white TV UNIT Butternut Brown-1508 SUDÂ top panel/side panel/skirting/shelf Frosty White for the bottom unit and open unit Kitchen Beige-1140 PGL-Base units Frosty white -1508 SUD -WALL AND LOFT STUDY UNIT Study table-Frosty white-1508 SUD Wall unit /loft/pooja base unit-frosty white 113SNT POOJA UNIT AND GLASS UNIT INTERNAL-1055 SLT Handle less push to open for pooja base units and loft Master bedroom Carolina Rovere-2289 SD Tidal Sand-1033 SDÂ Soldier Green-1037 SM | 2026-05-24 13:11:33 +0530 | Prathyusha Elangovan | Tapan (24/5/26) ENTRANCE PARTITION-REDUCE IT TO 3',EXISTING SHOE RACK IN THE BOTTOM HAS TO BE COMINED WITH THE PARTITION. DINING AREA TOP PART TO BE HIGHLIGHTED KITCHEN CHIMNEY-BOTH THE SIDES GLASS SHUTTERS GRANITE WASHING MACHINE HT 90CM ,WIDTH-60CM TV UNIT WALL DESIGN,BASE TO BE THE SAME SOFA BACK WALL TO BE HIGHLIGHTED STUDY UNIT DESIGNÂ TO BE SUGGESTED POOJA UNIT TO BE THE SAME EXISTING SPRINKLER TWILL BE COVERED WITH PERIPHERAL FALSE CEILING VANITY WALL UNIT WITH MIRROR | 2026-04-15 14:05:33 +0530 | Bency Chacko | Possession - RTMI The customer will pay in 10 days after closing the LFM by 25th April 2026 No on-site work is planned No civil work is planned B2C - Self-funded Clear with Quote, offers and timelines tkbhowmik@gmail.com 919830689595 | 2026-06-01 | 2026-05-31 19:10 | 2026-07-05 |  | RTMI
19302 | Turnkey | 2026-01-01 | Sandip mathuria | 56west | MUM - GOR | Yes | Zoya Ansari | Manzoor Shaikh | Kashmira Nerurkar |  | Anamika Ghate | Uday Yadruk | Rizwan Mistry |  | Manasi Patil | Prasad Bhivaji Hande | Active | Preproduction | 2D | 1576026 | 299931 | 2128373 | 1576026 | 0 | 21 | 0 | 0 | 0 | 711053 | 565042.4 |  |  | 2026-04-04 | 2026-04-17 16:05 | 2026-04-21 | 2026-04-21 11:11 | 2026-04-24 | 2026-04-24 12:23 | 2026-05-13 | 2026-05-13 18:46 | 2026-05-21 | 2026-05-20 09:07 | 2026-06-13 | 2026-06-13 21:02 | 2026-04-24 | 2026-04-25 11:33 | 2026-04-25 | 2026-04-27 13:29 | 2026-04-27 | 2026-04-29 16:02 | 2026-05-03 | 2026-05-03 19:08 |  |  |  |  | 2026-05-14 | 2026-05-11 12:22 | 2026-05-26 | 2026-05-27 07:54 | 2026-05-28 | 2026-05-27 09:29 |  |  | 2026-06-23 | 2026-06-24 14:52 | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-05-06 | 2026-05-13 18:40 | Site is RTMI | 2026-04-04 | 2026-04-17 16:05 | 1803706 | 324667 | 1751701.289 | 302266 | 0 | 0 | 1751701.289 | 302266 | 2026-06-26 18:49:44 +0530 | Zoya Ansari | Hi sir as discussed in todays meeting we are not aligned on the proposed timelines based on the final design , we shall get back to you by tomorrow regarding the best possible solution. We would request you to think over the conversation we had , if there can be any arrangements to complete the project with us. | 2026-06-21 16:38:23 +0530 | Anamika Ghate | Some Image was uploaded | 2026-06-21 16:38:01 +0530 | Anamika Ghate | Some Image was uploaded | 2026-05-14 | 2026-05-13 18:59 | 2026-05-21 | 2026-05-20 09:08
19303 | Turnkey | 2026-01-01 | Rupesh | Soulace Villas by Modern Spaaces | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Preproduction | DEM2 | 2144947 | 459706 | 3427655 | 0 | 0 | 47 | 0 | 0 | 0 | 843495 | 841746 |  |  | 2026-04-04 | 2026-04-10 13:56 | 2026-04-10 | 2026-04-10 14:01 | 2026-04-13 | 2026-04-13 00:01 | 2026-05-29 | 2026-05-29 16:16 | 2026-07-15 |  | 2026-08-03 |  | 2026-04-13 | 2026-04-16 12:24 | 2026-04-14 | 2026-04-16 13:01 | 2026-04-16 | 2026-04-17 12:02 | 2026-04-18 | 2026-04-18 17:03 |  |  |  |  | 2026-05-11 | 2026-05-29 12:48 | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-04-19 | 2026-04-26 19:12 | Site is RTMI | 2026-04-04 | 2026-04-04 18:50 | 2904793 | 522862 | 0 | 0 | 0 | 0 | 2233150.3606 | 368741 | 2026-05-24 17:36:48 +0530 | Abhinandan K S | Customer will be visiting our office on 28th May 2026 and make the next 10% payment as per the revised quote. | 2026-05-19 13:36:49 +0530 | Janush Bojamma C T | RUPESH- 17th May 1) used clothes - internal partition inside all wardrobeÂ 2) ventilation grill 3) PBR- no mirror as of nowÂ 4) Lift area- Silver mirror - plainÂ 5) Tinted glass for - tall unit in tv unitÂ 6) MBR- dresser more storageÂ glass shutterÂ 7) last section in wardrobe - slippers and sandals 8) Kids - wardrobe fully - 4 shutters 9) side wardrobe- glass shutter- fluted 10)loft above all area wardrobe - Loft above kidsÂ 11) Dresser - Behind storage with bottomÂ 12) all washrooms back lit mirrorÂ 13) magnifier mirror - all washrooms 14) study in 2nd floor - gypsum closure with wallpaper. 15) shoe rack- bottom open for usable slipper. 16) sensor - lights for the wardrobeÂ 17) drawers and pull outs. | 2026-04-26 17:43:52 +0530 | Janush Bojamma C T | Rupesh Cx Tv unit - Tall unit - Glass shutter on left sideÂ - Reference image to be shared - Back panel design - Plan some premium design ideas Sofa back wall-Â - Sofa back wall golden beading Cx liked to check on similar design Po0ja unitÂ - Not required from Bonito Crockery unitÂ - Not requiredÂ KitchenÂ - 2ft fridgeÂ - Tall unit and Roller shutterÂ - Sink on the left - Next to sink - dish washerÂ - Dish washer - checkÂ - Tall unit to left of fridgeÂ - Plumbing point to be checkedÂ - Possibility of sink Infront of windowÂ - ht check kitchen counterÂ -Loft area- Glass shutter as per reference imageÂ - 3ft hob from Bonito - Loft L shape above the chimney area- 1 option - Remove L shape - Storage near HobÂ - Wall units- Lift ups add Dining wash basinÂ - LED mirror with bottom storageÂ - Concealed door option in the GBR bedroom - Door possibility in offeringÂ Guest bedroomÂ - WardrobeÂ with centre bedÂ - Electrical points shifts - SuggestionÂ - Right to entry usable clothes storage and mirror - Opposite wall- Wallpaper and louvers/ punning - Common washroom- vanity suggestionÂ UtilityÂ Washing machine - Built inÂ Utility storage - above / add tall unit - Check optionÂ Stair case- doors for carpentry Kids- 10 yrs Girl L shape table with adding wardrobe -Â Study storage with wardrobe left wall Display unit - glass shutter with wardrobeÂ 3 door wardrobeÂ -Â Walkin - wardrobe - Partition to plan gypsum and concealed doorÂ Walkin wardrobe- storage close with loft Shift mirror to right side wall Dresser- Look wise storage - to option decision need to be done based on design Mirror - Design and light optionsÂ Kids - Bedroom - back wall ref image Master bedroomÂ Storage opp to bed - as per vastuÂ need for display no to look heavy MBR- back wall design - With gypsum and wallpaperÂ study area- not lookingÂ Concealed or door closureÂ Second floorÂ Concealed door - entry Half wall availableÂ Closed door with sound proof needed prathibhapallavi.he@gmail.com Shoe rack - Seater space - in car parkingÂ until wall length 2 seater - cushionÂ Vanities- possibilities for all washrooms Â near lift mirrorÂ Lift - silverÂ Lift - wallpaper - requirementÂ Handover - May end keys handoverÂ | 2026-05-30 | 2026-05-29 16:23 | 2026-07-16 |  | Under Construction | 2026-05-09
19304 | Turnkey | 2026-01-01 | Alok Roy | Arham arya | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 1811969 | 9999 | 0 | 0 | 0 | 92 | 0 | 171198 | 181197 | 730535 | 719040.4 |  |  | 2026-04-04 | 2026-04-14 13:12 | 2026-06-07 | 2026-06-07 15:15 | 2026-04-18 |  | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-04-04 | 2026-04-14 13:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1535567 | 276402 | 2026-04-17 20:23:27 +0530 | Pratima Kajwe | DCM: Customer and Project Profile1. Name of the customer Alok Roy, Shilpa, parent's, Son(28) and daughter (22) 2. Profession Work from home. 3. Project Name/Tower Name/Flat Number 2nd floor, 14 storey building 1050 sq.ft area 4. Typology (1BHK, 2BHK, 3BHK, etc) 3BHK 5. Site Access Date 2026-07-31 6. Possession Date 2026-06-30 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 1000000 Customer Preferences8. Who will be living in the house? Couple, Joint Family, Elderly Members 9. What activities do you usually prefer at your home ? Working From Home, Family Bonding 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any Basic 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Bookshelf, mandir option 1, 6 seater dining space, 96 inch sofa, Upload reference images 14. Any absolute no-go styles colours or materials No dark shades 15. Do you have any existing furniture that must be accommodated? Sofa seating 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Safety Door, Seating, Shoe rack 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Multipurpose, Entertaining guests 2. Must-have furniture or features? Sofa, Statement Wall/ Feature, Display unit , Puja unit, Bookshelves, Coffee table, Speakers, TV unit 3. Choose your decor inspirations Artwork 4. False ceiling required No Dining & Kitchen1. Any special furniture? Partitions 2. Must-have appliances? Washing machine, Chimney, Fridge, Microwave 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Study Table, TV unit, Dresser, Bookshelf 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Dresser , Bookshelf , Study table 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Parents 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units TV Unit, Dresser, Bookshelf, Study Table 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? NA Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date The day it is ready will move in. 6. Additional Requirements (Mention any requirements from customer not covered in the form) Accommodate Godrej Cupboard in master bedroom, hidden drawer in master bedroom and parent's bedroom. Space to accommodate yoga mat in master bedroom. Space for planters . 18th April Saturday CDP meeting. 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 1500000 | 2026-04-14 13:12:59 +0530 | Mrunali Mitkari | Some Image was uploaded |  |  |  | 2026-06-18 |  | 2026-06-25
19305 | Turnkey | 2026-01-01 | Sunil Jalan Jalan | Tanna Hights | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 5509795 | 9999 | 0 | 0 | 0 | 84 | 0 | 540981 | 550980 | 2311940 | 2095896.4 |  |  | 2026-04-04 | 2026-04-21 17:53 | 2026-04-04 | 2026-04-21 19:33 | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-04 | 2026-04-21 17:53 | 0 | 0 | 0 | 0 | 0 | 0 | 4669318 | 840477 | 2026-04-21 16:20:27 +0530 | Unknown | About the Customer **Introduction and Property Details** Agent Jamshed from Bonito Designs contacted the customer regarding interior design for their 3BHK property in Dadar, Mumbai, which is undergoing a complete renovation after recent possession. The customer sought a ballpark cost estimate for planning purposes. **Bonito Designs' Services and Consultation Fee** Jamshed explained Bonito Designs offers end-to-end interior solutions, including design, production, and execution, managed by a dedicated project manager. He mentioned an initial design consultation fee of â‚¹10,000 for customization. **Experience Center Visit and Next Steps** To provide a better understanding, Jamshed invited the customer to visit the Andheri East experience center. The customer agreed to visit with his wife after lunch, around 3:00 PM. Jamshed confirmed the appointment, promised to send the address via WhatsApp, and reminded the customer about the post-call feedback request. **Current Customer Stage and Immediate Next Steps** The customer's immediate next step is to visit the Bonito Designs experience center in Andheri East with his wife around 3:00 PM today. The agent will send a WhatsApp invitation with the address. **Customer Needs and Objectives** The customer's primary need is to get a ballpark cost estimate for interior design services for their 3BHK property undergoing renovation. Their main objective is to plan their renovation budget effectively. **Customer Engagement History** The customer's engagement history shows they have recently taken possession of a 3BHK property and are looking for comprehensive interior design solutions. They have agreed to visit the experience center after receiving initial information about Bonito Designs' services. **Recommended Follow-up Actions** Recommended follow-up actions include sending the confirmed WhatsApp invitation with the experience center address and agent Jamshed's profile. It is also important to ensure the customer provides feedback post-call as requested. | 2026-04-21 16:02:37 +0530 | Yash Jain | DCM: Sunil Jalan and fam 1400sq ft + 100 sqftÂ kitchen same as green membrane finish appliance - microwave oven, fridge double door fridge , U shaped kitchen, vastu, top northÂ tilted on left side littleÂ Living roomÂ -Â 6/8 seater dining area, square if poss, - 8 ppl sofa seating 3+3+2 - Tv unit big as possibleÂ dining table - 4feet all sides, can break wall of washroom to include in dining tableÂ entrance lobby back passage to be used as utility area includes - dryer washer etc top side bedroom - master bedroom Cx Room - king size bed , wardrobes, 7 feet hght with loft addingintion , sides table , dresser ,Â top side bedroom - master bedroom Cx Room - king size bed , wardrobes, 7 feet hght with loft addingintion , sides table , dresser.Â Above bedroom - master bedroom Cx Room - king size bed , wardrobes, 7 feet hght with loft addingintion , sides table , dresser.Â kitchen full modular, full house tiles breaking , paint, fc and electricals. shoe rack outside in lobby. basic room hght - 10 feet.Â and overall living more than 20 feet. pooja room/unit as per vastu , Design theme - combination of japandi for living and neo industrial , colours - beacon colour , off white, ivoryÂ Budget - 50L (including civil ) | 2026-04-15 18:22:08 +0530 | Manasi Patil | Some Image was uploaded | 2026-04-30 |  | 2026-05-07
19306 | Turnkey | 2026-01-01 | Prakash Ranjan | Shriram Whitfield | BNG - HSR | Yes | Chittipireddy Sriharish | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 962991 | 9999 | 0 | 0 | 0 | 102 | 0 | 86300 | 96299 | 385196 | 385196.4 |  |  | 2026-04-04 | 2026-04-04 18:22 | 2026-04-04 |  | 2026-04-09 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-04-07 |  | 2026-04-08 |  | 2026-04-08 |  | 2026-04-09 | [5 empty] | 2026-04-15 |  | 2026-04-23 |  | 2026-04-24 |  |  |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-04 | [6 empty] | 2026-05-22 |  | 2026-05-31 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-03 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-05-02 |  | 2026-04-10 |  | Unknown | 2026-04-04 | 2026-04-04 17:46 | 0 | 0 | 0 | 0 | 0 | 0 | 816094 | 146897 | 2026-04-04 19:06:20 +0530 | Chittipireddy Sriharish | DCM: Kitchen Granite Removal - need to be cross checked Wall ledges below the wall units Tall appliances unit 5 tandem drawers Utility Janitor unit Wall unit & loft Pipe outlet need to be covered - need to be cross checked Living room 3 feet - puja unit As per references Crockery unit - 3 feet Bedroom 1 Wardrobe - 6 feet Used clothes storage Study unit Master bedroom Wardrobe - L shaped Study with tall unit and wall ledges Vanity - 2 No Base and wall unit with mirror | [6 empty] | 2026-04-15 |  | 2026-04-22
19307 | Turnkey | 2026-01-01 | Sanjiv Arjunagi | L and T | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | suraj kumar | Aditya Vikram | Murali S | Anant Giri | Shailendra Mishra | Active | Production | 100% Payment | 1488682 | 916612 | 1811443 | 0 | 1488682 | 6 | 0 | 0 | 0 | 0 | 572070 |  |  | 2026-04-04 | 2026-04-04 20:21 | 2026-04-07 | 2026-04-07 19:36 | 2026-04-11 | 2026-04-11 20:17 | 2026-05-24 | 2026-05-24 11:57 | 2026-05-31 | 2026-05-30 11:01 | 2026-06-08 | 2026-06-08 11:36 | 2026-04-11 | 2026-04-14 19:00 | 2026-04-12 | 2026-04-14 19:01 | 2026-04-14 | 2026-04-16 10:35 | 2026-05-17 | 2026-05-17 14:25 |  |  |  |  | 2026-05-23 | 2026-05-23 15:46 | 2026-06-02 | 2026-06-04 21:06 | 2026-06-05 | 2026-06-04 21:07 |  |  | 2026-06-10 | 2026-06-17 20:26 | 2026-06-18 | 2026-06-18 17:00 | 2026-06-19 | 2026-06-18 18:23 | 2026-06-19 | 2026-06-22 19:09 |  |  |  |  | 2026-06-25 12:34 | 2026-07-01 | 2026-06-30 20:04 | 2026-07-11 | 2026-07-09 19:07 | 2026-07-10 |  | 2026-07-09 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-18 | 2026-06-23 23:54 | 2026-05-18 | 2026-05-23 16:26 | Site is RTMI | 2026-04-04 | 2026-04-04 20:21 | 1537922 | 273520 | 0 | 0 | 1677602.4663 | 269799 | 1677602.4663 | 269799 | 2026-07-08 11:40:21 +0530 | suraj kumar | Site report: - The floor covering work has been completed. - The False ceiling framing work has been completed. - Electrical work is in progress. | 2026-06-14 12:22:31 +0530 | Asavari Vare | Some Image was uploaded | 2026-06-10 16:48:45 +0530 | Asavari Vare | Some Image was uploaded | 2026-05-25 | 2026-05-24 11:58 | 2026-05-31 | 2026-05-30 11:07
19308 | Turnkey | 2026-01-01 | Lokesh | Prestige Finsbury Park | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Raghavendra S | Vishwa Hiremath | Active | Preproduction | CM | 1327360 | 232263 | 914532 | 0 | 0 | 1 | 0 | 0 | 0 | 564153 | 530944 |  |  | 2026-04-04 | 2026-04-12 11:25 | 2026-04-15 | 2026-04-15 19:53 | 2026-04-15 | 2026-04-15 20:06 | 2026-05-11 | 2026-05-10 11:29 | 2026-07-15 | 2026-07-14 15:32 | 2026-07-24 |  | 2026-04-15 | 2026-04-17 11:37 | 2026-04-16 | 2026-04-17 14:54 | 2026-04-17 | 2026-04-17 16:02 | 2026-04-18 | 2026-04-18 15:25 |  |  |  |  | 2026-05-10 | 2026-05-20 21:15 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-06-23 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-07-22 |  | 2026-05-06 | 2026-05-03 19:10 | Site is RTMI | 2026-04-04 | 2026-04-04 19:39 | 775027 | 139504 | 0 | 0 | 0 | 0 | 1343766.625 | 226885 | 2026-07-14 17:32:05 +0530 | Rajeshwari S | 10% paid.Â CM scheduled on 15th July PKO expected by 28th July followed by payment. | 2026-06-27 10:30:53 +0530 | Priyanka R | Some Image was uploaded | 2026-05-31 15:10:43 +0530 | Priyanka R | Minutes of meeting (31-05-2026) Living 1. TV unit- Base drawer height increased to 300mm 2. Pooja unit- add platform inside 3. Tv unit - add glass sutter for open unit in base cabinet 4. Tv base drawers changed to quadro channel Kitchen 1.Â Granite and tiles will be removedÂ 2. No changes in modular placement 3. Electrical needs to discuss on site 4. All the appliances details will be provided during cross measurments 5. Drawers in bedrooms will be finalized after Estimation since quadro channels needs to add in quote 6 BWP in base cabinet Bedrooms Post -lam quote for wardrobes | 2026-05-11 | 2026-05-10 11:31 | 2026-07-15 | 2026-07-14 15:40 | RTMI
19309 | Turnkey | 2026-01-01 | Gaurav Khatri | rejuve | MUM - GOR | Yes | Sonal Singh | Manzoor Shaikh | Kashmira Nerurkar |  |  | suraj kumar | Aditya Vikram |  | Nivesh Gupta | Siddhesh Gujrathi | Active | Design | DEM3 | 961012 | 192202.8 | 1130829 | 0 | 0 | 6 | 0 | 0 | 0 | 427598 | 341210.8 |  |  | 2026-04-04 | 2026-04-06 16:42 | 2026-04-05 | 2026-04-06 16:43 | 2026-04-12 | 2026-04-12 21:48 | 2026-05-10 | 2026-05-10 13:15 | 2026-06-15 |  | 2026-07-13 |  | 2026-04-12 | 2026-04-14 18:39 | 2026-04-13 | 2026-04-15 12:15 | 2026-04-15 | 2026-04-15 16:07 | 2026-04-21 | 2026-04-21 18:53 |  |  |  |  | 2026-05-10 | 2026-05-26 11:51 | 2026-07-08 | 2026-07-09 10:15 | 2026-07-10 | 2026-07-09 10:15 |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-04-22 | 2026-05-10 13:06 | Site is RTMI | 2026-04-04 | 2026-04-06 16:36 | 960428 | 170401 | 0 | 0 | 0 | 0 | 1047269.0387 | 168903 | 2026-07-07 15:29:49 +0530 | Manzoor Shaikh | Hello @~Gaurav K Sir, After the cross measurement, the PKO docket takes tentatively 18 working days. Once you receive and approve the PKO docket, please note that the project consists of two phases. As per the agreement, for project values upto Rs. lakhs, the timelines are as follows: 1. Production phase is of 19 working days. 2. The execution phase is of 36 +10 working days. Thank you. | 2026-07-02 16:42:28 +0530 | Manzoor Shaikh | The client has received the possession | 2026-05-22 11:38:54 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-11 | 2026-05-10 15:06 | 2026-06-16
19310 | Turnkey | 2026-01-01 | Gangeti Ramesh Kumar | Casagrand | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Hold | Preproduction | Site Readiness 1 | 1246657 | 249999 | 1696718 | 0 | 0 | 12 | 69 | 0 | 0 | 502813 | 493844.8 |  |  | 2026-04-04 | 2026-04-06 14:26 | 2026-04-07 | 2026-04-07 12:13 | 2026-04-09 | 2026-04-09 12:38 | 2026-04-25 | 2026-04-25 19:57 | 2026-08-09 |  | 2026-08-16 |  | 2026-04-09 | 2026-04-11 18:14 | 2026-04-10 | 2026-04-12 13:06 | 2026-04-12 | 2026-04-14 16:59 | 2026-04-19 | 2026-04-19 18:44 |  |  |  |  | 2026-04-25 | 2026-04-22 15:14 | 2026-08-11 |  | 2026-08-12 |  |  |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-08-20 |  | 2026-04-20 | 2026-04-25 19:55 | Site is Non-RTMI | 2026-04-04 | 2026-04-06 14:24 | 1437896 | 258821 | 0 | 0 | 0 | 0 | 1419582.705 | 234405 | 2026-06-16 19:12:07 +0530 | Akshay Ds | Some Image was uploaded | 2026-04-23 17:19:10 +0530 | Akshay Ds | The customer would like to proceed with the design phase based on the floor plan. Once the design is completed, the project will be placed on hold, as possession is expected in August. | 2026-04-14 16:59:06 +0530 | Bency Chacko | Possession - Aug end 2026 IMs can't be taken - site July/Aug. Can prepare the designs with a floor plan No on-site work is planned He will pay 10% once the 1 DEMs are closed and signed off No issues with the checklist Clear with timelines, Scope of work and Offers Clear with the process B2C - Self-funded | 2026-04-26 | 2026-04-25 19:58 | 2026-08-10 |  | Under Construction | 2026-08-31
19312 | Turnkey | 2026-01-01 | Shreya Shreya | Evo homes | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 3881186 | 9999 | 0 | 0 | 0 | 88 | 0 | 378120 | 388119 | 1583478 | 1521471.2 |  |  | 2026-04-05 | 2026-04-14 16:32 | 2026-04-05 | 2026-04-17 18:09 | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-05 | 2026-04-05 12:53 | 0 | 0 | 0 | 0 | 0 | 0 | 3289141 | 592045 | 2026-04-14 16:07:15 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-04-05 16:35:58 +0530 | Keerthan M | DCM: 1. Project Overview The villa is a 5 BHK layout distributed across: Ground Floor First Floor Second Floor Current Scope of Work: 2 Bedrooms 1 Office Room 1 Common Study Area Living, Dining, and Key Common Areas Exclusions: Second floor is not included in the current scope of work. --- 2. Budget Discussion Estimated budget: 2530 Lakhs Budget includes: Fixed interiors Loose furniture (beds, sofas, etc.) Approach: Design will be developed based on requirements first. Cost optimization will be undertaken after design finalization. --- 3. Floor-wise Scope Ground Floor Living Area Open layout design Sofa seating and TV unit required Focus on aesthetics and functionality Dining Area Connected with living space Standard dining setup Kitchen Modular kitchen design Material options to be explored: Bedroom (1 Room) Full interior setup required: Bed Wardrobe Side tables Open Study Area (Skylight Zone) Key feature: skylight/double-height cut-out To be designed as an open study or reading space Emphasis on natural lighting Additional Space (Near Skylight) Proposed usage: Storage Small seating arrangement (compact sofa) --- First Floor Bedroom 1 Complete interior design required Wardrobe, bed, and side units Bedroom 2 Similar scope as Bedroom 1 Theme flexibility allowed Office Room Converted from bedroom Requirements: Work desk Storage units Professional design aesthetic Common Study Room Shared workspace Requirements: Study desks Storage shelves Functional and minimal design approach --- Second Floor No work to be undertaken Excluded from design and costing --- 4. Costing and Estimation Costing to be provided: Room-wise Component-wise (where required) Methodology: Modular elements: software-based costing Custom elements: manual estimation False ceiling: manual calculation Final costing will be verified by the internal estimation team --- 5. Design and Execution Workflow Design platform: SketchUp Costing integration through internal plugin Capabilities include: Modular designs Custom-built elements Flexible material selection --- 6. Design Preferences Client is open to exploring different design themes Preference for: Practical designs Low-maintenance materials Functional layouts To avoid: Overly complex or high-maintenance styles --- 7. Timeline and Next Steps Next meeting: Tentatively scheduled for the next-to-next weekend Weekday meeting possible (to be confirmed) Client Actions: Share reference images and design inspirations Designer Actions: Develop initial design concepts Prepare room-wise layouts Provide preliminary cost estimates --- 8. Key Considerations Material selection (MDF vs Plywood) will significantly impact: Cost Durability Recommendation: Maintain a balance between budget and long-term quality --- 9. Conclusion Agreement to proceed with a design-first approach Detailed room-wise costing to be provided Focus on functionality, natural lighting, and scalable budgeting |  |  |  | 2026-05-04 |  | 2026-05-11
19313 | Turnkey | 2026-01-01 | Mr Rajesh Ramachandran | Radiance Gardenia | BNG - HRBR | Yes | Salpriyan Pm | Rajeshwari S | Shibin Lal | [7 empty] | Active | Preproduction | Site Readiness 1 | 3149873 | 441468 | 2943349 | 0 | 0 | 2 | 48 | 0 | 0 | 1671636 | 1036768.8 |  |  | 2026-04-05 | 2026-04-05 13:13 | 2026-04-11 | 2026-04-14 17:38 | 2026-04-22 | 2026-04-22 12:24 | 2026-05-10 | 2026-05-10 18:11 | 2026-07-22 |  | 2026-07-23 |  | 2026-04-22 | 2026-04-23 19:39 | 2026-04-23 | 2026-04-26 13:36 | 2026-04-26 | 2026-04-27 13:39 | 2026-05-03 | 2026-05-03 21:54 |  |  |  |  | 2026-05-10 | 2026-05-26 19:50 | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-05-04 | 2026-05-10 18:08 | Site is Non-RTMI | 2026-04-05 | 2026-04-05 13:12 | 2494364 | 448985 | 0 | 0 | 0 | 0 | 3436864.4691 | 567438 | 2026-05-20 14:41:57 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-07 19:38:37 +0530 | Yogesh B | Some Image was uploaded | 2026-05-07 18:49:44 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-11 | 2026-05-10 18:12 | 2026-07-23 |  | Under Construction | 2026-05-26
19314 | Turnkey | 2026-01-01 | Mukesh Jasani | Mahavir Vasundhara | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | Anamika Ghate | Anamika Ghate |  |  |  | Umang Shah | Aakash Gaikwad | Active | Preproduction | 2D | 1734342 | 261350 | 1673138 | 0 | 1734342 | 4 | 0 | 0 | 0 | 805959 | 667032.8 |  |  | 2026-04-05 | 2026-04-05 13:56 | 2026-04-05 | 2026-04-12 21:23 | 2026-04-12 | 2026-04-12 21:39 | 2026-05-13 | 2026-05-13 20:10 | 2026-05-30 | 2026-05-29 14:31 | 2026-06-06 | 2026-06-05 12:21 | 2026-04-12 | 2026-04-14 19:05 | 2026-04-13 | 2026-04-15 10:34 | 2026-04-09 | 2026-04-15 16:24 | 2026-04-21 | 2026-04-21 12:19 |  |  |  |  | 2026-05-16 | 2026-05-27 20:30 | 2026-05-30 | 2026-05-30 17:21 | 2026-06-20 | 2026-06-05 10:18 |  |  | 2026-06-17 | 2026-07-11 17:39 | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 | [6 empty] | 2026-07-18 |  | 2026-07-27 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-30 |  |  |  | 2026-08-21 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-06-28 |  | 2026-04-22 | 2026-05-13 19:46 | Site is RTMI | 2026-04-05 | 2026-04-05 13:53 | 1420201 | 252937 | 0 | 0 | 1801841.2178 | 304221 | 1801841.2178 | 304221 | 2026-07-05 14:56:29 +0530 | Reshma Melanta | Others: | 2026-07-05 12:58:59 +0530 | Reshma Melanta | Others: Project Overview Project ID:Â 19314 Client Name:Â Mukesh Jasani Net Date:Â 14th April 2026 Original Project Value:Â â‚¹13,06,750 Current Stage:Â PKO Stage Amount PaidÂ : 2,61,350 Current Status:Â Client insisting on cancellation and full refund. 1. Problem Statement The client has requested a full refund due to a drastic commercial escalation post-cross-measurement, where the project value increased from â‚¹13,06,750Â to â‚¹18,00,000 â€“ â‚¹20,00,000. This significantly breached the initial verbal commitment made to the client that the value would fluctuate by a maximum of â‚¹1â€“2 Lakhs. Despite multiple attempts by the team to retain the clientâ€”including optimizing the design to â‚¹17,34,342Â and later offering a minimum scope of â‚¹8,00,000â€”the client has refused to proceed due to a loss of trust from changing docket materials and the unviability of spending heavily on a rented apartment. RCA Inaccurate Initial Expectations:Â During the initial stage, the client was given an unapproved verbal assurance that the price variation would not exceed â‚¹1â€“2 Lakhs, establishing an unrealistic financial baseline. Massive Scope Variance:Â The initial estimation significantly underrepresented the actual site scope, resulting in an escalation of â‚¹5â€“7 Lakhs once physical cross-measurements were finalized. Loss of Confidence (Docket Inconsistencies):Â As the designer shared dockets, frequent changes to the material specifications caused client dissatisfaction and gave an impression of instability in planning. | 2026-06-21 21:15:00 +0530 | Mandar Ambre | Some Image was uploaded | 2026-05-14 | 2026-05-16 10:58 | 2026-05-30 | 2026-05-29 14:44
19315 | Turnkey | 2026-01-01 | Shubha Reddy | Independent villa | BNG - HSR | No Estimate | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-05 | 2026-04-05 14:15 | 2026-04-06 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-07 |  | 2026-07-02 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-02 |  | 2026-07-07 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-05 | 2026-04-05 14:13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-26 |  | 2026-05-03
19316 | Turnkey | 2026-01-01 | Arun Anand G | Sobha Brooklyn Towers Town Park | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik |  | Parvez Syed | Nanda Kumar |  |  | Pulivarthi Nirosha | Raghavendra Gowda | Active | Preproduction | 2D | 824659 | 142941 | 926258 | 824659 | 0 | 4 | 0 | 0 | 0 | 363157 | 318561.2 |  |  | 2026-04-05 | 2026-04-06 10:38 | 2026-04-10 | 2026-04-10 10:41 | 2026-04-14 | 2026-04-14 10:39 | 2026-05-15 | 2026-05-15 18:23 | 2026-07-04 | 2026-07-03 16:01 | 2026-07-09 | 2026-07-09 16:09 | 2026-04-14 | 2026-04-15 12:19 | 2026-04-15 | 2026-04-16 14:00 | 2026-04-16 | 2026-04-17 18:06 | 2026-04-19 | 2026-04-19 18:30 |  |  |  |  | 2026-05-16 | 2026-05-24 11:31 | 2026-07-15 | 2026-07-03 21:35 | 2026-07-04 | 2026-07-03 22:01 |  |  | 2026-07-10 | 2026-07-11 12:55 | 2026-07-11 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-11 |  | 2026-05-18 | 2026-05-15 17:03 | Site is RTMI | 2026-04-05 | 2026-04-06 10:37 | 784964 | 141293 | 886561.8025 | 146388 | 0 | 0 | 886561.8025 | 146388 | 2026-06-17 18:59:59 +0530 | Prathyusha Elangovan | Arun Anandh (Material Selection)(16/06/26) TV unit Orlando Walnut 7720 SD(GOLD) RAFTERS-Flava Rafters TL WL 1624 Black aluminium profile with grey tinted glass Groove provision for profile lights inside the wall unit Gate panelling Orlando Walnut 7720 SD All wall concepts to be descoped Kitchen Royale Touche 1174 crystal(for both base, wall and loft units) Clear fluted glass with black G profile handle and black profile Master Bedroom Option 1 -completed Purple 1159 SD Option 2 -Combination of Purple 1159SD with Tidal sand 1033 Tidal sand Kids Bedroom Option 1-Avio Blue 1709 AFP ,Beige 1715 AFP Option 2-Premium Green 1722 AFP,Tussock Beige 1588AFP Vanity Units Bronce Metallic 1591 SL HG | 2026-05-29 11:16:23 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-20 18:21:08 +0530 | Prathyusha Elangovan | ARUN ANAND(DESIGN BRIEF) LIVING AREA TV UNIT PLACE FOR KEEPING THE IDOL(SHELF) HIDDEN MCB L SHAPE SOFA(3+1) PARTITION POOJA UNIT EITHER ON WALL NEXT TO THE PARTITION OR WITH THE PARTITION FACING THE BALCONY POOJA UNIT STANDING WITH DRAWERS IN THE BOTTOM (BACK CNC IN TAMIL) TV CABINET HOME THEATER WOOFER,SOUNDBAR AND (SPEAKERS IN THE SOFA WALL) INVISIBLE DOORÂ PARTITION WITH BOTTOM STORAGE INBUILT FRIDGE NEED TO BE CHECKED KITCHEN C SHAPE NEEDS TO BE EXTENDED WALL UNIT AND LOFT MBR KING SIZE BED BAY WINDOW SEATER+STORAGE 6',6' PLATFORM BED AS PER REFERENCE STUDY FIXED+WARDROBE PARENTS BEDROOM PLATFORM BED NEEDS TO BE CHECKED STUDY UNIT,DRESSER+WLK IN WARDROBE END TO END LOFT U SHAPEÂ CORNICE IN THE LIVING AND PASSAGE | 2026-05-16 | 2026-05-24 12:51 | 2026-07-04 | 2026-07-03 16:05 | Under Construction | 2026-07-31
19317 | Turnkey | 2026-01-01 | Joshna Vemula | M M Apartment | BNG - HRBR | Yes | [10 empty] | Active | Prospect | 10% Payment | 1273456 | 9999 | 1273456 | 0 | 0 | 88 | 0 | 117347 | 127346 | 528845 | 489919.6 |  |  | 2026-04-05 | 2026-04-06 13:52 | 2026-04-05 | 2026-04-06 13:52 | 2026-04-22 | 2026-04-22 10:57 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-05 | 2026-04-05 14:49 | 1079200 | 194256 | 0 | 0 | 0 | 0 | 1079200 | 194256 | 2026-04-05 18:48:49 +0530 | Rhea Rathod | DCM: Possession - April 20 Family of 4- Twins - 23 years old North facing main-door Colour preferences - Brown and creams. Theme - not specific, but should be simple and elegant. Minimalist designs. Profession - developer company False ceiling - Living area Sons profession - Software engineers Changes in the plan- - no window on the right wall - D2 - is a full wall. entrance to the utility is via balcony. - Balcony - entrance is end to end sliding door - Master bedroom (next to kitchen) - there is no window on the right wall. Foyer - -Shoe rack existing Living - - Pooja on the bedroom 1 wall - TV unit - Wall mounted, Tall unit- with glass - L shaped sofa - Crockery unit - next to the pooja unit - Wall decor on both walls - Dining - 4 seater table - existing - Partition - to the dining area Kitchen - - Modular kitchen - L shaped with loft - Granite required - Right wall - existing window - RO unit - East facing hobÂ - Plumbing point is on the east wall. - One Wall unit on the north wall. - Double door fridgeÂ Master bedroom - - 8.5 dia - Round bed, 5' headboard- existing - Dresser and Wardrobe with loft Bedroom 1 - (11'6 X 11'8)- - Cot - queen size - existing - Wardrobe with loft on either side of the Bay window seater - Bay window seater - Wall concept - Son's height - 5'9" Bedroom 2 - (Guest bedroom) - Cot- south wall - required - Wardrobe with loftÂ - Wall concept | [6 empty] | 2026-04-30 |  | 2026-05-07
19318 | Turnkey | 2026-01-01 | Dr. Asif Kaskar | Aniruddha icon | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Preproduction | DEM2 | 1896327 | 379999 | 0 | 0 | 0 | 57 | 13 | 0 | 0 | 802581 | 713747.2 |  |  | 2026-04-05 | 2026-04-07 12:53 | 2026-04-07 | 2026-04-09 16:29 | 2026-04-14 | 2026-04-14 11:25 | 2026-05-06 | 2026-05-06 12:36 | 2026-12-01 |  | 2026-12-08 |  | 2026-04-14 | 2026-04-23 11:34 | 2026-04-15 | 2026-04-23 11:43 | 2026-04-23 | 2026-04-24 11:39 | 2026-05-05 | 2026-05-05 12:36 |  |  |  |  | 2026-05-20 | 2026-05-06 18:26 | 2026-12-03 |  | 2026-12-04 |  |  |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-13 |  | 2026-12-14 | [6 empty] | 2027-01-01 |  | 2027-01-10 |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-11 |  | 2027-01-13 |  |  |  | 2027-02-04 |  | 2027-02-06 |  | 2027-02-07 | [5 empty] | 2026-12-12 |  | 2026-05-06 | 2026-05-05 14:16 | Site is RTMI | 2026-04-05 | 2026-04-07 12:52 | 0 | 0 | 0 | 0 | 0 | 0 | 2191312.0531 | 356388 | 2026-06-26 11:44:36 +0530 | Naved Malik | Client is yet to receive possession, we are planning for PKO in this month once he gets approval from the builder to start work on soft possession. Material selection meeting aligned for 4th or 5th of July. | 2026-06-16 11:26:51 +0530 | Vandana Preet | Some Image was uploaded | 2026-06-10 16:40:34 +0530 | Naved Malik | Some Image was uploaded | 2026-05-07 | 2026-05-06 12:53 | 2026-12-02
19319 | Turnkey | 2026-01-01 | SHRUTHI AYYAPPA | Nava Vajra | BNG - HRBR | Yes | Chandini Nj | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Hold | Preproduction | Site Readiness 1 | 1383246 | 276649 | 1716628 | 0 | 0 | 3 | 69 | 0 | 0 | 611268 | 495328.8 |  |  | 2026-04-05 | 2026-04-14 11:38 | 2026-04-14 | 2026-04-14 17:18 | 2026-04-17 | 2026-04-15 11:53 | 2026-05-03 | 2026-05-03 12:35 | 2026-08-15 |  | 2026-08-22 |  | 2026-04-17 | 2026-04-14 17:36 | 2026-04-16 | 2026-04-15 13:15 | 2026-04-15 | 2026-04-25 10:55 | 2026-04-30 | 2026-04-30 18:39 |  |  |  |  | 2026-05-03 | 2026-05-04 19:17 | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-05-01 | 2026-05-03 12:20 | Site is Non-RTMI | 2026-04-05 | 2026-04-07 21:41 | 1454769 | 261858 | 0 | 0 | 0 | 0 | 1419239.425 | 244562 | 2026-05-05 17:23:41 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-03 12:09:09 +0530 | Unknown | About the Customer **Introduction and Project Value Discussion** Agent Benzie from HomeLane Designs initiated a call with Mr. Iyappan to discuss project offers and onboarding. The agent confirmed the customer's project value of â‚¹13,80,000 and discussed existing offers, including waivers on project management fees and upgrades for furniture, modular items, and laminates. **Possession Timeline and Exception Request** The customer's property, Nava Vajra, is expected to have possession in December, with registration planned for August. Mr. Iyappan is seeking an exception to start woodwork in November to ensure possession in December, indicating a tight timeline for the project. **Design and Production Process Explanation** The agent explained the design and production process, detailing site visits for measurements, design presentations, material selection, and payment milestones. It was clarified that the standard 90-day production timeline does not include any hold periods. **Transaction Details and Call Conclusion** The agent confirmed that the transaction is B2C and self-funded, and that an offer email has been sent to the customer. The call concluded with mutual thanks between the agent and Mr. Iyappan. | 2026-05-02 13:32:08 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-03 | 2026-05-03 12:39 | 2026-08-16 |  | Under Construction | 2026-12-31
19320 | Turnkey | 2026-01-01 | Varun Simhadri | Vaishno Serene | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1570410 | 9999 | 1570410 | 0 | 0 | 84 | 0 | 147042 | 157041 | 638928 | 617400 |  |  | 2026-04-05 | 2026-04-17 18:17 | 2026-04-05 | 2026-04-22 12:38 | 2026-04-25 | 2026-04-22 13:21 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-05 | 2026-04-12 12:29 | 1330856 | 239554 | 0 | 0 | 0 | 0 | 1330856 | 239554 | 2026-05-20 12:00:55 +0530 | S S Sri Akshita | DCM: Client - Varun Simhadri Family members - nuclear family and elder parentsÂ Possesion - September 26 Move in - December 26 Property - Vaishno SereneÂ Budget -Â Configuration - 3 bhkÂ Mbr - Door to balcony has been closedÂ Dining - Washbasin has been shifted to dining area right to the balcony (Dining - upper right) Living - main dbÂ Door is East facingÂ Tv unit - tv + pooja unitÂ Tv unit with storageÂ Tall unit - Option to be shownÂ Projector wall to be plannedÂ Lighter shadesÂ 1 wall in the common area - family photos to be plannedÂ Dining Area -Â Dining to a cornerÂ crockery - 2Â wash basinÂ KitchenÂ Sink shifted to left of utility opp hobÂ Parallel kitchen Double doorÂ otg in builtÂ mixer, grinder, airfryerÂ cylinder - bottom unit to be keptÂ spare cylinder spareÂ big vessels storageÂ hob and chimney - cook topÂ 10kg rice bagÂ granite - blackÂ Master bedroomÂ offsets in bedrooms to be checkedÂ wardrobe - options to be suggestedÂ tv cum studyÂ dresserÂ bed positionÂ AC positionÂ used clothes provisionÂ laundry basket space - to be planned in all roomsÂ big studyÂ Bedroom - 3Â wardrobeÂ big studyÂ ac provisionÂ used clothesÂ dresser to be suggestedÂ queen bedÂ Bedroom -2Â no kids theme in any roomÂ wardrobe with studyÂ Dresser with storageÂ bed with side tablesÂ Utility -Â dishwasher - options to be checkedÂ sinkÂ washing machine shifted to balcony beside diningÂ RO - OVER THE TOPÂ Provisions for appliances -Â Robo floor cleanerÂ Lighting - maintanence and easily availableÂ House should be kid friendlyÂ Welspun flooring - to be planned for future click and lock tilesÂ False ceilingÂ Height - 9'Â | 2026-04-28 17:43:08 +0530 | Losii Athisa | Some Image was uploaded |  |  |  | 2026-04-30 |  | 2026-05-07
19321 | Turnkey | 2026-01-01 | Shabir Ahmad | Menakshi | BNG - HSR | Yes | Sahana Kumbar | Akshay Ds | Priyanka Mathur | [5 empty] | Chanakya Panigrahi |  | Active | Preproduction | DEM2 | 2222934 | 341091 | 1787021 | 0 | 0 | 70 | 0 | 0 | 0 | 1019400 | 862442.8 |  |  | 2026-04-05 | 2026-04-05 15:54 | 2026-04-09 | 2026-04-09 19:20 | 2026-04-09 | 2026-04-09 20:51 | 2026-05-06 | 2026-05-06 14:31 | 2026-08-08 |  | 2026-08-15 |  | 2026-04-09 | 2026-04-11 18:04 | 2026-04-10 | 2026-04-17 10:32 | 2026-04-17 | 2026-04-17 13:25 | 2026-04-18 | 2026-04-18 19:30 |  |  |  |  | 2026-05-14 | 2026-05-05 14:24 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-05-09 | 2026-05-06 14:16 | Site is RTMI | 2026-04-05 | 2026-04-05 15:50 | 1514425 | 272596 | 0 | 0 | 0 | 0 | 2441607.7321 | 403159 | 2026-07-03 11:16:34 +0530 | Priyanka Mathur | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion ï»¿ Based on meeting, below is a list of all the requirements that were discussed during the meeting: | 2026-07-03 11:15:24 +0530 | Priyanka Mathur | Minutes of Meeting held on Date: Attendees: Discussion: ï»¿ Based on meeting, below is a list of all the requirements that were discussed during the meeting: | 2026-06-04 12:05:04 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-07 | 2026-05-07 00:46 | 2026-08-09 |  | RTMI
19322 | Turnkey | 2026-01-01 | Vipul Singh | Binary Temple Tree | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Design | DEM1 | 1014740 | 132900 | 1328157 | 0 | 0 | 92 | 0 | 0 | 70048 | 410714 | 401078 |  |  | 2026-04-05 | 2026-04-05 16:13 | 2026-04-08 | 2026-04-08 19:17 | 2026-04-09 | 2026-04-09 10:34 | 2026-09-01 |  | 2026-09-08 |  | 2026-09-15 |  | 2026-04-09 | 2026-04-10 17:23 | 2026-04-10 | 2026-04-11 12:17 | 2026-04-11 | 2026-04-14 11:43 | 2026-04-16 | 2026-04-16 14:43 |  |  |  |  | 2026-09-02 |  | 2026-09-10 |  | 2026-09-11 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 | [6 empty] | 2026-10-09 |  | 2026-10-18 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-21 |  |  |  | 2026-11-12 |  | 2026-11-14 |  | 2026-11-15 | [5 empty] | 2026-09-19 |  | 2026-05-14 | 2026-05-20 18:08 | Site is RTMI | 2026-04-05 | 2026-04-05 16:10 | 1125557 | 202600 | 0 | 0 | 0 | 0 | 1122192.096 | 185299 | 2026-07-14 17:34:12 +0530 | Abhinandan K S |  | 2026-06-05 15:22:42 +0530 | Prathyusha Elangovan | Some Image was uploaded | 2026-04-23 10:45:15 +0530 | Patil Madhavi | Some Image was uploaded | 2026-09-02 |  | 2026-09-09 |  | Under Construction | 2026-04-20
19323 | Turnkey | 2026-01-01 | Amit Thakur- | Purva Atmoshphere | BNG - HRBR | Yes | [10 empty] | Active | Prospect | 10% Payment | 2008808 | 9999 | 2008808 | 0 | 0 | 56 | 0 | 190882 | 200881 | 864709 | 742337.2 |  |  | 2026-04-05 | 2026-04-06 13:47 | 2026-04-05 | 2026-04-07 11:29 | 2026-05-19 | 2026-05-26 15:22 | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-04-05 | 2026-04-06 13:41 | 1702380 | 306428 | 0 | 0 | 0 | 0 | 1702380 | 306428 | 2026-04-28 18:00:48 +0530 | Losii Athisa | Some Image was uploaded | 2026-04-05 18:49:30 +0530 | Rhea Rathod | DCM: Possession - in hand Family of 4 - daughters - 11 yrs, 4 yrs Theme - earthy , minimalist, subtle, Japandi, clutter free, wooden textures Colours - white, toned down colours, beige. Profession - IT, Doctor North Facing - 22nd floor Foyer -Â - wall concept Dining- - 6 seater - Memory wall - wall concept Living area- - Beige sofa l shaped - No cabinets - Wall decor - 65" tvÂ - true ceiling to be designed beautifully - Curved edges to be designed Kitchen - - Crockery unit - floor to ceiling glass next to pooja unit. - Pooja unit - on shaft wall - Sit and pray - Double door fridge - Washing machine, dryer, dishwasher - Pantry unit - Hob unit - west facing - Sink unit in utility with top cabinets - Top cabinet in the utility right wall Master bedroom- - Bed - east wall with wall concept - Wardrobe with loft - Dresser unit on the right side of the bed Bedroom 2- - Kid's bedroom - Queen size Bed - Wall concept - Wardrobe with loft - Study for 2 - Dresser next to the bed Bedroom 3- - TVÂ - wall concept - Bed - east wall - Wardrobe with loft Bathrooms -Â Vanity units- bottom |  |  |  | 2026-06-03 |  | 2026-06-10
19324 | Turnkey | 2026-01-01 | Mr. Sagar Hiren Shah And Mrs. Athira Bhaskar | Nava Vajra | BNG - HRBR | Yes | [10 empty] | Active | Prospect | 10% Payment | 1445866 | 9999 | 0 | 0 | 0 | 88 | 0 | 134588 | 144587 | 588638 | 568054.4 |  |  | 2026-04-05 | 2026-04-06 13:40 | 2026-04-07 | 2026-04-10 14:46 | 2026-05-09 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-05-17 |  | 2026-05-25 |  | 2026-05-26 |  |  |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 | [6 empty] | 2026-06-23 |  | 2026-07-02 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-05 |  |  |  | 2026-07-27 |  | 2026-07-29 |  | 2026-07-30 | [5 empty] | 2026-06-03 |  | 2026-05-12 |  | Unknown | 2026-04-05 | 2026-04-06 13:35 | 0 | 0 | 0 | 0 | 0 | 0 | 1225310 | 220555 | 2026-04-05 18:30:47 +0530 | Keerthan M | DCM: Nava vajra 3Bhk 4 PPL 10L 3BHK Living - TV unit - Existing sofa - wall detailing - sofa wall detailing - partition Dining - Crockery unit on toilet wall - pooja unit near duct window - 6 seater dining table Kitchen - u shape - tall units - single door fridge - bottom, top, duct panel Utility - top storage and opp janitor unit MBR - need to confirm bed position - wardrobe with study and dresser - wall detailing - queen bed PBR(attch bathroom) - bed - wardrobe and dresser - wall detailing GBR - work space - lap top with 2 desktop - minimal top storage - sofa cum bed - false ceiling full house optional, but need to consider common area | [6 empty] | 2026-05-17 |  | 2026-05-24
19326 | Turnkey | 2026-01-01 | Atul Devghare | puranik city | MUM - Thane | Yes | [8 empty] | vinaya thakur |  | Active | Prospect | DCM Due | 828273 | 9999 | 0 | 0 | 0 | 101 | 0 | 72828 | 82827 | 355794 | 306824.4 |  |  | 2026-04-05 | 2026-04-05 21:05 | 2026-04-08 | 2026-04-09 11:24 | 2026-04-12 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-04-20 |  | 2026-04-28 |  | 2026-04-29 |  |  |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 | [6 empty] | 2026-05-27 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-08 |  |  |  | 2026-06-30 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-05-07 |  | 2026-04-15 |  | Unknown | 2026-04-05 | 2026-04-05 17:18 | 0 | 0 | 0 | 0 | 0 | 0 | 956899.1994 | 157999 | 2026-04-29 18:41:38 +0530 | Aakriti Parmar | Some Image was uploaded | [6 empty] | 2026-04-20 |  | 2026-04-27
19327 | Turnkey | 2026-01-01 | Gajanan Patil | RUNWAL FOREST | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | suraj kumar | Aditya Vikram |  | Foram Joshi | Prasad Bhivaji Hande | Hold | Design | 60% Payment | 847618 | 240799 | 1656010 | 0 | 847618 | 31 | 30 | 0 | 0 | 278594 | 328225.2 |  |  | 2026-04-05 | 2026-04-05 18:03 | 2026-04-07 | 2026-04-07 13:13 | 2026-04-08 | 2026-04-08 12:53 | 2026-04-24 | 2026-04-24 12:14 | 2026-04-28 | 2026-04-27 16:01 | 2026-05-08 | 2026-05-08 16:36 | 2026-04-08 | 2026-04-08 13:25 | 2026-04-09 | 2026-04-09 14:15 | 2026-04-09 | 2026-04-24 11:10 | 2026-04-24 | 2026-04-24 11:18 |  |  |  |  | 2026-04-16 | 2026-04-14 19:01 | 2026-05-06 | 2026-05-06 19:14 | 2026-05-07 | 2026-05-06 19:22 |  |  | 2026-05-09 | 2026-05-14 19:07 | 2026-05-14 | 2026-05-15 10:59 | 2026-05-15 | 2026-05-15 12:52 | 2026-07-30 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-04-25 | 2026-04-24 12:06 | Site is RTMI | 2026-04-05 | 2026-04-05 17:56 | 1403399 | 252611 | 0 | 0 | 998443.0188 | 168577 | 998443.0188 | 168577 | 2026-07-02 14:05:34 +0530 | Anil Jagtap | HOLD | 2026-06-16 10:46:15 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-15 18:40:31 +0530 | Anil Jagtap | Some Image was uploaded | 2026-04-25 | 2026-04-24 12:19 | 2026-04-28 | 2026-04-27 16:03
19328 | Turnkey | 2026-01-01 | Harsh Krishna | Brigade Calista | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 1938312 | 9999 | 0 | 0 | 0 | 101 | 0 | 183832 | 193831 | 801507 | 749142.8 |  |  | 2026-04-05 | 2026-04-05 19:37 | 2026-04-16 | 2026-04-17 13:37 | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-05 | 2026-04-05 19:35 | 0 | 0 | 0 | 0 | 0 | 0 | 1642637 | 295674 | 2026-04-16 16:01:54 +0530 | Saranya Thiyagarajan | DCM: Client name- Harsh Krishna 2bhk Property- Brigade Calista Possession- OctoberÂ Facing - North-East Members- 4 Kids Â Theme - Blue & GreenÂ Budget- 12-15L Next Design meeting - Â Foyer- Shoe rack with sitting and wall design Â Living & Dining- Living will get interchange with the Dining TV unit will be on the Bathroom wall Â Dining area- Crockery unit & Pooja unit Pooja unit in the corner (Try to match with the existing one with more storage) Accent wall for the Dining wall *Bar unit (Hidden one)* 6 seater dining *False ceiling for Living & Dining* Â Kitchen appliances- Microwave Mixie Air fryer griller Sandwich Under mount RO unit in Utility Base, Wall & Loft Mix of Glass & Lam Shutter Granite & Sink (3') Rolling shutter & OTG unit Loft & Wall units for Utility Janitor unit in the Utility Â MBR- TV unit ledge Wardrobe with lofts (if possible with lights) Dresser unit L-shape with sitting Study unit with the wardrobe Accent wall (Reference taken) *FALSE CEILING* Â BR1(GBR)- Wardrobes with Loft Study unit(with 2shutter storage) Â Bathrooms-Vanity units & Mirror with storage behind for both the Bathrooms Â Balcony design with ledges for plants | 2026-04-16 15:55:28 +0530 | Saranya Thiyagarajan | DCM: Client name- Harsh Krishna 2bhk Property- Brigade Calista Possession- OctoberÂ Facing - North-East Members- 4 Kids - Â Theme - Blue & GreenÂ Budget- 12-15L Â Foyer- Shoe rack with sitting and wall design Â Living & Dining- Living will get interchange with the Dining TV unit will be on the Bathroom wall Â Dining area- Crockery unit & Pooja unit Pooja unit in the corner (Try to match with the existing one with more storage) Accent wall for the Dining wall *Bar unit (Hidden one)* 6 seater dining *False ceiling for Living & Dining* Â Kitchen appliances- Microwave Mixie Air fryer griller Sandwich Under mount RO unit in Utility Base, Wall & Loft Mix of Glass & Lam Shutter Granite & Sink (3') Rolling shutter & OTG unit Loft & Wall units for Utility Janitor unit in the Utility Â MBR- TV unit ledge Wardrobe with lofts (if possible with lights) Dresser unit L-shape with sitting Study unit with the wardrobe Accent wall (Reference taken) *FALSE CEILING* Â BR1(GBR)- Wardrobes with Loft Study unit(with 2shutter storage) Â Bathrooms-Vanity units & Mirror with storage behind for both the Bathrooms Â Balcony design with ledges for plants |  |  |  | 2026-04-26 |  | 2026-05-03
19329 | Turnkey | 2026-01-01 | Usha Devadiga | Ashar Arise | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Aditya Vikram |  | Anant Giri | Shailendra Mishra | Active | Preproduction | Site Readiness 2 | 896433 | 591691 | 1044444 | 922299 | 896433 | 1 | 0 | 0 | 0 | 0 | 304742 |  |  | 2026-04-05 | 2026-04-05 20:32 | 2026-04-24 | 2026-04-24 19:53 | 2026-04-27 | 2026-04-25 14:35 | 2026-05-07 | 2026-05-07 17:04 | 2026-07-05 | 2026-07-04 11:10 | 2026-07-08 | 2026-07-07 23:38 | 2026-04-25 | 2026-04-27 16:57 | 2026-04-26 | 2026-04-27 18:28 | 2026-04-27 | 2026-04-28 10:08 | 2026-05-05 | 2026-05-05 12:05 |  |  |  |  | 2026-05-07 | 2026-05-29 11:40 | 2026-07-11 | 2026-07-07 16:04 | 2026-07-08 | 2026-07-07 16:05 |  |  | 2026-07-10 | 2026-07-12 18:25 | 2026-07-12 | 2026-07-12 19:25 | 2026-07-21 | 2026-07-12 21:47 | 2026-07-13 | 2026-07-14 18:31 | [5 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-12 |  | 2026-05-06 | 2026-05-06 16:13 | Site is RTMI | 2026-04-05 | 2026-04-05 20:30 | 887923 | 156520 | 962199.4013 | 169613 | 935791.5465 | 164958 | 935791.5465 | 164958 | 2026-07-10 21:14:16 +0530 | Nilofer Shaikh |  | 2026-06-11 16:34:01 +0530 | Shraddha Pansare | Possession delayed- expected July 1st week. | 2026-04-28 10:03:27 +0530 | Royden Henriques | @Rushika More / Rinisha Masurkar / Karuna Shinde - Kindly connect with Isha with the design dates. -------------------------------------------- Possession : End of May'26 Payment Mode : B2C Self funding - Yes Cx will pay on 8th May Post offers the amount is 8,49,553/- as per the offer email.Â 105 calendar days for handover which includes Sundays and public holidays. Doesn't include Civil Work delays. | 2026-05-08 | 2026-05-07 17:06 | 2026-07-05 | 2026-07-04 16:00
19330 | Turnkey | 2026-01-01 | Nagaraja | Independent house | BNG - HSR | Yes | Chittipireddy Sriharish | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 3069525 | 9999 | 0 | 0 | 0 | 96 | 0 | 296954 | 306953 | 1231477 | 1224143.2 |  |  | 2026-04-05 | 2026-04-10 11:11 | 2026-04-10 |  | 2026-04-10 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-05-04 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-04-21 |  | 2026-04-29 |  | 2026-04-30 |  |  |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 | [6 empty] | 2026-05-28 |  | 2026-06-06 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-09 |  |  |  | 2026-07-01 |  | 2026-07-03 |  | 2026-07-04 | [5 empty] | 2026-05-08 |  | 2026-04-16 |  | Unknown | 2026-04-05 | 2026-04-07 13:59 | 0 | 0 | 0 | 0 | 0 | 0 | 2601292 | 468232 | 2026-04-10 10:16:26 +0530 | Chittipireddy Sriharish | DCM: Individual Home Possession : 01.07.26 Family members : 2 adults, 2 kids Boy : 4 yrs Charith, 6 yrs girl Nayara Occupation : Regional fire officer Budget : 25LÂ Â MD : East facing Modern luxury style NO wallpaper preferred, textured paints wall concepts to be done Stairs back walls to be highlighted Stilt Foyer : Approx - 40 pairs of shoes Wall conceptÂ Store room : Storage 2 Vanity : Under counter storage Lobby with sofa Office :Â Table with bookshelf storage Â GBR King size existing bed, 1 side table FL mirror next to cot area Ground floor FoyerÂ Wall concept TV position as per FP, 85" TV size DiningÂ pooja with Alu frame & glass Â 6 seater dining table Kitchen :Â Position as per FPÂ Opening near chimney for exhaust DD fridge space Appliances : MW, oven, mixer, grinder Pantry storage Wicker basket Under stairs study room with bookshelf,Â under stairs storage Wash storage Vanity storage First floor SBR (15*12) Lamborgini Car themed / Iron man bedroom concept Wardrobe in dresser area Toy storage in main room space No study table Vanity storage dresser in dress area DBRÂ Pink themed concept WR as per FP in dress dresser in dress area toy storage cum wR in main room space Vanity storage Terrace double height MBR Aristo WR, in both dressing & main room space King size bed with side tables Vanity storage Wall frame wall design at the entrance of the MBR Multipurpose room (For gym & party/ Home theatre) Bar counter storage Vanity storage | [6 empty] | 2026-04-21 |  | 2026-04-28
19331 | Turnkey | 2026-01-01 | ashrfunisa kaskar | Aniruddha icon | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Preproduction | DEM2 | 1792987 | 360597 | 2339905 | 0 | 0 | 57 | 13 | 0 | 0 | 800699 | 631691.2 |  |  | 2026-04-05 | 2026-04-07 12:55 | 2026-04-08 | 2026-04-08 11:17 | 2026-04-14 | 2026-04-14 11:22 | 2026-05-07 | 2026-05-06 12:53 | 2026-12-01 |  | 2026-12-08 |  | 2026-04-14 | 2026-04-23 14:39 | 2026-04-15 | 2026-04-23 16:48 | 2026-04-23 | 2026-04-24 11:40 | 2026-05-05 | 2026-05-05 12:37 |  |  |  |  | 2026-05-22 | 2026-05-06 11:57 | 2026-12-03 |  | 2026-12-04 |  |  |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-13 |  | 2026-12-14 | [6 empty] | 2027-01-01 |  | 2027-01-10 |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-11 |  | 2027-01-13 |  |  |  | 2027-02-04 |  | 2027-02-06 |  | 2027-02-07 | [5 empty] | 2026-12-12 |  | 2026-05-06 | 2026-05-05 14:15 | Site is RTMI | 2026-04-05 | 2026-04-07 12:51 | 1982970 | 356934 | 0 | 0 | 0 | 0 | 1975247.9126 | 326133 | 2026-07-02 17:11:43 +0530 | Divya Rahangdale | Hold | 2026-06-26 11:46:16 +0530 | Naved Malik | Client is yet to receive possession, we are planning for PKO in this month once he gets approval from the builder to start work on soft possession. Material selection meeting aligned for 4th or 5th of July. | 2026-06-10 16:40:56 +0530 | Naved Malik | Some Image was uploaded | 2026-05-07 | 2026-05-06 12:54 | 2026-12-02
19332 | Turnkey | 2026-01-01 | Nitin lembhe | Lodha casa rio | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Asif Shaikh | Aditya Vikram | Murali S | Mustufa Sohagpurwala | Prasad Bhivaji Hande | Hold | Production | 100% Payment | 797285 | 500590 | 1303680 | 0 | 809376 | 0 | 25 | 0 | 0 | 0 | 296695 |  |  | 2026-04-05 | 2026-04-06 12:48 | 2026-04-10 | 2026-04-22 11:49 | 2026-04-25 | 2026-04-22 17:58 | 2026-05-06 | 2026-05-06 19:28 | 2026-05-21 | 2026-05-20 14:36 | 2026-05-26 | 2026-05-25 23:57 | 2026-04-22 | 2026-04-23 20:09 | 2026-04-23 | 2026-04-23 20:17 | 2026-04-23 | 2026-04-24 11:19 | 2026-05-05 | 2026-05-05 19:25 |  |  |  |  | 2026-04-30 | 2026-04-24 10:55 | 2026-05-24 | 2026-05-19 10:49 | 2026-05-22 | 2026-05-21 06:16 |  |  | 2026-05-27 | 2026-06-12 12:21 | 2026-06-12 | 2026-06-13 11:11 | 2026-06-14 | 2026-06-13 16:05 | 2026-06-30 | 2026-06-24 19:07 |  |  |  |  | 2026-06-25 13:10 | 2026-07-01 | 2026-06-30 20:03 | 2026-07-09 | 2026-07-07 16:03 | 2026-07-08 |  | 2026-07-14 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-20 | [5 empty] | 2026-05-30 | 2026-05-31 14:44 | 2026-05-06 | 2026-05-06 19:18 | Site is Non-RTMI | 2026-04-05 | 2026-04-06 12:47 | 1107100 | 196579 | 0 | 0 | 826132.1381 | 139481 | 826132.2815 | 137636 | 2026-07-03 15:57:53 +0530 | Anil Jagtap | cx | 2026-06-28 21:45:31 +0530 | Asif Shaikh | Procurement: Floor Covering work will be done during furniture dispatchedFurniture shall be dispatched 15th July to 20th July (19th days for Production).Site Handover : 20th August 2026 (36 days for installation). | 2026-06-23 15:05:43 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-07 | 2026-05-06 19:31 | 2026-05-21 | 2026-05-20 15:20
19335 | Turnkey | 2026-01-01 | Mr.Kamal Kumar Lakshmanan | Ankuraa meridian | BNG - HRBR | Yes | [10 empty] | Active | Prospect | DCM Due | 2741555 | 9999 | 0 | 0 | 0 | 99 | 0 | 264157 | 274156 | 1096622 | 1096622 |  |  | 2026-04-06 | 2026-04-07 15:57 | 2026-04-06 | 2026-04-07 18:56 | 2026-04-11 |  | 2026-04-17 |  | 2026-04-24 |  | 2026-05-01 |  | 2026-04-10 |  | 2026-04-11 |  | 2026-04-11 |  | 2026-04-12 | [5 empty] | 2026-04-18 |  | 2026-04-26 |  | 2026-04-27 |  |  |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 | [6 empty] | 2026-05-25 |  | 2026-06-03 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-06 |  |  |  | 2026-06-28 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-05-05 |  | 2026-04-13 |  | Unknown | 2026-04-06 | 2026-04-06 15:22 | 0 | 0 | 0 | 0 | 0 | 0 | 2323352 | 418203 | 2026-05-29 13:56:14 +0530 | Losii Athisa | Some Image was uploaded | 2026-04-28 18:03:07 +0530 | Losii Athisa | Some Image was uploaded | 2026-04-06 15:50:50 +0530 | Rhea Rathod | DCM: Possession - June/July Profession - Software developer - own business Family of 4 - wife - 5 yrs, just born Theme - bright space. Colours - beige tones, Colours can be suggested. False ceiling for living and dining area East facing Apartment - 12th floor Living area- - Partition - 3/4th of the living area - Buddha statue in the center of the partition - 2 Fish tanks to be accommodated - Swing option to be checked - 65" TV unit - Suspended tv unit - Wall concept - L shaped sofaÂ - Wall concept on sofa back wall Dining area - - 6 Seater dining - Pooja unit - On the west wall - Vanity unit Kitchen - - L shaped - Sink unit - 2 - Single bowl and double bowl - Base cabinets - Under sink RO - Tall pantry unit, Appliance unit - Wall units - Loft - Double door fridge - Granite Master bedroom - - King size bed - Wall concept - Dresser unit - Wardrobe with loft - Vanity unit - with mirror, Top unit Bedroom 2 - Daughter's bedroom - Queen + bunker bed/ king size hydraulic bed - wardrobe with loft - Study unit - Wall concept - Vanity unit - with Mirror and top unit Passage wall to be designed Toilet -Â washing machine - top unit Vacuum robo cleaner Sink unit Sliding doorÂ Office room - - Wardrobe with loft - Suspended TV unit - 50" tv - Display unit - glass shelves on either sides. - Wall concept - Bay window optional - Existing study table - 1500 x 750 | 2026-04-18 |  | 2026-04-25
19336 | Turnkey | 2026-01-01 | Pranav Chheda | Sheth montena | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Mrunali Mitkari |  | Active | Preproduction | DEM2 | 2053168 | 410633 | 2754765 | 0 | 0 | 2 | 14 | 0 | 0 | 877818 | 764717.2 |  |  | 2026-04-05 | 2026-04-14 13:15 | 2026-06-02 | 2026-06-02 13:12 | 2026-06-02 | 2026-06-02 17:16 | 2026-06-21 | 2026-06-21 14:04 | 2026-07-10 |  | 2026-07-17 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-03 15:57 | 2026-06-03 | 2026-06-08 12:20 | 2026-06-13 | 2026-06-13 19:58 |  |  |  |  | 2026-06-21 | 2026-07-13 16:03 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-14 | 2026-06-21 13:56 | Site is RTMI | 2026-04-05 | 2026-04-09 18:31 | 2334546 | 420218 | 0 | 0 | 0 | 0 | 2290026.9008 | 378120 | 2026-06-26 12:56:25 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-21 14:13:54 +0530 | Preeti Agarwal | Living room - Crockery unit next to shoe rackShoe rack with a bigger seating with storageGlass partition to be addedBack panels selected as per CDP meetingKid's bedroom - Single pull-out bed with ledge storageDresser with side storage next to wardrobeGlass shutter book storageWardrobe internal discussedWall ledge below study top cabinetParent's bedroom - Dresser with side storage next to wardrobeTV unit point to be consideredWardrobe internal discussedMaster bedroom - Dresser with side storage next to wardrobeHidden bar unit to be thought ofMore storage for wardrobe if any whereBay window seating with storage if possibleCAT-6 in all the roomsKitchen - Maximum storage with shutterBalcony - bamboo partition on the right side | 2026-06-14 14:32:18 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-06-22 | 2026-06-21 14:13 | 2026-07-11 |  | Under Construction | 2026-06-30
19337 | Turnkey | 2026-01-01 | Sourabh suman | Green cascade | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 3000474 | 9999 | 0 | 0 | 0 | 96 | 0 | 290048 | 300047 | 1252544 | 1147834.8 |  |  | 2026-04-06 | 2026-04-10 14:06 | 2026-04-07 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-04-29 |  | 2026-05-07 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-24 |  | Unknown | 2026-04-06 | 2026-04-10 14:02 | 0 | 0 | 0 | 0 | 0 | 0 | 2542775 | 457699 | 2026-05-02 08:21:13 +0530 | Aparna | RGM Cx name : Sourabh Address: Astro Green Cascade, Gattahalli Prof : IT Independent house Theme : Classic European *BEADING DESIGNS* Entrance facing : East Budget - 23L Members - 3 and a dog Kids- NO CDP meeting- 18/19.04.2026 GROUND FLOOR Foyer (Outside) - Shoe rack with seating and wall panelling (MCB and charger point need to be hidden by paneling) TV Unit wall (9'6") - Pencil drawers with (Tinted or Frosted Glass shutter, if possible) For the nish space one storage (1') Wall beadingÂ An extra storage on top of the DOG HOUSE (should be accessible) Sofa wall (Double height wall )- Wall beading with Wallpaper/wall paneling/Ratan finish wallpaper) Kitchen - (Show quartz) Membrane finish- Wall units mix of Mesh Glass & Solid shuttersÂ Design ref shared by the client Appliances- Microwave, Mixie, Sandwich maker Storage for the appliances will be inside the Island Pantry unit Microwave unit Loft units-1'6" Wall units will be longer then usual Filler should have moulding design RO unit beside the window Utility- 3' sink base unit Wall units Janitor unit - 1'x1' GBR- Wardrobe Drawer unit beside wall Queen side bed (5') Dining area- Stone cladding for the boundary wall Simple wall design for the LEFT WALL Stair wall- Vanity unit (4') Wall highlight for the wall Washroom- Vanity unit 2' Stair case - Storage FIRST FLOOR Puja Room- Puja unit design inside the room Queen size BR- Wardrobe - Lshaped or straight wardrobe with Dresser Two side units Vanity unit Entertainment room-Â Wall design with Wall trims Right wall with window will be an ACCENT WALL with Arc and Wallpaper and lights design (A proper accent wall) Partition based on the ACCENT Wall design SECOND FLOOR- Washing machine area- base units one sink unit(2') 3 Door Wardrobe with Loft Master BR- Workstation till the window Chest of Drawers under table 3' wardrobe with extra storage for used clothes (RATAN finish) To hide the AC (Options needed) Accent wall behind the BED Parallel walk in wardrobe with Mirror on the wall in between (Mix of glass and solid/wood) And tall units both the sides (profile door if possible) Vanity unit Partition (Fluted) FALSE CEILING FOR Bathroom (need to check to hide the ceiling shower pipe) | [6 empty] | 2026-04-29 |  | 2026-05-06
19340 | Turnkey | 2026-01-01 | Venkata prasad | Century Horizon | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Active | Installation | Execution | 812645 | 812646 | 994354 | 0 | 812645 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-25 | 2026-04-22 20:08 | 2026-04-26 | 2026-04-24 18:46 | 2026-04-27 | 2026-04-24 18:55 | 2026-05-17 | 2026-05-17 16:52 | 2026-06-01 | 2026-05-31 16:53 | 2026-06-10 | 2026-06-10 18:08 | 2026-04-29 | 2026-04-24 19:12 | 2026-04-30 | 2026-04-30 15:16 | 2026-04-30 | 2026-05-05 15:22 | 2026-05-09 | 2026-05-09 11:28 |  |  |  |  | 2026-05-17 | 2026-05-25 18:55 | 2026-06-05 | 2026-06-06 17:42 | 2026-06-07 | 2026-06-06 18:07 |  |  | 2026-06-14 | 2026-06-14 19:41 | 2026-06-16 | 2026-06-16 13:57 | 2026-06-17 | 2026-06-16 17:36 | 2026-06-17 | 2026-06-19 18:48 |  |  |  |  | 2026-06-23 21:19 | 2026-06-27 | 2026-06-26 20:56 | 2026-07-08 | 2026-07-06 17:08 | 2026-06-22 | 2026-04-23 20:06 | 2026-07-06 | 2026-07-11 15:06 | 2026-07-11 | 2026-07-11 18:32 | 2026-07-13 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-16 | 2026-06-23 21:18 | 2026-05-10 | 2026-05-17 16:17 | Site is RTMI | 2026-04-07 | 2026-04-14 15:58 | 842673 | 151681 | 0 | 0 | 861607.221 | 142267 | 861607.221 | 142267 | 2026-06-14 18:37:25 +0530 | Priyanka R | Some Image was uploaded | 2026-05-19 12:13:23 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-10 10:49:55 +0530 | Priyanka R | Some Image was uploaded | 2026-05-18 | 2026-05-17 16:53 | 2026-06-01 | 2026-05-31 16:57 | RTMI
19341 | Turnkey | 2026-01-01 | Vignesh | Devagiri Opal | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Mohammed Rasick |  | Active | Preproduction | Site Readiness 1 | 962822 | 192564 | 1175018 | 0 | 0 | 2 | 65 | 0 | 0 | 385129 | 385128.8 |  |  | 2026-04-05 | 2026-04-11 19:45 | 2026-04-07 | 2026-04-12 14:27 | 2026-04-15 | 2026-04-14 11:41 | 2026-05-10 | 2026-05-09 18:52 | 2026-07-21 |  | 2026-07-28 |  | 2026-04-15 | 2026-04-13 20:07 | 2026-04-16 | 2026-04-14 11:25 | 2026-04-15 | 2026-04-14 13:52 | 2026-04-16 | 2026-04-16 11:27 |  |  |  |  | 2026-05-09 | 2026-05-09 19:03 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-04-17 | 2026-05-09 18:13 | Site is Non-RTMI | 2026-04-05 | 2026-04-07 17:05 | 995778 | 179240 | 0 | 0 | 0 | 0 | 987462.25 | 170398 | 2026-07-12 16:58:26 +0530 | Parasa Sri |  | 2026-05-09 18:57:34 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 09/05/2026 Title: DEM 1 Project: 19341 Client: Vignesh Attendees: Designer & Client Objective: DEM 1 Discussion Based on 09/05/2026 meeting, below is a list of all the requirements that were discussed during the meeting: 19341 - Vignesh Living area & Dining Area- 1. Tv back panel with 1 side curved edges and rafters on the back- according to design and eliminants add on cost will added 2. tv base unit with center glass shutter and both the side units are flap down shutter 3. as mentioned, CX is having Existing Pooja unit so giving 3'6" space for pooja unit and placing the crockery unit- accordingly crockery unit width we have increased (cost may vary accordingly) 4. No sofa back panel design is considered 5. No false ceiling 6. Electrical Shifting and creation cost is not considered- as discussed once the cross measurement is done, then we get a accurate costingÂ 7. Dining Table we have considered 4 seater (Existing one) 8. as CX mentioned, They are going with Jula in between dining & Living area, Scope client scope 9. Door paneling was considered in initial estimate, as per initial measurement, size got changes accordingly price may vary Kitchen & Utility 1. as we discussed, due to measurement of appliances and few existing items, kitchen layout has to re discuss once the accurate measurement gets 2. dishwasher, and 2 washing machine are planned to keep in utility 3. wall unit and loft in utility are will be similarÂ 4. fridge we are planning to keep in dining area Master Bedroom 1. wardrobe size got decreased as there is not sufficient space 2. Loft has to confirm from CX side,due to ac placement 3. Study table removed 4. No wall paneling is considered 5. King size bed has to be considered- CX scope 6. No False ceilingÂ Bedroom 2 1. Wardrobe no changes 2. Loft has to be consider end to end 3. dresser & Study table has removed 4. Existing wardrobe has to place at the corner Bedroom 3 1. Wardrobe has got size decresed, due to electrical point placement 2. side of the wardrobe has to place base shutter and wall unit has to consider 3. Loft has to consider end to end 4. planning to place Sofa come bed - CX scope | 2026-05-09 15:03:26 +0530 | Parasa Sri | Client is not available next week and will be available for DEM-2 on 23rd. Furniture - Windows to Wonderful Home - rasik has given a word for cash discount or voucher. | 2026-05-10 | 2026-05-09 18:55 | 2026-07-22 |  | Under Construction | 2026-05-01
19344 | Turnkey | 2026-01-01 | Videeta ahalpara | Kalpataru Vienta | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2904730 | 9999 | 0 | 0 | 0 | 93 | 0 | 280474 | 290473 | 1260619 | 1063165.2 |  |  | 2026-04-05 | 2026-04-11 12:32 | 2026-04-11 | 2026-04-11 15:02 | 2026-04-20 |  | 2026-04-27 |  | 2026-05-04 |  | 2026-05-11 |  | 2026-04-20 |  | 2026-04-21 |  | 2026-04-21 |  | 2026-04-22 | [5 empty] | 2026-04-28 |  | 2026-05-06 |  | 2026-05-07 |  |  |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 | [6 empty] | 2026-06-04 |  | 2026-06-13 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-16 |  |  |  | 2026-07-08 |  | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-05-15 |  | 2026-04-23 |  | Unknown | 2026-04-05 | 2026-04-11 12:32 | 0 | 0 | 0 | 0 | 0 | 0 | 2461636 | 443094 | 2026-04-15 18:41:38 +0530 | Manasi Patil | Some Image was uploaded | 2026-04-11 14:42:29 +0530 | Yash Jain | DCM: possession in 15 days 3bhk - 1075 incl balconyÂ family of 5 ppl Living roomÂ Ent lobby tall shoe rack after door kitchenÂ Â washing machine in common bathroom double door fridge in the niche storage on both sides, chimney , tambour unit for appliances. wicker basket for potato/ onion / storageÂ Â / dryer inÂ utilityÂ pelmet for ac's living room area Sofa seating - sofa cum bed l or 3 seater - shaped formatÂ no tv unitÂ temple with seating. 2 seater jhula in balcony area dining table 6 seater crockery unit full length , platform,Â entry console unit to keep keys, children's bedroom -Â wardrobe - Slide 2 layer bed , study table with storage,Â top right ( cx room ) qsb , 2 side table, wardrobes, swing wardrobes, loft units, bed hydraulic bed,dressing mirror full height , tall unit after doorÂ bathroom ,Â wide mirror in all bathrooms , partition glass, vanity units bottom right ( parent's room ) qsb , no side table, wardrobes, swing wardrobes, loft units, bed hydraulic bed,dressing mirror full height , headboard k piche 4-5'' space.Â door relamination. Budget - japandi , timeless Â Â Â |  |  |  | 2026-04-28 |  | 2026-05-05
19345 | Turnkey | 2026-01-01 | Faiyaz Chunawala | Transcon Triumph | MUM - GOR | Yes | Saakshi Bhute | Manzoor Shaikh | Kashmira Nerurkar |  |  | Uday Yadruk | Rizwan Mistry |  | Manasi Patil | Sunil Poojary | Active | Preproduction | DEM2 | 1055819 | 211164 | 1394183 | 0 | 0 | 1 | 19 | 0 | 0 | 481571 | 363084.4 |  |  | 2026-04-06 | 2026-05-01 17:16 | 2026-04-22 | 2026-05-01 21:38 | 2026-05-03 | 2026-05-03 13:27 | 2026-05-12 | 2026-05-09 20:37 | 2026-07-01 | 2026-06-30 17:23 | 2026-07-16 |  | 2026-05-03 | 2026-05-04 11:42 | 2026-05-04 | 2026-05-05 13:32 | 2026-05-05 | 2026-05-06 10:50 | 2026-05-07 | 2026-05-07 14:01 |  |  |  |  | 2026-05-09 | 2026-06-19 11:13 | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-05-08 | 2026-05-09 20:30 | Site is RTMI | 2026-04-06 | 2026-05-01 17:15 | 1181511 | 212672 | 0 | 0 | 0 | 0 | 1177575.0548 | 198811 | 2026-05-22 18:19:30 +0530 | Manzoor Shaikh | Dear Mr. Faiyaz Chunawala, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 1 meeting for 24th May at 04:00 PM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Saakshi will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-05-08 10:47:04 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-07 15:21:33 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-10 | 2026-05-09 20:38 | 2026-07-01 | 2026-06-30 17:24
19346 | Turnkey | 2026-01-01 | Heena Raj | Raj heritage, mira road | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Akash Jadhav | Sandeep Tiwari | Murali S | Manasi Patil | Aakash Gaikwad | Active | Production | Dispatch Due | 1009404 | 1009415 | 1275140 | 0 | 1060613 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-02 | 2026-04-09 11:31 | 2026-04-07 | 2026-04-11 11:34 | 2026-04-11 | 2026-04-11 12:08 | 2026-04-26 | 2026-04-24 12:22 | 2026-05-23 | 2026-05-22 20:22 | 2026-05-27 | 2026-05-27 12:44 | 2026-04-11 | 2026-04-11 17:42 | 2026-04-12 | 2026-04-13 13:31 | 2026-04-13 | 2026-04-13 16:49 | 2026-04-18 | 2026-04-18 18:56 |  |  |  |  | 2026-04-24 | 2026-04-25 14:40 | 2026-05-24 | 2026-05-24 13:17 | 2026-05-25 | 2026-05-24 18:07 |  |  | 2026-06-03 | 2026-06-04 18:06 | 2026-06-12 | 2026-06-12 19:39 | 2026-06-13 | 2026-06-12 22:05 | 2026-06-13 | 2026-06-15 18:10 |  |  |  |  | 2026-06-19 11:29 | 2026-07-01 | 2026-06-30 20:06 | 2026-07-12 | 2026-07-10 18:36 | 2026-07-11 | 2026-07-11 13:11 | 2026-07-10 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-08-13 | [5 empty] | 2026-06-12 | 2026-06-19 11:28 | 2026-04-19 | 2026-04-22 16:36 | Site is RTMI | 2026-04-02 | 2026-04-08 17:10 | 1082914 | 192225 | 0 | 0 | 1170893.8647 | 193441 | 1173293.2647 | 185629 | 2026-06-13 15:18:13 +0530 | Avinash Jaiswal | Added Free Hob & Chimney Offer Instead of Free Bed | 2026-06-03 16:58:00 +0530 | Manisha Dubey | Some Image was uploaded | 2026-06-03 16:54:31 +0530 | Manisha Dubey | Others: | 2026-04-25 | 2026-04-24 12:35 | 2026-05-23 | 2026-05-23 15:00
19347 | Turnkey | 2026-01-01 | Swapnil Srivastava | SSVR Niyaara | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 1305501 | 170151 | 1665324 | 0 | 0 | 49 | 0 | 0 | 90949 | 550515 | 493886 |  |  | 2026-04-04 | 2026-04-08 17:31 | 2026-05-19 | 2026-05-19 10:29 | 2026-05-22 | 2026-05-19 12:43 | 2026-06-28 | 2026-06-28 19:39 | 2026-07-21 |  | 2026-07-28 |  | 2026-05-19 | 2026-05-19 13:32 | 2026-05-20 | 2026-05-22 18:17 | 2026-05-22 | 2026-05-27 18:34 | 2026-06-06 | 2026-06-06 17:32 |  |  |  |  | 2026-07-05 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-06-07 | 2026-06-24 15:50 | Site is RTMI | 2026-04-04 | 2026-04-08 17:19 | 1411291 | 254032 | 0 | 0 | 0 | 0 | 1464749.7604 | 241856 | 2026-06-14 19:00:55 +0530 | Sayed Byahatti | DDM1: Swapnil S - 19347 14-06-2026 6:00PM POOJA UNIT -TO BE DESIGNED FULL LENGTH AS SHARED REFERENCE. ABOVE CROCKRY UNIT ADD MORE STORAGE. ALL ROOM WALL CONCEPTS TO BE REWORK ALL BATHROOMS DESINER MIRROR TO ADD. POP FALL CEILING DESIGN IS BONITO SCOPE. PAINTING IS IN BONITO SCOPE. | 2026-06-12 12:07:14 +0530 | Sayed Byahatti | Minutes of Meeting held on Date: KT Crockery unitÂ Â all glass one Tv unit add tall unit and share some reference Master bedroom- ovel shape glassÂ wall concept also ( balcony design to reference)Â Kids room - wardrobe with glass shutter standard decent wall concept Wall mounted pooja unit 3rd room - pooja unit either here or some other good place.Â Living room peripheral fall ceiling design, all bedroom fall ceiling design profile light.Â Share some reference also. | 2026-06-10 19:05:34 +0530 | Sayed Byahatti | DDM1: Swapnil KT Â 10-06-2026 6:00PM Dining Area - Crockery unit all glass shutters. Tv Unit - Add tall unit and share some reference IN Group. Master Bedroom - Ovel shape glass, Wall concept have to add. ( Add Balcony design to reference are share)Â Kids Room - Wardrobe with mirror shutter standard decent wall concept Wall mounted Pooja unit 3rd room -Pooja unit either here or some other good place.Â Living Room - Peripheral fall ceiling design, all bedroom fall ceiling design profile light.Â Have Share some reference also. | 2026-07-05 |  | 2026-07-22 |  | Under Construction | 2026-06-06
19349 | Turnkey | 2026-01-01 | Mr Prashanth | Pride Vatika - Gated Community Project | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | [6 empty] | Vishwa Hiremath | Active | Preproduction | CM | 1025398 | 209999 | 2468084 | 0 | 0 | 6 | 5 | 0 | 0 | 405240 | 410159.2 |  |  | 2026-04-07 | 2026-04-22 13:08 | 2026-05-19 | 2026-05-19 12:16 | 2026-05-19 | 2026-05-19 12:56 | 2026-05-30 | 2026-05-27 19:55 | 2026-07-10 | 2026-07-09 16:25 | 2026-08-22 |  | 2026-05-19 | 2026-05-19 13:24 | 2026-05-20 | 2026-05-19 13:58 | 2026-04-13 | 2026-05-19 15:46 | 2026-05-25 | 2026-05-25 19:07 |  |  |  |  | 2026-06-10 | 2026-07-09 15:24 | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-08-26 |  | 2026-05-27 | 2026-05-27 19:50 | Site is RTMI | 2026-04-07 | 2026-04-13 15:27 | 2091596 | 376487 | 0 | 0 | 0 | 0 | 1090536.857 | 180073 | 2026-06-11 17:02:54 +0530 | Shivani Shet | Some Image was uploaded | 2026-05-29 16:42:32 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-25 19:08:41 +0530 | Rajeshwari S | Welcome call done Client wanted one online meeting with designer once the layout is finalized, project will go on hold Site is ready for IM anytime it can be taken She wants prior information in the group. | 2026-05-28 | 2026-05-27 19:58 | 2026-07-10 | 2026-07-09 18:42 | Under Construction | 2026-06-30
19350 | Turnkey | 2026-01-01 | debanjana ghosh | Ecolife Eon Akash | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1385911 | 9999 | 1385911 | 0 | 0 | 85 | 0 | 128592 | 138591 | 554364 | 554364.4 |  |  | 2026-04-08 | 2026-04-12 12:35 | 2026-04-08 | 2026-04-18 16:43 | 2026-04-21 | 2026-04-22 12:48 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-08 | 2026-04-08 16:00 | 1174501 | 211410 | 0 | 0 | 0 | 0 | 1174501 | 211410 | 2026-04-18 16:42:33 +0530 | Priyanka Gs | Family of 2Â LivingÂ TV unit - tall unit ,Â wall conceptÂ peripheral ceilingÂ Â Â Bedroom 2Â Pooja , study and wardrobeÂ A sofa cum bedÂ planning for a projectorÂ DiningÂ 6 seater DiningÂ Crockery unit - F/CÂ Kitchen & UtilityÂ Wall & Janitor unit for utilityÂ Kitchen tall unit- MicrowaveÂ 3'StoveÂ A bigger sink in kitchen itselfÂ Â Refrigerator - 1000mmÂ RO - Top mountÂ Breakfast counterÂ Corner unitÂ Cylinder unitÂ BPO wicker basketÂ LoftÂ an adj tall unit next to the fridgeÂ BFC - With storage Beam panelÂ Master BedroomÂ Wardrobe + Loft - 8'Â used cloth storageÂ Wall concept - CurvedÂ False ceilingÂ | [6 empty] | 2026-04-30 |  | 2026-05-07
19353 | Turnkey | 2026-01-01 | Sam prabhu | Bianca | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 2722646 | 9999 | 0 | 0 | 0 | 96 | 0 | 262266 | 272265 | 1215143 | 962973.6 |  |  | 2026-04-08 | 2026-04-10 16:50 | 2026-04-08 | 2026-04-10 16:54 | 2026-04-08 |  | 2026-04-20 |  | 2026-04-27 |  | 2026-05-04 |  | 2026-04-13 |  | 2026-04-14 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | 2026-04-21 |  | 2026-04-29 |  | 2026-04-30 |  |  |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 | [6 empty] | 2026-05-28 |  | 2026-06-06 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-09 |  |  |  | 2026-07-01 |  | 2026-07-03 |  | 2026-07-04 | [5 empty] | 2026-05-08 |  | 2026-04-16 |  | Unknown | 2026-04-08 | 2026-04-10 16:49 | 0 | 0 | 0 | 0 | 0 | 0 | 2310453 | 412193 | [9 empty] | 2026-04-21 |  | 2026-04-28
19354 | Turnkey | 2026-01-01 | Nayana Shah | Raheja | MUM - GOR | No Estimate | [8 empty] | Ashish Jha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-08 | 2026-04-09 16:40 | 2026-04-09 | 2026-04-09 18:12 | 2026-04-11 |  | 2026-04-19 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-04-12 |  | 2026-04-13 |  | 2026-04-13 |  | 2026-04-14 | [5 empty] | 2026-04-20 |  | 2026-04-28 |  | 2026-04-29 |  |  |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-09 | [6 empty] | 2026-05-27 |  | 2026-06-05 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-08 |  |  |  | 2026-06-30 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-05-07 |  | 2026-04-15 |  | Unknown | 2026-04-08 | 2026-04-09 16:37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-15 13:43:25 +0530 | Ashish Jha | Some Image was uploaded | [6 empty] | 2026-04-20 |  | 2026-04-27
19360 | Turnkey | 2026-01-01 | Vinay Mahajan |  | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Akshat Shrivastava | Murali S | Anant Giri | Shailendra Mishra | Active | Installation | Execution | 907691 | 907691 | 1401933 | 0 | 907691 | 2 | 15 | 0 | 0 | 0 | 0 |  |  | 2026-04-09 | 2026-04-09 15:53 | 2026-04-09 | 2026-04-10 13:25 | 2026-04-16 | 2026-04-17 11:22 | 2026-04-26 | 2026-04-26 18:51 | 2026-05-08 | 2026-05-07 12:01 | 2026-05-14 | 2026-05-14 19:55 | 2026-04-17 | 2026-04-17 18:10 | 2026-04-18 | 2026-04-17 19:18 | 2026-04-17 | 2026-04-20 13:03 | 2026-04-23 | 2026-04-23 11:50 |  |  |  |  | 2026-05-01 | 2026-04-24 17:52 | 2026-06-20 | 2026-05-07 20:13 | 2026-05-08 | 2026-05-07 20:14 |  |  | 2026-05-16 | 2026-05-22 15:24 | 2026-05-22 | 2026-05-22 19:03 | 2026-05-23 | 2026-05-23 08:50 | 2026-05-24 | 2026-05-25 13:00 |  |  |  |  | 2026-05-26 22:37 | 2026-06-03 | 2026-06-03 22:01 | 2026-06-13 | 2026-06-11 18:41 | 2026-06-12 | 2026-07-04 13:32 | 2026-07-05 | 2026-07-13 12:38 | 2026-07-13 | 2026-07-13 15:35 | 2026-07-15 |  |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-05-22 | 2026-05-26 22:36 | 2026-04-26 | 2026-04-26 18:16 | Site is RTMI | 2026-04-09 | 2026-04-09 15:52 | 1188079 | 213854 | 0 | 0 | 1063155.7826 | 175534 | 1063155.7826 | 175534 | 2026-07-12 13:48:53 +0530 | Faraz Soudagar | Dispatch Due: Material is in transit Modular delivery ETA - 14th July | 2026-06-19 13:30:00 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-01 15:19:27 +0530 | Faraz Soudagar | Execution: PI work - Only floor covering. | 2026-04-27 | 2026-04-26 19:01 | 2026-05-08 | 2026-05-07 12:11
19361 | Turnkey | 2026-01-01 | Prakash Bhartiya | Binary Temple Tree | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 2823793 | 9999 | 0 | 0 | 0 | 97 | 0 | 272380 | 282379 | 1218013 | 1041021.6 |  |  | 2026-04-09 | 2026-04-09 16:12 | 2026-04-12 |  | 2026-04-15 |  | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-04-15 |  | 2026-04-16 |  | 2026-04-16 |  | 2026-04-17 | [5 empty] | 2026-04-23 |  | 2026-05-01 |  | 2026-05-02 |  |  |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 | [6 empty] | 2026-05-30 |  | 2026-06-08 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-11 |  |  |  | 2026-07-03 |  | 2026-07-05 |  | 2026-07-06 | [5 empty] | 2026-05-10 |  | 2026-04-18 |  | Unknown | 2026-04-09 | 2026-04-09 16:11 | 0 | 0 | 0 | 0 | 0 | 0 | 2402142 | 421651 | 2026-04-23 10:45:35 +0530 | Patil Madhavi | Some Image was uploaded | 2026-04-12 12:19:05 +0530 | Maspi Das | Cx name : Prakash & NehaÂ (from UP) Address: Binary Temple tree 3BHK APT Prof : IT and house wife How many people will be staying- Total 4 (including 1 son) Theme : MinimalÂ Entrance facing : East facingÂ Budget - 10L to 12L Foyer - Shoe rack behind the doorÂ Wall trims for the long wall Living - Seating and TV arrangement rotatedÂ Pooja unit on the right side of tv unitÂ TV unit with marble laminate and one tall unit in other end and base unitÂ Seating - one L shape and 2 arm chairsÂ Need trims behind sofa wall Dining - Dining table of 4 seaterÂ 1 vanity unit with 1 tall glass shutter for crockeryÂ Common vanity wall need photo from or wall trimsÂ Kitchen - one side opening fridge - on the corner towards the utilityÂ Tall provision only for ovenÂ Granite counter top have to be consideredÂ single bowl sink without drain in corner HOB and Hood on window wall ( window is in centre not in corner as shown in plan) Base,wall cabinets and loft on one sideÂ Utility - Sink unit with 2 bowlsÂ MBR - Planning to retain 1 study table so will share the image, consider this in 3D (on bathroom wall) Full wardrobe with loft and dresser unit coming in the right corner with mirrorÂ and storageÂ Wall trims on bed wallÂ All bathrooms - Base unit for vanity and mirrorÂ KBR (Pransh 3yo) Queen size bed for 3DÂ WARDROBE WITH LOFTÂ Study table ( if possible consider the seating with storage) try using the open niche on both sidesÂ THEME - MarvelÂ Wall trims on bed wall PBR (Shakuntala) Wardrobe wit loftÂ Dresser need on bed wall with tall unit with storageÂ Wall trims on bed wall |  |  |  | 2026-04-23 |  | 2026-04-30
19364 | Turnkey | 2026-01-01 | Lovekeshwar Ranga | Aspen Greens @ The Prestige City | BNG - HSR | Yes | Preethi Shetty | Akshay Ds | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 2040630 | 168235 | 1682349 | 0 | 0 | 81 | 0 | 0 | 239891 | 857476 | 775028.4 |  |  | 2026-04-09 | 2026-04-09 16:27 | 2026-04-14 | 2026-04-14 18:37 | 2026-04-17 | 2026-04-14 19:48 | 2026-09-01 |  | 2026-09-08 |  | 2026-09-15 |  | 2026-04-14 | 2026-04-22 11:17 | 2026-04-15 | 2026-04-22 11:37 | 2026-04-22 | 2026-04-25 16:17 | 2026-05-06 | 2026-05-06 16:53 |  |  |  |  | 2026-09-02 |  | 2026-09-10 |  | 2026-09-11 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 | [6 empty] | 2026-10-09 |  | 2026-10-18 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-21 |  |  |  | 2026-11-12 |  | 2026-11-14 |  | 2026-11-15 | [5 empty] | 2026-09-19 |  | 2026-05-07 | 2026-06-16 10:54 | Site is RTMI | 2026-04-09 | 2026-04-09 16:26 | 1425719 | 256629 | 0 | 0 | 0 | 0 | 2268154.0366 | 374587 | 2026-06-17 11:41:55 +0530 | Preethi Shetty | We have discussed on Master Bedroom, Kids Bedroom & Kitchen. KBR - The layout has been finalised, need to check for switch board shifting MBR - layout has been finalised, Bed Back wall need to add mirror patti in the corners and dresser area bottom units to be with solid shutters with t-patti designs. Kitchen - Tall unit to be shifted on to the opposite wall & microwave placement to be given on the top. Chimney hole to be checked on site | 2026-06-11 17:37:00 +0530 | Preethi Shetty | We have scheduled a design discussion today at 5 pm | 2026-06-11 17:36:36 +0530 | Preethi Shetty | DDM -1 Foyer - Entrance wall with wallpaper textured & T- patti , in centre with mirror provision (either in U shape) Dining area - bottom storage unit, stand alone ,Â 5-6ft ,Â Note sll storage unit to be curved in TV unit, dining storages Utility - washing machine & dishwasher KBR - wall designs to be shared, with seating, pin board or white boards, laq. glass study table loose furniture Dresser to be added All bedrooms - sliding wardrobesÂ wall designs - redesign as per ref. images KBR - OPEN UNIT WITH MS FAB. BESIDE WARDROBEÂ Study unit wall cabinets - with curved shape designs seating storage with tall open unit on corner MBR -Â Dresser storage position changes,Â Both sides storage with middle mirror | 2026-09-02 |  | 2026-09-09 |  | Under Construction | 2026-05-10
19365 | Turnkey | 2026-01-01 | Dasan (Parasite Engineering) Rajan | Mahindra Alcove | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Uday Yadruk | Rizwan Mistry | Murali S | Moni Sahani | Aakash Gaikwad | Active | Production | Production | 1312923 | 1312923 | 1479224 | 0 | 1347626 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-09 | 2026-04-17 16:24 | 2026-04-09 | 2026-04-17 18:11 | 2026-04-20 | 2026-04-17 18:12 | 2026-04-28 | 2026-04-28 20:14 | 2026-05-22 | 2026-05-21 19:45 | 2026-05-24 | 2026-05-24 19:03 | 2026-04-17 | 2026-04-17 18:25 | 2026-04-18 | 2026-04-18 14:26 | 2026-04-18 | 2026-04-20 14:23 | 2026-04-22 | 2026-04-22 16:53 |  |  |  |  | 2026-04-28 | 2026-04-30 18:30 | 2026-05-22 | 2026-05-21 20:27 | 2026-05-22 | 2026-05-23 12:33 |  |  | 2026-05-27 | 2026-05-30 16:46 | 2026-05-31 | 2026-05-31 18:32 | 2026-06-01 | 2026-05-31 19:29 | 2026-06-01 | 2026-06-03 18:08 |  |  |  |  | 2026-06-05 13:04 | 2026-07-01 | 2026-06-30 20:08 | 2026-07-09 |  | 2026-07-08 | 2026-07-10 13:46 | 2026-07-09 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-05-31 | 2026-06-05 13:03 | 2026-04-23 | 2026-04-28 19:58 | Site is RTMI | 2026-04-09 | 2026-04-09 17:18 | 1253579 | 225644 | 0 | 0 | 1423034.6604 | 239129 | 1423035.141 | 233835 | 2026-05-31 19:27:34 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-31 13:55:42 +0530 | Priyanka Kamble | Some Image was uploaded | 2026-05-06 14:15:29 +0530 | Shantanu Parakh | Some Image was uploaded | 2026-04-29 | 2026-04-28 20:30 | 2026-05-22 | 2026-05-21 19:45 | RTMI
19368 | Turnkey | 2026-01-01 | Gaurav Waghela | praful jyotu | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | 10% Payment | 1133017 | 9999 | 1578325 | 0 | 0 | 92 | 0 | 103303 | 113302 | 490939 | 415474.4 |  |  | 2026-04-09 | 2026-04-10 11:40 | 2026-04-09 | 2026-04-10 12:19 | 2026-04-14 | 2026-04-14 13:45 | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-04-22 |  | 2026-04-30 |  | 2026-05-01 |  |  |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 | [6 empty] | 2026-05-29 |  | 2026-06-07 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-10 |  |  |  | 2026-07-02 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-05-09 |  | 2026-04-17 |  | Site is RTMI | 2026-04-09 | 2026-04-09 19:05 | 1339851 | 238474 | 0 | 0 | 0 | 0 | 1338525.9 | 212876 | 2026-04-30 20:19:16 +0530 | Meet Shah | Some Image was uploaded | 2026-04-15 16:56:38 +0530 | Umang Shah | Some Image was uploaded | 2026-04-10 11:40:32 +0530 | Rishika Malviya | Some Image was uploaded | 2026-04-22 |  | 2026-04-29
19369 | Sub Project |  | Cllaro Enterprises LLP | Urban Grandeur | MUM - Thane |  | Nazneen Chovvakkaran | Anamika Dolai | Rushika More |  |  | Faraz Soudagar | Aditya Vikram | Murali S |  |  | Active | Production | 100% Payment | 100400 | 0 | 0 | 0 | 100400 | 95 | 0 | 0 | 0 | 0 | 100400 |  |  | 2026-04-09 | 2026-04-10 11:07 | 2026-04-10 | 2026-04-10 11:07 | 2026-04-10 | 2026-04-10 11:08 | 2026-04-11 | 2026-04-10 11:09 | 2026-04-11 | 2026-04-10 11:10 | 2026-04-11 | 2026-04-10 11:12 | 2026-04-10 | 2026-04-10 11:08 | 2026-04-11 | 2026-04-10 11:08 | 2026-04-10 | 2026-04-10 11:08 | 2026-04-11 | 2026-04-10 11:09 |  |  |  |  | 2026-04-10 | 2026-04-10 11:09 | 2026-04-11 | 2026-04-10 11:11 | 2026-04-11 | 2026-04-10 11:11 |  |  | 2026-04-11 | 2026-04-10 11:12 | 2026-04-11 | 2026-04-10 12:07 | 2026-04-11 | 2026-04-10 12:17 | 2026-04-11 | 2026-04-10 12:18 |  |  |  |  | 2026-04-10 12:58 | 2026-04-12 | 2026-04-11 14:16 | 2026-04-13 | 2026-04-11 14:43 | 2026-04-12 |  | 2026-04-11 |  | 2026-04-25 |  | 2026-04-27 |  |  |  | 2026-05-04 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | 2026-04-10 | 2026-04-10 12:19 | 2026-04-11 | 2026-04-10 11:09 | Unknown | 2026-04-09 | 2026-04-10 11:07 | 0 | 0 | 0 | 0 | 85084 | 15315 | 85084 | 15315 | [9 empty] | 2026-04-11 | 2026-04-10 11:09 | 2026-04-11 | 2026-04-10 11:10
19373 | Turnkey | 2026-01-01 | Rahin Raj | NR Prime residency | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Shashank Singh |  | Hold | Preproduction | DEM2 | 1084110 | 155999 | 971156 | 0 | 0 | 3 | 64 | 0 | 0 | 512798 | 415312.8 |  |  | 2026-04-09 | 2026-04-10 12:20 | 2026-04-11 | 2026-04-11 11:27 | 2026-04-15 | 2026-04-15 13:38 | 2026-05-09 | 2026-05-09 18:35 | 2026-08-21 |  | 2026-08-28 |  | 2026-04-15 | 2026-04-15 19:13 | 2026-04-16 | 2026-04-17 19:41 | 2026-04-17 | 2026-04-24 17:12 | 2026-04-30 | 2026-04-30 19:31 |  |  |  |  | 2026-05-09 | 2026-05-09 19:21 | 2026-08-23 |  | 2026-08-24 |  |  |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 | [6 empty] | 2026-09-21 |  | 2026-09-30 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-03 |  |  |  | 2026-10-25 |  | 2026-10-27 |  | 2026-10-28 | [5 empty] | 2026-09-01 |  | 2026-05-01 | 2026-05-09 18:19 | Site is RTMI | 2026-04-09 | 2026-04-10 12:15 | 823014 | 148142 | 0 | 0 | 0 | 0 | 1149351.9433 | 189779 | 2026-06-25 19:02:43 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-26 18:59:24 +0530 | Shivani Shet | DDM2: 23 May 19373 - Rahin Raj 2nd meeting MOM Living Room / TV UnitÂ Â Â Â Â Â Pooja unit with CNC design Â Â Â Â Â Â Pooja unit with drawer and rest flap down Â Â Â Â Â Â Crockery unit with fluted glass and open unit to be changed to Fluted glass shutter Â Â Â Â Â Â Beveled mirror leaf design Â Â Â Â Â Â Hidden door fluted panel KitchenÂ Â Â Â Â Â Add open unit and reduced wall unit height adding contrast color Master Bedroom (MBR)Â Â Â Â Â Â Dresser unit added with curved sides Needs to be checked Â Â Â Â Â Â Storage for study table with drawer and shutter Â Guest Bedroom (GBR)Â Â Â Â Â Â dresser unit with curved sides Needs to be checked Â Â Â Â Â Â Â | 2026-05-21 17:33:04 +0530 | Shivani Shet | DDM1: 19373 - Rahin Raj MOM Living Room / TV UnitÂ Â Â Â Â Â Pooja unit with CNC design Â Â Â Â Â Â Pooja unit touching the floor KitchenÂ Â Â Â Â Â L shape kitchen to be considered Â Â Â Â Â Â Loft l shape on left side Â Â Â Â Â Â Cylinder space is considered blind corner Â Â Â Â Â Â No breakfast counter Â Â Â Â Â Â Only fridge and tall unit on right side Â Â Â Â Â Â Utility Only washing machine Â Â Â Â Â Â Door paneling with light Â Â Â Â Â Â Existing Stove 750mm Â Â Â Â Â Â Chimney 750mm Â Â Â Â Â Â Existing ro new Living areaÂ Â Â Â Â Â Crockery unit to be added Â Â Â Â Â Â Hidden wall concept near the bathroom Â Â Â Â Â Â Vanity unit with metal fabrication Master Bedroom (MBR)Â Â Â Â Â Â Fluted panel with wallpaper Â Â Â Â Â Â Storage for study table with drawer and shutter Â Â Â Â Â Â Plan for dresser unit Â Guest Bedroom (GBR)Â Â Â Â Â Â Plan for dresser unit Â Â Â Â Â Â Wallpaper to be considered All BathroomÂ Â Â Â Â Â Descoped Â Â Â Â Â Â | 2026-05-10 | 2026-05-09 18:38 | 2026-08-22 |  | RTMI
19374 | Turnkey | 2026-01-01 | Thomas and Jolly | Prestige Eden Parl | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Priyanka Mathur |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Muralikrishna Udupi | Affaan Abdulla | Active | Installation | Execution | 767458 | 767460 | 1194215 | 0 | 827458 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-09 | 2026-04-14 11:10 | 2026-04-14 | 2026-04-14 13:20 | 2026-04-17 | 2026-04-14 13:34 | 2026-04-25 | 2026-04-25 16:38 | 2026-05-05 | 2026-05-04 18:49 | 2026-05-14 | 2026-05-15 17:52 | 2026-04-14 | 2026-04-14 18:04 | 2026-04-15 | 2026-04-15 12:36 | 2026-04-15 | 2026-04-17 14:25 | 2026-04-18 | 2026-04-18 17:45 |  |  |  |  | 2026-04-25 | 2026-04-29 13:46 | 2026-05-05 | 2026-05-10 00:27 | 2026-05-11 | 2026-05-10 00:28 |  |  | 2026-05-19 | 2026-05-24 18:12 | 2026-05-24 | 2026-05-24 19:20 | 2026-05-25 | 2026-05-24 21:34 | 2026-05-25 | 2026-05-26 11:37 |  |  |  |  | 2026-05-28 19:01 | 2026-06-05 | 2026-06-04 21:20 | 2026-06-12 | 2026-06-11 12:29 | 2026-06-05 | 2026-06-20 19:03 | 2026-06-11 | 2026-06-23 18:55 | 2026-06-23 | 2026-06-24 11:06 | 2026-07-03 | 2026-07-02 13:08 |  |  | 2026-07-24 |  | 2026-07-13 |  | 2026-07-24 | [5 empty] | 2026-05-24 | 2026-05-28 19:00 | 2026-04-19 | 2026-04-25 16:28 | Site is RTMI | 2026-04-09 | 2026-04-14 10:41 | 1012047 | 182168 | 0 | 0 | 949232.6493 | 156731 | 949232.6493 | 156731 | 2026-06-24 15:49:09 +0530 | Ranjith Kumar | Execution: | 2026-06-22 21:00:44 +0530 | Ranjith Kumar | Dispatch Due: | 2026-06-19 10:42:17 +0530 | Ranjith Kumar | Cx Side Electrical - Delayed, Cx Also Started Painting - 22/Jun Bonito Side Floor Covering & False Ceiling | 2026-04-26 | 2026-04-25 16:38 | 2026-05-05 | 2026-05-04 18:49 | RTMI
19375 | Turnkey | 2026-01-01 | Surjeet Haldar | Sheetal Regalia | MUM - GOR | Yes | Riddhi Deshpande | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Moni Sahani |  | Active | Design | DEM1 | 1293941 | 158284 | 1583587 | 0 | 0 | 37 | 0 | 0 | 100504 | 557536 | 477616.8 |  |  | 2026-04-05 | 2026-04-10 15:25 | 2026-05-03 | 2026-05-03 15:00 | 2026-05-13 | 2026-05-13 18:17 | 2026-08-04 |  | 2026-08-11 |  | 2026-08-18 |  | 2026-05-13 | 2026-05-14 10:44 | 2026-05-14 | 2026-05-19 13:20 | 2026-05-19 | 2026-06-08 11:14 | 2026-06-12 | 2026-06-12 18:49 |  |  |  |  | 2026-08-05 |  | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-07-31 |  | Unknown | 2026-04-05 | 2026-04-10 15:24 | 1344310 | 239276 | 0 | 0 | 0 | 0 | 1340726.2665 | 228652 | 2026-07-10 13:24:12 +0530 | Vishakha Vaishnav | Others: DEM 1 IS ALIGNED FOR 18TH JULY 3P | 2026-06-18 12:42:28 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 18:48:39 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to align DEM Dates -Â DEM 1 - Can be done on next saturday which is 20th June DEM 2 - TBD DEM 3 - TBD Possession date : Under construction Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-08-05 |  | 2026-08-12 |  | RTMI
19376 | Turnkey | 2026-01-01 | Dhara Munna Singh | Transcon Triumph | MUM - GOR | Yes | Karan Chavda | Vishakha Vaishnav | Safalta Karkera |  | Neha Singh |  |  |  | Moni Sahani |  | Hold | Design | DEM1 | 1233247 | 161102 | 1611870 | 0 | 0 | 1 | 40 | 0 | 85547 | 577093 | 409504.8 |  |  | 2026-04-04 | 2026-05-07 12:58 | 2026-05-07 | 2026-05-07 18:17 | 2026-05-13 | 2026-05-13 18:22 | 2026-07-20 |  | 2026-07-27 |  | 2026-08-03 |  | 2026-05-13 | 2026-05-20 11:21 | 2026-05-14 | 2026-05-27 18:10 | 2026-05-27 | 2026-06-04 15:06 | 2026-06-05 | 2026-06-05 17:17 |  |  |  |  | 2026-07-21 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-07-16 |  | Unknown | 2026-04-04 | 2026-04-10 15:43 | 1368090 | 243780 | 0 | 0 | 0 | 0 | 1352641.7378 | 219508 | 2026-06-05 17:22:21 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-05 17:16:46 +0530 | Vishakha Vaishnav | "Welcome call done: Initial measurement : Site is not accessible (Cx may recevie soft possession in few days) DEM Dates -Â DEM 1 - cx will inform us of now he is in dubai DEM 2 - TBD DEM 3 - TBD Possession date : June / July end Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-04 15:05:30 +0530 | Athul Ajaykumar | Concerns are addressed on call. Moving the OB | 2026-07-21 |  | 2026-07-28 |  | Under Construction | 2026-07-31
19377 | Turnkey | 2026-01-01 | Patrick Fernandes | Lake Enclave | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1049969 | 206569 | 1315029 | 0 | 0 | 2 | 80 | 0 | 0 | 434273 | 409127.2 |  |  | 2026-04-10 | 2026-04-12 11:32 | 2026-04-11 | 2026-04-14 13:09 | 2026-04-17 | 2026-04-14 13:13 | 2026-04-23 | 2026-04-23 13:30 | 2026-10-05 |  | 2026-10-12 |  | 2026-04-14 | 2026-04-14 19:25 | 2026-04-15 | 2026-04-15 11:15 | 2026-04-15 | 2026-04-15 16:47 | 2026-04-22 | 2026-04-22 19:49 |  |  |  |  | 2026-04-23 | 2026-04-24 19:01 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-06-08 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-04-23 | 2026-04-23 13:26 | Site is Non-RTMI | 2026-04-10 | 2026-04-11 17:39 | 1114431 | 200597 | 0 | 0 | 0 | 0 | 1104965.611 | 190673 | 2026-07-04 17:18:31 +0530 | Anil Jagtap | The client is expected to receive possession by the end of December. | 2026-06-12 14:41:55 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-31 19:04:20 +0530 | Parnavi Joshi | Some Image was uploaded | 2026-04-24 | 2026-04-23 13:35 | 2026-10-06
19378 | Sub Project |  | Viraj Nadkarni | Seth Zuri | MUM - Thane |  | Shraddha Pansare | Anamika Dolai | Sneha Kadam |  |  | Faraz Soudagar | Rizwan Mistry | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-10 | 2026-04-17 14:39 | 2026-04-11 | 2026-04-17 14:39 | 2026-04-17 | 2026-04-17 14:39 | 2026-04-18 | 2026-04-17 14:40 | 2026-04-18 | 2026-04-17 14:42 | 2026-04-18 | 2026-04-17 14:43 | 2026-04-17 | 2026-04-17 14:39 | 2026-04-18 | 2026-04-17 14:40 | 2026-04-17 | 2026-04-17 14:40 | 2026-04-18 | 2026-04-17 14:40 |  |  |  |  | 2026-04-17 | 2026-04-17 14:41 | 2026-04-18 | 2026-04-17 14:42 | 2026-04-18 | 2026-04-17 14:42 |  |  | 2026-04-18 | 2026-04-17 14:59 | 2026-04-17 | 2026-04-18 12:38 | 2026-04-19 | 2026-05-08 10:42 | 2026-05-09 | 2026-05-08 10:43 |  |  |  |  | 2026-06-09 12:45 | 2026-06-12 | 2026-06-11 21:07 | 2026-06-15 | 2026-06-13 12:18 | 2026-06-14 |  | 2026-06-13 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-04-18 | 2026-04-18 16:55 | 2026-04-18 | 2026-04-17 14:40 | Unknown | 2026-04-10 | 2026-04-17 14:39 | 0 | 0 | 0 | 0 | 27457.6271 | 0 | 27457.6271 | 0 | [9 empty] | 2026-04-18 | 2026-04-17 14:40 | 2026-04-18 | 2026-04-17 14:42
19382 | Turnkey | 2026-01-01 | Pradheep | Pelican Square Sarjapur | BNG - HSR | Yes | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 2298882 | 9999 | 2298882 | 0 | 0 | 83 | 0 | 219889 | 229888 | 919553 | 919552.8 |  |  | 2026-04-11 | 2026-04-11 13:03 | 2026-04-16 | 2026-04-16 15:07 | 2026-04-23 | 2026-04-23 15:03 | 2026-04-30 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-05-01 |  | 2026-05-09 |  | 2026-05-10 |  |  |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-20 | [6 empty] | 2026-06-07 |  | 2026-06-16 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-19 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-18 |  | 2026-04-26 |  | Unknown | 2026-04-11 | 2026-04-11 13:00 | 1948205 | 350677 | 0 | 0 | 0 | 0 | 1948205 | 350677 | 2026-04-15 11:40:17 +0530 | Nayan Reddy | DCM: Cx NameÂ -PradeepÂ Â Crm - Chanakya RGM -11/04/26 Move in date -Â Â Budget - 20-30 L Property name - Direction -Â F to c -Â e facingÂ Shoe rack In parking areaÂ 4Â ft shoe rack withÂ Pooja room As per vastu 3ft width and 6ft Tv unitÂ -Â 75" tv unitÂ full tv unit design with storageÂ Â maximum storageÂ fc in living roomÂ Bedroom Gbr - 1 wardrobe and LoftÂ With mirrorÂ KitchenÂ Tall unitÂ - oven unitÂ Tall unit + 1Â FridgeÂ - 1000mm Dishwasher spaceÂ - optionalÂ Base UnitÂ wall unitÂ Dining areaÂ 6seaterÂ crockery unitÂ stair case wall design Bedroom 2Â MBR Wardrobe + loftÂ dresserÂ Study unit - L shapeÂ fc in all roomsÂ bedroom 1Â kbrÂ Wardrobe + loftÂ Study unitÂ 5ftÂ | [6 empty] | 2026-05-01 |  | 2026-05-08
19383 | Turnkey | 2026-01-01 | Neha Sirwani | Orovia Indigo | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 451681 | 9999 | 0 | 0 | 0 | 87 | 0 | 35169 | 45168 | 180672 | 180672.4 |  |  | 2026-04-11 | 2026-04-19 11:04 | 2026-04-12 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-11 | 2026-04-16 15:25 | 0 | 0 | 0 | 0 | 0 | 0 | 382781 | 68900 | 2026-04-30 17:32:07 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-04-15 12:12:14 +0530 | Pooja Nakul Sharma | CDP budget suggested 25-30L | 2026-04-11 14:21:46 +0530 | Pooja Nakul Sharma | DCM: Mr and Mrs Sirwani Poss- in handÂ Family- 4 members (2 sons)Â Prof- SalariedÂ basic vastu to be followed Entrance 1. shoerack outside with safety door and panelling 2. Foyer storage with wall concept 3. Dining- 4 seater, partition if feasible to divide dining and foyer.Â 4. Crockery storage (Base+wall mount) and puja unit if possible (as per vastu) 5. Tv unit+ wall panelling (display-optional), Sofa seating 3+2 or L shape. 6. Balcony - accent wall, seatingÂ 7. Common passage vanity/ pedestal wash basin 8. Study room- to be bedroom of youngest son. Extendable bed, study, wardrobe, Wall concept.Â 9. Bedroom 2- Elder son's bedroom. Wardrobe, study, tv provision, queen bed, wall concept.Â 10. MBR- Wardrobe, king bed, study, dresser, tv unit. Balcony- seating.Â 11. false ceiling as per sprinkler pipes, painting and electricals. 12. Loose furniture and civil will be out of scope.Â 13. Budget- To be mid range, no specific amount disclosed.Â 14. CDP- 18th April at 11 am | 2026-04-26 |  | 2026-05-03
19384 | Turnkey | 2026-01-01 | Mr.Sourabh | Rohan Ekanta | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Preproduction | DEM2 | 1497805 | 299561 | 1983576 | 0 | 0 | 20 | 0 | 0 | 0 | 599122 | 599122 |  |  | 2026-04-11 | 2026-04-11 14:00 | 2026-04-19 | 2026-04-19 10:03 | 2026-04-20 | 2026-04-20 03:15 | 2026-06-20 | 2026-06-20 19:37 | 2026-07-31 |  | 2026-09-06 |  | 2026-04-20 | 2026-04-23 14:30 | 2026-04-21 | 2026-04-25 13:08 | 2026-04-25 | 2026-04-27 19:01 | 2026-05-16 | 2026-05-17 17:26 |  |  |  |  | 2026-06-20 | 2026-06-25 13:42 | 2026-09-01 |  | 2026-09-02 |  |  |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 | [6 empty] | 2026-09-30 |  | 2026-10-09 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-12 |  |  |  | 2026-11-03 |  | 2026-11-05 |  | 2026-11-06 | [5 empty] | 2026-09-10 |  | 2027-03-04 | 2026-06-20 19:32 | Site is RTMI | 2026-04-11 | 2026-04-11 13:47 | 1680997 | 302579 | 0 | 0 | 0 | 0 | 1670060.286 | 275766 | 2026-05-17 17:27:37 +0530 | Parasa Sri | Welcome call done. | 2026-04-27 19:23:53 +0530 | Rishi Pandey | Some Image was uploaded | 2026-04-27 19:00:35 +0530 | Bency Chacko | Some Image was uploaded | 2026-06-21 | 2026-06-20 19:39 | 2026-08-01 |  | Under Construction | 2026-07-31
19385 | Turnkey | 2026-01-01 | Anil Patil | Devpriya | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  | Krutika Date | Yash Metha | Akshat Shrivastava | Murali S | Prashant Panigrahi | Prasad Bhivaji Hande | Active | Installation | Execution | 1150924 | 1150924 | 1655722 | 1298627 | 1163459 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-11 | 2026-04-12 22:01 | 2026-04-12 | 2026-04-12 22:01 | 2026-04-15 | 2026-04-12 22:03 | 2026-04-27 | 2026-04-22 16:49 | 2026-05-07 | 2026-05-06 11:51 | 2026-05-13 | 2026-05-13 15:23 | 2026-04-12 | 2026-04-14 19:20 | 2026-04-13 | 2026-04-15 10:41 | 2026-04-15 | 2026-04-15 17:30 | 2026-04-22 | 2026-04-22 13:48 |  |  |  |  | 2026-04-20 | 2026-04-20 19:42 | 2026-05-04 | 2026-05-03 17:15 | 2026-05-04 | 2026-05-06 01:05 |  |  | 2026-05-15 | 2026-05-19 17:56 | 2026-05-19 | 2026-05-19 20:45 | 2026-05-20 | 2026-05-19 20:55 | 2026-05-11 | 2026-04-27 18:17 |  |  |  |  | 2026-05-26 17:47 | 2026-06-03 | 2026-06-03 20:03 | 2026-06-18 | 2026-06-16 18:33 | 2026-06-17 | 2026-06-23 18:31 | 2026-06-16 | 2026-06-25 19:02 | 2026-06-26 | 2026-06-28 21:41 | 2026-06-30 | 2026-07-11 12:09 |  |  | 2026-06-25 |  | 2026-06-27 |  | 2026-08-17 | [5 empty] | 2026-05-19 | 2026-05-26 17:46 | 2026-04-23 | 2026-04-22 16:37 | Site is RTMI | 2026-04-11 | 2026-04-12 20:41 | 1403154 | 252567 | 1354443.2139 | 223646 | 1303482.5144 | 215231 | 1292859.5144 | 213318 | 2026-04-28 16:33:12 +0530 | Prashant Panigrahi | Some Image was uploaded | 2026-04-23 12:03:52 +0530 | Anamika Dolai | Done, milestones explained. | 2026-04-15 17:29:42 +0530 | Royden Henriques | abpatil78@gmail.com - Needs to be updated. _____________________ Possession : May'26 Payment Mode : B2C Self funding - Yes Cx will pay on 25th April B/602, shri krishna complex, plot no 16 a, sector 14, sanpada,Â Post offers the amount is 12,18,858/- as per the offer email. 90 + 15 = 105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays. | 2026-04-23 | 2026-04-22 16:59 | 2026-05-07
19387 | Turnkey | 2026-01-01 | Preeti Bhandarkar | Prescon Midtown Bay | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar | Neha Singh | Neha Singh | Nilesh Patel | Rizwan Mistry | Murali S | Harshaan Tiku | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 1596667 | 1596667 | 0 | 1484205 | 1661667 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-11 | 2026-04-11 15:57 | 2026-04-11 | 2026-04-11 16:54 | 2026-04-22 | 2026-04-22 19:19 | 2026-05-22 | 2026-05-22 16:45 | 2026-05-29 | 2026-05-28 20:22 | 2026-06-05 | 2026-06-05 16:33 | 2026-04-22 | 2026-04-24 12:14 | 2026-04-23 | 2026-04-24 12:23 | 2026-04-24 | 2026-04-24 13:11 | 2026-04-30 | 2026-04-30 14:39 |  |  |  |  | 2026-05-22 | 2026-05-26 12:06 | 2026-05-31 | 2026-05-31 14:57 | 2026-06-01 | 2026-05-31 20:36 |  |  | 2026-06-11 | 2026-06-13 12:56 | 2026-06-18 | 2026-06-18 19:59 | 2026-06-19 | 2026-06-18 21:29 | 2026-06-25 | 2026-06-19 18:44 |  |  |  |  | 2026-06-22 11:56 | 2026-07-01 | 2026-06-30 20:01 | 2026-07-10 | 2026-07-08 19:23 | 2026-07-09 | 2026-07-13 15:36 | 2026-07-08 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-23 | 2026-06-22 11:55 | 2026-05-01 | 2026-05-22 16:04 | Site is RTMI | 2026-04-11 | 2026-04-11 15:57 | 0 | 0 | 1539727.51 | 259963 | 1911333.5684 | 309152 | 1911333.5684 | 309152 | 2026-07-11 18:15:30 +0530 | Reshma Melanta | Others: | 2026-07-11 18:08:24 +0530 | Reshma Melanta | Others: | 2026-06-24 16:20:23 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-23 | 2026-05-22 20:02 | 2026-05-29 | 2026-05-28 20:24
19388 | Turnkey | 2026-01-01 | Ms Jyoti Yadav | 72 West | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Rashmita Das |  | Hold | Design | 20% Payment | 1734822 | 220283 | 2202836 | 0 | 0 | 6 | 62 | 0 | 126681 | 720784 | 667074 |  |  | 2026-04-11 | 2026-04-12 15:01 | 2026-04-12 | 2026-04-12 18:41 | 2026-04-15 | 2026-04-14 18:52 | 2026-05-09 | 2026-05-09 20:11 | 2026-08-02 |  | 2026-08-09 |  | 2026-04-12 | 2026-04-14 18:26 | 2026-04-15 | 2026-04-15 19:20 | 2026-04-15 | 2026-04-21 13:33 | 2026-04-23 | 2026-04-23 17:34 |  |  |  |  | 2026-05-09 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-04-24 | 2026-04-30 15:57 | Site is RTMI | 2026-04-11 | 2026-04-11 16:19 | 1866810 | 336025 | 0 | 0 | 0 | 0 | 1859480.8575 | 314210 | 2026-07-04 16:34:15 +0530 | Reshma Melanta | Others: | 2026-06-16 17:06:33 +0530 | Vishakha Vaishnav | Cx said that she will start her civil work i 2 days and then by next week she will make her payment | 2026-05-24 16:36:10 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-10 | 2026-05-09 20:13 | 2026-08-03 |  | RTMI
19390 | Turnkey | 2026-01-01 | Subir Verma | JP Infra | MUM - Thane | Yes | [8 empty] | Bhagyashree Salunkhe |  | Active | Prospect | DCM Due | 4726276 | 9999 | 0 | 0 | 0 | 92 | 0 | 462629 | 472628 | 2075324 | 1705696.4 |  |  | 2026-04-11 | 2026-04-14 13:40 | 2026-04-15 | 2026-04-15 12:04 | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-07 |  | 2026-07-02 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-02 |  | 2026-07-07 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-11 | 2026-04-11 16:17 | 0 | 0 | 0 | 0 | 0 | 0 | 4005318 | 720957 | 2026-04-15 12:05:02 +0530 | Pooja Nakul Sharma | DCM: Mr and Mrs VermaÂ JP Noth Barcelona 5BHKÂ Poss- to be expected in May 2026 Family- 4 membersÂ Prof- FinanceÂ 1. Entrance from one door only, currently shoerack cannot be kept outside, as builder is not allowing for the same. 2. Shoerack to be planned inside. 3. Kitchen- Window opening can be planned near dining.Â 4. Crockery unit can be planned. Dining can be 4 seater with bench.Â 5. TV will be 85 inches, sofa seating.Â 6. TV wall with panelling.Â 7. One door can be closed from outside and can be merged with panelling.Â 8. One common bathroom can be merged with bedroom to have walk in wardrobe or increase the bathroom size. 9. Proper sound system to be planned in living room and balcony.Â 10. Smaller bedroom can be made into puja room or home office. 11. One bedroom will be for guests and other 2 for kids and one MBR for couple.Â 12. Kitchen will have all standard appliances.Â 13. Bathroom vanities to be planned.Â 14. Budget- 35-40L | [6 empty] | 2026-04-26 |  | 2026-05-03
19391 | Turnkey | 2026-01-01 | Ganesh | sln serinity garden | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 2253378 | 9999 | 0 | 0 | 0 | 95 | 0 | 215339 | 225338 | 950588 | 852114.8 |  |  | 2026-04-11 | 2026-04-11 18:25 | 2026-04-22 |  | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-11 | 2026-04-11 18:22 | 0 | 0 | 0 | 0 | 0 | 0 | 1909642 | 343735 | 2026-04-22 03:30:36 +0530 | Saranya Thiyagarajan | DCM: Cx name : Ganesh & Shefali (Hyderabad and Mumbai) Address: SNN Raj Serenity Gardens-G6-002Â Profession : Data Scientist , clinical ScientistÂ Possession : May end (not sure) How many people will be staying : 3 (1 baby girl) Theme :Â Entrance facing :Â West facingÂ Budget :Â 15L Foyer - Laminate finish according to our exp centreÂ Need tall unit with loft and seating as wellÂ Cx has already mention in ppt refer that plan for placementÂ Need to check if we can do safety doorsÂ Ceiling light fixtureÂ Dining -Â 2nd opt (pooja right opposite to front door) Living -Â Tv wall panel with base unitÂ C Shape sofa (cx has the furniture) Sofa back wall add one big art work (no other work) Kitchen - MembraneÂ Fridge - 2 doors Sink side wall cabinets should be glass shuttersÂ Hob side solid shutters extend the counter top for breakfast counter (have to check with builder as well) 1 tall unit for Oven and other AppliancesÂ Granite from builders scopeÂ RO unit on wall cabinetÂ Gas piping is there at siteÂ HOB and chimney - 600mmÂ Utility - DW and WM coming on sink opposite wall Sink base cabinet and wall GTPT unit is required next to sink need one janitor unitÂ MBR - bed wall need simple design (not trims) Queen size bedÂ Bay window need panelling and light point on one side (consider the curve detailing on front )Â Wardrobe on bathroomÂ GBR -Â The full wall will be wardrobeÂ Bed opposite wall need mirrorÂ Queen size next to windowÂ Study tableÂ KBR - Bed with storage and loftÂ L shape studyÂ BalconyÂ 3d needed with the black grill detailing as in pptÂ Bar unit on pipe wallÂ | [6 empty] | 2026-04-30 |  | 2026-05-07
19392 | Turnkey | 2026-01-01 | Mr. Harjinder Sharma | Platinum East Wood | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 64219 | 9999 | 0 | 0 | 0 | 92 | 0 | 0 | 2845 | 25688 | 25687.6 |  |  | 2026-04-11 | 2026-04-14 15:43 | 2026-04-11 | 2026-04-14 17:35 | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-11 | 2026-04-11 18:08 | 0 | 0 | 0 | 0 | 0 | 0 | 54423 | 9796 | 2026-04-14 15:40:00 +0530 | Janvi Nagdeo | Some Image was uploaded | [6 empty] | 2026-05-04 |  | 2026-05-11
19393 | Turnkey | 2026-01-01 | Bhaskar Agnihotri | Lodha Serenity | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  | Viraj Jadhav | Asif Shaikh | Aditya Vikram |  | Aryan Singh | Prasad Bhivaji Hande | Active | Preproduction | 2D | 2236272 | 469999 | 2238607 | 1726497 | 0 | 3 | 7 | 0 | 0 | 911182 | 855091.2 |  |  | 2026-04-11 | 2026-04-11 17:38 | 2026-04-12 | 2026-04-11 23:36 | 2026-04-14 | 2026-04-11 23:41 | 2026-04-22 | 2026-04-22 11:20 | 2026-05-15 | 2026-05-14 12:23 | 2026-06-30 | 2026-06-30 20:40 | 2026-04-11 | 2026-04-13 19:59 | 2026-04-12 | 2026-04-14 13:31 | 2026-04-14 | 2026-04-14 14:21 | 2026-04-17 | 2026-04-17 17:56 |  |  |  |  | 2026-04-19 | 2026-04-13 20:00 | 2026-05-15 | 2026-05-17 09:11 | 2026-05-18 | 2026-05-21 06:36 |  |  | 2026-07-04 | 2026-07-12 19:15 | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-04-18 | 2026-04-21 11:45 | Site is Non-RTMI | 2026-04-11 | 2026-04-11 17:25 | 1897124 | 341482 | 1914439.291 | 323236 | 0 | 0 | 2442798.6075 | 412439 | 2026-07-12 12:40:46 +0530 | Honey Thakkar |  | 2026-07-11 12:13:30 +0530 | Sahil Gunde | Others: | 2026-07-11 10:49:17 +0530 | Honey Thakkar |  | 2026-04-23 | 2026-04-22 22:10 | 2026-05-15 | 2026-05-14 12:23
19396 | Turnkey | 2026-01-01 | Sanjay Sahoo | Rohan ekanta | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Priyanka Mathur | [5 empty] | Chanakya Panigrahi |  | Active | Preproduction | DEM2 | 1973231 | 338940 | 2373780 | 0 | 0 | 47 | 0 | 0 | 0 | 922531 | 711760.4 |  |  | 2026-04-11 | 2026-04-11 17:31 | 2026-04-15 | 2026-04-15 13:13 | 2026-04-18 | 2026-04-18 12:00 | 2026-05-29 | 2026-05-29 18:47 | 2026-09-01 |  | 2026-09-08 |  | 2026-04-18 | 2026-04-23 15:16 | 2026-04-19 | 2026-04-25 10:55 | 2026-04-25 | 2026-04-27 10:17 | 2026-04-29 | 2026-04-29 14:34 |  |  |  |  | 2026-05-30 | 2026-05-12 16:28 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-05-25 | 2026-05-29 18:37 | Site is RTMI | 2026-04-11 | 2026-04-11 17:30 | 2011678 | 362102 | 0 | 0 | 0 | 0 | 2238741.0217 | 369645 | 2026-06-11 17:35:44 +0530 | Preethi Shetty | Working on the changes as per the discussion with client Pooja unit - Back panel with cnc cutting Arch shape - cnc panel on top Master bedroom - Dresser draws to be added | 2026-05-15 11:37:50 +0530 | Preethi Shetty | Some Image was uploaded | 2026-05-15 11:34:56 +0530 | Preethi Shetty | Some Image was uploaded | 2026-05-30 | 2026-05-29 18:50 | 2026-09-02 |  | Under Construction | 2026-09-30
19398 | Turnkey | 2026-01-01 | Vaibhav Pawar | Neel Castle | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 1462134 | 9999 | 0 | 0 | 0 | 94 | 0 | 136214 | 146213 | 626452 | 543255.6 |  |  | 2026-04-11 | 2026-04-12 12:21 | 2026-04-13 | 2026-04-13 13:13 | 2026-04-25 |  | 2026-04-23 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-04-16 |  | 2026-04-17 |  | 2026-04-17 |  | 2026-04-18 | [5 empty] | 2026-04-24 |  | 2026-05-02 |  | 2026-05-03 |  |  |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 | [6 empty] | 2026-05-31 |  | 2026-06-09 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-12 |  |  |  | 2026-07-04 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-05-11 |  | 2026-04-19 |  | Unknown | 2026-04-11 | 2026-04-11 18:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1241384 | 220750 | 2026-04-14 14:03:10 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-04-11 19:35:34 +0530 | Yash Jain | DCM: Vaibhav pawar sir, flooring -Â sofa seater- 3+2 seater no L shape, dining table- 4 seater Tv size - 50'' tvÂ 5 internal door refurb 1 new safety door - Mandir - re use foldable tv Kitchen - full renovationÂ L shaped existing breakÂ and make parallel platform. Semi modular kitchen - hob chimney , refrigerator double doorÂ cx room sofa cum bed, qsbÂ wardrobeÂ dresser cum side table. master bedroom mandir room Qsb wardrobe dresser.Â lobby storage, with WASHING MAHCINEÂ store. neutral theme - |  |  |  | 2026-04-24 |  | 2026-05-01
19399 | Turnkey | 2026-01-01 | Kumudha Shree | House of Hiranandani akshayanagar | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Aman Kumar |  | Active | Preproduction | DEM2 | 1989206 | 397841 | 3337657 | 0 | 0 | 15 | 0 | 0 | 0 | 795683 | 795682.4 |  |  | 2026-04-11 | 2026-04-11 18:31 | 2026-04-17 | 2026-04-29 04:14 | 2026-05-02 | 2026-04-30 13:22 | 2026-06-07 | 2026-06-07 18:54 | 2026-07-27 |  | 2026-09-03 |  | 2026-04-30 | 2026-04-30 18:31 | 2026-05-01 | 2026-05-07 08:37 | 2026-05-07 | 2026-05-07 14:35 | 2026-05-08 | 2026-05-08 11:55 |  |  |  |  | 2026-06-07 | 2026-06-30 14:45 | 2026-08-29 |  | 2026-08-30 |  |  |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 | [6 empty] | 2026-10-02 |  | 2026-10-27 |  | 2026-10-26 |  | 2026-10-27 |  | 2026-10-27 |  | 2026-11-01 |  |  |  | 2026-12-10 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-09-07 |  | 2026-05-09 | 2026-05-26 19:38 | Site is RTMI | 2026-04-11 | 2026-04-11 18:30 | 2828523 | 509134 | 0 | 0 | 0 | 0 | 2345731.2 | 387336 | 2026-06-03 18:48:44 +0530 | Muskan Agarwal | The client has requested layout options for all spaces. Final confirmation on the layouts is still pending from the clients end. The updated and revised quotation will be shared once the layout is finalised. | 2026-06-03 18:46:54 +0530 | Muskan Agarwal | Minutes of Meeting - Points Discussed & Agreed Corrections Foyer: Loose furniture to be added only for the seating area. Remaining space to be planned with modular elements. Guest Bedroom: Layout approved; good to proceed. Kitchen: Wall storage to be added for appliances. Corner unit to be an Lcorner. Layout with breakfast counter and separate coffee console is finalised. Master Bedroom (MBR): Two layout options required. Dresser mirror to be placed on the north wall. Space for corner diwan MBR Bathroom: Layout to remain the same as per the reference video. Balcony: Seating to be provided along the walls only one near the kids bedroom and one in the middle. Kids Bedroom (KBR): One layout option feasible as per Vastu. Dresser to be placed on the north wall. Dressing and study to be integrated, along with integrated bedside tables. | 2026-05-20 18:26:11 +0530 | Muskan Agarwal | Minutes of Meeting - Points Discussed & Agreed Corrections 1. Overall Updates The client has opted for an open kitchen. Kitchenliving wall will be demolished. Duct areas will be included within the property layout through civil changes. Civil quotation has been shared. Immediate next step : Finalisation of design layout, starting with common areas. 2. Common Areas Design 2.1 Foyer No modular requirements. Feature wall to have mosaic art. 2.2 Kitchen Lshape kitchen extending into the existing maids room. Appliance tower (microwave + oven) to be placed next to the hob. Loft shutters to be provided for overhead storage. Full Lshape wall units endtoend. 2door refrigerator in the designated corner. Tall unit with internal drawers next to refrigerator for appliance storage. Waterfall sink extended till the tall unit. 2.3 Utility Area Existing utility bathroom to be converted into a storage unit. Two entrances option to be provided, with pipe separator in between. Sink to be placed opposite the window. Washing machine to be placed next to the sink. Small (8"approx) partition for cleaning supplies . Additional small partition for maids cleaning zone design to be refined (folding shutter option to be explored) 2.4 Dining Space Three layout options for a 6seater dining arrangement: Option 1:Without sofa + bar unit facing balcony + wine rack storage. Option 2: With Lshape sofa. Option 3: Bestcirculation layout with optimised storage. Additional notes: Storage below the island depending on space. Island wall concept shared by the client to be considered. Similar design direction to be explored for the bar unit. 2.5 Living Room Options to be shared: Marble flooring and Wooden flooring. Mandir to be 3 ft. Third mandir concept to include: Combination of earlier designs 1.Pocket door 2.Soft curves 3.Hanging elements Storage to be added next to the mandir. Wall concept to be finalised later. Sofa to be placed max 10 ft from the TV; sofa back visible from entrance. TV unit to be placed on bathroom wall, aligned with window and powder room. Soft curves on all wall edges. Tv Unit refences shared by the client Floorbased TV setup to include: Setup box, PS5, Space for weights & stepper 2.6 Powder Room Two layout options to be provided: Option 1: Sink located near the back storage, maintaining a straight passage. Option 2: Sink placed inside the passage bathroom itself. NOTE- As we are changing the design, the costing will be revised accordingly. This will not be the final costing, as it will vary based on: Final finishes selected Scope of work Post crossmeasurement quality check | 2026-06-08 | 2026-06-07 18:55 | 2026-07-28 |  | Under Construction | 2026-06-19
19402 | Turnkey | 2026-01-01 | Sanjeeb Patnaik | sn Celeste | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Aman Kumar |  | Lost | Preproduction | DEM2 | 1194874 | 187958 | 1040679 | 0 | 0 | 78 | 0 | 0 | 0 | 625706 | 381210.4 |  |  | 2026-04-11 | 2026-04-11 18:52 | 2026-04-17 | 2026-04-20 19:53 | 2026-04-21 | 2026-04-20 22:09 | 2026-04-26 | 2026-04-26 14:04 | 2026-05-22 | 2026-05-21 15:23 | 2026-11-06 |  | 2026-04-20 | 2026-04-21 19:31 | 2026-04-21 | 2026-04-22 11:40 | 2026-04-22 | 2026-04-22 15:50 | 2026-04-25 | 2026-04-25 19:17 |  |  |  |  | 2026-04-26 | 2026-04-28 13:41 | 2026-11-01 |  | 2026-11-02 |  |  |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-12 | [6 empty] | 2026-11-30 |  | 2026-12-09 |  | 2026-12-08 |  | 2026-12-09 |  | 2026-12-10 |  | 2026-12-12 |  |  |  | 2027-01-03 |  | 2027-01-05 |  | 2027-01-06 | [5 empty] | 2026-11-10 |  | 2026-04-26 | 2026-04-26 13:59 | Site is RTMI | 2026-04-11 | 2026-04-11 18:42 | 1054411.27 | 171723 | 0 | 0 | 0 | 0 | 1293133.4481 | 212024 | 2026-07-09 18:57:07 +0530 | Abhinandan K S |  | 2026-07-09 18:55:57 +0530 | Abhinandan K S |  | 2026-05-27 18:11:43 +0530 | Priyanka Mathur | Client mentioned in the design discussion that we have tight budget and initially it is said that 50k wall concept everything you will get. Also what was added in the 3d renders they want same design. Client has very tight budget . And as per the existing wall concepts and increase in the modular it is gone from 9lakh to 12 lakh. We had a call client is also saying light's we asked to add we trusted bonito but it is not added. Client want everything in 9 lakh | 2026-04-27 | 2026-04-26 14:06 | 2026-05-22 | 2026-05-21 15:26 | RTMI
19403 | Turnkey | 2026-01-01 | Vinoo Khanna | Kalpatru shrishti namah | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Moni Sahani |  | Hold | Preproduction | DEM2 | 1198393 | 239679 | 1696416 | 0 | 0 | 31 | 13 | 0 | 0 | 543479 | 415234.8 |  |  | 2026-04-11 | 2026-05-07 12:54 | 2026-04-11 | 2026-05-07 13:57 | 2026-05-07 | 2026-05-09 10:10 | 2026-06-04 | 2026-05-31 12:48 | 2026-11-01 |  | 2026-11-08 |  | 2026-05-09 | 2026-05-09 10:49 | 2026-05-10 | 2026-05-09 12:38 | 2026-05-09 | 2026-05-13 09:39 | 2026-05-16 | 2026-05-16 18:57 |  |  |  |  | 2026-05-31 | 2026-06-01 14:54 | 2026-11-03 |  | 2026-11-04 |  |  |  | 2026-11-11 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-14 | [6 empty] | 2026-12-02 |  | 2026-12-11 |  | 2026-12-10 |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-14 |  |  |  | 2027-01-05 |  | 2027-01-07 |  | 2027-01-08 | [5 empty] | 2026-11-12 |  | 2026-05-17 | 2026-05-31 12:31 | Site is RTMI | 2026-04-11 | 2026-04-11 19:02 | 1439739 | 256676 | 0 | 0 | 0 | 0 | 1421278.1527 | 232190 | 2026-07-02 17:53:26 +0530 | Vishakha Vaishnav | Others: CX WILL GET POSSESSION BY OCTOBER END | 2026-05-31 12:21:01 +0530 | Manisha Dubey | Minutes of Meeting (MOM) Client Name: Mr. Vinod Khanna Discussion Points & Requirements Living Area Mandir provision required. Wallpaper concept/style is not required. 55-inch TV provision required in all rooms. Double curtain provision required in all room. AC pelmet required in all rooms. Sons Bedroom (Hardik) Queen-size bed required. Study table required. Floor-mounted TV unit required. No loft required in any wardrobe. Full-length wardrobe required. Shoe provision required (tall)with clear glass and lighting. trouser pull-out required. Above the study table, stylish display shelves are required. Hanging light required above the side table. Mirror required between the bed and wardrobe wall. Additional lighting preferred in sons room. Curved mirror required. Master Bedroom Sliding wardrobe required. flush door concept required for washroom door . Locker provision required inside wardrobe. side opening wardrobe added with mirror shutter for used clothes . Glass fascia drawers required in wardrobe. Single drawer configuration required. organizer required for watch and sunglasses . trouser pull-out required. Kitchen renovating the entire kitchen Civil work is under client scope; assistance required for selection. Aquaguard provision below sink unit. GTPT unit required above sink area. Rolling shutter provision for microwave, mixer, and sandwich maker. Wall unit with mechanism required. Glossy laminate finish preferred in kitchen. Washroom Vanity unit required in both washrooms. Glass partition required in washrooms. General Requirements False ceiling required in all rooms plain design with profile detailing. Center table included in client scope. Shoe unit required. 2 beds and sofa included in our scope. | 2026-05-21 18:34:48 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-01 | 2026-05-31 12:50 | 2026-11-02
19404 | Turnkey | 2026-01-01 | Mr.Amit Kumar | SBR Earth & Sky | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Hold | Preproduction | Site Readiness 1 | 1254675 | 261999 | 1534329 | 0 | 0 | 2 | 40 | 0 | 0 | 505944 | 486732 |  |  | 2026-04-11 | 2026-04-18 12:59 | 2026-04-11 | 2026-04-18 13:17 | 2026-04-21 | 2026-04-22 15:25 | 2026-06-01 | 2026-05-31 15:58 | 2026-10-05 |  | 2026-10-12 |  | 2026-04-22 | 2026-04-23 20:45 | 2026-04-23 | 2026-04-28 11:33 | 2026-04-28 | 2026-04-28 17:39 | 2026-05-06 | 2026-05-03 15:40 |  |  |  |  | 2026-06-05 | 2026-06-03 13:31 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-05-04 | 2026-05-31 10:50 | Site is Non-RTMI | 2026-04-11 | 2026-04-18 12:58 | 1300278 | 234050 | 0 | 0 | 0 | 0 | 1284961.4926 | 219821 | 2026-06-18 19:10:15 +0530 | Priyanka R | Some Image was uploaded | 2026-05-24 13:37:55 +0530 | Priyanka R | Some Image was uploaded | 2026-05-05 16:51:58 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-01 | 2026-05-31 15:58 | 2026-10-06 |  | Under Construction | 2026-09-01
19405 | Sub Project |  | shubham Sanghavi/Varun Sanghavi sanghavi | Lodha Aura | MUM - GOR | Yes | Karan Chavda |  | Safalta Karkera |  | Hiba Shaikh | [5 empty] | Active | Preproduction | 2D | 35101 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 21061 | 14040.4 |  |  | 2026-04-11 | 2026-06-23 18:12 | 2026-04-12 | 2026-06-23 18:12 | 2026-06-23 | 2026-06-23 18:12 | 2026-06-24 | 2026-06-23 18:13 | 2026-06-24 | 2026-06-23 18:14 | 2026-06-24 | 2026-06-23 18:16 | 2026-06-23 | 2026-06-23 18:12 | 2026-06-24 | 2026-06-23 18:12 | 2026-06-23 | 2026-06-23 18:13 | 2026-06-24 | 2026-06-23 18:13 |  |  |  |  | 2026-06-23 | 2026-06-23 18:13 | 2026-06-24 | 2026-06-23 18:14 | 2026-06-24 | 2026-06-23 18:15 |  |  | 2026-06-24 | 2026-07-12 13:58 | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-28 | [5 empty] | 2026-07-08 |  | 2026-06-24 | 2026-06-23 18:13 | Unknown | 2026-04-11 | 2026-06-23 18:12 | 0 | 0 | 0 | 0 | 0 | 0 | 29746 | 5354 | [9 empty] | 2026-06-24 | 2026-06-23 18:13 | 2026-06-24 | 2026-06-23 18:14
19406 | Turnkey | 2026-01-01 | Max Flow Industries (Naeem Salema) Salema | Rosewalt | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Hold | Design | DEM1 | 1898806 | 245760 | 2491838 | 0 | 0 | 46 | 35 | 0 | 134001 | 810668 | 708376.4 |  |  | 2026-04-11 | 2026-04-12 12:31 | 2026-04-11 | 2026-04-12 18:59 | 2026-04-15 | 2026-04-15 11:59 | 2027-11-25 |  | 2027-12-02 |  | 2027-12-09 |  | 2026-04-15 | 2026-04-15 13:55 | 2026-04-16 | 2026-04-15 14:34 | 2026-04-15 | 2026-04-25 10:06 | 2026-04-28 | 2026-04-28 19:05 |  |  |  |  | 2027-11-26 |  | 2027-12-04 |  | 2027-12-05 |  |  |  | 2027-12-12 |  | 2027-12-13 |  | 2027-12-14 |  | 2027-12-15 | [6 empty] | 2028-01-02 |  | 2028-01-11 |  | 2028-01-10 |  | 2028-01-11 |  | 2028-01-12 |  | 2028-01-14 |  |  |  | 2028-02-05 |  | 2028-02-07 |  | 2028-02-08 | [5 empty] | 2027-12-13 |  | 2027-01-15 |  | Unknown | 2026-04-11 | 2026-04-11 20:00 | 2111727 | 380110 | 0 | 0 | 0 | 0 | 2086814.3126 | 346470 | 2026-06-10 14:59:21 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-21 12:04:45 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-30 19:27:08 +0530 | Meet Shah | Some Image was uploaded | 2027-11-26 |  | 2027-12-03 |  | Under Construction | 2026-12-31
19408 | Turnkey | 2026-01-01 | Anish Modak | Parijat | MUM - Thane | Yes | [8 empty] | Anjan Kumar |  | Active | Prospect | 10% Payment | 1105188 | 9999 | 1105188 | 0 | 0 | 90 | 0 | 100520 | 110519 | 442075 | 442075.2 |  |  | 2026-04-11 | 2026-04-11 20:17 | 2026-04-15 | 2026-04-15 12:11 | 2026-04-16 | 2026-04-17 12:13 | 2026-04-24 |  | 2026-05-01 |  | 2026-05-08 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-18 |  | 2026-04-19 | [5 empty] | 2026-04-25 |  | 2026-05-03 |  | 2026-05-04 |  |  |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 | [6 empty] | 2026-06-01 |  | 2026-06-10 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-13 |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-08 | [5 empty] | 2026-05-12 |  | 2026-04-20 |  | Unknown | 2026-04-11 | 2026-04-11 20:06 | 936600 | 168588 | 0 | 0 | 0 | 0 | 936600 | 168588 | 2026-04-11 20:20:26 +0530 | Anjan Kumar | Some Image was uploaded | 2026-04-11 20:18:32 +0530 | Anjan Kumar | Others: Silver Coin 21g |  |  |  | 2026-04-25 |  | 2026-05-02
19409 | Turnkey | 2026-01-01 | Anil Gawde | Avant Heritage | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Nivesh Gupta |  | Active | Preproduction | DEM2 | 825529 | 165106 | 1087662 | 0 | 0 | 58 | 0 | 0 | 0 | 330211 | 330211.6 |  |  | 2026-04-11 | 2026-04-12 11:12 | 2026-04-15 | 2026-04-22 13:58 | 2026-04-28 | 2026-04-28 13:03 | 2026-05-17 | 2026-05-17 14:30 | 2026-08-06 |  | 2026-08-13 |  | 2026-04-28 | 2026-04-28 20:12 | 2026-04-29 | 2026-04-28 20:20 | 2026-04-28 | 2026-04-29 15:13 | 2026-05-08 | 2026-05-08 17:39 |  |  |  |  | 2026-05-18 | 2026-05-18 18:33 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-05-09 | 2026-05-17 14:28 | Site is RTMI | 2026-04-11 | 2026-04-12 11:11 | 921747 | 165914 | 0 | 0 | 0 | 0 | 915937.4046 | 152623 | 2026-06-29 15:33:25 +0530 | Manzoor Shaikh | Dear Mr. Anil Gawde, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 05th July at 11:30 AM at Andheri EC. The agenda for this meeting will be to discuss the Layout Finalization with our designer, Neha will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-05-17 13:51:17 +0530 | Neha Yadav | Meeeting Discussion DDM 1Â Living Room: 1)Tv panel need to add with shelf with moulding design behind sofaÂ 2)Mandir unit need to addÂ Â 3)Bathroom vanity need to addÂ *False ceiling will be in bedroom also with bordered designÂ Feel free to addÂ pointers if i have missed any. | 2026-05-12 18:51:16 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-18 | 2026-05-19 15:49 | 2026-08-07 |  | Under Construction | 2026-07-31
19410 | Turnkey | 2026-01-01 | Mrs. RESHMA SHRIKANT KUMTHEKAR | regency luxuria dombivli | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | vinaya thakur |  | Active | Prospect | DCM Due | 1509403 | 9999 | 0 | 0 | 0 | 95 | 0 | 140941 | 150940 | 611880 | 595642.4 |  |  | 2026-04-11 | 2026-04-11 21:08 | 2026-04-22 | 2026-04-22 12:11 | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-11 | 2026-04-11 21:06 | 0 | 0 | 0 | 0 | 0 | 0 | 1279155 | 230247 | 2026-04-21 17:38:47 +0530 | Karuna Shinde | Some Image was uploaded | 2026-04-21 17:37:10 +0530 | Karuna Shinde | DCM: NAME:- Reshma kumthekar & Shrikant kumthekar PROPERTY:-Regency Luxuria, RUBY 904Â Â SQ,FT:- 840Â 2 BHK POSSESION:- AUGUST 2026 Profession :- Service FAMILY SIZE:-Â couple, Son(16) Dog.Â SCOPE OF WORK:-Â Â Modular, painting, False ceiling in living room, pelment in all rooms ,electrical.Â As per vastu - Yes LIVING ROOM:- Shoe rack outside,Â Safety Door+paneeling. Frame of maharaj in the entrance. 3 seater sofa, TV Unit with mandir. 4 seater dining foldable also fixed one option. Seven horse frame 39" width and height 21". Swing in Balcony 2 seater preferred. Kitchen:-Â Base Unit, Wall Unit. Loft on One side. Water purifier. Washing machine and storage above, Dishwasher in front it. Microwave, chimney. Fridge. Existing loft slab in kitchen.Â Master Bedroom :- Wardrobe, Existing sofa Bed need to suggest sunmica for it 6'*5' . Work station foldable+ book shelf cabinet(designer) one side.Â pull out mirror in wardrobe.Â Â Kid's Room:-Â Wardrobe, sofa cum bed, Mirror with little storage, book storage Unit with foldable bed.Â Lobby:- Existing slab need to give storage there below it.Â Bathroom:-Â Vanities.Â THEME:- European theme with low maintenance , it should look spacious.Â BUDGET PLANNED:- 9-10 lakh CDP :-Â 26 th April. 10.30 am. | 2026-04-11 21:09:53 +0530 | vinaya thakur | Some Image was uploaded | 2026-05-04 |  | 2026-05-11
19411 | Turnkey | 2026-01-01 | Rishabh Neekhara | Palava lodha city | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 2368436 | 9999 | 0 | 0 | 0 | 95 | 0 | 226845 | 236844 | 997117 | 897632 |  |  | 2026-04-11 | 2026-04-11 22:18 | 2026-04-14 | 2026-04-14 16:27 | 2026-04-22 |  | 2026-04-24 |  | 2026-05-01 |  | 2026-05-08 |  | 2026-04-17 |  | 2026-04-18 |  | 2026-04-18 |  | 2026-04-19 | [5 empty] | 2026-04-25 |  | 2026-05-03 |  | 2026-05-04 |  |  |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 | [6 empty] | 2026-06-01 |  | 2026-06-10 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-13 |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-08 | [5 empty] | 2026-05-12 |  | 2026-04-20 |  | Unknown | 2026-04-11 | 2026-04-11 22:17 | 0 | 0 | 0 | 0 | 0 | 0 | 2007149 | 361286 | 2026-05-03 21:52:21 +0530 | Anant Giri | Some Image was uploaded | 2026-04-14 16:22:24 +0530 | Moksh Mehta | DCM: Client Name:- Rishabh Neekhara Property:- Lodha Palava Casa Rio Possesion Date:- In Hand Sq Ft:- 960 sqft 2BHK Cluster Exotic B Wing 1902 No of Members: - Couple (35+) + Newborn Baby Boy Budget: - 15 L but expectation has been set for 18L Ent: - Shoe Rack (15-20 Pairs)Wall Concepts Living :- Seating Capacity for (4-5 Persons)TV Unit (65") with Display options6-Seater Dining Table (existing)Crockery Unit Theatre Area: - Workstation for 2 peopleFolding Partition option or Folding with Fixed partition option Diwan bed if possible Kitchen:- Loft Units x 2nosRefurbishing aspect to be checked.Tall Unit for Appliances Utility StorageTop Load Washing MachineSmall Appliances generic to be consideredOpen racks below wall cabinets Master Bedroom:- Queen size bedSide Table cum DresserWardrobe with Loftwall to be broken between the Wardrobe and room. Bedroom 2:- Kid's Bedroom Sofa cum Bed / Normal Bed provisionWardrobeFolding Study Table Washroom:- Vanities :- 2Nos |  |  |  | 2026-04-25 |  | 2026-05-02
19412 | Turnkey | 2026-01-01 | Priyanka Deshpande | The ICON | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Active | Preproduction | Site Readiness 1 | 1099581 | 299999 | 1452492 | 0 | 0 | 2 | 55 | 0 | 0 | 429460 | 370121.6 |  |  | 2026-04-11 | 2026-04-11 22:38 | 2026-04-14 | 2026-04-14 17:58 | 2026-04-17 | 2026-04-17 20:11 | 2026-05-18 | 2026-05-17 13:49 | 2026-11-06 |  | 2026-11-13 |  | 2026-04-17 | 2026-04-20 15:04 | 2026-04-18 | 2026-04-21 15:27 | 2026-04-21 | 2026-04-22 11:01 | 2026-04-24 | 2026-04-24 16:59 |  |  |  |  | 2026-05-17 | 2026-05-19 15:00 | 2026-11-08 |  | 2026-11-09 |  |  |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 |  | 2026-11-19 | [6 empty] | 2026-12-07 |  | 2026-12-16 |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-19 |  |  |  | 2027-01-10 |  | 2027-01-12 |  | 2027-01-13 | [5 empty] | 2026-11-17 |  | 2026-08-31 | 2026-05-17 11:29 | Site is Non-RTMI | 2026-04-11 | 2026-04-11 22:37 | 1233946 | 218545 | 0 | 0 | 0 | 0 | 1233946.3645 | 195220 | 2026-05-07 18:11:43 +0530 | Anil Kuwar | DDM1: 1st meeting planed for 9th of my | 2026-04-24 16:58:08 +0530 | Anil Jagtap | welcome call completed | 2026-04-22 11:01:03 +0530 | Royden Henriques |  | 2026-05-18 | 2026-05-17 13:51 | 2026-11-07
19413 | Turnkey | 2026-01-01 | Balaji | Independnet house | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  | Sethuragavan R | Nanda Kumar | Ranjith Kumar | Murali S | Muralikrishna Udupi | Affaan Abdulla | Active | Installation | Execution | 1646485 | 1646485 | 2127173 | 0 | 1646485 | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-11 | 2026-04-14 11:00 | 2026-04-14 | 2026-04-14 11:14 | 2026-04-14 | 2026-04-14 11:24 | 2026-04-28 | 2026-04-28 19:39 | 2026-05-02 | 2026-05-01 18:22 | 2026-05-05 | 2026-05-05 11:26 | 2026-04-14 | 2026-04-24 10:33 | 2026-04-15 | 2026-04-24 10:37 | 2026-04-24 | 2026-04-24 14:53 | 2026-04-25 | 2026-04-27 12:02 |  |  |  |  | 2026-04-28 | 2026-04-29 18:32 | 2026-05-02 | 2026-05-04 18:27 | 2026-05-05 | 2026-05-04 18:27 |  |  | 2026-05-06 | 2026-05-05 16:31 | 2026-05-05 | 2026-05-05 18:44 | 2026-05-06 | 2026-05-06 13:53 | 2026-05-07 | 2026-05-07 19:28 |  |  |  |  | 2026-05-11 08:08 | 2026-06-01 | 2026-05-31 18:26 | 2026-06-17 | 2026-06-16 15:27 | 2026-06-16 | 2026-06-16 18:54 | 2026-06-16 | 2026-06-18 23:05 | 2026-06-17 | 2026-06-19 11:10 | 2026-06-25 | 2026-06-24 17:52 |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-05 | 2026-05-11 08:07 | 2026-04-28 | 2026-04-28 18:57 | Site is RTMI | 2026-04-11 | 2026-04-13 19:38 | 1802689 | 324484 | 0 | 0 | 1798216.7193 | 296921 | 1798216.7193 | 296921 | 2026-06-24 15:48:37 +0530 | Ranjith Kumar | Execution: | 2026-06-08 11:00:08 +0530 | Ranjith Kumar | Procurement: | 2026-05-25 15:02:24 +0530 | Ranjith Kumar | Bonito Side Floor Covering only Cx Side Electrical. | 2026-04-29 | 2026-04-28 19:40 | 2026-05-02 | 2026-05-01 18:37 | RTMI
19414 | Turnkey | 2026-01-01 | harish | DS Max Skysupreme | BNG - HRBR | No Estimate | [8 empty] | Shashank Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-11 | 2026-04-22 13:40 | 2026-04-12 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-11 | 2026-04-22 13:34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-17 17:35:18 +0530 | Keerthan M | DCM: Harish 3BHK 4+1 ppl main door north facing Living room - Floating unit with minimal storage - Pooja room with glass wall and shutters on sofa wall corner. - give option for pooja unit as well Dining - 6 seater existing table - tall unit, double door fridge, crockery unit Kitchen - check for the provision for sliding door in kitchen entrance - Hob towards north - hob, chimney and sink(2 bowl), micro-wave,Â - Cylinder unit provision for future dish washerÂ - Sink in w/m space (right side of hob) - w/m and d/w plan it together - groceryÂ Note: ref site images during design washrooms - mirror with storage - washroom fixtures. MBR - existing 5x6 bed - wardrobe till door - mirror on wall with glass shutter unit - study unit towards balcony door, beside bed - check for layout option, with walk in closet provision KBR (near Living) - Wardrobe, dresser, l shape study - bed as per ref, (nest bed) - marvel and space theme. Guest bedroom - Existing bed 5x6 - wardrobe, mirror on shutter - study unit near window beside bed. | 2026-04-14 16:39:44 +0530 | Shashank Singh | Some Image was uploaded |  |  |  | 2026-04-26 |  | 2026-05-03
19415 | Turnkey | 2026-01-01 | Imran | Nexa Acuity | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 1683443 | 9999 | 0 | 0 | 0 | 88 | 0 | 158345 | 168344 | 694560 | 652194 |  |  | 2026-04-12 | 2026-04-16 21:43 | 2026-04-12 | 2026-04-16 21:46 | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-12 | 2026-04-16 21:40 | 0 | 0 | 0 | 0 | 0 | 0 | 1426647 | 256796 | 2026-04-14 16:39:06 +0530 | Shashank Singh | Some Image was uploaded | 2026-04-12 17:52:35 +0530 | Palak Thakur | DCM: Minutes of Meeting held on Date: <12Â -04/2026> Attendees:palak Discussion:rgm Based on <12Â -04/2026> meeting, below is a list of all the requirements that were discussed during the meeting: FINAL MOM 12Â -04/2026Â 19415 - ImranÂ Client Name:Â Â Imran Â Property:Â nexsaÂ acuityÂ hennurÂ bagalurÂ highwayÂ Â Floor: 2nd floor A^ Â Main Door Facing:Â east going outsideÂ Â Possession: in handÂ Site MeasurementÂ aprilÂ Â handover julyÂ Current residenceÂ RTÂ nagarÂ Â TotalÂ sqftÂ 1460 TYPE OF CONSTRUCTION RCC frames structure Family Details Family 3 members( couple + 1 son)SonÂ lkgÂ 12 years inÂ bangaloreÂ HometownÂ andraÂ pradeshÂ Sir inÂ delloiteÂ (hybrid setup )BudgetClient Budget: 15 Lakhs ALL MODULAR DESIGN includingÂ Recommended Budget (as per requirements): 13-17LakhsTheme themes can be suggestedÂ Design PreferencesÂ Colors, Finishes & Lighting Kitchen:Â Living Area:Â Overall Preference:Â Kitchen Countertop: by bonitoLighting:goodÂ lightingÂ Ceiling:Â ;living and diningÂ Â DesignÂ Requirements & Discussion PointsEXISTING FURNITUREÂ Sofa recliner 3+ 2+ fridge + diningÂ 4 seaterÂ +washing +king bedÂ for masterÂ Double bed for guestÂ 1Â foldablleÂ iron tableÂ anywereÂ in houseÂ Bedroom MASTER BEDROOM King bed existingÂ Wardrobe+ loftÂ (sliding) Dresser (sideÂ of wardrobe ) Study unitÂ Â 1 wallÂ textureÂ Bay window seater optionalÂ Used cloth storageguestÂ Â Bedroom centre 1 existing bed as marked 4'x6'All existing furniture 3+2+2wardrobe+showcase+dresserÂ Add loftÂ bedroom kids top right Queen bedÂ Wardrobe+loftÂ (hinged)Â Mirror in shutterÂ Kids theme false ceilingÂ Study table Used cloth storageKids balcony washing machineÂ LIVING ROOMTV 55"Partition in entranceÂ Sofa 3+ existing brownÂ 1 closed unit side of tvÂ Sofa backÂ wallÂ to highlightÂ ParyerÂ partition in guest bedroomÂ 1 partition in guest bedroom as marked inredÂ Door sliding to be marked in greenÂ Front storage + shelvesÂ UTILITYÂ 2 Cylinder in utilityÂ Â DishwasherÂ 1 sideÂ Â 1Â sinkÂ Tile installation ( open point) KITCHENÂ l shape kitchen to make as u Â shape handless Karpa stone given by builder can be used in utility Side wall has beamÂ extendÂ till end of diningÂ Slab toÂ entendÂ till marked in blue Base + loft + wallÂ Counter topÂ in bonito scope ( granite ) Tall unit for micro andÂ otgÂ Ro unit in bottom unitÂ Hob in centreÂ BreakfastÂ table to add for 1 seaterÂ Fridge 2 door marked inÂ orange Â 1 rollingÂ shutter Foyer storageOutside existing shoe storageMain door withÂ panelingÂ + lightÂ 1 vanity sink as marked in red + mirrorDININGÂ DiningÂ 4 seaterÂ existingÂ Â Crockery as marked in redÂ 1 tall + bottom + wall unitÂ PvcÂ ceiling inÂ dinngÂ (rafters) WASHROOMÂ wall unitÂ x 2 |  |  |  | 2026-04-26 |  | 2026-05-03
19416 | Turnkey | 2026-01-01 | gaurav pandey | Akruti kiran | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera |  |  | Akash Jadhav | Sandeep Tiwari |  | Sanskruti Yadav | Shailendra Mishra | Active | Preproduction | Procurement | 1148342 | 689005 | 1465197 | 0 | 1148342 | 1 | 0 | 0 | 0 | 0 | 459337 |  |  | 2026-04-11 | 2026-04-12 12:22 | 2026-04-14 | 2026-04-14 22:01 | 2026-04-15 | 2026-04-15 18:42 | 2026-04-30 | 2026-04-30 12:47 | 2026-06-26 | 2026-06-25 11:48 | 2026-06-27 | 2026-06-26 17:00 | 2026-04-15 | 2026-04-15 18:49 | 2026-04-16 | 2026-04-16 11:31 | 2026-04-16 | 2026-04-16 17:44 | 2026-04-23 | 2026-04-23 19:04 |  |  |  |  | 2026-04-30 | 2026-04-30 17:36 | 2026-06-14 | 2026-06-15 19:17 | 2026-06-16 | 2026-06-15 19:46 |  |  | 2026-07-03 | 2026-07-10 12:21 | 2026-07-10 | 2026-07-10 16:54 | 2026-07-11 | 2026-07-10 18:12 | 2026-07-11 | 2026-07-11 16:22 |  |  |  |  | 2026-07-14 18:11 | 2026-07-19 |  | 2026-07-28 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-31 |  |  |  | 2026-08-22 |  | 2026-08-24 |  | 2026-08-25 | [5 empty] | 2026-07-10 | 2026-07-14 18:10 | 2026-04-24 | 2026-04-30 12:44 | Site is RTMI | 2026-04-11 | 2026-04-12 11:41 | 1243979 | 221217 | 0 | 0 | 1267614.3686 | 206823 | 1267614.3686 | 206823 | 2026-07-09 17:50:16 +0530 | Sk Amirul Ali | Final Estimate Check: | 2026-07-09 17:48:18 +0530 | Sk Amirul Ali | 3DQA | 2026-07-09 17:48:02 +0530 | Sk Amirul Ali |  | 2026-05-01 | 2026-04-30 12:51 | 2026-06-26 | 2026-06-25 11:53
19417 | Turnkey | 2026-01-01 | Bhavin J Patel |  | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 2158381 | 9999 | 0 | 0 | 0 | 91 | 0 | 205839 | 215838 | 950165 | 776540 |  |  | 2026-04-11 | 2026-04-12 12:26 | 2026-04-15 | 2026-04-15 15:41 | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-05-18 |  | 2026-05-26 |  | 2026-05-27 |  |  |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 | [6 empty] | 2026-06-24 |  | 2026-07-03 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-06-04 |  | 2026-05-13 |  | Unknown | 2026-04-11 | 2026-04-12 12:22 | 0 | 0 | 0 | 0 | 0 | 0 | 1829136 | 329244 | 2026-06-05 12:42:32 +0530 | Meet Shah | Some Image was uploaded | 2026-04-14 15:22:29 +0530 | Khushi Khandelwal | DCM: 3BHK 1746SQFT- Super builtup Carpet-1304 SqftÂ RERA-1056 sqft 6 members-Joint family EAST WEST FACINGÂ LIVING ROOM- Shoe unit Main door panellingÂ Dining -6 seaterÂ Partition at entranceÂ Crockery unit False ceilingÂ 3 seater + 2 accent chairÂ Mandir unit in corner beside sofaÂ TV unit- modern unit sleek drawerÂ Display unit for trophy swing provision KITCHENÂ Stove on opp. platformÂ Appliances-Microwae, OTG, mixer juicer blender, chimney Sliding doorÂ BEDROOM-01 (Parent's bedroom) Wardrobe-provision for godrejÂ Bed-queen sizeÂ Side tableÂ TV wallÂ False ceilingÂ DresserÂ BEDROOM-02 (Master bedroom) WardrobeÂ bed queen sizeÂ DresserÂ TV Unit/wallÂ Side tableÂ Studio type set upÂ False ceilingÂ BEDROOM-03 (CHILDREN BEDROOM) (19/12 YO) Bed Wardrobe- Glass shuttersÂ Â Study tableÂ Mirror full heightÂ Display shelfÂ Bean bagÂ False ceilingÂ | 2026-04-14 14:02:32 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-05-18 |  | 2026-05-25
19419 | Turnkey | 2026-01-01 | Mr. Mahesh | Mahindra Eden | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Hold | Preproduction | Site Readiness 1 | 1040674 | 275496 | 1347807 | 0 | 0 | 4 | 8 | 0 | 0 | 362961 | 402216.8 |  |  | 2026-04-12 | 2026-04-17 18:11 | 2026-04-17 | 2026-04-17 18:19 | 2026-04-20 | 2026-04-22 12:11 | 2026-07-03 | 2026-07-03 19:32 | 2026-09-04 |  | 2026-09-11 |  | 2026-04-22 | 2026-04-27 12:33 | 2026-04-23 | 2026-05-01 13:56 | 2026-05-01 | 2026-05-06 14:05 | 2026-05-09 | 2026-05-09 19:13 |  |  |  |  | 2026-06-22 | 2026-06-22 17:23 | 2026-09-06 |  | 2026-09-07 |  |  |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 | [6 empty] | 2026-10-05 |  | 2026-10-14 |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-17 |  |  |  | 2026-11-08 |  | 2026-11-10 |  | 2026-11-11 | [5 empty] | 2026-09-15 |  | 2026-05-10 | 2026-07-03 19:17 | Site is Non-RTMI | 2026-04-12 | 2026-04-13 19:47 | 1142209 | 205597 | 0 | 0 | 0 | 0 | 1135991.616 | 187574 | 2026-06-23 12:44:07 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-06 14:04:00 +0530 | Sanjana Swami |  | 2026-05-02 13:55:39 +0530 | Sanjana Swami | Soft Possession - September 2026 Site is not accessible for IMs 1st DEM - End of May 2026, as customer is travelling 10% payment will be done by 11th May 2026 Clear with project stages and payment milestones Checklist and timelines are clear Transaction will be B2C self-funding Client said he will be doing civil work at site, but he is not sure what the civil work will be, so deviation is required Client mentioned that he has seen a 25% offer on the website, however, the overall project quotation does not reflect the same benefit | 2026-07-04 | 2026-07-03 19:33 | 2026-09-05 |  | Under Construction | 2026-09-01
19420 | Turnkey | 2026-01-01 | Shilpa Muniraju | Independent House | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Priyanka Mathur | [5 empty] | Pulivarthi Nirosha |  | Hold | Design | DEM1 | 1569076 | 313815 | 2181429 | 0 | 0 | 27 | 55 | 0 | 0 | 680223 | 575037.6 |  |  | 2026-04-12 | 2026-04-12 13:25 | 2026-04-21 | 2026-04-21 10:41 | 2026-04-24 | 2026-04-21 11:49 | 2026-12-02 |  | 2026-12-06 |  | 2027-01-06 |  | 2026-04-14 | 2026-04-20 19:19 | 2026-04-22 | 2026-04-23 19:12 | 2026-04-23 | 2026-04-24 14:40 | 2026-05-08 | 2026-05-08 11:19 |  |  |  |  | 2026-05-18 | 2026-05-18 18:48 | 2027-01-01 |  | 2027-01-02 |  |  |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-20 |  | 2027-01-21 | [6 empty] | 2027-02-08 |  | 2027-02-17 |  | 2027-02-16 |  | 2027-02-17 |  | 2027-02-18 |  | 2027-02-20 |  |  |  | 2027-03-14 |  | 2027-03-16 |  | 2027-03-17 | [5 empty] | 2027-01-10 |  | 2026-05-09 | 2026-05-16 11:00 | Site is RTMI | 2026-04-12 | 2026-04-12 13:23 | 1848669 | 332760 | 0 | 0 | 0 | 0 | 1848668.61 | 307994 | 2026-05-21 12:48:49 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-21 12:42:24 +0530 | Abhinandan K S | Hold period extended till end of December 2026 with the Price protection post collecting the 20% payment as per the Net quote. Deviation approval taken from CSO- Dipen Shah and posted here in Notes section | 2026-05-16 11:26:22 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-12-03 |  | 2026-12-07 |  | Under Construction | 2026-07-01
19421 | Turnkey | 2026-01-01 | Jingal Doshi | Lodha Imperia | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 3556569 | 9999 | 0 | 0 | 0 | 87 | 0 | 345658 | 355657 | 1450019 | 1395236 |  |  | 2026-04-12 | 2026-04-12 13:15 | 2026-04-19 | 2026-04-19 14:51 | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-12 | 2026-04-12 13:05 | 0 | 0 | 0 | 0 | 0 | 0 | 3014042 | 542527 | 2026-04-12 23:07:10 +0530 | Nishtha Valawalkar |  | 2026-04-12 13:18:25 +0530 | Nishtha Valawalkar | 3 BHK Lodha Imperia Budget Put - 25L Budget Expectation Setting - 45L 15G silver coin Civil:(15L) 3 Wshroom tile changing Italian Marble entire house balcony extension Interior can go 30 35 Client can spend post negotiation 35 to 38 lacs |  |  |  | 2026-04-30 |  | 2026-05-07
19422 | Turnkey | 2026-01-01 | Indranil Pawar (Indranath Gurunath Pawar) | Midtown bay Prescon | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Suraj Jaiswar | Rizwan Mistry | Murali S | Harshaan Tiku | Aakash Gaikwad | Active | Production | Dispatch Due | 1435354 | 1435354 | 1394363 | 0 | 1535354 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-12 | 2026-04-13 14:45 | 2026-04-13 | 2026-04-18 21:31 | 2026-04-21 | 2026-04-21 15:58 | 2026-05-03 | 2026-04-30 00:06 | 2026-05-28 | 2026-05-27 18:17 | 2026-06-11 | 2026-06-11 19:12 | 2026-04-21 | 2026-04-21 18:40 | 2026-04-22 | 2026-04-22 18:04 | 2026-04-22 | 2026-04-24 17:33 | 2026-04-26 | 2026-04-26 18:53 |  |  |  |  | 2026-04-30 | 2026-05-11 16:04 | 2026-05-19 | 2026-05-19 18:48 | 2026-05-20 | 2026-05-19 18:48 |  |  | 2026-06-14 | 2026-06-19 17:27 | 2026-06-20 | 2026-06-20 12:27 | 2026-06-21 | 2026-06-20 16:30 | 2026-06-21 | 2026-06-21 12:45 |  |  |  |  | 2026-06-23 22:35 | 2026-07-01 | 2026-06-30 20:07 | 2026-07-10 | 2026-07-08 19:39 | 2026-07-09 | 2026-07-10 14:29 | 2026-07-08 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-09-02 |  | 2026-09-02 |  | 2026-09-04 | [5 empty] | 2026-06-20 | 2026-06-23 22:34 | 2026-04-27 | 2026-04-29 23:46 | Site is RTMI | 2026-04-12 | 2026-04-13 14:44 | 1183951 | 210412 | 0 | 0 | 1624058.2679 | 267765 | 1624058.2679 | 267765 | 2026-07-13 10:45:36 +0530 | Suraj Jaiswar | Execution: Electrical work is in progress. cx. dependency :- AC piping Work. Site ready for modular- 18th | 2026-07-09 18:57:11 +0530 | Avinash Jaiswal | Added 10K against referral voucher | 2026-07-08 22:11:52 +0530 | Suraj Jaiswar | Execution: Floor covering work done. Electrical work is in progress. Blocker:- AC piping not done from CX. side. We can't start the pelmet work. | 2026-05-01 | 2026-04-30 00:08 | 2026-05-28 | 2026-05-27 18:18
19423 | Turnkey | 2026-01-01 | Satish Kini | rustomjee eden | MUM - GOR | Yes | Batskhem Marpna | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Umang Shah |  | Active | Preproduction | DEM2 | 1368513 | 273703 | 1780193 | 0 | 0 | 24 | 31 | 0 | 0 | 602920 | 491890 |  |  | 2026-04-12 | 2026-04-12 13:35 | 2026-04-15 | 2026-04-15 12:41 | 2026-04-21 | 2026-04-21 19:44 | 2026-06-14 | 2026-06-14 20:18 | 2026-06-20 |  | 2026-06-27 |  | 2026-04-21 | 2026-04-23 19:35 | 2026-04-22 | 2026-04-24 12:30 | 2026-04-24 | 2026-04-25 13:18 | 2026-05-02 | 2026-05-02 19:31 |  |  |  |  | 2026-06-14 | 2026-06-21 13:20 | 2026-06-22 |  | 2026-06-23 |  |  |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 | [6 empty] | 2026-07-21 |  | 2026-07-30 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-02 |  |  |  | 2026-08-24 |  | 2026-08-26 |  | 2026-08-27 | [5 empty] | 2026-07-01 |  | 2026-06-01 | 2026-06-14 20:12 | Site is RTMI | 2026-04-12 | 2026-04-12 13:35 | 1511440 | 268753 | 0 | 0 | 0 | 0 | 1497506.1225 | 244090 | 2026-06-21 14:08:36 +0530 | Batskhem Marpna | Minutes of Meeting held on Date: 21.06.2026 *MOM- Satish Kini- Dated: 21.06.2026* Living/ dining All set Remove the bench Kitchen: All set Janitor unit in the utility Sage green palette TV Room: Mandir 2'5' width TV Drawer width changed All set Kids room: 4'5 Width bed Study setup Bouldering/climbing setup Butter yellow and blue palette Master bedroom: Mirror on the wall adjacent to the wardrobe Two small side tables Subtle minimal wall design behind the bed Powder room: Vanity unit Full mirror Kids bath: Vanity unit Full wall vanity unit with mirror with light Master bath: Vanity unit Full wall vanity unit with mirror with light Note to be discussed: False ceiling designs to be shown, All rooms with colour theme and Colour selection. Thanks, Batskhem | 2026-05-02 19:33:32 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-30 14:00:33 +0530 | Reshma Melanta | CALLD THE CLIENT NO ANSWER ADDED MYSELF TO THE GROUP | 2026-06-15 | 2026-06-14 20:21 | 2026-06-21 |  | Under Construction | 2026-07-31
19425 | Turnkey | 2026-01-01 | Mr Raja Ram Shivane | Sky City | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar |  |  | Yash Metha | Aditya Vikram |  | Prashant Panigrahi | Prasad Bhivaji Hande | Active | Preproduction | DEM2 | 1100040 | 220008 | 1466548 | 0 | 0 | 21 | 17 | 0 | 0 | 447584 | 432447.6 |  |  | 2026-04-12 | 2026-04-14 14:07 | 2026-04-21 | 2026-04-21 12:07 | 2026-04-24 | 2026-04-21 15:08 | 2026-06-09 | 2026-05-30 13:42 | 2026-07-04 |  | 2026-07-11 |  | 2026-04-21 | 2026-04-21 19:03 | 2026-04-22 | 2026-04-21 19:40 | 2026-04-21 | 2026-04-22 11:17 | 2026-04-24 | 2026-04-24 17:04 |  |  |  |  | 2026-05-30 | 2026-06-03 18:07 | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-05 | 2026-05-30 12:48 | Site is RTMI | 2026-04-12 | 2026-04-14 14:07 | 1242837 | 223710 | 0 | 0 | 0 | 0 | 1233762.4149 | 205557 | 2026-07-04 14:16:36 +0530 | Honey Thakkar | DDM closed waiting for site possession for cross measurements | 2026-07-02 19:57:29 +0530 | Anamika Dolai | Civil work is still going on, will be completed in 4 days dated: 7th of july. | 2026-06-03 17:00:24 +0530 | Anil Kuwar | Others: Cx is getting the possession by june end.Need to keep project onhold | 2026-05-31 | 2026-05-30 13:45 | 2026-07-05
19426 | Turnkey | 2026-01-01 | Devang Soni | Hum Durga | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 1076210 | 9999 | 0 | 0 | 0 | 53 | 0 | 97622 | 107621 | 484574 | 376394.4 |  |  | 2026-04-12 | 2026-05-23 19:06 | 2026-05-23 | 2026-05-23 19:27 | 2026-04-12 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-04-12 | 2026-05-23 19:04 | 0 | 0 | 0 | 0 | 0 | 0 | 912042 | 164167 | 2026-05-23 19:26:00 +0530 | Sakshi Hire | DCM: Customer and Project Profile1. Name of the customer DEVANG 2. Profession JWELLER 3. Project Name/Tower Name/Flat Number hum durga 4. Typology (1BHK, 2BHK, 3BHK, etc) 1 5. Site Access Date 2026-05-14 6. Possession Date 2026-05-14 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 9 Customer Preferences8. Who will be living in the house? Nuclear Family 9. What activities do you usually prefer at your home ? Relaxing and Unwinding 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] na 11. Mention basic vastu principles agreed for integration in design, if any na 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) na Upload reference images 14. Any absolute no-go styles colours or materials black colour 15. Do you have any existing furniture that must be accommodated? na 13. Do you want the design to reflect any personal story, cultural influence, or special memory na ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? 2. Must-have furniture or features? TV unit, Puja unit, Sofa 3. Choose your decor inspirations Plants 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Bottom Storage Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any na 2. Other commitments made by Bonito to customer, if any n 3. What are offers committed to customers? NA 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date NA 6. Additional Requirements (Mention any requirements from customer not covered in the form) NA 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 9 | 2026-04-15 18:38:38 +0530 | Manasi Patil | Some Image was uploaded |  |  |  | 2026-06-03 |  | 2026-06-10
19427 | Turnkey | 2026-01-01 | Chennakeshavan C | Birla Tissya | BNG - HRBR | Yes |  | Parasa Sri | [8 empty] | Active | Design | DEM1 | 1069273 | 136560 | 1424720 | 0 | 0 | 68 | 0 | 0 | 77295 | 450477 | 404941.6 |  |  | 2026-04-12 | 2026-04-22 10:50 | 2026-04-22 | 2026-04-22 12:26 | 2026-04-22 | 2026-04-22 13:03 | 2026-08-05 |  | 2026-08-12 |  | 2026-08-19 |  | 2026-04-22 | 2026-04-24 12:09 | 2026-04-23 | 2026-05-08 14:50 | 2026-05-08 | 2026-05-08 17:33 | 2026-05-10 | 2026-05-10 19:55 |  |  |  |  | 2026-08-06 |  | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-08-01 |  | Unknown | 2026-04-12 | 2026-04-13 12:03 | 1207390 | 217330 | 0 | 0 | 0 | 0 | 1181843.247 | 195143 | 2026-05-14 15:59:19 +0530 | Parasa Sri | Welcome call done. Oc by june - 2026 | 2026-05-08 17:32:37 +0530 | Sanjana Swami | Possession - June 2026 Client will get the OC by the end of May 2026 Site is not accessible for IMs and the client wants the 1st DEM to be done by June 2026 after OC 10% will be done by 18th May 2026 Clear with the timelines, offers and payment milestones Checklist clear Transaction will be B2C self-funding. | 2026-05-08 14:49:43 +0530 | Pradeep Kumar | Some Image was uploaded | 2026-08-06 |  | 2026-08-13 |  | Under Construction | 2026-06-30
19428 | Turnkey | 2026-01-01 | Sunesh | Pelican Square | BNG - HSR | No Estimate | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-12 | 2026-04-12 15:16 | 2026-04-13 |  | 2026-04-14 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-04-14 |  | 2026-04-15 |  | 2026-04-15 |  | 2026-04-16 | [5 empty] | 2026-04-22 |  | 2026-04-30 |  | 2026-05-01 |  |  |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-11 | [6 empty] | 2026-05-29 |  | 2026-06-07 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-10 |  |  |  | 2026-07-02 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-05-09 |  | 2026-04-17 |  | Unknown | 2026-04-12 | 2026-04-12 15:12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-22 |  | 2026-04-29
19431 | Turnkey | 2026-01-01 | Priya Vivek Naik Naik | Kalpataru Vivant | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar |  | Fareed Shaikh | Uday Yadruk | Rizwan Mistry |  | Rashmita Das | Sunil Poojary | Active | Design | 60% Payment | 1174566 | 527812 | 1278124 | 0 | 0 | 5 | 0 | 0 | 0 | 229464 | 417289.6 |  |  | 2026-04-12 | 2026-04-22 13:17 | 2026-04-12 | 2026-04-22 13:22 | 2026-04-23 | 2026-04-23 12:59 | 2026-06-13 | 2026-06-13 11:03 | 2026-06-30 | 2026-07-02 19:37 | 2026-07-02 | 2026-07-02 20:21 | 2026-04-23 | 2026-04-24 18:57 | 2026-04-24 | 2026-04-28 16:25 | 2026-04-28 | 2026-04-29 14:22 | 2026-05-13 | 2026-05-13 18:27 |  |  |  |  | 2026-06-13 | 2026-06-26 16:21 | 2026-07-02 | 2026-06-30 01:19 | 2026-07-01 | 2026-06-30 01:51 |  |  | 2026-07-04 | 2026-07-09 14:26 | 2026-07-10 | 2026-07-10 14:13 | 2026-07-11 | 2026-07-10 20:23 | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-10 |  | 2026-05-14 | 2026-06-12 18:41 | Site is RTMI | 2026-04-12 | 2026-04-12 16:26 | 1083156 | 194968 | 0 | 0 | 0 | 0 | 1269933.7966 | 209679 | 2026-06-26 13:32:13 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-24 18:27:24 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-12 13:06:36 +0530 | Anjali Jain | DDM1: DEM 1 Living room Need to check For tv unit and mandir acc to the directionÂ L shape sofaÂ Wardrobe need to remove 1 shelves from bottomÂ Need to add 1 shelves on topÂ with lock on drawers as well as wardrobe Mandir need to ConsiderÂ 2 stepsÂ Need to add one drawer on top of shutter cabinet Mandir need to open Master bedroom Â Need to add mirror unit Upto Lintel level from side table Wardrobe need to add 2 shelves instead of hangerÂ Drawer need to add both the sideÂ Need to check the bed directionÂ Kitchen No need to change as per net | 2026-06-14 | 2026-06-13 11:07 | 2026-07-03 | 2026-07-02 19:38
19432 | Turnkey | 2026-01-01 | Karan Hunurkar | Nandanvan Homes II | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Rushika More | [5 empty] | Hitesh Rawal |  | Active | Prospect | DCM Due | 3429846 | 9999 | 0 | 0 | 0 | 94 | 0 | 332986 | 342985 | 1547646 | 1196231.2 |  |  | 2026-04-12 | 2026-04-12 21:17 | 2026-04-22 | 2026-04-22 12:14 | 2026-04-18 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-12 | 2026-04-12 21:14 | 0 | 0 | 0 | 0 | 0 | 0 | 2906649 | 523196 | 2026-04-14 11:47:59 +0530 | Karuna Shinde | Some Image was uploaded | [6 empty] | 2026-05-03 |  | 2026-05-10
19433 | Turnkey | 2026-01-01 | Omkar Kulkarni | Regency Luxuria | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | DCM Due | 3683371 | 9999 | 0 | 0 | 0 | 92 | 0 | 358338 | 368337 | 1615485 | 1331212 |  |  | 2026-04-12 | 2026-04-14 11:08 | 2026-05-07 | 2026-05-07 14:08 | 2026-04-19 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-05-18 |  | 2026-05-26 |  | 2026-05-27 |  |  |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 | [6 empty] | 2026-06-24 |  | 2026-07-03 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-06-04 |  | 2026-05-13 |  | Unknown | 2026-04-12 | 2026-04-14 11:04 | 0 | 0 | 0 | 0 | 0 | 0 | 3121501 | 561870 | 2026-04-16 19:40:15 +0530 | Naved Malik | PROPERTYÂ - Regency Luxuria PEOPLEÂ - 2 Adults / 2 Kids / 2 Parents LOCATIONÂ - Dombivali CONFIGURATIONÂ - 2+2 Jodi Flat LIVING ROOM; 3+2 Seater SofaJhoolaDining 6 SeaterTV Unit with Display UnitCrockery / Bar UnitOption for Crockery Unit in BalconyMANDIR ROOM; Mandir Unit on RIght Side Wall while entering FOYER; Shoe Rack unit for 15 - 18 Pairs with Seating space and wall concept. KITCHEN; Modular Base UnitWall UnitLoft UnitCivil work of Breaking and Installation of Platform and Wall tiles.Acrylic Finish CLIENTS BEDROOM; Murphy Bed on South WallWardrobe with Dressing and MirrorFoldable Study KIDS BEDROOM; Queen Size or 2 Single BedWardrobeStudy UnitSome Display Unit for cars and Legos GUEST BEDROOM; 2 Door WardrobeSofa cum Bed PARENTS BEDROOM; Seating chair in cornerBedWardrobe BATHROOMS; Base and Wall vanity Units SERVICES; PaintingFalse CeilingElectricalCivil work - Kitchen NOTEÂ - Indian Traditional yet Minimalistic Style of Interior | 2026-04-14 11:14:25 +0530 | Subhan Khan | Some Image was uploaded |  |  |  | 2026-05-18 |  | 2026-05-25
19434 | Turnkey | 2026-01-01 | Krishna C Bhat | Prescon Midtown Bay | MUM - GOR | Yes | Anjali Jain | Manzoor Shaikh | Kashmira Nerurkar | Ehtesham Bhati | Anamika Ghate | Suraj Jaiswar | Rizwan Mistry | Murali S | Harshaan Tiku | Siddhesh Gujrathi | Active | Preproduction | Procurement | 1143421 | 728897 | 1418930 | 0 | 1177442 | 12 | 0 | 0 | 0 | 0 | 414524 |  |  | 2026-04-12 | 2026-04-13 14:44 | 2026-04-21 | 2026-04-21 11:15 | 2026-04-22 | 2026-04-22 12:59 | 2026-05-10 | 2026-05-10 12:54 | 2026-06-11 | 2026-06-14 19:17 | 2026-06-14 | 2026-06-14 19:30 | 2026-04-12 | 2026-04-20 15:27 | 2026-04-23 | 2026-04-24 12:21 | 2026-04-24 | 2026-04-24 13:31 | 2026-04-29 | 2026-04-29 18:45 |  |  |  |  | 2026-05-10 | 2026-05-25 18:10 | 2026-06-13 | 2026-06-12 12:44 | 2026-06-13 | 2026-06-13 00:40 |  |  | 2026-06-19 | 2026-06-23 16:55 | 2026-06-23 | 2026-06-23 20:24 | 2026-06-24 | 2026-06-26 15:11 | 2026-06-27 | 2026-06-30 17:28 |  |  |  |  | 2026-07-03 17:23 | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-23 | 2026-07-02 17:57 | 2026-04-30 | 2026-05-10 12:05 | Site is RTMI | 2026-04-12 | 2026-04-13 14:43 | 1202483 | 216447 | 0 | 0 | 1394181.3435 | 234143 | 1394181.8418 | 228954 | 2026-07-13 18:56:34 +0530 | Suraj Jaiswar | Execution: Material delivered on 13th July. false ceiling work will start from 14th july. Site ready for modular- 21st July | 2026-07-13 10:41:09 +0530 | Suraj Jaiswar | Execution: Fitout form not filled, cx. dependency. Material will be deliver by today. | 2026-06-24 11:58:51 +0530 | Manzoor Shaikh | Out called the customer to prep on the next step post approval of the docket, said he has some pointers to discuss with Shweta and will be coming to the EC in a day or 2, On the same day he will approve and clear the due along with the key. Informed tentatively due amount would be Rs. 5,39,125 | 2026-05-11 | 2026-05-10 12:58 | 2026-06-15 | 2026-06-14 19:19
19435 | Turnkey | 2026-01-01 | Bharatesh Dinakar | Navavajra | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2179269 | 9999 | 0 | 0 | 0 | 88 | 0 | 207928 | 217927 | 894286 | 849128.8 |  |  | 2026-04-12 | 2026-04-17 18:14 | 2026-04-13 | 2026-04-18 12:15 | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-12 | 2026-04-12 17:57 | 0 | 0 | 0 | 0 | 0 | 0 | 1846838 | 332430 | 2026-05-04 15:51:57 +0530 | Rhea Rathod | DCM: Possession - Sept Family of 5Â Property - Nava Vajra Profession - Software engineerÂ North facing apartment - Ground floor Theme - Unsure FoyerÂ - Shoe rack - 3' wide Living - TV unit - Floor mounted - Tv unit on east wall - Wall concept on the south wall- buddha statue wall decor - L shaped sofa - False ceiling Toilet - - Mirror - Vanity unit Kitchen - - Single door fridge - L shaped kitchen - Hob east facing - RO unit, Gas cylinder unit - Base cabinets, loft, wall units Utility - - Top unit Dining area- - 4 seater dining table - Pooja unit - 3 feet depth - Sit and pray Master bedroom - - Bay windowÂ - Bed to be included- loose furniture king size - Sliding Wardrobe with loft - Study table - Mirror on the wardrobe side Bathroom - - Vanity and mirror Kid's bedroom - Sliding wardrobe with loft - Wallpaper - kids collection | 2026-04-28 17:37:26 +0530 | Losii Athisa | Some Image was uploaded |  |  |  | 2026-05-03 |  | 2026-05-10
19436 | Turnkey | 2026-01-01 | Khushipreet Kaur | Sipani Royal Haritage | BNG - HSR | Yes | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 1371554 | 9999 | 0 | 0 | 0 | 87 | 0 | 127156 | 137155 | 557341 | 539902 |  |  | 2026-04-12 | 2026-04-19 10:10 | 2026-05-02 | 2026-05-11 23:38 | 2026-05-12 |  | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-05-20 |  | 2026-05-28 |  | 2026-05-29 |  |  |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 | [6 empty] | 2026-06-26 |  | 2026-07-05 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-06-06 |  | 2026-05-15 |  | Unknown | 2026-04-12 | 2026-04-19 10:08 | 0 | 0 | 0 | 0 | 0 | 0 | 1164621 | 206932 | 2026-05-02 16:49:12 +0530 | Maspi Das | Cx name : Khushpreet Kaur Address: Chandapura Property - Sipani Royal Heritage Prof : IT 2BHK Theme - Mostly browns Entrance facing : North Budget -Â 8L Members - 2 Kids- 1 CDP meeting- 3rd May (after 12) Foyer-Â 1'-1'6" Shoe rack with seating With Wall design with mirror and wallpaper (can play with shapes) (No floral) Living area- Sofa wall (has little bit nish around 2") Reference taken no beading Dining area-Â Crockery unit ref taken Kitchen - Utility wall is not there L-shaped kitchen with Parallel Appliance unit tall unit - half crockery & Pantry (fluted and laminate) Spice rack under the wall unit Paneling for the entrance 3' Sink Pooja unit on the kitchen wall (can extend the wall with POP if needed) KBR- Study unit ref taken Wardrobe re shared by client (Mirror on shutter) MBR- Ref taken Tall unit shown in the 1st video should face the room/bed wardrobe and dresser as per planÂ Very minimal wall design just half paneling can be considered **Window need to hide right opposite to the door** MBR - Vanity unit ref taken common vanity -Â Storage behind mirror Vanity unit | [6 empty] | 2026-05-20 |  | 2026-05-27
19437 | Turnkey | 2026-01-01 | Shashi Kiran | Raki Amaryllis | BNG - HRBR | Yes | Shahid Afridi | Reshma Melanta | Shibin Lal | [5 empty] | Raghavendra S |  | Active | Preproduction | DEM2 | 1773895 | 274999 | 1661539 | 0 | 0 | 66 | 0 | 0 | 0 | 820329 | 678566.8 |  |  | 2026-04-12 | 2026-04-15 11:31 | 2026-04-15 | 2026-04-22 11:47 | 2026-04-25 | 2026-04-22 12:10 | 2026-05-06 | 2026-05-05 16:31 | 2026-07-06 |  | 2026-07-13 |  | 2026-04-22 | 2026-04-23 20:34 | 2026-04-23 | 2026-04-24 14:01 | 2026-04-24 | 2026-04-24 15:01 | 2026-04-30 | 2026-04-30 18:19 |  |  |  |  | 2026-05-05 | 2026-05-10 18:58 | 2026-07-08 |  | 2026-07-09 |  |  |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 | [6 empty] | 2026-08-28 |  | 2026-09-06 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-09 |  |  |  | 2026-10-01 |  | 2026-10-03 |  | 2026-10-04 | [5 empty] | 2026-08-08 |  | 2026-05-10 | 2026-05-05 16:27 | Site is RTMI | 2026-04-12 | 2026-04-12 18:24 | 1408083 | 253455 | 0 | 0 | 0 | 0 | 1869744.2733 | 308729 | 2026-06-10 14:43:14 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-07 19:44:29 +0530 | Yogesh B | Some Image was uploaded | 2026-05-05 17:50:33 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-06 | 2026-05-05 16:31 | 2026-07-07 |  | RTMI
19439 | Turnkey | 2026-01-01 | Paresh Purvi naik Naik | Anantam luxury | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Asif Shaikh | Akshat Shrivastava | Murali S | Mustufa Sohagpurwala | Shailendra Mishra | Active | Installation | Execution | 886478 | 886497 | 1347067 | 0 | 886478 | 12 | 6 | 0 | 0 | 0 | 0 |  |  | 2026-04-12 | 2026-04-12 19:17 | 2026-04-17 | 2026-04-17 11:54 | 2026-04-19 | 2026-04-19 18:53 | 2026-04-28 | 2026-04-27 15:03 | 2026-05-08 | 2026-05-07 19:11 | 2026-05-16 | 2026-05-15 18:37 | 2026-04-19 | 2026-04-20 15:34 | 2026-04-20 | 2026-04-20 19:30 | 2026-04-20 | 2026-04-21 12:44 | 2026-04-23 | 2026-04-23 12:04 |  |  |  |  | 2026-04-28 | 2026-04-28 19:50 | 2026-05-10 | 2026-05-15 18:30 | 2026-05-16 | 2026-05-15 18:31 |  |  | 2026-05-16 | 2026-05-21 11:12 | 2026-05-21 | 2026-05-21 13:42 | 2026-05-22 | 2026-05-21 15:41 | 2026-05-22 | 2026-05-21 16:26 |  |  |  |  | 2026-05-23 18:00 | 2026-06-01 | 2026-05-31 18:29 | 2026-06-11 | 2026-06-09 17:10 | 2026-06-10 | 2026-06-24 12:57 | 2026-06-22 | 2026-07-02 13:56 | 2026-06-14 | 2026-07-03 14:40 | 2026-07-09 | 2026-07-11 12:41 |  |  | 2026-07-01 |  | 2026-07-03 |  | 2026-08-05 | [5 empty] | 2026-05-21 | 2026-05-22 22:06 | 2026-04-24 | 2026-04-27 14:19 | Site is RTMI | 2026-04-12 | 2026-04-12 19:16 | 1141582 | 205484 | 0 | 0 | 889726.052 | 153530 | 889726.052 | 153530 | 2026-07-12 19:59:37 +0530 | Asif Shaikh | Execution: Modular star date - 10th July. Modular end date - 25th July. Custom carpentry work - 25th July (MDF beading & flat patti ) Wallpaper - Under Designer approval . | 2026-06-28 19:51:47 +0530 | Asif Shaikh | Execution: Furniture is in transit & will be delivered in 2 ti 3 days | 2026-06-14 15:01:23 +0530 | Asif Shaikh | Some Image was uploaded | 2026-04-28 | 2026-04-28 11:33 | 2026-05-08 | 2026-05-07 19:12
19441 | Turnkey | 2026-01-01 | Ayan Dalal | Entity the Edge | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 1663809 | 9999 | 0 | 0 | 0 | 84 | 0 | 156382 | 166381 | 702990 | 628057.2 |  |  | 2026-04-12 | 2026-04-14 11:51 | 2026-04-22 | 2026-04-22 12:38 | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-12 | 2026-04-12 19:40 | 0 | 0 | 0 | 0 | 0 | 0 | 1458239.9972 | 253801 | 2026-04-14 15:35:46 +0530 | Janvi Nagdeo | Some Image was uploaded | [6 empty] | 2026-04-30 |  | 2026-05-07
19442 | Turnkey | 2026-01-01 | Vipul Aggarwal | Pursuit of a Radical Rhapsody [Total Environment] | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 3437077 | 9999 | 0 | 0 | 0 | 94 | 0 | 333709 | 343708 | 1374831 | 1374830.8 |  |  | 2026-04-12 | 2026-04-12 19:50 | 2026-04-16 | 2026-05-15 11:07 | 2026-05-10 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-06-08 |  | 2026-08-04 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-05-26 |  | 2026-06-03 |  | 2026-06-04 |  |  |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 | [6 empty] | 2026-07-07 |  | 2026-08-01 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-01 |  | 2026-08-06 |  |  |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-06-12 |  | 2026-05-21 |  | Unknown | 2026-04-12 | 2026-04-12 19:47 | 0 | 0 | 0 | 0 | 0 | 0 | 2912777 | 524299 | 2026-04-17 17:06:04 +0530 | Aparna | RGM MOMClient Name: Vipul & Divya (Gurgaon) Address: Possession: In next 2 weeks Profession: Engineers Family Members: 2 Theme: As per demo flat (with indoor plants) Entrance Facing: East Budget: 20-25L CDP Date: Sunday, 19th Overall RequirementsDesign to match demo flat aestheticsIncorporate indoor plants across spacesFunctional design with balanced storage and aestheticsEntranceMud closet (shoe rack with maximum storage)Living RoomTV unit with panel + base storage (refer site image flooring)TV provision for 65 / 75Seating: 3-seater + 2 single chairsWall treatment to be designed as per themeDining Area6-seater dining (1 side bench + 1 side chairs)Crockery unit:Base unit with solid shutters onlyTop: mirror / artwork (no wall cabinets)KitchenQuartz countertop (instead of builder-provided granite)Space for double door fridgeOven provision requiredPreferably in tall unitIf not feasible integrate in base unitRO unit:Under counterPositioned on half wall (existing provision)Sink:Single bowl without drain board (on half wall)Gas connection:From utility provide cylinder unitUtilitySink with drain board + base unitGTPT unit above sinkMaster Bedroom (BR1)King size bed with 2 side tablesOpposite wall: highlight designWindow side wall: set of drawersWalk-in wardrobe:Carcass already availableProvide glass shuttersMirror on bathroom wallBathroomChange flooring and wall tilesTo be checked and confirmed with teamBedroom 2 Guest Room3-shutter wardrobe2 study tables (check and plan provision)Queen size bedLong mirror next to side tableBedroom 3 Guest RoomQueen size bed3-shutter wardrobeStudy unitDresser unitÂ | [6 empty] | 2026-05-26 |  | 2026-06-02
19443 | Turnkey | 2026-01-01 | Amit Patel |  | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Foram Joshi |  | Hold | Preproduction | DEM2 | 1375702 | 275140 | 1897278 | 0 | 0 | 16 | 13 | 0 | 0 | 562344 | 538218.4 |  |  | 2026-04-12 | 2026-04-12 19:51 | 2026-04-16 | 2026-04-16 13:06 | 2026-05-24 | 2026-05-26 12:16 | 2026-07-01 | 2026-06-16 16:15 | 2026-07-21 |  | 2026-07-28 |  | 2026-05-26 | 2026-05-27 18:02 | 2026-05-27 | 2026-05-27 18:21 | 2026-05-27 | 2026-06-02 11:47 | 2026-06-06 | 2026-06-06 12:19 |  |  |  |  | 2026-07-02 | 2026-06-14 17:53 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-06-07 | 2026-06-16 15:30 | Site is RTMI | 2026-04-12 | 2026-04-12 19:50 | 1607862 | 289415 | 0 | 0 | 0 | 0 | 1598614.875 | 256759 | 2026-07-02 18:48:00 +0530 | Anil Jagtap | Hold | 2026-06-29 12:38:41 +0530 | Rachna Abhyankar | Hello @~amitpatel008 sir Good AfternoonÂ MINUTES OF MEETING (MOM) PID: 19443 Client: Amit Patel 1. Living Room / Entrance Area Provide ceiling-mounted entrance light points. Design for shoe rack outside the entrance. (Client Scope) TV unit and mandir to be placed on the left side of the entrance with open shelving. Sofa and seating arrangement to be placed on the wall opposite the TV unit. Install a goddess photo/frame on the sofa backdrop wall. Add molding detail near the armchairs. Add a decorative mirror in the dining area. Provide cove lighting, spotlights, and focus lights on ceiling. Create a curved ceiling treatment at the beam location. Install a chandelier in the dining area. 2. Kitchen & Utility Area Main Kitchen Break/modify the existing service counter. Add a tall unit with: Wicker basket storage Mixxi pull-out Microwave provision Add: 1 bottle pull-out Overhead cabinet with profile glass shutters Second Kitchen Break/modify the existing counter as discussed. Utility Area Provide space for grain grinder. Provide grain storage unit. Sink provision required. Loft storage to be provided above the sink. 3. Parents' Bedroom Wardrobe Wardrobe height to be up to door height. Internal configuration: 2 standard bottom drawers 1 accessories drawer 2 clothes drawers Add dry wardrobe provision. Dressing Unit Mirror shape and dimensions to be given. (Client Scope) Furniture Remove bedside table. 4. Walk-in Wardrobe Provide foldable study unit on the right wall with seating and storage. Wardrobe height to be up to door height. Internal Layout Left Side: Same internal configuration as Parents' Room wardrobe. Right Side: Top hanging space. Bottom storage configuration same as Parents' Room wardrobe. 5. Master Bedroom Wardrobe Internal Configuration No hanging provision required. 2 standard bottom drawers. 1 accessories drawer. 1 pencil drawer. 2 clothes drawers. 6. Kids' Room Wardrobe No hanging provision required. Shelves to be provided with equal divisions. Study Area Increase study table storage height up to ceiling level. Wall Decor Add molding detail on the bed-back feature wall. Please Note :- The quotation will vary as per the addition of the components and the materials selection Thanks & regards, Preet KaraniaÂ Interior Designer | 2026-06-16 15:32:02 +0530 | Preet Karania | Some Image was uploaded | 2026-06-17 | 2026-06-16 16:15 | 2026-07-22 |  | Under Construction | 2026-07-31
19444 | Turnkey | 2026-01-01 | Kanush Oberoi | Dosti Mezzo | MUM - GOR | Yes | Zoya Ansari | Reshma Melanta | Kashmira Nerurkar |  | Priyanka Kamble | Nilesh Patel | Rizwan Mistry |  | Saloni Sagwekar | Siddhesh Gujrathi | Active | Preproduction | 2D | 2000453 | 400091 | 2797407 | 2000453 | 0 | 1 | 1 | 0 | 0 | 888901 | 711461.2 |  |  | 2026-04-12 | 2026-04-14 13:21 | 2026-04-12 | 2026-04-15 03:18 | 2026-04-15 | 2026-04-15 14:18 | 2026-05-10 | 2026-05-10 20:01 | 2026-06-22 | 2026-06-21 13:20 | 2026-07-12 | 2026-07-11 19:51 | 2026-04-15 | 2026-04-17 11:35 | 2026-04-16 | 2026-04-19 20:24 | 2026-04-19 | 2026-04-22 18:16 | 2026-04-24 | 2026-04-24 15:50 |  |  |  |  | 2026-05-10 | 2026-05-21 10:43 | 2026-06-21 | 2026-06-19 09:01 | 2026-06-20 | 2026-06-19 12:04 |  |  | 2026-07-15 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-04-25 | 2026-05-10 19:57 | Site is RTMI | 2026-04-12 | 2026-04-14 13:15 | 2370684 | 426723 | 2360951.569 | 381425 | 0 | 0 | 2360951.569 | 381425 | 2026-05-20 12:14:08 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-19 19:03:34 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-10 20:10:41 +0530 | Zoya Ansari | DDM2: Partition to be created in the LR with shoe unit l-shape peripheral False ceiling design in LR Dining Six seater check the size No false ceiling in the kids room just hide the sprinkler small activity area in the kids room pop of colour in the kids room add kitchen cabinets above the washing machine instead of ledge kitchen chimneh has to be with duct no false ceiling in kitchen kitchen loft storage above the fridge sliding door to be provided for kitchen in parents room full height storage in the corner no tv unit in PR In MB fit in the godrej cupboard near the bathroom door create carcass for the godrej cupboard main wardrobe create four shutters in the MB peripheral ceiling in the MB Client is available only on weekends | 2026-05-11 | 2026-05-10 20:12 | 2026-06-22 | 2026-06-21 13:20 | Under Construction | 2026-06-30
19445 | Turnkey | 2026-01-01 | Asish Biswal | SV Polaris | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 2051269 | 9999 | 0 | 0 | 0 | 94 | 0 | 195128 | 205127 | 820508 | 820507.6 |  |  | 2026-04-12 | 2026-04-12 20:14 | 2026-04-23 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-04-12 | 2026-04-12 20:12 | 0 | 0 | 0 | 0 | 0 | 0 | 1738363 | 312905 | 2026-04-15 11:46:28 +0530 | Aparna | Minutes of Meeting (MOM)Client Name: Asish & Binita (Odisha) Profession: IT Possession Timeline: Coming weeks No. of Occupants: 2 Entrance Facing: West Budget: 10 Lakhs CDP Meeting Scheduled: 17th April Design ThemeTo be finalized (suggest: modern / minimal / warm aesthetic based on lifestyle)EntranceShoe rack with integrated seatingFunctional and compact designFoyerHighlight wall with design element (texture / panel / wallpaper)Provision for:Mud closet (long storage)Key holder / utility ledgePooja UnitDesign as per reference imageTabletop height: 900 mmBase storage to be includedLiving RoomTV unit as per reference:Base unit2 tall units with internal shelves + glass shuttersBack panel with integrated lightingSeating:Fabric recliners (3+2 seater)Balcony (Living)Provide 3D design for nowFinal execution to be decided laterDining Area4-seater round dining tableExisting wooden crockery base unit (client-owned)To add:Wall-mounted cabinetLoft storage aboveGuest Bedroom (GBR)WardrobeDresser (client-owned) to be placed sidewiseStudy table (client-owned):Placement: Opposite to bedGBR BalconyJanitor unit in cornerWashing Machine provisionBalcony is extendedMaster Bedroom (MBR)Dresser unit on bathroom wallBase cabinet (NO drawers)Wardrobe opposite to bedProvision for used clothes sectionWindow seatingStudy table + corner storage on bed wallPutul Bedroom (PBR)Queen size bed on bathroom wall (corner placement)Wardrobe with:Used clothes unitMirror on single shutter onlySmall drawer (on kitchen wall side)Study table on window wallBase unit includedBathrooms (All)Vanity base unitMirror with storage provisionKitchenCountertop: Black granite (builder provided)Layout:U-shaped counter (as per reference print)Extended counter opposite fridgeAppliances:Double door fridgeStorage:Roll-up shutter unitEfficient workflow planning requiredÂ | [6 empty] | 2026-05-07 |  | 2026-05-14
19446 | Turnkey | 2026-01-01 | Amit Kumar | Sobha Manhattan | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1009200 | 135575 | 1366480 | 0 | 0 | 12 | 0 | 0 | 66265 | 434627 | 372733.2 |  |  | 2026-04-12 | 2026-04-12 20:15 | 2026-04-23 | 2026-06-30 17:23 | 2026-07-03 | 2026-07-01 14:51 | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-01 | 2026-07-02 16:38 | 2026-07-02 | 2026-07-02 19:39 | 2026-07-02 | 2026-07-03 20:37 | 2026-07-04 | [5 empty] | 2026-07-10 |  | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-07-05 |  | Unknown | 2026-04-12 | 2026-04-12 20:14 | 1161055 | 205425 | 0 | 0 | 0 | 0 | 1151962.888 | 186641 | 2026-07-03 20:36:45 +0530 | Bency Chacko | Address updated - moving OB | 2026-07-03 13:08:28 +0530 | Athul Ajaykumar | Possession Status: Under construction Soft Possession: August or September (Tentative) Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Will update to the sales team * DEM 1 â€“ Tentatively scheduled for next weekend * 10% Payment Stage â€“ Tentatively scheduled for (12th July) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Shoerack Offer May'26 laminate Campaig Free Hob & Chimney Offer PM fee waiver (5%) Design fee waiver (5%) May'26 100% GST waiver Silver Coin Offer Final Closing Value Discussed: 10,09,200 Checklist terms - descoping and agreement terms are cleared Rejections: The address is incomplete. Address needs to be updated | 2026-07-03 11:40:57 +0530 | Athul Ajaykumar | OB Initiated - Ringing (Dialled from Official number) | 2026-07-10 |  | 2026-07-17 |  | Under Construction | 2026-09-30 | 2026-06-30 17:13 | 125576 | Nidhi Shaw
19448 | Turnkey | 2026-01-01 | Abhinav Dubey | Transcon | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 1474533 | 9999 | 0 | 0 | 0 | 92 | 0 | 137454 | 147453 | 671749 | 507877.2 |  |  | 2026-04-12 | 2026-04-14 13:29 | 2026-04-14 | 2026-04-16 12:19 | 2026-04-18 |  | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-04-19 |  | 2026-04-20 |  | 2026-04-20 |  | 2026-04-21 | [5 empty] | 2026-04-27 |  | 2026-05-05 |  | 2026-05-06 |  |  |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-16 | [6 empty] | 2026-06-03 |  | 2026-06-12 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-15 |  |  |  | 2026-07-07 |  | 2026-07-09 |  | 2026-07-10 | [5 empty] | 2026-05-14 |  | 2026-04-22 |  | Unknown | 2026-04-12 | 2026-04-12 21:10 | 0 | 0 | 0 | 0 | 0 | 0 | 1251891 | 222641 | 2026-04-16 12:06:04 +0530 | Rishika Malviya | Some Image was uploaded | 2026-04-14 16:21:30 +0530 | Saloni Sagwekar | Some Image was uploaded |  |  |  | 2026-04-27 |  | 2026-05-04
19449 | Turnkey | 2026-01-01 | Binay Pathak | L&T Seawoods | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 971820 | 9999 | 971820 | 0 | 0 | 89 | 0 | 87183 | 97182 | 388728 | 388728 |  |  | 2026-04-12 | 2026-04-14 14:10 | 2026-04-15 | 2026-04-15 17:39 | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-04 |  | 2026-05-05 | [5 empty] | 2026-05-11 |  | 2026-05-19 |  | 2026-05-20 |  |  |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 | [6 empty] | 2026-06-17 |  | 2026-06-26 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-29 |  |  |  | 2026-07-21 |  | 2026-07-23 |  | 2026-07-24 | [5 empty] | 2026-05-28 |  | 2026-05-06 |  | Unknown | 2026-04-12 | 2026-04-14 14:09 | 823576 | 148243 | 0 | 0 | 0 | 0 | 823576 | 148243 | 2026-04-15 17:32:53 +0530 | Krutika Vernekar | DCM: 2BHK LNT WEST SQ G(101) Amber 1305 5 MEMBERS ( Husband , Wife , Daughter, Son , Mother ) Existing Furniture : 2 Beds ( 6' * 6" )- (5' * 6') (Sheesham ) Study : 4' * 1', Sofa ( 5'*6') Indian Theme + Blue + Rose Color Pallete Entry Name Plate Design Shelf in entry Base Units Shoerack (15 Pairs) Livin Room : Dining 6 Seater , DB board on Tv wall , Panel . 2 fan 1 Chandelier Kitchen : MNGL available, Appliances ; GAS Stove , 2 burner , sandwich maker , Microwave, Airfryer Matka Provision . Bathroom : Vanity , open Niche Storage Unit . MB : Passage Mouldings , wardobe , side table ,Wallpaper + Mirror Pullout Folding Study Guest Room : Wardobe + Study ( existing ) | 2026-04-15 16:39:02 +0530 | Prashant Panigrahi | Some Image was uploaded |  |  |  | 2026-05-11 |  | 2026-05-18
19451 | Turnkey | 2026-01-01 | Ramya BS | Durga Nivasa | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Lost | Design | DEM1 | 783110 | 94999 | 949976 | 0 | 0 | 83 | 0 | 0 | 61623 | 318468 | 308020.4 |  |  | 2026-04-12 | 2026-04-17 18:10 | 2026-04-18 | 2026-04-18 16:57 | 2026-04-21 | 2026-04-22 11:10 | 2027-10-01 |  | 2027-10-08 |  | 2027-10-15 |  | 2026-04-22 | 2026-04-23 11:06 | 2026-04-23 | 2026-04-23 15:34 | 2026-04-23 | 2026-04-23 17:09 | 2026-04-24 | 2026-04-24 19:44 |  |  |  |  | 2027-10-02 |  | 2027-10-10 |  | 2027-10-11 |  |  |  | 2027-10-18 |  | 2027-10-19 |  | 2027-10-20 |  | 2027-10-21 | [6 empty] | 2027-11-08 |  | 2027-11-17 |  | 2026-06-15 |  | 2027-11-17 |  | 2027-11-18 |  | 2027-11-20 |  |  |  | 2027-12-12 |  | 2027-12-14 |  | 2027-12-15 | [5 empty] | 2027-10-19 |  | 2026-04-25 |  | Unknown | 2026-04-12 | 2026-04-13 11:54 | 805065 | 144911 | 0 | 0 | 0 | 0 | 798341.1935 | 137762 | 2026-04-28 17:51:23 +0530 | Losii Athisa | Some Image was uploaded | 2026-04-26 17:09:17 +0530 | Priyanka Gs | CDP: Living Room The scope currently includes wall concept design only. No furniture or loose elements are included at this stage. Kitchen A tall unit has been discussed. This will be incorporated during the detailed design phase and is not part of the current scope. Master Bedroom The placement of the dresser and study table may require revision. Final positioning will be reassessed during the design development stage. Parents Bedroom The wardrobe placement was modified during the meeting. However, cost estimation for this change has not yet been generated and will need to be updated accordingly. GenericÂ All product internals have been reviewed.These can be personalized during the design phase. Inclusion of additional drawers will have an impact on the costing. Laminate catalogue was shown during CDP The following items are not included in the current quotation False ceiling, Painting, Electrical work , Lighting fixtures | 2026-04-24 19:44:26 +0530 | Parasa Sri | Welcome call done. Renovation project. site is ready for INITIAL MEASUREMENT | 2027-10-02 |  | 2027-10-09 |  | RTMI
19452 | Turnkey | 2026-01-01 | MADINENI RAVALI &POTTURU RAJESH | SSVR Niyaraa | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1346494 | 10000 | 0 | 0 | 0 | 88 | 0 | 124649 | 134649 | 538598 | 538597.6 |  |  | 2026-04-13 | 2026-04-17 18:09 | 2026-04-12 | 2026-04-18 12:16 | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-09 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-13 | 2026-04-14 17:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1141097 | 205397 | 2026-05-04 15:51:30 +0530 | Rhea Rathod | DCM: Possession - July Typology - 2BHK Family of 3 East facing apartment - 10th floor Profession - software engineers Theme - Blacks , greys, Wooden Elegant with less maintenance Living area - - window on the east wall, Window on the north wall to be removed - TV unit -Â minimal rafters, Wall mounted TV unit - to be planned on south wall - Sofa - existing 3 + 2 - Wall paper design on west wall - Aquarium - to be planned on the west wall Dining area - - Crockery unitÂ Kitchen - - Pooja unit to be planned on the north wall of the Kitchen - Modular kitchen - Pantry unit, Appliance unit - Sink to be planed on south wall with under sink ro - Spice - Single door fridge rack - Glass wall unit, loft - Granite Utility - - Sink unit, Gas cylinder unit - Wall unit Master bedroom - - Window is placed in the center - Wardrobe with loft - on west wall on either side of the window - Bay window seater - Wall paperÂ - Bathroom door - to be mirrored - Mirror on the left side of the bed - Existing king size bed - 6x6 Kids bedroom - Wardrobe with loft - Bed on the west wall - Existing Queen size bed - 5x Study unit6 | 2026-04-28 17:33:14 +0530 | Losii Athisa | Some Image was uploaded |  |  |  | 2026-05-03 |  | 2026-05-10
19454 | Turnkey | 2026-01-01 | Ashutosh Acharya | Sjr eastwood | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1609089 | 222026 | 2220618 | 0 | 0 | 63 | 0 | 0 | 99792 | 721134 | 566137.2 |  |  | 2026-04-13 | 2026-05-09 20:43 | 2026-04-16 | 2026-05-10 20:25 | 2026-05-13 | 2026-05-10 22:21 | 2026-07-29 |  | 2026-09-06 |  | 2026-09-13 |  | 2026-05-10 | 2026-05-12 11:27 | 2026-05-11 | 2026-05-13 12:30 | 2026-05-13 | 2026-05-13 18:58 | 2026-05-24 | 2026-05-24 13:51 |  |  |  |  | 2026-07-30 |  | 2026-09-08 |  | 2026-09-09 |  |  |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 | [6 empty] | 2026-10-07 |  | 2026-10-16 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-19 |  |  |  | 2026-11-10 |  | 2026-11-12 |  | 2026-11-13 | [5 empty] | 2026-09-17 |  | 2026-07-25 |  | Unknown | 2026-04-13 | 2026-04-14 17:37 | 1881879 | 338738 | 0 | 0 | 0 | 0 | 1874632.7194 | 309522 | 2026-05-22 10:56:36 +0530 | Vishal Haridas | Minutes of Meeting held on Date: 21-05-2026 Title: KT Call Project: Flat Client: Ashutosh Attendees: Ankita Objective: Discussion Client Doesn't require wallpaper design anywhere in the house. FOYER Foyer unit should be able to store at least 25 Pair of shoes. Client doesn't prefer to increase the width of foyer unit, But he is ok in increasing the height of it. We can add extra shelf to it. His only concern is that , it should atleast hold 25 Pair of shoes. On the wall adjacent to Puja unit ( Largest wall in the house) Cx want to add more details to the wall, He found current design to be so minimal, he wants to add more details to it. (Stencil Design Can be considered) Currently Puja unit is of complete single glass door and drawer inside. CX Prefer to have seperate drawer and a seperate glass door for the idol. LIVING ROOM TV Wall require even more elements, he found the wall empty On the Opposite of the TV wall, currently wallpaper is added. This have to be removed. Kitchen Wicker basket needs to be added under tall unit, Client prefers to keep oven on base cabinet, needs to get a confirmation from him. In bedrooms we can use trims ,beading and Texture paint as design options. But no wallpaper anywhere | 2026-05-13 18:51:51 +0530 | Sanjana Swami | Called the client he mentioned he will pay the 10% BY 23rd May 2026 and he will let us know about the IMs once the site will be accessible | 2026-05-13 18:32:16 +0530 | Rishi Pandey | Some Image was uploaded | 2026-07-30 |  | 2026-09-07 |  | Under Construction | 2026-08-31
19456 | Turnkey | 2026-01-01 | Riya Singla | brigade metropolis | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 2867625 | 9999 | 0 | 0 | 0 | 92 | 0 | 276764 | 286763 | 1170698 | 1123402.4 |  |  | 2026-04-12 | 2026-04-14 12:08 | 2026-04-15 | 2026-04-22 12:43 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-04-12 | 2026-04-14 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2430191 | 437434 | 2026-05-01 12:53:27 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-04-22 12:19:58 +0530 | Keerthan M | DCM: Living foyer area Mural art need to plannedmirror art need to be givenTV unitDining wall detailing6 seater tablemarble Pooja unit with crockery unit on MBR wall Kitchen BF counter need to be given , medium sizeBottom, top, loft unit.Give suggestions on design bedrooms wardrobe, study and dresserwall detailing need to be suggested Bathrooms Vanity unitsdesigns need to be suggested |  |  |  | 2026-05-07 |  | 2026-05-14
19462 | Turnkey | 2026-01-01 | Preeti Shah | Pratap Adhinath | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Nishant Jadhav | Sandeep Tiwari | Murali S | Avi Thakkar | Siddhesh Gujrathi | Active | Production | Production | 1591946 | 987287 | 1488862 | 0 | 1635084 | 5 | 0 | 0 | 0 | 0 | 604659 |  |  | 2026-04-14 | 2026-04-16 11:27 | 2026-04-15 | 2026-04-16 11:27 | 2026-04-17 | 2026-04-17 18:47 | 2026-04-28 | 2026-04-28 13:11 | 2026-06-13 | 2026-06-12 18:22 | 2026-06-16 | 2026-06-16 19:32 | 2026-04-17 | 2026-04-21 19:09 | 2026-04-18 | 2026-04-22 12:59 | 2026-04-22 | 2026-04-23 16:28 | 2026-04-24 | 2026-04-24 18:28 |  |  |  |  | 2026-04-28 | 2026-04-29 18:18 | 2026-06-07 | 2026-06-08 16:08 | 2026-06-09 | 2026-06-08 16:09 |  |  | 2026-06-19 | 2026-06-24 13:06 | 2026-06-28 | 2026-06-28 13:23 | 2026-06-29 | 2026-06-28 16:31 | 2026-06-29 | 2026-06-30 14:50 |  |  |  |  | 2026-07-03 13:17 | 2026-07-11 | 2026-07-10 22:16 | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-04 |  | 2026-08-05 | [5 empty] | 2026-06-28 | 2026-07-03 13:16 | 2026-04-25 | 2026-04-28 13:08 | Site is RTMI | 2026-04-14 | 2026-04-16 11:22 | 1264034 | 224827 | 0 | 0 | 1768346.2981 | 292131 | 1768345.7065 | 285551 | 2026-06-28 19:27:05 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-28 16:32:06 +0530 | Manzoor Shaikh | The client is at the PKO closure stage and the Project Value is upscaled to 45%. Hence added 2.5% additional Design fee waiver discount as a retention effort. | 2026-06-24 11:43:19 +0530 | Urvisha Prajapati | Some Image was uploaded | 2026-04-29 | 2026-04-28 13:13 | 2026-06-13 | 2026-06-12 18:24
19464 | Turnkey | 2026-01-01 | Anuradha Nandoskar | metro crown | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Shreyash Kotecha |  | Hold | Preproduction | Site Readiness 1 | 1346140 | 269999 | 1643276 | 0 | 0 | 2 | 61 | 0 | 0 | 607243 | 468898.4 |  |  | 2026-04-12 | 2026-04-15 19:06 | 2026-04-12 | 2026-04-19 19:36 | 2026-04-21 | 2026-04-21 11:49 | 2026-05-08 | 2026-05-07 12:32 | 2026-09-05 |  | 2026-10-06 |  | 2026-04-21 | 2026-04-23 20:25 | 2026-04-22 | 2026-04-24 11:13 | 2026-04-24 | 2026-04-27 09:30 | 2026-05-03 | 2026-05-03 11:39 |  |  |  |  | 2026-05-07 | 2026-05-13 19:20 | 2026-10-01 |  | 2026-10-02 |  |  |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 | [6 empty] | 2026-10-30 |  | 2026-11-08 |  | 2026-11-07 |  | 2026-11-08 |  | 2026-11-09 |  | 2026-11-11 |  |  |  | 2026-12-03 |  | 2026-12-05 |  | 2026-12-06 | [5 empty] | 2026-10-10 |  |  |  |  | 2026-04-12 | 2026-04-15 14:58 | 1395408 | 247867 | 0 | 0 | 0 | 0 | 1418391.4865 | 233050 | 2026-07-10 19:40:08 +0530 | Divya Rahangdale | CX will receive the possession by August. | 2026-06-26 16:05:39 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-05-15 12:02:44 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-08 | 2026-05-07 12:35 | 2026-09-06
19465 | Turnkey | 2026-01-01 | Ahmed Nauman Naik | Avenue Park - I | MUM - GOR | Yes | Saif Shaikh | Reshma Melanta | Shantanu Parakh | [5 empty] | Umang Shah |  | Active | Preproduction | DEM2 | 869368 | 173878 | 1148083 | 0 | 0 | 23 | 0 | 0 | 0 | 381805 | 313684.8 |  |  | 2026-04-14 | 2026-04-14 14:17 | 2026-04-14 | 2026-04-14 14:31 | 2026-04-29 | 2026-04-30 12:24 | 2026-06-17 | 2026-06-17 20:51 | 2026-07-22 |  | 2026-07-29 |  | 2026-04-30 | 2026-04-30 18:37 | 2026-05-01 | 2026-05-01 09:18 | 2026-05-01 | 2026-05-04 12:01 | 2026-05-09 | 2026-05-09 15:32 |  |  |  |  | 2026-06-17 | 2026-06-22 19:09 | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-05-10 | 2026-06-17 20:33 | Site is RTMI | 2026-04-14 | 2026-04-14 13:40 | 972952 | 175131 | 0 | 0 | 0 | 0 | 972951.8917 | 164268 | 2026-06-18 18:39:23 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-09 15:30:53 +0530 | Reshma Melanta | Minutes of Meeting: PID 19465 Ahmed Nauman NaikProject Status & Timeline Possession: The client is expected to receive possession of the property in July 2026.Internal Meeting (IM): Due to the client's frequent travel schedule, the IM must be aligned between May 12th and May 14th, 2026.Key Action Items & Coordination Meeting Scheduling: The client requested to schedule the next meeting only after the IM is completed. He will update the team on his availability based on his travel itinerary.Communication: I have been successfully added to the project WhatsApp group to streamline further updates. CX is not in hurry currently he wants to close the Design Meeting, and post that incase the possession is delayed by the Builder the CX might change the proeprty, he is not sure on that. | 2026-05-08 13:30:38 +0530 | Umang Shah | Some Image was uploaded | 2026-06-18 | 2026-06-17 20:53 | 2026-07-23 |  | Under Construction | 2026-07-31
19474 | Turnkey | 2026-01-01 | Dinkar Jayram Kare | Rustomjee La Familia | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar |  |  | Faraz Soudagar | Aditya Vikram |  | Vandana Preet | Shailendra Mishra | Active | Preproduction | DEM2 | 1312290 | 262458 | 1471738 | 0 | 0 | 22 | 31 | 0 | 0 | 568148 | 481683.6 |  |  | 2026-04-14 | 2026-04-15 11:27 | 2026-04-19 | 2026-04-19 08:06 | 2026-04-22 | 2026-04-22 11:41 | 2026-05-07 | 2026-05-05 13:54 | 2026-06-24 | 2026-06-23 18:30 | 2026-09-11 |  | 2026-04-22 | 2026-04-23 20:57 | 2026-04-23 | 2026-04-24 11:12 | 2026-04-24 | 2026-04-24 12:37 | 2026-05-02 | 2026-05-02 17:49 |  |  |  |  | 2026-05-21 | 2026-05-21 18:30 | 2026-09-06 |  | 2026-09-07 |  |  |  | 2026-09-14 |  | 2026-09-15 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-09-15 |  | 2026-05-03 | 2026-05-02 19:05 | Site is Non-RTMI | 2026-04-14 | 2026-04-15 11:25 | 1247236 | 224502 | 0 | 0 | 0 | 0 | 1446461.6617 | 240984 | 2026-07-12 00:26:11 +0530 | Rachna Abhyankar | CM ON 17TH JULY | 2026-07-11 10:51:47 +0530 | Siddhi Chaphekar | CM aligned for 17th July'26. | 2026-06-28 19:04:50 +0530 | Siddhi Chaphekar | Some Image was uploaded | 2026-05-06 | 2026-05-06 11:23 | 2026-06-24 | 2026-06-23 18:30
19476 | Turnkey | 2026-01-01 | Rajini | Purva parkhill | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1659270 | 9999 | 1659270 | 0 | 0 | 80 | 0 | 155928 | 165927 | 675224 | 652192.4 |  |  | 2026-04-14 | 2026-04-15 19:07 | 2026-04-24 | 2026-04-24 11:04 | 2026-04-27 |  | 2026-05-04 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-28 |  | 2026-04-29 | [5 empty] | 2026-05-05 |  | 2026-05-13 |  | 2026-05-14 |  |  |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 | [6 empty] | 2026-06-11 |  | 2026-06-20 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-23 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-05-22 |  | 2026-04-30 |  | Unknown | 2026-04-14 | 2026-04-15 19:05 | 1409182 | 250088 | 0 | 0 | 0 | 0 | 1409182 | 250088 | 2026-04-26 11:32:39 +0530 | Nayan Reddy | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion Infromed cxÂ Reagrding PrelamÂ Useing prelam for Wardrobes and Tv unit Need fridge and tall unit in single wallÂ Suggest break fast counterÂ ideas near kitchenÂ open spice rack below wall unitÂ Dishwasher planing to keep outside Dado tiles from Bonito endÂ - not added in quoteÂ Crockey unit designe need to be chnagedÂ no open space in crockery unitÂ MBRÂ dressing unit 3ftÂ 8ft wardrobeÂ Â 4 ft dressingÂ = 1ft storageÂ & 3 ft dressing unitÂ Â no study unit in bedroomÂ floadable tableÂ = 3ftÂ GBR 8ft wardroeb andÂ 3ft dressersÂ study near windowÂ | 2026-04-24 11:03:17 +0530 | Nayan Reddy | DCM: Cx name : Raman Kumar & Renjini (BLR) Address:Â Holiday Village RD , 906 Profession :Â Working Possession : JulyÂ Â How many people will be staying : 3Â Â Theme : MinimalÂ Â Entrance facing : South east facingÂ Â Budget : 10L Foyer - Shoe rack with walls to be highlightedÂ Dining - 6 Seater diningÂ simple crockery neededÂ Kitchen- Base, wall cabinet neededÂ 1 tall unit for OTG and microwave next to fridge (place space for mixie in-between)Â double door fridgeÂ RO unit below sink Granite to be addedÂ 4 burner HOB Cylinder unit next to HOBÂ Dishwasher next to sinkÂ Utility - Cylinder unit next to WMÂ Living -Â 65" tvÂ 3 seater -1nos and arm seater which cx has - 2nos TV unit Refer the image (pooja coming in corner with shutters)Â Sofa back try mural artÂ Wall trims should be addedÂ MBR -Â Bed corner side give foldable tableÂ Wardrobe with bottom drawers and no loftÂ Next to wardrobe need dresser cum study unitÂ GBR - Queen size bed Bay window and need study table in cornerÂ Wardrobe with mirror on side panelÂ KBR - (Ruhani) 20yo Wardrobe and dresser cum study on same wall Bed wall consider wallpaper (refer image ) Bay window neededÂ BathroomsÂ Vanity unit with mirror storageÂ False ceiling -Â All areas CDP - 9th May | 2026-04-15 10:54:33 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-05-05 |  | 2026-05-12
19479 | Turnkey | 2026-01-01 | Sekhar | Pavani Mariabilia | BNG - HRBR | Yes | Faizan Sharief | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Mohammed Rasick |  | Active | Design | DEM1 | 780439 | 79999 | 1045397 | 0 | 0 | 34 | 0 | 0 | 76089 | 312176 | 312175.6 |  |  | 2026-04-14 | 2026-05-20 12:23 | 2026-05-22 | 2026-05-22 19:48 | 2026-05-25 | 2026-06-10 19:20 | 2026-07-29 |  | 2026-08-05 |  | 2026-08-12 |  | 2026-06-10 | 2026-06-10 19:23 | 2026-06-11 | 2026-06-10 19:35 | 2026-06-10 | 2026-06-11 16:42 | 2026-06-12 | 2026-06-12 17:29 |  |  |  |  | 2026-07-30 |  | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-07-25 |  | Unknown | 2026-04-14 | 2026-04-15 12:20 | 885930 | 159467 | 0 | 0 | 0 | 0 | 861854.1 | 142312 | 2026-06-14 16:31:05 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-12 17:28:32 +0530 | Rajeshwari S | Welcome call done along with Surabhi and Fizan IM can be scheduled post 18th June Under construction project Possession expected in August. Project will go on hold post layout finalization 10% will be paid on 28th June Project closed @ Rs.7,80,440/- post offers | 2026-06-11 16:41:38 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: August 2026 Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Client will get the soft possession by 18th June 2026 for interior work * IM 18th June 2026 * DEM 1 Weekend after 18th June 2026 * 10% Payment Stage 28th June 2026 *No civil work planned *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 8,61,855 Offers Discussed During the Call: Free Shoerack Offer Design fee waiver (5%) PM fee waiver (5%) Laminate Upgrade - Windows to Wonderful home Services - Windows to Wonderful Home Furniture - Windows to Wonderful Home Modular - Windows to Wonderful home Final Closing Value Discussed: 7,80,440 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-30 |  | 2026-08-06 |  | Under Construction | 2026-08-01
19481 | Sub Project |  | Mohan Gowda | queens park | MUM - Thane |  | Sahil Gunde | Anamika Dolai | Anil Kuwar | [7 empty] | Active | Preproduction | Site Readiness 2 | -939 | 0 | 0 | 0 | -939 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-15 | 2026-07-10 12:51 | 2026-04-16 | 2026-07-10 12:51 | 2026-07-10 | 2026-07-10 12:51 | 2026-07-11 | 2026-07-10 12:52 | 2026-07-11 | 2026-07-10 12:54 | 2026-07-11 | 2026-07-10 12:55 | 2026-07-10 | 2026-07-10 12:52 | 2026-07-11 | 2026-07-10 12:52 | 2026-07-10 | 2026-07-10 12:52 | 2026-07-11 | 2026-07-10 12:52 |  |  |  |  | 2026-07-10 | 2026-07-10 12:53 | 2026-07-11 | 2026-07-10 12:54 | 2026-07-11 | 2026-07-10 12:54 |  |  | 2026-07-11 | 2026-07-10 12:56 | 2026-07-11 | 2026-07-10 14:46 | 2026-07-11 | 2026-07-10 15:41 | 2026-07-11 | 2026-07-10 15:41 | [29 empty] | 2026-07-10 |  | 2026-07-11 | 2026-07-10 12:52 | Unknown | 2026-04-15 | 2026-07-10 12:51 | 0 | 0 | 0 | 0 | 79712 | 14348 | 79712 | 14348 | 2026-07-09 17:32:52 +0530 | Avinash Jaiswal | Client had beds in turnkey PID which is now cancelled. Therefore, instead of giving refund we are giving another bed. To absorb the charge we have added a discount. | [6 empty] | 2026-07-11 | 2026-07-10 12:52 | 2026-07-11 | 2026-07-10 12:54
19483 | Turnkey | 2026-01-01 | Harsh Shah | Pratap Adinath | MUM - GOR | Yes | [8 empty] | Avi Thakkar |  | Active | Prospect | 10% Payment | 1619746 | 9999 | 0 | 0 | 0 | 78 | 0 | 151976 | 161975 | 689899 | 605898 |  |  | 2026-04-15 | 2026-04-28 13:09 | 2026-04-15 | 2026-04-28 13:16 | 2026-04-28 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-05-19 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-29 |  | 2026-04-30 | [5 empty] | 2026-05-06 |  | 2026-05-14 |  | 2026-05-15 |  |  |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 | [6 empty] | 2026-06-12 |  | 2026-06-21 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-24 |  |  |  | 2026-07-16 |  | 2026-07-18 |  | 2026-07-19 | [5 empty] | 2026-05-23 |  | 2026-05-01 |  | Unknown | 2026-04-15 | 2026-04-16 11:56 | 0 | 0 | 0 | 0 | 0 | 0 | 1772387.5727 | 285215 | 2026-04-15 20:26:49 +0530 | Rishika Malviya | Some Image was uploaded | [6 empty] | 2026-05-06 |  | 2026-05-13
19487 | Turnkey | 2026-01-01 | Madhuri srinivas | INDEPENDENT HOUSE | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 2268668 | 9999 | 2268668 | 0 | 0 | 61 | 0 | 216868 | 226867 | 907467 | 907467.2 |  |  | 2026-04-15 | 2026-04-16 16:45 | 2026-05-13 | 2026-05-15 09:55 | 2026-05-18 | 2026-05-15 11:26 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-05-23 |  | 2026-05-31 |  | 2026-06-01 |  |  |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 | [6 empty] | 2026-06-29 |  | 2026-07-08 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-11 |  |  |  | 2026-08-02 |  | 2026-08-04 |  | 2026-08-05 | [5 empty] | 2026-06-09 |  | 2026-05-18 |  | Unknown | 2026-04-15 | 2026-04-16 10:57 | 1922600 | 346068 | 0 | 0 | 0 | 0 | 1922600 | 346068 | 2026-05-13 11:43:21 +0530 | Saranya Thiyagarajan | DCM: Project: Individual Residence Location: HSR Extension Budget: 25 to 30 Lakhs Rental Budget: 5 to 6 Lakhs Ground Floor & First Floor Rental UnitsGeneralRental unit planning with functional and low-maintenance interiors.Wardrobes to be provided in both bedrooms.TV unit in living room with drawers and T-profile strip lighting.Entry shoe rack to be included.KitchenFridge space, sink, tandem drawers, wall and base cabinets.No loft cabinets.Simple and practical kitchen layout.UtilityBase cabinet below sink.One utility ledge provision.Master Bedroom (MBR)Wardrobe with mirror on shutter.Dresser near bedside corner.Bedroom 1Wardrobe with mirror on shutter.Common Wash AreaVanity unit for washbasin.Second Floor Main ResidenceEntranceShoe rack (450 mm height) near glass window.Living AreaSwing provision.Feature wall / design behind door.Pooja UnitNo window; shifted to opposite side.End-to-end pooja unit with glass or pocket doors.Option 1: Dedicated pooja.Option 2: Combined pooja + crockery unit.Seating/stool provision for pooja.CourtyardFloating TV unit with metal fabrication.Ledge wall detailing with back lighting behind TV.Main door and garden with arch design.One courtyard pillar with 2 ft height detail.Replace single courtyard window with 2 smaller vertical windows.KitchenIsland kitchen.Double-door fridge provision.Tall unit with roller shutter cabinet finish.Rearrangement of kitchen layout possible.Glass shutter wall cabinets with laminate finish.Internal wall cabinets with full glass shutters.UtilitySpace for washing machine, dishwasher, and sink.Parents Bedroom (PBR)SSV headboard design reference.Wardrobe and dresser with mirror + vanity unit.No wall separation for dresser area.Curve design similar to Mahaveer reference.Third FloorLiving AreaPool table provision.Lift LobbyLift opening facing garden side.Feature design for lift wall.Store RoomSpace to accommodate 2 ladders.Master BedroomNo bay window; provide balcony with sliding glass door options.Balcony with one-side glass and UPVC window for study area.SW locker provision.Beige shade theme with SSVR reference styling.Kids Bedroom Sai (Age 24)Dresser without wall partition.Bed back wall in black & white theme.Small standing balcony near opposite French door glass wall.Wardrobe on toilet wall side with one display unit.Bay seating and study provision.Grey-blue dresser theme or Mahaveer curve design reference.General Bedroom RequirementsHydraulic beds in 3 bedrooms.Simple wardrobe in guest bedroom.Â | 2026-05-13 11:42:53 +0530 | Saranya Thiyagarajan | DCM: Project: Individual Residence Location: HSR Extension Budget: 2530 Lakhs Rental Budget: 56 Lakhs Ground Floor & First Floor Rental UnitsGeneralRental unit planning with functional and low-maintenance interiors.Wardrobes to be provided in both bedrooms.TV unit in living room with drawers and T-profile strip lighting.Entry shoe rack to be included.KitchenFridge space, sink, tandem drawers, wall and base cabinets.No loft cabinets.Simple and practical kitchen layout.UtilityBase cabinet below sink.One utility ledge provision.Master Bedroom (MBR)Wardrobe with mirror on shutter.Dresser near bedside corner.Bedroom 1Wardrobe with mirror on shutter.Common Wash AreaVanity unit for washbasin.Second Floor Main ResidenceEntranceShoe rack (450 mm height) near glass window.Living AreaSwing provision.Feature wall / design behind door.Pooja UnitNo window; shifted to opposite side.End-to-end pooja unit with glass or pocket doors.Option 1: Dedicated pooja.Option 2: Combined pooja + crockery unit.Seating/stool provision for pooja.CourtyardFloating TV unit with metal fabrication.Ledge wall detailing with back lighting behind TV.Main door and garden with arch design.One courtyard pillar with 2 ft height detail.Replace single courtyard window with 2 smaller vertical windows.KitchenIsland kitchen.Double-door fridge provision.Tall unit with roller shutter cabinet finish.Rearrangement of kitchen layout possible.Glass shutter wall cabinets with laminate finish.Internal wall cabinets with full glass shutters.UtilitySpace for washing machine, dishwasher, and sink.Parents Bedroom (PBR)SSV headboard design reference.Wardrobe and dresser with mirror + vanity unit.No wall separation for dresser area.Curve design similar to Mahaveer reference.Third FloorLiving AreaPool table provision.Lift LobbyLift opening facing garden side.Feature design for lift wall.Store RoomSpace to accommodate 2 ladders.Master BedroomNo bay window; provide balcony with sliding glass door options.Balcony with one-side glass and UPVC window for study area.SW locker provision.Beige shade theme with SSVR reference styling.Kids Bedroom Sai (Age 24)Dresser without wall partition.Bed back wall in black & white theme.Small standing balcony near opposite French door glass wall.Wardrobe on toilet wall side with one display unit.Bay seating and study provision.Grey-blue dresser theme or Mahaveer curve design reference.General Bedroom RequirementsHydraulic beds in 3 bedrooms.Simple wardrobe in guest bedroom.Â | 2026-05-12 18:27:12 +0530 | Pulivarthi Nirosha | Some Image was uploaded | 2026-05-23 |  | 2026-05-30
19489 | Sub Project |  | Rakesh Pai | Silver Rock | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | Neha Singh | Neha Singh | Savita Parab | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Active | Installation | Execution | 923678 | 0 | 0 | 0 | 1028694 | 28 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 | 2026-04-21 13:28 | 2026-04-17 | 2026-04-21 13:28 | 2026-04-21 | 2026-04-21 13:28 | 2026-04-27 | 2026-04-27 14:54 | 2026-05-07 | 2026-05-06 19:19 | 2026-05-08 | 2026-05-08 18:13 | 2026-04-21 | 2026-04-21 13:28 | 2026-04-22 | 2026-04-21 13:28 | 2026-04-21 | 2026-04-21 13:28 | 2026-04-22 | 2026-04-21 13:29 |  |  |  |  | 2026-04-25 | 2026-04-24 12:12 | 2026-05-06 | 2026-05-05 20:25 | 2026-05-06 | 2026-05-05 20:25 |  |  | 2026-05-11 | 2026-05-13 15:10 | 2026-05-14 | 2026-05-14 16:50 | 2026-05-15 | 2026-05-17 13:40 | 2026-05-19 | 2026-05-19 17:27 |  |  |  |  | 2026-05-20 16:12 | 2026-06-03 | 2026-06-03 23:26 | 2026-06-12 | 2026-06-10 17:59 | 2026-06-11 | 2026-06-11 17:53 | 2026-06-10 | 2026-06-17 14:27 | 2026-06-17 | 2026-06-17 14:28 | 2026-06-19 | 2026-06-19 14:16 |  |  | 2026-07-07 |  | 2026-07-09 |  | 2026-06-28 | [5 empty] | 2026-05-14 | 2026-05-17 20:21 | 2026-04-22 | 2026-04-23 19:33 | Site is RTMI | 2026-04-16 | 2026-04-21 13:27 | 0 | 0 | 0 | 0 | 1301157 | 234208 | 1301157 | 214852 | 2026-06-15 23:30:07 +0530 | Savita Parab | Execution: floor covering done electrical wiring in progress (outdoor unit wiring boq not created from designer side) need to be shared with cx false ceiling framing started but ac marking and ac pipe covering pending from cx side Modular delivery : 15th June | 2026-06-07 23:27:02 +0530 | Savita Parab | Execution: floor covering done electrical wiring in progress (outdoor unit wiring boq not created from designer side) need to be shared with cx false ceiling framing started but ac marking and ac pipe covering pending from cx side | 2026-06-01 16:28:33 +0530 | Savita Parab | Execution: Floor covering done awaiting response from designer for docket clarity | 2026-04-28 | 2026-05-06 18:45 | 2026-05-07 | 2026-05-06 19:20
19491 | Sub Project |  | Anshul | DSR High Land Greenz | BNG - HSR |  | Chittipireddy Sriharish | Akshay Ds | Kowshik |  |  | Yogeshwaran | Ranjith Kumar | Murali S |  | Sunil Kumar S M | Active | Installation | Execution | 39948 | 39948 | 0 | 0 | 39948 | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 | 2026-05-05 18:50 | 2026-04-17 | 2026-05-05 18:50 | 2026-05-05 | 2026-05-05 18:50 | 2026-05-06 | 2026-05-05 18:51 | 2026-05-06 | 2026-05-05 18:53 | 2026-05-06 | 2026-05-05 18:54 | 2026-05-05 | 2026-05-05 18:50 | 2026-05-06 | 2026-05-05 18:50 | 2026-05-05 | 2026-05-05 18:51 | 2026-05-06 | 2026-05-05 18:51 |  |  |  |  | 2026-05-05 | 2026-05-05 18:52 | 2026-05-06 | 2026-05-05 18:53 | 2026-05-06 | 2026-05-05 18:53 |  |  | 2026-05-20 | 2026-05-20 17:27 | 2026-05-21 | 2026-05-20 18:10 | 2026-05-21 | 2026-05-22 10:49 | 2026-05-22 | 2026-05-20 21:16 |  |  |  |  | 2026-06-04 16:08 | 2026-06-06 | 2026-06-05 21:31 | 2026-06-08 | 2026-06-06 10:57 | 2026-06-17 | 2026-05-20 21:16 | 2026-06-06 | 2026-06-25 16:08 | 2026-06-25 | 2026-06-25 16:08 | 2026-06-27 |  |  |  | 2026-07-25 |  | 2026-07-27 |  | 2026-07-28 | [5 empty] | 2026-05-20 | 2026-06-04 16:07 | 2026-05-06 | 2026-05-05 18:51 | Unknown | 2026-04-16 | 2026-05-05 18:50 | 0 | 0 | 0 | 0 | 33854 | 6093 | 33854 | 6093 | [9 empty] | 2026-05-06 | 2026-05-05 18:52 | 2026-05-06 | 2026-05-05 18:53
19493 | Turnkey | 2026-01-01 | Anjum Sultana | Purva Atmosphere | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 737334 | 9999 | 0 | 0 | 0 | 90 | 0 | 63734 | 73733 | 294934 | 294933.6 |  |  | 2026-04-16 | 2026-04-16 18:13 | 2026-04-17 |  | 2026-04-23 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-05-01 |  | 2026-05-09 |  | 2026-05-10 |  |  |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-20 | [6 empty] | 2026-06-07 |  | 2026-06-16 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-19 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-18 |  | 2026-04-26 |  | Unknown | 2026-04-16 | 2026-04-16 17:29 | 0 | 0 | 0 | 0 | 0 | 0 | 624859 | 112474 | 2026-04-28 18:30:50 +0530 | Losii Athisa | Some Image was uploaded | 2026-04-18 16:03:03 +0530 | Keerthan M | DCM: Poorva atmosphereÂ 2BHK 2 ppl CDP Thursday 3PM Budget: 10L Foyer - shoe rack (20 pairs) - partition opp to main door Living - TV unit on kitchen wall - Floating unit with glass storage and wall detailing - L shape sofaÂ - sofa wall detailing Dining - 6 seater - Crockery unit on toilet wall - Bottom, top, and tall - Dining wall detailing - Passage, wall art Kitchen - 2 door fridge and tall units on left wall - Bottom, top and loft - Counter top and sink Utility - left side, W/M - Right side D/W and sink - Top storages and loft - Janitor unit MBR - King bed opp to door - Dresser near window beside bed - wall detailing - Bed with storage - ottoman near toilet wall - sliding wardrobe with loft Bedroom 2Â - Existing bed (Blue) - Sliding wardrobe with loft - Bed wall detailing. Note - Full house false ceiling - Vanity unit in toilets - glass partition |  |  |  | 2026-05-01 |  | 2026-05-08
19494 | Turnkey | 2026-01-01 | Devidas Pawar | Gm Infinity | BNG - HSR | No Estimate | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 | 2026-04-16 17:46 | 2026-04-17 |  | 2026-04-23 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-07-20 |  | 2026-04-24 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-05-01 |  | 2026-05-09 |  | 2026-05-10 |  |  |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-20 | [6 empty] | 2026-06-07 |  | 2026-06-16 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-19 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-18 |  | 2026-04-26 |  | Unknown | 2026-04-16 | 2026-04-16 17:35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-05-01 |  | 2026-05-08
19500 | Turnkey | 2026-01-01 | Ujjal | sobha Royal pavillion | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik |  | RaviKumar Battala | Yogeshwaran | Ranjith Kumar | Murali S | Ramesh Nayak | Affaan Abdulla | Active | Installation | Execution | 2399287 | 2399287 | 2661371 | 0 | 2574287 | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 | 2026-04-20 11:35 | 2026-04-20 | 2026-04-20 13:30 | 2026-04-23 | 2026-04-20 19:35 | 2026-05-04 | 2026-05-04 11:56 | 2026-05-06 | 2026-05-05 18:41 | 2026-05-21 | 2026-05-21 10:31 | 2026-04-20 | 2026-04-20 16:49 | 2026-04-21 | 2026-04-20 21:54 | 2026-04-20 | 2026-04-21 16:18 | 2026-04-22 | 2026-04-22 12:15 |  |  |  |  | 2026-05-04 | 2026-05-05 14:36 | 2026-05-10 | 2026-05-10 18:44 | 2026-05-11 | 2026-05-11 01:07 |  |  | 2026-05-24 | 2026-05-29 20:30 | 2026-05-29 | 2026-05-29 21:17 | 2026-05-30 | 2026-05-30 11:40 | 2026-05-31 | 2026-05-30 20:05 |  |  |  |  | 2026-06-01 14:02 | 2026-06-09 | 2026-06-08 21:34 | 2026-06-26 | 2026-06-24 18:26 | 2026-06-25 | 2026-06-25 14:12 | 2026-06-24 | 2026-06-26 10:39 | 2026-06-26 | 2026-06-26 10:43 | 2026-06-28 | 2026-07-08 18:50 |  |  | 2026-07-30 |  | 2026-07-03 |  | 2026-07-30 | [5 empty] | 2026-05-29 | 2026-06-01 14:01 | 2026-05-02 | 2026-05-04 11:50 | Site is RTMI | 2026-04-16 | 2026-04-20 11:30 | 2255399 | 405971 | 0 | 0 | 3256119 | 586101 | 3256119 | 586101 | 2026-07-06 15:49:21 +0530 | Ranjith Kumar | Execution: | 2026-06-13 10:33:44 +0530 | Ranjith Kumar | Design Changed in False Ceiling height by Cx, hence Delaying Cx Side - Dado tiles WIP, Core Cutting, Internet Point, Plumbing Point & Sprinkler Shifting. Bonito Side - Electrical, False Ceiling, Floor Covering, Painting | 2026-06-02 18:14:44 +0530 | Ranjith Kumar | Cx Side - Dado tiles WIP Bonito Side - Electrical, False Ceiling, Floor Covering, Painting | 2026-05-05 | 2026-05-04 11:56 | 2026-05-06 | 2026-05-05 18:43 | RTMI
19501 | Turnkey | 2026-01-01 | Niki Chirag shah | Dem Siddhivinayak | MUM - GOR | Yes | Batskhem Marpna | Manzoor Shaikh | Kashmira Nerurkar |  | Anamika Ghate | Nishant Jadhav | Rizwan Mistry |  | Avi Thakkar | Sunil Poojary | Active | Design | 60% Payment | 865182 | 186134 | 1325219 | 0 | 865182 | 1 | 0 | 0 | 0 | 332975 | 346072.8 |  |  | 2026-04-17 | 2026-04-30 12:27 | 2026-04-30 | 2026-04-30 16:07 | 2026-05-03 | 2026-04-30 16:21 | 2026-05-16 | 2026-05-16 17:17 | 2026-06-06 | 2026-06-05 16:48 | 2026-06-20 | 2026-06-20 11:30 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-07 14:46 | 2026-05-07 | 2026-05-07 16:05 | 2026-05-09 | 2026-05-09 18:10 |  |  |  |  | 2026-05-16 | 2026-06-01 16:19 | 2026-06-14 | 2026-06-14 18:11 | 2026-06-15 | 2026-06-14 19:10 |  |  | 2026-06-23 | 2026-07-12 19:06 | 2026-07-12 | 2026-07-12 20:41 | 2026-07-13 | 2026-07-14 17:33 | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-12 |  | 2026-05-10 | 2026-05-16 14:05 | Site is RTMI | 2026-04-17 | 2026-04-22 11:54 | 1125354 | 199864 | 0 | 0 | 1055617.6153 | 174307 | 1055617.6153 | 174307 | 2026-07-03 00:38:27 +0530 | Batskhem Marpna | MOM- Chirag-Dated: 02.07.2026 Living room: - Remove back panel in mandir - Wall shelves with metal to be removed - Mirror crockery-remove - Remove grey panel behind - Put wallpaper behind tv - TV drawers total width 1350 with 3 drawers - Gypsum oanel remove Kitchen- - Lofts one side remove - One soice rack added - Keep the wall unit at beam level - Plate rack - Remove 2 drawer and replace with shelves DBR- - Remove external drawers - remove study table, keep the drawer MBR- - External drawer to be removed - texture paint - remove hidden drawers - add regular drawer Thanks, Batskhem | 2026-07-03 00:37:44 +0530 | Batskhem Marpna | MOM- Chirag-Dated: 02.07.2026 Living room: - Remove back panel in mandir - Wall shelves with metal to be removed - Mirror crockery-remove - Remove grey panel behind - Put wallpaper behind tv - TV drawers total width 1350 with 3 drawers - Gypsum oanel remove Kitchen- - Lofts one side remove - One soice rack added - Keep the wall unit at beam level - Plate rack - Remove 2 drawer and replace with shelves DBR- - Remove external drawers - remove study table, keep the drawer MBR- - External drawer to be removed - texture paint - remove hidden drawers - add regular drawer Thanks, Batskhem | 2026-06-27 19:42:17 +0530 | Anamika Ghate | Some Image was uploaded | 2026-05-17 | 2026-05-16 17:18 | 2026-06-06 | 2026-06-05 16:50
19502 | Turnkey | 2026-01-01 | Vishal Bodke | Regency Luxuria | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1161870 | 9999 | 0 | 0 | 0 | 82 | 0 | 106188 | 116187 | 487287 | 442208.8 |  |  | 2026-04-17 | 2026-04-17 19:13 | 2026-04-17 | 2026-04-24 15:05 | 2026-04-27 |  | 2026-05-04 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-04-27 |  | 2026-04-28 |  | 2026-04-28 |  | 2026-04-29 | [5 empty] | 2026-05-05 |  | 2026-05-13 |  | 2026-05-14 |  |  |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 | [6 empty] | 2026-06-11 |  | 2026-06-20 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-23 |  |  |  | 2026-07-15 |  | 2026-07-17 |  | 2026-07-18 | [5 empty] | 2026-05-22 |  | 2026-04-30 |  | Unknown | 2026-04-17 | 2026-04-17 18:37 | 0 | 0 | 0 | 0 | 0 | 0 | 984635 | 177234 | 2026-06-21 12:07:03 +0530 | Foram Joshi | Some Image was uploaded | 2026-04-17 20:36:06 +0530 | Mansi Deshmukh | DCM: Name: Vishal bodke. Â Property Name: Regency anantam luxuria. Property type: 2bhk. Possession: 15 may 2026. Member: 3. Requirements: Living room: SHOERACK WITH SEATING , TV UNITÂ , 3 +1 SOFA SEATER WITH MANDIR WITH PARTITIONÂ , 4 SEATER DINING , CROCERY UNIT BASE WITH SHELL, tulsi design minimal theme balconyÂ balcony design with seating.Â Â Â Passage area - storage in niche .Â Kitchen : SEMI MODULARÂ KITCHEN , BASE/WALL/LOFT BOTH SIDE , MICROWAE UNIT, ROLLER SHUTTER.Â Â Â Â UTILITY AREA : washing machine , with storageÂ Master bedroom :bed,one side table , dresser beside bed, full length mirrorÂ , bookshelf, wardrobe with loft, used cloth storageÂ Â jhula in balcony, opp wall for art frames . Â Bathroom: vanityÂ Â Kid's bedroom - sofa cum bed , side table + dresser , storage for trophics, hot wheels collection for decor, study unit with storage, stoarage for piano 4'* 1/2' space ., football theme concept . wardrobe with loft , used cloth storage .Â Â Â Â Â Additional scope: Modern theme, minimal design ,neutral tone.Â shivaji maharaj theme wall at entrance. Â **BUDGET: 10 lakhs Â suggested 10- 13. |  |  |  | 2026-05-05 |  | 2026-05-12
19504 | Turnkey | 2026-01-01 | Elyas Gounde | anatalya | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 1638263 | 327653 | 1941134 | 0 | 0 | 13 | 55 | 0 | 0 | 716316 | 594294 |  |  | 2026-04-17 | 2026-04-18 19:48 | 2026-04-18 | 2026-04-18 19:53 | 2026-04-18 | 2026-04-18 19:59 | 2026-04-28 | 2026-04-28 17:30 | 2026-07-02 |  | 2026-07-09 |  | 2026-04-18 | 2026-04-20 12:14 | 2026-04-19 | 2026-04-20 13:12 | 2026-04-20 | 2026-04-21 17:51 | 2026-04-24 | 2026-04-24 12:49 |  |  |  |  | 2026-04-28 | 2026-06-01 12:20 | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-04-25 | 2026-04-28 14:54 | Site is RTMI | 2026-04-17 | 2026-04-18 17:01 | 1645029 | 296105 | 0 | 0 | 0 | 0 | 1642734.831 | 283463 | 2026-06-02 17:25:01 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-31 19:25:06 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-27 16:26:03 +0530 | Vishakha Vaishnav | Cx said that IM is done what are further steps need to be communicate on whatsapp | 2026-04-29 | 2026-04-28 17:31 | 2026-07-03 |  | Under Construction | 2026-04-30
19508 | Turnkey | 2026-01-01 | Saroj Kumar Choudhury | SSVR NIYAARA | BNG - HSR | Yes | Vishal Haridas | Akshay Ds | Soumya KP | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 1281079 | 175575 | 1746354 | 0 | 0 | 69 | 0 | 0 | 80641 | 512432 | 512431.6 |  |  | 2026-04-18 | 2026-04-18 13:59 | 2026-04-26 | 2026-04-26 15:27 | 2026-04-27 | 2026-04-27 12:50 | 2026-07-11 |  | 2026-06-01 |  | 2026-08-07 |  | 2026-04-27 | 2026-04-28 18:59 | 2026-04-28 | 2026-05-05 16:09 | 2026-05-05 | 2026-05-07 13:43 | 2026-05-14 | 2026-05-14 13:58 |  |  |  |  | 2026-07-16 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-11 |  | 2026-05-15 | 2026-05-27 10:02 | Site is RTMI | 2026-04-18 | 2026-04-18 13:53 | 1479961 | 266393 | 0 | 0 | 0 | 0 | 1442134.535 | 238130 | 2026-06-04 13:26:29 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-27 10:25:38 +0530 | Vishal Haridas | Design meeting is planned for Saturday | 2026-05-23 16:01:26 +0530 | Priyanka Mathur | Client is not ready to start the designs as site was not ready for IM. Than as mentioned we have slot for 20th after that we have aligned, now we have to align meetings post that | 2026-07-12 |  | 2026-06-02 |  | Under Construction | 2026-06-30
19509 | Turnkey | 2026-01-01 | akshay | Raymond Tenx Habitat | MUM - Thane | Yes | Yerra Bharat | Anamika Dolai | Rushika More | [5 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1592002 | 9999 | 0 | 0 | 0 | 80 | 0 | 149201 | 159200 | 704992 | 568610 |  |  | 2026-04-18 | 2026-04-25 11:05 | 2026-04-19 | 2026-04-25 21:41 | 2026-04-26 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-18 | 2026-04-21 13:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1350706 | 241295 | 2026-04-21 12:16:50 +0530 | Yerra Bharat | DCM: Also talked about matching furniture, said we have a studio where we offer different range of products for every room, and we have an option to get stylist and select the products for the house. He wants the guidance in selecting furniture options matching the design. | 2026-04-21 12:05:36 +0530 | Yerra Bharat | DCM: Akshay Investment Banker, Raymond Habitat, Tower J, 25th Floor. Couple both are working and have no time on weekdays; meetings are possible on weekends only. Main entrance opens towards East and Balcony on the North Side. - must be confirmed. Site Dates: Not Accessible Now Possession Date: By Builder early June but he asked for early date so ideally end of May. Budget 14 Lakhs He got quotes from other parties for 13.8L including shower glass partitions among other things. They Need Mostly painted wall, no wallpaper but design on the walls with paint.Planning to take Pet dog in the near future after moving in.Family from both sides will visit once or twice a year. Plants are a hobby, having nearly 20 pots which they want in new home also. They want the design organic and designed round plants. Pooja should be very simple smaller the better right now they are having it in the kitchen and the same is fine but not in any bedroom areas. No need for a special pooja room or mandir but can do with a small one incorporated into some wall cabinet is also fine. Likes Olive Green palette, turquoise color. Also, like brick color. Natural tones, wooden grain. White as background and others on top ideally.Corporate style ceiling, which he was shown in the EC, and kitchen in 3BHK model flat in EC. Wants Two rail system from Curtains. Shoe Racks: One external Step design where can sit and wear shoes, and shoe storage. Internal Shoe rack design may be in second bedroom, depending on possibility and design. Digital lock with camera for entrance. False Ceiling: Existing fie system has to be boxed and see the possibility of the design. Dining: 4 People sitting dining table - Design Considerations ideally whenever guests visit they must be able to sit in living area. Wants to watch TV while eating. Bar Unit: Small and Movable can also be on balcony or movable to balcony. With enough storage. A/C outlets are towards the Dry Area- Near the washrooms S.slab as mentioned in plan. Wall mounted RO existing. Master Bedroom: Sliding doors are suggested because of the space. Bedroom 1: He has a play station that he wants in this bedroom. He wants a worktable which can double as an entertainment table with TV/Monitor connected to PlayStation or Laptop. Space is mainly for Guests and Kids (Still in Planning may be after 3 years). Wants Bunkbed, For both adult and child. Asked aboutHidden locker space but said need to verify the possibility. No specific utility area, but area considered as Dry area is used for utility. Cloths Drying ceiling Mounted. Washing machine location must be determined builder gave option in kitchen also, must see where it is possible in kitchen or Dry area. also planning to take dishwasher have to consider dishwasher. Has microwave oven possibly in shelve.Â Â |  |  |  | 2026-05-04 |  | 2026-05-11
19510 | Turnkey | 2026-01-01 | Sanjay Bhatia | Oberoi splendor | MUM - GOR | Yes | Swapnali Shedekar | Reshma Melanta | Safalta Karkera | [5 empty] | Umang Shah |  | Active | Preproduction | DEM2 | 2300000 | 509999 | 3013576 | 0 | 0 | 10 | 0 | 0 | 0 | 962482 | 827519.2 |  |  | 2026-04-18 | 2026-04-18 15:37 | 2026-05-17 | 2026-05-17 19:35 | 2026-05-24 | 2026-05-26 13:53 | 2026-07-07 | 2026-07-07 14:24 | 2026-07-08 | 2026-07-07 14:31 | 2026-07-21 |  | 2026-05-26 | 2026-06-15 15:13 | 2026-05-27 | 2026-06-15 20:00 | 2026-06-15 | 2026-06-16 18:15 | 2026-06-21 | 2026-06-21 19:07 |  |  |  |  | 2026-07-10 | 2026-07-05 19:57 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-08-05 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-25 |  | 2026-07-05 | 2026-07-05 13:23 | Site is RTMI | 2026-04-18 | 2026-04-18 15:34 | 2557213 | 456362 | 0 | 0 | 0 | 0 | 2559167.6037 | 418614 | 2026-07-05 20:02:24 +0530 | Reshma Melanta | Others: | 2026-06-28 18:31:21 +0530 | Reshma Melanta | Project ID: 19510 Client Name: Mr. Sanjay Bhatia Project Value: 22,98,978 Scope of Work: Civil & Modular (Full Renovation) Location: Andheri Experience Center (EC) Key Discussion Points & Project MilestonesAs this is a full home renovation project, the primary discussion focused on the material selection timeline, design finalization, payment milestones, and the explicit timeline for the client to vacate the premises before site execution begins. The agreed-upon project timeline and dependencies are detailed below: Design & Material Selection Alignment:Date: 5th July 2026The Designer and Design Manager (DM) are aligned to freeze all material selections with the client by this date. Site Cross-Measurement:Date: 15th July 2026The execution team will visit the site to take final, accurate technical measurements post-material sign-off. Project Kick-Off (PKO):Timeline: 31st July 2026 10th August 2026Note: This window is subject to the client freezing the final design docket without any further changes. Commencement of On-Site Work:Timeline: 12th August 2026 15th August 2026Demolition and physical on-site work will formally begin during this window. Action Items & Next StepsAction ItemResponsible OwnerTarget DateDEM 1 Payment Milestone: Provide the complete financial breakdown and collect the payment.Account/Project Management4th July 2026Material Sign-off: Finalize colors, finishes, and core materials at the EC.Designer / DM / Client5th July 2026House Vacation & Moving Out: Client to completely pack and vacant the property to ensure an obstruction-free handover for civil work.ClientOn or before 11th August 2026 Critical Note for the Client: To ensure on-site work can smoothly commence between 12th15th August 2026, the premises must be entirely vacated by 11th August 2026. Any delay in packing or moving out will directly impact the project completion timeline.This breakdown will be shared with the client to keep both the civil and modular workflows perfectly synchronized. Let me know if you need any adjustments to the tone or specific phrasing before you send this out! | 2026-06-21 19:06:10 +0530 | Reshma Melanta | MOM Project Type: RTMI Renovation Project Status/Phase: Possession Date: June 21, 2026 Key Discussion Points & Updates Initial Milestones: The IM (Initial Measurement / Initial Meeting) has been successfully completed. Upcoming Site Alignment: The DEM 1 (Demolition / Design) meeting is scheduled and aligned for June 27, 2026. Commercials & Payments: The client (CX) has agreed to clear the 10% payment during their upcoming visit to the Andheri Experience Center (EC). HAVE ADDED THE DEISGNER DM AND BONITO CARE IN THE GROUP | 2026-07-08 | 2026-07-07 14:27 | 2026-07-08 | 2026-07-07 14:33 | RTMI
19514 | Turnkey | 2026-01-01 | Mr. Karthik | Isha Hi- life | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Kushal S |  | Hold | Preproduction | DEM2 | 1209635 | 241927 | 1529041 | 0 | 0 | 44 | 4 | 0 | 0 | 495052 | 472656.4 |  |  | 2026-04-18 | 2026-04-18 17:13 | 2026-04-18 | 2026-04-22 12:10 | 2026-05-01 | 2026-05-01 20:17 | 2026-05-26 | 2026-05-26 18:09 | 2026-09-01 |  | 2026-09-08 |  | 2026-05-01 | 2026-04-30 | 2026-05-02 | 2026-05-13 11:07 | 2026-05-13 | 2026-05-14 11:16 | 2026-05-15 | 2026-05-15 15:40 |  |  |  |  | 2026-05-26 | 2026-05-28 18:51 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-05-16 | 2026-05-26 16:54 | Site is RTMI | 2026-04-18 | 2026-04-18 16:59 | 1295797 | 233243 | 0 | 0 | 0 | 0 | 1264526.1712 | 213503 | 2026-05-21 10:52:21 +0530 | Priyanka Gs | CDP MOMÂ Living & Dining The Pooja unit may not require a pocket door. However, the unit is currently considered as per pocket-door standards for design and estimation purposes. Kitchen The placement of the sink and dishwasher needs to be revised. Updated layouts will be addressed during the designÂ stage. Guest Bedroom The entire guest bedroom has been redesigned as per the discussed requirements. GeneralÂ All product internals have been reviewed. These can be personalized during the design phase. Inclusion of additional drawers will have an impact on the costing. The following items are not included in the current quotation False ceiling, Painting, Electrical work & Lighting fixtures. | 2026-05-15 15:42:27 +0530 | Rajeshwari S | Possession expected in July Project will go on hold after layout finalization. Confirmed on 10th Payment after 1st meeting 1st DEM expected on 24th May. Designer to confirm timings. And designer to confirm on the IM date and time to client Estimation was finalized for Rs.12,09,635/- after all the offers Client is aligned for timings. | 2026-05-14 11:15:23 +0530 | Sanjana Swami | Possession - July 2026 Site is accessible so IMs can be done Client is available for 1st DEM on weekends Clear with the timelines and offers Clear with the payment milestone and project progress Checklist clear No civil work at site Transaction will be B2C self-funding. | 2026-05-27 | 2026-05-26 18:12 | 2026-09-02 |  | Under Construction | 2026-07-01
19515 | Turnkey | 2026-01-01 | Vishnu Vandana p v | The magic faraway tree | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 3652213 | 9999 | 0 | 0 | 0 | 88 | 0 | 355222 | 365221 | 1525888 | 1395882 |  |  | 2026-04-18 | 2026-04-18 17:25 | 2026-04-24 | 2026-04-24 20:14 | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-14 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-09 |  | 2026-07-14 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-18 | 2026-04-18 17:19 | 0 | 0 | 0 | 0 | 0 | 0 | 3095096 | 557117 | 2026-04-24 12:01:20 +0530 | Aparna | MOM Interior Design Discussion Address: 2281 Magic Far Away Tree Profession: Finance & IT Possession Timeline: June / July Family Members: 2 Adults + 2 Kids Theme: Vintage (Wood-focused design) Entrance Facing: South Budget: 32 Lakhs CDP Date: 25th March Overall Design DirectionTheme to follow vintage aesthetics with rich wooden elementsWarm tones, classic finishes, and subtle decorative detailingIntegration of functional storage with aesthetic elementsFoyerTall storage unit in niche areaDB panel to be concealed with designed shutter/panelArchitrave-style framing to enhance entrance lookLiving RoomWhite flooring (existing) to be complemented with warm wood finishesSofa wall: Cladding finishBook niche: Convert into artwork/picture wall with plantersSeating:3-seater sofa1 bench (near picture wall)1 swing in passageTV unit: To be designed as per referenceBehind sofa: Wooden console with bonsai dcorDining Area + PoojaPooja unit in niche wall:Designed to support 100kg marble idolTable-top pull-out provisionStone pillars on both sidesStone-finish back panelFalse ceiling:Wooden finish in centre above dining tableDining to kitchen transition:Wall ledge towards utilityCeiling detail:Frame ceiling with MS rods for hanging planters above islandHeight alignment to be checkedKids Bedroom 1 SwaraTheme: Blue & Burgundy with light wooden flooringEntrance passage niche:Base unit with shuttersFull-length mirrorBrass wall light (centered)Furniture:4-shutter wardrobeStudy tableQueen-size bedCozy L-shaped seating cornerAdd-ons:RugFan with integrated lightingKids Bedroom 2 ShraddhaTheme: Yellow & Green with dark wooden flooringWardrobe with seating in center (loft feasibility to be checked from bottom)Window-side dresserStudy provision requiredBalcony:Fixed seatingAdd-ons:Rug under bedBed back wall design as per referenceMaster Bedroom (MBR)Study unit on entrance view wallLong mirror on bathroom wallOpposite bed:Storage dresser with drawersWalk-in wardrobe: Existing (no changes)Entrance:Long standalone mirrorBathroomsGlass partition requiredAdditional RequirementsMosquito nets for all common windows | [6 empty] | 2026-05-03 |  | 2026-05-10
19517 | Turnkey | 2026-01-01 | Shrijit Ajithkumar | Runwal Eirene | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 872687 | 9999 | 0 | 0 | 0 | 82 | 0 | 77270 | 87269 | 367694 | 330455.6 |  |  | 2026-04-18 | 2026-04-21 13:05 | 2026-04-22 | 2026-04-22 18:13 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-04-18 | 2026-04-21 12:57 | 0 | 0 | 0 | 0 | 0 | 0 | 994046.857 | 160828 | 2026-04-28 16:29:15 +0530 | Prashant Panigrahi | Some Image was uploaded | 2026-04-18 18:57:41 +0530 | Pooja Nakul Sharma | DCM: Cx is also looking at civil work like flooring change and bathroom civil but its optional | 2026-04-18 18:56:58 +0530 | Pooja Nakul Sharma | Some Image was uploaded | 2026-05-07 |  | 2026-05-14
19518 | Turnkey | 2026-01-01 | Raj Onkar | rising city | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 2611575 | 9999 | 0 | 0 | 0 | 85 | 0 | 251159 | 261158 | 1114879 | 974380.8 |  |  | 2026-04-18 | 2026-04-21 13:17 | 2026-04-18 | 2026-04-21 18:33 | 2026-04-24 |  | 2026-05-01 |  | 2026-05-08 |  | 2026-05-12 |  | 2026-04-24 |  | 2026-04-25 |  | 2026-04-25 |  | 2026-04-26 | [5 empty] | 2026-05-02 |  | 2026-05-10 |  | 2026-05-11 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-27 |  | Unknown | 2026-04-18 | 2026-04-21 13:16 | 0 | 0 | 0 | 0 | 0 | 0 | 2213199 | 398375 | 2026-04-18 19:42:06 +0530 | Rishika Malviya | Some Image was uploaded | [6 empty] | 2026-05-02 |  | 2026-05-09
19519 | Turnkey | 2026-01-01 | Sonali Pagdhare | prescon midtown bay | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh |  |  | Nilesh Patel | Rizwan Mistry | Murali S | Harshaan Tiku | Siddhesh Gujrathi | Active | Preproduction | Procurement | 1308430 | 792428 | 2156264 | 0 | 1308430 | 3 | 6 | 0 | 0 | 0 | 516002 |  |  | 2026-04-18 | 2026-04-20 00:36 | 2026-04-20 | 2026-04-20 00:37 | 2026-04-23 | 2026-04-20 00:39 | 2026-05-03 | 2026-04-29 18:47 | 2026-05-25 | 2026-05-24 19:00 | 2026-06-23 | 2026-06-23 19:59 | 2026-04-20 | 2026-04-21 13:40 | 2026-04-21 | 2026-04-21 13:41 | 2026-04-21 | 2026-04-21 18:15 | 2026-04-26 | 2026-04-26 11:58 |  |  |  |  | 2026-04-29 | 2026-05-08 19:01 | 2026-06-20 | 2026-06-20 10:09 | 2026-06-21 | 2026-06-20 20:10 |  |  | 2026-06-25 | 2026-06-26 18:28 | 2026-06-28 | 2026-06-28 23:14 | 2026-06-29 | 2026-06-29 14:48 | 2026-08-01 | 2026-07-08 19:12 |  |  |  |  | 2026-07-12 12:02 | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-06-28 | 2026-07-09 12:58 | 2026-04-27 | 2026-04-29 18:45 | Site is RTMI | 2026-04-18 | 2026-04-20 00:13 | 1827342 | 328921 | 0 | 0 | 1458252.2403 | 246210 | 1458252.2403 | 246210 | 2026-07-08 19:33:16 +0530 | Reshma Melanta | Others: | 2026-07-08 13:51:33 +0530 | Reshma Melanta | Others: | 2026-06-29 19:35:36 +0530 | Reshma Melanta | Some Image was uploaded | 2026-04-30 | 2026-04-29 18:47 | 2026-05-25 | 2026-05-24 19:26 | RTMI
19520 | Turnkey | 2026-01-01 | Sushant Kumar Nanda | happy vally | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Anshul` Nikhar | Tanveer Patel | Akshat Shrivastava | Murali S | Anant Giri | Shailendra Mishra | Active | Installation | Execution | 888919 | 888919 | 1395285 | 0 | 888919 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-18 | 2026-04-18 19:24 | 2026-04-26 | 2026-04-26 19:33 | 2026-04-29 | 2026-04-27 15:15 | 2026-05-16 | 2026-05-16 14:12 | 2026-05-17 | 2026-05-16 15:04 | 2026-05-19 | 2026-05-19 08:23 | 2026-04-27 | 2026-04-28 19:28 | 2026-04-28 | 2026-04-28 20:19 | 2026-04-28 | 2026-04-29 10:45 | 2026-05-14 | 2026-05-14 16:21 |  |  |  |  | 2026-05-05 | 2026-04-28 19:28 | 2026-05-17 | 2026-05-17 20:31 | 2026-05-18 | 2026-05-17 20:31 |  |  | 2026-05-21 | 2026-05-28 18:16 | 2026-05-28 | 2026-05-28 19:38 | 2026-05-29 | 2026-05-28 20:47 | 2026-06-01 | 2026-05-30 18:54 |  |  |  |  | 2026-06-02 19:11 | 2026-06-09 | 2026-06-09 20:45 | 2026-06-21 | 2026-06-19 18:59 | 2026-06-19 | 2026-06-19 18:53 | 2026-06-19 | 2026-06-28 11:53 | 2026-06-29 | 2026-06-30 00:31 | 2026-07-04 | 2026-07-11 13:46 |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-05-28 | 2026-05-30 11:37 |  |  |  | 2026-04-18 | 2026-04-18 19:23 | 1185246 | 210038 | 0 | 0 | 951870.011 | 160005 | 951870.011 | 160005 | 2026-07-13 13:48:19 +0530 | Tanveer Patel | Execution: Membrane shutter pending Tandem drawers bottom panel received short Libra not received | 2026-07-01 23:39:38 +0530 | Tanveer Patel | Material delivered on 29 june Team is not planned yet | 2026-06-22 22:22:24 +0530 | Tanveer Patel | Procurement: Furniture is ready for disptached 25th june.Floor covering would be done on 24th june | 2026-05-17 | 2026-05-16 14:26 | 2026-05-17 | 2026-05-16 15:13
19521 | Turnkey | 2026-01-01 | Kannan Narayanan | independent house | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Design | 20% Payment | 1592956 | 219441 | 2242466 | 0 | 0 | 4 | 0 | 0 | 99150 | 685634 | 588731.2 |  |  | 2026-04-18 | 2026-04-19 17:10 | 2026-05-10 | 2026-05-10 12:04 | 2026-05-17 | 2026-05-18 00:26 | 2026-07-12 | 2026-07-11 19:21 | 2026-10-06 |  | 2026-10-13 |  | 2026-05-18 | 2026-05-20 19:16 | 2026-05-19 | 2026-05-20 19:16 | 2026-05-20 | 2026-05-29 17:37 | 2026-06-06 | 2026-06-06 17:25 |  |  |  |  | 2026-07-11 |  | 2026-10-08 |  | 2026-10-09 |  |  |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 | [6 empty] | 2026-11-06 |  | 2026-11-15 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-16 |  | 2026-11-18 |  |  |  | 2026-12-10 |  | 2026-12-12 |  | 2026-12-13 | [5 empty] | 2026-10-17 |  | 2026-07-20 | 2026-07-11 18:08 | Site is Non-RTMI | 2026-04-18 | 2026-04-19 17:07 | 1900395 | 342071 | 0 | 0 | 0 | 0 | 1859672.1722 | 307061 | 2026-07-14 17:45:08 +0530 | Purva Shiravle | Minutes of Meeting held on Date: 5-07-2026 & 11-07-2026 Attendees: Purva , Mr. Kannan and family Discussion: layout and design discussion Based on the meetings held on 05-07-2026 and 11-07-2026, please find below a summary of the requirements discussed: Living Room Sofa wall concept discussed TV unit placement and design finalized Addition of bottom unit on left side of tv unit Dining Area Wall concept discussed need warli art on dining area wall Bedrooms Placement of wardrobe, bed, study unit, and TV unit discussed and finalized Kitchen Cabinet placements discussed and finalized Addition of one wall unit above the sink area Loft addition in the service counter Pooja Unit To be discussed further based on direction and measurements | 2026-05-29 17:15:22 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-05-28 18:55:41 +0530 | Sanjana Swami |  | 2026-07-12 | 2026-07-11 19:31 | 2026-10-07 |  | Under Construction | 2026-08-31
19522 | Turnkey | 2026-01-01 | Rinku K Chawla | purvankara clarmount | MUM - Thane | No Estimate | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-18 | 2026-04-18 21:55 | 2026-04-19 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-18 | 2026-04-18 21:54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-30 15:03:42 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-04-21 15:43:00 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-04-18 21:56:33 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-04-26 |  | 2026-05-03
19523 | Turnkey | 2026-01-01 | Abhishek Agarwal | Minerva towers | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 4726009 | 9999 | 4726009 | 0 | 0 | 70 | 0 | 462602 | 472601 | 2086638 | 1694168.8 |  |  | 2026-04-18 | 2026-04-19 14:53 | 2026-04-18 | 2026-04-21 11:30 | 2026-05-07 | 2026-05-07 12:19 | 2026-05-14 |  | 2026-05-21 |  | 2026-05-28 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-08 |  | 2026-05-09 | [5 empty] | 2026-05-15 |  | 2026-05-23 |  | 2026-05-24 |  |  |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-03 | [6 empty] | 2026-06-21 |  | 2026-06-30 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-03 |  |  |  | 2026-07-25 |  | 2026-07-27 |  | 2026-07-28 | [5 empty] | 2026-06-01 |  | 2026-05-10 |  | Unknown | 2026-04-18 | 2026-04-18 20:21 | 4005093 | 720916 | 0 | 0 | 0 | 0 | 4005093 | 720916 | 2026-04-22 19:18:00 +0530 | Rishika Malviya | Some Image was uploaded | [6 empty] | 2026-05-15 |  | 2026-05-22
19524 | Turnkey | 2026-01-01 | Pratiksha Rao | Piramal Vaikunth | MUM - Thane | No Estimate | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-18 | 2026-04-18 20:27 | 2026-04-19 |  | 2026-04-23 |  | 2026-04-30 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-04-23 |  | 2026-04-24 |  | 2026-04-24 |  | 2026-04-25 | [5 empty] | 2026-05-01 |  | 2026-05-09 |  | 2026-05-10 |  |  |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-20 | [6 empty] | 2026-06-07 |  | 2026-06-16 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-19 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-05-18 |  | 2026-04-26 |  | Unknown | 2026-04-18 | 2026-04-18 20:27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-05-01 |  | 2026-05-08
19525 | Turnkey | 2026-01-01 | Anisha pendse | Lodha Sterling | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Faraz Soudagar | Aditya Vikram |  | Shreyash Kotecha | Shailendra Mishra | Active | Preproduction | Hoto | 1754475 | 272086 | 1741233 | 1754475 | 0 | 0 | 49 | 0 | 0 | 850770 | 631619.2 |  |  | 2026-04-18 | 2026-04-18 22:07 | 2026-04-22 | 2026-04-22 12:11 | 2026-04-27 | 2026-04-27 14:39 | 2026-05-15 | 2026-05-19 18:57 | 2026-07-05 | 2026-07-04 18:35 | 2026-07-11 | 2026-07-10 19:38 | 2026-04-27 | 2026-04-29 16:44 | 2026-04-28 | 2026-04-29 16:45 | 2026-04-29 | 2026-04-29 17:17 | 2026-05-05 | 2026-05-05 17:43 |  |  |  |  | 2026-05-19 | 2026-05-25 18:48 | 2026-07-06 | 2026-07-07 16:53 | 2026-07-08 | 2026-07-07 16:54 |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-18 |  | 2026-07-19 | [6 empty] | 2026-08-06 |  | 2026-08-15 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-12 | [5 empty] | 2026-07-14 |  | 2026-05-06 | 2026-05-15 13:25 | Site is Non-RTMI | 2026-04-18 | 2026-04-18 22:04 | 1475621 | 265611 | 1914953.525 | 323309 | 0 | 0 | 1914953.525 | 323309 | 2026-07-12 10:51:11 +0530 | Amisha Ahuja |  | 2026-07-12 10:41:10 +0530 | Amisha Ahuja |  | 2026-07-12 10:40:16 +0530 | Amisha Ahuja |  | 2026-05-20 | 2026-05-19 19:01 | 2026-07-05 | 2026-07-04 18:38
19528 | Turnkey | 2026-01-01 | Abhay Pendse | vasant prabha | MUM - GOR | Yes | Neha Yadav | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Ashish Jha |  | Active | Preproduction | DEM2 | 1288437 | 257687 | 1634048 | 0 | 0 | 24 | 0 | 0 | 0 | 606086 | 424664 |  |  | 2026-04-19 | 2026-04-19 13:24 | 2026-04-19 | 2026-05-29 20:11 | 2026-05-30 | 2026-05-30 16:54 | 2026-06-21 | 2026-06-21 12:28 | 2026-06-27 |  | 2026-07-04 |  | 2026-06-01 | 2026-05-30 15:47 | 2026-05-31 | 2026-06-02 12:08 | 2026-06-02 | 2026-06-02 19:06 | 2026-06-08 | 2026-06-08 13:59 |  |  |  |  | 2026-08-13 | 2026-06-20 14:33 | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-06-09 | 2026-06-21 12:19 | Site is RTMI | 2026-04-19 | 2026-04-19 13:23 | 1384786 | 249261 | 0 | 0 | 0 | 0 | 1381331.5428 | 231918 | 2026-06-21 12:45:12 +0530 | Neha Yadav | DDM2 will be align second Saturday of the next month as per his daughter availability. | 2026-06-21 12:39:32 +0530 | Neha Yadav | DDM1: DDM1 Meeting discussion: Kitchen: 1)Crockery unit need to do 3 which will be double shutter 2)Hob side wall unit & loft need to remove and there will be oven unit 3)masala unit need to add glass unit below 4)Mandir unit will have drawer with try & cnc shutter 138 Living: 1)TV unit will be 8 with tall unit & rafters on dinning wall 2)2 fan in the ceiling 3)3 shelf need to add in shoe unit Master: 1)wall packing need to do behind bed 2)Mirror need to add for dresser Dughter: 1)Storage need to arrange and extend near murphy bed Feel free to add a pointers if missed any.Â | 2026-06-08 13:58:59 +0530 | Vishakha Vaishnav | "Welcome call done " Initial measurement : Site is available for IM , cx said no civil work is going on at site DEM Dates -Â DEM 1 - Can be done 20th June need to confirm with designer DEM 2 - TBD DEM 3 - TBD Possession date : August 2026 Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-22 | 2026-06-21 12:42 | 2026-06-28 |  | Under Construction | 2026-08-01
19530 | Turnkey | 2026-01-01 | Anjani Kumar | Birla Tissya | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Preproduction | Site Readiness 1 | 1300364 | 260073 | 1730912 | 0 | 0 | 5 | 42 | 0 | 0 | 520145 | 520145.6 |  |  | 2026-04-19 | 2026-04-21 15:48 | 2026-04-21 | 2026-04-26 11:14 | 2026-05-03 | 2026-05-07 11:55 | 2026-05-25 | 2026-05-25 12:16 | 2026-08-06 |  | 2026-08-13 |  | 2026-05-07 | 2026-05-07 19:08 | 2026-05-08 | 2026-05-08 14:09 | 2026-05-08 | 2026-05-08 17:17 | 2026-05-17 | 2026-05-17 19:37 |  |  |  |  | 2026-05-23 | 2026-05-24 15:06 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-05-18 | 2026-05-25 12:12 | Site is Non-RTMI | 2026-04-19 | 2026-04-19 13:20 | 1466875 | 264037 | 0 | 0 | 0 | 0 | 1459948.473 | 241072 | 2026-07-14 15:00:12 +0530 | Akshay Ds |  | 2026-06-03 13:08:17 +0530 | Purva Shiravle | Some Image was uploaded | 2026-06-03 13:06:29 +0530 | Purva Shiravle | DDM1: Hi, Minutes of Meeting held on Date: 24-05-2026 Attendees: Mr. anjani kumar and family with purva Discussion: Based on 24-05-2026 meeting, below is a list of all the requirements that were discussed during the meeting: LVING ROOM- wall concept behind sofa and dining table was discussed and finalisedaddition of wooden rafters near entrance was therewill be retaining tv unit design as it is, just need - 2 options required one with tall glass unit & other w/o tall glass unit KITCHEN- 1.Layout for kitchen cabinets was discussed and finalised 2.addition of granite slab with shutter units below in utility area 3.addition of microwave unit near RO unit MASTER BEDROOM - Placements of bed, wardrobe and study unit was discussed and finalisedbed back design needs to retain i.e. with punning and wallpaperAddition of Used clothes unit near study unit and loft above wall unitsaddition of tall unit near bed side instead of dressing unit, reference image attached in PPTwardrobe internals are yet to be decided will be sharing pdf for internals suggestions PARENTS BEDROOM AND GUEST BEDROOM - Pooja unit was shifted from parents' room to guest bedroomwall designs finalised with the combination of wall beadings, wallpaper and paint for both the roomswardrobe internals are yet to be decided will be sharing pdf for internals suggestions WASHROOMS - Wall unit and base units of vanity were discussed | 2026-05-26 | 2026-05-29 18:33 | 2026-08-07 |  | Under Construction | 2026-07-01
19531 | Turnkey | 2026-01-01 | Parag Kachalia | Solitaire | MUM - GOR | Yes | [8 empty] | Avi Thakkar |  | Lost | Prospect | 10% Payment | 2211284 | 9999 | 3182714 | 0 | 0 | 82 | 0 | 211129 | 221128 | 996458 | 772568.8 |  |  | 2026-04-19 | 2026-04-24 11:52 | 2026-04-24 | 2026-04-24 12:01 | 2026-04-25 | 2026-04-26 22:19 | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-19 | 2026-04-21 18:09 | 2697215 | 485498 | 0 | 0 | 0 | 0 | 2653195.0281 | 457823 | 2026-05-20 17:49:05 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-20 17:48:27 +0530 | Christopher Macwan | Some Image was uploaded | 2026-05-08 12:58:39 +0530 | Avi Thakkar | Some Image was uploaded | 2026-05-04 |  | 2026-05-11
19532 | Turnkey | 2026-01-01 | Mahavir Jain | Dosti mezzo | MUM - GOR | Yes | Khyati Bandi | Reshma Melanta | Safalta Karkera | [5 empty] | Umang Shah |  | Hold | Design | 20% Payment | 1864194 | 219999 | 2450086 | 0 | 0 | 3 | 35 | 0 | 152840 | 838100 | 653255.2 |  |  | 2026-04-19 | 2026-04-19 20:32 | 2026-04-19 | 2026-04-21 11:25 | 2026-05-07 | 2026-05-07 14:16 | 2026-06-07 | 2026-06-07 19:35 | 2026-08-02 |  | 2026-08-09 |  | 2026-05-07 | 2026-05-08 19:26 | 2026-05-08 | 2026-05-09 11:02 | 2026-05-09 | 2026-05-12 14:47 | 2026-05-16 | 2026-05-16 13:57 |  |  |  |  | 2026-06-07 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-05-17 | 2026-06-07 17:43 | Site is RTMI | 2026-04-19 | 2026-04-19 20:31 | 2076344 | 373742 | 0 | 0 | 0 | 0 | 2063832.65 | 340046 | 2026-06-27 13:12:02 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-09 18:27:56 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-07 19:00:48 +0530 | Reshma Melanta | Date: 7th June 2026 Meeting Stage: DEM-1 Key Updates & Escalations: Designer Feedback & Re-assignment: The client expressed strong dissatisfaction with the current designer, noting a lack of interactivity and engagement. Furthermore, the client was concerned that the designer repeatedly highlighted limitations in Bonitos scope of work rather than focusing on solutions. Action Item: Designer change requested and initiated. Next Meeting: A revised DEM-1 meeting has been scheduled for next Sunday, 14th June 2026, with a new design partner. Commercials: The client has agreed to clear the 10% milestone payment by 25th June 2026, subject to Dipens approval. | 2026-06-08 | 2026-06-07 19:52 | 2026-08-03 |  | Under Construction | 2026-06-30
19534 | Turnkey | 2026-01-01 | Sonali Pethe | Puri velvet | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1079196 | 215793 | 1398054 | 0 | 0 | 13 | 24 | 0 | 0 | 439439 | 423963.6 |  |  | 2026-04-19 | 2026-04-20 12:14 | 2026-04-20 | 2026-04-20 13:55 | 2026-04-26 | 2026-04-26 19:35 | 2026-06-26 | 2026-06-26 20:56 | 2026-07-07 |  | 2026-07-27 |  | 2026-04-26 | 2026-04-28 17:04 | 2026-04-27 | 2026-04-30 12:18 | 2026-04-30 | 2026-04-30 18:39 | 2026-05-09 | 2026-05-09 16:09 |  |  |  |  | 2026-06-26 | 2026-07-02 11:44 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-06-01 | 2026-06-26 20:46 | Site is RTMI | 2026-04-19 | 2026-04-20 12:14 | 1184792 | 213262 | 0 | 0 | 0 | 0 | 1183696.7998 | 193606 | 2026-06-30 11:40:26 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-09 15:55:51 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-09 15:53:24 +0530 | Reshma Melanta | CX IS CURRENTLY NOT IN TOWN WILL BE BACK ON 31ST MAY 2026 POSSESSION JULY END NEED TO KEEP THE PROJECT ON HOLS TILL 1ST JUNE 2026 POST THAT WE CAN ALIGN A DEM - 1 MEETING ADDED MYSELF TO THE GROUP | 2026-06-27 | 2026-06-26 21:00 | 2026-07-08 |  | Under Construction | 2026-06-30
19535 | Turnkey | 2026-01-01 | Gaurav Gupta | Kalpataru Vivant | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 2648980 | 9999 | 0 | 0 | 0 | 83 | 0 | 254899 | 264898 | 1163938 | 955245.6 |  |  | 2026-04-19 | 2026-04-23 14:27 | 2026-04-18 | 2026-04-23 14:27 | 2026-04-25 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-19 | 2026-04-19 15:30 | 0 | 0 | 0 | 0 | 0 | 0 | 2378839.4038 | 419336 | 2026-04-23 14:14:07 +0530 | Priyanka Patel | DCM: Client Requirement CX Gaurav Family Details: 2 adults (parents), 2 kids (girls aged 14 & 7), and 2 elder membersSafety door requiredLiving Room: Sofa-cum-bedMandir with display unit (as per Vastu)TV unit with wall-mounted TV and shelvesBigger shoe rack outsideParents Bedroom: Queen size bedSide tablesWardrobe with mirror shuttersDressing unitTV provisionNo study table requiredKids Bedroom: Study table cum dresserSide tableWardrobeTV provisionAdditional storage requiredMaster Bedroom: Dresser cum studyMirror panelingTV unit provisionAdditional Notes: Mandir to be designed strictly as per Vastu guidelinesNext Meeting: 25th (scheduled) | [6 empty] | 2026-05-04 |  | 2026-05-11
19536 | Turnkey | 2026-01-01 | Ruchi Gupta | dosti eastern | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 1100232 | 9999 | 0 | 0 | 0 | 82 | 0 | 100024 | 110023 | 473782 | 406403.6 |  |  | 2026-04-18 | 2026-04-24 17:15 | 2026-04-18 |  | 2026-04-18 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-04-18 |  | 2026-04-19 |  | 2026-04-19 |  | 2026-04-20 | [5 empty] | 2026-04-26 |  | 2026-05-04 |  | 2026-05-05 |  |  |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-15 | [6 empty] | 2026-06-02 |  | 2026-06-11 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-07-06 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-05-13 |  | 2026-04-21 |  | Unknown | 2026-04-18 | 2026-04-21 17:34 | 0 | 0 | 0 | 0 | 0 | 0 | 934498 | 165733 | 2026-04-24 17:14:42 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-19 19:24:23 +0530 | Sakshi Hire | DCM: 741 carpet 20-30shoe rack 6 seater dining set with benchÂ crockery unit sofa with 2 chairs mandir in sofa corner 40" tv unit with back panel and drwer pipe covering shelf pvc with greenwall in balcony coffee table double door fridge microwave sink below window side 3 unit in kitchen rolling shutter unit pullout tray gbr sofa cum bed wardrobe loft workstation foldableÂ mirror on wardrobe shutter MBR bed king size dresser on left side table chest of drwers front side vanity fc for overall house except kitchen brick colour sofa or emerald | 2026-04-19 14:01:28 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-26 |  | 2026-05-03
19537 | Turnkey | 2026-01-01 | Rajnish Saklani | kia the lake | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 1323849 | 9999 | 1323849 | 0 | 0 | 57 | 0 | 122386 | 132385 | 544385 | 514694 |  |  | 2026-04-19 | 2026-04-19 14:14 | 2026-04-22 | 2026-04-22 12:21 | 2026-05-16 | 2026-05-19 12:32 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-04-19 | 2026-04-19 14:12 | 1124402 | 199447 | 0 | 0 | 0 | 0 | 1124402 | 199447 | 2026-05-19 10:58:32 +0530 | Priyamvada PV | CDP changes :Â No key holder, no seater in modular Pouffe, DD storageÂ Wall art can be added on left open space Mirror on dining wall art wall Suggesting vertical mirrorÂ on either sides of wallpaper 2 tandem drawers for kitchen extend island storage to 3'W storage for study No Pooja from BD scope MBR WR to be 3 set of double doors, Study wall mounted with DRS to be added remove wall punning from the top area and extend wallpaperÂ 2 Light points in living ceiling separated with dining ceiling, Passage with island ceiling | 2026-05-12 19:16:40 +0530 | Aman Kumar | Sales Insights Hello Team, The client is very particular about the budget and has already visited Livspace. Our CRM was also present there, but the deal was not closed. In short, the client is specifically looking for good design within a budget-focused approach. | 2026-04-22 12:21:32 +0530 | Nayan Reddy | DCM: Cx name : RajnishÂ & JyotiÂ (BLR) Address: KEYA , The leak terrace , A0604Â Profession : HR , ITÂ Â Â Possession :Â May 1st weekÂ Â How many people will be staying :Â 3 + 1Â Â Theme : MinimalÂ Â Entrance facing : North facingÂ Â Â Budget : 8L Â Foyer -Â Shoe rack with small seating Â Dining room- one wall make it highlighting Â Â Living room - TV size is 65" TV unit of base wall mounted drawers, open tall unit on one side and panel panel (refer image) Sofa back wall go for vertical trims (refer image ) Â Â Kitchen & Utility -Â Single door fridgeÂ Granite needed for kitchen, breakfast counter, Utility both sidesÂ RO unit on wall , check if we can accommodate GTPT Base, wall and loftÂ small storage under breakfast counter Â MBR- Sliding wardrobe -3 shutterÂ Bay window side panellingÂ Give ledge on wardrobe and bay window cornerÂ Highlight the bed wall with lighter toneÂ Refer plan Â PBR - (Asha & Ekansh) Refer planÂ Sliding 3 shutterÂ Pooja cum study table (refer the image ) Highlight the bed wall with lighter tone (wallpaper is also an option) Â Bathroom - Vanity base units and WC above give storage Â False ceiling - in all rooms Â CDP - 25th | 2026-05-27 |  | 2026-06-03
19538 | Turnkey | 2026-01-01 | Prajakta Kharade | Natasha avana | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Aryan Singh |  | Hold | Preproduction | DEM2 | 504277 | 101000 | 695287 | 0 | 0 | 0 | 66 | 0 | 0 | 238958 | 164319.2 |  |  | 2026-04-18 | 2026-04-22 11:42 | 2026-04-22 | 2026-04-22 14:37 | 2026-04-22 | 2026-04-22 14:39 | 2026-05-10 | 2026-05-10 14:19 | 2026-07-31 |  | 2026-08-07 |  | 2026-04-22 | 2026-04-22 21:13 | 2026-04-23 | 2026-04-24 22:42 | 2026-04-24 | 2026-04-25 10:16 | 2026-05-07 | 2026-05-07 11:17 |  |  |  |  | 2026-05-10 | 2026-05-10 16:02 | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-05-08 | 2026-05-10 13:43 | Site is RTMI | 2026-04-18 | 2026-04-19 14:23 | 589226 | 106060 | 0 | 0 | 0 | 0 | 589226 | 106060 | 2026-07-04 17:06:42 +0530 | Anil Jagtap | cx will receive possession by November *26 | 2026-05-27 13:59:57 +0530 | Amisha Ahuja | Some Image was uploaded | 2026-05-12 10:48:48 +0530 | Amisha Ahuja | Some Image was uploaded | 2026-05-11 | 2026-05-10 14:31 | 2026-08-01
19540 | Turnkey | 2026-01-01 | L. Sonali | Pelican square | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi | Sunil Kumar S M | Active | Preproduction | DEM2 | 1651356 | 436584 | 2365842 | 0 | 0 | 3 | 0 | 0 | 0 | 624602 | 590170.4 |  |  | 2026-04-19 | 2026-04-19 14:28 | 2026-04-29 | 2026-04-29 09:52 | 2026-04-30 | 2026-04-30 13:30 | 2026-06-14 | 2026-06-14 19:48 | 2026-07-15 | 2026-07-14 15:01 | 2026-08-15 |  | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-05 16:22 | 2026-05-05 | 2026-05-06 17:52 | 2026-05-17 | 2026-05-17 17:45 |  |  |  |  | 2026-06-14 | 2026-06-20 19:50 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-06-04 | 2026-06-14 12:04 | Site is RTMI | 2026-04-19 | 2026-04-19 14:26 | 2004951 | 360891 | 0 | 0 | 0 | 0 | 1962164.698 | 323978 | 2026-07-14 15:04:41 +0530 | Akshay Ds |  | 2026-06-16 13:15:07 +0530 | Purva Shiravle | DDM1: A.LIVING ROOM 1.TV unit design and placement discussed 2.addition of false ceiling (option with 3d panels) B. KITCHEN & DINING 1.placements of base, wall and top units discussed and finalised 2. addition of mid tall glass unit in niche 3.dining wall concept design finalised - combination of wall beading , wallpaper and gypsum panelling 4.need to check feasibility of corner open unit in island area 5. appliances sizes- chimney and hob 900mm 6. addition of panel above chimney C.GUEST BEDROOM Placement of dressing unit changed from bedside to opposite side of bed Addition of tall unit beside sliding wardrobe accrodingly sliding wardrobe size adjusted Wardrobe internals discussed and finalised combination of Mr.balanced and Mr. Casual required Wallconcept design discussed i.e. combination of gypsum panelling and wallpapers with cove light Addition of perifial False ceiling D. MASTER BEDROOM Placement of furniture discussed and finalised Addition of tall unit near study unit2 options for wall concept decided post material selection will finalise Aristo wardrobe shutter design finalised Internals of wardrobe discussed and finalised combination of Mr.balanced and Mr. Casual required Dressing unit design discussed - required 1 drawer with mirror on wall adjacent to wardrobe Study unit design discussed Addition of false ceiling with perifial double cove concept E. KIDS BEDROOM 1.kids room wallconcept discussed and finalised 2.addition of frame n shutters in mezzanine floor 3.study unit design discussed and finalised 4.Internals of wardrobe discussed and finalised combination of juni dhoni and little racer (note : remove hanger from juni dhoni and add 1 drawer instead) 5. need jungle theme 6.addition of false ceiling (cloud shape as per reference image) F. POOJA UNIT 1.Pooja unit design discussed 2.Internals discussed with the combination of wallpaper amd cnc cutting required 3.shutter design is yet to be finalised need to share some options G. BATHROOMS Vanity unit bedlow granite is required Vanity unit bedlow granite is requiredÂ | 2026-05-17 17:46:07 +0530 | Parasa Sri | client is expecting a call back from PH along with designer on tuesday | 2026-06-15 | 2026-06-14 19:48 | 2026-07-15 |  | Under Construction | 2026-07-01
19541 | Turnkey | 2026-01-01 | Shweta Varshney | Piramal Aranya | MUM - GOR | No Estimate | [8 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-19 | 2026-04-19 21:49 | 2026-04-20 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-04-19 | 2026-04-19 14:37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-08 13:34:41 +0530 | Moni Sahani | Some Image was uploaded | [6 empty] | 2026-05-07 |  | 2026-05-14
19542 | Turnkey | 2026-01-01 | Kamaljit Chawla | Raymond GS | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 6404547 | 9999 | 0 | 0 | 0 | 65 | 0 | 630456 | 640455 | 2637796 | 2485841.6 |  |  | 2026-04-19 | 2026-04-19 16:38 | 2026-04-30 | 2026-04-30 12:05 | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-04-19 | 2026-04-19 16:38 | 0 | 0 | 0 | 0 | 0 | 0 | 5427582 | 976964 | 2026-06-02 13:36:36 +0530 | Pooja Nakul Sharma | CDP link https://bonitodesigns-my.sharepoint.com/:v:/g/personal/meeting_organizer_bonito_in/IQDsolELRgVuQL9z-kp9t30RAcPGeb9aJNbWSJLGShWglLQ?referrer=Teams.TEAMS-ELECTRON&referrerScenario=MeetingChicletGetLink.view https://bonitodesigns-my.sharepoint.com/:v:/g/personal/meeting_organizer_bonito_in/IQBRYygDdx_cTJWQ8RQ36SAUAbfeo-73mUPUkZXBiOeW6-E?referrer=Teams.TEAMS-ELECTRON&referrerScenario=MeetingChicletGetLink.view | 2026-04-30 12:02:52 +0530 | Mayuri Patil | Minutes of Meeting (MOM)Client Name: Kamaljit Chawla Project: Raymond 5BHK 51st Floor (Flat No. 5101) Family Members: 6 (Couple + Parents + 2 Daughters) Overall PreferencesVastu: Basic compliance requiredView: Yogi Hills facingService: Full scope (excluding AC fixing client scope)Budget: ~60 Lakhs (flexible)Entrance & Living AreaDefined foyer areaShoe storage (approx. 30 pairs each)Dedicated altar spaceBar unit with accent chairProvision for jhula/exercise hookDining setup: Bench + 6-seater tableTV: 75-inch, wall-mountedKitchen & UtilityModular kitchenBalcony to be covered with shedPantry: L-shaped shelves with sliding doorsMaster Bedroom (Couple)King-size bed (with/without storage)Bedside tablesRocking chairAristo wardrobe with walk-in spaceTV unit (ledge)Dresser with mirrorParents BedroomKing/Queen bed with storageBed positioned on window wallAristo wardrobeGym RoomGym setupProvision for treadmillSpace for horse bars/standsDaughter 1 Kiara (18 yrs)Theme: BlueAristo wardrobeQueen-size bed without storageSleek, floating study unitSide table + mirrorWalk-in space to be createdGlass partition in bedroomDaughter 2 Krisha (15 yrs)Theme: Red & BlackAristo wardrobeQueen-size bed with storageSide table with mirrorTV ledgeGuest BedroomQueen-size bed with storageAristo wardrobeBase storage for bagsSide table / dresser with mirrorStudy + TV ledgeMurphy bed with sofa optionAdditional NotesFalse Ceiling, Painting, Electrical, Theme preference is vintage/ soft europeanAC fixing: Client scopeDesign to balance functionality + aesthetics across all rooms | 2026-04-19 16:40:19 +0530 | Nishtha Valawalkar | 5 BHK - Raymond GS 1800 sqft with balcony 2k sqft Budget idea given - 50 to 60L Clearly communicated that no floorng, tiling done. No silver coin pitched. A Tower 4 people will stay and 2 parents. | 2026-05-25 |  | 2026-06-01
19543 | Turnkey | 2026-01-01 | ketan madan | MICL Aaradhya Parkwood | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | Akash Jadhav | Sandeep Tiwari |  | Prashant Panigrahi | Shailendra Mishra | Active | Design | 60% Payment | 1191893 | 281697 | 1824119 | 0 | 1191893 | 4 | 0 | 0 | 0 | 447828 | 462367.6 |  |  | 2026-04-19 | 2026-04-21 13:07 | 2026-04-25 | 2026-05-09 21:55 | 2026-05-12 | 2026-05-11 13:04 | 2026-06-14 | 2026-06-14 15:40 | 2026-06-26 | 2026-06-25 11:44 | 2026-06-27 | 2026-06-26 12:02 | 2026-05-11 | 2026-05-11 13:59 | 2026-05-12 | 2026-05-12 12:07 | 2026-05-12 | 2026-05-13 10:57 | 2026-05-21 | 2026-05-21 17:04 |  |  |  |  | 2026-06-27 | 2026-06-14 12:37 | 2026-06-26 | 2026-06-25 16:21 | 2026-06-26 | 2026-06-25 16:21 |  |  | 2026-06-29 | 2026-07-10 21:28 | 2026-07-11 | 2026-07-11 15:49 | 2026-07-22 | 2026-07-11 21:39 | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-21 |  | 2026-06-10 | 2026-06-14 15:17 | Site is RTMI | 2026-04-19 | 2026-04-21 12:55 | 1548109 | 276010 | 0 | 0 | 1299298.128 | 214540 | 1299298.128 | 214540 | 2026-07-11 17:44:13 +0530 | Mehnaz Ashraf | Final docket and estimation link sent to client. | 2026-07-10 11:29:59 +0530 | Anil Jagtap | The cx wants a comparison of the quotation and also needs clarity regarding the design and pricing | 2026-07-05 16:48:49 +0530 | Mehnaz Ashraf | Pre Lam - sliding | 2026-06-15 | 2026-06-14 16:09 | 2026-06-26 | 2026-06-25 11:45
19544 | Turnkey | 2026-01-01 | yogesh ramani | landmark | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 4084553 | 9999 | 4084553 | 0 | 0 | 38 | 0 | 398456 | 408455 | 1688694 | 1578948.4 |  |  | 2026-04-19 | 2026-04-19 20:52 | 2026-05-12 | 2026-05-27 19:22 | 2026-06-06 | 2026-06-09 16:47 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-12 |  | Unknown | 2026-04-19 | 2026-04-19 20:25 | 3461486 | 623067 | 0 | 0 | 0 | 0 | 3461486 | 623067 | 2026-06-09 19:03:20 +0530 | Rinisha Masurkar | Recap: 19544 - Celebrity Design Presentation (CDP) with the customer 06 June ¦ Meeting ¦ Microsoft Teams Recap: 19544 - Celebrity Design Presentation (CDP) with the customer 06 June ¦ Meeting ¦ Microsoft Teams Recap: 19544 - Celebrity Design Presentation (CDP) with the customer 06 June ¦ Meeting ¦ Microsoft Teams Recap: 19544 - Celebrity Design Presentation (CDP) with the customer 06 June ¦ Meeting ¦ Microsoft Teams | 2026-06-02 13:13:46 +0530 | Rinisha Masurkar | Title: Design Consultation Meeting Project No: 19544 Client: yogesh ramani Hi, Mrs DishaÂ 1550SqftÂ 4 family membersÂ home office spaceÂ mandir opp kitchenÂ desk should be planned in the centerÂ 6 seater diningÂ 13' room heightÂ minimal tv setup no displayÂ 3 seater sofa with arm chairsÂ mandir and pantry storageÂ no L shapeÂ arm chair with foot restÂ rugsÂ wooden flooring can be planned in the study areaÂ space for bags, watches, - master bedroomÂ ottoman in front of the bed with storageÂ walkin wardrobeÂ king size bedÂ dresserÂ headboard with back storageÂ angular headboardÂ chest of drawers in the entrance if possible in the entranceÂ memory wall provisionÂ niche storage - son's bedroom (vedant) single platform bed with drawerÂ display for legoÂ Tv provision - parents roomÂ dresserÂ bedÂ layered lightsÂ service table near the dining console between the dining and sofaÂ 30 - 35Â |  |  |  | 2026-06-17 |  | 2026-06-24
19545 | Turnkey | 2026-01-01 | Sonia Bhandari | Adarsh | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 5428764 | 9999 | 5428764 | 0 | 0 | 66 | 0 | 532877 | 542876 | 2171506 | 2171505.6 |  |  | 2026-04-19 | 2026-04-19 17:14 | 2026-04-25 | 2026-05-02 09:07 | 2026-05-05 | 2026-05-15 10:04 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-09-11 |  | 2026-05-16 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-05-23 |  | 2026-05-31 |  | 2026-06-01 |  |  |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 | [6 empty] | 2026-06-29 |  | 2026-07-08 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-11 |  |  |  | 2026-08-02 |  | 2026-08-04 |  | 2026-08-05 | [5 empty] | 2026-06-09 |  | 2026-05-18 |  | Unknown | 2026-04-19 | 2026-04-19 17:10 | 4600647 | 828116 | 0 | 0 | 0 | 0 | 4600647 | 828116 | 2026-04-25 19:49:18 +0530 | Ramesh Nayak | Cx name : Suren And Sonia Address: Adarsh Welkin Park - 166 no Profession : HR Possession : Oct How many people will be staying : 2 Theme : Morden Tradition Entrance facing : W facing Budget : 45 to 50L Pet - 1 dog *Ground Floor* - Foyer - Thin wooden console with artwork or mirror (Check reference ) Check if something can be done on foyer side wall Living - No tv needed 3 seater sofa on both sides 2 arm chairs 2 ottoman Wall trims on both sofa walls Need a partition for living to dining area A bar unit coming on dining side of partition (18"x 2'.5"x H 42") - check the image cx likes floor lamps Need ceiling hanging light and fan as well Dining balcony- Need to extend the deck Need swing and coffee table with 4 seater 3d needed Dining - cx has dining table with 4 chairs - include a bench and consider this floor plan for placement Hanging light in centre and provision for fan Central AC needed Staircase bottom - Needed shoe rack and extra storage Lobby to BR1- Mid base unit (try keeping the cxs crockery unit) with wall art - refer image Kitchen - Monochrome and pastels Counter top is extending double door fridge Need tall unit for OTG and microwave Hob coming in centre of kitchen as marked in plan Need cylinder unit in utility or storage Sink and RO coming in corner (RO is Wall mounted ) Include quartz sintered stone (check if can be done) counter top should extend to dano tile Open unit of ledge in one side for small planters Provision for AG (no rollup shutter) Base wall and loft needed Need lighting as well Utility - DW,WM, and sink is coming so find placement Wall storage needed GBR - in ground floor Queen bed which cx has, keep according to placement in plan Base seating cum storage with small study table (check plan) Wardrobes coming in walk in *First floor* - MBR - Wooden flooring and minimal (no wallpapers ) CX has Foldable table so plan the study area with wall storage and the table they (need picture of table ) King size bed with side tables for 3D Tv unit oppo bed Walk in wardrobe needs one long mirror with storage for dresser as well with wardrobe Family Living - Need pooja room as a separate room and if not possible then give tall pooja unit, refer plan for placement BR2 - Ma'am King size bed with side table Bed back consider reference (wallpaper is also fine) Tv unit needed so place the bed accordingly Walk in need dresser unit with open tall unit and wardrobes Need armchair with footrest in corner BR3 - Son's Need study provision in corner 3 shutter wardrobe King size bed Tv unit Refer plan for placement *Second Floor* - Entertainment room - U shape Seating Tv unit with speaker provision Staircase railing give partition and bar unit provision GYM area - Need 3 shutter wardrobe in corner Open Terrace - Need gazebo as marked in plan Need provision for oven sink and some storage as marked in plan Extra - Check vendors for solar Bathrooms - need storage with LED mirrors False ceiling - Need for all area | 2026-04-19 17:13:37 +0530 | Ramesh Nayak | Some Image was uploaded |  |  |  | 2026-05-23 |  | 2026-05-30
19546 | Turnkey | 2026-01-01 | Ria Makwana | A N Heights | MUM - GOR | No Estimate | [8 empty] | Ashish Jha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-19 | 2026-04-19 19:46 | 2026-04-22 | 2026-04-22 12:10 | 2026-04-24 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-19 | 2026-04-19 19:39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-22 12:13:52 +0530 | Rishika Malviya | Some Image was uploaded | 2026-04-19 19:48:14 +0530 | Ashish Jha | Some Image was uploaded | 2026-04-19 16:47:59 +0530 | Unknown | About the Customer **Current Customer Stage and Next Steps** The customer is awaiting confirmation on a visit time with her husband and will provide an update by evening. In another instance, the customer requested to reschedule a discussion for the following week due to being out of town, with a confirmed meeting for Wednesday or Thursday. In a separate interaction, the customer was already present at the Bonito office, and the agent apologized for the missed inquiry. **Customer Needs, Concerns, and Budget** The customer's primary need is interior design services for a 2 BHK apartment, with a stated budget of 6 to 8 Lakhs. A key concern identified is the pricing, as Bonito's 2BHK pricing starts at 8 Lakhs, prompting the customer to discuss this with her husband. The customer also inquired about the scope of services, specifically plumbing and civil work. **Customer Engagement History** The customer previously inquired via Instagram for interior design services. One interaction involved scheduling a visit to Bonito's flagship interior design studio in Andheri, which was later postponed due to the customer being out of town. In another instance, the customer arrived at the Bonito office unexpectedly, leading to an apology from the agent for a missed inquiry. **Recommended Follow-up Actions** Follow-up actions should include sending personalized WhatsApp invitations with confirmed appointment details, emphasizing the importance of a family visit, and requesting feedback post-call. For the customer who is out of town, confirm the rescheduled appointment for Wednesday or Thursday of the following week. For the customer who arrived at the office unexpectedly, ensure the system is updated and apologize for the inconvenience. | 2026-05-03 |  | 2026-05-10
19548 | Turnkey | 2026-01-01 | Rushikesh Surve | 127 Raj Homes | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1184465 | 9999 | 1184465 | 0 | 0 | 76 | 0 | 108448 | 118447 | 509706 | 437866.4 |  |  | 2026-04-19 | 2026-04-20 12:16 | 2026-04-21 | 2026-04-21 17:49 | 2026-06-07 | 2026-06-07 13:53 | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-06-15 |  | 2026-06-23 |  | 2026-06-24 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 | [6 empty] | 2026-07-22 |  | 2026-07-31 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-03 |  |  |  | 2026-08-25 |  | 2026-08-27 |  | 2026-08-28 | [5 empty] | 2026-07-02 |  | 2026-06-10 |  | Unknown | 2026-04-19 | 2026-04-20 12:15 | 1006071 | 178393 | 0 | 0 | 0 | 0 | 1006071 | 178393 | 2026-04-30 16:25:43 +0530 | Meet Shah | Some Image was uploaded | [6 empty] | 2026-06-15 |  | 2026-06-22
19549 | Turnkey | 2026-01-01 | Shekar | Infinity Greenwoods | BNG - HSR | Yes | [8 empty] | Fuzail Girach |  | Active | Prospect | 10% Payment | 1757368 | 9999 | 1757368 | 0 | 0 | 57 | 0 | 165738 | 175737 | 702947 | 702947.2 |  |  | 2026-04-19 | 2026-04-19 17:18 | 2026-05-10 | 2026-05-10 13:31 | 2026-05-20 | 2026-05-20 11:01 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-05-28 |  | 2026-06-05 |  | 2026-06-06 |  |  |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-14 |  | 2026-05-23 |  | Unknown | 2026-04-19 | 2026-04-19 17:15 | 1489295 | 268073 | 0 | 0 | 0 | 0 | 1489295 | 268073 | 2026-05-10 12:37:05 +0530 | Nayan Reddy | DCM: Cx Name -Â Anugraha SÂ Crm - FuzailÂ RGM -19/04/26 Move in date -Â JulyÂ Budget - 10-15L Property name - Infinity GreenwoodÂ Direction -Â N facingÂ F to c -Â 10' Â brick ConstrctionÂ Living roomÂ 55" TvÂ maximum storage in tv unitÂ Display unitÂ 3+2 sofaÂ Dining areaÂ Crockery + Pooja unit as per vastuÂ Â 2.8*7' Display unit + wall glass shutter + Base unitÂ Modular kitchenÂ Fridge - 1000mm Granite -Â Cx scopeÂ Open for suggestionsÂ Tall unit -Â Â BAse unit Wall unitÂ LoftÂ GTPT cabinetÂ bar counter or Break fast counterÂ extended wall near fridge Cylinder cabinetÂ Wicker basketÂ UtilityÂ Washing machine + dishwaserÂ Janitor unitÂ wall unitÂ sink unit MBRÂ Wardrobe + loftÂ King bedÂ dresserÂ BedroomÂ - 11.6 *11.2 Work roomÂ false ceilingÂ Wardrobe + LoftÂ DresserÂ bay windowÂ + Work statitionÂ Bedroom 2 -GBRÂ WardorbeÂ +loftÂ Mirrort Queen sizeÂ Washroom vanity - base unit + wall unitÂ FC in living and Dining areaÂ Â | [6 empty] | 2026-05-28 |  | 2026-06-04
19551 | Turnkey | 2026-01-01 | Mr. Rahul Sadashiv Lokare Sadashiv Lokare | Arihant Aspire | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | 10% Payment | 1120461 | 9999 | 0 | 0 | 0 | 6 | 0 | 102047 | 112046 | 448184 | 448184.4 |  |  | 2026-04-19 | 2026-04-21 13:46 | 2026-06-21 | 2026-06-21 19:38 | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-04-19 | 2026-04-21 13:45 | 0 | 0 | 0 | 0 | 0 | 0 | 949543 | 170917 | 2026-06-21 19:34:20 +0530 | Hemant Sonar | DCM: Client Name: Rahul * Family Members: Husband & Wife Â Â * Daughter: 2.5 years * Possession: December 2026 Living Room * TV unit with ledges * 3-seater sofa (existing) * Shoe rack with seating * Temple unit * Mirror finish / design to be discussed Kitchen * Semi-modular kitchen * Base units * Wall units * Loft unit * Dedicated space for microwave Bedroom 1 (Guest / Daughters Bedroom) * Foldable study unit with ledges * Wardrobe with side mirror storage * Queen-size bed * Niche loft as per site condition Master Bedroom * Full-size wardrobe * Queen-size bed * Dresser with mirror * Niche loft near the window False Ceiling & Lighting * False ceiling in living room and master bedroom * Only side false ceiling treatment Washrooms * Vanity units * Mirror storage above vanity Budget * 1012 lakhs | 2026-04-22 12:01:24 +0530 | Subhan Khan | Some Image was uploaded | 2026-04-21 14:00:13 +0530 | Subhan Khan | Follow up to be taken on 15th May 2026. Client works for Bank and he will get to know whether he might get a transfer from his job by 15th May. If he doesn't gets transfer then he will be renting out the flat. DCM and CDP is scheduled as per his decision. | 2026-07-20 |  | 2026-07-27
19553 | Turnkey | 2026-01-01 | Surya Pratap Singh | Odion wood of east | BNG - HSR | Yes | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | 10% Payment | 4876771 | 9999 | 0 | 0 | 0 | 66 | 0 | 477678 | 487677 | 1998300 | 1903117.2 |  |  | 2026-04-19 | 2026-04-19 18:49 | 2026-05-03 | 2026-04-24 09:52 | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-04 |  | 2026-05-05 | [5 empty] | 2026-05-11 |  | 2026-05-19 |  | 2026-05-20 |  |  |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 | [6 empty] | 2026-06-17 |  | 2026-06-26 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-29 |  |  |  | 2026-07-21 |  | 2026-07-23 |  | 2026-07-24 | [5 empty] | 2026-05-28 |  | 2026-05-06 |  | Unknown | 2026-04-19 | 2026-04-19 18:39 | 0 | 0 | 0 | 0 | 0 | 0 | 4132857 | 743914 | 2026-04-24 09:49:37 +0530 | Ankita Agarwal | DCM: MOM Mr. Surya ResidenceProject ID: 19553 Client Name: Mr. Surya RGM: Surya Facing: East Possession Timeline: End of May No. of Members: 4 Kids: 2 Girls (13 yrs & 8 yrs) Budget: 2530L (+56L buffer) FOYERPartition to be designed (Crystal/Glass option to be proposed)No wall on living room opening sideShoe unit with seating (Curved design preferred)Shoe unit back wall to be designed (paneling / highlight wall) LIVING ROOMTV unit (Wall-mounted, minimal open storage)Fluted panel with minimal back panel designPreference for solid tonesClean, minimal aesthetic STAIRCASE WALLFeature wall design to be suggestedDouble height drop light to be included COURTYARDWall design required:Options: Mural / Stone Cladding / Terracotta finish KITCHENBase unit + Wall unitAcrylic finish kitchenPantry unit (Tall unit outside kitchen)Loft storage requiredFalse ceiling due to floor height differenceCombination shutters: Glass + PlainBreakfast counter with display unit DINING AREACrockery unit with handwash spaceBase + Wall unit till ceiling/design level UTILITYJanitor cabinet behind doorDishwasher to be accommodated with janitor unitSink remains in existing position BEDROOM 1 GROUND FLOOR (GBR)Wardrobe with loft (Hinged)King size bedWorkstation (34 ft, minimal storage with shelves)Bed back design (Wall trims + wallpaper)Dresser with foldable table near balconyEntrance wall design requiredBase vanityFalse ceiling FAMILY AREA (FIRST FLOOR)TV unit (65 inch)Minimal design with drawer storagePastel tone highlight with wallpaperSofa back wall to match themePlanter (Optional) MASTER BEDROOM FIRST FLOOR (GBR 2)L-shape wardrobe with loft (Hinged)Double king size bedWorkstation (34 ft, minimal storage)Bed back design (Wall trims + wallpaper)Dresser with foldable table near balconyEntrance wall design requiredBase vanityFalse ceilingTV unitWalk-in dresser provision SECOND FLOORPOOJA UNITOpen pooja unit with shutter/blind provisionSeating arrangement for poojaSpace for 67 idols + 1 main idolSTUDY AREAL-shape study unitWall-side storageWindow-side extensionAdditional seating: Coffee table + 2 armchairs KIDS BEDROOMKing size bedBed back designSide tables on both endsStudy unit with wall storageWalk-in wardrobe with dresserBathroom vanityWindow: W10 ventilator (top only) BALCONYDesign to be proposed BEDROOM 2 MASTER BEDROOMWindow W7 (First window closed at entrance)Amber tone theme preferredSame requirements as first floor master bedroomWork desk requiredTranslucent wardrobe to be designed FALSE CEILINGMinimal false ceiling across houseBalanced lighting approach (functional + ambient) | 2026-04-19 18:39:39 +0530 | Unknown | About the Customer **Customer Property Details and Visit Status** The customer has confirmed their property details, including location (Bangalore, Sarjapur, Odean Wood Of East) and type (3BHK), with possession expected in 4 months to 1 month. They have a budget of â‚¹15-20 lakhs for the 3BHK and 30-40 lakhs for another property, and are primarily interested in the execution of their existing interior design plan. An experience center visit was scheduled for April 7th at 11 AM at the HSR Layout center, with a tentative agreement for a Sunday visit for another interaction. **Customer Needs and Budget** The customer's primary need is the execution of their interior design plan, with a budget of â‚¹15-20 lakhs for a 3BHK and â‚¹30-40 lakhs for another property. They are looking for customization and discussion on modifications to their existing plan, and are interested in Bonito's comprehensive interior solutions, with a starting ticket price of â‚¹7 lakhs. **Customer Engagement History and Qualification** Across multiple interactions, agents from Bonito Designs have introduced the 'India's Biggest Interior Design Festival' and its offers, including a â‚¹1,00,001 Shagun amount, GST benefits, up to â‚¹4 lakh off on modular kitchens, and a postpaid payment scheme. They have also emphasized the value proposition of '2025 Home Interiors at 2022 Prices' and Bonito's quality assurance with a 10-year product warranty and 1-year service warranty. The customer has been qualified on location, property type, possession timeline, and budget. **Scheduled Visits and Follow-up Actions** The customer has shown a tentative agreement to visit the experience center, with a confirmed appointment for April 7th at 11 AM at the HSR Layout center, and a potential visit on Sunday. They prefer to discuss floor plan details in person at the center. A personalized WhatsApp invitation is to be sent, and the agent will call back at noon the following day to share details and request the floor plan. **Recommended Follow-up Actions** Recommended follow-up actions include sending the confirmed WhatsApp invitation for the April 7th visit, ensuring the agent calls back at noon as promised to discuss floor plans and gather necessary details, and preparing for the customer's preference to discuss floor plans in person at the HSR Layout experience center. |  |  |  | 2026-05-11 |  | 2026-05-18
19555 | Turnkey | 2026-01-01 | Sangeeta Arvind Karadkar | Leo Eminence | MUM - GOR | Yes | Riddhi Deshpande | Vishakha Vaishnav | Kashmira Nerurkar |  | Priyanka Kamble | Nilesh Patel | Rizwan Mistry |  | Ashish Jha | Sunil Poojary | Active | Design | 60% Payment | 1090392 | 382390 | 1258564 | 911952 | 1090392 | 1 | 0 | 0 | 0 | 315462 | 392539.6 |  |  | 2026-04-19 | 2026-04-19 19:56 | 2026-05-31 | 2026-05-31 12:48 | 2026-06-02 | 2026-06-02 14:21 | 2026-06-14 | 2026-06-13 16:59 | 2026-06-24 | 2026-06-23 19:05 | 2026-07-04 | 2026-07-04 12:21 | 2026-04-30 | 2026-05-30 23:02 | 2026-06-03 | 2026-06-02 17:34 | 2026-06-02 | 2026-06-03 18:50 | 2026-06-06 | 2026-06-06 15:30 |  |  |  |  | 2026-06-13 | 2026-06-20 20:21 | 2026-06-24 | 2026-06-25 17:09 | 2026-06-26 | 2026-06-25 17:26 |  |  | 2026-07-05 | 2026-07-12 12:52 | 2026-07-12 | 2026-07-12 17:05 | 2026-07-13 | 2026-07-14 19:55 | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-12 |  | 2026-06-07 | 2026-06-13 16:42 | Site is RTMI | 2026-04-19 | 2026-04-19 19:17 | 1066579 | 191984 | 1060989.6075 | 172701 | 1251248.7017 | 204820 | 1251248.7017 | 204820 | 2026-06-11 13:40:39 +0530 | Riddhi Deshpande | DDM1: tranSition MOM MOM: material Prelam with HDHMR. Living room: TV unit 2 drawers and a top Mandir unit Kitchen: Sink unit shutter unit- corner unit- 3 drawer pullout Wall unit all shutters Loft no base panel added Bed 1 Wardrobe and loft No internal knobs Bed added no study no dressing master bedroom 2x wardrobe and loft no internal knobs added bed added tv ledge study ledge pullout mirror added electrical cost considered 32k false ceiling for living room dcor only 16k considered tv panel 26k considered both vanities considered | 2026-06-06 15:29:36 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : As per cx IM is done on 6th June need to confirm with designer DEM Dates -Â DEM 1 - CX will update in group DEM 2 - TBD DEM 3 - TBD Possession date : June End Customer will make 10% onÂ Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-03 18:49:56 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: Next week of June 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM 4th June 2026 * DEM 1 12th June 2026 * 10% Payment Stage 13th June 2026 *Transaction will be B2C self funding *No civil work Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 10,60,990 Offers Discussed During the Call: Laminate Upgrade - May '26 Campaign Design fee waiver (5%) Free Bed Offer 100% GST Waiver PM fee waiver (2.5%) Free Shoerack Offer Laminate Upgrade - Windows to Wonderful home Final Closing Value Discussed: 9,11,953 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-14 | 2026-06-13 17:00 | 2026-06-24 | 2026-06-23 19:07 | Under Construction | 2026-06-13
19556 | Turnkey | 2026-01-01 | zameer | 3bhk Villa | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1814804 | 9999 | 0 | 0 | 0 | 87 | 0 | 171481 | 181480 | 725922 | 725921.6 |  |  | 2026-04-19 | 2026-04-19 19:19 | 2026-04-20 |  | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-19 | 2026-04-19 19:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1537970 | 276834 | 2026-04-24 13:00:15 +0530 | Aparna | MOM Interior Design DiscussionClient Name: Zameer Property: Earth Villas Profession: IT Theme: Classy with Moulding Details Entrance Facing: West Budget: 1520 Lakhs Family Members: 3 (2 Adults + 1 Child) CDP Meeting Date: 25.04.2026 Overall Design DirectionTheme to follow a classy aesthetic with extensive moulding elementsCombination of membrane and laminate finishesNeutral base palette with elegant detailing and highlightsFocus on functional storage + decorative wall treatmentsGROUND FLOORGeneral FinishesFinish: Membrane (Green tone palette)Flooring: Off-whiteKitchenUnits:Base unit, wall unit & loftWall units:Mix of glass + membrane shutters23 units dedicated as crockery displayPantry unit requiredOTG unit provisionChimney:Glass shutters on both left & right (mandatory)Dishwasher:To be placed beside sink unit (not below)Mixie storage:Sliding platform provisionDining AreaFalse ceiling for dining + passage areaLiving AreaTV unit:Wall paneling with moulding design (mandatory as per reference)Arch (ARC) design required (as per reference)Staircase wall:Moulding design (reference shared)Staircase AreaSingle storage unit with open/closed shelvingGuest Bedroom (GBR)Finish: LaminateWardrobe:Positioned on bathroom wall (as per reference)Study unit:Opposite bed wallIncludes table with base storage & wall cabinetFIRST FLOORMaster Bedroom (MBR)Finish: LaminateWall design:As per reference shared in groupWalk-in wardrobe:Design as per client referenceKids Bedroom (KBR)Finish: MembraneTheme: Pink & WhiteWardrobe:Mirror on shutter (ref taken, design can be enhanced)Study unit requiredStorage:White cabinet with glass shuttersStudy table:Pink finishSECOND FLOORTheatre RoomFinish: LaminateTV wall:Moulding designStorage:Straight wardrobe (instead of walk-in)Mirror on one shutterBathrooms (MBR & KBR)Storage units beside mirrorsDesign reference to be shared by clientAdditional RequirementsGlass partition for bathroomsSliding window for seating areaÂ | [6 empty] | 2026-05-03 |  | 2026-05-10
19557 | Turnkey | 2026-01-01 | Suneel Muppuri | Eco Life Akash | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  | Sethuragavan R | Affaan Abdulla | Jairam Joshi | Murali S | Rajoshi Sarkar | Raghavendra Gowda | Active | Production | 100% Payment | 1751794 | 1081873 | 2214990 | 0 | 1751794 | 1 | 0 | 0 | 0 | 0 | 669921 |  |  | 2026-04-19 | 2026-04-19 19:23 | 2026-04-20 | 2026-04-26 05:05 | 2026-04-29 | 2026-04-27 12:15 | 2026-06-07 | 2026-06-07 11:39 | 2026-06-17 | 2026-06-16 16:39 | 2026-06-26 | 2026-06-26 12:46 | 2026-04-27 | 2026-04-29 11:21 | 2026-04-28 | 2026-04-29 12:01 | 2026-04-29 | 2026-04-29 18:59 | 2026-05-02 | 2026-05-02 19:54 |  |  |  |  | 2026-06-07 | 2026-06-11 17:15 | 2026-06-17 | 2026-06-19 22:23 | 2026-06-20 | 2026-06-19 22:23 |  |  | 2026-06-27 | 2026-06-30 10:50 | 2026-06-30 | 2026-06-30 17:13 | 2026-07-01 | 2026-06-30 21:24 | 2026-07-01 | 2026-07-02 12:33 |  |  |  |  | 2026-07-03 18:31 | 2026-07-10 | 2026-07-09 20:42 | 2026-07-16 | 2026-07-14 18:44 | 2026-07-15 |  | 2026-07-14 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-30 | 2026-07-03 18:30 | 2026-05-31 | 2026-06-04 15:53 | Site is RTMI | 2026-04-19 | 2026-04-19 19:21 | 1877110 | 337879 | 0 | 0 | 2050254.826 | 338536 | 2050254.826 | 338536 | 2026-07-13 15:27:33 +0530 | Jairam Joshi | Procurement: CX side Ele work in progress key - 13th FC -14th False cieling and POP punning - 20th SRD -21st | 2026-07-06 18:15:26 +0530 | Jairam Joshi | Procurement: CX side Ele work in progress key - 8th FC -9th False cieling and POP punning - 18th SRD -19th | 2026-05-22 11:27:15 +0530 | Manoj Kumar R | DDM1: Please find the MOM for the meeting dated 09-05-2026. Shoe Rack * Shoe storage unit with seating to be considered on the right side of the main entrance door. Living Room TV Unit * TV unit to be redesigned. * Sofa back-wall design to be planned based on the finalized TV unit design. Â Crockery Unit * Curtain space to be considered. * DrawerÂ to be provided in the left-side bottom storage. * Ledge to be provided above the mirror & mirror to be extend above the ledge. * wall unit having 1 wooden shutter door & 2 glass shutter doors Pooja Unit * Pooja unit of 2.5 ft width to be planned. * CNC shutter design to be revised with Chakra & Namam design. Â Kitchen * Ventilation grills to be provided for Sink unit & Rice storage unit. * 2 wicker baskets to be considered. * Curved ledge option to be shown next to the tall unit. * Rolling shutter depth to be decide based on appliance dimensions. * Wall unit glass shutters to be maintained symmetrically, wall unit design to be adjusted accordingly. * Space to be provided for RO unit & next to the Ro Dish drainer unit to be considered. * Client has planned a partition wall in the washing machine area. Master Bedroom (MBR) * Aristo wardrobeÂ to be consider end-to-end. * Inside wardrobe dresser tall unit with mirror to be consider * currently Client is planned for an 8.5 ft wide bed, Based on available space foldable study table with ledges to be considered. * Bed back-wall design to be redesigned. * TV unit ledge to be curved ledge. Â Parents Bedroom (PBR) * Bed back-wall design to be considered. * Mirror to be provided on the right-side wardrobe shutter. * Study unit to be planned based on available space. Â Kids Bedroom (KBR) * Mirror to be provided on wardrobe shutter. * Study unit to be redesigned with additional storage. False Ceiling * False ceiling to be considered for the entire house. | 2026-06-08 | 2026-06-07 11:42 | 2026-06-17 | 2026-06-16 18:52 | Under Construction | 2026-05-15
19558 | Turnkey | 2026-01-01 | Sandeep patil | Narang Privado | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Hold | Design | DEM1 | 1746952 | 233867 | 2238688 | 0 | 0 | 35 | 43 | 0 | 115523 | 818024 | 579537.6 |  |  | 2026-04-19 | 2026-04-22 11:59 | 2026-04-24 | 2026-04-24 13:08 | 2026-04-26 | 2026-04-28 13:37 | 2026-10-05 |  | 2026-10-12 |  | 2026-10-19 |  | 2026-04-26 | 2026-04-27 18:45 | 2026-04-29 | 2026-04-28 13:56 | 2026-04-28 | 2026-04-28 14:28 | 2026-09-30 | [5 empty] | 2026-10-06 |  | 2026-10-14 |  | 2026-10-15 |  |  |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-25 | [6 empty] | 2026-11-12 |  | 2026-11-21 |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-22 |  | 2026-11-24 |  |  |  | 2026-12-16 |  | 2026-12-18 |  | 2026-12-19 | [5 empty] | 2026-10-23 |  | 2026-10-01 |  | Unknown | 2026-04-19 | 2026-04-22 11:58 | 1897193 | 341494 | 0 | 0 | 0 | 0 | 1897193.812 | 316060 | 2026-07-10 19:42:00 +0530 | Divya Rahangdale | CX will receive the possession by September. | 2026-06-29 13:40:51 +0530 | Harshali Bhuyar | Project on hold till 30th september | 2026-06-14 14:16:17 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-10-06 |  | 2026-10-13
19559 | Turnkey | 2026-01-01 | Akshata Mhatre | munot vastu | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | 10% Payment | 1052963 | 9999 | 0 | 0 | 0 | 65 | 0 | 95297 | 105296 | 449543 | 392827.6 |  |  | 2026-04-19 | 2026-04-22 12:01 | 2026-04-24 | 2026-04-24 20:17 | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-06-13 |  | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-08 |  | Unknown | 2026-04-19 | 2026-04-22 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 892342 | 160621 | 2026-06-10 12:51:46 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-09 12:46:54 +0530 | Krutika Vernekar | CDP: Recap: 20448 - Design Consultation Meeting (DCM) with the customer 07 June ¦ Meeting ¦ Microsoft Teams | 2026-06-09 12:45:16 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-13 |  | 2026-06-20
19560 | Turnkey | 2026-01-01 | Md Abuzar Shaikh | shelter river | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 1184848 | 9999 | 0 | 0 | 0 | 87 | 0 | 108486 | 118485 | 521548 | 426330 |  |  | 2026-04-19 | 2026-04-19 20:31 | 2026-04-20 |  | 2026-04-21 |  | 2026-04-28 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-04-21 |  | 2026-04-22 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | 2026-04-29 |  | 2026-05-07 |  | 2026-05-08 |  |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-04-24 |  | Unknown | 2026-04-19 | 2026-04-19 20:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1004109 | 180739 | 2026-05-21 12:58:02 +0530 | Umang Shah | Some Image was uploaded | [6 empty] | 2026-04-29 |  | 2026-05-06
19561 | Turnkey | 2026-01-01 | Acer Steel | lodha Bellevue | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 1958244 | 391649 | 2397866 | 0 | 0 | 1 | 43 | 0 | 0 | 906412 | 660183.2 |  |  | 2026-04-19 | 2026-05-03 20:30 | 2026-05-03 | 2026-05-03 20:30 | 2026-05-06 | 2026-05-06 12:50 | 2026-05-30 | 2026-05-30 18:09 | 2027-01-02 |  | 2027-01-09 |  | 2026-05-06 | 2026-05-07 19:13 | 2026-05-07 | 2026-05-07 19:16 | 2026-05-07 | 2026-05-12 11:41 | 2026-05-16 | 2026-05-16 13:30 |  |  |  |  | 2026-05-30 | 2026-06-01 14:58 | 2027-01-04 |  | 2027-01-05 |  |  |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 |  | 2027-01-15 | [6 empty] | 2027-02-02 |  | 2027-02-11 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-12 |  | 2027-02-14 |  |  |  | 2027-03-08 |  | 2027-03-10 |  | 2027-03-11 | [5 empty] | 2027-01-13 |  | 2026-05-17 | 2026-05-30 16:48 | Site is RTMI | 2026-04-19 | 2026-04-29 19:52 | 2032089 | 365776 | 0 | 0 | 0 | 0 | 2000807.3004 | 336850 | 2026-06-02 17:41:26 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-30 15:52:13 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-16 13:29:12 +0530 | Reshma Melanta | MOM Updates: Project Status & Next Steps Possession Timeline: The client's handover/possession is scheduled for January 2027. Upcoming Meeting: A alignment meeting needs to be scheduled with the client between May 23rd and May 24th, 2026. Payment Milestone: The client will release the 10% payment immediately following the conclusion of this meeting. Project Status: The project is to be officially placed on hold after the meeting and payment clearance. Project Oversight: Added myself to the communication group for direct monitoring and updates. | 2026-05-31 | 2026-05-30 18:35 | 2027-01-03 |  | Under Construction | 2027-01-01
19562 | Turnkey | 2026-01-01 | Sachin Khedekar | Hiranandani Falcon | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1451214 | 9999 | 0 | 0 | 0 | 81 | 0 | 135122 | 145121 | 660033 | 500938.4 |  |  | 2026-04-19 | 2026-04-19 20:51 | 2026-04-21 | 2026-04-21 19:38 | 2026-04-25 |  | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-04-25 |  | 2026-04-26 |  | 2026-04-26 |  | 2026-04-27 | [5 empty] | 2026-05-03 |  | 2026-05-11 |  | 2026-05-12 |  |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 | [6 empty] | 2026-06-09 |  | 2026-06-18 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-20 |  | 2026-04-28 |  | Unknown | 2026-04-19 | 2026-04-19 20:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1229843 | 221371 | 2026-04-21 19:39:17 +0530 | Maasoumeh Raza | Some Image was uploaded | 2026-04-21 19:36:19 +0530 | Maasoumeh Raza | DCM: Name: 19562 - Sachin KhedekarÂ Property Name: Hiranandani Falcon Property type: 2bhk Possession: June End Move in: August 10. Member: 5 member [1 couple ,1 senior & 18 & 20 boy & girls] Budget: 10LÂ Requirements: Existing : Mandir Living room: Safety door with panelling Shoe rack outside [40 pairs] Tv Unit & display [55 inch] MandirÂ L shape sofaÂ 6 Seater diningÂ Balcony design option needed.Â Kids bedroom:Â Queen size bed [Hydrolic] Wardrobe with loft Study table with bookshelf Master bedroom:Â Queen size bed Wardrobe with loft Dressing Unit Cum Study table Additional scope: Full home Painting |  |  |  | 2026-05-03 |  | 2026-05-10
19563 | Turnkey | 2026-01-01 | Jignesh Thaker | krishna kunj | MUM - GOR | No Estimate | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-19 | 2026-04-28 12:47 | 2026-05-13 | 2026-05-13 17:10 | 2026-04-20 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-04-19 | 2026-04-19 20:40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-21 12:57:25 +0530 | Umang Shah | Some Image was uploaded | 2026-05-13 17:09:42 +0530 | Priyanka Patel | DCM: 1. Name of the customer jignesh thakkar 2. Profession Bussiness 3. Project Name/Tower Name/Flat Number krishna kunj 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK 5. Site Access Date 2026-05-13 6. Possession Date 2026-05-13 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 800000 Customer Preferences8. Who will be living in the house? Couple 9. What activities do you usually prefer at your home ? Pursuing Hobbies, Relaxing and Unwinding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] yes 11. Mention basic vastu principles agreed for integration in design, if any yes 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) yes Upload reference images 14. Any absolute no-go styles colours or materials no dark colours 15. Do you have any existing furniture that must be accommodated? no 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Console, Partition 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests, TV Focus 2. Must-have furniture or features? TV unit, Home speakers, Speakers, Coffee table, Puja unit, Display unit , Statement Wall/ Feature, Sofa 3. Choose your decor inspirations 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Built-in Oven, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type 2. Master Bedroom - Wardrobe style 3. Master Bedroom - Additional units 4. False Ceiling Required - Master Bedroom 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any yes 2. Other commitments made by Bonito to customer, if any yes 3. What are offers committed to customers? yes 4. Move-in date confirmed with customer 2026-09-13 5. Any special occasion mentioned by the customer wrt handover date no 6. Additional Requirements (Mention any requirements from customer not covered in the form) yes 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 800000 | 2026-04-19 20:33:03 +0530 | Unknown | About the Customer **Customer Status and Next Steps** Customer Vignesh has confirmed his budget for a 2BHK renovation in Kandivali West, Mumbai, aligning with Bonito Designs' starting price range of 8-10 lakhs. He is scheduled to visit the Andheri experience center after receiving a WhatsApp invitation with further details and images. Customer Jignesh Thakkar was unable to confirm his visit for Monday and requested a callback then, indicating he would plan accordingly. **Customer Needs and Concerns** Customer Vignesh requires kitchen and living room renovation and expressed uncertainty about his budget, having received varying quotes from other providers. He also found the 60-90 day home vacation requirement for renovation difficult but potentially manageable. Customer Jignesh Thakkar's primary need was to reschedule his visit to the experience center. **Customer Engagement History - Vignesh & Jignesh** Agent Pratiksha from Bonito Designs confirmed Vignesh's appointment and discussed his renovation needs in Kandivali West, Mumbai. Vignesh proposed visiting the Andheri experience center the following Wednesday, Thursday, or the subsequent Sunday. Jignesh Thakkar was contacted to confirm his visit for Monday, but he requested a callback on Monday as he would be back in Mumbai then. **Bonito Designs' Offerings and Follow-up** Bonito Designs highlighted their experience centers in Thane and Andheri, featuring sample flats, material galleries, and Gauri Khan-designed themes, along with their ISO certification. For Vignesh, the agent confirmed the starting price range of 8-10 lakhs for a 2BHK and promised to send a WhatsApp invitation with details and images. For Jignesh, the agent acknowledged his rescheduling request. **Recommended Follow-up Actions** Follow up with Vignesh via WhatsApp to confirm his visit to the Andheri experience center, ensuring he receives the invitation with all necessary details and images. For Jignesh Thakkar, ensure a callback is made on Monday as requested to reschedule his visit. | 2026-05-24 |  | 2026-05-31
19564 | Turnkey | 2026-01-01 | Dipali Shah | pratap aadinath | MUM - GOR | Yes | Rajnish Mishra | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Avi Thakkar |  | Lost | Design | DEM1 | 752128 | 109785 | 1077850 | 0 | 0 | 47 | 0 | 0 | 40641 | 320720 | 280982.4 |  |  | 2026-04-19 | 2026-05-26 14:58 | 2026-05-20 | 2026-05-26 15:05 | 2026-05-29 | 2026-05-27 19:27 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-05-23 | 2026-05-25 00:46 | 2026-05-30 | 2026-05-27 19:25 | 2026-05-28 | 2026-05-29 15:43 | 2026-05-31 | 2026-05-31 17:03 |  |  |  |  | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-01 |  | Unknown | 2026-04-19 | 2026-04-20 13:14 | 932479 | 165370 | 0 | 0 | 0 | 0 | 932479.551 | 145056 | 2026-06-23 15:18:49 +0530 | Ahtesham Shaikh | Some Image was uploaded | 2026-06-18 18:20:30 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-11 21:36:05 +0530 | Yash Jain | DDM1: when we asked client for DDM1 - the client said they are planning to cancle as they have medical emergency in the house. They were in contact with avi thakkar (crm) for the communication of cancellation of project | 2026-06-17 |  | 2026-06-24 |  | Under Construction | 2026-06-06
19565 | Turnkey | 2026-01-01 | Nilam S Shahji | Wadhwa Atmosphere | MUM - Thane | Yes | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | 10% Payment | 2143415 | 9999 | 0 | 0 | 0 | 52 | 0 | 204343 | 214342 | 874390 | 840342 |  |  | 2026-04-19 | 2026-04-19 21:06 | 2026-05-12 | 2026-05-13 12:32 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-04-19 | 2026-04-19 21:04 | 0 | 0 | 0 | 0 | 0 | 0 | 1818741 | 324674 | 2026-05-13 12:33:02 +0530 | Yerra Bharat | Have to call on 18th may to get conformation on CDP | 2026-05-07 11:48:22 +0530 | Yerra Bharat | DCM: Name: SameerÂ Budget: 18-22LÂ Will be living with parents.Â (4 Adults)Â Kids planning after moving in. Plans inÂ 18months.Â Â Family meet upÂ happensÂ everyÂ 15days,Â max 7-8 people.Â Â Entry:Â Name plateÂ Entry Shoe Box, Step style- one side can sit., Outside the door.Â Â Opp to main door is the door for the opp. Flat, so corridor is a common corridor.Â Â Need a water feature outside the house beside theÂ shoebox butÂ said weÂ haveÂ toÂ see the possibility and connivence.Â Entry Into the house,Â Â ItÂ mustÂ beÂ very good, welcoming, may not beÂ GodÂ idol exactly as soon as entry, picture frame or something which is calming andÂ soothing.Â Sofa alignmentÂ mustÂ be mirrored,Â TV unit on to the longer wall, (WallÂ b/w living and study room as mentioned in builder plan)Â Wall beside the TV unit,Â mustÂ be like pin interest ready where people can take pictures.Â Â LikesÂ metallic rose gold color, pastelÂ colors,Â Â liked Abstract LUX, Art Deco Themes.Â Dining Table: Expanding table - starting with 4 people, can be expanded to bigger.Â CrookeryÂ unit: Shutter doors.Â Â wants unit mixed with mirror, tinted glass doorsÂ Wants lots of storage.Â Â Deck:Â Plantation wall possible only on one side because there is aÂ ~2ft wide full height wall.Â The remainingÂ part is normal glass railing.Â Wants small pots along the railing on the deck, but not too many. TheyÂ cantÂ maintainÂ it.Â Swing is needed.Â Â Sofa: requirementÂ Three-seaterÂ sofa with one side expandable and two loose chairs, with a corner table on the deck side, with a coffee table in the center.Â Kitchen:Â TwoÂ ways:Â Â Â 1.Builder is giving aÂ kitchen;Â they want to change cosmeticallyÂ withoutÂ civilÂ changes.Â 2.Â They want to removeÂ everythingÂ and do it fromÂ theÂ scratch.Â Â Appliances they want to have:Â Washing machineÂ Dish washerÂ ChimneyÂ HobÂ Microwave ovenÂ Mixer and Grinder.Â Ok to place on side kitchen platform, and other side service platform because of washing machine.Â Â Cooking happens regularly, 3 meals aÂ day,Â and other daily cooking.Â Wants to haveÂ an acrylicÂ finish.Â Kictchen is a darker place,Â wantÂ to light it up and make it look brighter.Â In case of completeÂ makeover,Â quartzÂ or granite with orange dots.Â Common Washroom:Â Under sink storageÂ Profile Lighting around mirrorÂ mirrorÂ Ledge above the WCÂ Glass door for shower area.Â Â There is a common sink area, asked for the possibility of shifting washing machine to here by making the sink and counter size smaller.Â Â Study Room:Â For now,Â it'sÂ a Guestroom but after 4-5 yearsÂ itsÂ going to beÂ kidsÂ room.Â Convertible bed.Â Simple wardrobe with two shutters, mirror on one shutter,Â Â Foldable table for working.Â Headboard withÂ cushion.Â No need of more storage here.Â Have doubts aboutÂ theÂ future if they want to change the color of the walls, will the present selectedÂ workÂ orÂ not.Â Parents'Â Bedroom / Bedroom 1:Â Want minimalist and simpleÂ Â WardrobeÂ with sliding doorÂ Queensize bed, with cushion style headboard and under bed storage.Â Storage on the wall is like a dressing unit with a mirror.Â Also,Â a separate dressing unit.Â Basic design with some highlights on the wall, like pictures or framing style.Â Side tables for the bed, some kind ofÂ design onÂ both sides of the bed.Â Master Bedroom:Â Ok with Queen side bed.Â Bed Side tables.Â Lights above the tables.Â Wardrobe with sliding styleÂ With organizing in mind. Need space for Jewelry,Â handbags,Â goggles,Â doesntÂ have long dresses andÂ very littleÂ hanging style dresses. Need organizing asÂ the mainÂ part.Â Dressing Table Husband suggested dressing table attached to one side table so that theyÂ can haveÂ aÂ small, dedicatedÂ sittingÂ areaÂ near theÂ window whereÂ they sitÂ and work ifÂ the guestÂ roomÂ is occupied.Â Â Study table / Sitting table: NeedÂ a longÂ ottoman style bench under the fixed shelf/table onto the wall, which they can push this when not in use.Â Need the loft space can haveÂ separateÂ doors.Â Dressing table:Â Storage for makeup, one short mirror in the dressing unit and one long mirror somewhere depending on the possibility in the room, butÂ not exactly opp. To the bed.Â Â Every bedroom headboard needs to be cushioned.Â Master bedroom premium and remaining bedroom can be minimalist and normal design.Â Â have to call after 10th may to get the CDP arranged. |  |  |  | 2026-06-01 |  | 2026-06-08
19566 | Turnkey | 2026-01-01 | Neeta Kadam | swastik platinum | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  |  | suraj kumar | Akshat Shrivastava |  | Nivesh Gupta | Aakash Gaikwad | Active | Preproduction | CM | 1265441 | 253088 | 1499601 | 0 | 0 | 1 | 12 | 0 | 0 | 561267 | 451086 |  |  | 2026-04-19 | 2026-04-21 16:14 | 2026-04-21 | 2026-04-25 19:03 | 2026-04-28 | 2026-04-28 12:56 | 2026-05-21 | 2026-05-21 17:51 | 2026-07-15 | 2026-07-14 19:38 | 2026-10-24 |  | 2026-04-28 | 2026-04-28 16:47 | 2026-04-29 | 2026-04-29 11:10 | 2026-04-29 | 2026-04-29 11:47 | 2026-05-07 | 2026-05-07 13:26 |  |  |  |  | 2026-05-21 | 2026-05-25 18:38 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-10-27 |  | 2026-10-28 |  | 2026-10-29 |  | 2026-10-30 | [6 empty] | 2026-11-17 |  | 2026-11-26 |  | 2026-11-25 |  | 2026-11-26 |  | 2026-11-27 |  | 2026-11-29 |  |  |  | 2026-12-21 |  | 2026-12-23 |  | 2026-12-24 | [5 empty] | 2026-10-28 |  | 2026-05-08 | 2026-05-21 17:41 | Site is RTMI | 2026-04-19 | 2026-04-21 16:09 | 1273135 | 226465 | 0 | 0 | 0 | 0 | 1262507.9711 | 215153 | 2026-07-02 18:14:02 +0530 | Vishakha Vaishnav | Others: CX WILL GET KEYS BY NEXT WEEK | 2026-05-24 18:25:48 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-15 16:32:36 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-22 | 2026-05-21 17:54 | 2026-07-15
19567 | Turnkey | 2026-01-01 | Jitendra | Mahalaxmi | MUM - GOR | Yes | [8 empty] | Nivesh Gupta |  | Active | Prospect | DCM Due | 1568955 | 9999 | 0 | 0 | 0 | 48 | 0 | 146897 | 156896 | 666804 | 588359.6 |  |  | 2026-04-19 | 2026-05-28 15:29 | 2026-05-27 | 2026-06-02 14:44 | 2026-05-28 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-06-13 |  | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-08 |  | Unknown | 2026-04-19 | 2026-05-17 17:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1329623 | 239332 | 2026-06-02 14:49:49 +0530 | Priyanka Patel | CDP: Project Name/Tower Name/Flat Number juhu, dn nagar Typology 2BHK Site Access Date 2026-07-02 Possession Date 2026-07-02 Customer ProfileFamily members (no. & age) 4 MEMBER Profession NA Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc YES Signed off celebrity theme Neo Industrial, Abstract Luxury Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 12 Mention basic vastu principles agreed for integration in design, if any Design VisionEntrance Foyer must-haves YES Upload reference images Living key features and furniture must-haves YES Upload reference images Dining setup, table size and other furniture must -haves YES Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves YES Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves YES Upload reference images Other space/ room (if any) must-haves YES Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves YES Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves YES Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves YES Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves YES Upload reference images Styling and Dcor must-haves YES Space identified for signature design features and its specifics YES Specify if design to reflect any personal story, cultural influence or special memory MiscellaneousTimeline related commitment made by Bonito to customer, if any: YES Other commitments made by Bonito to customer, if any: YES RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? YES Re-confirm the Move-in Date 2026-12-02 Re-confirm the Possession Date 2026-12-02 Any special occasion mentioned by customer wrt handover date YES | 2026-06-02 14:47:03 +0530 | Priyanka Patel | CDP: 19567 - Jitendra Design Discussion Meeting.-20260527_203117-Meeting Recording.mp4 | 2026-05-27 21:12:12 +0530 | Priyanka Patel | DCM: Hello Jitendra Sir, It was nice talking to you. Sharing todays meeting MOM [27-05-26] regarding your requirements: Project Details Possession End of June Location Ghatkopar, 11th Floor, Flat No. 1107 Budget Approx. 12L Design Style Minimal, elegant, and low-maintenance Theme Elements Mirrors, rafters, beading details, textures, and wallpaper accents Basic Vastu to be considered Existing Furniture Existing coffee table to be retained Kindly share a picture of the existing coffee table for design coordination Living Room Requirements L-shaped sofa with 1 accent chair 65 TV with TV unit integrated with mandir Mandir option sitting style or tall unit Minimal false ceiling only to conceal pipes/services Swing chair in balcony area Privacy partition near entrance/dining area with shoe storage for approximately 50 pairs Dining table 6 seater (3 chairs + 1 bench seating) Kitchen Requirements Parallel platform kitchen layout Black granite countertop with white dado tiles Microwave placement on parallel platform wall Base storage, wall storage, and loft storage on both sides Utility storage above washing machine area Functional, minimal, and easy-maintenance Washroom Requirements Base vanity units in both washrooms Final design/execution to be based on site plumbing conditions Bedroom 2 Kids Bedroom Two single beds in L-shaped placement Study table integrated within wardrobe space No TV unit required No side tables required Master Bedroom King-size bed wardrobe StorageÂ Dresser + side table combination 48 wall-mounted TV provision Foldable ironing table size 1 x 4 Additional Requirements Safety door with net/jail design [Custom Carpenter]Â painting and ceiling treatment Next Meeting: 28-05-26 at 4:30 PM 5:00 PM | 2026-06-13 |  | 2026-06-20
19568 | Turnkey | 2026-01-01 | Gaurav Tiwari | Avalon Park @ The Prestige City | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1514996 | 316441.85 | 2215682 | 0 | 0 | 3 | 0 | 0 | 0 | 595802 | 602752 |  |  | 2026-04-18 | 2026-04-20 12:15 | 2026-04-22 | 2026-04-22 13:40 | 2026-04-24 | 2026-04-24 11:27 | 2026-06-27 | 2026-06-26 08:50 | 2026-07-22 |  | 2026-11-12 |  | 2026-04-24 | 2026-04-28 20:07 | 2026-04-25 | 2026-04-28 20:08 | 2026-04-28 | 2026-04-29 13:36 | 2026-05-07 | 2026-05-07 12:27 |  |  |  |  | 2026-07-08 | 2026-07-12 15:19 | 2026-11-07 |  | 2026-11-08 |  |  |  | 2026-11-15 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 | [6 empty] | 2026-12-06 |  | 2026-12-15 |  | 2026-12-14 |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-18 |  |  |  | 2027-01-09 |  | 2027-01-11 |  | 2027-01-12 | [5 empty] | 2026-11-16 |  | 2026-06-13 | 2026-06-26 08:19 | Site is RTMI | 2026-04-18 | 2026-04-20 12:13 | 1877697 | 337985 | 0 | 0 | 0 | 0 | 1706015.3974 | 286779 | 2026-06-24 17:16:03 +0530 | Aishwarya C | *MBR* hinge wardrobe are now changd to aristo wardrobesnext to that need a tall open unit and bottom drawers and dressing table as pencil drawers with metal supportÂ for the headwall need to have space for curtain opening and side tables wall treatments are not finalisedÂ wall treatmetns needs to be withing 50 mm and more depth will affect the depth of the wardrobe *PBR* Â hinged wardrobe changed to slidersÂ dressing table will act like strudy table tooÂ loft inside panels are removedÂ internals are not discussedÂ for the head wall we are panning for wallpaper need to finalise *KBR* no chnge sliding wardrobe remains sameÂ no two wardrobes needed only one wardrobe is needed and one stdy tableÂ existing king cot will be placed here circulation space is narrow but that will be adjusted is the descision takenÂ loft ends above wardrobe not extensionÂ pooja unit completely client scope as the required design is not done by usÂ crockery unit need only wall cabinet and base cabinet with bevelled mirrorÂ base unit needs to be with drawers (tandem) tv unit only back panel and base cabinet with metal patti in the panel designÂ need a curved botom box to place wooferÂ and a partition for the same dimensionÂ foyer unit to hide the db board need a paneling and push to open door need to check with the team and confirmÂ in the kithen tall unit will remain the same to hold the microwave need to addledge below the wall unitÂ sink unit is aligned to the existing plumbing pointÂ need to plan for RO unitÂ finished kitchen will be in acrylic living will be in lamiante parents room and kids room will be in laminate finishÂ master bedroom is in aristo and laminate finishÂ | 2026-06-06 15:21:59 +0530 | Aishwarya C | client asked for acrylic and aristo considered costing shared that | 2026-05-23 18:47:53 +0530 | Aishwarya C | TV UNIT WITH A CURVED ENDÂ FOYER UNIT NEED TO EXPLORE ART POINT FOR WTHE WALLÂ SINGLE STORAGE FOR HELMET AND DOUBLE FOR SHOES NEED SPACE FOR ROUTER TV UNIT BACK DESING ON HOLDÂ POOJA UNIT SHIV IS NEEDÂ WTH THE COLAPSABLE DOORS NEED TO SUGGEST VENDOR FOR THE SAME parents room mirror on side tableÂ mbr need dressing unit with the study unitÂ tall unit for storageÂ broader and taller mirror till the ceilingÂ and wall storage also till the ceilingÂ share sme reference for the head board wallÂ | 2026-06-27 | 2026-06-26 08:54 | 2026-07-23 |  | Under Construction | 2026-07-31
19569 | Turnkey | 2026-01-01 | Arijit Sarkar | Godrej Exquisite | MUM - Thane | Yes |  | Anil Jagtap | [6 empty] | Anant Giri |  | Hold | Design | DEM1 | 1246340 | 326925 | 1584627 | 0 | 0 | 23 | 54 | 0 | 0 | 438145 | 481270 |  |  | 2026-04-20 | 2026-04-20 16:34 | 2026-04-22 | 2026-04-25 11:06 | 2026-04-26 | 2026-04-26 19:25 | 2026-10-14 |  | 2026-10-21 |  | 2026-10-28 |  | 2026-04-26 | 2026-04-28 19:19 | 2026-04-27 | 2026-04-28 20:19 | 2026-04-28 | 2026-04-29 11:13 | 2026-05-22 | 2026-05-22 13:26 |  |  |  |  | 2026-05-04 | 2026-04-28 19:19 | 2026-10-23 |  | 2026-10-24 |  |  |  | 2026-10-31 |  | 2026-11-01 |  | 2026-11-02 |  | 2026-11-03 | [6 empty] | 2026-11-21 |  | 2026-11-30 |  | 2026-11-29 |  | 2026-11-30 |  | 2026-12-01 |  | 2026-12-03 |  |  |  | 2026-12-25 |  | 2026-12-27 |  | 2026-12-28 | [5 empty] | 2026-11-01 |  | 2026-10-10 |  | Unknown | 2026-04-20 | 2026-04-20 16:34 | 1342904 | 241722 | 0 | 0 | 0 | 0 | 1336019.5105 | 230543 | 2026-05-22 18:44:33 +0530 | Anjali Singh | CDP: remove dining storage.Â , keep normal dining which is in cx scope. video door phone.Â lights and switch boards - with usb ports + dim and temper adjustable. ro and dishtray unit.Â projector provision in PKOÂ | 2026-05-22 13:26:51 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-22 13:25:08 +0530 | Anil Jagtap | welcome call completed | 2026-10-15 |  | 2026-10-22
19572 | Turnkey | 2026-01-01 | Priya Parab | kalpataru elitus | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar | [5 empty] | Shreyash Kotecha |  | Hold | Preproduction | Site Readiness 1 | 1107415 | 221483 | 1294394 | 0 | 0 | 7 | 15 | 0 | 0 | 491907 | 394025.2 |  |  | 2026-04-19 | 2026-04-22 15:51 | 2026-05-16 | 2026-05-22 11:14 | 2026-05-26 | 2026-05-26 11:09 | 2026-07-14 | 2026-06-23 16:34 | 2026-10-05 |  | 2026-10-12 |  | 2026-05-26 | 2026-05-26 19:39 | 2026-05-27 | 2026-05-26 20:07 | 2026-05-26 | 2026-05-28 15:11 | 2026-05-31 | 2026-05-31 11:37 |  |  |  |  | 2026-07-15 | 2026-06-21 20:12 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-07-10 | 2026-06-23 16:06 | Site is RTMI | 2026-04-19 | 2026-04-22 15:44 | 1099231 | 195162 | 0 | 0 | 0 | 0 | 1084672.6271 | 180399 | 2026-06-30 12:00:36 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-26 19:53:15 +0530 | Rachna Abhyankar | Possession in sept or oct tentatively | 2026-06-25 18:48:33 +0530 | Mehnaz Ashraf | Some Image was uploaded | 2026-06-24 | 2026-06-23 16:35 | 2026-10-06 |  | Under Construction | 2026-07-10
19573 | Sub Project |  | Ruddhi Softtech Pvt Ltd - Pranav Shirke | Elixir reserve | MUM - GOR |  | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-21 | 2026-05-07 15:28 | 2026-04-22 | 2026-05-07 15:28 | 2026-05-07 | 2026-05-07 15:28 | 2026-05-13 | 2026-05-07 15:29 | 2026-05-08 | 2026-05-07 15:30 | 2026-05-08 | 2026-05-07 15:31 | 2026-04-25 | 2026-05-07 15:28 | 2026-05-08 | 2026-05-07 15:28 | 2026-05-07 | 2026-05-07 15:29 | 2026-05-08 | 2026-05-07 15:29 |  |  |  |  | 2026-05-13 | 2026-05-07 15:29 | 2026-05-08 | 2026-05-07 15:30 | 2026-05-08 | 2026-05-07 15:30 |  |  | 2026-05-08 | 2026-05-07 15:33 | 2026-05-08 | 2026-05-07 16:17 | 2026-05-08 | 2026-05-07 18:25 | 2026-05-08 | 2026-05-07 18:26 |  |  |  |  | 2026-05-13 16:18 | 2026-05-23 | 2026-05-23 18:54 | 2026-05-27 | 2026-05-25 15:01 | 2026-05-26 | 2026-05-30 12:15 | 2026-05-25 | 2026-06-10 11:06 | 2026-06-08 | 2026-06-10 20:07 | 2026-06-10 | 2026-06-08 11:58 |  |  | 2026-06-12 | 2026-06-11 17:37 | 2026-06-13 | 2026-06-11 17:41 | 2026-06-11 | 2026-06-11 17:44 |  |  |  |  | 2026-05-07 | 2026-05-07 17:51 | 2026-05-08 | 2026-05-07 15:29 | Unknown | 2026-04-21 | 2026-05-07 15:28 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 2026-06-01 16:36:11 +0530 | Savita Parab | Execution: Site is ready for dispatch | 2026-05-11 23:09:06 +0530 | Savita Parab | Execution: Site is ready for dispatch |  |  |  | 2026-05-14 | 2026-05-07 15:29 | 2026-05-08 | 2026-05-07 15:30
19574 | Turnkey | 2026-01-01 | kiran jagtap | Oberoi Eternia | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 449723 | 108000 | 595852 | 0 | 0 | 0 | 53 | 0 | 0 | 183934 | 157789.2 |  |  | 2026-04-21 | 2026-04-21 14:20 | 2026-04-21 | 2026-04-21 15:31 | 2026-04-21 | 2026-04-21 20:25 | 2026-12-04 | 2026-06-13 15:59 | 2026-12-05 |  | 2026-12-12 |  | 2026-04-21 | 2026-04-21 19:23 | 2026-04-22 | 2026-04-24 11:14 | 2026-04-24 | 2026-04-24 12:58 | 2026-05-05 | 2026-05-05 19:24 |  |  |  |  | 2026-05-11 | 2026-05-13 15:31 | 2026-12-07 |  | 2026-12-08 |  |  |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-18 | [6 empty] | 2027-01-05 |  | 2027-01-14 |  | 2027-01-13 |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-17 |  |  |  | 2027-02-08 |  | 2027-02-10 |  | 2027-02-11 | [5 empty] | 2026-12-16 |  | 2026-11-30 | 2026-06-13 15:49 | Site is Non-RTMI | 2026-04-21 | 2026-04-21 14:20 | 504960 | 90892 | 0 | 0 | 0 | 0 | 504960 | 90892 | 2026-07-04 16:59:42 +0530 | Anil Jagtap | The client is expected to receive possession by the end of October. | 2026-06-30 11:27:05 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-13 19:11:12 +0530 | Siddhi Chaphekar | Some Image was uploaded | 2026-06-14 | 2026-06-13 15:59 | 2026-12-06
19576 | Sub Project |  | Amit Joshi | LODHA AMARA | MUM - Thane |  | Harshali Bhuyar | Anamika Dolai | Sneha Kadam |  | Nilofer Shaikh | Vinay Bulani | Aditya Vikram | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-21 | 2026-04-21 17:35 | 2026-04-22 | 2026-04-21 17:35 | 2026-04-21 | 2026-04-21 17:36 | 2026-04-22 | 2026-04-21 17:37 | 2026-04-22 | 2026-04-21 17:37 | 2026-04-22 | 2026-04-21 17:38 | 2026-04-21 | 2026-04-21 17:36 | 2026-04-22 | 2026-04-21 17:36 | 2026-04-21 | 2026-04-21 17:36 | 2026-04-22 | 2026-04-21 17:36 |  |  |  |  | 2026-04-21 | 2026-04-21 17:37 | 2026-04-22 | 2026-04-21 17:38 | 2026-04-22 | 2026-04-21 17:38 |  |  | 2026-04-22 | 2026-04-21 17:40 | 2026-04-22 | 2026-04-21 17:52 | 2026-04-22 | 2026-04-21 18:21 | 2026-04-22 | 2026-04-21 18:22 |  |  |  |  | 2026-04-23 12:17 | 2026-04-30 | 2026-04-29 19:30 | 2026-05-01 | 2026-04-29 22:16 | 2026-04-30 |  | 2026-04-29 |  | 2026-05-13 |  | 2026-05-15 |  |  |  | 2026-05-22 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-04-21 | 2026-04-21 18:22 | 2026-04-22 | 2026-04-21 17:36 | Unknown | 2026-04-21 | 2026-04-21 17:35 | 0 | 0 | 0 | 0 | 16222.5 | 0 | 16222.5 | 0 | [9 empty] | 2026-04-22 | 2026-04-21 17:37 | 2026-04-22 | 2026-04-21 17:37
19577 | Turnkey | 2026-01-01 | Shweta Jain | Hiranandani Falcon | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Shreyash Kotecha |  | Active | Design | DEM1 | 959136 | 230999 | 1151649 | 0 | 0 | 43 | 0 | 0 | 0 | 397903 | 330234.4 |  |  | 2026-04-19 | 2026-04-29 16:02 | 2026-05-13 | 2026-05-13 19:49 | 2026-05-21 | 2026-05-21 20:59 | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-05-21 | 2026-05-29 18:43 | 2026-05-22 | 2026-05-29 19:42 | 2026-05-29 | 2026-06-02 17:16 | 2026-06-07 | 2026-06-07 15:47 |  |  |  |  | 2026-05-29 | 2026-05-27 18:07 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-06-08 |  | Unknown | 2026-04-19 | 2026-04-22 21:15 | 975973 | 175675 | 0 | 0 | 0 | 0 | 979395.4569 | 172644 | 2026-07-11 10:59:42 +0530 | Nazneen Chovvakkaran | DDM1: | 2026-07-05 11:55:03 +0530 | Nazneen Chovvakkaran | DDM1: | 2026-07-02 17:32:48 +0530 | Anamika Dolai | DEM 1 meeting scheduled for 5th-07-2026. Next milestone payment has been done. | 2026-07-07 |  | 2026-07-14 |  | Under Construction | 2026-09-01
19578 | Turnkey | 2026-01-01 | Mr.Rudra Pratim Sircar | Purva Park Hill | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Muralikrishna Udupi |  | Hold | Preproduction | Site Readiness 1 | 1914216 | 382843 | 2569154 | 0 | 0 | 0 | 19 | 0 | 0 | 797277 | 734096 |  |  | 2026-04-21 | 2026-04-21 15:46 | 2026-05-10 | 2026-05-10 20:22 | 2026-05-13 | 2026-05-10 22:32 | 2026-06-24 | 2026-06-24 22:05 | 2026-08-05 |  | 2026-08-12 |  | 2026-05-10 | 2026-05-14 10:19 | 2026-05-11 | 2026-05-14 12:43 | 2026-05-14 | 2026-05-21 10:44 | 2026-05-26 | 2026-05-26 15:12 |  |  |  |  | 2026-06-25 | 2026-06-26 15:09 | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-05-27 | 2026-06-04 17:51 | Site is Non-RTMI | 2026-04-21 | 2026-04-21 15:42 | 2177249 | 391904 | 0 | 0 | 0 | 0 | 2137945.4287 | 353016 | 2026-06-26 15:15:47 +0530 | Akshay Ds | Some Image was uploaded | 2026-06-26 15:12:12 +0530 | Akshay Ds | Possession not received Project HOLD till July end | 2026-06-24 21:29:41 +0530 | Kiran Agarampalli | Daughters bedroom: Swing to be moved to balconyStudy table moved towards the wallPooja will be on the partition (Option 1)MBR: Option 1- Aristo pivoted wardrobe Option 2- External drawer's wardrobe Pooja Unit Option 2- to be placed near study Storage above the door Initial Measurements date tentatively after july mid, till then project will be on hold | 2026-06-25 | 2026-06-25 14:39 | 2026-08-06 |  | Under Construction | 2026-09-01
19579 | Turnkey | 2026-01-01 | Veena Balgi | RUNWAL FOREST | MUM - Thane | Yes | Siddhi Chaphekar | Anamika Dolai | Rushika More | [5 empty] | Shreyash Kotecha |  | Active | Prospect | DCM Due | 2109844 | 9999 | 0 | 0 | 0 | 77 | 0 | 200985 | 210984 | 939107 | 748768 |  |  | 2026-04-19 | 2026-04-29 15:58 | 2026-04-30 | 2026-04-30 13:14 | 2026-05-01 |  | 2026-05-08 |  | 2026-05-15 |  | 2026-05-22 |  | 2026-05-01 |  | 2026-05-02 |  | 2026-05-02 |  | 2026-05-03 | [5 empty] | 2026-05-09 |  | 2026-05-17 |  | 2026-05-18 |  |  |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 | [6 empty] | 2026-06-15 |  | 2026-06-24 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-05-26 |  | 2026-05-04 |  | Unknown | 2026-04-19 | 2026-04-22 18:43 | 0 | 0 | 0 | 0 | 0 | 0 | 1790805 | 319039 | 2026-04-30 12:54:08 +0530 | Siddhi Chaphekar | DCM OF PID-19579 Veena Balgi No.of people-2 Storage is their main concern. Â Requirements- Whole house- False ceiling(only to hide fire pipe),Electrical,Painting Livingroom-Shoe unit,4+2 seating extendable dining, crockery unit+mandir (full ht storage),Tv unit-drawers+tall unit, Sofa and centre table. Kitchen- Ciivil work-Making of new platform(granite in our scope), semi modular kitchen with base wall loft. Master bedroom-Queen size bed,wardrobe,dresser and side table(1) Bedroom 1-Sofa cum bed, wardrobe ,study table+wall unit Â Client is expecting a quote as per his requirement in bedroom 1- murphy bed with storage below and study unit+sofa cum bed Â | 2026-04-30 12:51:38 +0530 | Maasoumeh Raza | DCM: DCM OF PID-19579 Veena Balgi No.of people-2 Storage is their main concern. Â Requirements- Whole house- False ceiling(only to hide fire pipe),Electrical,Painting Livingroom-Shoe unit,4+2 seating extendable dining, crockery unit+mandir (full ht storage),Tv unit-drawers+tall unit, Sofa and centre table. Kitchen- Ciivil work-Making of new platform(granite in our scope), semi modular kitchen with base wall loft. Master bedroom-Queen size bed,wardrobe,dresser and side table(1) Bedroom 1-Sofa cum bed, wardrobe ,study tableÂ Â | 2026-04-21 16:03:43 +0530 | Unknown | About the Customer **Current Customer Stage and Next Steps** The customer, Veena Ji, is in the process of finalizing interior design for her new 2BHK flat in Mumbai, with possession expected in two months. She needs to confirm visit timing with her spouse for today or tomorrow to proceed with the consultation at Bonito Designs' Thane experience center. **Customer Needs, Pain Points, and Concerns** Veena Ji's primary need is to understand the budget for her 2BHK interiors in Runwal Forest, Kanjurmarg, with a possession timeline of two months. Her key concerns include potential project delays and a preference for seeing actual completed work rather than just showroom displays, though she was assured of a personalized and efficient experience at the center. **Customer Engagement History** The initial interaction involved a customer inquiry about an account balance and an extra charge, which was resolved by crediting the fee back. Subsequently, agent Prashant from Bonito Designs followed up on Veena Ji's inquiry for home interiors, noting it might be a re-inquiry. **Qualification and Discussion Summary** The conversation focused on qualifying Veena Ji's needs for interior design, including her property location (Mumbai), apartment type (2BHK), possession timeline (2 months), and budget. The agent discussed the starting budget for a 2BHK in her specific building and emphasized the importance of visiting the Thane experience center for personalized designs and offers. **Recommended Follow-up Actions** Recommended follow-up actions include confirming the visit timing with Veena Ji's spouse, sending a personalized WhatsApp invitation for the experience center visit, and ensuring the appointment is booked for today or tomorrow as per her preference. The agent should also be prepared to address any further concerns regarding timelines or design preferences during the visit. | 2026-05-09 |  | 2026-05-16
19580 | Sub Project |  | Ravi Kumar Maheshwari & Pooja Maheshwari | Prestige Green Gables | BNG - HSR |  | Priyanka Mathur | Abhinandan K S | Kowshik |  | Sethuragavan R | Yogeshwaran | Ranjith Kumar | Murali S |  | Sunil Kumar S M | Active | Installation | Execution | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-21 | 2026-04-22 18:25 | 2026-04-22 | 2026-04-22 18:26 | 2026-04-22 | 2026-04-22 18:26 | 2026-04-23 | 2026-04-22 18:29 | 2026-04-23 | 2026-04-22 18:31 | 2026-04-23 | 2026-04-22 18:36 | 2026-04-22 | 2026-04-22 18:26 | 2026-04-23 | 2026-04-22 18:27 | 2026-04-22 | 2026-04-22 18:27 | 2026-04-23 | 2026-04-22 18:27 |  |  |  |  | 2026-04-22 | 2026-04-22 18:30 | 2026-04-23 | 2026-04-22 18:34 | 2026-04-23 | 2026-04-22 18:34 |  |  | 2026-04-23 | 2026-04-22 18:44 | 2026-04-23 | 2026-04-23 17:34 | 2026-05-10 | 2026-05-09 19:30 | 2026-05-10 | 2026-05-09 19:30 |  |  |  |  | 2026-05-13 15:44 | 2026-05-23 | 2026-05-23 18:55 | 2026-05-27 | 2026-05-25 15:09 | 2026-05-26 | 2026-06-23 13:53 | 2026-05-25 | 2026-06-24 12:21 | 2026-06-24 | 2026-06-24 12:23 | 2026-06-26 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-04-23 | 2026-05-09 19:29 | 2026-04-23 | 2026-04-22 18:27 | Unknown | 2026-04-21 | 2026-04-22 18:25 | 0 | 0 | 0 | 0 | 42285 | 0 | 42285 | 0 | 2026-06-10 15:00:11 +0530 | Ranjith Kumar | Execution: | [6 empty] | 2026-04-23 | 2026-04-22 18:29 | 2026-04-23 | 2026-04-22 18:31
19582 | Turnkey | 2026-01-01 | UMAKANT RANE | Satyadeep Enclave | MUM - Thane | Yes | [8 empty] | Shreyash Kotecha |  | Active | Prospect | 10% Payment | 1676094 | 9999 | 0 | 0 | 0 | 70 | 0 | 157610 | 167609 | 795524 | 545351.2 |  |  | 2026-04-21 | 2026-04-22 16:18 | 2026-04-27 | 2026-04-28 11:05 | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-05-27 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-05-14 |  | 2026-05-22 |  | 2026-05-23 |  |  |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 | [6 empty] | 2026-06-20 |  | 2026-06-29 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-02 |  |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-31 |  | 2026-05-09 |  | Unknown | 2026-04-21 | 2026-04-22 16:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1423220 | 252873 | 2026-04-27 17:27:10 +0530 | Maasoumeh Raza | Some Image was uploaded | 2026-04-27 17:16:33 +0530 | Maasoumeh Raza | DCM: Timeline: Possession expected by mid-July Move-in planned around Diwali or December Member: 5 [Couple , son[10 years] & in-law] Profession: Business man Theme: Modern traditional Budget: 10 to 12L Existing furniture: NO Entrance: Shoe rack [30 pairs] Safety door merge with main door Outside paneling. Living Room 55-inch TV is ideal (based on viewing distance) Wall-mounted TV unit with minimal storage and some display shelves Flexible seating: 3-seater + chairs/bench Optional swing (jhula), but space needs to be checked Sofa wall with paneling or glass At the entrance, the left wall has the distribution board and main switch. client would like to conceal them with a panel while maintaining easy access. Dining & Mandir 6-seater dining table Crockery with Floor-touch mandir with storage and seating option. Kitchen Plan to extend and make it open (after permissions) Civil work : demolition & Installation of wall [entrance & window wall for extension] , removing existing window & reinstallation of window , installation of tiles & platform [floor & dado] L-shaped layout Standard setup: base units, wall units, loft Appliance : existing microwave ,fridge & mixer cx will purchase new. Master Bedroom Wardrobe + bed + dresser Murphy bed with sofa considered [queen size] [Cx have already used murphy bed in previous home] Small TV provision with minimal shelving if possible. [tv 43 inch] No study table. The client wants to explore the option of closing the existing duct access from the bathroom and rerouting it through the master bedroom. Additionally, what types of storage solutions can be incorporated in duct Common Bedroom Murphy bed + wardrobe + optional TV (43-inch) Layout will ensure proper walking space Wardrobe can be corner or side placement Bathroom Vanity with storage Glass partition for shower Balcony Compact seating (24 chairs + small table) Add planters for dcor Flooring Option 1: Interlocking wooden flooring Option 2: Full replacement with tiles (more durable long-term) Additional 3 AC units (living + both bedrooms) Option for motorized curtains (automation) Simple ceiling design with modern + traditional touch Electrical & Painting full home. |  |  |  | 2026-05-14 |  | 2026-05-21
19583 | Turnkey | 2026-01-01 | Mrs.Rashmi Shinde Rashmi | L & T | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | suraj kumar | Aditya Vikram | Murali S | Nishtha Valawalkar | Shailendra Mishra | Active | Production | Dispatch Due | 1035353 | 1035353 | 1228974 | 0 | 1035353 | 2 | 8 | 0 | 0 | 0 | 0 |  |  | 2026-04-21 | 2026-04-30 20:33 | 2026-04-22 | 2026-04-30 20:34 | 2026-05-03 | 2026-04-30 20:49 | 2026-05-13 | 2026-05-13 15:17 | 2026-06-03 | 2026-06-02 11:27 | 2026-06-10 | 2026-06-10 09:47 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-02 11:05 | 2026-05-02 | 2026-05-05 17:31 | 2026-05-08 | 2026-05-08 12:28 |  |  |  |  | 2026-05-13 | 2026-05-21 10:43 | 2026-06-03 | 2026-06-04 20:58 | 2026-06-05 | 2026-06-04 20:58 |  |  | 2026-06-13 | 2026-06-23 11:02 | 2026-06-23 | 2026-06-23 19:37 | 2026-06-24 | 2026-06-23 20:29 | 2026-06-24 | 2026-06-25 18:18 |  |  |  |  | 2026-06-27 18:55 | 2026-07-04 | 2026-07-03 21:05 | 2026-07-13 | 2026-07-11 18:33 | 2026-07-12 | 2026-07-13 16:27 | 2026-07-11 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-28 |  | 2026-07-29 | [5 empty] | 2026-06-23 | 2026-06-27 18:54 | 2026-05-09 | 2026-05-13 11:18 | Site is Non-RTMI | 2026-04-21 | 2026-04-22 13:30 | 1041503 | 187470 | 0 | 0 | 1082853 | 194913 | 1082853 | 194913 | 2026-07-08 11:40:42 +0530 | suraj kumar | Site report: - The floor covering work has been completed. - The False ceiling framing work has been completed. - Electrical work is in progress. | 2026-06-23 11:49:49 +0530 | Asavari Vare | Some Image was uploaded | 2026-06-19 18:51:49 +0530 | Asavari Vare | Some Image was uploaded | 2026-05-14 | 2026-05-13 16:31 | 2026-06-03 | 2026-06-02 13:07
19586 | Turnkey | 2026-01-01 | Vani (VP Palisetty) | Na | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Active | Production | Production | 769186 | 769186 | 852048 | 0 | 784186 | 14 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-25 | 2026-04-24 10:20 | 2026-04-24 | 2026-04-24 18:46 | 2026-04-27 | 2026-04-24 18:54 | 2026-05-17 | 2026-05-17 16:55 | 2026-06-01 | 2026-05-31 17:50 | 2026-06-12 | 2026-06-11 17:59 | 2026-04-24 | 2026-04-24 19:12 | 2026-04-25 | 2026-04-30 15:16 | 2026-04-30 | 2026-05-05 15:21 | 2026-05-09 | 2026-05-09 11:33 |  |  |  |  | 2026-05-17 | 2026-05-25 18:55 | 2026-06-11 | 2026-06-10 20:34 | 2026-06-11 | 2026-06-10 20:34 |  |  | 2026-06-16 | 2026-06-16 14:38 | 2026-06-16 | 2026-06-16 16:21 | 2026-06-21 | 2026-06-16 17:58 | 2026-06-17 | 2026-06-19 18:47 |  |  |  |  | 2026-06-24 11:04 | 2026-07-02 | 2026-07-01 19:09 | 2026-07-15 |  | 2026-06-22 | 2026-04-23 19:18 | 2026-07-10 |  | 2026-07-15 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-06-16 | 2026-06-24 11:03 | 2026-05-10 | 2026-05-17 16:32 | Site is RTMI | 2026-04-25 | 2026-04-23 19:18 | 722074 | 129973 | 0 | 0 | 772744.8891 | 135069 | 772744.8891 | 135069 | 2026-06-16 15:15:27 +0530 | Priyanka R | Some Image was uploaded | 2026-05-19 12:17:23 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-10 10:50:43 +0530 | Priyanka R | Some Image was uploaded | 2026-05-18 | 2026-05-17 16:58 | 2026-06-01 | 2026-05-31 17:54 | RTMI
19587 | Turnkey | 2026-01-01 | Dinesh Jain | bhoomi simara | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2268061 | 9999 | 0 | 0 | 0 | 74 | 0 | 216807 | 226806 | 969974 | 844474.8 |  |  | 2026-04-19 | 2026-04-24 16:29 | 2026-04-26 | 2026-04-26 00:43 | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-03 |  | 2026-05-04 | [5 empty] | 2026-05-10 |  | 2026-05-18 |  | 2026-05-19 |  |  |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 | [6 empty] | 2026-06-16 |  | 2026-06-25 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-28 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-05-27 |  | 2026-05-05 |  | Unknown | 2026-04-19 | 2026-04-22 10:55 | 0 | 0 | 0 | 0 | 0 | 0 | 1922086 | 345975 | 2026-04-30 20:14:39 +0530 | Meet Shah | Some Image was uploaded | 2026-04-26 00:40:57 +0530 | Yash Jain | DCM: Mr.Jain & family 840 sqftÂ possession in hand family - 2 couples airavat - parel propertyÂ Budget-20L Raw flat -Â lobby- shoe rackÂ 20-25pairs kitchen - parallel platformÂ hob bottomÂ refrigerator on bottomÂ bottom platform till end living room dining table 6 seaterÂ sofa seater - L shaped 4 seater tv unit - mandir unit NE corner No column in living roomÂ crockery unit toi wall Bedroom 1 QSB, wardrobes,side table, dresser,Â Bedroom 1 QSB, wardrobes,side table, dresser,Â storage behind utilily. walk-in wadrobe membrane finish - Theme - luxury , abstract modern luxe.Â washing machine - utility area | 2026-04-24 16:32:30 +0530 | Manasi Patil | Some Image was uploaded | 2026-05-10 |  | 2026-05-17
19588 | Turnkey | 2026-01-01 | Dr. KAUSHAL KUMAR SINGH | Leo Eminence | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Nilesh Patel | Rizwan Mistry | Murali S | Manasi Patil | Aakash Gaikwad | Active | Production | Dispatch Due | 1194142 | 1194142 | 1352103 | 0 | 1194142 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-19 | 2026-05-03 11:18 | 2026-05-04 | 2026-05-04 09:13 | 2026-05-07 | 2026-05-06 13:44 | 2026-05-22 | 2026-05-22 17:30 | 2026-06-05 | 2026-06-04 19:06 | 2026-06-11 | 2026-06-11 13:46 | 2026-05-04 | 2026-05-05 13:11 | 2026-05-07 | 2026-05-07 14:38 | 2026-05-07 | 2026-05-14 18:10 | 2026-05-19 | 2026-05-19 19:06 |  |  |  |  | 2026-05-25 | 2026-05-20 16:10 | 2026-06-06 | 2026-06-07 14:35 | 2026-06-08 | 2026-06-09 15:25 |  |  | 2026-06-13 | 2026-06-17 15:46 | 2026-06-18 | 2026-06-18 18:50 | 2026-06-19 | 2026-06-18 19:02 | 2026-06-19 | 2026-06-20 18:20 |  |  |  |  | 2026-06-22 11:51 | 2026-07-01 | 2026-06-30 19:59 | 2026-07-09 | 2026-07-07 19:05 | 2026-07-08 | 2026-07-11 13:05 | 2026-07-07 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-08-15 | [5 empty] | 2026-06-18 | 2026-06-22 11:50 | 2026-05-20 | 2026-05-21 18:44 | Site is RTMI | 2026-04-19 | 2026-05-03 11:17 | 1145850 | 206253 | 0 | 0 | 1296737.2098 | 214114 | 1296737.2098 | 214114 | 2026-07-13 11:21:13 +0530 | Nilesh Patel | False Ceiling frame works And Gypsum installation has been completed on site Electrical Works and switch board shifting has been completed at site 1st Coat of paint has been started at site Blockers - Require Electrical Materials at site (CX scope) | 2026-07-10 11:35:32 +0530 | Vishakha Vaishnav | Others: SPOKE TO CX YESTERDAY HE MENTIOEND BECAUSE OF BANK SERVER ISSUE HE IS UNABLE TO MAKE THE PAYMENT | 2026-06-17 11:49:55 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-05-23 | 2026-05-22 17:34 | 2026-06-05 | 2026-06-04 19:07 | RTMI
19589 | Turnkey | 2026-01-01 | Sangita Vivek Goyal | Ajmera Manhattan | MUM - GOR | No Estimate | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-19 | 2026-05-15 13:08 | 2026-04-20 |  | 2026-04-22 |  | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-04-22 |  | 2026-04-23 |  | 2026-04-23 |  | 2026-04-24 | [5 empty] | 2026-04-30 |  | 2026-05-08 |  | 2026-05-09 |  |  |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-19 | [6 empty] | 2026-06-06 |  | 2026-06-15 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-18 |  |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-05-17 |  | 2026-04-25 |  | Unknown | 2026-04-19 | 2026-05-15 13:07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-04-30 |  | 2026-05-07
19594 | Turnkey | 2026-01-01 | Jagruti Tomar | Puri velvet | MUM - GOR | No Estimate | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 84 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-22 | 2026-04-22 13:39 | 2026-04-23 |  | 2026-04-22 |  | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-04-26 |  | 2026-04-27 |  | 2026-04-27 |  | 2026-04-28 | [5 empty] | 2026-05-04 |  | 2026-05-12 |  | 2026-05-13 |  |  |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-22 |  | 2026-05-23 | [6 empty] | 2026-06-10 |  | 2026-06-19 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-22 |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-05-21 |  | 2026-04-29 |  | Unknown | 2026-04-22 | 2026-04-22 13:39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-23 19:10:30 +0530 | Sakshi Hire | DCM: carpet 860 member 2 adults juneÂ diwaliÂ 4 seater diningÂ entrance design l shape sofa cum bed cwc extend till kintchen entrance make it study room 55 tv with storageÂ 15 pair shoe rack horiz double door fridge right side sink hob left fridge microwaveÂ storage above washing machine front load gbr chest of drwer bed storage drw wardrobe & loft mbr storage front wall above below bed king size storage. side table with dresser wardrobe loft vanity & mirror false ceiling living & dining balcony deck emerald green sofa l shape 15 may | [6 empty] | 2026-05-04 |  | 2026-05-11
19597 | Turnkey | 2026-01-01 | Rachana Patil | Natasha Atlantis | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Aryan Singh |  | Hold | Preproduction | DEM2 | 512927 | 135775 | 699908 | 0 | 0 | 0 | 57 | 0 | 0 | 175464 | 201688.4 |  |  | 2026-04-21 | 2026-04-22 19:02 | 2026-04-22 | 2026-04-22 19:26 | 2026-04-25 | 2026-04-22 20:02 | 2026-05-20 | 2026-05-19 13:27 | 2026-12-01 |  | 2026-12-08 |  | 2026-04-22 | 2026-04-23 20:22 | 2026-04-23 | 2026-04-24 22:42 | 2026-04-24 | 2026-04-27 14:08 | 2026-05-05 | 2026-05-05 19:22 |  |  |  |  | 2026-05-25 | 2026-05-13 15:31 | 2026-12-03 |  | 2026-12-04 |  |  |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-13 |  | 2026-12-14 | [6 empty] | 2027-01-01 |  | 2027-01-10 |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-11 |  | 2027-01-13 |  |  |  | 2027-02-04 |  | 2027-02-06 |  | 2027-02-07 | [5 empty] | 2026-12-12 |  | 2026-05-06 | 2026-05-19 10:31 | Site is RTMI | 2026-04-21 | 2026-04-22 15:24 | 593142 | 106765 | 0 | 0 | 0 | 0 | 593142 | 106765 | 2026-06-30 11:30:55 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-19 18:07:30 +0530 | Siddhi Chaphekar | DDM1: Please find the attached MOM for DEM 1 17th May'26, Livingroom- TV unit- Base unit floor mounted and space for dumbell on floor but with shutter. Tv unit wall design-Back Panel with groove in paint finish Sofa wall- mouldings and wallpaper concept with wall lights .(Sofa in CX Scope) Foldable DiningÂ Wardrobe unitÂ Kitchen- Base + wall +loft units Master Bedroom- Wardrobe unit with loftÂ Mirror on single shutterÂ Bed back wall-in wallpaper or texture paint with frameÂ Note- There is no scope in bathrooms as of now, once we do the initial measurement will add storage if there is any space. Thanks & Regards, Interior Designer Siddhi Chaphekar. | 2026-05-19 17:00:12 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-20 | 2026-05-19 14:09 | 2026-12-02
19599 | Turnkey | 2026-01-01 | Firoj Mollick | others | BNG - HRBR | Yes | Faizan Sharief | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | 20% Payment | 702835 | 70299 | 904062 | 0 | 0 | 21 | 0 | 0 | 70268 | 281134 | 281134 |  |  | 2026-04-25 | 2026-06-10 14:37 | 2026-06-10 | 2026-06-10 14:43 | 2026-06-13 | 2026-06-10 15:22 | 2026-06-29 | 2026-06-24 20:05 | 2026-08-27 |  | 2026-09-03 |  | 2026-06-10 | 2026-06-22 18:19 | 2026-06-11 | 2026-06-22 18:20 | 2026-06-22 | 2026-06-23 18:13 | 2026-06-24 | 2026-06-24 16:25 |  |  |  |  | 2026-06-24 |  | 2026-08-29 |  | 2026-08-30 |  |  |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 | [6 empty] | 2026-09-27 |  | 2026-10-06 |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-09 |  |  |  | 2026-10-31 |  | 2026-11-02 |  | 2026-11-03 | [5 empty] | 2026-09-07 |  | 2026-06-25 | 2026-06-24 19:50 | Site is Non-RTMI | 2026-04-25 | 2026-04-22 20:27 | 766154 | 137907 | 0 | 0 | 0 | 0 | 766154.335 | 126510 | 2026-06-25 18:18:13 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-24 16:28:07 +0530 | Rajeshwari S | Welcome call done along with Designer at the HRBR EC Call recorded. RTMI Project. Wanted to complete the CM & design phase by 3rd July as they are leaving to Singapore DEM 1 & Material selection is schedule don 24th June. 10% payment will be done by 3rd July. Aligned with payment terms and process. | 2026-06-23 18:13:24 +0530 | Athul Ajaykumar | Possession Status: RTMI Â Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40, Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend) * DEM 1 Will update to the sales team * 10% Payment Stage Tentatively scheduled for (2nd of July) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Hob & Chimney Offer 100% GST Waiver Design fee waiver (5%) PM fee waiver (5%) Final Closing Value Discussed: 7,02,836 Checklist terms descoping, agreement terms are cleared | 2026-06-25 | 2026-06-24 20:05 | 2026-08-28 |  | RTMI
19601 | Turnkey | 2026-01-01 | Vasanta | other | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | Arun Kumar | Arun Kumar | Ankith Rodrigues | Saddam Hussain Z M | Murali S |  | Abdul Shafeen | Active | Installation | Execution | 822897 | 822897 | 882788 | 0 | 837897 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 | 2026-04-27 11:39 | 2026-04-24 | 2026-04-28 13:17 | 2026-05-01 | 2026-04-28 18:53 | 2026-05-18 | 2026-05-17 16:53 | 2026-06-01 | 2026-05-31 17:15 | 2026-06-11 | 2026-06-10 18:06 | 2026-04-24 | 2026-04-27 19:15 | 2026-04-29 | 2026-04-30 15:16 | 2026-04-30 | 2026-05-05 15:21 | 2026-05-09 | 2026-05-09 11:35 |  |  |  |  | 2026-05-17 | 2026-05-25 18:55 | 2026-06-10 | 2026-06-06 18:10 | 2026-06-07 | 2026-06-06 18:36 |  |  | 2026-06-11 | 2026-06-12 16:57 | 2026-06-13 | 2026-06-13 14:19 | 2026-06-14 | 2026-06-13 17:32 | 2026-06-14 | 2026-06-19 18:48 |  |  |  |  | 2026-06-23 21:20 | 2026-06-27 | 2026-06-26 20:55 | 2026-07-05 | 2026-07-03 19:31 | 2026-06-22 | 2026-04-23 19:15 | 2026-07-03 | 2026-07-11 15:01 | 2026-07-11 | 2026-07-11 18:33 | 2026-07-13 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-13 | 2026-06-23 21:19 | 2026-05-10 | 2026-05-17 16:26 | Site is RTMI | 2026-04-23 | 2026-04-23 19:15 | 748125 | 134662 | 0 | 0 | 851886.2188 | 143831 | 851886.2188 | 143831 | 2026-06-16 17:53:02 +0530 | Priyanka R | Some Image was uploaded | 2026-05-19 12:12:34 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-10 10:50:22 +0530 | Priyanka R | Some Image was uploaded | 2026-05-18 | 2026-05-17 16:54 | 2026-06-01 | 2026-05-31 17:16 | RTMI
19606 | Turnkey | 2026-01-01 | Dinesh KM KM | Birla Tisya | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Preproduction | DEM2 | 1011281 | 196599 | 1190209 | 0 | 0 | 36 | 0 | 0 | 0 | 472399 | 342283.2 |  |  | 2026-04-23 | 2026-04-26 12:26 | 2026-04-26 | 2026-04-26 12:38 | 2026-05-02 | 2026-05-02 19:38 | 2026-06-06 | 2026-06-06 14:36 | 2026-08-07 |  | 2026-08-14 |  | 2026-05-02 | 2026-04-30 | 2026-05-03 | 2026-05-20 12:07 | 2026-05-23 | 2026-05-25 17:42 | 2026-05-31 | 2026-05-31 18:59 |  |  |  |  | 2026-06-06 | 2026-06-09 18:01 | 2026-08-09 |  | 2026-08-10 |  |  |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 | [6 empty] | 2026-09-07 |  | 2026-09-16 |  | 2026-06-18 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-19 |  |  |  | 2026-10-11 |  | 2026-10-13 |  | 2026-10-14 | [5 empty] | 2026-08-18 |  | 2026-06-01 | 2026-06-06 13:23 | Site is RTMI | 2026-04-23 | 2026-04-24 17:44 | 1010939 | 179270 | 0 | 0 | 0 | 0 | 1031894.448 | 175356 | 2026-06-09 15:23:24 +0530 | Hemalatha D | DDM1: DEM 1 19606 -06/06/26 Living Room TV back panel need to add Dining RoomÂ Crockery Unit need to changes mirror to be removed tall unit to be added Kitchen Black galaxy granite fridge - 2 door shelves need to remove and cabinet need to add Loft to be added sink needÂ add Master Bedroom Bed Side table need to add Kids bedroom Bed Side table need to add Mirror placement need to checkÂ after IM GBRÂ Mirror need to add Vanity unit need to add for 3 bathrooms | 2026-05-27 12:01:26 +0530 | Priyanka Gs | Some Image was uploaded | 2026-05-25 17:41:47 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Client mentioned once he comes back to Bangalore, he will let the sales team know * DEM 1 TClient mentioned once he comes back to bangalore he will let the sales team know * 10% Payment Stage Tentatively scheduled for (3rd June 2026 ) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin Offer PM fee waiver (5%) Laminate Upgrade Windows to Wonderful home Services Windows to Wonderful Home Furniture - Windows to Wonderful Home Modular Windows to Wonderful home Final Closing Value Discussed: 9,82,995 Client VOC Client mentioned he will get the possession within a month, tentatively by the end of June. Client informed that he is currently in his native town and will return to Bangalore by 29th May. The client is planning to meet the developer by 1st June. Dates for IMs and DEM1 will be updated to the sales team accordingly. | 2026-06-07 | 2026-06-06 14:37 | 2026-08-08 |  | Under Construction | 2026-06-30
19607 | Turnkey | 2026-01-01 | Sagar Dalvi Shraddha Dalvi | jp dex | MUM - GOR | Yes | Swapnali Shedekar | Reshma Melanta | Safalta Karkera |  | Urvisha Prajapati |  |  |  | Mrunali Mitkari | Siddhesh Gujrathi | Active | Design | DEM3 | 1403030 | 479514 | 1795140 | 0 | 0 | 29 | 0 | 0 | 0 | 413096 | 510420.4 |  |  | 2026-04-23 | 2026-05-05 15:31 | 2026-05-05 | 2026-05-05 19:15 | 2026-05-08 | 2026-05-06 12:02 | 2026-05-31 | 2026-05-27 20:29 | 2026-06-13 | 2026-06-13 14:30 | 2026-06-20 |  | 2026-05-06 | 2026-05-06 12:14 | 2026-05-07 | 2026-05-06 16:31 | 2026-05-06 | 2026-05-07 12:52 | 2026-05-24 | 2026-05-24 17:50 |  |  |  |  | 2026-05-30 | 2026-05-27 19:51 | 2026-06-14 | 2026-06-16 01:11 | 2026-06-17 | 2026-06-16 01:12 |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-05-25 | 2026-05-27 20:23 | Site is RTMI | 2026-04-23 | 2026-05-05 15:04 | 1523592 | 271547 | 0 | 0 | 0 | 0 | 1504987.5518 | 251395 | 2026-06-12 15:18:16 +0530 | Swapnali Shedekar |  | 2026-05-27 19:58:38 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-27 19:45:24 +0530 | Reshma Melanta | TO ADD REFERRAL AMOUNT FOR THE SAME AMAZON VOUCHER - 2500/- (REFERRAL VISIT IF THIIER VISIT) JUNE END THE REFERRAL WILL VISIT ANDHERI EC AND ACCORDINGLY WILL MAKE THE DECISION | 2026-05-28 | 2026-05-29 14:38 | 2026-06-14 | 2026-06-13 14:35
19611 | Turnkey | 2026-01-01 | Rajkumar Shah | Prescon Midtown Bay | MUM - GOR | Yes | Priyanka Murarka | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Nilesh Patel | Rizwan Mistry |  | Moni Sahani | Aakash Gaikwad | Active | Preproduction | 3D Sign off | 3697815 | 461062 | 3559543 | 0 | 3697815 | 4 | 0 | 0 | 0 | 1795617 | 1441136.4 |  |  | 2026-04-23 | 2026-05-03 12:10 | 2026-05-03 | 2026-05-03 14:30 | 2026-05-06 | 2026-05-06 13:45 | 2026-06-09 | 2026-06-09 12:48 | 2026-07-05 | 2026-07-04 14:35 | 2026-07-04 | 2026-07-04 16:07 | 2026-05-06 | 2026-04-30 | 2026-05-08 | 2026-05-07 17:00 | 2026-05-07 | 2026-05-27 18:36 | 2026-05-30 | 2026-05-30 20:31 |  |  |  |  | 2026-06-12 | 2026-06-08 18:50 | 2026-06-29 | 2026-06-29 20:10 | 2026-06-30 | 2026-06-29 20:11 |  |  | 2026-07-08 | 2026-07-10 20:53 | 2026-07-11 | 2026-07-12 18:04 | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-05-31 | 2026-06-07 17:15 | Site is RTMI | 2026-04-23 | 2026-04-30 18:47 | 3016562 | 542981 | 0 | 0 | 3979655.234 | 657124 | 3979655.234 | 657124 | 2026-07-08 13:42:48 +0530 | Neha Singh | HOTO: | 2026-06-11 11:48:59 +0530 | Priyanka Murarka | DDM2: 10th JUNE KITCHEN AC to installed either ducted or a split ac above door Tall unit to have oven in bottom & than a shelf with telescopic for mixer & than space for microwave quartz - wicker or bianco desert laminate - royal touche - 2024-0001 crystal Zhandle - G profile - brushed gold custom work - panel to cover the exhaust & fixed glass space quartz sink - SK FU FS 2220 NQ WHEAT SPOT - FUTURA STUDY ROOM PU 7032 gloss pebble grey profile 2 - pu-102 wallpaper - 71063-2 essen tall unit to be divided in 3 parts - centre to be kept for printer space. WALK IN WARDROBE - MBR snow white matt (SM1) Wedge F shutter champagne handle 1 full mirror wardrobe in centre SON'S ROOM wallpaper - 36924-9 excel- hot spots - behind bed & on front column laminate - cross bar HG 1486- bedback wall panel with indirect light-custom work same laminate for side tablesFull length mirror in the front wall of the entrance WALK IN WARDROBE - SON'S ROOM Membrane -sand satin SM1 Countertop - Bronze metallic 1591 sd Mirror end to end in the space between cabinets Profile- KP 12 CL 20 SM1 LIVING ROOM Entrance front to have mirror design same decor on the walls to be continued behind dining wall & sofa long wall | 2026-06-09 12:56:32 +0530 | Priyanka Murarka | DDM1: 7th june Kitchen Tall appliance unit. Hob & chimney to be placed next to the tall unit. Dishwasher to be accommodated in the utility area. Change the sink and provide a waste crusher. Increase the utility area flooring level to match the kitchen flooring level. Pipe cladding/custom covering required. Additional sink required in the utility area for washing utensils. Full kitchen civil work to be involved Entrance / Passage Safety door required. Full-height storage in the passage area. Outside area to have shoe cabinet & wall panelling decor. Master Bedroom (MBR) Walk in wardrobe space to have 1 full length mirror on shutter & small mirror above vanity drawers. Bed direction to be finalized/confirmed (North side discussed or under the beam) References for bed back panel is discussed along with false ceiling design. Sons Bedroom Storage unit requirement: Top cabinet storage. Open space for ironing accessories and keeping suitcase for guests. Shelf provision. Bottom cabinet storage. Wardrobe to include: Glass display section. Organizer compartments. Trolley storage. Washrooms to have glass partition & vanity units. | 2026-06-10 | 2026-06-09 13:07 | 2026-07-05 | 2026-07-04 16:31 | RTMI
19614 | Turnkey | 2026-01-01 | Chandrakanth | independent house | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [7 empty] | Active | Preproduction | DEM2 | 1017940 | 203588 | 1318088 | 0 | 0 | 25 | 0 | 0 | 0 | 440214 | 374138 |  |  | 2026-04-25 | 2026-04-24 20:03 | 2026-04-29 | 2026-04-29 19:33 | 2026-04-30 | 2026-05-01 12:39 | 2026-05-22 | 2026-05-22 16:36 | 2026-06-18 | 2026-06-17 19:35 | 2026-07-17 |  | 2026-05-01 | 2026-04-30 | 2026-05-02 | 2026-05-01 20:17 | 2026-05-01 | 2026-05-04 10:40 | 2026-05-09 | 2026-05-09 19:39 |  |  |  |  | 2026-05-22 | 2026-05-23 21:25 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-06-22 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-05-10 | 2026-05-22 16:30 | Site is RTMI | 2026-04-25 | 2026-04-24 17:38 | 1117024 | 201064 | 0 | 0 | 0 | 0 | 1088250.156 | 179685 | 2026-06-17 19:17:07 +0530 | Ashiya Sanam | Living Room: 1.Cx wants to go with the same design theme 2.Painting for beading in bonito scope 3.Pooja Unit in bonito scope, need to share some Cnc Door designs and estimate to be provided 3.Tv unit materials are selected 4.Louvers are selected 5.Wallpaper is selected 6.Wall design to be done on one extra wall near TV Unit 7.False ceiling in Bonito scope, Electrification in cx scope Kitchen: 1.Materials are selected 2.Kitchen to go with complete loft on both sides 3.Appliances unit tall unit to be made as closed single tall unit 4.Fridge space to be provided accordingly 5.False ceiling in bonito scope,Electrification in cx scope6..Layout is finalised 6..As per the floor to ceiling height units might increase in height or PoP Is suggested 7.Granite is added in bonito scope Dining Unit: 1.Materials are selected 2.False ceiling in Bonito scope, Electrification in cx scope 3.Layout is finalised 4.Wall designs are finalised Master Bedroom: 1.Wall designs are finalised 2.Dresser unit to be beside bed, Suggested with loose furniture, Mirror in cx scope 3.wardrobe to be shifted to the corner and study unit to be shifted at the right side. 4.Extra Storage to be provided for hanging 5.Wallpaper is finalised 6.False ceiling in bonito scope Bathroom and toilet: 1.Vanity unit to be shifted on the other side 2.Materials are selected | 2026-05-22 15:58:14 +0530 | Ashiya Sanam | Minutes of Meeting held on Date: Title:DEM-1 Project:19614 Client:Chandrakanth Attendees:Ashiya Objective: Discussion Based on 22-05-2026 meeting, below is a list of all the requirements that were discussed during the meeting: Living Room: 1.Cx wants to go with the same design theme 2.Painting for beading in bonito scope 3.Pooja Unit in bonito scope, need to share some Cnc Door designs and estimate to be provided 3.Tv unit materials are selected 4.Louvers are selected 5.Wallpaper is selected 6.Wall design to be done on one extra wall near TV Unit 7.False ceiling in Bonito scope, Electrification in cx scope 8.Layout is finalised Kitchen: 1.Materials are selected 2.Kitchen to go with complete loft on both sides 3.Appliances unit tall unit to be made as closed single tall unit 4.As per IM File , Units needs o be adjusted. 5.Fridge space to be provided accordingly 6.False ceiling in bonito scope,Electrification in cx scope 7.Layout is finalised 8.As per the floor to ceiling height units might increase in height or PoP Is suggested 9.Granite is added in bonito scope Dining Unit: 1.Materials are selected 2.False ceiling in Bonito scope, Electrification in cx scope 3.Layout is finalised 4.Wall designs are finalised Master Bedroom: 1.Wall designs are finalised 2.Dresser unit to be beside bed, Suggested with loose furniture, Mirror in cx scope 3.wardrobe to be shifted to the corner and study unit to be shifted at the right side. 4.Extra Storage to be provided for hanging 5.Wallpaper is finalised 6.False ceiling in bonito scope Bathroom and toilet: 1.Vanity unit to be shifted on the other side 2.Materials are selected NOTE; 1.As per the IM File Units may have variation in dimensions and the cost might increase. 2.Estimation may have variation according to adding or descoping of units. 3.Electricals and full house painting in cx scope | 2026-05-21 11:31:41 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-23 | 2026-05-22 16:36 | 2026-06-18 | 2026-06-17 19:35 | Under Construction | 2026-05-09
19617 | Turnkey | 2026-01-01 | Ruchi Kothari | Jainson | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Sanskruti Yadav |  | Active | Preproduction | DEM2 | 1647464 | 226142 | 1611980 | 0 | 0 | 42 | 2 | 0 | 0 | 800743 | 620578.8 |  |  | 2026-04-23 | 2026-04-30 14:25 | 2026-04-30 | 2026-04-30 20:04 | 2026-05-02 | 2026-05-02 12:47 | 2026-05-24 | 2026-05-24 21:27 | 2026-07-29 |  | 2026-08-05 |  | 2026-05-02 | 2026-05-05 13:06 | 2026-05-03 | 2026-05-10 11:50 | 2026-05-10 | 2026-05-15 14:26 | 2026-05-20 | 2026-05-20 14:24 |  |  |  |  | 2026-05-24 | 2026-06-03 19:05 | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-05-21 | 2026-05-24 15:06 | Site is RTMI | 2026-04-23 | 2026-04-25 14:26 | 1368330 | 243650 | 0 | 0 | 0 | 0 | 1900574.2752 | 327960 | 2026-06-21 13:32:46 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-05-31 12:19:50 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-27 14:06:18 +0530 | Preeti Agarwal | Minutes of Meeting held on Date: 24/05/2026 1. BENCH SEATING DINING - 4SEATER 2. HANGING TV UNIT - L-SHAPE WITH TALL UNIT 3. 65" TV IN LIVING DINING 4. CIVIL IN LIVING DINING, KITCHEN 5. Right side GAS STOVE - GREEN BARIDA MARBLE 6. WASHING MACHINE UNDER - BLACK TILE 7. SPICE RACK OPPOSITE SIDE 8. GLASS SHUTTER OPPOSITE SIDE 9. Wardrobe internal light provision 10. MIRROR IN BEDROOM 1 - SAME AS REFERENCE SHARED 11. SHOWER PARTITION TO BE CHECKED DURING CM 12. VANITIES TO BE CONSIDERED IN WASHROOM 13. WARDROBE INTERNAL DISCUSSION DONE - SHARED REFERENCE 14. MASTER BEDROOM - 40" TV TO BE CONSIDERED 15. KITCHEN - MEMBRANE FINISH 16. EVERY WHERE MEMBRANE FINISH 17. SHOE RACK - L-SHAPE WITH SEATING & TALL UNIT 18. SAFETY DOOR - PDF SHARED 19. CROCKERY UNIT PLACEMENT TO BE CHECKED 20. AC PELMETS IN ALL THE ROOMS NEXT MEETING - 7TH JUNE - 5:30PM | 2026-05-25 | 2026-05-24 21:27 | 2026-07-30 |  | RTMI
19618 | Sub Project |  | Suraksha Dhanur | Independent Villa | BNG - HSR | Yes | Priyanka Mathur |  | Kowshik | [7 empty] | Active | Preproduction | DEM2 | 44097 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 26458 | 17638.8 |  |  | 2026-04-24 | 2026-04-24 16:32 | 2026-04-25 | 2026-04-24 16:32 | 2026-04-24 | 2026-04-24 16:32 | 2026-04-24 | 2026-04-24 16:49 | 2026-04-25 |  | 2026-05-02 |  | 2026-04-24 | 2026-04-24 16:33 | 2026-04-25 | 2026-04-24 16:33 | 2026-04-24 | 2026-04-24 16:33 | 2026-04-25 | 2026-04-24 16:33 |  |  |  |  | 2026-04-29 | 2026-04-24 16:36 | 2026-04-27 |  | 2026-04-28 |  |  |  | 2026-05-05 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-08 | [6 empty] | 2026-05-26 |  | 2026-06-04 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-29 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-05-06 |  | 2026-04-25 | 2026-04-24 16:36 | Unknown | 2026-04-24 | 2026-04-24 16:32 | 0 | 0 | 0 | 0 | 0 | 0 | 37371 | 6726 | [9 empty] | 2026-04-25 | 2026-04-24 19:14 | 2026-04-26
19620 | Sub Project |  | Sandhya | Grand Pallazo | BNG - HSR |  | Manoj Kumar R | Akshay Ds | Kowshik |  |  | Yogeshwaran | Ranjith Kumar | Murali S |  | Vishwa Hiremath | Active | Production | Dispatch Due | 46586 | 46587 | 0 | 0 | 46586 | 42 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-24 | 2026-04-25 16:23 | 2026-04-25 | 2026-04-25 16:23 | 2026-04-25 | 2026-04-25 16:23 | 2026-04-26 | 2026-04-25 16:24 | 2026-04-26 | 2026-04-25 16:26 | 2026-04-28 | 2026-04-28 18:47 | 2026-04-25 | 2026-04-25 16:23 | 2026-04-26 | 2026-04-25 16:23 | 2026-04-25 | 2026-04-25 16:23 | 2026-04-26 | 2026-04-25 16:24 |  |  |  |  | 2026-04-25 | 2026-04-25 16:25 | 2026-04-26 | 2026-04-25 16:26 | 2026-04-26 | 2026-04-25 16:26 |  |  | 2026-04-29 | 2026-04-28 19:06 | 2026-04-29 | 2026-04-28 19:21 | 2026-04-29 | 2026-04-29 10:59 | 2026-04-30 | 2026-04-30 20:07 |  |  |  |  | 2026-05-14 19:29 | 2026-05-23 | 2026-05-23 18:57 | 2026-05-27 | 2026-05-25 15:14 | 2026-05-26 | 2026-06-03 16:45 | 2026-05-25 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-04-28 | 2026-05-14 19:28 | 2026-04-26 | 2026-04-25 16:24 | Unknown | 2026-04-24 | 2026-04-25 16:23 | 0 | 0 | 0 | 0 | 148072 | 22360 | 148072 | 22360 | 2026-06-10 15:31:06 +0530 | Ranjith Kumar | Execution: | [6 empty] | 2026-04-26 | 2026-04-25 16:24 | 2026-04-26 | 2026-04-25 16:26
19621 | Turnkey | 2026-01-01 | Melsina Fredy Kinni | independent House | MUM - GOR | Yes | Khyati Bandi | Reshma Melanta | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 1107890 | 221578 | 1447523 | 0 | 0 | 45 | 0 | 0 | 0 | 450819 | 435492.8 |  |  | 2026-04-23 | 2026-04-27 15:19 | 2026-04-29 | 2026-04-29 17:50 | 2026-05-02 | 2026-04-30 13:36 | 2026-06-04 | 2026-05-31 15:52 | 2026-06-13 | 2026-06-12 16:45 | 2026-07-04 |  | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-05 09:32 | 2026-05-05 | 2026-05-05 15:20 | 2026-05-24 | 2026-05-24 18:36 |  |  |  |  | 2026-05-30 | 2026-05-25 18:42 | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-05-25 | 2026-05-31 15:51 | Site is RTMI | 2026-04-23 | 2026-04-24 18:31 | 1226714 | 220808 | 0 | 0 | 0 | 0 | 1222318.63 | 197983 | 2026-05-23 16:10:53 +0530 | Khyati Bandi | LIVING AREA 1. Add wall ledges to keep show pieces near window 2. To cover full wall with decor (tv unit) 3. L shape sofa to be planned KITCHEN -Â 1. Front load washing machine near sinkÂ 2. Add 4 seater dining tabeÂ 3. Add breakfast counter near fridgeÂ Â 4. Add hand wash near dining tableÂ 5. Aquaguard under sink 6. Cylinder unit near 3 tandem drawer unit then one shutter unitÂ 7. Inbuilt hob is thereÂ 8. Kitchen - Need exceptional design, require all units 9. Loft unit to be added MBR- 1. Add hidden drawer in left wardrobeÂ 2. Mirror on bay window wall 3. Add bedÂ 4. off white/ beige themeÂ False ceiling in curveÂ Pelmet for ACÂ | 2026-05-23 15:44:32 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-14 14:15:05 +0530 | Riddhi Deshpande | DDM1: have asked pratima for transition | 2026-06-01 | 2026-05-31 15:54 | 2026-06-13 | 2026-06-12 16:46
19622 | Sub Project |  | Mr. MALLIKARJUN S | TVS Emerald Jardin - Official | BNG - HRBR |  | Salpriyan Pm | Rajeshwari S | Shibin Lal |  |  | Ruthwik S K | Ranjith Kumar | Murali S |  |  | Active | Installation | Execution | -3233 | 0 | 0 | 0 | -3233 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-24 | 2026-04-24 18:18 | 2026-04-25 | 2026-04-24 18:18 | 2026-04-24 | 2026-04-24 18:18 | 2026-04-25 | 2026-04-24 18:19 | 2026-04-25 | 2026-04-24 18:21 | 2026-04-25 | 2026-04-24 18:22 | 2026-04-24 | 2026-04-24 18:18 | 2026-04-25 | 2026-04-24 18:18 | 2026-04-24 | 2026-04-24 18:18 | 2026-04-25 | 2026-04-24 18:18 |  |  |  |  | 2026-04-24 | 2026-04-24 18:19 | 2026-04-25 | 2026-04-24 18:21 | 2026-04-25 | 2026-04-24 18:21 |  |  | 2026-04-25 | 2026-04-24 18:23 | 2026-04-25 | 2026-05-13 17:35 | 2026-05-14 | 2026-05-14 10:31 | 2026-05-15 | 2026-05-14 10:32 |  |  |  |  | 2026-05-14 11:06 | 2026-05-23 | 2026-05-23 18:58 | 2026-05-27 | 2026-05-25 15:19 | 2026-05-26 | 2026-05-26 11:01 | 2026-05-25 | 2026-07-02 07:31 | 2026-07-02 | 2026-07-02 07:32 | 2026-07-04 |  |  |  | 2026-08-21 |  | 2026-08-23 |  | 2026-08-24 | [5 empty] | 2026-05-13 | 2026-05-13 18:53 | 2026-04-25 | 2026-04-24 18:19 | Unknown | 2026-04-24 | 2026-04-24 18:17 | 0 | 0 | 0 | 0 | 31158 | 5608 | 31158 | 5608 | 2026-06-10 17:53:07 +0530 | Ranjith Kumar | Execution: | 2026-04-25 20:01:29 +0530 | Vidhya Achu Roy | Some Image was uploaded |  |  |  | 2026-04-25 | 2026-04-24 18:19 | 2026-04-25 | 2026-04-24 18:21
19623 | Turnkey | 2026-01-01 | Harvinder Kaur | bhoomi gardenia 1 | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 1538880 | 213999 | 2041414 | 0 | 0 | 79 | 0 | 0 | 93777 | 711818 | 519286 |  |  | 2026-04-24 | 2026-04-24 18:18 | 2026-04-24 | 2026-04-24 22:08 | 2026-04-27 | 2026-04-24 22:14 | 2026-11-04 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-04-24 | 2026-04-25 14:39 | 2026-04-25 | 2026-04-27 14:40 | 2026-04-27 | 2026-04-27 15:18 | 2026-05-23 | 2026-05-23 13:16 |  |  |  |  | 2026-12-24 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-10-31 |  | Site is RTMI | 2026-04-24 | 2026-04-24 18:18 | 1730012 | 311402 | 0 | 0 | 0 | 0 | 1724356.8406 | 284702 | 2026-07-05 11:28:38 +0530 | Divya Rahangdale | Store Credit against Cancellation | 2026-07-02 13:39:39 +0530 | Divya Rahangdale | Store Credit as an Exception | 2026-06-13 19:32:19 +0530 | Naved Malik | Some Image was uploaded | 2026-11-05 |  | 2026-06-24
19626 | Turnkey | 2026-01-01 | Ravi Chavan | Mahavir Spring | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Mustufa Sohagpurwala |  | Hold | Design | DEM1 | 1954573 | 199999 | 3890151 | 0 | 0 | 19 | 43 | 0 | 190916 | 830679 | 732979.2 |  |  | 2026-04-24 | 2026-04-24 19:39 | 2026-05-01 | 2026-05-07 11:18 | 2026-05-09 | 2026-05-11 14:24 | 2026-09-03 |  | 2026-09-10 |  | 2026-09-17 |  | 2026-05-11 | 2026-05-12 13:50 | 2026-05-12 | 2026-05-12 13:51 | 2026-05-12 | 2026-05-14 12:44 | 2026-05-22 | 2026-05-22 11:48 |  |  |  |  | 2026-09-04 |  | 2026-09-12 |  | 2026-09-13 |  |  |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 | [6 empty] | 2026-10-11 |  | 2026-10-20 |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-23 |  |  |  | 2026-11-14 |  | 2026-11-16 |  | 2026-11-17 | [5 empty] | 2026-09-21 |  | 2026-08-30 |  | Unknown | 2026-04-24 | 2026-04-24 19:38 | 3296738 | 593412 | 0 | 0 | 0 | 0 | 1656418 | 298155 | 2026-07-04 12:42:37 +0530 | Anil Jagtap | The client will make the payment after the layout is finalized. Possession: Tentative â€“ March 2027. | 2026-06-02 10:22:15 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-27 12:22:44 +0530 | Parnavi Joshi | Layout changes as per zoning and space planning was discussed. Overall design theme and details were discussed Design theme-European-Neo classical. with Arch door opening, wall mouldings etc. - Entrance to be retained as per original layout. Safety door enclosing the lobby to not be taken - Shoe rack to be placed in the lobby with wall decor and name plate. Carpet flooring/vinyl flooring to be kept in the lobby with European/Moroccan theme and motifs.Â - Previously planned kitchen to be changed as mandir with Marble mandir with carvings and inlay (cx scope). - Mandir will have traditional seating like Deewan, pichwai wallpaper behind the deewan and wall niches for the diyas etc (jharoka shaped) - Previously planned lounge area to be made as kitchen with parallel counters. Dishwasher space to be made below sink. Rest as per the space planning. Open kitchen concept. Breakfast counter to be added near the kitchen entranceÂ - Previously planned utility & bar section to be planned next to kitchen in line with breakfast counterÂ - Master bedroom dresser unit to be redone as per the reference discussed (top openable unit with mirror etc) - Master bathroom to be reworked in terms of space and as per zone-dry & wet zone. Bathtub to be considered, free standing bathtub/built in tub. Bathroom theme will be black and gold.Â - Walk in wardrobe area will be made retaining previous walls in previous layout - Previously planned utility and bar section to be made into a studio/lounge and study. Theme to be retained as planned with dark green wall, 7 horses painting, tan leather chair etcÂ - Living room zoning to be swapped. Dining next to kitchen , sofa seating to be kept where there was dining space Do let me know if there are any more pointers to discuss, Also, do share references with me i will take a note of it. | 2026-09-04 |  | 2026-09-11
19627 | Turnkey | 2026-01-01 | VinitG | Ankuraa Meridian | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1625521 | 9999 | 0 | 0 | 0 | 82 | 0 | 152553 | 162552 | 650208 | 650208.4 |  |  | 2026-04-24 | 2026-04-24 20:01 | 2026-04-26 | 2026-04-27 10:56 | 2026-04-29 |  | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-04-29 |  | 2026-04-30 |  | 2026-04-30 |  | 2026-05-01 | [5 empty] | 2026-05-07 |  | 2026-05-15 |  | 2026-05-16 |  |  |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 | [6 empty] | 2026-06-13 |  | 2026-06-22 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-25 |  |  |  | 2026-07-17 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-05-24 |  | 2026-05-02 |  | Unknown | 2026-04-24 | 2026-04-24 20:01 | 0 | 0 | 0 | 0 | 0 | 0 | 1377560 | 247960 | 2026-04-29 17:43:28 +0530 | Nayan Reddy | Minutes of Meeting held on Date: 29/04/26 Title: Project: Client: Attendees: Objective: Discussion Using Prelam HDHMR used in project Kitchen Loft dept need to increase RO placements need to confirm Dado tiles from vendor side Dining area Crockery unit designee planning to change to single glass shutter or planning to keep dining table with bench Civil work quote and Electrical work quote will be added in Validation stage MBR Need Deferent design for Dressing unit KBR need to plan study unit in KBR with bay window Living room Pooja unit buying from outside and Shoe rack Dining area Handwash cabinet need to be planned | 2026-04-27 10:54:20 +0530 | Nayan Reddy | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion MINUTES OF MEETING (MoM) Client Name: Vinit Project: Anukra Meridean (East Facing) CRM: Nidi RGM Date: 26/04/2026 Move-in Date: 30/06/2026 Budget: 8 Lakhs Floor to Ceiling Height: 96 1. KitchenModular kitchen finalizedGranite: Bonito (selected)Refrigerator space: 900mm provisionTall unit with internal drawers includedOpen to design suggestions for optimizationKitchen tiles: From vendorCylinder unit plannedBase unit and wall units includedLoft storage aboveRO provision near dishwasher areaRolling shutter unit includedHob side depth: 26Arch paneling at kitchen entranceAdditional: +2 tandem drawers2. Utility AreaWashing machine provisionDishwasher placed above washing machineGranite counter includedSink unit plannedWall storage unit includedJanitor unit: 1 x 63. Common AreasHandwash cabinet near common washroom4. Dining AreaCrockery unit with single tall unit4-seater dining table5. Living RoomTV unit with integrated pooja unit up to ceilingDisplay unit as part of TV unitPooja unit size: 3 x 66. False Ceiling (FC)Planned in Living Room, Dining Area, and Master BedroomBalcony & entrance: PVC false ceiling (vendor quote to be considered)7. FoyerShoe rack unit near entrance8. Master Bedroom (MBR)Wardrobe with loftDressing unitBay window seatingTV unitFoldable study unit9. Kids Bedroom (KBR)Bay window concept with wardrobe & loftStudy table included10. WashroomsVanity cabinets in all washrooms |  |  |  | 2026-05-07 |  | 2026-05-14
19628 | Turnkey | 2026-01-01 | Amit Parmar | The Icon Park 1 | MUM - Thane | Yes | [8 empty] | vinaya thakur |  | Active | Prospect | 10% Payment | 1435513 | 9999 | 1435513 | 0 | 0 | 74 | 0 | 133552 | 143551 | 586772 | 561638.8 |  |  | 2026-04-24 | 2026-04-24 21:27 | 2026-04-29 | 2026-04-29 12:03 | 2026-05-02 | 2026-05-03 13:42 | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-04 |  | 2026-05-05 | [5 empty] | 2026-05-11 |  | 2026-05-19 |  | 2026-05-20 |  |  |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 | [6 empty] | 2026-06-17 |  | 2026-06-26 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-29 |  |  |  | 2026-07-21 |  | 2026-07-23 |  | 2026-07-24 | [5 empty] | 2026-05-28 |  | 2026-05-06 |  | Unknown | 2026-04-24 | 2026-04-24 21:22 | 1216537 | 218976 | 0 | 0 | 0 | 0 | 1216537 | 218976 | 2026-04-29 16:51:59 +0530 | Anjali Singh | DCM: Client Requirement Summary Mr. Amit ParmarFamily Details4 family membersCouple + 2 daughters (25 & 23 years old)Daughters work in Mass Media / Production HouseHusband: BusinessWife: Makeup ArtistOverall Style PreferenceRoyal / Indian / Traditional themeKitchen specifically traditional styleTV unit in Indian wooden finishLiving / Dining AreaShoe rack required both outside + insideNeed partition near dining so dining area is not directly visible - suggested by designer as it was there main concern.TV unit (Indian wooden style)Sofa seating: 3 + 2 seaterExisting Sheesham sitting mandir to be reused (no new mandir)KitchenBreakfast counter by removing false wallAppliance planning for:OTGMicrowaveAppliance unitBase units for big storageBottle pull-outYellow kitchen themeSingle door fridge3 burner hob + chimneyExisting double bowl sink to remainNo pantry unitGlass shutters for crockeryNo kitchen door requiredNo granite countertopUtility AreaCabinet for detergentNeed to check whether utility can be merged inside or notDaughters BedroomSingle wardrobeBedNo TV unitFoldable workstation with drawers / floating shelvesDresser + full mirrorSofa cum bed (queen size)Theme to be suggestedMaster BedroomKing size bedWardrobeFoldable workstation + cabinet / shelvesNo TV unitDresser with full-length mirrorKettle space + electrical pointCoffee table with chairs / accent chairsSide tablesEnd-to-end windows in bedroomAll furniture newBathroomsVanity to be added in washroomBathroom tiles to be changedFlooring / CivilFlooring changes requiredBathroom & kitchen tiles to be changedBudget8 lakh Interior only10 lakh max With kitchen civil workTimeline3rd May CDP Presentation | 2026-04-24 21:29:08 +0530 | vinaya thakur | Some Image was uploaded | 2026-04-24 21:28:48 +0530 | vinaya thakur | Others: Silver Coin | 2026-05-11 |  | 2026-05-18
19629 | Turnkey | 2026-01-01 | Avni & Tanuj | Park East by Ruchira | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 2031442 | 9999 | 0 | 0 | 0 | 78 | 0 | 193145 | 203144 | 820194 | 804960 |  |  | 2026-04-24 | 2026-04-28 16:23 | 2026-05-19 | 2026-05-19 18:58 | 2026-04-30 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-04-24 | 2026-04-25 12:34 | 0 | 0 | 0 | 0 | 0 | 0 | 1721561 | 309881 | 2026-05-01 13:00:47 +0530 | Janvi Nagdeo | Some Image was uploaded | [6 empty] | 2026-05-30 |  | 2026-06-06
19630 | Turnkey | 2026-01-01 | Madhurima D. Chakraborty | orchid Salisbury | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Preproduction | DEM2 | 1139897 | 227979 | 1375703 | 0 | 0 | 50 | 0 | 0 | 0 | 478982 | 432936 |  |  | 2026-04-23 | 2026-05-01 12:48 | 2026-05-01 | 2026-05-01 13:23 | 2026-05-04 | 2026-05-01 15:35 | 2026-05-26 | 2026-05-26 19:29 | 2026-12-03 |  | 2026-12-10 |  | 2026-05-01 | 2026-04-30 | 2026-05-02 | 2026-05-03 11:51 | 2026-05-03 | 2026-05-07 15:19 | 2026-05-10 | 2026-05-16 11:30 |  |  |  |  | 2026-05-22 | 2026-05-23 19:51 | 2026-12-05 |  | 2026-12-06 |  |  |  | 2026-12-13 |  | 2026-12-14 |  | 2026-12-15 |  | 2026-12-16 | [6 empty] | 2027-01-03 |  | 2027-01-12 |  | 2027-01-11 |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-15 |  |  |  | 2027-02-06 |  | 2027-02-08 |  | 2027-02-09 | [5 empty] | 2026-12-14 |  | 2026-05-26 | 2026-05-26 17:36 | Site is RTMI | 2026-04-23 | 2026-04-28 20:12 | 1165850 | 209853 | 0 | 0 | 0 | 0 | 1149111.7685 | 198289 | 2026-05-08 12:48:18 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-05-07 18:22:21 +0530 | Palak Thakur | DCM: Title:Â Design Consultation Meeting Project No:Â 19630 Client:Â Madhurima D. Chakraborty Hi, Minutes of Meeting held on Date:Â <23/04/26> Attendees:palak Discussion:rgm Based on <23/04/26> meeting, below is a list of all the requirements that were discussed during the meeting: FINAL MOM 23-04/2026 PID Â Client Name:Â anneshÂ sir andÂ madhurima Â Property:orchidsÂ salsberryÂ kanishandraÂ nearÂ bharatiyaÂ city mallÂ Â Floor: 10th floorÂ Â Main Door Facing:Â east going outsideÂ Â Possession:Â decemberÂ or marchÂ Â Site Measurement may\juneÂ Â handover febÂ end or march endÂ Current residenceÂ 25 km from siteÂ soladevanahalliÂ TotalÂ sqftÂ 1650Â BuildupÂ TYPE OF CONSTRUCTION cement block Family Details 10 years inÂ bng Couple + daughter 8 monthsÂ Mam epsilonÂ manyataÂ SirÂ synachronÂ BCITÂ Working hybrid orÂ wfhÂ setupÂ BudgetClient Budget:Â 7-10 /-Recommended Budget (as per requirements): 10-14LakhsTheme themes traditional +Â jaipuriÂ (bedroom )+ industrial (tv unit livingDesign PreferencesÂ Colors, Finishes & Lighting Kitchen:Â paralleLLiving Area:Â Overall Preference:Â brightÂ colorsÂ no white to goÂ conpletelyÂ but good withÂ patelsKitchen Countertop:Â by bonitoLighting:Ceiling:Â ;living and dining and master bedroomÂ DesignÂ Requirements & Discussion PointsMasterÂ kitchen all bathroomsÂ Living roomÂ Bedroom 2 and 3 on hold as off nowEXISTING FURNITURE Master king bed fromÂ ikeaÂ , wardrobe in master presentÂ Dining foldingÂ 4 seaterÂ , metal black kitchen storage , metal bed in bedroom 3Â Bedroom MASTER BEDROOM top King existingÂ Wardrobe existingÂ Dresser unit to be given Study unit (optional )with keyboard trayÂ Â Tv unitÂ Mirror in corner in wardrobe spaceÂ marked in blue Bed + sideÂ tables guestÂ Â 03 Bedroom bottom Hold on now maybe add laterÂ Bay window + loft + wardrobe onÂ side of wallÂ AsÂ denoted in drawingÂ LIVINGÂ ROOMlayoutÂ same asdenotedÂ L shape sofa l towards thewindowÂ (sofa cum bed )56-64 "tvÂ Tv unitÂ Bottom storageÂ similar toÂ ECÂ Side and top glass conceptÂ AestheticÂ moreÂ Sofa wall back designÂ Balcony outside industrial livingBalcony master traditionalÂ UTILITYÂ Washing machine top load Open shelf in 1 side and topÂ storageÂ 1 single sink + dustbinÂ KITCHENÂ folding or folding door for entrance ParallelÂ Cylinder 2 2 door fridgeÂ Base + wall + loftÂ TsllÂ appliance unitÂ Micro +Â airfriyerÂ barbequeÂ electriacÂ mixtureÂ tosterÂ ,baby sterlizerÂ rice cooker ,blenderÂ HandlessÂ Chimney from bonito can be selected inÂ cdpÂ No sink in kitchenÂ dishwasher DININGÂ FoldableÂ 4 seaterÂ Crockery unit / cum hidden barÂ makedÂ in blueÂ shelf inÂ otherÂ wall (wall fall concept) Pooja in corner + keyboardÂ tray tall wit bottomÂ stoargeÂ + pocket doorsÂ cncÂ With shelf and bellsÂ FoyerÂ ShoeÂ storage existing to be suggested were to putÂ 4 boxes cheese board typeÂ Ganesha concept in foyer with shoe /consoleÂ Slider image frame for keys marked in blue Washroom x3 Base x3 Top mirror x3 TopÂ storageÂ x3 Yellow existingÂ furnitureÂ everywere | 2026-05-07 18:21:38 +0530 | Palak Thakur | CDP: Hello Mam and sir @~Katty @~anneshchakraborty 19630 - Madhurima D. ChakrabortyÂ , the MOM for cdp meeting are as follows-Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â the MOM 19630 - Madhurima D. ChakrabortyÂ Â Subject: Design and Quote Changes already incorporatedÂ MOM - 30/04/26 CHANGES IN CDP MEETINGÂ kitchenÂ hydralic wall cabinet added x2 master bedroomÂ loft added on top of existing wardrobe as of nowÂ dresser unit )base + top storage + mirrorÂ used cloth storage wardrobe addedÂ study unit drawer and shelf cost to be used for flat down of table from tv 1 sideÂ guest bedroomÂ tv unit base 2 drawer addedÂ living room 2 shelf extended for tv unit 2 drawer + 1 open unit addedÂ crockery unitÂ top glass unit shifted 1 feet highÂ 1 double shutter wall unit added in between for bar unit foyerÂ base drawer cost be be switched for wall storage as discussed Changes in design phase after measurement final the position of loft and used cloth storage in master bedroomÂ kitchen + utility platforms to be reversed addition of customized wall paper of german shephard in sofa back wallÂ foyer side wall which might be projected will be designed according to the black and white shoe box quantity and sizes passageÂ picture wall to not linear but ambiguity strip light (blinking /flicker/multicolor) to checkÂ dining area crockery on topÂ middle bar (should be hidden) base crockery solid shutter mandir will go in corner cnc door cost addedÂ mechanism to be in custom kids bedroomÂ existing sofa cum bed + white chest of drawer +black ikea shelf + green box to be placed. master bedroomÂ marriage picture in bed back wall NOTE - false ceiling + lighting , painting , dado tiles , granite not in bonito scope as of now not added in quote . | 2026-05-27 | 2026-05-26 19:59 | 2026-12-04 |  | RTMI
19631 | Turnkey | 2026-01-01 | Mr.Mangesh karande | Raymond GS | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 2456723 | 9999 | 0 | 0 | 0 | 78 | 0 | 235673 | 245672 | 1084832 | 880546.8 |  |  | 2026-04-25 | 2026-04-28 12:57 | 2026-04-29 | 2026-04-29 17:32 | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-03 |  | 2026-05-04 | [5 empty] | 2026-05-10 |  | 2026-05-18 |  | 2026-05-19 |  |  |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 | [6 empty] | 2026-06-16 |  | 2026-06-25 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-28 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-05-27 |  | 2026-05-05 |  | Unknown | 2026-04-25 | 2026-04-26 21:46 | 0 | 0 | 0 | 0 | 0 | 0 | 2081969 | 374754 | 2026-04-29 17:29:19 +0530 | Krutika Vernekar | Luxury Abstract Color scheme: White and Gold Style direction: Clean luxury with statement elements, not cluttered or traditional. Entry (13 ft wide)Entry to feel lavish and impactfulMust be a strong design statementNo common or standard design approachesLuxury abstract language onlySafety Door needed FoyerFoyer space with seating provisionStorage to be integratedShould continue the white and gold luxury themeLiving RoomSeating for 8 peopleL-shaped sofa layout1 accent chairTV unit includedBar Counter + DiningBar counter designed for display of liquor collectionProvision to remove liquor during festivalsSlab required for Ganpati placement during festivalsDining: 6-seater dining tableNo bench seatingKitchenParallel kitchen layoutSemi modular conceptFront-load Washing Machine planningDouble door refrigerator provisionMicrowave space includedMembrane finish for kitchenStorage: Base units, wall units, and loft storage plannedDishwasher provision to be considered in layout if possibleGlass shutters beside RO unit for crockery displayKids Bedroom (Bedroom 3)WardrobeStudy setup for two childrenDresserBed with storageWallpaper Concept + Mouldingsround wall conceptsGuest Room (Mothers Room)Mandir to be placed in this room (for mothers use) Exisiting mandir in Corean material will use the same Wardrobe DC pattern BedMaster BedroomWork-from-home setupBedside tablesWardrobe in membrane finishTotal two wardrobes plannedDresser includedMaster wall to highlighted nicely Masteroom passage also as memory wall to be decoratedBalcony PVC ceiling (asked if we do or not )Jhoola wall decor concepts | 2026-04-28 13:01:45 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-04-28 13:01:00 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-10 |  | 2026-05-17
19635 | Turnkey | 2026-01-01 | Karthik | independent house | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP |  | Sethuragavan R | Ruthwik S K | Ranjith Kumar |  | Chanakya Panigrahi | Sunil Kumar S M | Active | Preproduction | 2D | 1423795 | 230390 | 1633335 | 0 | 0 | 15 | 0 | 0 | 0 | 659274 | 534131.2 |  |  | 2026-04-25 | 2026-04-25 16:12 | 2026-04-25 | 2026-05-01 13:01 | 2026-05-04 | 2026-05-02 09:29 | 2026-06-02 | 2026-05-29 11:48 | 2026-06-26 | 2026-06-25 12:13 | 2026-06-30 | 2026-06-29 13:31 | 2026-05-02 | 2026-04-30 | 2026-05-03 | 2026-05-07 14:53 | 2026-05-07 | 2026-05-08 10:09 | 2026-05-09 | 2026-05-09 19:22 |  |  |  |  | 2026-05-18 | 2026-05-28 14:13 | 2026-06-22 | 2026-06-23 17:50 | 2026-06-24 | 2026-06-23 17:50 |  |  | 2026-06-29 | 2026-06-30 13:44 | 2026-12-31 |  | 2027-01-01 |  | 2027-01-02 | [6 empty] | 2027-01-20 |  | 2027-01-29 |  | 2027-01-28 |  | 2027-01-29 |  | 2027-01-30 |  | 2027-02-01 |  |  |  | 2027-02-23 |  | 2027-02-25 |  | 2027-02-26 | [5 empty] | 2026-12-31 |  | 2026-05-10 | 2026-05-29 11:43 | Site is RTMI | 2026-04-25 | 2026-04-25 16:09 | 1384182 | 249152 | 0 | 0 | 0 | 0 | 1620081.1894 | 269914 | 2026-07-09 19:04:54 +0530 | Soumya KP |  | 2026-06-28 19:50:08 +0530 | Aishwarya C | Some Image was uploaded | 2026-06-04 12:14:17 +0530 | Aishwarya C | The project was in a hurry, client had asked for back-to-back meeting but kitchen layout took a lot of time from the client end to finalise on designs as of today material selection is still not planned | 2026-05-30 | 2026-05-29 18:35 | 2026-06-26 | 2026-06-25 12:28 | RTMI
19636 | Turnkey | 2026-01-01 | Anjum Barudgar | Mira crest Kashimira | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | Akash Jadhav | Sandeep Tiwari | Murali S | Prashant Panigrahi | Shailendra Mishra | Active | Installation | Execution | 1448194 | 1448194 | 2034600 | 0 | 1448194 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-25 | 2026-04-26 11:24 | 2026-04-25 | 2026-04-26 12:02 | 2026-04-26 | 2026-04-26 21:03 | 2026-05-06 | 2026-05-06 15:01 | 2026-05-16 | 2026-05-15 11:30 | 2026-05-20 | 2026-05-20 19:28 | 2026-04-26 | 2026-04-28 19:59 | 2026-04-27 | 2026-04-29 11:22 | 2026-04-29 | 2026-04-29 15:56 | 2026-05-05 | 2026-05-05 12:35 |  |  |  |  | 2026-05-04 | 2026-04-28 19:59 | 2026-05-16 | 2026-05-17 19:25 | 2026-05-18 | 2026-05-17 19:25 |  |  | 2026-05-25 | 2026-05-30 15:48 | 2026-05-30 | 2026-05-30 19:39 | 2026-06-01 | 2026-05-30 19:59 | 2026-05-31 | 2026-06-01 16:21 |  |  |  |  | 2026-06-03 18:32 | 2026-06-23 | 2026-06-22 21:19 | 2026-06-27 | 2026-06-27 18:54 | 2026-06-27 | 2026-06-25 18:52 | 2026-06-27 | 2026-07-08 10:56 | 2026-07-08 | 2026-07-09 13:25 | 2026-07-11 |  |  |  | 2026-07-12 |  | 2026-07-14 |  | 2026-08-31 | [5 empty] | 2026-05-31 | 2026-06-03 12:45 | 2026-05-06 | 2026-05-05 18:54 | Site is RTMI | 2026-04-25 | 2026-04-26 11:24 | 1724237 | 310362 | 0 | 0 | 1523158.7058 | 260572 | 1523158.7058 | 260572 | 2026-07-05 14:44:12 +0530 | Sarita Jangid | Priority Pass - Request Raised by Sales team - The email Was not Pasted by Prashant.P in the App. | 2026-06-15 13:22:32 +0530 | Akash Jadhav | Procurement: key task close on 3rd June site readiness on 30th June | 2026-05-30 15:36:51 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-05-07 | 2026-05-06 16:45 | 2026-05-16 | 2026-05-15 11:30
19637 | Turnkey | 2026-01-01 | Shreyas Shivakumar | RRBC Piccassso | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Lost | Design | DEM1 | 2396335 | 205000 | 2831007 | 0 | 0 | 70 | 0 | 0 | 274267 | 994495 | 922572.8 |  |  | 2026-04-25 | 2026-04-25 22:07 | 2026-04-25 | 2026-04-27 20:32 | 2026-04-29 | 2026-04-30 21:36 | 2026-11-04 |  | 2026-11-11 |  | 2026-11-18 |  | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-05 11:04 | 2026-05-05 | 2026-05-06 12:49 | 2026-05-22 | 2026-05-22 16:53 |  |  |  |  | 2026-11-05 |  | 2026-11-13 |  | 2026-11-14 |  |  |  | 2026-11-21 |  | 2026-11-22 |  | 2026-11-23 |  | 2026-11-24 | [6 empty] | 2026-12-12 |  | 2026-12-21 |  | 2026-12-20 |  | 2026-12-21 |  | 2026-12-22 |  | 2026-12-24 |  |  |  | 2027-01-15 |  | 2027-01-17 |  | 2027-01-18 | [5 empty] | 2026-11-22 |  | 2026-10-31 |  | Site is RTMI | 2026-04-25 | 2026-04-25 21:42 | 2399158 | 431848 | 0 | 0 | 0 | 0 | 2675718.5065 | 441813 | 2026-07-09 17:29:57 +0530 | Abhinandan K S |  | 2026-07-09 17:28:11 +0530 | Abhinandan K S |  | 2026-06-05 16:38:13 +0530 | Aishwarya C | In the first meeting client was discussing among themselves that if they want to cancel the project and they were in a hurry. we did provide back-to-back meeting, and client wanted a clear understanding on the material cost variation. Hence, we accommodated that as well no renders or any images were shared. but the costing clarity was given to them. on May 28th he did mention that he will come back on June 2nd and pay kept following with the client for when he is available after freezing the time for the meeting. he dropped a cancellation message | 2026-11-05 |  | 2026-11-12 |  | RTMI
19639 | Turnkey | 2026-01-01 | Lignetta Silveira | wadhwa the West | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2498181 | 9999 | 0 | 0 | 0 | 75 | 0 | 239819 | 249818 | 1105976 | 892568.4 |  |  | 2026-04-25 | 2026-05-01 10:48 | 2026-05-01 | 2026-05-01 11:30 | 2026-05-04 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-05-25 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-05 |  | 2026-05-06 | [5 empty] | 2026-05-12 |  | 2026-05-20 |  | 2026-05-21 |  |  |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 | [6 empty] | 2026-06-18 |  | 2026-06-27 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-30 |  |  |  | 2026-07-22 |  | 2026-07-24 |  | 2026-07-25 | [5 empty] | 2026-05-29 |  | 2026-05-07 |  | Unknown | 2026-04-25 | 2026-04-25 17:43 | 0 | 0 | 0 | 0 | 0 | 0 | 2117102 | 381078 | 2026-05-18 10:46:53 +0530 | Priyanka Patel | CDP: Project Name/Tower Name/Flat Number 19639 - Lignetta Silveira Typology 3bhk Site Access Date 2026-05-18 Possession Date 2026-05-18 Customer ProfileFamily members (no. & age) 3 member Profession NA Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc yes for civil Signed off celebrity theme Neo Industrial, Abstract Luxury, Japandi Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 2400000 Mention basic vastu principles agreed for integration in design, if any yes Design VisionEntrance Foyer must-haves yes decor Upload reference images Living key features and furniture must-haves minimal design Upload reference images Dining setup, table size and other furniture must -haves 6 seater ad tv storage Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves wardrobe and bed with storage Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves wardrobe and bed with storage Upload reference images Other space/ room (if any) must-haves study room Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves yes parallel Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves yes utlity space ad plants yes Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves yes Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves as per site Upload reference images Styling and Dcor must-haves wall decor and wall paining Space identified for signature design features and its specifics molding and trims Specify if design to reflect any personal story, cultural influence or special memory yes MiscellaneousTimeline related commitment made by Bonito to customer, if any: yes Other commitments made by Bonito to customer, if any: yes RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? yes Re-confirm the Move-in Date 2026-12-30 Re-confirm the Possession Date 2026-12-30 Any special occasion mentioned by customer wrt handover date no | 2026-04-28 13:03:19 +0530 | Priyanka Patel | DCM: 1. Name of the customer Lignetta Silveira 2. Profession NA 3. Project Name/Tower Name/Flat Number wadhwa the West 4. Typology (1BHK, 2BHK, 3BHK, etc) 3 bhk 5. Site Access Date 2026-04-28 6. Possession Date 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 1600000 Customer Preferences8. Who will be living in the house? Single, Couple, Joint Family, Elderly Members, Live-In Help 9. What activities do you usually prefer at your home ? Working From Home, Relaxing and Unwinding 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any NA 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) NA Upload reference images 14. Any absolute no-go styles colours or materials NO DARK COLOURS AND JAZZY DESIGN 15. Do you have any existing furniture that must be accommodated? NO 13. Do you want the design to reflect any personal story, cultural influence, or special memory NO ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Safety Door, Partition, Seating, Console, Shoe rack, Digital lock 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? TV Focus, Multipurpose 2. Must-have furniture or features? Sofa, Statement Wall/ Feature, Display unit , Bookshelves, Coffee table, Speakers, Home speakers, TV unit 3. Choose your decor inspirations Artwork, Travel souvenirs 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Bar Unit, Partitions, Crockery unit 2. Must-have appliances? Washing machine, Built-in Oven, Dishwasher, Chimney, Hob, Fridge, Microwave 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Study Table, TV unit, Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Dresser , Bookshelf , Study table 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Parents 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units TV Unit, Dresser 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? Utility, Storage 2. Outdoor Mood How do you intend to use the utility Storage Miscellaneous1. Timeline related commitment made by Bonito, if any NO 2. Other commitments made by Bonito to customer, if any NO 3. What are offers committed to customers? YES 4. Move-in date confirmed with customer 2026-11-06 5. Any special occasion mentioned by the customer wrt handover date NO 6. Additional Requirements (Mention any requirements from customer not covered in the form) NO 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 1500000 |  |  |  | 2026-05-12 |  | 2026-05-19
19640 | Turnkey | 2026-01-01 | Prakash Gharat | Runwal century | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  | Nilofer Shaikh | suraj kumar | Akshat Shrivastava | Murali S | vinaya thakur | Siddhesh Gujrathi | Active | Preproduction | Procurement | 1147686 | 724620 | 1575535 | 0 | 1146087 | 8 | 0 | 0 | 0 | 0 | 423066 |  |  | 2026-04-25 | 2026-04-25 18:54 | 2026-05-03 | 2026-05-03 13:58 | 2026-05-24 | 2026-05-24 20:41 | 2026-06-11 | 2026-06-11 17:21 | 2026-06-19 | 2026-06-18 11:42 | 2026-06-23 | 2026-06-23 18:34 | 2026-05-24 | 2026-05-24 20:45 | 2026-05-25 | 2026-05-24 21:23 | 2026-05-24 | 2026-05-25 12:35 | 2026-06-10 | 2026-06-10 13:22 |  |  |  |  | 2026-06-16 | 2026-06-13 13:11 | 2026-06-19 | 2026-06-19 20:17 | 2026-06-20 | 2026-06-19 20:17 |  |  | 2026-06-25 | 2026-06-29 18:15 | 2026-06-30 | 2026-06-30 15:51 | 2026-07-01 | 2026-06-30 18:47 | 2026-07-03 | 2026-07-04 14:39 |  |  |  |  | 2026-07-07 10:16 | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-07-01 | 2026-07-07 10:15 | 2026-06-11 | 2026-06-11 17:16 | Site is RTMI | 2026-04-25 | 2026-04-25 18:38 | 1337487 | 238048 | 0 | 0 | 1237013.0238 | 206295 | 1238929.6738 | 206583 | 2026-07-08 11:26:26 +0530 | suraj kumar | All POs are not released yet. | 2026-05-28 18:33:19 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-05-26 13:59:26 +0530 | Anjali Singh | CDP: dining table in cx scope , bench already provided. | 2026-06-16 | 2026-06-11 18:12 | 2026-06-19 | 2026-06-18 11:46
19641 | Turnkey | 2026-01-01 | Vinod Sharma | RUNWAL FOREST | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 1393898 | 9999 | 0 | 0 | 0 | 80 | 0 | 129391 | 139390 | 611640 | 503478.8 |  |  | 2026-04-25 | 2026-04-26 11:47 | 2026-04-25 | 2026-05-27 11:18 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-06-04 |  | 2026-06-12 |  | 2026-06-13 |  |  |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-06-21 |  | 2026-05-30 |  | Unknown | 2026-04-25 | 2026-04-25 18:39 | 0 | 0 | 0 | 0 | 0 | 0 | 1184071 | 209827 | 2026-04-28 17:50:26 +0530 | Vandana Preet | Some Image was uploaded | 2026-04-26 14:00:44 +0530 | Vandana Preet | Handed over the receipt to Vartika, on 25th April |  |  |  | 2026-06-04 |  | 2026-06-11
19642 | Turnkey | 2026-01-01 | Kunal Shah | Birla Tisya | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | [7 empty] | Active | Design | DEM1 | 911750 | 117999 | 1179212 | 0 | 0 | 56 | 0 | 0 | 64351 | 377464 | 351936 |  |  | 2026-04-26 | 2026-05-04 15:29 | 2026-04-25 | 2026-05-04 15:41 | 2026-05-07 | 2026-05-04 17:56 | 2026-07-12 |  | 2027-03-24 |  | 2027-03-31 |  | 2026-05-04 | 2026-05-11 12:09 | 2026-05-05 | 2026-05-13 13:19 | 2026-05-13 | 2026-05-20 11:59 | 2026-05-26 | 2026-05-26 11:51 |  |  |  |  | 2026-07-13 |  | 2027-03-26 |  | 2027-03-27 |  |  |  | 2027-04-03 |  | 2027-04-04 |  | 2027-04-05 |  | 2027-04-06 | [6 empty] | 2027-04-24 |  | 2027-05-03 |  | 2027-05-02 |  | 2027-05-03 |  | 2027-05-04 |  | 2027-05-06 |  |  |  | 2027-05-28 |  | 2027-05-30 |  | 2027-05-31 | [5 empty] | 2027-04-04 |  | 2026-05-27 |  | Site is Non-RTMI | 2026-04-26 | 2026-05-04 15:08 | 999332 | 179879 | 0 | 0 | 0 | 0 | 990113.73 | 163487 | 2026-07-12 19:13:43 +0530 | Rajeshwari S | Client not confirming on the meeting he wants to make the 10% payment once the 1st meeting is done. | 2026-05-26 13:17:13 +0530 | Shivani Shet | CDP: Surabhi's team KT.xlsx | 2026-05-26 12:46:55 +0530 | Rhea Rathod | CDP: Pre-lam Foyer - -Bottom cabinets -Metal fabrication with fluted glass Tv unit- -Loose pooja unit (Not considered in the quote) -TV unit -Charcoal beadings -(False ceiling removed) Dining area- -Crockery unit -Pop punning Kitchen - -Loft on one side -Base cabinets (One cabinet under the hob needs to be added) -Tall unit, Wall units Utility - -Wall unit Master bedroom- -Wardrobe with loft (2) -Mirror -The client needs a Dresser unit which needs to be added Kids bedroom- -Wardrobe with loft -Study unit (The study unit can be combined with dresser unit - needs to be space planned as per initial measurements) -Metal fabrication Bedroom 3- -Initially a storeroom was created which was later removed. -The client needs extra storage in the utility instead of the bedroom- which needs to be planned as per the space available (the clients arent sure, hence the open wardrobe for the storeroom was removed) -Study unit added, with metal fabrication Washrooms- -Vanities added in the washrooms | 2026-07-13 |  | 2027-03-25 |  | Under Construction | 2026-12-01
19644 | Turnkey | 2026-01-01 | Govindrajan | Builder floor | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Hold | Preproduction | DEM2 | 912548 | 199999 | 1159932 | 0 | 0 | 38 | 3 | 0 | 0 | 350776 | 361772.8 |  |  | 2026-04-25 | 2026-04-25 19:15 | 2026-04-29 | 2026-04-29 15:47 | 2026-05-06 | 2026-05-06 12:39 | 2026-06-05 | 2026-06-04 11:22 | 2026-12-16 |  | 2026-12-23 |  | 2026-05-06 | 2026-04-30 | 2026-05-07 | 2026-05-06 13:39 | 2026-05-06 | 2026-05-07 16:33 | 2026-05-08 | 2026-05-08 18:01 |  |  |  |  | 2026-05-11 | 2026-04-30 19:12 | 2026-12-18 |  | 2026-12-19 |  |  |  | 2026-12-26 |  | 2026-12-27 |  | 2026-12-28 |  | 2026-12-29 | [6 empty] | 2027-01-16 |  | 2027-01-25 |  | 2027-01-24 |  | 2027-01-25 |  | 2027-01-26 |  | 2027-01-28 |  |  |  | 2027-02-19 |  | 2027-02-21 |  | 2027-02-22 | [5 empty] | 2026-12-27 |  | 2026-05-09 | 2026-06-04 11:21 | Site is RTMI | 2026-04-25 | 2026-04-25 19:01 | 982993 | 176938 | 0 | 0 | 0 | 0 | 943749.07 | 164258 | 2026-06-24 17:42:41 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 03-06-2026 Attendees: Client and Designer Discussion: DEM 1 Based on 03-06-2026 meeting, below is a list of all the requirements that were discussed during the meeting: Tv Unit size has been changed to 7 feetTv size - 65inchestv back has to be with curved design wallpaper designTV point shifting has to check from the builderPooja unit Cx scope- 3x4Sofa wall design has to match with TV wall designpooja wall has to be with contrast colourFalse ceiling has to be consider - island ceilingentrance panel has to be placedcrockery and study table placement has to done as per space availabilityvanity unit placement has to be given option4 seater dining tablekitchen breakfast counter with top panel and drop lightkitchen has to be re design as per the initial measurementutility has ta plan for janitor unit and storageKBR- dresser pullout has to addedstudy table with pencil drawerMBR has to be plan as discussed | 2026-05-12 11:30:38 +0530 | Ehthisham Durgam | CDP: Living room Color changes back door design might get removed puja is client scope Dining color changes add breakfast counter wall panel (Lshape)granite client scope Kitchen color changes Kids room color changes wall pattern might change Master Bedroom Color changes back wall design might change Recording - Recap: Meeting with Ehthisham Durgam Tuesday, April 28 ¦ Meeting ¦ Microsoft Teams | 2026-05-08 17:45:28 +0530 | Parasa Sri | Welcome call done. Agreement with builders regarding registration by June. The site is ready for initial measurement. | 2026-06-05 | 2026-06-04 11:22 | 2026-12-17 |  | Under Construction | 2026-06-03
19645 | Turnkey | 2026-01-01 | Uma Bhagavatula | Sarang By Sumadhura | BNG - HSR | Yes | Sreenivasulu Reddy | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Design | DEM1 | 2491555 | 338566 | 3323743 | 0 | 0 | 22 | 0 | 0 | 159745 | 996622 | 996622 |  |  | 2026-04-25 | 2026-04-28 11:26 | 2026-05-24 | 2026-06-04 12:52 | 2026-06-07 | 2026-06-09 11:37 | 2026-07-24 |  | 2026-12-15 |  | 2026-12-22 |  | 2026-06-09 | 2026-06-09 12:34 | 2026-06-10 | 2026-06-13 18:25 | 2026-06-13 | 2026-06-23 15:48 | 2026-06-30 | 2026-06-30 20:50 |  |  |  |  | 2026-07-25 |  | 2026-12-17 |  | 2026-12-18 |  |  |  | 2026-12-25 |  | 2026-12-26 |  | 2026-12-27 |  | 2026-12-28 | [6 empty] | 2027-01-15 |  | 2027-01-24 |  | 2027-01-23 |  | 2027-01-24 |  | 2027-01-25 |  | 2027-01-27 |  |  |  | 2027-02-18 |  | 2027-02-20 |  | 2027-02-21 | [5 empty] | 2026-12-26 |  | 2026-07-20 |  | Unknown | 2026-04-25 | 2026-04-25 19:15 | 2816731 | 507011 | 0 | 0 | 0 | 0 | 2763614.132 | 456338 | 2026-06-23 15:48:34 +0530 | Bency Chacko |  | 2026-06-23 15:43:32 +0530 | Pulivarthi Nirosha | Some Image was uploaded | 2026-06-22 17:13:35 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: December 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 120 + 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible * DEM 1 2nd week of July 2026 * 10% Payment Stage after 1st DEM *Transaction will be B2C self-funding. *No civil work Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 27,63,615 Offers Discussed During the Call: Special offer (100000) Laminate Upgrade - Windows to Wonderful home Design fee waiver (5%) PM fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Silver Coin 21g Final Closing Value Discussed: 24,91,556 Checklist termsdescoping, delay compensation are clear agreement terms not clear Rejections: She mentioned that the GST waiver was promised, and she paid the 10%the promised offer was not applied.Client wants to visit the factory at the time of production to check if the same material is being used (which is added by her in the quote). She mentioned this request as she read negative reviews online.She requested contact details of previous happy customers so she can speak with them and validate herself about Bonito's quality of work.She mentioned that it was explained to her until possession of all the designs is closed, and once she gets possession, the material will be sent to production. Process states OB call> DEM 1> 10%> Hold > Site validation> DEM 2> CM> DEM 3> PKO approval> 40%> production> 40%> dispatch> execution> Handover | 2026-07-25 |  | 2026-12-16 |  | Under Construction | 2026-12-31 | 2026-06-07 | 338566 | Ravi Roy
19647 | Turnkey | 2026-01-01 | Vishal Raigala | * | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 3516338 | 9999 | 0 | 0 | 0 | 78 | 0 | 341635 | 351634 | 1441044 | 1372026.4 |  |  | 2026-04-25 | 2026-04-28 12:01 | 2026-04-25 |  | 2026-05-02 |  | 2026-05-05 |  | 2026-05-12 |  | 2026-05-19 |  | 2026-04-28 |  | 2026-04-29 |  | 2026-04-29 |  | 2026-04-30 | [5 empty] | 2026-05-06 |  | 2026-05-14 |  | 2026-05-15 |  |  |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-25 | [6 empty] | 2026-06-12 |  | 2026-06-21 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-24 |  |  |  | 2026-07-16 |  | 2026-07-18 |  | 2026-07-19 | [5 empty] | 2026-05-23 |  | 2026-05-01 |  | Unknown | 2026-04-25 | 2026-04-28 12:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2979948 | 536390 | 2026-05-07 16:30:02 +0530 | Ishan Patle | CDP Quote: 39L ¦ CX Budget: 20L. Client is CFO at Raymond Realty . Proper pre-preparation was done before client visit, and client also acknowledged the same during discussion. To align closer to client budget, multiple items/scopes were descoped and value engineering options were discussed. However, client remained stuck on the budget expectations. In the last discussion, client requested 23 days time to evaluate and confirm further. Post that, client has not been responding to calls or messages. Client already had another end-to-end quotation of approx. 18L, however designer had clearly explained the material and scope difference comparison during the discussion. | 2026-05-07 14:05:56 +0530 | Moksh Mehta | Some Image was uploaded |  |  |  | 2026-05-06 |  | 2026-05-13
19648 | Turnkey | 2026-01-01 | Suverna Bhoir | Arun kamal | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 2417336 | 9999 | 0 | 0 | 0 | 22 | 0 | 231735 | 241734 | 1028578 | 905291.2 |  |  | 2026-04-25 | 2026-06-18 14:50 | 2026-05-31 | 2026-06-18 18:33 | 2026-06-21 |  | 2026-06-29 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-15 |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-04-25 | 2026-05-05 15:47 | 0 | 0 | 0 | 0 | 0 | 0 | 2048589 | 368746 | 2026-06-23 17:40:33 +0530 | Priyanka Patel | CDP: Project Name/Tower Name/Flat Number Arun kamal Typology 3bhk Site Access Date 2027-03-31 Possession Date 2027-03-31 Customer ProfileFamily members (no. & age) 4 member Profession bussiness Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc yes Signed off celebrity theme Abstract Luxury Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 300000 Mention basic vastu principles agreed for integration in design, if any Design VisionEntrance Foyer must-haves yes Upload reference images Living key features and furniture must-haves yes with decor Upload reference images Dining setup, table size and other furniture must -haves yes Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves yes with storage Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves yes with storage Upload reference images Other space/ room (if any) must-haves yes with storage Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves yes with storage and appliances Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves yes Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves yes Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves on site Upload reference images Styling and Dcor must-haves Space identified for signature design features and its specifics Specify if design to reflect any personal story, cultural influence or special memory MiscellaneousTimeline related commitment made by Bonito to customer, if any: yes Other commitments made by Bonito to customer, if any: yes RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? yes Re-confirm the Move-in Date 2027-03-31 Re-confirm the Possession Date Any special occasion mentioned by customer wrt handover date no | 2026-06-23 17:36:29 +0530 | Priyanka Patel | Some Image was uploaded | 2026-06-16 13:58:49 +0530 | Priyanka Patel | DCM: 1. Name of the customer 19648 - Suverna Bhoir 2. Profession NA 3. Project Name/Tower Name/Flat Number Arun kamal 4. Typology (1BHK, 2BHK, 3BHK, etc) 3BHK 5. Site Access Date 2026-11-30 6. Possession Date 2026-11-30 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 2500000 Customer Preferences8. Who will be living in the house? Elderly Members, Joint Family, Nuclear Family, Couple 9. What activities do you usually prefer at your home ? Prayer, Pursuing Hobbies, Relaxing and Unwinding, Family Bonding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] yes 11. Mention basic vastu principles agreed for integration in design, if any yes 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials no dark colours 15. Do you have any existing furniture that must be accommodated? no 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Console, Seating, Partition, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests, Multipurpose 2. Must-have furniture or features? TV unit, Home speakers, Speakers, Coffee table, Bookshelves, Puja unit, Display unit , Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Artwork 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Dishwasher 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Guest 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Study table , Bookshelf , Dresser , TV unit 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility Guests 16. Bedroom 3 - Bed Type Storage 17. Bedroom 3 - Wardrobe Style Swing 18. Bedroom 3 - Additional Units Study Table, Bookshelf, Dresser, TV Unit 19. False Ceiling Required - Bedroom 3 Yes Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Bottom Storage, Laundry space, Washing machine space, Dryer Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any yes 2. Other commitments made by Bonito to customer, if any yes 3. What are offers committed to customers? yes 4. Move-in date confirmed with customer 2027-01-31 5. Any special occasion mentioned by the customer wrt handover date no 6. Additional Requirements (Mention any requirements from customer not covered in the form) no 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 2000000 | 2026-06-30 |  | 2026-07-06
19650 | Turnkey | 2026-01-01 | Bhagyesh Joshi | Regency Luxeria | MUM - Thane | Yes | Bhawaya Goyal | Anamika Dolai | Rushika More | [5 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 1580176 | 9999 | 1580176 | 0 | 0 | 66 | 0 | 148019 | 158018 | 642119 | 622022 |  |  | 2026-04-25 | 2026-04-25 21:18 | 2026-05-06 | 2026-05-06 13:53 | 2026-05-10 | 2026-05-11 13:26 | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-04-25 | 2026-04-25 21:17 | 1339132 | 241043 | 0 | 0 | 0 | 0 | 1339132 | 241043 | 2026-05-07 11:24:17 +0530 | Krutika Vernekar | DCM: Client Details Client Name: Bhagyesh Joshi Project: Regency Luxuria (Ruby) Area: 833 sq ft Language: Hindi Planned Budget : 12 L Approx Budget: 15L - 16 L suggested Timeline Mentioned: Possession around JulyJuly (site not ready yet) Space Planning Entrance / Living : Entry planning Shoe rack: 3 Safety door 6-seater dining L-shape sofa (2+1) Wall art behind sofa wall Wall lamps False ceiling : Peripheral false ceiling Kitchen : Provision for MNGL Gas unit Base + overhead + loft storage Loft extension Double-door refrigerator space Microwave unit + mixer + grinder space Passage Bar unit in passage Bedroom Planning Parents + Daughter Room Queen bed + bunk bed Daughter age: approx. 4 years Folding study table Mirror + dresser TV in kids room Masteroom : WFH Requirement Work-from-home setup needed TV in master bedroom | 2026-05-06 13:50:09 +0530 | Krutika Vernekar | DCM: Â 2BHK (840 sq ft) Quick Plan Entrance Safety door: simple modern designShoe rack outside Living Linear sofa + floating TV unitKeep center open Dining 6-seater (existing) Mandir As per direction Kitchen parallel layoutUse chajja for sink/plantsTall pantry Passage storage Master Bedroom Bed + wardrobeDresserSmall study near window Kids Room Bed + wardrobeKeep flexible (guest + future kid) StyleModern minimal + warmLight colors + wood + mirrors | 2026-05-06 13:12:18 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-05-19 |  | 2026-05-26
19651 | Turnkey | 2026-01-01 | Krishnamurti kulkarni | Birla tisya | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Hold | Preproduction | DEM2 | 783054 | 159999 | 919526 | 0 | 0 | 24 | 4 | 0 | 0 | 326282 | 296773.2 |  |  | 2026-04-25 | 2026-05-06 12:05 | 2026-05-06 | 2026-05-06 13:51 | 2026-05-09 | 2026-05-15 12:20 | 2026-06-14 | 2026-06-14 15:02 | 2026-08-02 |  | 2026-08-09 |  | 2026-05-15 | 2026-05-29 11:33 | 2026-05-16 | 2026-05-29 11:47 | 2026-05-29 | 2026-05-29 19:35 | 2026-06-09 | 2026-06-09 11:08 |  |  |  |  | 2026-06-14 | 2026-06-17 10:45 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-06-10 | 2026-06-14 11:06 | Site is RTMI | 2026-04-25 | 2026-04-27 18:18 | 781316 | 138210 | 0 | 0 | 0 | 0 | 846009.0295 | 138523 | 2026-05-31 21:22:50 +0530 | Priyanka Gs | Some Image was uploaded | 2026-05-31 21:19:18 +0530 | Priyanka Gs | Some Image was uploaded | 2026-05-29 19:35:03 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: 1st week of July 2026 Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Client has taken the approval for the IMs and that is done last Saturday itself (as the client was there in Bangalore for 1 week and he had taken special permission for measurements) * DEM 1 on 8th June 2026 virtually, as the client is not in Bangalore * 10% Payment Stage 13th June 2026 Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 8,46,010 Offers Discussed During the Call: Silver Coin 21g Free Hob & Chimney Offer Design fee waiver (5%) Laminate Upgrade - May '26 Campaign 100% GST Waiver PM Fee Waiver (4%) Final Closing Value Discussed: 7,83,055 Checklist terms - descoping, delay compensation, agreement terms are clear Extra commitments : nothing Note : Typology of the project is 2BHK | 2026-06-15 | 2026-06-14 17:20 | 2026-08-03 |  | Under Construction | 2026-07-04
19652 | Turnkey | 2026-01-01 | Sumitra Banerjee | Purvankara | MUM - Thane | Yes | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | DCM Due | 2444354 | 9999 | 0 | 0 | 0 | 77 | 0 | 234436 | 244435 | 1062866 | 892616.8 |  |  | 2026-04-25 | 2026-04-29 11:51 | 2026-06-16 | 2026-06-16 18:21 | 2026-06-25 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-04-25 | 2026-04-27 18:21 | 0 | 0 | 0 | 0 | 0 | 0 | 2071487 | 372867 | 2026-05-22 17:37:40 +0530 | Mansi Deshmukh | DCM: DCM: SUMITRA BANERJEE - 19652NOTES LIVING ROOMSHOERACK 4 SEATER DINING TABLE L SHAPE SOFA OR 3 SEATER SOFA + CHAIR TV UNIT WITH DISPLAY KITCHENU SHAPE KITCHEN BASE UNIT WALL UNIT LOFT UNIT APPLIANCES UNIT MICROWAVE DISHWAHER FRIDGE WASHING MACHINE HOB ON WINDOW SIDE COMMON + STUDY ROOMQUEEN SIZE BED WARDROBE SIDE TABLE STUDY TABLE DAUGHTER'S ROOMWARDROBE DRESSING UNIT SIDE TABLE BED MASTER BEDROOMDOUBLE BED (3'X 6') SIDE TABLE WARDROBE IN NICHE EXTRA WARDROBE + TV UNIT DRESSING BATHROOMVANITY UNIT BUDGET 20 LAKH | 2026-05-22 17:14:03 +0530 | Mansi Deshmukh | DCM: SUMITRA BANERJEE - 19652 NOTES LIVING ROOM SHOERACK 4 SEATER DINING TABLE L SHAPE SOFA OR 3 SEATER SOFA + CHAIR TV UNIT WITH DISPLAY KITCHEN U SHAPE KITCHEN FRIDGE DISHWAHER WASHING MACHINE HOB ON WINDOW SIDE COMMON + STUDY ROOM QUEEN SIZE BED WARDROBE SIDE TABLE STUDY TABLE DAUGHTER'S ROOM WARDROBE DRESSING UNIT SIDE TABLE BED MASTER BEDROOM DOUBLE BED (3'X 6') SIDE TABLE WARDROBE IN NICHE EXTRA WARDROBE + TV UNIT DRESSING BATHROOM VANITY UNIT BUDGET 20 LAKH |  |  |  | 2026-06-27 |  | 2026-07-04
19654 | Turnkey | 2026-01-01 | Shampa Mukherjee & Pritam Mukherjee | Shriram WYTfield | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | 20% Payment | 1540374 | 203866 | 2030962 | 0 | 0 | 3 | 0 | 0 | 104209 | 631369 | 600930 |  |  | 2026-04-25 | 2026-05-06 12:48 | 2026-05-07 | 2026-05-07 14:21 | 2026-05-10 | 2026-05-15 11:24 | 2026-07-11 | 2026-07-11 14:25 | 2026-09-01 |  | 2026-09-08 |  | 2026-05-15 | 2026-05-31 20:48 | 2026-05-16 | 2026-06-05 11:55 | 2026-06-05 | 2026-06-08 15:49 | 2026-06-09 | 2026-06-09 18:57 |  |  |  |  | 2026-07-12 |  | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-06-10 | 2026-06-19 19:24 | Site is RTMI | 2026-04-25 | 2026-04-25 22:07 | 1721154 | 309807 | 0 | 0 | 0 | 0 | 1690077.8088 | 279067 | 2026-06-08 15:46:45 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: 15 June 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM 13th June 2026 * DEM 1 Client will check with his family and then let us know * 10% Payment Stage by 18th June 2026 (after 1st DEM) *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 16,90,078 Offers Discussed During the Call: Special Offer (10000) 100% GST Waiver PM fee waiver (5%) Design fee waiver (5%) Laminate Upgrade - May '26 Campaign Silver Coin 21g Final Closing Value Discussed: 15,40,374 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-08 14:15:50 +0530 | Sanjana Swami |  | 2026-06-04 19:29:06 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-07-12 | 2026-07-12 17:20 | 2026-09-02 |  | Under Construction | 2026-06-15
19655 | Turnkey | 2026-01-01 | Sonali Ganguly | L&T powai | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 1780934 | 356187 | 2258886 | 0 | 0 | 29 | 20 | 0 | 0 | 788872 | 635875.2 |  |  | 2026-04-25 | 2026-04-27 14:42 | 2026-04-28 | 2026-04-28 13:13 | 2026-05-01 | 2026-04-30 10:55 | 2026-05-24 | 2026-05-24 18:51 | 2026-06-16 |  | 2026-06-23 |  | 2026-05-01 | 2026-04-28 19:16 | 2026-05-02 | 2026-04-29 11:54 | 2026-05-02 | 2026-04-29 12:53 | 2026-05-09 | 2026-05-09 15:49 |  |  |  |  | 2026-05-24 | 2026-06-09 18:01 | 2026-06-18 |  | 2026-06-19 |  |  |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-29 | [6 empty] | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-06-27 |  | 2026-05-10 | 2026-05-24 18:10 | Site is RTMI | 2026-04-25 | 2026-04-26 17:19 | 1917112 | 341774 | 0 | 0 | 0 | 0 | 1893263.2179 | 318442 | 2026-06-09 12:03:00 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-06 15:20:52 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-24 16:59:14 +0530 | Reshma Melanta | 24th MAY 2026 DEM - 1 MEETING ALIGN IN ANDHERI EC | 2026-05-25 | 2026-05-24 19:02 | 2026-06-17 |  | Under Construction | 2026-05-15
19656 | Turnkey | 2026-01-01 | Mr. Swapnil Shivshankar Giri | Arista | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Nilesh Patel | Rizwan Mistry |  | Rashmita Das | Aakash Gaikwad | Active | Preproduction | Site Readiness 2 | 1158531 | 722956 | 1422005 | 0 | 1158531 | 2 | 0 | 0 | 0 | 0 | 435575 |  |  | 2026-04-26 | 2026-05-14 14:20 | 2026-05-13 | 2026-05-28 18:56 | 2026-05-31 | 2026-05-28 19:17 | 2026-06-15 | 2026-06-11 13:40 | 2026-06-21 | 2026-06-20 14:07 | 2026-06-26 | 2026-06-24 20:54 | 2026-05-28 | 2026-05-30 18:25 | 2026-05-29 | 2026-06-02 18:20 | 2026-06-02 | 2026-06-04 16:29 | 2026-06-05 | 2026-06-05 14:31 |  |  |  |  | 2026-06-12 | 2026-06-15 18:06 | 2026-06-21 | 2026-06-21 21:09 | 2026-06-22 | 2026-06-21 21:09 |  |  | 2026-06-27 | 2026-07-11 11:47 | 2026-07-11 | 2026-07-12 11:55 | 2026-07-13 | 2026-07-12 20:48 | 2026-07-22 | 2026-07-13 17:22 | [5 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-12 |  | 2026-06-06 | 2026-06-11 12:54 | Site is RTMI | 2026-04-26 | 2026-04-26 12:33 | 1205089 | 216916 | 0 | 0 | 1356475.6941 | 208535 | 1356475.6941 | 208535 | 2026-07-07 13:52:37 +0530 | Viraj Chavan | 3DQA | 2026-07-02 18:52:50 +0530 | Viraj Chavan | HOTO: | 2026-06-26 21:43:19 +0530 | Viraj Chavan | Some Image was uploaded | 2026-06-12 | 2026-06-12 12:46 | 2026-06-21 | 2026-06-20 15:39 | RTMI
19657 | Turnkey | 2026-01-01 | Vinod Venugopal | SBR Earth & Sky | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 1606261 | 9999 | 0 | 0 | 0 | 62 | 0 | 150627 | 160626 | 653034 | 631975.2 |  |  | 2026-04-26 | 2026-04-26 13:10 | 2026-05-06 | 2026-05-12 19:16 | 2026-05-14 |  | 2026-05-21 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-15 |  | 2026-05-16 | [5 empty] | 2026-05-22 |  | 2026-05-30 |  | 2026-05-31 |  |  |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 | [6 empty] | 2026-06-28 |  | 2026-07-07 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-08 |  | 2026-05-17 |  | Unknown | 2026-04-26 | 2026-04-26 12:55 | 0 | 0 | 0 | 0 | 0 | 0 | 1361238 | 245022 | 2026-05-06 18:58:01 +0530 | Yogesh Patidar | Please find the MOM for the RGM meeting(6th May) Customer -Mr and Mrs. Venugopal Customer Profile- Works in TCS and SAP Budget- 15L ( Including Loose Furniture) Family of 4 includes a Kid( 11Yrs) Possession -June - Aug Existing furniture: Wardrobe -6.5h* 7W 1 Signe BedÂ Theme- Indian Tradition (To look very Spacious and Uncluttered) Entrance- (Shoe Rack-Wall mounter in Balcony area) Living area- Front wall to be highlighted Understairs- Reading Corner, bookshelf, storage. Staircase wall to be highlighted with Texture Paint Sofa Placement 3+2Â with Pouffe Powder Room to be converted to Pooja Room ( No Sanitary Fitted) Base unit (Floating unit with North East Direction), Pullout tray, Back wall design, Pooja Door with Glass. LightingÂ GF-1 Bedroom: Existing Wardrobe with Additional loft storage Existing Single bed ( Collapsible Partition to be given to segregate Bathroom and Balcony) Vanity in Bathroom Kitchen: Color Shade ( Light Shade) Countertop Quartz No wall partition and Duct in Corner Appliances- Dishwasher, Washing Machine, Fridge -Double Door, Hob, No Chimney, Tiles till Top Maximum Storage with base unit, Loft, Wall unit with some glass shutter, pantry unit sleek. Wall unit on Duct space Space for Mixi, Grinder 1st Floor- Family Area: Tv with Base unit -75inch, Sound bar,Â Foldable study ledge Seating space-(Includes Recliner, Bean Bag, Poufee) Master Bedroom: Low Height Bed, Walk in wardrobe, foldable work station, Pullout Mechanism for Hanger, Mirror on wardrobe, Vanity Kids Room- Murphy Bed, Mirror on wall on Full wall(For Dance Purpose), Study Unit(Foldable) Bookshelf with Tall unit Sliding wardrobe | [6 empty] | 2026-05-22 |  | 2026-05-29
19658 | Turnkey | 2026-01-01 | Renuka Chordiya | DLF | BNG - HSR | No Estimate | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-25 | 2026-05-06 12:49 | 2026-05-13 |  | 2026-05-15 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-04-25 | 2026-05-06 12:48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-13 13:54:07 +0530 | Nidhi Shaw | Budget Centric-10-12 Lakhs (I told it may stretch a bit to 13-14 for standard 3 bhk) Had a thought that Bonito is expensive as per market research. Rahul Gupta is his boss. They paid 9999 after talking to him. | 2026-04-26 12:54:26 +0530 | Unknown | About the Customer **Customer Visit Confirmation and Appointment Booking** The customer, Renuka, has confirmed her intention to visit the Bonito Designs HSR experience center on Saturday afternoon, tentatively before 3 PM, for an interior design consultation. An appointment has been tentatively booked for Saturday from 2 to 4 PM, and she has agreed to share her floor plan via WhatsApp. The initial consultation is free of charge. **Customer Needs and Concerns** Renuka is seeking interior design services for her 3 BHK apartment in DLF Woodland Height, Bangalore, with a budget of 7 to 10 lakhs. Her primary concerns include comparing quotes, ensuring good quality materials (like HDMR and Green Ply woods), and timely project delivery. She is particularly interested in unique TV unit designs and wants to avoid excessive follow-ups. **Customer Engagement History** The customer initially inquired about interior design services and experience center locations. Following up on this, agent Preeti from Bonito Designs provided information on offerings, discounts, and warranty details. Renuka expressed interest but needed time to compare and requested information via WhatsApp, eventually confirming a visit for Saturday. **Family Participation and Agent Commitment** Renuka confirmed that her family of four will be attending the visit. Agent Preeti assured her of her presence at the experience center and committed to sending the location details via WhatsApp, along with a personalized invitation. **Recommended Follow-up Actions** The next step is for Renuka and her family to attend the scheduled visit at the HSR experience center on Saturday between 2-4 PM. The agent should ensure all promised information is sent via WhatsApp and be prepared to address Renuka's concerns about quality and timely delivery during the visit. |  |  |  | 2026-05-24 |  | 2026-05-31
19659 | Turnkey | 2026-01-01 | bhaumik Shah | Ruparel Panache | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Sanskruti Yadav |  | Lost | Design | DEM1 | 2287743 | 283959 | 2839593 | 0 | 0 | 40 | 21 | 0 | 173590 | 962276 | 867918.4 |  |  | 2026-04-26 | 2026-04-28 12:21 | 2026-05-03 | 2026-05-11 14:10 | 2026-05-14 | 2026-05-12 14:52 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-05-10 | 2026-05-11 13:51 | 2026-05-13 | 2026-05-12 14:57 | 2026-05-12 | 2026-05-15 14:28 | 2026-05-26 | 2026-05-26 16:47 |  |  |  |  | 2026-06-20 |  | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-06-15 |  | Unknown | 2026-04-26 | 2026-04-26 13:56 | 2406434 | 433158 | 0 | 0 | 0 | 0 | 2375970.9108 | 409994 | 2026-06-05 12:05:39 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-26 16:46:16 +0530 | Reshma Melanta | CX IS ASKING FOR A REFUND HAVE SEND A MAIL ALREADY FOR TE SAME | 2026-05-23 20:14:17 +0530 | Priyanka Murarka | Some Image was uploaded | 2026-06-20 |  | 2026-06-27 |  | Under Construction | 2026-06-15
19660 | Turnkey | 2026-01-01 | FUZEL MUSARATALI KHAN | Lodha Suprimo | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 1097399 | 39999 | 1344123 | 0 | 0 | 70 | 0 | 69741 | 109740 | 455880 | 422039.2 |  |  | 2026-04-26 | 2026-05-05 15:29 | 2026-05-03 | 2026-05-06 23:24 | 2026-05-07 | 2026-05-06 23:34 | 2026-05-13 |  | 2026-05-20 |  | 2026-05-27 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-05-14 |  | 2026-05-22 |  | 2026-05-23 |  |  |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 | [6 empty] | 2026-06-20 |  | 2026-06-29 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-02 |  |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-31 |  | 2026-05-09 |  | Unknown | 2026-04-26 | 2026-04-26 14:22 | 1139087 | 205035 | 0 | 0 | 0 | 0 | 1136029.837 | 191806 | 2026-04-26 20:10:43 +0530 | Rishika Malviya | Some Image was uploaded | [6 empty] | 2026-05-14 |  | 2026-05-21
19661 | Turnkey | 2026-01-01 | Prashant More | Adani - The Views | MUM - Thane | Yes | [8 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 3420102 | 9999 | 0 | 0 | 0 | 61 | 0 | 332011 | 342010 | 1392574 | 1343507.6 |  |  | 2026-04-26 | 2026-04-26 14:11 | 2026-05-01 | 2026-05-07 15:15 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-04-26 | 2026-04-26 14:10 | 0 | 0 | 0 | 0 | 0 | 0 | 2898392 | 521710 | 2026-05-14 17:13:38 +0530 | Rinisha Masurkar | Some Image was uploaded | 2026-05-13 19:46:55 +0530 | Pooja Nakul Sharma | DCM: 19661 - Prashant MoreÂ 9 family members, 4 kidsÂ 2 + 2 jodi partment aprox 1587sqft area 05 unitÂ open kitchen concept with breakfast counterÂ crockery spaceÂ suficient storageÂ 1 option without including the common washroomÂ double door fridge placementÂ entrance door of unit 05 will be closedÂ 1 option including the common washroom in the kitchen with island kitchen platformÂ 9 seater dining placementÂ center wall will be removed mbr in unit 05 will be daughters and grandmothers roomÂ tv placementÂ study in the daughters roomÂ common room in unit 05 will be boys room sofa cum bed and wardrobe placementÂ study if possibleÂ 04 unit L shape shoe rack in the entrance full height Shivaji maharaj frame in niche storage in the bottomÂ tv unit with closed and open storageÂ tv back wall will be extendedÂ Nitin sir's room door will be taken outÂ storage in the entranceÂ bed will on the entrance wallÂ tv on the opp sideÂ wardrobe on the entrance wall 04 unit kitchen will be converted into mandir and study room sliding doorÂ indian seating on opp wall Dumy wall to be planned on the entrance of prashant sir's room next to the nicheÂ wardrobe on the entrance wall tv unit to be plannedÂ king size bedÂ budget - 35-40LÂ overall budget including civil is 50LÂ Civil in cx scope. | 2026-04-28 13:46:17 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-05-24 |  | 2026-05-31
19663 | Turnkey | 2026-01-01 | Nihar | Adarsh Park Height | BNG - HSR | Yes | Shefali | Akshay Ds | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Hold | Preproduction | DEM2 | 1551277 | 310255 | 2171905 | 0 | 0 | 16 | 22 | 0 | 0 | 620511 | 620510.8 |  |  | 2026-04-26 | 2026-04-26 15:39 | 2026-04-28 | 2026-05-05 10:58 | 2026-05-08 | 2026-05-05 16:29 | 2026-06-08 | 2026-06-07 12:22 | 2026-08-17 |  | 2026-08-24 |  | 2026-05-05 | 2026-05-14 18:20 | 2026-05-06 | 2026-05-19 15:32 | 2026-05-19 | 2026-05-21 11:28 | 2026-05-25 | 2026-05-25 18:04 |  |  |  |  | 2026-05-31 | 2026-06-06 13:03 | 2026-08-19 |  | 2026-08-20 |  |  |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 | [6 empty] | 2026-09-17 |  | 2026-09-26 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-29 |  |  |  | 2026-10-21 |  | 2026-10-23 |  | 2026-10-24 | [5 empty] | 2026-08-28 |  | 2026-05-26 | 2026-06-07 11:57 | Site is RTMI | 2026-04-26 | 2026-04-26 15:38 | 1840597 | 331307 | 0 | 0 | 0 | 0 | 1848790.4598 | 305279 | 2026-06-28 14:46:39 +0530 | Preethi Shetty | Initial Design Discussion has been scheduled today with client, Ihave shared the MOM, kids' bedroom & guest bedroom needs to be discussed yet! site is not yet ready for initial measurements, once we receive initial measurements we need to the dimensions for kitchen, utility area. | 2026-06-28 14:40:03 +0530 | Preethi Shetty | NiharÂ 28/06/2026 Foyer -Â Punning not req. as dust accumulates Trims with photo frames Foyer wall- trims with paint / wallpaper Living- Sofa Wall - Trims with wallpaper / paint - wall lightsÂ 3+2 recliner sofa (off white shade) TV Unit - 2 draws + 1 flap down with glass shutter + Tall unit (need to leave 150mm gap for curtains) TV Back panel - Louvers + back panel overlapping on louvers as per ref. Need to check space for laptops storage (not preferred to have in bedrooms) Dining-Â Pooja Unit on kitchen entrance , need to check as per site measurements Breakfast counter on holdÂ Crockery unit - bottom cabinets solid shutters, top cabinets with clear glass to display kettles Tall unit descoped Kitchen- wall cabinets beside window RO unit provision is given, need to provide RO unit a ledge to place the pot in the corner below RO unitÂ near Utility door in kitchen need to provide a storage for 3ft with 8-10 inches as per site conditions acc. to that breakfast counter to be given with storage below Utility -Â 2 Cylinder, dishwasher, Washing machine top load, janitor storage, one sink unitÂ counter ht 85cm MBR -Â Lshape wardrobe , dresser mirror to be checked, south wall mirror not suggested Bay window seating - loose storageÂ Foldable study ledge with wall ledgesÂ GBR -Â Study - one ledge with open unitÂ beside wardrobe add one storage for suitcase & bags 2ft or 2.5ft width Need storage for bags, suitcase etc. in the bottom in bedrooms | 2026-06-23 16:01:54 +0530 | Akshay Ds | Some Image was uploaded | 2026-06-08 | 2026-06-07 12:22 | 2026-08-18 |  | Under Construction | 2026-07-01
19665 | Turnkey | 2026-01-01 | Krishanu Das | Shriram WYTfield | BNG - HRBR | Yes | Faizan Sharief | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | 20% Payment | 1395347 | 147999 | 1478736 | 0 | 0 | 3 | 0 | 0 | 131070 | 605824 | 510453.2 |  |  | 2026-04-26 | 2026-04-29 13:22 | 2026-04-26 | 2026-04-29 18:04 | 2026-05-31 | 2026-06-02 11:29 | 2026-07-12 | 2026-07-12 11:19 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-05 12:59 | 2026-06-05 | 2026-06-10 16:02 | 2026-06-12 | 2026-06-13 11:17 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-06-14 | 2026-07-12 11:10 | Site is RTMI | 2026-04-26 | 2026-04-26 16:20 | 1253166 | 225569 | 0 | 0 | 0 | 0 | 1523397.5401 | 251162 | 2026-06-14 19:28:39 +0530 | Rajeshwari S | Welcome call done along with Faizan Project almost completed Registration on 25th June Apartment is ready for IM - Faizan to book the IM slot and inform client. Post that 1st Design meeting to be done and layout to be finalized 10% will be done post Layout finalization Estimation was finalized for 11,62,870/- after all the offers Aligned with the process. | 2026-06-10 16:03:00 +0530 | Bency Chacko |  | 2026-06-10 12:28:47 +0530 | Kushal S | Some Image was uploaded | 2026-07-13 | 2026-07-12 11:45 | 2026-07-19 |  | Under Construction | 2026-08-31
19666 | Turnkey | 2026-01-01 | Anup Shirsat | Raymond GS | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 6288604 | 9999 | 6288604 | 0 | 0 | 69 | 0 | 618861 | 628860 | 2699833 | 2331050 |  |  | 2026-04-26 | 2026-04-26 21:44 | 2026-05-02 | 2026-05-02 21:07 | 2026-05-05 | 2026-05-07 11:57 | 2026-05-14 |  | 2026-05-21 |  | 2026-05-28 |  | 2026-05-07 |  | 2026-05-08 |  | 2026-05-08 |  | 2026-05-09 | [5 empty] | 2026-05-15 |  | 2026-05-23 |  | 2026-05-24 |  |  |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-03 | [6 empty] | 2026-06-21 |  | 2026-06-30 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-03 |  |  |  | 2026-07-25 |  | 2026-07-27 |  | 2026-07-28 | [5 empty] | 2026-06-01 |  | 2026-05-10 |  | Unknown | 2026-04-26 | 2026-04-26 21:41 | 5329325 | 959278 | 0 | 0 | 0 | 0 | 5329325 | 959278 | 2026-05-01 07:30:09 +0530 | Pooja Nakul Sharma | Some Image was uploaded | 2026-05-01 07:29:40 +0530 | Pooja Nakul Sharma | DCM: LR- shoerack outside Foyer- console + wall concepts Foyer - left side bedroom entry to be changed as marked in layoutÂ plan it as normal bedroom as of now- bed, wardrobe, stduy, mirror (will also be GBR).Â Left side MBR- couple. Plan Walkin wardrobe as showed, with glass partition. King bed, dresser (in WW only), side table. - Any tinge of turqoise colour. Tv also to be planned.Â Right side MBR- Daughter's bedroom. (Pink and beige theme) (She is a teenager), walk in wardrobe to be planned similar to MBR and same requirements, study will be added. Tv also to be planned.Â Bedroom left to living room- Parents bedroom- Bed, wardrobe, dresser, tv.Â LR- Tv wall (85 inches TV), dining-6-8 seater, crockery unit, wall concepts, proper seating and accomodation of table for ganpati in mandir area. (as per vastu).Â Kitchen to be planned as marked in the layout.Â Hidden bar unit to be planned in LR or MBR. Only LR will be neutral with tinge of dark colour in sofa, reast colour as mentioned above.Â Client is not keen on having brown and beige palette. Budget- open Suggested- 50L | 2026-04-28 17:25:14 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-15 |  | 2026-05-22
19667 | Turnkey | 2026-01-01 | Anchal | Assetz Sun & Sanctum | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Hold | Preproduction | DEM2 | 827655 | 175999 | 1036668 | 0 | 0 | 10 | 8 | 0 | 0 | 334334 | 317322.4 |  |  | 2026-04-26 | 2026-04-26 16:46 | 2026-04-28 | 2026-04-29 18:04 | 2026-05-03 | 2026-05-06 10:55 | 2026-06-20 | 2026-06-20 19:14 | 2026-08-02 |  | 2026-08-09 |  | 2026-05-06 | 2026-05-06 13:40 | 2026-05-07 | 2026-05-06 13:40 | 2026-05-06 | 2026-05-06 18:45 | 2026-05-08 | 2026-05-08 15:32 |  |  |  |  | 2026-06-20 | 2026-06-27 14:14 | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-10-16 |  | 2026-10-17 | [6 empty] | 2026-11-04 |  | 2026-11-13 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-16 |  |  |  | 2026-12-08 |  | 2026-12-10 |  | 2026-12-11 | [5 empty] | 2026-08-13 |  | 2026-05-09 | 2026-06-20 19:07 | Site is RTMI | 2026-04-26 | 2026-04-26 16:46 | 878532 | 158135 | 0 | 0 | 0 | 0 | 855961.4922 | 148977 | 2026-06-24 17:40:24 +0530 | Vishal Bandi | Project No: 19667 Client: Anchal Minutes of Meeting held on Date: 20-06-2026 Attendees: Designers & Client Discussion: DEM 1 as per the discussion, all the units were there in a design is confirmed and mainly the concern is Site measurement, as site is not ready for the initial measurement, not able to discuss on the kitchen design and few area, once we get initial measurement, we can have the detailed discussion on the dimension and placement | 2026-05-08 19:16:01 +0530 | Rhea Rathod | CDP: Post lam CDP 20% was collected Kitchen - as per the initial measurements, the dimensions will differ - especially in the utility -2 tall units were added -one side loft -Chimney patta -Base cabinets -Wall units -Granite - is being provided by the builder -One single bowl sink was added -Pantry unit accessory (they were inclined towards having it post CDP) Master Bedroom- Wardrobe with loft Dresser unit Bedroom 02- Wardrobe with loft Study unit TV unit, Shoe rack, Crockery unit, Pooja unit - loose furniture Vanities Wall trims, one wallpaper was added | 2026-05-08 15:28:08 +0530 | Parasa Sri | Welcome call done. June 1st week can plan for the initial measurement. post that to plan for DEM-1. | 2026-06-21 | 2026-06-20 19:16 | 2026-08-03 |  | Under Construction | 2026-07-01
19668 | Turnkey | 2026-01-01 | Rajesh | Radiance Floresta | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | Vaishali G | Vaishali G | Vanlalrammawia Tombing | Saddam Hussain Z M |  |  | Abdul Shafeen | Active | Design | DEM3 | 1694477 | 320684 | 2173082 | 0 | 0 | 3 | 0 | 0 | 0 | 728955 | 644838 |  |  | 2026-04-26 | 2026-05-06 20:09 | 2026-04-26 | 2026-05-13 11:52 | 2026-05-16 | 2026-05-14 00:12 | 2026-06-08 | 2026-06-08 20:27 | 2026-07-05 | 2026-07-12 11:02 | 2026-07-16 |  | 2026-05-14 | 2026-05-14 10:45 | 2026-05-15 | 2026-05-21 11:08 | 2026-05-21 | 2026-05-21 19:08 | 2026-05-23 | 2026-05-23 17:20 |  |  |  |  | 2026-06-08 | 2026-06-14 16:30 | 2026-07-13 | 2026-07-12 19:30 | 2026-07-13 | 2026-07-12 19:30 |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-20 |  | 2026-05-24 | 2026-06-08 20:22 | Site is RTMI | 2026-04-26 | 2026-04-28 20:59 | 1841595 | 331487 | 0 | 0 | 0 | 0 | 1898975.0489 | 313555 | 2026-06-19 18:14:17 +0530 | Vishal Bandi | 1. as per our discussion, for foyer we are going to create dummy wall which is projecting from the wall (150mm) and curve ceiling on the top, for the dummy wall need to give 4 small niche and 1 bigger open space with wall paper in it 2. Pooja unit has to be considered in our scope (pricing is not added in initial estimation) as mentioned more customization is not possible in Modular work 3. Have consider Plain false ceiling in evry room 4. Tv unit has to give option with different material 5. as per last discussion - shown tv unit with the option of wallpaper and rafters on the wall 6. one more option need to give tv unit with different design 7. Kitchen part as discussed in the meeting and done the changes in the meeting only 8. under the staircase, as per CX request need to show design with CNC jaaliÂ design (client scope) 9. staircase photo fame wall- as discussed in the meeting (Client scope) 10.Geust bedroom- loft has to e consider wall to wall 11. No wallpaper in GBR 12. For full length mirror need to give back panel which needs to extend all around 50mm extra 13.study table with bottom pencil drawer has been added 14. Internal of drawer with all shelfs 15. double height wall with wallpaper 16.Door entry panel has to be consider 17. kids room with wardrobe and loft (loft till the end) 18. between 2 wardrobe units 1 glass shutter is addedÂ 19. wallpaper has to add for the bed wall 20. bed CX scope 21.For full length mirror need to give back panel which needs to extend all around 50mm extra 22. MBR bed wall with wallpaper 23.bed side need to place dresser tall unit mirror 24. study table will be as it is 25.walkin wardrobe will be as discussed and need to give provision for existing almirah 26. Study room with wardrobe and loft - last wardrobe shutter with alu glass shutter 27. study table CX scope and above that need to provide ledge for the soft toys | 2026-06-19 18:13:55 +0530 | Vishal Bandi | Foyer- has to design with wall concept and minimal storage for artefactsPooja unit CX scopeFalse ceiling design has to give above the pooja unitTV unit with no back panel ( as mentioned need to check from Builder side for the conduit piping to just to hide the Wire)3 feet need to leave from the left side of wallDouble Hight ceiling has to give deign with wallpaper and cladding ( mainly with lighter shades)Kitchen has to design as per the last discussion - ( need a confirmation from the builder for the plumbing changes- Plumbing CX scope)Bellow the staircase no need of wall concept and only wash basine will be ther and frame and shutterGBR with only wardrobe and loft and full length mirrorStair case wall need to plan for photo wallMBR- with wardrobe and Loft with dresser storageKBR- with wardrobe Loft and dresser with mirror and one full lenth mirrorStudy Room with Wardrobe and loft- Study Table will be CX scope and need to make space for Soft toys | 2026-05-27 17:17:31 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-09 | 2026-06-08 20:29 | 2026-07-13 | 2026-07-12 19:25 | Under Construction | 2026-06-15
19669 | Turnkey | 2026-01-01 | Pragya singh | Prestige Meridian Park | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1368119 | 9999 | 1368119 | 0 | 0 | 57 | 0 | 126813 | 136812 | 556763 | 537732 |  |  | 2026-04-26 | 2026-04-28 11:31 | 2026-04-26 | 2026-05-08 20:41 | 2026-05-11 | 2026-05-19 18:12 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-04-26 | 2026-04-26 17:18 | 1161919 | 206200 | 0 | 0 | 0 | 0 | 1161919 | 206200 | 2026-05-07 17:42:43 +0530 | Gayathri Krishna | DCM: Cx name : Pragya Singh & Rishav Address : Prestige - 62193 Profession :Â IT Possession : July 1st week How many people will be staying : Theme : Minimal Entrance facing : W facing Budget : 8L Foyer- Highlight the wall with wallpaper or trims Give Wall one ledge Find provision For Pooja unit on sofa back wall or dining wall - Open Unit no shutters (refer image ) Dining area - 6 seater dining is there with cx need crockery unit on bathroom wall Living area - TV unit refer image - wall mounted base and ledges Tv size 51" 3 seater sofa and 2 single seaters Sofa back wall need wall trims TV unit and wall ledge ends should be curved Kitchen - Acrylic finish Base, wall and loft on 1 side AG needed double door fridge need 1 cylinder unit granite countertop to be included RO is wall mounted so need cabinet Utility - Laminate Need wall cabinets Need counter top for WM and sink Â MRB - 4 shutter cane with wooden wardrobe long mirror with small dresser storage next to wardrobe Need a wooden drawers set next to room entrance as marked in plan (only for 3D) cx will retain king size wooden bed Bed wall need wall trims with curve details GBR - 4 shutter wardrobe with laminate finish Bed wall need wall trims Bathrooms - Builder is give mirror so give vanity base CDP - May 9th | [6 empty] | 2026-05-27 |  | 2026-06-03
19670 | Turnkey | 2026-01-01 | Sunil choulwad | Kalpataru Vivant | MUM - GOR | Yes | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera | [5 empty] | Rashmita Das |  | Hold | Preproduction | DEM2 | 986650 | 197330 | 1212081 | 0 | 0 | 30 | 13 | 0 | 0 | 454300 | 335020 |  |  | 2026-04-26 | 2026-05-02 12:19 | 2026-05-02 | 2026-05-02 12:26 | 2026-05-05 | 2026-05-02 12:43 |  |  | 2026-09-19 |  | 2026-09-26 |  | 2026-05-02 | 2026-05-04 11:21 | 2026-05-03 | 2026-05-07 16:02 | 2026-05-07 | 2026-05-08 12:24 | 2026-05-13 | 2026-05-13 18:40 |  |  |  |  | 2026-05-20 | 2026-06-02 11:28 | 2026-09-21 |  | 2026-09-22 |  |  |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-02 | [6 empty] | 2026-10-20 |  | 2026-10-29 |  | 2026-10-28 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-11-01 |  |  |  | 2026-11-23 |  | 2026-11-25 |  | 2026-11-26 | [5 empty] | 2026-09-30 |  | 2026-05-14 | 2026-05-20 18:37 | Site is RTMI | 2026-04-26 | 2026-04-29 12:04 | 1027187 | 184893 | 0 | 0 | 0 | 0 | 1020425.7802 | 177597 | 2026-05-24 10:31:36 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-15 17:24:03 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-13 18:39:14 +0530 | Manzoor Shaikh | "Welcome call done along with the Designer. Initial measurement to be aligned DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : May End Customer will make 10% post LFM Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-05-22 | 2026-05-20 18:45 | 2026-09-20
19671 | Turnkey | 2026-01-01 | Mr. Ananth S | Shapoorji Pallonji Parkwest | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 1542537 | 9999 | 0 | 0 | 0 | 77 | 0 | 144255 | 154254 | 642659 | 591370.8 |  |  | 2026-04-26 | 2026-04-29 13:21 | 2026-04-26 | 2026-05-02 16:50 | 2026-05-02 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-02 |  | 2026-05-03 |  | 2026-05-03 |  | 2026-05-04 | [5 empty] | 2026-05-10 |  | 2026-05-18 |  | 2026-05-19 |  |  |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 | [6 empty] | 2026-06-16 |  | 2026-06-25 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-28 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-05-27 |  | 2026-05-05 |  | Unknown | 2026-04-26 | 2026-04-26 18:15 | 0 | 0 | 0 | 0 | 0 | 0 | 1307234 | 235302 | 2026-06-05 18:28:59 +0530 | Yogesh B | Some Image was uploaded | 2026-05-02 16:45:11 +0530 | Priyanka Gs | DCM: Foyer Shoe rack designed within the niche spaceFeature wall concept for the foyer areaLiving Room Minimal TV unit with integrated storageExtension of the sofa back wall, either through a partition or a full wall treatmentDining Area Pooja unit with internal storageCabinet for the common washroomKitchen Bottom cabinetsTop cabinetsLoft storageMaster Bedroom Aristo wardrobeDresser unitFoldable tableVanity with bottom cabinet storageKids Bedroom Wardrobe with loft storageStudy unitParents Bedroom Wardrobe with loft storageDresser unitVanity unitsAdditional Details False ceiling for the common areas, specifically the living roomPreferred color palette: Beiges, browns, and off-white tonesAristo wardrobes were initially discussed for all bedrooms; however, it was suggested to opt for Aristo only in the master bedroom | 2026-04-28 17:27:56 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-10 |  | 2026-05-17
19672 | Turnkey | 2026-01-01 | Sujit Jadhav | Rustomjee Uptown Urbania | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Nishtha Valawalkar |  | Hold | Preproduction | Site Readiness 1 | 1997964 | 399593 | 2459249 | 0 | 0 | 2 | 43 | 0 | 0 | 828356 | 770015.2 |  |  | 2026-04-26 | 2026-04-26 21:24 | 2026-04-30 | 2026-04-30 19:51 | 2026-05-02 | 2026-05-02 11:21 | 2026-06-15 | 2026-05-31 19:19 | 2026-09-08 |  | 2026-09-15 |  | 2026-05-02 | 2026-05-04 11:18 | 2026-05-03 | 2026-05-04 12:13 | 2026-05-04 | 2026-05-05 14:28 | 2026-05-20 | 2026-05-20 11:32 |  |  |  |  | 2026-06-16 | 2026-05-30 12:12 | 2026-09-10 |  | 2026-09-11 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 | [6 empty] | 2026-10-09 |  | 2026-10-18 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-21 |  |  |  | 2026-11-12 |  | 2026-11-14 |  | 2026-11-15 | [5 empty] | 2026-09-19 |  | 2026-06-11 | 2026-05-31 19:06 | Site is Non-RTMI | 2026-04-26 | 2026-04-26 21:22 | 2084110 | 375139 | 0 | 0 | 0 | 0 | 2084109.1977 | 359633 | 2026-06-02 10:26:05 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-28 15:09:54 +0530 | Anil Jagtap | Some Image was uploaded | 2026-05-22 14:51:40 +0530 | Amisha Ahuja | Points which we discussed on Sunday. Entrance: - Wall to be checked by the builder to confirm if it can be broken and if the MCB can be shifted. The plan will be changed accordingly. Kitchen Entrance: - Entrance wall to be broken and adjusted as per the layout. Living Area: - TV unit base with stucco paint on the back wall and two golden pattis on both sides. - Sofa back wall with louvers, rectangular beading, and glass on one side. - Service counter to be made with 1.5-inch depth. - Mandir unit to be discussed with Mayuri and Nishtha. Bedroom 1: - Front wall to be confirmed for customised wallpaper. - Bed back wall to include a showpiece area. Master Bedroom: - Bed back wall with round beading, wallpaper, and mirror beside it. - Rest remains the same. Guest Bedroom: - Simple minimal panelling and trims. - Wardrobe remains the same. Kitchen: - Tall unit to be removed. - Chimney and cooktop positions to be changed. - Shutter unit to be changed to a glass unit. - kitchen laminated and handles selected . Overall theme to be in beige cream theme . Initial measurements will be done in june due to possession .Â Thank youÂ Amisha Ahuja Interior Designer | 2026-06-01 | 2026-05-31 19:23 | 2026-09-09
19673 | Turnkey | 2026-01-01 | aparna naik | velvet puri | MUM - GOR | Yes | Neha Yadav | Manzoor Shaikh | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Preproduction | DEM2 | 1372415 | 274483 | 1724677 | 0 | 0 | 42 | 0 | 0 | 0 | 602766 | 495166.4 |  |  | 2026-04-26 | 2026-05-05 13:10 | 2026-05-06 | 2026-05-06 11:22 | 2026-05-06 | 2026-05-06 19:52 | 2026-05-31 | 2026-05-31 17:35 | 2026-06-24 |  | 2026-08-12 |  | 2026-05-06 | 2026-05-06 20:12 | 2026-05-07 | 2026-05-07 12:10 | 2026-05-07 | 2026-05-08 16:38 | 2026-05-19 | 2026-05-19 17:36 |  |  |  |  | 2026-05-31 | 2026-06-03 18:44 | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-05-20 | 2026-05-29 17:56 | Site is RTMI | 2026-04-26 | 2026-05-05 13:09 | 1463878 | 260799 | 0 | 0 | 0 | 0 | 1441193.2956 | 240623 | 2026-07-14 11:51:40 +0530 | Neha Yadav | DDM2 Meeting Discusion: 1)Mater room - dresser will be with wardrobe and base storage need to do 2 drawer. 2)Tall unit need to remove from master room 3)Living- tv panel need to add and tall unit need to add here from mb 4)Sons room- Study top open space storage to make shutter 5)Kitchen- Golden handle with clear flutted shutter need to do 6)Loft need to add above fridge. Feel free to ad pointers if missed any. | 2026-06-28 12:25:07 +0530 | Manzoor Shaikh | Dear Ms. Aparna Naik, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 07th July at 11:30 AM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Neha will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-06-28 12:23:14 +0530 | Manzoor Shaikh | Initial measurement is Done | 2026-06-01 | 2026-05-31 17:37 | 2026-06-25 |  | Under Construction | 2026-07-15
19674 | Turnkey | 2026-01-01 | Vanashree Vishal Shinde | Dhananjay Heights | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 1098712 | 9999 | 0 | 0 | 0 | 70 | 0 | 99872 | 109871 | 475052 | 403917.6 |  |  | 2026-04-26 | 2026-05-06 12:48 | 2026-05-06 | 2026-05-09 16:09 | 2026-04-26 |  | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-05-20 |  | 2026-05-28 |  | 2026-05-29 |  |  |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 | [6 empty] | 2026-06-26 |  | 2026-07-05 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-06-06 |  | 2026-05-15 |  | Unknown | 2026-04-26 | 2026-05-06 12:48 | 0 | 0 | 0 | 0 | 0 | 0 | 931111 | 167600 | 2026-05-09 16:09:43 +0530 | Sweta Bhise | DCM: t Profile1. Name of the customer vanashree vishal shinde 2. Profession service 3. Project Name/Tower Name/Flat Number Dhananjay Heights 4. Typology (1BHK, 2BHK, 3BHK, etc) 1bhk 5. Site Access Date 2026-06-15 6. Possession Date 2026-06-20 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 900000 Customer Preferences8. Who will be living in the house? Couple 9. What activities do you usually prefer at your home ? Family Bonding 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any NA 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) NA Upload reference images 14. Any absolute no-go styles colours or materials NA 15. Do you have any existing furniture that must be accommodated? NA 13. Do you want the design to reflect any personal story, cultural influence, or special memory NA ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Partition 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests 2. Must-have furniture or features? TV unit, Puja unit 3. Choose your decor inspirations Plants 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Chimney 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 800000 | [6 empty] | 2026-05-20 |  | 2026-05-27
19675 | Turnkey | 2026-01-01 | Mrs Deepti Shah | Puri velvet | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 2490639 | 9999 | 2490639 | 0 | 0 | 39 | 0 | 239065 | 249064 | 1058475 | 934036 |  |  | 2026-04-26 | 2026-04-29 12:22 | 2026-05-01 | 2026-06-04 13:35 | 2026-06-07 | 2026-06-11 21:13 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-04-26 | 2026-04-29 12:16 | 2110711 | 379928 | 0 | 0 | 0 | 0 | 2110711 | 379928 | 2026-06-12 19:18:21 +0530 | Yash Jain | Some Image was uploaded | 2026-06-11 21:12:54 +0530 | Yash Jain | CDP: RE - CDP to take place as client is still revieweing the quote and comapring with other vendors as well. and not in hurry as they still have 6 months for possessionn Living room- shoe rack requires partition above kitchen Requires more drawer and loft on both platforms masterbedroom all wardrobes has to be glass doors. comon bedroom additonal wardrobes with lesser depth in place of dresser unit. | 2026-06-11 13:54:51 +0530 | Ishrat Khan | Some Image was uploaded | 2026-06-19 |  | 2026-06-26
19676 | Turnkey | 2026-01-01 | Sonu Shringi | Hiranandani Falcon | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 1328954 | 9999 | 0 | 0 | 0 | 78 | 0 | 122896 | 132895 | 651602 | 411560.8 |  |  | 2026-04-26 | 2026-04-28 12:06 | 2026-04-28 | 2026-04-28 12:29 | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-04-26 | 2026-04-28 12:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1128540 | 200413 | 2026-05-03 18:50:56 +0530 | Anjali Singh | DCM: Heres a compact yet detailed version you can directly use: MR. MOHIT DESIGN SUMMARYFamily4 membersMaster: CoupleGuest: Grandparents + 11 y/o daughterProfession: Garment production & mediaConceptMinimal + functionalEarthy palette: beige, tan, brown, soft greensTextured finishes, no heavy floralsClean, cosy, storage-focusedLiving Room3+2 seating + low-height L-sofaSofa-cum-bed for extra useCompact 4-seater diningSleek TV unit with storageSmall mandir (existing + Vastu check)Hidden storage integrationBalconyWooden ceiling + warm lightsMini bar (concealable)2-chair seating with tableRelaxed cosy vibeKitchenExisting modular retainedAdd open shelves for boxesDishwasher provisionShaftFull-height storage (important)Grandparents + Daughter RoomBunk + sofa-cum-bedPastel pink + beige + brownStudy + dresser comboWardrobe + book storageFunctional layout with mirrorMaster BedroomFull-height wardrobe (no gaps)Storage bed + side tablesTV unit (if space allows)Dressing + mirrorSmall cosy seatingDevice charging pointsBathroomsGlass shower partitionEasy maintenanceEntranceShoe rack + bench (20 pairs, ~1 ft depth)Lighting & ElectricalMinor changesWarm ambient + task lightingKey FocusMaximum storageMulti-functional furnitureClutter-free layoutVastu for mandirBudget12 Lakhs (end-to-end) | 2026-04-28 15:54:37 +0530 | Prashant Panigrahi | Some Image was uploaded |  |  |  | 2026-05-25 |  | 2026-06-01
19677 | Turnkey | 2026-01-01 | Mr Sudesh keshav kani | Puri velvet | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 1890508 | 9999 | 1890508 | 0 | 0 | 36 | 0 | 179052 | 189051 | 823814 | 688592 |  |  | 2026-04-26 | 2026-04-29 12:20 | 2026-06-09 | 2026-06-09 11:49 | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-13 |  | 2026-06-14 | [5 empty] | 2026-06-20 |  | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-06-15 |  | Unknown | 2026-04-26 | 2026-04-29 12:16 | 1605063 | 285445 | 0 | 0 | 0 | 0 | 1605063 | 285445 | 2026-06-09 16:41:51 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-09 16:38:09 +0530 | Rahul Agrawal | CDP: Client found our quote to be on higher side and client needs more time to discuss with family and then will come to a decision. | 2026-06-09 11:54:26 +0530 | Rahul Agrawal | Project Details Project: Pure Velvet Possession: Around August Configuration: 2 BHK Area: Approx. 873 sq. ft. Profile: Retired couple Son & daughter will be visiting occasionally. Basic Vastu required. Main entrance in the East. Foyer Shoe rack Living Room Sofa + 1 chair TV unit with mandir 4/6-seater dining table Kitchen Single-door refrigerator Single-door pantry Base cabinet + top cabinet Not fond of excessive storage; prefers minimal and less bulky design Microwave box concept Bedroom 01 (Kids Room) Theme: Scandinavian / Bohemian Window seating space Flush door for washroom Queen-size bed Wardrobe (No loft) Master Bedroom Theme: Modern & Elegant King-size bed W.I.W. (Walk-in Wardrobe) with sliding wardrobe Open wardrobe concept inside Wardrobe with loft Side tables TV ledge Working desk Additional Requirements 2 Vanity units Soft civil work: False ceiling Painting Electrical work Full-length mirror Timeline CDP: 6th June (Saturday) Budget Budget: 15 Lakhs (Gross) Client asked for: 17 Lakhs | 2026-06-20 |  | 2026-06-27
19680 | Turnkey | 2026-01-01 | RAJAKUMAR Nadar | Dosti Mezzo | MUM - GOR | Yes | Riddhi Deshpande | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Hold | Design | 20% Payment | 1064678 | 133999 | 1338268 | 0 | 0 | 15 | 34 | 0 | 78937 | 449365 | 402377.6 |  |  | 2026-04-26 | 2026-04-30 12:14 | 2026-04-26 | 2026-04-30 12:24 | 2026-05-03 | 2026-04-30 13:10 | 2026-05-27 | 2026-05-27 16:06 | 2026-07-23 |  | 2026-07-30 |  | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-12 14:07 | 2026-05-12 | 2026-05-19 12:14 | 2026-05-21 | 2026-05-21 17:17 |  |  |  |  | 2026-07-15 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-05-22 | 2026-05-24 16:00 | Site is RTMI | 2026-04-26 | 2026-04-26 20:14 | 1134125 | 204142 | 0 | 0 | 0 | 0 | 1133622.5616 | 191391 | 2026-07-05 13:15:06 +0530 | Vishakha Vaishnav | Others: POSSESSION BY AUGUST 2026 | 2026-06-12 13:31:47 +0530 | Riddhi Deshpande | DDM1: cx can come for a meeting between - 20-25june - discussed with rahul | 2026-06-12 13:27:47 +0530 | Riddhi Deshpande | DDM1: have asked in group for the meeting | 2026-05-28 | 2026-05-27 16:11 | 2026-07-24
19681 | Turnkey | 2026-01-01 | Akhil daftary | neelog aarana | MUM - GOR | Yes | Zoya Bhatkar | Reshma Melanta | Shantanu Parakh | [5 empty] | Sanskruti Yadav |  | Active | Preproduction | DEM2 | 2202783 | 327308 | 2106330 | 0 | 0 | 19 | 0 | 0 | 0 | 1028371 | 847104 |  |  | 2026-04-26 | 2026-04-28 12:24 | 2026-04-29 | 2026-05-02 11:57 | 2026-05-10 | 2026-05-10 22:47 | 2026-06-18 | 2026-06-17 20:43 | 2026-06-23 |  | 2026-07-03 |  | 2026-05-10 | 2026-05-10 23:05 | 2026-05-11 | 2026-05-12 14:40 | 2026-05-12 | 2026-05-23 14:23 | 2026-05-29 | 2026-05-29 13:43 |  |  |  |  | 2026-06-17 | 2026-06-26 19:19 | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-05-30 | 2026-05-29 15:55 | Site is RTMI | 2026-04-26 | 2026-04-28 12:21 | 1785025 | 321304 | 0 | 0 | 0 | 0 | 2342843.5737 | 404280 | 2026-06-26 19:23:08 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-21 13:31:43 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-06-17 19:06:34 +0530 | Zoya Bhatkar | Minutes of Meeting held on Date: 17th June 2026 Attendees: Discussion: DEM 1 Based on 17th June 2026 meeting, below is a list of all the requirements that were discussed during the meeting: Kitchen Pull out for Detergent in Sink Unit 2 Tier Hetitch Drawer & Pull out 3 DrawerÂ 1 Bottle Pull out Shelf Unit Corner Unit Accessories Wall Unit Glass Shutter Loft to be added in L Shape inÂ Roller Shutter Microwave Unit Daughter's BedroomÂ Wardrobe InternalsÂ Accessories Tray Trouser Pull out Bed Size : 4x6 1' Depth Horizontal Drawer opp Bed Wall Double Curtain Washroom Wall Unit with Shelves with Fluted glass MirrorÂ 1 or 2 Accent Lights Living Room Crockery Unit 1 Drawer with shutter Mirror Panelling TV Unit as per image shared in WhatsApp Group Texture Paint Plain False Ceiling with flushed lights from side Guest BedroomÂ Wardrobe Internals Only Horizontal Shelves 1 Drawer in Dresser Wall Unit with Shelves Son's Bedroom Dresser 2 Drawer with Mirror WardrobeÂ Left internal drawer with Sensor lock Washroom Wall storage above ledge PassageÂ wall storage above Washing Machine Parents Bedroom Dresser 2 Drawer Unit Wall Mounted with Wall Storage Wardrobe Internals Left Locker Space 12inches x 18INCHES | 2026-06-18 | 2026-06-17 20:44 | 2026-06-24 |  | Under Construction | 2026-06-01
19683 | Turnkey | 2026-01-01 | Alisha Ajani | MICL Aaradhya Parkwood | MUM - GOR | Yes | Swapnali Shedekar | Vishakha Vaishnav | Safalta Karkera |  | Hiba Shaikh | Akash Jadhav | Sandeep Tiwari |  | Avi Thakkar | Shailendra Mishra | Active | Preproduction | 2D | 940600 | 182120 | 1357605 | 940600 | 0 | 4 | 17 | 0 | 0 | 422810 | 335670.4 |  |  | 2026-04-26 | 2026-04-30 13:41 | 2026-04-27 | 2026-04-30 13:42 | 2026-05-03 | 2026-04-30 22:30 | 2026-05-27 | 2026-05-26 11:32 | 2026-06-27 | 2026-06-26 19:19 | 2026-07-06 | 2026-07-06 11:33 | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-06 12:57 | 2026-05-06 | 2026-05-08 12:42 | 2026-05-19 | 2026-05-19 17:16 |  |  |  |  | 2026-06-08 | 2026-06-14 19:23 | 2026-07-01 | 2026-06-25 20:36 | 2026-06-26 | 2026-06-25 20:36 |  |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-05-20 | 2026-05-26 11:25 | Site is Non-RTMI | 2026-04-26 | 2026-04-30 13:34 | 1150512 | 207092 | 1148500.322 | 181235 | 0 | 0 | 1148500.322 | 181235 | 2026-06-09 17:05:56 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-06 12:12:46 +0530 | Safalta Karkera | Some Image was uploaded | 2026-06-03 13:20:45 +0530 | Vishakha Vaishnav | 1.Team is trying to connect the cx since thursday (28/5/26) cx is not responding, have dropped the message in group as well. 2.Welcome call is done 19th May 2026 3.DEM 1 meeting was aligned for 22nd may 4.IM was aligned for 27th may also on 27th spoke to ms sonya that she will get 2-3 options for her apartment in terms of designing but as swapnali was on leave asked for some time cx said that she is ok if we give the designs on friday 5.After then now cx has esclated that designs have not been shared but cleared this developer and have aligned the meeting for saturday with designer with 2-3 options | 2026-05-27 | 2026-05-26 19:57 | 2026-06-27 | 2026-06-26 19:19 | Under Construction | 2026-05-30
19684 | Turnkey | 2026-01-01 | pradeep K | centro | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1101016 | 9999 | 0 | 0 | 0 | 80 | 0 | 100103 | 110102 | 440406 | 440406.4 |  |  | 2026-04-26 | 2026-04-26 20:52 | 2026-04-27 |  | 2026-04-26 |  | 2026-05-07 |  | 2026-05-14 |  | 2026-05-21 |  | 2026-04-30 |  | 2026-05-01 |  | 2026-05-01 |  | 2026-05-02 | [5 empty] | 2026-05-08 |  | 2026-05-16 |  | 2026-05-17 |  |  |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-27 | [6 empty] | 2026-06-14 |  | 2026-06-23 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-26 |  |  |  | 2026-07-18 |  | 2026-07-20 |  | 2026-07-21 | [5 empty] | 2026-05-25 |  | 2026-05-03 |  | Unknown | 2026-04-26 | 2026-04-26 20:51 | 0 | 0 | 0 | 0 | 0 | 0 | 933065 | 167951 | [9 empty] | 2026-05-08 |  | 2026-05-15
19686 | Turnkey | 2026-01-01 | Prashant Ghule | Natasha avana | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Aryan Singh |  | Hold | Design | DEM1 | 472908 | 108359 | 566598 | 0 | 0 | 34 | 43 | 0 | 0 | 188495 | 176054 |  |  | 2026-04-25 | 2026-04-28 12:01 | 2026-04-28 | 2026-04-28 12:18 | 2026-04-28 | 2026-04-28 12:24 | 2026-09-05 |  | 2026-09-12 |  | 2026-09-19 |  | 2026-04-28 | 2026-04-28 12:58 | 2026-04-29 | 2026-04-29 11:59 | 2026-04-29 | 2026-04-29 12:57 | 2026-08-31 | [5 empty] | 2026-05-06 | 2026-06-02 15:03 | 2026-09-14 |  | 2026-09-15 |  |  |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 | [6 empty] | 2026-10-13 |  | 2026-10-22 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-25 |  |  |  | 2026-11-16 |  | 2026-11-18 |  | 2026-11-19 | [5 empty] | 2026-09-23 |  | 2026-09-01 |  | Unknown | 2026-04-25 | 2026-04-26 20:53 | 480168 | 86430 | 0 | 0 | 0 | 0 | 480167.6488 | 83579 | 2026-07-10 12:37:12 +0530 | Anil Jagtap | cx will receive the possession by November*26 | 2026-07-03 13:25:11 +0530 | Monika Pal | 2026-07-03 | 2026-06-18 11:37:37 +0530 | Monika Pal | Some Image was uploaded | 2026-09-06 |  | 2026-09-13
19688 | Turnkey | 2026-01-01 | FINVESTONOMICS ( Lalit Nandkumar Temkar ) | prescon midtown | MUM - GOR | Yes | Anjali Jain | Manzoor Shaikh | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Hold | Preproduction | DEM2 | 1850415 | 370083 | 2357108 | 0 | 0 | 1 | 47 | 0 | 0 | 826889 | 653443.2 |  |  | 2026-04-26 | 2026-04-26 21:43 | 2026-05-02 | 2026-05-02 15:21 | 2026-05-05 | 2026-05-02 16:21 | 2026-05-24 | 2026-05-20 15:50 | 2026-10-08 |  | 2026-10-15 |  | 2026-05-02 | 2026-04-30 | 2026-05-03 | 2026-05-04 12:56 | 2026-05-04 | 2026-05-04 18:32 | 2026-05-08 | 2026-05-08 18:08 |  |  |  |  | 2026-05-20 | 2026-05-28 19:12 | 2026-10-10 |  | 2026-10-11 |  |  |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 | [6 empty] | 2026-11-08 |  | 2026-11-17 |  | 2026-06-19 |  | 2026-11-17 |  | 2026-11-18 |  | 2026-11-20 |  |  |  | 2026-12-12 |  | 2026-12-14 |  | 2026-12-15 | [5 empty] | 2026-10-19 |  | 2026-05-09 | 2026-05-20 12:20 | Site is RTMI | 2026-04-26 | 2026-04-26 21:43 | 1997549 | 359558 | 0 | 0 | 0 | 0 | 1983584.8709 | 334893 | 2026-07-03 16:00:29 +0530 | Meet Shah | Others: | 2026-06-05 13:29:25 +0530 | Meet Shah | Some Image was uploaded | 2026-05-27 15:00:33 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-05-21 | 2026-05-20 15:55 | 2026-10-09 |  | Under Construction | 2026-05-15
19689 | Turnkey | 2026-01-01 | Tushar Patil | Prescon Midtown Bay | MUM - GOR | Yes | Preeti Agarwal | Christopher Macwan | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Suraj Jaiswar | Rizwan Mistry |  | Harshaan Tiku | Sunil Poojary | Active | Preproduction | Site Readiness 2 | 867085 | 538800 | 972573 | 0 | 914585 | 1 | 0 | 0 | 0 | 0 | 328285 |  |  | 2026-04-25 | 2026-04-26 21:35 | 2026-04-29 | 2026-04-29 21:45 | 2026-05-02 | 2026-04-30 15:38 | 2026-05-21 | 2026-05-21 17:27 | 2026-06-07 | 2026-06-06 19:23 | 2026-06-16 | 2026-06-16 09:46 | 2026-04-30 | 2026-04-30 15:50 | 2026-05-01 | 2026-04-30 15:50 | 2026-04-30 | 2026-04-30 17:50 | 2026-05-03 | 2026-05-03 11:56 |  |  |  |  | 2026-05-09 | 2026-05-14 11:51 | 2026-06-07 | 2026-06-11 18:21 | 2026-06-12 | 2026-06-11 19:02 |  |  | 2026-06-17 | 2026-06-19 19:44 | 2026-06-25 | 2026-06-25 20:54 | 2026-06-26 | 2026-06-26 19:29 | 2026-06-27 | 2026-07-14 12:50 | [5 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-06-25 | 2026-07-14 19:39 | 2026-05-04 | 2026-05-21 17:19 | Site is RTMI | 2026-04-25 | 2026-04-26 21:35 | 824215 | 148358 | 0 | 0 | 1013532.3353 | 163919 | 1013532.3353 | 163919 | 2026-06-25 18:26:31 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-06-25 13:34:53 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-06-25 12:37:23 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-05-22 | 2026-05-21 17:30 | 2026-06-07 | 2026-06-06 19:28 | RTMI
19690 | Turnkey | 2026-01-01 | Kirti Pawar | prescon | MUM - GOR | Yes | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera |  |  | Nilesh Patel | Rizwan Mistry |  | Harshaan Tiku | Sunil Poojary | Active | Preproduction | 2D | 1257263 | 199319 | 1317163 | 0 | 0 | 11 | 0 | 0 | 0 | 603267 | 454676.8 |  |  | 2026-04-26 | 2026-04-26 21:44 | 2026-05-02 | 2026-05-02 15:29 | 2026-05-05 | 2026-05-02 16:22 | 2026-06-07 | 2026-06-07 17:11 | 2026-06-29 | 2026-06-28 19:42 | 2026-07-02 | 2026-07-02 17:46 | 2026-04-26 | 2026-04-30 | 2026-05-03 | 2026-05-04 19:11 | 2026-05-04 | 2026-05-05 14:30 | 2026-05-13 | 2026-05-13 20:09 |  |  |  |  | 2026-06-07 | 2026-06-19 11:13 | 2026-06-29 | 2026-06-30 00:20 | 2026-07-01 | 2026-06-30 00:43 |  |  | 2026-07-23 | 2026-07-04 18:47 | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-05-14 | 2026-06-07 17:07 | Site is RTMI | 2026-04-26 | 2026-04-26 21:44 | 1116240 | 200923 | 0 | 0 | 0 | 0 | 1355557.0622 | 223819 | 2026-07-07 17:08:45 +0530 | Kripesh Melath | floor undulation vm approval | 2026-07-05 15:49:35 +0530 | Meet Shah | Others: | 2026-06-09 17:52:43 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-08 | 2026-06-07 17:13 | 2026-06-29 | 2026-06-28 19:42 | Under Construction | 2026-05-11
19691 | Turnkey | 2026-01-01 | Mohamed Gous Sayed | National Trinity Paradise | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | DCM Due | 2671655 | 9999 | 0 | 0 | 0 | 79 | 0 | 257167 | 267166 | 1121544 | 1015780.4 |  |  | 2026-04-26 | 2026-04-27 10:53 | 2026-04-30 | 2026-04-30 11:34 | 2026-05-03 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-04 |  | 2026-05-05 | [5 empty] | 2026-05-11 |  | 2026-05-19 |  | 2026-05-20 |  |  |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 | [6 empty] | 2026-06-17 |  | 2026-06-26 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-29 |  |  |  | 2026-07-21 |  | 2026-07-23 |  | 2026-07-24 | [5 empty] | 2026-05-28 |  | 2026-05-06 |  | Unknown | 2026-04-26 | 2026-04-26 21:15 | 0 | 0 | 0 | 0 | 0 | 0 | 2264115 | 407540 | 2026-04-30 11:29:04 +0530 | Rutuja Kotwal | DCM: Mr. MohamedÂ Gous.Â 5 BHK.Â Â Trinity Paradise KalyanÂ Phata.Â Â Area 1340Â sq.ft.Â Â Possession June 1stÂ week.Â Â Move in 7 people.Â Â Husband, Wife, 3 sons and 2Â daughterÂ in law.Â Â Profession MarketingÂ Manager .Â Elder son Â Civil EngineerÂ Â 2ndÂ son MBBS.Â Â Younger son BMS 2ndÂ year.Â Â Direction mentioned in the layoutÂ Â BedÂ should not face east .Â HeadÂ should not beÂ inÂ eastÂ direction.Â Â Flat notÂ 2 will the entrance and flat 1 will beÂ closedÂ and Shoe rack and outside paneling will be incorporated.Â Â Living room Â 6 seaterÂ dining table, Sofa curve not straight,Â TV unit, Informal seating for guest near entrance,Â crockery unit.Â Including 1 common bathroom in living room.Â Some plantersÂ alsoÂ to be kept.Â Â Kitchen Platform is onÂ the bothÂ sides.Â KitchenÂ will be from flat 1.Â Â Stove and sink on one side.Â Â Base units, wallÂ unitsÂ andÂ Lofts\.Â Â Younger Sons Bedroom -( Common bedroom from flat 1)-Â op.1Â BedÂ in the corner, Wardrobe, Study table with Above storageÂ and add. Lofts.Â Â Op.2-Â Bed,Â Wardrobe, Study table with Above storageÂ and add.Â Wardrobe.Â Â Flat no 2 kitchen-Â ( GuestÂ Bedroom )- Arabic Baithak. For guests.Â with Above storage.Â Parents bedroom - (Common bedroom from flat 2) -Â op.1 Bed in the corner, Wardrobe,Â DressingÂ tableÂ andÂ add. Lofts.Â Â Op.2-Â Bed,Â Wardrobe,Â Â DressingÂ tableÂ andÂ add. Wardrobe.Â Asads BedroomÂ (master bedroom from flat 1)-Â Bed, wardrobe, Side table, dressing Table,Â bench, Folding table.Â Â FlutedÂ panelÂ to be suggested.Â Â Osamas BedroomÂ (master bedroom from flat 2)Â -Â Bed, wardrobe, Side table, dressing Table, bench, Folding table.Â Â PanelingÂ to be suggested.Â CDP.-Â 3rdÂ May 2026.Â @Â 3pm.Â Â BudgetÂ 20 lakhs.Â Budget SuggestedÂ Â 40Â Â lakhs.Â Â ReceivedÂ otherÂ estimate ofÂ 14.91LÂ rupees.Â Â | [6 empty] | 2026-05-11 |  | 2026-05-18
19692 | Turnkey | 2026-01-01 | Fatema harnesswala | Piramal Aranya | MUM - GOR | Yes | [8 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 4281050 | 9999 | 4281050 | 0 | 0 | 63 | 0 | 418106 | 428105 | 1846268 | 1578572 |  |  | 2026-04-26 | 2026-05-06 12:38 | 2026-05-07 | 2026-05-07 12:58 | 2026-05-13 | 2026-05-13 22:24 | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-15 | [5 empty] | 2026-05-21 |  | 2026-05-29 |  | 2026-05-30 |  |  |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 | [6 empty] | 2026-06-27 |  | 2026-07-06 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-09 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-07 |  | 2026-05-16 |  | Site is RTMI | 2026-04-26 | 2026-05-06 12:37 | 3628008 | 653041 | 0 | 0 | 0 | 0 | 3628008 | 653041 | 2026-05-14 15:59:32 +0530 | Rishika Malviya | Some Image was uploaded | 2026-05-14 13:25:55 +0530 | Rishika Malviya | Some Image was uploaded |  |  |  | 2026-05-21 |  | 2026-05-28
19693 | Turnkey | 2026-01-01 | Sanket Bhagat | Ashar Arise | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Hitesh Rawal |  | Active | Preproduction | DEM2 | 1240074 | 251549 | 1489235 | 0 | 0 | 15 | 0 | 0 | 0 | 501694 | 486831.2 |  |  | 2026-04-26 | 2026-04-26 22:31 | 2026-04-29 | 2026-04-30 12:34 | 2026-05-03 | 2026-05-05 12:19 | 2026-06-12 | 2026-06-11 17:04 | 2026-06-30 |  | 2026-07-24 |  | 2026-05-05 | 2026-05-07 19:05 | 2026-05-06 | 2026-05-07 19:27 | 2026-05-07 | 2026-05-08 09:39 | 2026-06-10 | 2026-06-10 12:39 |  |  |  |  | 2026-06-26 | 2026-06-30 15:26 | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-28 |  | 2026-06-11 | 2026-06-11 16:22 | Site is RTMI | 2026-04-26 | 2026-04-26 22:06 | 1262064 | 227171 | 0 | 0 | 0 | 0 | 1382952.6943 | 230413 | 2026-06-11 16:27:46 +0530 | Shraddha Pansare | There is a discrepancy in the initial quotation hecne there is hurdle for DEM payment collection. | 2026-06-11 16:26:41 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-06-11 16:26:17 +0530 | Shraddha Pansare | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion Based on meeting, below is a list of all the requirements that were discussed during the meeting: | 2026-06-12 | 2026-06-26 13:21 | 2026-07-01
19694 | Turnkey | 2026-01-01 | Mr. Sunil Gorakh Vhanavate | Arihant Aspair | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | vinaya thakur |  | Active | Prospect | 10% Payment | 1127852 | 9999 | 0 | 0 | 0 | 55 | 0 | 102786 | 112785 | 459860 | 442421.2 |  |  | 2026-04-26 | 2026-04-26 21:57 | 2026-05-05 | 2026-05-07 14:02 | 2026-08-31 |  | 2026-09-07 |  | 2026-09-14 |  | 2026-09-21 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-09-08 |  | 2026-09-16 |  | 2026-09-17 |  |  |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 | [6 empty] | 2026-10-15 |  | 2026-10-24 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-25 |  | 2026-10-27 |  |  |  | 2026-11-18 |  | 2026-11-20 |  | 2026-11-21 | [5 empty] | 2026-09-25 |  | 2026-09-03 |  | Unknown | 2026-04-26 | 2026-04-26 21:51 | 0 | 0 | 0 | 0 | 0 | 0 | 958094 | 169758 | 2026-05-05 21:13:40 +0530 | Moksh Mehta | DCM: Client Name:- Sunil Vhanavate Property:- Arihant Aspire Possesion Date:- Dec'26 Sq Ft:- Sqft, Della - 601 No of Members: - Couple (40+) & Parents ( 70+), Daughter (18+) Sir in Mechanical Engineer, Mam is Home Maker Budget:- 8-10L not ready to stretch nor disclosing the extended the Budget. Ent: - Shoe Rack (10-15 Pairs)Wall Concepts Living :- Seating Capacity for (5 -6 Persons)TV Unit (50") without Display options4-Seater Dining Table Mandir unit on the top left side of the living areaBreakfast Counter for Two People on the right wall of the kitchen Kitchen:- Base Units x 2NosWall Units x 2NosLoft Units x 1 Nos Master Bedroom:- Queen size bedSide TableWardrobe with Loft with DresserTV Ledge Bedroom :- Daughter's Bedroom Queen Size BedWardrobe with loftStudy Table Washroom:- Vanities :- 2 Nos.Additional Shoe Rack in SS area | [6 empty] | 2026-09-08 |  | 2026-09-15
19696 | Turnkey | 2026-01-01 | Archana Sheth | Lodha divino | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 7150529 | 9999 | 7150529 | 0 | 0 | 65 | 0 | 705054 | 715053 | 2913902 | 2806520.8 |  |  | 2026-04-26 | 2026-04-26 22:01 | 2026-05-07 | 2026-05-07 13:59 | 2026-05-10 | 2026-05-11 13:06 | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-04-26 | 2026-04-26 21:58 | 6059770 | 1090758 | 0 | 0 | 0 | 0 | 6059770 | 1090758 | 2026-05-07 13:56:57 +0530 | Moksh Mehta | Some Image was uploaded | 2026-04-28 13:49:23 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-04-26 21:57:04 +0530 | Unknown | About the Customer **Introduction and Scope of Work Inquiry** Agent Jamshed from Bonito Designs contacted Archana regarding interior design for her 4 BHK property in Sion, Mumbai, with possession expected in six months. Archana is considering converting it to a 3 BHK and inquired about the scope of work, specifically if civil and electrical work are included. **Budget Estimation and Service Clarification** The agent clarified that electrical work and extension are included, but civil work depends on specific requirements. A preliminary budget estimate of 20-25 lakhs was provided for end-to-end interiors for a 4 BHK with 1680 sq ft carpet area, emphasizing the benefit of starting the design process now given the six-month possession timeline. **Appointment Scheduling and Next Steps** Archana agreed to visit the Thane experience center on the upcoming Sunday. The agent offered a cab facility for pick and drop and requested the property layout and name (Lodha Divino) to share with the team. A personalized WhatsApp invitation will be sent. **Customer Stage and Immediate Next Steps** The customer's immediate next step is to visit the Thane experience center on the upcoming Sunday for a consultation. The agent has committed to sending a personalized WhatsApp invitation and arranging cab services for the visit. **Customer Needs and Concerns** Archana's primary need is interior design for her new 4 BHK property, with a key concern about the inclusion of civil and electrical work. She is also exploring the possibility of converting the 4 BHK to a 3 BHK. The agent provided a budget estimate and emphasized the benefits of early engagement. **Customer Engagement History** This is the first interaction summarized, where the agent introduced Bonito Designs, discussed the property details, clarified service inclusions, provided a preliminary budget, and successfully scheduled a visit to the experience center. **Recommended Follow-up Actions** Recommended follow-up actions include confirming the appointment details with Archana, ensuring the property layout and name are received for team preparation, and following up with the personalized WhatsApp invitation as committed. | 2026-05-19 |  | 2026-05-26
19697 | Turnkey | 2026-01-01 | Sachin Mehta | UNIQUE VISTAS | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1632582 | 9999 | 0 | 0 | 0 | 79 | 0 | 153259 | 163258 | 715826 | 590239.2 |  |  | 2026-04-26 | 2026-04-27 12:05 | 2026-05-13 | 2026-05-13 11:22 | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-04-26 | 2026-04-27 12:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1385832 | 246750 | 2026-06-05 13:29:20 +0530 | Maasoumeh Raza | CDP: The client did not proceed with the booking due to budget constraints. Our quotation was in the range of 15.31 lakh, whereas the client's expectation was to complete the project within a budget of approximately 10 lakh. | 2026-06-05 13:20:02 +0530 | Maasoumeh Raza | CDP: meeting link Recap: 19697 - Celebrity Design Presentation (CDP) with the customer Thursday, May 28 ¦ Meeting ¦ Microsoft Teams | 2026-05-13 10:58:06 +0530 | Yerra Bharat | DCM: Sachin Mehta -Â Â Unique Vistas, 10th floor, possession in July tentative.Â Â refuge area below this floor.Â 2adults, + kids (18y, 11y boys).Â Entry:Â Shoerack kids each one has 20pairsÂ Â safety door, normal lock.Â Living and Dining:Â 6 people dining table.Â TV & sofa for 6 people.Â Pooja:Â with floor clarence raised from floor level, full standingÂ Â South wall parent's photosÂ Â Two balconies connected to living room.Â Main door placement needs suggestion.Â SimpleÂ Â Wall paper use is also ok.Â Kitchen:Â wants to have door sliding.Â Kitchen is fully finished,Â Â Mixer use is more, microwave less use.Â Â Rollup shutter need to see can be fitted.Â For water has an RO but doesnt drink directly from RO, need space for Mud pot.Â Washing machine in the balcony connected to kitchen.Â Storeroom:Â Â Converted from washroom,Â Â Need storage for grain, suitcases and lower shelves need to be of more height.Â Door solution for the room.Â Bedroom 1 : Bedroom near kitchen.Â For 18y of son, studying +2, 6 height, into music, guitar.Â Sliding wardrobe with loft.Â Queen size bed, bed placement have to be seen.Â Fixed study table with book storage.Â Vanity and shower partition in connected washroom.Â Bedroom 2: Converted from kitchen space.Â Single bed, for younger son,Â Single person wardrobe.Â Mirror can be on shutter.Â Vanity unit in the common washroom.Â Masterbedroom:Â queen size,Â Â sidetables with drawer on one sideÂ wardrobe with loft space.Â Dressing unit.Â Washroom Vanity, shower partition..Â Â wall papers are ok,Â Â dont need heavy designs, simple design.Â Light colors are preferred, not loud colors or furniture.Â Concealed handles, and locks on every wardrobe.Â Natural color temp. Lighting. (not warm tone than lightning in the meeting cabins)Â Space for Godrej locker in master bedroom.Â Â Budget 12L said 14L is the max.Â Â but said 3BHK interiors will go up to 18-20LÂ He has a hard stop of 15-16L in budget.Â Talked about a complete breakup. And has electrical, civil, and painter persons.Â Have to call on 21st to confirm CDP for 24th as family is travelling to their home town. | 2026-06-05 |  | 2026-06-12
19700 | Turnkey | 2026-01-01 | Saumitra Rawat | Sobha Royal Pavilion W12 | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 1598702 | 9999 | 0 | 0 | 0 | 66 | 0 | 149871 | 159870 | 639481 | 639480.8 |  |  | 2026-04-26 | 2026-05-10 20:32 | 2026-05-01 | 2026-05-15 11:49 | 2026-05-09 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-06-08 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-05-26 |  | 2026-06-03 |  | 2026-06-04 |  |  |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 | [6 empty] | 2026-07-02 |  | 2026-07-11 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-14 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-12 |  | 2026-05-21 |  | Unknown | 2026-04-26 | 2026-05-02 18:19 | 0 | 0 | 0 | 0 | 0 | 0 | 1354832 | 243869 | 2026-05-01 14:42:36 +0530 | Ankita Agarwal | DCM:MOM Mrs. Soumitra & FamilyProject: Residence Interior Design Location: Sarjapur SRP Date: (Add date) Client DetailsFamily Members: 3 Adults + 1 Kid (2 years Samarth)Facing: East Facing (North Entrance)Theme: Contemporary MinimalColor Preference: Neutral base with subtle pop colorsBudget: 2025 LakhsScope: Full home interiors (No loose furniture)1. Foyer AreaShoe unit (2530 pairs capacity)Design to include mix of drawers & shutters (decorative, not plain)Optional seating provisionDecorative wall with mirror elementsGypsum curved design with mirror detailingSoft curved edges in passage design2. Living RoomTV unit on kitchen-side wallCrockery + pooja unit on Bedroom 3 wallOpen pooja unit (no shutters for mandir section)Provision for base ottomanCurved edges for TV & crockery (to be cost evaluated)No overhead storageFloating/suspended TV unitWall finish options:Texture paint / subtle wallpaper (no prints)Half wall paneling with trimsSofa layout:3+2 or L-shape (without back bulk)2 accent armchairsSofa backdrop:Wall trims + textured wallpaperDining:4-seater with bench seating3. Pooja UnitSitting-height designSpace for:67 small idols1 medium Krishna idol (highlight circular niche)34 photo framesOpen concept with blinds provisionMarble countertop (outsourced under Bonito scope)Integrated with crockery unit4. Passage AreaFeature photo wallUneven beading design detailingFinal design to be selected based on visual fit5. Kitchen (10 x 8)Base + wall units (maximum storage)Granite countertop (clean clutter-free slab)Microwave integrated in wall unit90 cm refrigerator spaceLoft storage includedUtility planning:Dedicated space for mixer & air fryer6. Utility AreaSink provided by builderProvision for future dishwasherOverhead storage units7. Bedroom 2 (Kids Room Blue Theme)Existing workstation retainedL-shaped study (to be finalized based on space)Overhead shelvingWindow seatingSofa-cum-bed (space-based suggestion)Wardrobe: Aristo8. Master BedroomKing-size bedBed repositioned (opposite current wall)Feature bed-back wall designWindow seating (based on layout feasibility)Wardrobe: Existing (Aristo)Dresser unit included9. Bedroom 3 (Guest Bedroom)Study + TV unit combinationWindow seatingWardrobe with bed centeredLoft storage above wardrobeLayout to be optimized10. BathroomsVanity with storageGlass partition (half division)Essential storage unitsReference designs to be shared11. BalconySeating with storageDecorative wall treatment ideasMarble countertop12. Additional RequirementsMinimal false ceiling across 3BHKKids room ceiling design (playful element)Spot lighting (under cabinets & highlights) | [6 empty] | 2026-05-26 |  | 2026-06-02
19701 | Turnkey | 2026-01-01 | Hemant jain | Rohan Ekanta | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 2338986 | 9999 | 2338986 | 0 | 0 | 57 | 0 | 223900 | 233899 | 940412 | 930776.4 |  |  | 2026-04-25 | 2026-05-02 18:41 | 2026-05-13 | 2026-05-13 14:52 | 2026-05-16 | 2026-05-19 15:43 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-04-25 | 2026-05-02 18:30 | 1982191 | 356794 | 0 | 0 | 0 | 0 | 1982191 | 356794 | 2026-05-14 20:00:49 +0530 | Priyamvada PV | CDP MOM dated : 14.05.26 1. TV unit back wall design to be done as per modern themeÂ 2. Pooja to face entry wall of 2'W with blinds & bottom storage cum seating 3. Sofa wall will have beadings projected but in curved shape only with peacock wallpaper inside 4. Crockery storage is fine 5. TV required base storage with drawer storage 6. Bench not needed instead will have chairs 7. Dining ceiling wallpaper to be modern 8. Roller shutter 1.5'D instead of tall appliance unit with pullout for mixer 9. Wicker basket below counter level and tandem,Â 10. L corner base to be blind corner (mechanism but with shelf) ref to be shared 11. Addn'l tandem on left of blind corner unit 12. Island counter with tandem drawers required 13. Utility as per new changes, top load WM opp to door, cyl unit to left then sink unit, wall storage facing WM on left wall 14. Island counter with 3'W around, as done in the 3D modelÂ having tandem drawers & dining side & living side back panel to be highlighted , with open space on left 15. GBR - WR of 6 doors with inbuilt side table storage from left corner with mirror above as per previous, new side table on right side, wall storage with glass above study next to WR left | 2026-05-13 14:43:30 +0530 | Priyamvada PV | Name : Hemant JainÂ Â Profession : IT Property :Â Rohan Ekanta Site access date : Jun'26 Site possession date : june'26Â Family members : 5 adults Kids : 2 kids, Shaurya 7 yrs , 1 expected Main door : East facing Budget : 15-20L (For modular furniture excluding loose furniture, lights, appliances) Foyer: Shoe unit with seating, wall elements outside entrance(name plate, plants)Â wall decor inside foyer area (storages optional) Living: TV unit with drawers, tall units with storages, wall decor, puja unit with drawers with stool below Bi fold doors with swing, wall decors behind sofa (Rajasthani theme) NO FALSE CEILING- With profile lights Kitchen: Double door fridge provision, tall appliance unit, tandem units+ steel units, gas cylinder provision, aquagard provision, lofts until ceiling, pantry unit shelves, bottle pull out, granite (breakfast counter/ island counter both designs) Dining: Crockery unit (tall/ base unit) Chandelier in dining area Round or oval dining table with wall mounted bench.Â Utility: Wash basin, provision for washing machine. Common washroom: Vanity unit+ mirror Master Bed: Bay window seating with open selves and with swing wardrobes with loftÂ Bed side table with mirror, foldable study unit beside bay window, wall elements behind bed.Â King size bed with head rest.Â Master bed bathroom: Mirror with vanity unit.Â Kids Bedroom: Swing wardrobe (drawers) with lofts Parents Bed: Swing wardrobe with lofts, study unit, bed side table, wall decors behind bed.Â Provision for AC in Living and 3beds.Â Queen size bed for parents bed with storages and head rest. Vanity with mirror for parents bed. Color:Â earth tones, light tones of color, Rajasthani theme. Laminates matt. |  |  |  | 2026-05-27 |  | 2026-06-03
19702 | Turnkey | 2026-01-01 | Ankush Rawle | Arth | MUM - GOR | Yes | Swapnali Shedekar | Reshma Melanta | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 903405 | 209999 | 1292731 | 0 | 0 | 6 | 0 | 0 | 0 | 358706 | 334700 |  |  | 2026-04-27 | 2026-04-27 13:28 | 2026-04-27 | 2026-04-27 13:57 | 2026-05-01 | 2026-05-01 21:18 | 2026-07-10 | 2026-07-09 18:50 | 2026-07-15 |  | 2026-07-22 |  | 2026-05-01 | 2026-05-04 11:55 | 2026-05-02 | 2026-05-05 14:28 | 2026-05-05 | 2026-05-06 12:42 | 2026-05-09 | 2026-05-09 15:45 |  |  |  |  | 2026-05-09 | 2026-05-04 11:55 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-05-10 | 2026-07-09 18:46 | Site is RTMI | 2026-04-27 | 2026-04-27 12:56 | 1097633 | 195097 | 0 | 0 | 0 | 0 | 1093267.552 | 178039 | 2026-06-17 18:54:45 +0530 | Swapnali Shedekar | Transition has been done, IM has to be aligned according to the Cx. confirmation once the civil work is completed which is in Cx.scope Note - CIVIL WORK , FALSE CEILING AND ELECTRICAL IS IN CIENT SCOPE | 2026-06-12 13:13:25 +0530 | Shweta Dalvi | Some Image was uploaded | 2026-05-09 15:40:11 +0530 | Reshma Melanta | Possession - RTMI Currently CIVIL WORK IS GOING ON WHICH WILL BE DONE IN 8 - 9 DAYS CLIENT WILL UPDATE THE SAME IN THE GROUP IM - CAN BE ALIGNED POST THE SAME. ADDED MYSELF TO THE GROUP | 2026-07-10 | 2026-07-09 18:53 | 2026-07-16
19705 | Turnkey | May'26 | Manish Vichare | Shiv parbat | MUM - Thane | Yes | [8 empty] | vinaya thakur |  | Active | Prospect | 10% Payment | 2480612 | 9999 | 0 | 0 | 0 | 64 | 0 | 238062 | 248061 | 1075128 | 909362 |  |  | 2026-04-27 | 2026-04-27 17:39 | 2026-04-30 | 2026-05-07 17:48 | 2026-05-12 |  | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-05-20 |  | 2026-05-28 |  | 2026-05-29 |  |  |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 | [6 empty] | 2026-06-26 |  | 2026-07-05 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-06-06 |  | 2026-05-15 |  | Unknown | 2026-04-27 | 2026-04-27 17:36 | 0 | 0 | 0 | 0 | 0 | 0 | 2105015 | 375597 | 2026-05-08 15:40:56 +0530 | Pooja Nakul Sharma | DCM: Hi, 19705 - Manish VichareÂ 2 kids, parents husband & wife dining to be planned Â 2 opt for the layoutÂ placement for the dining areaÂ mandir as per directionÂ sofa seating provision beside the mandirÂ 1st opt - breakfast counter and corner storageÂ parallel kitchenÂ sink to be placed as per vastuÂ dining area provision if possibleÂ b1 will be parents room queen size bed can be plannedÂ dresser beside wardrobe ' wardrobe with loftÂ study if possibleÂ B2 will be master bedroomÂ wardrobe with dresser on the sideÂ arm chair if possibleÂ false ceiling in all roomÂ overall modern style, open spaces, light color combinationsÂ b3 will be study cum guest roomÂ sofa cum bed provisionÂ study unit instead of wardrobeÂ civil in cx scopeÂ civil changes can be done as per the design proposedÂ opt 2Â mbr door and study room door placement to be shifted towards the cornerÂ so the center wall can b utilised for the tvÂ wall near to the kitchen can be utilised for the dining insteadÂ rest room orientation will be sameÂ budget 15 - 20 excluding civilÂ | 2026-04-28 13:47:44 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-04-27 17:35:28 +0530 | Unknown | About the Customer **Inquiry About Visit and Family Emergency** The agent, Akriti from Bonito Designs, called to inquire about a scheduled visit. The customer informed the agent about a death in the family, making it impossible to attend the appointment. **Customer Unable to Attend Due to Death and Call Conclusion** The customer explained that due to a death in a relative's house, they would be unable to come for the scheduled appointment. The agent acknowledged the situation, and the call concluded without rescheduling or further discussion. **Current Customer Stage and Immediate Next Steps** The customer's immediate next step is to deal with the family emergency, which has caused them to miss their scheduled appointment. No new appointment was booked. **Customer's Primary Needs and Objectives** The customer's primary need was to attend the scheduled visit, but this was prevented by a family emergency. Their main objective was to proceed with the interior design consultation, which is now on hold. **Customer's Engagement History** The customer's engagement history shows a scheduled visit that could not be attended due to an unforeseen family emergency. The call concluded without rescheduling. **Recommended Follow-up Actions** Recommended follow-up actions include reaching out to the customer after a suitable period to reschedule the visit, acknowledging their difficult circumstances. | 2026-05-20 |  | 2026-05-27
19712 | Turnkey | May'26 | rushabh solani | Dahisar | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 3839563 | 9999 | 0 | 0 | 0 | 75 | 0 | 373957 | 383956 | 1728701 | 1342949.6 |  |  | 2026-04-28 | 2026-05-01 20:06 | 2026-04-28 | 2026-05-01 22:53 | 2026-05-01 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-05-25 |  | 2026-05-04 |  | 2026-05-05 |  | 2026-05-05 |  | 2026-05-06 | [5 empty] | 2026-05-12 |  | 2026-05-20 |  | 2026-05-21 |  |  |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-31 | [6 empty] | 2026-06-18 |  | 2026-06-27 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-30 |  |  |  | 2026-07-22 |  | 2026-07-24 |  | 2026-07-25 | [5 empty] | 2026-05-29 |  | 2026-05-07 |  | Unknown | 2026-04-28 | 2026-04-28 12:39 | 0 | 0 | 0 | 0 | 0 | 0 | 3253867 | 585696 | 2026-05-05 13:06:27 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-04-28 18:47:27 +0530 | Moksh Mehta | DCM: Client Name:- Rushabh Solani Property:- Lodha Divino Possesion Date:- In Hand Sq Ft:- 1121 Sqft, Tower 3, A-1002 No of Members: - Couple (40+) for MBD & Parents ( 70+), Son (11+) Business into chemicals & Mam is as School Teacher Budget:- 25-35L Ex of White Goods Ent: - Shoe Rack (25-30 Pairs)Football cum sports stand (existing)Wall ConceptsSafety at the entrance (if Possible) Living :- Seating Capacity for (6-7 Persons)TV Unit (65") without Display options only sound bar 6 or 8 -Seater Dining TableCrockery Unit Mandir unit with door or without door both the options to be explored. Kitchen:- Sliding DoorBase Units x 2NosWall Units x 2NosLoft Units x 1 NosUtility Counter Master Bedroom:- King size bedSide Table cum DresserWardrobe with LoftTV Ledge (43") Bedroom 3:- Son's Bedroom Queen size bed Wardrobe with loftStudy Table facing the windowSide table with the mirror on wallTheme to be suggested by Cx Bedroom 2:- Parent's Bedroom King size BedWardrobe Unit Additional Wardrobe TV Spacing (43")Bed Side table with MirrorLighter shades of Grey & White's Wall design would be suggested by CxArmchair possibility to be checked Washroom:- Vanities :- 3Nos | 2026-04-28 13:50:18 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-05-12 |  | 2026-05-19
19713 | Turnkey | May'26 | Samir Mishra | Wadhava wise city | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Hold | Preproduction | DEM2 | 850508 | 170102 | 1127392 | 0 | 0 | 7 | 22 | 0 | 0 | 351110 | 329296 |  |  | 2026-04-28 | 2026-04-28 13:34 | 2026-05-01 | 2026-05-01 13:01 | 2026-05-04 | 2026-05-02 15:12 | 2026-06-11 | 2026-06-11 19:43 | 2026-10-01 |  | 2026-10-08 |  | 2026-05-02 | 2026-04-30 | 2026-05-03 | 2026-05-08 13:29 | 2026-05-08 | 2026-05-08 14:14 | 2026-05-23 | 2026-05-23 12:25 |  |  |  |  | 2026-06-11 | 2026-06-16 13:09 | 2026-10-03 |  | 2026-10-04 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-14 | [6 empty] | 2026-11-01 |  | 2026-11-10 |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-13 |  |  |  | 2026-12-05 |  | 2026-12-07 |  | 2026-12-08 | [5 empty] | 2026-10-12 |  | 2026-05-24 | 2026-06-09 16:09 | Site is RTMI | 2026-04-28 | 2026-04-28 13:31 | 955417 | 171975 | 0 | 0 | 0 | 0 | 988962.163 | 163297 | 2026-06-16 13:15:43 +0530 | Akshay Ds | Project HOLD til sep End | 2026-06-09 13:00:19 +0530 | Sayed Byahatti | DDM2: 19713 - Samir Mishra DDM1 - 9th/06/26 , 12:30am Living area - Wall Beading frames vertical long length, not double keep single single. Master bedroom - Remove beading and wallpaper. kids bedroom - Remove Beading & wallpaper Double shutter wardrobe same as MBR 1ST Wardrobe, Full white profile light for study unit.Â Dining Area - Add pendent hanging light. Entrance - Shoes Rack add 1 or 2 shelfs for more storage.Â ALL ROOM KIDS BEDROOM, MASTER BED ROOM,KITCHEN,BALCONY ADD NORMAL LIGHTS PAINT IS CLIENT SCOPEÂ | 2026-06-07 15:22:24 +0530 | Sayed Byahatti | DDM2: 19713 - Samir Mishra DDM1 - 7th/06/26 , 12:30am TV unit - Side wall remove panning, add charcoal beading.30x12mm Remove louvers from back sofa wall. ALL House Lights from Bonito scope. Master Bedroom - Dresser unit mirror ovel shape. Remove panning, add wallpaper along with beading. Pooja Unit - Add internal 2 shelves as short one not full length. Kids room - Bottom storage for study unit to shift near wardrobe. | 2026-06-12 | 2026-06-11 19:48 | 2026-10-02 |  | Under Construction | 2026-06-01
19715 | Turnkey | May'26 | Rahul Yadav | Kalpataru ELlitus | MUM - Thane | Yes | Vaishnavi Sawant | Anamika Dolai | Anil Kuwar | [5 empty] | Aryan Singh |  | Active | Preproduction | DEM2 | 810568 | 172199 | 1019710 | 0 | 0 | 10 | 0 | 0 | 0 | 334522 | 303847.2 |  |  | 2026-04-28 | 2026-04-28 20:08 | 2026-06-16 | 2026-06-16 16:25 | 2026-06-21 | 2026-06-23 11:29 | 2026-07-03 | 2026-07-07 16:35 | 2026-07-15 |  | 2026-07-22 |  | 2026-06-23 | 2026-06-23 11:47 | 2026-06-24 | 2026-06-23 13:08 | 2026-06-23 | 2026-06-24 17:26 | 2026-06-25 | 2026-06-25 20:12 |  |  |  |  | 2026-07-01 | 2026-06-25 20:13 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-06-26 | 2026-07-05 12:25 | Site is RTMI | 2026-04-28 | 2026-04-28 15:37 | 864161 | 155549 | 0 | 0 | 0 | 0 | 864161.2825 | 145902 | 2026-06-25 20:15:15 +0530 | Anamika Dolai | Done, Milestones explained. | 2026-06-24 17:26:00 +0530 | Sanjana Swami |  | 2026-06-24 16:20:50 +0530 | Aryan Singh | Some Image was uploaded | 2026-07-08 | 2026-07-07 16:59 | 2026-07-16 |  | Under Construction | 2026-06-24 | 2026-06-21 | 172199 | Ravi Roy
19716 | Turnkey | May'26 | shradha n k | Birla Tisya | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 1441469 | 9999 | 0 | 0 | 0 | 75 | 0 | 134148 | 144147 | 589689 | 563486.4 |  |  | 2026-04-27 | 2026-05-01 12:58 | 2026-05-19 | 2026-05-19 18:56 | 2026-05-03 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-04-27 | 2026-04-29 18:38 | 0 | 0 | 0 | 0 | 0 | 0 | 1221584 | 219885 | 2026-05-29 12:07:25 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-04-28 15:22:47 +0530 | Unknown | About the Customer **Customer Property Details** Customer Shraddha has a 4 BHK apartment in Rajajinagar, Birla Tisya, with possession expected in June or July. She is looking for complete home interiors. **Budget Range Hesitation** Customer is hesitant to provide a budget range, preferring to hear the quote first. Agent mentioned a minimum ticket size of 7 lakhs for 4 BHK and a broad range of 10-40 lakhs. **Experience Center Visit Pending Confirmation** Tentative experience center visit scheduled for today at 4:30 PM, pending confirmation with husband. Customer will provide an update via WhatsApp within an hour. **Next Steps: Location Share & Floor Plan** Agent to share experience center location via WhatsApp. Customer to share floor plan on the same WhatsApp number. |  |  |  | 2026-05-30 |  | 2026-06-06
19717 | Turnkey | May'26 | Truptesh Gosalia | * | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 1881946 | 333068 | 2319812 | 0 | 0 | 46 | 0 | 0 | 0 | 877144 | 671734 |  |  | 2026-04-28 | 2026-05-09 00:06 | 2026-04-29 | 2026-05-09 00:08 | 2026-05-12 | 2026-05-09 00:18 | 2026-05-27 | 2026-05-27 17:05 | 2026-07-01 |  | 2026-07-08 |  | 2026-05-09 | 2026-05-09 19:08 | 2026-05-10 | 2026-05-09 19:49 | 2026-05-09 | 2026-05-12 18:06 | 2026-05-19 | 2026-05-19 14:01 |  |  |  |  | 2026-05-27 | 2026-05-30 15:53 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-05-20 | 2026-05-27 14:59 | Site is RTMI | 2026-04-28 | 2026-04-28 15:45 | 1965942 | 353869 | 0 | 0 | 0 | 0 | 2212157.2575 | 365254 | 2026-06-27 20:17:35 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-27 19:55:15 +0530 | Reshma Melanta | Some Image was uploaded | 2026-06-23 13:52:25 +0530 | Reshma Melanta | PID 19717 - Truptesh Gosalia Measurements: Out for all bedrooms. Design Updates: Bathroom design is pending. 3rd bedroom needs a sofa-cum-bed. Magic corner (L-corner) removed as it is not required. Commercials: Net estimation is 16,65,340. Quotation/estimation discussion is yet to happen. Action Required: The CX has requested a change in designer. | 2026-05-28 | 2026-05-27 17:09 | 2026-07-02 |  | Under Construction | 2026-05-30
19719 | Turnkey | May'26 | Priya Singhi | DNR ARISTA | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Ravikiran K |  | Active | Preproduction | DEM2 | 1789109 | 313936 | 2033686 | 0 | 0 | 31 | 0 | 0 | 0 | 810175 | 664998 |  |  | 2026-04-28 | 2026-05-10 20:31 | 2026-05-08 | 2026-05-11 13:41 | 2026-05-14 | 2026-05-13 18:35 | 2026-06-14 | 2026-06-14 18:47 | 2026-07-12 |  | 2026-07-27 |  | 2026-05-13 | 2026-05-14 10:45 | 2026-05-14 | 2026-05-16 12:23 | 2026-05-16 | 2026-05-18 13:35 | 2026-05-19 | 2026-05-19 13:04 |  |  |  |  | 2026-05-28 | 2026-06-14 16:08 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-07-31 |  | 2026-05-20 | 2026-05-26 17:10 | Site is RTMI | 2026-04-28 | 2026-04-30 11:59 | 1726483 | 307202 | 0 | 0 | 0 | 0 | 2052208.9656 | 338889 | 2026-05-24 18:54:38 +0530 | Vishal Haridas | Minutes of Meeting held on Date: 24-05-2026 FOYER L -Shaped Foyer unit have to be considered. Tall cabinet should come on the right sideTall unit should Sleek designBase cabinets should be floor mounted KITCHEN Sleek Partition have to be added near fridgeOpen storage below breakfast tableCylinder unit near tall cabinetProvision for keeping Drinking water Pot have to be considered below Water Purifier cabinet. UTILITY Janitor unit have to be added in utility area.Sink with drainboard will be provided by the builderStorage till Loft area is required KIDS BEDROOM Two design option for Kids bedroom have to provided. One with Bay window and one withoutPrefers to have Pastel colours ( Beige, white etc) Master Bedroom Dresser with Fluted Glass shutter tall unit on side Open storage have to added near the mirrorUsed clothes storage have to be added on WardrobeVanity Design have to changed in Master bedroom, Open storage should come in middle and closed cabinets on the sides.Wallpaper designs have to be send to ClientCurtain Pelmet have to considered above Balcony door GUEST BEDROOM TV Unit in Guest bedroom ( LEDGE )Study table reference is sent in the group by the client.Limewash paint idea can be considered on walls, Overall theme can be considered in Pastel colors | 2026-05-23 23:42:03 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-18 13:24:24 +0530 | Sanjana Swami | Spoke with the client He will be paying 10% by 28th May 2026 (after 1st DEM) clear with the offers. IMs to be planned on 19th May 2026 Client is only available on weekends for 1st DEM. | 2026-06-15 | 2026-06-14 18:55 | 2026-07-13 |  | RTMI
19720 | Turnkey | May'26 | Seema Sajdeh | * | MUM - GOR | Yes | Shweta Dalvi | Vishakha Vaishnav | Safalta Karkera |  |  | Nilesh Patel | Rizwan Mistry | Murali S | Sahil Sethi | Aakash Gaikwad | Active | Production | Dispatch Due | 2282669 | 0 | 0 | 0 | 2282669 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-28 | 2026-04-30 15:45 | 2026-04-29 | 2026-04-30 15:46 | 2026-04-30 | 2026-04-30 15:46 | 2026-05-01 | 2026-04-30 15:49 | 2026-06-19 | 2026-06-18 16:58 | 2026-06-18 | 2026-06-18 17:46 | 2026-04-30 | 2026-04-30 15:47 | 2026-05-01 | 2026-04-30 15:47 | 2026-04-30 | 2026-04-30 15:47 | 2026-05-01 | 2026-04-30 15:47 |  |  |  |  | 2026-04-30 | 2026-04-30 15:49 | 2026-06-19 | 2026-06-18 17:32 | 2026-06-19 | 2026-06-18 17:33 |  |  | 2026-06-19 | 2026-06-21 12:43 | 2026-06-21 | 2026-06-21 14:15 | 2026-06-22 | 2026-06-21 17:18 | 2026-06-22 | 2026-06-25 11:32 |  |  |  |  | 2026-06-25 20:04 | 2026-06-28 | 2026-06-27 21:03 | 2026-07-04 | 2026-07-02 19:16 | 2026-08-08 | 2026-06-25 11:28 | 2026-07-02 |  | 2026-07-26 |  | 2026-07-31 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-06-21 | 2026-06-25 20:03 | 2026-05-01 | 2026-04-30 15:48 | Site is RTMI | 2026-04-28 | 2026-04-30 15:45 | 0 | 0 | 0 | 0 | 1934465 | 348203 | 1934465 | 348203 | 2026-07-13 11:17:01 +0530 | Nilesh Patel | Modulars has been delivered at site 2 wardrobe carcass has been delivered at site Installation works is on hold for now as GKD team is working at site and site is not clear | 2026-06-21 17:17:51 +0530 | Pratima Kajwe | Some Image was uploaded |  |  |  | 2026-05-01 | 2026-04-30 15:49 | 2026-06-19 | 2026-06-18 16:59
19721 | Turnkey | May'26 | Pankaj Jage | Rustomjee La Familia | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 2054029 | 9999 | 2054029 | 0 | 0 | 64 | 0 | 195404 | 205403 | 829557 | 813666.4 |  |  | 2026-04-28 | 2026-04-28 17:49 | 2026-05-08 | 2026-05-11 14:00 | 2026-05-12 | 2026-05-20 12:16 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-05-28 |  | 2026-06-05 |  | 2026-06-06 |  |  |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-14 |  | 2026-05-23 |  | Unknown | 2026-04-28 | 2026-04-28 17:39 | 1740702 | 313326 | 0 | 0 | 0 | 0 | 1740702 | 313326 | 2026-05-09 13:35:08 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-05-09 13:32:09 +0530 | Krutika Vernekar | DCM: 636 sq ft 4 ppl Husband : Builder (only working) Kids : Teenagers Minimal + modern theme with functional storage focus. Living Room: 55 TV unit Minimal theme POP punning design on sofa wall Linear Dining Area: Dining near kitchen 4 seater Crockery unit + mandir placement planned Kitchen: Gas + Oven Below (foreign concept ) Appliances : Air Fryer , Food Processor , Microwave Utility storage needed in service slab Kids Bedroom: 33' TV 22" Wardrobe Wardrobe with loft (2) Wallpaper + LED automation Black/grey tinted glass on wardrobe Accessories + jewellery storage Black grey theme has sneaker shoes need a rack Irregular shape : Mirror Master Bedroom: Bed Fabricated Tv unit needed wardrobe + nice dresser Wall design behind bed General Design Notes: Neutral modern palette with subtle luxury touch Service Slab Storage Needed movable for broom and pocha | 2026-05-05 11:52:14 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-05-28 |  | 2026-06-04
19722 | Turnkey | May'26 | Ashish Gosalia | Jaykant Bliss | MUM - GOR | Yes | Khyati Bandi | Manzoor Shaikh | Safalta Karkera | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 1680019 | 331278 | 2328252 | 0 | 0 | 37 | 0 | 0 | 0 | 727027 | 621714 |  |  | 2026-04-28 | 2026-05-09 00:07 | 2026-05-06 | 2026-05-09 00:11 | 2026-05-09 | 2026-05-09 00:31 | 2026-05-24 | 2026-05-24 18:18 | 2026-07-01 |  | 2026-07-08 |  | 2026-05-09 | 2026-05-09 18:37 | 2026-05-10 | 2026-05-09 19:13 | 2026-05-09 | 2026-05-12 18:33 | 2026-05-17 | 2026-05-17 18:30 |  |  |  |  | 2026-05-24 | 2026-06-08 18:56 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-05-18 | 2026-05-24 18:10 | Site is RTMI | 2026-04-28 | 2026-05-07 19:26 | 1973095 | 355157 | 0 | 0 | 0 | 0 | 1998452.6888 | 329976 | 2026-06-18 11:06:29 +0530 | Khyati Bandi | MBR -Â 1. Cloth hanging unit one shelf for perfume 8" 2. Locker will be fixed with shelf heightÂ 3. Add one wall hung drawer below dresser unit, space between drawer and dressing unit will be 10" for SBÂ 4. Remove Side membrane panel for side tableÂ Living area - 1. 75" tv 2. Space to be leftÂ 3. Swing dimension to be givenÂ 4. TV unit height finished level 21" SONS ROOM - 1. Wardrobe loose shelvesÂ 2. L shape profile light in ceiling KITCHEN -Â 1. Microwave unit at standard height 21x18" 2. Flapup shutter above microwaveÂ | 2026-06-07 16:12:35 +0530 | Khyati Bandi | Sons room -Â 1. Ceiling - 6 Panel lights+ indirect light Cove light both the sideÂ Profile light above wardrobeÂ Profile light in ceilingÂ 3 shelves in washroom nicheÂ Kitchen -Â 1. Platform height 33" with pani pattiÂ MBR -Â 1. Panel lights+ profile lights+indirect light | 2026-06-04 19:28:47 +0530 | Khyati Bandi | Sons room -Â 1. Ceiling - 6 Panel lights+ indirect light Kitchen -Â 1. Platform height 33" with pani pattiÂ MBR -Â 1. Panel lights+ profile lights+indirect light | 2026-05-25 | 2026-05-24 18:20 | 2026-07-02 |  | Under Construction | 2026-05-30
19723 | Turnkey | May'26 | Spark Vision | Jaykant Bliss | MUM - GOR | Yes | Sonal Singh | Reshma Melanta | Kashmira Nerurkar |  | Anamika Ghate | Rajkumar Suthar | Sandeep Tiwari | Murali S | Avi Thakkar | Sunil Poojary | Active | Preproduction | Procurement | 713757 | 447710 | 1051207 | 780024 | 711227 | 3 | 0 | 0 | 0 | 0 | 266047 |  |  | 2026-04-28 | 2026-05-07 16:02 | 2026-05-02 | 2026-05-07 20:52 | 2026-05-09 | 2026-05-09 00:34 | 2026-05-23 | 2026-05-23 20:22 | 2026-06-13 | 2026-06-13 12:41 | 2026-06-16 | 2026-06-16 18:14 | 2026-05-09 | 2026-05-13 19:35 | 2026-05-10 | 2026-05-14 11:54 | 2026-05-14 | 2026-05-15 11:11 | 2026-05-19 | 2026-05-19 14:01 |  |  |  |  | 2026-05-23 | 2026-05-30 15:59 | 2026-06-14 | 2026-06-14 15:34 | 2026-06-15 | 2026-06-14 17:10 |  |  | 2026-06-19 | 2026-06-29 22:59 | 2026-06-30 | 2026-06-30 16:25 | 2026-07-01 | 2026-06-30 16:44 | 2026-07-01 | 2026-07-07 19:02 |  |  |  |  | 2026-07-12 09:16 | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-07-12 | 2026-07-12 09:15 | 2026-05-20 | 2026-05-23 20:15 | Site is RTMI | 2026-04-28 | 2026-05-02 15:57 | 890853 | 160353 | 893846.479 | 147588 | 857128.9274 | 141670 | 860338.5274 | 142056 | 2026-07-12 09:20:10 +0530 | Rajkumar Suthar | Execution: Key task closed : 12th July Key handover will be done by 22nd July Scope of work : Paint, pop cornice and modulars only | 2026-07-11 11:52:13 +0530 | Reshma Melanta | Others: | 2026-06-29 19:40:05 +0530 | Kashmira Nerurkar | Some Image was uploaded | 2026-05-24 | 2026-05-23 20:26 | 2026-06-14 | 2026-06-13 12:45 | RTMI
19724 | Turnkey | May'26 | Sandip Shah | MICL Aaradhya | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 994143 | 9999 | 0 | 0 | 0 | 70 | 0 | 89415 | 99414 | 441302 | 354012 |  |  | 2026-04-28 | 2026-04-28 20:06 | 2026-05-06 | 2026-05-06 11:25 | 2026-05-06 |  | 2026-05-13 |  | 2026-05-20 |  | 2026-05-27 |  | 2026-05-06 |  | 2026-05-07 |  | 2026-05-07 |  | 2026-05-08 | [5 empty] | 2026-05-14 |  | 2026-05-22 |  | 2026-05-23 |  |  |  | 2026-05-30 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-02 | [6 empty] | 2026-06-20 |  | 2026-06-29 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-02 |  |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-31 |  | 2026-05-09 |  | Unknown | 2026-04-28 | 2026-04-28 20:05 | 0 | 0 | 0 | 0 | 0 | 0 | 842494 | 151649 | 2026-05-06 13:15:16 +0530 | Yerra Bharat | DCM: MICL ghatkopar Tower Eden, 8th floor. 4BHK Living 4 Adults & 2-month-old baby Son is a distributor for Samsung. Wants to look at previous projects and talk to clients. Budget 25L (from their side), suggested it might go to 35- 40L on avg. Civil work if needed for the main door, needed safety door and digital lock. Their Vastu person suggested using MB-1, MB-2. But we said MB-1 is near the entrance, so for privacy and ease of movement, suggested MB-2, MB-3 can be for family, and MB-1 is for guest use. Entrance: safety door, Digital lock Welcome Foyer: good and decorative mirror paneling, Loose furniture with small table for sitting instead of shoe rack. as the MB-1 Door is exactly opp. To the main entrance, suggested Flush door with paneling to cover the existence of door. Living: Planing for 65TV or Frame TV (Samsung) or Projector. Sound system needed with ceiling speakers. Sofa 3-seater + 1 wing chair / 2-Seater. Swing reversable either to the living room side or towards the balcony. Need an end-to-end sofa with side tables. Sleek TV unit simple sober look is fine. Ok with no vertical units or excess storage options. Palning for cassette AC Deck: Need small temple style pooja unit for small idol. If not temple seating can be planned. Dining: As the is ideal for the pooja unit, we suggested moving the table towards living and placing the pooka unit near the window. 6-seater table, center rotation table (lazy Sussan style). Crockery Unit Opp to the pooja unit, with washbasin concealed style (not visible directly). No need for display style with glass. Fluted paneling on the side of the crockery unit. Kitchen: It is a finished kitchen, but must be checked for hardware, need multipurpose sink, need to check and see the location for dishwasher (location mentioned for washing machine in Builder plan) and pantry opp. To dishwasher. Bedroom 1 (MB-1): Has to be designed for visiting parents visits once or twice a year. 2 single beds / murphy bed side table (depending on possibility) Normal sliding style wardrobe with loft storage. No Tv unit Vanity Unit. Make the door flush rocking chair / recliner. Bedroom 2 (MB-2): Mr. & Mrs. Umang and their daughter. Aristo wardrobe with loft King Size bed with under storage hydraulic. Mirror on the wall near the window. Vanity and shower partition in the washroom. Bedroom 3 (MB-3): Mr. & Mrs. Sandeep. Aristo wardrobe with loft. Queen size with hydraulic under bed storage. recliner near the window, small ledge style storage behind or near bed, no side tables. Room layout needs to be changed- Wardrobe on the longer wall (with wardrobe + dressing unit + small wardrobe near the door). Vanity and shower partition in the washroom. Bedroom 3 (MB-4): Guest Need to additional door inside the bedroom to make the washroom as common washroom when needed. Chnage in layout, murphy bed. Sliding style wardrobe with loft space. Side table on one side. Fixed Study table which can be multipurpose. (to open heavy luggage bags or suitcases by keeping them on the table or work or study). Home Automation: smart switches in all rooms except MB-1, MB-2 which can be normal. Notes: Handles should be push to open or concealed handle. Cloths drying in the Living / Dining window. Wooden style flooring for the house. No side tables in the room unless said OK. (ok to MB-4, MB-1 and MB-2). No TV Units in the bedroom. Has photo frames (Jain photos) for the wall in foyer and living room, needs to be taken into consideration. Washing machine in the guest bedroom washroom.Â | 2026-05-01 21:59:33 +0530 | Aryan Singh | Some Image was uploaded | 2026-04-28 18:55:34 +0530 | Unknown | About the Customer **Property Details and Design Needs** Customer has a 4BHK apartment in Ghatkopar with soft possession and requires interior design for dining hall, hall, and bedrooms. Kitchen is already done. **Budget Alignment** Customer is comfortable with the estimated pricing of 15 to 20 lakhs for a 4BHK, which includes end-to-end solutions. **Appointment Confirmed for Today** Agreed to visit the Thane experience center today at 4 PM, despite traveling and weak network. **Agent to Confirm Appointment Details** Agent to send address via WhatsApp and confirm the appointment for today at 4 PM at the Thane experience center. | 2026-05-14 |  | 2026-05-21
19730 | Turnkey | May'26 | Chethan S Raju | Siddartha Solitaire | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP | [5 empty] | Pulivarthi Nirosha |  | Active | Design | DEM1 | 1182010 | 139999 | 1674741 | 0 | 0 | 62 | 0 | 0 | 96403 | 552539 | 393068.8 |  |  | 2026-04-28 | 2026-05-04 10:45 | 2026-05-05 | 2026-05-05 10:49 | 2026-05-08 | 2026-05-11 14:54 | 2026-07-11 |  | 2026-07-18 |  | 2026-07-31 |  | 2026-05-11 | 2026-05-13 11:29 | 2026-05-12 | 2026-05-13 11:32 | 2026-05-13 | 2026-05-14 10:01 | 2026-05-24 | 2026-05-24 19:37 |  |  |  |  | 2026-07-12 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-08-04 |  | 2026-07-07 |  | Site is RTMI | 2026-04-28 | 2026-04-28 20:08 | 1421768 | 252972 | 0 | 0 | 0 | 0 | 1399386.94 | 227768 | 2026-06-10 15:34:44 +0530 | Aishwarya C | in quotation there is a foldable table given and cost for the same is 3k aprox client understanding is 3k for the folding table near the kitchen entrance need to give clarity to client regarding that as per quote understanding is laminate finish for the all the rooms there is custom carpentry for partition | 2026-05-24 19:40:15 +0530 | Abhinandan K S | RTMI project Initial measurement is planned on 26th May 2026. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. Customer is not available till this weekend. Need to align the design discussion on 1st Week of June 2026. | 2026-05-14 10:01:09 +0530 | Bency Chacko | Some Image was uploaded | 2026-07-12 |  | 2026-07-19 |  | RTMI
19732 | Turnkey | May'26 | Akshara Anant | Shobha Sentosa | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 1614736 | 218420 | 2184195 | 0 | 0 | 61 | 0 | 0 | 104527 | 654614 | 637174.8 |  |  | 2026-04-28 | 2026-04-28 23:29 | 2026-04-29 | 2026-05-02 10:47 | 2026-05-05 | 2026-05-02 11:22 | 2026-07-22 |  | 2026-08-23 |  | 2026-08-30 |  | 2026-05-02 | 2026-05-07 11:10 | 2026-05-03 | 2026-05-12 13:40 | 2026-05-12 | 2026-05-15 08:03 | 2026-05-31 | 2026-05-31 19:23 |  |  |  |  | 2026-07-23 |  | 2026-08-25 |  | 2026-08-26 |  |  |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 | [6 empty] | 2026-09-23 |  | 2026-10-02 |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-05 |  |  |  | 2026-10-27 |  | 2026-10-29 |  | 2026-10-30 | [5 empty] | 2026-09-03 |  | 2026-07-18 |  | Unknown | 2026-04-28 | 2026-04-28 23:26 | 1853300 | 330895 | 0 | 0 | 0 | 0 | 1810617.227 | 296274 | 2026-05-28 12:57:13 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-24 19:50:03 +0530 | Abhinandan K S | Some Image was uploaded | 2026-05-15 00:22:23 +0530 | Athul Ajaykumar | The concerns have been addressed. We also received clarification via email. Accordingly, an amount of Rs. 2,35,000/- has been added to the quote under Additional Scope of Work towards appliances, loose furniture, and false ceiling work, which can be availed from Bonito Studio. | 2026-07-23 |  | 2026-08-24 |  | RTMI
19736 | Turnkey | May'26 | Ranganath BK | independent house | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1914042 | 10000 | 0 | 0 | 0 | 57 | 0 | 181404 | 191404 | 815373 | 715860.8 |  |  | 2026-04-29 | 2026-05-01 19:47 | 2026-05-08 | 2026-05-08 16:58 | 2026-05-11 |  | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-06-25 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-04-29 | 2026-04-29 16:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1622069 | 291972 | 2026-05-01 13:43:38 +0530 | Yogesh Patidar | Hi Mam/Sir, Sharing the Requirment Details here. Please if add anything is missed: Requirement for Rental Property 1BHK ( Overall Ceiling Height-10'5") Living Area: Pooja unit - wall unit 2feet x 2feet Tv unit only base unit Hidden door to be planned next to Tv unitÂ Kitchen: Base unit, Wall unit and LoftÂ Bedroom 1: Wardrobe ( hinged with loft) Dresser with 2 drawers Own House Requirement: Flooring Finish (Grey Marble - Laid already) Look and Feel to be very Appealing with Paneling, Rafter, Lights and Bright colors to be used. House warming is been planned in August. Painting will be Started in Coming week. 4 People will be staying including 2 kids All door colors wood finish Living area: Tv unit base unit Display unit on both side with glass shutter and Lights Back panel with raftersÂ Sound bar placement False ceiling with raftersÂ Sofa wall with decors/ wallpapers Paneling for beamÂ Curtain from ceiling Tv - 55inch Parents room: Wardrobe till window along with Loft Window seater with storage Bed with headboard (Panelling/ wallpaper) Dresser (Mirror inside shutter) Basic Island false ceilingÂ UnderstairsÂ Mirror and washbasin Understairs storageÂ (Just Shutters) Step lighters are been provided KitchenÂ Hob and chimney next to windowÂ Sink with purifier on top unit Microwave space Fridge single door Rolling shutter Loft on both side Option and single side option to be shown Breakfast counter with panel and lightsÂ Dining Space: Table 6 seater Pooja Mandir -Teak door for Pooja cnc Pooja Internal -Base unit 2feet height Window seating near dining space( Opposite to Pooja) Entrance panelling in kitchenÂ Staircase Area: window with glass and Frame ( In Staircase area and Double Height wall) Double height wall glass and frame (Size 7*7) Skylight glass with CNC design 1st floor - Common Space Study area L shape for one person with Base and Wall unit Double height wall design Master Bedroom Wardrobe sliding with loft( External Space) Headboard with cot and Bed wall design Walkin wardrobe with loft and dresserÂ False ceiling DesignÂ Kids room Headboard with cot False ceiling (optional( Design to be shown)Â Walkin with dresser and loft Colors -Mix of Pink and blue as it will be used by both the Kids. Book shelf and study table Design Presentation has been aligned on Saturday/ Sunday (9-10th May 1st Half | 2026-04-29 11:36:59 +0530 | Unknown | About the Customer **Customer Visit Booked for Saturday Afternoon** The customer, Rangnath, has booked an experience center visit for Saturday between 2 PM and 4 PM. This follows an initial inquiry via Facebook regarding home interiors. **Property and Budget Details** Rangnath is looking for minimalistic interiors for his 4 BHK independent house in Nagarbhavi, with possession expected in August. His budget for interiors is between 10 to 15 lakhs. **Bonito Design Services and Offers Explained** Agent Preeti from Bonito Design detailed the company's services, emphasizing their ISO certification, a 10-year product warranty with a 1-year service warranty, and current offers including an 18% discount and no-cost EMI. The experience centers in HSR and HRBR Layout were highlighted. **Appointment Confirmation and Follow-up Details** The appointment was confirmed for Saturday between 2 PM and 4 PM, with Rangnath agreeing to visit with his family. Preeti committed to sending a WhatsApp invitation with location and project details, and requested floor plans. **Recommended Follow-up Actions** The customer is currently in the lead stage, with a confirmed experience center visit scheduled for Saturday. The next steps involve the customer attending the visit with his family and potentially sharing floor plans. |  |  |  | 2026-05-19 |  | 2026-05-26
19737 | Turnkey | May'26 | Ankur singh | Godrej Urban Park | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 1773552 | 9999 | 0 | 0 | 0 | 71 | 0 | 167356 | 177355 | 785657 | 633184.8 |  |  | 2026-04-26 | 2026-05-05 15:44 | 2026-04-30 | 2026-05-05 15:45 | 2026-05-09 |  | 2026-05-15 |  | 2026-05-22 |  | 2026-05-29 |  | 2026-05-08 |  | 2026-05-09 |  | 2026-05-09 |  | 2026-05-10 | [5 empty] | 2026-05-16 |  | 2026-05-24 |  | 2026-05-25 |  |  |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 | [6 empty] | 2026-06-22 |  | 2026-07-01 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-04 |  |  |  | 2026-07-26 |  | 2026-07-28 |  | 2026-07-29 | [5 empty] | 2026-06-02 |  | 2026-05-11 |  | Unknown | 2026-04-26 | 2026-04-30 19:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1503010 | 270541 | 2026-05-05 15:33:02 +0530 | Priyanka Patel | DCM: 1. Name of the customer Ankur Singh 2. Profession NA 3. Project Name/Tower Name/Flat Number 2BHK 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK 5. Site Access Date 2026-05-01 6. Possession Date 2026-05-01 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 1000000 Customer Preferences8. Who will be living in the house? Single 9. What activities do you usually prefer at your home ? Prayer, Relaxing and Unwinding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any YES 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials NO JAZZY COLOURS AND 15. Do you have any existing furniture that must be accommodated? YES 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Dcor & Living Room1. Whats the primary use of your living room? TV Focus 2. Must-have furniture or features? TV unit, Coffee table, Puja unit, Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Heritage items, Travel souvenirs 4. False ceiling required Dining & Kitchen1. Any special furniture? Crockery unit, Bar Unit 2. Must-have appliances? Fridge, Hob, Chimney, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser 4. False Ceiling Required - Master Bedroom 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Laundry space, Washing machine space, Top Storage Balcony & Outdoor1. How do you intend to use your balcony? 2. Outdoor Mood How do you intend to use the utility Cloths Drying Miscellaneous1. Timeline related commitment made by Bonito, if any no 2. Other commitments made by Bonito to customer, if any no 3. What are offers committed to customers? yes 4. Move-in date confirmed with customer 2026-09-30 5. Any special occasion mentioned by the customer wrt handover date Before Navratri 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 1000000 | 2026-04-29 12:07:57 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-04-29 12:03:06 +0530 | Unknown | About the Customer **Customer Books Experience Center Visit** The customer, Ankush, has booked a visit to the Bonito Designs experience center for next Sunday at 11 AM for an interior design consultation. This follows an initial inquiry and discussion about his property details and budget concerns. **Customer Concerns and Property Details** Ankush expressed concerns about a previous negative sales experience and emphasized the need for a mature discussion. He also questioned the minimum budget requirement of 10-12 lakhs for his 2BHK property in Godrej Urban Park, indicating a potential budget sensitivity. **Addressing Concerns and Service Overview** The agent assured Ankush that a senior manager would handle his visit to address past issues and discussed the standard 60-90 day timeline for 2BHK interiors, highlighting personalized design and comprehensive services within the package. The agent also confirmed that Ankush would attend the visit alone. **Appointment Confirmation and Follow-up** The agent committed to sending a WhatsApp confirmation for the scheduled visit. The call concluded with the booking of the experience center visit for next Sunday at 11 AM, with the agent ensuring a senior manager would be present to provide a better experience. | 2026-05-16 |  | 2026-05-23
19740 | Turnkey | May'26 | Milli Shah | Dosti Mezzo | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 2368752 | 473750 | 3352577 | 0 | 0 | 22 | 0 | 0 | 0 | 992266 | 902736 |  |  | 2026-04-29 | 2026-05-02 13:01 | 2026-05-12 | 2026-05-12 18:10 | 2026-05-15 | 2026-05-29 15:52 | 2026-06-23 | 2026-06-23 13:49 | 2026-06-26 |  | 2026-07-08 |  | 2026-05-17 | 2026-05-29 14:33 | 2026-05-30 | 2026-05-30 14:11 | 2026-05-30 | 2026-05-30 18:15 | 2026-06-05 | 2026-06-05 19:11 |  |  |  |  | 2026-06-23 | 2026-06-23 19:14 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-06 | 2026-06-13 11:19 | Site is RTMI | 2026-04-29 | 2026-04-29 18:03 | 2841167 | 511410 | 0 | 0 | 0 | 0 | 2831825.3957 | 458580 | 2026-06-30 13:37:02 +0530 | Meet Shah | Some Image was uploaded | 2026-06-24 10:50:37 +0530 | Priyanka Murarka | DDM2: 23 JUNE PARENTS ROOM Laminate - 638 LUV siciliy bright 7706 SD Brick Wood - all main doors & countertop Handle - black - BD-HNA-2025-0152 GUEST ROOM Laminate - 5571 STN Creme Marguina 1661 HM Brown Rattan cane same handle in parents room MBR 8231 CL coffee 638 LUV sicily bright same handle in parents room All room doors 1587 SD Harley Marble 1587 LUV harsley Marble | 2026-06-14 16:09:15 +0530 | Priyanka Murarka | DDM1: 13th June GUEST ROOM IB without storage queen size mirror on the right side of IB with folding table lime wash on walls & ceiling profile lights in ceiling design - 100 mm drop Removed the 2 slim wardrobes from both sides of IB BEDROOM1 - PARENTS ROOM bed - 4'x6' custom work with 2 drawer mechanism Ledge to be added b/w both wardrobes Laminate finish 1 sensor light outside washroom bottom side Left side single wardrobe to have a mirror inside the wardrobe 1 full length mirror on left panel of double door wardrobe Profile light on ceiling MBR 1 full mirror next to side table wall & ceiling on window side to have beading design dressing with mirror storage at back and the same counter to be used as a study table 2 hanging light provision on both sides of side table LIVING ROOM Dining space to have a arch design which will have traditional wallpaper inside it. Peripheral false ceiling design Shoe cabinet behind door - end to end which will have cornice moulding & wall sticker inside it. At back of sofa to have arch design wherein pop punning design to be done inside it. KITCHEN 160MM tall pantry unit to be provided next to appliance tall unit - custom carpentry work Dish drainer set of 900mm to be provided next to aqua unit. Dry & wet dustbin to be given Matka placement along with provision for keeping glasses Roll tissue paper accessory to be provided Chimney left side wall cabinets to be removed & placed 2 ledges. Sliding shutter for door entrance to be provided new SBs to be added on column on service platform on surface box All wall shutters to be in glass finish for service side platform All modular internals have been finalized along with decor elements. ceiling designs also confirmed. All references are saved in the folder. | 2026-06-24 | 2026-06-23 13:54 | 2026-06-27 |  | Under Construction | 2026-07-10
19743 | Turnkey | May'26 | Nibhu's Kitchen | Devagiri Opal | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Design | 20% Payment | 1016919 | 139999 | 1349115 | 0 | 0 | 3 | 0 | 0 | 63385 | 422050 | 391485.2 |  |  | 2026-04-28 | 2026-05-12 14:22 | 2026-05-19 | 2026-05-19 13:49 | 2026-05-22 | 2026-05-19 15:54 | 2026-07-12 | 2026-07-12 15:18 | 2026-07-18 |  | 2026-09-06 |  | 2026-05-19 | 2026-04-30 | 2026-05-20 | 2026-05-28 13:10 | 2026-05-28 | 2026-06-25 18:04 | 2026-07-11 | 2026-07-03 12:47 |  |  |  |  | 2026-07-12 |  | 2026-09-01 |  | 2026-09-02 |  |  |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 | [6 empty] | 2026-09-30 |  | 2026-10-09 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-12 |  |  |  | 2026-11-03 |  | 2026-11-05 |  | 2026-11-06 | [5 empty] | 2026-09-10 |  | 2026-07-12 | 2026-07-12 14:38 | Site is RTMI | 2026-04-28 | 2026-04-29 20:29 | 1143318 | 205797 | 0 | 0 | 0 | 0 | 1132400.943 | 186775 | 2026-07-14 17:44:20 +0530 | Rajeshwari S | Welcome call done along with Designer Non RTMI Project. Client has permission for IM and CM. Execution can start only after OC which is end of Sept. 1st Design meeting is done on 12th July. 10% payment will be done by 15th. Aligned with process. | 2026-07-08 16:19:17 +0530 | Alekhya Korada | . | 2026-07-08 15:45:47 +0530 | Alekhya Korada | Recap: RGM meeting of Ms.Bhuvaneswari 29 April ¦ Meeting ¦ Microsoft Teams RGM recording link | 2026-07-13 | 2026-07-12 15:21 | 2026-07-19 |  | Under Construction | 2026-07-31
19744 | Turnkey | May'26 | Diksha Sinha | Brigade | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Preproduction | Site Readiness 1 | 1954126 | 390825 | 2687593 | 0 | 0 | 16 | 0 | 0 | 0 | 806849 | 756452.4 |  |  | 2026-04-29 | 2026-04-30 18:49 | 2026-04-30 | 2026-04-30 18:53 | 2026-05-03 | 2026-04-30 19:00 | 2026-06-29 | 2026-06-29 17:30 | 2026-12-06 |  | 2026-12-13 |  | 2026-04-30 | 2026-04-30 | 2026-05-01 | 2026-05-02 12:25 | 2026-05-02 | 2026-05-08 15:23 | 2026-05-17 | 2026-05-17 17:59 |  |  |  |  | 2026-06-30 | 2026-06-29 17:26 | 2026-12-08 |  | 2026-12-09 |  |  |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-18 |  | 2026-12-19 | [6 empty] | 2027-01-06 |  | 2027-01-15 |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-18 |  |  |  | 2027-02-09 |  | 2027-02-11 |  | 2027-02-12 | [5 empty] | 2026-12-17 |  | 2026-05-18 | 2026-06-28 11:55 | Site is Non-RTMI | 2026-04-29 | 2026-04-30 18:26 | 2277621 | 409971 | 0 | 0 | 0 | 0 | 2243582.3619 | 383510 | 2026-07-14 15:09:55 +0530 | Akshay Ds |  | 2026-07-14 15:04:54 +0530 | Purva Shiravle | site will be on hold till December | 2026-06-28 19:29:18 +0530 | Purva Shiravle | DDM1: Layout finalisation done for full home Living roomÂ 1. Sofa backwall design - to be retain as per cdp 2. pooja unit shifted to study room KitchenÂ 1. Add slab on opposite of hobÂ 2. (2 options req.)Â with tall unit and w/o tall unit Bedrooms 1.wall concepts are yet to be finalised | 2026-06-30 | 2026-06-29 17:32 | 2026-12-07 |  | Under Construction | 2026-05-08
19746 | Turnkey | May'26 | Asit Kumar Gachhayat | Sipani Royal Heritage | BNG - HSR | No Estimate | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-29 | 2026-05-19 13:03 | 2026-04-30 |  | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-05-18 |  | 2026-05-26 |  | 2026-05-27 |  |  |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 | [6 empty] | 2026-06-24 |  | 2026-07-03 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-06-04 |  | 2026-05-13 |  | Unknown | 2026-04-29 | 2026-04-30 11:45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-30 12:24:59 +0530 | Nayan Reddy | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion Cx Name - AsitKumarÂ Â Crm - RavikiranÂ RGM -30/04/26 Move in date -Â AugustÂ Budget -10LÂ Informed cx ragarding budget - 13L -15L Property name -Sipani royal heritageÂ Direction - N facingÂ F to c -Â Â 9.6 Brick Constrctioi Open for suggestion on themes and colour KitchenÂ Fridge - 800mmÂ Granite -Â Bonito SideÂ no changes is foor planÂ oven ,mixer - tall unitÂ Cylinder cabinetÂ Base unitÂ wall unitÂ LoftÂ Chimney panelÂ UtilityÂ Sink cabinetÂ wall cabinetÂ Handwash cabinet opp to sink unitÂ Dining areaÂ 6 seater dining tableÂ crockery unit wall cabinet onlyÂ Living area 3 + 2 saeter sofaÂ Tv unitÂ suspended drawerÂ Display unitÂ 55" tvÂ Pooja unit near kitchen wallÂ facing balconyÂ Foyer areaÂ End to end Storage unit for shoe rackÂ False ceiling in living and dining areaÂ Master bedroomÂ Wardrobe and loftÂ and small wardorbe near toilet areaÂ DressingÂ Bedroom (GBR) 12 x 10 Wardrobe and LoftÂ dresserÂ bed placemnt near tv sideÂ need on work stattion and tv unitÂ 40" tvÂ Bedroom (KBR) 10 x 9Â Wardrobe and LoftÂ Study tableÂ dresserÂ WashroomÂ vanity cabinets in all washroomÂ | 2026-04-30 11:45:20 +0530 | Unknown | About the Customer **3BHK Property with August Possession** Customer Ashish Kumar requires complete home interiors for his 3BHK property, Sipani Royal Heritage, with possession expected in August. **Budget of 8-10 Lakhs** Customer's interior design budget is between 8-10 lakhs. **HSR Experience Center Visit Booked** Customer agreed to visit the HSR experience center tomorrow at 11 AM. **Floor Plan to be Shared** Customer will share the floor plan via WhatsApp. **Appointment Confirmed for Tomorrow** Agent confirmed the appointment for tomorrow at 11 AM at the HSR experience center. |  |  |  | 2026-05-18 |  | 2026-05-25
19747 | Turnkey | May'26 | Chandra Mohan | upvan tower | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Safalta Karkera | [5 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1219048 | 9999 | 1219048 | 0 | 0 | 73 | 0 | 111906 | 121905 | 507301 | 467937.6 |  |  | 2026-04-29 | 2026-04-30 16:08 | 2026-05-03 | 2026-05-03 11:51 | 2026-05-07 | 2026-05-03 13:52 | 2026-05-10 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-03 |  | 2026-05-04 |  | 2026-05-04 |  | 2026-05-05 | [5 empty] | 2026-05-11 |  | 2026-05-19 |  | 2026-05-20 |  |  |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-30 | [6 empty] | 2026-06-17 |  | 2026-06-26 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-29 |  |  |  | 2026-07-21 |  | 2026-07-23 |  | 2026-07-24 | [5 empty] | 2026-05-28 |  | 2026-05-06 |  | Unknown | 2026-04-29 | 2026-04-30 12:34 | 1033091 | 185956 | 0 | 0 | 0 | 0 | 1033091 | 185956 | 2026-05-03 11:46:42 +0530 | Anjali Singh | DCM: JAMMULA FAMILY-Â FINANCE CONSULANT - FARMA INDUSTRY VP // SAME BUSINESSÂ 3 peopleÂ 1 son(12 y/o)and couple EAST FACING vastu remedy for southwest door mainÂ MORDERN + TRADITIONAL NO DUST MAGNETSÂ WIDE AIRYÂ NO DARK COLOUR SCHEMESÂ VASTU WILL BE SEENÂ ENTRANCE SPACE REMEDY AND OUTSIDEÂ BALCONY- auto-water dripping in plantsÂ drainageÂ specific place for docx , meds , sports items , linen , woolens , toiletries , trunks , extra furniture ,Â PLANTERS MAINLY, WATER COLLECTIONÂ SHADE IN BALCONYÂ AC placements to be replacedÂ Mandir (existing)(krishna) sitting - vastuÂ WASHROOM DOORS - PLASTIC TO BE CHANGEDÂ DECAL = VINYL SHEETSÂ ENTERTAINMENT ROOM -Â LIVING AND DINING -Â 3+2 SEATING SOFAÂ 6 seater dining - personalized (personalized interior space.) retain sofa and rocking chair. tv unitÂ crockeryÂ KITCHEN-Â no tall shelfsÂ acc to heightÂ whole kitchen to be changed without breaking the slabÂ same HOBÂ acqa guardÂ appliancesÂ microwaveÂ otgÂ appliance unit // juicer heightÂ small fridge to be removedÂ BPOÂ INVERTER TO BE PLACED ABOVE BIG SINK IN UTILITY . FOLDABLE PARTITION IN WOODEN is available , need to see if we can accomdate that anywhere. ------- FAMILY GATHERING /HANGOUT ROOM =Â cosy , comfortable , tv unitÂ mandir to be dedicatly have a space. ONE EXTRA STORAGE for hanging clothes should have a depth of minimun 2'Â SONS roomÂ - study + play + sleepÂ -lower sitting in bay windowÂ -study + book shelfsÂ wall mounted pullup barÂ existing dressing table is thereÂ Toys , sportsÂ what he likes : hangout for friendsÂ reader , making stuff / is creative Master Bedroom- peacefulÂ king size bedÂ hanging daily use clothesÂ small study unitÂ dresser + mirrorÂ internal doors - sameÂ Â NO FALSE CEILINGÂ washroom -Â make a storageÂ shower change 2 washroom tiles to be changed , only floor sir - plan walls , minimalÂ ma'am - elegance and warmth (art work)Â small storages in balcony in entertainment room and master in north to store janitor stuff , ladder 10th floorÂ 1001- house on budget-Â 15 lakh everythingÂ - 16 MAXÂ NOT APPLIANCESÂ AVOID ARCHS AS DUST MAGNETSÂ 11-12PM , 1 may 2026 - cdp | 2026-04-30 12:33:46 +0530 | Unknown | About the Customer **Call Rescheduled for Evening** Customer requested to reschedule the call for 6:00 PM due to being in the office. **Agent Confirmed Reschedule Time** Agent confirmed the rescheduled time with the customer. |  |  |  | 2026-05-11 |  | 2026-05-18
19748 | Turnkey | May'26 | Shubham Bhanushali | Tsaaya | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 1600006 | 9999 | 0 | 0 | 0 | 74 | 0 | 150002 | 160001 | 713255 | 566749.6 |  |  | 2026-04-30 | 2026-05-02 13:10 | 2026-04-30 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-05-17 |  | 2026-05-25 |  | 2026-05-26 |  |  |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 | [6 empty] | 2026-06-28 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-23 |  | 2026-07-28 |  |  |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-06-03 |  | 2026-05-12 |  | Unknown | 2026-04-30 | 2026-04-30 13:29 | 0 | 0 | 0 | 0 | 0 | 0 | 1861800.699 | 304705 | 2026-04-30 14:54:30 +0530 | Khushi Khandelwal | DCM: 3BHK 815 SqftÂ 6 members Posession-Soft (may end) 9th floorÂ EAST-WEST facing EntranceÂ Safety doorÂ Shoe unitÂ Paneling LIVING & DINING AREA AC on dining wall TV unit with Mandir unitÂ 3+1+1 seater Storage on dining wall No dining Flush door for bedroom-01 BEDROOM-01 (Parent's bedroom) WardrobeÂ Side table cum dresser Tall unit storage beside bed King size bed Study table foldable with wall unit Â Washroom-Vanity storage below basin and above WC ledge wall KITCHEN Base cabinet Wall cabinet Loft in U shaped Appliances-Washing machine, Ref., Chimney provision, Microwave BEDROOM-02 Sister's bedroomÂ Wardrobe with loft Queen size bed/ sofa cum bed BEDROOM-03 Master bedroom Wardrobe with loft Bed-king size Side tableÂ Dresser | 2026-04-30 13:28:34 +0530 | Unknown | About the Customer **Current Customer Stage and Next Steps** The customer is in the process of gathering information for interior design services with Bonito Designs. They have shared initial requirements and are scheduled to visit the experience center in Andheri next week or the week after for a more detailed discussion and to view sample setups. One customer is traveling and will visit after one week, while another has already spoken with a representative named Pooja. **Customer Needs and Objectives** The customer's primary need is for comprehensive interior design services, including furniture, POP, electrical, and paint work, with a specific request for maximum storage and no civil work for their new 2.5 BHK property. They are seeking a tentative estimate and information on Bonito's USPs and latest work before committing to a visit. **Customer Engagement History** Across multiple interactions, agents from Bonito Designs have followed up on interior design inquiries. One customer is providing a floor plan and video for a tentative estimate and has scheduled a visit. Another customer is traveling and has postponed their visit by a week. A third interaction indicated the customer had already spoken with another representative, Pooja, and seemed slightly annoyed by the follow-up. **Unrelated Call Interactions** One call summary indicates a voicemail left by a customer referencing Holi, with subsequent interactions involving different agents and companies (Global Tech Solutions, Bajaj Finance), suggesting potential misdirected calls or separate customer service issues not related to Bonito Designs. **Recommended Follow-up Actions** Follow up with the customer to confirm the exact date and time for the experience center visit next week, ensuring all necessary details, including catalogs and USPs, are sent via WhatsApp as promised. For the customer who has already spoken with Pooja, it's crucial to verify their status and avoid redundant contact. |  |  |  | 2026-05-17 |  | 2026-05-24
19750 | Turnkey | May'26 | Vk Sharma | Dreams Society Bhandup west | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  |  | Snehankit Agre | Aditya Vikram |  | Nishtha Valawalkar |  | Hold | Preproduction | Site Readiness 1 | 809509 | 200839 | 914946 | 0 | 0 | 2 | 55 | 0 | 0 | 338238 | 270432 |  |  | 2026-04-30 | 2026-04-30 16:46 | 2026-05-08 | 2026-05-08 17:04 | 2026-05-08 | 2026-05-08 17:10 | 2026-05-20 | 2026-05-19 11:56 | 2026-09-01 |  | 2026-09-08 |  | 2026-05-08 | 2026-05-08 19:29 | 2026-05-09 | 2026-05-08 20:20 | 2026-05-08 | 2026-05-13 09:42 | 2026-05-14 | 2026-05-14 19:01 |  |  |  |  | 2026-05-15 | 2026-05-09 19:05 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-12-01 |  | 2026-12-02 |  | 2026-12-03 |  | 2026-12-04 | [6 empty] | 2026-12-22 |  | 2026-12-31 |  | 2026-12-30 |  | 2026-12-31 |  | 2027-01-01 |  | 2027-01-03 |  |  |  | 2027-01-25 |  | 2027-01-27 |  | 2027-01-28 | [5 empty] | 2026-12-02 |  |  |  |  | 2026-04-30 | 2026-04-30 16:44 | 779070 | 135875 | 0 | 0 | 0 | 0 | 779069.5344 | 131233 | 2026-07-10 19:48:22 +0530 | Divya Rahangdale | The project is on hold until November, as the client is currently abroad. | 2026-06-29 13:26:17 +0530 | Harshali Bhuyar | Project is on hold till November,as client is in abroad. | 2026-06-11 12:34:40 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-20 | 2026-05-19 12:01 | 2026-09-02
19752 | Sub Project |  | Shilpi Rai | Bren Zahara | BNG - HSR |  | Priyanka Mathur | Akshay Ds | Kowshik |  |  | Yogeshwaran | Ranjith Kumar | Murali S |  | Sunil Kumar S M | Active | Installation | Execution | 3666 | 3667 | 0 | 0 | 3666 | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 | 2026-05-05 15:46 | 2026-05-01 | 2026-05-05 15:46 | 2026-05-05 | 2026-05-05 15:46 | 2026-05-06 | 2026-05-05 15:47 | 2026-05-06 | 2026-05-05 15:48 | 2026-05-06 | 2026-05-05 15:50 | 2026-05-05 | 2026-05-05 15:46 | 2026-05-06 | 2026-05-05 15:46 | 2026-05-05 | 2026-05-05 15:46 | 2026-05-06 | 2026-05-05 15:46 |  |  |  |  | 2026-05-05 | 2026-05-05 15:47 | 2026-05-06 | 2026-05-05 15:49 | 2026-05-06 | 2026-05-05 15:49 |  |  | 2026-05-06 | 2026-05-05 15:57 | 2026-05-06 | 2026-05-05 16:26 | 2026-05-10 | 2026-05-09 19:31 | 2026-05-10 | 2026-05-09 19:31 |  |  |  |  | 2026-05-26 16:28 | 2026-05-30 | 2026-05-30 13:19 | 2026-06-01 | 2026-05-30 15:55 | 2026-05-31 | 2026-06-03 16:52 | 2026-05-30 | 2026-07-02 07:36 | 2026-07-02 | 2026-07-02 07:36 | 2026-07-04 |  |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-05 | 2026-05-09 19:31 | 2026-05-06 | 2026-05-05 15:47 | Unknown | 2026-04-30 | 2026-05-05 15:46 | 0 | 0 | 0 | 0 | 45480 | 8186 | 45480 | 8186 | 2026-06-10 15:32:13 +0530 | Ranjith Kumar | Execution: | 2026-06-02 18:38:39 +0530 | Yogeshwaran | Execution: stylish project |  |  |  | 2026-05-06 | 2026-05-05 15:47 | 2026-05-06 | 2026-05-05 15:48
19755 | Turnkey | May'26 | Mr sandeep Mahadik | DGS Sheetal Ekta | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 1971848 | 9999 | 0 | 0 | 0 | 76 | 0 | 187186 | 197185 | 865091 | 712387.2 |  |  | 2026-04-30 | 2026-04-30 18:29 | 2026-05-05 |  | 2026-05-14 |  | 2026-05-21 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-15 |  | 2026-05-16 | [5 empty] | 2026-05-22 |  | 2026-05-30 |  | 2026-05-31 |  |  |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 | [6 empty] | 2026-06-28 |  | 2026-07-07 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-08 |  | 2026-05-17 |  | Unknown | 2026-04-30 | 2026-04-30 18:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1673345 | 298503 | 2026-05-14 13:19:39 +0530 | Sweta Bhise | DCM: 1. Name of the customer sandeep mahadik 2. Profession service 3. Project Name/Tower Name/Flat Number DGS sheetal ekta 4. Typology (1BHK, 2BHK, 3BHK, etc) 2bhk 5. Site Access Date 2026-08-15 6. Possession Date 2026-08-15 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 900000 Customer Preferences8. Who will be living in the house? 9. What activities do you usually prefer at your home ? 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] NA 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials 15. Do you have any existing furniture that must be accommodated? 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? 2. How would you like your entrance to feel? 3. False ceiling required -yes Dcor & Living Room1. Whats the primary use of your living room? 2. Must-have furniture or features? 3. Choose your decor inspirations 4. False ceiling required Dining & Kitchen1. Any special furniture? 2. Must-have appliances? 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Bedrooms1. Master Bedroom - Bed type 2. Master Bedroom - Wardrobe style 3. Master Bedroom - Additional units 4. False Ceiling Required - Master Bedroom 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) | [6 empty] | 2026-05-22 |  | 2026-05-29
19756 | Turnkey | May'26 | Geeta | independent house | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Shijin C C | Jairam Joshi |  | Raghavendra S |  | Hold | Preproduction | DEM2 | 1134535 | 226907 | 1465989 | 0 | 0 | 43 | 5 | 0 | 0 | 453814 | 453814 |  |  | 2026-04-30 | 2026-04-30 19:26 | 2026-05-09 | 2026-05-09 13:50 | 2026-05-12 | 2026-05-09 13:58 | 2026-05-27 | 2026-05-27 19:42 | 2026-06-26 | 2026-06-25 11:46 | 2026-07-26 |  | 2026-04-30 | 2026-05-08 18:59 | 2026-05-10 | 2026-05-09 17:13 | 2026-05-09 | 2026-05-13 13:53 | 2026-05-15 | 2026-05-15 18:46 |  |  |  |  | 2026-05-27 | 2026-05-28 12:57 | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-05-21 | 2026-05-27 19:38 | Site is RTMI | 2026-04-30 | 2026-04-30 19:03 | 1242364 | 223625 | 0 | 0 | 0 | 0 | 1198943.8595 | 204216 | 2026-06-19 12:46:37 +0530 | Sandeep Madhukar Achari | Some Image was uploaded | 2026-05-15 18:52:12 +0530 | Rajeshwari S | Welcome call done RTMI Project. Independent house. Clients wants to start with the design phase immediately as there is a delay for more than 15 days from the date of booking. IM scheduled on 19th May First Design meeting to confirm by Designer. Estimation close for Rs.11,40,000/- after all the offers informed about the 10% to be paid after 1st design meeting and Initial measurement. Informed about timeline. | 2026-05-13 13:53:21 +0530 | Sanjana Swami | Site is RTMI. Client has civil work ongoing at the site in the kitchen area. When informed that the civil work needs to be completed before conducting the IMs, the client mentioned that she can pause the civil work and would prefer to complete the IMs firstshe would complete her work after Bonito's scope of work Client is available for both the IMs and the 1st DEM. Transaction will be B2C self-funding. Client is clear with the timelines, offers, and payment milestones. Checklist is clear. | 2026-05-28 | 2026-05-27 19:44 | 2026-06-26 | 2026-06-25 11:49 | RTMI
19758 | Turnkey | May'26 | Anand Jayaraman | Purva Atmosphere | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal |  |  | Harshit Choudhary | Saddam Hussain Z M |  |  | Abdul Shafeen | Active | Design | DEM3 | 1445094 | 289019 | 2062034 | 0 | 0 | 10 | 0 | 0 | 0 | 611929 | 544146.4 |  |  | 2026-04-30 | 2026-05-13 14:13 | 2026-05-19 | 2026-05-19 11:00 | 2026-05-19 | 2026-05-19 11:45 | 2026-06-07 | 2026-06-07 18:02 | 2026-07-01 | 2026-06-30 14:41 | 2026-07-20 |  | 2026-05-19 | 2026-05-20 11:22 | 2026-05-20 | 2026-05-21 18:06 | 2026-05-21 | 2026-05-22 17:52 | 2026-05-28 | 2026-05-28 14:20 |  |  |  |  | 2026-06-13 | 2026-06-15 17:07 | 2026-07-02 | 2026-07-03 10:29 | 2026-07-04 | 2026-07-05 12:55 |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-24 |  | 2026-05-29 | 2026-06-03 10:29 | Site is RTMI | 2026-04-30 | 2026-04-30 20:05 | 1747486 | 314547 | 0 | 0 | 0 | 0 | 1725235.61 | 284866 | 2026-06-07 18:49:34 +0530 | Vishnu S | Some Image was uploaded | 2026-06-03 13:35:54 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-03 13:16:49 +0530 | Surabhi Ravichandran | Some Image was uploaded | 2026-06-08 | 2026-06-07 18:04 | 2026-07-01 | 2026-06-30 14:42 | RTMI
19762 | Turnkey | May'26 | Jimit Vijay Parekh | Velvet Puri | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1059014 | 211803 | 1478130 | 0 | 0 | 34 | 0 | 0 | 0 | 464848 | 382363.2 |  |  | 2026-04-30 | 2026-05-19 12:39 | 2026-05-19 | 2026-05-19 22:09 | 2026-05-22 | 2026-05-19 22:17 | 2026-06-12 | 2026-06-11 12:45 | 2026-06-27 | 2026-06-27 19:21 | 2026-07-03 |  | 2026-05-19 | 2026-05-19 22:38 | 2026-05-20 | 2026-05-20 15:48 | 2026-05-20 | 2026-05-25 18:27 | 2026-05-26 | 2026-05-26 18:47 |  |  |  |  | 2026-06-11 | 2026-06-11 18:23 | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-05-27 | 2026-06-11 12:44 | Site is RTMI | 2026-04-30 | 2026-05-19 12:38 | 1252653 | 225477 | 0 | 0 | 0 | 0 | 1252652.481 | 197822 | 2026-06-27 19:28:43 +0530 | Manisha Dubey | DDM2: Minutes of Meeting held on Date: 25/06/2026 A back panel with lights will be provided on the kids' bedroom bed wall. A fixed study table with drawers will be installed in the kids' room. A glass partition will be provided in the master bedroom bathroom. The master bedroom wardrobe shutters will be finished with glass doors. Wall storage has been added in the utility area. A mandir has been added in the living area. The client will proceed with the L-shaped kitchen execution. Cross measurements will be scheduled only after the kitchen work is completed. A plain false ceiling with profile lighting has been finalized. Light grey paint has been selected for the kids' room. All finalized material selections have already been shared in the project group. | 2026-06-27 19:28:06 +0530 | Manisha Dubey | DDM1: DEM 1 MOMÂ 04/06/26 1. Living Area Double curtain to be consider TV size consider: 55 inches. Crockery unit to be added in the living room. Pooja unit to be added in living near the diningÂ 2. Kids Bedroom 1 tall unit added for books. Study table removed. Folding study panel provided. Mirror to be placed on the wall between the bed and wardrobe. 3. Master Bedroom Hidden drawer to be added in wardrobe. 2 shelves added in the wardrobe. Mirror to be provided above the side table. Plain ceiling design with profile lighting. Hanging light to be provided above the side table. 4. Kitchen Tall unit to be added (subject to feasibility). Folding panel to be provided in the kitchen. The master bedroom should have a peach color theme. Laminate and material selection will be done in the next meeting. | 2026-06-03 11:28:56 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 | 2026-06-11 12:47 | 2026-06-28 | 2026-06-27 19:21 | Under Construction | 2026-06-05
19763 | Turnkey | May'26 | Dharmin Vijay Parekh | Girnar Residency | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Preproduction | DEM2 | 1115241 | 223048 | 1537543 | 0 | 0 | 22 | 23 | 0 | 0 | 466439 | 425754 |  |  | 2026-04-30 | 2026-05-02 21:22 | 2026-05-19 | 2026-05-19 22:07 | 2026-05-19 | 2026-05-19 22:18 | 2026-06-12 | 2026-06-12 19:41 | 2026-11-02 |  | 2026-11-09 |  | 2026-05-19 | 2026-05-19 22:20 | 2026-05-20 | 2026-05-20 15:49 | 2026-05-20 | 2026-05-25 18:21 | 2026-05-26 | 2026-05-26 18:36 |  |  |  |  | 2026-06-13 | 2026-06-12 17:56 | 2026-11-04 |  | 2026-11-05 |  |  |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 | [6 empty] | 2026-12-03 |  | 2026-12-12 |  | 2026-12-11 |  | 2026-12-12 |  | 2026-12-13 |  | 2026-12-15 |  |  |  | 2027-01-06 |  | 2027-01-08 |  | 2027-01-09 | [5 empty] | 2026-11-13 |  | 2026-06-08 | 2026-06-12 18:47 | Site is RTMI | 2026-04-30 | 2026-05-02 21:19 | 1303003 | 234540 | 0 | 0 | 0 | 0 | 1303002.277 | 206143 | 2026-07-02 16:53:27 +0530 | Vishakha Vaishnav | Others: CX will receive the possession in month of October | 2026-05-28 17:24:33 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-28 17:14:37 +0530 | Vishakha Vaishnav | Cx said that he is available for the meeting after 8th June 2026 in week days only as he is on vacation | 2026-06-13 | 2026-06-12 19:43 | 2026-11-03 |  | Under Construction | 2026-10-31
19765 | Turnkey | May'26 | Sachindra Patil | Regency Luxuria | MUM - Thane | Yes | [8 empty] | Saloni Chawan |  | Active | Prospect | DCM Due | 1560848 | 9999 | 1560848 | 0 | 0 | 75 | 0 | 146086 | 156085 | 720435 | 528243.6 |  |  | 2026-05-01 | 2026-05-01 15:33 | 2026-05-01 | 2026-05-07 14:14 | 2026-05-14 |  | 2026-05-21 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-15 |  | 2026-05-16 | [5 empty] | 2026-05-22 |  | 2026-05-30 |  | 2026-05-31 |  |  |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 | [6 empty] | 2026-06-28 |  | 2026-07-07 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-08 |  | 2026-05-17 |  | Unknown | 2026-05-01 | 2026-05-01 14:21 | 1322753 | 238095 | 0 | 0 | 0 | 0 | 1322753 | 238095 | 2026-05-07 14:13:25 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-05-07 14:11:52 +0530 | Krutika Vernekar | DCM: 2BHK 840 sq ft 4 members Budget: 8L Suggested Budget: 14L Living Entry Shivaji wall Folding dining Master Bedroom Bed + wardrobe Passage Storage Kids Room Bed + wardrobe + study Wall Concepts needed in each wall Master Room Bed + wardrobe + folding study | 2026-05-01 15:33:40 +0530 | Anant Giri | Some Image was uploaded | 2026-05-22 |  | 2026-05-29
19766 | Turnkey | May'26 | Sabarish | Atul limbu | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 1100206 | 9999 | 0 | 0 | 0 | 75 | 0 | 100022 | 110021 | 440082 | 440082.4 |  |  | 2026-05-01 | 2026-05-01 21:09 | 2026-05-20 | 2026-05-20 11:06 | 2026-05-02 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-01 | 2026-05-01 21:05 | 0 | 0 | 0 | 0 | 0 | 0 | 932378 | 167828 | 2026-05-29 11:14:50 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-29 11:12:45 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-03 09:22:11 +0530 | Aparna | RGM Cx Name - SabarishÂ Crm -Â NiroshaÂ RGM -01/05/26 Move in date - In handÂ Budget - 7 -8Â Property name -Greenfinch HabitatÂ Direction - E facingÂ F to c -Â Â 9.6 MivonÂ Open for suggestionÂ ivory,greenÂ Kitchen Granite - Cx scopeÂ Fridge - 800mmÂ Cylinder cabinetÂ Sink cabinet - 900 Base unitÂ wall unitÂ LoftÂ Pooja unit - wall mountedÂ Living RoomÂ Tv unitÂ Suspended Drawers wall LedgesÂ 43" tvÂ Dining AreaÂ 4 seater Dining tableÂ Crockery unit - OptionalÂ Bedroom -MBRÂ King size bedÂ 7 xÂ 7Â Wardrobe and LoftÂ check head position as per vastuÂ Bedroom _KBRÂ single cot 5 x 6 Wardrobe andÂ loftÂ Â Bay window option -Â Wall cabinet - un washroomÂ shoe rack | 2026-05-31 |  | 2026-06-07
19772 | Turnkey | May'26 | Agni | Purva Atmoshphere | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | Arun Kumar |  | Harshit Choudhary | Saddam Hussain Z M |  | Mohammed Rasick | Abdul Shafeen | Active | Preproduction | 3D Sign off | 1093469 | 189605 | 1238558 | 1040513 | 0 | 1 | 12 | 0 | 0 | 479599 | 424265.2 |  |  | 2026-05-01 | 2026-05-16 11:42 | 2026-05-17 | 2026-05-17 11:16 | 2026-05-20 | 2026-05-17 12:03 | 2026-05-26 | 2026-05-26 19:31 | 2026-06-27 | 2026-06-26 17:30 | 2026-07-05 | 2026-07-05 20:48 | 2026-05-17 | 2026-05-19 18:45 | 2026-05-18 | 2026-05-20 14:23 | 2026-05-20 | 2026-05-21 13:39 | 2026-05-24 | 2026-05-24 18:28 |  |  |  |  | 2026-06-15 | 2026-06-23 17:02 | 2026-06-29 | 2026-06-26 19:18 | 2026-06-27 | 2026-06-26 19:18 |  |  | 2026-07-14 | 2026-07-14 17:14 | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-05-25 | 2026-05-26 19:19 | Site is RTMI | 2026-05-01 | 2026-05-01 17:02 | 1049626 | 188932 | 1109292.5633 | 187292 | 0 | 0 | 1165744.3379 | 196824 | 2026-07-14 17:14:14 +0530 | Abdul Shafeen | HOTO: in custom 2D false ceiling all side measurements required (two sides are missing) | 2026-06-21 13:09:13 +0530 | Ashiya Sanam | Minutes of Meeting held on Date: Attendees:Ashiya Discussion: Based on meeting, below is a list of all the requirements that were discussed during the meeting: KITCHEN: 1.To go with the same laminate for the kitchen carolina rovere and tidal Sand, 2.Granite is selected, both granite and dado tiles installation in bonito scope. 3.Cylinder Unit to added after the Hob according to site conditions and one more unit for cylinder to be discussed near the sink unit 4.Top Storage unit on top of the sink is removed 5.Hob and chimney in bonito offer, need to send the hob and chimney details. 6.All unit details and positions to be acknowledged during cross Measurements. LIIVING ROOM; 1.Wall designs are finalised 2.TV Unit, one panel to be removed and to adjust with one single panel behind the TV unit adding some louvers behind it as per the design, 3.Laminates for TV unit are finalised 4.Foyer design is finalised 5.Laminates for foyer are finalised 6.Crockery unit is finalised with the laminates 7.Painting for beadings in bonito scope, need to check once with the builder regarding final coat of full house paint after interiors 8.Texture paint or wallpaper needs to be decided after CM 9.False ceiling in Bonito scope with lighting and electrification Master Bedroom: 1.side wardrobe with loft is removed 2.Internals are discussed 3.To go the finalised handles 4.Laminates are finalised 5.Dresser unit and study unit are finalised Bedroom-1 1.Wardrobe Internals are finalised 2.To go with texture paint on the wall Vanity areas are decided and laminates are finalised NOTE: 1.Laminates are finalised 2.Electricals and painting in bonito scope 3.False ceiling in bonito scope 4.Quote may have a variation after the final site visit | 2026-05-29 18:34:36 +0530 | Yogesh B | Some Image was uploaded | 2026-05-27 | 2026-05-26 19:34 | 2026-06-27 | 2026-06-26 17:32 | RTMI
19773 | Turnkey | May'26 | Kashish Bhatia & S Pradeep | United Dream City | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 2047045 | 214999 | 2047045 | 0 | 0 | 6 | 0 | 0 | 194410 | 840375 | 797261.2 |  |  | 2026-05-01 | 2026-07-08 18:19 | 2026-05-19 | 2026-07-09 11:12 | 2026-07-09 | 2026-07-12 21:03 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-09 | 2026-07-09 11:54 | 2026-07-13 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-05-01 | 2026-05-08 14:06 | 1734784 | 312261 | 0 | 0 | 0 | 0 | 1734784 | 312261 | 2026-07-12 19:45:47 +0530 | Raghavendra S |  | 2026-05-06 13:48:02 +0530 | Ehthisham Durgam | DCM: Minutes of Meeting (MoM) Project: Interior Design Discussion Kasish Residence Clients: Kasish & Pradeep Date: 06-05-26 Budget: 15L 1. General OverviewProject discussed for full home interior design.Preference for modern, minimal, and functional design with aesthetic wall treatments.Focus on smart storage solutions and clean finishes. 2. Foyer AreaCushion seating to be incorporated.Design for main door panel to be developed. 3. KitchenCorner pantry with loft storage.Provision for:Separate break sink and main sink outside.Storage behind door (MOP utility style).Net shutter units.Extended wall to accommodate fridge.Microwave integrated into wall unit.Rolling shutter unit with space for mixer and granite counter. 4. Vanity AreaVanity storage with coordinated wall design. 5. Master Bedroom (Bedroom 1)Wardrobe with dressing unit:Solid matte laminate finish.Glass shutters.King-size bed with designed background wall.Balcony:Civil work modifications required.Track lighting to be installed. 6. Living RoomSofa back wall design.Feature wall design elements.Minimal TV unit with speaker bar.Seamless door integration. 7. Dining AreaDedicated dining wall design.Picture wall concept.Puja unit:Single large image/idol focus.Glass door enclosure.Pebble/grass base detail.Floating crockery unit. 8. Master Bedroom 2 (Bedroom 2)Bathroom design to be finalized.Walk-in closet:L-shaped layout.Combination of open and closed storage.Queen-size bed.Projector wall setup.Color theme: Peach tones.Wall design and wallpaper inclusion. 9. Additional Design ElementsRestroom wall to continue overall wall design theme.Existing wardrobe: optional (to be retained or modified).Dining table area:Floor design to be highlighted.Ceiling detail:Thin wooden beams in black finish. |  |  |  | 2026-07-20 |  | 2026-07-27
19775 | Turnkey | May'26 | Radhika | Sobha Windsor | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 1664029 | 9999 | 1664029 | 0 | 0 | 64 | 0 | 156404 | 166403 | 727076 | 604146.8 |  |  | 2026-05-01 | 2026-05-02 13:57 | 2026-05-06 | 2026-05-09 03:32 | 2026-05-12 | 2026-05-15 09:58 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-16 |  | 2026-05-17 | [5 empty] | 2026-05-23 |  | 2026-05-31 |  | 2026-06-01 |  |  |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 | [6 empty] | 2026-06-29 |  | 2026-07-08 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-11 |  |  |  | 2026-08-02 |  | 2026-08-04 |  | 2026-08-05 | [5 empty] | 2026-06-09 |  | 2026-05-18 |  | Unknown | 2026-05-01 | 2026-05-01 17:26 | 1410194 | 253834 | 0 | 0 | 0 | 0 | 1410194 | 253834 | 2026-05-09 09:49:35 +0530 | Aparna | DCM: DCM DCM: Client Name:Â Radhika Location:Â Whitefield Property:Â Sobha Windsor Configuration:Â 3BHK Theme Preference:Â Dark Grey / Brown Entrance Facing:Â East Family Members:Â 2 + 2 Cats Budget : 15L Foyer AreaRequirements:Console unit on the left sideWooden finish/colorReference image taken from clientShoe storage unit in passage areaAdditional storage beside passageProvision to hang clothes/jackets/bagsDesign Notes:Warm wooden tones preferredMinimal clutter appearanceFunctional storage integrationLiving RoomSofa WallRequirements:Wall beadings with textured wallpaperReference shared in groupDesign Direction:Elegant panel moulding/beading detailsPremium textured wallpaper finishDark neutral paletteTV UnitRequirements:TV wall to be extended using false wallTV panel/wall design as per referenceBase unit with textured laminate finishWooden panel detailing on top of base unitColor combination reference shared in groupDesign Notes:Combination of:Dark grey laminateWooden texturesMinimal luxury stylingSeamless concealed finish preferredDining AreaCrockery UnitRequirements:Crockery/storage unitSame color palette as TV unitReplace black finish with dark grey finishShelf design with golden rods to be consideredReference shared in groupDesign Direction:Premium display shelvingGold detailing accentsCombination of closed + open storageKitchenRequirementsBase unitsWall unitsLoft storageExtend right-side counter with breakfast counterTall unit beside refrigeratorCorner appliance storage provisionReference taken from clientDesign Notes:Functional kitchen planningMaximum storage utilizationModern modular finishEasy maintenance surfacesDedicated appliance organizationUtility AreaRequirementsBase unitsWall unitsDesign Notes:Utility-focused storageEasy access for cleaning essentials and washing utilitiesMaster Bedroom (MBR)RequirementsWall design as per referenceStudy unit as per referenceDesign Direction:Elegant modern bedroom stylingFunctional study/workspace integrationCoordinated color palette with overall home themeBedroom 2RequirementsWardrobeWall design as per referenceDesign Notes:Clean modern finishSpace-efficient storageTheme continuity with overall designBathroomsRequirementsVanity unitsFull-length mirror wall-to-wall if feasibleAlternative Option:Mirror with side storageDesign Notes:Premium modern vanity stylingFunctional storage optimizationSpacious visual appearance through mirror detailingÂ | 2026-05-09 03:26:49 +0530 | Saranya Thiyagarajan | DCM: Client Name: Radhika Location: Whitefield Property: Sobha Windsor Configuration: 3BHK Theme Preference: Dark Grey / Brown Entrance Facing: East Family Members: 2 + 2 Cats Kids: No Foyer AreaRequirements:Console unit on the left sideWooden finish/colorReference image taken from clientShoe storage unit in passage areaAdditional storage beside passageProvision to hang clothes/jackets/bagsDesign Notes:Warm wooden tones preferredMinimal clutter appearanceFunctional storage integrationLiving RoomSofa WallRequirements:Wall beadings with textured wallpaperReference shared in groupDesign Direction:Elegant panel moulding/beading detailsPremium textured wallpaper finishDark neutral paletteTV UnitRequirements:TV wall to be extended using false wallTV panel/wall design as per referenceBase unit with textured laminate finishWooden panel detailing on top of base unitColor combination reference shared in groupDesign Notes:Combination of:Dark grey laminateWooden texturesMinimal luxury stylingSeamless concealed finish preferredDining AreaCrockery UnitRequirements:Crockery/storage unitSame color palette as TV unitReplace black finish with dark grey finishShelf design with golden rods to be consideredReference shared in groupDesign Direction:Premium display shelvingGold detailing accentsCombination of closed + open storageKitchenRequirementsBase unitsWall unitsLoft storageExtend right-side counter with breakfast counterTall unit beside refrigeratorCorner appliance storage provisionReference taken from clientDesign Notes:Functional kitchen planningMaximum storage utilizationModern modular finishEasy maintenance surfacesDedicated appliance organizationUtility AreaRequirementsBase unitsWall unitsDesign Notes:Utility-focused storageEasy access for cleaning essentials and washing utilitiesMaster Bedroom (MBR)RequirementsWall design as per referenceStudy unit as per referenceDesign Direction:Elegant modern bedroom stylingFunctional study/workspace integrationCoordinated color palette with overall home themeBedroom 2RequirementsWardrobeWall design as per referenceDesign Notes:Clean modern finishSpace-efficient storageTheme continuity with overall designBathroomsRequirementsVanity unitsFull-length mirror wall-to-wall if feasibleAlternative Option:Mirror with side storageDesign Notes:Premium modern vanity stylingFunctional storage optimizationSpacious visual appearance through mirror detailingÂ | 2026-05-06 19:38:57 +0530 | Maspi Das | Cx name : Radhika Location- Whitefield Property - Sobha Windsor Prof :Â 3BHKÂ Theme - Dark Grey / Brown Entrance facing : East Budget -Â Members - 2 (2 cats) Kids- --- CDP meeting-Â Foyer- Console with wooden finish/color for the left side (Ref taken) Passage - shoe storageÂ Beside the passage some storage to hang clothes Sofa wall - Wall beadings with wallpaper (textured wallpaper) Ref shared in group TV Unit- need to extend by false wall TV panel/wall design (ref shared in group) Base unit (prefers some textured laminate) Base unit ref (wooden panel on top) Base unit color combination ref also shared in the group Dining area- Crockery unit- color combo (instead of black it will be dark grey same as TV unit color) Also refer the shelf with golden rods for design (shared in the group) Kitchen- Base units Wall units Lofts Need to extend the right side counter with a breakfast counter Tal unit beside Fridge *Consider a corner appliance storage* Ref taken Utility- Base Units Wall units MBR- Wall design ref taken Study unit ref taken BR2- Wardrobe Wall design ref taken Bathrooms- Vanity units Full length mirror wall to wall if possible orÂ Mirror with side storage | 2026-05-23 |  | 2026-05-30
19776 | Turnkey | May'26 | Kanaka Manoj Garapati | Sobha Dream Acres | BNG - HSR | Yes | Preethi Shetty | Akshay Ds | Soumya KP | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 1104987 | 134999 | 1323012 | 0 | 0 | 70 | 0 | 0 | 85998 | 471510 | 412480 |  |  | 2026-05-01 | 2026-05-01 17:13 | 2026-05-03 | 2026-05-03 18:45 | 2026-05-03 | 2026-05-03 18:51 | 2026-09-01 |  | 2026-09-08 |  | 2026-09-15 |  | 2026-05-03 | 2026-05-05 13:10 | 2026-05-04 | 2026-05-05 13:21 | 2026-05-05 | 2026-05-06 14:58 | 2026-05-08 | 2026-05-08 12:47 |  |  |  |  | 2026-09-02 |  | 2026-09-10 |  | 2026-09-11 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 | [6 empty] | 2026-10-09 |  | 2026-10-18 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-21 |  |  |  | 2026-11-12 |  | 2026-11-14 |  | 2026-11-15 | [5 empty] | 2026-09-19 |  | 2026-05-09 | 2026-05-29 19:04 | Site is RTMI | 2026-05-01 | 2026-05-01 17:12 | 1121196 | 201815 | 0 | 0 | 0 | 0 | 1179042.1507 | 199065 | 2026-06-03 17:05:56 +0530 | Preethi Shetty | Some Image was uploaded | 2026-06-03 17:04:27 +0530 | Preethi Shetty | DM1 - Design Discussions are done, need to collect 10% payment but client few doubts regarding the initial and revised quotation, we have shared the compared quote, following up with the client as well. | 2026-05-26 13:22:21 +0530 | Akshay Ds | Customer is mentioned that pooja unit and dresser unit were discussed at the time of CDP, how exactly he wanted those were not considered in the initional quote. He need the clarity from the NET designer, Overall experience : Average he is planning to meet on friday | 2026-09-02 |  | 2026-09-09 |  | RTMI
19777 | Turnkey | May'26 | Abhinav ayanippa | Nava vajra | BNG - HRBR | Yes | Asmitha Saif | Parasa Sri | Shibin Lal | [5 empty] | Kushal S |  | Active | Design | 20% Payment | 782943 | 110699 | 1106982 | 0 | 0 | 17 | 0 | 0 | 45890 | 320029 | 306325.6 |  |  | 2026-05-01 | 2026-05-06 12:07 | 2026-05-19 | 2026-05-19 18:51 | 2026-05-27 | 2026-05-27 19:18 | 2026-06-28 | 2026-06-28 14:26 | 2026-08-24 |  | 2026-08-31 |  | 2026-05-27 | 2026-05-29 18:28 | 2026-05-28 | 2026-05-30 11:23 | 2026-05-30 | 2026-06-10 18:00 | 2026-06-14 | 2026-06-14 13:20 |  |  |  |  | 2026-08-05 |  | 2026-08-26 |  | 2026-08-27 |  |  |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 | [6 empty] | 2026-09-24 |  | 2026-10-03 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-06 |  |  |  | 2026-10-28 |  | 2026-10-30 |  | 2026-10-31 | [5 empty] | 2026-09-04 |  | 2026-06-15 | 2026-06-25 12:15 | Site is Non-RTMI | 2026-05-01 | 2026-05-01 18:07 | 938121 | 168861 | 0 | 0 | 0 | 0 | 905271.388 | 149479 | 2026-06-28 14:42:54 +0530 | Asmitha Saif | Minutes of Meeting held on Date: 28.06.2026 Title: Layout Finalization Project: 19777 Client: Abhinav ayanippa Attendees: Asmitha Objective: Recorded meeting Link Discussion 19777 - DEM-1 agenda points finalization with customer (including cost alignment)-20260628_073857UTC-Meeting Recording.mp4 | 2026-06-28 14:25:55 +0530 | Asmitha Saif | Minutes of Meeting held on Date: 28.06.2026 Title: Layout Finalization Project: 19777 Client: Abhinav ayanippa Attendees: Asmitha Objective: Initial Layout Finalization Discussion Based on 28.06.2026 meeting, below is a list of all the requirements that were discussed during the meeting: General Notes:Project handover is expected in December (probably have a design discussion post that).Detailed design discussion is planned for mid/end of August.Initial site measurements can be taken in July.Overall design theme expected: Traditional Concept.1. Living Room:Entrance: Shoe rack to be planned outside the entrance.Furniture placement to be as per the finalized floor plan.CX is planning to have a sofa-cum-bed in living area.2. Dining Area:Handwash sink unit required with some nice catchy design which can blend with the living & dining space and the placement is ok as per initial file,Plumbing point has already been provided at the site.3. Puja Unit:Simple wall-mounted puja unit preferred.Client will share a reference image later.Placement to be finalized after verifying the Vastu direction.4. Kitchen & Utility:Appliance placements are correct as per the site.Provide top cabinets above the washing machine wall (in work area)Dado tiles, asked for Athangudi tiles.5. Passage Area Wall:Display/showcase unit required.Redesign of the display unit is needed.6. Master Bedroom:Balcony sit-out to be shown in the design, as it is already part of the plan. Kindly verify with the Net designer.All initially proposed wall fittings and furniture layouts are good to go,Bed size: Queen Size (Existing one)One bedside table is sufficient.Wardrobe to have hinged (swing) shutters.During the site visit, verify the balcony dimensions, as it is quite spacious.Client would like the balcony designed as a play area for their 3-year-old child.7. Bedroom 2:Room should not appear like a kid's bedroom, because parents also uses sometimesWardrobe with swing shutters.Bay window seating with storage required, (Outside window view: the outdoor play area)Placement of the wardrobe, bay window, and study unit placements are finalized.Additional Notes: Verify the Master Bedroom balcony sit-out with the design team.Take initial site measurements in July.Confirm Vastu direction before finalizing the Puja unit location.Inspect the balcony during the site visit and develop a kid-friendly play area design.Client has to share the reference image for the Puja unit.Schedule the detailed design discussion in mid/end of August. | 2026-06-25 12:26:47 +0530 | Asmitha Saif | Title: Site Visit for Measurement Project No: 19777 Client: Abhinav ayanippa Minutes of Meeting held on Date: 14.06.2026 Attendees: Thanusree & Asmitha Discussion: Welcome call & Site availability check. Based on 14th June call, below listed were discussed during the meeting: Welcome Call Updates: Possession: Expected around November.Initial Measurements: Can be scheduled as per clients availability.DEM-1 Meeting: Client will be available from next week and will be returning to Bengaluru over the coming weekend, so a face-to-face meeting can be planned accordingly. | 2026-06-29 | 2026-06-28 14:32 | 2026-08-25 |  | Under Construction | 2026-08-31
19778 | Turnkey | May'26 | Mr.Girish B A | INDEPENDENT HOUSE | BNG - HRBR | Yes | Vijin Venu | Parasa Sri | Shibin Lal | [5 empty] | Kushal S |  | Active | Preproduction | DEM2 | 1294843 | 269999 | 1681180 | 0 | 0 | 4 | 0 | 0 | 0 | 528901 | 495943.2 |  |  | 2026-04-30 | 2026-05-01 19:31 | 2026-05-06 | 2026-05-09 17:02 | 2026-05-12 | 2026-05-14 12:25 | 2026-06-10 | 2026-06-10 13:47 | 2026-07-03 |  | 2026-07-15 |  | 2026-05-14 | 2026-05-14 18:47 | 2026-05-15 | 2026-05-19 14:29 | 2026-05-19 | 2026-05-22 16:22 | 2026-05-25 | 2026-05-25 18:55 |  |  |  |  | 2026-06-10 | 2026-06-11 18:19 | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-05 | 2026-06-10 12:20 | Site is RTMI | 2026-04-30 | 2026-05-01 18:06 | 1424729 | 256451 | 0 | 0 | 0 | 0 | 1353918.9397 | 241621 | 2026-07-10 12:19:07 +0530 | Sunil Kumar S M | Dear Team, This is to inform you that yesterday we completed the civil scope site meeting along with the client, designer, VM, and vendors. During the meeting, all the required site dimensions and detailing were taken. @Rajeshwari K S, kindly inform the client of the following points related to Bonito's scope of work: For safety reasons, the client isÂ requested to temporarily vacate the flat until the civil work & Modular work is completed. All three bedroom wardrobes must be completely cleared, and all valuable belongings should be removed by the client before the work begins. The granite flooring installation in the kitchen partition wall demolition area is under the client's scope. The client has been informed that after the partition wall is demolished, the existing flooring in that area will have a cement finish until the flooring work is completed. As per the client's requirement, the platforms in all bedrooms will be removed. The client has also been informed that the exposed areas will have a cement finish after demolition, and the flooring tile and granite patchwork will be under the client's scope. The client has been informed that the cross measurement can only be carried out after all the civil and dependency works are fully completed. Please find attached the site photographs along with the client's signed cross measurement hard copy for documentation purposes. | 2026-06-10 13:46:32 +0530 | Chandini Nj | Kitchen - Placement we have marked as per that need to update the kitchen Livng area - removing the swing MBR - halmeraw as per that need to update the wardrobeÂ Son room - Dresser and study unit need to be updated Daughter room - Dresser unit with side storage | 2026-06-03 17:14:57 +0530 | Priyanka Gs | Recap: 19778 - Celebrity Design Presentation (CDP) with the customer 10 May ¦ Meeting ¦ Microsoft Teams | 2026-06-11 | 2026-06-10 13:50 | 2026-07-04 |  | RTMI
19779 | Turnkey | May'26 | Sowmya | Independant House | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1714981 | 9999 | 0 | 0 | 0 | 59 | 0 | 161499 | 171498 | 685992 | 685992.4 |  |  | 2026-05-01 | 2026-05-01 19:32 | 2026-05-14 | 2026-05-14 19:14 | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-01 | 2026-05-01 18:06 | 0 | 0 | 0 | 0 | 0 | 0 | 1453374 | 261607 | 2026-05-13 11:38:12 +0530 | Keerthan M | DCM: Independent villa 3BHK Renovation Foyer shoe rackKrishna idol spaceunder stare display unit Living TV unit double heightpartition design staircase detailing Dining Gowri Ganesh wall detailingchange crockery unit positionpooja room full renovation Kitchen utility-kitchen wall demolitiontall unitisland unitbottom unit, top unit. GBR Change bed positionwalk in closet 1st floor living give home theater option KBR wardrobe and dresserbed wall detailing MBR change bed positionwall detailing wardrobe dresserstudy unit need to be extended. | 2026-05-01 18:04:47 +0530 | Unknown | About the Customer **Villa Renovation Project Details** Customer is undertaking a villa renovation for an empty property in M.S. Ramaiah North City, requiring false ceiling and woodwork for the foyer, hall, mezzanine, and one room. The kitchen needs minor woodwork. The customer desires a premium finish with a budget of 15+ lakhs. **Experience Center Preference and Designer Requirement** Customer requests an appointment at the HRBR Layout experience center due to its convenience, as they visit North Bangalore weekly. They specifically need an experienced designer familiar with double-height villa projects and examples of such work. **Project Timeline and Readiness** Civil work is scheduled to begin around the end of May or June. The customer plans to start interior discussions during this period, with the house being empty and ready for installation post-civil work and painting. **Appointment Confirmed for Today** An appointment is confirmed for today at 3:00 PM at the HRBR Layout experience center, with the customer's husband also attending. Location details will be sent via WhatsApp. |  |  |  | 2026-05-25 |  | 2026-06-01
19780 | Turnkey | May'26 | Kalpesh Parmar | Lake lunsan | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1461129 | 186006 | 1860064 | 0 | 0 | 51 | 0 | 0 | 106220 | 624430 | 544472.8 |  |  | 2026-05-01 | 2026-05-13 11:54 | 2026-05-05 | 2026-05-14 16:45 | 2026-05-17 | 2026-05-14 21:05 | 2026-06-11 |  | 2026-06-19 |  | 2026-06-30 |  | 2026-05-14 | 2026-05-14 20:57 | 2026-05-15 | 2026-05-15 13:17 | 2026-05-15 | 2026-05-25 16:36 | 2026-05-30 | 2026-05-30 16:30 |  |  |  |  | 2026-06-12 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-05-31 | 2026-06-14 14:48 | Site is RTMI | 2026-05-01 | 2026-05-13 11:53 | 1576325 | 283738 | 0 | 0 | 0 | 0 | 1557735.8025 | 263003 | 2026-07-10 13:27:51 +0530 | Vishakha Vaishnav | After DEM 1 meetin cx said that she will connect in ah hour for 10% due however on the next day cx mentioned they don't want to continue , tried connecting cx there is no respond from cx end | 2026-07-08 13:37:17 +0530 | Preeti Agarwal | Need PH intervention | 2026-06-06 13:12:53 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 |  | 2026-06-20 |  | RTMI
19781 | Turnkey | May'26 | Sujata Panigrahi | Rain Tree Oliva | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2702581 | 9999 | 0 | 0 | 0 | 34 | 0 | 260259 | 270258 | 1143436 | 1018628.4 |  |  | 2026-05-01 | 2026-05-06 10:22 | 2026-05-17 | 2026-05-17 18:25 | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-20 |  | 2026-06-07 |  | 2026-06-07 |  | 2026-06-08 | [5 empty] | 2026-06-14 |  | 2026-06-22 |  | 2026-06-23 |  |  |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 | [6 empty] | 2026-07-21 |  | 2026-07-30 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-02 |  |  |  | 2026-08-24 |  | 2026-08-26 |  | 2026-08-27 | [5 empty] | 2026-07-01 |  | 2026-06-09 |  | Unknown | 2026-05-01 | 2026-05-04 10:51 | 0 | 0 | 0 | 0 | 0 | 0 | 2290322 | 412258 | 2026-06-12 18:50:05 +0530 | Ankita Agarwal | DCM: Recap: 19781 - Celebrity Design Presentation (CDP) with the customer 06 June ¦ Meeting ¦ Microsoft Teams | 2026-06-12 18:49:50 +0530 | Ankita Agarwal | Some Image was uploaded | 2026-06-04 13:57:51 +0530 | Patil Madhavi | Some Image was uploaded | 2026-06-14 |  | 2026-06-21
19782 | Turnkey | May'26 | Trupti Ambani | shreeji skyrise | MUM - GOR | Yes | Neha Yadav | Reshma Melanta | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Design | DEM1 | 4200773 | 771463 | 5714632 | 0 | 0 | 39 | 0 | 0 | 68692 | 1743577 | 1617041.2 |  |  | 2026-05-01 | 2026-05-23 15:52 | 2026-05-05 | 2026-05-24 15:40 | 2026-05-27 | 2026-05-27 13:27 | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-05-27 | 2026-06-04 14:37 | 2026-05-28 | 2026-06-04 19:01 | 2026-06-04 | 2026-06-06 19:51 | 2026-06-20 | 2026-06-20 16:21 |  |  |  |  | 2026-06-26 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-07-16 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-21 |  | Site is RTMI | 2026-05-01 | 2026-05-01 19:21 | 4842908 | 871723 | 0 | 0 | 0 | 0 | 4782514.361 | 764689 | 2026-07-04 18:38:19 +0530 | Reshma Melanta | Others: | 2026-07-04 18:09:40 +0530 | Reshma Melanta | Others: | 2026-06-27 19:42:02 +0530 | Neha Yadav | DDM1 Meeting discussion: Kitchen:RS 1)Kitchen on right side- hob side no wall unit masala unit. 2)There wont be any tall unit. Master Room:RS 1)Bed position need to change , need to add 2 side table & tv paneling ,bathroom door will be flush need to add 2)Breather unit needs to add there will be only 1 shelf 3)WD- One side there wont be hanging will be full shelf other side half shelf & hanging 4)Niche need to create in bath tub wall 5)Storage 4 need with glass shutter to add bathroom area 6)Track light in ceiling design Guest room:RS 1)Wardrobe will be openable not sliding - 6 size 2)Breather unit need to add half for cloth hanging second for cosmetics , Full mirror next to 3)Need to add tv panel Daughter Room:LS 1)WD- open shutter glass need to do Living & Foyer: 1)Foyer storage need to remove, will have ganpati mural 2)Mandir storage 20 3)Basin stand alone out side Kitchen:LS 1)Microwave unit will be on counter Guest Room:LS 1)Murphy bed need to add instead of sofa Feel free to add pointers if missed any. | 2026-06-26 |  | 2026-07-03 |  | Under Construction | 2026-09-01
19785 | Turnkey | May'26 | Vishal Shah | Lodha Fiorenza | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 2517735 | 9999 | 2517735 | 0 | 0 | 59 | 0 | 241775 | 251774 | 1114427 | 899761.2 |  |  | 2026-04-26 | 2026-05-07 12:33 | 2026-05-17 | 2026-05-17 21:23 | 2026-05-17 | 2026-05-17 22:07 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-04-26 | 2026-05-02 12:19 | 2142246 | 375489 | 0 | 0 | 0 | 0 | 2142246 | 375489 | 2026-05-10 21:56:18 +0530 | Pratima Kajwe | CDP: CDP: MOM Civil scope of balcony. Bar Carpentry or loose can be considered. Loose furniture Sofa - 50kcenter table - 7kChair - 30kdining table - 75kconsole table - 30kAppliance -TV in studio room - 50kMattress - 35kDecor lights - 20kAutomation in studio room - 75kIkea study table - 75kProjector console in studio room - 25kBed - 2 - 90k + 90kTotal 6L | 2026-05-10 21:27:27 +0530 | Pratima Kajwe | CDP: MOM Civil scope of balcony. Bar Carpentry or loose can be considered. Loose furniture Sofa - 50kcenter table - 7kChair - 30kdining table - 75kconsole table - 30kAppliance - TV in studio room - 50kMattress - 35kDecor lights - 20kAutomation in studio room - 75kIkea study table - 75kProjector console in studio room - 25kBed - 2 - 90kTotal 5L |  |  |  | 2026-05-25 |  | 2026-06-01
19786 | Turnkey | May'26 | Mihir Pasad | Kalpataru Elitus | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 3636588 | 9999 | 0 | 0 | 0 | 75 | 0 | 353660 | 363659 | 1532636 | 1376634 |  |  | 2026-05-01 | 2026-05-01 21:57 | 2026-05-06 | 2026-05-07 11:44 | 2026-05-23 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-05-18 |  | 2026-05-26 |  | 2026-05-27 |  |  |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 | [6 empty] | 2026-06-24 |  | 2026-07-03 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-06-04 |  | 2026-05-13 |  | Unknown | 2026-05-01 | 2026-05-01 20:18 | 0 | 0 | 0 | 0 | 0 | 0 | 3081854 | 554733 | 2026-05-09 10:58:22 +0530 | Rinisha Masurkar | 19786 - Mihir Pasad Kalpataru elitus B wing 7 family membersÂ 1329sqftÂ servant room will be utilized by the sister in lawÂ open kitchen concept with dining table and sliding folding windowÂ washroom in the servant room to be closed completelty and utilise the space in the bedroomÂ pantry storage in the kitchen if possibleÂ L shape seatingÂ tv and mandir on dining wallÂ minimal tv unitÂ bigger bed in the small roomÂ wardrobe storage in the niche areaÂ exhaust on the ventilation windowÂ open shelf on the opp of the bed for soft toys in the small roomÂ curve wall on every 90 degree no sharpe design for the false ceiling only curve designÂ no working desk in any roomsÂ tv provision in mbr room and grand parents room tall unit in the parents roomÂ floating dresser with pouf space- mbr end to end wardrobe - mbr minimal false ceiling in bedroomsÂ vanity in all washroom close storage in the passage curve in the passage ceilingÂ 35 - 40 l budgetÂ | 2026-05-05 12:58:12 +0530 | Aryan Singh | Some Image was uploaded | 2026-05-01 20:17:40 +0530 | Unknown | About the Customer **Possession Expected September** Customer is receiving possession of a 3.5 BHK apartment in Mulund in September. **Budget Not Finalized** Budget for interiors is not yet finalized, with a potential range of 25-30 lakhs indicated. **Thane Experience Center Visit Booked** Customer agreed to visit the Thane experience center today between 2:00 PM and 2:30 PM with one or two family members. **WhatsApp Confirmation Pending** Agent will share the Thane experience center address and details via WhatsApp. | 2026-05-18 |  | 2026-05-25
19787 | Turnkey | May'26 | Shilpa | Casagrand Hazen | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Priyanka Mathur | [5 empty] | Korak Ganguly |  | Hold | Design | DEM1 | 822591 | 164519 | 1126420 | 0 | 0 | 27 | 22 | 0 | 0 | 329036 | 329036.4 |  |  | 2026-05-01 | 2026-05-10 10:38 | 2026-05-05 | 2026-05-10 11:16 | 2026-05-13 | 2026-05-10 20:55 | 2027-08-08 |  | 2027-08-15 |  | 2027-08-22 |  | 2026-05-10 | 2026-05-22 18:56 | 2026-05-11 | 2026-05-26 12:31 | 2026-05-26 | 2026-05-27 13:31 | 2026-06-05 | 2026-06-05 19:09 |  |  |  |  | 2027-08-09 |  | 2027-08-17 |  | 2027-08-18 |  |  |  | 2027-08-25 |  | 2027-08-26 |  | 2027-08-27 |  | 2027-08-28 | [6 empty] | 2027-09-15 |  | 2027-09-24 |  | 2027-09-23 |  | 2027-09-24 |  | 2027-09-25 |  | 2027-09-27 |  |  |  | 2027-10-19 |  | 2027-10-21 |  | 2027-10-22 | [5 empty] | 2027-08-26 |  | 2027-08-04 |  | Unknown | 2026-05-01 | 2026-05-10 10:38 | 954594 | 171826 | 0 | 0 | 0 | 0 | 944676.9 | 155988 | 2026-06-23 16:16:30 +0530 | Abhinandan K S | Some Image was uploaded | 2026-06-23 13:35:18 +0530 | Abhinandan K S | Some Image was uploaded | 2026-06-05 19:12:26 +0530 | Abhinandan K S | Non RTMI project. Price protection deviation given till July 2027. Possession expected by June 2027 and project will be kept on hold in Pulse till then. Initial measurement cannot be aligned as the possession is not taken. Customer is ok with the Offers. timeline and Net quote. 20% payment collected during the Net closure. Meeting dates and timings to be shared with the Customer. | 2027-08-09 |  | 2027-08-16 |  | Under Construction | 2027-06-30
19788 | Turnkey | May'26 | sourav | Prestige | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Nidhi Shaw |  | Lost | Prospect | 10% Payment | 2011352 | 0 | 2011352 | 0 | 0 | 62 | 0 | 201135 | 201135 | 813260 | 795821.2 |  |  | 2026-05-01 | 2026-05-01 20:41 | 2026-05-04 | 2026-05-14 19:26 | 2026-05-17 | 2026-05-19 17:13 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-01 | 2026-05-01 20:39 | 1706823 | 304529 | 0 | 0 | 0 | 0 | 1706823 | 304529 | 2026-06-06 11:25:54 +0530 | Varun Mandana | Some Image was uploaded | 2026-06-06 11:25:05 +0530 | Varun Mandana | Some Image was uploaded | 2026-05-08 12:04:33 +0530 | Aparna | RGM Cx name : Saurav & Swati Address :Â Profession : IT Possession : Handover is doneÂ How many people will be staying : 2Â Theme : Minimal with golden detailÂ Â Entrance facing :Â E facingÂ Budget : 8 - 10L Foyer - Need shoe rack -900x1200 (need foldable seating no fixed seating ) Oppo wall cx has art work which needs to be retainedÂ Dining area - 6 seaterÂ Need crockery unit on dining wall-cx will share referenceÂ Need wall treatment on dining side wall Living - Tv is 65" TV unit - cx has referenceÂ cx has speakers to store there has well Pooja unit - need cnc shutters - refer imageÂ Kitchen - Glossy laminateÂ Single door fridgeÂ counter top to be includedÂ need one cylinder unitÂ Base and wall cabinetsÂ small sinkÂ Utility- sink with drain boardÂ WM and DW needed so provision for L shape placementÂ Door to utility will be removed from cx's end and will keep double door for clearanceÂ RO unit is under counterÂ BR-3 (PBR) Need study with ledge as mention in plan 3 shutter wardrobe with loftÂ The room is dark so consider thatÂ BR-2 (KBR)Â study with storageÂ Wardrobe with loftÂ MBR- Entrance need dresser unit- cx will share referenceÂ Wardrobe with loft 4 shutters king size bed for 3D small tv unit | 2026-05-27 |  | 2026-06-03
19789 | Turnkey | May'26 | ARCHIT GIRISH MANURKAR | Leo Eminence | MUM - GOR | Yes | [8 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 1260480 | 9999 | 1260480 | 0 | 0 | 64 | 0 | 116049 | 126048 | 585123 | 423261.2 |  |  | 2026-05-01 | 2026-05-09 18:35 | 2026-05-03 | 2026-05-11 15:03 | 2026-05-14 | 2026-05-13 11:58 | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-15 | [5 empty] | 2026-05-21 |  | 2026-05-29 |  | 2026-05-30 |  |  |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 | [6 empty] | 2026-06-27 |  | 2026-07-06 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-09 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-07 |  | 2026-05-16 |  | Unknown | 2026-05-01 | 2026-05-09 18:34 | 1068203 | 192276 | 0 | 0 | 0 | 0 | 1068203 | 192276 | 2026-05-03 19:38:03 +0530 | Sakshi Hire | DCM: 508 bandra east 4 adults june 3+1 sofa 55" tv unit wall mounted tv unit with drw mirror img of kitchen sink below window corner washing machine fridge oopening corner microwave dishwasher placement seating pooja unit in bed 1 in left corner facing eastÂ sofa cum bed workstation with storage like wardrobe 2' depth storage in mbr in niche queen size bed storage side table with mirrorÂ false ceiling living shoe rack 15 pairs | [6 empty] | 2026-05-21 |  | 2026-05-28
19790 | Turnkey | May'26 | Swati Patil | Dottom | MUM - GOR | Yes | Karan Chavda | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Rashmita Das |  | Hold | Preproduction | Site Readiness 1 | 1324618 | 264924 | 1706352 | 0 | 0 | 0 | 20 | 0 | 0 | 554153 | 505540.8 |  |  | 2026-05-01 | 2026-06-02 10:44 | 2026-06-02 | 2026-06-02 19:12 | 2026-06-02 | 2026-06-02 19:49 | 2026-06-23 | 2026-06-23 14:36 | 2026-06-29 |  | 2026-07-06 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-04 14:12 | 2026-06-04 | 2026-06-06 15:11 | 2026-06-12 | 2026-06-12 17:08 |  |  |  |  | 2026-10-20 | 2026-06-25 18:05 | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-13 | 2026-06-23 14:32 | Site is Non-RTMI | 2026-05-01 | 2026-05-02 11:34 | 1446061 | 260291 | 0 | 0 | 0 | 0 | 1444000.3342 | 238431 | 2026-06-25 13:56:32 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 16:58:01 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to align DEM Dates -Â DEM 1 - cx said that she will update DEM 2 - TBD DEM 3 - TBD Possession date : September Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-06 15:09:31 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: September Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM 7th June 2026 * DEM 1 14th June 2026 * 10% Payment Stage 16th June 2026(after 1st DEM) *No civil work at site *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 14,44,001 Offers Discussed During the Call: Design Fee Waiver (2.5%) 100% GST Waiver PM fee waiver (7.5%) Laminate Upgrade - May '26 Campaign Anniversary '26 Studio Offer: 30,000 Final Closing Value Discussed: 13,24,619 Checklist terms - descoping, delay compensation agreement terms are clear. | 2026-06-24 | 2026-06-23 14:39 | 2026-06-30 |  | Under Construction | 2026-09-30
19791 | Turnkey | May'26 | Jigar gupta | Avalon Park Prestige city | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 2503917 | 9999 | 2503917 | 0 | 0 | 57 | 0 | 240393 | 250392 | 1001567 | 1001566.8 |  |  | 2026-05-01 | 2026-05-19 12:44 | 2026-05-02 | 2026-05-19 17:04 | 2026-05-22 | 2026-05-19 17:08 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-01 | 2026-05-04 10:55 | 2121963 | 381953 | 0 | 0 | 0 | 0 | 2121963 | 381953 | 2026-05-02 22:56:56 +0530 | Priyamvada PV | Cx Name - Jigar Crm -Â Varun RGM -01/05/26 Move in date -Sep (Soft handover is in 2027) Budget - 10 -15L Informed cx about budget it will go uptoÂ 17L Property name -Prestige Lavender Fields Direction - E facing F to c -Â Â 9.6 Mivon Pastel shades , lighter tone Foyer area Shoe rack for 30pairs for shoes Living Room TV unit (Minimal Design) Suspended Drawers with open ledges Tv - 50 - 60" 3 +2 seaterÂ sofa Dining area Pooja unit + Crockery unit 6 seater Dining table False ceiling in Living ,Dining and Foyer Kitchen Fridge - 1000mm Small sink in kitchen - 600mm Tall unit - oven unit Base unit wall loft Cylinder cabinet Quartz - countertop Utility Washing machine Sink unit Dishwasher - optional Wall cabinet janitor unit - open utility BEDROOM - 1Â (MBR) Bed direction plan as per vastu Wardrobe and Loft Dresser study unit - optional BEDROOM _2 (PBR) Wardrobe and Loft Dresser BEDROOM 3 (GBR orÂ KBR ) Wardrobe and Loft Dresser add wall ledges kids theme bay window All 3 bedroom Sliding wardrobe Study Room open for suggestion option 1 study room option - 2 Storage + studyÂ unit Washroom vanity in all cabinets | [6 empty] | 2026-05-27 |  | 2026-06-03
19792 | Turnkey | May'26 | Veeresh Veeru | Gr floret | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 1122977 | 9999 | 0 | 0 | 0 | 57 | 0 | 102299 | 112298 | 449191 | 449190.8 |  |  | 2026-05-01 | 2026-05-19 13:13 | 2026-05-06 | 2026-05-26 16:43 | 2026-05-16 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-30 |  | 2026-05-31 | [5 empty] | 2026-06-06 |  | 2026-06-14 |  | 2026-06-15 |  |  |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-23 |  | 2026-06-01 |  | Unknown | 2026-05-01 | 2026-05-02 12:51 | 0 | 0 | 0 | 0 | 0 | 0 | 951675 | 171301 | 2026-05-26 18:52:53 +0530 | Ravikiran K | Client - Veeresh Budget - 8 - 9lakhs Property - GR Floret Note - customer is looking for elegant designs and also, we have prepared the customers to close on spot Kannada speaking customer | 2026-05-26 16:39:43 +0530 | Rajasekar Ranganathan | Requirement Meeting MOMClient: Mr. VeereshProject Type: 2BHK Interior Works Property: Ground Floor Budget: 6.0 7.5 Lakhs Expected Handover: Next Month Scope of Work1. Foyer AreaFoyer wall design conceptsDecorative wall treatment / paneling options2. Dining AreaFolding dining table 4 seaterDining wall conceptHandwash basin unit near dining3. Pooja UnitDedicated pooja room/unit design4. Living RoomTV unit with decorative wall designBookshelf/storage unitSofa backdrop wall conceptsL-shape sofa unit5. KitchenProvision for double-door refrigeratorGranite countertopTile installation worksCylinder storage unitBreakfast counter/table6. Master BedroomSliding partition wallDresser unitBathroom vanity with large-size mirrorWardrobe with loft storageWall design conceptsKing-size storage bedStudy table unitBookshelf/storage unit7. Ceiling WorksFalse ceiling for all common areasExisting FurnitureExisting furniture details to be reviewed during site measurement and integrated wherever possible.Discussion NotesClient prefers functional storage with aesthetic wall concepts.Budget to be optimized within 67.5 Lakhs.Priority on completing execution before next month handover.Material selections and final finishes to be frozen after design presentation.Next StepsSite measurement verificationConcept design & 3D presentationMaterial and finish selectionFinal quotation submissionProduction & execution schedule planning | 2026-05-02 12:51:07 +0530 | Unknown | About the Customer **Current Customer Stage and Next Steps** The customer, Veeresh, is in the process of planning interior design for his 2 BHK apartment, which is expected to be handed over in three months. His immediate next step is to review the details sent via WhatsApp and contact the agent to book a visit to the experience center the following week. **Customer Needs, Concerns, and Objectives** Veeresh's primary need is interior design for his new 2 BHK home, with a budget of approximately 8 lakhs. He is concerned about the materials used, specifically laminates and acrylic for the kitchen, and is looking for clarity on options and costs. He also needs to understand the company's pricing and benefits. **Customer Engagement History** The customer, Veeresh, initiated contact via Facebook and received an outbound call from Preeti at Bonito Designs. The call focused on gathering property details, discussing budget, explaining services, and suggesting a visit to the experience center. **Additional Engagement Details** Veeresh is currently out of town but will be available the following week. The agent has sent details via WhatsApp and encouraged a visit to the HSR Layout experience center. The current festival offers are confirmed to be available for another month. **Recommended Follow-up Actions** The recommended follow-up action is for Veeresh to contact the agent to book a confirmed appointment for the experience center visit next week, ensuring he visits with a family member to discuss options and costs comprehensively. | 2026-06-06 |  | 2026-06-13
19793 | Turnkey | May'26 | abin abraham | Modern space | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Rajoshi Sarkar |  | Active | Prospect | 10% Payment | 2182905 | 9999 | 2182905 | 0 | 0 | 34 | 0 | 208292 | 218291 | 873162 | 873162 |  |  | 2026-05-01 | 2026-05-06 11:11 | 2026-05-17 | 2026-05-17 18:50 | 2026-06-07 | 2026-06-11 12:52 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-01 | 2026-05-04 12:05 | 1849919 | 332985 | 0 | 0 | 0 | 0 | 1849919 | 332985 | 2026-05-17 18:37:08 +0530 | Swati Rathod | RGM Date : 17-05-2026 PID: 19793Â Â Name : abin abraham Profession: IT Property - 3BHK Budget - 15L possession - 01-09-2026 Site Access Date: 01-07-2026 Total Members - 02Â Orientation : NORTH Floor : 03 - False ceiling in common area FOYER : - shoerack with seating and some storage with drawer - wall conceptÂ LIVING: - TV unit cum Pooja unit(open with some storage) - sofa DINNING: - 6 seater - sink on common toilet wall BALCONY: - Ledges for books KITCHEN:01 - Crockery unit - break fast counter KITCHEN:02 - 2door fridge (3') - bottom unit - top unit - Loft - Granite BD scope - Tall unit for oven UTILITY: - W.M , D.W - Top units - look space for janitor unit - Loft BEDROOM-1:(M. bedroom) - King size bed(BD Scope) - 2 Wardrobe with study with ledges - Dresser BEDROOM-2: (guest) - King size bed - Openable wardrobe with loft BEDROOM-3: (Kid) - Partition @ entry - Openable wardrobe with loft - Study unit - Q size bed Toilet: Â - bottom vanity in all bathroom Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. Meeting Date: | [6 empty] | 2026-06-19 |  | 2026-06-26
19794 | Turnkey | May'26 | Swapnil Patil | Satra nexus | MUM - GOR | Yes | Saakshi Bhute | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Hold | Design | DEM1 | 952068 | 120179 | 1201785 | 0 | 0 | 49 | 12 | 0 | 70235 | 424619 | 337035.6 |  |  | 2026-05-02 | 2026-05-05 15:23 | 2026-05-09 | 2026-05-09 13:34 | 2026-05-13 | 2026-05-13 18:10 | 2026-08-04 |  | 2026-08-11 |  | 2026-08-18 |  | 2026-05-12 | 2026-05-13 18:03 | 2026-05-14 | 2026-05-14 12:34 | 2026-05-14 | 2026-05-15 13:28 | 2026-05-19 | 2026-05-19 14:59 |  |  |  |  | 2026-08-05 |  | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-07-31 |  | Unknown | 2026-05-02 | 2026-05-02 13:19 | 1020749 | 181036 | 0 | 0 | 0 | 0 | 1015044.478 | 168673 | 2026-07-03 11:28:49 +0530 | Vishakha Vaishnav | Others: Cx is saying he want to go ahead with project cancellation as he was forced to sign the deal and he is not getting his desired things done in bonito scope have asked for meeting at office as well cx is not responding properly | 2026-06-12 15:21:23 +0530 | Kashmira Nerurkar | Some Image was uploaded | 2026-06-12 11:26:50 +0530 | Vishakha Vaishnav | Spoke with cx twice cx said that he want cancellation because he had to get the losse furtinre from outside so he and also that he was not aware of that tried convincing him with shahid however cx want to go ahead with cancellation only . | 2026-08-05 |  | 2026-08-12 |  | Under Construction | 2026-07-15
19795 | Turnkey | May'26 | Nikhil Lugade | Ambassy one | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 2697347 | 9999 | 2697347 | 0 | 0 | 15 | 0 | 259736 | 269735 | 1144960 | 1012917.6 |  |  | 2026-05-02 | 2026-05-07 11:46 | 2026-05-02 | 2026-05-07 11:46 | 2026-06-27 | 2026-06-30 11:17 | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-05-02 | 2026-05-02 13:45 | 2285887 | 411459 | 0 | 0 | 0 | 0 | 2285887 | 411459 | 2026-06-30 16:45:22 +0530 | Rinisha Masurkar | Recap: 19795 - Design Consultation Meeting (DCM) with the customer 02 May ¦ Meeting ¦ Microsoft Teams | 2026-06-30 15:05:50 +0530 | Yerra Bharat | CDP: Living ok with space planed as discussed dining - wanted to face turned 90 degrees. Pooja - make bigger - wants it to be like a person has to sit and pray. Kitchen - ok with layout - cooking hob in the corner with east facing layout, rolling shutter storage beside the fridge. Master bedroom: Added a tall single door wardrobe with loft beside the washroom door, for extra storage. wardrobe in the niche area and work table Queen bed Side tables study table Bedroom -2, parents bedroom queen bed with side and top dresser unit. Bedroom -3 pooja mandir area is created into this room and in the remaining area, need a reading table for kid and study table similar to master bedroom. Client is still exploring stage and still waiting quotes. need an end to end solution as client is planning to renovate the washrooms also. As they don't have time to do other things, he is expecting to get things done from single person, including civil, material selection and transport of that material. | 2026-06-28 12:21:10 +0530 | Yerra Bharat | Some Image was uploaded | 2026-07-08 |  | 2026-07-15
19796 | Turnkey | May'26 | Mr.Devendra Semwal | Arihant Aspire | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Shreyash Kotecha |  | Hold | Preproduction | DEM2 | 812727 | 166299 | 1087099 | 0 | 0 | 17 | 13 | 0 | 0 | 332976 | 313451.6 |  |  | 2026-05-02 | 2026-05-02 16:43 | 2026-05-13 | 2026-05-13 13:00 | 2026-05-14 | 2026-05-15 11:41 | 2026-06-10 | 2026-06-10 13:41 | 2027-01-09 |  | 2027-01-16 |  | 2026-05-15 | 2026-05-16 14:25 | 2026-05-16 | 2026-05-16 14:27 | 2026-05-16 | 2026-05-19 11:08 | 2026-05-30 | 2026-05-30 19:14 |  |  |  |  | 2026-06-15 | 2026-06-15 17:43 | 2027-01-11 |  | 2027-01-12 |  |  |  | 2027-01-19 |  | 2027-01-20 |  | 2027-01-21 |  | 2027-01-22 | [6 empty] | 2027-02-09 |  | 2027-02-18 |  | 2027-02-17 |  | 2027-02-18 |  | 2027-02-19 |  | 2027-02-21 |  |  |  | 2027-03-15 |  | 2027-03-17 |  | 2027-03-18 | [5 empty] | 2027-01-20 |  | 2026-05-31 | 2026-06-10 12:58 | Site is RTMI | 2026-05-02 | 2026-05-02 16:37 | 921271 | 165828 | 0 | 0 | 0 | 0 | 921270.8535 | 153490 | 2026-07-14 13:04:43 +0530 | Divya Rahangdale | The client will receive possession by December. | 2026-06-26 12:20:07 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-05-30 16:26:23 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-11 | 2026-06-10 14:31 | 2027-01-10
19797 | Turnkey | May'26 | Pratik N Pandya & Co. | Runwal Sanctury | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anant Giri |  | Hold | Design | DEM1 | 862196 | 172439 | 863606 | 0 | 0 | 19 | 43 | 0 | 0 | 344879 | 344878.4 |  |  | 2026-05-02 | 2026-05-02 14:48 | 2026-05-02 | 2026-05-02 18:23 | 2026-05-09 | 2026-05-12 12:53 | 2026-10-04 |  | 2026-10-11 |  | 2026-10-18 |  | 2026-05-10 | 2026-05-11 13:44 | 2026-05-11 | 2026-05-11 20:09 | 2026-05-13 | 2026-05-14 11:50 | 2026-05-17 | 2026-05-17 11:27 |  |  |  |  | 2026-06-15 | 2026-05-28 19:10 | 2026-10-13 |  | 2026-10-14 |  |  |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 | [6 empty] | 2026-11-11 |  | 2026-11-20 |  | 2026-11-19 |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-23 |  |  |  | 2026-12-15 |  | 2026-12-17 |  | 2026-12-18 | [5 empty] | 2026-10-22 |  | 2026-09-30 |  | Unknown | 2026-05-02 | 2026-05-02 14:46 | 938907.029 | 155449 | 0 | 0 | 0 | 0 | 911141.6891 | 155195 | 2026-07-11 10:55:40 +0530 | Anil Jagtap |  | 2026-07-11 10:45:44 +0530 | Anil Jagtap | cx will receive the possession by September *2026 | 2026-06-25 16:07:47 +0530 | Siddhi Chaphekar | Some Image was uploaded | 2026-10-05 |  | 2026-10-12
19800 | Turnkey | May'26 | Sai Priya | Prestige City | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Rajoshi Sarkar |  | Active | Preproduction | DEM2 | 1201670 | 240333.65 | 1673283 | 0 | 0 | 36 | 0 | 0 | 0 | 480668 | 480668 |  |  | 2026-05-02 | 2026-05-07 12:36 | 2026-05-10 | 2026-05-10 12:12 | 2026-05-10 | 2026-05-10 12:35 | 2026-06-07 | 2026-06-07 11:23 | 2026-07-23 |  | 2026-07-30 |  | 2026-05-10 | 2026-05-12 11:17 | 2026-05-11 | 2026-05-14 14:05 | 2026-05-14 | 2026-05-14 15:13 | 2026-05-24 | 2026-05-24 19:47 |  |  |  |  | 2026-06-07 | 2026-06-09 18:06 | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-05-25 | 2026-05-28 11:50 | Site is RTMI | 2026-05-02 | 2026-05-06 18:03 | 1418036 | 255246 | 0 | 0 | 0 | 0 | 1387251.747 | 229068 | 2026-06-07 11:20:55 +0530 | Avishkar Sargam | MOM 6th May Living Room TV unit wall moulding design finalized.Match the sofa wall design to the shared reference.Continue simple wall beading design on the dining wall.Kitchen Add a microwave wall unit.Convert the remaining section into a 2-shutter unit.Add wicker baskets.Reduce the width of the 3-drawer unit to 600 mm.Pooja Room Revise the pooja unit design.Change the wardrobe position and place it adjacent to the existing wardrobe.Master Bedroom Add square beading on the bed-back wall.Add 2 drawers to the dresser.Modify wardrobe internals as discussed.Bedroom 2 / Parents' Bedroom No changes to the bedroom layout.Apply texture paint on the bed-back wall. | 2026-06-04 15:37:14 +0530 | Patil Madhavi | Some Image was uploaded | 2026-06-04 15:03:53 +0530 | Avishkar Sargam | MOMÂ - 29th MayÂ Living Room - Shoe rack design to be revised as per the shared reference. - TV unit to be updated with minimal changes while retaining the initial design concept. - Retain the existing wall moulding design on the sofa wall. - Dining wall design to be developed as per the shared reference. Kitchen - Increase the height of the single drawer in the 2-drawer unit. - Convert the tall unit into a full shelf storage unit. Study Room - Pooja unit to remain in the same location. - Shift the wardrobe to the adjacent wall. - Add wallpaper on the pooja unit wall. Master Bedroom - Increase storage capacity in the dresser unit. - No changes to the existing bed-back wall design concept. Bedroom 3 - Provide a simple textured wall design. - Wardrobe layout to remain unchanged. - Add a simple foldable study unit. | 2026-06-08 | 2026-06-07 19:33 | 2026-07-24 |  | RTMI
19802 | Turnkey | May'26 | Prathamesh Tayade | Agarwal Floresta Oak | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1162825 | 232565 | 1519634 | 0 | 0 | 32 | 0 | 0 | 0 | 521459 | 408800.8 |  |  | 2026-05-02 | 2026-05-02 21:19 | 2026-05-03 | 2026-05-13 14:37 | 2026-05-16 | 2026-05-16 16:59 | 2026-06-08 | 2026-06-07 15:28 | 2026-07-10 |  | 2026-07-17 |  | 2026-05-16 | 2026-05-16 15:50 | 2026-05-17 | 2026-05-19 14:05 | 2026-05-19 | 2026-05-21 15:34 | 2026-05-24 | 2026-05-24 16:27 |  |  |  |  | 2026-06-07 | 2026-06-13 13:25 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-05-25 | 2026-06-07 15:26 | Site is RTMI | 2026-05-02 | 2026-05-02 21:18 | 1287825 | 231808 | 0 | 0 | 0 | 0 | 1282411.0058 | 209308 | 2026-06-07 11:34:22 +0530 | Zoya Bhatkar | Minutes of Meeting held on Date: 6th June 2026 Attendees: Discussion: DEM 1 Based on 6th June 2026 meeting, below is a list of all the requirements that were discussed during the meeting: LivingÂ Room Mandir in L Shape Mirror Panelling near MandirÂ TV Unit wall decor as per reference shared in WhatsApp Group Dinning Area Texture Paint or Wallpaper with Artifact/Paintings/Photo Frames Invisible Door not Required anywhere in Living Room Parents Bedroom Wardrobe Internals as discussed shared in WhatsApp Group Study wall Unit 4' HeightÂ 1 glass shutter wall Unit to be added Wall Decor Half n Half pattern behind Sofa Paint Pattern with Wall paper or Texture Paint KitchenÂ Foldable Door Tall unit not Required Kitchen platform to be extended & dividedÂ Master BedroomÂ Wardrobe Internals as discussed shared in WhatsApp Group Side Table with 2 Drawer Tall unit with glass Study Table with Single Horizontal Drawer Dresser Design as per reference shared in WhatsApp Group Wall Decor Design behind BED as per reference shared in WhatsApp Group | 2026-06-02 12:56:12 +0530 | Sakshi Hire | CDP: need to do civil changes right side of liivng area considerd as liivng left for dining master bedroom bed head position is towards window | 2026-06-02 12:53:38 +0530 | Sakshi Hire | Some Image was uploaded | 2026-06-08 | 2026-06-07 15:28 | 2026-07-11 |  | Under Construction | 2026-07-01
19803 | Turnkey | May'26 | Saud Shaikh | Roswalt Zaiden | MUM - GOR | Yes | Anjali Jain | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Sanskruti Yadav |  | Hold | Design | DEM1 | 1255163 | 157937.9 | 1579367 | 0 | 0 | 7 | 41 | 0 | 93095 | 546772 | 457358 |  |  | 2026-05-02 | 2026-05-02 18:39 | 2026-05-19 | 2026-05-19 13:00 | 2026-05-23 | 2026-05-24 21:04 | 2026-07-24 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-05-24 | 2026-05-27 12:04 | 2026-05-25 | 2026-05-27 12:16 | 2026-05-27 | 2026-05-28 17:49 | 2026-06-04 | 2026-06-04 15:20 |  |  |  |  | 2026-07-25 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-07-20 |  | Unknown | 2026-05-02 | 2026-05-02 18:37 | 1338447 | 240920 | 0 | 0 | 0 | 0 | 1338037.2927 | 225929 | 2026-06-04 15:30:30 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-04 15:18:17 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Site in not accessible DEM Dates -Â DEM 1 - Can be done in month of july only as cx have asked for payment deviation also for july DEM 2 - TBD DEM 3 - TBD Possession date : Dec 2026 Customer will make 10% : July 2026 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-05-30 17:01:58 +0530 | Vishakha Vaishnav | Tried connecting cx , didn't answered the call | 2026-07-25 |  | 2026-08-01 |  | Under Construction | 2026-12-31
19805 | Turnkey | May'26 | Ravina Keni | Seth Zuri | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Hold | Preproduction | DEM2 | 1278541 | 344999 | 1666616 | 0 | 0 | 2 | 27 | 0 | 0 | 425608 | 507934 |  |  | 2026-05-02 | 2026-05-02 19:27 | 2026-05-11 | 2026-05-11 17:53 | 2026-05-16 | 2026-05-17 11:30 | 2026-06-17 | 2026-06-16 11:35 | 2027-01-01 |  | 2027-01-08 |  | 2026-05-17 | 2026-05-18 19:02 | 2026-05-18 | 2026-05-19 11:39 | 2026-05-19 | 2026-05-19 11:58 | 2026-06-10 | 2026-06-10 13:09 |  |  |  |  | 2026-05-25 | 2026-05-18 19:02 | 2027-01-03 |  | 2027-01-04 |  |  |  | 2027-01-11 |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 | [6 empty] | 2027-02-01 |  | 2027-02-10 |  | 2027-02-09 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-13 |  |  |  | 2027-03-07 |  | 2027-03-09 |  | 2027-03-10 | [5 empty] | 2027-01-12 |  | 2026-06-11 | 2026-06-16 11:32 | Site is RTMI | 2026-05-02 | 2026-05-02 19:26 | 1412386 | 254229 | 0 | 0 | 0 | 0 | 1381288.5118 | 230137 | 2026-07-10 19:51:10 +0530 | Divya Rahangdale | CX will receive the possession by December. | 2026-06-26 13:39:14 +0530 | Sakshi Pokharkar | Cx will get the possession in November or December 2026. | 2026-06-26 12:53:24 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-17 | 2026-06-16 11:45 | 2027-01-02
19806 | Turnkey | May'26 | Jagdeepsingh Sandhu (Swagat Roadlines) | Alta monte | MUM - GOR | Yes | Anjali Jain | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 1862305 | 372461 | 2531710 | 0 | 0 | 53 | 0 | 0 | 0 | 825079 | 664765.2 |  |  | 2026-05-02 | 2026-05-05 14:20 | 2026-05-05 | 2026-05-05 14:53 | 2026-05-08 | 2026-05-07 13:21 | 2026-05-24 | 2026-05-23 16:24 | 2026-06-17 |  | 2026-06-24 |  | 2026-05-07 | 2026-05-09 18:32 | 2026-05-08 | 2026-05-09 20:32 | 2026-05-09 | 2026-05-11 13:55 | 2026-05-16 | 2026-05-16 13:16 |  |  |  |  | 2026-05-23 | 2026-05-23 21:16 | 2026-06-19 |  | 2026-06-20 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-05-17 | 2026-05-23 16:21 | Site is RTMI | 2026-05-02 | 2026-05-02 19:20 | 2145517 | 386193 | 0 | 0 | 0 | 0 | 2136313.382 | 344334 | 2026-06-05 12:46:16 +0530 | Meet Shah | Some Image was uploaded | 2026-05-23 16:15:22 +0530 | Anjali Jain | Living room Tv unit drawer consider Crockery unit base consider Kitchen Hob and chimney consider Wall unit consider loft base unit consider Utility Need to add wall cabinet Bedroom 1 Wardrobe with loft consider bed consider Side table consider Master bedroom Wardrobe with loft consider need to check after IM alignment of wardrobe Dresing need to add 2 side table consider bed consider Additional scope of work paint added acoustic panel added electrification added false ceiling added Decor element added Note Door need to change not in quotation need to add Loose furniture after Final design costing of Automation will consider after cm Lights need to be more | 2026-05-22 19:20:35 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-24 | 2026-05-23 16:26 | 2026-06-18 |  | RTMI
19807 | Turnkey | May'26 | Priya ramesh | 3bhk Villa | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 2808816 | 9999 | 0 | 0 | 0 | 54 | 0 | 270883 | 280882 | 1123526 | 1123526.4 |  |  | 2026-05-02 | 2026-05-12 19:22 | 2026-05-12 | 2026-05-13 02:33 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-02 | 2026-05-02 19:25 | 0 | 0 | 0 | 0 | 0 | 0 | 2380353 | 428463 | 2026-05-19 18:26:55 +0530 | Priyamvada PV | CDP: Changes : Daughter's bedroom Straight wardrobe to be changed to L shape wardrobe Bay window seating to be replaced with pullout drawers for the bottom as platform with opening is getting constructed on window side Son's bedroom Bay window seating to be replaced with pullout drawers for the bottom as platform with opening is getting constructed on cot side right | 2026-05-12 18:47:05 +0530 | Priyamvada PV | Cx name : Priya & RameshÂ Address : 57&58 BTM meadows Akshay nagar, VillaÂ Â Profession : ITÂ Â Possession :Â OCT How many people will be staying :Â 5 to 7 Theme :Â Â Entrance facing : N facingÂ Budget : 20L Entrance - As marked in plan give shoe rack and beside give planterÂ In patio give a bench or 2 seatingÂ Living - Check if the lift side wall needs to be extendedÂ TV Unit refer image - need base, tall unit with shutters and Pooja side need half wall for seatingÂ Add trims for wallsÂ Show sofas and chairs with 200mm height clearance for Robo vacuumÂ Staircase - below need room space and entrance is marked in planÂ Dining area - 6 seater tableÂ Need swing as marked in plan - points have been given at siteÂ Need seating on lift wall (Bench or 2 chairs) Kitchen - Grey or beige need extended breakfast counter as marked in planÂ Double door fridgeÂ counter top is from builderÂ Need OTG tall unitÂ Pantry unit with fixed shelfÂ all tall unit should be in one sideÂ Hob and Hod as marked in plan and no need to give wall cabinets 1feet near hoodÂ Window wall and fridge wall give wall and loftÂ Ground floor bedroom -GBR Need 2shutter wardrobe with loftÂ extended table next to wardrobe and TV on wall Queen bed in cornerÂ First Floor - Music room - Need L shape study and book shelf beside the studyÂ Single seater swing as per planÂ SBR- Blue and greyÂ Walk in wardrobe L shape (try sliding doors)Â 1 shutter for used cloths Semi partition going inside wardrobe on entranceÂ Bathroom wall give long mirror with base storageÂ queen bed as marked in planÂ Door and window on balcony wall is updated according to planÂ Place Bay window as markedÂ Library room -Â Study table as marked Bay window with 2 tall units both sides and loftÂ Need cozy seating space for 4Â Swing point markedÂ DBR- earthy tone , sage greenÂ Walk in wardrobe as marked on one wall long mirror with storage on side wallÂ deck coming on balcony wall as marked queen size bedÂ 2nd Floor- Landscape - amphitheatre seating conceptÂ Roof cut-out is as markedÂ Study room- L shape study tableÂ MBR- beige and goldÂ Walk in wardrobe - L shape with one space for used clothsÂ Long mirror with small ledgeÂ King size bed as markedÂ Study table with set of deep drawersÂ 2 arm chairsÂ PBR - Queen size bed as markedÂ 3 shutter wardrobe with loftÂ Long mirror with base next to wardrobeÂ study table with base storage next to bedÂ Multipurpose Room- 3 shutter wardrobe as marked near bathroom wallÂ CDP - 15th May |  |  |  | 2026-05-24 |  | 2026-05-31
19809 | Turnkey | May'26 | Reena Apandkar | Kalpatru elitus | MUM - Thane | Yes | Bhawaya Goyal | Anamika Dolai | Rushika More | [5 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 2951224 | 9999 | 2951224 | 0 | 0 | 61 | 0 | 285123 | 295122 | 1250688 | 1110290.8 |  |  | 2026-05-02 | 2026-05-11 12:09 | 2026-05-09 | 2026-05-11 13:45 | 2026-05-16 | 2026-05-19 12:14 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-02 | 2026-05-10 11:26 | 2503282 | 447941 | 0 | 0 | 0 | 0 | 2503282 | 447941 | 2026-05-20 13:11:07 +0530 | Hitesh Rawal | Some Image was uploaded | 2026-05-11 11:57:07 +0530 | Bhawaya Goyal | DCM: Client Details Client Name: Mrs. ReenaÂ Project: Kalpataru Elitus Area: 1000 sq ft Language: Hindi/English Planned Budget : 20 L Approx Budget: 25L-27L suggested Design Preference: Modern, easy to clean Space Planning Entrance: Entry planning Shoe rack Safety door Name plate Place to keep Ganpati idol Living Room: 6-seater dining (existing, refurbishment can be done) L-shape sofa (existing, refurbishment can be done) Wall moulding with wallpaper design long with louvers (depends on desing) Wall lamps for aesthetics Trophy display behind dining table Decorative wall on entrance left wall (wallpaper) Wooden laminate mandir False ceiling : Peripheral Kitchen : Fully modular kitchen, civil in our scope (quartz, ceramic sink) Membrane kitchen (white and green colour preferred) Pantry unit Base + overhead + loft storage Refrigerator space Microwave unit + mixer + grinder space + wicker basket Washing machine next to sink Foldable table (iron board) in utility. (keep utility empty, no storage as per Vaastu) Janitor storage Passage : No storage (only wall decor) paintings/wall art Bedroom 2 :Â Grandfather stays Single bed Wardrobe + loft + storage Study table for 2Â MirrorÂ TV provision Bedroom 1 : Daughter + Granny 2 single beds Wardrobe + loft no studyÂ dressing table lavender shade Master Bedroom : Couple + son King size bed Work station Tv on wall + ledge Pull out dressing storage Used cloth hanging heighted headboard aesthetic lights wardrobe + loft (pull out hanging) mouldng with louvers + wallpaper (pastel colour) accent chair Washroom : Vanities + mirrorÂ (lock req. in vanity) Master washroom : free standing bathtub compulsory Mirror with storage behind Additional work : false ceiling electrical painting hanging design washable design |  |  |  | 2026-05-27 |  | 2026-06-03
19810 | Turnkey | May'26 | Sayali N Gaikwad | Arihant Aspair | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | Subhan Khan |  | Active | Design | DEM1 | 1047408 | 119999 | 1199771 | 0 | 0 | 12 | 45 | 0 | 89483 | 468487 | 369439.2 |  |  | 2026-05-02 | 2026-05-03 11:23 | 2026-05-05 | 2026-05-06 15:43 | 2026-05-15 | 2026-05-15 20:06 | 2026-08-05 |  | 2026-08-12 |  | 2026-08-19 |  | 2026-05-15 | 2026-05-16 11:05 | 2026-05-16 | 2026-05-16 11:19 | 2026-05-16 | 2026-05-19 11:05 | 2026-07-31 | [5 empty] | 2026-08-06 |  | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-08-01 |  | Unknown | 2026-05-02 | 2026-05-03 11:20 | 1019043 | 180728 | 0 | 0 | 0 | 0 | 1131662.268 | 185834 | 2026-07-10 19:55:20 +0530 | Divya Rahangdale | CX will receive the possession by End of July. | 2026-06-14 14:30:08 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-05-30 18:48:23 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-08-06 |  | 2026-08-13
19811 | Turnkey | May'26 | Akshay Pramod Konzarkar | Kalpatru elitus | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 2502880 | 9999 | 0 | 0 | 0 | 65 | 0 | 240289 | 250288 | 1074342 | 927962.4 |  |  | 2026-05-02 | 2026-05-06 11:20 | 2026-05-06 | 2026-05-06 13:07 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-05-02 | 2026-05-05 14:50 | 0 | 0 | 0 | 0 | 0 | 0 | 2121085 | 381795 | 2026-05-06 13:03:54 +0530 | Krutika Vernekar | DCM: PROJECT BRIEF 3BHK INTERIOR DESIGN (1340 SQ FT) Client ProfileFamily of 4: Husband, Wife, 2 daughters (Age 5 & 10)Lifestyle: Modern, family-oriented, values comfort + functionalityPersonal Interests: Loves reading (approx. 80 books collection)Design Preference: European minimal, clean, fresh, clutter-free spacesKids: Need playful yet organized environment Design Theme & DirectionStyle: European Minimal (soft Parisian touch)Color Palette: White base, warm beige, light wood tonesKids Room Accent: Lilac pastelOverall Look: Bright, elegant, minimal, functionalFinishes: Matte, subtle textures, clean lines Overall Requirements3 Bedrooms + 1 Study Room + Living + Kitchen + Utility + Servant RoomSmart storage solutions across houseClean, uncluttered visual appealFalse ceiling only in living room FOYER / ENTRYFeature wall with moulding + mirrorShoe storage 2 units (living + study room) 30 pairsInside unit with seating + storage LIVING ROOMLinear sofa (minimal style)TV unit for 65 TV (existing 58)Mandir integrated within TV unit6-seater dining bench setupFalse ceiling STUDY ROOM (HUSBAND & WIFE)Two workstationsFull-height bookshelf (to accommodate ~80 books)Mix of open shelving + closed storageComfortable, well-lit reading/work environment MASTER BEDROOMFull-height wardrobeDresser / vanitySide tables 2Frame TV wall with KIDS ROOM (2 GIRLS)Two separate beds (with storage)WardrobeStudy areaLilac themeAtlantis wallpaper feature wall GUEST ROOMSofa-cum-bedWardrob KITCHEN (PARALLEL SEMI MODULAR)Parallel layoutAppliances: Hob, chimney, OTG ovenTall unit for pantry + ovenFinish: White + light grey, matteHandleless / profile handles UTILITY AREAFront-load washing machineStorage for cleaning suppliesShelving (open + closed mix) PASSAGE STORAGEStorage for kids books & skatesShallow cabinets + open shelves BATHROOM VANITIESFloating vanity units in all bathrooms BUDGETTarget: 2025 LakhsStretch: 26 Lakhs KEY DESIGN GUIDELINESMaintain minimal, clutter-free spacesAvoid bulky furnitureMaximize hidden storageKeep overall look light, airy, and elegantCDP : 12th or 23rd cx travelling to Konkan in middle | [6 empty] | 2026-06-01 |  | 2026-06-08
19812 | Turnkey | May'26 | Suvendu Panigrahi | Raymond - Ten X Habitat | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Aryan Singh |  | Active | Design | DEM1 | 1059124 | 140699 | 1307390 | 0 | 0 | 29 | 26 | 0 | 71126 | 434853 | 412446 |  |  | 2026-05-02 | 2026-05-02 22:44 | 2026-05-10 | 2026-05-12 17:11 | 2026-05-20 | 2026-05-20 21:03 | 2026-07-15 |  | 2026-07-22 |  | 2026-07-29 |  | 2026-05-20 | 2026-05-20 21:44 | 2026-05-21 | 2026-05-20 22:19 | 2026-05-20 | 2026-05-21 12:08 | 2026-07-10 | 2026-07-10 12:40 |  |  |  |  | 2026-07-16 |  | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-07-11 |  | Unknown | 2026-05-02 | 2026-05-02 22:32 | 1107958 | 199432 | 0 | 0 | 0 | 0 | 1109571.9956 | 190642 | 2026-07-10 12:44:21 +0530 | Divya Rahangdale | Welcome call done : Meeting Dates - 10th july DEM 1 : 10th July Possession date : RTMI 10% payment aligned : 10th July Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-06-26 12:57:42 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-14 14:38:04 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-07-16 |  | 2026-07-23
19813 | Turnkey | May'26 | Shaik Iliyas Basha | independent house | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP |  | Sethuragavan R | Sachin I Betageri | Ranjith Kumar |  | Aman Kumar | Raghavendra Gowda | Active | Preproduction | 3D Sign off | 989713 | 269622 | 1837740 | 1348108 | 989713 | 1 | 0 | 0 | 0 | 334085 | 386006.4 |  |  | 2026-05-02 | 2026-05-03 10:17 | 2026-05-04 | 2026-05-10 11:00 | 2026-05-13 | 2026-05-10 11:11 | 2026-06-13 | 2026-06-12 14:46 | 2026-07-10 | 2026-07-09 13:26 | 2026-07-09 | 2026-07-09 13:06 | 2026-05-10 | 2026-05-12 18:39 | 2026-05-11 | 2026-05-16 13:29 | 2026-05-16 | 2026-05-20 14:03 | 2026-05-24 | 2026-05-24 19:24 |  |  |  |  | 2026-06-12 | 2026-06-14 18:47 | 2026-06-19 | 2026-06-26 11:18 | 2026-06-27 | 2026-06-26 11:18 |  |  | 2026-07-11 | 2026-07-14 15:28 | 2026-07-14 | 2026-07-14 19:33 | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-14 |  | 2026-05-25 | 2026-05-31 11:09 | Site is RTMI | 2026-05-02 | 2026-05-03 07:52 | 1557406 | 280333 | 1502664 | 248125 | 1136034.472 | 187583 | 1136034.472 | 187583 | 2026-07-10 21:00:17 +0530 | Aman Kumar | During the meeting held today (10-07-2026), the client raised concerns regarding the descoping charges and the minimum order value. Both concerns were explained in detail. Initially, the client mentioned that he was not aware of the descoping charges. However, we played the onboarding call recording and also shared the offer email, in which the client had acknowledged the same. After reviewing these, the client agreed to bear the descoping charges. Additionally, the client was informed that the minimum order value must remain above â‚¹7 lakhs after all applicable offers, and that the refund is not possible. The client acknowledged and understood these terms. | 2026-05-24 19:29:33 +0530 | Abhinandan K S | RTMI project Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. There is a delay in clearing the Onboarding call and Customer has concerns with the timeline of the project. | 2026-05-23 23:33:03 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-06-13 | 2026-06-12 15:09 | 2026-07-10 | 2026-07-09 13:29 | RTMI
19814 | Turnkey | May'26 | Gitanjali | adarsh | BNG - HSR | Yes | Shefali | Akshay Ds | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Hold | Preproduction | DEM2 | 710959 | 160000 | 946482 | 0 | 0 | 16 | 22 | 0 | 0 | 266575 | 284383.6 |  |  | 2026-05-02 | 2026-05-14 19:00 | 2026-05-15 | 2026-05-15 11:22 | 2026-05-18 | 2026-05-15 15:22 | 2026-06-07 | 2026-06-07 12:13 | 2026-08-17 |  | 2026-08-24 |  | 2026-05-15 | 2026-05-16 14:27 | 2026-05-16 | 2026-05-19 14:53 | 2026-05-19 | 2026-05-21 11:27 | 2026-05-25 | 2026-05-25 18:03 |  |  |  |  | 2026-05-31 | 2026-06-06 16:59 | 2026-08-19 |  | 2026-08-20 |  |  |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 | [6 empty] | 2026-09-17 |  | 2026-09-26 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-29 |  |  |  | 2026-10-21 |  | 2026-10-23 |  | 2026-10-24 | [5 empty] | 2026-08-28 |  | 2026-08-10 | 2026-06-07 11:49 | Site is RTMI | 2026-05-02 | 2026-05-14 18:55 | 802103 | 144378 | 0 | 0 | 0 | 0 | 799977.007 | 132095 | 2026-06-23 16:02:20 +0530 | Akshay Ds | Some Image was uploaded | 2026-06-11 17:32:16 +0530 | Preethi Shetty | Need schedule for design discussion upcoming weekend as per client availability | 2026-06-03 17:00:40 +0530 | Preethi Shetty | Some Image was uploaded | 2026-06-08 | 2026-06-07 12:21 | 2026-08-18 |  | Under Construction | 2026-07-01
19815 | Turnkey | May'26 | Namita Jain Banerjee | SJR | BNG - HSR | Yes | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | DCM Due | 1219706 | 9999 | 0 | 0 | 0 | 73 | 0 | 111972 | 121971 | 487882 | 487882.4 |  |  | 2026-05-02 | 2026-05-03 11:58 | 2026-06-21 | 2026-07-07 13:11 | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-07-18 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-07-13 |  | Unknown | 2026-05-02 | 2026-05-03 11:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1033649 | 186056 | 2026-07-07 13:10:39 +0530 | Maspi Das | RGM Date : 21.06.2026 PID: 19815 Name : Namita Jain Banerjee Typology : 3Bhk From : Kolkata Profession : Sr. HR Property : SJR Parkway Homes Location : Rayasandra Site Access Date : 15th July Main door facing : West Total Members : 4 Kids - 1 9 years old Boy Theme : Aesthetic and warms colors (Beige and Browns with little bit of Gold) Budget : 8-10Lakhs (not more than that) A pet dog CDP date : Yet to Decide Notes- Wall/door between Kitchen and Utility will be removed it will be a full length kitchen Space Walk-in wardrobe for MBR BR2 washroom will become Common washroom and the BR entrance door will come on the bathroom wall so that the bedroom and washroom gets separated Corridor- Show cabinet suggestions (Loose) Foyer- Ledge or Slick drawers on the wall with Wall design Living area- Design I have shown can be considered for the design Notes- Do not make it bulky and cluttered (can considered golden decors to give a statement to the design) Ref opt 2 shared in the group Below 50" TV Sofa wall- Design ref taken Dining area- 6 Seater Crockery with Pooja (Ref taken) Wall design/ picture wall for the parallel wall to the sofa Kitchen- Base units Wall units Lofts Double door fridge Microwave 3' cooktop 3' Chimney Chimney panel towards Cook top side Glass and Laminate Utility - Sink unit will shift to the half all side And storage will come on the opposite side (trying planning a Tall storage) BR1 (Study room)- Wardrobe Study unit (ref taken) BR2 (KBR)- not Kid's BR theme Simple minimal design Study unit Wardrobe Wall design ref taken Study unit (simple and minimal) MBR- Walk-in wardrobe in the bathroom WITH DRESSER Minimal storage beside the bed Cozy corner oppo to bed with book storage Vanity for two bathrooms | 2026-05-03 11:40:14 +0530 | Unknown | About the Customer **3 BHK Renovation Planned for May** Customer is looking to renovate a 3 BHK property (1420 sq ft) with interiors starting by the last week of May. The tentative budget is 8-10 lakhs. **Hesitation for Immediate Experience Center Visit** Customer is hesitant to visit the experience center immediately due to the property work starting in a month. **Agreed to Visit Tomorrow for Offers** Agreed to visit the experience center tomorrow to avail current offers. **Visit Time Confirmation Pending** Customer will confirm the visit time for tomorrow via WhatsApp. **Experience Center Hours Confirmed** Experience center is open until 8 PM. |  |  |  | 2026-07-18 |  | 2026-07-25
19816 | Turnkey | May'26 | Shailesh Panchal | Kalpataru Elitus | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1970364 | 9999 | 0 | 0 | 0 | 73 | 0 | 187037 | 197036 | 804496 | 771795.2 |  |  | 2026-05-03 | 2026-05-03 14:25 | 2026-05-12 | 2026-05-21 20:43 | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-03 | 2026-05-03 14:24 | 0 | 0 | 0 | 0 | 0 | 0 | 1669800 | 300564 | 2026-05-21 16:01:09 +0530 | Maasoumeh Raza | DCM: Requirement Notes 3 BHK Apartment Member: 4 member [couple, daughter & Parents] Possession timeline: October. Interior theme preference: modern and functional. Client prefers minimal yet practical storage solutions. Entrance / Foyer Safety door required at entrance. Shoe rack with angular edge profile inside. Mirror Paneling to be provided near entrance. Provision for pooja unit in foyer area. Kitchen & Utility Base and wall storage cabinets required. Microwave unit provision. OTG provision. Juice mixer storage space. Dishwasher and washing machine provision in utility. Crockery / console unit near dining area. Living & Dining Area 4-seater dining setup required. TV unit with aesthetic detailing. Living area to include comfortable seating arrangement. Common Bedroom 1 (Guest cum study room) The client would like to explore the possibility of shifting the entrance door towards the living area. propose two layout options: Option 1: Without shifting the entrance door (existing door location retained).Option 2: With the entrance door shifted towards the living area, as per the client's preference.Mandir provision as per vastu. Study table with storage/base & wall units. Sofa-cum-bed provision. Vanity unit required. Bedroom 2 (Kids Bedroom) Study table required. Side table provision. Queen size bed. Master Bedroom: Master king-size bed required. Side tables on both sides. TV unit provision. Dressing Unit Vanity unit required. Bathroom: Vanity units required in common/master Bathroom Functional storage and mirror provision. Additional scope of work: Electrical Painting False ceiling | 2026-05-13 11:35:04 +0530 | Maasoumeh Raza | Some Image was uploaded |  |  |  | 2026-05-31 |  | 2026-06-07
19817 | Turnkey | May'26 | Kishor Bapurav Deokar | Canvas residency | MUM - GOR | Yes | Sonal Singh | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Hold | Design | DEM1 | 1155924 | 159719 | 1597186 | 0 | 0 | 8 | 27 | 0 | 71466 | 492977 | 431762.4 |  |  | 2026-05-03 | 2026-06-03 11:53 | 2026-05-08 | 2026-06-03 12:37 | 2026-06-06 | 2026-06-06 13:05 | 2026-08-04 |  | 2026-08-11 |  | 2026-08-18 |  | 2026-05-11 | 2026-05-31 21:36 | 2026-06-04 | 2026-06-03 13:51 | 2026-06-07 | 2026-06-10 17:46 | 2026-06-16 | 2026-06-16 18:29 |  |  |  |  | 2026-08-05 |  | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-07-31 |  | Unknown | 2026-05-03 | 2026-05-03 13:50 | 1355646 | 241540 | 0 | 0 | 0 | 0 | 1350871.527 | 214140 | 2026-06-18 13:06:47 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-17 19:09:12 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - Want to do later o so need to keep the project o hold also there is a payment deviation of 10% DEM 2 - TBD DEM 3 - TBD Possession date : September 2026 Customer will make 10% as per deviation need to collect Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-16 18:30:38 +0530 | Vishakha Vaishnav | IGNORE PREVIOUS COMMENTS | 2026-08-05 |  | 2026-08-12 |  | Under Construction | 2026-10-31
19818 | Turnkey | May'26 | zeena puri | Puri velvet | MUM - GOR | No Estimate | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-03 | 2026-05-15 13:07 | 2026-05-17 |  | 2026-05-03 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-05-28 |  | 2026-06-05 |  | 2026-06-06 |  |  |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-14 |  | 2026-05-23 |  | Unknown | 2026-05-03 | 2026-05-15 13:06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-17 22:15:02 +0530 | Yash Jain | DCM: Zeena puri property- puri velvet - 1246 sq ft 3bhk, possession Dec 2026. occupants - 1 couple, inlaw, 1 son small. D wing - 9th floor. basic - vastuÂ Living room. shoe rack with seating Sofa seating - L shaped sofa plus accent chair. Tv unit - 65'' , with proper storage below, Mandir - near dining table, dining table - 6 seater. kitchen - 3 level storage, Ceiling hght 11' - 1'6'' Dry balcony - washing machine Bedroom 1 - inlaws bedroomÂ QSB , wardrobe,1 side table, mirror for dressing. Bedroom 2 - biggest room QSB,big wardrobe spaces,children single bed, 2 side tableÂ , study table with storage. Bedroom 3- children room no side table, study tbale, qsb, wardrobes, Theme - 2 bhk , bedroom , little vibrant and brighter,Â Budget - 15-20L comfortable for client she said, 20-22L is what i have asked the client to stretch | [6 empty] | 2026-05-28 |  | 2026-06-04
19819 | Turnkey | May'26 | Manik Kale | Nilkanth palm | MUM - Thane | No Estimate | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-03 | 2026-05-03 14:24 | 2026-05-04 |  | 2026-11-30 |  | 2026-12-07 |  | 2026-12-14 |  | 2026-12-21 |  | 2026-11-30 |  | 2026-12-01 |  | 2026-12-01 |  | 2026-12-02 | [5 empty] | 2026-12-08 |  | 2026-12-16 |  | 2026-12-17 |  |  |  | 2026-12-24 |  | 2026-12-25 |  | 2026-12-26 |  | 2026-12-27 | [6 empty] | 2027-01-14 |  | 2027-01-23 |  | 2027-01-22 |  | 2027-01-23 |  | 2027-01-24 |  | 2027-01-26 |  |  |  | 2027-02-17 |  | 2027-02-19 |  | 2027-02-20 | [5 empty] | 2026-12-25 |  | 2026-12-03 |  | Unknown | 2026-05-03 | 2026-05-03 14:02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-03 21:51:36 +0530 | Anant Giri | Some Image was uploaded | 2026-05-03 14:02:08 +0530 | Unknown | About the Customer **Callback Requested After 8th** Customer is currently abroad and requested a callback after the 8th of the month. **Thane Visit Confirmed** Customer confirmed visit to Thane experience center with one other person. Property is at Nilkanth Palms, Ghodbunder. **Renovation Timeline Confirmed** Customer plans to move to a rental property for three months during renovation of their existing home. **Transportation and Address Sent** Car pickup arranged for 11:30 am from Nilkanth Palms, Ghodbunder. Experience center address to be sent via WhatsApp. |  |  |  | 2026-12-08 |  | 2026-12-15
19820 | Turnkey | May'26 | Suresh and Associated | independent villa | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [7 empty] | Active | Preproduction | DEM2 | 944270 | 229999 | 1302071 | 0 | 0 | 38 | 0 | 0 | 0 | 387263 | 327007.6 |  |  | 2026-05-03 | 2026-05-03 16:04 | 2026-05-11 | 2026-05-11 11:50 | 2026-05-14 | 2026-05-13 11:00 | 2026-05-31 | 2026-05-31 18:37 | 2026-10-01 |  | 2026-10-08 |  | 2026-05-13 | 2026-05-19 11:27 | 2026-05-14 | 2026-05-23 15:17 | 2026-05-23 | 2026-05-23 16:05 | 2026-05-24 | 2026-05-24 18:49 |  |  |  |  | 2026-05-31 | 2026-06-07 18:34 | 2026-10-03 |  | 2026-10-04 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-14 | [6 empty] | 2026-11-01 |  | 2026-11-10 |  | 2026-11-09 |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-13 |  |  |  | 2026-12-05 |  | 2026-12-07 |  | 2026-12-08 | [5 empty] | 2026-10-12 |  | 2026-05-25 | 2026-05-31 18:30 | Site is RTMI | 2026-05-03 | 2026-05-03 14:03 | 1103450 | 198621 | 0 | 0 | 0 | 0 | 1201126.466 | 198318 | 2026-06-19 12:26:09 +0530 | Vishal Bandi | MOM DEM 2 Design Discussion and Material Selection 07-06-2026 1.As per our last discussion, Curtain pelmet is added ( it was not there in initial estimation) 2.Dummy wall/invisible door is considered in estimate 9 as mentioned last meeting its not a part of initial estimation), as CX mentioned if we want to hide the door, it will be projecting outside 150mm and CX were asking us to add rafters in it which is technically not possible on existing door + Golden strip has been added now 3. Tv unit with back panel and the tall unit is added (initial design there was no back panel and tall unit for storage, only wall concept were considered) 4. dining entry - both the side Wall moulding is added 5. false ceiling for the living area is added (light and electrifications are not apart of estimation) 6. Pooja unit False ceiling is added- as mentioned photo frame is CX scope 7. Kitchen placements are almost same only changed the fridge placement and added one more extra cabinet 8. Office Room- Bookshelf is addedÂ 9. Study table with one drawer (added) and for the study table added alu strip in itÂ 10. Office room added false ceiling (light and electrifications are not apart of estimation) 11. wall paper is added in Study room 12. MBR- False ceiling is addedÂ 13. loft extended till the wall 14. Wardrobe internal has been discussed 15.Dresser area - as there is existing granite, accordingly need to place the cabinet 16.MBR as there is confusion in measurement, as of now i have considered standard height for the wardrobe and for the loft, it might vary after the cross measurements 17. kids bedroom- wardrobe was not a part of initial estimate - its added now 18. bay window seater has been adjusted according to the space availability 19.study table width has been increasedÂ 20. Dresser base unit has been added( it was not a part of estimation before) 21. Mirror is CX scope 22.Informal Living area- Bar unit design has been changed as per CX requirement 23.false ceiling is added for informal living and for the double height ceiling (light and electrifications are not apart of estimation) 24. as discussed , demolition is not a part of estimation- we are checking out this from backend 25.CX Scope - Plumbing, electrical, Countertop, any civil works costings are not part of estimation 26. as u mentioned, Painting charges has to considered in estimation- i checked with team regarding the charges, so once we come for Cross measurement we will be come with painting vendor - once he check the site according to the area we will be giving you the quote for painting | 2026-06-05 16:54:00 +0530 | Surabhi Ravichandran | Some Image was uploaded | 2026-06-05 16:35:58 +0530 | Keerthan M | CDP: Recap: 19820 - Celebrity Design Presentation (CDP) with the customer Sunday, May 10 ¦ Meeting ¦ Microsoft Teams | 2026-06-01 | 2026-05-31 18:56 | 2026-10-02 |  | RTMI
19821 | Turnkey | May'26 | Mohan | Nambiar Ellegenza | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2394731 | 9999 | 2394731 | 0 | 0 | 66 | 0 | 229474 | 239473 | 988227 | 927558 |  |  | 2026-05-03 | 2026-05-08 17:38 | 2026-05-10 | 2026-05-10 20:24 | 2026-05-13 |  | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-15 | [5 empty] | 2026-05-21 |  | 2026-05-29 |  | 2026-05-30 |  |  |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 | [6 empty] | 2026-06-27 |  | 2026-07-06 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-09 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-07 |  | 2026-05-16 |  | Unknown | 2026-05-03 | 2026-05-08 17:36 | 2029433 | 365297 | 0 | 0 | 0 | 0 | 2029433 | 365297 | 2026-05-26 15:24:21 +0530 | Ankita Agarwal | CDP: Mr. MohanÂ -Tv unit options to be provided with wallpaper/ panelling - Shoe unit to be in parking (Not added in quote) - Dining wall Wallpaper wall to have curved optionÂ - Crockery To be suggested with furniture curve optionÂ - BD will not provide it but give designs for the sameÂ KitchenÂ take fridge in the living along with crockery wall Frdge to be decided if 2 door or 1 doorÂ Kitchen counter to be extended (Price to be differd according) - add wicker basket in the designÂ - more glass cabinetÂ - Loft to be confirmedÂ Stair case to be with wall beading and photos design to be suggestedÂ - Move pooja setÂ - Opp to bed wall frames or paiting to be suggestedÂ | 2026-05-08 14:31:12 +0530 | Ankita Agarwal | DCM: MOM Interior Design Requirement DiscussionProject: Nambiar Ellengenza Budget: 1520 Lakhs Project Status: RTMI (Ready to Move In) Theme Preference: Calm, soothing interiors with a subtle spiritual touch using light pastel shades and optional soft blue accents. 1. Overall Design DirectionTheme to follow a calm and serene aesthetic.Use of light pastel tones with subtle blue accents wherever suitable.Minimal yet elegant design language.Warm ambient lighting with soft finishes.Combination of functional storage and aesthetic detailing.Spiritual and peaceful atmosphere throughout the home.2. Area-wise RequirementsFoyerShoe unit with seating (optional).Compact and functional entry setup.Minimal partition/design element if space permits.Ground Floor Living AreaWall-mounted TV unit.Open ledge/display shelf above or beside TV.Wall panels/wallpaper behind TV unit.Simple false ceiling for living and dining area.Soft ambient lighting with warm profile lights.Calm and elegant visual appearance.Dining AreaFalse ceiling continuation from living.Space planning to maintain openness and easy movement.Integration with crockery/storage unit if possible.Modular KitchenKitchen Requirements:Tall appliance unit.Dishwasher provision.Dedicated storage for mixer grinder and small appliances.Functional zoning for:Cutting/chopping vegetables.Sink usage.Cooking preparation.Efficient storage planning.Utility Area:Base units.Wall-mounted storage units.Functional utility organization.Crockery UnitCombination of:Tall units.Wall units.Base storage units.Elegant and functional display/storage balance.Washroom 1Vanity unit for wash basin.Storage-oriented design with clean finish.3. BedroomsGuest BedroomSwing wardrobe with loft storage.Functional and simple design approach.Master BedroomRequirements:King-size bed with headboard.Swing wardrobe for walk-in closet.Dressing table with mirror and storage.Bay window seating for 1800 1250 window.Calm pastel theme with soothing ambience.Master Bathroom:Vanity unit for wash basin.Kids BedroomRequirements:Queen-size bed.Swing wardrobe for walk-in closet.Bay window seating for 1500 1250 window.Standalone study unit.Wall-mounted storage units.Soft pastel colour palette.Kids Bathroom:Vanity unit for wash basin.Head RoomRequirements:Queen-size bed.Library storage space.Dedicated working/study area.Standalone study unit.Wall-mounted storage units.Swing wardrobes.Vanity unit.Multi-functional and organized layout.4. Puja UnitClosed tall puja unit.Standing-position usability.Elegant spiritual design language.Soft lighting and subtle detailing preferred. | 2026-05-03 14:26:07 +0530 | Ramesh Nayak | Property - Nambiar Ellengenza Budget - 15-20 L RTMI Foyer: Shoe unit(optional) Ground floor Living: Wall mounted tv unit with open ledge above/ side Simple False ceiling on living and dining area Modular kitchen(tall appliance unit, dishwasher provision and storage for mixer grinder, different space usage for cutting, chopping vegetables and sink usage) with utility base units and wall unitsÂ Crockery unit: tall/wall/base units Vanity unit in washroom 1 Swing Wardrobe with lofts for Guest bedroomÂ Vanity unit for wash basin Wall panels behind tv unit/ wall paper Master bed: Swing wardrobe for walkin closet with dressing table with storage with mirror and bay window for 1800*1250 window Vanity unit for Master bed bathroom Kids bed: Swing wardrobe for walkin closet and bay window seating for 1500*1250 vanity unit for kids bathroom Study unit standalone with wall storage unit Puja unit: Closed tall puja unit (standing position) Head room: Library storage space + working space standalone study unit + wall units with swing wardrobes and vanity unitÂ Queen size bed for Head room King size bed with headboard in Master bed Queen size bed in Kids bed calm and soothing with spiritual touch (light shades of blue optional with light tones/ pastel tones of colour) | 2026-05-21 |  | 2026-05-28
19822 | Turnkey | May'26 | Manoj Kumar | Pavani Mirabillia | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | DEM1 | 1084769 | 146999 | 1471659 | 0 | 0 | 34 | 0 | 0 | 69955 | 433908 | 433907.6 |  |  | 2026-05-03 | 2026-05-06 12:08 | 2026-05-19 | 2026-05-19 13:13 | 2026-05-22 | 2026-05-19 14:36 | 2026-07-17 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-05-19 | 2026-05-22 18:39 | 2026-05-20 | 2026-05-30 12:08 | 2026-05-30 | 2026-06-11 11:48 | 2026-06-14 | 2026-06-14 13:18 |  |  |  |  | 2026-07-18 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-06-15 |  | Unknown | 2026-05-03 | 2026-05-04 11:49 | 1247169 | 224490 | 0 | 0 | 0 | 0 | 1234276.7 | 203808 | 2026-07-12 15:01:59 +0530 | Parasa Sri | Client responce | 2026-06-11 14:26:39 +0530 | Athul Ajaykumar |  | 2026-06-11 11:19:50 +0530 | Kushal S | Some Image was uploaded | 2026-07-18 |  | 2026-07-25 |  | Under Construction | 2027-03-01
19823 | Turnkey | May'26 | Parth sakhale | rushtamjee | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Foram Joshi |  | Active | Design | DEM1 | 802838 | 169999 | 802838 | 0 | 0 | 44 | 0 | 0 | 0 | 324664 | 308175.2 |  |  | 2026-05-03 | 2026-05-03 15:00 | 2026-05-13 | 2026-05-19 11:16 | 2026-05-22 | 2026-05-28 20:51 | 2026-08-05 |  | 2026-08-12 |  | 2028-02-15 |  | 2026-05-28 | 2026-05-28 21:37 | 2026-05-29 | 2026-05-29 11:43 | 2026-05-29 | 2026-06-01 13:13 | 2026-06-10 | 2026-06-10 12:56 |  |  |  |  | 2026-08-06 |  | 2028-02-10 |  | 2028-02-11 |  |  |  | 2028-02-18 |  | 2028-02-19 |  | 2028-02-20 |  | 2028-02-21 | [6 empty] | 2028-03-10 |  | 2028-03-19 |  | 2028-03-18 |  | 2028-03-19 |  | 2028-03-20 |  | 2028-03-22 |  |  |  | 2028-04-13 |  | 2028-04-15 |  | 2028-04-16 | [5 empty] | 2028-02-19 |  | 2026-08-01 |  | Unknown | 2026-05-03 | 2026-05-03 14:56 | 680371 | 122466 | 0 | 0 | 0 | 0 | 680371 | 122466 | 2026-07-10 16:23:54 +0530 | Divya Rahangdale | Hold till December 2027 | 2026-07-02 18:55:02 +0530 | Divya Rahangdale | Hold | 2026-06-26 13:55:15 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-08-06 |  | 2026-08-13 |  | Under Construction | 2027-12-01
19824 | Turnkey | May'26 | Chirag Shah | Puri velvet | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1786727 | 9999 | 0 | 0 | 0 | 73 | 0 | 168674 | 178673 | 753177 | 676204.8 |  |  | 2026-05-03 | 2026-05-03 21:42 | 2026-06-02 | 2026-06-16 16:55 | 2026-05-31 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-05-03 | 2026-05-03 21:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1514175 | 272551 | 2026-06-02 17:35:02 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-02 17:31:05 +0530 | Rishika Malviya | DCM: DCM Chirag shah CDP - Sunday - 04/05/26 Possession - June/July VELvet PURI 5 members - 2 couple - a kid. LIVING sofa TV as shown dining KITCHEN want open kitchen concept, but pitched centre kitchen wall opening of dining wall. parallel platform base + top + loft pantry unit. Bedroom (12x10) PARENTS Washroom - W.I.W. make entry in common wash 2 opening in common washroom Bunk Bed with study unit below. [show name of son in Bedroom in 3d] MASTER BEDROOM Basic bedroom req. dry balcony storage see if window seating possible Projector in M.B. Theme: white, beiges. Jain family. Kalpavriksha Name of house. | 2026-06-02 14:43:29 +0530 | Rishika Malviya | CDP: 19824 - Celebrity Design Presentation (CDP) with the customer-20260531_091905UTC-Meeting Recording.mp4 | 2026-06-27 |  | 2026-07-04
19825 | Turnkey | May'26 | Gunjan Gala | Kalpataru Elitus | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 5014915 | 9999 | 0 | 0 | 0 | 66 | 0 | 491493 | 501492 | 2077893 | 1934038.8 |  |  | 2026-05-03 | 2026-05-10 11:34 | 2026-05-10 | 2026-05-21 11:44 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-05-03 | 2026-05-03 15:38 | 0 | 0 | 0 | 0 | 0 | 0 | 4321381.9732 | 764987 | 2026-05-29 10:26:45 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-29 10:26:02 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-21 11:42:48 +0530 | Moksh Mehta | DCM: Client Name:- Gunjan Gala Property:- Kalptaru Elitus Possesion Date:- Aug 2026 Sq Ft:- 1330Sqft No of Members: - Couple (40+) & Mother (70+) Budget :- 55L Ex of White Goods Ent: - Shoe Rack (20-25 Pairs)Wall Concepts Living :- Seating Capacity (as per space)No TV Unit 6 - Seater Dining TableMandir unit with Partition Kitchen:- Base Units x 2NosWall Units x 2NosLoft Units x 1 NosUtility Storage Master Bedroom:- Queen size bedSide TableWardrobe with Loft with Dresser Bedroom :- Guest Bedroom Queen Bed SizeWardrobe with loftStudy TableBook Storage Bedroom 2:- Parent's Bedroom Queen Size BedWardrobe Unit with LoftSide Table with Dresser Washroom:- Vanities :- 3 Nos.To be Re-worked entirely | 2026-06-01 |  | 2026-06-08
19827 | Turnkey | May'26 | Nilesh Mehta | gauri excellence | MUM - GOR | Yes | [8 empty] | Avi Thakkar |  | Lost | Prospect | 10% Payment | 1029104 | 9999 | 0 | 0 | 0 | 56 | 0 | 92911 | 102910 | 444207 | 379076 |  |  | 2026-05-01 | 2026-05-19 12:42 | 2026-05-06 | 2026-05-20 12:07 | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-01 | 2026-05-03 17:07 | 0 | 0 | 0 | 0 | 0 | 0 | 1169985.2314 | 179101 | 2026-06-05 12:59:05 +0530 | Meet Shah | Some Image was uploaded | 2026-05-06 21:59:02 +0530 | Khushi Khandelwal | DCM: 2BHKÂ 733 sqft Posession-Month end Budget-Â ENTRANCE Shoe unit with seating Safety door POP outside the doorÂ Â LIVING & DINING AREA L shaped sofaÂ TV unit with MnadirÂ Floating TV unit 65" TVÂ Mandir- Eye level 4 Seater dining Â double trck for curtain AC above window Magnetic track light KITCHEN Window to outer wall Complete start to end platformÂ Washing machine in utility area with wall cabinet Appliances- Microwave on wall, ref., chimney Wall cabinets Base cabinet BEDROOM-01 Study unit TV unitÂ Queen size bed-Hydraulic Side tableÂ Slinding wardrobe with Fluted glass Double track curtain Mirror on bed wall MASTER BEDROOM Wardrobe in front of bed Dresser beside bed King/queen size bed-Hydraulic Balcony- BarÂ unit in deck area with ref. and crockery storage Swing provision in both the balconies Finishes- MembraneÂ |  |  |  | 2026-05-31 |  | 2026-06-07
19828 | Turnkey | May'26 | RIGHT ADVISORY & CONSULTANCY SERVICES (DHARA SANGNANI) | Elanza | MUM - GOR | Yes | Swapnali Shedekar | Vishakha Vaishnav | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry |  | Rashmita Das | Prasad Bhivaji Hande | Active | Design | DEM3 | 1321247 | 258964 | 1670712 | 0 | 0 | 13 | 6 | 0 | 0 | 600810 | 461472.8 |  |  | 2026-05-03 | 2026-05-05 15:22 | 2026-05-05 | 2026-05-05 15:25 | 2026-05-10 | 2026-05-10 16:12 | 2026-05-27 | 2026-05-26 11:34 | 2026-06-10 | 2026-06-09 12:55 | 2026-07-06 |  | 2026-05-10 | 2026-05-13 19:26 | 2026-05-11 | 2026-05-15 13:40 | 2026-05-15 | 2026-05-19 12:03 | 2026-05-20 | 2026-05-20 12:41 |  |  |  |  | 2026-05-26 | 2026-06-09 12:45 | 2026-06-30 | 2026-06-30 22:01 | 2026-07-01 | 2026-07-02 11:41 |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-05-21 | 2026-05-25 10:50 | Site is RTMI | 2026-05-03 | 2026-05-03 17:01 | 1415858 | 254854 | 0 | 0 | 0 | 0 | 1408648.2915 | 237824 | 2026-05-31 12:25:32 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-26 20:25:21 +0530 | Swapnali Shedekar | MOM - 20/05/2026Â *Living room* - Crockery unit need to re- designed as per site measurementsÂ - Drawers are added to crockery unit and height has been increased. - TV base drawer with open unit is consideredÂ - 4 seater dining to be considered with chairs (Recommended bench with 2 chairs combination) - Shoe unit height to be increased as per requirement. - Mandir placement to be finalised as per vastu directionÂ *Kitchen* - Parallel Semi modular Membrane kitchen is consideredÂ - Appliances sizes are requiredÂ *Master bedroom* - Wardrobe with loft & Breather unit is considered in design and internals are freezed with single glass shutter wardrobeÂ - Queen size bedÂ - Wall design to be finalisedÂ *Bedroom 2* - Platform bed with storage to be considered in this roomÂ - 2 Foldable desk are given in front of the bedÂ - Membrane finished Wardrobe internals are freezed (Can be revisited if needed) *Bathrooms* - Vanity units to be given in both the bathrooms | 2026-05-21 14:38:29 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-27 | 2026-05-26 20:24 | 2026-06-10 | 2026-06-09 12:56 | RTMI
19830 | Turnkey | May'26 | Neha Sinha | saritha Serene | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Priyanka Mathur |  | Sethuragavan R | Suchendra Shetty | Jairam Joshi | Murali S | Aman Kumar | Affaan Abdulla | Active | Handover | Project Closure Pending | 495376 | 495376 | 501059 | 0 | 498395 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-03 | 2026-05-07 11:58 | 2026-05-08 | 2026-05-08 16:27 | 2026-05-08 | 2026-05-08 17:37 | 2026-05-09 | 2026-05-09 10:45 | 2026-05-10 | 2026-05-09 11:42 | 2026-05-10 | 2026-05-10 20:05 | 2026-05-07 | 2026-05-06 20:13 | 2026-05-09 | 2026-05-08 17:50 | 2026-05-08 | 2026-05-08 18:50 | 2026-05-08 | 2026-05-08 19:31 |  |  |  |  | 2026-05-09 | 2026-05-09 10:53 | 2026-05-10 | 2026-05-10 10:27 | 2026-05-11 | 2026-05-10 10:31 |  |  | 2026-05-12 | 2026-05-12 17:08 | 2026-05-13 | 2026-05-13 19:08 | 2026-05-14 | 2026-05-14 12:12 | 2026-05-15 | 2026-05-14 19:57 |  |  |  |  | 2026-05-15 17:32 | 2026-05-30 | 2026-05-30 20:56 | 2026-06-06 | 2026-06-04 21:33 | 2026-06-05 | 2026-06-06 12:42 | 2026-06-04 | 2026-06-06 15:12 | 2026-06-06 | 2026-06-07 17:34 | 2026-06-16 | 2026-06-16 14:21 |  |  | 2026-06-27 | 2026-06-29 10:45 | 2026-06-29 | 2026-06-29 13:13 | 2026-06-30 | 2026-06-29 14:54 |  |  |  |  | 2026-05-13 | 2026-05-14 20:09 | 2026-05-09 | 2026-05-08 19:33 | Site is RTMI | 2026-05-03 | 2026-05-03 16:53 | 481264.3231 | 79483 | 0 | 0 | 478802.5035 | 79077 | 482158.3035 | 79379 | 2026-06-29 15:49:28 +0530 | Jairam Joshi | Project Closure Pending: Pooja unit CNC - vendor FOC ETA - 6th July Installation -8th July Observations -14th July Closure 14th July | 2026-06-16 18:33:20 +0530 | Jairam Joshi | Some Image was uploaded | 2026-05-25 10:24:03 +0530 | Jairam Joshi | Procurement: PI works completed SRD task closed | 2026-05-10 | 2026-05-09 10:48 | 2026-05-10 | 2026-05-09 11:44 | RTMI
19832 | Turnkey | May'26 | Madhukar | Adarsh | BNG - HSR | Yes | Muskan Agarwal | Abhinandan K S | Soumya KP | [5 empty] | Ravikiran K |  | Active | Preproduction | DEM2 | 3024096 | 604819 | 3351994 | 0 | 0 | 16 | 0 | 0 | 0 | 1244986 | 1174290.8 |  |  | 2026-05-03 | 2026-05-10 10:45 | 2026-05-09 | 2026-05-10 12:27 | 2026-05-13 | 2026-05-19 13:18 | 2026-06-22 | 2026-06-22 12:02 | 2026-08-21 |  | 2026-08-28 |  | 2026-05-19 | 2026-05-20 19:00 | 2026-05-20 | 2026-05-20 19:21 | 2026-05-20 | 2026-05-21 18:40 | 2026-05-31 | 2026-05-31 19:28 |  |  |  |  | 2026-06-22 | 2026-06-29 18:43 | 2026-08-23 |  | 2026-08-24 |  |  |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 | [6 empty] | 2026-09-21 |  | 2026-09-30 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-03 |  |  |  | 2026-10-25 |  | 2026-10-27 |  | 2026-10-28 | [5 empty] | 2026-09-01 |  | 2026-06-01 | 2026-06-22 11:57 | Site is RTMI | 2026-05-03 | 2026-05-03 17:38 | 2840672 | 511321 | 0 | 0 | 0 | 0 | 3440408.9015 | 568082 | 2026-05-31 19:30:58 +0530 | Abhinandan K S | RTMI project Initial measurement done. Civil vendor visited the site and given the quote. Most of the civil works will not be done from our side. Need clarity on this to proceed with the design phase. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1 Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. | 2026-05-21 18:39:24 +0530 | Athul Ajaykumar | Possession Status: RTMI Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 120 + 10 business days (explained) Detailed timelines were explained to the customer during the call, based on the finalized scope of work. . Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 -Â Plan of Action Discussed During the Call: * IMs - 22nd May 2026 * DEM 1 - 30th May 2026 * 10% Payment - 30th may 2026 Explained that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special offer (100000) Special offer (50000) PM fee waiver (5%) Design fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Silver Coin 21g Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 23,34,194 Suggested for Hold after collecting 10% Client VOC Client mentioned he has civil work planned (wall demolition in the kitchen and entry of the servant room) and shifting the entry point of the master bedroom's washroom. | 2026-05-20 19:20:53 +0530 | Ravikiran K | Some Image was uploaded | 2026-06-23 | 2026-06-22 12:12 | 2026-08-22 |  | RTMI
19834 | Turnkey | May'26 | Mr. Abhay Bhaskar | Assetz Soho & Sky | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Hold | Preproduction | Site Readiness 1 | 2842574 | 568515 | 3544318 | 0 | 0 | 0 | 4 | 0 | 0 | 1438109 | 835950 |  |  | 2026-05-03 | 2026-05-06 12:03 | 2026-05-12 | 2026-05-12 16:17 | 2026-05-17 | 2026-05-29 14:27 | 2026-07-11 | 2026-07-11 17:20 | 2026-09-20 |  | 2026-09-27 |  | 2026-05-29 | 2026-05-29 18:32 | 2026-05-30 | 2026-06-03 16:40 | 2026-06-03 | 2026-06-10 13:18 | 2026-06-12 | 2026-06-12 18:58 |  |  |  |  | 2026-07-12 | 2026-07-11 13:06 | 2026-09-22 |  | 2026-09-23 |  |  |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 | [6 empty] | 2026-10-21 |  | 2026-10-30 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-02 |  |  |  | 2026-11-24 |  | 2026-11-26 |  | 2026-11-27 | [5 empty] | 2026-10-01 |  | 2026-07-31 | 2026-07-11 13:43 | Site is Non-RTMI | 2026-05-03 | 2026-05-05 16:52 | 3003660 | 540658 | 0 | 0 | 0 | 0 | 2939975.7558 | 511663 | 2026-07-12 15:03:01 +0530 | Parasa Sri | Hold till september | 2026-06-10 13:18:01 +0530 | Athul Ajaykumar |  | 2026-06-06 18:07:39 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: September Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 160 days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 will update to the sales team * 10% Payment Stage Tentatively scheduled for (15th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Anniversary '26 Studio Offer : 50,000 Silver Coin 21g Laminate Upgrade - May '26 Campaign PM Fee Waiver (4%) 100% GST Waiver Final Closing Value Discussed: 28,42,575 Checklist terms descoping and agreement terms are cleared Rejections: Address not updated | 2026-07-12 | 2026-07-11 17:23 | 2026-09-21 |  | Under Construction | 2026-09-30
19835 | Turnkey | May'26 | Utkarsh Mishra | Adarsh greens | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2913397 | 9999 | 0 | 0 | 0 | 55 | 0 | 281341 | 291340 | 1165359 | 1165358.8 |  |  | 2026-05-03 | 2026-05-06 12:06 | 2026-05-12 | 2026-05-12 16:19 | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-05-28 |  | 2026-06-05 |  | 2026-06-06 |  |  |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-14 |  | 2026-05-23 |  | Unknown | 2026-05-03 | 2026-05-05 16:53 | 0 | 0 | 0 | 0 | 0 | 0 | 2468981 | 444416 | 2026-06-23 18:48:22 +0530 | Alekhya Korada | CDP MOM 1)Shoe rack, -Â -floor to ceiling -Glass shuttersÂ -Loft -tall unit -bottom and top unit with ledges next to tall unit -no bottom framing needed. Only skirting is sufficient.Â Adiyogi wall -Wall mural to be shown without bottom console (wall mounted) -Glass partition or any other partition with door for study room.Â All walls need to be curved and full house limewash paint - painting to be added in the quotationÂ Crockery and pooja unit- -floor to ceiling - fully covered with glass unitÂ -bottom and top unit with glass -crockery to be planned with Pooja unit and the whole wall to be covered.Â -depth to be the sameÂ -Pooja unit- to have asymmetric ledges for the idols.Â -sit and pray -pull out seater -no cnc designs- needs to be covered with glass or solid shutters in carpentry.Â Kitchen- -They were more or less okay,Â -Plumbing needs to be checked -dado tiles - black marble finish with gold grains or any such design -Countertop- granite -Kitchen entrance partition- multicoloured glass blocks -Vanity unit to be provided for the dedicated space at the entrance of the kitchen.Â Master bedroom- -L shaped end to end wardrobeÂ -Drawers at the bottom with full length wardrobe -dresser unit to be planned on the column (which starts with the wardrobe on the right) -not a fan of an elaborate dresser unit. Just a full length mirror is sufficientÂ -bay window seater to be planned after the wardrobe.Â -the entire walkin wardrobe to look harmonious and in continuity.Â -Bed headrest -Â to be added in quotation -modular bed with fixed bedside drawersÂ -wall concept Kids bedroom- -modular bed with steps.Â -sliding wardrobe- up till the ceiling to be planned starting from top of the step up bed.Â -head rest to be added in quotation.Â -wall concept Guest bedroom -Drawers at the bottom -Full length wardrobe up till the ceiling -bed-existing , maybe they will need side tables - to be added in the quoteÂ Note- Painting- limewash or any equivalent, electrical fixtures, false ceiling, carpentry, living room partition walls, head rests, modular beds (MBR and KBR), carpentry- all these should be added in the quote. | 2026-05-04 13:10:06 +0530 | Yogesh Patidar | RGM MOM for Mr and Mrs. Mishra - 3rd May ( Budget 20L) Civil Details: Kitchen and Study space is been switched along with Living and Dinning Couple will be staying in the house with a Guest Room and Kids room room for future with Muted Colors. Existing Furniture( Optional to use) 4Cane Chair for Balcony 1 Existing Bed ( Queen size) will be used for Guest Room Existing Shoe Rack (3'*4') , 1.5*2) Coffee Table 2 nos Appliances- WM front load, RO New Sofa is Finalized- 3seater (7feet *2.6feet) False ceiling with Wave Pattern Finish in Common Space with Lights.( Lighting Option to be suggested) Curve option in Edges and Top Space of Entrance Spaces Door Color -Wooden Finish, Mosquito mesh panel for windows See-through sheet for Windows Paint Option with Lime Wash Space For Laundry Basket Trap Door Option in Passage Living Are Pelmet option for Curtian and AC Digital Lock Entrance Space: Shoe Rack- Internal Niche space with Everyday use space with Maximum Storage, Seating space, Loft. Wall with Adiyogi Mural and connected to Study Room with Door/ Any other details and Same detail continued with Bathroom Room Study Space: Study Space for one person with curve and granite material, tall unit, ledge, Sofa space and Book Shelf Living area: Tall unit, Base unit, Sound Bar, speaker space in tall unit Â Wall Finish to be something different ( to be excluded Wallpaper, Rafters) Space Between Living and Dining ( Beam to be highlighted and Internal space to utilized with either swing/ Decor space Dining area: Crockery unit- Base unit with Top glass shutter and Mirror In between Pooja Mandir- Pocket Door with Storage, width of Pooja to be 2.6feet and Internal shelf to be keep at least 20 Idols includes of Photo frames, Abstract shelf with 8inch space, Bells Hanging, Pullout tray. Balcony- Janitor Unit Kitchen-( Green, Black, Wood Finish) Counter Height to be 37/38inch Base unit, wall unit and Loft Entrance Wall to be Removed and curve Arch to be incorporated as an option Refrigerator (Double Door) along with Pantry - to look as Partition from Dining wall Pedestal Sink in Dining space for Hand wash Tall unit with Drawers, Ho, Chimney, Single sink with under RO,Spice Rack, Mesh Drawer for Veggies Utility to be created in space of Bathroom Washing Machine and Dishwasher space Big Bowl Sink Mesh Drawer for Veggies Storages Kids Room: Step up Bed with drawers ( Queen Size with Hydraulic Lift), Sliding wardrobe opposite to bed, Bed Back wall highlighter, Lighting Option Guest Room: Hinged wardorbe with Bottom Drawer and Shutter to be full length (Rattan Shutter) Existing Bed, headboard to be created ( FInish Walnut Brown),Side table, Due to KuberMool no cluter in corner space,Space for Soil clothes, Mirror Master Bedroom:(No Projected Hanlde) Hinged wardorbe with Lshape Bottom Drawer and Shutter to be full length (Curve Shutter) Curve Bed,Foldabe study table,Hidden drawer as a Locker,Window seater with Arch, Mirror with some cosmetic space Washroom: Vanity and Mirror MBR Washroom Vanity, Mirror, Top storage |  |  |  | 2026-05-28 |  | 2026-06-04
19836 | Turnkey | May'26 | Bharati anandraj | siddha sky | MUM - GOR | Yes | Khyati Bandi | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Design | DEM1 | 923652 | 116275 | 1162749 | 0 | 0 | 28 | 28 | 0 | 68455 | 428082 | 310839.6 |  |  | 2026-05-03 | 2026-05-05 15:30 | 2026-05-14 | 2026-05-14 13:13 | 2026-05-17 | 2026-05-19 14:35 | 2026-06-24 |  | 2026-07-01 |  | 2026-07-08 |  | 2026-06-05 | 2026-05-13 19:01 | 2026-05-18 | 2026-05-15 11:47 | 2026-05-20 | 2026-05-20 12:48 | 2026-05-24 | 2026-05-24 17:50 |  |  |  |  | 2026-06-25 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-20 |  | Unknown | 2026-05-03 | 2026-05-05 15:30 | 985380 | 177368 | 0 | 0 | 0 | 0 | 984767.981 | 166257 | 2026-06-05 13:21:35 +0530 | Meet Shah | Some Image was uploaded | 2026-05-26 16:18:26 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-24 17:49:38 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Can be done after cx receives OC DEM Dates -Â DEM 1 - Cx said that he want to do DEM 1 after IM only DEM 2 - TBD DEM 3 - TBD Possession date : OC Expected May end Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-25 |  | 2026-07-02
19838 | Turnkey | May'26 | Avinash | 2BHK | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 3707509 | 9999 | 3707509 | 0 | 0 | 57 | 0 | 360752 | 370751 | 1483004 | 1483003.6 |  |  | 2026-05-03 | 2026-05-03 19:24 | 2026-05-07 | 2026-05-07 19:32 | 2026-05-10 | 2026-05-19 17:38 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-03 | 2026-05-03 19:13 | 3141957 | 565552 | 0 | 0 | 0 | 0 | 3141957 | 565552 | 2026-05-09 18:28:48 +0530 | Priyamvada PV | Avinash CDP MOMÂ : 09.05.26 Shoe rack, centre storage to extend higher TV unit bas extend towards left and remove ledges in right TV design to check (ref required) TV tall unit not preferred, but have decor to be kept in living flap down with alu frame & glass for tv open unit Â DW & WM at a certain height with pullout storage below and check space in site, DD sink unit towards right with large bowl Loft towards opp of utility door wall Pooja above CNC panellingz to be done,Â Kitchen glass shutter on either sides of chimney, a tall unit on fridge side too. Metal partition next to fridge, partition in kit entry also to be metal partition Additional tandem drawers, Sink in kitchen to be single bowl Wicker basket in tall unit Crockery drawer unit below Wall glass unit above Tall glass unit 1 will be in laminate finish MBR - used cloth remove , will decide later extend wardrobe to 8 feet W Add a tall unit with glass next to cot with drawers below Add storage below tv unit & next to existing drawer add drawer storage, remove tall unit on dresser wall 8'H wardrobe with bottom drawers for MBR along with used cloth storage side table extended from left wall from hinged wardrobe area PBR Wardrobe to be extended towards left Floating drawer unit on either side of cot & bay window storage for entire wall drawer unit on either sides rest doors GBR Tall unit on left wall with mirror on doorÂ Space inside to keep the locker (size required) Projector space on cot opp wall drawer below study storage | 2026-05-07 18:45:01 +0530 | Priyamvada PV | Cx name : Avinash Address : SSVR - 1206 Profession : BankerÂ Possession : Sep 1st weekÂ How many people will be staying : 4Â Theme : Morden tradition / MinimalÂ Entrance facing : E facingÂ Budget : 15 - 20 maxÂ Entrance - Need shoe rack with 1 shutter for cylinder and need seating with storage as well - refer imageÂ Living - 75" tvÂ tv unit need space for showcasing so give tall unit (open or closed ) - Dark tone is fineÂ Sofa back wall need trimsÂ Main Balcony - Need janitor unit as marked in planÂ Dining area - 6 seater dining table - placement as marked in planÂ The utility door is coming on crockery wall as marked in plan and 3' wall will be extended as wellÂ Crockery unit need space for book shelf which is closed, base storage and counter top , provision for basin needed as marked in planÂ Kitchen -Â need partition from living to kitchenÂ pooja unit of 3' and need 650mm depth for the unit - note - unit shouldn't look alike kitchen - refer imageÂ counter top extending as U Shape Sink on window wallÂ Double door fridge and placement on extended wallÂ Roll up unit neededÂ Add base, wall and loft ( not for pooja) Add pantry unitÂ Granite to be includedÂ Utility - Need sink unit WM and DW provision (check space ) wall and loft storageÂ MBR -Â Mirror should not be in south or west wallÂ Long mirror with tall unit as marked in planÂ Need panelling for bathroom door - extend the panel with dresser tall unitÂ Tv unit needed along with dresserÂ 4 shutter wardrobe with full heigh shutters (not aristo sliding )- need used cloths unit King size bed and side table and balcony corner place a tall unit as referenceÂ Bed back panelling needed (no fabric) PBR -Â 3 shutter wardrobe with loft - thin handles - need used cloths unit Mirror should not be in south or west wall Long mirror with storage - find placementÂ King size bedÂ Bed back panelling needed (no fabric) Need bay window as marked in planÂ Tv unit need wall ledgeÂ GBR- Need design for sofa cum bed and murphy bedÂ work station with wall storage was marked in plan and extend the table top till windowÂ long mirrorÂ Sliding wardrobe with loft - need used cloths unit Bathrooms- Need vanity unit for all bathroomsÂ CDP - 9thÂ | 2026-05-07 17:46:30 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-27 |  | 2026-06-03
19839 | Turnkey | May'26 | Ashutosh Khetan | Purva Atmosphere | BNG - HRBR | Yes | [10 empty] | Active | Prospect | 10% Payment | 1240635 | 9999 | 1240635 | 0 | 0 | 63 | 0 | 114065 | 124064 | 500940 | 491568.4 |  |  | 2026-05-03 | 2026-05-08 17:01 | 2026-05-04 | 2026-05-08 22:48 | 2026-05-13 | 2026-05-13 11:31 | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-05-13 |  | 2026-05-14 |  | 2026-05-14 |  | 2026-05-15 | [5 empty] | 2026-05-21 |  | 2026-05-29 |  | 2026-05-30 |  |  |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 | [6 empty] | 2026-06-27 |  | 2026-07-06 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-09 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-07 |  | 2026-05-16 |  | Unknown | 2026-05-03 | 2026-05-08 12:08 | 1051386 | 189249 | 0 | 0 | 0 | 0 | 1051386 | 189249 | 2026-05-29 12:17:49 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-07 18:50:40 +0530 | Rhea Rathod | DCM: Possession - In hand Rental purpose The clients may shift to this property after 4-5 years Purva atmosphere 3BHKÂ False ceiling in dining and living Foyer - -Shoe rack - w -4.5 feet h - 3 feet without skirting Living area - -TV unit - middle glass flap down, 2 drawers Kitchen - - Modular kitchenÂ - Base cabinets, wall cabinets, Loft - Granite - to be given - Dado tiles - installation - Fridge - single door Utility - - Dado tile installationÂ - Sink and tap - RO unit and dishÂ - Sink cabinet - Wall unit - On top of the washing machine All bedroomsÂ - sliding wardrobe with loft Balcony -Â - tall unit | 2026-05-03 19:21:13 +0530 | Unknown | About the Customer **Rental Property Interior Requirements** Customer requires basic interiors for a 3.5 BHK property in Thanisandra, Bangalore, for rental purposes, including a modular kitchen, wardrobes for three bedrooms, and a utility sink. Possession has been received. **Budget Below Minimum Ticket Size** Customer's budget of â‚¹6-8 lakhs is below the company's minimum ticket size of â‚¹7 lakhs. **Experience Center Visit Pending Confirmation** Customer plans to visit the experience center, open seven days a week, but needs to confirm a time with his wife due to work commitments. **Agent to Share Details and Await Time** Agent will share experience center details via WhatsApp and await the customer's confirmed time slot. | 2026-05-21 |  | 2026-05-28
19840 | Turnkey | May'26 | Manoj Rai | Assetz Soho & sky | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Shashank Singh |  | Active | Preproduction | DEM2 | 1703313 | 340664 | 2203517 | 0 | 0 | 2 | 0 | 0 | 0 | 681324 | 681325.2 |  |  | 2026-05-03 | 2026-05-19 19:11 | 2026-05-19 | 2026-05-20 14:09 | 2026-05-23 | 2026-05-20 14:13 | 2026-06-24 | 2026-06-23 11:53 | 2026-09-07 |  | 2026-09-22 |  | 2026-05-20 | 2026-05-21 18:50 | 2026-05-21 | 2026-05-28 19:26 | 2026-05-28 | 2026-05-29 16:41 | 2026-05-30 | 2026-05-30 20:17 |  |  |  |  | 2026-06-23 | 2026-07-13 16:14 | 2026-09-17 |  | 2026-09-18 |  |  |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-28 | [6 empty] | 2026-10-16 |  | 2026-10-25 |  | 2026-10-24 |  | 2026-10-25 |  | 2026-10-26 |  | 2026-10-28 |  |  |  | 2026-11-19 |  | 2026-11-21 |  | 2026-11-22 | [5 empty] | 2026-09-26 |  | 2026-06-03 | 2026-06-23 11:37 | Site is RTMI | 2026-05-03 | 2026-05-16 22:23 | 1867387 | 336129 | 0 | 0 | 0 | 0 | 1815868.6638 | 306596 | 2026-05-30 20:19:04 +0530 | Rajeshwari S | Welcome call done along with designer Possession in Sept 2026 Soft possession will be given in August for Initial measurement Layout can be finalized on floor plan Client needs one meeting in June first week post that 10% payment will be given. once layout is finalized -project will be on hold till August | 2026-05-29 16:40:59 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Soft Possession: August 2026 Under construction completion date: September 2026 Scope of Work: Modular + Painting (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible. * DEM 1 7th June 2026 on basis of layouts * 10% Payment Stage 8th June 2026 (after 1st DEM) *Transaction will be B2C self-funding. *No civil work at site. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,15,869 Offers Discussed During the Call: Silver Coin 21g Free Hob & Chimney Offer Design Fee Waiver (2.5%) PM fee waiver (5%) Laminate Upgrade - May '26 Campaign 100% GST Waive Final Closing Value Discussed: 17,03,314. Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-05-29 16:03:12 +0530 | Shashank Singh |  | 2026-06-24 | 2026-06-23 11:55 | 2026-09-08 |  | Under Construction | 2026-08-31
19841 | Turnkey | May'26 | Mr. Prakash Assudani | Godrej Park Retreat | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1674720 | 9999 | 1674720 | 0 | 0 | 34 | 0 | 157473 | 167472 | 685562 | 654213.6 |  |  | 2026-05-03 | 2026-05-03 19:33 | 2026-05-06 | 2026-05-06 18:35 | 2026-06-02 | 2026-06-11 13:09 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-03 | 2026-05-03 19:31 | 1421542 | 253178 | 0 | 0 | 0 | 0 | 1421542 | 253178 | 2026-05-31 16:30:25 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-05-06 18:12:07 +0530 | Swati Rathod | Some Image was uploaded | 2026-05-06 18:10:28 +0530 | Swati Rathod | Based on 06-05-2026 meeting, below is a list of all the requirements that were discussed during the meeting: PID: 19841 Property - 3BHK possession - 01-05-2026 Budget - 15L Members - 3 Profession - software - Japandi theme - false ceiling in common space - tv space in 2 bedroom(bedroom-2& MBD) - No bright colours - wooden tones should be used - space for existing paintings.(plane wall design) - wall niches for some storage FOYER : - shoe rackÂ LIVING: - Tv unit(65") curved @ edges - tv back wall fluted - l curved sofa DINNING: - 4 seater Pooja unit:Â - placement to be look afterÂ KITCHEN: - bottom unit - top units - loft - brk fast counter(opp) - tall unit - 1 bowl sink - double door fridge UTILITY: - W.M - Single bowl with drainer sink TOILETS: - vanityÂ - glass partition in only 2 bathrooms M.BEDROOM: - Q size bed(full upholstered head board) - Sliding wardrobe with loft(matt lam) - dresser - study unit BEDROOM - 1: Q size bed openable wardrobe with loft dresser BEDROOM - 2:(MBR) - Q size bed - Sliding wardrobe with loft - dresser - study unit with top ledges and only counter in bottom. | 2026-06-19 |  | 2026-06-26
19842 | Turnkey | May'26 | Ashwini Suresh | Independent house | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 3241128 | 9999 | 0 | 0 | 0 | 57 | 0 | 314114 | 324113 | 1373552 | 1219350.8 |  |  | 2026-05-03 | 2026-05-06 12:04 | 2026-05-19 | 2026-05-19 13:46 | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-03 | 2026-05-04 11:49 | 0 | 0 | 0 | 0 | 0 | 0 | 2786973 | 501655 | 2026-05-19 13:55:51 +0530 | Alekhya Korada | Some Image was uploaded | [6 empty] | 2026-05-27 |  | 2026-06-03
19843 | Turnkey | May'26 | sagar | 2BHK | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1562413 | 9999 | 1562413 | 0 | 0 | 66 | 0 | 146242 | 156241 | 624965 | 624965.2 |  |  | 2026-05-03 | 2026-05-03 21:03 | 2026-05-04 | 2026-05-07 14:11 | 2026-05-10 | 2026-05-19 17:34 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-03 | 2026-05-03 20:59 | 1324078 | 238334 | 0 | 0 | 0 | 0 | 1324078 | 238334 | 2026-05-19 17:32:07 +0530 | Priyamvada PV | CDP Notes 08.05.26 1. POP punning on sofa left side to be removed 2. Pooja unit to be done as double door unit bottom storage with top open unit 3. TV unit back panel with cove light provision to be done curved edge 4. Wall ledges has to be curved edges 5. Kitchen, gap between walls on either sides is 3'W only 6. Symmetrical glass unit on either sides of chimneyÂ 7. Spice rack ledge on left side of kitchen below wall unit 8. Sink unit to be smaller of 1.5'W shutter 9. Beam is running b/w kitchen & utility 10. MBR mirror to be on left side of the cot on wall 11. Instead of tall appliance unit, require wall mounted M/W unit and separate base storage with countertop 12. Wallpaint design, with color codes to be proposed for the passage area where ledges are present in design phase, paint client scope | 2026-05-04 17:02:01 +0530 | Priyamvada PV | Cx : Sagar Karira From : UP Residing in Blore Property : Ankura Meridian 3 BHK F2C height : 9' Facing :Â West Property Location : Kadugodi Site access date : May'26 Possession date : Aug'26 Family members : 2 + 2 Kids : NA Budget : 10L including granite & FC Scope of Work :Â FoyerÂ Shoe rack (Approx 8-10 pairs) SeatingÂ Living TV unit as per FP Floating TV with ledgesÂ Back panel with mirror on left Ref images shared Existing 3 + 2Â sofa Dining Space for 6 seater dining table Pooja 2' with gap between pooja & crockery Crockery - base w/o drawers , mirror then wall units with glass Hand wash area :Â Plumbing removed L corner wall to be designed with either shelves / mouldings / open for suggestion based on aesthetics Kitchen Half 4'H walls between kitchen & utility Parrallel kitchen Small sink in kitchen Main sink 4'W from builder for utility Granite - BD scope No dishwasherÂ WM as per FP Hob - spice rack , base , wall units with glass & loft Fridge side - tall unit with M/W space, above mixer & fryer, loft aboveÂ 2'W Wicker basket at bottom Wall storage above WM Dish drainer + Ro above utility sink No loft in utility above utility sink area Entry paneling in kitchen entry MBRÂ Existing King size with side tables 72 x 78 with 2x2 Dressing table WR 8'W sliding With loft MBR vanity Existing granite Base storage with mirror BR-1 (KBR) 3350x3600 No cot for now - queen size cot space to be considered 6'W hinged wardrobe with loft only above wardrobe Study table (placement to be checked) Wall ledges Common vanityÂ Existing granite Base storageÂ BR-2 (GBR) 3350x3650 Queen size as per FP 6'W sliding WR with loft above wardrobe Dressing on left of wardrobe / next to cot False ceiling :Â Peripheral FC in Common areaÂ Not in kitchen & bedroom | 2026-05-04 16:52:42 +0530 | Priyamvada PV | Cx : Sagar Karira & From : UP Residing in Blore Property : Independent house F2C height : 9' Facing :Â West Property Location : Kadugodi Site access date : May'26 Possession date : Aug'26 Family members : 2 + 2 Kids : NA Budget : 10L including granite & FC Scope of Work :Â FoyerÂ Shoe rack (Approx 8-10 pairs) SeatingÂ Living TV unit as per FP Floating TV with ledgesÂ Back panel with mirror on left Ref images shared Existing 3 + 2Â sofa Dining Space for 6 seater dining table Pooja 2' with gap between pooja & crockery Crockery - base w/o drawers , mirror then wall units with glass Hand wash area :Â Plumbing removed L corner wall to be designed with either shelves / mouldings / open for suggestion based on aesthetics Kitchen Half 4'H walls between kitchen & utility Parrallel kitchen Small sink in kitchen Main sink 4'W from builder for utility Granite - BD scope No dishwasherÂ WM as per FP Hob - spice rack , base , wall units with glass & loft Fridge side - tall unit with M/W space, above mixer & fryer, loft aboveÂ 2'W Wicker basket at bottom Wall storage above WM Dish drainer + Ro above utility sink No loft in utility above utility sink area Entry paneling in kitchen entry MBRÂ Existing King size with side tables 72 x 78 with 2x2 Dressing table WR 8'W sliding With loft MBR vanity Base storage with mirror BR-1 (KBR) 3350x3600 No cot for now - queen size cot space to be considered 6'W hinged wardrobe with loft only above wardrobe Study table (placement to be checked) Wall ledges Common vanityÂ Existing granite Base storageÂ BR-2 (GBR) 3350x3650 Queen size as per FP 6'W sliding WR with loft above wardrobe Dressing on left of wardrobe / next to cot False ceiling :Â Peripheral FC in Common areaÂ Not in kitchen & bedroom | 2026-05-27 |  | 2026-06-03
19844 | Turnkey | May'26 | Rajendra Panidepu | OTHERS | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1382833 | 9999 | 0 | 0 | 0 | 73 | 0 | 128284 | 138283 | 565049 | 541217.2 |  |  | 2026-05-03 | 2026-05-03 21:05 | 2026-05-06 |  | 2026-05-09 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-05-09 |  | 2026-05-10 |  | 2026-05-10 |  | 2026-05-11 | [5 empty] | 2026-05-17 |  | 2026-05-25 |  | 2026-05-26 |  |  |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 | [6 empty] | 2026-06-23 |  | 2026-07-02 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-05 |  |  |  | 2026-07-27 |  | 2026-07-29 |  | 2026-07-30 | [5 empty] | 2026-06-03 |  | 2026-05-12 |  | Unknown | 2026-05-03 | 2026-05-03 21:03 | 0 | 0 | 0 | 0 | 0 | 0 | 1175018 | 207814 | 2026-05-15 14:55:28 +0530 | Rajasekar Ranganathan | Requirement Discussion MOMClient Name: Rajendra & Meena Project Location: Ankura Meridian - C 401, Hyderabad Profession: IT Expected Possession: September Family Size: 2 Adults + 2 Kids Design Theme: Minimal Entrance Facing: West Facing Overall Budget: 12 Lakhs CDP Submission: May 16th Living RoomExtend TV wall as discussed.TV unit to include:1 Tall UnitBase UnitDesign as per shared reference image.Seating requirement:3-Seater SofaArm Chairs as marked in layout.Sofa back wall:Wallpaper finish only.No trims / mouldings / curves.Dining Area6-Seater Dining Table.Pooja unit in dining corner as per reference.Include only 2 long LEDges inside.Client has only one photo frame for placement.Crockery unit to be positioned after pooja unit.Master Bedroom (MBR)Bed position shifted to window wall.Electrical switch points to be revised accordingly.Sliding wardrobe with loft storage.600 mm long mirror with base unit for dresser setup.Kids Bedroom (KBR)Sliding wardrobe with side dressing mirror.Study table near bathroom wall.Wall-mounted storage above study area.Parents Bedroom (PBR)Wardrobe with side dressing mirror.Study table near bathroom wall.Wall-mounted storage above study area.Bed position changed as discussed.Bathroom entrance to be modified as marked in plan.KitchenPreferred finishes:Beige or Sage GreenGlossy finish.Profile handles required.Double-door refrigerator provision.Granite countertop included in scope.Sink provision from both sides as marked.One wall removed as per updated layout.Tile cladding required inside both sink units.Scope includes:Base UnitsWall UnitsLoft StorageTall pantry unit beside refrigerator.Add 2 additional tandem drawers on hob side.BathroomsMirror cabinets with storage in all bathrooms.Vanity with storage required in Master Bathroom.NotesOverall design language to follow a clean minimal aesthetic.Storage planning to be optimized for a family of four.All modifications to be coordinated with updated electrical and plumbing provisions where required. | 2026-05-13 13:59:54 +0530 | Nidhi Shaw | 10-12 Lakhs is budget I told, it may increase a bit based on requirements. Standard budget told 13-15 for 3 bhk. Got referred by some people in same property. Happy with the explanation, given reviews also. They are ready to pay 10% if offers are good. | 2026-05-03 21:06:09 +0530 | Nidhi Shaw | silver coin will be given on CDP | 2026-05-17 |  | 2026-05-24
19845 | Turnkey | May'26 | Nitin Jawale | Regency Luxeria | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Bhagyashree Salunkhe |  | Active | Preproduction | DEM2 | 1049608 | 209922 | 1462670 | 0 | 0 | 28 | 0 | 0 | 0 | 419843 | 419843.2 |  |  | 2026-05-03 | 2026-05-05 11:11 | 2026-05-05 | 2026-05-05 13:03 | 2026-05-16 | 2026-05-19 11:46 | 2026-06-17 | 2026-06-17 18:34 | 2026-06-24 |  | 2026-07-01 |  | 2026-05-16 | 2026-05-20 12:13 | 2026-05-20 | 2026-05-20 17:51 | 2026-05-20 | 2026-05-21 10:33 | 2026-06-06 | 2026-06-06 11:57 |  |  |  |  | 2026-06-30 | 2026-06-17 17:25 | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-07-05 |  | 2026-06-25 | 2026-06-17 17:34 | Site is RTMI | 2026-05-03 | 2026-05-03 21:09 | 1239551 | 223119 | 0 | 0 | 0 | 0 | 1239551.434 | 204679 | 2026-07-12 00:28:14 +0530 | Rachna Abhyankar |  | 2026-07-12 00:27:45 +0530 | Rachna Abhyankar |  | 2026-06-09 20:29:12 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-18 |  | 2026-06-25
19846 | Turnkey | May'26 | Bency riju varghese | Aratt Alchemy Elixir | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 1450086 | 9999 | 0 | 0 | 0 | 64 | 0 | 135010 | 145009 | 580034 | 580034.4 |  |  | 2026-05-03 | 2026-05-12 19:29 | 2026-05-07 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-03 | 2026-05-03 21:23 | 0 | 0 | 0 | 0 | 0 | 0 | 1228886 | 221199 | 2026-05-07 20:06:50 +0530 | Gayathri Krishna | Cx name : Riju Varghese & Bency (Kerala) Address : aratt elixir -1002BÂ Profession :Â ITÂ Possession : SepÂ How many people will be staying : 3 + 1kid Theme : MinimalÂ Entrance facing : W facingÂ Budget : 15L-Â Foyer - Need shoe rack with seatingÂ Living room - TV unit with wall mounted drawers and 1 tall unit with glass shutters - refer imageÂ TV size -53" Sofa wall - give trimsÂ Need to break the design from living to foyerÂ Dining area -Â 4 seater tableÂ Crockery unit need 2 options for placement - refer image for designÂ Passage wall - Give artwork or mirrorÂ Kitchen - Glossy laminateÂ Double door fridgeÂ Granite to be addedÂ 1 cylinder unitÂ Sink drain board should be in corner as markedÂ WM coming in the entrance of kitchen and countertop starts after thatÂ Extend the counter top and give U shapeÂ Base, wall, loft needed MBR - Queen size bed with 2 side tables 4 shutter wardrobe with long mirror and dresser unitÂ Study table opposite to bed with wall cabinets and ledgesÂ Bed wall go for wallpaper or texture paintÂ GBR- 4 shutter wardrobesÂ Long mirror with base storage on bed side Queen size bedÂ KBR- 2 shutter wardrobe and study with wall storage single bed Bathrooms - Vanity units with mirrorÂ | 2026-05-03 21:20:00 +0530 | Unknown | About the Customer **Property and Budget Details** Customer owns a 3BHK in Aratt Alchemy Elixir, Electronic City Phase 1, with possession expected between July and September. Budget is 20-25 lakh for complete end-to-end interiors with a minimalist yet elegant style. **Visit Hesitation Due to Husband's Travel** Customer is hesitant to visit the experience center without her husband, who returns Wednesday night. They are busy with functions Thursday to Saturday. **Tentative Visit Confirmation** Customer will confirm availability for a visit on Saturday or the following week after receiving company details and videos. **Agent to Send Information** Agent to send WhatsApp message with company details and videos. |  |  |  | 2026-05-24 |  | 2026-05-31
19848 | Turnkey | May'26 | Sandhya Desai | 100 | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 3378316 | 9999 | 0 | 0 | 0 | 50 | 0 | 327833 | 337832 | 1457761 | 1244892 |  |  | 2026-05-03 | 2026-05-03 21:41 | 2026-05-19 | 2026-05-26 10:38 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-06-04 |  | 2026-06-12 |  | 2026-06-13 |  |  |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-06-21 |  | 2026-05-30 |  | Unknown | 2026-05-03 | 2026-05-03 21:40 | 0 | 0 | 0 | 0 | 0 | 0 | 2865267 | 513049 | 2026-06-05 13:17:33 +0530 | Meet Shah | Some Image was uploaded | 2026-05-27 18:05:17 +0530 | Yash Jain | CDP: living room flip the dining and sofa seating areas with crockery unit and mandir unit, sitar to be in closed storage. big shoe rack to be placed inside. Glass tall storage unit required. Kitchen to be entirely in acrylic instead of membrane. want all drawers no shutter. Daughters bedroom Change the bed orientation and add 1 side tablerest is same Mothers Room. Side table to be on another side of bed rest is same Master Bedroom consider 3 glass drawer in all sliding wardrobes, add massage chair as well, with study table and top sotrage cabinet, 1 side table. Study room entire book rack to be in glass cbainet with trophy storage. | 2026-05-27 12:36:38 +0530 | Yash Jain | CDP: changes in planning and mode were done in meeting itself , All the changes which client required were done in CDP itself and the quote for the same was shared with client as well, they will let us know by saturday whether the want to go with us ahead or not. | 2026-06-04 |  | 2026-06-11
19849 | Turnkey | May'26 | Sujata Sawant | L&T Rejevue | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  |  | suraj kumar | Akshat Shrivastava |  | Prashant Panigrahi | Shailendra Mishra | Active | Preproduction | DEM2 | 1162453 | 224599 | 1446141 | 0 | 0 | 5 | 0 | 0 | 0 | 478960 | 458893.6 |  |  | 2026-05-03 | 2026-05-06 11:24 | 2026-05-07 | 2026-05-08 11:44 | 2026-05-11 | 2026-05-11 12:38 | 2026-07-10 | 2026-07-10 14:20 | 2026-07-12 | 2026-07-11 19:56 | 2026-07-18 |  | 2026-05-11 | 2026-05-12 13:22 | 2026-05-12 | 2026-05-12 13:23 | 2026-05-12 | 2026-05-13 14:43 | 2026-06-10 | 2026-06-10 13:01 |  |  |  |  | 2026-07-11 | 2026-07-09 19:39 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-21 | 2026-07-10 14:16 | Site is RTMI | 2026-05-03 | 2026-05-05 14:49 | 1227830 | 218310 | 0 | 0 | 0 | 0 | 1244760.9608 | 209241 | 2026-05-29 11:54:46 +0530 | Harshali Bhuyar | DEM 1 to be planned on 20th June. Client is not in rush. Wants to move in by January. | 2026-05-22 18:49:28 +0530 | Anjali Singh | CDP: no false ceiling LOcker hidden in wardrobe.Â - to be planned as priority. no mirror in daughter'sÂ - she will get it herself as a small mirror | 2026-05-19 15:26:49 +0530 | Anjali Singh | Some Image was uploaded | 2026-07-11 | 2026-07-10 15:38 | 2026-07-12
19850 | Turnkey | May'26 | Mr. Ritesh ladiwala | Kalpataru Elitus | MUM - Thane | Yes | [8 empty] | Mustufa Sohagpurwala |  | Active | Prospect | 10% Payment | 1068139 | 9999 | 0 | 0 | 0 | 8 | 0 | 96815 | 106814 | 427256 | 427255.6 |  |  | 2026-05-03 | 2026-05-03 22:08 | 2026-06-12 | 2026-06-12 11:44 | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-05-03 | 2026-05-03 22:06 | 0 | 0 | 0 | 0 | 0 | 0 | 905202 | 162936 | 2026-07-07 11:19:07 +0530 | Moksh Mehta | DCM done at Site hence no recording is available | 2026-07-07 11:08:59 +0530 | Moksh Mehta | CDP: Recap: 19850 - Celebrity Design Presentation (CDP) with the customer 05 July ¦ Meeting ¦ Microsoft Teams | 2026-06-12 11:41:37 +0530 | Moksh Mehta | DCM: Client Name: - Ritesh Ladiwala Property: - Kalpataru Elitus Possesion Date: - Ready to Take Sq Ft: - 465Sqft, Tower A 3602 No of Members: - Couple & Daughter Budget: - 8L Max Ent: - Shoe Rack (15-20 Pairs)Wall Concepts Living: - Seating Capacity for (3 +1 Persons)TV Unit as per wall size4 - Seater Dining Table Kitchen: - Base Units x 2NosWall Units x 1NosLoft Units x 1 Nos Master Bedroom: - Queen size bedSide TableWardrobe with Loft with Dresser Bedroom 2:- Daughter's Bedroom Single Size BedWardrobe Unit with LoftStudy Table with Wall Storage Washroom:- Vanities :- 2 Nos. Additional Scope of Work: - False CeilingPaintingElectrical | 2026-07-13 |  | 2026-07-20
19851 | Turnkey | May'26 | Vishakha Wakkar | Kalpatru elitus | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 2382849 | 9999 | 0 | 0 | 0 | 65 | 0 | 228286 | 238285 | 1073577 | 832702 |  |  | 2026-05-03 | 2026-05-05 13:25 | 2026-05-10 | 2026-05-10 12:00 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-03 | 2026-05-03 23:08 | 0 | 0 | 0 | 0 | 0 | 0 | 2019363 | 363485 | 2026-05-10 11:55:06 +0530 | Moksh Mehta | DCM: Client Name:- Vishakha Wakkar Property:- Kalpataru Elitus Possesion Date:- In Hand Sq Ft:- 790Sqft, A 267 No of Members: - Couple (50+) & Daughter ( 18+) Sir in Business Automotive Manufacturing, Mam in Finance, Daughter is Study (Finance). Budget: - 25L Ex of White Goods Ent: - Shoe Rack (20-25 Pairs)Safety Door (Optional)Wall Concepts Living: - Seating Capacity for (4 -5 Persons)TV Unit (50") with Display options4 - Seater Dining TableCool shades Kitchen: - Base Units x 2NosWall Units x 1Nos on Service Loft Units x 1 Nos on Service Fully Modular kitchenNo More TrolliesWhite Countertop Fridge will be 36"Dishwasher Provision Sink to be changedUtility StorageMandir Unit Master Bedroom: - Queen size bedSide Table with DresserWardrobe with LoftWorkstation with Some Book StorageAdditional WardrobeBlue Shade if possible Bedroom: - Daughter's Bedroom Queen Bed SizeWardrobe with loftStudy TableBook Storage Bigger in size (300 - 400)Pastel Blue Moon Effect to be added Full Length Mirror Washroom: - Vanities: - 2 Nos.Mirrors. Additional Scope: - Wooden Flooring Pet Parrot: - Cage Size 2ft x 2ft Design Brief: - More Classy Not more FlashyElegant CDP: - | 2026-05-09 23:56:37 +0530 | Aryan Singh | Some Image was uploaded |  |  |  | 2026-05-24 |  | 2026-05-31
19852 | Turnkey | May'26 | Pushpanjali jha | Alchemy One | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Soumya KP | [5 empty] | Ravikiran K |  | Active | Preproduction | Site Readiness 1 | 1098316 | 219663 | 1298470 | 0 | 0 | 1 | 0 | 0 | 0 | 474315 | 404338.4 |  |  | 2026-05-02 | 2026-05-19 13:06 | 2026-05-07 | 2026-05-20 10:51 | 2026-05-20 | 2026-05-20 10:54 | 2026-07-11 | 2026-07-11 10:31 | 2026-07-30 |  | 2026-08-06 |  | 2026-05-20 | 2026-05-20 11:27 | 2026-05-21 | 2026-05-20 19:24 | 2026-05-20 | 2026-05-26 11:22 | 2026-05-30 | 2026-05-30 16:09 |  |  |  |  | 2026-07-11 | 2026-07-14 12:26 | 2026-08-01 |  | 2026-08-02 |  |  |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 | [6 empty] | 2026-08-30 |  | 2026-09-08 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-11 |  |  |  | 2026-10-03 |  | 2026-10-05 |  | 2026-10-06 | [5 empty] | 2026-08-10 |  | 2026-05-31 | 2026-06-04 18:00 | Site is Non-RTMI | 2026-05-02 | 2026-05-04 11:20 | 1103524 | 194946 | 0 | 0 | 0 | 0 | 1222553.3852 | 201861 | 2026-05-26 11:24:24 +0530 | Athul Ajaykumar |  | 2026-05-26 11:16:14 +0530 | Athul Ajaykumar | Concerns are addressed had a word with the client. Moving the OB | 2026-05-26 10:42:19 +0530 | Ravikiran K | Some Image was uploaded | 2026-07-12 | 2026-07-11 10:35 | 2026-07-31 |  | Under Construction | 2026-06-30
19853 | Turnkey | May'26 | Bhavik Chauhan | LNT | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 3883288 | 9999 | 0 | 0 | 0 | 61 | 0 | 378330 | 388329 | 1572473 | 1534157.2 |  |  | 2026-05-04 | 2026-05-11 12:38 | 2026-05-10 | 2026-05-12 17:09 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-04 | 2026-05-04 12:56 | 0 | 0 | 0 | 0 | 0 | 0 | 3293723 | 589564 | 2026-05-13 18:30:15 +0530 | Pooja Nakul Sharma | DCM: 19853 - Bhavik ChauhanÂ astheic but functional spaceÂ tech obssesedÂ foldable seating outside the houseÂ key cuboardÂ mirror in the entranceÂ shoe rack to be floatingÂ washroom in the servant room will be removedÂ washing machine will be placed in the servant washroom big basin will be placed in the servant washroomÂ storage as well in the servant room and in the washroomÂ croos ventilation window near diningÂ furniture to be planned roboat cleaner friendlyÂ tv - 55" home theater systemÂ sofa cum bed if possible but a modern designÂ swing provisionÂ small center tableÂ convertable dining 4 X 6Â 2 clock indian time and uk timeÂ flutted design in gthe bottom part of the wall to avoid it to get damagedÂ tv with the display less clutteredÂ mandir with tv opt 1 and amndir towards the dining opt 2 sink to be placed on the oposite platform if possibleÂ dishwasher provision for futher as of now storage to be plannedÂ too many appliancesÂ good amount of stoargeÂ matka provisionÂ place to keep phone and charging pointÂ appliance storage - bread maker, gola maker, etcÂ B1 - parents roomÂ queen size bedÂ wardrobeÂ openable side table in all rooms for safeÂ foldable study with mini book shlefsÂ plumbing to be checkedÂ false ceiling in all roomsÂ storage for used clothesÂ b2 - kids cum guest bedroomÂ toys storageÂ study areaÂ sofa cum bedÂ wardrobeÂ memory wall in the passageÂ Mbr - nirbhay sir's roomÂ bed with hydraulicÂ wardrobe full lenght to be usedÂ openable side table for the safeÂ queen size bed studyÂ longer deskÂ 2 people should at the same timeÂ 250 booksÂ storage as wellÂ single bed provision colasble bedÂ pocession - may end to june 1st week | [6 empty] | 2026-05-24 |  | 2026-05-31
19857 | Turnkey | May'26 | Saji Mathews | Hubtown rising city | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 3706952 | 9999 | 0 | 0 | 0 | 61 | 0 | 360696 | 370695 | 1652386 | 1313176 |  |  | 2026-05-03 | 2026-05-05 12:41 | 2026-05-08 | 2026-05-08 21:00 | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-03 | 2026-05-05 12:40 | 0 | 0 | 0 | 0 | 0 | 0 | 3141485 | 565467 | 2026-05-29 10:16:42 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-29 10:15:42 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-08 20:58:11 +0530 | Moksh Mehta | DCM: Client Name:- Saji Mathew Property:- Hubtown Rising City Possesion Date:- Ready to Take Sq Ft:- 1128Sqft, A1 405 No of Members: - Couple (50+) & Son ( 19+), Mother (83+) Sir in Business ( Institutional ), Mam (ICMR ) Government Employee, Son in B.Tech Data Science. Budget :- 45L Ex of White Goods Ent: - Shoe Rack (20-25 Pairs)Wall Concepts Serv Room: - To be Converted to Home Office Work Station Chair ( Sadguru's Chair)Book Shelf Living :- Seating Capacity for (3 -5 Persons)TV Unit (65") with Display options6 - Seater Dining Table Mandir unit on the Longer Wall near dining Kitchen:- Base Units x 2NosWall Units x 2NosLoft Units x 1 NosUtility Storage Master Bedroom:- Queen size bedSide TableWardrobe with Loft with DresserFolding Study with Some Book Storage Small Bedroom :- Son's Bedroom Single Bed SizeWardrobe with loftStudy TableBook Storage Bedroom 2:- Parent's Bedroom Single Bed's x 2 NosWardrobe Unit with LoftHandicapped Friendly Washroom:- Vanities :- 3 Nos. CDP:- 17/05/2026 - 3:00pm | 2026-05-25 |  | 2026-06-01
19858 | Turnkey | May'26 | Sunil Padhi | Kalpaturu elitus | MUM - Thane | Yes | [8 empty] | Shreyash Kotecha |  | Active | Prospect | 10% Payment | 1140380 | 9999 | 1140380 | 0 | 0 | 65 | 0 | 104039 | 114038 | 467608 | 444696.4 |  |  | 2026-05-03 | 2026-05-07 11:27 | 2026-05-06 | 2026-05-07 12:14 | 2026-05-11 | 2026-05-11 14:23 | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-05-03 | 2026-05-05 14:39 | 1295937.985 | 210873 | 0 | 0 | 0 | 0 | 1295937.985 | 210873 | 2026-05-06 18:48:13 +0530 | Maasoumeh Raza | DCM: Timeline: Possession in ~12 weeks Target move-in around September (Ganesh Chaturthi). 8 member : 3 couple , 7 year old girl & 4 year old boy. Profession : IT & Bank CDP: 10 May Entrance: Safety door, Shoe rack outside (~25 pairs). Inside: console + key holder + decor. Living Room: Compact/foldable dining. Temple ~3 ft wide, ~1824 inches deep. 3-seater sofa (~6 ft), 4 seater dining table. 48 TV with floating unit (hidden storage + display shelves). Marble-finish TV backdrop with LED. No full false ceilingprofile/peripheral lighting, RGB, hanging lights/chandelier. Theme: To be finalised (European/modern etc.) based on references. Master Bedroom: Queen bed, side tables, dressing, study/workstation. Large wardrobe (L-shape or bigger straight for 4 member). No TV. Optional seating near window [ottoman or diwan] Common Bedroom: Similar setup as master; wardrobe shared by multiple members. No TV , Optional seating near window [ottoman or diwan]. Bathrooms: Vanity storage. Window/storage & shower partition to be checked on-site. Kitchen (Parallel): 3 layer hop side + 2 layer (sink side), crockery unit. Appliances: mixer + toaster only. Breakfast counter [if space allows]. Chimney: Reuse existing ductless. Good ventilation expected on 35th floor. Future duct option possible (site check). Utility: Washing machine (top-load now, future front-load). Overhead storage + adjustable shelves. Ceiling & Lighting: Partial ceiling (living, bedrooms, passage). All lights (panels, strips, chandelier) to be purchased by client; design guidance provided. Electrical: Wiring & installation included; fixtures to be client-provided. Budget : 12 to 15L 15L max including light fixture & curtains. | [6 empty] | 2026-05-19 |  | 2026-05-26
19859 | Turnkey | May'26 | Pavan Banavalikar | Ashar 16 | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Active | Preproduction | Site Readiness 1 | 1101724 | 224999 | 1363146 | 0 | 0 | 15 | 0 | 0 | 0 | 444513 | 432211.6 |  |  | 2026-05-03 | 2026-05-05 14:32 | 2026-05-08 | 2026-05-08 15:40 | 2026-05-11 | 2026-05-11 12:39 | 2026-06-10 | 2026-06-10 16:03 | 2026-07-20 |  | 2026-07-27 |  | 2026-05-11 | 2026-05-11 12:54 | 2026-05-12 | 2026-05-11 14:06 | 2026-05-11 | 2026-05-13 11:56 | 2026-06-10 | 2026-06-10 12:21 |  |  |  |  | 2026-06-10 | 2026-06-30 12:40 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  |  |  |  | 2026-05-03 | 2026-05-05 14:27 | 1155209 | 207937 | 0 | 0 | 0 | 0 | 1200995.596 | 198310 | 2026-06-20 15:09:03 +0530 | Harshali Bhuyar | After DEM1 there was increase in cost as the changes made by client, but client thought that was not the difference that he expected. As per client there should be only a 50k difference in total amount after the designing. I have conveyed that if thats the case , then there is no more scope for changes , we will just go ahead with laminate selection. also DC patterns wont be possible as there will be fluctuations in costing due to that. have shared an options by removing some items from the quote which were added later. and kept it same as cdp meeting scope. | 2026-06-20 15:04:36 +0530 | Harshali Bhuyar | DEM MOM : CDP was rediscussed, client added a side opening wardrobe in Master Wardrobe, and internals for both the wardrobes were customized. In daughters bedroom wardrobe , internals were customized. Storage above study was added. Kitchen was kept the same. In living room , 1 drawer was added in TV unit instead of open unit. 3-4 options were shortlisted in laminates for all the rooms. | 2026-06-20 14:54:28 +0530 | Harshali Bhuyar | Some Image was uploaded | 2026-06-11 | 2026-06-10 16:14 | 2026-07-21
19860 | Turnkey | May'26 | Amit Mehta | Monte South | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 3405644 | 340564 | 3405644 | 0 | 0 | 29 | 0 | 0 | 340565 | 1441136 | 1283379.6 |  |  | 2026-05-03 | 2026-06-16 18:52 | 2026-06-14 | 2026-06-16 19:01 | 2026-06-19 | 2026-06-16 19:18 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 | 2026-06-22 17:52 | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-05-03 | 2026-05-05 13:25 | 2886139 | 519505 | 0 | 0 | 0 | 0 | 2886139 | 519505 | 2026-07-11 15:38:15 +0530 | Sanjana Swami | the project value in the overview is not matching with the offer email | 2026-06-15 15:43:45 +0530 | Moni Sahani | Some Image was uploaded | 2026-05-20 13:18:58 +0530 | Shreya Sonavane | Some Image was uploaded | 2026-06-24 |  | 2026-07-01 |  |  |  | 2026-06-14 | 340564 | Ravi Roy
19861 | Turnkey | May'26 | Parin Satra | R A residency | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 3658430 | 9999 | 0 | 0 | 0 | 69 | 0 | 355844 | 365843 | 1524893 | 1401850.8 |  |  | 2026-04-26 | 2026-05-07 12:30 | 2026-05-08 | 2026-05-10 10:48 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-04-26 | 2026-05-05 14:14 | 0 | 0 | 0 | 0 | 0 | 0 | 3104582 | 553847 | 2026-05-10 10:48:26 +0530 | Priyanka Patel | DCM: 1. Name of the customer Parin Satra 2. Profession Bussiness 3. Project Name/Tower Name/Flat Number RA Resi 4. Typology (1BHK, 2BHK, 3BHK, etc) 3BHK 5. Site Access Date 2026-05-08 6. Possession Date 2026-05-08 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 4000000 Customer Preferences8. Who will be living in the house? Joint Family, Couple 9. What activities do you usually prefer at your home ? Prayer, Pursuing Hobbies, Relaxing and Unwinding, Family Bonding, Hosting Guests 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] Yes 11. Mention basic vastu principles agreed for integration in design, if any yes 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials No dark colours and jazzy and bulky 15. Do you have any existing furniture that must be accommodated? NO 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Digital lock, Shoe rack, Console, Seating, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Multipurpose 2. Must-have furniture or features? Speakers, Puja unit, Sofa 3. Choose your decor inspirations Plants 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser, Study Table 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Others 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Study table , Dresser 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Guest 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Bottom Storage, Laundry space, Washing machine space, Dryer, Top Storage Balcony & Outdoor1. How do you intend to use your balcony? Furniture, Planters, Utility 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any YES 2. Other commitments made by Bonito to customer, if any YES 3. What are offers committed to customers? YES 4. Move-in date confirmed with customer 2026-09-08 5. Any special occasion mentioned by the customer wrt handover date No 6. Additional Requirements (Mention any requirements from customer not covered in the form) yes 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 4000000 | 2026-05-05 14:13:45 +0530 | Unknown | About the Customer **3BHK Dadar East Interiors Planned** Customer is planning complete interiors for a 3BHK flat in Dadar East, with possession expected in the first week of May. The carpet area is 1750 sq ft. **Budget and Civil Work Concerns** Customer has concerns about the budget and extent of civil work, specifically asking if breaking a kitchen wall is included. Agent clarified minor civil work is included. **Experience Center Visit Scheduled** An appointment is scheduled for tomorrow, April 26, 2026, in the first half at the Andheri branch. The customer will attend with two family members. **WhatsApp Invite and Building Name Confirmed** Agent to send a WhatsApp invitation with the address and details for the scheduled visit. Customer's building name is RA Residencies. |  |  |  | 2026-05-30 |  | 2026-06-06
19862 | Sub Project |  | Shailja Tiwari | Lodha Amara | MUM - Thane |  | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  |  | Asif Shaikh | Akshat Shrivastava | Murali S |  |  | Active | Handover | Project Closure Pending | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-05 | 2026-05-12 10:54 | 2026-05-06 | 2026-05-12 10:54 | 2026-05-12 | 2026-05-12 10:54 | 2026-05-13 | 2026-05-12 11:03 | 2026-05-13 | 2026-05-12 13:15 | 2026-05-12 | 2026-05-12 14:36 | 2026-05-12 | 2026-05-12 10:55 | 2026-05-13 | 2026-05-12 10:55 | 2026-05-12 | 2026-05-12 10:55 | 2026-05-13 | 2026-05-12 10:56 |  |  |  |  | 2026-05-12 | 2026-05-12 11:03 | 2026-05-13 | 2026-05-12 14:22 | 2026-05-13 | 2026-05-12 14:34 |  |  | 2026-05-13 | 2026-05-30 14:45 | 2026-05-30 | 2026-05-30 19:24 | 2026-05-25 | 2026-05-25 10:45 | 2026-06-01 | 2026-05-31 11:58 |  |  |  |  | 2026-05-31 14:46 | 2026-06-03 | 2026-06-03 23:31 | 2026-06-08 | 2026-06-06 11:06 | 2026-06-07 | 2026-07-12 12:29 | 2026-06-06 | 2026-07-13 11:43 | 2026-07-11 | 2026-07-13 11:43 | 2026-07-13 | 2026-07-13 11:36 |  |  | 2026-07-15 | 2026-07-13 12:25 | 2026-07-15 | 2026-07-13 12:27 | 2026-07-13 | 2026-07-14 17:53 |  |  |  |  | 2026-05-30 | 2026-05-31 12:08 | 2026-05-13 | 2026-05-12 10:56 | Unknown | 2026-05-05 | 2026-05-12 10:54 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | [9 empty] | 2026-05-13 | 2026-05-12 11:03 | 2026-05-13 | 2026-05-12 13:15
19863 | Turnkey | May'26 | Shankar kr suman | Casa Supremo | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | Neha Singh | Neha Singh | Rajkumar Suthar | Sandeep Tiwari | Murali S | Moni Sahani | Siddhesh Gujrathi | Active | Production | Production | 876597 | 570342 | 1057301 | 0 | 876007 | 1 | 0 | 0 | 0 | 0 | 306255 |  |  | 2026-05-05 | 2026-05-05 17:48 | 2026-05-10 | 2026-05-10 10:50 | 2026-05-10 | 2026-05-10 21:18 | 2026-05-31 | 2026-05-31 21:17 | 2026-06-12 | 2026-06-13 14:58 | 2026-06-17 | 2026-06-17 17:36 | 2026-05-10 | 2026-05-19 19:07 | 2026-05-11 | 2026-05-22 16:19 | 2026-05-22 | 2026-05-22 19:07 | 2026-05-26 | 2026-05-26 13:03 |  |  |  |  | 2026-06-01 | 2026-05-30 18:42 | 2026-06-16 | 2026-06-17 12:15 | 2026-06-18 | 2026-06-17 12:33 |  |  | 2026-06-19 | 2026-06-23 15:49 | 2026-06-23 | 2026-06-23 19:05 | 2026-06-24 | 2026-06-23 20:04 | 2026-06-24 | 2026-06-24 17:53 |  |  |  |  | 2026-06-28 22:35 | 2026-07-14 | 2026-07-14 16:49 | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-23 | 2026-06-28 22:34 | 2026-05-27 | 2026-05-31 21:10 | Site is RTMI | 2026-05-05 | 2026-05-05 17:48 | 896018 | 161283 | 0 | 0 | 946269.2158 | 157681 | 947113.8058 | 157787 | 2026-07-12 09:42:05 +0530 | Rajkumar Suthar | Execution: Floor covering, ceiling, electrical : Completed 1st coat of paint : 13th-18th July Site readiness : 18th July | 2026-05-26 13:02:43 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to align IM will confirm once with priyanka site is acessible DEM Dates -Â DEM 1 - TBD DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM - 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-05-24 16:45:15 +0530 | Vishakha Vaishnav | Tried connecting cx , number not available | 2026-06-01 | 2026-05-31 21:17 | 2026-06-14 | 2026-06-13 14:59 | RTMI
19865 | Turnkey | May'26 | Hemali Manek | Oberoi Eternia | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 2135916 | 9999 | 2135916 | 0 | 0 | 66 | 0 | 203593 | 213592 | 863423 | 845309.6 |  |  | 2026-05-05 | 2026-05-05 20:30 | 2026-05-06 | 2026-05-07 13:31 | 2026-05-10 | 2026-05-11 11:44 | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-05-05 | 2026-05-05 20:28 | 1810098 | 325817 | 0 | 0 | 0 | 0 | 1810098 | 325817 | 2026-05-26 16:12:05 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-26 16:11:41 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-19 12:45:13 +0530 | Bency Chacko | Some Image was uploaded | 2026-05-19 |  | 2026-05-26
19867 | Turnkey | May'26 | Susweta Ghosh | Asset 63 | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 2215696 | 9999 | 0 | 0 | 0 | 69 | 0 | 211571 | 221570 | 957462 | 815095.2 |  |  | 2026-05-03 | 2026-05-07 10:28 | 2026-05-09 |  | 2026-05-12 |  | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-05-12 |  | 2026-05-13 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | 2026-05-20 |  | 2026-05-28 |  | 2026-05-29 |  |  |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-08 | [6 empty] | 2026-06-26 |  | 2026-07-05 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-08 |  |  |  | 2026-07-30 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-06-06 |  | 2026-05-15 |  | Unknown | 2026-05-03 | 2026-05-06 18:03 | 0 | 0 | 0 | 0 | 0 | 0 | 1877708 | 337987 | 2026-05-09 22:49:19 +0530 | Maspi Das | Cx : Subhodeep, Susweta RGM dated : 04.05.26 CDP date : 10.05.26 11.30am From : Kolkata Residing in BloreÂ Profession : IT Family members : 2Â Kids : 1 girl Shloka Budget : 12L Based on requirements (it will extend to 15L+) informed. Property : Assets 63 deg F2C height (approx) : 9.5' Facing : West Property Location : Sarjapur Site access date : Nov'26 Possession date : Nov'26 Preferred style : Modern Scope of Work :Â In laminate finishes False ceiing for Living, dining, passage, foyer, not for bedrooms Foyer :Â extended mirror and panel decor on the wall ottoman on left wall small base storage on entry wall shoe storage on tv right side fluted laminate pullout drawerÂ shoe storage not fixed to the wall Living :Â Beige, off white finishes 65" TV size TV unit space as per FP Wall mounted unit, with 1 tall unit with glass & back panel (modern) TV reference as per EC TV on 2nd floor centre of base unit with flap down glass Punning for tv left side Wallpaper in some light pink/beige/green 3 seater claire sofa opp to TV, single seater sofa chair with coffee table in between on entry opp wall Sofa wall with beading with 2 diff textures depending on design withÂ Dining :Â Crockery on kitchen wall with pantry storage with gap near the balcony wall (as per ref image) Wall moulding similar to sofa wall to be done on the dining back wall(bedroom) wall with loose furniture console table with deco lights base in pastel green and wall & 2 tall units(in fluted laminate) in other color fluted glass in wall units (same as per ref)Â drawer pullout in base Wall moulding/ some similar for kitchen left wall Kitchen :Â Side by side fridge space Kitchen sink in quartz, under mount RO in kitchen Utility WM opp wall with storage below theres MCB box WM space in FP will have sink with drain board and DW next to it and WMÂ counter in L shape and storage next to WM will be of more height to match counter with counter above WM & DW Wall units with fluted glass and laminate combo G profile black for kitchen Granite - BD scope (black galaxy) Dado tile installation from BD scope Appliances : M/W, OTG, fryer, mixer, wet grinder Tall appliance unit (not built in m/w & otg) GBR : Sofa cum bed Hinged wardrobe with loft Mirror on shutter Pooja to be checked as per vastu4 in GBRÂ CNC doors with back panel having marble laminate Tray, drawer storage & bottom storage No seater study near window (as per ref image) base storage with wall drawer in bottom KBR Kids themed (moon & star) wallpaper hinged wardrobe with mirror with loft Queen size bed space MBR King size bed space Hinged wardrobe with bay window seating with lighting & paneling Fluted laminate with fabric laminate/plain laminate based on design Loft above Wooden flooring existing for MBR Long handles for MBR WR TV unit with pullout for 55" TV size Wall concept with cove light / wall with focus lights on ceiling dressing with long mirror little above skirting level (cove light behind mirror) & tall storage & base storage Vanities :Â CV - fixed shower partition MBR V - sliding shower partition Existing granite & bowl Storage below | [6 empty] | 2026-05-20 |  | 2026-05-27
19868 | Turnkey | May'26 | Kajal | 4bhk independent house | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Rajoshi Sarkar |  | Active | Design | 20% Payment | 1964864 | 273879 | 2796280 | 0 | 0 | 3 | 0 | 0 | 119094 | 822505 | 749386.4 |  |  | 2026-05-03 | 2026-05-06 12:01 | 2026-05-09 | 2026-06-04 12:16 | 2026-06-07 | 2026-06-09 16:17 | 2026-07-13 | 2026-07-12 18:41 | 2026-12-20 |  | 2026-12-27 |  | 2026-06-09 | 2026-06-12 10:57 | 2026-06-10 | 2026-06-16 16:44 | 2026-06-16 | 2026-06-16 17:31 | 2026-06-17 | 2026-06-17 11:31 |  |  |  |  | 2026-07-12 |  | 2026-12-22 |  | 2026-12-23 |  |  |  | 2026-12-30 |  | 2026-12-31 |  | 2027-01-01 |  | 2027-01-02 | [6 empty] | 2027-01-20 |  | 2027-01-29 |  | 2027-01-28 |  | 2027-01-29 |  | 2027-01-30 |  | 2027-02-01 |  |  |  | 2027-02-23 |  | 2027-02-25 |  | 2027-02-26 | [5 empty] | 2026-12-31 |  | 2026-07-15 | 2026-07-12 18:36 | Site is Non-RTMI | 2026-05-03 | 2026-05-06 11:56 | 2369729 | 426551 | 0 | 0 | 0 | 0 | 2321005.0663 | 383242 | 2026-07-12 18:42:49 +0530 | Kiran Agarampalli | Living: Tv Unit with marble finish laminate and wallpaper with metal strips on the back wall Kitchen: Make the drawer width 2.5' add more drawers remove roller shutter unit and add wall unit add wicker basket in the tall unit Guest bedroom: Move the wardrobe to the window wall with dresser and used cloths unit Master bedroom: Diagonal corner need to plan the design Walk in space dresser with mirror Kids Bedroom: Swap both wardrobe layout IM yet to be done | 2026-06-16 17:30:35 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: December Soft Possession: September Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (25th June 2026) * 10% Payment Stage Tentatively scheduled for (25th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special offer (50000) Special offer (30000) Special Offer (20000) Free Shoerack Offer Modular - Windows to Wonderful home PM fee waiver (5%) Services - Windows to Wonderful Home Design fee waiver (5%) Laminate Upgrade - Windows to Wonderful home Final Closing Value Discussed: Checklist terms descoping and agreement terms are cleared | 2026-06-16 16:45:20 +0530 | Rajoshi Sarkar | Some Image was uploaded | 2026-07-13 | 2026-07-12 18:42 | 2026-12-21 |  | Under Construction | 2026-09-30 | 2026-06-07 | 273879 | Ravi Roy
19869 | Turnkey | May'26 | Archana | Independant House | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Korak Ganguly |  | Active | Prospect | 10% Payment | 873849 | 9999 | 873849 | 0 | 0 | 62 | 0 | 77386 | 87385 | 424703 | 274376 |  |  | 2026-05-03 | 2026-05-10 14:47 | 2026-05-10 | 2026-05-14 18:55 | 2026-05-14 | 2026-05-14 19:30 | 2026-05-21 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-05-14 |  | 2026-05-15 |  | 2026-05-15 |  | 2026-05-16 | [5 empty] | 2026-05-22 |  | 2026-05-30 |  | 2026-05-31 |  |  |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-09 |  | 2026-06-10 | [6 empty] | 2026-06-28 |  | 2026-07-07 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-06-08 |  | 2026-05-17 |  | Unknown | 2026-05-03 | 2026-05-06 18:02 | 740550 | 133299 | 0 | 0 | 0 | 0 | 740550 | 133299 | 2026-05-12 18:07:26 +0530 | Swati Rathod | PID: 19869 Name : Archana Profession: IT Property - 5BHK Budget - 7L possession - RTMI Site Access Date: 01-05-2026 Members - 4 Orientation : North Facing - 4 beds with side table - 2 dresser - false ceilingÂ - wall concept forÂ 1 bedroom. KITCHEN: - 2door fridgeÂ - bottom unit - top unit - Loft - Granite CX scope - 2 bowl sinkÂ | 2026-05-06 11:27:05 +0530 | Unknown | About the Customer **Renovation Needs for 4 BHK Duplex** Customer is looking for interior renovation for a 4 BHK independent duplex house in Jigani, near Electronic City, with modifications including beds, wallpaper, lighting, false ceiling, and partial kitchen redo. The customer is willing to vacate the house for 45-60 days during execution. **Budget Below Minimum Ticket Value** Customer's budget is between 5-7 lakhs, which is slightly below Bonito Designs' minimum ticket value of 7 lakhs for renovations. Customer is open to discussing the final cost based on requirements. **Hesitation for Experience Center Visit** Customer is hesitant about visiting the experience center due to distance from Jigani and travel arrangements. Initially requested a virtual discussion, but agent insisted on an in-person visit. **Virtual Meet Option Exploration** Agent Anupma agreed to check with the team about arranging a virtual meet for the customer, acknowledging this possibility. **Tentative Experience Center Appointment** A tentative appointment is scheduled for Sunday at 4 PM at the HSR experience center, with the agent offering cab facilities. Agent Priti confirmed her identity and will call back on Friday to confirm the exact day and time. |  |  |  | 2026-05-22 |  | 2026-05-29
19870 | Turnkey | May'26 | Dev | Independent Property | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 6135927 | 9999 | 0 | 0 | 0 | 22 | 0 | 603594 | 613593 | 2471806 | 2436935.6 |  |  | 2026-05-03 | 2026-05-19 13:08 | 2026-05-08 | 2026-05-19 13:27 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-11 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-09 |  | 2026-08-13 |  |  |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-06 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-05-03 | 2026-05-19 13:07 | 0 | 0 | 0 | 0 | 0 | 0 | 5199938 | 935988 | 2026-06-24 11:34:37 +0530 | Gayathri Krishna | Recap: 19870 - Design Consultation Meeting (DCM) with the customer 08 May ¦ Meeting ¦ Microsoft Teams | 2026-06-23 18:44:11 +0530 | Ankita Agarwal | DCM: https://teams.microsoft.com/l/chat/19:meeting_NGEwYmMzMDAtOWIxYS00ZWE5LWE3ODMtOWY2YTk0NGQ1ZTc5@thread.v2/conversations?context=%7B%22contextType%22%3A%22chat%22%7D | 2026-06-23 17:15:58 +0530 | Ankita Agarwal | CDP: NO NOTES FOR CDP CLIENT WILL CHANGE LAYOUT OF HOUSE AS PER INTERIOR SUGGESTED IN DESIGN PHASE IF PROCEEDS | 2026-05-30 |  | 2026-06-06
19872 | Turnkey | May'26 | Priya Jakkannavar | Billa tiseya | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 3100139 | 9999 | 0 | 0 | 0 | 57 | 0 | 300015 | 310014 | 1240056 | 1240055.6 |  |  | 2026-05-03 | 2026-05-19 13:02 | 2026-05-17 | 2026-05-19 13:03 | 2026-05-13 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-05-03 | 2026-05-19 13:01 | 0 | 0 | 0 | 0 | 0 | 0 | 2627236 | 472902 | 2026-05-20 15:31:50 +0530 | Nayan Reddy | DCM: Cx NameÂ - Priya Crm - Ravikiran RGM -17/05/26 Move in date -Â Â Budget -Â 20 - 25 LÂ Inlcude sofa and Dining tbaleÂ Cots - 3 nos Property name - Birla Tisya Direction -Â W facingÂ F to c -Â 9.5 Mivon constructionÂ Open for suggestionÂ FoyerÂ Shoe rack with parttitonÂ seating (optional) Space near Powder room (existing Nish) Full wall storage unit till ceilingÂ Bedroom 3 (Grand Parents )Â Bed position on E wall near big windowÂ wardrobe + loftÂ and study tableÂ end to end wardrobeÂ Queen sizeÂ Bedroom 2 (Guest bedroom) Wardrobe + LoftÂ L shape till windowÂ Dressing near windowÂ Bed position on E wall near big windowÂ Bedroom 1Â (Kids bedroom) Sliding WardrobeÂ Proper study spaceÂ Wardrobe + loftÂ Bed side Storage unit to keep books MBRÂ Wardrobe + LoftÂ Bed side Storage unit to keep books L shape study unitÂ ALL WASHROOM VANITY CABINET ONLY BASE UNITÂ Modular KitchenÂ Granite - BonitoÂ Fridge - 800mm Cylinder cabinetÂ Pooja unitÂ in kitchen near fridge sapceÂ (optional)Â Tall unit - Oven Base unitÂ Wall UnitÂ LoftÂ UtilityÂ Need Pantry unit near wasing macine spaceÂ Sink unitÂ under mount RO Living roomÂ Â Tv unitÂ Suspended drawersÂ display cabinetÂ Glass and Wooden shutter cabinetÂ 52" Tv existingÂ 3 + 2 seater sofaÂ Dining AreaÂ 6 seater dining tableÂ Crockery unitÂ Maids room Small Storage cabinetÂ FC in Living ,Dining and Foyer | 2026-05-17 15:40:03 +0530 | Nayan Reddy | DCM: Cx NameÂ - Priya Crm - Ravikiran RGM -17/05/26 Move in date -Â Â Budget -Â 20 - 25 LÂ Inlcude sofa and Dining tbaleÂ Cots - 3 nos Property name - Birla Tisya Direction -Â W facingÂ F to c -Â 9.5 Mivon constructionÂ Open for suggestionÂ Zen or Japandi theme FoyerÂ Shoe rack with parttitonÂ seating (optional) Space near Powder room (existing Nish) Full wall storage unit till ceilingÂ Bedroom 3 (Grand Parents )Â Bed position on E wall near big windowÂ wardrobe + loftÂ and study tableÂ end to end wardrobeÂ Queen sizeÂ Bedroom 2 (Guest bedroom) Wardrobe + LoftÂ L shape till windowÂ Dressing near windowÂ Bed position on E wall near big windowÂ Bedroom 1Â (Kids bedroom) Sliding WardrobeÂ Proper study spaceÂ Wardrobe + loftÂ Bed side Storage unit to keep books MBRÂ Wardrobe + LoftÂ Bed side Storage unit to keep books L shape study unitÂ ALL WASHROOM VANITY CABINET ONLY BASE UNITÂ Modular KitchenÂ Granite - BonitoÂ Fridge - 800mm Cylinder cabinetÂ Pooja unitÂ in kitchen near fridge sapceÂ (optional)Â Tall unit - Oven Base unitÂ Wall UnitÂ LoftÂ UtilityÂ Need Pantry unit near wasing macine spaceÂ Sink unitÂ under mount RO Living roomÂ Â Tv unitÂ Suspended drawersÂ display cabinetÂ Glass and Wooden shutter cabinetÂ 52" Tv existingÂ 3 + 2 seater sofaÂ Dining AreaÂ 6 seater dining tableÂ Crockery unitÂ Maids room Small Storage cabinetÂ FC in Living ,Dining and Foyer | 2026-05-06 11:42:29 +0530 | Unknown | About the Customer **Property Details and Timeline** Customer's property is a new construction on Magadi Road, Bangalore, with handover expected in approximately three months. **Visit Confirmation Pending Family Approval** Customer needs to confirm visit timings with family members before finalizing a visit, likely next weekend. **Agent to Share Information** Agent will share Bonito Designs' details and location via WhatsApp. **Customer to Confirm Visit Time** Customer will confirm their visit time after receiving details and consulting with family. | 2026-05-30 |  | 2026-06-06
19876 | Turnkey | May'26 | Anandrao Mane | Sapphire court | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 2276618 | 9999 | 2276618 | 0 | 0 | 59 | 0 | 217663 | 227662 | 910647 | 910647.2 |  |  | 2026-05-06 | 2026-05-07 12:36 | 2026-05-09 | 2026-05-09 18:06 | 2026-05-13 | 2026-05-17 21:29 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-06 | 2026-05-06 16:54 | 1929337 | 347280 | 0 | 0 | 0 | 0 | 1929337 | 347280 | 2026-05-14 10:59:34 +0530 | Pratima Kajwe | CDP: MOM Project ProfileProject Name/Tower Name/Flat Number Azad nagar Typology 2BHK Site Access Date 2026-05-10 Possession Date 2026-05-10 Customer ProfileFamily members (no. & age) Couple, one daughter and one son Profession Jewelers Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc Civil and Vaastu Signed off celebrity theme Abstract Luxury, Japandi Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 1200000 Mention basic vastu principles agreed for integration in design, if any Design VisionEntrance Foyer must-haves Shoe-rack with seating and space to keep umbrella and other necessary. Upload reference images Living key features and furniture must-haves Mandir facing entrance and 4 seater dining space, window seating with TV unit (making it look as one level), sofa, center table Upload reference images Dining setup, table size and other furniture must -haves Either folding or fixed, open to ideas. If fixed suggested for bench + 2 chairs. Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves King size bed with openable wardrobe and dresser with storage behind, Another storage next to dresser for laundry and ironing pull out desk, with small TV ledge aligned with it. Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves Murphy bed with single bed. and openable wardrobe Upload reference images Other space/ room (if any) must-haves Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves Fully modular kitchen with appliances unit and roller shutter Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves Upload reference images Styling and Dcor must-haves Space identified for signature design features and its specifics Specify if design to reflect any personal story, cultural influence or special memory MiscellaneousTimeline related commitment made by Bonito to customer, if any: Other commitments made by Bonito to customer, if any: RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse No CDP recording handed over on Pulse No What are offers committed to customers? Re-confirm the Move-in Date 2026-09-30 Re-confirm the Possession Date 2026-09-30 Any special occasion mentioned by customer wrt handover date | 2026-05-14 10:59:05 +0530 | Pratima Kajwe | DCM: MOM User ResponseCustomer and Project Profile1. Name of the customer Anandrao Mane 2. Profession Business in jewellery making and Store in 7 bungalows 3. Project Name/Tower Name/Flat Number 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK renovation 5. Site Access Date 2026-05-10 6. Possession Date 2026-05-10 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 1200000 Customer Preferences8. Who will be living in the house? Nuclear Family, Couple 9. What activities do you usually prefer at your home ? Relaxing and Unwinding, Family Bonding, Hosting Guests 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] Civil and Vaastu 11. Mention basic vastu principles agreed for integration in design, if any Bed direction and its placement, colors 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) In each room Upload reference images 14. Any absolute no-go styles colours or materials dark shades 15. Do you have any existing furniture that must be accommodated? No 13. Do you want the design to reflect any personal story, cultural influence, or special memory open to ideas ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Seating, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required No Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests, Multipurpose, TV Focus 2. Must-have furniture or features? TV unit, Home speakers, Coffee table, Puja unit, Display unit , Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Artwork 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Built-in Oven, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Bookshelf , Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type No storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Study table , Bookshelf , Dresser , TV unit 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 2026-09-30 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 2500000 | 2026-05-06 16:54:16 +0530 | Unknown | About the Customer **Customer Property Details and Scope of Work** Customer has a 2BHK apartment in Andheri West with 765 carpet area, possession received, and is looking for full interior work including renovation of toilet and bathroom, and minor civil work like covering a beam and breaking a small wall in the kitchen. **Concerns on Materials and Civil Work Scope** Customer is concerned about the quality of plywood and the extent of civil work, specifically regarding plumbing and breaking large walls. **Budget and Offer Details Shared** Agent confirmed starting budget for 2BHK is 10-15 lakhs and mentioned a 100% GST waiver offer. Agent will send further details on WhatsApp. **Experience Center Visit Scheduled** Customer agreed to visit the Andheri experience center today around 2:00 PM. Agent will send the location via WhatsApp and will be available at the center. | 2026-05-25 |  | 2026-06-01
19877 | Turnkey | May'26 | Swaroop Raipure Raipure | Transcon | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 2414195 | 9999 | 0 | 0 | 0 | 63 | 0 | 231421 | 241420 | 1063985 | 867371.2 |  |  | 2026-05-06 | 2026-05-13 15:14 | 2026-05-19 | 2026-05-19 14:31 | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-20 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-14 |  | 2026-08-19 |  |  |  | 2026-09-27 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-05-06 | 2026-05-13 15:13 | 0 | 0 | 0 | 0 | 0 | 0 | 2048215 | 365979 | [9 empty] | 2026-06-08 |  | 2026-06-15
19878 | Turnkey | May'26 | Ganesh Salian | Damji shamji mahavir spring | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 1534562 | 9999 | 0 | 0 | 0 | 69 | 0 | 143457 | 153456 | 679623 | 548026.8 |  |  | 2026-05-06 | 2026-05-07 11:55 | 2026-05-07 | 2026-05-07 13:30 | 2026-05-26 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-05-10 |  | 2026-05-11 |  | 2026-05-11 |  | 2026-05-12 | [5 empty] | 2026-05-18 |  | 2026-05-26 |  | 2026-05-27 |  |  |  | 2026-06-03 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 | [6 empty] | 2026-06-24 |  | 2026-07-03 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-28 |  | 2026-07-30 |  | 2026-07-31 | [5 empty] | 2026-06-04 |  | 2026-05-13 |  | Unknown | 2026-05-06 | 2026-05-07 11:50 | 0 | 0 | 0 | 0 | 0 | 0 | 1300476 | 234085 | 2026-05-07 13:29:41 +0530 | Anjali Singh | Some Image was uploaded | 2026-05-07 13:22:43 +0530 | Anjali Singh | DCM: MR. GANESH & KALAWATI REQUIREMENTSGeneral3 peopleCouple + daughterDaughter: 26 y/o Business DevelopmentMaam Shipping lineSir RetiredStyle: Modern TraditionalFalse ceiling for water sprinkler concealmentBudget:8 lakh10 lakh maxCDP: 9th May 2026LIVING / DINING3+2 seatingTV unitDisplay unitLarge mandirNo dining tableOpen layoutCozy and functional planningKITCHENSingle door fridgePantry unitWicker basketsClient to finalize backsplash tilesAir fryer spaceLarge mixer/chakki storage spaceDAUGHTERS BEDROOMSofa cum bedSliding wardrobeStudy tableDresser with mirrorDisplay shelves/bookshelfMASTER BEDROOMBedWardrobeDresser with mirrorNo TV |  |  |  | 2026-05-18 |  | 2026-05-25
19882 | Turnkey | May'26 | Rao Praveen | Dreams | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Foram Joshi |  | Active | Design | DEM1 | 1769289 | 230279 | 2202796 | 0 | 0 | 27 | 0 | 0 | 123579 | 769910 | 645521.2 |  |  | 2026-05-06 | 2026-05-06 21:01 | 2026-05-27 | 2026-05-27 19:42 | 2026-05-31 | 2026-05-31 20:16 | 2027-01-04 |  | 2027-01-11 |  | 2027-01-18 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-05 10:53 | 2026-06-05 | 2026-06-18 11:30 | 2026-06-23 | 2026-06-23 18:20 |  |  |  |  | 2027-01-05 |  | 2027-01-13 |  | 2027-01-14 |  |  |  | 2027-01-21 |  | 2027-01-22 |  | 2027-01-23 |  | 2027-01-24 | [6 empty] | 2027-02-11 |  | 2027-02-20 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-21 |  | 2027-02-23 |  |  |  | 2027-03-17 |  | 2027-03-19 |  | 2027-03-20 | [5 empty] | 2027-01-22 |  | 2026-12-31 |  | Unknown | 2026-05-06 | 2026-05-06 21:00 | 1866777 | 336019 | 0 | 0 | 0 | 0 | 1866777.0731 | 318472 | 2026-07-03 13:09:53 +0530 | Monika Pal | Minutes of Meeting held on Date: <03-07-2026> | 2026-07-02 18:47:07 +0530 | Anamika Dolai | Client is willing to do the payment of next milestone is few days. | 2026-07-02 13:16:26 +0530 | Anamika Dolai | Possession on nov'26 end, will have DEM after 15th as the client is not available. | 2027-01-05 |  | 2027-01-12 |  | Under Construction | 2026-12-31
19883 | Turnkey | May'26 | Pushparaj Moolya | Puranik arambha | MUM - Thane | Yes |  | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Aditya Vikram |  | Nishtha Valawalkar |  | Active | Design | DEM1 | 1273483 | 152299 | 1422887 | 0 | 0 | 62 | 0 | 0 | 102398 | 519638 | 499148.4 |  |  | 2026-05-06 | 2026-05-10 20:21 | 2026-05-10 | 2026-05-10 20:27 | 2026-05-11 | 2026-05-11 14:26 | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-05-11 | 2026-05-12 11:06 | 2026-05-12 | 2026-05-12 11:06 | 2026-05-12 | 2026-05-14 09:47 | 2026-06-25 | 2026-06-25 20:03 |  |  |  |  | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-24 | 2026-07-07 13:45 | Site is RTMI | 2026-05-06 | 2026-05-07 13:58 | 1205837 | 217050 | 0 | 0 | 0 | 0 | 1205836.5698 | 212565 | 2026-06-29 11:23:20 +0530 | Yerra Bharat | DDM2: Recap: DEM - 2 19883 Friday, June 5 ¦ Meeting ¦ Microsoft Teams | 2026-06-25 20:21:55 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-09 15:47:11 +0530 | Yerra Bharat | DDM1: Living room: Storge Unit at the entrance - wanted to have more partitions. TV Unit - increase in drawer depth. Kitchen - wanted tall pantry unit with Kesseboehmer - MiO Tall Unit Set 2 Master Bedroom: Will use less hanging space so need less hanging space and more partitions. Same with wardrobe in bedroom -2 Not satisfied with shutter wardrobe but explained that because of the width available sliding wardrobe cannot be placed. want to see more options for wall concepts. Want to see option possibility of space planning in bedroom 2 | 2026-07-13 |  | 2026-07-20
19884 | Turnkey | May'26 | Gaurav Modi |  | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Nivesh Gupta |  | Active | Preproduction | DEM2 | 716268 | 209999 | 1046034 | 0 | 0 | 6 | 26 | 0 | 0 | 272401 | 233867.6 |  |  | 2026-05-06 | 2026-05-11 12:21 | 2026-05-09 | 2026-05-13 12:25 | 2026-05-17 | 2026-05-17 21:45 | 2026-07-08 | 2026-07-09 13:35 | 2026-07-15 |  | 2026-07-22 |  | 2026-05-17 | 2026-05-19 11:24 | 2026-05-18 | 2026-05-19 13:31 | 2026-05-19 | 2026-05-19 16:45 | 2026-05-24 | 2026-05-24 17:10 |  |  |  |  | 2026-05-30 | 2026-05-26 12:45 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-06-20 | 2026-07-09 12:50 | Site is RTMI | 2026-05-06 | 2026-05-09 19:04 | 888568 | 157466 | 0 | 0 | 0 | 0 | 740855.5532 | 126229 | 2026-07-14 12:25:05 +0530 | Batskhem Marpna | MOM- Gaurav- Dated:12.07.2026 - False ceiling to be done with profile lights - wifi setup close to the connection point - Tv cabinet and removed the Projector screen - Dining chairs - Placement of dining table to be checked - Side table instead of coffee table - Wicker basket to be added. Notes to be checked on CM - External nook with tiles - Window outside as seating/ AC outlet confirmation Thanks, Batskhem | 2026-07-08 23:35:35 +0530 | Batskhem Marpna | MOM Master bedroom: - Sliding wardrobe- 6.5x6.5+loft - Dresser/study - Walldesign behind bed - Bed considered as per exisiting mattress - storage below the window - Wndow seater - False ceiling Living/dining - Projector to incorporate - Foldable dining table - 6 foot sofa - Mandir - False ceiling Kitchen: - Wicker basket - RO with Claypot - Retain the stone - Remove the existing cabinet - POT to be finalised as per site - Basin to be replaced and with cabinet below. -Entrance: - Shoerack with seating NOTE: TO check on the seating idea in the Master's door behind the window As discussed will plan for the next meeting online I will confirm the time and date. Thanks. | 2026-05-26 21:15:20 +0530 | Rishika Malviya | Some Image was uploaded | 2026-07-10 | 2026-07-09 13:37 | 2026-07-16
19885 | Turnkey | May'26 | Nitesh Temkar | Prescon Midtown Bay | MUM - GOR | Yes | Umang Ratnani | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Design | DEM1 | 1274995 | 181287 | 1812866 | 0 | 0 | 13 | 48 | 0 | 73712 | 557716 | 462280.4 |  |  | 2026-05-07 | 2026-05-07 16:15 | 2026-05-11 | 2026-05-11 14:43 | 2026-05-12 | 2026-05-12 14:50 | 2026-08-13 |  | 2026-08-20 |  | 2026-08-27 |  | 2026-05-12 | 2026-05-12 18:42 | 2026-05-13 | 2026-05-13 19:36 | 2026-05-13 | 2026-05-15 13:38 | 2026-05-22 | 2026-05-22 15:48 |  |  |  |  | 2026-08-14 |  | 2026-08-22 |  | 2026-08-23 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 | [6 empty] | 2026-09-20 |  | 2026-09-29 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-02 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-27 | [5 empty] | 2026-08-31 |  | 2026-08-09 |  | Unknown | 2026-05-07 | 2026-05-07 16:15 | 1536327 | 276538 | 0 | 0 | 0 | 0 | 1525795.2465 | 242923 | 2026-06-17 13:33:24 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-05 13:28:49 +0530 | Meet Shah | Some Image was uploaded | 2026-05-26 16:15:56 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-08-14 |  | 2026-08-21 |  | RTMI
19886 | Sub Project |  | Dharmesh Rana | charkop kshitij | MUM - GOR |  | Neha Yadav | Manzoor Shaikh | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-07 | 2026-05-12 14:13 | 2026-05-08 | 2026-05-12 14:14 | 2026-05-12 | 2026-05-12 14:14 | 2026-05-13 | 2026-05-12 14:15 | 2026-05-13 | 2026-05-12 14:16 | 2026-05-13 | 2026-05-12 14:18 | 2026-05-12 | 2026-05-12 14:14 | 2026-05-13 | 2026-05-12 14:14 | 2026-05-12 | 2026-05-12 14:15 | 2026-05-13 | 2026-05-12 14:15 |  |  |  |  | 2026-05-12 | 2026-05-12 14:16 | 2026-05-13 | 2026-05-12 14:17 | 2026-05-13 | 2026-05-12 14:17 |  |  | 2026-05-13 | 2026-05-12 14:18 | 2026-05-13 | 2026-05-12 14:31 | 2026-05-13 | 2026-05-13 12:51 | 2026-05-14 | 2026-05-13 12:51 |  |  |  |  | 2026-05-15 11:58 | 2026-05-23 | 2026-05-23 19:02 | 2026-05-27 | 2026-05-25 15:28 | 2026-05-26 | 2026-06-04 16:06 | 2026-05-25 | 2026-06-10 11:05 | 2026-06-08 | 2026-06-10 19:57 | 2026-06-10 | 2026-06-08 11:53 |  |  | 2026-06-12 | 2026-06-11 17:37 | 2026-06-13 | 2026-06-11 17:41 | 2026-06-11 | 2026-06-11 17:46 |  |  |  |  | 2026-05-12 | 2026-05-12 14:48 | 2026-05-13 | 2026-05-12 14:15 | Unknown | 2026-05-07 | 2026-05-12 14:13 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 0 | 2026-06-01 16:33:46 +0530 | Savita Parab | Execution: Site is ready for dispatch | 2026-05-10 16:37:02 +0530 | Safalta Karkera | Some Image was uploaded |  |  |  | 2026-05-13 | 2026-05-12 14:16 | 2026-05-13 | 2026-05-12 14:17
19887 | Sub Project | Dec'25 | Sulochana |  | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S |  |  | Active | Installation | Execution | 1097 | 1097 | 0 | 0 | 1097 | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-07 | 2026-05-13 16:46 | 2026-05-08 | 2026-05-13 16:46 | 2026-05-13 | 2026-05-13 16:46 | 2026-05-14 | 2026-05-13 16:47 | 2026-05-14 | 2026-05-13 16:48 | 2026-05-14 | 2026-05-13 16:50 | 2026-05-13 | 2026-05-13 16:46 | 2026-05-14 | 2026-05-13 16:47 | 2026-05-13 | 2026-05-13 16:47 | 2026-05-14 | 2026-05-13 16:47 |  |  |  |  | 2026-05-13 | 2026-05-13 16:48 | 2026-05-14 | 2026-05-13 16:49 | 2026-05-14 | 2026-05-13 16:49 |  |  | 2026-05-14 | 2026-05-13 17:56 | 2026-05-13 | 2026-05-14 18:25 | 2026-05-15 | 2026-05-14 18:41 | 2026-05-19 | 2026-05-22 15:44 |  |  |  |  | 2026-05-22 17:35 | 2026-05-30 | 2026-05-29 21:02 | 2026-06-05 | 2026-06-03 14:19 | 2026-06-04 | 2026-05-22 18:41 | 2026-06-03 | 2026-06-04 22:19 | 2026-06-04 | 2026-06-05 08:51 | 2026-06-22 | 2026-06-17 13:29 |  |  | 2026-07-24 |  | 2026-07-26 |  | 2026-07-27 | [5 empty] | 2026-05-14 | 2026-05-17 18:13 | 2026-05-14 | 2026-05-13 16:47 | Unknown | 2026-05-07 | 2026-05-13 16:46 | 0 | 0 | 0 | 0 | 81862 | 14735 | 81862 | 14735 | 2026-05-15 15:40:08 +0530 | Salpriyan Pm | Since Offer bed is discontinued special offer taken as an exception for the project. | [6 empty] | 2026-05-14 | 2026-05-13 16:47 | 2026-05-14 | 2026-05-13 16:48
19888 | Sub Project |  | Amit Sadashiv Hankare | Kukreja Com | MUM - GOR |  | Rajnish Mishra | Reshma Melanta | Safalta Karkera |  |  | Faizal Shaikh | Rizwan Mistry | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-07 | 2026-06-11 14:46 | 2026-05-08 | 2026-06-11 14:47 | 2026-06-11 | 2026-06-11 14:47 | 2026-06-12 | 2026-06-11 14:48 | 2026-06-12 | 2026-06-11 14:49 | 2026-06-12 | 2026-06-11 14:51 | 2026-06-11 | 2026-06-11 14:47 | 2026-06-12 | 2026-06-11 14:48 | 2026-06-11 | 2026-06-11 14:48 | 2026-06-12 | 2026-06-11 14:48 |  |  |  |  | 2026-06-11 | 2026-06-11 14:48 | 2026-06-12 | 2026-06-11 14:50 | 2026-06-12 | 2026-06-11 14:50 |  |  | 2026-06-12 | 2026-06-11 14:52 | 2026-06-12 | 2026-06-12 16:09 | 2026-06-13 | 2026-06-15 09:47 | 2026-06-16 | 2026-06-15 09:47 |  |  |  |  | 2026-06-27 10:38 | 2026-07-01 | 2026-06-30 20:09 | 2026-07-15 | 2026-07-13 17:52 | 2026-07-14 |  | 2026-07-13 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-15 | [5 empty] | 2026-06-12 | 2026-06-27 10:37 | 2026-06-12 | 2026-06-11 14:48 | Unknown | 2026-05-07 | 2026-06-11 14:46 | 0 | 0 | 0 | 0 | 47767.52 | 0 | 47767.52 | 0 | 2026-05-10 16:36:04 +0530 | Safalta Karkera | Some Image was uploaded | [6 empty] | 2026-06-12 | 2026-06-11 14:48 | 2026-06-12 | 2026-06-11 14:49
19889 | Turnkey | May'26 | Tarannum Yunus | Tys Apartment | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Mohammed Rasick |  | Hold | Preproduction | DEM2 | 1095234 | 219050 | 1371747 | 0 | 0 | 3 | 5 | 0 | 0 | 484100 | 392084 |  |  | 2026-05-08 | 2026-05-20 12:29 | 2026-05-23 | 2026-05-29 17:58 | 2026-06-01 | 2026-05-31 12:14 | 2026-07-06 | 2026-07-05 10:47 | 2026-10-31 |  | 2026-11-07 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-02 19:06 | 2026-06-02 | 2026-06-04 17:25 | 2026-06-06 | 2026-06-06 13:07 |  |  |  |  | 2026-07-05 | 2026-07-07 12:14 | 2026-11-02 |  | 2026-11-03 |  |  |  | 2026-11-10 |  | 2026-11-11 |  | 2026-11-12 |  | 2026-11-13 | [6 empty] | 2026-12-01 |  | 2026-12-10 |  | 2026-12-09 |  | 2026-12-10 |  | 2026-12-11 |  | 2026-12-13 |  |  |  | 2027-01-04 |  | 2027-01-06 |  | 2027-01-07 | [5 empty] | 2026-11-11 |  | 2026-06-07 | 2026-07-05 10:44 | Site is RTMI | 2026-05-08 | 2026-05-19 18:39 | 1162497 | 209249 | 0 | 0 | 0 | 0 | 1132711.9264 | 197142 | 2026-07-07 12:56:16 +0530 | Ashiya Sanam | Title: Design Presentation Project No: 19889 Client: Tarannum Yunus Hi, MOM - 04/05/26 LIVING ROOM 1. tv unit To be added as per reference image 2.To be kept with beige wallpaper theme 3.Foyer unit to be added with a mirror design 4.Beige theme to be considered 5.Crockery unit as per EC reference kitchenÂ 1.door panel for kitchen removedÂ 2.kitchen entrance wall to keep as existing not to extend or break loft in side wall in kitchen ( add or remove as per design change - open point) 3.add island counter in kitchenÂ with Hob 4.roller shutter unit in door sideÂ 5.Wicker basket to be added beside the door units sons's bedroomÂ 1.room orientation to changeÂ ,Study to be placed in place of wardrobe 2. wardrobe to be added 3.Theme as per reference image Guest Bedroom: 1.Sliding wardrobe to be added which will cover the existing wardrobe 1.Both vanity units to be added with mirror storage note - all modular + wall design in scopeÂ painting , electrical ,civil , plumbing not in scope currently | 2026-06-07 18:57:51 +0530 | Palak Thakur | (20) Calendar ¦ 19889 - Celebrity Design Presentation (CDP) with the customer ¦ Microsoft Teams (20) Calendar ¦ 19889 - Design Consultation Meeting (DCM) with the customer (External) ¦ Microsoft Teams | 2026-06-06 13:07:12 +0530 | Rajeshwari S | Welcome call done along with Ashiya RTMI & Renovation project Duplex house. Client is staying at house. during execution - client will move to first and second floor. They have two separate entry. there will not be any disturbance from client side during execution. one set of keys will be given if required. IM is already completed. Since client not is station wanted design meeting on 20th June. Estimation was closed for Rs.10,95,235/- after all the offers 10% Invoice to be raised on 20th June Informed about timeline and process. | 2026-07-06 | 2026-07-05 10:54 | 2026-11-01 |  | RTMI
19890 | Turnkey | May'26 | Rachit Gupta | Kalpataru vivant | MUM - GOR | Yes | Shweta Dalvi | Manzoor Shaikh | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Design | DEM1 | 2017008 | 268999 | 2010043 | 0 | 0 | 36 | 0 | 0 | 134403 | 849500 | 764106 |  |  | 2026-05-08 | 2026-05-30 21:12 | 2026-05-13 | 2026-05-30 21:18 | 2026-05-31 | 2026-05-31 22:11 | 2026-06-25 |  | 2026-08-10 |  | 2026-08-17 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-03 13:14 | 2026-06-03 | 2026-06-09 15:11 | 2026-06-16 | 2026-06-16 20:00 |  |  |  |  | 2026-06-26 |  | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-06-17 |  | Unknown | 2026-05-08 | 2026-05-08 15:26 | 1703426 | 306616 | 0 | 0 | 0 | 0 | 2199284.632 | 363061 | 2026-06-29 14:22:41 +0530 | Neha Yadav | DDM1: DDM1 Discussion: 1)Crockery one side will have I shelf internal 2)L shape sofa need to do 3)Kitchen- will be micro , oven 4)Sons room - Drawers need to add below wardobe both side , no vertical below shelf,pul out tray need to add , hanging space will be 40, one side saree space 32 below 2 drawer & shelf. 5)Guest room-Sofa cumbed ,wd full 2d & pull out tray to done 6)Master room- wardrobe his side 2 drawer wit hanging space 40 , 2 side 1 drawer with 35 hanging space , pull out tray need to add 7)Study will be next to bed with2 side table , opposite side there will be tb unit with dresser mirror and tall cosmetic storage need to add 8)Bed will be 2 top openable hydaulic Feel free to add apointers if missed any. | 2026-06-29 14:22:41 +0530 | Neha Yadav | DDM1: DDM1 Discussion: 1)Crockery one side will have I shelf internal 2)L shape sofa need to do 3)Kitchen- will be micro , oven 4)Sons room - Drawers need to add below wardobe both side , no vertical below shelf,pul out tray need to add , hanging space will be 40, one side saree space 32 below 2 drawer & shelf. 5)Guest room-Sofa cumbed ,wd full 2d & pull out tray to done 6)Master room- wardrobe his side 2 drawer wit hanging space 40 , 2 side 1 drawer with 35 hanging space , pull out tray need to add 7)Study will be next to bed with2 side table , opposite side there will be tb unit with dresser mirror and tall cosmetic storage need to add 8)Bed will be 2 top openable hydaulic Feel free to add apointers if missed any. | 2026-06-23 15:26:24 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-26 |  | 2026-08-11 |  | Under Construction | 2026-07-01
19893 | Turnkey | May'26 | Dinaz Shaikh | 72 West | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 6512992 | 9999 | 0 | 0 | 0 | 29 | 0 | 641300 | 651299 | 2892365 | 2318028.8 |  |  | 2026-05-08 | 2026-06-09 12:45 | 2026-06-04 | 2026-06-11 13:19 | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-08-03 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-28 |  | 2026-09-02 |  |  |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-05-08 | 2026-05-08 18:46 | 0 | 0 | 0 | 0 | 0 | 0 | 5519485 | 993507 | 2026-06-16 20:28:42 +0530 | Priyanka Patel | CDP: Project Name/Tower Name/Flat Number 72 West Typology 4bhk Site Access Date 2026-08-30 Possession Date 2026-08-30 Customer ProfileFamily members (no. & age) 4 members Profession bussiness Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc yes basic vastu Signed off celebrity theme Neo Industrial, Abstract Luxury Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 8000000 Mention basic vastu principles agreed for integration in design, if any Design VisionEntrance Foyer must-haves yes storage Upload reference images Living key features and furniture must-haves yes Upload reference images Dining setup, table size and other furniture must -haves yes Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves yes storage Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves yes storage Upload reference images Other space/ room (if any) must-haves yes storage Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves yes storage Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves yes storage Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves yes Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves yes Upload reference images Styling and Dcor must-haves yes Space identified for signature design features and its specifics Specify if design to reflect any personal story, cultural influence or special memory MiscellaneousTimeline related commitment made by Bonito to customer, if any: yes Other commitments made by Bonito to customer, if any: yes RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? yes Re-confirm the Move-in Date 2026-11-30 Re-confirm the Possession Date 2026-11-30 Any special occasion mentioned by customer wrt handover date yes | 2026-06-16 12:37:39 +0530 | Priyanka Patel | Some Image was uploaded | 2026-06-12 13:48:19 +0530 | Priyanka Patel | Some Image was uploaded | 2026-06-22 |  | 2026-06-29
19897 | Sub Project |  | Pranav Sreedhar | Prestige Meridian Park | BNG - HRBR |  | Shivani Shet | Rajeshwari S | Shibin Lal |  |  | Nanda Kumar | Ranjith Kumar | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-09 | 2026-05-19 17:10 | 2026-05-10 | 2026-05-19 17:10 | 2026-05-19 | 2026-05-19 17:11 | 2026-05-20 | 2026-05-19 17:11 | 2026-05-20 | 2026-05-19 17:12 | 2026-05-20 | 2026-05-19 17:13 | 2026-05-19 | 2026-05-19 17:11 | 2026-05-20 | 2026-05-19 17:11 | 2026-05-19 | 2026-05-19 17:11 | 2026-05-20 | 2026-05-19 17:11 |  |  |  |  | 2026-05-19 | 2026-05-19 17:12 | 2026-05-20 | 2026-05-19 17:12 | 2026-05-20 | 2026-05-19 17:12 |  |  | 2026-05-20 | 2026-05-19 17:14 | 2026-05-20 | 2026-05-19 18:47 | 2026-05-20 | 2026-05-19 18:58 | 2026-05-20 | 2026-05-19 18:58 |  |  |  |  | 2026-05-19 19:00 | 2026-05-23 | 2026-05-23 19:04 | 2026-05-27 | 2026-05-25 15:35 | 2026-05-26 |  | 2026-05-25 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-05-19 | 2026-05-19 18:47 | 2026-05-20 | 2026-05-19 17:11 | Unknown | 2026-05-09 | 2026-05-19 17:10 | 0 | 0 | 0 | 0 | 46609 | 0 | 46609 | 0 | 2026-06-10 14:56:56 +0530 | Ranjith Kumar | Execution: | [6 empty] | 2026-05-20 | 2026-05-19 17:12 | 2026-05-20 | 2026-05-19 17:12
19898 | Turnkey | May'26 | Prakash | Birla Tisya | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [5 empty] | Mohammed Rasick |  | Active | Design | DEM1 | 1576444 | 206499 | 2064138 | 0 | 0 | 55 | 0 | 0 | 108790 | 720948 | 540207.2 |  |  | 2026-05-09 | 2026-05-15 10:55 | 2026-05-09 | 2026-05-15 12:34 | 2026-05-17 | 2026-05-18 13:21 | 2026-09-12 |  | 2026-09-19 |  | 2026-09-26 |  | 2026-05-18 | 2026-05-21 10:18 | 2026-05-19 | 2026-05-21 10:20 | 2026-05-21 | 2026-05-21 16:46 | 2026-05-24 | 2026-05-24 18:52 |  |  |  |  | 2026-09-13 |  | 2026-09-21 |  | 2026-09-22 |  |  |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-01 |  | 2026-10-02 | [6 empty] | 2026-10-20 |  | 2026-10-29 |  | 2026-10-28 |  | 2026-10-29 |  | 2026-10-30 |  | 2026-11-01 |  |  |  | 2026-11-23 |  | 2026-11-25 |  | 2026-11-26 | [5 empty] | 2026-09-30 |  | 2026-05-25 |  | Unknown | 2026-05-09 | 2026-05-09 12:00 | 1749269 | 314868 | 0 | 0 | 0 | 0 | 1718639.013 | 283760 | 2026-07-12 15:04:30 +0530 | Parasa Sri | Client has mentioned to hold till builder confirmation | 2026-06-08 16:35:15 +0530 | Amruta Vaishampayan |  | 2026-05-29 13:20:11 +0530 | Losii Athisa | Some Image was uploaded | 2026-09-13 |  | 2026-09-20 |  | Under Construction | 2026-05-31
19900 | Turnkey | May'26 | Saral Chandra | SNN Raj Serenity | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Preproduction | DEM2 | 2255199 | 451040 | 2429994 | 0 | 0 | 8 | 0 | 0 | 0 | 961250 | 842908.8 |  |  | 2026-05-09 | 2026-05-09 14:03 | 2026-05-14 | 2026-05-14 15:49 | 2026-05-17 | 2026-05-19 13:20 | 2026-07-09 | 2026-07-04 19:10 | 2026-07-16 |  | 2026-07-23 |  | 2026-05-16 | 2026-05-16 19:19 | 2026-05-20 | 2026-05-20 16:30 | 2026-05-20 | 2026-05-21 17:35 | 2026-05-26 | 2026-05-26 15:16 |  |  |  |  | 2026-07-05 | 2026-07-07 19:20 | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-05-27 | 2026-06-16 13:12 | Site is RTMI | 2026-05-09 | 2026-05-09 13:59 | 2059317 | 370677 | 0 | 0 | 0 | 0 | 2521985.3684 | 416471 | 2026-07-04 19:04:28 +0530 | Kiran Agarampalli | 04.07.26 Rafters in living is retained Sons' bedroom and master bedroom rafters are changed to POP punning Loft panels are added in all 3 bedrooms Kitchen wall units' height is increased to 4' Aristo finish for MBR and PBR is finalized Wallpaper options are selected Shoe rack in living removed skirting and Bonito legs got added MBR foldable table and panel is removed, dresser open unit is removed Kids study unit width got reduced and base drawers changed to shutter Common vanity open tall unit is removed | 2026-06-16 13:19:48 +0530 | Kiran Agarampalli | Discussion: Materials selection completed TV Unit design changed as per the refEntrance straight wall rafters added Sofa back wall gypsum paneling with texture/wallpaper design retained Partition bottom storage added, Pooja to have Side panel with CNC design, Back Panel with CNC (OM, Swastik)Front CNC design with archFalse ceiling design changed, peripheral at dining and living in-between space to have CNC Jaali design.MBR- Aristo shutters design changed PBR: Color and pattern changed, earthenware and double cream combination. laminate to match with that.CX wants to optimise the quotation and bring down it around 20L. | 2026-06-04 13:29:45 +0530 | Patil Madhavi | Some Image was uploaded | 2026-07-05 | 2026-07-05 11:52 | 2026-07-17 |  | Under Construction | 2026-06-15
19902 | Turnkey | May'26 | Alekya | Disha pursuit of elements | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2522377 | 9999 | 2522377 | 0 | 0 | 57 | 0 | 242239 | 252238 | 1008951 | 1008950.8 |  |  | 2026-05-09 | 2026-05-09 15:14 | 2026-05-09 | 2026-05-19 09:58 | 2026-05-22 | 2026-05-19 12:32 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-09 | 2026-05-09 15:00 | 2137608 | 384769 | 0 | 0 | 0 | 0 | 2137608 | 384769 | 2026-05-19 10:52:20 +0530 | Priyamvada PV | CDP MOM dated 17.05.26 KBR back wall to be customized with different theme of sports Suggesting toy storage with baskets on left wall Study on window wall only since cot to be towards window Pooja - CNC design to be provided for front side panels & back panel no glass shutters required, base platform to be removed TV back panel to be required Kitchen wall units in membrane, wall units in utility in laminate finish Lofts to be added in kitchen & utility in membrane & laminate finishes Wall units in utility in laminate finish L shape wall behind dining to be in onyx/ paneling (Onyx client procurement) Master bedroom - Wardrobe on TV wall included Crockery to be excluded for now | 2026-05-09 17:13:02 +0530 | Priyamvada PV | CxÂ : Alekya , Pradeep Property : Gunjur Disha Pursuit of elements RGM : 09.05.26 CDP date : 17.05.26 12pm Site access date : Sep'2026Â Soft handover : Sep'2026 Possession : Dec'2027 MD : East facingÂ Family members : 5 adults + 1 kid Kid - 1 year Shiva Sharvil Budget : 15L (open for discussion as need quote for all line items discussed below) Laminates to be considered for Diamond/platinum category only Interior style :Â Modern luxury no wooden textures in dark brown Preferred pastel colors like pink, beige, green & yellow Scope of workÂ : Foyer - Mural artÂ (ref shared) other option is paneling with cove light provision Left wall (MCB box ) with wallpaper arch shape in living entry with partition of 1'W on left side foyer ceiling : no false ceiling Paneling with HDHMR/laminate or other option 3D paneling to be checked Living :Â Pooja in tv left side (ref shared) need bottom step L shape wall (kitchen & BR-3 wall) to be highlighted with some alabaster sheet which reflects light (Ceiling with cornerÂ Back panel with cnc TV : 55" size L shape sofa with corner storage/coffee table marble finish laminate for back paneling DiningÂ - 4 seater table or foldable table in design Crockery on CT wall Base storage wall unit with glass (for decor storage) (not rectangle shape) (estimate to be provided for any curvy shapes) Kitchen :Â Membrane finish Entry paneling in arch shape design to be shown (approx costing to be provided) Wall units with some fluted glass shutter L shape loft Quartz for kitchen (stain proof quartz only to be considered) Granite for utility builder not providing BR-3 (MBR) king size bed space Hinged Wardrobe behind doorÂ Â Locker storage below on right of bed designer semi circle mirror above bed opp tv unit with wallpaper bed back wall design (as per ref) rafters/ beading with wallpaper Hinged wardrobe as per fp position with loft BR-2 (KBR) not very kiddish theme but neutral kids theme window is till floor until 7'H Hinged wardrobe behind door & as per FP position bed position in window side with study on right (single bed) bookshelf on left wall mirror in room GBR hinged wardrobeÂ with loft minimal bed wall design with wallpaper tv unit for 32" size mirror in room workstation in GBR with base drawer storage TV wall to be designed cute bookshelf to be done Vanity storage will be added in design phase based on wash basin Balcony PVC rafters to be added |  |  |  | 2026-05-27 |  | 2026-06-03
19903 | Turnkey | May'26 | Jayesh parikh | Neelkant park | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1731964 | 9999 | 0 | 0 | 0 | 61 | 0 | 163197 | 173196 | 705584 | 679986.8 |  |  | 2026-05-09 | 2026-05-09 16:17 | 2026-05-12 | 2026-05-13 10:33 | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-05-28 |  | 2026-06-05 |  | 2026-06-06 |  |  |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-14 |  | 2026-05-23 |  | Unknown | 2026-05-09 | 2026-05-09 16:14 | 0 | 0 | 0 | 0 | 0 | 0 | 1470012 | 261952 | 2026-05-19 13:10:33 +0530 | Bhawaya Goyal | DCM: Client : Jayesh Parikh conf. : 2 bhk + 1 bhk People : 3 (2 brothers + mother) Floor : 5thÂ BUDGET : 15LÂ POSS. : NEXT MONTHÂ MOVE IN : AS SOON AS POSSIBLE 2bhk Foyer area :Â shoe rack safety doorÂ Living room : sofa cum bed folding dining table / free standingÂ (mirror panelling) TV, mandirÂ (moulding + wallpaper ) crockery unit (golden touch little) Kitchen : (civil or fully modular) Parallel platformÂ cooktop in east (LR) washing machine + fridgeÂ Bedroom 1 : converted in master with attached washroom 1 sonÂ Queen size bed (access both side) side table work stationÂ wardrobe storage for 2 MIRRORÂ (OFFICE CUM BEDROOM) Master bedroom : older son + motherÂ King size bedÂ side table work station wardrobe +LOFTÂ (entrance shifted towards kitchen)Â dressing + medical spaceÂ Washroom : VanityÂ wardrobe in southÂ TV IN EASTÂ BED IN SOUTH / EASTÂ LR SEATING SOFA IN EAST / NORTH DINING IN WESTÂ Diff design for all 3 rooms. mouldings, louvers, wallpaperÂ FALSE CEILING PAINTING ELECTRICAL 1 BHKÂ BUDGET: AS PER RENT (basic) 2 TV UNITS + 3+1+1 SOFA DINING 4 SEATER = EXISTING KITCHEN : WALL UNITÂ LOFT UNIT BASE UNITSÂ LIVING ROOM : STORAGE + CROCKERY ON LEFT WALLÂ BEDROOM : WARDROBE + LOFT FALSE CEILINGÂ PAINTINGÂ ELECTRICAL MOULDING,WALLPAPER, LOUVER.Â | 2026-05-09 15:08:18 +0530 | Unknown | About the Customer **Customer Project Details and Budget** Customer is undergoing redevelopment with expected OC in 2-3 months and is interested in end-to-end interior design for a 2 BHK flat in Ghatkopar with a budget of 10-12 lakhs. Agent confirmed projects below 8 lakhs are not taken to ensure warranty. **Visit Availability Confirmation Pending** Customer needs to confirm visit availability with family for Saturday or Sunday and will call back tomorrow. **Customer Unavailable Until Tomorrow Morning** Customer is currently traveling and will be available to discuss requirements tomorrow morning upon reaching Ahmedabad. **Experience Center Visit Logistics and Customer Hesitation** Agent arranged pick-up from Ghatkopar to Thane experience center and will provide drop-off service. Customer is hesitant about on-the-spot decisions but agent clarified it's a consultation. **Agent Follow-up Scheduled** Agent will call back tomorrow at 5:30 PM IST to confirm visit details. |  |  |  | 2026-05-28 |  | 2026-06-04
19904 | Turnkey | May'26 | Chandresh Rao | anmol Complex | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 3210537 | 9999 | 3210537 | 0 | 0 | 58 | 0 | 311055 | 321054 | 1316315 | 1252114.8 |  |  | 2026-05-09 | 2026-05-12 15:04 | 2026-05-14 | 2026-05-14 15:44 | 2026-05-17 | 2026-05-19 11:01 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-09 | 2026-05-12 14:59 | 2720794 | 489743 | 0 | 0 | 0 | 0 | 2720794 | 489743 | 2026-05-19 11:01:56 +0530 | Pratima Kajwe | CDP: MOM Project ProfileProject Name/Tower Name/Flat Number Anmol Apartment Typology 1+2BHK Site Access Date 2026-05-20 Possession Date 2026-05-20 Customer ProfileFamily members (no. & age) 5 members Profession investment banker Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc Signed off celebrity theme Abstract Luxury, Japandi Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) Mention basic vastu principles agreed for integration in design, if any Design VisionEntrance Foyer must-haves Safety door, shoe-rack Upload reference images Living key features and furniture must-haves Sofa, bar unit, TV unit, dining Upload reference images Dining setup, table size and other furniture must -haves 6 seater dining Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves Bed, swing wardrobe, dresser Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves existing wardrobe, bed, study table, bookshelf Upload reference images Other space/ room (if any) must-haves Existing metal wardrobe, swing wardrobe, single sofa cum bed, Study room storage + study table and storage Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves Semi modular kitchen, storage top to bottom, dishwasher provision Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves NA Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves Space for washing machine and dryer Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves Upload reference images Styling and Dcor must-haves Space identified for signature design features and its specifics Specify if design to reflect any personal story, cultural influence or special memory MiscellaneousTimeline related commitment made by Bonito to customer, if any: Other commitments made by Bonito to customer, if any: RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? Re-confirm the Move-in Date 2026-09-19 Re-confirm the Possession Date 2026-05-17 Any special occasion mentioned by customer wrt handover date Before Ganesh Chaturthi | 2026-05-17 16:17:12 +0530 | Pratima Kajwe | CDP: MOM Plumbing fittings - 120000 Electrical Fittings - 90000 (switch boards, lights, Distribution board) - Kitchen Fittings - 25000 + 15000 + 10,000 plumbing (Sink, tap,) Dishwasher - 18000 Tiles - 173000 (bathroom + flooring) Mattress - 50000 Appliances - Curtains - 80000 Total: 5,80,000 | 2026-05-14 10:57:06 +0530 | Pratima Kajwe | DCM: MOM Latika and Chandresh Raos. Kids 2 : 21 YO and 11 YO Living room Breaking wall joining two flats. Mandir in Left top corner Bar Unit with crockery Shoe-rack Using door no. 1 as main door entrance Pichwai art work behind mandir. Bells provision. Bar on the bottom left corner. 6 seater dining space near bottom right corner False ceiling in whole house. Painting, Electrification, Bedroom top right (daughters bedroom) Wardrobe already done no change Flooring as it is Only Dcor for this room. Double bed in daughters bedroom with storage Bedroom bottom right (master bedroom) Wardrobe and bed with storage One metal cupboard can be shifted to mothers bedroom. Openable wardrobe style. King size bed existing. Dcor Mirror space in 3 rooms. Bedroom Mothers (top left) Tv console to keep mandir storage and utility for the same. Wardrobe and single bed/Queen size Civil scope Breaking of common wall Dismanteling on kitchen and making it as guest room Portuguese style for kitchen theme Dishwasher space in kitchen. Dismentaling kitchen of 2 BHK kitchen Membrane finish. Kitchen of 1 bhk as store room Budget :Â | 2026-05-27 |  | 2026-06-03
19905 | Turnkey | May'26 | Shankar | Nava Vajra | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Preproduction | DEM2 | 1117423 | 223485 | 1439751 | 0 | 0 | 26 | 0 | 0 | 0 | 446969 | 446969.2 |  |  | 2026-05-09 | 2026-05-09 16:44 | 2026-05-12 | 2026-05-12 19:16 | 2026-05-16 | 2026-05-20 15:07 | 2026-06-12 | 2026-06-12 21:28 | 2026-11-22 |  | 2026-11-29 |  | 2026-05-20 | 2026-05-22 11:05 | 2026-05-21 | 2026-05-22 11:47 | 2026-05-22 | 2026-05-25 10:17 | 2026-06-03 | 2026-06-03 17:42 |  |  |  |  | 2026-06-12 | 2026-06-19 18:17 | 2026-11-24 |  | 2026-11-25 |  |  |  | 2026-12-02 |  | 2026-12-03 |  | 2026-12-04 |  | 2026-12-05 | [6 empty] | 2026-12-23 |  | 2027-01-01 |  | 2026-12-31 |  | 2027-01-01 |  | 2027-01-02 |  | 2027-01-04 |  |  |  | 2027-01-26 |  | 2027-01-28 |  | 2027-01-29 | [5 empty] | 2026-12-03 |  | 2026-06-04 | 2026-06-12 20:46 | Site is RTMI | 2026-05-09 | 2026-05-09 16:40 | 1220128 | 219623 | 0 | 0 | 0 | 0 | 1207215.3989 | 201136 | 2026-05-24 12:01:04 +0530 | Raghavendra S | Some Image was uploaded | 2026-05-22 16:50:53 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession by September/October Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days (explained) Detailed timelines were explained to the customer during the call, based on the finalized scope of work. . Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 -Â Plan of Action Discussed During the Call: * IMs - 31st May 2026 * DEM 1 - Client said he will give the clarity to the sales team * 10% Payment Client said he will give the clarity to the sales team Explained that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Hob & Chimney Offer Laminate Upgrade - May '26 Campaign 100% GST Waiver PM Fee Waiver (4%) Design fee waiver (5%) Silver Coin 21g Final Closing Value Discussed: 11,17,423 Client VOC Client is not willing to pay 10% within 10 days. Client also didn't give any dates for DEM1 | 2026-05-22 11:48:34 +0530 | Raghavendra S | PID - 19905 - Shankar - Client is available today at 4pm for the onboarding call | 2026-06-13 | 2026-06-12 21:29 | 2026-11-23 |  | Under Construction | 2026-10-08
19906 | Turnkey | May'26 | Mr. Ram Pandey | 100trees | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh | Savita Parab | Rizwan Mistry |  | Mrunali Mitkari | Aakash Gaikwad | Active | Design | 60% Payment | 869863 | 174163 | 1058827 | 0 | 869863 | 2 | 0 | 0 | 0 | 370352 | 325347.6 |  |  | 2026-05-09 | 2026-05-18 15:50 | 2026-05-19 | 2026-05-19 12:37 | 2026-05-19 | 2026-05-19 15:56 | 2026-06-01 | 2026-05-31 15:04 | 2026-06-25 | 2026-06-24 13:19 | 2026-06-27 | 2026-06-27 20:14 | 2026-05-19 | 2026-05-19 17:17 | 2026-05-20 | 2026-05-20 12:59 | 2026-05-20 | 2026-05-21 16:03 | 2026-05-24 | 2026-05-24 20:21 |  |  |  |  | 2026-05-31 | 2026-06-06 13:00 | 2026-06-25 | 2026-06-24 13:41 | 2026-06-25 | 2026-06-24 13:41 |  |  | 2026-07-16 | 2026-07-12 18:07 | 2026-07-12 | 2026-07-12 19:28 | 2026-07-13 | 2026-07-13 01:48 | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-05-25 | 2026-05-31 14:01 | Site is RTMI | 2026-05-09 | 2026-05-09 17:21 | 901529 | 157298 | 0 | 0 | 899620.019 | 156575 | 899620.019 | 156575 | 2026-07-12 18:13:31 +0530 | Zoya Bhatkar |  | 2026-07-12 17:26:42 +0530 | Zoya Bhatkar |  | 2026-07-10 17:45:08 +0530 | Zoya Bhatkar |  | 2026-06-01 | 2026-05-31 15:04 | 2026-06-25 | 2026-06-24 13:19 | RTMI
19907 | Turnkey | May'26 | Yogini Mukhi | neelam solstice | MUM - GOR | Yes | Sonal Singh | Vishakha Vaishnav | Kashmira Nerurkar |  |  | Uday Yadruk | Rizwan Mistry |  | Manasi Patil | Aakash Gaikwad | Active | Preproduction | DEM2 | 1199294 | 239859 | 1608274 | 0 | 0 | 7 | 0 | 0 | 0 | 509868 | 449566.8 |  |  | 2026-05-09 | 2026-05-11 14:14 | 2026-05-09 | 2026-05-14 12:56 | 2026-05-14 | 2026-05-14 13:04 | 2026-06-01 | 2026-05-31 19:02 | 2026-06-27 | 2026-06-26 13:13 | 2026-07-08 |  | 2026-05-14 | 2026-05-16 14:37 | 2026-05-15 | 2026-05-16 15:09 | 2026-05-16 | 2026-05-18 15:59 | 2026-05-19 | 2026-05-19 16:09 |  |  |  |  | 2026-05-31 | 2026-06-12 18:55 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-05-20 | 2026-05-31 11:51 | Site is RTMI | 2026-05-09 | 2026-05-11 14:13 | 1365231 | 243042 | 0 | 0 | 0 | 0 | 1359288.9068 | 226800 | 2026-06-26 19:53:15 +0530 | Saakshi Bhute | Some Image was uploaded | 2026-05-31 11:45:31 +0530 | Saakshi Bhute | DDM1: CX Yogini - DEM 1 Appliance listÂ Parents BedroomÂ Horizontal part in wardrobe Â Â Kids BedroomÂ Add mirror with storageÂ study desk no foldable Side wardrobeÂ Master bed Stirage study desk Add single shutter wardrobeÂ | 2026-05-27 12:18:35 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-01 | 2026-05-31 19:02 | 2026-06-27 | 2026-06-26 13:16 | RTMI
19908 | Turnkey | May'26 | Aniruddh Gupta | Hiranandani tribeca | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 2412071 | 9999 | 0 | 0 | 0 | 22 | 0 | 231208 | 241207 | 1030128 | 899528.4 |  |  | 2026-05-09 | 2026-05-10 10:26 | 2026-06-19 | 2026-06-19 11:00 | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-05-09 | 2026-05-10 10:23 | 0 | 0 | 0 | 0 | 0 | 0 | 2044128 | 367943 | 2026-06-30 16:14:00 +0530 | Krutika Vernekar | CDP: Cx needed to check on his finances . As his outer expenses were 20 L and wanted to find GST number before onboarding Cx has no time to disgest such big decision due to office pressure . he will be free bt 4th of July | 2026-06-30 16:12:26 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-19 11:24:37 +0530 | Bhawaya Goyal | DCM: Recap: 19908 Mr Anirudh Gupta and Family Requirement gathering meeting Friday, May 29 ¦ Meeting ¦ Microsoft Teams | 2026-07-06 |  | 2026-07-13
19909 | Turnkey | May'26 | Mukesh Sharma | Sky Heights | MUM - GOR | Yes | Saif Shaikh | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1489411 | 201329 | 1995138 | 0 | 0 | 39 | 0 | 0 | 96553 | 644110 | 547419.2 |  |  | 2026-05-09 | 2026-05-09 18:38 | 2026-06-02 | 2026-06-02 19:36 | 2026-06-05 | 2026-06-02 19:50 | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-03 17:05 | 2026-06-03 | 2026-06-06 17:34 | 2026-06-12 | 2026-06-12 16:35 |  |  |  |  | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-07-01 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-05-09 | 2026-05-09 18:38 | 1690795 | 304343 | 0 | 0 | 0 | 0 | 1676641.5425 | 276644 | 2026-06-12 16:33:51 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to align the measurement DEM Dates -Â DEM 1 - Cx will update us for the meeting after IM DEM 2 - TBD DEM 3 - TBD Possession date : December Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-06 17:32:35 +0530 | Athul Ajaykumar |  | 2026-06-06 15:44:01 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: December Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (8th June 2026) * DEM 1 Tentatively scheduled for (14th June 2026) * 10% Payment Stage Tentatively scheduled for (15th June) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - May '26 Campaign 100% GST Waiver Free Bed Offer Free Shoerack Offer PM fee waiver (7.5%) Final Closing Value Discussed: 14,89,411 Checklist terms descoping, agreement terms are cleared Rejections: Address Not Updated Client VOC Client mentioned he has civil work which is under bonito's scope | 2026-06-18 |  | 2026-06-25 |  | Under Construction | 2026-10-31
19910 | Sub Project |  | Jay 1 | ** | BNG - HRBR |  | Shivani Shet | Rajeshwari S | Surabhi Ravichandran |  |  | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S |  |  | Active | Production | 100% Payment | 23 | 0 | 0 | 0 | 23 | 51 | 0 | 0 | 0 | 0 | 23 |  |  | 2026-05-09 | 2026-05-13 12:12 | 2026-05-10 | 2026-05-13 12:12 | 2026-05-13 | 2026-05-13 12:12 | 2026-05-14 | 2026-05-13 12:15 | 2026-05-14 | 2026-05-13 12:16 | 2026-05-14 | 2026-05-13 12:19 | 2026-05-13 | 2026-05-13 12:13 | 2026-05-14 | 2026-05-13 12:14 | 2026-05-13 | 2026-05-13 12:14 | 2026-05-14 | 2026-05-13 12:14 |  |  |  |  | 2026-05-13 | 2026-05-13 12:15 | 2026-05-14 | 2026-05-13 12:17 | 2026-05-14 | 2026-05-13 12:17 |  |  | 2026-05-14 | 2026-05-13 12:20 | 2026-05-14 | 2026-05-14 15:34 | 2026-05-15 | 2026-05-14 16:44 | 2026-05-25 | 2026-05-13 12:13 |  |  |  |  | 2026-05-14 17:37 | 2026-05-23 | 2026-05-23 18:59 | 2026-05-27 | 2026-05-25 15:22 | 2026-05-26 |  | 2026-05-25 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-05-14 | 2026-05-13 12:21 | 2026-05-14 | 2026-05-13 12:14 | Unknown | 2026-05-09 | 2026-05-13 12:12 | 0 | 0 | 0 | 0 | 35612 | 6410 | 35612 | 6410 | [9 empty] | 2026-05-14 | 2026-05-13 12:15 | 2026-05-28 | 2026-05-13 12:13
19911 | Sub Project |  | jay j | Radiance Gardenia | BNG - HRBR |  | Shivani Shet | Rajeshwari S | Surabhi Ravichandran |  |  | Vanlalrammawia Tombing | Saddam Hussain Z M | Murali S |  |  | Active | Production | Dispatch Due | -887 | 0 | 0 | 0 | -887 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-09 | 2026-05-13 12:22 | 2026-05-10 | 2026-05-13 12:22 | 2026-05-13 | 2026-05-13 12:22 | 2026-05-14 | 2026-05-13 12:24 | 2026-05-14 | 2026-05-13 12:25 | 2026-05-14 | 2026-05-13 12:28 | 2026-05-13 | 2026-05-13 12:22 | 2026-05-14 | 2026-05-13 12:22 | 2026-05-13 | 2026-05-13 12:23 | 2026-05-14 | 2026-05-13 12:23 |  |  |  |  | 2026-05-13 | 2026-05-13 12:24 | 2026-05-14 | 2026-05-13 12:26 | 2026-05-14 | 2026-05-13 12:26 |  |  | 2026-05-14 | 2026-05-13 12:29 | 2026-05-14 | 2026-05-14 15:35 | 2026-05-15 | 2026-05-14 16:44 | 2026-05-16 | 2026-05-13 12:30 |  |  |  |  | 2026-05-14 17:37 | 2026-05-23 | 2026-05-23 19:00 | 2026-05-27 | 2026-05-25 15:25 | 2026-05-26 | 2026-06-24 16:30 | 2026-06-09 |  | 2026-06-05 |  | 2026-06-07 |  |  |  | 2026-06-14 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-05-14 | 2026-05-13 12:30 | 2026-05-14 | 2026-05-13 12:23 | Unknown | 2026-05-09 | 2026-05-13 12:22 | 0 | 0 | 0 | 0 | 41620 | 7491 | 41620 | 7491 | [9 empty] | 2026-05-14 | 2026-05-13 12:24 | 2026-05-14 | 2026-05-13 12:26
19912 | Turnkey | May'26 | MR.Shubhangi Jadhav | Monte South | MUM - GOR | Yes | Sonal Singh | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Active | Design | DEM1 | 1260422 | 169732 | 1679318 | 0 | 0 | 36 | 0 | 0 | 82352 | 535920 | 472418 |  |  | 2026-05-09 | 2026-05-19 13:18 | 2026-05-23 | 2026-05-23 17:58 | 2026-05-29 | 2026-05-29 19:22 | 2026-08-03 |  | 2026-08-10 |  | 2026-08-17 |  | 2026-05-29 | 2026-05-31 | 2026-05-30 | 2026-06-03 15:40 | 2026-06-03 | 2026-06-09 14:16 | 2026-06-12 | 2026-06-12 16:14 |  |  |  |  | 2026-08-04 |  | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-07-30 |  | Unknown | 2026-05-09 | 2026-05-09 19:44 | 1423151 | 256167 | 0 | 0 | 0 | 0 | 1413006.2717 | 226876 | 2026-07-10 11:18:44 +0530 | Vishakha Vaishnav | TEHERE IS NO RESPONSE FROM CX END FOR THE DEM 1 MEETING TRIED CALLING HER EVEN DROPPED MESSAGE ON WHATSAPP | 2026-06-12 16:13:13 +0530 | Vishakha Vaishnav | "Welcome call done". Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - Cx will update us as cx is busy with her daughter college admission asked cx to update us 3 days prior for meeting DEM 2 - TBD DEM 3 - TBD Possession date : August Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-09 14:15:23 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: August 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible. * DEM 1 Next week * 10% Payment Stage 19th June 2026 *Client will take suggestions with designers and then think *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 14,13,007 Offers Discussed During the Call: PM fee waiver (7.5%) Free Bed Offer Design Fee Waiver (2.5%) Laminate Upgrade - May '26 Campaign Anniversary '26 Studio Offer: 30,000 100% GST Waiver Silver Coin 21g Final Closing Value Discussed: 12,60,422 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-08-04 |  | 2026-08-11 |  | Under Construction | 2026-08-01
19914 | Turnkey | May'26 | Jeeva Karunanithy | Brigade Sanctuary | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Preproduction | DEM2 | 1747909 | 359999 | 2303468 | 0 | 0 | 15 | 0 | 0 | 0 | 688746 | 699163.6 |  |  | 2026-05-08 | 2026-05-16 20:55 | 2026-05-15 | 2026-05-19 13:15 | 2026-05-25 | 2026-05-26 13:03 | 2026-07-03 | 2026-06-29 19:48 | 2029-01-05 |  | 2029-01-12 |  | 2026-05-26 | 2026-05-26 13:11 | 2026-05-27 | 2026-05-27 13:19 | 2026-05-27 | 2026-05-27 18:44 | 2026-05-31 | 2026-05-31 19:40 |  |  |  |  | 2026-06-30 | 2026-06-30 16:36 | 2029-01-07 |  | 2029-01-08 |  |  |  | 2029-01-15 |  | 2029-01-16 |  | 2029-01-17 |  | 2029-01-18 | [6 empty] | 2029-02-05 |  | 2029-02-14 |  | 2029-02-13 |  | 2029-02-14 |  | 2029-02-15 |  | 2029-02-17 |  |  |  | 2029-03-11 |  | 2029-03-13 |  | 2029-03-14 | [5 empty] | 2029-01-16 |  | 2026-06-01 | 2026-06-29 19:43 | Site is RTMI | 2026-05-08 | 2026-05-09 20:29 | 1952092 | 351376 | 0 | 0 | 0 | 0 | 1910161.381 | 314623 | 2026-05-27 18:43:58 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Under construction Completion Detail : December 2028 Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: Client don't want to move with the design meet. Client directly he wants to put the project on hold * 10% Payment Stage Client already done with 20% Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) 100% GST Waiver Design fee waiver (5%) Silver Coin 21g Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 17,47,910 Clinet VOC Client mentioned he doesn't want to move ahead. Directly, the client wants to put the Project on hold | 2026-05-27 16:51:43 +0530 | Athul Ajaykumar |  | 2026-05-27 13:49:04 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-06-30 | 2026-06-30 12:35 | 2029-01-06 |  | Under Construction | 2028-12-31
19915 | Turnkey | May'26 | Asim Kaul | SNN Raj | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 891582 | 178316 | 1414021 | 0 | 0 | 22 | 0 | 0 | 0 | 374417 | 338848.8 |  |  | 2026-05-09 | 2026-05-09 21:01 | 2026-05-10 | 2026-05-17 06:05 | 2026-05-20 | 2026-05-19 10:59 | 2026-06-19 | 2026-06-19 20:21 | 2026-08-08 |  | 2026-08-15 |  | 2026-05-19 | 2026-05-19 11:46 | 2026-05-20 | 2026-05-20 16:30 | 2026-05-20 | 2026-05-23 11:38 | 2026-06-04 | 2026-06-04 16:04 |  |  |  |  | 2026-06-19 | 2026-06-23 12:59 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-06-05 | 2026-06-19 20:15 | Site is RTMI | 2026-05-09 | 2026-05-09 21:00 | 1198323 | 215698 | 0 | 0 | 0 | 0 | 1050015.3702 | 173377 | 2026-06-19 18:58:29 +0530 | Sayed Byahatti | DDM1: ASIM KAUL (19/06/2026) - 5:30PM LIVING AREA - TV UNIT TO BE REMOVE,SOFA BACK WALL PUNING TO BE ADD. KIDS ROOM - REMOVE L-CORNER ADD 2SHUTTER WALL UNIT. MASTER BEDROOM - DRESSER MIRROR TO BE REMOVE ADD HEAD BOARD MIRROR WITH MDF BEADING. UTILITY - REMOVE LEGDS & WALL UNIT. | 2026-06-18 17:34:01 +0530 | Sayed Byahatti | DDM1: Asim Kaul - 19915 (18/06/2026) Kitchen - Remove bottle pullout, pantry unit to add accessories along with roller shutter. Add handwash in the corner. Bathrooms - Vanity unit to be add. | 2026-06-17 10:55:48 +0530 | Sayed Byahatti | DDM1: Asim Kaul - 19915 (17/06/2026) Kitchen - Entrance wall panels to be add as frame shared reference. -crockery unit to confirm add or not, rollerÂ Â Â shutter to add. -Fridge area to be covered with loft. Utility area - Add one shelf Master bedroom - wall panning design to be add, mirror to be shift right side of the bed. Kids room - Corner l-shape wall unit, wall panning to be remove. Â Â | 2026-06-20 | 2026-06-19 20:25 | 2026-08-09 |  | Under Construction | 2026-07-15
19916 | Turnkey | May'26 | Hima | Pelican white hill | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 2960768 | 9999 | 2960768 | 0 | 0 | 34 | 0 | 286078 | 296077 | 1294596 | 1074018 |  |  | 2026-05-09 | 2026-05-12 19:25 | 2026-05-17 | 2026-05-29 16:23 | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-13 |  | 2026-06-14 | [5 empty] | 2026-06-20 |  | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-06-15 |  | Unknown | 2026-05-09 | 2026-05-09 21:01 | 2509125 | 451642 | 0 | 0 | 0 | 0 | 2509125 | 451642 | 2026-06-11 12:22:55 +0530 | Priyamvada PV | Some Image was uploaded | 2026-05-28 18:29:23 +0530 | Pulivarthi Nirosha | Name-Hima & Ajesh Kid- 1 -15 years old- Advik Budget 20L possession- 9 months He is thinking of either giving it for rent or using it for his own purpose; nothing has been confirmed yet. We need to check both the quotations | 2026-05-17 19:28:33 +0530 | Priyamvada PV | Hima & Ajesh Pelican SquareÂ BHK : 4 BHKÂ Site access date : Need to check Property possession : Mostly 9 months Family members : 3-4 Adults Kids - Name & Age : 15 yr old Advik CDP date : only weekend Date : 30.05.26 2pm Budget : 20-25L including painting, modular furniture, wall concepts exclude loose furniture , appliances, lighting Preferences : Modern with touch of traditional (Need to share ref to chose the theme exactly) Scope of work : Shoe rackÂ Existing seating to be accommodated (need ref image of the same) Lift in Home office area Storage below staircase opening (Check if any) TV unit : Showcase to put trophies / medalsÂ Badminton/ TT / karateÂ Wall mounted storage (larger 1s) Back wall to be designed Sofa to be L shape (need to check door opening of courtyard entry) Existing lacquered glass sliding WRs) Need to check for Hinged WRs, share references for hinged & membrane (preferably handless doors) Blazers has to be fitted inside internals Vanity base storage Grid ceiling for the Vanity (need to check) Kitchen Base, wall & loft units Pantry storage Tall appliance unitÂ Appliances : OTG , Mixer, hob, rice cooker,DW, no wet grinder/MW, RO 6 seater dining table space Crockery unit , hand wash unit Check for hand wash near vanity (plumbing from builder) opening behind dining to be closed till Glass partition which can be blurred when not required for opening to be checked/other alternative options to be provided suggestion for chimney (ductless/duct to be suggested) references for under mount RO to be shared Builder is providing black granite Quartz to be added in BD scope SFÂ MBRÂ King size bed space L shape hinged WR with loft, dresser to be designed Headboard position to be checked Storage for linens, bedsheets Mirror in maain bedroom space TV placement WFH - so office setup as per floor plan position / some other area/other floor to be checked Pooja unit in lobby area - sitting pooja (Approx 4-5 frames, 1 idol) Ganesh/Krishna headboard wall to be designedÂ KBRÂ Queen size bed space L shape wardrobe with loft, dresser, bokshelf, study table theme (need to check with son Advik) on any particular preference study as per vastu headboard wall to be designedÂ (cot might be moved around), headboard wall design to be done accordingly till floor level Storage for linens, bedsheets (2-3 blankets) or can be accomodated in the cot Storage for school equipments movable study table (metal with wheels) to be shown Multipurpose room sofa cum bed, party room/ sports activity room Hinged wardrobe with loft for clothes/ storageÂ Vanity base storage for all vanities Utility :Â WM placement,base storage Store roomÂ Hinged wardrobe w/O loft Lobby wall design to be done Design for terrace & courtyard will be provided in design phase post onboarding. | 2026-06-20 |  | 2026-06-27
19917 | Turnkey | May'26 | MR. DEVENDRA D KALANTRE | Regency Luxeria | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1108081 | 9999 | 1108081 | 0 | 0 | 60 | 0 | 100809 | 110808 | 443232 | 443232.4 |  |  | 2026-05-09 | 2026-05-11 12:29 | 2026-05-13 | 2026-05-15 17:12 | 2026-05-17 | 2026-05-17 20:43 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-09 | 2026-05-11 12:28 | 939051 | 169029 | 0 | 0 | 0 | 0 | 939051 | 169029 | 2026-05-14 10:59:10 +0530 | Yerra Bharat | DCM: Site: Regency luxuria, Building 4, 506, 5th floor.Â Couple (In service supply chain & CA) + parents (60+ Both are Doctors)Â Kids after 1-2 years.Â Parents both travel for work, and couple are working, max no work from home situation.Â NO too many dark colors.Â Whites, Pastel colors, Greens.Â Has to be light, airy and calm.Â Existing Two Godrej wardrobes plans for guestroom.Â Kitchen Appliances.Â Wallpaper and wall concept is ok on Living room area only, No need for wall concepts in remaining room plain simple colors.Â The present house went to redevelopment, so will be shifting into this house for next 2years and later going to shift.Â Builder provided the false ceiling for the fire suppression system, no plans for false ceiling for whole house.Â Entry Foyer:Â safty doorÂ shierackÂ its going to be a functional foyer area.Â Pooja:Â wanted to be the highlight.Â Step style design, storage under it for storing pooja items.Â Platform at the front extendable to perform pooja during festival times.Â Bottom half as storage and will be doing pooja by sitting puffy style seating which can be stored under it.Â CNC door with design not a completely closed style.Â Living:Â Layered lighting planning to have chandelier also.Â L-shape sofa with one side resting style.Â Â 1 wing chairÂ Flating style TV unit with minimalistic storage for books.Â Centre table.Â Â Balcony attached to livingÂ Â one person swing,Â Â seating for 2 peopleÂ Covering for AC UnitÂ Â Dining:Â 6 people diningÂ Â crockery unit not a major requirement but needs idea if provided with no glass shutters.Â Kitchen:Â semi modular builder provided slabÂ Â Needed storage with loft .Â Has to the direction for the cook top.Â Beam in the kitchen above the fridge must be blended in the design.Â Need a tall pantry unit but no space in the kitchen want to explore the option to move the fridge into dining and pantry in its place. - need as an option.Â Balcony attached to kitchen UtilityÂ washing machineÂ Â storage solutionÂ Â need a second sink platform for maid to wash utensils.Â Sink in corridor outside common washroom: vanity unit.Â Common washroom vanity unit.Â Service slab has a service slab of waste height opp. To common washroom storage under the slab- might use for ironing.Â Guest Room: - bedroom 1:Â Two existing godrej wardrobes will be in this roomÂ Â study table Not like WFH setup kind of multipurpose table.Â No top storage needed.Â Sofa bedÂ Â Master bedroom: Bedroom 2 (parents bedroom):Â Near the door one storage unit. maybe one godrej unit here.Â Â Main wardrobe sliding with loft storageÂ No TV unit.Â No dressing table.Â Just a side tableÂ Â floor length mirror (tall)Â Â queen size bed.Â Attached washroom vanity unit.Â Ch. Bedroom Bedroom 3:Â Similar to master with storage behind the door space, sliding wardrobe with loftÂ Â Dressing tableÂ side tablesÂ queen size bedÂ No tv unit.Â In attached balcony simple sitting area.Â Vanity unit in the attached washroom.Â Â Need solution for drying clothsÂ Â Â Living room:Â Sofa darkÂ dining table top and center table top whitish, creme tones.Â Guestbedroom ivory white sky blue shades.Â Kitchen Dark green needed suggestions for the theme and color grading for the space. More towards darker colors because of the probability of oil stains.Â No constraints on design front open to suggestions.Â Rooms must look airy and lighter.Â In general colors selected -Â Â Parents room beige / Blush pinkÂ Â Ch. Bedroom lavender / ivory / princess purpleÂ considerin coffee color also.Â from client side but open to suggestions on colors. | [6 empty] | 2026-05-25 |  | 2026-06-01
19918 | Turnkey | May'26 | Vijay Kamble | Newa Bhakti park | MUM - Thane | Yes | [8 empty] | Saloni Chawan |  | Active | Prospect | 10% Payment | 3334987 | 9999 | 0 | 0 | 0 | 31 | 0 | 323500 | 333499 | 1424636 | 1243353.6 |  |  | 2026-05-09 | 2026-05-10 11:29 | 2026-06-06 | 2026-06-12 18:06 | 2026-06-15 |  | 2026-06-22 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-06-23 |  | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-18 |  | Unknown | 2026-05-09 | 2026-05-10 11:26 | 0 | 0 | 0 | 0 | 0 | 0 | 2826260 | 508726 | 2026-06-15 11:22:37 +0530 | Anant Giri | Some Image was uploaded | 2026-05-09 21:38:55 +0530 | Unknown | About the Customer **3BHK Inquiry with Budget** Customer Vijay inquired about interior design for his 3BHK flat, expecting possession in June/July, with a budget of 20-25 lakhs for a luxurious and aesthetic finish. **Agreed to Visit Experience Center** Customer Vijay agreed to visit experience centers in Thane or Andheri with his wife and will call back in 5-10 minutes to finalize a time. **WhatsApp Invite and Confirmation Pending** Agent Jagruti will send a personalized WhatsApp invitation with all details and requested Vijay to message back on WhatsApp to confirm the appointment. **Possession December, Prefers to Contact Later** Customer Vijay Kamble has a 3 BHK property, possession around December, and prefers to contact Bonito Designs later when he has more time. **Visit Availability and Reminder Request** Customer's possession expected August-September, move-in around December. Customer is available for a visit on the 9th or 10th, or potentially the 16th, and requested a reminder call on the 8th. |  |  |  | 2026-06-23 |  | 2026-06-30
19919 | Turnkey | May'26 | Isha Chhoker | DOSTI WEST COUNTY | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1907291 | 9999 | 0 | 0 | 0 | 61 | 0 | 180730 | 190729 | 762916 | 762916.4 |  |  | 2026-05-09 | 2026-05-12 19:05 | 2026-05-12 | 2026-05-12 19:07 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-09 | 2026-05-12 19:03 | 0 | 0 | 0 | 0 | 0 | 0 | 1616348 | 290942 | 2026-05-11 13:32:04 +0530 | Maasoumeh Raza | Some Image was uploaded | [6 empty] | 2026-05-24 |  | 2026-05-31
19920 | Turnkey | May'26 | Ajay kumar singh | N.G Grand Plaza | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-09 | 2026-05-09 23:38 | 2026-05-10 |  | 2026-05-11 |  | 2026-05-18 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-05-11 |  | 2026-05-12 |  | 2026-05-12 |  | 2026-05-13 | [5 empty] | 2026-05-19 |  | 2026-05-27 |  | 2026-05-28 |  |  |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-07 | [6 empty] | 2026-06-25 |  | 2026-07-04 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-07 |  |  |  | 2026-07-29 |  | 2026-07-31 |  | 2026-08-01 | [5 empty] | 2026-06-05 |  | 2026-05-14 |  | Unknown | 2026-05-09 | 2026-05-09 22:53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-09 22:53:04 +0530 | Unknown | About the Customer **Customer Property Details** Customer Ajay is looking to get interiors done for a 2 BHK property in Ghansoli, Navi Mumbai. The property was taken on resale and has been vacated by the previous tenant. **Budget Discussion Blocked** Customer is hesitant to provide a budget, stating the company should guide him on pricing. Agent mentioned a starting price of â‚¹10 lakh for a 2 BHK. **Timeline and Vacancy Confirmation** Customer can keep the house empty until December and wants work completed within three to six months. Agent informed about the 60-90 day delivery timeline. **Confirmed Appointment Details** Customer Ajay confirmed a pickup for 10:30 AM with two family members attending. **Customer Action for Pickup** Customer needs to send a WhatsApp message when ready for pickup. | [6 empty] | 2026-05-19 |  | 2026-05-26
19921 | Turnkey | May'26 | Jani Gada | Kalpatru garden | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 2423441 | 9999 | 2423441 | 0 | 0 | 55 | 0 | 232345 | 242344 | 1071017 | 867736 |  |  | 2026-05-09 | 2026-05-19 12:34 | 2026-05-19 | 2026-05-21 11:31 | 2026-05-22 | 2026-05-22 21:11 | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-05-09 | 2026-05-10 10:30 | 2056051 | 367390 | 0 | 0 | 0 | 0 | 2056051 | 367390 | 2026-05-23 12:25:23 +0530 | Aryan Singh | Some Image was uploaded | 2026-05-22 21:11:34 +0530 | Yerra Bharat | CDP: There are civil changes that needs to be finalized and made the modifications to the model depending on how they wanted it to be with suggestions from our side on space planning. In the CDP before discussion on quote, the client mentioned about her experience with bonito while booking that she wanted to cancel and return of the booking amount after looking at google reviews. But she had trouble getting in touch with the exact person who can answer her. and later got to know its nonrefundable, she lost interest in the company after-support system. Said how can I go with the company which is having tougher channels to get in touch. Explained how things are evolving and how we work, CRM's manager explained the whole process and clients' experiences in detail and process every project goes through. Clients' Family asked for time at least 8days. | 2026-05-19 20:30:09 +0530 | Yerra Bharat | CDP Update: CDP planned for 22nd Friday 3PM.Â | 2026-05-30 |  | 2026-06-06
19922 | Turnkey | May'26 | P R A C H I Dudani | Aaradhya One By MICL | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Hold | Preproduction | DEM2 | 1226601 | 245320 | 1226601 | 0 | 0 | 7 | 35 | 0 | 0 | 522654 | 458627.2 |  |  | 2026-05-09 | 2026-05-19 20:15 | 2026-05-14 | 2026-05-20 15:20 | 2026-05-20 | 2026-05-20 15:56 | 2026-05-24 | 2026-05-24 21:36 | 2026-06-17 | 2026-06-16 14:16 | 2026-07-27 |  | 2026-05-20 | 2026-05-21 18:28 | 2026-05-21 | 2026-05-22 11:31 | 2026-05-22 | 2026-05-22 11:48 | 2026-05-24 | 2026-05-24 15:47 |  |  |  |  | 2026-05-24 | 2026-05-29 19:08 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-05-25 | 2026-05-24 19:21 | Site is Non-RTMI | 2026-05-09 | 2026-05-10 14:23 | 1316777.2335 | 218089 | 0 | 0 | 0 | 0 | 1316777.2335 | 218089 | 2026-06-23 15:03:45 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-16 13:19:50 +0530 | Batskhem Marpna | Minutes of Meeting held on Date: Note:Â - Kitchen two color combination to be decided after sharing renders - Same for MBR and GBR - Sharing Mandir options from BonitoÂ - renders to be shared. | 2026-06-03 17:15:47 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-25 | 2026-05-24 21:39 | 2026-06-17 | 2026-06-16 14:17
19923 | Turnkey | May'26 | Thirumalesh r | sai ragavendhra tiara | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP |  | RaviKumar Battala | Deekshith P | Jairam Joshi |  | Muralikrishna Udupi | Vishwa Hiremath | Active | Preproduction | Hoto | 1639091 | 272232 | 2063902 | 1639091 | 0 | 1 | 0 | 0 | 0 | 769500 | 597358.8 |  |  | 2026-05-09 | 2026-05-13 15:06 | 2026-05-13 | 2026-05-16 21:00 | 2026-05-19 | 2026-05-18 13:49 | 2026-06-13 | 2026-06-13 15:45 | 2026-07-04 | 2026-07-03 14:46 | 2026-07-15 | 2026-07-14 19:05 | 2026-05-18 | 2026-05-19 11:36 | 2026-05-19 | 2026-05-22 13:35 | 2026-05-22 | 2026-05-23 14:59 | 2026-05-31 | 2026-05-31 19:33 |  |  |  |  | 2026-06-13 | 2026-06-15 16:02 | 2026-07-06 | 2026-07-03 12:24 | 2026-07-04 | 2026-07-03 13:49 |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-16 |  | 2026-06-01 | 2026-06-13 15:42 | Site is RTMI | 2026-05-09 | 2026-05-10 13:54 | 1749069 | 314832 | 1772977.0529 | 292742 | 0 | 0 | 1772977.0529 | 292742 | 2026-05-23 14:58:10 +0530 | Sanjana Swami | Client mentioned that site is not accessible, so 1st DEM can be done next weekends on the basis of layouts | 2026-05-23 11:11:23 +0530 | Sanjana Swami |  | 2026-05-23 10:53:00 +0530 | Muralikrishna Udupi | Explained Client clearly on timeline and he is okay with it. | 2026-06-14 | 2026-06-13 15:48 | 2026-07-04 | 2026-07-03 14:51 | Under Construction | 2026-06-10
19924 | Turnkey | May'26 | Deepak Nandkumar moris | Dosti Mezzo | MUM - GOR | Yes | Priyanka Murarka | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Nivesh Gupta |  | Hold | Preproduction | Site Readiness 1 | 1767586 | 353517 | 2344564 | 0 | 0 | 9 | 32 | 0 | 0 | 770096 | 643972.8 |  |  | 2026-05-09 | 2026-05-14 12:54 | 2026-05-13 | 2026-05-20 12:36 | 2026-05-24 | 2026-05-24 18:48 | 2026-06-21 | 2026-06-21 15:58 | 2026-08-07 |  | 2026-08-14 |  | 2026-05-24 | 2026-05-24 17:48 | 2026-05-25 | 2026-05-26 00:23 | 2026-05-26 | 2026-05-26 16:56 | 2026-05-27 | 2026-05-27 13:19 |  |  |  |  | 2026-06-20 | 2026-06-21 14:20 | 2026-08-09 |  | 2026-08-10 |  |  |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 | [6 empty] | 2026-09-07 |  | 2026-09-16 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-19 |  |  |  | 2026-10-11 |  | 2026-10-13 |  | 2026-10-14 | [5 empty] | 2026-08-18 |  | 2026-06-15 | 2026-06-21 15:56 | Site is Non-RTMI | 2026-05-09 | 2026-05-11 12:56 | 1986919 | 357645 | 0 | 0 | 0 | 0 | 1972300.4454 | 318165 | 2026-07-02 19:19:10 +0530 | Vishakha Vaishnav | Others: CX HAS NOT YET RECEVIED THE POSSESSION | 2026-06-23 12:01:27 +0530 | Priyanka Murarka | DDM1: 21 JUNE Kids room Window seating with 1 tall unit on left side Study table with wardrobe Loft to be made end to end Single bed Parents room Queen bed Wardrobe internal finalized with 1 trouser pullout accessory 1 side table with mirror storage wall unit MBR Queen bed Sliding wardrobe 1 side table with mirror storage wall unit Tv provision to be provided Ac pelmet Drawers below tv unit sleek KITCHEN Fridge & tall unit to be on opposite sides Microwave unit - next to fridge - wall hung open unit Sliding door to be provided for kitchen door Kitchen - in depth discussion will happen post the measurements are done for better clarity of verticals provided by builder. LIVING ROOM Mandir to be custom made as per design which would be selected Entrance partition above the shoe rack - not included in the estimate Glass Tall unit next to mandir on left side Wall decors, false ceiling designs to be finalized in the next meeting. Zoning & furniture layout along with modular internals has been finalized. | 2026-06-09 15:28:22 +0530 | Priyanka Murarka | On call discussion - 9th June TV & sofa to be interchanged - opposite wall Stove on the opposite side of platform wherein the civil work is taken care by client. sons room to have full single wardrobe instead of side table with mirror for important documents Mandir to be full length & on the corner side. IM is not yet done Possession - July end MEETINGS TO BE DONE ON SUNDAYS MORNING ONLY. | 2026-06-22 | 2026-06-23 12:05 | 2026-08-08 |  | Under Construction | 2026-06-30
19925 | Turnkey | May'26 | sachin | NCC nepolite | BNG - HSR | Yes | Preksha Sajjanshettar | Akshay Ds | Soumya KP | [5 empty] | Aman Kumar |  | Active | Preproduction | DEM2 | 816554 | 196099 | 960986 | 0 | 0 | 8 | 0 | 0 | 0 | 296618 | 323836.8 |  |  | 2026-05-10 | 2026-05-10 12:31 | 2026-05-19 | 2026-05-19 18:13 | 2026-05-24 | 2026-05-27 09:44 | 2026-06-19 | 2026-06-19 19:37 | 2026-07-01 | 2026-06-30 18:21 | 2026-07-09 |  | 2026-05-24 | 2026-05-26 18:43 | 2026-05-28 | 2026-05-27 15:51 | 2026-05-27 | 2026-05-28 18:43 | 2026-06-06 | 2026-06-06 17:23 |  |  |  |  | 2026-06-19 | 2026-06-21 14:32 | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-07 | 2026-06-16 11:08 | Site is RTMI | 2026-05-10 | 2026-05-10 12:30 | 814395 | 146591 | 0 | 0 | 0 | 0 | 890123.406 | 146979 | 2026-07-04 15:26:02 +0530 | Preksha Sajjanshettar | 1. Demolition - Bonito scope - Foyer area - Wall mount shoe rack - Living - TV Unit - Wall panel, base units - Kitchen - Base unit, Wall unit, Loft and Granite - Utility - Granite and Loft 2. Things retained by Client - Kitchen - Chimney, corner unit mechanism, sink with drain board and Wall tiles - Utility - Sink and Wall tiles - Dining - Handwash unit - Bedroom 1 and 2 - Entire furniture 3. Bonito Scope of Work - Foyer - Shoe rack with wall concept(Beading and Rafters) - Living - TV Unit - Base unit with wall concept(Beading and Rafters) - Sofa back wall concept(Beading) - Kitchen - Base unit, Wall unit, Loft and Granite - Utility - Granite and Base unit (YET TO CONFIRM BY CLIENT) - Master bedroom - Wardrobe and loft 4. Client Scope of Work - Electrical -Shifting and addition of electric points - Paint - ON beadings, Rafters and full house - Plumbing - Shifting of Gas pipeline motor - If possible | 2026-06-30 18:14:34 +0530 | Preethi Shetty | Some Image was uploaded | 2026-06-30 18:13:10 +0530 | Preethi Shetty | Some Image was uploaded | 2026-06-20 | 2026-06-19 19:38 | 2026-07-01 | 2026-06-30 18:22 | RTMI
19926 | Turnkey | May'26 | Suresh | 3bhk independent house | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 2863450 | 9999 | 0 | 0 | 0 | 63 | 0 | 276346 | 286345 | 1257938 | 1032821.6 |  |  | 2026-04-25 | 2026-05-13 15:35 | 2026-05-10 | 2026-06-23 13:23 | 2026-05-13 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-04-25 | 2026-05-12 13:53 | 0 | 0 | 0 | 0 | 0 | 0 | 2426652 | 436797 | 2026-05-13 11:45:33 +0530 | Muralikrishna Udupi | Clients Budget-20-25L mentioned in Gross table. | 2026-05-12 19:21:42 +0530 | Gayathri Krishna | Cx name :Â Suresh B.N & Mamtha Address: IP villaÂ Profession :Â Medical % constructionÂ Possession :Â Already handed overÂ How many people will be staying : 4Â Theme : luxury contemporaryÂ Â Entrance facing :NE facingÂ Budget : 15-20L Correction in plan which is marked and all room height is 12' Entrance foyer- Need POP work panelling as markedÂ Need shoe rack of 900mm infront of POP work as a consoleÂ Living room- TV unit with base unit and back panel - check reference image (Wall is double height) Sofa back wall - wallpaper is also fine- cx will refer image (Wall is double height) Kitchen - Builder is providing the counter topÂ Double door fridgeÂ Gas pipe is there - no cylinder unitÂ Tall unit for OTGÂ HOB and sink position marked as per planÂ Island kitchen needed and only L shape counter to be providedÂ Base, wall (no loft) Kitchen window is coming on dado areaÂ MRB - Plan changes to be considered (golden, maroon and beige ) Wardrobe on 20' wall as marked with centre long mirror with dresser storageÂ need centre curved partition front on wardrobe and place 2 arm chairs as markedÂ King size bed as markedÂ Window position changedÂ First FloorÂ DBR- (Sushmitha) Plan changes to be considered (Bridgeton theme ) Need niche round seating next to entrance to washroom Need sliding door to Walk in wardrobeÂ Need long mirror on 1 shutter of wardrobeÂ Give solid and open wardrobe combinationÂ Need separate dressing table with proper storageÂ study table next to entrance doorÂ Second Floor SBR - (Abijith) Plan changes to be considered (rustic theme ) Sliding door to entrance of walk in as markedÂ Â Walk in wardrobe coming with dresser similar to DBR in balcony wallÂ Study table as per marked in planÂ Bay window coming oppo to door (no storage , consider in 3D) Need simple 3D for Home theatreÂ False ceiling - Need for MBR and SBR (consider MBR design as per furniture layout)Â CDP- 13th MayÂ |  |  |  | 2026-07-04 |  | 2026-07-11
19927 | Turnkey | May'26 | Anand V | OTHERS | BNG - HRBR | Yes | [10 empty] | Active | Prospect | 10% Payment | 1339053 | 9999 | 0 | 0 | 0 | 59 | 0 | 123906 | 133905 | 556648 | 514594.8 |  |  | 2026-05-10 | 2026-05-16 10:46 | 2026-05-12 | 2026-05-16 11:07 | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-10 | 2026-05-10 22:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1134791 | 204262 | 2026-06-06 16:01:37 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-14 16:35:33 +0530 | Rhea Rathod | DCM: 1BHKÂ Serene amara Possession - 15th may Theme - minimalist , modern Light colours spacious Vastu oriented West facing Family of 2 (son visits often) False ceiling - full house Centralised air conditioner Foyer - - Mirror with seating - Shoe rack with the seating Kitchen- - Fridge - single door - Sink and dishwasher - U shaped kitchen - Breakfast counter - for 3 - Wall units and loft - Oven spacing to be checked and planned - Under sink RO - Granite - to be provided Living area- - Sleek tv unit - suspended - spacious look - 65 " - Pooja unit to be planned as per vastu - 3 seater - Leather sofa - tan colour - Wall concept - Vanity unit with mirror Master Bedroom - - L shaped wardrobe with bay window seater - Study with dresser with drawersÂ - King size bed - leather - Wall concept Washrooms - - Vanity unit - Tall unit - Mirror Balcony -Â - Washer and dryerÂ - DesignÂ |  |  |  | 2026-06-07 |  | 2026-06-14
19928 | Turnkey | May'26 | Raghuveer Anad | Divine Green Leaf | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Hold | Preproduction | DEM2 | 1203428 | 234000 | 1568859 | 0 | 0 | 9 | 6 | 0 | 0 | 503812 | 465616.4 |  |  | 2026-05-10 | 2026-05-10 13:55 | 2026-05-10 | 2026-05-13 12:20 | 2026-05-17 | 2026-05-19 11:09 | 2026-06-21 | 2026-06-21 15:56 | 2026-10-16 |  | 2026-10-23 |  | 2026-05-19 | 2026-05-20 12:16 | 2026-05-20 | 2026-05-21 12:01 | 2026-05-21 | 2026-05-22 17:42 | 2026-05-31 | 2026-05-31 12:45 |  |  |  |  | 2026-06-21 | 2026-06-30 16:39 | 2026-10-18 |  | 2026-10-19 |  |  |  | 2026-10-26 |  | 2026-10-27 |  | 2026-10-28 |  | 2026-10-29 | [6 empty] | 2026-11-16 |  | 2026-11-25 |  | 2026-11-24 |  | 2026-11-25 |  | 2026-11-26 |  | 2026-11-28 |  |  |  | 2026-12-20 |  | 2026-12-22 |  | 2026-12-23 | [5 empty] | 2026-10-27 |  | 2026-06-06 | 2026-06-21 13:35 | Site is RTMI | 2026-05-10 | 2026-05-10 13:55 | 1329542 | 239317 | 0 | 0 | 0 | 0 | 1300160.9818 | 216617 | 2026-06-28 18:10:41 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-28 17:48:41 +0530 | Parasa Sri | Hold till October 15th | 2026-06-21 21:26:37 +0530 | Yogesh B | Some Image was uploaded | 2026-06-22 | 2026-06-21 15:59 | 2026-10-17 |  | Under Construction | 2026-05-31
19929 | Turnkey | May'26 | Chetan Surve | ajmera boulevard | MUM - GOR | Yes | Priyanka Murarka | Reshma Melanta | Shantanu Parakh | [5 empty] | Manasi Patil |  | Lost | Design | 20% Payment | 1100818 | 112227 | 1122273 | 0 | 0 | 24 | 35 | 0 | 107937 | 467428 | 413226.4 |  |  | 2026-05-10 | 2026-05-10 19:23 | 2026-05-10 | 2026-05-10 19:31 | 2026-05-10 | 2026-05-10 19:57 | 2026-05-17 | 2026-05-17 13:26 | 2026-07-01 |  | 2026-07-08 |  | 2026-05-13 | 2026-05-10 19:31 | 2026-05-11 | 2026-05-14 12:51 | 2026-05-14 | 2026-05-14 13:56 | 2026-05-16 | 2026-05-16 12:48 |  |  |  |  | 2026-05-17 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-05-17 | 2026-05-17 13:25 | Site is RTMI | 2026-05-10 | 2026-05-10 19:22 | 953366 | 168906 | 0 | 0 | 0 | 0 | 1145610.2094 | 190040 | 2026-06-14 18:12:11 +0530 | Shahid Chougley | CX Chetan Surve (19929) is currently not responding to our calls. We have also sent him a text message and are awaiting a response. The NET for this project was completed on 14 May 2026, with an estimated project value of 8,78,031.92. During the NET stage, we clearly communicate to all clients that the quoted amount is not the final project cost. The final costing is determined during the PKO stage, and clients are advised to keep a contingency buffer of 710%, even if there are no scope changes. In this case, during the very first DEM meeting, the client requested multiple design modifications, which resulted in a cost escalation of approximately 1,58,825. We have made several attempts to explain the impact of these design changes and the associated increase in project cost. However, the client has not been receptive to understanding the process and is currently not responding to our calls or messages. | 2026-05-28 12:59:00 +0530 | Reshma Melanta | Some Image was uploaded | 2026-05-26 17:26:21 +0530 | Reshma Melanta | NOT ANSWERING THE CALL | 2026-05-18 | 2026-05-17 13:34 | 2026-07-02 |  | RTMI
19930 | Turnkey | May'26 | Marrisa Mascarenhas Pinto | Sajay Avenue 18 | MUM - GOR | Yes | Neha Yadav | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Manasi Patil |  | Active | Preproduction | DEM2 | 852019 | 171025 | 1125797 | 0 | 0 | 48 | 0 | 0 | 0 | 344018 | 336976 |  |  | 2026-05-09 | 2026-05-15 13:06 | 2026-05-16 | 2026-05-16 19:38 | 2026-05-19 | 2026-05-17 12:30 | 2026-05-28 | 2026-05-28 15:10 | 2026-08-07 |  | 2026-08-14 |  | 2026-05-16 | 2026-05-16 19:35 | 2026-05-18 | 2026-05-18 11:54 | 2026-05-18 | 2026-05-18 14:01 | 2026-05-19 | 2026-05-19 18:30 |  |  |  |  | 2026-05-28 | 2026-05-28 19:03 | 2026-08-09 |  | 2026-08-10 |  |  |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 | [6 empty] | 2026-09-07 |  | 2026-09-16 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-19 |  |  |  | 2026-10-11 |  | 2026-10-13 |  | 2026-10-14 | [5 empty] | 2026-08-18 |  | 2026-05-20 | 2026-05-28 14:18 | Site is RTMI | 2026-05-09 | 2026-05-15 13:05 | 954065 | 171731 | 0 | 0 | 0 | 0 | 946430.0335 | 153363 | 2026-07-14 11:47:57 +0530 | Vishakha Vaishnav | CX MENTIONED ON CALL THAT SHE HAS NOT YET RECEVIED THE POSSESSION SHE WILL CONFIRM IN DAY OR TWO WHEN SHE WILL GET THE POSSESSION AFTER THAT ONLY CROSS MEASUREMENT CAN BE DONE NEED TO KEEP THE PROJECT ON HOLD | 2026-05-28 15:47:23 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-28 14:15:40 +0530 | Neha Yadav | DDM1 Meeting Discussion: 1)Master room -Loft need to add above brether unit 2)MB- need to add shelf in hanging space in wardrobe one side 3)2Drawer need to add next sink unit 4) TV will be 43 in living room 5)2 fan in living room and chandeli in center 6)Texture paint on tv wall 7)Lock need to add in shoe unit *Ac pelmet, safety door , kitchen counter change & refurbishment need to done by cx. Feel free to add pointers if missed any. | 2026-05-29 | 2026-05-28 15:12 | 2026-08-08 |  | Under Construction | 2026-06-30
19931 | Turnkey | May'26 | PRANAV D MEHTA | Grandeur | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Design | 20% Payment | 806060 | 99222 | 992215 | 0 | 0 | 3 | 0 | 0 | 61990 | 383404 | 261444 |  |  | 2026-05-10 | 2026-05-10 14:15 | 2026-05-10 | 2026-05-10 22:54 | 2026-05-17 | 2026-05-18 17:00 | 2026-07-12 | 2026-07-12 19:00 | 2026-12-17 |  | 2026-12-24 |  | 2026-05-18 | 2026-05-20 18:39 | 2026-05-19 | 2026-05-21 14:33 | 2026-05-21 | 2026-05-21 17:07 | 2026-05-24 | 2026-05-24 16:15 |  |  |  |  | 2026-07-12 |  | 2026-12-19 |  | 2026-12-20 |  |  |  | 2026-12-27 |  | 2026-12-28 |  | 2026-12-29 |  | 2026-12-30 | [6 empty] | 2027-01-17 |  | 2027-01-26 |  | 2027-01-25 |  | 2027-01-26 |  | 2027-01-27 |  | 2027-01-29 |  |  |  | 2027-02-20 |  | 2027-02-22 |  | 2027-02-23 | [5 empty] | 2026-12-28 |  | 2026-05-25 | 2026-07-12 16:06 | Site is RTMI | 2026-05-10 | 2026-05-10 14:14 | 840860 | 151354 | 0 | 0 | 0 | 0 | 840860.4626 | 145090 | 2026-07-10 15:03:50 +0530 | Vishakha Vaishnav | DEM 1 IS ALIGNED FOR 12 JULY BY 12 | 2026-06-18 12:41:16 +0530 | Vishakha Vaishnav | The customer would like to proceed with the interior work at a different property. He has requested a meeting on Sunday at 11:30 AM to discuss the project and the next steps. | 2026-06-03 16:49:43 +0530 | Vishakha Vaishnav | Cx said that he is busy for this week he can come for the meeting in next week only have asked the cx to inform 1-2 days prior | 2026-07-13 | 2026-07-12 19:33 | 2026-12-18
19932 | Turnkey | May'26 | K Mahipal Reddy | Nirmaanika Aria | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Preproduction | Site Readiness 1 | 1275651 | 255130 | 1549711 | 0 | 0 | 7 | 0 | 0 | 0 | 525727 | 494793.6 |  |  | 2026-05-10 | 2026-05-12 19:33 | 2026-05-13 | 2026-05-13 13:07 | 2026-05-22 | 2026-05-22 17:18 | 2026-06-20 | 2026-06-20 18:26 | 2026-09-05 |  | 2026-09-12 |  | 2026-05-22 | 2026-05-22 17:51 | 2026-05-23 | 2026-05-23 13:50 | 2026-05-23 | 2026-05-23 16:16 | 2026-05-26 | 2026-05-26 15:11 |  |  |  |  | 2026-07-07 | 2026-07-08 17:35 | 2026-09-07 |  | 2026-09-08 |  |  |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 | [6 empty] | 2026-10-06 |  | 2026-10-15 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-18 |  |  |  | 2026-11-09 |  | 2026-11-11 |  | 2026-11-12 | [5 empty] | 2026-09-16 |  | 2026-05-27 | 2026-06-20 18:22 | Site is Non-RTMI | 2026-05-10 | 2026-05-12 19:29 | 1313314 | 236396 | 0 | 0 | 0 | 0 | 1363243.0151 | 225099 | 2026-07-14 15:50:03 +0530 | Akshay Ds |  | 2026-06-25 17:10:38 +0530 | Akshay Ds | Payment delayed as customer need to arrange the money, customer mentioned that he will pay by monday | 2026-06-17 11:13:33 +0530 | Sayed Byahatti | DDM1: MAHIPAL REDDY - 19932 (16/0/2026) Pooja unit - Beading design in traditional way & shared reference for pooja unit. parents photo frame for plan wall opposite to dining area reference, fire work kind below the photo frame. wall papers kind design traditional kind. Living area -Shared reference wooden beading kind design & Venkateshwara Kalyan wallpaper or else wall painting frame. Master bedroom - Remove this panning add painting or wall papers kind of design, beside this dresser unit to be add, designer mirror kind design. Children's bedroom - chilrens kind of theme room design. Working area or study area -wallpaper world kind of or kids kind of theme for wall. | 2026-06-21 | 2026-06-20 18:30 | 2026-09-06 |  | Under Construction | 2026-07-10
19934 | Turnkey | May'26 | Nakul Kulkarni | Kalpataru vivant | MUM - GOR | Yes | Neha Yadav | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Manasi Patil |  | Hold | Preproduction | DEM2 | 1349120 | 269824 | 1902080 | 0 | 0 | 9 | 13 | 0 | 0 | 552784 | 526511.6 |  |  | 2026-05-10 | 2026-05-15 13:09 | 2026-05-21 | 2026-05-21 15:35 | 2026-05-24 | 2026-06-01 11:01 | 2026-06-23 | 2026-06-23 14:32 | 2026-09-06 |  | 2026-09-13 |  | 2026-05-24 | 2026-05-31 18:35 | 2026-06-02 | 2026-06-04 14:50 | 2026-06-04 | 2026-06-08 14:10 | 2026-06-10 | 2026-06-10 16:16 |  |  |  |  | 2026-06-16 | 2026-06-21 20:04 | 2026-09-08 |  | 2026-09-09 |  |  |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 | [6 empty] | 2026-10-07 |  | 2026-10-16 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-19 |  |  |  | 2026-11-10 |  | 2026-11-12 |  | 2026-11-13 | [5 empty] | 2026-09-17 |  | 2026-06-11 | 2026-06-23 14:19 | Site is RTMI | 2026-05-10 | 2026-05-14 17:44 | 1611932 | 290147 | 0 | 0 | 0 | 0 | 1588691.175 | 255891 | 2026-07-02 13:54:46 +0530 | Vishakha Vaishnav | Others: Cx will receive the possession till august end after that only IM can be done hence kept the project on hold | 2026-06-23 14:14:23 +0530 | Neha Yadav | DDM 1 Meeting Discussion: 1)Kitchen Dish drainer needs to add 2)Bedrooms wardrobe internal has to redesign by adding drawers. 3)Living passage entrance need to do curve Feel free to add pointers if missed any. | 2026-06-10 16:15:16 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : SIte is not accessible DEM Dates -Â DEM 1 - can be done on weekends only cx is available for the meeting on 14th June need to check with designer DEM 2 - TBD DEM 3 - TBD Possession date : October 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-24 | 2026-06-23 14:33 | 2026-09-07 |  | Under Construction | 2026-06-08
19935 | Turnkey | May'26 | sandeep | 3 bedroom independent home | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 3594780 | 9999 | 0 | 0 | 0 | 66 | 0 | 349479 | 359478 | 1438995 | 1436828.8 |  |  | 2026-05-10 | 2026-05-10 16:11 | 2026-05-10 | 2026-06-02 11:39 | 2026-05-24 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-06-13 |  | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-08 |  | Unknown | 2026-05-10 | 2026-05-10 16:08 | 0 | 0 | 0 | 0 | 0 | 0 | 3046423 | 548356 | 2026-06-02 11:48:17 +0530 | Saranya Thiyagarajan | The client is a referral lead, he would like to make the payment after his friend completes their payment. Since his friend is currently out of town, there is a delay in moving forward. The client's friend has also requested a visit to one of our ongoing/completed project sites before confirming. As discussed, once his friend returns, visits the site, and proceeds with the payment, the client is also expected to come forward with his payment and project confirmation. | 2026-06-02 11:43:56 +0530 | Saranya Thiyagarajan | CDP: living- tv with gypsum with wood finish design Living chest drawers area- add Tanjore paint existing from client for reference pooja- ht- 1.5 ft and small traditional pillars on side and check feasibility for sit and do pooja- 2 ppl hob side crockery remove and add partition remove tandem under hob and add seating stool add roller shutter on utility utility- wet kitchen- move tall unit to right end and extend utility kids-window- half bay seating- corner- create arch niche with seating extend study table till the end of frames MBR- L shape wardrobe- aristo wardrobe mbr- sliding door open only on main door sideÂ wooden ceiling - island ceiling on all bedrooms garbage crusher to be considered | 2026-06-02 11:40:50 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-13 |  | 2026-06-20
19936 | Turnkey | May'26 | Sakshat Mhatre | Midtown bay Prescon | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  |  | Nilesh Patel | Rizwan Mistry |  | Anant Giri | Prasad Bhivaji Hande | Active | Design | DEM3 | 2504973 | 516999 | 3060583 | 0 | 0 | 1 | 0 | 0 | 0 | 1082684 | 905289.6 |  |  | 2026-05-10 | 2026-05-10 20:20 | 2026-05-26 | 2026-05-26 13:08 | 2026-05-31 | 2026-05-31 17:15 | 2026-06-24 | 2026-06-23 15:06 | 2026-07-15 | 2026-07-14 10:28 | 2026-07-20 |  | 2026-05-31 | 2026-05-31 20:52 | 2026-06-01 | 2026-05-31 21:21 | 2026-05-31 | 2026-06-08 10:59 | 2026-06-23 | 2026-06-23 14:35 |  |  |  |  | 2026-07-05 | 2026-06-23 14:33 | 2026-07-15 | 2026-07-12 22:59 | 2026-07-13 | 2026-07-14 08:02 |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-07-23 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-06-24 | 2026-06-23 14:48 | Site is RTMI | 2026-05-10 | 2026-05-10 20:19 | 2593715 | 466868 | 0 | 0 | 0 | 0 | 2557863.8996 | 450895 | 2026-07-02 13:04:10 +0530 | Naved Malik | Cross Measurement aligned for 12th July | 2026-06-13 19:29:00 +0530 | Naved Malik | Some Image was uploaded | 2026-06-08 10:44:18 +0530 | Anant Giri | Some Image was uploaded | 2026-06-29 | 2026-06-23 18:30 | 2026-07-15 | 2026-07-14 10:30 | RTMI
19937 | Sub Project |  | Marshal Lopes | Applaud 38 | MUM - GOR |  | Shweta Dalvi |  | Safalta Karkera |  |  |  |  | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-10 | 2026-05-27 12:17 | 2026-05-11 | 2026-05-27 12:17 | 2026-05-27 | 2026-05-27 12:17 | 2026-05-28 | 2026-05-27 12:18 | 2026-05-28 | 2026-05-27 12:20 | 2026-05-28 | 2026-05-27 12:21 | 2026-05-27 | 2026-05-27 12:18 | 2026-05-28 | 2026-05-27 12:18 | 2026-05-27 | 2026-05-27 12:18 | 2026-05-28 | 2026-05-27 12:18 |  |  |  |  | 2026-05-27 | 2026-05-27 12:18 | 2026-05-28 | 2026-05-27 12:20 | 2026-05-28 | 2026-05-27 12:20 |  |  | 2026-05-28 | 2026-05-27 12:22 | 2026-05-28 | 2026-05-27 17:34 | 2026-05-28 | 2026-05-27 17:39 | 2026-05-28 | 2026-05-27 12:23 |  |  |  |  | 2026-05-27 16:39 | 2026-05-30 | 2026-05-30 13:26 | 2026-06-01 | 2026-05-30 15:55 | 2026-05-31 |  | 2026-05-30 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-05-27 | 2026-05-27 17:39 | 2026-05-28 | 2026-05-27 12:18 | Unknown | 2026-05-10 | 2026-05-27 12:17 | 0 | 0 | 0 | 0 | 49999 | 0 | 49999 | 0 | [9 empty] | 2026-05-28 | 2026-05-27 12:18 | 2026-05-28 | 2026-05-27 12:20
19938 | Turnkey | May'26 | nikhil Chandran | Samarth aura | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1568739 | 9999 | 0 | 0 | 0 | 66 | 0 | 146875 | 156874 | 641643 | 613348 |  |  | 2026-05-10 | 2026-05-10 20:28 | 2026-05-10 | 2026-05-11 16:44 | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-10 | 2026-05-10 20:27 | 0 | 0 | 0 | 0 | 0 | 0 | 1329440 | 239299 | 2026-05-16 20:44:24 +0530 | Anant Giri | Some Image was uploaded | 2026-05-12 13:25:23 +0530 | Hitesh Rawal | Some Image was uploaded |  |  |  | 2026-05-24 |  | 2026-05-31
19939 | Turnkey | May'26 | Soaid | Independant House | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 4120976 | 9999 | 0 | 0 | 0 | 49 | 0 | 402099 | 412098 | 1667495 | 1629286 |  |  | 2026-05-10 | 2026-05-12 13:28 | 2026-05-19 | 2026-05-19 18:43 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-06-04 |  | 2026-06-12 |  | 2026-06-13 |  |  |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-06-21 |  | 2026-05-30 |  | Unknown | 2026-05-10 | 2026-05-12 13:22 | 0 | 0 | 0 | 0 | 0 | 0 | 3492352 | 628623 | 2026-05-19 18:42:10 +0530 | Ehthisham Durgam | DCM: Minutes of Meeting (MOM)Client Name: Soaid Akhtar Project Type: Builder Residence Floors Discussed: Third, Fourth & Fifth Floor Meeting Agenda: Interior planning and space requirements 15 to 20L Fourth FloorLiving AreaNo TV unit required.A round window to be provided.Bench seating to be placed in front of the round window.Lift lobby wall to feature a console table setup.Full house false ceiling required.Dining Area6-seater dining arrangement planned.Crockery unit to be provided on the bedroom-side wall along with a hand wash area.KitchenMembrane finish to be used.Dry kitchen to be positioned on the left side.Wet kitchen to be positioned on the right side.Island hob included in the layout.Utility area required.Fifth FloorNamaz room with low seating arrangement.Open hall space planned for outsiders/guests.Third FloorBedroomsWardrobes required in all bedrooms.No study tables required.False ceiling to be provided in all rooms.Master BedroomBunk bed planned for kids.Additional NotesClient will share reference images/design inspirations for the discussed spaces.Detailed design development will proceed after receiving references | 2026-05-10 16:43:21 +0530 | Unknown | About the Customer **Property Details and Previous Visit** Customer has a 4 BHK duplex independent house in Kogilu Cross, with plastering done and planning to start interiors. They previously visited the HBR experience center two years ago. **Undecided Interior Budget** Customer has not yet decided on a budget for the interiors. **Hesitation for Experience Center Visit** Customer is hesitant to visit the experience center again, preferring a site visit first, but agent is pushing for the experience center visit to discuss the anniversary offer (18% off GST waiver). **Confirmed Visit Details** Confirmed visit for 3:00 PM today, with family participation. Agent will call at 2:30 PM to confirm location and visit. Two-way cab facility accepted. **Follow-up Call Scheduled** Agent will call back in two hours, around 12:30 PM IST, to continue the discussion. |  |  |  | 2026-06-04 |  | 2026-06-11
19940 | Turnkey | May'26 | Mrs. Vidya Rajesh Salvi | Asher arise | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1228308 | 245662 | 1489978 | 0 | 0 | 2 | 41 | 0 | 0 | 554682 | 427964.4 |  |  | 2026-05-10 | 2026-05-11 12:28 | 2026-05-10 | 2026-05-12 14:59 | 2026-05-17 | 2026-05-19 11:56 | 2026-06-02 | 2026-06-02 19:11 | 2026-08-04 |  | 2026-08-11 |  | 2026-05-17 | 2026-05-17 15:43 | 2026-05-20 | 2026-05-19 16:10 | 2026-05-19 | 2026-05-21 12:35 | 2026-05-22 | 2026-05-22 16:07 |  |  |  |  | 2026-06-09 | 2026-05-31 14:34 | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-06-04 | 2026-06-02 19:00 | Site is Non-RTMI | 2026-05-10 | 2026-05-11 12:27 | 1264938 | 225039 | 0 | 0 | 0 | 0 | 1264938.4482 | 218445 | 2026-07-09 12:05:23 +0530 | Rachna Abhyankar | IM schedule 11th july | 2026-06-30 13:54:57 +0530 | Preet Karania | Some Image was uploaded | 2026-06-18 18:35:18 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-03 | 2026-06-02 19:17 | 2026-08-05
19941 | Turnkey | May'26 | Prita Dey | Sri balaji | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 3249204 | 9999 | 0 | 0 | 0 | 66 | 0 | 314921 | 324920 | 1299682 | 1299681.6 |  |  | 2026-05-10 | 2026-05-10 18:06 | 2026-05-10 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-10 | 2026-05-10 18:05 | 0 | 0 | 0 | 0 | 0 | 0 | 2753563 | 495641 | 2026-05-10 20:14:49 +0530 | Priyamvada PV | Name : Jaideep Roy, Prita RGM date : 10.05.26 CDP date : 16.05.26 2pm Property : Shree Balaji Urban retreat Location : Sarajapur (opp to Azim Premji Uni) From : Assam Residing in BloreÂ Family members :Â Jyaan (4 yrs boy) Sie access date : Sep'26 Only foundation done Site possession date : Sep'26 Budget : 30L including lighting & wall concepts excluding loose furniture, appliances Scope of work : Beige, cream, highlights of teal, golden accents Wooden textures (not darker shades) can be used GFÂ MBR is GBRÂ Â Queen size bed, side table Sliding WR with loft Plain FC in GBRÂ Living :Â End to end French door to left of sofa L shape sofa TV unit floating , wall paneling for back side till ceiling open tall unitÂ simple dining table with Italian marble top (medium shade) 4 seater Utility :Â ceiling covered for utility, half wallÂ Need a wash basin mop storageÂ pantry storageÂ (need to check) DW & sink unitÂ Dish drainer No crockery unit Sliding partition for Kit entry (sleeker designs preferred) Kitchen :Â single bowl sink (bigger smart sink) placement under mount RO Appliances : Mixer, built in MW, fryer Side by side fridge Mixer pullout mechanism need to be checked then pantry unitÂ Tall unit with appliancesÂ Base cabinets in U shape Granite by builder only for L shape provided Chimney panel above hob area, loft in sink area No loft near tall unit area Foyer wall opp to door to be highlighted, ganesha/ radha krishna idol/paintingÂ Entry left wall with paneling & mirror Shoe rack outside (approx. 20 pairs) (Design element to be done not just boxes) Staircase - need a partition (glass) bottom has to be with fountain (Design option ) LED lit staircasesÂ FF MBR - L walk-in closet with sliding partition, dresser to be integrated along with WR King size bedÂ Wardrobe in seater section (Aristo glass option) Other option is having tall units on either sides with chest of drawers in between No TV unit high chair in WR area in floor plan corner window on right side of pillar next to balcony door back wall to be highlighted Vanity in 2 bathrooms hinged shower partition in 2 vanities KBR walk-in closet, dresser inside queen size murphy bed (hydraulic) with storage placement back wall to be highlightedÂ Space themeÂ Study table (with toy storage)Â wall climbing & play deck design to be done No TV unit centre living wall with paneling (Family portrait with console) fancy modern A reading nook to be done for library/bookshelfÂ Pooja back wall with stone sculpture & idol (As per ref image) Need storage inside pooja area the glass door (for pooja separation) to be done from BD scope as builder is not doing it Wall opp to sofa can have wall art Staircase wall (design suggestions to be provided) TF :Â Servant room Hinged wardrobeÂ Utility extend till back, servant vanity entry from right Utility will have WM space, ironing, storage Home theatre (home theatre concept) Projector on op wall murphy bed on screen wall, 2 recliners bar unit on left wall Vanity storage Office - simple office setup with 1 chair False ceiling for MBR, KBR, HT Room Decorative items like mirrors, or custom made designs, home theatre fabric panelings estimation will be provided in design phase as per accurate designs | 2026-05-10 18:04:30 +0530 | Unknown | About the Customer **Customer Property and Budget Details** Customer Preeta has a 4BHK villa in Sarjapur with possession expected in January/February and a budget of 25-30 lakh. **Hesitation on Design Process and Fees** Customer is hesitant to commit to a visit without understanding the design process and potential revisions, and seeks clarity on the â‚¹9999 fee. **Process and Offer Explanation Provided** Agent explained the design process, including a free initial consultation, a â‚¹9999 fee for 3D renders with a refund policy, and highlighted the GST waiver offer. **Tentative Visit Confirmation** Customer agreed to visit the HSR Layout experience center on Saturday, needs to confirm exact time via WhatsApp or phone call. **Follow-up on Visit Time Confirmation** Confirm exact visit time via WhatsApp or phone call after this call. |  |  |  | 2026-05-24 |  | 2026-05-31
19942 | Turnkey | May'26 | Harikha Hema | Nivara Viento | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 2316013 | 9999 | 0 | 0 | 0 | 56 | 0 | 221602 | 231601 | 969584 | 883226.8 |  |  | 2026-05-10 | 2026-05-12 13:28 | 2026-05-15 | 2026-05-19 14:10 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-05-10 | 2026-05-12 13:22 | 0 | 0 | 0 | 0 | 0 | 0 | 1962722 | 353290 | 2026-05-15 15:21:22 +0530 | S S Sri Akshita | DCM: Client -HemaÂ Date - 10-05-2026 Property - Nivara Vinto - Rajankunte , YelahankaÂ kids - couple & 2 kidsÂ guest - senior roomÂ budget - 20 lakhsÂ move in - August endÂ Possesion - already haveÂ height - 11'Â False ceiling - minimalÂ living and mbr - experiment with the designÂ no gaps or stepsÂ Kitchen - breakfast counterÂ sink shifted towards bf counterÂ hobÂ tall unit - pantryÂ fridge granite - blackÂ microwaveÂ dishwasher - under the stairsÂ foyer - FROM THE green line (extended than in the plan) - 5'*4' shoe rack with seating to accommodate more pairs with accent wall Living - tv unit , pooja wall shifted to living (NE corner) pooja unit with doors - sittin poojaÂ highlight wallÂ Guest bedroom - Wardrobe & mirrorÂ existing bed (wood - walnut color) side tablesÂ highlight wallÂ vanity unitÂ kids bedroom - wardrobeÂ bunk bed - furniture to be included in the quotationÂ study unit - foldableÂ kids themeÂ girl and boy - 7& 2 Family living - window seatingÂ study - work spaceÂ Balcony - design has to be plannedÂ Incase swing is eliminated from the main living would prefer to accommodate in the balcony (FF)Â Master Bedroom -Â king bed & side tables - to be includedÂ mirror to be plannedÂ dresserÂ - mirror to be concealed or panelledÂ walk in wardrobe - L shapeÂ benchÂ master bath - vanity and shower partitionÂ kids - vanity and showerÂ colors - lighter shadesÂ no green color in the houseÂ browns kids - lavender and blues - check for floral - no wallpaperÂ Terrace -Â pergola - glassÂ seating - externalÂ sink with storage - for get togethersÂ only walls and flooring along - existingÂ terracotta to be added in the interiors . | 2026-05-10 18:15:42 +0530 | Unknown | About the Customer **Designs finalized, ready for production** Customer has finalized 3D designs and measurements for their property in Niwara Vinto, Yelakhanka Rajankunte, and is ready to start factory work this month. **Seeking quotation, design concerns** Customer is seeking a quotation and is concerned about design feasibility for specific elements like full curves. **Experience center visit confirmed for tomorrow** Customer agreed to visit the experience center tomorrow around 3:30 PM or 4:00 PM. **Budget â‚¹15-20 Lakhs** Customer's budget is between â‚¹15-20 Lakhs. **Agent to confirm visit via WhatsApp** Agent to send WhatsApp confirmation for the visit. |  |  |  | 2026-05-30 |  | 2026-06-06
19943 | Turnkey | May'26 | Pragya Bharti | Rohan Ekanta | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Hold | Preproduction | Site Readiness 1 | 701686 | 140619 | 886422 | 0 | 0 | 3 | 51 | 0 | 0 | 280393 | 280674.4 |  |  | 2026-05-10 | 2026-05-10 18:34 | 2026-05-13 | 2026-05-14 19:08 | 2026-05-17 | 2026-05-17 22:55 | 2026-05-31 | 2026-05-31 20:24 | 2026-10-05 |  | 2026-10-12 |  | 2026-05-17 | 2026-05-18 00:19 | 2026-05-18 | 2026-05-19 11:56 | 2026-05-19 | 2026-05-19 14:07 | 2026-05-22 | 2026-05-22 17:10 |  |  |  |  | 2026-05-26 | 2026-05-22 16:50 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-05-23 | 2026-05-22 18:56 | Site is Non-RTMI | 2026-05-10 | 2026-05-10 18:34 | 751205 | 135217 | 0 | 0 | 0 | 0 | 741521.5426 | 126303 | 2026-06-03 13:17:24 +0530 | Priyanka Mathur | Some Image was uploaded | 2026-05-31 19:40:11 +0530 | Priyanka Mathur | Client don't want any design meeting as possession in next year. This is informed to client and updated the same. | 2026-05-26 17:15:41 +0530 | Vishal Haridas | As design meeting is not done, we are not closing the task | 2026-06-01 | 2026-05-31 20:27 | 2026-10-06 |  | Under Construction | 2026-09-02
19945 | Turnkey | May'26 | Pramod Dangaich | Mantri Serinity | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1511518 | 9999 | 1511518 | 0 | 0 | 59 | 0 | 141153 | 151152 | 631546 | 577668 |  |  | 2026-05-10 | 2026-05-10 18:43 | 2026-05-11 | 2026-05-15 18:33 | 2026-05-17 | 2026-06-11 22:06 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-10 | 2026-05-10 18:42 | 1283234 | 228283 | 0 | 0 | 0 | 0 | 1283234 | 228283 | 2026-05-15 19:03:27 +0530 | Yash Jain | DCM: client also mentoined sofa and beds are existing with them, and can be used | 2026-05-11 15:50:57 +0530 | Yash Jain | DCM: Notes Cx Pramod - (harshen) bottom - east side 2bhk 676 sq ftÂ 4 occupants - couple and 2 daughters - 18yrs and 14yrs. possession - rtmi (renovation) location -Â vastu compliant house room sizes would be same Kitchen- all outer box to be included in all rooms. entire renovation. parallel,all three level of storages.new platform. pantry -Â Living room sofa seating - 3+2 = 5 seating, dining table, seating - in niche , duct to be taken inside -Â tv size - 60 inches tv on kitchen wall.Â dining table - 4 seater. minimal less furniture, storage ,temple on bigger sharing flat wall. bedroom 1-Â 1 qsb, wardrobe, mirrors, study table foldable. Master bedroom -Â 1 qsb, wardrobe, mirrors,small tv wall mounted , dressing unit besides bed. vanity unit, bathrooms. Colours - minimal white, gold ,ivory , beige, nude colours, green light, sober , bright colours. theme - rafter, mirror , metal patti.Â fc eletricial , painting . Budget - 12L - 13L |  |  |  | 2026-06-19 |  | 2026-06-26
19946 | Turnkey | May'26 | Prakash Mulchand Jain | Monte South | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | DCM Due | 1854505 | 9999 | 0 | 0 | 0 | 57 | 0 | 175452 | 185451 | 789024 | 694580 |  |  | 2026-05-10 | 2026-05-19 13:21 | 2026-05-11 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-10 | 2026-05-10 19:03 | 0 | 0 | 0 | 0 | 0 | 0 | 1573713 | 280792 | 2026-05-16 09:17:42 +0530 | Rahul Agrawal | DCM: Client Name: Prakash Mulchand Jain Project Location: 2BHK, Monte South Possession: Approx. next week Family Members: 4 members Parents: Real estate agent & housewife (h.w.) Husband & Wife (Couple): CA (Husband) & Teacher (Wife) CDP Meeting: 17th May, Sunday at 4:30 PM Budget: 10 Lakhs DCM Budget: 13 Lakhs Living Room Shoe rack requirement. L-shape sofa cum bed on the short wall. Opposite wall: TV unit cum mandir. L-shape dining seating. Note: Light house tone; sofa and dining seating "pop-up." Kitchen Structural: Break two entrance walls. Storage: Make both walls a crockery unit (show option with slide). Layout/Components: * Includes Fridge, Platform (Pf.), and Washing Machine (W.M.). Base + Top + Loft storage. No Chimney. Passage Shift door ahead and add sleek storage there. Bedroom (Parents) Size: 11'2" \times 10'3" Queen size bed. Wardrobe with loft. Storage: Extra storage with fluted glass. Dressing: Mirror inside. Master Bedroom Layout includes Wardrobe (W), Side Table (ST), Bed, and TV unit. Book storage requirement. Soft civil work mentioned. | [6 empty] | 2026-06-07 |  | 2026-06-14
19947 | Turnkey | May'26 | Prem Dalvi | Kohinoor eden | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  | Deepa kamboj | Asif Shaikh | Aditya Vikram |  | Anant Giri | Shailendra Mishra | Active | Preproduction | Site Readiness 2 | 718001 | 476781 | 880063 | 0 | 718001 | 4 | 7 | 0 | 0 | 0 | 241220 |  |  | 2026-05-10 | 2026-05-10 20:26 | 2026-05-11 | 2026-05-11 13:23 | 2026-05-11 | 2026-05-11 13:57 | 2026-06-19 | 2026-06-19 13:03 | 2026-06-24 | 2026-06-23 17:34 | 2026-06-24 | 2026-06-24 16:51 | 2026-05-11 | 2026-05-11 16:19 | 2026-05-12 | 2026-05-11 20:10 | 2026-05-11 | 2026-05-14 11:54 | 2026-05-16 | 2026-05-16 11:39 |  |  |  |  | 2026-06-20 | 2026-06-23 17:22 | 2026-06-24 | 2026-06-23 19:48 | 2026-06-24 | 2026-06-23 19:49 |  |  | 2026-06-26 | 2026-06-29 21:07 | 2026-06-30 | 2026-06-30 14:27 | 2026-07-10 | 2026-06-30 17:15 | 2026-07-15 | 2026-07-11 13:23 | [5 empty] | 2026-07-19 |  | 2026-07-28 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-31 |  |  |  | 2026-08-22 |  | 2026-08-24 |  | 2026-08-25 | [5 empty] | 2026-06-30 | 2026-07-05 12:03 | 2026-05-17 | 2026-05-22 14:39 | Site is RTMI | 2026-05-10 | 2026-05-10 19:40 | 745816 | 134246 | 0 | 0 | 858042.2514 | 135091 | 858042.2514 | 135091 | 2026-07-12 10:39:04 +0530 | Amisha Ahuja |  | 2026-06-28 22:01:09 +0530 | Amisha Ahuja | Some Image was uploaded | 2026-06-28 21:37:36 +0530 | Amisha Ahuja | Some Image was uploaded | 2026-06-20 | 2026-06-20 19:08 | 2026-06-24 | 2026-06-23 17:38
19948 | Turnkey | May'26 | Abhishek Pandey | Kalpavriksha Garden | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1585102 | 24999 | 0 | 0 | 0 | 57 | 0 | 133511 | 158510 | 719290 | 548792 |  |  | 2026-05-10 | 2026-05-10 21:09 | 2026-05-14 | 2026-05-16 12:23 | 2026-05-19 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-08 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-10 | 2026-05-10 21:07 | 0 | 0 | 0 | 0 | 0 | 0 | 1344859 | 240243 | 2026-06-02 12:26:32 +0530 | Foram Joshi | Some Image was uploaded | 2026-05-22 18:43:24 +0530 | Anjali Singh | CDP: NO BAY WINDOW IN PARENTS. SMALL MIRROR IN CX SCOPE IN PARENTS. SOFA CUM BED IN LIVING.Â LIGHTS IMP.Â -try IndianÂ -TV placement can be changed according to 55" or 65" | 2026-05-17 11:14:51 +0530 | Anjali Singh | Some Image was uploaded | 2026-05-27 |  | 2026-06-03
19949 | Turnkey | May'26 | Sanket Sali | 49 Simandhar Royal | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 2462223 | 9999 | 0 | 0 | 0 | 34 | 0 | 236223 | 246222 | 984889 | 984889.2 |  |  | 2026-05-10 | 2026-05-10 21:40 | 2026-05-13 | 2026-05-19 11:52 | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-06-21 |  | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-08-02 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-27 |  | 2026-09-01 |  |  |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-07-08 |  | 2026-06-16 |  | Unknown | 2026-05-10 | 2026-05-10 20:25 | 0 | 0 | 0 | 0 | 0 | 0 | 2735824.821 | 451750 | 2026-07-05 17:53:34 +0530 | Aryan Singh | Receipt | 2026-05-28 18:17:14 +0530 | Aakriti Parmar | Some Image was uploaded | 2026-05-23 11:53:35 +0530 | Maasoumeh Raza | DCM: Member: 5 member Possession : June mid Quote : 15 to 20L modular [30L with civil work] ENTRANCE / FOYER Shoe rack storage for approximately 2025 pairs. Safety door to be considered. Entrance foyer/console area should feel aesthetic and welcoming, not storage-heavy. Passage area outside the door belongs to the clients space. LIVING ROOM L-shaped living layout. Flexible seating arrangement for around 8 people including guests. Sofa-cum-bed to be considered. 65-inch TV unit required. Dining seating to integrate comfortably with living space. MANDIR AREA Open mandir in the north-east corner as per Vastu. Seating space for sitting and praying comfortably. Platform height around 22.5 feet. Decorative designer wall treatment without storage. Mandir width approximately 33.5 feet. KITCHEN Side-by-side double-door refrigerator. Oven, mixer, juicer, dishwasher, chimney, and hob required. Pantry unit and crockery unit to be included. Appliance storage unit to be planned. Kitchen layout to be designed from scratch. Ceiling and beam treatment to be integrated aesthetically. Possibility of additional storage/island near dining area. DINING AREA Flexible dining arrangement connected with living room. Additional storage below dining/island area if possible. KIDS / GUEST BEDROOM Multi-functional room for child and guests. Trundle/pull-out bed or convertible bed arrangement. Wardrobe with loft storage. Study table and play area required. Design should be modern and timeless with subtle playful/kids elements. Adjustable furniture options for future flexibility. IN-LAWS BEDROOM Bed and full-height wardrobe with loft storage. Maximum storage depth preferred. Room expansion option to be explored by adjusting common bathroom layout. OVERALL HOUSE REQUIREMENTS Entire house to have new furniture and interiors. False ceiling, painting, and electrical work included. Space planning is the key focus due to compact layout. Multiple theme and design references to be shared before finalization. Civil/plumbing scope to be reconfirmed internally. Move-in target around Diwali. Next detailed presentation and space-planning meeting scheduled for 24th at 11 AM. | 2026-06-21 |  | 2026-06-28
19950 | Turnkey | May'26 | Sana Idris khokar | Roswalt Zaiden | MUM - GOR | Yes | Saakshi Bhute | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Nivesh Gupta |  | Hold | Preproduction | DEM2 | 1065298 | 213060 | 1439283 | 0 | 0 | 0 | 18 | 0 | 0 | 467775 | 384462.8 |  |  | 2026-05-10 | 2026-05-14 12:53 | 2026-05-14 | 2026-05-14 20:11 | 2026-05-17 | 2026-05-19 18:09 | 2026-06-24 | 2026-06-20 15:52 | 2026-07-21 |  | 2026-07-28 |  | 2026-05-19 | 2026-05-20 11:25 | 2026-05-20 | 2026-05-20 11:30 | 2026-05-20 | 2026-05-23 14:42 | 2026-05-26 | 2026-05-26 13:32 |  |  |  |  | 2026-06-20 | 2026-07-08 15:59 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-05-27 | 2026-06-20 15:48 | Site is RTMI | 2026-05-10 | 2026-05-12 18:10 | 1219732 | 219551 | 0 | 0 | 0 | 0 | 1216498.4494 | 198953 | 2026-07-03 16:34:33 +0530 | Vishakha Vaishnav | Others: | 2026-06-27 11:49:01 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-24 15:59:12 +0530 | Vishakha Vaishnav | Cx said that she will speak to developer about the possession , as cx is asking for the price protection till April / may however we have approval till Dec 2026. | 2026-06-21 | 2026-06-20 15:52 | 2026-07-22 |  | Under Construction | 2026-12-01
19951 | Turnkey | May'26 | Jayshree Munde | Adani - The Views | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam | [5 empty] | vinaya thakur |  | Active | Design | DEM1 | 1025172 | 145000 | 1440779 | 0 | 0 | 54 | 0 | 0 | 60034 | 410069 | 410068.8 |  |  | 2026-05-10 | 2026-05-10 21:16 | 2026-05-14 | 2026-05-15 12:08 | 2026-05-17 | 2026-05-17 20:30 | 2026-07-13 |  | 2026-07-20 |  | 2026-07-27 |  | 2026-05-17 | 2026-05-17 22:27 | 2026-05-18 | 2026-05-19 12:54 | 2026-05-19 | 2026-05-22 12:17 | 2026-06-10 | 2026-06-10 13:26 |  |  |  |  | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-11-01 |  | 2026-11-02 | [6 empty] | 2026-11-20 |  | 2026-11-29 |  | 2026-11-28 |  | 2026-11-29 |  | 2026-11-30 |  | 2026-12-02 |  |  |  | 2026-12-24 |  | 2026-12-26 |  | 2026-12-27 | [5 empty] | 2026-07-31 |  | 2026-06-11 |  | Unknown | 2026-05-10 | 2026-05-10 21:15 | 1220999 | 219779 | 0 | 0 | 0 | 0 | 1200106.292 | 191730 | 2026-06-26 16:37:47 +0530 | Shraddha Pansare | The project will go on hold post DEM 1. The project will be on hold till October | 2026-06-25 18:11:31 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-06-11 16:23:51 +0530 | Shraddha Pansare | Some Image was uploaded | 2026-07-14 |  | 2026-07-21
19953 | Turnkey | May'26 | Rahul Sachan | Adarsh Tropica | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1318391 | 261216 | 1802978 | 0 | 0 | 12 | 0 | 0 | 2462 | 552380 | 502333.2 |  |  | 2026-05-10 | 2026-05-10 21:47 | 2026-06-14 | 2026-06-14 13:46 | 2026-06-28 | 2026-06-30 13:32 | 2026-07-14 |  | 2026-11-05 |  | 2026-11-12 |  | 2026-06-30 | 2026-06-30 16:05 | 2026-07-01 | 2026-07-02 15:53 | 2026-07-02 | 2026-07-03 12:52 | 2026-07-09 | 2026-07-09 16:29 |  |  |  |  | 2026-07-15 |  | 2026-11-07 |  | 2026-11-08 |  |  |  | 2026-11-15 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 | [6 empty] | 2026-12-06 |  | 2026-12-15 |  | 2026-12-14 |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-18 |  |  |  | 2027-01-09 |  | 2027-01-11 |  | 2027-01-12 | [5 empty] | 2026-11-16 |  | 2026-07-10 |  | Unknown | 2026-05-10 | 2026-05-10 21:46 | 1527948 | 275030 | 0 | 0 | 0 | 0 | 1488994.8967 | 245860 | 2026-07-03 12:51:19 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: October 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible * DEM 1 â€“ Client will let us know (after 1st DEM) * 10% Payment Stage â€“ 12th July 2026 *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin Offer May'26 laminate Campaign PM fee waiver (5%) Design fee waiver (5%) May'26 100% GST waiver Free Shoerack Offer Free Hob & Chimney Offer Final Closing Value Discussed: â‚¹ 13,18,391 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-03 11:59:44 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-02 17:33:06 +0530 | Sanjana Swami | CB | 2026-07-15 |  | 2026-11-06 |  | Under Construction | 2026-10-30 | 2026-06-28 | 261216 | Ravi Roy
19954 | Turnkey | May'26 | Vipra | Modern Spaaces | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik |  |  | Nanda Kumar | Ranjith Kumar |  | Nidhi Shaw |  | Active | Preproduction | DEM2 | 3276841 | 661540 | 4615400 | 0 | 0 | 21 | 0 | 0 | 0 | 1310286 | 1305014.8 |  |  | 2026-05-10 | 2026-05-10 21:44 | 2026-05-13 | 2026-05-21 20:54 | 2026-05-24 | 2026-05-26 13:30 | 2026-06-22 | 2026-06-22 12:18 | 2026-08-08 |  | 2026-08-15 |  | 2026-05-26 | 2026-05-26 14:42 | 2026-05-27 | 2026-05-29 13:59 | 2026-05-29 | 2026-05-29 18:24 | 2026-06-05 | 2026-06-05 17:14 |  |  |  |  | 2026-06-23 | 2026-06-24 17:55 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-06-06 | 2026-06-22 12:15 | Site is RTMI | 2026-05-10 | 2026-05-10 21:43 | 3911356 | 704044 | 0 | 0 | 0 | 0 | 3856922 | 694246 | 2026-06-22 12:46:33 +0530 | Kiran Agarampalli | Ground Floor: Entrance: Mirror will be readymade Living: Back panel for TV unit with curved edges and pendant lightfalse ceiling curved on beam sidesofa back wall to accommodate 8' sofastaircase bottom unit, flap down shutters and pebble bed fullyPooja unit on kitchen entrance left side, 1.5' depth 2.5' wide pocket door pooja unit with pullout stool and cnc shuttersKitchen: Additional 3 drawer cutlery unit right to hobnext to fridge 300mm and 150mm bottle pulloutnext to fridge microwave to be on the wall unitAdd loft on the HOB sideBreakfast counter side 300mm depth, Move wicker basket next to sink cabinetL corner cabinet on the cornerremove 2 drawers tandem and add single shutter unitRight side of window single shutter fluted glass unitUtility: Dish drainer above sink Left side- cabinet for mixer, air fryeradd one pullout tray for that unitGuest Bedroom: Plan for Robo vacuum position on left side of bedExternal drawers wardrobe till ceilingAdd pullout hangersPeripheral false ceiling First Floor: Master Bedroom: Bed Headboard wall with curved design, Curved Dresser with storage and mirrorAdd used cloths unit behind doorExternal drawers wardrobeHidden drawer and hidden storage MBR Toilet: Closed wall unit with storage left side of mirrorBottom drawers on right sideleft side open box without shelf Kids Bedroom: Walkin Wardrobe entrance both side storage Right side- next to toilet door dresser unit 450mmexternal drawers wardrobeLeft side wardrobe- Aristo wardrobe/ Hettich sliding KBR Toilet: Closed wall unit with storage left side of mirrorBottom drawers on right sideleft side open box without shelf Study Room: Check for Curved door with arch on topRemove Countertop- Readymade unit CX is buyingStorage for documents requiredPainting concept and design with interesting concept 2Nd Floor: AV Room planned in future External drawer full height wardrobe Terrace: Right side washing machine space Laundry bin storage | 2026-06-16 13:09:37 +0530 | Kiran Agarampalli | Discussion on 06.06.26 Ground Floor: Parking: Entire wall shoe rack unit, Bottom open unit with sliding out panel for daily wear.left corner tall unit for tools storage, right side seating unit as per ref in group. space between wall unit and bottom unit add mirror entrance left wall tinted mirror Living: DB box to be covered with carpentry shutters, right side wall ledge to be added with curved edges Sofa back wall design to be done from sliding door beam drop in the living to be Designed Below staircase- pebble bed design with seating in the corner with wall ledges for books Dining double height wall design Pooja Unit to be placed on left or right side of kitchen (need 2 options) Kitchen: Fridge placement on the left side. Breakfast counter storage to have wicker basket Above sink wall cabinets to be fluted glass All wall cabinets in the kitchen to have profile lights with sensor. Add skirting lights in the kitchen utility corner space need to place tall pantry unit Utility 1' counter with wall units for Mixer, toaster for 2' length Sink and dish washer to be planned as per site condition, add dishdrainer unit above the sink Common Vanity: to be design as per the referenceGuest Bedroom: Headboard wall to have texture paint, mirror and pendant light Curtain AC pelmet on the right-side window wall Dresser to be followed with bay seater followed by curved study table in the corner, as per the reference. Space after study unit will be fully wardrobe Behind the door wardrobe to have pullout hangers for used cloths First Floor:(Discussion as per site visit) KBR: Wardrobe to be in the Walkin space2 single cot to be used(no bunker bed) Vanity to have wall storage and bottom storage with big mirror balcony loft to be closed with frame and shutter MBR: Right side to door to be created like a walk in wardrobe space Dresser to be placed next to bed headboard. Custom Dresser, curved mirror with back storage Lift back space: 1. Workstation setup on the left wall, door to be included to the room | 2026-05-29 18:24:52 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-06-23 | 2026-06-23 19:55 | 2026-08-09 |  | Under Construction | 2026-06-06
19955 | Turnkey | May'26 | YOGESH DHANAVADE | Risland Icon | MUM - Thane | Yes | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar | [5 empty] | Vandana Preet |  | Hold | Design | DEM1 | 1125219 | 234999 | 1507832 | 0 | 0 | 5 | 13 | 0 | 0 | 440132 | 450087.6 |  |  | 2026-05-10 | 2026-05-10 21:55 | 2026-06-11 | 2026-06-20 12:06 | 2026-06-23 | 2026-06-20 21:19 | 2027-01-05 |  | 2027-01-12 |  | 2027-01-19 |  | 2026-06-20 | 2026-06-22 18:46 | 2026-06-21 | 2026-06-23 13:00 | 2026-06-23 | 2026-06-27 12:55 | 2026-12-31 | [5 empty] | 2026-07-04 | 2026-06-28 17:07 | 2027-01-14 |  | 2027-01-15 |  |  |  | 2027-01-22 |  | 2027-01-23 |  | 2027-01-24 |  | 2027-01-25 | [6 empty] | 2027-02-12 |  | 2027-02-21 |  | 2027-02-20 |  | 2027-02-21 |  | 2027-02-22 |  | 2027-02-24 |  |  |  | 2027-03-18 |  | 2027-03-20 |  | 2027-03-21 | [5 empty] | 2027-01-23 |  | 2027-01-01 |  | Unknown | 2026-05-10 | 2026-05-10 21:50 | 1277823 | 230008 | 0 | 0 | 0 | 0 | 1266957.1196 | 211089 | 2026-06-27 12:54:24 +0530 | Sanjana Swami |  | 2026-06-27 12:51:11 +0530 | Vandana Preet | Some Image was uploaded | 2026-06-24 14:51:45 +0530 | Bency Chacko |  | 2027-01-06 |  | 2027-01-13 |  | Under Construction | 2027-02-01 | 2026-06-20 | 158283 | Ravi Roy
19956 | Turnkey | May'26 | Karthikeyan L & Subha | Rohan Ekanta | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Preproduction | Site Readiness 1 | 784144 | 157406 | 1114136 | 0 | 0 | 15 | 0 | 0 | 0 | 333636 | 293102.4 |  |  | 2026-05-10 | 2026-05-10 21:46 | 2026-05-22 | 2026-05-22 23:06 | 2026-05-25 | 2026-05-26 11:38 | 2026-07-01 | 2026-06-30 18:09 | 2026-09-06 |  | 2026-09-13 |  | 2026-05-23 | 2026-05-25 18:26 | 2026-05-27 | 2026-05-28 19:00 | 2026-05-28 | 2026-05-30 11:37 | 2026-06-06 | 2026-06-06 17:26 |  |  |  |  | 2026-06-30 | 2026-06-30 20:28 | 2026-09-08 |  | 2026-09-09 |  |  |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 | [6 empty] | 2026-10-07 |  | 2026-10-16 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-19 |  |  |  | 2026-11-10 |  | 2026-11-12 |  | 2026-11-13 | [5 empty] | 2026-09-17 |  | 2026-06-07 | 2026-06-30 16:47 | Site is Non-RTMI | 2026-05-10 | 2026-05-10 21:44 | 944183 | 169953 | 0 | 0 | 0 | 0 | 919385.2286 | 153174 | 2026-07-14 15:16:53 +0530 | Akshay Ds |  | 2026-07-14 15:07:55 +0530 | Kowshik | Site will be ready by Sep for IM | 2026-05-30 11:36:20 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: September 2026 Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Client has asked us to coordinate with the builder and then come for IMs. * DEM 1 6th June 2026 * 10% Payment Stage already paid 20% Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 9,19,386. Offers Discussed During the Call: Special Offer (40000) Special Offer (20000) Modular - Windows to Wonderful home Services - Windows to Wonderful Home PM fee waiver (5%) Design Fee Waiver (4%) Silver Coin 21g Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 7,84,144. Checklist terms - descoping, delay compensation, agreement terms are clear Extra commitments - nothing | 2026-07-01 | 2026-06-30 19:28 | 2026-09-07 |  | Under Construction | 2026-09-01
19957 | Turnkey | May'26 | Naitik furia | 49 Simandhar Royal | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 1485787 | 9999 | 0 | 0 | 0 | 66 | 0 | 138580 | 148579 | 682996 | 505633.6 |  |  | 2026-05-10 | 2026-05-10 22:16 | 2026-05-21 | 2026-05-21 19:50 | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-05-10 | 2026-05-10 22:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1262015 | 223771 | 2026-07-05 17:55:41 +0530 | Aryan Singh | Receipt | 2026-06-28 12:18:48 +0530 | Anjali Singh | DCM: cx dcm was taken on normal phone call as cx was not able to access teams or google meet because of network issue. | 2026-06-28 12:18:01 +0530 | Anjali Singh | Some Image was uploaded | 2026-07-05 |  | 2026-07-12
19958 | Turnkey | May'26 | Sarika Hile | DOSTI WEST COUNTY | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Aryan Singh |  | Hold | Preproduction | Site Readiness 1 | 869269 | 173854 | 1166715 | 0 | 0 | 2 | 46 | 0 | 0 | 415919 | 279496 |  |  | 2026-05-10 | 2026-05-10 22:43 | 2026-05-14 | 2026-05-15 20:56 | 2026-05-15 | 2026-05-16 11:49 | 2026-05-31 | 2026-05-26 18:31 | 2027-01-05 |  | 2027-01-12 |  | 2026-05-16 | 2026-05-16 12:11 | 2026-05-17 | 2026-05-16 12:12 | 2026-05-16 | 2026-05-18 11:43 | 2026-05-26 | 2026-05-26 16:52 |  |  |  |  | 2026-05-28 | 2026-05-28 19:17 | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 | [6 empty] | 2027-02-05 |  | 2027-02-14 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-17 |  |  |  | 2027-03-11 |  | 2027-03-13 |  | 2027-03-14 | [5 empty] | 2027-01-16 |  | 2026-05-27 | 2026-05-26 17:05 | Site is Non-RTMI | 2026-05-10 | 2026-05-10 22:42 | 991029 | 175686 | 0 | 0 | 0 | 0 | 993294.7474 | 153769 | 2026-07-03 17:14:57 +0530 | Anamika Dolai | Delayed posession till jan'27. | 2026-07-03 13:17:34 +0530 | Monika Pal | 2026-07-03 | 2026-07-02 14:42:07 +0530 | Anil Kuwar | Others: | 2026-05-27 | 2026-05-26 18:36 | 2027-01-06
19959 | Turnkey | May'26 | Sindhu Bejoy | Sheth Avante | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 2258114 | 9999 | 0 | 0 | 0 | 60 | 0 | 215812 | 225811 | 1004856 | 801635.6 |  |  | 2026-05-10 | 2026-05-10 23:14 | 2026-05-16 | 2026-05-16 19:32 | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-10 | 2026-05-10 22:56 | 0 | 0 | 0 | 0 | 0 | 0 | 1915943 | 342170 | 2026-05-13 12:41:17 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-05-13 12:12:41 +0530 | Rachna Abhyankar | Client Name - Mrs Sindhu BejoyÂ Property Type - New - 3.5BHK - sheth Avante - Kanjurmarg - 1060 Sqft Possession - June EndÂ Family - 4 Adults + 1 pet Budget - 20L (without white goods) Occupation - Banker & InsuranceÂ Entrance :- 1-Safety doorÂ Living Room:- 1- Shoe rack - 4 people 2- Mandir at small dining areaÂ 3- 3 seater sofa + recliner chairÂ 4- TV Unit - 50-55" 5- FoyerÂ or console table at entrance wallÂ 6- Door besides the TV Unit needs to be flushedÂ 7- Wall concepts - Minimalist Kitchen:- 1-Semi Modular KitchenÂ - parallel (Base + Loft(1side) + Wall) (Might go for full demolishing of the kitchen and convert into L Shape ) Bedroom 1( opp. Kitchen )_ storage roomÂ 1- Placement of Washing Machine & DishwasherÂ 2- Dining - 6 seaterÂ 3- Crockery Unit 4- Storage unit 5- Wall concepts Bedroom 01(Guest Bedroom):- Room behind the TV Unit wall 1- Sofa cum bedÂ 2- Vertical storage unitÂ 3- Study table with upper storageÂ 4- Wall conceptsÂ Bedroom 02 (Daughter's Room) 1- Queen size bed with storageÂ 2- Foldable study table + upper storage 3- Wardrobe + LoftÂ 4- Wall conceptsÂ Master Bedroom :- 1- Wardrobe + Loft 2-Foldable table + upper storageÂ 3-Queen size bed with storage 4-DressingÂ 5-wall concepts 6- Window bay seating -Â if possibleÂ Bathrooms:- 1-Upper / Bottom storage Vanity in Both Bathroom + Mirror Civil Requirements:- Entire home 1-False ceilingÂ 2-ElectricalÂ 3-PaintingÂ CDP aligned for May 17th,2026 - 11:00 AMÂ | 2026-05-10 23:11:36 +0530 | Aryan Singh | Possession on 15th July Ventured Live Space | 2026-05-25 |  | 2026-06-01
19960 | Turnkey | May'26 | Samisham singh | Trifecta Vanto | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 1741809 | 9999 | 0 | 0 | 0 | 57 | 0 | 164182 | 174181 | 707837 | 685610 |  |  | 2026-05-10 | 2026-05-19 12:35 | 2026-05-21 | 2026-05-22 11:51 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-05-10 | 2026-05-19 12:34 | 0 | 0 | 0 | 0 | 0 | 0 | 1476109 | 265699 | 2026-05-27 13:38:36 +0530 | Priyamvada PV | Samisham CDP changes : 24.05.26 Kitchen loft to be done in u shape Kitchen has to be with green countertop washing machine above wall unit to start from right above appliances for 4'H appliance unit to be on right side of sink area facing hob (client not confirmed on roller shutter/glass door unit) Mirror pullout in the MBR next to WR for 7'H KBR mirror pullout w/o storage in left (explained that its not possible in 75mm filler width) single bed on top level with queen size bed below that (custom work) with detachable slide to be shown MBR - proper bay window with paneling around with bottom fixed storage required for entire left wall of cot MBR loft to be extended above door GBR - proper bay window with paneling around with bottom fixed storage required next to pooja unit Pooja to be till 8'H, then storage above Study table to on right wall of door entry complete library/ wardrobe storage required on left wall of entrance door for entire wall TV unit has to be re-done with more wall storage/ tall unit balcony mop unit to be included Living actual 5'H plants to be shown (for tropical feel) instead of wallpaper | 2026-05-27 13:35:09 +0530 | Priyamvada PV | Samisham CDP changes : 24.05.26 Kitchen loft to be done in u shape Kitchen has to be with green countertop washing machine above wall unit to start from right above appliances for 4'H appliance unit to be on right side of sink area facing hob (client not confirmed on roller shutter/glass door unit) Mirror pullout in the MBR next to WR for 7'H KBR mirror pullout w/o storage in left (explained that its not possible in 75mm filler width) single bed on top level with queen size bed below that (custom work) with detachable slide to be shown MBR - proper bay window with paneling around with bottom fixed storage required for entire left wall of cot MBR loft to be extended above door GBR - proper bay window with paneling around with bottom fixed storage required next to pooja unit Pooja to be till 8'H, then storage above Study table to on right wall of door entry complete library/ wardrobe storage required on left wall of entrance door for entire wall | 2026-05-23 18:07:56 +0530 | Ravikiran K | Client - Samisham Singh Budget - 9 - 10lakhs Property - Trifecta Vanto Kids - one small kid Note - customer is from Rajasthan and wants a homely feeling and wants to recreate the same thing in her house in terms of theme. | 2026-06-01 |  | 2026-06-08
19962 | Turnkey | May'26 | Satyam tiwari S | 2BHK | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Ravikiran K |  | Active | Design | 20% Payment | 1368409 | 124026 | 1240257 | 0 | 0 | 21 | 0 | 0 | 149656 | 582146 | 512581.6 |  |  | 2026-05-09 | 2026-05-14 10:42 | 2026-05-15 | 2026-05-17 17:35 | 2026-05-20 | 2026-05-17 19:33 | 2026-06-25 | 2026-06-24 13:48 | 2026-07-16 |  | 2026-07-23 |  | 2026-05-17 | 2026-05-19 18:38 | 2026-05-18 | 2026-05-20 15:04 | 2026-05-20 | 2026-05-20 16:23 | 2026-05-23 | 2026-05-23 11:42 |  |  |  |  | 2026-07-15 |  | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-05-24 | 2026-06-24 10:51 | Site is RTMI | 2026-05-09 | 2026-05-13 19:07 | 1051066 | 189191 | 0 | 0 | 0 | 0 | 1548097.383 | 255647 | 2026-05-26 19:23:36 +0530 | Purva Shiravle | DDM1: Minutes of Meeting held on Date: 26-05-2026 Attendees: Mr. & Mrs. Tiwari with purva Discussion: Based on 26-05-2026 meeting, below is a list of all the requirements that were discussed during the meeting: LVING ROOM- 1.wall concept behind sofa and adjucent wall was discussed with the combination of wall beadings in arch shape 2.placement of pooja unit changed from left wall to right wall 3. pooja unit size increased from 600mm to 750mm (widthwise) 4. wall shelves were descoped 5.tv unit design - need to work and design according to retro theme KITCHEN & UTILITY - 1.Layout for kitchen cabinets was discussed and finalised 2.addition of granite and sink installation in kitchen by bonito, procurement will be in builders' scope 3.Replacement of cylinder unit to blind shelf unit 4.addition of glass crockery units above fridge - 3shutter 5.Wall utility unit descoped instead of that 1 open wall unit added MASTER BEDROOM 1.Bed back design discussed need combination of beading with european cornices 2.Need suggestions for tv unit in master bedroom 3.Wardrobe internals need to finalise 4.Placement of furniture discussed & finalised KIDS ROOM- 1.Wardrobe internals need to finalise 2.Placement of furniture discussed & finalised 3.bedbac design needs to be retain as per initial discussion i.e. punning and wallpaper 4.study unit placement and design options discussed, need 7 width for study unit instead of small one 5. accordingly wall design will be revisedÂ | 2026-05-20 17:15:32 +0530 | Maspi Das | Cx name : Priti & SatyamÂ Address: 1101 Profession : ITÂ Possession : JuneÂ How many people will be staying : 3 Theme : RetroÂ Entrance facing : E facingÂ Budget : 7 to 8L Entrance -Â Shoe rack with seatingÂ Living - TV unit position as marked In plan L shape sofa TV 65"Â TV unit needs one tall unit with glass shutters, base unit, wall panelling (refer image) Sofa back wall need curved trims designÂ Foyer long wall need ledge and curve detailing (refer image ) Dining area - 2'x5' pooja unit with low height base unit (for seating height)- refer imageÂ 4 seater diningÂ Need ledges with back panel as per reference imageÂ Kitchen -Â Double door fridgeÂ Counter top from builder's endÂ Sink and dado tile from builder's endÂ Gas connection is there so no cylinder unitÂ Next to fridge need less depth wall unitÂ Wall cabinets need 2 glass shutterÂ wall, base and loftÂ Utility - Above WM give wall cabinetÂ MBR- Queen size bed with one side table (only for 3D) Wardrobe with dresser as markedÂ Tv unit need ledge as marked with wall designÂ Bed wall need curve trims designÂ KBR- Peehu (14yo)- no pinksÂ Wardrobe with loft and give long mirror on 1 end shutterÂ Study table with base unit wall cabinet and tall unit opposite to bedÂ Bed wall need trim detailÂ Bathroom - vanity unit need with mirrorÂ False ceiling - needed for all areaÂ CDP- 12th May | 2026-05-20 16:23:00 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion Date: 30th June 2026 Site is accessible for the IMs. Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Immediately to be scheduled this week * DEM 1 by 27th May 2026 (after 27th May 2026, client is not available in town so he wants IMs and 1st DEM to happen before 27th May 2026) * 10% Payment Stage 30th May 2026 Please note that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 10,41, 915 Offers Discussed During the Call: Free Shoerack Offer Modular - Windows to Wonderful home Services - Windows to Wonderful Home PM fee waiver (5%) Design fee waiver (5%) Free Hob & Chimney Offer Special Offer (40000) Silver Coin 21g Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 8,80,351 Checklist terms - descoping, delay compensation, agreement terms are clear. No civil work at site Transaction will be B2C self-funding. | 2026-06-25 | 2026-06-24 13:59 | 2026-07-17 |  | Under Construction | 2026-06-30
19966 | Turnkey | May'26 | Balakrishna | SNN Raj High Gardens | BNG - HSR | Yes | Preksha Sajjanshettar | Akshay Ds | Soumya KP | [5 empty] | Ravikiran K |  | Active | Design | DEM1 | 769631 | 106992 | 1069485 | 0 | 0 | 4 | 0 | 0 | 46934 | 321291 | 294414 |  |  | 2026-05-10 | 2026-05-19 12:34 | 2026-06-03 | 2026-06-04 12:16 | 2026-06-27 | 2026-06-27 19:49 | 2026-07-17 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-06-27 | 2026-06-30 12:05 | 2026-06-28 | 2026-07-07 13:32 | 2026-07-07 | 2026-07-11 13:21 | 2026-07-12 | [5 empty] | 2026-07-18 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-07-13 |  | Unknown | 2026-05-10 | 2026-05-15 11:27 | 906344 | 163141 | 0 | 0 | 0 | 0 | 890774.894 | 147083 | 2026-07-11 13:19:57 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: October 2026 Client will get the soft possession in the month of August 2026 Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible. * DEM 1 â€“ Next weekends * 10% Payment Stage â€“ 21st July 2026 *No civil work planned *Transaction will be b2c self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - Windows to Wonderful home PM fee waiver (5%) Design fee waiver (5%) Free Hob & Chimney Offer Free Shoerack Offer May'26 100% GST waiver Silver Coin Offer Final Closing Value Discussed: â‚¹ 7,69,631 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-10 12:49:27 +0530 | Sanjana Swami | client asked to call back tomorrow after 10 am | 2026-07-10 11:39:39 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-18 |  | 2026-07-25 |  | Under Construction | 2026-10-30 | 2026-06-27 | 106992 | Ravi Roy
19967 | Turnkey | May'26 | Aishwarya Shetty | Dosti mezzo | MUM - GOR | Yes | Khyati Bandi | Vishakha Vaishnav | Safalta Karkera |  |  | Faizal Shaikh | Rizwan Mistry |  | Umang Shah | Aakash Gaikwad | Active | Preproduction | DEM2 | 1427092 | 285418 | 1894238 | 0 | 0 | 28 | 0 | 0 | 0 | 640179 | 501494.8 |  |  | 2026-05-12 | 2026-05-12 17:03 | 2026-05-14 | 2026-05-14 13:04 | 2026-05-17 | 2026-06-02 14:52 | 2026-06-15 | 2026-06-11 16:32 | 2026-07-23 |  | 2026-07-30 |  | 2026-05-15 | 2026-05-31 | 2026-05-18 | 2026-06-02 14:39 | 2026-06-03 | 2026-06-04 16:05 | 2026-06-05 | 2026-06-05 16:54 |  |  |  |  | 2026-06-11 | 2026-06-17 19:19 | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-06-06 | 2026-06-11 16:21 | Site is RTMI | 2026-05-12 | 2026-05-12 17:03 | 1607574 | 286664 | 0 | 0 | 0 | 0 | 1607573.7507 | 262727 | 2026-06-21 16:13:36 +0530 | Khyati Bandi | KITCHEN -Â 1. Remove tall glass shutter unitÂ 2. Add fan 3. Janitor unit will be thereÂ 4. Add loftÂ LIVING AREA -Â 1. Change wall paint 2. Add two wall light in dining areaÂ Bedroom 1 1. profile light ceiling with cove on headboard 2. inbuilt light in mirrorÂ 3. Shelf to keep hand bags vertical/ horizontalÂ MBR-Â 1. Add hanging light and side tableÂ Foyer -Â 1. Shoe unit with seatingÂ | 2026-06-17 16:46:12 +0530 | Khyati Bandi | 1. Living ceiling 2 fans with one chadelier in centerÂ 2. Wall light in dining area alsoÂ Kitchen -Â 1. layout is changes. paralle kitchenÂ 2. Ro will be placed under sink 3. Fridge will be placed near dining tableÂ 4. shutter unit to keep grain container, no drawer for thisÂ BEDROOM 1Â 1. Curve shape mirror on vanityÂ BEDROOM 2 -Â 1. high gloss laminate wardrobe with metal strip on itÂ COMMON WASHROOM -Â 1. Hanging light provisionÂ Â | 2026-06-09 16:02:23 +0530 | Khyati Bandi | LIVING AREA -Â 1. 3 seater sofa+ one single accent chairÂ MBR -Â 1.Queen size bed with drawer storageÂ 2. Add hidden drawer in left wardrobeÂ KITCHEN - 1. Inbuilt hobÂ 2. Add microwave unitÂ 3. Washing machine top loadÂ 4. Add one unit to keep detergents and broom 5. Sink in golden colorÂ 6. Detergent holder under basin +dustbasin 7. One shelf above sink to keep soap Cornice in ceiling + chandelierÂ | 2026-06-12 | 2026-06-11 16:32 | 2026-07-24 |  | Under Construction | 2026-07-31
19968 | Sub Project |  | Pankaj Gujar | Tricity Montview | MUM - Thane | Yes | Sahil Gunde | Anil Jagtap | Rachna Abhyankar |  |  | Yash Metha | Aditya Vikram | Murali S |  |  | Active | Production | Dispatch Due | 72897 | 0 | 0 | 0 | 72897 | 22 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-12 | 2026-05-13 17:12 | 2026-05-13 | 2026-05-13 17:12 | 2026-05-13 | 2026-05-13 17:13 | 2026-05-14 | 2026-05-13 17:14 | 2026-05-14 | 2026-05-13 17:16 | 2026-05-14 | 2026-05-13 17:19 | 2026-05-13 | 2026-05-13 17:13 | 2026-05-14 | 2026-05-13 17:13 | 2026-05-13 | 2026-05-13 17:13 | 2026-05-14 | 2026-05-13 17:13 |  |  |  |  | 2026-05-13 | 2026-05-13 17:14 | 2026-05-14 | 2026-05-13 17:17 | 2026-05-14 | 2026-05-13 17:17 |  |  | 2026-05-14 | 2026-05-16 13:22 | 2026-05-16 | 2026-05-29 15:48 | 2026-05-30 | 2026-05-31 18:47 | 2026-06-01 | 2026-06-01 11:16 |  |  |  |  | 2026-06-15 12:21 | 2026-06-21 | 2026-06-20 22:13 | 2026-06-25 | 2026-06-23 18:48 | 2026-06-27 | 2026-06-01 11:17 | 2026-06-23 | 2026-07-06 14:05 | 2026-07-08 |  | 2026-07-10 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-05-29 | 2026-06-15 12:20 | 2026-05-14 | 2026-05-13 17:13 | Unknown | 2026-05-12 | 2026-05-13 17:12 | 0 | 0 | 0 | 0 | 61777 | 11119 | 61777 | 11119 | [9 empty] | 2026-05-14 | 2026-05-13 17:14 | 2026-05-14 | 2026-05-13 17:16
19969 | Sub Project |  | Martino Rodrigues | Gurukrupa Nirmalam | MUM - GOR |  | Rajnish Mishra | Manzoor Shaikh | Safalta Karkera |  |  | Faizal Shaikh | Rizwan Mistry | Murali S |  |  | Active | Installation | Execution | 0 | 0 | 0 | 0 | 65797 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-12 | 2026-05-15 17:13 | 2026-05-13 | 2026-05-15 17:13 | 2026-05-15 | 2026-05-15 17:14 | 2026-05-16 | 2026-05-15 17:15 | 2026-05-16 | 2026-05-15 17:16 | 2026-05-16 | 2026-05-15 17:18 | 2026-05-15 | 2026-05-15 17:14 | 2026-05-16 | 2026-05-15 17:14 | 2026-05-15 | 2026-05-15 17:14 | 2026-05-16 | 2026-05-15 17:14 |  |  |  |  | 2026-05-15 | 2026-05-15 17:15 | 2026-05-16 | 2026-05-15 17:17 | 2026-05-16 | 2026-05-15 17:17 |  |  | 2026-05-16 | 2026-05-16 11:58 | 2026-05-16 | 2026-05-17 12:25 | 2026-05-18 | 2026-05-19 18:43 | 2026-05-22 | 2026-05-27 10:52 |  |  |  |  | 2026-05-27 11:27 | 2026-05-30 | 2026-05-30 13:28 | 2026-06-01 | 2026-05-30 15:53 | 2026-05-31 | 2026-06-02 18:54 | 2026-05-30 | 2026-06-30 14:30 | 2026-06-30 | 2026-06-30 17:17 | 2026-07-01 | 2026-06-30 17:47 |  |  | 2026-07-02 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-05-17 | 2026-05-20 19:06 | 2026-05-16 | 2026-05-15 17:14 | Unknown | 2026-05-12 | 2026-05-15 17:13 | 0 | 0 | 0 | 0 | 55760 | 10036 | 55760 | 10036 | 2026-05-19 18:25:16 +0530 | Rajnish Mishra | Some Image was uploaded | [6 empty] | 2026-05-16 | 2026-05-15 17:15 | 2026-05-16 | 2026-05-15 17:16
19970 | Turnkey | May'26 | Tejas Sankhe | Shahpoorji Sienna | MUM - GOR | Yes | Umang Ratnani | Reshma Melanta | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Active | Design | DEM1 | 1778065 | 226738 | 2267381 | 0 | 0 | 55 | 0 | 0 | 128875 | 836114 | 586338.4 |  |  | 2026-05-09 | 2026-05-19 16:29 | 2026-05-17 | 2026-05-19 16:40 | 2026-05-22 | 2026-05-20 11:48 | 2026-08-08 |  | 2027-03-11 |  | 2027-03-18 |  | 2026-05-20 | 2026-05-20 12:06 | 2026-05-21 | 2026-05-20 12:25 | 2026-05-20 | 2026-05-21 16:27 | 2026-05-27 | 2026-05-27 18:52 |  |  |  |  | 2026-08-09 |  | 2027-03-13 |  | 2027-03-14 |  |  |  | 2027-03-21 |  | 2027-03-22 |  | 2027-03-23 |  | 2027-03-24 | [6 empty] | 2027-04-11 |  | 2027-04-20 |  | 2027-04-19 |  | 2027-04-20 |  | 2027-04-21 |  | 2027-04-23 |  |  |  | 2027-05-15 |  | 2027-05-17 |  | 2027-05-18 | [5 empty] | 2027-03-22 |  | 2026-08-04 |  | Unknown | 2026-05-09 | 2026-05-12 13:40 | 1924006 | 343375 | 0 | 0 | 0 | 0 | 1913976.817 | 318310 | 2026-06-05 13:02:14 +0530 | Meet Shah | Some Image was uploaded | 2026-06-05 13:00:55 +0530 | Meet Shah | Some Image was uploaded | 2026-06-05 12:47:11 +0530 | Meet Shah | Some Image was uploaded | 2026-08-09 |  | 2027-03-12 |  | Under Construction | 2027-03-31
19972 | Turnkey | May'26 | sundar | Birla Tissya | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 889828 | 9999 | 0 | 0 | 0 | 64 | 0 | 78984 | 88983 | 376582 | 335280.8 |  |  | 2026-05-09 | 2026-05-12 15:56 | 2026-05-26 | 2026-05-26 14:43 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-09 | 2026-05-12 14:32 | 0 | 0 | 0 | 0 | 0 | 0 | 754091 | 135736 | 2026-05-29 13:50:08 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-26 14:39:24 +0530 | Priyanka Gs | Some Image was uploaded |  |  |  | 2026-06-03 |  | 2026-06-10
19973 | Turnkey | May'26 | Vishwanath | Birla Tisya | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 1302897 | 9999 | 0 | 0 | 0 | 63 | 0 | 120291 | 130290 | 531839 | 510478.8 |  |  | 2026-05-12 | 2026-05-13 13:59 | 2026-05-21 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-12 | 2026-05-12 18:40 | 0 | 0 | 0 | 0 | 0 | 0 | 1106952 | 195945 | 2026-05-29 13:49:19 +0530 | Losii Athisa | Some Image was uploaded | [6 empty] | 2026-06-03 |  | 2026-06-10
19980 | Turnkey | May'26 | Sonal Lad | LODHA AMARA | MUM - Thane | No Estimate | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-12 | 2026-05-13 10:45 | 2026-05-13 |  | 2026-05-16 |  | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-17 |  | 2026-05-18 | [5 empty] | 2026-05-24 |  | 2026-06-01 |  | 2026-06-02 |  |  |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 | [6 empty] | 2026-06-30 |  | 2026-07-09 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-12 |  |  |  | 2026-08-03 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | 2026-06-10 |  | 2026-05-19 |  | Unknown | 2026-05-12 | 2026-05-13 10:43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-13 10:46:23 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-12 21:41:26 +0530 | Unknown | About the Customer **2BHK Interior Plans and Budget** Customer is planning interiors for a 2BHK property with possession expected in October-November, and has a budget of 10-12 lakhs. **Hesitation for Visit Due to Possession Uncertainty** Customer is hesitant to commit to a visit due to uncertainty about the possession date, stating they will wait if possession is not by October. **Information Request for Designs and Address** Customer requested designs on WhatsApp and the Thane experience center address. **Agent to Share Info, Customer to Book Slot** Agent will share design videos and office address via WhatsApp; customer will review and message before booking a visit slot. |  |  |  | 2026-05-24 |  | 2026-05-31
19981 | Turnkey | May'26 | Rutuja Kadam | Puranik rumah bali | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | 10% Payment | 815675 | 9999 | 0 | 0 | 0 | 55 | 0 | 71569 | 81568 | 326270 | 326270 |  |  | 2026-05-12 | 2026-05-13 13:56 | 2026-05-13 | 2026-05-15 14:41 | 2028-03-31 |  | 2028-04-07 |  | 2028-04-14 |  | 2028-04-21 |  | 2028-03-31 |  | 2028-04-01 |  | 2028-04-01 |  | 2028-04-02 | [5 empty] | 2028-04-08 |  | 2028-04-16 |  | 2028-04-17 |  |  |  | 2028-04-24 |  | 2028-04-25 |  | 2028-04-26 |  | 2028-04-27 | [6 empty] | 2028-05-15 |  | 2028-05-24 |  | 2028-05-23 |  | 2028-05-24 |  | 2028-05-25 |  | 2028-05-27 |  |  |  | 2028-06-18 |  | 2028-06-20 |  | 2028-06-21 | [5 empty] | 2028-04-25 |  | 2028-04-03 |  | Unknown | 2026-05-12 | 2026-05-12 22:00 | 0 | 0 | 0 | 0 | 0 | 0 | 691250 | 124425 | 2026-05-15 14:41:23 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-13 14:12:13 +0530 | Aryan Singh | Some Image was uploaded | 2026-05-13 14:10:47 +0530 | Aryan Singh | CX have multiple civil requirement's Possession in Dec currently staying in Lodha Splendora as tenant Pitched to have Civil & White Goods (Electronics, Mattress, Lights & Fixtures) from outsource No as discussion regarding budget but cx mentioned 10L in form DCM on 13 5PM Offline CDP 21st 3 PM tentative | 2028-04-08 |  | 2028-04-15
19982 | Sub Project |  | Sandeep Rajadhyaksha | 10 BKC | MUM - GOR |  | Mandar Ambre | Reshma Melanta | Shantanu Parakh |  |  | Nilesh Patel | Rizwan Mistry | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-13 | 2026-05-14 13:24 | 2026-05-14 | 2026-05-14 13:24 | 2026-05-14 | 2026-05-14 13:25 | 2026-05-15 | 2026-05-14 13:26 | 2026-05-15 | 2026-05-14 13:27 | 2026-05-15 | 2026-05-14 13:30 | 2026-05-14 | 2026-05-14 13:25 | 2026-05-15 | 2026-05-14 13:25 | 2026-05-14 | 2026-05-14 13:25 | 2026-05-15 | 2026-05-14 13:25 |  |  |  |  | 2026-05-14 | 2026-05-14 13:26 | 2026-05-15 | 2026-05-14 13:28 | 2026-05-15 | 2026-05-14 13:28 |  |  | 2026-05-15 | 2026-05-14 13:32 | 2026-05-15 | 2026-05-14 14:23 | 2026-05-15 | 2026-05-15 11:57 | 2026-05-16 | 2026-05-15 11:58 |  |  |  |  | 2026-05-16 15:14 | 2026-05-23 | 2026-05-23 19:03 | 2026-05-27 | 2026-05-25 15:31 | 2026-05-26 | 2026-05-30 13:22 | 2026-05-25 | 2026-06-04 13:10 | 2026-06-04 | 2026-06-04 14:32 | 2026-06-06 | 2026-06-05 18:10 |  |  | 2026-06-07 | 2026-06-05 19:06 | 2026-06-07 | 2026-06-05 19:15 | 2026-06-05 | 2026-06-05 19:28 |  |  |  |  | 2026-05-14 | 2026-05-14 15:33 | 2026-05-15 | 2026-05-14 13:26 | Unknown | 2026-05-13 | 2026-05-14 13:24 | 0 | 0 | 0 | 0 | 46609 | 0 | 46609 | 0 | [9 empty] | 2026-05-15 | 2026-05-14 13:26 | 2026-05-15 | 2026-05-14 13:27
19983 | Turnkey | May'26 | Sunita Gade | ********************************** | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar | [5 empty] | Vandana Preet |  | Hold | Preproduction | Site Readiness 1 | 1290503 | 258101 | 1535497 | 0 | 0 | 2 | 32 | 0 | 0 | 573103 | 459298.8 |  |  | 2026-05-13 | 2026-05-14 12:02 | 2026-05-15 | 2026-05-15 17:39 | 2026-05-17 | 2026-05-17 20:30 | 2026-06-07 | 2026-06-07 19:18 | 2026-07-06 |  | 2026-07-13 |  | 2026-05-17 | 2026-05-22 18:40 | 2026-05-18 | 2026-05-30 18:15 | 2026-05-30 | 2026-06-06 17:28 | 2026-06-07 | 2026-06-07 14:59 |  |  |  |  | 2026-06-07 | 2026-06-11 16:34 | 2026-07-08 |  | 2026-07-09 |  |  |  | 2026-07-16 |  | 2026-07-17 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-07-17 |  | 2026-06-17 | 2026-06-07 19:11 | Site is Non-RTMI | 2026-05-13 | 2026-05-14 12:00 | 1301269 | 234228 | 0 | 0 | 0 | 0 | 1301268.9213 | 232290 | 2026-07-05 11:10:54 +0530 | Anil Jagtap | The client is expected to receive possession by 10th July 2026. | 2026-06-26 19:51:58 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-14 18:36:46 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-08 | 2026-06-07 19:46 | 2026-07-07 |  | Under Construction | 2026-06-15
19985 | Sub Project |  | Vinod Menon |  | MUM - GOR | Yes | Neha Yadav |  | Safalta Karkera | [7 empty] | Active | Preproduction | Hoto | 84010 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 50406 | 33604 |  |  | 2026-05-13 | 2026-05-14 17:43 | 2026-05-14 | 2026-05-14 17:43 | 2026-05-14 | 2026-05-14 17:43 | 2026-05-15 | 2026-05-14 17:44 | 2026-05-15 | 2026-05-14 17:46 | 2026-05-15 | 2026-05-14 17:49 | 2026-05-14 | 2026-05-14 17:43 | 2026-05-15 | 2026-05-14 17:43 | 2026-05-14 | 2026-05-14 17:43 | 2026-05-15 | 2026-05-14 17:43 |  |  |  |  | 2026-05-14 | 2026-05-14 17:44 | 2026-05-15 | 2026-05-14 17:47 | 2026-05-15 | 2026-05-14 17:47 |  |  | 2026-05-15 |  | 2026-05-16 |  | 2026-05-17 |  | 2026-05-18 | [6 empty] | 2026-06-05 |  | 2026-06-14 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-17 |  |  |  | 2026-07-09 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-05-16 |  | 2026-05-15 | 2026-05-14 17:44 | Unknown | 2026-05-13 | 2026-05-14 17:43 | 0 | 0 | 0 | 0 | 0 | 0 | 71195 | 12815 | [9 empty] | 2026-05-15 | 2026-05-14 17:44 | 2026-05-15 | 2026-05-14 17:46
19986 | Turnkey | May'26 | Mr. yogesh patil | SNN Raj High Gardens | BNG - HSR | Yes | [8 empty] | Korak Ganguly |  | Active | Prospect | DCM Due | 1352803 | 0 | 0 | 0 | 0 | 42 | 0 | 135280 | 135280 | 552402 | 529840 |  |  | 2026-04-28 | 2026-06-03 15:05 | 2026-05-17 | 2026-06-11 11:55 | 2026-05-31 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-04-28 | 2026-05-14 11:55 | 0 | 0 | 0 | 0 | 0 | 0 | 1146443 | 206359 | 2026-06-03 11:50:21 +0530 | Priyamvada PV | CDP changes : BR-1 - Hinged wardrobe to change to sliding wardrobe BR-2 fixed study table with pencil drawer instead of foldable table BR-2 Remove wall ledges | 2026-05-17 16:39:56 +0530 | Maspi Das | Cx name : Yogesh Patil (Maharashtra) Property - SNN RAJ HIGH GARDEN 3BHK Profession : Service Possession : October How many people will be staying : 4 Kids- 2 Lavith - 8, Devashree - 16 Parents - 2 Theme : NeutralÂ Kid's BR theme- Neutral with RED Entrance -facing : North Budget : 8-10L Foyer- Shoe rack with seatingÂ Can be placed outside or may be inside (not confirmed yet) If shoe rack is coming outside (Reference image is taken) Wall paneling (need to design and show) Living area- TV Unit ref taken Opt2 is including wallpaper, fluted and Gold pattis Dining wall- Pooja unit (need to create a false wall near Balcony door) (non-negotiable) So that client can sit inside and do pooja Crockery unit- Plan in Bathroom wallÂ Add opposite wall will be Picture wall Kitchen- Fridge, WM & DW will be in the Left side one after another One Oven unitÂ 3' SinkÂ HOB and Sink placement will be as per plan Base, Wall and Lofts (Chimney/without chimney) BR1 is MBR (Mom & Son) King size bed Wall design ref taken Study unit on the Balcony wall along with Piano table Sliding wardrobe (but also give costing for Hinged wardrobe) Show Rolling curtains in design Add/suggest minimal pop-up color for the bedroom Bay window seating storage Hidden mirror (can plan inside the wardrobe, if not some alternative option) **FOR ALL THE WASHROOMS- VANITY UNITS FOR NOW** BR2 is Daughter's BR- Accent wall Single size bed Dressing table beside the BedÂ Study table minimal 3' Infront of the window BR3 (His room) Single size bed/Queen size bed optionÂ Wardrobe One study table/foldable table One Ledge for TV unit **NEED TO PLAN & DESIGN THIS ROOM WITH QUEEN AND SINGLE SIZE BED KEEPING THE REQUIREMENTS SAME** | 2026-05-15 18:14:08 +0530 | Korak Ganguly | DCM: client budget is 10 lacs 3bhk handover is in next 3 to 4 mnth reason he booked 9999 because same day when he came for vd some of his friend visited for cdp so due to FOMO he paid silver coin is pending | 2026-06-22 |  | 2026-06-29
19987 | Turnkey | May'26 | Ugly Duckling enterprises | Builder Floor | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S | Vishwa Hiremath | Active | Preproduction | CM | 1029656 | 205931 | 1387148 | 0 | 0 | 4 | 0 | 0 | 0 | 468920 | 354804.8 |  |  | 2026-05-12 | 2026-05-16 10:53 | 2026-05-23 | 2026-05-23 19:07 | 2026-05-26 | 2026-05-27 15:54 | 2026-06-14 | 2026-06-14 14:14 | 2026-07-10 |  | 2026-07-17 |  | 2026-05-27 | 2026-05-28 11:02 | 2026-05-28 | 2026-05-29 13:37 | 2026-05-29 | 2026-06-04 18:28 | 2026-06-07 | 2026-06-07 19:13 |  |  |  |  | 2026-06-14 | 2026-06-27 14:15 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-08 | 2026-06-14 14:10 | Site is RTMI | 2026-05-12 | 2026-05-13 15:07 | 1175549 | 211598 | 0 | 0 | 0 | 0 | 1163811.2104 | 193888 | 2026-06-14 14:28:52 +0530 | Vishal Bandi | Minutes of Meeting held on Date: 14-06-2026 , Title: DEM 1 Project: 19987 Client: Ugly Duckling enterprises Attendees: Designer and client Objective: DEM 1 Discussion 1. near the main door, need to plan ledges and next to that pooja unit 2. Aquarium base storage shutter opening has to confirm , as of now keeping as it is 3. Kitchen - wall unit has to be alu shutter with glass 4. Tall unit placement has to be change 5. utility- need to plan for Cylinder storage 6. KBR ( daughters room) need to plan for Jhula 7. Media Room- wardrobe and study table has to placeÂ 8. Bar unknit design has to change 9. MBR- single wardrobe has to remove and need to place in Media room 10. wardrobe has to change it to 5 shutter 11. dresser need to planÂ | 2026-06-07 19:14:28 +0530 | Parasa Sri | Welcome call done, client is available for weekends for meetings Site is RTMI. | 2026-06-04 18:28:37 +0530 | Sanjana Swami |  | 2026-06-15 | 2026-06-14 14:27 | 2026-07-11 |  | RTMI
19988 | Turnkey | May'26 | Prajakta Kumar | Oberoi woods | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 1973457 | 9999 | 0 | 0 | 0 | 63 | 0 | 187347 | 197346 | 839486 | 739280 |  |  | 2026-05-10 | 2026-05-13 15:12 | 2026-06-27 | 2026-06-27 16:01 | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-07-19 |  | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-14 |  | Unknown | 2026-05-10 | 2026-05-13 15:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1674708 | 298748 | 2026-07-12 10:59:52 +0530 | Pratima Kajwe | 19988 - Celebrity Design Presentation (CDP) with the customer-20260711_100531UTC-Meeting Recording.mp4 19988 - Celebrity Design Presentation (CDP) with the customer-20260711_140530UTC-Meeting Recording.mp4 | 2026-06-27 15:58:14 +0530 | Pratima Kajwe | DCM: MOM Customer and Project Profile1. Name of the customer Prajakta Kumar, Aparna Wadkar, Rajnish Kumar, 8 year old son. and 2 more members 2. Profession CA, Merchant Navy oil and gas. 3. Project Name/Tower Name/Flat Number 12th floor, 4. Typology (1BHK, 2BHK, 3BHK, etc) 2.5BHK 5. Site Access Date 2026-07-31 6. Possession Date 2026-06-30 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 2000000 Customer Preferences8. Who will be living in the house? Elderly Members, Nuclear Family, Couple 9. What activities do you usually prefer at your home ? Relaxing and Unwinding, Family Bonding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] In house vaastu consultant. 11. Mention basic vastu principles agreed for integration in design, if any Living room - blue or green shade, Study room - green shade, Master bed room 1 - Beige brown shade, Parent's bedroom - Red shade 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) 950sq.ft, Minimal and sleek. Upload reference images 14. Any absolute no-go styles colours or materials Anything dark 15. Do you have any existing furniture that must be accommodated? Open to discussion 13. Do you want the design to reflect any personal story, cultural influence, or special memory Navy wall, family wall and travel souvenirs, ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Console, Seating, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests, Multipurpose, TV Focus 2. Must-have furniture or features? Speakers, Coffee table, Puja unit, Display unit , Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Travel souvenirs, Artwork 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit, Bar Unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Dishwasher, Built-in Oven, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing , Sliding 3. Master Bedroom - Additional units Dresser 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Parents 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Sliding , Swing 8. Bedroom 1 - Additional units Dresser , TV unit 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Guest 11. Bedroom 2 - Bed Type No Storage 12. Bedroom 2 - Wardrobe Style Sliding 13. Bedroom 2 - Additional Units Study Table, Bookshelf 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Tall Storage, Bottom Storage, Laundry space, Washing machine space, Top Storage Balcony & Outdoor1. How do you intend to use your balcony? Storage 2. Outdoor Mood How do you intend to use the utility Cloths Drying Miscellaneous1. Timeline related commitment made by Bonito, if any 6 months as per the scope of work, would be confirmed once the scope of work. 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? GST waiver offer would be confirmed with Mrunali. 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 15th July will be getting possession of flat for civil and everything 6. Additional Requirements (Mention any requirements from customer not covered in the form) Automation and steps to be incorporated in the utility section, change flooring and break existing Italian marble, Powder bathroom provision, re-wiring of the flat - 4th or 5th July second half. 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 2500000 | 2026-06-27 15:56:49 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-07-19 |  | 2026-07-26
19993 | Turnkey | May'26 | Shashi Shekhar Jha | Rohan Ekanta | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Design | 20% Payment | 1656292 | 224498 | 2279507 | 0 | 0 | 10 | 0 | 0 | 106760 | 673197 | 651836.8 |  |  | 2026-05-13 | 2026-06-01 14:15 | 2026-05-17 | 2026-06-03 14:51 | 2026-06-04 | 2026-06-04 11:57 | 2026-07-05 | 2026-07-05 15:45 | 2026-09-20 |  | 2026-10-10 |  | 2026-06-04 | 2026-05-31 | 2026-06-05 | 2026-06-06 10:33 | 2026-06-06 | 2026-06-13 11:07 | 2026-06-17 | 2026-06-17 11:41 |  |  |  |  | 2026-07-05 |  | 2026-10-05 |  | 2026-10-06 |  |  |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 | [6 empty] | 2026-11-03 |  | 2026-11-12 |  | 2026-11-11 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-15 |  |  |  | 2026-12-07 |  | 2026-12-09 |  | 2026-12-10 | [5 empty] | 2026-10-14 |  | 2026-07-15 | 2026-07-05 11:55 | Site is Non-RTMI | 2026-05-13 | 2026-05-28 18:46 | 1934587 | 344919 | 0 | 0 | 0 | 0 | 1905326.05 | 310870 | 2026-07-09 18:58:48 +0530 | Janush Bojamma C T | 19993- 4th juky 1_ TV design independent 2) Tv , play stations , sound bar, wifi 3) Glass tinted 4) Foyer and outside confirmation on MCB box and usage 5) Pooja unit - As per refrenec and pocket design Crockery- Tinted glass unit Continue with the appliances- unit on l side 1.5ft - Partition to kitchen entry MBR Dresser proper utilisation Aristo Wall concept to plan Lights 2 places -used clothes storage Laundry in wash bain Study - Tropical 3 ac - in living and bedrooms FC - living and dining Dish drainer in utility | 2026-06-13 11:06:19 +0530 | Sanjana Swami |  | 2026-06-13 10:58:14 +0530 | Muralikrishna Udupi | Some Image was uploaded | 2026-07-06 | 2026-07-05 18:37 | 2026-09-21 |  | Under Construction | 2027-01-31
19996 | Turnkey | May'26 | Rakesh Sinha | RUNWAL FOREST | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Vandana Preet |  | Hold | Preproduction | DEM2 | 1148427 | 306827 | 1484137 | 0 | 0 | 22 | 23 | 0 | 0 | 437372 | 404228 |  |  | 2026-05-13 | 2026-05-13 20:34 | 2026-05-13 | 2026-05-15 14:41 | 2026-05-18 | 2026-05-15 19:20 | 2026-05-26 | 2026-05-26 18:00 | 2026-06-11 | 2026-06-10 15:49 | 2026-08-11 |  | 2026-05-15 | 2026-05-19 19:04 | 2026-05-16 | 2026-05-20 11:21 | 2026-05-20 | 2026-05-22 13:24 | 2026-05-26 | 2026-05-26 16:50 |  |  |  |  | 2026-05-23 | 2026-05-19 19:04 | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-05-26 | 2026-05-26 17:39 | Site is Non-RTMI | 2026-05-13 | 2026-05-13 20:13 | 1257743 | 226393 | 0 | 0 | 0 | 0 | 1251817.0412 | 206716 | 2026-07-03 12:57:15 +0530 | Monika Pal | CROSS MEASUREMENT DELAY | 2026-06-18 11:31:23 +0530 | Monika Pal | Measurement is aligned for today | 2026-06-11 18:51:01 +0530 | Monika Pal | Dear @Cx Dhruv Sinha Bonito Greetings of the Day! Thank you for your valuable time during todays meeting. We truly appreciate your inputs and will incorporate the discussed changes into the design. Please find below the Minutes of Meeting (MOM) for your reference: Requirements: Living Room: The design has been finalized. The selected laminates, paint, and wallpaper have already been shared in the group. We have also finalized the false ceiling design. Kids Room: The design has been finalized along with the laminates, louvers, handles, and false ceiling. The selected materials have already been shared with you. For the glass unit, we have finalized brown tinted glass. Master Bedroom: The design, laminates, wallpaper, and false ceiling have been finalized, and the selected materials have already been shared with you. Bathroom: The vanity laminates and knobs have been finalized. Kitchen: The design and laminates have been finalized, and the selected materials have already been shared with you. As discussed, you requested one lock provision in the kitchen unit; we will check the feasibility and update you accordingly. Paint Selection: The paint selection has also been finalized and shared in the group. Note: The final cost may vary depending on wall design, colour, finish, size modifications, and any modular or civil changes. Thank you. Best Regards, Monika | 2026-05-27 | 2026-05-26 18:05 | 2026-06-11 | 2026-06-10 15:51
20001 | Turnkey | May'26 | Sachin | Ds max Sangam Grand | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 1144035 | 10000 | 1144035 | 0 | 0 | 57 | 0 | 104404 | 114404 | 492068 | 423160 |  |  | 2026-05-14 | 2026-05-17 12:25 | 2026-05-17 | 2026-05-17 19:20 | 2026-05-20 | 2026-05-19 11:28 | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-27 |  | 2026-06-04 |  | 2026-06-05 |  |  |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 | [6 empty] | 2026-07-03 |  | 2026-07-12 |  | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-13 |  | 2026-05-22 |  | Unknown | 2026-05-14 | 2026-05-14 18:54 | 969521 | 174513 | 0 | 0 | 0 | 0 | 969521 | 174513 | 2026-05-14 13:43:32 +0530 | Rituparna Chakraborty | DCM: Mr.sachin geeta 4 people , 11yr daughter - sanvi 9year son ojas IT company - TCSÂ RTMIÂ Orthodox hindu brahmin familyÂ FunctionalÂ Contemporary - traditional wooden 3rd floor , MD east facingÂ Shoe unit outside ,Â Seating l sofa ,partition to prevent view f MBR 3+2 can be possible as well 50"-60" tvÂ KitchenÂ -sink can come under the window - DW, small otg, wet grinder , mixer , airfrier, kettle , toaster , rolling shutter or normal shutter to keep it closed .Â - smaller sinkÂ - Tall unit may beÂ - 2 up down door fridge 400ltrsÂ - Some traditional wooden look matching the L/DÂ - bigger dado tilesÂ - UtilityÂ - DW with a bigger sink , WM , small cabinet , small broom closet - Clothes haning option as well BalconyÂ My be change it to study and work space if possibleÂ Common bathroom - tiles & plumbing changeÂ Inbuilt niche ideas seating for the shower- for parentsÂ Dining/puja - the wall sharing MBR corner will have puja unit - seating puja , closed , 5-6 idolsÂ - blind for pujaÂ 4-6 extendable dining MBRÂ - major change in washroom , small wardrobe area to be considered for washroom entry and shower may beÂ - queen size bed , side table ,Â - sliding 6ft or even lesserÂ - window seating if possibleÂ - TV if possibleÂ - study if possible - white peach pastel ojasÂ - Single bed- extendable into double - wardrobeÂ - study, gamingÂ - anime movies , football themeÂ - bookshelvesÂ - neon lightÂ Sanvi - Single bed- extendable into double - wardrobeÂ - study - light blue and whiteÂ - animeÂ - bookshelvesÂ - badminton storage 7-10lakhs excluding civil , decorÂ Little greeneryÂ | 2026-05-14 11:20:44 +0530 | Unknown | About the Customer **3BHK Bangalore Renovation Needs** Customer Sachin is looking to renovate his 3 BHK apartment in Bangalore, DS Max Sangam. He has an existing modular kitchen and wardrobes but wants to renovate the kitchen and bathrooms. His budget is between 7 to 10 lakhs. **Customer Abroad, Needs Process Clarity** Customer is currently in Scotland and plans to move back in September. He wants to understand the process and pricing before committing to a visit or detailed discussion. **Inquiry on Civil Work and Accountability** Customer is seeking clarity on whether Bonito Designs handles associated civil work for bathrooms and takes accountability for vendor-provided services. **Team Transfer and Bangalore Callback** Agent mistakenly connected the customer to the Mumbai team and is arranging for the Bangalore team to call back within 5 minutes on the provided UK number. **Schedule Virtual Call and Share Offers** Next step is to schedule a virtual call with the design team for today or tomorrow, after the customer shares property details via WhatsApp. Agent will also share offer details. |  |  |  | 2026-05-27 |  | 2026-06-03
20002 | Turnkey | May'26 | Nitul Talukdar | Sumadhura Folium Phase - 3 | BNG - HRBR | Yes |  | Parasa Sri | [6 empty] | Shashank Singh |  | Active | Design | DEM1 | 1253949 | 341999 | 1664572 | 0 | 0 | 15 | 33 | 0 | 0 | 436747 | 475202.8 |  |  | 2026-05-10 | 2026-05-20 13:23 | 2026-05-22 | 2026-05-22 11:22 | 2026-05-25 | 2026-05-23 11:09 | 2026-10-08 |  | 2027-01-05 |  | 2027-01-12 |  | 2026-05-23 | 2026-05-26 18:37 | 2026-05-24 | 2026-05-26 19:23 | 2026-05-26 | 2026-05-28 16:16 | 2026-06-03 | 2026-06-03 11:15 |  |  |  |  | 2026-06-01 | 2026-05-26 18:37 | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 | [6 empty] | 2027-02-05 |  | 2027-02-14 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-17 |  |  |  | 2027-03-11 |  | 2027-03-13 |  | 2027-03-14 | [5 empty] | 2027-01-16 |  | 2026-10-04 |  | Unknown | 2026-05-10 | 2026-05-14 11:59 | 1410654 | 253917 | 0 | 0 | 0 | 0 | 1354758.1427 | 225710 | 2026-06-03 11:01:07 +0530 | Parasa Sri | The welcome call is done. RERA ON DECEMBER, site is not ready for IM | 2026-05-28 16:16:03 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Soft Possession: September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible. * DEM 1 Client did not mentioned the dates as they have a new born baby and his wife cannot plan to come for 1st DEM, will inform the sales team for the 1st DEM * 10% Payment Stage already paid *No civil work planned at site *Transaction will be B2C Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 13,54,759 Offers Discussed During the Call: Design fee waiver (5%) Free Bed Offer Silver Coin 21g 100% GST Waiver Laminate Upgrade - May '26 Campaign PM Fee Waiver (4%) Final Closing Value Discussed: 12,53,949 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-05-28 15:02:29 +0530 | Sanjana Swami |  | 2026-10-09 |  | 2027-01-06 |  | Under Construction | 2026-09-07
20004 | Turnkey | May'26 | Jayesh S | Brigade | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | [5 empty] | Active | Design | DEM1 | 1048938 | 133999 | 1341199 | 0 | 0 | 54 | 0 | 0 | 75789 | 429044 | 410106 |  |  | 2026-05-14 | 2026-05-18 14:23 | 2026-05-15 | 2026-05-18 15:38 | 2026-05-21 | 2026-05-19 12:50 | 2026-08-26 |  | 2026-09-02 |  | 2026-09-09 |  | 2026-05-19 | 2026-05-21 11:00 | 2026-05-20 | 2026-05-21 11:29 | 2026-05-21 | 2026-05-22 17:46 | 2026-05-26 | 2026-05-26 12:16 |  |  |  |  | 2026-08-27 |  | 2026-09-04 |  | 2026-09-05 |  |  |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 | [6 empty] | 2026-10-03 |  | 2026-10-12 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-13 |  | 2026-10-15 |  |  |  | 2026-11-06 |  | 2026-11-08 |  | 2026-11-09 | [5 empty] | 2026-09-13 |  | 2026-06-05 |  | Unknown | 2026-05-14 | 2026-05-15 16:04 | 1136610 | 204589 | 0 | 0 | 0 | 0 | 1103676.4039 | 188808 | 2026-07-14 22:10:33 +0530 | Rajeshwari S | Client will make the 10% payment around 18th July Post that project will go on hold till possession. | 2026-06-18 13:13:21 +0530 | Rajeshwari S | Some Image was uploaded | 2026-05-29 13:55:07 +0530 | Losii Athisa | Some Image was uploaded | 2026-08-27 |  | 2026-09-03 |  | Under Construction | 2027-03-30
20008 | Turnkey | May'26 | Md Khalil Shaikh | prerna apartment | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | Neha Singh | Neha Singh | Shashwat Joshi | Rizwan Mistry | Murali S | Manasi Patil | Sunil Poojary | Hold | Preproduction | Site Readiness 2 | 868717 | 576089 | 1195813 | 0 | 868717 | 3 | 8 | 0 | 0 | 0 | 292628 |  |  | 2026-05-14 | 2026-05-15 13:11 | 2026-05-14 | 2026-05-15 13:11 | 2026-05-18 | 2026-05-16 14:54 | 2026-05-27 | 2026-05-27 12:46 | 2026-06-13 | 2026-06-19 21:40 | 2026-06-20 | 2026-06-19 23:43 | 2026-05-16 | 2026-05-16 14:48 | 2026-05-17 | 2026-05-16 16:29 | 2026-05-16 | 2026-05-18 11:39 | 2026-05-19 | 2026-05-19 18:00 |  |  |  |  | 2026-05-27 | 2026-05-27 15:59 | 2026-06-20 | 2026-06-19 21:41 | 2026-06-20 | 2026-06-19 22:41 |  |  | 2026-06-23 | 2026-06-27 11:49 | 2026-06-27 | 2026-06-27 20:16 | 2026-06-28 | 2026-06-29 18:07 | 2026-06-30 | 2026-07-04 12:49 | [5 empty] | 2026-07-23 |  | 2026-08-01 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-04 |  |  |  | 2026-08-26 |  | 2026-08-28 |  | 2026-08-29 | [5 empty] | 2026-06-27 |  | 2026-05-20 | 2026-05-26 15:42 | Site is RTMI | 2026-05-14 | 2026-05-15 13:09 | 1013401 | 182412 | 0 | 0 | 926198.6316 | 156369 | 926198.6316 | 156369 | 2026-07-07 11:45:50 +0530 | Vishakha Vaishnav | ON SOITE DOOR INSTALLATION WORK ON GOING | 2026-06-24 12:27:56 +0530 | Neha Singh | Some Image was uploaded | 2026-06-24 12:01:12 +0530 | Neha Singh | Some Image was uploaded | 2026-05-28 | 2026-05-27 12:46 | 2026-06-20 | 2026-06-19 21:40 | Under Construction | 2026-07-30
20009 | Turnkey | May'26 | Priti Jha | Imperial lururia | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 911682 | 229999 | 1280839 | 0 | 0 | 12 | 16 | 0 | 0 | 395565 | 286117.6 |  |  | 2026-05-14 | 2026-05-14 21:29 | 2026-05-24 | 2026-05-23 23:52 | 2026-05-26 | 2026-05-24 12:44 | 2026-07-07 | 2026-07-03 12:16 | 2026-07-09 |  | 2026-07-16 |  | 2026-05-24 | 2026-05-24 22:15 | 2026-05-25 | 2026-05-24 22:47 | 2026-05-24 | 2026-05-25 18:24 | 2026-05-26 | 2026-05-26 19:12 |  |  |  |  | 2026-06-01 | 2026-05-27 11:18 | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-15 | 2026-07-03 10:49 | Site is RTMI | 2026-05-14 | 2026-05-14 21:28 | 1088069 | 192769 | 0 | 0 | 0 | 0 | 1084799.5448 | 164619 | 2026-05-31 16:41:16 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-29 16:00:25 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-26 19:10:31 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to confirm with rishika for IM slot DEM Dates -Â DEM 1 - Cx said that she will discuss with family and update us DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% onÂ 3rd june Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-07-04 | 2026-07-03 12:17 | 2026-07-10 |  | RTMI
20010 | Turnkey | May'26 | Subramanian | Sobha chrysanthemum | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran |  |  | Harshit Choudhary | Saddam Hussain Z M |  | Mohammed Rasick | Abdul Shafeen | Active | Preproduction | DEM2 | 1540323 | 318000 | 1930152 | 0 | 0 | 6 | 0 | 0 | 0 | 630920 | 591402.8 |  |  | 2026-05-16 | 2026-05-20 12:17 | 2026-05-20 | 2026-05-22 11:22 | 2026-05-25 | 2026-05-25 21:21 | 2026-06-06 | 2026-06-06 19:13 | 2026-07-03 | 2026-07-02 17:30 | 2026-07-12 |  | 2026-05-25 | 2026-05-26 09:34 | 2026-05-26 | 2026-05-26 16:09 | 2026-05-26 | 2026-05-26 17:59 | 2026-05-29 | 2026-05-29 18:19 |  |  |  |  | 2026-06-06 | 2026-06-30 16:34 | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-09-19 |  | 2026-05-30 | 2026-06-06 19:07 | Site is RTMI | 2026-05-16 | 2026-05-18 17:57 | 1635722 | 294430 | 0 | 0 | 0 | 0 | 1593000.4384 | 277258 | 2026-06-02 13:55:17 +0530 | Keerthan M | CDP: Foyer Suggest wall decor Dining change wall paper Kitchen check for dish washer provision. Bedroom 1 wall detailing gradient paintbook shelf (loose furniture ) CX scope Bedroom 2 Wall detaining - texture paint can be suggested MBR Bronze mirror need to be added Note: False ceiling in common areaMost of the designs are finalised | 2026-05-29 12:58:41 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-26 17:58:19 +0530 | Athul Ajaykumar | Possession Status: Renovation Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10,10,40,40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (27th June 2026 or 30th June 2026) * DEM 1 Will let the sales team know accordingly * 10% Payment Stage 20% already done Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin 21g Laminate Upgrade - May '26 Campaign PM Fee Waiver (4%) 100% GST Waiver Final Closing Value Discussed: 15,40,323 Client VOC The client has requested civil work involving: Removal of the wardrobe from the bedroomRemoval of the kitchen cabinetRemoval of the granite from the kitchen platform/tableThe client also mentioned that the sales team had committed to sharing the contact details of a vendor who could assist with this civil work. | 2026-06-07 | 2026-06-06 19:16 | 2026-07-03 | 2026-07-06 16:14 | RTMI
20011 | Turnkey | May'26 | Amit kumar choudhary | l t emerald | MUM - GOR | Yes | [8 empty] | Umang Shah |  | Active | Prospect | DCM Due | 1281494 | 9999 | 0 | 0 | 0 | 61 | 0 | 118150 | 128149 | 524462 | 500732.8 |  |  | 2026-05-15 | 2026-05-15 12:28 | 2026-05-15 | 2026-05-15 13:56 | 2026-05-16 |  | 2026-05-25 |  | 2026-06-01 |  | 2026-06-08 |  | 2026-05-18 |  | 2026-05-19 |  | 2026-05-19 |  | 2026-05-20 | [5 empty] | 2026-05-26 |  | 2026-06-03 |  | 2026-06-04 |  |  |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 | [6 empty] | 2026-07-02 |  | 2026-07-11 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-14 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-12 |  | 2026-05-21 |  | Unknown | 2026-05-15 | 2026-05-15 12:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1325315.2706 | 230669 | 2026-05-21 12:58:36 +0530 | Umang Shah | Some Image was uploaded | 2026-05-15 14:00:22 +0530 | Shreya Sonavane | DCM: sq.ft- 990 Bedroom3- son-10yrÂ Â wardrobe, study Bed 2- Daughter- 5yr wardrobe, study Master-Â study, wardrobe, TV unit Bathroom- vanity 3no kitchen semi modular- sink & fridge on same platform Living-Â TV with mandir unit, crockery, shoe rack, safety door bed, sofa, dinning, side table is existing | 2026-05-15 13:55:01 +0530 | Shreya Sonavane | DCM: User ResponseCustomer and Project Profile1. Name of the customer Amit kumar choudhary 2. Profession salaried 3. Project Name/Tower Name/Flat Number L&T Emerald 4. Typology (1BHK, 2BHK, 3BHK, etc) 3bhk 5. Site Access Date 2026-05-15 6. Possession Date 2026-04-30 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 12 Customer Preferences8. Who will be living in the house? Nuclear Family 9. What activities do you usually prefer at your home ? Prayer, Family Bonding 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] VASTU 11. Mention basic vastu principles agreed for integration in design, if any MANDIR 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials WALLPAPER 15. Do you have any existing furniture that must be accommodated? BED, SIDE TABLE, SOFA, DINNING FOR 6 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Seating, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? TV Focus 2. Must-have furniture or features? TV unit, Puja unit 3. Choose your decor inspirations 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Bookshelf , Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom No 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Study table , Bookshelf 9. False Ceiling Required - Bedroom 1 No 10. Bedroom 2 - Utility Kids 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units Study Table, Bookshelf 14. False Ceiling Required - Bedroom 2 No 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Bottom Storage Balcony & Outdoor1. How do you intend to use your balcony? Storage 2. Outdoor Mood How do you intend to use the utility Storage Miscellaneous1. Timeline related commitment made by Bonito, if any NA 2. Other commitments made by Bonito to customer, if any NA 3. What are offers committed to customers? NA 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date NA 6. Additional Requirements (Mention any requirements from customer not covered in the form) EXISTING BED SIZE- 6'X6'6" 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 1200000 | 2026-05-26 |  | 2026-06-02
20012 | Turnkey | May'26 | Sivaraman Ramakrishanan | SBR Earth and Sky | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 1782444 | 9999 | 0 | 0 | 0 | 53 | 0 | 168245 | 178244 | 712978 | 712977.6 |  |  | 2026-05-15 | 2026-05-20 13:21 | 2026-05-22 | 2026-05-22 13:52 | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-15 | 2026-05-15 12:46 | 0 | 0 | 0 | 0 | 0 | 0 | 1510546 | 271898 | 2026-05-29 13:57:15 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-21 17:34:09 +0530 | Ehthisham Durgam | DCM: MOM Interior Design MeetingClient Name: Shivaraman Project Type: Duplex House Profession: IT Budget: 1520 Lakhs Meeting Schedule: Friday 4:00 PM Requirements DiscussionOverall ThemeChettinad style interior conceptMinimal and functional storage approachPeripheral false ceiling in common areasFocus on elegant traditional detailing with modern functionalityGround Floor / Common AreasFoyer (Outside)Exterior foyer setup requiredFunctional and welcoming entrance designLiving RoomMinimal TV unit designFloating TV unit preferredNew sofa to be addedPeripheral false ceiling designChettinad-style aesthetics to be incorporatedDining Area4-seater rectangular dining tableCrockery unit requiredStore room conversion/connection to puja unit as per referencePuja unit with carved traditional door designKitchenKitchen layout to be executed as per finalized planLoft storage requiredNo tall unitUtility area to include:Sink unitWashing machine provisionParents BedroomWardrobe with loft storageWardrobe to be positioned in current TV unit locationDressing area in walk-in closetQueen-size bedMinimal wall design/themeFormal Living AreaFloating shelf with storageDisplay unit requiredBean bags seatingNiche space to be designed for aquariumOpen shelves with bottom storageTV provision requiredMaster BedroomWardrobe with loftStudy unit to be placed in front of windowMinimal TV unitWindow seating requiredKids RoomWardrobe with loft storageStudy table extending till bedside tableOpen bookshelf designQueen-size bedAdditional RequirementVanity units 4 Nos | 2026-05-15 12:45:15 +0530 | Unknown | About the Customer **Mother-in-law admission confirmed** Customer's mother-in-law's admission is confirmed. **Proceed with query requested** Customer requests to proceed with their query. **Follow-up on prior discussion** Agent is following up on a previous conversation. | 2026-05-31 |  | 2026-06-07
20013 | Turnkey | May'26 | Anuj Gupta | SNN Clermont | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Preproduction | DEM2 | 1090302 | 214006 | 1370177 | 0 | 0 | 23 | 0 | 0 | 0 | 448682 | 427613.6 |  |  | 2026-05-15 | 2026-05-15 13:54 | 2026-05-19 | 2026-05-19 14:02 | 2026-05-27 | 2026-05-28 10:59 | 2026-06-20 | 2026-06-20 17:27 | 2026-07-26 |  | 2026-08-02 |  | 2026-05-28 | 2026-05-29 11:18 | 2026-05-29 | 2026-05-30 15:41 | 2026-05-30 | 2026-06-02 18:22 | 2026-06-03 | 2026-06-03 17:26 |  |  |  |  | 2026-06-20 | 2026-06-22 19:10 | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-06-04 | 2026-06-20 17:14 | Site is RTMI | 2026-05-15 | 2026-05-15 13:31 | 1161167 | 209010 | 0 | 0 | 0 | 0 | 1127583.7961 | 196254 | 2026-06-10 11:18:20 +0530 | Sagarika Venkatesh | Some Image was uploaded | 2026-06-09 11:57:39 +0530 | Palak Thakur | CDP: (19) Calendar ¦ 20013 - Celebrity Design Presentation (CDP) with the customer ¦ Microsoft Teams rgm recording in drive | 2026-06-02 18:21:32 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: June Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (3th June 2026) * DEM 1 Will update to the sales team * 10% Payment Stage Tentatively scheduled for (11th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin 21g 100% GST Waiver Laminate Upgrade - May '26 Campaign PM Fee Waiver (4%) Final Closing Value Discussed: 10,90,302 Checklist terms descoping, agreement terms are cleared Â | 2026-06-21 | 2026-06-20 17:36 | 2026-07-27 |  | Under Construction | 2026-06-30
20015 | Turnkey | May'26 | Lalit Gupta Gupta | Enclave cornwood | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 2001745 | 0 | 0 | 0 | 0 | 61 | 0 | 200175 | 200175 | 905914 | 695481.6 |  |  | 2026-05-15 | 2026-05-15 15:10 | 2026-05-22 | 2026-05-23 15:51 | 2026-06-10 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-15 | 2026-05-15 15:10 | 0 | 0 | 0 | 0 | 0 | 0 | 1698639 | 303105 | 2026-05-23 15:53:17 +0530 | Krutika Vernekar | DCM: Cx Asking for Site visit on Tuesday | 2026-05-23 14:31:26 +0530 | Krutika Vernekar | DCM: 3BHK Interior Scope Client Brief Summary carpet 1350 Entry / Foyer: Safety doorEntry wall designFoyer seating with long shoe rackKitchen: Demolition work requiredWall opening between kitchen & living/dining areaHob + chimney provisionMicrowave provisionBase units + tall unit + loft storageLiving & Dining: Long 4-seater sofaTV unitOffice/study area in dining with storage6-seater dining setupCommon Requirements: Vanity required in all roomsMaster Bedroom: BedWardrobeStudy areaKids Room (2 Boys 24 & 22 yrs): Large PS gaming setup requiredWall-hung TV setup on gaming wallWardrobe in niche areaCouples Room: WardrobeDresserStudy area | 2026-05-15 14:52:39 +0530 | Unknown | About the Customer **3 BHK Property in Thane, Possession June 15th** Customer is looking to design interiors for a 3 BHK property in Thane, with possession expected around June 15th. The customer is in the process of purchasing the property. **Father's Approval and Customer Fatigue Pending** Customer needs to get father's approval and is experiencing fatigue, requiring rest before visiting the experience center. **Inquiry on Pricing, Payment, and Quality** Customer is interested in pricing, payment plans, negotiation, material quality, and timely delivery. **Agent to Send Address, Customer to Confirm Visit** Agent to send experience center address via WhatsApp; customer will confirm visit time after resting and consulting with father. | 2026-06-03 |  | 2026-06-10
20016 | Turnkey | May'26 | Kaustubh Shisode | Own villa | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 8719844 | 9999 | 0 | 0 | 0 | 55 | 0 | 861985 | 871984 | 3523371 | 3452504 |  |  | 2026-05-15 | 2026-05-16 10:12 | 2026-05-15 | 2026-05-21 16:18 | 2026-05-22 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-05-22 |  | 2026-05-23 |  | 2026-05-23 |  | 2026-05-24 | [5 empty] | 2026-05-30 |  | 2026-06-07 |  | 2026-06-08 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 | [6 empty] | 2026-07-06 |  | 2026-07-15 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-18 |  |  |  | 2026-08-09 |  | 2026-08-11 |  | 2026-08-12 | [5 empty] | 2026-06-16 |  | 2026-05-25 |  | Unknown | 2026-05-15 | 2026-05-15 19:03 | 0 | 0 | 0 | 0 | 0 | 0 | 7389698 | 1330145 | 2026-05-29 10:28:30 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-29 10:27:47 +0530 | Moksh Mehta | Some Image was uploaded | 2026-05-15 16:39:31 +0530 | Unknown | About the Customer **Villa Undergoing Civil Work** Customer Mr. Kaustubh has a 5 BHK villa in Dombivli, currently undergoing civil work, expected to be completed in 1-2 months. He is looking for interior planning before civil work finishes. **Hesitant for Immediate Visit** Customer is hesitant to visit the experience center immediately, preferring to understand services and procedure first, as civil work is ongoing and measurements cannot be taken yet. **Service Offering Details** Bonito Designs offers end-to-end interior solutions (excluding white goods) with a 10-year warranty and celebrity designer collaborations. **Thane Experience Center Visit Booked** Appointment scheduled for today at 2:00 PM at the Thane experience center. Customer will bring a soft copy of the floor plan. | 2026-05-30 |  | 2026-06-06
20017 | Sub Project |  | Ankit Patel | Hari smruti | MUM - GOR |  | Saakshi Bhute | Manzoor Shaikh | Safalta Karkera |  |  | Rajkumar Suthar | Rizwan Mistry | Murali S |  |  | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-15 | 2026-05-27 12:01 | 2026-05-16 | 2026-05-27 12:01 | 2026-05-27 | 2026-05-27 12:01 | 2026-05-28 | 2026-05-27 12:02 | 2026-05-28 | 2026-05-27 12:03 | 2026-05-29 | 2026-05-27 12:04 | 2026-05-27 | 2026-05-27 12:01 | 2026-05-28 | 2026-05-27 12:01 | 2026-05-27 | 2026-05-27 12:01 | 2026-05-28 | 2026-05-27 12:01 |  |  |  |  | 2026-05-27 | 2026-05-27 12:02 | 2026-05-28 | 2026-05-27 12:03 | 2026-05-28 | 2026-05-27 12:03 |  |  | 2026-05-28 | 2026-05-27 16:58 | 2026-05-27 | 2026-05-28 13:19 | 2026-05-29 | 2026-05-28 14:40 | 2026-05-29 | 2026-05-28 14:40 |  |  |  |  | 2026-05-28 18:54 | 2026-05-30 | 2026-05-30 13:35 | 2026-06-01 | 2026-05-30 15:53 | 2026-05-31 |  | 2026-05-30 |  | 2026-06-12 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-23 |  | 2026-06-24 | [5 empty] | 2026-05-28 | 2026-05-28 13:45 | 2026-05-28 | 2026-05-27 12:01 | Unknown | 2026-05-15 | 2026-05-27 12:01 | 0 | 0 | 0 | 0 | 35720.34 | 0 | 35720.34 | 0 | [9 empty] | 2026-05-28 | 2026-05-27 12:02 | 2026-05-28 | 2026-05-27 12:03
20021 | Turnkey | May'26 | Sunil Malhotra | L&T Rejuve | MUM - Thane | No Estimate | [8 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-15 | 2026-05-19 19:07 | 2026-05-16 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-15 | 2026-05-19 12:35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-15 22:14:53 +0530 | Unknown | About the Customer **Rescheduled Visit for Tomorrow** Customer Sunil Malhotra plans to visit the Thane experience center tomorrow, as he missed his scheduled visit last weekend. The center is open until 8 PM. **Location Request via WhatsApp** Customer requested the experience center location via WhatsApp. He resides near the Mulund-Thane border at Wagle Estate. **Cab Service Offered and Accepted** Agent offered a cab for pick and drop, which the customer initially declined but later accepted as a possibility. **Request for Family Visit** Agent requested the customer to visit with family. Agent's name is Subhan. | [6 empty] | 2026-06-03 |  | 2026-06-10
20024 | Sub Project |  | Deepak | Purva Almosphere | BNG - HRBR |  | Sanjay Kulkarni | Parasa Sri | Shibin Lal |  |  | Harshit Choudhary | Saddam Hussain Z M | Murali S |  |  | Completed | Complete | Completed | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-16 | 2026-05-16 12:22 | 2026-05-17 | 2026-05-16 12:23 | 2026-05-16 | 2026-05-16 12:24 | 2026-05-17 | 2026-05-16 12:24 | 2026-05-17 | 2026-05-16 12:25 | 2026-05-17 | 2026-05-16 12:27 | 2026-05-16 | 2026-05-16 12:24 | 2026-05-17 | 2026-05-16 12:24 | 2026-05-16 | 2026-05-16 12:24 | 2026-05-17 | 2026-05-16 12:24 |  |  |  |  | 2026-05-16 | 2026-05-16 12:25 | 2026-05-17 | 2026-05-16 12:26 | 2026-05-17 | 2026-05-16 12:26 |  |  | 2026-05-17 | 2026-05-16 12:31 | 2026-05-17 | 2026-05-16 12:41 | 2026-05-17 | 2026-05-16 14:05 | 2026-05-17 | 2026-05-16 14:05 |  |  |  |  | 2026-05-22 18:03 | 2026-05-30 | 2026-05-30 12:15 | 2026-06-01 | 2026-05-30 15:57 | 2026-06-02 | 2026-05-30 12:47 | 2026-05-30 | 2026-05-30 16:08 | 2026-05-30 | 2026-05-30 16:14 | 2026-05-31 | 2026-05-30 19:02 |  |  | 2026-06-01 | 2026-05-30 20:05 | 2026-06-01 | 2026-05-30 20:06 | 2026-06-06 | 2026-05-30 21:58 |  |  |  |  | 2026-05-16 | 2026-05-16 14:05 | 2026-05-17 | 2026-05-16 12:24 | Unknown | 2026-05-16 | 2026-05-16 12:21 | 0 | 0 | 0 | 0 | 46609 | 0 | 46609 | 0 | [9 empty] | 2026-05-17 | 2026-05-16 12:24 | 2026-05-17 | 2026-05-16 12:25
20026 | Turnkey | May'26 | Prashanth and Anjali | Ramki 1 Karnival | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 1229328 | 171964 | 1752067 | 0 | 0 | 49 | 0 | 0 | 73902 | 522373 | 461089.2 |  |  | 2026-05-16 | 2026-05-16 12:28 | 2026-05-16 | 2026-05-22 16:18 | 2026-05-25 | 2026-05-26 12:43 | 2026-08-04 |  | 2026-10-08 |  | 2026-10-15 |  | 2026-05-26 | 2026-05-27 11:06 | 2026-05-27 | 2026-05-27 14:11 | 2026-05-27 | 2026-05-27 16:25 | 2026-06-05 | 2026-06-05 13:52 |  |  |  |  | 2026-08-05 |  | 2026-10-10 |  | 2026-10-11 |  |  |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 | [6 empty] | 2026-11-08 |  | 2026-11-17 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-18 |  | 2026-11-20 |  |  |  | 2026-12-12 |  | 2026-12-14 |  | 2026-12-15 | [5 empty] | 2026-10-19 |  | 2026-07-31 | 2026-07-03 15:41 | Site is Non-RTMI | 2026-05-16 | 2026-05-16 12:27 | 1484802 | 267264 | 0 | 0 | 0 | 0 | 1412861.7995 | 233287 | 2026-07-03 15:24:29 +0530 | Vishal Haridas | HANDOVER DELAYED | 2026-06-05 13:51:34 +0530 | Abhinandan K S | Possession expected by end of September 2026. Initial measurement cannot be aligned as the site is not ready. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings are shared with the Customer. Project will go on hold after DEM and 20% closure. | 2026-06-04 13:33:12 +0530 | Patil Madhavi | Some Image was uploaded | 2026-08-05 |  | 2026-10-09 |  | Under Construction | 2026-09-30
20027 | Turnkey | May'26 | Lalitha Meduri | Sri Vishnu heights | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Kushal S | Abdul Shafeen | Active | Preproduction | CM | 1138551 | 143611 | 905501 | 0 | 0 | 2 | 0 | 0 | 0 | 574043 | 420896.8 |  |  | 2026-05-16 | 2026-05-19 14:16 | 2026-05-16 | 2026-05-20 11:09 | 2026-05-23 | 2026-05-23 12:30 | 2026-06-13 | 2026-06-13 17:47 | 2026-07-03 |  | 2026-07-19 |  | 2026-05-23 | 2026-05-25 11:02 | 2026-05-24 | 2026-05-27 17:11 | 2026-05-25 | 2026-05-28 12:06 | 2026-06-04 | 2026-06-03 11:13 |  |  |  |  | 2026-06-13 | 2026-06-15 18:10 | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-06-04 | 2026-06-13 17:46 | Site is RTMI | 2026-05-16 | 2026-05-16 13:05 | 767374 | 138127 | 0 | 0 | 0 | 0 | 1292968.6481 | 213489 | 2026-06-13 18:56:11 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-03 11:12:25 +0530 | Parasa Sri | Welcome call done. Initial measurements can be planned. on weekends meeting can be planned on weekends. | 2026-05-28 12:05:33 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Under construction Completion Date: 15 June 2026 Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (30th May 2026) * DEM 1 Tentatively scheduled for (6th June 2026) * 10% Payment Stage Tentatively scheduled for (6th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin 21g Free Hob & Chimney Offer Free Shoerack Offer 100% GST Waiver Final Closing Value Discussed: 7,18,056 Clinet VOC The client mentioned about planned civil work involving wall tiling in the kitchen, pooja room, vanity area, and utility room and would like to execute the civil work with Bonito. | 2026-06-14 | 2026-06-13 17:49 | 2026-07-04 |  | Under Construction | 2026-06-15
20028 | Turnkey | May'26 | PABITRA PRADHAN | transcon allstars | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 2897851 | 9999 | 2897851 | 0 | 0 | 50 | 0 | 279786 | 289785 | 1255106 | 1063174.4 |  |  | 2026-05-16 | 2026-05-17 11:59 | 2026-05-16 | 2026-05-18 14:12 | 2026-05-22 | 2026-05-26 16:15 | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-16 | 2026-05-16 19:11 | 2455806 | 442045 | 0 | 0 | 0 | 0 | 2455806 | 442045 | 2026-06-29 15:27:43 +0530 | Rishika Malviya | Some Image was uploaded | 2026-05-27 12:33:31 +0530 | Rishika Malviya | Some Image was uploaded | 2026-05-16 14:05:49 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-03 |  | 2026-06-10
20029 | Turnkey | May'26 | Mr. Sadanand Kohad | Arihant Aspire | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar |  |  | Yash Metha | Aditya Vikram | Murali S | Subhan Khan | Prasad Bhivaji Hande | Active | Preproduction | Procurement | 1028325 | 648409 | 1238585 | 0 | 1028325 | 1 | 6 | 0 | 0 | 0 | 379916 |  |  | 2026-05-16 | 2026-05-16 13:33 | 2026-05-16 | 2026-05-16 15:05 | 2026-05-19 | 2026-05-18 08:03 | 2026-05-31 | 2026-05-31 16:18 | 2026-06-17 | 2026-06-16 18:10 | 2026-06-24 | 2026-06-24 21:09 | 2026-05-18 | 2026-05-19 11:32 | 2026-05-19 | 2026-05-21 13:21 | 2026-05-21 | 2026-05-21 13:45 | 2026-05-30 | 2026-05-30 19:11 |  |  |  |  | 2026-05-31 | 2026-06-01 17:49 | 2026-06-19 | 2026-06-24 14:48 | 2026-06-25 | 2026-06-24 14:49 |  |  | 2026-06-27 | 2026-07-05 19:33 | 2026-07-05 | 2026-07-07 15:07 | 2026-07-08 | 2026-07-07 18:19 | 2026-07-08 | 2026-07-08 19:11 |  |  |  |  | 2026-07-14 17:28 | 2026-07-19 |  | 2026-07-28 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-31 |  |  |  | 2026-08-22 |  | 2026-08-24 |  | 2026-08-25 | [5 empty] | 2026-07-07 | 2026-07-11 07:39 | 2026-05-31 | 2026-05-30 19:24 | Site is Non-RTMI | 2026-05-16 | 2026-05-16 13:26 | 1049648 | 188936 | 0 | 0 | 1222556.0544 | 197248 | 1222556.0544 | 197248 | 2026-06-16 18:18:23 +0530 | Swami Vadnere | DDM2: Mom 14/06/2026 Living Room Moulding and wallpaper design finalized.Wallpaper selection to be finalized.Existing sofa to be retained in client scope.Shift the photo frame to the kitchen wall.TV wall to be finished in texture paint.Kitchen Layout remains the same as previously discussed.Laminate changed as per selections shared in the group.G-profile handles selected.Wall unit to have extended handles.Loft shutters to be push-to-open.Master Bedroom Wardrobe laminate changed as per selection shared in the group.Long handles selected as per approved design (cost will vary accordingly).Loft shutters to be push-to-open.Bed fabric selected.Vanity unit laminate selected (cost will vary as per final selection).Parents' Room Existing wardrobe and bed to be retained.Texture paint to be provided in the room. | 2026-05-30 17:02:12 +0530 | Swami Vadnere | DDM1: MOM 30-05-2026 Living Room Need to explore design options for the dining area and mandir area. Add a photo frame beside the mandir unit (Size: 104 cm x 87 cm). Add a photo frame above the dining area mirror for father's photograph (Tentative Size: 1 ft x 1 ft). Explore sofa back wall design options with mouldings and trims as per the reference images. Internal layouts for the TV unit and crockery unit are finalized. Need to review ceiling design options as per the finalized design theme. Kitchen Internal layouts are finalized. Need to review color options as per the selected finishes. Gold laminate option has been selected; pricing will be updated accordingly Master Bedroom Need to explore bed back wall design options. Wardrobe internals are finalized. Wardrobe finish options shortlisted: Laminate Acrylic Finish (Pricing will vary based on the final selection.) Add a full-size mirror in the dressing area. Wallpaper options have been shortlisted; need to review the selected options in the 3D views. Review and finalize the wardrobe finish option. Parents' Bedroom Need to explore minimal and traditional design options. Existing bed and wardrobe to be retained and incorporated into the design. Bed Size: 5 ft x 6 ft. Wardrobe Size: 7'11" x 5'5". Add a foldable study table in the bedroom. Existing study table size: 600 mm x 450 mm. General Need to verify the shoe rack offer, as it is reflected in the offer but is not appearing in the line-item quotation. | 2026-05-21 13:45:38 +0530 | Royden Henriques | ____________________________________________ Possession : 24th May'26 Payment Mode : B2CÂ CX will pay on 30th May Post offers the amount is 8,69,612/- as per the offer email.Â 105 calendar days for handover which includes Sundays and public holidays.Â Doesn't include Civil Work delays/possession delays. | 2026-06-01 | 2026-05-31 18:26 | 2026-06-17 | 2026-06-16 18:24
20031 | Turnkey | May'26 | Vivek Nalawade | Kalpataru Park Riviera | MUM - GOR | Yes |  |  | Rachna Abhyankar | [5 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1356224 | 9999 | 0 | 0 | 0 | 60 | 0 | 125623 | 135622 | 566802 | 518176.8 |  |  | 2026-05-16 | 2026-05-16 13:49 | 2026-05-17 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-16 | 2026-05-16 13:32 | 0 | 0 | 0 | 0 | 0 | 0 | 1152363 | 203860 | 2026-05-16 13:29:49 +0530 | Unknown | About the Customer **Property Status and Requirements** Customer has received possession and completed tile work for their 2 BHK in Panvel, requiring modular kitchen, TV unit, bed, and wardrobes. **Budget Adjustment for Partial Work** Customer's initial budget of 7-8 lakhs was below the 8-10 lakhs minimum for a 2 BHK, but they agreed to the 8-9 lakhs range for partial work. **Hesitation for Experience Center Visit** Customer is hesitant about travel to the Thane experience center, despite offered pick-up and drop service. **Experience Center Visit Scheduled** Appointment confirmed for Saturday at 12:00 PM at the Thane experience center; customer's wife will attend. | [6 empty] | 2026-05-25 |  | 2026-06-01
20032 | Turnkey | May'26 | Nitish | SNN RAJ | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 2568158 | 319999 | 3599890 | 0 | 0 | 51 | 0 | 0 | 193633 | 1027263 | 1027263.2 |  |  | 2026-05-16 | 2026-05-16 13:41 | 2026-05-16 | 2026-05-21 20:30 | 2026-05-24 | 2026-05-22 12:57 | 2026-08-19 |  | 2026-08-26 |  | 2026-09-02 |  | 2026-05-22 | 2026-05-22 15:56 | 2026-05-23 | 2026-05-25 11:45 | 2026-05-25 | 2026-05-25 14:42 | 2026-06-06 | 2026-06-06 19:03 |  |  |  |  | 2026-08-20 |  | 2026-08-28 |  | 2026-08-29 |  |  |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 | [6 empty] | 2026-09-26 |  | 2026-10-05 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-08 |  |  |  | 2026-10-30 |  | 2026-11-01 |  | 2026-11-02 | [5 empty] | 2026-09-06 |  | 2026-08-15 |  | Unknown | 2026-05-16 | 2026-05-16 13:36 | 3050755 | 549135 | 0 | 0 | 0 | 0 | 2996330.298 | 493956 | 2026-06-29 14:11:29 +0530 | Abhinandan K S | The customer informed us that there is an issue with the construction of the tower due to poor soil quality identified by the builder. As a result, the builder has decided to demolish the entire tower and reconstruct it. The revised timeline indicates that the project is expected to be completed by the end of 2028 or early 2029. In view of this significant delay, the customer wishes to cancel the booking and is seeking a refund of the amount paid to date. The customer will be sending us an email formally requesting the cancellation and refund. We need to discuss this matter with the higher management internally to evaluate the available options and revert to the customer with the appropriate course of action regarding the project. | 2026-06-06 19:22:23 +0530 | Abhinandan K S | RTMI project. Initial measurement to be planned. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. 1st Meeting is aligned on 6th June 2026. | 2026-06-04 13:39:34 +0530 | Patil Madhavi | Some Image was uploaded | 2026-08-20 |  | 2026-08-27 |  | RTMI
20033 | Turnkey | May'26 | Sandya & Vadiraj Pavaman B R | ELEGANT TRANQUILITY | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Hold | Preproduction | Site Readiness 1 | 1358006 | 353999 | 1777389 | 0 | 0 | 23 | 5 | 0 | 0 | 516291 | 487716.4 |  |  | 2026-05-16 | 2026-05-19 17:17 | 2026-05-19 | 2026-05-19 17:27 | 2026-05-21 | 2026-05-21 18:34 | 2026-06-21 | 2026-06-17 12:57 | 2027-01-20 |  | 2027-01-27 |  | 2026-05-21 | 2026-05-25 18:08 | 2026-05-22 | 2026-05-25 18:41 | 2026-05-25 | 2026-05-26 12:09 | 2026-06-04 | 2026-06-04 11:38 |  |  |  |  | 2026-05-29 | 2026-05-25 18:08 | 2027-01-22 |  | 2027-01-23 |  |  |  | 2027-01-30 |  | 2027-01-31 |  | 2027-02-01 |  | 2027-02-02 | [6 empty] | 2027-02-20 |  | 2027-03-01 |  | 2027-02-28 |  | 2027-03-01 |  | 2027-03-02 |  | 2027-03-04 |  |  |  | 2027-03-26 |  | 2027-03-28 |  | 2027-03-29 | [5 empty] | 2027-01-31 |  | 2026-06-05 | 2026-06-17 12:53 | Site is RTMI | 2026-05-16 | 2026-05-16 13:52 | 1506262 | 271127 | 0 | 0 | 0 | 0 | 1447820.3675 | 244441 | 2026-06-17 12:40:29 +0530 | Salpriyan Pm | 20033 - Sandya & Vadiraj Pavaman B R DD1 entry wall - ledgeÂ tv on the left wallÂ partition to separate the foyer and tv cabinetsÂ Partition to be added near the common basinÂ Â builder will provide the pooja doorÂ pooja design to be changedÂ KitchenÂ need to change the designs and coloursÂ All three sides loftÂ sink to the right corner - remove the right-side top and bottom cabinetsÂ wicker basket at the bottom of tall unitÂ only microwave (not inbuild) and mixer (will take out and operate) loft extended above the fridgeÂ UtilityÂ wm and sink to be on the same side (need to check during IM) No dishwasherÂ Gbr mirror inside the wardrobeÂ FF workstationÂ need to redesign as per -imageÂ MBR the door in the walk-in wardrobe area will be closed so need to extend the wardrobe till the endÂ ledge on the tv wall and back wall designÂ DBR loose furniture to be removed on the left of wardrobeÂ the bathroom wall to be plain as to put a DecoreÂ bed back to be similarÂ bed -4'6"x 6'6" mirror inside the wardrobeÂ BathroomÂ remove bottom cabinetsÂ partition wall Modern designs (warm lights)Â False ceiling rose goldÂ Staircase railings to be done from bonito- as agreed by supreet and rasickÂ | 2026-06-04 11:40:47 +0530 | Parasa Sri | Welcome call done. Site will be ready for Initial measurement on december, Client is available on weekend | 2026-05-27 12:10:06 +0530 | Palak Thakur | CDP: (5) Calendar ¦ 20033 - Celebrity Design Presentation (CDP) with the customer ¦ Microsoft Teams | 2026-06-18 | 2026-06-17 13:02 | 2027-01-21 |  | Under Construction | 2026-10-01
20035 | Sub Project |  | SANJAY M TORASKAR | bhoomi pratishtha | MUM - GOR |  | Zoya Ansari |  | Safalta Karkera | [7 empty] | Active | Preproduction | 3D Sign off | 61301 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 36781 | 24520.4 |  |  | 2026-05-16 | 2026-06-11 14:34 | 2026-05-17 | 2026-06-11 14:35 | 2026-06-11 | 2026-06-11 14:35 | 2026-06-12 | 2026-06-11 14:37 | 2026-06-12 | 2026-06-11 14:40 | 2026-06-12 | 2026-06-11 14:44 | 2026-06-11 | 2026-06-11 14:35 | 2026-06-12 | 2026-06-11 14:35 | 2026-06-11 | 2026-06-11 14:36 | 2026-06-12 | 2026-06-11 14:36 |  |  |  |  | 2026-06-11 | 2026-06-11 14:39 | 2026-06-12 | 2026-06-11 14:42 | 2026-06-12 | 2026-06-11 14:42 |  |  | 2026-06-12 | 2026-06-11 14:47 | 2026-06-12 |  | 2026-06-13 |  | 2026-06-14 | [6 empty] | 2026-07-02 |  | 2026-07-11 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-14 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-06-12 |  | 2026-06-12 | 2026-06-11 14:36 | Unknown | 2026-05-16 | 2026-06-11 14:34 | 0 | 0 | 0 | 0 | 0 | 0 | 87670.34 | 9351 | [9 empty] | 2026-06-12 | 2026-06-11 14:39 | 2026-06-12 | 2026-06-11 14:41
20036 | Turnkey | May'26 | Vijay Yadav | yutopia | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | DCM Due | 1535827 | 9999 | 0 | 0 | 0 | 57 | 0 | 143584 | 153583 | 663957 | 564704.4 |  |  | 2026-05-16 | 2026-05-19 13:17 | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-05-16 | 2026-05-16 18:23 | 0 | 0 | 0 | 0 | 0 | 0 | 1301549 | 234278 | 2026-05-17 18:06:52 +0530 | Shreya Sonavane | DCM: Living room- shoe rack with partition on left from entrance, sofa, TV unit, mandir as per vastu, crockery, dinning for 4 Balcony- bar unit Master bedroom- bed, wardrobe, dresser, side table, TV unit Kid's room- for 2 daughter's Bed, wardrobe, side table, dresser Kitchen- civil work linear platform, Flase ceiling to be consider in full flat, mandir & bed position as per vastu | [6 empty] | 2026-06-01 |  | 2026-06-08
20037 | Turnkey | May'26 | Sagar Nautiyal | metro DevBhumi jogeshwari | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1462832 | 9999 | 0 | 0 | 0 | 49 | 0 | 136284 | 146283 | 649651 | 520614.8 |  |  | 2026-05-16 | 2026-05-19 19:44 | 2026-05-17 | 2026-05-23 14:46 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-06-04 |  | 2026-06-12 |  | 2026-06-13 |  |  |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-06-21 |  | 2026-05-30 |  | Unknown | 2026-05-16 | 2026-05-16 17:27 | 0 | 0 | 0 | 0 | 0 | 0 | 1241786 | 221045 | 2026-05-17 15:27:48 +0530 | Khushi Khandelwal | DCM: 750 sqft 4 members Posesseion- Diwali DINING & LIVING AREA 4 seaterÂ Partition in front of door TV wall 3 seater sofa + 2 arm chairÂ Pooja unit KITCHENÂ Parallel kitchen Appliances- Ref., oven, Washing machine, chimney, HOB Crockery/ bar unit- Glass doors Matka provision & RO above sink BEDROOM-01 (Parent's room) WardrobeÂ Bed-Queen / King Side table & dresser BEDROOM-02 (STUDY ROOM) Study table Sofa cum bed Wardrobe Planters BEDROOM-03 (Master bedroom) WardrobeÂ bed-king/ queen Side tableÂ dresser TV provision on wall | 2026-05-16 17:27:36 +0530 | Unknown | About the Customer **Customer Unavailable for Call** Customer is currently in a meeting and unavailable to speak. **Details to be Sent via WhatsApp** Customer requested details via WhatsApp for review. **Agent Seeking Callback Time** Agent asked for a suitable time to connect later. **Customer to Review WhatsApp Details** Customer confirmed they will review details on WhatsApp. |  |  |  | 2026-06-04 |  | 2026-06-11
20038 | Turnkey | May'26 | Gitesh Prabhu |  | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar |  |  | Suraj Jaiswar | Rizwan Mistry |  | Rashmita Das | Sunil Poojary | Active | Preproduction | DEM2 | 1070592 | 316480 | 1414805 | 0 | 0 | 34 | 0 | 0 | 0 | 331099 | 423013.2 |  |  | 2026-05-16 | 2026-05-19 13:16 | 2026-05-16 | 2026-05-19 18:57 | 2026-05-22 | 2026-05-19 22:35 | 2026-06-12 | 2026-06-12 16:51 | 2026-07-02 |  | 2026-07-09 |  | 2026-05-19 | 2026-05-19 22:27 | 2026-05-20 | 2026-05-20 12:56 | 2026-05-20 | 2026-05-21 16:05 | 2026-05-24 | 2026-05-24 17:45 |  |  |  |  | 2026-06-16 | 2026-06-08 18:56 | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-11 | 2026-06-11 19:39 | Site is RTMI | 2026-05-16 | 2026-05-16 18:22 | 1198988 | 215817 | 0 | 0 | 0 | 0 | 1197009.4154 | 192706 | 2026-06-27 20:18:36 +0530 | Batskhem Marpna | Minutes of Meeting held on Date: 27.06.2-2026 MOM-Dated: 27.06.2026 The following pointers have been covered during the session: Foyer: - Shoerack given 4 feet tall and loft addedÂ - TV unit with base shutter and drawers on top - Wall behind tv options to be shown. - Wall design behind sofa to be shown. - Sofa finalised to move towards the window side. - Side table/coffee table incorporated to save space. - Bookshelf changed to fluted glass unit 2 feet wide - False ceiling to be shown Kitchen: - GAIL pipe to be moved towards the window wall to have clear space for wall unit. - Filtered chimney suggested - Blind corner wall unit considered - To check the pull out shelves to be incorporated inside the sink unit - For blind corner at the base, to check if we can remove the vertical partition - Cutlery, cup&saucer and thali tandem considered. - Bottle pull out. Bathrooms: - Common bathroom confirmed to have the mirror with storage only on right hand side of the mirror. - Glass partition in common bath - 2nd bathroom to have both base vanity unit and mirror storage unit to be confirmed. Master bedroom: - Wardrobe internals finalised - Study setup finalised as demonstrated. - side drawers on both side of the bedÂ - Mirror storageÂ - False ceiling considered - Wall design behind bed options to be shown. Other bedroom: - Wardrobe internals finalised * Study setup finalised as demonstrated. * Mirror storageÂ * False ceiling considered * Wall design behind bed options to be shown. Let me know if I missed any pointers. Thanks, Batskhem | 2026-06-07 12:12:19 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-02 13:12:56 +0530 | Sakshi Hire | CDP: civil changes need to make after IM as per site condition need to recheck mandir facing direction as per vastu in mbr wc need to fix washing machine in place of basin | 2026-06-13 | 2026-06-12 16:54 | 2026-07-03 |  | RTMI
20039 | Turnkey | May'26 | VK Anandan Anandan | MJR North Park | BNG - HSR | No Estimate | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-16 | 2026-05-17 10:56 | 2026-05-22 |  | 2026-05-26 |  | 2026-06-01 |  | 2026-06-08 |  | 2026-06-15 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-26 |  | 2026-05-27 | [5 empty] | 2026-06-02 |  | 2026-06-10 |  | 2026-06-11 |  |  |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 | [6 empty] | 2026-07-09 |  | 2026-07-18 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-21 |  |  |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-15 | [5 empty] | 2026-06-19 |  | 2026-05-28 |  | Unknown | 2026-05-16 | 2026-05-17 10:52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-04 13:50:18 +0530 | Patil Madhavi | Some Image was uploaded | 2026-05-16 18:23:53 +0530 | Unknown | Design Brief Doctor has an independent house closeby , but rental property this is , 2 bhk , told him 5.5 including maximiser offer. |  |  |  | 2026-06-02 |  | 2026-06-09
20040 | Turnkey | May'26 | Sinchana | TVS Emerald | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP |  | RaviKumar Battala | Sachin I Betageri | Ranjith Kumar | Murali S | Nidhi Shaw | Raghavendra Gowda | Hold | Preproduction | Site Readiness 2 | 749734 | 449840 | 1218832 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 299894 |  |  | 2026-05-16 | 2026-05-16 21:09 | 2026-05-16 | 2026-05-26 12:32 | 2026-05-26 | 2026-05-26 13:07 | 2026-06-13 | 2026-06-13 16:04 | 2026-06-19 | 2026-06-18 17:54 | 2026-06-27 | 2026-06-26 11:53 | 2026-05-26 | 2026-05-26 13:12 | 2026-05-27 | 2026-05-28 17:23 | 2026-05-28 | 2026-05-28 19:27 | 2026-06-05 | 2026-06-05 13:49 |  |  |  |  | 2026-06-18 | 2026-06-13 13:19 | 2026-06-19 | 2026-06-22 19:55 | 2026-06-23 | 2026-06-22 19:56 |  |  | 2026-06-27 | 2026-06-30 19:44 | 2026-07-03 | 2026-07-03 19:21 | 2026-07-15 | 2026-07-04 11:08 | 2026-07-05 | 2026-07-07 19:16 | [5 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-11 |  | 2026-06-06 | 2026-06-13 15:58 | Site is RTMI | 2026-05-16 | 2026-05-16 18:35 | 1032909 | 185923 | 0 | 0 | 0 | 0 | 875655.58 | 136484 | 2026-07-11 12:30:50 +0530 | Abhinandan K S |  | 2026-06-28 18:41:44 +0530 | Aishwarya C | Some Image was uploaded | 2026-06-28 13:37:04 +0530 | Aishwarya C | Some Image was uploaded | 2026-06-14 | 2026-06-13 16:11 | 2026-06-19 | 2026-06-18 17:54 | Under Construction | 2026-06-13
20041 | Turnkey | May'26 | Rajesh narkar | 77 cross road | MUM - GOR | Yes | Khyati Bandi | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Hold | Design | DEM1 | 1091380 | 144351 | 1443508 | 0 | 0 | 21 | 28 | 0 | 73925 | 489319 | 383784.8 |  |  | 2026-05-16 | 2026-05-16 19:04 | 2026-05-23 | 2026-05-23 16:34 | 2026-05-26 | 2026-05-26 17:06 | 2026-08-06 |  | 2026-08-13 |  | 2026-09-29 |  | 2026-05-26 | 2026-05-23 22:09 | 2026-05-27 | 2026-05-26 17:11 | 2026-05-26 | 2026-05-27 12:07 | 2026-05-30 | 2026-05-30 16:45 |  |  |  |  | 2026-08-07 |  | 2026-09-24 |  | 2026-09-25 |  |  |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 | [6 empty] | 2026-10-23 |  | 2026-11-01 |  | 2026-10-31 |  | 2026-11-01 |  | 2026-11-02 |  | 2026-11-04 |  |  |  | 2026-11-26 |  | 2026-11-28 |  | 2026-11-29 | [5 empty] | 2026-10-03 |  | 2026-08-02 |  | Unknown | 2026-05-16 | 2026-05-16 19:04 | 1223312 | 220196 | 0 | 0 | 0 | 0 | 1216907.7971 | 196448 | 2026-07-03 11:13:10 +0530 | Vishakha Vaishnav | Others: Cx mom is hospitalized so cx is unable to attend the meetings | 2026-06-06 11:48:14 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-30 16:43:41 +0530 | Vishakha Vaishnav | "Welcome call done". Initial measurement : TBD as site is not accessible DEM Dates -Â DEM 1 - on 7th June 2026 DEM 2 - TBD DEM 3 - TBD Possession date :September 2026 Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-08-07 |  | 2026-08-14 |  | Under Construction | 2026-09-01
20042 | Turnkey | May'26 | shravan sanil | 73 East | MUM - GOR | Yes | Anjali Jain | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Sanskruti Yadav |  | Active | Design | DEM1 | 1476281 | 205026 | 2050264 | 0 | 0 | 37 | 0 | 0 | 90230 | 631408 | 549616.4 |  |  | 2026-05-16 | 2026-05-17 11:59 | 2026-05-30 | 2026-05-30 11:46 | 2026-06-02 | 2026-06-02 19:42 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-02 | 2026-05-31 00:38 | 2026-06-03 | 2026-06-06 11:00 | 2026-06-06 | 2026-06-08 18:33 | 2026-06-13 | 2026-06-13 19:09 |  |  |  |  | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-16 | 2026-05-16 19:12 | 1739819 | 310444 | 0 | 0 | 0 | 0 | 1732814.248 | 276958 | 2026-07-10 15:16:34 +0530 | Vishakha Vaishnav | There was a discrepancy in the quotation because of the flat height cx wanted an clarification and then he will proceed | 2026-06-26 18:34:03 +0530 | Anjali Jain | DDM1 Transition Download As discussed with Sweta, A. Living Room Modular Unit are (Pre laminate) Â 1. Shoe rack Â 2. Tall unitÂ 3. Tv unit Drawer 4. Crockery unit 5.Safety door (21 Sqft) 6. The mandir store Product B. Kitchen Semi Modular units are 1.Loft Cabinet -Â Â (laminate) 2.Base Unit 3 Drawers qty 1 (Wire basket), Bottel pull out qty 1,Â shutter (Semi modular units) (laminate) 3.Â Top cabinetÂ (laminate) C. Kids Bedroom Modular unit are (Pre laminate) 1.Side table 2. Loft cabinet 3. Wardrobe with loftÂ 4. Free bedÂ D. Master Bedroom Modular unit are (Pre laminate) 1.Wardrobe with Loft (internals given basic) 2.Kid Wardrobe 3.SIDE TABLE 4.Bed Kids bedroom vanity 1.Vaity base (consider basic) Master bedroom Bathroom & Vanity 1. Vaity base (consider basic) Living and dining Bathroom & Toilet 1. vanity unitÂ Additional Scope of Work 1.Electrical (55 NOS added in quotation - 39325) 2.False ceiling (300 sq.ft added in quotation For living room) 3.Royal Luxury Emulsion matt (1950 sqft added in quotation) 4.Tractor Emulsion(750 sq.ft added in quotation) 5. Wall paneling Ac pelmetÂ 6. Texture paint (10000-/) 7. Pop punning 8. Quartz Installtion only consider Others Cleaning Charges, Thinner Cleaning and Floor Cleaning - 2 BHK 10 to 15Â Project Management fees -Â Celebrity Design fees -Â Transportation & Lifting Charges -Â Floor Covering - 750 sqft - Note Â Units are not proper attching images for the sameÂ quartz is not in bonito scopeÂ Decor not consider in BOQ only pop punning and texture paint is thereÂ Paint quantity is not proper It'll change after design meeting Decor and additional scope of unit | 2026-06-13 19:08:39 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Done DEM Dates -Â DEM 1 - Need to align for weekend only 20th June DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-19 |  | 2026-06-26 |  | RTMI
20043 | Turnkey | May'26 | Mayuresh Mohan Jadhav | Siddhivinayak | MUM - GOR | Yes | Saif Shaikh | Vishakha Vaishnav | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Uday Yadruk | Rizwan Mistry |  | Ashish Jha | Sunil Poojary | Active | Design | DEM3 | 1418532 | 229949 | 1418095 | 0 | 0 | 3 | 0 | 0 | 0 | 649234 | 539348.8 |  |  | 2026-05-16 | 2026-05-16 20:25 | 2026-05-16 | 2026-05-17 16:08 | 2026-05-23 | 2026-05-23 22:19 | 2026-06-11 | 2026-06-12 12:14 | 2026-07-12 | 2026-07-11 20:22 | 2026-07-16 |  | 2026-05-23 | 2026-05-27 17:54 | 2026-05-24 | 2026-05-30 13:51 | 2026-05-30 | 2026-05-30 16:16 | 2026-06-04 | 2026-06-04 19:05 |  |  |  |  | 2026-06-10 | 2026-06-11 17:37 | 2026-07-12 | 2026-07-12 19:58 | 2026-07-13 | 2026-07-12 20:13 |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-05 | 2026-06-11 19:34 | Site is RTMI | 2026-05-16 | 2026-05-16 19:46 | 1201775 | 216319 | 0 | 0 | 0 | 0 | 1479701.7848 | 255335 | 2026-06-04 19:00:19 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Already done DEM Dates -Â DEM 1 - Can align the meeting either on weekends or on 11th June 2026 DEM 2 - TBD DEM 3 - TBD Possession date : Mid July 2026 Customer will make 10% after DEM 1 meeting Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-02 15:19:37 +0530 | Rahul Agrawal | CDP RECORDING 20043 - Celebrity Design Presentation (CDP) with the customer-20260523_072606UTC-Meeting Recording.mp4 | 2026-05-30 16:14:31 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: 15th July 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible. * IM 31st May 2026 * DEM 1 6th June 2026 * 10% Payment Stage 8th June 2026 *Civil work - client would be adding the wash basin in the bathroom, which will take 2 days. *Transaction will be B2C self-funding. Informed that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11, 99,346 Offers Discussed During the Call: PM fee waiver (5%) May '26 Net Special Studio Offer Laminate Upgrade - May '26 Campaign 100% GST Waiver Final Closing Value Discussed: 11,49, 746 Checklist terms - descoping, delay compensation, agreement terms are clear Extra commitments - nothing | 2026-06-13 | 2026-06-12 12:16 | 2026-07-12 | 2026-07-11 20:27 | Under Construction | 2026-07-15
20046 | Turnkey | May'26 | Sameer More | haware horizon | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 871529 | 174306 | 1153017 | 0 | 0 | 3 | 39 | 0 | 0 | 356275 | 340948.4 |  |  | 2026-05-16 | 2026-05-19 16:14 | 2026-05-16 | 2026-05-19 16:26 | 2026-05-19 | 2026-05-19 21:09 | 2026-05-30 | 2026-05-30 18:28 | 2026-07-13 | 2026-07-12 13:14 | 2026-07-18 |  | 2026-05-20 | 2026-05-17 20:15 | 2026-05-20 | 2026-05-19 20:07 | 2026-05-20 | 2026-05-20 10:15 | 2026-05-24 | 2026-05-24 16:56 |  |  |  |  | 2026-05-30 | 2026-05-30 18:32 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-05-25 | 2026-05-30 18:08 | Site is Non-RTMI | 2026-05-16 | 2026-05-16 19:59 | 977133 | 175884 | 0 | 0 | 0 | 0 | 977132.7105 | 156875 | 2026-07-08 13:53:38 +0530 | Batskhem Marpna | MOM- Sameer More Dated: 08.07.2026 These points have been covered during discussion - Living/Dining: - Wall mouldings behind the sofa with Wallpaper in a niche - Tv base unit - No dining table needed - wall design in Dining wall - storage cabinet below the existing Mandir - All designs are good to go - False ceiling Kitchen: - Wall open unit added in the corner - One cabinet changed to fluted glass unit - All designs are good to go Parents bedroom: - No bed required - study table - wardrobe - internals changed - no false ceiling Master bedroom: - wardrobe - internals changed - wall designs behind the bed - fasle ceiling. As discussed we will meet on 11th on the second half for material selection. Thanks, Batskhem | 2026-05-30 18:50:31 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-30 11:03:15 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-31 | 2026-05-30 18:32 | 2026-07-13 | 2026-07-12 13:16
20047 | Turnkey | May'26 | Aparajita Singh | SOBHA Sentosa | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1802125 | 9999 | 0 | 0 | 0 | 59 | 0 | 170214 | 180213 | 765386 | 676313.6 |  |  | 2026-05-16 | 2026-05-17 21:34 | 2026-05-19 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-16 | 2026-05-16 20:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1527225 | 274900 | 2026-05-22 12:06:29 +0530 | Maspi Das | Cx name : Aparajita Property - Sobha Sentosa 3BHK Profession : IT Possession : Done How many people will be staying : 5 (mostly 2) Kids- ---- Theme : Contemporary + Bohemian with Pop-up colors (Pastel colors) Entrance -facing : West Budget : below 15L CDP - 23.05.2026 at 12 Foyer- Shoe rack (slick one) Wallpapers with wall paneling design (no beading) TV unit- 55" TV Base drawer units Side storage but not something box kind of storage should be little open Something with texture and patterns (wallpaper) Sofa wall- Curved sofa No beading Some ledges on top for artifacts Some wall papers *Can add partition* OPTIONAL **FALSE CEILING- THE DROPDOWN ONE FOR THE COMMON AREAS** **FALSE CEILING- THE DROPDOWN ONE FOR THE BEDROOMS** Dining area- 4-seater circular table Pooja Unit with Crockery unit (concept ref images shared in group by client Dining right wall (some photos or paintings) Kitchen- Sink on the left wall in center HOB on Foyer side wall in between Tall unit - microwave and oven Rolling shutter for appliances Tall unit - Pantry cum Appliance unit (opt2) Mix of Glass & Laminate *Cylinder unit* Utility- As much as storage WM on the right corner- on top Ledges 3' sink (sink is given) On top of sink wall units with ledges (no LOFT) Granite can be consider (inside the kitchen) BR3 (GBR)- Queen size bed Wardrobes Accent wall Study unit (can consider) *Can consider a seating cozy space on the corner beside the Window* BR2 (KBR) - Minimal Kid's element or designs as a KBR Queen size bed Wardrobes Accent wall Study unit (can consider) BR1 (MBR)- Queen size bed Accent wall Dresser unit- right corner most Wardrobe Dresser wall complimenting the Accent wall Vanity only for the MBR Storage | 2026-05-21 18:58:52 +0530 | Nidhi Shaw | Gross Budget max 15 lakhs RTMI Husband and wife Family will keep visiting | 2026-05-16 20:53:59 +0530 | Unknown | About the Customer **3 BHK Interior Design Needs** Customer requires interior design for a 3 BHK apartment in Sobha Sentosa, Varthur, with possession received. Budget is 20-25 Lakhs, preferring a minimalist boho, space-saving design. **Hesitation for Experience Center Visit** Customer is hesitant to visit the experience center due to distance and traffic, preferring an online meeting. **Cab Arrangement Offered** Agent offered to arrange a cab for pick-up and drop to overcome travel concerns. **Agreed to Visit Today** Customer agreed to visit the experience center today. **Location Details and Floor Plan Pending** Agent to share experience center locations via WhatsApp and requested the floor plan. | 2026-06-07 |  | 2026-06-14
20048 | Turnkey | May'26 | Pallavi Arsekar | Wadhwa Atmosphere | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1364540 | 9999 | 0 | 0 | 0 | 55 | 0 | 126455 | 136454 | 565825 | 525806.8 |  |  | 2026-05-16 | 2026-05-16 22:59 | 2026-05-20 | 2026-05-20 17:52 | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-16 | 2026-05-16 22:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1156390 | 208150 | 2026-05-20 17:52:11 +0530 | Krutika Vernekar | DCM: 2 BHK Interior Scope 650 Sq. Ft. Carpet Area Safety door with premium finish and coordinated main door design.False ceiling design planned across living and passage areas with balanced lighting layout for a clean and spacious look.Functional shoe rack near entrance with concealed storage and minimal elevation treatment.TV unit designed with practical storage and modern panelling details.Folding dining setup in carpentry to optimize space utilization while maintaining comfortable movement flow.Mandir planned behind the sofa wall as per Vastu considerations with subtle partition detailing and warm ambience.POP panning wall designs proposed for both sofa backdrop and TV wall to create elegant focal features in the living area.Kitchen & UtilityExisting loft to be retained and finished neatly with matching laminate treatment.Additional utility storage planned for daily-use items and maintenance essentials.Dry balcony maintenance door to be fully panelled for a seamless and uniform kitchen elevation appearance.Mothers BedroomSliding wardrobe designed for efficient space management with organized internal storage.Dedicated dresser unit with mirror and utility storage integrated within the design language.Existing bed to be retained and coordinated with the overall room aesthetics.Master BedroomSliding wardrobe with modern finish and optimized storage planning.Mirror storage unit designed with functional utility and clean elevation treatment.Existing bed to be retained and blended with the new interior theme for a cohesive look. | [6 empty] | 2026-05-31 |  | 2026-06-07
20050 | Turnkey | May'26 | Suchi Pandey | Ajmera Florenza | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | DCM Due | 1488915 | 9999 | 0 | 0 | 0 | 56 | 0 | 138893 | 148892 | 595566 | 595566 |  |  | 2026-05-16 | 2026-05-20 12:15 | 2026-05-17 | 2026-05-20 12:19 | 2026-05-22 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-16 | 2026-05-17 11:27 | 0 | 0 | 0 | 0 | 0 | 0 | 1261793 | 227122 | 2026-05-29 12:15:34 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-20 12:08:51 +0530 | Rhea Rathod | DCM: Possession - In hand Family of 3 Profession - IT West facing Modern zen - Earthy Earthy yellow, brown beiges, creams, Greens in the form of plants Existing furniture -Â -Bed - King size bed(6x6.6)Â -Study table, TV unit(bottom) - Cane finishÂ -Dining table - 6 seater -Book shelf (Wooden)- 4x4 rotating -Side tables -2Â -Sitar Â Foyer -Â - Ganapati photo frame - existing - 1.2x1.9 - ivory frame existing - Shoe rack - 20-25 pairs wall mounted - Seater - wall mounted - foldable seater to be checked Living - - Wall concept for the existing tv unit - 42" TV - Cane finished sofa - Just one 3+1 seater sofa - Sofa back wall - wall concept - with beadings and wallpaper Pooja unitÂ - sleek - to be integrated into the design Kitchen - - Single door fridge - Microwave, grinder, stone grinder - L counter - Granite and sink - existing - Pantry unit with shelf - One side loft with chimney patta - Sleek tall unit with wall unit- Crockery unit - collection of glasses - Height of the Counter top to be checked Master bedroom- - Wardrobe with loft - King size existing bed - Wall concept - Foldable study - Marker board - 2.5' Bedroom - 1 - Bunker bed - Wardrobe with loft - Wall concept as per the Kids theme Washrooms - Glass partition - master bedroom - Vanity units - both bathrooms |  |  |  | 2026-05-31 |  | 2026-06-07
20052 | Turnkey | May'26 | Paresh Jain | Alpine Primo | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | DCM Due | 3045502 | 9999 | 0 | 0 | 0 | 57 | 0 | 294551 | 304550 | 1273076 | 1163326 |  |  | 2026-05-17 | 2026-05-19 13:15 | 2026-05-17 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-05-17 | 2026-05-19 13:15 | 0 | 0 | 0 | 0 | 0 | 0 | 2580934 | 464568 | 2026-05-17 18:16:38 +0530 | Rahul Agrawal | DCM: Date: 17/05/26 Property Type: 3BHK [Design Full Flat] Area: 949 sq. ft. Possession: Next Month (Soft) / August (Ready Possession) Family Profile: * Working professional couple (Husband: Big F / Wife: Manager) Son: 19 years old Parents: Visiting General Requirement: Vastu Compliant Area-Wise Requirements 1. Foyer Shoe rack (Outside or Inside) with single drawer. Safety door. Foyer wall design. Wants proper panelling. 2. Living & Dining Crockery: In-wall / broke (Basic). Mandir: On dining wall with storage below. Dining: 4-seater dining table. Shoe Rack: If inside. Sofa: 3 + 1 seating. Jhulla: (Swing). TV Unit: Included. Panelling: All 3 walls panelling. Note: Removing powder toilet. 3. Guest Bedroom Study table with wardrobe (Facing West). Sofa cum Bed. TV Unit: 2 drawers / 2 feet / 2 drawers with center glass. Panelling for both rooms. 4. Master Bedroom Room Height: 11 ft total room height. Queen Bed. Wardrobe with loft (Befiler unit / Glass fluted). Side table cum dressing. Glass cabinet (Pure display). Washroom door flush. 5. Son's Bedroom Wardrobe + loft (Sliding). Queen Bed. Side table. Study unit. Dressing unit. False ceiling down 6 (Wants heavy). Civil & Additional Work Soft Civil: False ceiling, Painting, Electrical. Bathrooms: * Vanity units x 2. Glass partition (Optional). Budget Details Initial Budget: 10 12 Lakh | [6 empty] | 2026-06-05 |  | 2026-06-12
20053 | Sub Project |  | Madhumita Das Pal | Bhartiya City Nikoo Homes | BNG - HRBR |  | Sreelakshmi M | Rajeshwari S | Shibin Lal |  |  | Nikhil Mogeraya | Saddam Hussain Z M | Murali S |  |  | Completed | Complete | Completed | 3157 | 3196 | 0 | 0 | 3157 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-17 | 2026-05-19 18:34 | 2026-05-18 | 2026-05-19 18:34 | 2026-05-19 | 2026-05-19 18:34 | 2026-05-20 | 2026-05-19 18:36 | 2026-05-20 | 2026-05-19 18:37 | 2026-05-20 | 2026-05-19 18:39 | 2026-05-19 | 2026-05-19 18:34 | 2026-05-20 |  | 2026-05-20 |  | 2026-05-21 | [5 empty] | 2026-05-19 | 2026-05-19 18:36 | 2026-05-20 | 2026-05-19 18:38 | 2026-05-20 | 2026-05-19 18:38 |  |  | 2026-06-12 | 2026-05-19 18:34 | 2026-05-21 | 2026-05-20 17:12 | 2026-05-27 | 2026-05-26 10:54 | 2026-05-27 | 2026-05-26 10:54 |  |  |  |  | 2026-06-15 11:59 | 2026-06-16 | 2026-06-15 13:58 | 2026-06-17 | 2026-06-15 14:47 | 2026-06-16 | 2026-06-20 15:04 | 2026-06-15 | 2026-06-20 16:59 | 2026-06-20 | 2026-06-20 17:00 | 2026-06-21 | 2026-06-20 17:12 |  |  | 2026-06-22 | 2026-06-20 17:36 | 2026-06-22 | 2026-06-20 17:37 | 2026-06-22 | 2026-06-22 17:40 |  |  |  |  | 2026-05-20 | 2026-05-26 10:53 | 2026-05-22 | 2026-05-19 18:35 | Unknown | 2026-05-17 | 2026-05-19 18:33 | 0 | 0 | 0 | 0 | 45049 | 8108 | 45049 | 8108 | [9 empty] | 2026-05-20 | 2026-05-19 18:36 | 2026-05-20 | 2026-05-19 18:38
20054 | Turnkey | May'26 | Saiveena Suresh | shree ram | BNG - HSR | Yes | Chittipireddy Sriharish | Akshay Ds | Kowshik |  |  | Nanda Kumar |  |  | Rajoshi Sarkar | Sunil Kumar S M | Active | Preproduction | CM | 1603271 | 320654 | 2105563 | 0 | 0 | 4 | 0 | 0 | 0 | 697842 | 584774.8 |  |  | 2026-05-17 | 2026-05-17 15:18 | 2026-05-18 | 2026-05-19 13:29 | 2026-05-22 | 2026-05-22 12:01 | 2026-06-14 | 2026-06-14 20:03 | 2026-07-11 | 2026-07-10 16:10 | 2026-07-17 |  | 2026-05-22 | 2026-05-23 11:06 | 2026-05-23 | 2026-05-27 11:00 | 2026-05-27 | 2026-05-27 18:06 | 2026-06-06 | 2026-06-06 17:28 |  |  |  |  | 2026-06-14 | 2026-06-16 12:27 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-07 | 2026-06-14 19:59 | Site is RTMI | 2026-05-17 | 2026-05-17 15:07 | 1784375 | 321187 | 0 | 0 | 0 | 0 | 1739885.8154 | 287278 | 2026-06-14 14:04:44 +0530 | Chittipireddy Sriharish | DDM1: Foyer - Shoe rack need to be placed next to the parking wall Living room TV unit - no changes Partition - need suggestions Kitchen - tall unit need to be added lofts above the window ( wall to wall) Chimney side wall need to be constructed Cylinder provision need to be cross checked during cross measurements Dining area wash basin - need to be provided next to the tall units Stair case wall need to be high lighted ( wall accents options) PBR No changes first floor MBR Bed need to be placed adjust to the wardrobe wall wardrobe placement to be changed to window opposite wall Foldable table KBR No changes Servant room wardrobe wall - minimal storage need to be added same as wall depth | 2026-06-02 11:36:35 +0530 | Saranya Thiyagarajan | CDP shoe storage as per vastu dining- corner- tall unit into washbasin area fridge space need to be checked kitchen top corner- create tall unit- right end kitchen door- 2'9" chimney option- on window or ceiling pooja - wooden door- bells hanging gopuram shape kitchen design is the first priority | 2026-06-02 11:35:55 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-15 | 2026-06-14 20:06 | 2026-07-11 |  | RTMI
20055 | Turnkey | May'26 | Nikhil Agarwal | Shobha | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 3540358 | 9999 | 0 | 0 | 0 | 59 | 0 | 344037 | 354036 | 1471301 | 1360985.6 |  |  | 2026-05-17 | 2026-05-17 14:21 | 2026-05-17 | 2026-05-26 15:47 | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-17 | 2026-05-17 14:20 | 0 | 0 | 0 | 0 | 0 | 0 | 3000304 | 540054 | 2026-06-02 11:57:05 +0530 | Ankita Agarwal | CDP: CX NikhilÂ - FOYER AND LIVING TO BE IN MEMBRANE FINISHÂ - CHANGE MIRROR PLACE TO OPP SIDEÂ - CUSTOM WALLPAPERÂ - OPEN PLACE FOR SHOE TO BE SLIPPED INÂ - BUDDHA IDOL TO BE KEPT SUGGEST THE PLACEÂ - ADD WALL TRIMS OPP TO THE foyer - add shelves on the painting wallÂ - change the sofa layout to l shape with 2 seaterÂ - wall beading on dining wall (arch to be considered) - close the crockery unitÂ - change the dining back wallÂ - add wall cabinet no open shelf maybe one or twoÂ - gbr mirror with storageÂ - COD ON TV AREAÂ - BEADINGÂ - TALL CABINETÂ | 2026-05-26 15:38:09 +0530 | Ankita Agarwal | DCM: CX NikhilÂ Name : Nikhil AgarwalÂ MD : East facing Family members : 4+1 daughter 1yr & parents (Daughter - kiwi) possession : SEP move in : DECÂ Â CDP date :Â Budget : 20L (25-30 BUDGET) location : chimaya road theme : santorni Property -Sobha neopolisÂ FoyerÂ - shoe Unit with arch panel on topÂ - seating space - white and pastel tonesÂ - plats to be involved in the designÂ - Mirror option if possibleÂ -Â LIVINGÂ - TV AND POOJA UNITÂ - FLOOR BASEDÂ - DISPLAY UNITÂ - ALL THE WIERS TO BE HIDDENÂ - FLAP UP SHUTTER FOR SOCKET - STANDING POOJA SET UPÂ - 4-5 IDOLS AND SHIVLING - FLUTED GLASS SHUTTER (ARCH SOOR TAKE SHOE UNIT DISPLAY REFF) - TV UNIT REFF TAKENÂ - CURVED SOFAÂ + RECLINERÂ - ATTACHED DINING TABLE TO WALLÂ - CROCKERY + COFFEE MAKER + BAR - DINING BACK WALL DESIGNÂ - ADD PLATFORM FOR CURVE SOFA - ADD ARCH BEHIND THE DINING AREAÂ - TRY FOR MIRROR OR WALLPAPER INSIDE THE ARCHÂ - MEMORY WALLÂ KITCHENÂ -Â MICROWAVE (APPIANCES UNIT) - PANTRY UNIT (IN UTILITY) - APPLIANSE TO GO INÂ - TOP CABINETÂ - MUG HOLDERÂ - WALL UNIT HEIGHT TO BE MAXÂ COVER CHIMNEY PANELÂ - NO LOFTÂ - ROLL UP SHUTTERÂ - SINGLE DOOR FRIDGEÂ - UTILITYÂ - JANITOR CABINET (PULLOUT) - EXTRA SINKÂ - LOFTÂ - DW WMÂ - STORAGE AS MUCH AS POSSIBLEÂ BALCONYÂ - WALL GARDEN NEAR THE GARDE SET UP - LEDGE TO SIT AT RAILINGÂ - SWING A BALCONYÂ - BALCONY DECOR TO BE SUGGESTEDÂ - FLOOR WOODENÂ - FLOEING WATER CONCEPTÂ ALCOVEÂ - FLOTING DRAWERÂ - PRNTERÂ - STUDY OR WFHÂ - 4' TO BE SLEEK SIDEÂ -REFF TAKEN ALONG WITH WALL SHELFSÂ Â Bathroom 3Â Â - Decor it nicelyÂ bedroom (kids room) - rock climbingÂ - lego wallÂ - wardrobe aristo with wallpaper - activity area - soft toy display - net corner for the soft toyÂ - pastel green with pastel yellow (mint green) - study option check for size of room Master bedroomÂ - walk in wardrobe aristo - dresser set up in walkin - Tv UnitÂ - Study table (2 seater) curve the break of tv and studyÂ - dresserÂ - King/queen size bedÂ - side tableÂ - bed back wall deignÂ - dresser Next to the bed - tv and study on bed wallÂ - bathroom StorageÂ Â Parents bedroom (Bedroom 2) - Wardrobe (hinged with loft) - tv unitÂ - work space (optional) - queen side bed + side tableÂ - bed back wall designÂ other areaÂ Â - common area FC | 2026-05-17 14:22:38 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-06-07 |  | 2026-06-14
20056 | Turnkey | May'26 | Rajesh Bidaye | Puranik rumha | MUM - Thane | No Estimate | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-17 | 2026-05-19 11:13 | 2026-05-18 |  | 2026-05-17 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-05-17 |  | 2026-05-18 |  | 2026-05-18 |  | 2026-05-19 | [5 empty] | 2026-05-25 |  | 2026-06-02 |  | 2026-06-03 |  |  |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-13 | [6 empty] | 2026-07-01 |  | 2026-07-10 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-08-04 |  | 2026-08-06 |  | 2026-08-07 | [5 empty] | 2026-06-11 |  | 2026-05-20 |  | Unknown | 2026-05-17 | 2026-05-19 11:09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-19 11:17:31 +0530 | Nishtha Valawalkar | CX have property at Puranik's which is 2 BHK and also at Dadar. Property finalization is pending. I pitched pre-lam. CX Budget - 10 Lacs Budget expectation setting - 13 to 15 lacs CX wants to renovate a washroom - It has been explained to that this will be in their scope. | 2026-05-19 11:14:39 +0530 | Nishtha Valawalkar | Some Image was uploaded |  |  |  | 2026-05-25 |  | 2026-06-01
20057 | Turnkey | May'26 | janmenjaya mohanty | Mahavir empire | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 2155017 | 9999 | 0 | 0 | 0 | 56 | 0 | 205503 | 215502 | 955748 | 768266 |  |  | 2026-05-17 | 2026-05-17 22:15 | 2026-05-19 | 2026-05-19 13:00 | 2026-05-20 |  | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-05-20 |  | 2026-05-21 |  | 2026-05-21 |  | 2026-05-22 | [5 empty] | 2026-05-28 |  | 2026-06-05 |  | 2026-06-06 |  |  |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-16 | [6 empty] | 2026-07-04 |  | 2026-07-13 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-08-07 |  | 2026-08-09 |  | 2026-08-10 | [5 empty] | 2026-06-14 |  | 2026-05-23 |  | Unknown | 2026-05-17 | 2026-05-17 22:15 | 0 | 0 | 0 | 0 | 0 | 0 | 1826286 | 328731 | 2026-05-21 11:42:59 +0530 | Bhawaya Goyal | DCM: Cx - Mohanty No of people - 4-6 MB will be used by couple and childÂ Direction - WestÂ Budget : 10 max suggested : 15-17 L Common Bedroom will be for parentsÂ Planning done as per vaastuÂ Existing bed in common bedroomÂ Living -Â 6x4 shoerack 2/1.5 seating. Safety door 2ft balcony living to master bedroom 3+2seater sofa ,tv unit ,4 seater dining, aquarium, Tv unit with glass displayÂ Panelling to level the wall Swing (client scope) Kitchen- Modular kitchenÂ Gas burner on oppo. side Tall appliance unitÂ Service platform 20" Wicker basketÂ 2 Gas cylinder cabinetÂ Rolling shutterÂ (Not very congested need open units ) Base , wall , loft Bathroom Â vanity unitÂ Wall mounted wash basin Common bedroom Existing bed Wardrobe 18" depth Dressing table Master bedroomÂ King size bedÂ 18" wardrobe depth mirror in south Used cloth storageÂ Window side study unitÂ Dressing + wardrobeÂ (2'6" dressing -8' wardrobe-3'feet study unit ) Pooja room 2ft storage for PoojaÂ Low seating pooja unitÂ Sofa cum bedÂ Study unitÂ L Glass rack 3x3 Washing machine back, ACP sheet for packing Opp pooja wall open storageÂ Crocery or display unit beside study unit (open shelves) / Spiritual theme wallÂ wooden partition Partition at kitchen entrance due to open kitchen. Colour theme - all south wall red theme colour or decor Kitchen cabinet -white theme Â False ceiling should mainly in terrace area Cornices in entire ceiling border ElectricalÂ Painting Profile light / surface light No wall behind washing machine , packing req. ACP sheet 4ft balcony extension in living room CDP- next Sunday 24th May | [6 empty] | 2026-05-28 |  | 2026-06-04
20058 | Turnkey | May'26 | Vaishali desai | integrated ramicon | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Hold | Design | DEM1 | 1084083 | 151037 | 1510370 | 0 | 0 | 37 | 13 | 0 | 65780 | 481036 | 386230.8 |  |  | 2026-05-17 | 2026-05-24 20:09 | 2026-05-17 | 2026-05-24 20:27 | 2026-05-27 | 2026-05-26 15:47 | 2026-09-14 |  | 2026-09-21 |  | 2026-09-28 |  | 2026-05-24 | 2026-05-24 20:27 | 2026-05-27 | 2026-05-26 15:54 | 2026-05-26 | 2026-05-26 19:21 | 2026-06-03 | 2026-06-03 19:05 |  |  |  |  | 2026-09-15 |  | 2026-09-23 |  | 2026-09-24 |  |  |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-04 | [6 empty] | 2026-10-22 |  | 2026-10-31 |  | 2026-10-30 |  | 2026-10-31 |  | 2026-11-01 |  | 2026-11-03 |  |  |  | 2026-11-25 |  | 2026-11-27 |  | 2026-11-28 | [5 empty] | 2026-10-02 |  | 2026-09-10 |  | Unknown | 2026-05-17 | 2026-05-24 20:08 | 1279974 | 230395 | 0 | 0 | 0 | 0 | 1273200.0612 | 203685 | 2026-07-02 17:01:52 +0530 | Vishakha Vaishnav | Others: CX will get the possession in month of September | 2026-06-03 19:04:34 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : As project is under construction cx will update us i group DEM Dates -Â DEM 1 - Can be done on 13 June need to confirm with designer DEM 2 - TBD DEM 3 - TBD Possession date : August / September Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-05-30 16:48:57 +0530 | Vishakha Vaishnav | Tried connecting cx , didn't answered the call | 2026-09-15 |  | 2026-09-22 |  | Under Construction | 2026-09-30
20060 | Turnkey | May'26 | Jenish Mansukhlal | Raymond Address Season 1 | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 3765526 | 9999 | 0 | 0 | 0 | 59 | 0 | 366554 | 376553 | 1591330 | 1421090.4 |  |  | 2026-05-17 | 2026-05-17 22:17 | 2026-05-18 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-15 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-13 |  | 2026-08-17 |  |  |  | 2026-10-06 |  | 2026-10-07 |  | 2026-10-10 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-17 | 2026-05-17 22:16 | 0 | 0 | 0 | 0 | 0 | 0 | 3191124 | 574402 | [9 empty] | 2026-06-03 |  | 2026-06-10
20061 | Turnkey | May'26 | Deepak Lohani | SNN Raj Etternia | BNG - HSR | No Estimate | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-16 | 2026-05-19 12:33 | 2026-06-14 |  | 2026-06-01 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-07-08 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-06-25 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-20 |  | Unknown | 2026-05-16 | 2026-05-19 12:32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-21 12:28:58 +0530 | Maspi Das | RGM Date : 14.06.2026 CDP date : Client will let us know PID: 20061 Name : Deepak Lohani From - Lucknow Profession : IT Budget : 10-12L 3BHK Property : SNN RAJ ETTERNIA Location : Kudlu Site Access Date : October Main door facing : EAST Total Members : 3 Kids - 1Â Boy - 9 yearsÂ Theme : NeutralÂ **Pooja unit plan based on the plan, space and Vastu** **False ceiling for the Common areas**Â Scope of Work :Â Foyer- One long floor to ceiling mirror One side mirror and one design with shoe cabinet (full length) TV unit- Base unit with Ledges or a unit for storageÂ With wall design (simple and minimal) Consider a partition (based on design and space) Sofa wall- 3 seater with and accent chair and a small ottoman Wall design ref (can play around with colors and lights- Focus wall so need to design based on that) Dining wall- 6 seater Crockery unit Kitchen- Tall unit Appliances- microwave, air fryer, mixer, toaster, coffee maker Chimney panel LoftsÂ Wall Base *Breakfast counter need to check the space and plan* **Plan and show janitor where it can be placed - NOT IN BD SCOPE** GBR- Accent wall WorkstationÂ Queen size bed wardrobe (with drawers below) mirror on wall can be planned WorkstationÂ KBR- Queen size bed Wardrobe with mirror and extra storage for used clothesÂ Piano, guitar display Study unitÂ KBR based themeÂ MBR- Cozy corner with loose furniture Wardrobe Foldable table for work purpose need to plan Vanity units for all the washrooms | 2026-05-17 15:08:06 +0530 | Unknown | About the Customer **Callback Requested for 11 AM** Customer requested a callback at 11:00 AM due to being in a meeting. **Agent to Reschedule and Send WhatsApp** Agent agreed to call back and will send a WhatsApp message. |  |  |  | 2026-06-25 |  | 2026-07-02
20062 | Turnkey | May'26 | Abhijit Hingmare | Aklavya CHS | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | DCM Due | 1425101 | 9999 | 0 | 0 | 0 | 50 | 0 | 132511 | 142510 | 570040 | 570040.4 |  |  | 2026-05-17 | 2026-05-26 13:18 | 2026-06-13 | 2026-06-23 17:33 | 2026-06-03 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-05-17 | 2026-05-20 14:09 | 0 | 0 | 0 | 0 | 0 | 0 | 1207712 | 217388 | 2026-06-13 18:31:27 +0530 | Priyanka Patel | Some Image was uploaded | 2026-06-13 18:30:09 +0530 | Priyanka Patel | DCM: . Name of the customer 20062 - Abhijit Hingmare 2. Profession Bussiness 3. Project Name/Tower Name/Flat Number Aklavya CHS 4. Typology (1BHK, 2BHK, 3BHK, etc) Bungalow 5. Site Access Date 2026-06-13 6. Possession Date 2026-06-13 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 3000000 Customer Preferences8. Who will be living in the house? Elderly Members, Joint Family, Nuclear Family, Couple, Single 9. What activities do you usually prefer at your home ? Prayer, Pursuing Hobbies, Relaxing and Unwinding, Family Bonding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] basic Vastu 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) yes Upload reference images 14. Any absolute no-go styles colours or materials no drak colours 15. Do you have any existing furniture that must be accommodated? no 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Console, Seating, Partition, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests, Multipurpose, TV Focus 2. Must-have furniture or features? TV unit, Home speakers, Speakers, Coffee table, Bookshelves, Puja unit, Display unit , Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Heritage items, Travel souvenirs, Artwork 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit, Partitions, Bar Unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Dishwasher, Built-in Oven, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Bookshelf , Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Parents 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Bookshelf , Dresser , TV unit 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Guest 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units Bookshelf, Dresser, TV Unit 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility Others 16. Bedroom 3 - Bed Type Storage 17. Bedroom 3 - Wardrobe Style Swing 18. Bedroom 3 - Additional Units Bookshelf, Dresser, TV Unit 19. False Ceiling Required - Bedroom 3 Yes Bathrooms1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Tall Storage, Bottom Storage, Laundry space, Extra sink, Washing machine space, Dryer, Top Storage Balcony & Outdoor1. How do you intend to use your balcony? Furniture, Planters, Storage, Utility 2. Outdoor Mood How do you intend to use the utility Any other, Appliances, Cloths Drying, Storage Miscellaneous1. Timeline related commitment made by Bonito, if any Yes 2. Other commitments made by Bonito to customer, if any Yes 3. What are offers committed to customers? Yes 4. Move-in date confirmed with customer 2026-12-31 5. Any special occasion mentioned by the customer wrt handover date Jan 2027 6. Additional Requirements (Mention any requirements from customer not covered in the form) yes 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 3000000 | 2026-05-26 13:17:08 +0530 | Mrunali Mitkari | Some Image was uploaded | 2026-07-04 |  | 2026-07-11
20064 | Turnkey | May'26 | Rahul Bhosale | Raymond | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | DCM Due | 1256168 | 0 | 0 | 0 | 0 | 57 | 0 | 125617 | 125617 | 561949 | 442985.2 |  |  | 2026-05-17 | 2026-05-19 11:33 | 2026-05-23 | 2026-05-23 10:34 | 2026-05-23 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-05-23 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-25 | [5 empty] | 2026-05-31 |  | 2026-06-08 |  | 2026-06-09 |  |  |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 | [6 empty] | 2026-07-07 |  | 2026-07-16 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-08-10 |  | 2026-08-12 |  | 2026-08-13 | [5 empty] | 2026-06-17 |  | 2026-05-26 |  | Unknown | 2026-05-17 | 2026-05-19 11:07 | 0 | 0 | 0 | 0 | 0 | 0 | 1066836 | 189331 | 2026-06-04 14:16:09 +0530 | Subhan Khan | Silver coin handed over to Vartika Punjabi. | 2026-06-04 14:03:48 +0530 | Subhan Khan | Some Image was uploaded | 2026-06-04 12:17:22 +0530 | Subhan Khan | 21g Silver coin is collected from the client. | 2026-05-31 |  | 2026-06-07
20065 | Turnkey | May'26 | Kalpak Kubal | Lodha Crown Kolshet¦Kolshet Road¦Thane | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Anjan Kumar |  | Hold | Preproduction | DEM2 | 971157 | 197214 | 1122150 | 0 | 0 | 11 | 12 | 0 | 0 | 436120 | 337822.8 |  |  | 2026-05-17 | 2026-05-17 17:33 | 2026-05-19 | 2026-05-20 17:22 | 2026-05-24 | 2026-05-24 19:15 | 2026-06-16 | 2026-06-16 12:27 | 2026-08-03 |  | 2026-08-10 |  | 2026-05-24 | 2026-05-25 11:08 | 2026-05-25 | 2026-05-26 10:51 | 2026-05-26 | 2026-05-26 14:20 | 2026-06-07 | 2026-06-07 18:04 |  |  |  |  | 2026-06-18 | 2026-06-22 19:07 | 2026-08-05 |  | 2026-08-06 |  |  |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 | [6 empty] | 2026-09-03 |  | 2026-09-12 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-15 |  |  |  | 2026-10-07 |  | 2026-10-09 |  | 2026-10-10 | [5 empty] | 2026-08-14 |  | 2026-06-08 | 2026-06-11 17:47 | Site is RTMI | 2026-05-17 | 2026-05-17 17:25 | 953220 | 168930 | 0 | 0 | 0 | 0 | 947512.1608 | 157943 | 2026-07-03 14:07:15 +0530 | Divya Rahangdale | Hold till July end | 2026-06-26 12:25:02 +0530 | Sakshi Pokharkar | DEM 2 meeting aligned on 27th JUNE, CX has lot of civil work in his scope, Hence PKO will happen by august. | 2026-06-25 12:18:39 +0530 | Sakshi Pokharkar | Some Image was uploaded | 2026-06-17 | 2026-06-16 12:41 | 2026-08-04 |  | Under Construction | 2026-06-14
20067 | Turnkey | May'26 | Jignesh Bhatt | Auris Serenity | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Active | Design | 20% Payment | 1510636 | 196093 | 1960933 | 0 | 0 | 6 | 12 | 0 | 106034 | 682769 | 525740 |  |  | 2026-05-17 | 2026-05-19 19:49 | 2026-05-23 | 2026-05-23 21:38 | 2026-05-23 | 2026-05-23 22:34 | 2026-06-27 | 2026-06-27 20:33 | 2026-07-12 |  | 2026-07-19 |  | 2026-05-23 | 2026-05-23 21:21 | 2026-05-24 | 2026-05-27 19:34 | 2026-05-27 | 2026-05-29 12:33 | 2026-06-03 | 2026-06-03 18:56 |  |  |  |  | 2026-06-27 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-06-04 | 2026-06-09 15:27 | Site is RTMI | 2026-05-17 | 2026-05-17 18:17 | 1663906 | 297027 | 0 | 0 | 0 | 0 | 1663905.537 | 269438 | 2026-06-27 20:34:40 +0530 | Zoya Bhatkar | Minutes of Meeting held on Date:27th June 2026 Attendees: Discussion: DEM 1 Based on27th June 2026 meeting, below is a list of all the requirements that were discussed during the meeting: Living Room 2 option For Shoe Rack 1 with as per existing layout 1 with right side Shoe Rack with wall storage with partition Double Curtains Kitchen Sliding Partition Pantry Unit above Platform 7' Height Wicker Basket Cooking Platform Wall Unit in Glass Bedroom 1 2 drawer side table 450 Wardrobe Internals as discussed Single Curtain Master Bedroom Dresser cum Side Table with Wall Storage Existing Godrej Metal Wardrobe WardrobeÂ Internals as discussed Double Curtains Single layer False Ceiling Vanity & Ceiling to be discussed with Rahul | 2026-06-03 18:54:08 +0530 | Vishakha Vaishnav | "Welcome call done along with the Designer. Initial measurement done : 3 June 2026 DEM Dates -Â DEM 1 - TBD Can be done only on weekends DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-05-31 16:30:20 +0530 | Vishakha Vaishnav | Tried connecting cx , didn't answered the call | 2026-06-28 | 2026-06-27 20:34 | 2026-07-13 |  | RTMI
20070 | Turnkey | May'26 | Rahul Patel | 77 crossroads | MUM - GOR | Yes | Riddhi Deshpande | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Sanskruti Yadav |  | Active | Design | DEM1 | 863276 | 217213 | 1086068 | 0 | 0 | 21 | 26 | 0 | 0 | 354823 | 291240.4 |  |  | 2026-05-17 | 2026-05-18 11:43 | 2026-05-24 | 2026-05-24 20:45 | 2026-05-28 | 2026-05-28 22:39 | 2026-07-17 |  | 2026-07-24 |  | 2026-09-29 |  | 2026-05-28 | 2026-05-28 21:22 | 2026-05-29 | 2026-05-29 12:30 | 2026-05-29 | 2026-05-29 18:15 | 2026-05-31 | 2026-05-31 16:11 |  |  |  |  | 2026-06-08 | 2026-05-28 21:22 | 2026-09-24 |  | 2026-09-25 |  |  |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 | [6 empty] | 2026-10-23 |  | 2026-11-01 |  | 2026-10-31 |  | 2026-11-01 |  | 2026-11-02 |  | 2026-11-04 |  |  |  | 2026-11-26 |  | 2026-11-28 |  | 2026-11-29 | [5 empty] | 2026-10-03 |  | 2026-07-13 |  | Unknown | 2026-05-17 | 2026-05-18 11:30 | 920397 | 165671 | 0 | 0 | 0 | 0 | 920396.8655 | 155389 | 2026-06-18 18:39:01 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-16 11:43:44 +0530 | Riddhi Deshpande | Some Image was uploaded | 2026-06-12 13:26:09 +0530 | Riddhi Deshpande | DDM1: have asked for transition - dem 1 scheduled on 20th june - 11 am - saturday | 2026-07-18 |  | 2026-07-25 |  | Under Construction | 2026-09-01
20071 | Turnkey | May'26 | Neeraj Sadhwani | Marwel pride nx | MUM - Thane | Yes | [8 empty] | vinaya thakur |  | Active | Prospect | DCM Due | 1787967 | 12499 | 0 | 0 | 0 | 56 | 0 | 166298 | 178797 | 723747 | 706626.8 |  |  | 2026-05-17 | 2026-05-20 12:18 | 2026-05-26 | 2026-05-31 14:53 | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-13 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-05-17 | 2026-05-20 12:11 | 0 | 0 | 0 | 0 | 0 | 0 | 1517472 | 270495 | 2026-05-30 12:48:40 +0530 | Bhawaya Goyal | DCM: Cx - Neeraj Poss. - receivedÂ Prof. - advocateÂ Budget - 12-15 L Suggested - 22-25L 4 people mother father son daughter + dogÂ Foyer area :Â shoe rackÂ Living room : 3+1 seater sofa with center tableÂ TV unitÂ Dining table - 4 seaterÂ mandir false ceilingÂ Â profile lights, hanging light , focus track Kitchen :Â Cylinder unit cooktop in south sink on both side, need to have dishwasher on south side wall fridge on upper right cornerÂ more storage is required easy to accessÂ microwave, dishwasherÂ Bottom left for parents : Master bedroom TV unit wardrobeÂ king sizeÂ dressingÂ side table Bottom right as daughter + guestÂ wardrobeÂ queen sizeÂ dressingÂ side table top room = son bedroom wardrobeÂ queen sizeÂ dressingÂ side table Preference : minimalist designÂ false ceilingÂ Â profile lights, hanging light , focus track paintingÂ electrical | 2026-05-19 12:28:17 +0530 | vinaya thakur | Some Image was uploaded | 2026-05-19 11:27:15 +0530 | vinaya thakur | Some Image was uploaded | 2026-06-08 |  | 2026-06-15
20072 | Turnkey | May'26 | Pavan Kumar Singh | Assetz Marq 3 | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Active | Preproduction | DEM2 | 1519797 | 303959 | 2031684 | 0 | 0 | 20 | 0 | 0 | 0 | 658707 | 557130.8 |  |  | 2026-05-17 | 2026-05-19 17:20 | 2026-05-19 | 2026-05-22 11:09 | 2026-05-23 | 2026-05-28 15:13 | 2026-06-16 | 2026-06-15 17:56 | 2026-07-12 |  | 2026-07-19 |  | 2026-05-28 | 2026-05-29 11:17 | 2026-05-29 | 2026-05-30 14:48 | 2026-05-30 | 2026-06-02 10:20 | 2026-06-03 | 2026-06-03 17:20 |  |  |  |  | 2026-06-15 | 2026-06-25 11:48 | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-23 |  | 2026-06-04 | 2026-06-15 17:23 | Site is RTMI | 2026-05-17 | 2026-05-17 20:59 | 1721766 | 309918 | 0 | 0 | 0 | 0 | 1708592.8322 | 282113 | 2026-06-26 12:40:43 +0530 | Yogesh B | Some Image was uploaded | 2026-06-26 12:39:31 +0530 | Yogesh B | Some Image was uploaded | 2026-06-15 13:20:14 +0530 | Sagarika Venkatesh | DDM1: DEM MeetingÂ Date - 14-06-26 Name -Â Pavan Kumar SinghÂ PID - 20072 Layout design finalisionÂ FoyerÂ Layout is fixedTall unit placemet to be rethoughtÂ ventilation grill to be addedÂ Living RoomÂ layout is fixedÂ tv unit design to redesign as it looks too simple also to add more storage spaceÂ Â Pooja cnc door design to change & add inside ledge with cnc designÂ sofa back wall design to enance more on the right wallÂ crockery to extend the unit as the walls are biggerÂ add wooden top panelÂ KitchenÂ layout is chnaged & now it is to actualÂ counter top to be quartzÂ Parents bed roomÂ layout is fixedÂ no dresserÂ wall paper need optionÂ PBR - BathroomÂ Open unit to be addedÂ Master bedroomÂ layout is fixedÂ wallpaper option to be givenÂ can add cornice designÂ walkin in drawer to be removed and add a tall open unitÂ MBR- BathroomÂ Open unit to be addedÂ Kids bedroomÂ layout is fixedÂ wall design to be chnaged and also to keep in mind that study is coming next to the windowÂ add a horizontal wall design conceptÂ Overn all design to be a littel interms of color and depthÂ keeping the budget in mindÂ Pending Client Approval Electrical chipping workplumbing shiftingÂ appliences list with dimentionsÂ | 2026-06-16 | 2026-06-15 17:57 | 2026-07-13 |  | RTMI
20073 | Turnkey | May'26 | Sowndharya J J | prestige meredan park | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1809303 | 9999 | 0 | 0 | 0 | 59 | 0 | 170931 | 180930 | 723721 | 723721.2 |  |  | 2026-05-17 | 2026-05-17 21:03 | 2026-05-19 |  | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-05-17 | 2026-05-17 21:01 | 0 | 0 | 0 | 0 | 0 | 0 | 1533308 | 275995 | 2026-05-21 19:04:33 +0530 | Nidhi Shaw | 3 BHK Budget I mentioned clearly 13-15 for 3 BHK is required and they are okay with it. Parents involvement is required I told to bring them in cdp | 2026-05-21 11:03:47 +0530 | Gayathri Krishna | Cx name : Sowdharya & SriRam ( Chennai ) Address : Prestige - 62005 Profession : ITÂ Possession : July endÂ How many people will be staying :4 + 2kidsÂ Theme : Minimal with few pop upsÂ Entrance facing :Â E facingÂ Budget : 10 - 12L Foyer -Â Shoe rack with seaterÂ Dining area - 6 seater dining table (dark wooden ) pooja unit with long shutters - 950mm neededÂ Need crockery unit along with pooja - refer imageÂ Living - TV size - 65" base unit , 1 tall unit with glass shutter and back panelÂ L shape sofa Kitchen - give 2 layout opts - E and W Single door fridgeÂ Black granite cooktop on sink wall as markedÂ Need tall unit for rollup unit next to hob 1 cylinder unitÂ wall, base and loftÂ Utility-Â Need sink unitÂ wall cabinetÂ MBR- Blue and greyÂ Wardrobe with loftÂ Study table with wall cabinets and loft needed Dresser unit with long mirror and tall unit on wall side with base unitÂ King size bed KBR - Shreya 8yo & Vedanth 1yo Queen size bed wardrobe with loft - need designÂ Study table for 2 , with wall cabinets for books and toysÂ Theme - pink and blueÂ PBR- green or neutralÂ Queen size bed Wardrobe with loftÂ Study unit opposite to bedÂ Dresser unit which cx has keep next to bedÂ Plan a bay window after site visitÂ Bathrooms - Need base vanity unitsÂ Shower partition only for MBRÂ Â False ceiling - common area & kids room CDP - 23th or 24thÂ |  |  |  | 2026-06-01 |  | 2026-06-08
20074 | Turnkey | May'26 | Shayani Bardhan | Ajmera | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Shashwat Joshi | Rizwan Mistry | Murali S | Hitesh Rawal | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 925633 | 925633 | 1092893 | 0 | 982267 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-17 | 2026-05-17 21:46 | 2026-05-19 | 2026-05-19 17:07 | 2026-05-20 | 2026-05-20 20:31 | 2026-05-29 | 2026-05-24 21:50 | 2026-05-28 | 2026-05-27 12:40 | 2026-06-17 | 2026-06-15 09:27 | 2026-05-20 | 2026-05-21 18:48 | 2026-05-21 | 2026-05-21 18:52 | 2026-05-21 | 2026-05-22 10:53 | 2026-05-24 | 2026-05-24 20:17 |  |  |  |  | 2026-05-28 | 2026-05-21 18:48 | 2026-06-04 | 2026-06-05 11:02 | 2026-06-06 | 2026-06-05 11:20 |  |  | 2026-06-16 | 2026-06-17 16:15 | 2026-06-24 | 2026-06-24 19:27 | 2026-06-25 | 2026-06-25 15:13 | 2026-06-26 | 2026-06-26 18:41 |  |  |  |  | 2026-06-30 11:59 | 2026-07-04 | 2026-07-03 21:04 | 2026-07-15 | 2026-07-13 18:36 | 2026-07-13 | 2026-07-12 18:17 | 2026-07-13 |  | 2026-07-17 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-28 |  | 2026-07-29 | [5 empty] | 2026-06-24 | 2026-06-30 11:58 | 2026-05-25 | 2026-05-24 21:49 | Site is RTMI | 2026-05-17 | 2026-05-17 21:41 | 928468 | 164425 | 0 | 0 | 1104469.614 | 176808 | 1104469.1945 | 175164 | 2026-06-30 16:54:58 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-27 11:28:47 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-17 20:16:01 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-05-25 | 2026-05-24 21:53 | 2026-05-28 | 2026-05-27 12:40
20075 | Turnkey | May'26 | Ajit Patil | Balaji Heights | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Nivesh Gupta |  | Active | Design | DEM1 | 1206869 | 148906.6 | 1489072 | 0 | 0 | 47 | 0 | 0 | 92467 | 499539 | 465956 |  |  | 2026-05-17 | 2026-05-25 17:48 | 2026-05-25 | 2026-05-25 19:24 | 2026-05-27 | 2026-05-27 12:42 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-28 |  | 2026-05-27 | 2026-05-28 11:49 | 2026-05-28 | 2026-05-28 11:57 | 2026-05-28 | 2026-05-29 14:15 | 2026-05-30 | 2026-05-30 17:21 |  |  |  |  | 2026-06-19 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-05-31 |  | Unknown | 2026-05-17 | 2026-05-25 17:46 | 1261925 | 227146 | 0 | 0 | 0 | 0 | 1259029.8181 | 217236 | 2026-07-10 15:30:34 +0530 | Vishakha Vaishnav | MEETING WAS SCHEDULED FOR LAST WEEK BUT CX CANCELLED | 2026-06-03 13:23:20 +0530 | Sweta Bhise | CDP: Crockery unit1Rs. 44,070/-Safety Door Design 1 - SS Jaali - PU Black (Satin) - RAL 9005 - Antique Brass21Rs. 54,055.02/-Shoe rack1Rs. 23,542/-Vito 3 Seater Sofa - Premium Fabric with Sturdy Wooden Legs (April Offer) [BBP]1Rs. 27,457.63/-TV unit1Rs. 84,304/-Ebco Wall Shelf Rod HD - 10x145x75x12 (15kg)4Rs. 300/-ODP - Panel - Gold, Laminate, 50, 300, 18, OSL, PLY6Rs. 622.5/-KitchenRs. 1,99,830/- Loft1Rs. 37,636/-Top Unit1Rs. 73,944/-Bottom Unit1Rs. 88,250/-Master BedroomRs. 1,83,529/- Seating Area1Rs. 40,968/-Wardrobe with loft1Rs. 1,20,203/-Single Tall Unit - 300 x 1390, Diamond, Laminate, None, None1Rs. 22,358/-Son's Bed RoomRs. 1,66,314/- Study Unit1Rs. 23,810/-Wardrobe with loft1Rs. 1,20,146/-Single Tall Unit - 300 x 1390, Diamond, Laminate, None, None1Rs. 22,358/-Living or Dining (Bathroom & Toilet)Rs. 7,848/- ODP - Single Bottom Vanity Unit - Diamond, Laminate, 600, 560, G Profile, NA, BWP PLY1Rs. 7,848/-Master Bed room (Bathroom & Toilet)Rs. 7,848/- ODP - Single Bottom Vanity Unit - Diamond, Laminate, 600, 560, G Profile, NA, BWP PLY1Rs. 7,848/-Additional Scope of WorkRs. 2,16,113.03/- False ceiling - Saint Gobain Gypsum Board - Channel - Megasteel - sft - Only Mumbai350Rs. 38,930.5/-POP Punning (Plum) 12-15mm thick2Rs. 7,638/-Charcoal Beading with Type and Designs - Raw - VB-6510Rs. 10,566.93/-Excel - Essen Wallpaper 71051-12Rs. 8,118/-Royale Luxury Emulsion1,300Rs. 51,298/-Quartz: installation2Rs. 28,800/-Primary Light Point - Up to 5m55Rs. 39,325/-Tractor Emulsion550Rs. 14,899.5/-Saint Gobain 5 MM Silver Mirror (Miralite) Non Toughened70Rs. 16,537.1/- client have his own beds | 2026-05-30 17:20:08 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Cx will let us know as it is expected in july DEM Dates -Â DEM 1 - Cx will discuss with wife and let us know DEM 2 - TBD DEM 3 - TBD Possession date : July end Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-19 |  | 2026-06-26 |  | Under Construction | 2026-07-31
20080 | Turnkey | May'26 | Jisha | Brigade Cornerstone Utopia | BNG - HRBR | Yes | Vijin Venu | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari | Deekshith P | Jairam Joshi |  | Kushal S | Abdul Shafeen | Active | Design | DEM3 | 1057596 | 205579 | 1336699 | 0 | 0 | 1 | 0 | 0 | 0 | 452427 | 399589.6 |  |  | 2026-05-17 | 2026-05-19 11:44 | 2026-05-22 | 2026-05-22 11:20 | 2026-05-25 | 2026-05-23 18:33 | 2026-06-16 | 2026-06-16 19:18 | 2026-06-22 |  | 2026-07-18 |  | 2026-05-23 | 2026-05-23 20:59 | 2026-05-24 | 2026-05-26 18:48 | 2026-05-26 | 2026-05-29 12:02 | 2026-06-04 | 2026-06-04 16:44 |  |  |  |  | 2026-06-16 | 2026-06-19 18:53 | 2026-07-12 | 2026-07-14 17:10 | 2026-07-15 | 2026-07-14 18:49 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-22 |  | 2026-06-05 | 2026-06-16 19:07 | Site is RTMI | 2026-05-17 | 2026-05-19 10:58 | 1132796 | 203903 | 0 | 0 | 0 | 0 | 1142622.0681 | 190367 | 2026-07-10 16:59:41 +0530 | Vijin Venu | As discussed in today's meeting, please find the updated design and scope details below: 20080-10-07-2026 Living Room 1)TV unit design is confirmed. 2)Pooja unit design is confirmed. 3)Remove the beading and mirror. (Mirror and console table are under the client's scope.) Kitchen 1)Appliance details need to be discussed. 2)RO (Reverse Osmosis) unit placement will be finalized during the cross-measurement. Master Bedroom 1)Added a used clothes unit. 2)Existing 20" Ã— 20" chest of drawers will be retained. (Client scope.) Guest Bedroom 2)Existing 48" Ã— 24" study unit will be retained. (Client scope.) 2)Dresser unit is under the client's scope. Common Door demolition and refixing feasibility will be checked with the VM during the cross-measurement. | 2026-07-08 11:01:53 +0530 | Vijin Venu | 20080-design discussion-5-07-2026 living area 1)pooja design are finalized 2)dining sofa placement need to mark on site during CM 3)suggest paint code (full house-client scope) kitchen 1)swap the sink and dishwasher (design changes need to send) 2)kitchen quartz and granite -estimation comparison need to share MBR 1)wardrobe design -need to confirm GBR 1)drawer design same -first one | 2026-06-27 12:32:17 +0530 | Vijin Venu | 20080-jisha 25-06-2026 living area 1)tv design change to (DD2 final design) 2)pooja need design suggestions(no cnc-) 3)mirror design options (client scope) 4) kitchen 1)hob and chimney offer need to check (type of chimney) 2) open wall unit required 3)laminates are selected 4)dish washer/washin machine MBR 1)remove aristo add sliding wardrobe 2)bed back wall design (wallpaper/strips) 3)bags and used clothes storageÂ /clothes hook need to check availability shutter grill 4)curtain split designÂ GBR 1)bed back wall design 2)dresser unit (swap) 3)mirror on shutter | 2026-06-17 | 2026-06-16 19:19 | 2026-06-23 |  | RTMI
20082 | Turnkey | May'26 | Pooja Lotia | Vora icon | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 2028106 | 9999 | 0 | 0 | 0 | 46 | 0 | 192812 | 202811 | 890532 | 731953.2 |  |  | 2026-05-18 | 2026-05-19 12:34 | 2026-05-22 | 2026-05-22 12:30 | 2026-05-25 |  | 2026-06-01 |  | 2026-06-08 |  | 2026-06-15 |  | 2026-05-25 |  | 2026-05-26 |  | 2026-05-26 |  | 2026-05-27 | [5 empty] | 2026-06-02 |  | 2026-06-10 |  | 2026-06-11 |  |  |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 | [6 empty] | 2026-07-09 |  | 2026-07-18 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-21 |  |  |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-15 | [5 empty] | 2026-06-19 |  | 2026-05-28 |  | Unknown | 2026-05-18 | 2026-05-19 12:33 | 0 | 0 | 0 | 0 | 0 | 0 | 1721042 | 307063 | 2026-05-19 15:35:36 +0530 | Siddhi Chaphekar | DCM: 2bhk Vora Icon (kandivali) Clients profession-Husband-Stock market Wife- traveller Family members-3ppl Budget-15lacs Livingroom- Entrance foyer-shoe rack Crockery unit with mirror panelling,dining for 4 people Frame of Maharaj above dining Sofa wall-design and horse frame Tv unit and mandir on the same wall for now(mandir will be as per vastu) Master Bedroom- Queen size bed Wardrobe Tall unit for handbags Loft opposite to bed for storage Working desk Guitar display but not open Dressing table Daughters Bedroom- Bed Bunk bed style option ( tentative cost) Wardrobe Study table with storage wall unit and loft Swing if possible Overall theme in lilac shades Both Bathrooms- vanity and open storage above WC Electrical,false ceiling and painting. Cx wants as much storage possible. | [6 empty] | 2026-06-02 |  | 2026-06-09
20083 | Turnkey | May'26 | MR. Amit ASWANI | 72 West | MUM - GOR | Yes | Sonal Singh | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 1090234 | 218047 | 1425095 | 0 | 0 | 2 | 0 | 0 | 0 | 479519 | 392668 |  |  | 2026-05-17 | 2026-05-26 15:09 | 2026-05-19 | 2026-05-26 15:55 | 2026-05-27 | 2026-05-27 12:11 | 2026-07-12 | 2026-07-11 20:12 | 2026-07-17 |  | 2026-07-29 |  | 2026-05-22 | 2026-05-25 13:48 | 2026-05-27 | 2026-05-26 16:22 | 2026-05-28 | 2026-05-29 11:31 | 2026-06-04 | 2026-06-04 15:04 |  |  |  |  | 2026-07-11 | 2026-07-13 17:20 | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-06-05 | 2026-07-11 19:58 | Site is RTMI | 2026-05-17 | 2026-05-26 15:00 | 1209806 | 215289 | 0 | 0 | 0 | 0 | 1200443.1666 | 193766 | 2026-06-07 12:21:30 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-04 15:03:46 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Can be done site is accessible flooring & everything is done need to check for lots with khushi DEM Dates -Â DEM 1 - cx is available for 5th june between 12-1 pm need to confirm designer availability DEM 2 - TBD DEM 3 - TBD Possession date : Anytime this week Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-03 17:42:36 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-07-12 | 2026-07-11 20:23 | 2026-07-18 |  | Under Construction | 2026-06-06
20085 | Turnkey | May'26 | Swaroop Pattanaik | Adani The View | MUM - GOR | Yes | Shweta Dalvi | Christopher Macwan | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Design | DEM1 | 1642845 | 219194 | 2195639 | 0 | 0 | 20 | 0 | 0 | 109375 | 681670 | 632605.6 |  |  | 2026-05-16 | 2026-06-07 19:26 | 2026-06-04 | 2026-06-07 19:49 | 2026-06-10 | 2026-06-08 16:39 | 2026-07-02 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-06-08 | 2026-06-10 17:56 | 2026-06-09 | 2026-06-12 15:05 | 2026-06-12 | 2026-06-25 12:36 | 2026-06-27 | 2026-06-27 12:57 |  |  |  |  | 2026-07-03 |  | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-28 |  | Unknown | 2026-05-16 | 2026-05-19 11:52 | 1860711 | 334928 | 0 | 0 | 0 | 0 | 1842676.54 | 304262 | 2026-06-27 13:02:04 +0530 | Christopher Macwan | Welcome call done. Initial measurement already done. DEM Dates -Â DEM 1 - Only weekend at the earliest. Checking for DEM1 for tomorrow, 28th June 2026. DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of July 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-27 10:23:50 +0530 | Christopher Macwan | Called for welcome call, but no response | 2026-06-25 12:34:21 +0530 | Sanjana Swami |  | 2026-07-03 |  | 2026-07-10 |  | Under Construction | 2026-07-31 | 2026-06-07 | 219194 | Ravi Roy
20086 | Turnkey | May'26 | Samyuktha R | 3bhk independent house | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 777493 | 9999 | 0 | 0 | 0 | 57 | 0 | 67750 | 77749 | 310997 | 310997.2 |  |  | 2026-05-17 | 2026-05-19 12:19 | 2026-05-18 |  | 2026-05-26 |  | 2026-06-02 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-05-26 |  | 2026-05-27 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | 2026-06-03 |  | 2026-06-11 |  | 2026-06-12 |  |  |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 | [6 empty] | 2026-07-10 |  | 2026-07-19 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-22 |  |  |  | 2026-08-13 |  | 2026-08-15 |  | 2026-08-16 | [5 empty] | 2026-06-20 |  | 2026-05-29 |  | Unknown | 2026-05-17 | 2026-05-19 12:18 | 0 | 0 | 0 | 0 | 0 | 0 | 658893 | 118600 | 2026-05-19 12:14:47 +0530 | Unknown | About the Customer **Customer Requirements and Service Scope** Customer Samyukta requires interior work and some civil changes, including adding a bathroom and wardrobes for her two-floor house in Vasanth Nagar. Bonito Designs can handle interiors and suggest vendors for limited civil work (10-15%). **Information Required for Visit** Customer needs to provide a floor plan and video of the property before the visit. **Confirmed Experience Center Visit** Confirmed appointment for experience center visit today between 5:00 PM and 6:00 PM with husband. **Initial Pricing Mentioned** Pricing mentioned starts from 7 lakhs for end-to-end interiors. **WhatsApp Invite to be Sent** Agent will send appointment details via WhatsApp. | [6 empty] | 2026-06-03 |  | 2026-06-10
20087 | Turnkey | May'26 | Avneet Saxena k | Independent House | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 4266211 | 9999 | 0 | 0 | 0 | 47 | 0 | 416622 | 426621 | 1722212 | 1690756.8 |  |  | 2026-05-17 | 2026-05-19 12:32 | 2026-05-20 | 2026-05-29 11:36 | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-17 | 2026-05-19 12:28 | 0 | 0 | 0 | 0 | 0 | 0 | 3615433 | 650778 | 2026-05-28 15:36:37 +0530 | Saranya Thiyagarajan | DCM: MOM Interior Design DiscussionClient DetailsClient Name: Avneet & Shruti Project Address: Adharsh Estate Garden 149 No Profession: IT Expected Possession: October Family Members Staying: 2 + 1 Design Theme: Traditional Contemporary Entrance Facing: West Facing Overall Budget: 3040 Lakhs (Including Furniture) Ground FloorFront GardenRequirements:Landscape planning requiredCozy seating benchWarm and inviting ambiance Entrance AreaRequirements:Feature wall treatmentSeating provisionNeed 3D design visualization Store RoomsRequirements:Maximum storage optimizationStorage for both large and small items FoyerRequirements:Shoe rack with mirrorPlanter in cornerAppealing wall treatmentIndian touch in design Staircase WallRequirements:Wall design inspired by Jharokha concept First FloorDaughter Bedroom Tavisha (12 Years)Requirements:Pastel tone themeWooden flooringQueen-size bedWalk-in wardrobe as markedDresser unitWorkstation with proper storageTheme inspiration:CraftAnimeMusicNo traditional elementsBathroom vanity and storage Staircase Passage AreaRequirements:Shoe rack provision Master Bedroom (MBR)Requirements:Wooden flooringLong mirror with dresser in walk-inWardrobe after dresser with cane shutters and wooden finishExplore innovative wardrobe detailingTexture wall treatmentTropical wallpaper as per referenceBathroom vanity and storage Second FloorLiving RoomRequirements:Kota stone or natural-look tile flooringCladding work on courtyard wall (double height with skylight)Hanging light in courtyard as per referenceTV unit to complement claddingPooja unit integrationPooja Requirements:Base storageLedges for small idolsPartition if possibleComfortable seating provision Parents Bedroom (PBR)Requirements:3-shutter wardrobeLong mirror on last shutterBathroom vanity and storage Dining AreaRequirements:6-seater dining tableCorner wash basin with design detailingHanging light at marked cornerCrockery unit if space permitsArtwork placement KitchenRequirements:Matte finish kitchenPreferred colors:Sage GreenBlueGranite countertop (not black)Double-door refrigeratorTall unit for ovenBase unitsWall unitsLoft storage Utility AreaRequirements:Sink unit with drain boardGTPT unit above sinkWashing machine areaWall cabinet above washing machine Third FloorPantry RoomRequirements:Base storage unit Multi-Purpose RoomRequirements:Provision for bar unitSofa-cum-bed seatingAdditional storage if possibleHome TheaterRequirements:Workstation provisionTheater planning accordingly Terrace FloorUtility Near Washing MachineRequirements:Base storageStore RoomRequirements:Tall storage units as marked | [6 empty] | 2026-06-07 |  | 2026-06-14
20088 | Turnkey | May'26 | Akhil Mohanlal | Nambiar Millenia | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 1745977 | 9999 | 0 | 0 | 0 | 57 | 0 | 164599 | 174598 | 698391 | 698390.8 |  |  | 2026-05-17 | 2026-05-19 12:28 | 2026-05-26 |  | 2026-05-28 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-30 |  | 2026-05-31 | [5 empty] | 2026-06-06 |  | 2026-06-14 |  | 2026-06-15 |  |  |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-23 |  | 2026-06-01 |  | Unknown | 2026-05-17 | 2026-05-19 12:26 | 0 | 0 | 0 | 0 | 0 | 0 | 1479641 | 266335 | 2026-05-28 15:33:55 +0530 | Gayathri Krishna | Cx name : Akhil & Ragi (Kerala) Address : Nambiar Millenia - C804 Profession : IT Possession : Sep 1st week How many people will be staying : 2 +1 kid + 2 cats Theme : Minimal with few pop ups Entrance facing : E entry Budget : 10 - 15L Entrance - Need partition with shoe rack as marked (one tall unit with storage and seating ) Dining area - crockery cum bar unit Need 6 seater dining with bench on beam side (cx has the table ) note - beam side wall to be removed Living room - 3 seater and 2 armchairs needed TV unit - Wall mounted drawers , need tv wall designs (no floral wallpapers) Sofa back wall need design (column projection is there) Need wall ledges on corner as marked Kitchen entrance - need vanity unit with mirror and stone wall cladding Kitchen - single door fridge Counter top to be included Need 2 cylinder cabinet provision Base, wall & Loft Tall unit with microwave provision near crockery Need roll up unit (find provision) Half wall to utility to be removed Need WM on the corner as marked sink unit with under counter RO after window Need Janitor unit opposite to WM MBR - neutral + sage green King size bed Wardrobe on oppo wall Small study on bed wall Need to plan the bay window Dresser unit behind the door to room BR3- GBR Queen size bed as marked in plan Wardrobe with loft need study with ledges after wardrobe Need mirror one 1st shutter of wardrobe BR2-KBR (Dhruv 13yo) Theme - Rustic texture grey and black with football theme King size bed (cx has black shade bed) Wardrobe with loft on entrance wall L shape study with tall unit for book shelf on window wall Balcony- need planter boxes Bathrooms- Vanity unit for all bathrooms CDP - 28th May | [6 empty] | 2026-06-06 |  | 2026-06-13
20089 | Turnkey | May'26 | Harvinder Singh Matta | siddha sky | MUM - GOR | Yes | Karan Chavda | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Hold | Preproduction | Site Readiness 1 | 1138952 | 227790.3 | 1389459 | 0 | 0 | 0 | 26 | 0 | 0 | 498473 | 412688.8 |  |  | 2026-05-17 | 2026-05-26 13:23 | 2026-05-27 | 2026-05-27 18:05 | 2026-05-30 | 2026-05-29 21:30 | 2026-06-19 | 2026-06-19 19:12 | 2026-08-04 |  | 2026-08-11 |  | 2026-05-29 | 2026-05-31 | 2026-05-30 | 2026-06-02 19:40 | 2026-06-02 | 2026-06-08 18:54 | 2026-06-12 | 2026-06-12 15:27 |  |  |  |  | 2026-07-31 | 2026-06-22 18:50 | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-06-13 | 2026-06-19 19:03 | Site is Non-RTMI | 2026-05-17 | 2026-05-20 14:09 | 1177507 | 211951 | 0 | 0 | 0 | 0 | 1177923.3744 | 205011 | 2026-06-19 15:58:49 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-18 14:43:54 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 19:42:27 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - Cx is available for the meeting by friday 19th June 2026 DEM 2 - TBD DEM 3 - TBD Possession date : July 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-20 | 2026-06-19 19:17 | 2026-08-05 |  | Under Construction | 2026-07-31
20090 | Turnkey | May'26 | Neelam | Radiance Gardenia | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2481770 | 9999 | 2481770 | 0 | 0 | 49 | 0 | 238178 | 248177 | 1024384 | 961032 |  |  | 2026-05-19 | 2026-05-20 11:55 | 2026-05-19 | 2026-05-22 11:20 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-06-04 |  | 2026-06-12 |  | 2026-06-13 |  |  |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-06-21 |  | 2026-05-30 |  | Unknown | 2026-05-19 | 2026-05-19 14:24 | 2103195 | 378575 | 0 | 0 | 0 | 0 | 2103195 | 378575 | 2026-05-29 13:50:50 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-22 17:49:51 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-19 14:22:51 +0530 | Unknown | About the Customer **Customer Availability Delayed by Exams** Customer is busy with exams for the next two weeks and may visit in April or sooner if time permits. **Hesitation to Visit Experience Center** Customer prefers a phone consultation or quotation and is hesitant about visiting the experience center due to having children. **Budget Inquiry for 3BHK** Customer inquired about budget for a 3BHK, aiming for â‚¹10-13 lakhs for basic interiors. Agent provided a range of â‚¹15-20 lakhs for 3BHKs. **Concerns on Design Trends** Customer is concerned about current design trends, specifically paneling and gypsum designs for curves, and prefers lime wash paint. **Customer to Update via WhatsApp** Customer to update via WhatsApp regarding availability for an experience center visit. | 2026-06-04 |  | 2026-06-11
20091 | Turnkey | May'26 | Shishir Vijay Pimplikar | Raymond Address Season 1 | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Active | Design | DEM1 | 1705490 | 210999 | 2108312 | 0 | 0 | 11 | 0 | 0 | 130099 | 682196 | 682196 |  |  | 2026-05-19 | 2026-06-09 14:59 | 2026-09-30 | 2026-06-09 19:07 | 2026-06-28 | 2026-06-29 20:55 | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-06-29 | 2026-07-03 16:16 | 2026-06-30 | 2026-07-03 16:17 | 2026-07-03 | 2026-07-04 14:42 | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-05-19 | 2026-05-23 14:17 | 1786705 | 321606 | 0 | 0 | 0 | 0 | 1786705.3354 | 306988 | 2026-07-07 13:38:14 +0530 | Moksh Mehta | Others: | 2026-07-04 14:41:32 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion Date: 1st week of August 2026 Project Timelines: 99 business days Detailed timelines explained to the customer during the call Project Execution Plan: Fast Track Plan of Action Discussed During the Call: * Site is not accessible. * DEM 1 â€“ Client will check with his family and let us know * 10% Payment Stage â€“ 14th July 2026 *Civil work is not yet decided (maybe there will be a bathroom attachment in the bedroom) *Transaction will be B2C self-funding. Offers Discussed During the Call: PM fee waiver (2.5%) Design Fee Waiver (3%) May'26 100% GST waiver Final Closing Value Discussed: â‚¹ 17,05,490 | 2026-07-04 14:02:30 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-11 |  | 2026-07-18 |  | Under Construction | 2026-08-05 | 2026-06-29 | 210999 | Ravi Roy
20092 | Turnkey | May'26 | N. Srivani | Independnt House | BNG - HSR | Yes | Sreenivasulu Reddy | Abhinandan K S | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 1559344 | 155935 | 2187685 | 0 | 0 | 37 | 0 | 0 | 155934 | 642259 | 605216 |  |  | 2026-05-18 | 2026-05-21 11:14 | 2026-05-19 | 2026-05-22 11:46 | 2026-05-26 | 2026-06-02 12:07 | 2026-07-04 |  | 2026-07-11 |  | 2026-09-06 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-06 10:59 | 2026-06-06 | 2026-06-08 15:45 | 2026-06-09 | 2026-06-09 19:11 |  |  |  |  | 2026-07-05 |  | 2026-09-01 |  | 2026-09-02 |  |  |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-19 |  | 2026-09-20 | [6 empty] | 2026-10-08 |  | 2026-10-17 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-20 |  |  |  | 2026-11-11 |  | 2026-11-13 |  | 2026-11-14 | [5 empty] | 2026-09-10 |  | 2026-07-16 |  | Unknown | 2026-05-18 | 2026-05-20 18:17 | 1853970 | 333714 | 0 | 0 | 0 | 0 | 1853969.7417 | 306128 | 2026-06-08 15:32:05 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: End of July 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM 10th June 2026 * DEM 1 13th June 2026 * 10% Payment Stage by 18th June 2026 (after 1st DEM) *No civil work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,53,971 Offers Discussed During the Call: Free Shoerack Offer Special Offer (40000) Special Offer (35000) Free Hob & Chimney Offer PM fee waiver (5%) Design fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Laminate Upgrade - May '26 Campaign Silver Coin 21g Final Closing Value Discussed: 15,59,345 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-06 11:38:46 +0530 | Chanakya Panigrahi | Some Image was uploaded | 2026-06-02 16:08:15 +0530 | Chanakya Panigrahi | Some Image was uploaded | 2026-07-05 |  | 2026-07-12 |  | Under Construction | 2026-07-31
20093 | Turnkey | May'26 | Nibedita N | Prestige City | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | DCM Due | 2031076 | 9999 | 0 | 0 | 0 | 56 | 0 | 193109 | 203108 | 836200 | 788660.8 |  |  | 2026-05-16 | 2026-05-20 11:25 | 2026-05-20 | 2026-05-25 19:20 | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-05-16 | 2026-05-20 11:20 | 0 | 0 | 0 | 0 | 0 | 0 | 1721250 | 309825 | 2026-05-29 11:51:52 +0530 | Priyamvada PV | Nibedita CDP changes 28.05.26 MBR Aristo on left wall after entrance (opp of balcony) for entire wall along with Used cloth unit, storage above - doneMBR dresser drawers with tall storage on right, mirror panel on left of tall unit - doneKitchen glass shutters remove from wall unit add a oil pullout - donePooja need pocket door storage unit only -done (As pooja shouldnt look like pooja unit)Guest study, remove left open unit & ledges, add a TV above study - doneSofa wall - preferred HDHMR panel with duco option shown with wallpaper in between (additional cost incurs) - addedMBR, PBR vanity requires frame & shutter closure for laundry baskets on either side of base unit - Will be done in design phase as per actual measurements | 2026-05-20 16:56:09 +0530 | Priyamvada PV | Nibedita & Divyaprakash Panda RGM MOM 20.05.26 CDP date :Â 28.05.26 12/12.30pm Property : Prestige City Ashton park Site access date : Jun'26 end Site possession date (Ready for Interiors) : Aug'26 end Main door facing : West Interiors color palette : Not white/wooden, cool light pastel colors Family members : 3-4 adults Kids- Name & Age : NA Style : Modern (not same theme for entire home) Budget : for modular furniture - 15LÂ excluding loose furniture, lighting, painting, decorative stuff Â Scope Of Work :Â Foyer - Shoe rack storage, no fixed seating (pouffe/ ottoman space can be planned)Â Wall to be highlighted Not wallpaper, similar to ref image Living : TV unit to be minimal 65-70"Â TV size TV right wall - to be highlighted Sofa (shape to be decided) preferably L or 2+3 Sofa wall to be done with arches / mouldings 4 seater dining table, with bench Pooja unit - usually sitting on floor (need to check based on design) on right north wall Crockery unit, with mirror (similar to ref image) Kitchen WM, DW, 2 sinkÂ Appliances : M/W, mixer, wet grinder, air fryer DD fridge 3'W Kitchen- builder not providing , BD scope BR-3Â Gaming room, office space theme recreational Sofa cum bed in study space shown in Floor plan Hinged wardrobe with loft study on cot side as per Floor plan study for 2 persons Common VanityÂ :Â base storage BR-2 (PBR) Hinged WR with loft TV drawer unit TV size : 45-48" Vanity - base storage with laundry basket space on either sides dresser mirror BR-1 (MBR)Â Aristo WR with mirror dresser storage study 1 person space projector accent chair space (cozy reading nook) Headboard wall to be designed MBR vanity base vanity storage with laundry basket space False ceiling : Living , Dining, MBR - peripheral | 2026-05-20 11:38:10 +0530 | Aman Kumar | Sales Takeaway VDNB Client Client Type: IT ProfessionalsBudget: 15 LakhsVery design-centric clientsNot looking for Pinterest images or external ideasExpecting more insights and suggestions from the designerWife is more particular and focused on design aesthetics | 2026-06-05 |  | 2026-06-12
20095 | Turnkey | May'26 | Shweta Agrawal | Rohan Ekanta | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 1282753 | 9999 | 0 | 0 | 0 | 46 | 0 | 118276 | 128275 | 513101 | 513101.2 |  |  | 2026-05-17 | 2026-05-30 10:52 | 2026-05-20 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-17 | 2026-05-19 17:09 | 0 | 0 | 0 | 0 | 0 | 0 | 1087078 | 195674 | 2026-05-27 19:35:22 +0530 | Rajasekar Ranganathan | Requirement Meeting MOM Shwetha ResidenceClient DetailsClient Name: ShwethaProperty: Rohan Ekanta 2BHKProfession: ITPossession Timeline: September EndFamily Members: 2 Adults + Visiting Parents + 1 KidChild: Vritika 1 Year 4 MonthsPreferred Theme: Neutral palette with pastel pop-up colorsStrictly No Grey tonesEntrance Facing: WestBudget: 1012 LakhsCDP Meeting Date: 30th After 1 PMDesign Direction & Theme NotesElegant neutral base with soft pastel accentsWarm and welcoming ambienceFunctional family-friendly planning with child-safe considerationsModern contemporary styling with clean detailingFocus on smart storage and clutter-free spacesAccent walls to be uniquely designed aesthetically (minimal but premium)Area-wise RequirementsFoyer AreaCheck feasibility for shoe cabinet outsideEntrance accent wall requiredNo reference image providedDesign to be elegant and aesthetically premiumLiving AreaSeatingL-shaped sofa cum bedTV UnitWall-mounted drawer designTall unit optionalNeed to explore during design stageSofa Back WallWall design should complement TV unit aestheticsClient may share reference images laterDining AreaDining4-Seater dining setupDining WallPicture wall conceptSimple elegant wall designKitchenRequirementsPantry unitAppliance unit for:Mixer grinderMicrowaveAir fryerSink Planning2 sink in kitchenGranite countertopUtility AreaRequirements3 sink in utilityWashing machine beside sinkOpposite side:Single storage unit for extra storageBalconyRequirementsSeating areaPlanters / greeneryDecorative lightingIf feasible:Exterior accent wallMaster Bedroom (MBR)Furniture & StorageDresser unit integrated with study unitWardrobe with full-length mirrorCheck if sliding wardrobe is required based on spaceKing-size bedSleek bedside tablesSeparate study tableAccent WallTheme-based design with pastel highlightsMaster BathroomVanityVanity unit requiredBedroom 2 (BR2)FurnitureExisting queen-size bed to be retainedWardrobe within niche areaStudy unit towards windowAccent WallRequiredCommon WashroomVanityVanity unit requiredExtra Sink AreaOne vanity unit required | 2026-05-27 19:34:49 +0530 | Rajasekar Ranganathan | Requirement Meeting MOM Shwetha ResidenceClient DetailsClient Name: ShwethaProperty: Rohan Ekanta 2BHKProfession: ITPossession Timeline: September EndFamily Members: 2 Adults + Visiting Parents + 1 KidChild: Vritika 1 Year 4 MonthsPreferred Theme: Neutral palette with pastel pop-up colorsStrictly No Grey tonesEntrance Facing: WestBudget: 1012 LakhsCDP Meeting Date: 30th After 1 PMDesign Direction & Theme NotesElegant neutral base with soft pastel accentsWarm and welcoming ambienceFunctional family-friendly planning with child-safe considerationsModern contemporary styling with clean detailingFocus on smart storage and clutter-free spacesAccent walls to be uniquely designed aesthetically (minimal but premium)Area-wise RequirementsFoyer AreaCheck feasibility for shoe cabinet outsideEntrance accent wall requiredNo reference image providedDesign to be elegant and aesthetically premiumLiving AreaSeatingL-shaped sofa cum bedTV UnitWall-mounted drawer designTall unit optionalNeed to explore during design stageSofa Back WallWall design should complement TV unit aestheticsClient may share reference images laterDining AreaDining4-Seater dining setupDining WallPicture wall conceptSimple elegant wall designKitchenRequirementsPantry unitAppliance unit for:Mixer grinderMicrowaveAir fryerSink Planning2 sink in kitchenGranite countertopUtility AreaRequirements3 sink in utilityWashing machine beside sinkOpposite side:Single storage unit for extra storageBalconyRequirementsSeating areaPlanters / greeneryDecorative lightingIf feasible:Exterior accent wallMaster Bedroom (MBR)Furniture & StorageDresser unit integrated with study unitWardrobe with full-length mirrorCheck if sliding wardrobe is required based on spaceKing-size bedSleek bedside tablesSeparate study tableAccent WallTheme-based design with pastel highlightsMaster BathroomVanityVanity unit requiredBedroom 2 (BR2)FurnitureExisting queen-size bed to be retainedWardrobe within niche areaStudy unit towards windowAccent WallRequiredCommon WashroomVanityVanity unit requiredExtra Sink AreaOne vanity unit requiredKey Design ConsiderationsChild-friendly edges and finishesEasy maintenance materialsSpace optimization for visiting parentsHidden storage wherever possibleSoft warm lighting strategyPastel accents to be introduced through:UpholsteryWall panelsDecor elementsLoose furniture accentsFollow-up RequirementsAwaiting possible reference images from client for:Sofa wallTV unit inspirationNeed site measurement verification for:Sliding wardrobe feasibilityExternal shoe cabinet feasibilityBalcony accent wall feasibility | 2026-05-26 19:03:25 +0530 | Muralikrishna Udupi | 2bhk, Developer tie-up. 9-10 lakh budget. Husband and wife both It professionals. Price protection has to be given. | 2026-06-07 |  | 2026-06-14
20098 | Turnkey | May'26 | Harsh mehta | Sheth Montana | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Hitesh Rawal |  | Active | Prospect | DCM Due | 847678 | 9999 | 0 | 0 | 0 | 54 | 0 | 74769 | 84768 | 347631 | 330511.2 |  |  | 2026-05-19 | 2026-05-22 12:11 | 2026-05-20 | 2026-05-22 16:49 | 2026-05-24 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-05-24 |  | 2026-05-25 |  | 2026-05-25 |  | 2026-05-26 | [5 empty] | 2026-06-01 |  | 2026-06-09 |  | 2026-06-10 |  |  |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-20 | [6 empty] | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-08-14 | [5 empty] | 2026-06-18 |  | 2026-05-27 |  | Unknown | 2026-05-19 | 2026-05-19 20:32 | 0 | 0 | 0 | 0 | 0 | 0 | 971649.9187 | 158482 | 2026-05-20 14:47:03 +0530 | Bhawaya Goyal | DCM: Cx- Harsh Mehta Poss. in 2 weeksÂ budget : not disclosedÂ suggested : 15-20LÂ People : 5Â parents sister + nieceÂ yourself 48th floor - city view Master bedroom - parentsÂ Common bedroom - Sister + Harsh entrance - EAST facingÂ FOYER: shoe rackÂ safety doorÂ Living room : design pref. - modern + minimalist (open to options) sofa seating - 3/4 seaterÂ TV unit + book shelvesÂ dining table - if possible 6 seater otherwise 4 minimal storage for crockeryÂ mirror panelling on 1 wall.Â mandirÂ Storage console Balcony : single seater swingÂ plantersÂ Kitchen : modular kitchenÂ no open storageÂ wall unit only on sink sideÂ avoid storage on hob side goods storage in dry balconyÂ covering optionsÂ Bedroom 1 :Â work station sliding wardrobeÂ queen size bedÂ dressing mirrorÂ Master Bedroom : wardrobeÂ queen size bedÂ work station TV unit sliding space for dressing (father is working) washroom : vanity covering of duct areas in washroom (ceiling) texture paint / colour blocking/ wallpaper false ceiling painting electricals | [6 empty] | 2026-06-01 |  | 2026-06-08
20100 | Turnkey | May'26 | Arpita | Prestige City Serjapur | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 1457225 | 172744 | 1724323 | 0 | 0 | 39 | 0 | 0 | 118701 | 615399 | 550380.8 |  |  | 2026-05-20 | 2026-05-26 10:53 | 2026-05-26 | 2026-05-26 11:33 | 2026-05-29 | 2026-05-26 11:48 | 2026-07-05 |  | 2026-08-15 |  | 2026-08-22 |  | 2026-05-26 | 2026-05-26 12:45 | 2026-05-27 | 2026-06-01 13:31 | 2026-06-01 | 2026-06-06 14:39 | 2026-06-09 | 2026-06-09 19:02 |  |  |  |  | 2026-07-06 |  | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-07-20 |  | Unknown | 2026-05-20 | 2026-05-20 18:33 | 1461291 | 263032 | 0 | 0 | 0 | 0 | 1586950.7756 | 262164 | 2026-07-03 16:23:03 +0530 | Avishkar Sargam | Minutes of Meeting (MOM) â€“ ArpitaLiving RoomProceed with a simple wall beading design in the foyer area with a pendant light. Incorporate a hidden cabinet within the crockery unit. Shift the pooja unit to the opposite wall. TV unit to include floating drawers. No wall treatment or design concept on the entrance wall. KitchenRemove the tall unit. Add a dedicated wall unit for the microwave. Increase storage in the utility area. Add three wicker basket units on the service side. Master BedroomMinimal bed-back wall design with floating shelves. Add POP panelling on the entrance wall. Install a Victorian-style mirror on the bathroom-side wall. Kids' BedroomWallpaper with framed jersey display on the bed-back wall. Study unit on the opposite wall with extended storage. Wardrobe to include bottom drawers and an open display unit. Guest BedroomWallpaper with POP panelling on the bed-back wall. Provide a foldable study table. | 2026-06-06 14:39:25 +0530 | Athul Ajaykumar |  | 2026-06-05 14:19:10 +0530 | Athul Ajaykumar |  | 2026-07-06 |  | 2026-08-16 |  | Under Construction | 2026-07-31
20101 | Turnkey | May'26 | Karishma Tanna |  | MUM - GOR | Yes | Zoya Ansari | Vishakha Vaishnav | Kashmira Nerurkar |  | Priyanka Kamble | Nilesh Patel | Rizwan Mistry | Murali S | Manasi Patil | Aakash Gaikwad | Active | Installation | Execution | 481839 | 0 | 550340 | 550340 | 481839 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-19 | 2026-05-20 14:55 | 2026-05-20 | 2026-05-20 16:02 | 2026-05-20 | 2026-05-20 17:27 | 2026-05-23 | 2026-05-22 16:18 | 2026-05-23 | 2026-05-22 16:20 | 2026-06-03 | 2026-06-03 00:06 | 2026-05-20 | 2026-05-21 18:21 | 2026-05-21 | 2026-05-22 16:17 | 2026-05-22 | 2026-05-22 16:17 | 2026-05-23 | 2026-05-22 16:17 |  |  |  |  | 2026-05-22 | 2026-05-22 16:18 | 2026-05-22 | 2026-05-22 14:36 | 2026-05-23 | 2026-05-22 14:36 |  |  | 2026-06-04 | 2026-06-11 18:22 | 2026-06-12 | 2026-06-13 15:27 | 2026-06-14 | 2026-06-13 16:27 | 2026-06-14 | 2026-06-16 15:35 |  |  |  |  | 2026-06-22 11:54 | 2026-06-27 | 2026-06-26 20:53 | 2026-07-02 | 2026-06-30 11:10 | 2026-07-10 | 2026-06-16 15:36 | 2026-06-30 | 2026-06-30 17:31 | 2026-06-30 | 2026-07-13 15:42 | 2026-07-15 |  |  |  | 2026-07-19 |  | 2026-07-21 |  | 2026-07-22 | [5 empty] | 2026-06-13 | 2026-06-22 11:53 | 2026-05-23 | 2026-05-22 16:18 | Unknown | 2026-05-19 | 2026-05-20 14:55 | 466390 | 83950 | 466390 | 83950 | 408338 | 73500 | 408338 | 73500 | 2026-07-13 11:14:15 +0530 | Nilesh Patel | PI works has been completed at site Modulars carcass Installation has been completed at site PU shutters has bene delivered at site on 11th July and Installation works is in progress Ceiling final Coat of paint has been completed Blocker - PVC beading has not been delivered at site | [6 empty] | 2026-05-23 | 2026-05-22 16:18 | 2026-05-23 | 2026-05-22 16:20
20102 | Turnkey | May'26 | Supriya | Sobha dream garden | BNG - HRBR | Yes |  | Parasa Sri | [6 empty] | Raghavendra S |  | Active | Design | DEM1 | 807915 | 214999 | 1075962 | 0 | 0 | 41 | 0 | 0 | 0 | 302558 | 290358 |  |  | 2026-05-20 | 2026-05-20 13:42 | 2026-05-20 | 2026-05-23 15:29 | 2026-05-28 | 2026-05-28 15:17 | 2026-08-13 |  | 2026-08-20 |  | 2026-08-27 |  | 2026-05-28 | 2026-05-29 18:57 | 2026-05-29 | 2026-05-31 11:59 | 2026-05-31 | 2026-06-04 14:09 | 2026-06-09 | 2026-06-09 12:10 |  |  |  |  | 2026-06-05 | 2026-05-29 18:57 | 2026-08-22 |  | 2026-08-23 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 | [6 empty] | 2026-09-20 |  | 2026-09-29 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-02 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-27 | [5 empty] | 2026-08-31 |  | 2026-08-09 |  | Unknown | 2026-05-20 | 2026-05-20 13:39 | 911832 | 164129 | 0 | 0 | 0 | 0 | 880763.2458 | 145424 | 2026-06-19 19:18:52 +0530 | Rajeshwari S | Welcome call done along with Surabhi Non RTMI Project Client wants to start design phase only after IM IM can be done in Sept. Price protection - Client is saying that internally team has given price protection till he gets handover . @Raghav has to confirm on this. | 2026-06-04 14:09:13 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site accessibilityClient mentioned that he will be getting the site by next month * DEM 1 Next month * 10% Payment Stagealready paid 20% *No civil work planned in the client's scope of work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 8,80,764 Offers Discussed During the Call: PM fee waiver (5%) Laminate Upgrade - May '26 Campaign 100% GST Waiver Design fee waiver (5%) Silver Coin 21g Final Closing Value Discussed: 8,07,915 Checklist terms - descoping, delay compensation, agreement terms are clear Note: The client mentioned that he will be doing the 1st DEM after the IMs are done. He will get the site accessibility by next month for IMs. | 2026-06-04 11:16:16 +0530 | Sanjana Swami |  | 2026-08-14 |  | 2026-08-21 |  | Under Construction | 2026-09-01
20103 | Turnkey | May'26 | Vimal Singhania | Kalpataru Vivant North Wing A | MUM - GOR | Yes | Riddhi Deshpande | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Active | Design | DEM1 | 1575015 | 209762 | 2097622 | 0 | 0 | 20 | 0 | 0 | 105241 | 633488 | 626523.6 |  |  | 2026-05-17 | 2026-06-19 14:09 | 2026-06-19 | 2026-06-19 20:46 | 2026-06-22 | 2026-06-19 20:54 | 2026-07-01 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-06-19 | 2026-06-19 20:44 | 2026-06-20 | 2026-06-22 12:31 | 2026-06-22 | 2026-06-25 13:57 | 2026-06-26 | 2026-06-26 14:40 |  |  |  |  | 2026-07-02 |  | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-27 |  | Unknown | 2026-05-17 | 2026-06-19 14:09 | 1777646 | 319976 | 0 | 0 | 0 | 0 | 1768695.398 | 292052 | 2026-07-14 13:43:17 +0530 | Kashmira Nerurkar | Cx agitated with PH's followup. He would update us once he is available to align the DEM-1. | 2026-06-26 14:42:32 +0530 | Christopher Macwan | Welcome call done. Initial measurement not done as would receive possession by End of July 2026 DEM Dates -Â DEM 1 - Customer not sure on the DEM1 dates and will update on the whatsapp group DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of July 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-25 13:56:24 +0530 | Athul Ajaykumar |  | 2026-07-02 |  | 2026-07-09 |  | Under Construction | 2026-07-31 | 2026-06-19 | 209762 | Ravi Roy
20105 | Turnkey | May'26 | IBAADAT ENTERPRISES LLP (Simmi Madan) Madan | Triton | MUM - GOR | Yes | Neha Yadav | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Moni Sahani |  | Active | Preproduction | DEM2 | 2656653 | 531331 | 3608843 | 0 | 0 | 20 | 0 | 0 | 0 | 1079521 | 1045801.2 |  |  | 2026-05-20 | 2026-05-28 12:39 | 2026-05-20 | 2026-05-28 12:40 | 2026-05-31 | 2026-05-28 18:09 | 2026-06-23 | 2026-06-23 18:50 | 2026-06-29 |  | 2026-07-06 |  | 2026-05-28 | 2026-05-28 18:43 | 2026-05-29 | 2026-06-06 16:37 | 2026-06-06 | 2026-06-09 12:36 | 2026-06-12 | 2026-06-12 15:20 |  |  |  |  | 2026-06-23 | 2026-06-25 19:43 | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-13 | 2026-06-23 18:38 | Site is RTMI | 2026-05-20 | 2026-05-20 15:09 | 3058342 | 550501 | 0 | 0 | 0 | 0 | 3045949.992 | 495747 | 2026-07-03 17:09:49 +0530 | Meet Shah | Others: | 2026-06-23 18:35:13 +0530 | Neha Yadav | RE DDM1 Meeting Discussion: Living & kitchen: 1)Passage storage wall unit need to remove and need to add tall unit ,storage behind door will be lesser depthÂ 2)Need to add flush door for passage & worship room wallÂ 3)Breakfast counter will be same as kitchen counterÂ 4)Need to add glass tall storage on counterÂ 5)Console need to add next to main enterance 6)Tv unit need to redesign need to add tall display unit. 7)Sofa wall will have pop design 8) Crocker base will have 4 drawers on topÂ 9)Tall open unit will have solid shutter near crockery 10)Foyer area need to redesignÂ Master : 1)Need to add open tall unit and dresser with mirror near wardrobeÂ 2)Curve wall panelling need to do behind bedÂ 3)Need to do packing behind tv unit & tv unit depth will be same as wardrobeÂ Guest Room: 1)Bed will be queen bedÂ 2)Side table need to add both side with 2 drawer one will be dresser with mirrorÂ 3)Need to add 4 study table with tall storage with printerÂ Feel free to addÂ a pointers if missed any. | 2026-06-12 15:19:56 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Done on 9th june DEM Dates -Â DEM 1 - Aligned for 16th June by 2:30 pm DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-24 | 2026-06-23 18:53 | 2026-06-30 |  | RTMI
20107 | Turnkey | May'26 | Rohit Bhatia | Godrej Exquisite | MUM - Thane | No Estimate | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-20 | 2026-05-20 19:11 | 2026-06-30 | 2026-07-02 19:52 | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-05-20 | 2026-05-20 19:10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-28 13:10:08 +0530 | Anant Giri | Some Image was uploaded | [6 empty] | 2026-07-13 |  | 2026-07-20
20110 | Turnkey | May'26 | Srividya Vydianathan | Deep Jyoti | MUM - GOR | Yes | Karan Chavda | Reshma Melanta | Safalta Karkera | [5 empty] | Ashish Jha |  | Hold | Preproduction | Site Readiness 1 | 1542797 | 308559 | 2053552 | 0 | 0 | 2 | 28 | 0 | 0 | 673270 | 560968.4 |  |  | 2026-05-20 | 2026-05-21 14:56 | 2026-05-28 | 2026-05-28 15:37 | 2026-05-31 | 2026-05-30 12:35 | 2026-06-14 | 2026-06-14 16:25 | 2026-06-20 |  | 2026-07-28 |  | 2026-05-30 | 2026-05-30 18:31 | 2026-05-31 | 2026-05-30 18:40 | 2026-05-30 | 2026-06-02 17:28 | 2026-06-07 | 2026-06-07 15:27 |  |  |  |  | 2026-06-14 | 2026-06-15 15:59 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-06-08 | 2026-06-14 16:16 | Site is Non-RTMI | 2026-05-20 | 2026-05-21 13:57 | 1740298 | 313253 | 0 | 0 | 0 | 0 | 1710114.8045 | 277703 | 2026-06-14 16:13:26 +0530 | Karan Chavda | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion Based on meeting, below is a list of all the requirements that were discussed during the meeting: Ms. Srividya Minutes Of Meeting 14/06/2026 Guest bedroom 1. Used clothes unit 2. Invisble bed 3. sliding wardrobe 4. Shoe pull out in ritgh side wardrobe 5. Acoustic panels on wallÂ Master bedroom 1. 3 drawers in both wardrobes 2. Flip bed to opposite wall and vice versa Living roomÂ 1. Optional jhula in living 2. Extended reclined sofa chair 3. 3 seater sofa 4. Console table near entranceÂ KitchenÂ 1. To be checked during measurementsÂ 2. Inlet outlet for washing machine to be done. 3. Parallel kitchen False ceiling - outer cove ceiling, with tracj light in all rooms Next meeting thursday - 5.30 pm | 2026-06-07 15:26:16 +0530 | Reshma Melanta | Please find the Minutes of Meeting (MOM) and project updates below: Key Updates: Site Status: The lift at the site (B Wing, 10th Floor) is currently not working. Because of this, the Inward Movement (IM) of materials cannot be aligned at the moment. We are monitoring this closely and will update once the lift is operational. Group Updates: Project Management and the Bonito Care team have been added to this group to ensure seamless coordination and support moving forward. Upcoming Milestone / Meeting:Event: DEM - 1 MeetingDate: 11th June 2026Time: 6:00 PM - 8:00 PM | 2026-06-02 17:27:34 +0530 | Sanjana Swami |  | 2026-06-15 | 2026-06-14 16:28 | 2026-06-21 |  | Under Construction | 2026-07-31
20111 | Turnkey | May'26 | Nishant Singh | Pavani Mariabilia | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Mohammed Rasick |  | Active | Design | 20% Payment | 1487867 | 205999 | 1487867 | 0 | 0 | 4 | 0 | 0 | 91574 | 623072 | 567221.2 |  |  | 2026-05-20 | 2026-05-23 11:43 | 2026-05-21 | 2026-05-23 12:16 | 2026-05-27 | 2026-05-27 11:40 | 2026-07-12 | 2026-07-11 18:21 | 2026-07-17 |  | 2026-07-24 |  | 2026-05-24 | 2026-05-25 19:03 | 2026-05-28 | 2026-05-27 12:41 | 2026-05-27 | 2026-06-05 17:53 | 2026-06-09 | 2026-06-09 10:57 |  |  |  |  | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-12 | 2026-07-11 10:38 | Site is Non-RTMI | 2026-05-20 | 2026-05-20 20:52 | 1673742.669 | 276366 | 0 | 0 | 0 | 0 | 1673742.669 | 276366 | 2026-07-12 15:19:41 +0530 | Parasa Sri | Client response | 2026-06-27 16:15:02 +0530 | Parasa Sri | Welcome call Done , Site is not ready for Initial measurement, Client is not available in banglore | 2026-06-05 17:50:52 +0530 | Sanjana Swami |  | 2026-07-12 | 2026-07-11 18:24 | 2026-07-18 |  | Under Construction | 2026-08-01
20116 | Turnkey | May'26 | Rajesh Ungratwar | Swastik Platinum | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam |  |  | suraj kumar | Aditya Vikram |  | Nishtha Valawalkar | Shailendra Mishra | Active | Design | DEM3 | 1361227 | 223699 | 1486618 | 0 | 0 | 3 | 0 | 0 | 0 | 672476 | 465052 |  |  | 2026-05-21 | 2026-05-21 16:01 | 2026-05-21 | 2026-05-23 18:36 | 2026-05-24 | 2026-05-30 16:24 | 2026-06-17 | 2026-06-16 18:57 | 2026-07-12 | 2026-07-12 01:30 | 2026-07-16 |  | 2026-05-24 | 2026-05-30 15:19 | 2026-05-31 | 2026-05-30 19:18 | 2026-05-30 | 2026-06-05 11:01 | 2026-06-10 | 2026-06-10 12:53 |  |  |  |  | 2026-06-13 | 2026-06-13 17:41 | 2026-08-14 | 2026-07-12 13:32 | 2026-07-13 | 2026-07-12 13:33 |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-11 | 2026-06-16 13:21 | Site is Non-RTMI | 2026-05-21 | 2026-05-21 16:00 | 1262648 | 223970 | 0 | 0 | 0 | 0 | 1557552.8234 | 265455 | 2026-06-13 19:27:40 +0530 | Naved Malik | Some Image was uploaded | 2026-06-05 11:00:42 +0530 | Athul Ajaykumar | The overview page project value and the discounted value in the client's offer email are the same now. Changes are done. Moving OB | 2026-06-03 12:17:13 +0530 | Bhawaya Goyal | Onboarding Due: Changes has been done by Nishta | 2026-06-18 | 2026-06-16 18:58 | 2026-07-13 | 2026-07-12 01:33 | Under Construction | 2026-06-30
20117 | Turnkey | May'26 | Santosh | Heritage Firefly Fields | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 880535 | 89999 | 1193409 | 0 | 0 | 36 | 0 | 0 | 86108 | 352214 | 352214 |  |  | 2026-05-21 | 2026-06-01 11:08 | 2026-05-22 | 2026-06-02 09:22 | 2026-06-05 | 2026-06-03 17:58 | 2026-07-09 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-06-03 | 2026-05-31 | 2026-06-04 | 2026-06-05 09:24 | 2026-06-05 | 2026-06-09 11:14 | 2026-06-10 | 2026-06-10 12:51 |  |  |  |  | 2026-07-10 |  | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-06-11 | 2026-06-24 15:52 | Site is RTMI | 2026-05-21 | 2026-05-21 18:24 | 1011364 | 182045 | 0 | 0 | 0 | 0 | 999551.37 | 164827 | 2026-07-12 11:28:41 +0530 | Sayed Byahatti | DDM1:SANTOSH - 07-07-2026 Please refer TV unit kind of good design Also all the bed room walls and celling Full Pooja room as discussed Near kitchen entrance arch which we discussed vegetable basket remove pop add wood legdes with wooden kind of design all area. Remove wallpaper. l shape storage and washing machine area to be plan for utility area. | 2026-07-10 12:21:39 +0530 | Sayed Byahatti | DDM1: SANTOSH - 09/07/2026 KITCHEN - Vegetable basket to be add. DINING AREA - Remove wall pop, add wood legdes with wooden concepts. PARENTS BEDROOM - Change this wall concepts & also false ceiling design. TV UNIT- Design need to be change as per shared reference. Remove pop design simple design need to be plan. POOJA UNIT - Seating pooja unit to be design. KIDS BEDROOM -Remove wallpaper concept add other design. MASTER BEDROOM -Remove wallpaper concept add other design. | 2026-06-21 11:32:57 +0530 | Sayed Byahatti | Minutes of Meeting held on Date: SANTOSH - 14-06-2026 (KT) GROUND FLOOR POOJA UNIT TO BE ADD IN COTATION AS PER THE DESIGN FINALIZATION. STAIRCASE BELOW STORAGE TO BE DESIGN AS PER THE SITE CONDITION.L CORNER PLAN TO SUGEST. PARENT BDEROOM WALL CONCEPT AND PANNING WORK. KICHEN FRIDGE AREA COVERD AS PER SHARED REFERENCE VEDIO. GRANITE OR QUARTZ IS IN BONITO SCOPE. ADD DADO TILES IS IT IN BONITO SCOPE & ALSO IN COTATION. KITCHEN EXCEPT SHUTTER ALL CARCAS SHOULD BE BWP. 1ST FLOORÂ LIVING AREA WALL & CEILING CONCEPTS TO BE DESIGN. DAUGHTER BEDROOM RE - WORKÂ MASTER BEDROOM - WARDROBE DESIGN WITH CONCEALED HANDS, STORAGE AND BAY WINDOW REFERE THE VEDIO. ALL CEILING DESIGN AND LIGHTS IS IN BONITO SCOPEÂ DINING AREA VANITY MIRROR & ALL BATHROOM MIRROR. HEAD ROOM ABOVE WASHING MACHINE AREA ABOVE IT WALL STORAGE. 2BED'S COMPLIMENTARY FROM BONITO. | 2026-07-10 |  | 2026-08-02 |  | Under Construction | 2026-06-30
20120 | Turnkey | May'26 | SANDIP GAIKAR | Shivkrupa | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 1035903 | 9999 | 1035903 | 0 | 0 | 46 | 0 | 93591 | 103590 | 462923 | 365799.2 |  |  | 2026-05-21 | 2026-05-21 20:37 | 2026-05-21 | 2026-05-23 18:36 | 2026-05-27 | 2026-05-30 12:09 | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-21 | 2026-05-21 20:37 | 880171 | 155731 | 0 | 0 | 0 | 0 | 880171 | 155731 | 2026-05-27 12:37:18 +0530 | Pooja Nakul Sharma | DCM: MOM SANDIP GAIKAR ResidenceProject Details: Unit No.: 20120Carpet Area: 275 SqftFamily Members: Husband, Wife & 1 Daughter (9 Years)Budget: 810 LakhsCDP Meeting Scheduled: 27/28 at 6:00 PMLiving RoomTV unit to be planned on the entrance wall.Entrance wall can be extended post OC.Provision for sofa-cum-bed required.43 TV provision to be incorporated.False ceiling already provided by the builder.KitchenL-shape open kitchen layout.Existing bottom cabinets already provided by the builder.Top cabinets and loft storage to be designed and planned.Refrigerator provision can be incorporated.Washing machine location not fixed yet.Master Bedroom (MBR)Queen size bed required.Wardrobe with integrated dresser.Foldable study unit to be explored as an optional feature.Additional NotesNo existing furniture on site.Space planning to focus on multifunctional and space-saving solutions considering the compact apartment size.Design language to remain minimal, practical, and storage-efficient within the discussed budget range | [6 empty] | 2026-06-07 |  | 2026-06-14
20121 | Turnkey | May'26 | Abdul ghani | Independent House | BNG - HRBR | No Estimate | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-21 | 2026-05-22 11:40 | 2026-05-22 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-21 | 2026-05-22 11:40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-21 18:57:55 +0530 | Unknown | About the Customer **Property Handover in 3-4 Months** Customer is building a house near Whitefield, Old Madras Road, with construction expected to be handed over in 3-4 months. They are looking for interior design services for a 4BHK duplex where they will reside, and a separate 1BHK/2BHK for rent. **Financing and GST Waiver Key Concerns** Customer's primary concern is the EMI option; they will only proceed if financing is available. They are also interested in the 100% GST waiver offer. **Scope of Work and Budget Estimate** Customer has already contracted painting and POP work, and is looking for interiors, curtains, and modular kitchen services. They estimate the budget for the duplex could be around 10 lakhs. **Experience Center Visit Confirmed** Customer agreed to visit the HSR Layout experience center tomorrow with their brother and family, after confirming with them. **WhatsApp Location Invite Pending** Agent will send the experience center location via WhatsApp. | [6 empty] | 2026-06-07 |  | 2026-06-14
20124 | Turnkey | May'26 | Chayanika Chandamajumder | Radiance Floresta | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 1813520 | 9999 | 1813520 | 0 | 0 | 36 | 0 | 171353 | 181352 | 741876 | 708939.6 |  |  | 2026-05-21 | 2026-05-22 17:47 | 2026-05-22 | 2026-05-30 18:36 | 2026-06-09 | 2026-06-09 11:49 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-12 |  | Unknown | 2026-05-21 | 2026-05-21 19:56 | 1536881 | 276638 | 0 | 0 | 0 | 0 | 1536881 | 276638 | 2026-06-09 11:42:38 +0530 | Rituparna Chakraborty | Some Image was uploaded | 2026-06-09 11:41:38 +0530 | Rituparna Chakraborty | Some Image was uploaded | 2026-05-22 14:14:23 +0530 | Rituparna Chakraborty | DCM: Mrinmoy - telecom NTT data Chayanika - Homemaker, boutiq Mishika- 8Th grade, fond of reading Out side the MD a small shoe unit , open and close main shoe unit that will come under the stairs , with rattan may be , the basin will be used for puja utensils , iron table and iron , granite slab with a drawer,Â 3+2 for formal living , wall decor , partitionÂ curved sofa , 65" tv , tv unit with storageÂ Dining wall double ht, koi fish & lotus wallpaper with molding , 5 seater dining existing KItchen Countertop - greyÂ tiles- tealÂ Green & brown kitchenÂ Air fryer , rolling shutter - mixer grinder, kettle Fridge , tall unit for MW & otg , pantry storageÂ cylinder storage , one in kitchen other one under the stairsÂ geyser existingÂ point, existing aquaguard single bowl with drain board GBR Queen bed & dresser existing , wardrobe , minimal , Rattan wardrobe , workstation with tv ledgeÂ some book storage , bay window seating if possible or some seatingÂ vanity with mirror , fluted glass partition Â Powder roomÂ VanityÂ Mishika (M bedroom) Y2K themeÂ beige white backgroundÂ queen size bedÂ bay window, single seater corner , bookshelves wall shelvesÂ pastel blue Dresser with bulbs and seating , everyday clothing wardrobeÂ StudyÂ North-East L studyÂ wall shelves for books , white board , pin board , sir's workstation provision if possibleÂ wardrobe tinted glass & solid shutterÂ Master bedroomÂ low bed , fabric headboard,Â wallpaper wih panel , minimal tv unitÂ Dresser and wardrobe in WIC wardrobe tinted glass & solid shutter very light mix of beige and lavenderÂ chair spaceÂ Tall storage with glass , mirror and drawers vanity and mirror | 2026-06-17 |  | 2026-06-24
20126 | Turnkey | May'26 | Navin Girishchandra Upadhyay | Pearl GArden | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1148640 | 9999 | 0 | 0 | 0 | 55 | 0 | 104865 | 114864 | 534958 | 383954 |  |  | 2026-05-21 | 2026-05-21 20:50 | 2026-05-27 | 2026-05-28 12:40 | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-05-21 | 2026-05-21 20:50 | 0 | 0 | 0 | 0 | 0 | 0 | 975711 | 172929 | 2026-06-03 18:50:02 +0530 | Krutika Vernekar | DCM: Budget : 10 L Stretch : 13 L Suggested : 15 L | 2026-05-28 12:23:19 +0530 | Krutika Vernekar | DCM: MOM Navin Upadhye Residence Project: Mansarovar Configuration: 1 + 2 Carpet Area: Approx. 917 sq.ft. Ceiling Height: 10 civil changes already taken care ready project Family Members: 5 Members Client Requirements Living Room: Existing TV unit to be retained partially. New TV size: 75 (existing 65). Safety door required. Shoe rack at entrance. Informal 6-seater loose dining setup outside. Mandir provision required. Entry wall design required. False ceiling required. already done Kitchen : Existing kitchen to be converted into daughters bedroom. Room is compact and feels claustrophobic; space optimization is important. Requirements: Single bed Folding study table 2 wardrobe Existing loft to be maintained / utilized. Master Bedroom TV size: 65. Bed with storage. Wardrobe required. Dresser required. TV unit required. Kids / Sons Room Workstation setup required. Client owns PS setup. TV size: 42. Wardrobe to be designed within existing niche. Additional Notes Vanity and safety-related provisions discussed. Base units near entry door discussed. Shoe rack budget/approximation noted. |  |  |  | 2026-06-08 |  | 2026-06-15
20129 | Sub Project |  | Vinayak Raj Sharma | L&T Elixir Reserve | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Safalta Karkera |  |  | Savita Parab | Rizwan Mistry | Murali S |  | Aakash Gaikwad | Active | Production | 100% Payment | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-22 | 2026-05-27 12:09 | 2026-05-23 | 2026-05-27 12:09 | 2026-05-27 | 2026-05-27 12:09 | 2026-05-28 | 2026-05-27 12:10 | 2026-05-28 | 2026-05-27 12:12 | 2026-05-28 | 2026-05-27 12:13 | 2026-05-27 | 2026-05-27 12:09 | 2026-05-28 | 2026-05-27 12:09 | 2026-05-27 | 2026-05-27 12:09 | 2026-05-28 | 2026-05-27 12:09 |  |  |  |  | 2026-05-27 | 2026-05-27 12:10 | 2026-05-28 | 2026-05-27 12:12 | 2026-05-28 | 2026-05-27 12:12 |  |  | 2026-05-28 | 2026-05-27 15:18 | 2026-05-28 | 2026-05-27 21:00 | 2026-05-29 | 2026-05-28 15:12 | 2026-05-29 | 2026-05-28 12:04 |  |  |  |  | 2026-05-30 12:28 | 2026-06-03 | 2026-06-03 23:27 | 2026-06-08 | 2026-06-06 11:03 | 2026-06-07 |  | 2026-06-06 |  | 2026-07-01 |  | 2026-07-06 |  |  |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-05-27 | 2026-05-28 15:12 | 2026-05-28 | 2026-05-27 12:09 | Unknown | 2026-05-22 | 2026-05-27 12:09 | 0 | 0 | 0 | 0 | 35720.34 | 0 | 35720.34 | 0 | 2026-06-01 16:33:13 +0530 | Savita Parab | Execution: Main order work in progress please plan delivery with main order | [6 empty] | 2026-05-28 | 2026-05-27 12:10 | 2026-05-28 | 2026-05-27 12:12
20130 | Sub Project |  | Dipen Shah | Runwal Forests | MUM - GOR |  | Mandar Ambre | Manzoor Shaikh | Shantanu Parakh | Priyanka Kamble | Priyanka Kamble | Suraj Jaiswar | Rizwan Mistry | Murali S |  | Prasad Bhivaji Hande | Active | Production | Dispatch Due | 145576 | 145576 | 0 | 0 | 378863 | 20 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-22 | 2026-05-26 13:49 | 2026-05-23 | 2026-05-26 13:49 | 2026-05-26 | 2026-05-26 13:49 | 2026-05-27 | 2026-05-26 13:50 | 2026-05-27 | 2026-05-26 13:52 | 2026-05-27 | 2026-05-26 13:56 | 2026-05-26 | 2026-05-26 13:49 | 2026-05-27 | 2026-05-26 13:49 | 2026-05-26 | 2026-05-26 13:49 | 2026-05-27 | 2026-05-26 13:50 |  |  |  |  | 2026-05-26 | 2026-05-26 13:50 | 2026-05-27 | 2026-05-26 13:53 | 2026-05-27 | 2026-05-26 13:55 |  |  | 2026-06-03 | 2026-06-05 16:19 | 2026-06-05 | 2026-06-05 17:58 | 2026-06-06 | 2026-06-06 11:13 | 2026-06-07 | 2026-06-10 17:37 |  |  |  |  | 2026-06-12 17:28 | 2026-06-21 | 2026-06-20 22:14 | 2026-06-26 | 2026-06-25 16:49 | 2026-06-25 | 2026-06-13 19:56 | 2026-06-25 |  | 2026-07-04 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-06-05 | 2026-06-05 18:20 | 2026-05-27 | 2026-05-26 13:50 | Unknown | 2026-05-22 | 2026-05-26 13:49 | 0 | 0 | 0 | 0 | 574052 | 86257 | 219962 | 33144 | 2026-06-06 11:03:06 +0530 | Mandar Ambre | Some Image was uploaded | 2026-06-05 17:56:33 +0530 | Mandar Ambre | Some Image was uploaded | 2026-06-05 17:25:07 +0530 | Mandar Ambre | Some Image was uploaded | 2026-05-27 | 2026-05-26 13:50 | 2026-05-27 | 2026-05-26 13:52
20133 | Turnkey | May'26 | Siddhant Kandhare | sawant complex | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Preproduction | Site Readiness 1 | 958491 | 194699 | 1297303 | 0 | 0 | 28 | 0 | 0 | 0 | 380396 | 383396.4 |  |  | 2026-05-22 | 2026-05-22 19:35 | 2026-05-22 | 2026-05-26 11:15 | 2026-05-31 | 2026-05-31 19:28 | 2026-06-11 | 2026-06-11 18:07 | 2026-06-17 |  | 2026-09-06 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-05 14:02 | 2026-06-05 | 2026-06-06 19:06 | 2026-06-10 | 2026-06-10 15:53 |  |  |  |  | 2026-06-11 | 2026-06-17 18:44 | 2026-09-01 |  | 2026-09-02 |  |  |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 | [6 empty] | 2026-09-30 |  | 2026-10-09 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-12 |  |  |  | 2026-11-03 |  | 2026-11-05 |  | 2026-11-06 | [5 empty] | 2026-09-10 |  |  |  |  | 2026-05-22 | 2026-05-22 19:16 | 1099409 | 197893 | 0 | 0 | 0 | 0 | 1072465.6938 | 181078 | 2026-07-14 17:55:24 +0530 | Divya Rahangdale |  | 2026-06-27 15:59:56 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: Layout is finalised & material selection is done. Client has made 10% payment so we need to share renders. Site is not ready hence put the project on hold later. | 2026-06-06 19:05:47 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: November Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (7th June ) * DEM 1 will update to the sales team * 10% Payment Stage Tentatively scheduled for (15th June) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - May '26 Campaign PM fee waiver (2.5%) Design fee waiver (5%) Free Shoerack Offer 100% GST Waiver Silver Coin 21g Final Closing Value Discussed: 9,58,491 Checklist terms descoping and agreement terms are cleared | 2026-06-12 | 2026-06-11 18:12 | 2026-06-18 |  | Under Construction | 2026-11-30
20134 | Turnkey | May'26 | Avinash Kumar V | Srinidhi | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 2871467 | 9999 | 0 | 0 | 0 | 36 | 0 | 277148 | 287147 | 1250500 | 1046673.2 |  |  | 2026-05-22 | 2026-05-22 17:51 | 2026-05-23 | 2026-05-23 15:28 | 2026-07-01 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-07-22 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-07-09 |  | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-07-04 |  | Unknown | 2026-05-22 | 2026-05-22 17:49 | 0 | 0 | 0 | 0 | 0 | 0 | 2433447 | 438020 | 2026-06-09 15:07:10 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-23 15:26:44 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-22 17:32:51 +0530 | Unknown | About the Customer **Property and Budget Details** Customer Avinash Kumar is expecting possession of his 3BHK apartment in Bangalore in 3-4 months, with interiors potentially starting in June. He has a tentative budget of around 15 lakhs. **Budget Flexibility** Customer is hesitant about finalizing a budget, stating it's flexible and depends on the final cost. **Market Confusion** Customer expressed confusion about various interior design companies in the market, indicating a need for clear differentiation. **Experience Center Visit Scheduled** Appointment scheduled for customer and family to visit the HRBR Experience Center on Saturday from 4:00 PM to 5:00 PM. | 2026-07-09 |  | 2026-07-16
20135 | Turnkey | May'26 | Yogesh Hemani | orchid | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 4290104 | 9999 | 0 | 0 | 0 | 54 | 0 | 419011 | 429010 | 1867520 | 1564563.2 |  |  | 2026-05-22 | 2026-05-22 20:39 | 2026-05-22 | 2026-05-28 11:15 | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-17 |  | 2026-08-15 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-15 |  | 2026-08-19 |  |  |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-12 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-05-22 | 2026-05-22 20:38 | 0 | 0 | 0 | 0 | 0 | 0 | 3635682 | 654422 | 2026-06-05 13:02:53 +0530 | Rinisha Masurkar | Some Image was uploaded | 2026-05-22 20:52:34 +0530 | Vandana Preet | Some Image was uploaded | 2026-05-22 20:39:30 +0530 | Vandana Preet |  | 2026-06-05 |  | 2026-06-12
20136 | Turnkey | May'26 | Santosh Pawar | Shrishti residency | MUM - GOR | Yes | Rajnish Mishra | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Rashmita Das |  | Hold | Design | 20% Payment | 1277065 | 165460 | 1654603 | 0 | 0 | 3 | 30 | 0 | 89953 | 546748 | 474904.4 |  |  | 2026-05-22 | 2026-05-25 12:06 | 2026-05-28 | 2026-05-28 20:45 | 2026-05-31 | 2026-05-28 20:55 | 2026-06-27 | 2026-06-27 21:10 | 2026-07-16 |  | 2026-07-23 |  | 2026-05-28 | 2026-05-29 11:47 | 2026-05-29 | 2026-05-29 12:34 | 2026-05-29 | 2026-06-02 15:13 | 2026-06-05 | 2026-06-05 16:33 |  |  |  |  | 2026-06-27 |  | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-07-13 | 2026-06-27 20:47 | Site is RTMI | 2026-05-22 | 2026-05-25 12:05 | 1402206 | 252397 | 0 | 0 | 0 | 0 | 1399607.7843 | 229871 | 2026-07-10 13:17:19 +0530 | Vishakha Vaishnav | Others: CX MENTIONED ON WHATSAPP THAT BY NEXT WEEK HE CAN MAKE THE PAYMENT AS THE LOAN PROCESS IS NOT YET DONE | 2026-06-30 12:35:07 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 15:55:05 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-28 | 2026-06-27 21:12 | 2026-07-17 |  | Under Construction | 2026-06-20
20137 | Turnkey | May'26 | Sourav Ghosh | Adarsh Green | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 840279 | 9999 | 0 | 0 | 0 | 54 | 0 | 74029 | 84028 | 336112 | 336111.6 |  |  | 2026-05-22 | 2026-05-22 19:27 | 2026-05-23 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-05-22 | 2026-05-22 19:26 | 0 | 0 | 0 | 0 | 0 | 0 | 712101 | 128178 | 2026-05-27 12:17:48 +0530 | Varun Mandana | Ramesh - Client ia aware that the minimum order value is 7L and he is aligned with the same. Rishi - Conveyed him that minimum order value can come upto 8-10L and client agreed. | 2026-05-26 10:45:15 +0530 | Maspi Das | Configuration - It is not 3Bhk, it is 2Bhk | 2026-05-26 10:29:28 +0530 | Maspi Das | Cx name : Sourav Ghosh Property - Adarsh Greens 3BHK Profession : Software Designer How many people will be staying :Â 4 Kids- --- Theme :Â Â Not decided Entrance -facing : East Budget : 5L CDP date - 28.05.2026 *Only kitchen and Wardrobes* Kitchen- Base units Wall units Lofts Roll up shutter and Pantry unit (need to check and plan) Beside the Fridge Bedroom2- Sliding wardrobeÂ Need to plan dresser unit (Optional) MBR- Sliding wardrobe with an Extra storage for used clothes Need to plan dresser unit (Optional) | 2026-06-05 |  | 2026-06-12
20140 | Turnkey | May'26 | Syed Abid Husain | piramal mahalaxmi | MUM - GOR | Yes | Anjali Jain | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Active | Preproduction | DEM2 | 2401808 | 480362 | 3154964 | 0 | 0 | 32 | 0 | 0 | 0 | 977572 | 943874 |  |  | 2026-05-22 | 2026-05-28 19:32 | 2026-05-24 | 2026-05-31 21:27 | 2026-06-03 | 2026-06-01 11:37 | 2026-06-13 | 2026-06-14 18:23 | 2026-06-20 |  | 2026-06-27 |  | 2026-06-03 | 2026-05-31 21:33 | 2026-06-02 | 2026-06-04 12:36 | 2026-06-04 | 2026-06-06 20:31 | 2026-06-13 | 2026-06-13 19:28 |  |  |  |  | 2026-06-16 | 2026-06-13 18:46 | 2026-06-22 |  | 2026-06-23 |  |  |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 | [6 empty] | 2026-07-21 |  | 2026-07-30 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-02 |  |  |  | 2026-08-24 |  | 2026-08-26 |  | 2026-08-27 | [5 empty] | 2026-07-01 |  | 2026-06-14 | 2026-06-13 20:30 | Site is RTMI | 2026-05-22 | 2026-05-28 19:31 | 2673698 | 481265 | 0 | 0 | 0 | 0 | 2670305.56 | 440875 | 2026-06-13 19:29:39 +0530 | Vishakha Vaishnav | "Welcome call done F2F" Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - done on 13th june DEM 2 - TBD DEM 3 - TBD Possession date : June end Customer will make 10% paid on 13th june Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-06 20:30:58 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: 16th June 2026 Scope of Work: Modular + Painting + Wallpaper + membrane (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 10+31 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM client will let us know in the group (can be done after possession, which is in 10 days) * DEM 1 20th June 2026 * 10% Payment Stage 20th June 2026 (after 1st DEM) *Transaction will be B2C Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 26,70,306 Offers Discussed During the Call: Anniversary '26 Studio Offer: 50,000 PM fee waiver (7.5%) Free Shoerack Offer Design Fee Waiver (2.5%) Laminate Upgrade - May '26 Campaign 100% GST Waiver Final Closing Value Discussed: 24,10,808 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-06 14:19:47 +0530 | Sanjana Swami |  | 2026-06-15 | 2026-06-14 18:47 | 2026-06-21 |  | Under Construction | 2026-06-16
20142 | Turnkey | May'26 | Bindiya Sharma | Devhans Mahesh Krupa | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Aryan Singh |  | Active | Preproduction | Site Readiness 1 | 1598163 | 323329 | 1933302 | 0 | 0 | 20 | 0 | 0 | 0 | 661489 | 613345.2 |  |  | 2026-05-22 | 2026-05-22 22:53 | 2026-05-23 | 2026-05-26 11:06 | 2026-05-29 | 2026-05-29 20:16 | 2026-06-15 | 2026-06-23 18:38 | 2026-06-29 |  | 2026-07-06 |  | 2026-05-29 | 2026-05-30 15:32 | 2026-05-30 | 2026-05-30 16:59 | 2026-05-30 | 2026-06-06 15:24 | 2026-06-10 | 2026-06-10 12:27 |  |  |  |  | 2026-06-23 | 2026-06-25 18:51 | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  |  |  |  | 2026-05-22 | 2026-05-22 22:35 | 1638391 | 294910 | 0 | 0 | 0 | 0 | 1638163 | 287669 | 2026-06-06 15:23:24 +0530 | Athul Ajaykumar |  | 2026-06-06 15:18:21 +0530 | Aryan Singh | Some Image was uploaded | 2026-06-02 17:22:15 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession: June/July Soft Possession: Site is Accessible Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Will update to the sales team * DEM 1 Will update to the sales team * 10% Payment Stage Will update to the sales team Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Bed Offer 100% GST Waiver Final Closing Value Discussed: 15,98,163 Checklist terms descoping, agreement terms are cleared Rejections: The client is unsure whether to proceed with the payment as a personal or business transaction and is not comfortable closing the 10% milestone at this stage. She will discuss both matters with the sales team and confirm. Client VOC: The client mentioned she has civil work planned, specifically breaking a wall, which will be done by the developer. The client mentioned that he will update the Sales team with the confirmed dates for the IMs and DEM1. | 2026-06-24 | 2026-06-23 18:43 | 2026-06-30 |  | Under Construction | 2026-07-15
20143 | Turnkey | May'26 | Gauthami | Rohan Ekanta | BNG - HSR | Yes | Preksha Sajjanshettar | Akshay Ds | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | Site Readiness 1 | 1661503 | 333184 | 2282819 | 0 | 0 | 15 | 0 | 0 | 0 | 704205 | 624114 |  |  | 2026-05-23 | 2026-05-23 12:34 | 2026-05-23 | 2026-05-31 20:03 | 2026-06-03 | 2026-06-02 11:59 | 2026-06-30 | 2026-06-30 19:08 | 2026-07-21 |  | 2026-07-28 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-03 10:31 | 2026-06-03 | 2026-06-06 12:51 | 2026-06-09 | 2026-06-09 19:13 |  |  |  |  | 2026-06-15 | 2026-06-30 18:47 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-07-23 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-06-10 | 2026-06-30 18:55 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 12:15 | 1934593 | 348226 | 0 | 0 | 0 | 0 | 1904504.1115 | 314466 | 2026-06-29 13:15:52 +0530 | Preksha Sajjanshettar | PID - 20143 DEM 1 MOM - 29-06-2026 Next meeting - 30-06-2026 at 5pm (Virtual)Â EntranceÂ Shoe rack - Client scope FoyerÂ As per reference - complete mirror paneling concept LivingÂ TV UnitÂ Wallpaper instead of texture paintÂ Remove the tall unit and add open wall ledges with metal fabrication as per referenceÂ Both the ends of drawer curving need to be doneÂ Sofa back wallÂ According to early design - CNC Tree - add some flowers to the CNC design, rest all pattern remains sameÂ KitchenÂ L corner unit added and open cabinet is removedÂ Island counter - side granite removed and back surface - rafters or fluted laminate can be considered according to material selectionÂ UtilityÂ Modular units are removedÂ only granite need to be consideredÂ Pooja UnitÂ Add pull out trayÂ Add one step inside next to pooja unit chest of drawer need to be added (Client scope) Master bedroomÂ Dresser unitÂ as per reference (fluted panel not needed) open unit facing towards wallÂ both wardrobe width will be reduced by 100mmÂ Wardrobe - bottom drawer-Push to open handle need to be considered Master bedroom ToiletÂ Glass partition - to separate wet and dry area Parents bedroomÂ Mirror removedÂ Study unit removedÂ Kids bedroomÂ Study unit removedÂ L corner ledge removedÂ Mirror removed and wallpaper on mirror back also removedÂ Wardrobe - bottom drawer-Push to open handle need to be considered BalconyÂ Remove bottom drawer unit and retain bottom shutter unit Increase the top unit width and remove the open unit False ceiling details Foyer, Living and dining - Plain false ceilingÂ Master and parents bedroom - Island false ceilingÂ Kids - Cloud design false ceiling (Peripheral false ceiling) | 2026-06-12 17:17:46 +0530 | Preksha Sajjanshettar | PID - 20143 Initial meeting (KT Meeting) Minutes of Meeting (MoM) Date: 20/03 1. Pre-Foyer Â Â -Existing design approved. Â Â -Explore texture/wallpaper options. 2. Foyer Â Â -Designer mirror options as per reference 3. TV Unit Area Â Â -Remove the tall unit. Â Â -Provide an alternative display solution with an open rack/display shelf. 4. Sofa Back Wall Â Â -Explore tree-themed CNC design or other suitable CNC design options. 5. Kitchen Â Â -remove side granite on either side of an island counter. Â Â -Provide louvers on the visible side of Island counter - Living room side. Â Â -Swap the hob and bottle-pull out unit positions. Â Â -Consider an "L"-shaped ledge design. 6. Utility Area Â Â -Design to be finalized based on site conditions. 7. Hand Wash Area Â Â -Design options to be proposed. 8. Parents/Guest bedroom Â Â -with blue color combinations - as per reference Â Â -Mirror design options on bedhead board wall without dresser unit. Â Â -Increase the depth of the study unit to accommodate one desktop. Â Â -Curving need to done at the corner of study unit 9. Kids bedroom Â Â -Share handle design options. Â Â -Mirror to be placed on toilet wall with 'L' shape ledge with wallpaperÂ 10. Master bedroomÂ Â Â -Provide design options for dresser unit Â Â -Share handle design options. 11. Balcony Â Â -Remove the drawer. Â Â -Provide an openable shutterÂ Â Â -Consider a free-standing water fountain feature - Client scopeÂ Client is travelling to aboard from 12-06-2026 to 28-06-2026 DEM-1 meeting is scheduled on 29-06-2026 - 10:30am (Virtually)Â Â | 2026-06-07 09:37:51 +0530 | Ankita Agarwal | CDP: Mr AkashÂ - check the l shape shelf on kitchen corner - give options for the tall unit in the glass cabinetÂ - add fluted panel on the left on gbr wall (no beading fluted ) - use Nikhil mbr santorni reffÂ - suggest the mirror set upÂ - handle to be suggestedÂ - curve tv unit from both end and keep the gap towards the balconyÂ | 2026-07-01 | 2026-06-30 19:13 | 2026-07-22 |  | Under Construction | 2026-08-15
20144 | Turnkey | May'26 | Dilip Gopalakrishna | independent house | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 5158891 | 617433 | 6174326 | 0 | 0 | 5 | 0 | 0 | 414345 | 2141420 | 1985692.8 |  |  | 2026-05-23 | 2026-06-14 11:00 | 2026-05-28 | 2026-06-14 12:43 | 2026-06-17 | 2026-07-07 10:51 | 2026-07-19 |  | 2026-12-06 |  | 2026-12-13 |  | 2026-07-07 | 2026-07-09 11:51 | 2026-07-08 | 2026-07-09 12:39 | 2026-07-09 | 2026-07-10 11:38 | 2026-07-14 | 2026-07-14 13:33 |  |  |  |  | 2026-07-20 |  | 2026-12-08 |  | 2026-12-09 |  |  |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-18 |  | 2026-12-19 | [6 empty] | 2027-01-11 |  | 2027-02-09 |  | 2027-02-08 |  | 2027-02-09 |  | 2027-02-09 |  | 2027-02-13 |  |  |  | 2027-04-04 |  | 2027-04-05 |  | 2027-04-08 | [5 empty] | 2026-12-17 |  | 2026-07-15 |  | Unknown | 2026-05-23 | 2026-05-23 12:27 | 5232479 | 941846 | 0 | 0 | 0 | 0 | 5158890 | 928600 | 2026-07-10 11:37:29 +0530 | Athul Ajaykumar | OB Accepted: Price protection approval has been received. Moving the OB | 2026-07-10 11:26:35 +0530 | Nidhi Shaw | Others: | 2026-07-09 15:28:48 +0530 | Athul Ajaykumar | Possession Status: Under construction handover by the developer: next 5 to 6 months (No proper clarity) Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: The timeline depends on the case-to-case basis scope of work; the project value is more than 40 lakh, which is 51,58,891 Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Site is not accessible * DEM 1 â€“ Tentatively scheduled for (11th July) * 10% Payment Stage â€“ Tentatively scheduled for (18th July) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin Offer May'26 100% GST waiver May'26 laminate Campaign Final Closing Value Discussed: 51,58,891 Checklist terms â€“ descoping, agreement terms are cleared Rejections: The client didn't give clarity regarding possession. Need approval for the extended price protection. | 2026-07-20 |  | 2026-12-07 |  | Under Construction | 2027-03-31 | 2026-07-03 21:58 | 607434 | Nidhi Shaw
20145 | Turnkey | May'26 | Sreedevi | SNN Serenity Garden | BNG - HSR | Yes | Aishwarya C | Akshay Ds | Soumya KP | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 2263606 | 244634 | 2487316 | 0 | 0 | 43 | 0 | 0 | 208087 | 951112 | 859772.4 |  |  | 2026-05-23 | 2026-05-23 13:28 | 2026-05-23 | 2026-05-26 15:17 | 2026-05-29 | 2026-05-28 09:48 | 2026-07-20 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-05-28 | 2026-05-28 11:07 | 2026-05-29 | 2026-05-30 12:32 | 2026-05-30 | 2026-06-02 15:53 | 2026-06-09 | 2026-06-09 12:29 |  |  |  |  | 2026-07-21 |  | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-07-16 |  | Site is RTMI | 2026-05-23 | 2026-05-23 13:26 | 2107895 | 379421 | 0 | 0 | 0 | 0 | 2548254.6522 | 420804 | 2026-06-09 12:21:48 +0530 | Parasa Sri | Welcome call done. The site is not available for the initial measurement; meeting is been planned for 10thJune, client is been informed regarding payment. | 2026-06-04 13:29:26 +0530 | Patil Madhavi | Some Image was uploaded | 2026-06-02 15:42:48 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM will update to the sales team because client wants to take confirmation from the developer * DEM 1 Tentatively scheduled for (8th June ) * 10% Payment Stage Tentatively scheduled for (8th June) after closing the layout Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (40000) Special Offer (35000) Referred Customer Discount Services Windows to Wonderful Home Modular Windows to Wonderful home PM fee waiver (5%) Design fee waiver (5%) Laminate Upgrade - May '26 Campaign Silver Coin 21g Final Closing Value Discussed: 18,00,926 Checklist terms descoping, agreement terms are cleared Client VOC The client stated that he will close the 10% milestone once the layouts are finalized and locked. | 2026-07-21 |  | 2026-08-02 |  | Under Construction | 2026-07-15
20147 | Turnkey | May'26 | Harsha Joshi | Raheja sherwood | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2088267 | 9999 | 0 | 0 | 0 | 32 | 0 | 198828 | 208827 | 872242 | 798371.6 |  |  | 2026-05-23 | 2026-06-13 16:37 | 2026-05-23 | 2026-06-13 18:13 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-05-23 | 2026-06-13 16:37 | 0 | 0 | 0 | 0 | 0 | 0 | 1769718 | 318549 | 2026-06-12 19:17:25 +0530 | Yash Jain | CDP: Client will be coming for re discussion on 13th june afternoon | 2026-06-11 21:34:17 +0530 | Yash Jain | Some Image was uploaded | 2026-06-11 21:34:04 +0530 | Yash Jain | Some Image was uploaded | 2026-06-24 |  | 2026-07-01
20148 | Turnkey | May'26 | Parikshit Karmarkar | Athena | MUM - GOR | Yes | Anjali Jain | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Design | 20% Payment | 1716258 | 234268 | 2413482 | 0 | 0 | 3 | 0 | 0 | 108984 | 694166 | 678840 |  |  | 2026-05-23 | 2026-05-26 13:10 | 2026-05-23 | 2026-05-28 19:51 | 2026-06-02 | 2026-06-02 19:31 | 2026-07-13 | 2026-07-12 19:55 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-02 | 2026-06-10 18:37 | 2026-06-03 | 2026-06-10 18:53 | 2026-06-10 | 2026-06-11 16:28 | 2026-06-16 | 2026-06-16 19:18 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-06-17 | 2026-07-12 19:31 | Site is RTMI | 2026-05-23 | 2026-05-26 13:06 | 2045324 | 368158 | 0 | 0 | 0 | 0 | 1977220.353 | 317476 | 2026-07-12 19:38:27 +0530 | Anjali Jain | Need to descope shoe rack tv unit False ceiling just need to consider in Dining area only Need to add mandir bottom unit need to change the master bedroom wardrobe depth Parents bedroom wardrobe placement need to change storage need to convert in back painted glass in kids bedroom | 2026-06-16 19:17:51 +0530 | Vishakha Vaishnav | "Welcome call done along with the Designer. Initial measurement : Need to align IM DEM Dates -Â DEM 1 - Cx will do DEM 1 after IM only as he is not ready to pay 20% without any work DEM 2 - TBD DEM 3 - TBD Possession date : August Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-11 16:27:39 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: August End Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Will update to the sales team * DEM 1 Will update to the sales team * 10% Payment Stage Tentatively scheduled for (26th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - May '26 Campaign Free Hob & Chimney Offer Anniversary '26 Studio Offer : 50,000 Design fee waiver (5%) Free Shoerack Offer May '26 Net Special Studio Offer 100% GST Waiver PM fee waiver (5%) Final Closing Value Discussed: 17,62,160 Checklist terms descoping and agreement terms are cleared | 2026-07-13 | 2026-07-12 19:57 | 2026-07-19 |  | Under Construction | 2026-08-31
20149 | Turnkey | May'26 | Neeta Nair | Alpine Primo | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 2632929 | 9999 | 2632929 | 0 | 0 | 43 | 0 | 253294 | 263293 | 1113383 | 992960 |  |  | 2026-05-23 | 2026-05-25 12:07 | 2026-05-23 | 2026-05-26 12:55 | 2026-05-31 | 2026-06-02 19:26 | 2026-06-09 |  | 2026-06-16 |  | 2026-06-23 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-06-10 |  | 2026-06-18 |  | 2026-06-19 |  |  |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-29 | [6 empty] | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-06-27 |  | 2026-06-05 |  | Unknown | 2026-05-23 | 2026-05-23 13:44 | 2231296 | 401633 | 0 | 0 | 0 | 0 | 2231296 | 401633 | 2026-06-02 18:33:39 +0530 | Pratima Kajwe | CDP: MOM Project ProfileProject Name/Tower Name/Flat Number Alpine Primo Typology 3BHK Site Access Date 2026-08-31 Possession Date 2026-08-31 Customer ProfileFamily members (no. & age) 6 adults and 1.5 year old baby Profession Finance, mechanical designer, architect, software engineer Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc NA Signed off celebrity theme Japandi Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 2000000 Mention basic vastu principles agreed for integration in design, if any Basic Design VisionEntrance Foyer must-haves Shoe-rack, safety door Upload reference images Living key features and furniture must-haves Sofa, TV unit, Dining table 6 seater folding or fixed to be decided. Upload reference images Dining setup, table size and other furniture must -haves Dining table 6 seater folding or fixed to be decided with bench Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves Walk-in wardrobe, king size bed, chest of drawers, side table, study table with top storage Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves Wardrobe with l-shaped existing wardrobe or normal wardrobe with study table and space for crib with study table Upload reference images Other space/ room (if any) must-haves murphy bed with wardrobes on the sides, study table Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves Fully modular kitchen with combination of laminate and membrane (mint green shade or olive green) color, tamber and appliances unit provision of dishwasher and washing machine along with plumbing location. Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves Outdoor furniture Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves NA Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves Vanity unit and mirror Upload reference images Styling and Dcor must-haves as per actuals Space identified for signature design features and its specifics passage and one wall Specify if design to reflect any personal story, cultural influence or special memory Picture collage MiscellaneousTimeline related commitment made by Bonito to customer, if any: Other commitments made by Bonito to customer, if any: RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? Re-confirm the Move-in Date 2026-12-31 Re-confirm the Possession Date 2026-08-31 Any special occasion mentioned by customer wrt handover date Cx would be clear once they will visit the site as they haven't even received sample flat access as of now. and will close post that. | 2026-06-02 17:59:37 +0530 | Pratima Kajwe | CDP: 20149 - Celebrity Design Presentation (CDP) with the customer-20260531_061506UTC-Meeting Recording.mp4 | 2026-06-02 17:59:02 +0530 | Pratima Kajwe | DCM: 20149 - Design Consultation Meeting (DCM) with the customer-20260523_085328UTC-Meeting Recording.mp4 | 2026-06-10 |  | 2026-06-17
20150 | Turnkey | May'26 | Rajesh Pawar | Vastu | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1059597 | 211919 | 1368585 | 0 | 0 | 3 | 7 | 0 | 0 | 423839 | 423838.8 |  |  | 2026-05-23 | 2026-06-09 12:16 | 2026-06-04 | 2026-06-09 14:06 | 2026-06-12 | 2026-06-09 14:12 | 2026-07-06 | 2026-07-05 23:26 | 2027-01-05 |  | 2027-01-12 |  | 2026-06-09 | 2026-06-09 14:13 | 2026-06-10 | 2026-06-09 19:39 | 2026-06-09 | 2026-06-10 15:34 | 2026-06-12 | 2026-06-12 16:45 |  |  |  |  | 2026-08-06 | 2026-07-04 14:19 | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 | [6 empty] | 2027-02-05 |  | 2027-02-14 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-17 |  |  |  | 2027-03-11 |  | 2027-03-13 |  | 2027-03-14 | [5 empty] | 2027-01-16 |  | 2026-08-01 | 2026-07-05 23:25 | Site is Non-RTMI | 2026-05-23 | 2026-06-09 12:15 | 1159818 | 208767 | 0 | 0 | 0 | 0 | 1159818.2636 | 199277 | 2026-07-08 15:30:06 +0530 | Anil Jagtap | Possession - Dec*26 | 2026-07-07 16:45:36 +0530 | Rachna Abhyankar | DEM1 MOM | 2026-07-07 16:42:34 +0530 | Rachna Abhyankar | Project Needs to put on HOLD - Possession in Dec 2026 | 2026-07-06 | 2026-07-05 23:26 | 2027-01-06 |  | Under Construction | 2026-10-31 | 2026-06-06 | 146999 | Ravi Roy
20151 | Turnkey | May'26 | Adarsh | ARS Zurich Phase 2 | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Ravikiran K |  | Active | Preproduction | DEM2 | 1320321 | 264064 | 1744496 | 0 | 0 | 4 | 0 | 0 | 0 | 528129 | 528128.4 |  |  | 2026-05-23 | 2026-05-23 14:20 | 2026-05-23 | 2026-06-02 09:09 | 2026-06-05 | 2026-06-02 15:05 | 2026-07-12 | 2026-07-11 19:11 | 2026-08-01 |  | 2026-08-08 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-07 19:39 | 2026-06-07 | 2026-06-09 13:54 | 2026-06-10 | 2026-06-10 12:52 |  |  |  |  | 2026-07-15 | 2026-07-07 18:51 | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-07-10 | 2026-07-11 18:13 | Site is RTMI | 2026-05-23 | 2026-05-23 14:16 | 1478386 | 266109 | 0 | 0 | 0 | 0 | 1478385.555 | 244116 | 2026-06-09 13:53:33 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: End of June/July Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (20th or 21st June 2026) * DEM 1 Tentatively scheduled for (27th June 2026) * 10% Payment Stage Tentatively scheduled for (21st June 2026) *B2C Self *Civil work - Yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (40000) Special Offer (20000) PM fee waiver (5%) Design fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Laminate Upgrade - May '26 Campaign Silver Coin 21g Final Closing Value Discussed: 13,20,322 Checklist terms descoping and agreement terms are cleared Client VOC: The client mentioned that the planned civil work includes items under Bonito's scope. However, the kitchen wall tile work falls outside Bonito's scope and will be carried out by another vendor. | 2026-06-09 11:41:15 +0530 | Bency Chacko |  | 2026-06-08 17:17:08 +0530 | Sanjana Swami |  | 2026-07-12 | 2026-07-11 19:17 | 2026-08-02 |  | Under Construction | 2026-07-31
20152 | Turnkey | May'26 | Sagar Kunte | Narayan Nivas | MUM - GOR | Yes | Karan Chavda | Vishakha Vaishnav | Safalta Karkera |  |  | Nilesh Patel | Rizwan Mistry |  | Mrunali Mitkari | Aakash Gaikwad | Active | Design | DEM3 | 1097492 | 219498 | 1339349 | 0 | 0 | 5 | 1 | 0 | 0 | 479682 | 398312 |  |  | 2026-05-23 | 2026-05-26 13:14 | 2026-05-30 | 2026-05-29 13:49 | 2026-05-30 | 2026-05-30 19:57 | 2026-06-17 | 2026-06-13 18:37 | 2026-07-12 |  | 2026-07-19 |  | 2026-05-30 | 2026-05-30 19:59 | 2026-05-31 | 2026-06-02 16:13 | 2026-06-02 | 2026-06-04 13:07 | 2026-06-05 | 2026-06-05 16:10 |  |  |  |  | 2026-06-13 | 2026-06-15 17:07 | 2026-07-10 | 2026-07-10 19:37 | 2026-07-11 | 2026-07-10 19:37 |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-06-06 | 2026-06-13 18:13 | Site is Non-RTMI | 2026-05-23 | 2026-05-26 13:06 | 1135041 | 204307 | 0 | 0 | 0 | 0 | 1135041.4012 | 197548 | 2026-06-13 18:44:16 +0530 | Karan Chavda | Minutes of Meeting held on Date: Title: Project: Client: Attendees: Objective: Discussion Based on meeting, below is a list of all the requirements that were discussed during the meeting: Mr. Sagar kunthe minutes of meeting 13/06/2026 Living room 1. Mirror on north wall 2. Ac pelmet to be added 3. Shoe rack internal change 4. Existing foldable dinign 5. Existing sofa foam and fabric change KitchenÂ 1. Mandir unit should have a step, a tray and a drawer 2. Microwave, airfryer, bread maker, dishwasher, fridgeÂ 3. Add loft above fridge area 4. Tall unit for broom in passage area 5. Deteregent rack Common washroom 1. Change door orientation 2. Cover loft in both washrooms Master bedroom 1. Hanging light above dressingÂ Next meeting 20th june 11am | 2026-06-05 16:09:59 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Aligned for 11th June 11 am DEM Dates -Â DEM 1 - Cx said that he is available for the meeting on 13th June need to confirm with designer DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-04 13:06:34 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM 6th June 2026 (client mentioned that he will be * DEM 1 13th June 2026 * 10% Payment Stage 14th June 2026 (after 1st DEM) *No civil work at site *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11,35,042 Offers Discussed During the Call: Silver Coin 21g Anniversary '26 Studio Offer: 30,000 PM Fee Waiver (4%) 100% GST Waiver Final Closing Value Discussed: 10,97,492 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-14 | 2026-06-13 18:41 | 2026-07-13 |  | RTMI
20153 | Turnkey | May'26 | Manoj lodaya | Anant siddhi | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Active | Preproduction | Site Readiness 1 | 1414968 | 282994 | 1952403 | 0 | 0 | 5 | 3 | 0 | 0 | 625380 | 506594 |  |  | 2026-05-23 | 2026-05-23 17:05 | 2026-05-27 | 2026-05-28 19:03 | 2026-05-31 | 2026-05-30 10:58 | 2026-07-11 | 2026-07-10 16:38 | 2027-01-05 |  | 2027-01-12 |  | 2026-05-30 | 2026-05-30 12:12 | 2026-05-31 | 2026-05-31 22:21 | 2026-05-31 | 2026-06-20 16:20 | 2026-06-23 | 2026-06-23 18:18 |  |  |  |  | 2026-08-05 | 2026-07-07 18:52 | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 | [6 empty] | 2027-02-05 |  | 2027-02-14 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-17 |  |  |  | 2027-03-11 |  | 2027-03-13 |  | 2027-03-14 | [5 empty] | 2027-01-16 |  | 2026-07-31 | 2026-07-10 16:07 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 16:16 | 1654579 | 297824 | 0 | 0 | 0 | 0 | 1633307.1826 | 263244 | 2026-07-14 13:06:49 +0530 | Anamika Dolai | Possession- December'26. | 2026-07-07 13:13:49 +0530 | Anamika Dolai | Posession Delayed till 31st of July | 2026-06-23 18:16:53 +0530 | Anamika Dolai | done, milestones explained. Soft possession - july end can continue with the initial measurement | 2026-07-11 | 2026-07-10 16:42 | 2027-01-06 |  | Under Construction | 2026-07-31
20155 | Turnkey | May'26 | Neha bharuka | bryony , nahar Amrit shakti | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 7374985 | 9999 | 0 | 0 | 0 | 29 | 0 | 727500 | 737499 | 3053226 | 2846761.6 |  |  | 2026-05-23 | 2026-05-23 16:33 | 2026-06-13 | 2026-06-16 11:43 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-05-23 | 2026-05-23 16:33 | 0 | 0 | 0 | 0 | 0 | 0 | 6249987 | 1124997 | 2026-06-13 11:52:04 +0530 | Sakshi Hire | DCM: 1600 carpet 5 family mem it profession Â julyÂ flooring overall 4 wc reno basic vastuÂ living 30-40 shoe pairs safety doorÂ 60" tv unit 6 dining seating with crokery unit sofa seating on right side 3+2 left side dining tableÂ accent tv wall below crokery unit mandir wall mouted pooja unit ontrance right or left kitchen open kitchen put slider dishwasher 2 sinks l shape kitchenÂ below side sinkÂ fridge in the start i-land kithen fro breakfastÂ slider for utility washing machine & dryingÂ drying area servent bed storage & bed storage service slab extention for kbr powder room comm wcÂ kbr bunk bedpulloutÂ above side playing area as per safetyÂ window seating till duct area wardrobe floor ceilingÂ study table piano drawer wihin study table gbr wardrobe loft behind the door workstation placemnt next to wc seating windowÂ queen bed storage service slab needs to divided in 2( we can accomodate washing machine in here also if not in utility) mbr walk in wardrobe in niche king size bed storage murphy bed or pullout bed for both kids wc area for walk in area dresser service slab needs to convert into wc foldable study table services false ceiling in liiving & dining area balony jhula single seatoutÂ planters | [6 empty] | 2026-06-27 |  | 2026-07-04
20156 | Turnkey | May'26 | Kiran Khurana | Arthaya | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | Viraj Chavan | Viraj Chavan | Nilesh Patel | Rizwan Mistry |  | Moni Sahani | Sunil Poojary | Active | Preproduction | 2D | 1018523 | 179383 | 1262861 | 1018523 | 0 | 1 | 0 | 0 | 0 | 458434 | 380706 |  |  | 2026-05-23 | 2026-06-03 13:15 | 2026-05-23 | 2026-06-03 14:44 | 2026-06-06 | 2026-06-03 14:50 | 2026-06-20 | 2026-06-13 20:57 | 2026-06-29 | 2026-06-28 12:11 | 2026-07-08 | 2026-07-08 17:13 | 2026-06-03 | 2026-05-31 | 2026-06-04 | 2026-06-05 13:50 | 2026-06-05 | 2026-06-08 15:41 | 2026-06-10 | 2026-06-10 15:42 |  |  |  |  | 2026-06-16 | 2026-06-13 20:38 | 2026-07-06 | 2026-07-05 17:08 | 2026-07-06 | 2026-07-07 16:04 |  |  | 2026-07-09 | 2026-07-14 20:16 | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-11 | 2026-06-13 20:50 | Site is RTMI | 2026-05-23 | 2026-05-26 13:35 | 1070221 | 192639 | 1162113.634 | 191884 | 0 | 0 | 1162113.634 | 191884 | 2026-06-10 15:41:28 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : As per cx is its done on 10th June need to confirm with designer DEM Dates -Â DEM 1 - Cx is available for the meetings need to confirm with deisgner and also cx want to finalize the designs asap DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-08 15:40:39 +0530 | Athul Ajaykumar |  | 2026-06-08 15:33:25 +0530 | Sahil Sethi | I explained the timelines to the client | 2026-06-14 | 2026-06-13 20:57 | 2026-06-29 | 2026-07-05 14:06 | RTMI
20157 | Turnkey | May'26 | Mr.Vijay Krishna J | Pavani Mariabilia | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik | [5 empty] | Aman Kumar |  | Active | Preproduction | Site Readiness 1 | 1560261 | 312396 | 2024930 | 0 | 0 | 4 | 0 | 0 | 0 | 661667 | 586198 |  |  | 2026-05-23 | 2026-05-23 17:19 | 2026-05-23 | 2026-06-02 07:35 | 2026-06-05 | 2026-06-02 12:42 | 2026-07-05 | 2026-07-05 17:38 | 2026-11-10 |  | 2026-11-17 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-06 15:26 | 2026-06-06 | 2026-06-08 18:49 | 2026-06-09 | 2026-06-09 19:09 |  |  |  |  | 2026-07-05 | 2026-07-11 18:06 | 2026-11-12 |  | 2026-11-13 |  |  |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-22 |  | 2026-11-23 | [6 empty] | 2026-12-11 |  | 2026-12-20 |  | 2026-12-19 |  | 2026-12-20 |  | 2026-12-21 |  | 2026-12-23 |  |  |  | 2027-01-14 |  | 2027-01-16 |  | 2027-01-17 | [5 empty] | 2026-11-21 |  | 2026-07-18 | 2026-07-05 17:26 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 16:52 | 1716043 | 308887 | 0 | 0 | 0 | 0 | 1700116.8874 | 280717 | 2026-07-05 17:43:33 +0530 | Janush Bojamma C T | Vijay Krishna - 5th July 1) Living room- Tv unit need more storage, bottom unit and tall unit increase 2) Crockery unit - wall unit increase glass shutter 3) Kids room - Shelves for the pooja unit for grandparent- Wallpaper - can be adult or neutral one 4) MBR can be kids centric 5) Brother law - room 6) Kids and grand parent 7) parents room 8) MBR - study - closed storage 9) 2 drawers in the bottom for study 10 ) All study unit has to be drawer | 2026-06-08 18:48:25 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: October 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible * DEM 1 20th June 2026 (will be done virtually) * 10% Payment Stage by 20th (after 1st DEM) *No civil work planned in client's scope of work *Transaction will be B2C self funding Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 17,00,117 Offers Discussed During the Call: Special Offer (40000) Special Offer (20000) PM fee waiver (5%) Design fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 15,60,261 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-08 17:10:57 +0530 | Sanjana Swami |  | 2026-07-06 | 2026-07-05 17:41 | 2026-11-11 |  | Under Construction | 2026-10-01
20158 | Turnkey | May'26 | Manas Himanshu Vishwaroop | MICL Aaradhya | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Foram Joshi |  | Active | Preproduction | Site Readiness 1 | 1558572 | 311714 | 1873183 | 0 | 0 | 5 | 0 | 0 | 0 | 672909 | 573949.2 |  |  | 2026-05-23 | 2026-05-23 21:01 | 2026-05-24 | 2026-05-24 21:12 | 2026-05-28 | 2026-05-28 20:44 | 2026-07-08 | 2026-07-08 19:46 | 2026-07-14 |  | 2026-07-21 |  | 2026-05-28 | 2026-05-29 11:21 | 2026-05-29 | 2026-05-29 11:21 | 2026-05-29 | 2026-05-30 12:26 | 2026-06-12 | 2026-06-12 12:31 |  |  |  |  | 2026-07-08 | 2026-07-10 14:30 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-07-25 |  | 2026-07-05 | 2026-07-08 19:43 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 21:00 | 1589731 | 283452 | 0 | 0 | 0 | 0 | 1591476.4155 | 277844 | 2026-06-30 12:10:31 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-12 12:32:08 +0530 | Anil Jagtap | welcome call completed | 2026-06-09 20:41:03 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-07-09 | 2026-07-08 19:51 | 2026-07-15 |  | Under Construction | 2026-06-06
20159 | Turnkey | May'26 | Shiva | Devagiri opal | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [7 empty] | Active | Design | DEM1 | 954669 | 124664 | 1307903 | 0 | 0 | 30 | 0 | 0 | 66270 | 397426 | 366308.8 |  |  | 2026-05-23 | 2026-05-25 12:19 | 2026-05-23 | 2026-05-27 15:41 | 2026-05-30 | 2026-06-04 12:00 | 2026-07-12 |  | 2026-07-19 |  | 2026-08-18 |  | 2026-05-30 | 2026-05-31 | 2026-06-05 | 2026-06-04 12:09 | 2026-06-04 | 2026-06-15 10:54 | 2026-06-17 | 2026-06-17 11:01 |  |  |  |  | 2026-07-13 |  | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-06-18 |  | Unknown | 2026-05-23 | 2026-05-23 17:22 | 1108392 | 199510 | 0 | 0 | 0 | 0 | 1103387.6208 | 182190 | 2026-06-16 11:08:35 +0530 | Kushal S | Some Image was uploaded | 2026-06-15 10:55:12 +0530 | Bency Chacko |  | 2026-06-13 15:32:08 +0530 | Bency Chacko | Some Image was uploaded | 2026-07-13 |  | 2026-07-20 |  | Under Construction | 2026-07-31
20160 | Turnkey | May'26 | Rohit Kumar | 2bhk independent house | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Preproduction | Site Readiness 1 | 1335750 | 267150 | 1761854 | 0 | 0 | 4 | 0 | 0 | 0 | 534300 | 534300 |  |  | 2026-05-23 | 2026-05-23 17:47 | 2026-05-26 | 2026-06-02 10:50 | 2026-06-02 | 2026-06-02 12:46 | 2026-07-12 | 2026-07-11 21:27 | 2026-08-06 |  | 2026-08-13 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-02 13:00 | 2026-06-02 | 2026-06-03 16:31 | 2026-06-09 | 2026-06-09 14:14 |  |  |  |  | 2026-07-15 | 2026-07-11 15:42 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-07-10 | 2026-07-11 20:56 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 17:30 | 1493097 | 268757 | 0 | 0 | 0 | 0 | 1459877.679 | 240435 | 2026-06-03 16:30:50 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: July End Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (13th June 2026 or 14th June 2026) * 10% Payment Stage Tentatively scheduled for (13th June 2026) *B2C Self Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Laminate Upgrade - May '26 Campaign Silver Coin 21g Final Closing Value Discussed: 13,35,751 Checklist terms descoping, agreement terms are cleared | 2026-06-02 13:08:38 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-06-02 10:39:25 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-07-12 | 2026-07-11 21:28 | 2026-08-07 |  | Under Construction | 2026-07-31
20161 | Turnkey | May'26 | Karthikeya | hinduja el jardin | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Preproduction | Site Readiness 1 | 1445747 | 289149 | 1895941 | 0 | 0 | 16 | 0 | 0 | 0 | 629087 | 527510.8 |  |  | 2026-05-23 | 2026-05-23 18:24 | 2026-05-30 | 2026-05-31 12:03 | 2026-05-31 | 2026-05-31 12:18 | 2026-06-27 | 2026-06-27 19:25 | 2026-07-03 |  | 2026-10-05 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-02 16:56 | 2026-06-02 | 2026-06-03 18:44 | 2026-06-06 | 2026-06-06 12:27 |  |  |  |  | 2026-06-27 | 2026-06-29 18:44 | 2026-09-30 |  | 2026-10-01 |  |  |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-11 | [6 empty] | 2026-10-29 |  | 2026-11-07 |  | 2026-11-06 |  | 2026-11-07 |  | 2026-11-08 |  | 2026-11-10 |  |  |  | 2026-12-02 |  | 2026-12-04 |  | 2026-12-05 | [5 empty] | 2026-10-09 |  | 2026-06-23 | 2026-06-27 19:21 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 18:23 | 1606730 | 289211 | 0 | 0 | 0 | 0 | 1562010.096 | 260234 | 2026-06-27 13:39:19 +0530 | Ashiya Sanam | Minutes of Meeting held on Date: Title:DEM-1 Project:20161 Client:Karthikeya Attendees:Ashiya Objective: Discussion:Layout finalisation As discussed during the meeting, please find the finalized requirements below: Living RoomFollow a traditional theme with beige and wooden tones, incorporating minimalist storage.Layout has been finalized, and all requirements have been discussed.The TV unit should include provisions for speakers, with a minimalistic panel design.Partition design options to be shared.Pooja unit is included within the client's scope.Crockery unit to include a tall storage unit. Avoid mirrors; instead, use dado tiles and feature designs on the dining wall.KitchenLayout has been finalized.Kitchen units have been discussed.Verify the chimney pipe location and requirements.Built-in oven details to be finalized after the site visit.Utility area layout has been finalized.Staircase AreaDesign elements should complement the overall traditional theme of the home.Study RoomDesign the space as a combined living and study area.The front wall should serve as the highlight feature.Incorporate an arch design with storage on the left-side wall.Master BedroomInclude a dresser with an integrated storage unit.The design should be aesthetically pleasing while ensuring practical feasibility.A sliding wardrobe is to be incorporated.Kids' BedroomLayout has been finalized.Furniture positions have been finalized.Design options to be shared based on the provided reference, including a bunk bed design.Parents' BedroomLayout has been finalized.Furniture positions have been discussed.Wall design options to be shared.NoteElectrical works and painting are included within Bonito's scope.Any additions or changes to the finalized design may result in revisions to the quoted cost | 2026-06-16 14:21:56 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-09 16:44:05 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-28 | 2026-06-27 19:29 | 2026-07-04 |  | Under Construction | 2026-09-01
20162 | Turnkey | May'26 | Bhooshan chaudhari | L&T Rejuve 360 | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1529359 | 9999 | 0 | 0 | 0 | 53 | 0 | 142937 | 152936 | 690604 | 532883.6 |  |  | 2026-05-23 | 2026-05-23 18:49 | 2026-05-23 | 2026-05-23 19:37 | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-21 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-08-08 |  | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-08-03 |  | Unknown | 2026-05-23 | 2026-05-23 18:46 | 0 | 0 | 0 | 0 | 0 | 0 | 1296067 | 233292 | 2026-05-23 20:07:07 +0530 | Nishtha Valawalkar | 20 lacs budget for interiors. Pre lam | 2026-05-23 20:05:01 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-23 18:29:56 +0530 | Unknown | About the Customer **Appointment Booked for Thane** Appointment booked for Thane experience center for tomorrow at 3 PM. Property is a new 3 BHK in Mulund with possession expected in one month. **Wants Detailed Design Discussion** Customer wants to discuss the design process in detail during the visit. **Appointment Confirmed and Details Shared** Appointment confirmed for tomorrow at 3 PM. Address will be shared via WhatsApp. Three family members will attend. | 2026-08-08 |  | 2026-08-15
20163 | Turnkey | May'26 | varghese jacob j | 2bhk independent house | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Hold | Preproduction | Site Readiness 1 | 1057197 | 211439 | 1433658 | 0 | 0 | 10 | 5 | 0 | 0 | 422879 | 422878.8 |  |  | 2026-05-23 | 2026-05-24 11:27 | 2026-05-25 | 2026-05-28 11:12 | 2026-06-02 | 2026-06-02 16:16 | 2026-06-22 | 2026-06-18 13:00 | 2026-07-22 |  | 2026-07-29 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-02 19:45 | 2026-06-02 | 2026-06-03 17:42 | 2026-06-04 | 2026-06-07 19:10 |  |  |  |  | 2026-06-18 | 2026-06-30 12:40 | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-06-08 | 2026-06-18 12:46 | Site is RTMI | 2026-05-23 | 2026-05-23 18:41 | 1214965 | 218693 | 0 | 0 | 0 | 0 | 1204220.5 | 198845 | 2026-06-03 17:42:04 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Client will get the Handover within 3 months Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business Days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Will update to the sales team * DEM 1 Tentatively scheduled for (6th June 2026) * 10% Payment Stage Tentatively scheduled for (11th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: May '26 Net Special Studio Offer Free Shoerack Offer Laminate Upgrade - May '26 Campaign Design fee waiver (5%) PM fee waiver (5%) 100% GST Waiver Final Closing Value Discussed: 10,57,197 Checklist terms descoping, agreement terms are cleared | 2026-06-02 19:33:52 +0530 | Mohammed Rasick | Some Image was uploaded | 2026-05-29 13:08:05 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-19 | 2026-06-18 13:00 | 2026-07-23 |  | Under Construction | 2026-08-31
20164 | Turnkey | May'26 | Chandramani Baladkar | Lodha amara | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar |  | Viraj Jadhav | Asif Shaikh | Aditya Vikram | Murali S | Aryan Singh | Shailendra Mishra | Active | Preproduction | Procurement | 866486 | 521999 | 1027681 | 0 | 866486 | 12 | 2 | 0 | 0 | 0 | 344487 |  |  | 2026-05-23 | 2026-05-23 20:25 | 2026-05-23 | 2026-05-24 13:40 | 2026-05-24 | 2026-05-24 13:43 |  |  | 2026-06-19 | 2026-06-18 13:19 | 2026-06-21 | 2026-06-21 17:51 | 2026-05-24 | 2026-05-24 13:55 | 2026-05-25 | 2026-05-24 13:56 | 2026-05-24 | 2026-05-25 12:43 | 2026-05-31 | 2026-05-31 17:59 |  |  |  |  | 2026-06-06 | 2026-06-03 18:08 | 2026-06-19 | 2026-06-19 19:53 | 2026-06-20 | 2026-06-19 19:53 |  |  | 2026-06-22 | 2026-06-24 17:14 | 2026-06-24 | 2026-06-24 19:43 | 2026-07-04 | 2026-06-24 20:16 | 2026-06-29 | 2026-07-02 10:56 |  |  |  |  | 2026-07-03 17:35 | 2026-07-08 |  | 2026-07-17 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-20 |  |  |  | 2026-08-11 |  | 2026-08-13 |  | 2026-09-08 | [5 empty] | 2026-06-24 | 2026-06-27 22:04 | 2026-06-01 | 2026-06-04 11:52 | Site is Non-RTMI | 2026-05-23 | 2026-05-23 18:55 | 873161 | 154519 | 0 | 0 | 884784.9334 | 155967 | 884784.9334 | 155967 | 2026-07-12 12:08:47 +0530 | Asif Shaikh | Procurement: Floor Covering work done Planned on 13th July False Ceiling & electrical work shall be commencing from 10thÂ July & will be completed by 20thÂ July (Tentative). First coat painting work shall be commencing from 20thÂ July & will be completed by 27thÂ July (Tentative) SRD - 25th July. Delayed in PI work BOM closed on 3rd july Vendor assigned on 10th July -- 7 days in procurement delayed. | 2026-07-08 20:09:06 +0530 | Asif Shaikh | Procurement: Procurement: Floor Covering work done on 8thÂ July to 10thÂ July (Tentative). False Ceiling & electrical work shall be commencing from 10thÂ July & will be completed by 20thÂ July (Tentative). First coat painting work shall be commencing from 20thÂ July & will be completed by 27thÂ July (Tentative) SRD - 25th July Delayed in PI work Vendor not assign after BOM closure -- 5 days delayed. | 2026-07-06 23:50:08 +0530 | Asif Shaikh | PI vendor Yet to be assigned. Floor Covering work done on 8thÂ July to 10thÂ July (Tentative). False Ceiling & electrical work shall be commencing from 10thÂ July & will be completed by 20thÂ July (Tentative). First coat painting work shall be commencing from 20ththÂ July & will be completed by 27thÂ July (Tentative) Furniture shall be ready for dispatched between 27thÂ July to 30thÂ July (Tentative) | 2026-06-05 | 2026-06-04 13:24 | 2026-06-19 | 2026-06-18 15:18
20165 | Turnkey | May'26 | Rajesh Vinayakrao Bhaldhare | gee cee emrald | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | 10% Payment | 1492946 | 9999 | 0 | 0 | 0 | 46 | 0 | 139296 | 149295 | 652838 | 541518.4 |  |  | 2026-05-23 | 2026-05-24 10:51 | 2026-05-24 | 2026-05-24 12:56 | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-23 | 2026-05-23 19:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1265209 | 227737 | 2026-06-09 12:17:19 +0530 | Ishan Patle | Cx is in US spo he will come in sept mid then CDP he will do the CDP | 2026-05-24 12:53:16 +0530 | Maasoumeh Raza | DCM: Possession : Diwali or December Move in- as soon as possible Budget : 10 to 12L Without appliances [12 max] Member : 4 member [Couple , daughter & son] Living & Dining AreaShoe rack inside Buddha statue required at a focal point; designer to suggest the best location.Buddha statue size considered: 2 ft width.4-seater dining table required.Mirror feature wall required in the living/dining area.Two options to be explored:Full-panel mirror wall.Decorative designer mirror panels/shapes. KitchenParallel kitchen layout.Base unitWall unitAppliances planned:RefrigeratorChimneyMicrowaveMixerFront-load washing machineFamily is non-vegetarian chimney is required.All appliances will be newly purchased. Kitchen StorageStandard storage required:Base unitsWall unitsLoft storageDedicated space for appliances to be planned. Common Bedroom (Kids' Room)Queen-size bed with storage drawers.Wardrobe with loft.Optional study table. Master BedroomQueen-size bed with storage drawers.Wardrobe with loft.Side tables.Dressing unit. Washing MachineFront-load washing machine.Overhead storage can be provided above the unit. Finishes & LightingPreferred colour palette: Neutral shades (Beige tones).Current focus:Space planningStorage planningLighting details (under-cabinet lights, profile lights, glass-unit lighting, etc.) Additional ScopeFalse ceiling.Painting work.Electrical work. |  |  |  | 2026-06-07 |  | 2026-06-14
20166 | Turnkey | May'26 | Satish Mudaliar | DRUSHTI EMERALD | MUM - GOR | No Estimate | [5 empty] | suraj kumar | Aditya Vikram |  | Rashmita Das |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-23 | 2026-05-25 12:08 | 2026-05-24 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-23 | 2026-05-23 19:32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-06-07 |  | 2026-06-14
20168 | Turnkey | May'26 | Rekha kulkarni | Monika gardens | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 1866990 | 9999 | 0 | 0 | 0 | 53 | 0 | 176700 | 186699 | 810896 | 682696 |  |  | 2026-05-23 | 2026-05-23 20:59 | 2026-05-27 | 2026-05-28 11:13 | 2026-05-29 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-05-23 | 2026-05-23 20:57 | 0 | 0 | 0 | 0 | 0 | 0 | 1584440 | 282549 | 2026-06-17 11:09:36 +0530 | Bhawaya Goyal | DCM: Recap: 20168 - Design Consultation Meeting (DCM) with the customer Wednesday, May 27 ¦ Meeting ¦ Microsoft Teams | 2026-06-02 12:30:17 +0530 | Foram Joshi | Some Image was uploaded | 2026-05-28 11:11:47 +0530 | Bhawaya Goyal | DCM: Project DetailsClient Name: RekhaProperty: JVM Monica Garden, MulundNo. of Occupants: 2Possession: ReceivedMove-in Timeline: 3 MonthsCDP Meeting: 31st at 10:30 AMBudget: 1520 LakhsDesign Theme & PreferencesModern minimalist themeFunctional and easy-to-maintain designMaximum storage optimizationWarm and elegant ambienceClean false ceiling with integrated lightingPractical electrical planningAC pelmet provisions throughout Space-wise RequirementsFoyer AreaSafety doorShoe rack with storageMaster BedroomQueen size bedWardrobe with loft storageExisting TV unit to be retainedSide tablesDressing mirrorMaster WashroomVanity unitHalf glass shower partitionKitchenStorage for:MicrowaveChimneyMixer grinder appliancesBase + wall cabinets + loft storageWashing machine placement on left sideMicrowave storage provisionTall unit above counter for mixer grinder and appliance storageUtility AreaDetergent storageConceal plumbing pipes neatlyLiving RoomSeating: 3+2 sofa arrangementTV unitOpen display shelvesMandir unit6-seater dining setupMaster Bedroom / Guest RoomQueen size bedWardrobeSide tableDressing tableFoldable study tableWashroomVanityHalf fixed glass partitionBedroom 1Existing sofa-cum-bed to be retainedWardrobeSide tableAdditional ScopeFalse ceilingElectrical planningPaintingAC pelmet design and provision | 2026-06-08 |  | 2026-06-15
20169 | Turnkey | May'26 | Shreyasi More Redkar | LODHA AMARA | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | DCM Due | 2603069 | 9999 | 0 | 0 | 0 | 49 | 0 | 250308 | 260307 | 1078432 | 1004023.6 |  |  | 2026-05-23 | 2026-05-27 11:49 | 2026-05-23 | 2026-05-29 14:27 | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-05-23 | 2026-05-27 11:49 | 0 | 0 | 0 | 0 | 0 | 0 | 2205991 | 397078 | 2026-05-23 20:04:35 +0530 | Unknown | About the Customer **4 BHK Thane Property Requirements** Customer requires interior design for a 4 BHK property in Thane, Kolshet Road, with possession next Sunday. They plan to convert one bedroom into a wardrobe and design the remaining rooms for a family of four. **Budget Not Qualified** Budget was not qualified, preventing detailed discussion on offers. **Visit to Thane Experience Center Tomorrow** Customer expressed interest in GST waiver offer and plans to visit the Thane experience center tomorrow evening around 5:30 PM. **Appointment Booked for Tomorrow 5:30 PM** Agent to book a slot for the customer at the Thane experience center for tomorrow at 5:30 PM and share details via WhatsApp. | [6 empty] | 2026-06-08 |  | 2026-06-15
20170 | Turnkey | May'26 | Kalpana Dhokale Rath | triveni chs | MUM - GOR | Yes | Sonal Singh | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Active | Design | DEM1 | 1027052 | 153400 | 1444018 | 0 | 0 | 4 | 0 | 0 | 52010 | 474042 | 347600 |  |  | 2026-05-23 | 2026-06-27 10:42 | 2026-05-26 | 2026-06-27 11:41 | 2026-06-30 | 2026-06-30 13:57 | 2026-07-17 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-06-30 | 2026-06-30 15:24 | 2026-07-01 | 2026-07-02 14:08 | 2026-07-02 | 2026-07-11 13:20 | 2026-07-12 | [5 empty] | 2026-07-18 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-07-13 |  | Unknown | 2026-05-23 | 2026-05-26 17:21 | 1226031 | 217986 | 0 | 0 | 0 | 0 | 1226030.659 | 190720 | 2026-07-14 13:02:23 +0530 | Christopher Macwan | Others: Called customer For Welcome call but no answer. | 2026-07-14 12:13:46 +0530 | Athul Ajaykumar |  | 2026-07-14 12:12:41 +0530 | Athul Ajaykumar |  | 2026-07-18 |  | 2026-07-25 |  | RTMI |  | 2026-06-26 | 102705 | Ravi Roy
20172 | Turnkey | May'26 | Nisha Parshuram Mankar | MICL Aaradhya | MUM - GOR | No Estimate | [8 empty] | Ashish Jha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-23 | 2026-05-23 21:37 | 2026-05-24 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-23 | 2026-05-23 21:35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-23 21:40:28 +0530 | Ashish Jha | Some Image was uploaded | [6 empty] | 2026-06-07 |  | 2026-06-14
20173 | Turnkey | May'26 | Mahesh | Mangam elite | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Preproduction | DEM2 | 1007096 | 249264 | 1444399 | 0 | 0 | 38 | 0 | 0 | 0 | 364461 | 393370.8 |  |  | 2026-05-23 | 2026-05-24 20:14 | 2026-05-24 | 2026-05-24 20:37 | 2026-05-24 | 2026-05-24 20:40 | 2026-06-07 | 2026-06-07 11:36 | 2026-07-19 |  | 2026-07-31 |  | 2026-05-24 | 2026-05-25 11:13 | 2026-05-25 | 2026-05-26 13:45 | 2026-05-26 | 2026-05-27 10:43 | 2026-05-31 | 2026-05-31 19:37 |  |  |  |  | 2026-06-07 | 2026-06-07 11:39 | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-04 |  | 2026-06-01 | 2026-06-03 11:22 | Site is RTMI | 2026-05-23 | 2026-05-24 20:09 | 1224067 | 220332 | 0 | 0 | 0 | 0 | 1119645.3787 | 184877 | 2026-06-03 15:34:08 +0530 | Vishal Haridas | Crockery and Washbasin have to be incorporated together. Breakfast table have to be incorporated Dressing unit have to be sleek in master bedroom and a bigger one in bedroom 2 Panelling work above breakfast table Provision for study unit have to be considered near TV unit Sleek Puja unit have to be designed | 2026-05-31 15:48:26 +0530 | Vishal Haridas | CDP: WALL CONCEPTS PRICING IS NOT ADDED BY THE NET DESIGNER | 2026-05-27 10:43:00 +0530 | Athul Ajaykumar |  | 2026-06-08 | 2026-06-07 11:38 | 2026-07-20 |  | RTMI
20174 | Turnkey | May'26 | Shrikant Gaikwad | LODHA AMARA | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Aditya Vikram |  | Vandana Preet | Prasad Bhivaji Hande | Active | Design | DEM3 | 1358516 | 227064 | 1557354 | 0 | 0 | 1 | 0 | 0 | 0 | 684300 | 447152.4 |  |  | 2026-05-23 | 2026-05-24 20:50 | 2026-05-28 | 2026-05-29 11:13 | 2026-05-30 | 2026-05-31 11:21 | 2026-06-24 | 2026-06-23 12:35 | 2026-07-13 | 2026-07-12 12:45 | 2026-07-18 |  | 2026-05-31 | 2026-05-31 11:52 | 2026-06-01 | 2026-06-02 14:24 | 2026-06-02 | 2026-06-09 12:18 | 2026-06-10 | 2026-06-10 13:03 |  |  |  |  | 2026-06-27 | 2026-06-21 13:07 | 2026-07-13 | 2026-07-12 13:08 | 2026-07-13 | 2026-07-14 08:34 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  |  |  |  | 2026-05-23 | 2026-05-24 20:29 | 1319791 | 237562 | 0 | 0 | 0 | 0 | 1532873.7833 | 248899 | 2026-07-08 12:27:48 +0530 | Harshali Bhuyar | shared comparision sheet with the client. | 2026-06-26 14:03:55 +0530 | Harshali Bhuyar | Client is not okay with the cost escalation , wanted to speak to the PH / Sneha for discussing the same. (Metal fabrication was supposed to be included from CDP as he had clearly asked for it to be added , but was not icluded ) | 2026-06-23 13:21:21 +0530 | Harshali Bhuyar | Living room- Glass shutter unit added in crockery unit.Base cabinets increased by 2 shuttersmirror has been added.Metal fabrication cost was not added in the initial quote.3 seater offer sofa has been changed to L shape sofa with storage.Mandir unit has been changed to ready made mandir. Bedroom 1 - Bed direction has been changed.Wardrobe internals have been customized.study table design has been changed.Wall concept has been finalized. Bedroom 2- Bed direction has been changedWardrobe internals have been customized. wardrobe changed from 3 shutter to 4 shutter.Study table design has been changed.Wall concept has been finalized. | 2026-06-24 | 2026-06-23 13:20 | 2026-07-13 | 2026-07-12 13:07 | RTMI
20175 | Turnkey | May'26 | Naresh Bajaj | evana | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 7421590 | 9999 | 0 | 0 | 0 | 29 | 0 | 732160 | 742159 | 3132838 | 2804434 |  |  | 2026-05-23 | 2026-06-16 12:56 | 2026-06-08 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-06-28 |  | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-23 |  | Unknown | 2026-05-23 | 2026-05-26 11:52 | 0 | 0 | 0 | 0 | 0 | 0 | 6289483 | 1132107 | 2026-05-23 23:38:05 +0530 | Unknown | About the Customer **4 BHK Khar West Property Details** Customer requires end-to-end interiors for a 4 BHK apartment (2,200 sq ft) in Khar West, with possession expected in 3-4 months (soft possession in 2-3 months). **Callback Requested Due to Call Quality** Customer requested a callback on a proper line due to poor call quality on the current WhatsApp call. **Agent to Call Back** Agent collected the customer's number to call back on a proper line. | [6 empty] | 2026-06-28 |  | 2026-07-05
20176 | Turnkey | May'26 | Ayushi Tiwari | Sher e punjb | MUM - GOR | Yes | Sonal Singh | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1259465 | 176861 | 1768606 | 0 | 0 | 20 | 0 | 0 | 75032 | 545169 | 462402.8 |  |  | 2026-05-23 | 2026-06-07 13:23 | 2026-06-07 | 2026-06-07 13:25 | 2026-06-20 | 2026-06-24 11:25 | 2026-07-02 |  | 2026-07-09 |  | 2026-07-16 |  | 2026-06-24 | 2026-06-24 18:55 | 2026-06-25 | 2026-06-25 15:36 | 2026-06-25 | 2026-06-25 17:24 | 2026-06-27 | 2026-06-27 13:42 |  |  |  |  | 2026-07-03 |  | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-28 |  | Unknown | 2026-05-23 | 2026-06-07 13:22 | 1498819 | 269787 | 0 | 0 | 0 | 0 | 1479338.8682 | 235253 | 2026-07-14 15:21:33 +0530 | Kashmira Nerurkar |  | 2026-06-27 13:37:43 +0530 | Christopher Macwan | Welcome call done. Initial measurement not done as would receive possession by End of September 2026 DEM Dates -Â DEM 1 - Customer will update on whatsapp group on DEM1 DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of September 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-25 17:23:29 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: September Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM will Update to sales team * DEM 1 will update to sales team * 10% Payment Stage Tentatively scheduled for (4th July 2026) * B2C - Self * Civil work - Yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (2.5%) Laminate Upgrade - May '26 Campaign Free Shoerack Offer Free Hob & Chimney Offer 100% GST Waiver PM fee waiver (7.5%) Final Closing Value Discussed: 12,59,465 Checklist terms descoping, agreement terms are cleared Client VOC: The client mentioned that civil work involving wall demolition and wall construction is required, both of which are under Bonito's scope. | 2026-07-03 |  | 2026-07-10 |  | Under Construction | 2026-09-30 | 2026-06-21 | 176861 | Ravi Roy
20178 | Turnkey | May'26 | Tanvi prabhu | 7 square Avenue | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Aditya Vikram |  | Vandana Preet | Shailendra Mishra | Hold | Preproduction | Site Readiness 1 | 801886 | 163599 | 1286402 | 0 | 0 | 7 | 13 | 0 | 0 | 323253 | 315034.4 |  |  | 2026-05-24 | 2026-05-24 20:19 | 2026-05-24 | 2026-05-29 14:27 | 2026-05-30 | 2026-05-31 21:22 | 2026-06-12 | 2026-06-12 19:30 | 2026-06-25 | 2026-06-24 18:58 | 2027-01-06 |  | 2026-05-31 | 2026-05-31 21:40 | 2026-06-01 | 2026-06-02 14:21 | 2026-06-02 | 2026-06-04 18:10 | 2026-06-11 | 2026-06-11 18:04 |  |  |  |  | 2026-06-12 | 2026-06-22 17:55 | 2027-01-01 |  | 2027-01-02 |  |  |  | 2027-01-09 |  | 2027-01-10 |  | 2027-01-11 |  | 2027-01-12 | [6 empty] | 2027-01-30 |  | 2027-02-08 |  | 2027-02-07 |  | 2027-02-08 |  | 2027-02-09 |  | 2027-02-11 |  |  |  | 2027-03-05 |  | 2027-03-07 |  | 2027-03-08 | [5 empty] | 2027-01-10 |  | 2026-06-12 | 2026-06-12 09:57 | Unknown | 2026-05-24 | 2026-05-24 20:18 | 1092667 | 193734 | 0 | 0 | 0 | 0 | 909581.4575 | 144339 | 2026-07-02 19:00:11 +0530 | Divya Rahangdale | Hold till December 2026 | 2026-06-27 15:58:14 +0530 | Asavari Vare | Some Image was uploaded | 2026-06-04 18:09:40 +0530 | Sanjana Swami |  | 2026-06-13 | 2026-06-12 19:32 | 2026-12-31 |  | Under Construction | 2026-08-01
20180 | Turnkey | May'26 | Shrestha | SBR Earth & Sky | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | [5 empty] | Shashank Singh |  | Active | Design | 20% Payment | 1120125 | 147999 | 1482969 | 0 | 0 | 10 | 0 | 0 | 76026 | 448058 | 448041.6 |  |  | 2026-05-21 | 2026-05-31 12:24 | 2026-05-24 | 2026-05-31 13:17 | 2026-06-03 | 2026-06-03 17:18 | 2026-07-05 | 2026-07-05 11:04 | 2027-02-12 |  | 2027-02-19 |  | 2026-06-03 | 2026-05-31 | 2026-06-04 | 2026-06-08 12:21 | 2026-06-08 | 2026-06-09 12:00 | 2026-06-13 | 2026-06-13 17:30 |  |  |  |  | 2026-07-05 |  | 2027-02-14 |  | 2027-02-15 |  |  |  | 2027-02-22 |  | 2027-02-23 |  | 2027-02-24 |  | 2027-02-25 | [6 empty] | 2027-03-15 |  | 2027-03-24 |  | 2027-03-23 |  | 2027-03-24 |  | 2027-03-25 |  | 2027-03-27 |  |  |  | 2027-04-18 |  | 2027-04-20 |  | 2027-04-21 | [5 empty] | 2027-02-23 |  | 2026-07-14 | 2026-07-04 11:01 | Site is Non-RTMI | 2026-05-21 | 2026-05-24 12:54 | 1256753 | 226215 | 0 | 0 | 0 | 0 | 1221039.622 | 201622 | 2026-06-11 15:30:39 +0530 | Palak Thakur | Some Image was uploaded | 2026-06-11 15:29:05 +0530 | Palak Thakur | Some Image was uploaded | 2026-06-09 12:00:14 +0530 | Palak Thakur | CDP: (17) Calendar ¦ 20180 - Design Consultation Meeting (DCM) with the customer ¦ Microsoft Teams (16) Calendar ¦ 20180 - Celebrity Design Presentation (CDP) with the customer ¦ Microsoft Teams | 2026-07-06 | 2026-07-05 11:10 | 2027-02-13 |  | Under Construction | 2026-08-31
20181 | Turnkey | May'26 | Mohammad Parvez | MICL Aaradhya Parkwood | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Rashmita Das |  | Hold | Design | DEM1 | 1048307 | 145566 | 1455657 | 0 | 0 | 11 | 28 | 0 | 64095 | 448725 | 389920.4 |  |  | 2026-05-24 | 2026-05-25 12:12 | 2026-05-30 | 2026-05-30 19:59 | 2026-06-02 | 2026-05-30 20:31 | 2026-08-05 |  | 2026-08-12 |  | 2026-08-19 |  | 2026-05-30 | 2026-05-30 19:35 | 2026-05-31 | 2026-05-30 21:28 | 2026-05-30 | 2026-06-06 12:18 | 2026-06-12 | 2026-06-12 13:34 |  |  |  |  | 2026-08-06 |  | 2026-08-14 |  | 2026-08-15 |  |  |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-08-23 |  | 2026-08-01 |  | Unknown | 2026-05-24 | 2026-05-24 12:57 | 1233608 | 222049 | 0 | 0 | 0 | 0 | 1233554.4136 | 197245 | 2026-07-03 11:36:21 +0530 | Vishakha Vaishnav | Others: Hold till july end as cx will receive the possession by july end and also there is a payment deviation till july | 2026-06-16 13:47:29 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-10 15:59:47 +0530 | Vishakha Vaishnav | "Welcome call attempted" Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - Cx said that he will do either June end or after possession DEM 2 - TBD DEM 3 - TBD Possession date : July End Customer will make 10% : need to explain this to cx Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-08-06 |  | 2026-08-13 |  | Under Construction | 2026-07-31
20182 | Turnkey | May'26 | Aman Jaiswal | Platinum | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Design | DEM1 | 1381860 | 170165 | 1711647 | 0 | 0 | 33 | 0 | 0 | 106207 | 584256 | 521232 |  |  | 2026-05-24 | 2026-05-27 13:37 | 2026-05-24 | 2026-06-03 14:17 | 2026-06-07 | 2026-06-10 12:07 | 2026-07-13 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-10 | 2026-06-12 10:56 | 2026-06-11 | 2026-06-12 14:52 | 2026-06-12 | 2026-06-12 17:38 | 2026-06-17 | 2026-06-17 11:28 |  |  |  |  | 2026-07-14 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 | 2026-07-09 18:43 | Site is RTMI | 2026-05-24 | 2026-05-24 13:01 | 1450548 | 261098 | 0 | 0 | 0 | 0 | 1597652.2752 | 263800 | 2026-07-09 17:46:46 +0530 | Sayed Byahatti | DDM1:20182 - Aman Jaiswal - ( 07/07/2026) TV UNIT - Add storage Drawers as shared reference. Electrical work is in Bonitos scope. POOJA UNIT - Increase the width & add shlefs for pooja unit. KITCHEN - Plan for Double storage sink unit and remove washing machine. MASTER BEDROOM - Below wardrobe shoes storage to be add. BALCONY AREA - Near master bedroom side balcony plan washing machine and add shelfs for storage. Plan seating area also. AUGEST FIRST WEEK FOR MATERIAL SELECTION & CROSS MEASUREMENT PLANING. | 2026-06-29 12:13:34 +0530 | Sayed Byahatti | Minutes of Meeting held on Date: KT Â (25/06/2026) Aman Jaiswal Balcont - Fluted ceiling design are in bonito scope.full balcony need to be plan and plantation to be add. Kitchen - Need to be plan as per the initail measurement and plan for washing machine area in kitchen area along with dishwasher. TV unit - To be plan if any changes is required. Pooja unit - Need to plan as per shared reference for pooja unit. Crockery unitÂ (Dining area ) - Plan as per convenient space. Â | 2026-06-12 18:43:56 +0530 | Ankita Agarwal | CDP: No changes as of now client will discuss changes during the meeting | 2026-07-14 |  | 2026-07-15 |  | Under Construction | 2026-07-31 | 2026-06-07 | 170165 | Ravi Roy
20183 | Turnkey | May'26 | Manikanta | Saranya Swarovski | BNG - HRBR | Yes | Sreelakshmi M | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 1437891 | 9999 | 1437891 | 0 | 0 | 36 | 0 | 133790 | 143789 | 590682 | 559630.8 |  |  | 2026-05-24 | 2026-05-24 13:13 | 2026-05-24 | 2026-05-31 10:09 | 2026-06-09 | 2026-06-09 11:44 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-12 |  | Unknown | 2026-05-24 | 2026-05-24 13:12 | 1218552 | 219339 | 0 | 0 | 0 | 0 | 1218552 | 219339 | 2026-06-16 14:19:29 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-09 11:43:10 +0530 | Priyanka Gs | Some Image was uploaded | 2026-05-31 10:08:22 +0530 | Priyanka Gs | Family of 2Â Posession - DecemberÂ East FacingÂ Shoe rack - to be planned in the CorridorÂ Living RoomÂ TV unit - Minimal Partition next to the TV unit is preferre Place a swing in between Living & Dining DiningÂ Crockery UnitÂ WorkstationÂ with ledges on either side False Ceiling for Living & Dining Â KitchenÂ 2' FridgeÂ Pooja UnitÂ to be accommodated in the kitchen itself Bottom, Top & LoftÂ is required top mount Ro unitÂ to be planned Master BedroomÂ Wardrobe + Loft DresserÂ Door is moved 1ft away from the existing wall cabinetsÂ Bedroom 2Â Wardrobe +loftÂ StudyÂ mirrorÂ Vanity unit between Bedroom 1 & 2Â Guest BedroomÂ Wardrobe + Loft Budget Conveyed - 13L | 2026-06-17 |  | 2026-06-24
20184 | Turnkey | May'26 | Lohitaksh Pattar | Esteem South Park | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1679171 | 9999 | 0 | 0 | 0 | 48 | 0 | 157918 | 167917 | 708568 | 634768.8 |  |  | 2026-05-24 | 2026-05-24 13:22 | 2026-05-24 | 2026-05-26 12:45 | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-05-24 | 2026-05-24 13:17 | 0 | 0 | 0 | 0 | 0 | 0 | 1423026 | 256144 | 2026-05-24 16:13:42 +0530 | Swati Rathod | RGM Date : 24-05-2026 PID: 20184 Name : Lohitaksh Pattar Profession: Engineers Property - 2.5 BHK Budget - 12L-15L possession - 01-07-2026 Site Access Date: 01-07-2026 Total Members -Â 03Â , Kids - 01(Name :Aaryan ) Orientation : EastÂ Floor : 10th - Bedroom 02 is going to extendÂ - bedroom 01 no sliding door(going to shift on balcony wall) - need to create wallÂ - pooja unit space to be look after - more storage in wardrobe DINNING: - L bottom unitsÂ - square table with 2 seating - reff has been shared LIVING: - TV unitÂ - 3 sofa KITCHEN: - 2door fridge (top&bott), tall unit(lil more width), OTG unit(bottom storage with ventilation on shutter), D.W, single bowl sink - bottom unit - top unit (on East wall more ht to be considred then full cover @ top) - Loft full on west wall - Granite Bd scope - top unit above W.M - gas bottom unit BEDROOM-1:(kid/guest) - Queen size bed (Invisible bed (with tall unitÂ on both side and lofts) - wardrobe and study @ balcony - toilet door to design in invisible door with wall concept - vanity in bathroom - full length mirror - ledge with metal fab @ SE corner BEDROOM-2: (M. bedroom) - King size bed (BD scope) - L shaped wardrobe - DresserÂ TOILET: - vanity - glass partition Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. Meeting Date: 28-05-2026 | 2026-05-24 13:21:58 +0530 | Ramesh Nayak | Some Image was uploaded |  |  |  | 2026-06-05 |  | 2026-06-12
20185 | Turnkey | May'26 | Senthil Pazhmalai | Sheth Avante | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | suraj kumar | Akshat Shrivastava |  | Prashant Panigrahi | Prasad Bhivaji Hande | Active | Design | DEM3 | 1382788 | 210999 | 1209140 | 0 | 0 | 1 | 32 | 0 | 0 | 629115 | 542674 |  |  | 2026-05-24 | 2026-05-27 11:47 | 2026-05-24 | 2026-05-28 20:44 | 2026-05-31 | 2026-05-29 11:13 | 2026-07-13 | 2026-07-13 13:38 | 2026-07-14 | 2026-07-13 14:22 | 2026-07-18 |  | 2026-05-29 | 2026-05-29 11:14 | 2026-05-30 | 2026-05-29 12:40 | 2026-05-29 | 2026-05-30 12:50 | 2026-07-30 | 2026-07-09 13:00 |  |  |  |  | 2026-07-15 | 2026-07-12 17:06 | 2026-07-14 | 2026-07-14 15:30 | 2026-07-15 | 2026-07-14 22:42 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-07-10 | 2026-07-13 13:24 | Site is RTMI | 2026-05-24 | 2026-05-27 11:46 | 1024695 | 184445 | 0 | 0 | 0 | 0 | 1362901.726 | 240252 | 2026-07-09 12:59:11 +0530 | Divya Rahangdale | Welcome call done : Meeting Dates - 12th July DEM 1 : 12th July Possession date : RTMI 10% payment aligned : Yes Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-07-07 15:22:14 +0530 | Asavari Vare | Minutes of Meeting held on Date: 05-07-26 Attendees: Client & Designer Discussion: Layout ï»¿ Based on meeting, below is a list of all the requirements that were discussed during the meeting: MOM- 05-07-26 - PID 20185Â Extra sockets to be provided in glass drawer units. Â 2 tall units required one will be solid & the other will be clear glass.Â 4 sockets required for TV unit area below inside drawer unit. Â TV wall floral patterns on both sides. - Pattern design in client's scope.Â Mandir unit single door with cnc cut floral circular pattern. Â Crockery unit top will be granite & Tiling installation required in dado area. Â Hanging bell provision to be made inside mandir unit.Â PVC paneling for Outside waste pipe. To be checked during cross measurementsÂ One electric point is required for balcony & Provision for swing check feasibility on site. Â Provision of space for placement of steel baskets with wheels Â Need a cutout in microwave unit for Wirring towards the bottom socket.Â The storage above microwave unit to be kept covered. Â Need provision for Chimney point by shifting existing.Â Master bedroom bottom vanity unit replaced with top unit. The top unit will have glass shelves.Â Master bedroom will have shower partition. Â Master Bedroom wardrobe dimensions altered. Depth of wardrobe in bed front is reduced since there was not sufficient space for door opening. Â Additional Tall wardrobe cabinets given in master bedroom. Â Pelmets required in master & Living room both.Â | 2026-06-29 14:02:04 +0530 | Asavari Vare | Minutes of Meeting held on Date: Based on meeting, below is a list of all the requirements that were discussed during the meeting: IM is done project will be active from july 5th | 2026-07-14 | 2026-07-13 13:42 | 2026-07-14 | 2026-07-13 14:25 | Under Construction | 2026-06-13
20187 | Turnkey | May'26 | Ramesh Joshi | Bhushan Heritage | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | DCM Due | 1167792 | 9999 | 0 | 0 | 0 | 51 | 0 | 106780 | 116779 | 509652 | 424582 |  |  | 2026-05-24 | 2026-05-25 12:10 | 2026-06-05 | 2026-06-05 16:29 | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-06-21 |  | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-06-16 |  | Unknown | 2026-05-24 | 2026-05-24 13:55 | 0 | 0 | 0 | 0 | 0 | 0 | 989654 | 178137 | 2026-05-24 13:55:19 +0530 | Unknown | About the Customer **Callback Requested** Customer Ramesh Joshi requested a callback in 10 minutes as he was outside. **Callback Agreed** Agent Vinay agreed to call Ramesh Joshi back in 10 minutes. **Renovation Needs and Budget Defined** Customer is looking for a full home renovation for their 2BHK property in Borivali, Mumbai, with a budget of 10-20 lakhs. They are currently living in the property and will vacate it for renovation. **Hesitation on Visit Process Resolved** Customer initially hesitated about visiting the experience center first, preferring an on-site visit for quoting. Agent explained the process requires an initial visit to the experience center for design ideas and a tentative quote before an on-site measurement. **Experience Center Visit Scheduled** An appointment is scheduled for the customer to visit the Andheri East experience center on Sunday after 12:00 PM. Two family members will attend. Details will be sent via WhatsApp. | [6 empty] | 2026-06-21 |  | 2026-06-28
20188 | Turnkey | May'26 | Suguna Ashok | Independent House | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 2563482 | 9999 | 0 | 0 | 0 | 51 | 0 | 246349 | 256348 | 1057902 | 992883.2 |  |  | 2026-05-24 | 2026-05-25 12:17 | 2026-05-24 |  | 2026-05-30 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-05-30 |  | 2026-05-31 |  | 2026-05-31 |  | 2026-06-01 | [5 empty] | 2026-06-07 |  | 2026-06-15 |  | 2026-06-16 |  |  |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 | [6 empty] | 2026-07-14 |  | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-26 |  |  |  | 2026-08-17 |  | 2026-08-19 |  | 2026-08-20 | [5 empty] | 2026-06-24 |  | 2026-06-02 |  | Unknown | 2026-05-24 | 2026-05-25 11:23 | 0 | 0 | 0 | 0 | 0 | 0 | 2172443 | 391039 | 2026-05-29 13:23:27 +0530 | Losii Athisa | Some Image was uploaded | 2026-05-24 16:14:03 +0530 | Keerthan M | DCM: Independent houseÂ 3BHK 3PPL Foyer - Storage with seating on left wall - partition with mirror and display unit - mural art on north wall Living - Floating unit with display unit - combination of ledge and glass shutter storage - L shape + Jula opt need to be given - wall detailing behind tv unit - Suggest false ceiling designs Pooja unit - wood carving door with glass - Stand and pray (mid height) - Chakra CNC Design on ceiling - Storage behind door Dining - Circular dining table 4/6 seater - Crockery unit, ledges Kitchen - double door fridge on entrance wall - dishwasher provision - tall unit on south wall - bottom top and loft Utility - Washing machine -Â single bowl sink - top storage on north wall Lobby - Try to hide washroom view from pooja unit Bedroom 1Â - Wardrobe on washroom wall - Dresser give option 1. near wardrobe 2. inside toilet opp to door - Queen bed Bedroom 2 (Parents room) - Wardrobe - dresser on bed wall - Queen bed Bedroom 3 - near living - queen bedÂ - wardrobe on wash room wall | 2026-05-24 14:30:25 +0530 | Unknown | About the Customer **Property Under Construction** Customer is building a G+1 property in Chikkabanavara, Bangalore. Ground floor is 2BHK for rent, first floor is 3BHK for personal use. Construction is ongoing with plastering complete and flooring pending. **Interior Budget Set** Customer has a budget of 10 to 15 lakhs for the 3BHK interiors. **Visit Scheduled for Tomorrow** Customer tentatively agreed to visit the experience center tomorrow (Saturday) around 5-6 PM, with a cab arranged for pickup and drop. Customer will send the floor plan by evening. **Hesitation on Visit Timing** Customer is hesitant about visit timing due to son's schedule. **GST Waiver Offer Mentioned** Agent highlighted a 100% GST waiver offer for May. | 2026-06-07 |  | 2026-06-14
20189 | Turnkey | May'26 | Rajendra Kumar b | ashtapal | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 2039758 | 9999 | 2039758 | 0 | 0 | 34 | 0 | 193977 | 203976 | 815903 | 815903.2 |  |  | 2026-05-24 | 2026-05-24 14:59 | 2026-05-24 | 2026-06-04 12:35 | 2026-06-07 | 2026-06-11 12:32 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-24 | 2026-05-24 14:58 | 1728608 | 311149 | 0 | 0 | 0 | 0 | 1728608 | 311149 | 2026-05-28 18:13:50 +0530 | Ramesh Nayak | Client Name - Rajendra Family Size - 7(Hus, Wife, 2 Girl, 1 Boy, Mother Father) Profession - Business Budget - 10-12L Max Apartment - 3 BHK Property - Ashtapad Sankalp Possession - Sept 2026 Looking for Quality Material and Quality Work. Brand Centric | 2026-05-24 18:41:11 +0530 | Maspi Das | Cx name : Rajendra Kumar Property - Ashtapad Sankalph 3BHK Profession : Whole saler Possession : September How many people will be staying : 7 Kids- 3 2 girls 1 boy 15 & 17, boy - 20 Theme :Â Neutral (for now) (minimal luxury with a little bit of Rajasthani touch Entrance -facing : East Budget : 10LÂ CDP date - 07.06.2026 **FALSE CEILING FOR THE WHOLE HOUSE** *BALCONY DESIGN WITH GLASS RAILING- There is a partition in between the BR and Living area* *DOOR DESIGN SUGGESTIONS* Shoe rack with seating Foyer wall Design (Slick drawer with Wall design) Dining- 1 fan 6 Seater dining table (Hanging lights) Living area- 1 Fan Pooja unit (Room alike so that can go inside and do pooja) Concept - Base unit with Tall unit Sofa wall based on the TV unit designÂ L-shaped sofa with Two accent chairs and 1-2 ottomans (for design) *PARTITION IN BETWEEN DINIG AND LIVING* (Design and show) Common washroom - Vanity unit with storage/decor and mirrorÂ Kitchen- BaseÂ Wall Lofts Plan and design the kitchen based on the plan Storage & Utility- Sink 3' with base and wall storage Storage plan in a way that everything gets fit (essentials, kitchen props) MBR- Two wardrobes (Sliding wardrobe) King size bedÂ Bedside tables Accent wall Son's BR- light colors (premium royal look) Design accordingly 9' sliding Wardrobe with 3' Study table with Storage on top Accent wall King size/Queen size bed GBR- Sliding Wardrobe TV Ledge Accent wall |  |  |  | 2026-06-19 |  | 2026-06-26
20190 | Turnkey | May'26 | Abhijeet Satish Ramchandra Gharat | GeeCee Emerald | MUM - Thane | No Estimate | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-24 | 2026-05-24 20:56 | 2026-05-25 |  | 2026-05-28 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-05-28 |  | 2026-05-29 |  | 2026-05-29 |  | 2026-05-30 | [5 empty] | 2026-06-05 |  | 2026-06-13 |  | 2026-06-14 |  |  |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 | [6 empty] | 2026-07-12 |  | 2026-07-21 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-24 |  |  |  | 2026-08-15 |  | 2026-08-17 |  | 2026-08-18 | [5 empty] | 2026-06-22 |  | 2026-05-31 |  | Unknown | 2026-05-24 | 2026-05-24 20:51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-02 13:47:58 +0530 | Foram Joshi | Some Image was uploaded | 2026-06-02 13:46:47 +0530 | Foram Joshi | Gross Note Mem - 6 budget - 25-30lacÂ 2+2 BhkÂ poss - August Minimal themeÂ LIving RoomÂ Safety door + pannelling Tv UnitÂ Pooja ( need seperate space ) Crockery unit bedroom 1 bedÂ wardrobe + loftÂ dresserÂ study unitÂ bedroom 2Â bedÂ wardrobe + loftÂ dresserÂ study unitÂ bedroom 3Â bedÂ wardrobe + loftÂ Walkin typeÂ dresserÂ study unitÂ ServicesÂ PaintingÂ false cellingÂ eletrification wall concpetÂ Excluded - Curtains , lights whitegoods,Â Loose furniture suggested from outside | 2026-06-02 12:28:57 +0530 | Foram Joshi | Some Image was uploaded | 2026-06-05 |  | 2026-06-12
20191 | Turnkey | May'26 | Ian Daniel Dsouza | MICL Aaradhya | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 1005477 | 201095 | 1130155 | 0 | 0 | 0 | 34 | 0 | 0 | 460052 | 344330.4 |  |  | 2026-05-24 | 2026-05-30 11:57 | 2026-05-24 | 2026-05-31 21:07 | 2026-06-03 | 2026-05-31 22:52 | 2026-06-12 | 2026-06-11 14:45 | 2026-08-08 |  | 2026-08-15 |  | 2026-05-29 | 2026-05-30 15:17 | 2026-05-30 | 2026-05-30 23:58 | 2026-06-01 | 2026-06-02 18:42 | 2026-06-05 | 2026-06-05 14:00 |  |  |  |  | 2026-06-11 | 2026-06-11 16:29 | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-06-06 | 2026-06-11 14:38 | Site is RTMI | 2026-05-24 | 2026-05-24 22:19 | 957759 | 172396 | 0 | 0 | 0 | 0 | 957758.8139 | 168830 | 2026-06-11 18:22:10 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-10 16:53:15 +0530 | Zoya Bhatkar | Minutes of Meeting held on Date: 10th June 2026 Attendees: Discussion: DEM 1 Based on 10th June 2026 meeting, below is a list of all the requirements that were discussed during the meeting: Living Room Sofa Wall Design as per reference shared in Group TV Unit Design as per reference shared in Group Dinning Wall Design as per reference shared in Group False Ceiling Design as per reference shared in Group Kitchen Extra Base Storage on Service SideÂ Glass Shutter on Service Side Roller Shutter 450mm Master Bedroom Wardrobe Internals as discussed shared in WhatsApp Group Foldable Study Side Table 2 Drawer NO Flase Ceiling Fire Pipe Box Packing | 2026-06-05 13:59:34 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Site is not accessible cx will update us on same DEM Dates -Â DEM 1 - Can be done on weekends , tuesday,wednesday,friday need to check with designer DEM 2 - TBD DEM 3 - TBD Possession date : June end Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-12 | 2026-06-11 15:45 | 2026-08-09 |  | Under Construction | 2026-06-30
20192 | Turnkey | May'26 | Prakram singh | La familia rustomjee | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1593646 | 405999 | 2034549 | 0 | 0 | 2 | 32 | 0 | 0 | 608728 | 578918.8 |  |  | 2026-05-24 | 2026-05-27 12:00 | 2026-05-24 | 2026-05-30 12:18 | 2026-06-02 | 2026-05-31 21:29 | 2026-06-14 | 2026-06-09 19:36 | 2026-06-21 |  | 2026-07-20 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-03 14:38 | 2026-06-03 | 2026-06-04 15:00 | 2026-06-09 | 2026-06-09 19:12 |  |  |  |  | 2026-06-12 | 2026-06-11 16:58 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-06-10 | 2026-06-09 19:15 | Site is Non-RTMI | 2026-05-24 | 2026-05-27 11:57 | 1726481 | 308067 | 0 | 0 | 0 | 0 | 1726481.6186 | 284157 | 2026-07-10 19:57:43 +0530 | Divya Rahangdale | CX will receive the possession by End of July. | 2026-06-26 12:04:43 +0530 | Naved Malik | Client is yet to receive possession in another 10-15 days | 2026-06-13 19:26:35 +0530 | Naved Malik | Some Image was uploaded | 2026-06-10 | 2026-06-09 19:40 | 2026-06-22 |  | Under Construction | 2026-07-31
20193 | Turnkey | May'26 | Avishkar Pathak | Aurum Ventures | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1113673 | 9999 | 0 | 0 | 0 | 52 | 0 | 101368 | 111367 | 521483 | 369455.2 |  |  | 2026-05-24 | 2026-05-24 16:03 | 2026-05-24 | 2026-05-26 14:01 | 2026-05-30 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-30 |  | 2026-05-31 | [5 empty] | 2026-06-06 |  | 2026-06-14 |  | 2026-06-15 |  |  |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-23 |  | 2026-06-01 |  | Unknown | 2026-05-24 | 2026-05-24 16:02 | 0 | 0 | 0 | 0 | 0 | 0 | 946078 | 167595 | 2026-05-26 12:00:07 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-05-26 11:06:16 +0530 | Karuna Shinde | Some Image was uploaded | 2026-05-24 16:06:04 +0530 | Nishtha Valawalkar | 3 people are living 1 son (Transpotation Business) 1 Mother -Working in Municipal Corporation 1 small kid Husband has been passed away. | 2026-06-06 |  | 2026-06-13
20194 | Turnkey | May'26 | Amish Thakkar | Raymond 10X Habitat | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Subhan Khan |  | Active | Preproduction | DEM2 | 1300432 | 260086 | 1626571 | 0 | 0 | 27 | 3 | 0 | 0 | 562172 | 478174 |  |  | 2026-05-24 | 2026-05-24 15:33 | 2026-05-30 | 2026-05-31 14:06 | 2026-05-31 | 2026-05-31 22:42 | 2026-06-09 | 2026-06-09 18:36 | 2026-06-22 |  | 2026-06-29 |  | 2026-05-31 | 2026-05-31 22:44 | 2026-06-01 | 2026-05-31 22:45 | 2026-05-31 | 2026-06-05 12:48 | 2026-06-06 | 2026-06-06 12:04 |  |  |  |  | 2026-06-20 | 2026-06-09 17:08 | 2026-06-24 |  | 2026-06-25 |  |  |  | 2026-07-02 |  | 2026-07-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-07-23 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-07-03 |  | 2026-06-15 | 2026-06-09 17:45 | Site is Non-RTMI | 2026-05-24 | 2026-05-24 15:27 | 1378450 | 248121 | 0 | 0 | 0 | 0 | 1370154.2656 | 234077 | 2026-06-30 12:08:46 +0530 | Preet Karania | Some Image was uploaded | 2026-06-09 18:34:37 +0530 | Preet Karania |  | 2026-06-09 18:33:18 +0530 | Preet Karania | Cx Name - Amish Thakkar PD 20194 Project Stage- DEM 1 Date & Time- 7th June, 5:00pm Living Room Provide a sofa-cum-bed in the living room.(cx scope) Install a swing near the window with a swing stopper.(cx scope) Add arch moulding on the left side of the entrance along with wallpaper or textured paint. Install a large mirror on the dining wall (maximize mirror area and minimize visible wall surface). Complete curtain rod fittings. Kitchen Redirect the gas pipe to the opposite platform.(cx scope) Avoid any open cabinets in the kitchen design. Provide a loft above the refrigerator. Add a 3-drawer unit below/alongside the sink platform. Daughters Bedroom Provide a foldable study table. Add additional open shelves above the mandir area. Revise wardrobe internals as discussed. Install a world map wallpaper on the bed-back wall. Master Bedroom Option 1 Integrate a study table within the wardrobe design. Install a TV adjacent to the study table. Option 2 Provide a foldable study table. Install a TV adjacent to the foldable study table. Modify wardrobe internals as discussed. Add rafters and wallpaper on the bed-back wall. Please Note :- The quotation will vary as per the addition of the components and the materials selection Thanks & regards, Preet KaraniaÂ Interior Designer | 2026-06-10 | 2026-06-09 18:37 | 2026-06-23 |  | RTMI
20195 | Turnkey | May'26 | Anand Mungre | shivom | MUM - GOR | Yes | Anjali Jain | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Hold | Design | 20% Payment | 808781 | 154532 | 1045315 | 0 | 0 | 18 | 29 | 0 | 7224 | 327760 | 319265.2 |  |  | 2026-05-24 | 2026-05-24 15:39 | 2026-05-27 | 2026-05-27 21:49 | 2026-05-28 | 2026-05-28 16:00 | 2026-05-29 | 2026-05-29 20:17 | 2026-08-11 |  | 2026-08-18 |  | 2026-05-30 | 2026-05-27 22:17 | 2026-05-31 | 2026-05-28 14:03 | 2026-05-29 | 2026-05-28 19:14 | 2026-05-29 | 2026-05-29 12:58 |  |  |  |  | 2026-05-29 |  | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-05-30 | 2026-05-29 20:10 | Site is RTMI | 2026-05-24 | 2026-05-24 15:38 | 885860 | 159454 | 0 | 0 | 0 | 0 | 881126.195 | 145580 | 2026-07-03 13:13:04 +0530 | Vishakha Vaishnav | Others: | 2026-06-14 11:50:07 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-09 18:02:16 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-05-30 | 2026-05-29 20:20 | 2026-08-12 |  | RTMI
20196 | Turnkey | May'26 | Abhay Prakash Naik | UNIQUE VISTAS | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anant Giri |  | Active | Design | DEM1 | 800062 | 80007 | 994045 | 0 | 0 | 34 | 0 | 0 | 80005 | 372285 | 267764.4 |  |  | 2026-05-24 | 2026-05-24 22:05 | 2026-05-27 | 2026-05-28 12:12 | 2026-06-05 | 2026-06-09 19:18 | 2026-07-26 |  | 2026-08-02 |  | 2026-08-09 |  | 2026-06-09 | 2026-06-11 17:15 | 2026-06-10 | 2026-06-11 17:16 | 2026-06-11 | 2026-06-11 18:52 | 2026-06-12 | 2026-06-12 16:53 |  |  |  |  | 2026-07-27 |  | 2026-08-04 |  | 2026-08-05 |  |  |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 | [6 empty] | 2026-09-02 |  | 2026-09-11 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-14 |  |  |  | 2026-10-06 |  | 2026-10-08 |  | 2026-10-09 | [5 empty] | 2026-08-13 |  | 2026-07-01 |  | Unknown | 2026-05-24 | 2026-05-24 22:05 | 844907 | 149137 | 0 | 0 | 0 | 0 | 834596.5391 | 141065 | 2026-07-12 00:18:04 +0530 | Rachna Abhyankar | IM Done - cx will be coming next week - post visit of vastu consultant | 2026-07-10 10:47:08 +0530 | Anil Jagtap | The cx needs the floor plan & design for vastu. They will continue with the design and pay the 10% milestone after that | 2026-07-03 10:58:36 +0530 | Rachna Abhyankar | IM Schedule on 3rd July | 2026-07-27 |  | 2026-08-03 |  | Under Construction | 2026-07-31 | 2026-06-07 | 80007 | Ravi Roy
20197 | Turnkey | May'26 | Dipti shah | sky avenue | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 1254886 | 250977 | 1606165 | 0 | 0 | 23 | 0 | 0 | 0 | 507928 | 495980.8 |  |  | 2026-05-24 | 2026-05-26 13:03 | 2026-05-24 | 2026-05-26 16:35 | 2026-05-26 | 2026-05-26 16:45 | 2026-06-21 | 2026-06-21 14:16 | 2026-06-27 |  | 2026-09-21 |  | 2026-05-26 | 2026-05-27 17:39 | 2026-05-27 | 2026-05-27 17:42 | 2026-05-27 | 2026-05-29 15:10 | 2026-05-31 | 2026-05-31 17:16 |  |  |  |  | 2026-06-21 | 2026-06-22 18:18 | 2026-09-16 |  | 2026-09-17 |  |  |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 | [6 empty] | 2026-10-15 |  | 2026-10-24 |  | 2026-10-23 |  | 2026-10-24 |  | 2026-10-25 |  | 2026-10-27 |  |  |  | 2026-11-18 |  | 2026-11-20 |  | 2026-11-21 | [5 empty] | 2026-09-25 |  | 2026-06-01 | 2026-06-20 22:22 | Site is RTMI | 2026-05-24 | 2026-05-26 11:51 | 1361157 | 245008 | 0 | 0 | 0 | 0 | 1361157.0445 | 225879 | 2026-07-08 23:29:10 +0530 | Batskhem Marpna | MOM- Dated: 08.07.26 The following points have been covered during the discussion - Living-dining- done - Designs as per screenshot and design behind sofa to be changed as per image - Sliding photo frame to cover DB to check - CNC laser wall art reduced in size Kitchen- - Laminate kitchen glossy monochrome - Loft height reduced - Wall cabinet increased - lights under the skirting and counter - Gola handles for handleless look - Big container cabinets - Thali basket - Crockery unit to be checked at site Parents room: - Wardrobe position and bed changed - Single drawer each at the bottom 250mm H - Small side table to be incorporated - Wall behind options shared GUEST ROOM - SAME FORMAT AS PARENTS for wardrobe - Wall behind bed options to be shown - Sliding door outside as pocket door - Wall passage ideas to be shown Entrance: - Shoerack outside - Name plate Vanity in bathrooms. As discussed we will do the Material selection on 12th at 2:30pm Sliding door fluted for kitchen entry noted as per initial discussion. Thanks. | 2026-07-03 16:52:44 +0530 | Meet Shah | Others: | 2026-06-20 19:39:47 +0530 | Batskhem Marpna | DDM1: 20.06.2026 MOM-Dipti shah- Dated: 20.06.2026 Living: - L shape sofa - Wall design behind sofa - Light below the tv unit - Laminate panel in TV wall - Show AC pelmet Dining- - Devotional wall mural 3d - Puja mandir with mandala interiorÂ - Fluted glass door with bells - Display unit left wall kitchen Kitchen:Â - Membrabe glossy - Cover panel - Wall unit design - soft colour palette - Lights under the cabinets and under platform MBR- - Retain the placement - Pull out setup in the bedside wardrobe - Drawers for medicene - 1 drawer bottom of the drawer - mirror on the wall adjacent to the hanging clothes unit - TV unit design Guest room: - Dresser with mirror - Wardrobe - Wall design behind bed Note: False ceiling in three rooms Vanities Pendant lights in bedrooms Sconces in living Partition entering the bedroom DB covering Doors design Shoerack outside Thanks, Batskhem | 2026-06-22 | 2026-06-21 14:18 | 2026-06-28 |  | Under Construction | 2026-09-23
20198 | Turnkey | May'26 | Priya Kumar Kaliravana | GeeCee Emerald | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | 10% Payment | 2182018 | 9999 | 0 | 0 | 0 | 49 | 0 | 208203 | 218202 | 1001063 | 744551.2 |  |  | 2026-05-24 | 2026-05-24 21:17 | 2026-05-27 | 2026-05-27 12:41 | 2026-05-27 |  | 2026-06-03 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-05-27 |  | 2026-05-28 |  | 2026-05-28 |  | 2026-05-29 | [5 empty] | 2026-06-04 |  | 2026-06-12 |  | 2026-06-13 |  |  |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-23 | [6 empty] | 2026-07-11 |  | 2026-07-20 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-23 |  |  |  | 2026-08-14 |  | 2026-08-16 |  | 2026-08-17 | [5 empty] | 2026-06-21 |  | 2026-05-30 |  | Unknown | 2026-05-24 | 2026-05-24 21:15 | 0 | 0 | 0 | 0 | 0 | 0 | 1851969 | 330048 | 2026-05-24 21:51:08 +0530 | Vandana Preet | Some Image was uploaded | 2026-05-24 21:18:56 +0530 | Vandana Preet | Already Given | 2026-05-24 21:18:26 +0530 | Vandana Preet | Some Image was uploaded | 2026-06-04 |  | 2026-06-11
20199 | Turnkey | May'26 | ANIKIT JOSHI &KALPA PANDEY JOSHI | SSVR Niyaraa | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 863647 | 124029 | 1234185 | 0 | 0 | 37 | 0 | 0 | 48700 | 363588 | 327330 |  |  | 2026-05-24 | 2026-06-01 13:56 | 2026-05-27 | 2026-06-02 11:31 | 2026-06-05 | 2026-06-02 12:09 | 2026-07-19 |  | 2026-08-08 |  | 2026-08-15 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-06 10:57 | 2026-06-06 | 2026-06-08 17:19 | 2026-06-09 | 2026-06-09 19:15 |  |  |  |  | 2026-07-20 |  | 2026-08-10 |  | 2026-08-11 |  |  |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 | [6 empty] | 2026-09-08 |  | 2026-09-17 |  | 2026-07-22 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-20 |  |  |  | 2026-10-12 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-08-19 |  | 2026-07-15 |  | Unknown | 2026-05-24 | 2026-05-24 16:04 | 1048206 | 185978 | 0 | 0 | 0 | 0 | 1029015.816 | 167209 | 2026-06-08 17:18:31 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: August/September Soft Possession: June/July Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM will update to the sales team by 29th June 2026 * DEM 1 will update to the sales team * 10% Payment Stage Tentatively scheduled for (30th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (40000) Modular - Windows to Wonderful home PM fee waiver (5%) Design fee waiver (5%) Services - Windows to Wonderful Home Free Shoerack Offer Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 8,63,648 Checklist terms descoping and agreement terms are cleared Client VOC: The client mentioned that they will confirm the dates for the IMs by 29 June 2026, as lift work is currently being carried out on the developer's side | 2026-06-06 10:58:51 +0530 | Muralikrishna Udupi | Some Image was uploaded | 2026-06-05 10:46:21 +0530 | Muralikrishna Udupi | Some Image was uploaded | 2026-07-20 |  | 2026-08-09 |  | Under Construction | 2026-09-30
20200 | Turnkey | May'26 | David Dsouza | MICL Aaradhya Parkwood | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 925441 | 185088 | 1040187 | 0 | 0 | 1 | 28 | 0 | 0 | 407437 | 332916 |  |  | 2026-05-24 | 2026-05-30 20:30 | 2026-05-24 | 2026-05-31 21:07 | 2026-06-03 | 2026-05-31 22:27 | 2026-06-14 | 2026-06-14 18:25 | 2026-08-09 |  | 2026-08-16 |  | 2026-05-29 | 2026-05-29 18:31 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-03 14:11 | 2026-06-05 | 2026-06-05 14:15 |  |  |  |  | 2026-06-14 | 2026-06-16 18:57 | 2026-08-11 |  | 2026-08-12 |  |  |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-08-20 |  | 2026-06-06 | 2026-06-14 18:04 | Site is RTMI | 2026-05-24 | 2026-05-26 11:51 | 881514 | 158672 | 0 | 0 | 0 | 0 | 881513.6057 | 155391 | 2026-06-17 12:10:05 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-14 18:24:01 +0530 | Zoya Bhatkar | Minutes of Meeting held on Date: 12th June 2026 Discussion: DEM 1 Based on 12th June 2026 meeting, below is a list of all the requirements that were discussed during the meeting: EntranceÂ Altar Design as per reference shared in WhatsApp Group Living RoomÂ Existing TV Unit Base Unit Sofa Wall Design as per reference shared in WhatsApp Group TV Wall Design as per reference shared in WhatsApp Group Dinning Wall Design as per reference shared in WhatsApp Group False Ceiling Design as per reference shared in WhatsApp Group Double Curtains Track Curtains Floor to Ceiling Master BedroomÂ Wardrobe Internals as discussed shared in WhatsApp Group Floor Mounted Side Table with 2 Drawers Bed Wall Design as per reference shared in WhatsApp Group NO False Ceiling required Fire Pipe Box Packing WashroomWashroom Bottom Vanity in Both Washrooms | 2026-06-05 14:15:14 +0530 | Vishakha Vaishnav | Spoke to Mr Daniel as he is the decision maker "Welcome call done" Initial measurement : Site is not accessible cx will update us on same DEM Dates -Â DEM 1 - Can be done on weekends , tuesday,wednesday,friday need to check with designer DEM 2 - TBD DEM 3 - TBD Possession date : June end Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-15 | 2026-06-14 18:25 | 2026-08-10 |  | Under Construction | 2026-06-30
20201 | Turnkey | May'26 | Aniket Hajare | MICL Aaradhya Parkwood | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Ashish Jha |  | Active | Design | 20% Payment | 864274 | 118722 | 1187232 | 0 | 0 | 8 | 0 | 0 | 54133 | 362654 | 328765.2 |  |  | 2026-05-24 | 2026-05-24 17:30 | 2026-06-09 | 2026-06-09 12:38 | 2026-06-12 | 2026-06-09 16:03 | 2026-07-07 | 2026-07-07 16:38 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-09 | 2026-06-10 14:11 | 2026-06-10 | 2026-06-10 14:11 | 2026-06-10 | 2026-06-11 19:28 | 2026-06-17 | 2026-06-17 18:13 |  |  |  |  | 2026-07-07 |  | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-06-18 | 2026-07-07 16:30 | Site is RTMI | 2026-05-24 | 2026-05-24 17:29 | 1006129 | 181103 | 0 | 0 | 0 | 0 | 993950.898 | 164119 | 2026-07-10 16:19:36 +0530 | Vishakha Vaishnav | CX WILL BE COMING FOR THE MEETING ON 11TH JULY AT THAT TIME HE WILL MAKE THE 10% DUE | 2026-06-26 16:01:00 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-17 18:11:35 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to be aligned asap DEM Dates -Â DEM 1 - Cx said he will do the meeting after IM only DEM 2 - TBD DEM 3 - TBD Possession date : June Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-07-08 | 2026-07-07 16:38 | 2026-07-14 |  | Under Construction | 2026-06-30 | 2026-06-07 | 118722 | Ravi Roy
20202 | Turnkey | May'26 | Sujatha annandan | Rohan Ekanta | BNG - HSR | Yes | Vishal Haridas | Abhinandan K S | Soumya KP | [5 empty] | Aman Kumar |  | Active | Design | DEM1 | 1604209 | 218689 | 2229209 | 0 | 0 | 36 | 0 | 0 | 102153 | 696046 | 587320.8 |  |  | 2026-05-24 | 2026-05-24 17:11 | 2026-05-24 | 2026-05-26 12:44 | 2026-05-31 | 2026-06-02 12:53 | 2026-07-20 |  | 2026-10-05 |  | 2026-10-12 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-07 10:34 | 2026-06-07 | 2026-06-09 11:28 | 2026-06-16 | 2026-06-16 11:52 |  |  |  |  | 2026-07-21 |  | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-27 |  | 2026-10-28 | [6 empty] | 2026-11-15 |  | 2026-11-24 |  | 2026-11-23 |  | 2026-11-24 |  | 2026-11-25 |  | 2026-11-27 |  |  |  | 2026-12-19 |  | 2026-12-21 |  | 2026-12-22 | [5 empty] | 2026-10-16 |  | 2026-07-10 |  | Unknown | 2026-05-24 | 2026-05-24 17:03 | 1889160 | 340048 | 0 | 0 | 0 | 0 | 1851603.7635 | 305726 | 2026-07-03 15:04:15 +0530 | Vishal Haridas | Fridge unit dimension reduced Tall unit with storage required Provision for keeping all appliances have to be provided Dishwasher will be in Utility Flutted glass on kitchen glass cabinet Reduce rod dimension on TV Corner sink cabinet Reading corner in Balcony Study table have to be shifted to other side of Wardrobe | 2026-06-09 11:28:16 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible, client will get the site by August 2026 * DEM 1 13th June 2026 (with layouts) * 10% Payment Stage 19th June 2026 (after 1st DEM) *No civil work planned in client's scope of work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,51,604 Offers Discussed During the Call: Special offer (50000) Special Offer (25000) PM fee waiver (5%) Design fee waiver (5%) Modular - Windows to Wonderful home Services - Windows to Wonderful Home Free Hob & Chimney Offer Laminate Upgrade - May '26 Campaign Final Closing Value Discussed: 16,04,209 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-08 20:33:19 +0530 | Bency Chacko |  | 2026-07-21 |  | 2026-10-06 |  | Under Construction | 2026-09-01
20203 | Turnkey | May'26 | anjali hardia | L and T Powai | MUM - GOR | Yes | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 1426055 | 285211 | 1827508 | 0 | 0 | 12 | 13 | 0 | 0 | 607313 | 533531.2 |  |  | 2026-05-24 | 2026-06-03 13:31 | 2026-05-25 | 2026-06-03 14:44 | 2026-06-06 | 2026-06-03 14:50 | 2026-06-19 | 2026-06-19 16:35 | 2026-09-11 |  | 2026-09-18 |  | 2026-05-31 | 2026-05-31 15:29 | 2026-06-04 | 2026-06-03 17:46 | 2026-06-03 | 2026-06-06 14:23 | 2026-06-10 | 2026-06-10 19:17 |  |  |  |  | 2026-06-19 | 2026-06-20 19:14 | 2026-09-13 |  | 2026-09-14 |  |  |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 | [6 empty] | 2026-10-12 |  | 2026-10-21 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-24 |  |  |  | 2026-11-15 |  | 2026-11-17 |  | 2026-11-18 | [5 empty] | 2026-09-22 |  | 2026-06-11 | 2026-06-19 16:30 | Site is RTMI | 2026-05-24 | 2026-06-01 08:58 | 1548735 | 278772 | 0 | 0 | 0 | 0 | 1524832.9798 | 256690 | 2026-07-02 19:15:15 +0530 | Vishakha Vaishnav | Others: | 2026-06-11 10:24:31 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-10 19:16:55 +0530 | Manzoor Shaikh | "Welcome call done along with the Designer. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : 13th June Tentatively Customer will make 10% post LFM Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-20 | 2026-06-19 16:47 | 2026-09-12 |  | Under Construction | 2026-06-30
20205 | Turnkey | May'26 | Guneet | Prestige City | BNG - HSR | Yes | Janush Bojamma C T | Abhinandan K S | Kowshik |  | Parvez Syed | Nanda Kumar |  |  | Chanakya Panigrahi | Raghavendra Gowda | Active | Preproduction | 2D | 917299 | 174912 | 1277508 | 917299 | 0 | 1 | 0 | 0 | 0 | 391417 | 350970.4 |  |  | 2026-05-24 | 2026-05-24 17:50 | 2026-05-26 | 2026-05-28 16:42 | 2026-05-29 | 2026-05-31 20:20 | 2026-06-13 | 2026-06-13 19:49 | 2026-07-08 | 2026-07-07 11:19 | 2026-07-09 | 2026-07-09 11:39 | 2026-05-29 | 2026-05-29 19:49 | 2026-06-01 | 2026-06-04 12:14 | 2026-06-04 | 2026-06-05 12:44 | 2026-06-06 | 2026-06-06 19:36 |  |  |  |  | 2026-06-13 | 2026-06-15 16:01 | 2026-07-02 | 2026-07-03 21:59 | 2026-07-04 | 2026-07-03 21:59 |  |  | 2026-07-12 | 2026-07-14 16:08 | 2026-07-13 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-14 |  | 2026-06-07 | 2026-06-13 19:44 | Site is RTMI | 2026-05-24 | 2026-05-24 17:48 | 1082634 | 194874 | 1105223.7939 | 173486 | 0 | 0 | 1105223.7939 | 173486 | 2026-06-16 12:51:31 +0530 | Janush Bojamma C T | DEM1 was done on 13th June - The inputs or change of design was less so that - the 2nd DEm2 meeting is planned on 18th June | 2026-06-06 19:37:21 +0530 | Abhinandan K S | RTMI project. Initial measurement is planned for 7th June 2026. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. | 2026-06-05 12:44:23 +0530 | Athul Ajaykumar |  | 2026-06-14 | 2026-06-13 19:50 | 2026-07-08 | 2026-07-07 11:20 | RTMI
20206 | Turnkey | May'26 | Shubhangi Jaywant | TATA SEREIN | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar |  |  | Asif Shaikh | Aditya Vikram | Murali S | Anant Giri | Shailendra Mishra | Active | Preproduction | Procurement | 2862804 | 1781016 | 2628400 | 0 | 2986260 | 7 | 0 | 0 | 0 | 0 | 1081788 |  |  | 2026-05-24 | 2026-05-24 22:05 | 2026-05-24 | 2026-05-26 11:03 | 2026-05-29 | 2026-05-26 20:24 | 2026-06-09 | 2026-06-09 19:20 | 2026-06-13 | 2026-06-16 11:27 | 2026-06-27 | 2026-06-26 23:46 | 2026-05-26 | 2026-05-26 20:43 | 2026-05-27 | 2026-05-26 21:15 | 2026-05-26 | 2026-05-27 13:58 | 2026-05-31 | 2026-05-31 11:16 |  |  |  |  | 2026-07-06 | 2026-06-09 18:12 | 2026-06-17 | 2026-06-16 17:12 | 2026-06-17 | 2026-06-16 17:13 |  |  | 2026-06-27 | 2026-06-30 11:08 | 2026-06-30 | 2026-06-30 19:09 | 2026-07-21 | 2026-07-03 20:06 | 2026-07-04 | 2026-07-06 19:17 |  |  |  |  | 2026-07-08 15:07 | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-10-08 | [5 empty] | 2026-07-20 | 2026-07-07 16:50 | 2026-07-01 | 2026-06-09 18:28 | Unknown | 2026-05-24 | 2026-05-24 22:04 | 2229745 | 398655 | 0 | 0 | 2986260 | 537526 | 2986260.4736 | 515304 | 2026-07-12 12:56:45 +0530 | Asif Shaikh | Procurement: Floor Covering work will be done by 14th July 2. False Ceiling & electrical work shall be commencing from 15th July & will be completed by 25th July (Tentative). 3. First coat painting work shall be commencing from 25th July & will be completed by 30th July (Tentative) 4. Furniture shall be ready for dispatched between 28th July to 30th July (Tentative) | 2026-06-24 11:31:08 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-14 18:58:50 +0530 | Rachna Abhyankar | Hello @~Shubhangi Jaywant ma'amÂ Good morninhg Cross Measurements M.O.M Entrance Shoe rack to be added. Safety door frame to be provided, as there is no existing frame for the new door. Living Area Mandir depth to be maintained at 1'-8". Hidden door concept to be incorporated for the Living Area and Bedroom 1 door. Cove lighting to be provided on all sides, excluding the area above the TV wall. Kitchen Existing kitchen wall to be demolished. Storage units/cabinets to be taken up to full height as per the previous design. Existing wall tiles (dado tiles) to be demolished. New floor tiles to be installed. Bedroom 1 Bed to be replaced with a sofa-cum-bed. Internal wardrobe lighting to be provided for all rooms . Bedroom 2 Bed to be replaced with a sofa-cum-bed. Existing study table to be removed. Only one shelf to be provided. Bedroom 3 No changes proposed. All Doors Quote to be shared for new doors. Utility : Â we do not takeÂ metal grill work for balconies. Client Scope Shifting of smoke detector. Procurement of floor tiles. Procurement of dado tiles. Sink. Lights. Switchboards. Plumbing shifting work. Note: As per the above changes, a revised quotation will be shared. | 2026-06-10 | 2026-06-09 20:25 | 2026-06-17 | 2026-06-16 11:30 | Under Construction | 2026-05-31
20207 | Turnkey | May'26 | Ashwin dhirwani | Dosti Mezzo | MUM - GOR | Yes | [8 empty] | Rashmita Das |  | Active | Prospect | 10% Payment | 2648929 | 9999 | 0 | 0 | 0 | 36 | 0 | 254894 | 264893 | 1120918 | 998225.6 |  |  | 2026-05-24 | 2026-05-25 12:09 | 2026-05-24 | 2026-05-26 12:54 | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-06-15 |  | 2026-06-23 |  | 2026-06-24 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 | [6 empty] | 2026-07-22 |  | 2026-07-31 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-03 |  |  |  | 2026-08-25 |  | 2026-08-27 |  | 2026-08-28 | [5 empty] | 2026-07-02 |  | 2026-06-10 |  | Unknown | 2026-05-24 | 2026-05-25 12:09 | 0 | 0 | 0 | 0 | 0 | 0 | 2244855 | 404074 | 2026-06-09 15:22:31 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-09 15:21:15 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-08 14:13:51 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-15 |  | 2026-06-22
20209 | Turnkey | May'26 | Mr. Chetan Reddy | Casagrand flamingo | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1592918 | 222424 | 2276200 | 0 | 0 | 40 | 0 | 0 | 96160 | 637167 | 637167.2 |  |  | 2026-05-24 | 2026-05-24 18:25 | 2026-05-26 | 2026-05-26 13:12 | 2026-05-31 | 2026-06-03 10:30 | 2026-07-24 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-06-03 | 2026-05-31 | 2026-06-04 | 2026-06-03 10:33 | 2026-06-03 | 2026-06-05 18:01 | 2026-06-09 | 2026-06-09 14:13 |  |  |  |  | 2026-07-25 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-07-20 |  | Unknown | 2026-05-24 | 2026-05-24 18:24 | 1928983 | 347217 | 0 | 0 | 0 | 0 | 1884949.266 | 311250 | 2026-07-14 18:28:59 +0530 | Manoj Kumar R | Pooja unit Pooja unit width increased & internals design modified. Pooja door to be check . T v unit Metal fabrication to be check sofa wall to be design as per reference. Dining Dining table option to be check. Mirror to be consider in crockery unit Kitchen spice rack to consider in both side. cylinder unit to be consider tall unit accessories to be remove. check without rolling shutter. | 2026-06-05 18:00:10 +0530 | Athul Ajaykumar | Possession Status:Under constructionÂ Possession: September End Soft Possession: July End Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (13th June 2026) * 10% Payment Stage Tentatively scheduled for (14th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (40000) Special Offer (35000) Modular Windows to Wonderful home Design fee waiver (5%) PM fee waiver (5%) Services Windows to Wonderful Home Free Shoerack Offer Free Hob & Chimney Offer Laminate Upgrade - May '26 Campaign Silver Coin 21g Final Closing Value Discussed: 15,92,918 Checklist terms descoping, agreement terms are cleared | 2026-06-03 10:45:42 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-07-25 |  | 2026-08-01 |  | Under Construction | 2026-09-30
20210 | Turnkey | May'26 | Himanshu Mishra | SOBHA Dream Gardens | BNG - HRBR | Yes | Asmitha Saif | Parasa Sri | Shibin Lal | [5 empty] | Kushal S | Vishwa Hiremath | Active | Preproduction | CM | 876897 | 144156 | 1027920 | 0 | 0 | 3 | 0 | 0 | 0 | 400345 | 332396.4 |  |  | 2026-05-24 | 2026-05-25 12:11 | 2026-05-24 | 2026-05-25 12:12 | 2026-05-28 | 2026-05-29 12:47 | 2026-06-23 | 2026-06-23 19:17 | 2026-06-29 | 2026-06-28 18:38 | 2026-07-19 |  | 2026-05-29 | 2026-05-29 18:52 | 2026-05-30 | 2026-06-10 12:38 | 2026-06-10 | 2026-06-11 14:18 | 2026-06-12 | 2026-06-12 18:57 |  |  |  |  | 2026-06-18 | 2026-06-22 18:53 | 2026-07-13 | 2026-07-14 10:52 | 2026-07-15 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-06-13 | 2026-06-23 19:02 | Site is RTMI | 2026-05-24 | 2026-05-24 18:24 | 871119 | 156801 | 0 | 0 | 0 | 0 | 1034963.9435 | 170891 | 2026-07-04 20:41:16 +0530 | Asmitha Saif | Minutes of Meeting held on Date: 04.07.2026 Title: Material Finalization Project: 20210 Client: Himanshu mishra Attendees: Asmitha Objective: Material, color and design finalising Discussion ï»¿ Based on 04.07.2026 meeting, below is a list of all the requirements that were discussed during the meeting: â€¢ Living Room: TV unit design and colors are finalized. TV wall fluted panel will be updated in the 3D with top & bottom cove lighting. Require 3 wallpaper options for the sofa wall with matching sofa color suggestions. â€¢ Puja Unit: Design, color, and glass pattern are finalized. â€¢ Dining Area: Top cabinet glass will be changed to plain glass, and a matching fluted panel design/ tv unit wall, the same fluted panel will be added to the wall between the top and bottom cabinets of the crockery unit. â€¢ Kitchen: Vent grills, L-shaped closed spice unit, top panel above the chimney, and microwave placement on the countertop will be updated. Kitchen laminate and granite are finalized. â€¢ Utility: No changes. Material and colors are finalized. â€¢ Master Bedroom: Wardrobe design and colors are finalized. Dresser mirror height will be increased to 2000 mm, and the toilet vanity will have a darker wooden finish. â€¢ Bedroom 1: Wardrobe colors will be updated as finalized, and the dresser mirror height will be increased to 2000 mm. â€¢ Common Vanity: Dark wooden finish is ok, as same as bedroom laminate. Others: Floor-to-ceiling curtain option with gypsum pelmet has to shown in 3d, We will verify the revised costing with the estimation team, Handle catalogue- Soft copy will be shared. Updated 3D renders with finalized materials will be shared before the next meeting. Cross measurement is tentatively planned for the coming weekend, as per the cx availability. | 2026-06-28 19:45:16 +0530 | Asmitha Saif | Minutes of Meeting held on Date: 28.06.2026 Title: DEM 2 Project: 20210 Client: Himanshu Mishra Attendees: Asmitha Objective: Design changes discussion Discussion Based on 28.06.2026 meeting, below is a list of all the requirements that were discussed during the meeting: 1. Living Room:Puja Unit:Change the bottom drawers to shutter units.Provide a 100 mm pull-out.Add ledges for placing idols.Provide lighting:Ceiling spot light at the top.Profile lights on both side panels.Provide provision for hanging bells.TV Unit:Add an open unit in the center for the set-top box.Extend the TV unit up to the door opening level.2. Kitchen:Sink Area:Change to a single-shutter sink unit.Convert the left-side open space into a closed shutter.Provide ventilation fittings at the top and bottom of the shutter.Position the water purifier near the existing plumbing/electrical point.Chimney:Replace the inclined chimney with a straight chimney model.Top CabinetsProvide a blind corner unit on the left side.On the right side of the chimney, provide fluted glass shutter finish.3. Utility:Provide end-to-end base and overhead cabinets.Remove the dishwasher provision.Provide a sink with a side drain tray.Sink width should be more than 2 ft.Sink bowl length should be more than 1 ft.Confirm the sink dimensions with the execution team.4. Master Bedroom:WardrobeWardrobe design is approved.Dresser UnitIncrease the mirror height.Provide storage on both sides of the mirror.Redesign as per standard dimensions.ToiletKeep only the mirror.Remove the storage behind the mirror.5. Bedroom 1:WardrobeExtend the wardrobe from end to end of the wall.Relocate the switchboard onto the wardrobe side panel.6. Common Vanity:Increase the mirror width and height.Remove the mirror storage cabinet.Provide a separate wall-mounted storage cabinet in the common area.Additional Notes:All loft units will have a pre-lam finish.Verify with the Estimation Team regarding the increase in:Floor covering chargesDcor chargesTransportation chargesLifting chargesCleaning chargesSpecifications as compared to the original quotation.Kids' Bedroom: Wardrobe cost shows a 1,000 price difference despite no design changes. Please verify with the estimation team.Share the handle catalogue/options with the client.Next meeting is scheduled for the coming weekend. | 2026-06-24 14:53:59 +0530 | Asmitha Saif | Minutes of Meeting held on Date: 21.06.2026 Title: DEM 1 Project: 20210 Client: Himanshu Mishra Attendees: Asmitha, shibin & Thanusree Objective: Layout Finalization Discussion Based on 21.06.2026 meeting, below is a list of all the requirements that were discussed during the meeting: Minutes of Meeting held on Date: 21.06.2026 Attendees: Asmitha, Shibin, Thanusree & Himanshu mishra Discussion: DEM 1- Meeting Based on 21.06.2026 meeting, below is a list of all the requirements that were discussed during the meeting: 1. Entrance:Shoe rack placement to be provided as per offer.2. Living Room:TV UnitPlacement to be done as per standard height (wall-mounted).Electrical point overlap to be checked.Pooja UnitFull-height shutter from top till floor (floor-mounted).Mandir design to have only step design (no ledges).Internal lighting required.Width: 2.5 ftBottom storage with:1 pull-out tray for divaRemaining storage as cabinetOption 2Pocket door option requested.Sofa WallExisting beadings to remain unchanged.No design modifications required.WallpaperOptions to be shared.3. Dining Room:Crockery UnitTop cabinet shutters to have fluted glass.Internal lighting required.4. Kitchen:L-Corner unit required.BPO No SS finish.Tandem unit required.Single long spice rack ledge required with lighting.Depth: 200 mmRO point- Water Purifier unitClosed cabinet required for RO unit.Sink faucet to be positioned at center of cabinet.Remove open ledges from top unit.L-Corner top unit to align with bottom unit.Kitchen loft to be added.Chimney side cabinets:Glass shutters required on both sides as one design option.5. Utility:Sink unit to be changed to single shutter as per available space.Utility sink:9" sink depth required- needs to check in the scope,Dishwasher placement beside sink.Open utility area provision required.6. Common Toilet:Double shutter vanity unit required.Additional 2 ft closed storage unit required.7. Master Bedroom:WardrobeSide shutter storage for used clothes.Opening direction towards wall.Dresser unit: Height to match side table height for dual usability.Study TableCable wire fixture provision required.with 1 socket to be provided on the table.Wardrobe Internal Layout1 long cloth rail on top inside a single carcass,2 drawers in the middle section,remaining space- Shelves below,Reference: Similar to EC Rattan Sliding Wardrobe.8. Master Bedroom Toilet:Double shutter vanity unit required.Mirror with storage behind required.9. Kids Bedroom:Study unit length to be increased slightly.Cable wire fixture provision required.with 1 socket to be provided on the table. | 2026-06-24 | 2026-06-24 14:48 | 2026-06-29 | 2026-06-28 19:52 | RTMI
20211 | Turnkey | May'26 | samidha gaikwad | MICL Aaradhya Parkwood | MUM - GOR | No Estimate | [8 empty] | Ashish Jha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-24 | 2026-05-24 19:23 | 2026-05-25 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-30 |  | 2026-05-31 | [5 empty] | 2026-06-06 |  | 2026-06-14 |  | 2026-06-15 |  |  |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-23 |  | 2026-06-01 |  | Unknown | 2026-05-24 | 2026-05-24 19:22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 19:25:53 +0530 | Ashish Jha | Some Image was uploaded | [6 empty] | 2026-06-06 |  | 2026-06-13
20212 | Turnkey | May'26 | Priya Kadam | Empire Towers | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Active | Preproduction | Site Readiness 1 | 1749700 | 461164 | 2255820 | 0 | 0 | 29 | 0 | 0 | 0 | 624256 | 664280 |  |  | 2026-05-24 | 2026-05-27 11:52 | 2026-05-24 | 2026-05-27 17:16 | 2026-06-06 | 2026-06-06 21:37 | 2026-06-17 | 2026-06-16 18:30 | 2026-08-06 |  | 2026-08-13 |  | 2026-06-06 | 2026-06-09 12:26 | 2026-06-07 | 2026-06-09 19:53 | 2026-06-09 | 2026-06-10 16:11 | 2026-06-12 | 2026-06-12 17:14 |  |  |  |  | 2026-06-18 | 2026-06-12 17:15 | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-06-13 | 2026-06-16 15:41 | Site is Non-RTMI | 2026-05-24 | 2026-05-27 11:51 | 1913957 | 341862 | 0 | 0 | 0 | 0 | 1908041.5413 | 312296 | 2026-06-30 13:42:12 +0530 | Preet Karania | Some Image was uploaded | 2026-06-24 12:36:39 +0530 | Anil Jagtap | Possession - MID July*26 | 2026-06-17 12:46:46 +0530 | Preet Karania | Some Image was uploaded | 2026-06-17 | 2026-06-16 18:31 | 2026-08-07 |  | Under Construction | 2026-07-15 | 2026-06-06 | 461164 | Ravi Roy
20214 | Turnkey | May'26 | Loveleen | neelam solstice | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | Viraj Chavan | Viraj Chavan | suraj kumar | Rizwan Mistry |  | Rashmita Das | Sunil Poojary | Active | Preproduction | 3D Sign off | 2171119 | 344115 | 2206492 | 2171119 | 0 | 3 | 0 | 0 | 0 | 1037350 | 789653.6 |  |  | 2026-05-24 | 2026-05-29 11:41 | 2026-05-24 | 2026-05-29 11:47 | 2026-05-29 | 2026-05-29 14:14 | 2026-06-19 | 2026-06-14 18:25 | 2026-07-08 | 2026-07-07 14:44 | 2026-07-12 | 2026-07-07 16:58 | 2026-05-29 | 2026-05-29 20:28 | 2026-05-30 | 2026-05-29 20:28 | 2026-05-29 | 2026-06-16 12:40 | 2026-06-14 | 2026-06-14 15:07 |  |  |  |  | 2026-06-23 | 2026-06-19 11:13 | 2026-07-08 | 2026-07-07 16:06 | 2026-07-08 | 2026-07-07 16:07 |  |  | 2026-07-11 | 2026-07-12 12:30 | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-15 | 2026-06-14 17:53 | Site is RTMI | 2026-05-24 | 2026-05-25 11:33 | 1872195 | 334296 | 2314695.6892 | 390801 | 0 | 0 | 2314695.6892 | 390801 | 2026-07-03 12:05:01 +0530 | Manzoor Shaikh | The Cross measurement is aligned on 03rd July at 3 PM. | 2026-06-20 11:54:22 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-18 16:33:12 +0530 | Manzoor Shaikh | Dear Ms. Loveleen, Greetings from Bonito! We are pleased to inform you that we have scheduled your DEM 2 meeting for 20th June at 12:00 PM at Andheri EC. The agenda for this meeting will be to discuss the Material Selection with our designer, Zoya will guide you through this process and address any initial design preferences or ideas you have in mind. Looking forward to collaborating with you to bring your vision to life! DEM 2: AGENDA All aesthetic Material Finishes Selection of light fittings Finalize kitchen accessories Finalize appliances Selection of loose furniture Warm regards, Manzoor Shaikh, Customer Success Manager | 2026-06-15 | 2026-06-14 18:25 | 2026-07-08 | 2026-07-07 14:45 | RTMI
20215 | Turnkey | May'26 | Surya Prakash Prakash | Sona Vistaas | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Design | 20% Payment | 1704731 | 227469 | 2274688 | 0 | 0 | 3 | 0 | 0 | 113477 | 707728 | 656057.2 |  |  | 2026-05-24 | 2026-05-30 10:49 | 2026-05-29 | 2026-05-30 11:09 | 2026-06-06 | 2026-06-09 11:30 | 2026-07-13 | 2026-07-12 19:47 | 2026-06-23 |  | 2026-08-03 |  | 2026-06-09 | 2026-06-09 12:25 | 2026-06-10 | 2026-06-11 12:59 | 2026-06-11 | 2026-06-11 15:10 | 2026-06-17 | 2026-06-17 11:42 |  |  |  |  | 2026-07-15 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-06-18 | 2026-06-18 19:24 | Site is RTMI | 2026-05-24 | 2026-05-26 12:05 | 1927702 | 346986 | 0 | 0 | 0 | 0 | 1961017.9874 | 323802 | 2026-07-03 15:47:12 +0530 | Avishkar Sargam | Minutes of Meeting (MoM) â€“ 28/06 Foyer - Proceeding with the mirror design. A central circular mirror option will be included in the render. - Wall moulding to be added on the MCB wall. - Confirmation required on whether to continue with wall moulding or opt for wall art on the entrance wall. Living Room - As discussed, electrical points will be shifted to conceal them within the TV unit. - The existing pooja unit will be retained. - Crockery unit to be provided on the dining wall. Kitchen - Kitchen layout remains unchanged. - Additional design options to be explored for the wall units. - Kitchen wicker basket to be incorporated. - Sink position to be shifted (final location to be confirmed). - will get back on Sliding Partition. Utility - Provision for one cylinder unit and one sink unit. - Confirmation required on whether to continue with the janitor pull-out. Kids' Bedroom - Proceeding with a simple wallpaper design. - Wardrobe to be extended. - Book storage unit added. - Loose study table to be provided. Master Bedroom - Two wall concept options to be presented. Parents' Bedroom - Confirmation required on the final layout. | 2026-06-11 14:45:41 +0530 | Athul Ajaykumar | Possession Status: RTMI Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40, Plan of Action Discussed During the Call: * IM Tentatively scheduled for (12th June 2026) * DEM 1 Tentatively scheduled for (19th June 2026) * 10% Payment Stage will update to the sales team * Civil work - NO Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special offer (50000) Special Offer (25000) Laminate Upgrade - Windows to Wonderful home PM fee waiver (5%) Modular - Windows to Wonderful home Design fee waiver (5%) Services - Windows to Wonderful Home Free Shoerack Offer Final Closing Value Discussed: 15,90,108 Checklist terms descoping and agreement terms are cleared | 2026-06-11 13:00:26 +0530 | Muralikrishna Udupi | Client wants onboarding call to be arranged at 2:30 Pm | 2026-07-13 | 2026-07-12 19:58 | 2026-06-24 |  | RTMI |  | 2026-06-06 | 227469 | Ravi Roy
20216 | Turnkey | May'26 | Ravindra Kulkarni | runwal sanctuary | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 2022295 | 9999 | 0 | 0 | 0 | 52 | 0 | 192231 | 202230 | 872572 | 745263.6 |  |  | 2026-05-24 | 2026-05-24 21:21 | 2026-06-04 | 2026-06-07 11:33 | 2026-05-30 |  | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-05-24 | 2026-05-24 20:30 | 0 | 0 | 0 | 0 | 0 | 0 | 1713809 | 308485 | 2026-06-17 16:52:58 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-09 15:36:47 +0530 | Anjali Singh | DCM: Recap: 20216 - Design Consultation Meeting (DCM) with the customer 04 June ¦ Meeting ¦ Microsoft Teams | 2026-06-09 15:35:19 +0530 | Anjali Singh | CDP: Recap: Meeting with Anjali Pratap Singh 07 June ¦ Meeting ¦ Microsoft Teams | 2026-06-18 |  | 2026-06-25
20218 | Turnkey | May'26 | Srinivas PL | 2bhk independent house | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 3040186 | 9999 | 0 | 0 | 0 | 47 | 0 | 294020 | 304019 | 1313346 | 1118802.4 |  |  | 2026-05-24 | 2026-05-29 11:53 | 2026-05-30 |  | 2026-06-07 |  | 2026-06-09 |  | 2026-06-16 |  | 2026-06-23 |  | 2026-06-02 |  | 2026-06-03 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | 2026-06-10 |  | 2026-06-18 |  | 2026-06-19 |  |  |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-29 | [6 empty] | 2026-07-17 |  | 2026-07-26 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-20 |  | 2026-08-22 |  | 2026-08-23 | [5 empty] | 2026-06-27 |  | 2026-06-05 |  | Unknown | 2026-05-24 | 2026-05-29 11:50 | 0 | 0 | 0 | 0 | 0 | 0 | 2576429 | 463757 | 2026-05-29 11:55:53 +0530 | Janvi Nagdeo | Some Image was uploaded | [6 empty] | 2026-06-10 |  | 2026-06-17
20219 | Turnkey | May'26 | Vithal Nayak | Sobha city | BNG - HRBR | No Estimate | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-24 | 2026-05-29 11:49 | 2026-06-11 |  | 2026-06-06 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-05-24 | 2026-05-26 11:21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-29 11:50:26 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-05-24 20:31:34 +0530 | Unknown | About the Customer **3BHK Ready Apartment in Hebbal** Customer has a 3BHK apartment in Shobha City, Hebbal, ready to move in, with an interior design budget of 7-10 lakhs. They are looking for end-to-end interior design services including false ceiling and painting. **Bathroom Civil Work Requirement** Customer requires minor civil work in the bathroom, specifically checking and potentially fixing pipe connections by opening tiles. **Concern on Post-Design Communication** Customer expressed concern about potential communication breakdowns and issues post-design based on online reviews. **Experience Center Visit Scheduled** Appointment scheduled for today between 3:30 PM and 4:00 PM at the HRBR experience center for the customer and family. **Agent to Send WhatsApp Invite** Agent to send WhatsApp invite with location, project videos, and floor plan request. |  |  |  | 2026-06-22 |  | 2026-06-29
20220 | Turnkey | May'26 | shailaja gharat | greecee emrald | MUM - Thane | No Estimate | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-24 | 2026-05-24 20:51 | 2026-06-04 |  | 2026-05-28 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-06-15 |  | 2026-06-23 |  | 2026-06-24 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 | [6 empty] | 2026-07-22 |  | 2026-07-31 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-03 |  |  |  | 2026-08-25 |  | 2026-08-27 |  | 2026-08-28 | [5 empty] | 2026-07-02 |  | 2026-06-10 |  | Unknown | 2026-05-24 | 2026-05-24 20:49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-02 12:25:27 +0530 | Foram Joshi | Some Image was uploaded | 2026-05-28 18:11:07 +0530 | Aakriti Parmar | Some Image was uploaded |  |  |  | 2026-06-15 |  | 2026-06-22
20221 | Turnkey | May'26 | santosh bawaskar | Lakhani Empire Tower | MUM - Thane | No Estimate | [8 empty] | vinaya thakur |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-24 | 2026-05-26 17:51 | 2026-05-25 |  | 2026-06-06 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-06-06 |  | 2026-06-07 |  | 2026-06-07 |  | 2026-06-08 | [5 empty] | 2026-06-14 |  | 2026-06-22 |  | 2026-06-23 |  |  |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 | [6 empty] | 2026-07-21 |  | 2026-07-30 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-02 |  |  |  | 2026-08-24 |  | 2026-08-26 |  | 2026-08-27 | [5 empty] | 2026-07-01 |  | 2026-06-09 |  | Unknown | 2026-05-24 | 2026-05-26 17:49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-06-14 |  | 2026-06-21
20222 | Turnkey | May'26 | Shree Novelty | MICL Aaradhya Parkwood | MUM - GOR | Yes | Zoya Bhatkar | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 1083289 | 216658 | 1506227 | 0 | 0 | 15 | 0 | 0 | 0 | 483478 | 383153.2 |  |  | 2026-05-24 | 2026-05-28 16:08 | 2026-05-31 | 2026-06-02 15:45 | 2026-06-07 | 2026-06-11 15:09 | 2026-06-29 | 2026-06-28 20:54 | 2026-07-04 |  | 2026-07-11 |  | 2026-06-07 | 2026-06-08 19:21 | 2026-06-08 | 2026-06-11 14:47 | 2026-06-12 | 2026-06-16 17:31 | 2026-06-19 | 2026-06-19 19:16 |  |  |  |  | 2026-06-28 | 2026-06-30 12:33 | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-06-20 | 2026-06-28 20:46 | Site is RTMI | 2026-05-24 | 2026-05-28 16:06 | 1276463 | 229763 | 0 | 0 | 0 | 0 | 1276362.3323 | 210742 | 2026-06-25 12:36:08 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-19 19:15:36 +0530 | Manzoor Shaikh | "Welcome call done. DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : June End Customer will make 10% post LFM Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-19 18:58:34 +0530 | Manzoor Shaikh | Called the customer said he is busy and will call back in sometime. | 2026-06-29 | 2026-06-28 20:54 | 2026-07-05 |  | Under Construction | 2026-06-30 | 2026-06-07 | 150623 | Ravi Roy
20223 | Turnkey | May'26 | Neelam Shinde | Nascon matoshree | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Hold | Design | DEM1 | 1817808 | 477999 | 2378129 | 0 | 0 | 33 | 8 | 0 | 0 | 708933 | 630875.6 |  |  | 2026-05-24 | 2026-05-27 11:56 | 2026-05-24 | 2026-05-27 12:45 | 2026-05-30 | 2026-05-31 12:00 | 2027-03-04 |  | 2027-03-11 |  | 2027-03-18 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-02 17:14 | 2026-06-02 | 2026-06-04 16:18 | 2026-06-10 | 2026-06-10 13:27 |  |  |  |  | 2026-06-11 | 2026-06-10 13:23 | 2027-03-13 |  | 2027-03-14 |  |  |  | 2027-03-21 |  | 2027-03-22 |  | 2027-03-23 |  | 2027-03-24 | [6 empty] | 2027-04-11 |  | 2027-04-20 |  | 2027-04-19 |  | 2027-04-20 |  | 2027-04-21 |  | 2027-04-23 |  |  |  | 2027-05-15 |  | 2027-05-17 |  | 2027-05-18 | [5 empty] | 2027-03-22 |  | 2027-02-28 |  | Unknown | 2026-05-24 | 2026-05-27 11:54 | 2015364 | 362765 | 0 | 0 | 0 | 0 | 2015363.3906 | 335755 | 2026-07-07 13:26:44 +0530 | Anamika Dolai | Posession Delayed Till Feb'27 | 2026-06-05 13:20:32 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-04 16:17:19 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: Feb 2027 Scope of Work: Modular + Painting (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible * DEM 1 By weekends (with layouts) (client have not give the confirmed dates, he will check with his family and then let us know) * 10% Payment Stage already paid *No civil work planned yet Transaction will be B2C self funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 20,15,364 Offers Discussed During the Call: Free Shoerack Offer Design Fee Waiver (4%) 100% GST Waiver PM fee waiver (5%) Silver Coin 21g Final Closing Value Discussed: 18,17,808 Checklist terms - descoping, delay compensation, agreement terms are clear | 2027-03-05 |  | 2027-03-12 |  | Under Construction | 2027-02-28
20224 | Turnkey | May'26 | Anand Ramakant Patkar | L&T 77 cross road | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Hold | Preproduction | Site Readiness 1 | 827636 | 165527 | 1104929 | 0 | 0 | 12 | 12 | 0 | 0 | 339513 | 322595.6 |  |  | 2026-05-24 | 2026-05-26 17:27 | 2026-05-27 | 2026-05-27 13:16 | 2026-05-30 | 2026-05-31 00:14 | 2026-06-21 | 2026-06-21 21:30 | 2026-08-15 |  | 2026-08-22 |  | 2026-05-30 | 2026-05-30 23:12 | 2026-06-01 | 2026-06-03 15:55 | 2026-06-03 | 2026-06-05 16:38 | 2026-06-10 | 2026-06-10 13:04 |  |  |  |  | 2026-06-16 | 2026-06-21 19:33 | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-06-11 | 2026-06-21 20:51 | Site is Non-RTMI | 2026-05-24 | 2026-05-26 17:27 | 936380 | 168548 | 0 | 0 | 0 | 0 | 935672.9035 | 148974 | 2026-07-03 10:52:11 +0530 | Vishakha Vaishnav | Others: CX haven't received possession | 2026-06-21 20:52:22 +0530 | Batskhem Marpna | Minutes of Meeting held on Date: 21.06.2026 MOM- Anand: Dated-21.06.2026 The following pointers have been covered during the discussion- Foyer- - MandirÂ - Foyer wall devotional 3d mural - Wall design as per refernece behind sofaÂ Living - TV drawers floaating 8" from the floor - Tall glass unit added - Plain wall design behind the TV Son bedroom - Wavy shaped shape mirror - Pullout shelves inside wardrobe - Add Hidden drawers in both wardrobes - Hanging clothes unit - Wavy mirror with similar pattern in wall design - False ceiling as per reference Master bedroom: - Same wardrobe setup as bedroom 1 - Wall design with mirror - False ceiling as per reference Bathrooms- - Vanity units with mirrors Thanks, Batskhem | 2026-06-18 14:48:32 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-22 | 2026-06-21 21:32 | 2026-08-16 |  | Under Construction | 2026-10-31
20226 | Turnkey | May'26 | Neha and Bhushan | Adarsh Century | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Preproduction | DEM2 | 1431448 | 286290 | 1892064 | 0 | 0 | 24 | 0 | 0 | 0 | 588955 | 556202.8 |  |  | 2026-05-24 | 2026-05-30 14:40 | 2026-05-30 | 2026-05-31 21:33 | 2026-06-07 | 2026-06-09 11:12 | 2026-06-21 | 2026-06-21 20:11 | 2026-07-09 |  | 2026-07-16 |  | 2026-06-09 | 2026-06-09 12:59 | 2026-06-10 | 2026-06-13 19:24 | 2026-06-13 | 2026-06-16 18:12 | 2026-06-17 | 2026-06-17 11:40 |  |  |  |  | 2026-06-26 | 2026-06-21 19:21 | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-21 | 2026-06-21 20:05 | Site is RTMI | 2026-05-24 | 2026-05-24 22:13 | 1603444 | 288620 | 0 | 0 | 0 | 0 | 1560439.239 | 257660 | 2026-07-14 17:02:37 +0530 | Manoj Kumar R | Notes & MOM - 04-07-2026 DB area design to be changed to realistic which is available in market. Shoe rack- flatstrip to be remove, add knobs. Sofa wall- double beading with wallpaper -as per Reference. Pooja unit. Internal 2 step to be consider. crockery unit design to be change as per references with minimal storage. dining vanity unit to be remove. Kitchen Fridge color to be change. MBR Bed wall - wing chair to be remove , add indoor plant(Bigger plant). Bedsize - king Wallpaper to be change. Brown mirror & rose gold mirror option to be consider. MBR main Right side wardrobe internals modified, in secondary wardrobe(Behind main door) locker to be consider. PBR Dresser- 1 drawer to be consider(Wall mounted drawer) GBR word Quote to be check . | 2026-07-14 17:01:33 +0530 | Manoj Kumar R | Notes & MOM, Date: 27-06 AC position to be consider in the design in all the area. Master bedroom Study +glass tall unit + wardrobe Bed backwall - keep previous design. sprinkler cutout to be shown in MBR wardrobe area. side table to be shown in render. bed side right side wall to be design with curved design with storage. Guest bedroom Dresser & bed to be move towards right side. Wardrobe internals modified. Check for alternate design for study. show hanging light in dresser area. PBR Check for PULLOUT wardrobe with sprinkler extension , gap Laminate shade to be change Mirror position to be change Mirror to be consider in left side wardrobe, framed mirror shutter & mirror on Wooden shutter option to be shown. library unit to be redesign. Base storage + wardrobe to be consider in the design. with sprinkler extension & Gap between wardrobe & false ceiling to be shown. Living Tv unit check for shoe unit next to the tv unit Keep the previous design except drawer storage. DB Box covering design to be consider alligning with shoe unit Sofa & chair color to be change. Sofa wall Double beading with wallpaper , Wall light to be shown in design Passage area Add wall art & hanging light Pooja Unit Pooja unit to be consider till the ceiling. Kitchen double door glass tall unit to be consider | 2026-06-16 18:14:09 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-06-22 | 2026-06-21 20:26 | 2026-07-10 |  | RTMI |  | 2026-06-07 | 190272 | Ravi Roy
20227 | Turnkey | May'26 | Sourabh | Navami | BNG - HRBR | Yes | [10 empty] | Active | Prospect | 10% Payment | 2425053 | 9999 | 2425053 | 0 | 0 | 36 | 0 | 232506 | 242505 | 1172510 | 767532 |  |  | 2026-05-24 | 2026-05-25 12:15 | 2026-05-29 | 2026-05-29 18:51 | 2026-06-01 |  | 2026-06-08 |  | 2026-06-15 |  | 2026-06-22 |  | 2026-06-01 |  | 2026-06-02 |  | 2026-06-02 |  | 2026-06-03 | [5 empty] | 2026-06-09 |  | 2026-06-17 |  | 2026-06-18 |  |  |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 | [6 empty] | 2026-07-16 |  | 2026-07-25 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-28 |  |  |  | 2026-08-19 |  | 2026-08-21 |  | 2026-08-22 | [5 empty] | 2026-06-26 |  | 2026-06-04 |  | Unknown | 2026-05-24 | 2026-05-24 23:13 | 2055129 | 369923 | 0 | 0 | 0 | 0 | 2055129 | 369923 | 2026-06-09 11:31:22 +0530 | Rituparna Chakraborty | Some Image was uploaded | 2026-05-29 18:52:23 +0530 | Rituparna Chakraborty | Minutes of Meeting held on Date: 17.05.2026 Attendees: Client & Rituparna Discussion: RGM discussion Living - 6 seater sofa seating with molding design on sofa back TV unit as per the design shared 6Seater dining - dining wall same concept as shared Puja - seating puja unit , with designer door One basin unit is there in front of the kitchen Kitchen - full modular kitchen , utility sectio also has storage MBR & PBR - King size bed , wingline wardrobe , loft , TV unit in PBR . European design GBR- wardrobe + Loft , Study , simple bedback Toilet - vanity units in all the toilet & shower partition Theywant budget including loosse furniture as well european + Contemporary designs CDP on 29th May , time to be confirmed . Budget - 15-18L including all | 2026-05-24 23:13:30 +0530 | Unknown | About the Customer **3BHK RR Nagar Property Details** Customer requires interiors for a 3BHK in RR Nagar, with handover in 15-20 days. Property is with Navami Builders. **Weekend Visit Planned** Customer plans to visit the experience center on the weekend, not available today. **Anniversary Month Offer** Bonito Designs is offering an 18% GST waiver. **Appointment Time Confirmation Pending** Customer needs to confirm appointment time for tomorrow's HRBR experience center visit by 6 PM today. **Agent to Confirm Weekend Appointment** Agent to call back Friday evening to confirm weekend appointment and share experience center details via WhatsApp. | 2026-06-09 |  | 2026-06-16
20231 | Turnkey | May'26 | RAMKUMAR VAISHYA | Integrated | MUM - GOR | Yes | Riddhi Deshpande | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 800438 | 80000 | 800438 | 0 | 0 | 39 | 0 | 0 | 80088 | 366117 | 274233.2 |  |  | 2026-05-17 | 2026-06-03 18:49 | 2026-06-03 | 2026-06-03 19:28 | 2026-06-06 | 2026-06-04 13:39 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-06-04 | 2026-05-31 | 2026-06-05 | 2026-06-04 17:12 | 2026-06-04 | 2026-06-06 17:46 | 2026-06-11 | 2026-06-11 18:13 |  |  |  |  | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-12 |  | Unknown | 2026-05-17 | 2026-06-03 18:35 | 993343.0404 | 152628 | 0 | 0 | 0 | 0 | 993343.0404 | 152628 | 2026-07-10 15:40:32 +0530 | Vishakha Vaishnav | TRIED CONNECTING WITH CX MULTIPLE TIME FOR MEETING ALIGNMENT HOWEVER NO PROPER RESPONSE FROM CX | 2026-06-18 14:50:23 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-12 13:21:50 +0530 | Riddhi Deshpande | DDM1: meeting scheduled on 25th june | 2026-06-17 |  | 2026-06-24 |  | Under Construction | 2026-09-01
20232 | Turnkey | May'26 | Sylvester Dsouza | citadel Bungalow | MUM - Thane | Yes | Amisha Ahuja | Anamika Dolai | Rachna Abhyankar | [5 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 1165511 | 9999 | 0 | 0 | 0 | 49 | 0 | 106552 | 116551 | 549652 | 382757.2 |  |  | 2026-05-25 | 2026-05-27 13:07 | 2026-05-26 |  | 2026-05-31 |  | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-05-31 |  | 2026-06-01 |  | 2026-06-01 |  | 2026-06-02 | [5 empty] | 2026-06-08 |  | 2026-06-16 |  | 2026-06-17 |  |  |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 | [6 empty] | 2026-07-15 |  | 2026-07-24 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-27 |  |  |  | 2026-08-18 |  | 2026-08-20 |  | 2026-08-21 | [5 empty] | 2026-06-25 |  | 2026-06-03 |  | Unknown | 2026-05-25 | 2026-05-27 13:06 | 0 | 0 | 0 | 0 | 0 | 0 | 987721 | 177789 | 2026-06-04 11:49:47 +0530 | Amisha Ahuja | Kitchen Requirements Layout & Structure Fully modular kitchen. Consider a kitchen island as an optional feature. Explore an option of closing one window and utilizing that wall for additional loft and wall-mounted storage units. Appliances Dishwasher: decision to be taken later. Under-sink water purifier (Aquaguard): can be considered later. Dedicated service counter for small appliances and daily-use equipment. Storage Requirements Space for a deep freezer. Large crockery storage unit. Separate glassware/crockery display unit. Ample storage for pulses, grains, and dry groceries. Loft storage units for infrequently used items. Functional Areas Service counter with provision for: Mixer/grinder Microwave Coffee machine (if required) Other countertop appliances Additional Considerations Evaluate island vs. additional wall storage based on available space. Assess whether closing the window would improve storage capacity without compromising ventilation and natural light. Key Priorities Fully modular design. Maximum storage (pulses, groceries, crockery, deep freezer). Dedicated appliance/service counter. Optional island. Optional under-sink Aquaguard. Dishwasher provision for future installation. | 2026-05-25 17:33:24 +0530 | Unknown | About the Customer **Wants to visit Thane experience center tomorrow** Customer wants to visit the Thane experience center tomorrow to discuss interior design for their existing 4 BHK bungalow where some work has already started. **Concerned about monsoon delays and wants to expedite** Customer is concerned about monsoon delays impacting ongoing work and wants to expedite the interior design process. **Agent to share address and arrange designers** Agent will forward the Thane experience center address via WhatsApp and arrange for designers upon confirmation of visit time. **Customer to confirm visit time tomorrow** Customer will confirm their visit time tomorrow morning after receiving the address. |  |  |  | 2026-06-08 |  | 2026-06-15
20234 | Turnkey | May'26 | Bharat S. Dubhele | L&T 77 crossword | MUM - GOR | Yes | Sonal Singh | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Harshaan Tiku |  | Hold | Preproduction | Site Readiness 1 | 839978 | 167996 | 1115346 | 0 | 0 | 12 | 12 | 0 | 0 | 339473 | 332508.8 |  |  | 2026-05-25 | 2026-05-25 20:22 | 2026-05-26 | 2026-05-28 17:33 | 2026-05-31 | 2026-05-30 23:21 | 2026-06-21 | 2026-06-21 20:05 | 2026-08-15 |  | 2026-08-22 |  | 2026-05-30 | 2026-05-31 | 2026-05-31 | 2026-06-03 16:47 | 2026-06-03 | 2026-06-06 15:15 | 2026-06-13 | 2026-06-13 11:20 |  |  |  |  | 2026-06-26 | 2026-06-21 19:49 | 2026-08-17 |  | 2026-08-18 |  |  |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 | [6 empty] | 2026-09-15 |  | 2026-09-24 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-27 |  |  |  | 2026-10-19 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | 2026-08-26 |  | 2026-06-14 | 2026-06-21 19:49 | Site is Non-RTMI | 2026-05-25 | 2026-05-25 20:22 | 945208 | 170137 | 0 | 0 | 0 | 0 | 945207.836 | 151196 | 2026-07-03 10:57:34 +0530 | Vishakha Vaishnav | Others: Cx has not yet received the possession | 2026-06-18 14:52:06 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-13 11:19:00 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - cx is available for the meeting on 20th June DEM 2 - TBD DEM 3 - TBD Possession date : September 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-22 | 2026-06-21 20:10 | 2026-08-16 |  | Under Construction | 2026-09-01
20240 | Turnkey | May'26 | Amar Ananda Kasurde | Vivanta kalpatru | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | DCM Due | 2604791 | 9999 | 0 | 0 | 0 | 36 | 0 | 250480 | 260479 | 1113585 | 970247.6 |  |  | 2026-05-24 | 2026-06-09 12:51 | 2026-05-25 |  | 2026-05-29 |  | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-05-29 |  | 2026-05-30 |  | 2026-05-30 |  | 2026-05-31 | [5 empty] | 2026-06-06 |  | 2026-06-14 |  | 2026-06-15 |  |  |  | 2026-06-22 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-25 | [6 empty] | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-06-23 |  | 2026-06-01 |  | Unknown | 2026-05-24 | 2026-06-09 12:49 | 0 | 0 | 0 | 0 | 0 | 0 | 2207450 | 397341 | [9 empty] | 2026-06-06 |  | 2026-06-13
20241 | Turnkey | May'26 | Avinash Ingole | Prescon Midtown Bay | MUM - GOR | Yes | Zoya Ansari | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 2388858 | 477772 | 3204255 | 0 | 0 | 20 | 0 | 0 | 0 | 996823 | 914263.2 |  |  | 2026-05-26 | 2026-06-04 19:10 | 2026-05-26 | 2026-06-05 11:17 | 2026-06-08 | 2026-06-06 16:08 | 2026-06-26 | 2026-06-25 12:43 | 2026-07-01 |  | 2026-07-08 |  | 2026-06-08 | 2026-06-06 13:14 | 2026-06-09 | 2026-06-06 16:06 | 2026-06-07 | 2026-06-10 20:01 | 2026-06-16 | 2026-06-16 18:12 |  |  |  |  | 2026-06-25 | 2026-06-25 18:08 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-17 | 2026-06-25 12:17 | Site is RTMI | 2026-05-26 | 2026-05-26 13:57 | 2715471 | 488784 | 0 | 0 | 0 | 0 | 2699567.182 | 438544 | 2026-06-18 14:54:02 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-16 18:11:08 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : need to be scheduled asap DEM Dates -Â DEM 1 - cx is available for the meeting by 20th June by 2:30 - 3pm DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-10 20:01:24 +0530 | Athul Ajaykumar |  | 2026-06-26 | 2026-06-25 12:44 | 2026-07-02 |  | RTMI |  | 2026-06-04 | 477772 | Ravi Roy
20242 | Sub Project |  | Anushree Gupta Kesari | Mahavir Spring | MUM - Thane |  | Nazneen Chovvakkaran | Anamika Dolai | Anil Kuwar |  |  | Faraz Soudagar | Aditya Vikram | Murali S |  |  | Completed | Complete | Completed | -1898 | 0 | -1898 | 0 | -1898 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-26 | 2026-05-29 11:23 | 2026-05-27 | 2026-05-29 11:24 | 2026-05-29 | 2026-05-29 11:24 | 2026-05-30 | 2026-05-29 11:25 | 2026-05-30 | 2026-05-29 11:27 | 2026-05-30 | 2026-05-29 11:28 | 2026-05-29 | 2026-05-29 11:24 | 2026-05-30 | 2026-05-29 11:24 | 2026-05-29 | 2026-05-29 11:24 | 2026-05-30 | 2026-05-29 11:25 |  |  |  |  | 2026-05-29 | 2026-05-29 11:26 | 2026-05-30 | 2026-05-29 11:27 | 2026-05-30 | 2026-05-29 11:27 |  |  | 2026-05-30 | 2026-05-29 11:29 | 2026-05-30 | 2026-05-29 12:36 | 2026-05-30 | 2026-05-29 14:58 | 2026-05-31 | 2026-05-29 14:42 |  |  |  |  | 2026-06-04 10:50 | 2026-06-06 | 2026-06-05 21:32 | 2026-06-08 | 2026-06-06 11:01 | 2026-06-07 | 2026-06-26 18:55 | 2026-06-06 | 2026-06-26 19:06 | 2026-06-26 | 2026-06-26 19:07 | 2026-06-21 | 2026-06-26 18:39 |  |  | 2026-06-28 | 2026-06-26 19:15 | 2026-06-28 | 2026-06-26 19:16 | 2026-06-26 | 2026-06-26 19:55 |  |  |  |  | 2026-05-29 | 2026-06-03 14:12 | 2026-05-30 | 2026-05-29 11:25 | Unknown | 2026-05-26 | 2026-05-29 11:23 | 32289 | 5812 | 0 | 0 | 32289 | 5812 | 32289 | 5812 | [9 empty] | 2026-05-30 | 2026-05-29 11:25 | 2026-05-30 | 2026-05-29 11:27
20243 | Turnkey | May'26 | Vinodini Kallarakal | poddar harmani | MUM - GOR | Yes | [8 empty] | Avi Thakkar |  | Active | Prospect | Onboarding Due | 913058 | 123572 | 1235718 | 0 | 0 | 1 | 0 | 0 | 59040 | 430384 | 300062 |  |  | 2026-05-24 | 2026-07-14 14:04 | 2026-07-14 | 2026-07-14 14:08 | 2026-07-17 | 2026-07-14 15:08 | 2026-07-21 |  | 2026-07-28 |  | 2026-08-04 |  | 2026-07-12 | 2026-07-12 16:53 | 2026-07-13 | 2026-07-14 14:05 | 2026-07-15 |  | 2026-07-16 | [5 empty] | 2026-07-22 |  | 2026-07-30 |  | 2026-07-31 |  |  |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 | [6 empty] | 2026-08-28 |  | 2026-09-06 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-09 |  |  |  | 2026-10-01 |  | 2026-10-03 |  | 2026-10-04 | [5 empty] | 2026-08-08 |  | 2026-07-17 |  | Unknown | 2026-05-24 | 2026-05-29 11:24 | 1047219 | 188499 | 0 | 0 | 0 | 0 | 1047218.2943 | 172900 | 2026-07-14 15:48:46 +0530 | Sanjana Swami | Possession Status: Under construction Under construction Completion Date: December 2026 (soft possession) Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible. * DEM 1 â€“ 24th July 2026 * 10% Payment Stage â€“ 24th July 2026 Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) Free Hob & Chimney Offer Free Shoerack Offer Design fee waiver (5%) May'26 100% GST waiver Final Closing Value Discussed: â‚¹ 9,13,058 Checklist terms - descoping, delay compensation, agreement terms are clear Rejection: Client will be getting the soft possession by December 2026, approval for extended price protection is required. Address is not updated. | 2026-07-14 14:39:55 +0530 | Avi Thakkar | Onboarding Due: | 2026-07-14 14:28:42 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-22 |  | 2026-07-29
20245 | Turnkey | May'26 | A V Logistics Express LLP | MICL Aaradhya Parkwood | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Shreyash Kotecha |  | Active | Preproduction | DEM2 | 1249364 | 218999 | 1367618 | 0 | 0 | 4 | 0 | 0 | 0 | 587525 | 442840 |  |  | 2026-05-26 | 2026-05-27 13:25 | 2026-05-26 | 2026-05-27 18:12 | 2026-06-07 | 2026-06-07 11:11 | 2026-07-11 | 2026-07-11 19:58 | 2026-07-17 |  | 2026-07-26 |  | 2026-06-07 | 2026-06-13 17:10 | 2026-06-08 | 2026-06-14 13:12 | 2026-06-14 | 2026-06-15 15:56 | 2026-06-25 | 2026-06-25 20:28 |  |  |  |  | 2026-06-22 | 2026-06-25 18:21 | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-06-26 | 2026-07-11 19:20 | Site is RTMI | 2026-05-26 | 2026-05-27 12:47 | 1160550 | 207067 | 0 | 0 | 0 | 0 | 1324157.5813 | 233435 | 2026-06-26 12:27:37 +0530 | Sakshi Pokharkar | DEM 1 Meeting planned on 29th June. | 2026-06-17 16:58:18 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-15 15:55:47 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: Mid July Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Will update to the sales team * DEM 1 Tentatively scheduled for (24th June 2026) * 20% closed * B2B * Civil work - NO Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (2.5%) Free Shoerack Offer 100% GST Waiver Final Closing Value Discussed: 10,89,037 Checklist terms descoping and agreement terms are cleared Client VOC: The client mentioned that the actual site is currently not accessible. However, for IM purposes, measurements can be taken from the sample flat, as it has the same carpet area and layout as the client's unit. | 2026-07-12 | 2026-07-11 20:23 | 2026-07-18 |  | Under Construction | 2026-07-31 | 2026-06-13 | 136762 | Ravi Roy
20247 | Sub Project |  | Mr.Amitabh Mishra | Adarsh Park height | BNG - HRBR |  | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran |  |  | Suchendra Shetty | Jairam Joshi | Murali S |  |  | Active | Production | Dispatch Due | 25967 | 25968 | 0 | 0 | 25967 | 39 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-26 | 2026-05-27 10:54 | 2026-05-27 | 2026-05-27 10:54 | 2026-05-27 | 2026-05-27 10:55 | 2026-05-28 | 2026-05-27 10:56 | 2026-05-28 | 2026-05-27 11:38 | 2026-05-28 | 2026-05-27 11:43 | 2026-05-27 | 2026-05-27 10:55 | 2026-05-28 | 2026-05-27 10:55 | 2026-05-27 | 2026-05-27 10:55 | 2026-05-28 | 2026-05-27 10:55 |  |  |  |  | 2026-05-27 | 2026-05-27 10:56 | 2026-05-28 | 2026-05-27 11:38 | 2026-05-28 | 2026-05-27 11:40 |  |  | 2026-05-28 | 2026-05-27 11:44 | 2026-05-28 | 2026-05-27 12:16 | 2026-05-28 | 2026-06-02 12:06 | 2026-05-29 | 2026-05-29 18:48 |  |  |  |  | 2026-06-02 12:09 | 2026-06-06 | 2026-06-05 21:26 | 2026-06-08 | 2026-06-06 10:47 | 2026-06-24 | 2026-05-29 18:48 | 2026-06-06 |  | 2026-06-19 |  | 2026-06-21 |  |  |  | 2026-06-28 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-05-27 | 2026-06-02 12:06 | 2026-05-28 | 2026-05-27 10:55 | Unknown | 2026-05-26 | 2026-05-27 10:54 | 0 | 0 | 0 | 0 | 22006 | 3961 | 22006 | 3961 | [9 empty] | 2026-05-28 | 2026-05-27 10:56 | 2026-05-28 | 2026-05-27 11:38
20250 | Turnkey | May'26 | chaluvaraj | Birla Tissya | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | DEM1 | 998265 | 210999 | 1246863 | 0 | 0 | 27 | 0 | 0 | 0 | 445863 | 341403.2 |  |  | 2026-05-27 | 2026-06-04 13:03 | 2026-05-27 | 2026-06-04 13:10 | 2026-06-04 | 2026-06-04 13:19 | 2026-09-27 |  | 2026-10-04 |  | 2026-10-11 |  | 2026-06-04 | 2026-06-18 12:36 | 2026-06-05 | 2026-06-18 12:37 | 2026-06-18 | 2026-06-18 18:54 | 2026-06-28 | 2026-06-28 17:05 |  |  |  |  | 2026-06-12 | 2026-06-18 12:36 | 2026-10-06 |  | 2026-10-07 |  |  |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 | [6 empty] | 2026-11-04 |  | 2026-11-13 |  | 2026-11-12 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-16 |  |  |  | 2026-12-08 |  | 2026-12-10 |  | 2026-12-11 | [5 empty] | 2026-10-15 |  | 2026-06-29 |  | Unknown | 2026-05-27 | 2026-05-27 13:57 | 1056663 | 190199 | 0 | 0 | 0 | 0 | 1032436.2377 | 179687 | 2026-07-14 22:37:43 +0530 | Rajeshwari S | 10% payment done. Client dont have permission for IM. He wants to start design phase after IM | 2026-06-28 17:03:22 +0530 | Rajeshwari S | Welcome call done Under construction project Possession expected in spet. or max by oct. No permission for initial measurement Builder has confirmed that we can take IM on 10th Sept. Shivani to schedule the Initial measurement on 10th spet. and confirm to client. Project will go on hold till September 10th. as client wants to start with design meeting only after initial measurement. Estimation finalized for Rs.9,98,265/- 20% paid. | 2026-06-18 18:53:57 +0530 | Athul Ajaykumar |  | 2026-09-28 |  | 2026-10-05 |  | Under Construction | 2026-09-30 | 2026-06-04 | 210999 | Ravi Roy
20252 | Turnkey | May'26 | TRIAXIS INFRA PROJECTS | Madhura Gardens | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 3265226 | 487347 | 4873472 | 0 | 0 | 21 | 0 | 0 | 165698 | 1390127 | 1222054 |  |  | 2026-05-27 | 2026-05-29 15:10 | 2026-05-27 | 2026-06-04 12:51 | 2026-06-08 | 2026-06-10 12:40 | 2026-07-24 |  | 2026-12-15 |  | 2026-12-22 |  | 2026-06-10 | 2026-06-12 10:57 | 2026-06-11 | 2026-06-14 13:08 | 2026-06-14 | 2026-06-24 13:12 | 2026-06-30 | 2026-07-04 19:02 |  |  |  |  | 2026-07-25 |  | 2026-12-17 |  | 2026-12-18 |  |  |  | 2026-12-25 |  | 2026-12-26 |  | 2026-12-27 |  | 2026-12-28 | [6 empty] | 2027-01-15 |  | 2027-01-24 |  | 2027-01-23 |  | 2027-01-24 |  | 2027-01-25 |  | 2027-01-27 |  |  |  | 2027-02-18 |  | 2027-02-20 |  | 2027-02-21 | [5 empty] | 2026-12-26 |  | 2026-07-20 |  | Unknown | 2026-05-27 | 2026-05-28 18:42 | 4130061 | 743411 | 0 | 0 | 0 | 0 | 4130061 | 743411 | 2026-06-24 13:12:05 +0530 | Athul Ajaykumar |  | 2026-06-24 12:09:38 +0530 | Chanakya Panigrahi | Some Image was uploaded | 2026-06-15 17:33:08 +0530 | Bency Chacko |  | 2026-07-25 |  | 2026-12-16 |  | Under Construction | 2026-12-31 | 2026-06-08 | 487347 | Ravi Roy
20253 | Turnkey | May'26 | kalyank B | 2bhk independent house | BNG - HSR | No Estimate | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-27 | 2026-05-27 16:15 | 2026-06-19 | 2026-07-03 10:36 | 2026-05-30 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-07-27 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-07 |  | 2026-07-08 | [5 empty] | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-07-09 |  | Unknown | 2026-05-27 | 2026-05-27 16:14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-07-14 |  | 2026-07-21
20256 | Sub Project |  | Rising Star (Nasir Ismail Khan) | Auris Serenity | MUM - GOR |  | Rajnish Mishra | Reshma Melanta | Safalta Karkera |  |  | Shashwat Joshi | Rizwan Mistry | Murali S |  |  | Active | Preproduction | Site Readiness 2 | 201663 | 0 | 0 | 0 | 201663 | 37 | 0 | 0 | 0 | 0 | 201663 |  |  | 2026-05-27 | 2026-06-04 12:38 | 2026-05-28 | 2026-06-04 12:38 | 2026-06-04 | 2026-06-04 12:38 | 2026-06-05 | 2026-06-04 12:48 | 2026-06-05 | 2026-06-04 12:49 | 2026-06-05 | 2026-06-04 12:51 | 2026-05-31 | 2026-05-27 17:59 | 2026-06-05 | 2026-06-04 12:38 | 2026-06-04 | 2026-06-04 12:38 | 2026-06-05 | 2026-06-04 12:38 |  |  |  |  | 2026-06-08 | 2026-05-27 18:00 | 2026-06-05 | 2026-06-04 12:50 | 2026-06-05 | 2026-06-04 12:50 |  |  | 2026-06-05 | 2026-06-04 12:51 | 2026-06-05 | 2026-06-04 19:39 | 2026-06-05 | 2026-06-08 10:26 | 2026-06-27 | 2026-05-27 18:00 | [5 empty] | 2026-06-27 |  | 2026-07-06 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-09 |  |  |  | 2026-07-31 |  | 2026-08-02 |  | 2026-08-03 | [5 empty] | 2026-06-04 |  | 2026-06-05 | 2026-06-04 12:38 | Unknown | 2026-05-27 | 2026-06-04 12:37 | 0 | 0 | 0 | 0 | 170901 | 30762 | 170901 | 30762 | [9 empty] | 2026-06-05 | 2026-06-04 12:48 | 2026-06-05 | 2026-06-04 12:49
20261 | Turnkey | May'26 | Ryan Ferrao | MICL Aaradhya Parkwood | MUM - GOR | Yes | Riddhi Deshpande | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Hold | Preproduction | DEM2 | 1577537 | 315507 | 1834755 | 0 | 0 | 0 | 29 | 0 | 0 | 703256 | 558774.4 |  |  | 2026-05-27 | 2026-05-31 00:25 | 2026-05-24 | 2026-05-31 21:06 | 2026-06-03 | 2026-05-31 22:16 | 2026-06-14 | 2026-06-14 19:07 | 2026-09-01 |  | 2026-09-08 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-03 13:18 | 2026-06-03 | 2026-06-05 18:27 | 2026-06-13 | 2026-06-13 16:31 |  |  |  |  | 2026-06-14 | 2026-06-30 14:51 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-06-14 | 2026-06-14 11:36 | Site is RTMI | 2026-05-27 | 2026-05-29 22:36 | 1554877 | 279877 | 0 | 0 | 0 | 0 | 1554877.2803 | 274089 | 2026-07-02 11:19:20 +0530 | Vishakha Vaishnav | Others: As cx stays in USA and he has not yet received the possession , cx will be visiting in month of august for further meeting | 2026-06-16 14:34:44 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-13 17:03:41 +0530 | Vishakha Vaishnav | "Welcome call done". Initial measurement : site is not accessible DEM Dates -Â DEM 1 - Done on 13th May DEM 2 - TBD DEM 3 - TBD Possession date : August 1st week as per Customer he will make 10% on 26-27th june need to connect again for same Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-15 | 2026-06-14 19:09 | 2026-09-02 |  | Under Construction | 2026-06-30
20263 | Turnkey | May'26 | Parvathy P | United Dream City | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Mohammed Rasick |  | Active | Preproduction | DEM2 | 1859606 | 371921 | 2563482 | 0 | 0 | 15 | 0 | 0 | 0 | 776352 | 711332.8 |  |  | 2026-05-27 | 2026-06-01 16:52 | 2026-06-02 | 2026-06-02 15:31 | 2026-06-02 | 2026-06-02 16:32 | 2026-06-20 | 2026-06-20 18:38 | 2026-08-11 |  | 2026-08-18 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-02 19:22 | 2026-06-02 | 2026-06-06 14:07 | 2026-06-09 | 2026-06-09 18:54 |  |  |  |  | 2026-06-20 | 2026-06-30 14:20 | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-07-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-06-10 | 2026-06-20 18:33 | Site is RTMI | 2026-05-27 | 2026-05-30 13:45 | 2172443 | 391039 | 0 | 0 | 0 | 0 | 2100782.881 | 346879 | 2026-07-14 16:05:11 +0530 | Losii Athisa |  | 2026-06-24 12:23:47 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-09 18:57:18 +0530 | Rajeshwari S | Welcome call done along with designer IM to be planned before 13th and start with the design phase. will pay 10% after 1st DM as he needs to see some progress before making the payment. Informed the process. Estimation closed value. Aligned with payment and timeline. | 2026-06-21 | 2026-06-20 18:40 | 2026-08-12 |  | RTMI
20270 | Turnkey | May'26 | Apoorv Jain | SBR Earth & Sky | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Preproduction | Site Readiness 1 | 1772741 | 232250 | 1516628 | 0 | 0 | 15 | 0 | 0 | 0 | 895725 | 644766 |  |  | 2026-05-28 | 2026-05-31 12:23 | 2026-05-28 | 2026-06-02 11:28 | 2026-06-05 | 2026-06-02 16:43 | 2026-06-21 | 2026-06-21 18:17 | 2026-08-25 |  | 2026-09-01 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-06 21:04 | 2026-06-06 | 2026-06-10 20:40 | 2026-06-13 | 2026-06-13 11:20 |  |  |  |  | 2026-06-21 | 2026-06-30 14:50 | 2026-08-27 |  | 2026-08-28 |  |  |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 | [6 empty] | 2026-09-25 |  | 2026-10-04 |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-07 |  |  |  | 2026-10-29 |  | 2026-10-31 |  | 2026-11-01 | [5 empty] | 2026-09-05 |  | 2026-06-14 | 2026-06-21 13:39 | Site is Non-RTMI | 2026-05-28 | 2026-05-31 12:22 | 1285278 | 231350 | 0 | 0 | 0 | 0 | 1932572.724 | 319093 | 2026-06-24 12:30:55 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-16 14:15:12 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-14 17:33:18 +0530 | Rajeshwari S | Welcome call done along with Vishnu NON RTMI project Estimation was finalized for Rs.11,61,249/- after all the offers IM can be arranged in next 10 days. Vishnu to call client and schedule the IM in the next week Informed about 10% payment Client wants to make the 10% payment only after layout finalization. aligned for other payment process and timeline. | 2026-06-22 | 2026-06-21 18:21 | 2026-08-26 |  | Under Construction | 2026-09-30
20271 | Turnkey | May'26 | Kush Karia | Daivi Eterneety | MUM - GOR | Yes | Karan Chavda | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Design | DEM1 | 1763049 | 228553 | 2285531 | 0 | 0 | 40 | 0 | 0 | 124057 | 706961 | 703478.4 |  |  | 2026-05-28 | 2026-05-31 17:50 | 2026-05-31 | 2026-05-31 20:51 | 2026-05-31 | 2026-05-31 22:07 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-01 16:26 | 2026-06-01 | 2026-06-05 16:09 | 2026-06-14 | 2026-06-14 19:05 |  |  |  |  | 2026-06-20 |  | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-06-15 |  | Unknown | 2026-05-28 | 2026-05-28 16:40 | 1936891 | 348640 | 0 | 0 | 0 | 0 | 1932889.7163 | 317348 | 2026-07-10 15:35:37 +0530 | Vishakha Vaishnav | TREID CONNECTIN MULTIPLE TIME WITH CX FOR MEETING ALIGNMENT HOWEVER NO RESPONSE FRO CX END , HAVE MESSAGED HIM ON WHATSAPP AS WELL | 2026-06-17 12:02:06 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Site is not accessible DEM Dates -Â DEM 1 - Cx will inform us for next week availability , cx wants the meeting on week days DEM 2 - TBD DEM 3 - TBD Possession date : April 2027 Customer will make 10% onÂ after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-14 19:08:41 +0530 | Vishakha Vaishnav | Cx said he is busy will be able to connect tomorrow morning | 2026-06-20 |  | 2026-06-27 |  | Under Construction | 2027-04-30
20272 | Turnkey | May'26 | Madhu Kankanala | Pavani Mirabilia | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal |  |  | Deekshith P | Jairam Joshi |  | Raghavendra S | Abdul Shafeen | Active | Design | DEM3 | 1218580 | 246499 | 1582255 | 0 | 0 | 1 | 0 | 0 | 0 | 504451 | 467630 |  |  | 2026-05-28 | 2026-05-28 17:15 | 2026-05-28 | 2026-06-04 13:42 | 2026-06-07 | 2026-06-10 12:51 | 2026-06-17 | 2026-06-19 06:31 | 2026-07-08 | 2026-07-07 12:10 | 2026-07-18 |  | 2026-06-10 | 2026-06-10 18:42 | 2026-06-11 | 2026-06-10 19:24 | 2026-06-10 | 2026-06-11 12:26 | 2026-06-12 | 2026-06-12 14:58 |  |  |  |  | 2026-06-18 | 2026-06-10 18:42 | 2026-07-12 | 2026-07-14 11:19 | 2026-07-15 | 2026-07-14 11:47 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-13 | 2026-06-17 18:33 | Site is RTMI | 2026-05-28 | 2026-05-28 17:14 | 1340894 | 241361 | 0 | 0 | 0 | 0 | 1380180.895 | 227894 | 2026-06-16 16:26:31 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-11 20:04:04 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-11 14:19:52 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-20 | 2026-06-19 06:36 | 2026-07-08 |  | Under Construction | 2026-06-19 | 2026-06-07 | 128247 | Ravi Roy
20273 | Turnkey | May'26 | Sravani | Birla Alokya | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2174595 | 9999 | 0 | 0 | 0 | 31 | 0 | 207461 | 217460 | 910599 | 829077.2 |  |  | 2026-05-28 | 2026-05-29 16:48 | 2026-05-30 | 2026-05-30 15:35 | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-06-21 |  | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-06-16 |  | Unknown | 2026-05-28 | 2026-05-29 16:46 | 0 | 0 | 0 | 0 | 0 | 0 | 2248969.0413 | 391427 | 2026-06-11 14:33:58 +0530 | Alekhya Korada | Some Image was uploaded | 2026-05-30 15:25:41 +0530 | Yogesh Patidar | DCM: Property -Birla Alokya- RTMI 5 including kids and mother Kids age - 9yrs and 3.5yrs Existing furntiure Bed - king size*2 Moving in date - Aug end Look and feel -Functional and minimal Â Work profile -Telecom industry Foyer - Below staircase shoe rack 20- 30pairsÂ Right wall - wallpaper to conceal the DB panel Small wall needs to be highlightedÂ Partition - With ArchÂ in between foyer and Living Focus wall - Mural art With krishna deatils and lightsÂ Â TV Adjacent wall - wallpaperÂ Tv unit - home theaterÂ Play station , 75inch, sound bar 5.1 Below storage and plain wall option Sofa seating 7-8people no false ceilingÂ Wood panellingÂ Crockery unitÂ -Right side of windowsÂ Crockery unit - bottom storage and top unit displayÂ with granite top SinkÂ Invisible door near guest room foyerÂ Pooja unit- facing towards tvÂ Sitting and doing pooja Seating movableÂ Height till lintel Minimal 7 phots fmrans and idolsÂ Lit up designÂ Contemporary pooja Kitchen -Â GraniteÂ Appliances - Breakfast counter With 2 seatingÂ With pendant light Refrigerator 3feet in NicheÂ Microwave - talk unit Wicker basketÂ Base unit , wall unit and loftÂ No glass shutterÂ Hob on opposite wall Hob 4burnersÂ UtilityÂ SinkÂ Washing machine ( front load) Dishwasher provision Maid room Storage - talk unit storage in one wallÂ Guest room ( Pbr ) Wardrobe and loft hinged 6 feet And loft to be extendedÂ Mirror on side of wardrobe Paint options behind bedÂ Staircase - wall deisgnÂ Vanity unit MirrorÂ Mbr - Wardrobe with loft on other wall open / sliding option Working space for single space Existing bed rose wood Mirror and dresser Wooden flooring existingÂ Bathroom - vanity and mirror with storageÂ Kids room both are girls - Shades of Pink Krictika and shanvika Bed newÂ Hydraulic queen size bed StudyÂ for 2 kidsÂ YouTube video for refrenceÂ No ceilingÂ Likes head boardÂ Window seater with storageÂ Wardrobe - hinged/ sliding optionÂ Mirror and dresser Book space with window setaer Budget -25L |  |  |  | 2026-06-21 |  | 2026-06-28
20275 | Turnkey | May'26 | Nilam Sagar Shinde | Haware | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Manasi Patil |  | Active | Preproduction | DEM2 | 958310 | 191662 | 1298385 | 0 | 0 | 24 | 0 | 0 | 0 | 397267 | 369380.8 |  |  | 2026-05-28 | 2026-05-28 19:34 | 2026-05-28 | 2026-05-29 15:32 | 2026-06-01 | 2026-05-31 22:28 | 2026-06-21 | 2026-06-23 14:17 | 2026-06-29 |  | 2026-08-24 |  | 2026-05-30 | 2026-05-30 17:30 | 2026-06-01 | 2026-06-02 12:12 | 2026-06-02 | 2026-06-04 17:07 | 2026-06-05 | 2026-06-05 13:30 |  |  |  |  | 2026-06-11 | 2026-06-21 15:10 | 2026-08-19 |  | 2026-08-20 |  |  |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 | [6 empty] | 2026-09-17 |  | 2026-09-26 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-29 |  |  |  | 2026-10-21 |  | 2026-10-23 |  | 2026-10-24 | [5 empty] | 2026-08-28 |  | 2026-06-06 | 2026-06-21 23:10 | Site is RTMI | 2026-05-28 | 2026-05-28 19:31 | 1102614 | 195771 | 0 | 0 | 0 | 0 | 1101405.5855 | 178346 | 2026-06-05 13:29:58 +0530 | Vishakha Vaishnav | "Welcome call done along with the Designer. Initial measurement : Possession is expected in august & cx will update us once site is available for IM DEM Dates -Â DEM 1 - 13th June 2026 DEM 2 - TBD DEM 3 - TBD Possession date : August 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-04 17:05:17 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: Aug 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Client will check with his builder and then let us know * DEM 1 13th June 2026 * 10% Payment Stage 14th June 2026 (after 1st DEM) *Transaction will be B2C self-funding. *If the builder does not give permission for IMs, then client is ok for the 1st DEM with layouts. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11,01,406 Offers Discussed During the Call: Anniversary '26 Studio Offer: 30,000 Free Hob & Chimney Offer PM fee waiver (5%) 100% GST Waiver Laminate Upgrade - May '26 Campaign Free Shoerack Offer Silver Coin 21g Final Closing Value Discussed: 9,58,311 Checklist terms: descoping, delay compensation, agreement terms are clear | 2026-06-04 14:45:36 +0530 | Manasi Patil | Kindly call to client now Ive asked him for time | 2026-06-24 | 2026-06-23 14:20 | 2026-06-30 |  | Under Construction | 2026-08-31
20276 | Turnkey | May'26 | Vishnu Narayanan | Green View Residency | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Sandeep Madhukar Achari | Sandeep Madhukar Achari |  |  |  | Kushal S |  | Hold | Preproduction | DEM2 | 1055758 | 207494 | 1380313 | 0 | 0 | 18 | 4 | 0 | 0 | 458161 | 390103.2 |  |  | 2026-05-28 | 2026-05-29 12:07 | 2026-05-29 | 2026-05-31 21:06 | 2026-06-03 | 2026-06-02 12:48 | 2026-06-24 | 2026-06-23 11:59 | 2026-09-01 |  | 2026-09-08 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-04 11:54 | 2026-06-04 | 2026-06-06 18:18 | 2026-06-09 | 2026-06-09 19:04 |  |  |  |  | 2026-06-15 | 2026-06-22 19:10 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-06-10 | 2026-06-23 11:06 | Site is RTMI | 2026-05-28 | 2026-05-29 10:49 | 1169757 | 210556 | 0 | 0 | 0 | 0 | 1140651.4857 | 190036 | 2026-06-12 14:36:32 +0530 | Rajeshwari S | Welcome call done along with Sandeep RTMI Project Next weekend IM to be scheduled. - Sandeep to confirm to client on the same. Client will make the 10% payment by 25th June. has some fund issues for the final payment. Will plan the project accordingly. | 2026-06-06 18:18:03 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM 7th June 2026 * DEM 1 Next weekends * 10% Payment Stage 16th June 2026 (after 1st dem) *Transaction will be B2C self funding. *Client has planned civil work which is discussed at the time of CDP Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11,40,652 Offers Discussed During the Call: Free Hob & Chimney Offer May '26 Net Special Studio Offer Design fee waiver (5%) Laminate Upgrade - May '26 Campaign PM Fee Waiver (4%) 100% GST Waiver Final Closing Value Discussed: 10,55,658 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-06 13:14:10 +0530 | Sanjana Swami |  | 2026-06-24 | 2026-06-23 12:03 | 2026-09-02 |  | RTMI
20279 | Turnkey | May'26 | Bechar Patel | Raymond Ten X | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 2575703 | 9999 | 0 | 0 | 0 | 43 | 0 | 247571 | 257570 | 1111981 | 948581.2 |  |  | 2026-05-28 | 2026-06-02 13:04 | 2026-05-30 | 2026-06-02 13:54 | 2026-05-31 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-06-13 |  | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-08 |  | Unknown | 2026-05-28 | 2026-05-28 23:18 | 0 | 0 | 0 | 0 | 0 | 0 | 2182799 | 392903 | 2026-06-02 13:55:03 +0530 | Rinisha Masurkar | Client: Bechar Patel Hi, Project ID: 20279 Bechar Patel POSSESSION: June Carpet Area: 598 Sq. Ft. Family Members: 5 Project Type: 2 BHK Budget: 10 11 Lakhs Design Style: Minimal, light-toned interiors with subtle wooden textures and clean paneling details. General RequirementsNo existing furniture to be retained.Safety door to be provided.Minimal paneling approach throughout the residence.False ceiling required in all rooms with a simple and minimal design language.Overall design to follow a light color palette with warm wooden textures and minimal visual clutter.Living RoomL-shaped sofa seating arrangement.TV unit with display shelving.Mandir to be planned in the living room as per the appropriate direction/Vastu consideration.Minimal wall treatments and storage solutions.KitchenHob to be placed on the same countertop platform.Dedicated appliance storage for:MicrowaveOther small kitchen appliancesEfficient storage planning with a clutter-free appearance.Light-toned finishes with minimal detailing.Common WashroomIndian WC required.Washing machine placement to be explored and finalized.Vanity unit required.Master Bedroom (MBR)Wardrobe with sliding shutters.Dresser unit with mirror and back storage provision.Minimal and functional design approach.Bedroom 2 (B2)Wardrobe with sliding shutters.Foldable study/work desk required.Mirror only (no dresser storage).Window seating to be explored, subject to available space.WashroomsVanity units required in both washrooms.Key Design DirectionModern minimalist aesthetics.Light shades complemented with wooden textures.Avoid heavy decorative elements.Focus on functionality, storage optimization, and clean visual appeal.Explore feasibility of window seating in Bedroom 2.Finalize washing machine location in common washroom.Develop layout options aligned with budget and design brief.CDP Status: TBS | 2026-06-02 13:03:14 +0530 | Aryan Singh | Some Image was uploaded |  |  |  | 2026-06-13 |  | 2026-06-20
20280 | Turnkey | May'26 | aditya mehrotra | Assetz Bloom & Dell | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1990653 | 9999 | 1830312 | 0 | 0 | 38 | 0 | 189066 | 199065 | 805644 | 786878 |  |  | 2026-05-28 | 2026-05-29 12:05 | 2026-06-05 | 2026-06-05 12:13 | 2026-06-08 | 2026-06-09 11:50 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-12 |  | Unknown | 2026-05-28 | 2026-05-29 11:29 | 1551112 | 279200 | 0 | 0 | 0 | 0 | 1686994 | 303658 | 2026-06-16 15:32:34 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-11 15:24:59 +0530 | Palak Thakur | DCM: rgm recording uploaded as zip file in drive | 2026-06-11 15:24:35 +0530 | Palak Thakur | Some Image was uploaded | 2026-06-17 |  | 2026-06-24
20285 | Turnkey | May'26 | Anita Singh | Assetz Marq | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Active | Preproduction | DEM2 | 1532969 | 306594 | 2034958 | 0 | 0 | 18 | 0 | 0 | 0 | 663975 | 562399.6 |  |  | 2026-05-29 | 2026-06-02 19:49 | 2026-06-03 | 2026-06-03 16:18 | 2026-06-06 | 2026-06-03 16:52 | 2026-06-19 | 2026-06-19 20:42 | 2026-08-07 |  | 2026-08-14 |  | 2026-06-03 | 2026-05-31 | 2026-06-04 | 2026-06-04 11:42 | 2026-06-04 | 2026-06-06 13:44 | 2026-06-09 | 2026-06-09 17:48 |  |  |  |  | 2026-06-19 | 2026-06-27 14:16 | 2026-08-09 |  | 2026-08-10 |  |  |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 | [6 empty] | 2026-09-07 |  | 2026-09-16 |  | 2026-07-27 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-19 |  |  |  | 2026-10-11 |  | 2026-10-13 |  | 2026-10-14 | [5 empty] | 2026-08-18 |  | 2026-06-10 | 2026-06-19 20:38 | Site is RTMI | 2026-05-29 | 2026-06-02 18:09 | 1724540 | 310417 | 0 | 0 | 0 | 0 | 1721765.8322 | 284484 | 2026-06-26 12:39:11 +0530 | Yogesh B | Some Image was uploaded | 2026-06-09 17:49:34 +0530 | Parasa Sri | Welcome call done, IM is planned on 11th Design meeting on 14th | 2026-06-09 16:45:11 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-20 | 2026-06-19 20:55 | 2026-08-08 |  | Under Construction | 2026-08-15
20291 | Turnkey | May'26 | Praveen Kumar | BUILDER FLOOR | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Design | DEM1 | 700138 | 95999 | 961635 | 0 | 0 | 34 | 0 | 0 | 44029 | 301852 | 258258.4 |  |  | 2026-05-17 | 2026-06-03 12:01 | 2026-06-04 | 2026-06-04 13:01 | 2026-06-04 | 2026-06-04 16:16 | 2026-07-13 |  | 2026-08-06 |  | 2026-08-13 |  | 2026-06-04 | 2026-06-10 19:19 | 2026-06-05 | 2026-06-10 19:20 | 2026-06-10 | 2026-06-11 12:59 | 2026-06-11 | 2026-06-11 18:33 |  |  |  |  | 2026-07-14 |  | 2026-08-08 |  | 2026-08-09 |  |  |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 | [6 empty] | 2026-09-06 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-18 |  |  |  | 2026-10-10 |  | 2026-10-12 |  | 2026-10-13 | [5 empty] | 2026-08-17 |  | 2026-07-05 |  | Unknown | 2026-05-17 | 2026-06-03 12:00 | 961636 | 173094 | 0 | 0 | 0 | 0 | 815035.774 | 134574 | 2026-06-11 18:32:22 +0530 | Parasa Sri | Welcome call done. Initial measurement can be done on 17th. Weekend meetings are preferred.Designs | 2026-06-11 15:37:55 +0530 | Keerthan M | Some Image was uploaded | 2026-06-11 12:58:25 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: July 2026 Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM Next weekend * DEM 1 in the month of July 2026, as the client is in US. * 10% Payment Stage by 21st June 2026 *No civil work in client's scope of work *Transaction will be B2C Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 8,15,036 Offers Discussed During the Call: Free Shoerack Offer May '26 Net Special Studio Offer Free Hob & Chimney Offer PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Final Closing Value Discussed: 7,00,138 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-14 |  | 2026-08-07 |  | Under Construction | 2026-07-01
20292 | Turnkey | May'26 | Sachin Jayaram Kadam | Canvas | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Hold | Design | DEM1 | 828722 | 165744 | 1087815 | 0 | 0 | 28 | 12 | 0 | 0 | 372939 | 290039.2 |  |  | 2026-05-29 | 2026-06-02 18:44 | 2026-06-02 | 2026-06-02 20:37 | 2026-06-02 | 2026-06-02 20:40 | 2026-10-04 |  | 2026-10-11 |  | 2026-10-18 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-03 16:55 | 2026-06-03 | 2026-06-05 14:48 | 2026-06-11 | 2026-06-11 18:59 |  |  |  |  | 2026-06-17 | 2026-06-21 12:36 | 2026-10-13 |  | 2026-10-14 |  |  |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-23 |  | 2026-10-24 | [6 empty] | 2026-11-11 |  | 2026-11-20 |  | 2026-11-19 |  | 2026-11-20 |  | 2026-11-21 |  | 2026-11-23 |  |  |  | 2026-12-15 |  | 2026-12-17 |  | 2026-12-18 | [5 empty] | 2026-10-22 |  | 2026-09-30 |  | Unknown | 2026-05-29 | 2026-05-30 19:01 | 921877 | 165938 | 0 | 0 | 0 | 0 | 916656.7545 | 149169 | 2026-07-03 11:02:56 +0530 | Vishakha Vaishnav | Others: CX IS NOT AVAILABLE FOR THE MEETING FOR 3MONTHS 10% DUE IS CLEARED | 2026-06-11 18:58:27 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement Site is not accessible DEM Dates -Â DEM 1 - Cx is available for the meeting on 20th june by 2nd half after that need to place the project on hold till cx receives the possession DEM 2 - TBD DEM 3 - TBD Possession date : Jan 2027 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-05 14:48:17 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: December or January Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (20th June 2026) * 10% Payment Stage Tentatively scheduled for (20th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - May '26 Campaign PM fee waiver (5%) 100% GST Waiver Free Hob & Chimney Offer Final Closing Value Discussed: 8,28,722 Checklist terms descoping, agreement terms are cleared or notÂ | 2026-10-05 |  | 2026-10-12 |  | Under Construction | 2027-01-31
20294 | Turnkey | May'26 | Francina | SBR Earth and Sky | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Preproduction | DEM2 | 1956160 | 391232 | 2482837 | 0 | 0 | 13 | 0 | 0 | 0 | 832544 | 732383.6 |  |  | 2026-05-30 | 2026-05-30 11:20 | 2026-05-30 | 2026-06-05 17:47 | 2026-06-08 | 2026-06-07 11:20 | 2026-06-28 | 2026-06-28 18:03 | 2026-09-27 |  | 2026-10-04 |  | 2026-06-07 | 2026-06-11 17:12 | 2026-06-08 | 2026-06-13 11:26 | 2026-06-13 | 2026-06-16 12:51 | 2026-06-17 | 2026-06-17 11:03 |  |  |  |  | 2026-06-28 | 2026-07-02 11:44 | 2026-09-29 |  | 2026-09-30 |  |  |  | 2026-10-07 |  | 2026-10-08 |  | 2026-10-09 |  | 2026-10-10 | [6 empty] | 2026-10-28 |  | 2026-11-06 |  | 2026-11-05 |  | 2026-11-06 |  | 2026-11-07 |  | 2026-11-09 |  |  |  | 2026-12-01 |  | 2026-12-03 |  | 2026-12-04 | [5 empty] | 2026-10-08 |  | 2026-06-18 | 2026-06-28 17:55 | Site is RTMI | 2026-05-30 | 2026-05-30 11:06 | 2104099 | 378737 | 0 | 0 | 0 | 0 | 2040523.9689 | 352108 | 2026-06-16 13:49:24 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-16 10:41:51 +0530 | Kushal S | Adress U0dated and concerns are cleared | 2026-06-13 13:21:38 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99 + 10 business day Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible for measurement * IM Client will check with the developer and then let us know * DEM 1 Client will let us know after the IMs are taken * 10% Payment Stage by 27th June 2026 Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 20,40,525. Offers Discussed During the Call: PM fee waiver (5%) Laminate Upgrade - Windows to Wonderful home 100% GST Waiver Final Closing Value Discussed: 19,56,161. Checklist terms - descoping, delay compensation, agreement terms are clear. Note: Client requires clarification on the designer allocation, as he was committed that a single designer would be assigned throughout the entire project. Address needs to be updated | 2026-06-29 | 2026-06-28 18:03 | 2026-09-28 |  | Under Construction | 2026-09-30 | 2026-06-06 | 248284 | Ravi Roy
20295 | Turnkey | May'26 | Siva Kumar | Sobha manhattan | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik |  |  | Nanda Kumar | Ranjith Kumar |  | Rajoshi Sarkar | Sunil Kumar S M | Active | Design | DEM3 | 824916 | 166863 | 1145459 | 0 | 0 | 1 | 0 | 0 | 0 | 328087 | 329966.4 |  |  | 2026-05-30 | 2026-06-03 15:00 | 2026-05-31 | 2026-06-03 16:30 | 2026-06-11 | 2026-06-11 11:48 | 2026-06-29 | 2026-06-29 11:25 | 2026-07-13 | 2026-07-12 15:25 | 2026-07-18 |  | 2026-06-11 | 2026-06-13 15:36 | 2026-06-12 | 2026-06-16 19:31 | 2026-06-16 | 2026-06-17 16:54 | 2026-06-28 | 2026-06-28 17:44 |  |  |  |  | 2026-06-29 | 2026-06-29 18:50 | 2026-07-13 | 2026-07-14 15:54 | 2026-07-15 | 2026-07-14 16:37 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-29 | 2026-06-28 20:00 | Site is RTMI | 2026-05-30 | 2026-06-03 14:29 | 970728 | 174731 | 0 | 0 | 0 | 0 | 1001472.032 | 157035 | 2026-06-17 16:53:41 +0530 | Athul Ajaykumar | Possession Status: RTMI Â Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend) * DEM 1 Tentatively scheduled for (Next weekend) * 10% Payment Stage will close after finalizing the layout * B2C-Self * Civil work - NO Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Laminate Upgrade - May '26 Campaign Free Shoerack Offer Free Shoerack offer for the customer Free Hob and Chimney Offer Final Closing Value Discussed: 8,34,315 Checklist terms descoping and agreement terms are cleared | 2026-06-17 14:44:20 +0530 | Rajoshi Sarkar | Please arrange the onboarding call at 4:30 pm As mentioned by cx. | 2026-06-17 13:49:13 +0530 | Athul Ajaykumar |  | 2026-06-30 | 2026-06-29 11:30 | 2026-07-13 | 2026-07-12 15:30 | RTMI |  | 2026-06-13 | 117161.65 | Ravi Roy
20296 | Turnkey | May'26 | Nayna Rohit Shah | Dosti mezzo | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Design | 20% Payment | 1324129 | 180205 | 1802043 | 0 | 0 | 10 | 8 | 0 | 84621 | 552151 | 507152.4 |  |  | 2026-05-30 | 2026-06-01 16:13 | 2026-06-02 | 2026-06-02 17:40 | 2026-06-05 | 2026-06-02 19:05 | 2026-06-27 | 2026-06-27 19:40 | 2026-07-08 |  | 2026-07-15 |  | 2026-06-02 | 2026-05-31 | 2026-06-03 | 2026-06-03 19:22 | 2026-06-03 | 2026-06-05 17:33 | 2026-06-12 | 2026-06-12 13:33 |  |  |  |  | 2026-06-27 |  | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-13 | 2026-06-27 19:17 | Site is RTMI | 2026-05-30 | 2026-06-01 16:02 | 1527155 | 274887 | 0 | 0 | 0 | 0 | 1515122.246 | 242790 | 2026-06-30 13:38:00 +0530 | Meet Shah | Some Image was uploaded | 2026-06-12 13:20:51 +0530 | Riddhi Deshpande | DDM1: have asked for transition | 2026-06-11 17:16:53 +0530 | Vishakha Vaishnav | SPOKE TO CX DAUGHTER MILLI (Â 19740 - Milli ShahÂ ) SHE SAID THAT SHE IS COMING FOR THE MEETING ON SATURDAY FOR HER PROJECT AT THAT TIME SHE WILL DISCUSS THINGS | 2026-06-28 | 2026-06-27 19:42 | 2026-07-09 |  | Under Construction | 2026-07-10
20297 | Turnkey | May'26 | Tony Thomas | Ashar Pulse | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Vandana Preet |  | Active | Preproduction | Site Readiness 1 | 1730063 | 355999 | 2220575 | 0 | 0 | 22 | 0 | 0 | 0 | 740018 | 634045.6 |  |  | 2026-05-30 | 2026-05-30 14:17 | 2026-05-30 | 2026-06-03 13:33 | 2026-06-06 | 2026-06-06 21:38 | 2026-06-26 | 2026-06-23 15:44 | 2026-06-29 |  | 2026-07-06 |  | 2026-06-06 | 2026-06-09 12:34 | 2026-06-07 | 2026-06-12 11:55 | 2026-06-12 | 2026-06-12 16:31 | 2026-06-21 | 2026-06-21 19:11 |  |  |  |  | 2026-06-19 | 2026-06-20 18:37 | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-22 | 2026-06-21 19:22 | Site is Non-RTMI | 2026-05-30 | 2026-05-30 13:55 | 1881843 | 338731 | 0 | 0 | 0 | 0 | 1873756.01 | 311411 | 2026-06-27 18:58:05 +0530 | Swami Vadnere | DDM2: Minutes of Meeting (MOM)Client: Tony Thomas Date: 27-06-2026 Living RoomPresent one design option with a mirror and one without a mirror.Add an L-shaped glass display unit near the window wall.Incorporate drawers into the bar unit for additional storage.Kids' RoomMaintain a light and subtle colour palette.Present multiple options for wall colours and wallpapers.Guest RoomShare a few design options for the TV feature wall.Master BedroomDevelop bed-back wall design options using wallpaper with an arch detail.Keep the wardrobe in a solid colour finish.Present new design options for the TV feature wall. | 2026-06-12 16:29:50 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: October 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible. * DEM 1 This weekend (client wont be available next weekend so needs the 1st DEM this weekend only) * 10% Payment Stage already paid 20% *Transaction will be B2C self-funding. *Client mentioned that he will be planning to change the kitchen countertop height, but he needs to check the site and then he will decide Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,73,757 Offers Discussed During the Call: Laminate Upgrade - Windows to Wonderful home Design Fee Waiver (2.5%) Free Sofa Offer 100% GST Waiver PM fee waiver (5%) Silver Coin 21g Final Closing Value Discussed: 17,30,063 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-12 16:22:01 +0530 | Vandana Preet | Some Image was uploaded | 2026-06-24 | 2026-06-23 15:45 | 2026-06-30 |  | Under Construction | 2026-10-01 | 2026-06-06 | 355999 | Ravi Roy
20299 | Turnkey | May'26 | Pragyan sarith | Rohan Ekanta | BNG - HSR | No Estimate | [8 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-30 | 2026-05-30 14:50 | 2026-05-31 |  | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-06-21 |  | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-06-16 |  | Unknown | 2026-05-30 | 2026-05-30 14:49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-11 19:03:27 +0530 | Nidhi Shaw | Rohan Ekanta 2bhk 8-9 lakhs budget She is having her own sister. They will proceed together They are from Odisha | [6 empty] | 2026-06-21 |  | 2026-06-28
20300 | Turnkey | May'26 | Rajendra Mahadev Pareet | gee cee emrald | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 1007623 | 201525 | 1007623 | 0 | 0 | 29 | 0 | 0 | 0 | 403049 | 403049.2 |  |  | 2026-05-30 | 2026-06-02 10:16 | 2026-05-30 | 2026-06-05 14:08 | 2026-06-13 | 2026-06-14 21:17 | 2026-07-12 | 2026-07-12 19:40 | 2026-07-20 |  | 2026-07-27 |  | 2026-06-14 | 2026-06-15 11:14 | 2026-06-15 | 2026-06-15 16:48 | 2026-06-15 | 2026-06-16 12:41 | 2026-06-25 | 2026-06-25 20:19 |  |  |  |  | 2026-07-12 | 2026-07-12 17:29 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-07-10 | 2026-07-12 19:31 | Site is Non-RTMI | 2026-05-30 | 2026-06-02 10:16 | 853918 | 153705 | 0 | 0 | 0 | 0 | 853918 | 153705 | 2026-07-12 19:22:12 +0530 | Monika Pal | Minutes of Meeting held on Date: 12-07-2026 -- Attendees: Discussion: ï»¿ | 2026-07-12 17:32:00 +0530 | Anamika Dolai | Posession - mar'27, DEM 1- 12/07/2026 10%- paid price protection informed., as spoke with ishan price protection extended till mar'26. | 2026-07-12 17:21:12 +0530 | Anamika Dolai | possession- Feb'26. | 2026-07-14 |  | 2026-07-21 |  | Under Construction | 2026-09-30 | 2026-06-13 | 109999 | Ravi Roy
20301 | Turnkey | May'26 | Sabita Kumari Choudhary | gee cee emrald | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Hold | Preproduction | Site Readiness 1 | 1686384 | 337277 | 2081166 | 0 | 0 | 7 | 15 | 0 | 0 | 764128 | 584979.2 |  |  | 2026-05-30 | 2026-06-02 10:12 | 2026-06-02 | 2026-06-02 17:34 | 2026-06-06 | 2026-06-07 11:19 | 2026-06-23 | 2026-06-23 16:29 | 2027-01-04 |  | 2027-01-11 |  | 2026-06-07 | 2026-06-09 12:06 | 2026-06-08 | 2026-06-11 13:11 | 2026-06-11 | 2026-06-13 11:06 | 2026-06-17 | 2026-06-17 16:55 |  |  |  |  | 2026-06-23 | 2026-06-23 16:55 | 2027-01-06 |  | 2027-01-07 |  |  |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 | [6 empty] | 2027-02-04 |  | 2027-02-13 |  | 2027-02-12 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-16 |  |  |  | 2027-03-10 |  | 2027-03-12 |  | 2027-03-13 | [5 empty] | 2027-01-15 |  | 2026-06-18 | 2026-06-23 16:11 | Unknown | 2026-05-30 | 2026-06-02 10:09 | 1765945 | 315220 | 0 | 0 | 0 | 0 | 1765945.6991 | 300899 | 2026-06-30 11:56:55 +0530 | Anil Jagtap | Some Image was uploaded | 2026-06-26 19:31:52 +0530 | Rachna Abhyankar | Some Image was uploaded | 2026-06-25 18:47:23 +0530 | Mehnaz Ashraf | Some Image was uploaded | 2026-06-24 | 2026-06-23 16:31 | 2027-01-05 |  | Under Construction | 2027-03-31 | 2026-06-06 | 337277 | Ravi Roy
20302 | Turnkey | May'26 | Utkarsh Rathii | Ruchira Park East | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 2205974 | 9999 | 0 | 0 | 0 | 40 | 0 | 210598 | 220597 | 903859 | 860920 |  |  | 2026-05-30 | 2026-05-30 19:48 | 2026-05-30 | 2026-06-05 05:07 | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-06-13 |  | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-08 |  | Unknown | 2026-05-30 | 2026-05-30 16:47 | 0 | 0 | 0 | 0 | 0 | 0 | 1869470 | 336504 | 2026-06-06 10:46:46 +0530 | Saranya Thiyagarajan | CDP: Pooja unit- instead ofÂ 2 full ledges remove one and one reduce width and 3 small ledges on both sides Add cnc pattern for pooja glass door kitchen- Corner- blind corner- add magic pullout Entry wall- Add texture wallpaper with Mirror kitchen- Breakfast counter needs to check as per site window heightÂ add WPC rafters for breakfst counter bottom- and ledges on top. kids room- no bay window and above study- add fluted panel for above ledges Add tall unit cum study type | 2026-06-05 05:07:04 +0530 | Saranya Thiyagarajan | DCM: Client: Rahul Mishra Project: Infinity Green Woods, Varthur Facing: East Facing Family Members: 3 Members Budget: 15 Lakhs 1. Foyer3-shutter shoe rack required.Seating integrated with shoe rack.Opposite side to have a sleek glass partition for visual separation.Design to be minimal and elegant.2. Living RoomLayout RevisionTV unit and sofa positions to be swapped from existing layout.TV Unit + Pooja UnitFloating TV unit.Integrated Pooja unit extending from floor level.Glass shutters for pooja enclosure.3 storage drawers for pooja.Display ledges integrated with pooja unit.Storage provision for:PS5SpeakersSeating Arrangement3-seater sofa.2-seater bench seating.1 recliner chair/ accent chair.Sofa Back WallBeading design - Unique.Charging ledge behind sofa for phones and gadgets.3. Dining AreaDining6-seater dining setup.Bench seating on one side.Crockery UnitShift crockery unit to window wall.Crockery cum bar unit.Display-focused design with premium and eye-catching aesthetics.Combination of closed storage and open display shelves.4. KitchenAppliances & StorageDouble-door refrigerator.Tall unit with dedicated OTG space.Loft storage on one side.Utility AreaOverhead storage above washing machine.Sink storage cabinet.5. Master Bedroom (MBR)BedKing-size bed.Two side tables.Bed Back WallFeature bed-back design to be designed.Wardrobe & DressingWalk-in wardrobe.Dresser positioned between bed and wardrobe/walk-in zone.6. Bedroom 2 Kid's RoomEntertainment & StorageTV unit provision.Wardrobe as per layout.Display AreaGlass display unit at corner.Seating & StudyBay seating near window.Existing adjustable study table to be retained.Overhead ledges above study area.7. Bedroom 1 Guest RoomBedKing-size bed.Floating side tables.Wardrobe & StudyWardrobe as per approved layout.One tall glass display unit adjacent to wardrobe.Adjustable study table exisisting.Overhead ledges above study area.8. ToiletsVanity units in all toilets. | 2026-05-31 16:19:45 +0530 | Aman Kumar | Client Summary: The client's budget for modular interiors is between 1315 lakhs. They are looking for a complete turnkey interior solution. The client has already received quotations from multiple vendors and is in the final stage of evaluation. They are keen to finalize the interior partner at the earliest and are looking for the best overall value and design proposition. | 2026-06-13 |  | 2026-06-20
20303 | Turnkey | May'26 | Debarati S | Mana Jardin Neo | BNG - HSR | Yes | [8 empty] | Piyush Kumar |  | Active | Prospect | 10% Payment | 2693745 | 9999 | 2693745 | 0 | 0 | 34 | 0 | 259376 | 269375 | 1077498 | 1077498 |  |  | 2026-06-02 | 2026-06-02 12:35 | 2026-06-03 | 2026-06-03 11:28 | 2026-06-11 | 2026-06-11 12:19 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-30 | 2026-06-02 12:27 | 2282835 | 410910 | 0 | 0 | 0 | 0 | 2282835 | 410910 | 2026-06-03 11:26:22 +0530 | Rajasekar Ranganathan | REQUIREMENT GATHERING MOMClient Name:Ms. Debarti Family Details:Total Members: 64 Family Members1 Parent1 MaidDesign PreferencesOverall ThemeElegant and timeless interiors.No jazzy finishes or golden elements.Preference for warm and natural tones.Wooden shades to be explored and presented during concept stage.Foyer & Formal LivingFoyerDedicated foyer planning required.Shoe storage for approximately 30 pairs.Feature wall concept required.Formal LivingSophisticated formal seating arrangement.Wall treatment/concept design to be proposed.Space planning to maintain openness and elegance.Additional RequirementsLarge Bookshelf Storage to accommodate approximately 100 books.Existing Servant RoomConversion RequirementConvert servant room into a Pooja Room.No cabinet-based pooja design.Dedicated spiritual space with clean and minimal aesthetics.Informal Living / Family LoungeTV UnitTV unit with decorative wall trims/panel designs.SeatingComfortable lounge-style sofa arrangement.Designed for family relaxation and entertainment.Dining AreaStorage & DisplayCrockery unit.Enclosed bar unit.Functional RequirementsAdditional serving platform/counter.DecorProvision for indoor plants and greenery elements.KitchenAppliancesDouble-door refrigerator.Dishwasher provision.StorageAppliance unit.Pantry unit.Full base storage.Full wall storage.Loft storage.Counter PlanningIsland counter with:StorageSeating provisionContinuous countertop finish matching kitchen counterUtility PlanningCylinder provision to be planned carefully.Sink Requirements1 Sink in Kitchen1 Sink in UtilityUtility AreaRequirementsUtility sink.Dish drainer unit.Washing machine provision.Janitor storage unit.Kids Bedroom 01WardrobeWalk-in wardrobe area.Loft storage above wardrobe.Study AreaOpen ledge design with metal fabrication concept.Study table positioned above bookshelf storage.Additional ElementsDresser mirror.Wall concept design.Parents Bedroom (PBR)WardrobeFull wardrobe cabinet with loft unit.Additional RequirementsDresser mirror.Feature wall concept.TV base unit designed to double as seating bench.Bedside tables.WashroomFull glass partition.Vanity unit.Powder RoomRequirementsVanity unit.Mirror.Kids Bedroom 02StorageWardrobe with display cabinet.Loft storage.Dedicated bookshelf storage.Existing FurnitureExisting study table to be retained.Existing single bed to be retained.Additional ElementsWall concept design.Vanity unit.Glass partition in attached washroom.Master Bedroom (MBR)WardrobeWalk-in Aristo wardrobe.Additional openable wardrobe on right side with shelving storage.FurnitureTV unit.Dresser positioned outside wardrobe area.Design ElementsFeature wall concept.WashroomVanity unit.Glass partition.Mirror design concept.Areas Under DiscussionRemaining areas of the residence are currently under discussion and will be finalized during the next design review meeting. | 2026-06-03 11:25:48 +0530 | Rajasekar Ranganathan | Requirement gathering Meeting MOM Ms, Debarti Family of 6 4 family, 1 parent, 1 maid Formal living spaceÂ Plan for foyer as well No jazzy / golden elements Wooden shades also prepared Servent room - convert to Pooja room Not cabinet Rest of the area is under discussion Shoe rack -30 pairs Wall concept Book shelf storage 100 nos Informal livingÂ tv unit and Wall trims designs . Lounge comfortable sofas. Dining Crockery & enclosed bar unit. additional serving platform. Space to accomodate Indoor plants. Kitchen Â Double door fridge. appliance unit and Pantry unit Full base , wall and loft storage, diswasher in the kitchen 1 sink in kitchen & 1 in utility Cylinder provisionÂ to be planned island counterÂ with storage adn seating ,same counter topÂ Utility Sink and dishdraiwner unit Washring machine area, janitor unit Kids bedroom Walk in wardobe areaÂ with loft unit Walki in area, open ledge with metal fabrication concept withÂ STUDY TABLE ABOVE BOOKS SHELF STORAGE wALL COCNPET DRESSER MIRROR pbr wARDROBE CABINET WITH LOFT UNIT DRESSER MIRROR, WALL COCNEPT TV BASE UNIT CAN BE USED AS SEATING UNIT. BED SIDE TABLE Full Glass parition with vanity unit Pwd room Vanity unit + mirror Kids 2 room Wardrobe with Display cabinet and Loft unit Books shelf storage Existing study table & single Bed wall concpet Vanity unit & glass parition MBR vanity unit with glass parition with Mirrors, MBR walk in aristo wardrobe and right side openable wardrob with shelfs Dresser outside , tv unit , wall concept |  |  |  | 2026-06-19 |  | 2026-06-26
20304 | Turnkey | May'26 | Ragadeep jonna | Affinity Brundaavana | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 2268604 | 9999 | 0 | 0 | 0 | 29 | 0 | 216861 | 226860 | 977252 | 837631.6 |  |  | 2026-05-30 | 2026-06-16 15:48 | 2026-06-10 | 2026-06-18 13:50 | 2026-06-07 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-05-30 | 2026-05-30 17:58 | 0 | 0 | 0 | 0 | 0 | 0 | 1922545 | 346058 | 2026-06-16 14:01:07 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-11 14:10:09 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-10 16:02:28 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-29 |  | 2026-07-06
20306 | Turnkey | May'26 | Ayas Rath | SOBHA - Town park | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1963487 | 9999 | 1963487 | 0 | 0 | 34 | 0 | 186350 | 196349 | 811923 | 758866.8 |  |  | 2026-05-30 | 2026-05-30 21:01 | 2026-06-02 | 2026-06-04 12:58 | 2026-06-07 | 2026-06-11 11:38 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-20 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-30 | 2026-05-30 18:52 | 1666259 | 297227 | 0 | 0 | 0 | 0 | 1666259 | 297227 | 2026-06-04 12:31:13 +0530 | Gayathri Krishna | Cx name : Ayas Kumar Rath & Barsa Baisali Address: Sobha - 2113 - wing 2Â Â Profession : DHL Supply chain India Pvt ltdÂ Â Possession : Dec 2026Â How many people will be staying : 2 + 1kid Theme : Wooden little pop u coloursÂ Entrance facing :Â SE facingÂ Budget : 15L Foyer - Need shoe rack with ledge for budha (add mirror if needed ) Dining - 6 seating dining tableÂ Partition with storage as per reference imageÂ Living - sage green TV size 55" Base unit, need storage for displayÂ Plan the seatingÂ WFH area - need pooja unit in corner (BS) need bench seating after pooja Table and bottom storageÂ Wall storage on window wallÂ Kitchen - dark greenÂ Single door fridgeÂ granite to be addedÂ Base , wall, and loft on sink sideÂ Need tall unit for OTGÂ 2 fluted glass shutter next to hood Utility - Sink unitÂ wall cabinetÂ BR1 - MBR theme - sage greenÂ king size bedÂ need dresser with study tableÂ Need to design bed wallÂ BR2 - KBR - Aahan Rath - 3.5yo Queen sizeÂ wardrobe with loftÂ Study table with open close units neededÂ BR3 - PBR Queen size bedÂ Wardrobe with loftÂ CDP- 6th or 7th | 2026-06-03 13:21:18 +0530 | Tiwari Sandhya | Some Image was uploaded | 2026-06-02 13:25:27 +0530 | Ramesh Nayak | ::::::::---------------RGM Notes For DCM Meeting---------------:::::::: 1. Budget - 15L & 20L with Loos Furniture 2. Property Name & Possession - Sobha Town Park & Dec-2026 3. Carpet Area - 1400 4. BHK - 3 BHK 5. Family Size - 3 Husband in IT Service Wife Home Maker Son 4 Years Old They are from Odisha (BBSR) Wife Design Centric They Already Discussing with Sobha for their Interior. | 2026-06-19 |  | 2026-06-26
20307 | Turnkey | May'26 | Asit Kumar Choudhary | MICL Aaradhya Parkwood | MUM - Thane | No Estimate | [8 empty] | Aryan Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-30 | 2026-06-02 12:34 | 2026-05-30 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-05-30 | 2026-06-02 12:34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-09 18:25:50 +0530 | Maasoumeh Raza | DCM: Recap: 20307 - Design Consultation Meeting (DCM) with the customer Saturday, May 30 ¦ Meeting ¦ Microsoft Teams | 2026-05-31 19:06:02 +0530 | Maasoumeh Raza | Some Image was uploaded |  |  |  | 2026-07-11 |  | 2026-07-18
20308 | Turnkey | May'26 | Watan Bhajanka | MICL Aaradhya Parkwood | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Aryan Singh | Shailendra Mishra | Active | Prospect | Onboarding Due | 1691582 | 148576 | 1385771 | 0 | 0 | 43 | 0 | 0 | 189740 | 709281 | 643984.4 |  |  | 2026-05-30 | 2026-05-30 19:41 | 2026-05-31 | 2026-05-31 21:27 | 2026-05-31 | 2026-05-31 21:51 | 2026-06-08 |  | 2026-06-15 |  | 2026-06-22 |  | 2026-05-31 | 2026-05-31 21:55 | 2026-06-01 | 2026-06-02 14:01 | 2026-06-02 |  | 2026-06-03 | [5 empty] | 2026-06-09 |  | 2026-06-17 |  | 2026-06-18 |  |  |  | 2026-06-25 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-28 | [6 empty] | 2026-07-16 |  | 2026-07-25 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-28 |  |  |  | 2026-08-19 |  | 2026-08-21 |  | 2026-08-22 | [5 empty] | 2026-06-26 |  | 2026-06-04 |  | Unknown | 2026-05-30 | 2026-05-30 19:39 | 1174382 | 211388 | 0 | 0 | 0 | 0 | 1887679.4196 | 304484 | 2026-06-25 11:34:16 +0530 | Bency Chacko | Some Image was uploaded | 2026-06-22 17:21:24 +0530 | Bency Chacko |  | 2026-06-21 19:27:11 +0530 | Asavari Vare | Some Image was uploaded | 2026-06-09 |  | 2026-06-16
20310 | Turnkey | May'26 | Mayur Lad | Regency Luxaria Emerald | MUM - Thane | Yes | [8 empty] | Anjan Kumar |  | Active | Prospect | 10% Payment | 1136732 | 9999 | 1136732 | 0 | 0 | 42 | 0 | 103674 | 113673 | 471016 | 438370 |  |  | 2026-05-30 | 2026-05-30 21:36 | 2026-05-30 | 2026-06-02 12:31 | 2026-06-07 | 2026-06-10 15:37 | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-05-30 | 2026-05-30 21:34 | 963332 | 173399 | 0 | 0 | 0 | 0 | 963332 | 173399 | 2026-06-15 20:07:32 +0530 | Yerra Bharat | CDP: Recap: 20310 - Celebrity Design Presentation (CDP) with the customer Sunday, June 7 ¦ Meeting ¦ Microsoft Teams | 2026-06-03 16:32:58 +0530 | Pooja Nakul Sharma | DCM budget- 8-9L | 2026-06-02 12:30:47 +0530 | Yerra Bharat | DCM: Regency Luxuria - emerald 17th floor 3 adults (couple + 80Y senior citizen) 1 kid Living Room: Safety door, shoe rack ledge at the entrance on the right side Mandir - Marble Mandir existing - have to make changes to base and more pictures will be added. TV Unit - Lower storage - two side storage L-sofa and center table - existing Kirchen: Appliances - Microwave, chimney, hob, mixer, fridge for mixer need closed storage solution Semi modular loft - suggested in L-shape to close beam loft. Washing machine in the dry balcony - connected to kitchen. Bedroom - 1: Foldable study Bedroom -2: Master Bedroom couple + 8Y kid Bed existing - Dressing needed wardrobe - sliding + loft Storage for books - similar to console style - Liked the study table in EC - European theme Bathroom - Vanity units in both bathrooms Niche area b/w bathrooms - needs storage False Ceiling - Limited - Peripheral to cover fire suppression pipes CDP - Weekdays are working 6th Mrng - 11AM | 2026-06-18 |  | 2026-06-25
20311 | Turnkey | May'26 | Satavisha Sarkar Banerjee | Sipani Viveza | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 1849907 | 9999 | 1849907 | 0 | 0 | 15 | 0 | 174992 | 184991 | 739963 | 739962.8 |  |  | 2026-05-30 | 2026-05-30 19:52 | 2026-06-13 | 2026-06-30 15:43 | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-05-30 | 2026-05-30 19:50 | 1567718 | 282189 | 0 | 0 | 0 | 0 | 1567718 | 282189 | 2026-06-27 20:05:49 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-26 16:53:37 +0530 | Ravikiran K | Client name - Satavisha Sarkar Banerjee Property - Sipani Viveza The possession of the property mention in July cx is planning to move in before Dusshera No of people going to stay - 3 (wife, husband & one elder person) By profession madam is scientist Budget is 12 to 15L Closing mindset is 50 - 50, if impressed might take call on spot also is what was mentioned from cx end. | 2026-06-24 11:50:12 +0530 | Swati Rathod | Cx name : Satavisha Sarkar & Arghya BanerjeeÂ Address : Sipani Viveza - A808 Profession : ScientistÂ Possession : JulyÂ How many people will be staying : 3 to 4Â Theme :Â Minimal with pop up (blue and green) Entrance facing : e FacingÂ Â Budget : 12 to 15 L Foyer - Need architraveÂ Need curved console with wall treatmentÂ Living room- TV size -55" opt 1- Need tall unit with glass shutter, base unit and wall concept - refer image (add pop up colour if possible) opt 2- Need base unit and tv wall panel (no tall unit) Corner plant placement to be planedÂ Big L shape sofa which cx hasÂ Need wall design behind sofa wall and center area for art displayÂ Dining areaÂ 6 Seater dining tableÂ need hanging light below tableÂ Crockery unit with tall glass shutter, base unit, loftÂ Kitchen - double door fridgeÂ cylinder unit neededÂ granite to be addedÂ Need to check if we can make the entry to utility sliding door for spaceÂ Tall unit for microwave and OTGÂ Base, wall, loftÂ Wall units need fluted glass shuttersÂ RO unit wall mountedÂ Utility- WM, DW as markedÂ Need cylinder unit as markedÂ Janitor unitÂ wall ledges above cylinder unit because of the shaftÂ MBR-Â Â Wardrobe with extended loftÂ dresser next to wardrobe (design with storage ) need bed wall design - Wall trims as per referenceÂ GBR-Â Wardrobe with extended loftÂ dresser unit next to wardrobe (simple one ) wall trims on bed wallÂ Study room 2 sides wardrobe with bay window as marked in planÂ Sofa cum bed on wardrobe wall as markedÂ Need to place the pooja unit in NW corner unitÂ CDP- 27th June | 2026-07-11 |  | 2026-07-18
20312 | Turnkey | May'26 | rahul sangole s | 2bhk independent house | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 2037756 | 9999 | 0 | 0 | 0 | 31 | 0 | 193777 | 203776 | 815102 | 815102.4 |  |  | 2026-05-30 | 2026-05-30 20:30 | 2026-06-04 | 2026-06-12 18:56 | 2026-06-15 |  | 2026-06-22 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-06-23 |  | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-18 |  | Unknown | 2026-05-30 | 2026-05-30 20:29 | 0 | 0 | 0 | 0 | 0 | 0 | 1726912 | 310844 | 2026-06-11 18:44:08 +0530 | Nidhi Shaw | Client visited with his father. It was his first visit He is having 15-20 Lakhs budget He got a call for Rohan Ekanta, our builder tie up, But he has cancelled property there and purchased in Park West. They are flexible in budget but want good designs. | 2026-06-04 13:54:39 +0530 | Rajasekar Ranganathan | Requirement Gathering MOMClient Name: Mr. Rahul Project Type: Residential Interior Design Possession Date: July 2026 (Next Month) Usage: Personal Residence Family Members: 4 (Parents + Couple) Budget: 1520 Lakhs (Including Furniture & Interior Works) Overall Design RequirementsEntire furniture scope to be newly designed and executed.False ceiling required across all areas.Functional, storage-focused design with premium aesthetics.Adequate lighting and storage planning throughout the residence. 1. FoyerRequirementsShoe rack storage for approximately 30 pairs.Integrated seating provision.Decorative wall concept.Functional entry space with storage and aesthetic appeal. 2. Dining AreaRequirements4-seater dining table.Feature wall concept behind dining.Dedicated pooja unit adjacent to dining area.Storage integration wherever feasible. 3. Living AreaRequirements5-seater sofa arrangement.Feature wall concept.TV provision for 65-inch television.TV unit with tall storage cabinets.Elegant and practical design suitable for family gatherings. 4. KitchenAppliance PlanningDouble-door refrigerator (Top & Bottom configuration).Appliance storage provisions.Storage RequirementsBase units.Wall units.Loft units.Dedicated pantry unit.Appliance unit.Utility RequirementsDish drainer provision within kitchen/utility area.Functional storage optimization. 5. Common WashroomRequirementsVanity unit.Builder-provided mirror to be retained.Granite countertop required.Additional storage planning as feasible. 6. Master Bedroom (MBR)Furniture RequirementsKing-size storage bed.Wardrobe cabinet.TV unit integrated with wardrobe.Study unit.Dresser with mirror.Design RequirementsFeature wall concept.Balanced storage and functionality.Master WashroomVanity unit.Wall-mounted mirror storage cabinet. 7. Guest Bedroom (GBR)Furniture RequirementsWardrobe with loft unit.Dresser mirror provision.Study table.Book ledges/storage shelves.Design RequirementsWallpaper feature wall.Functional workspace integration. 8. Parents Bedroom (PBR)Furniture RequirementsWardrobe with dresser.Bed with side tables.Relaxation/lounge space.WashroomMirror storage cabinet.Additional storage provisions.Design RequirementsBedroom wall concept.Comfortable and accessible furniture layout. 9. BalconyRequirementsSwing seating.Outdoor furniture.Planters on one side.Janitor/utility storage unit on the opposite side.Easy maintenance and weather-resistant finishes. Ceiling & LightingRequirementsFalse ceiling across all rooms.Integrated ambient lighting.Functional task lighting in key areas.Decorative lighting as per design theme. Budget ConsiderationOverall Budget15,00,000 20,00,000 |  |  |  | 2026-06-23 |  | 2026-06-30
20313 | Turnkey | May'26 | Mr. Nitish Kumar | Adarsh park land | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1008345 | 9999 | 1008345 | 0 | 0 | 31 | 0 | 90836 | 100835 | 403338 | 403338 |  |  | 2026-05-30 | 2026-05-30 20:45 | 2026-05-31 | 2026-05-31 18:49 | 2026-06-13 | 2026-06-14 16:46 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-05-30 | 2026-05-30 20:44 | 854529 | 153815 | 0 | 0 | 0 | 0 | 854529 | 153815 | 2026-06-13 18:33:27 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-13 18:32:13 +0530 | Swati Rathod | CDP Notes: - Tv unit arrangement - Pooja unit decided to take from Bonito studio - Sofa cum bed in living area. | 2026-06-13 13:18:13 +0530 | Nayan Reddy | Some Image was uploaded | 2026-06-22 |  | 2026-06-29
20314 | Turnkey | May'26 | Shobha R. Jain | gee cee emrald | MUM - Thane | Yes | Naved Malik | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Active | Design | DEM1 | 2050022 | 293999 | 2839581 | 0 | 0 | 20 | 0 | 0 | 116005 | 851815 | 788202.8 |  |  | 2026-05-30 | 2026-05-31 22:21 | 2026-06-06 | 2026-06-10 12:11 | 2026-06-19 | 2026-06-19 23:58 | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-06-19 | 2026-06-20 11:04 | 2026-06-20 | 2026-06-25 10:49 | 2026-06-25 | 2026-06-25 13:29 | 2026-07-05 | 2026-07-05 12:51 |  |  |  |  | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-05-30 | 2026-05-30 23:47 | 2406425 | 433156 | 0 | 0 | 0 | 0 | 2353045.966 | 388534 | 2026-07-05 12:48:35 +0530 | Divya Rahangdale | Welcome call done : Meeting Dates - TBD IM date: TBD DEM 1 : 8th July Possession date : March 2027 10% payment aligned : 8th July Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-06-25 13:27:24 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: March 2027 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 120 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (7th or 8th July) (preferred Virtual) * 10% Payment Stage Will close after finalizing the design * B2C - Self * Civil work - yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (21000) Special Offer (40000) PM fee waiver (5%) Free Shoerack Offer Design fee waiver (5%) Laminate Upgrade - May '26 Campaign 100% GST Waiver Silver Coin 21g Final Closing Value Discussed: 20,50,022 Checklist terms descoping and agreement terms are cleared Client VOC: The client mentioned that certain civil works are under her scope, including plumbing work in the kitchen, minor tile work in the common bathroom (which is being converted into a utility area), kitchen countertop work, wall tiling, and balcony tile work. The client has requested written confirmation of the project timeline (120 + 10 + 10 business days for modular work, painting, and wallpaper) along with the project milestones. | 2026-06-25 10:59:21 +0530 | Anant Giri | Some Image was uploaded | 2026-07-11 |  | 2026-07-18 |  | Under Construction | 2027-03-31 | 2026-06-19 | 293999 | Ravi Roy
20316 | Turnkey | May'26 | Shruti Vijay Ninawe | gee cee emrald | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar | [5 empty] | Nishtha Valawalkar |  | Hold | Design | DEM1 | 1332016 | 316926 | 1584639 | 0 | 0 | 15 | 13 | 0 | 0 | 496364 | 518726.4 |  |  | 2026-05-30 | 2026-05-30 22:41 | 2026-06-02 | 2026-06-03 12:55 | 2026-06-14 | 2026-06-14 21:20 | 2027-01-03 |  | 2027-01-10 |  | 2027-01-17 |  | 2026-06-14 | 2026-06-15 15:29 | 2026-06-15 | 2026-06-15 18:27 | 2026-06-15 | 2026-06-17 11:02 | 2026-06-24 | 2026-06-24 11:25 |  |  |  |  | 2026-06-22 | 2026-06-15 15:29 | 2027-01-12 |  | 2027-01-13 |  |  |  | 2027-01-20 |  | 2027-01-21 |  | 2027-01-22 |  | 2027-01-23 | [6 empty] | 2027-02-10 |  | 2027-02-19 |  | 2027-02-18 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-22 |  |  |  | 2027-03-16 |  | 2027-03-18 |  | 2027-03-19 | [5 empty] | 2027-01-21 |  | 2026-08-10 |  | Unknown | 2026-05-30 | 2026-05-30 22:41 | 1342914 | 241724 | 0 | 0 | 0 | 0 | 1332016 | 239763 | 2026-07-02 18:15:13 +0530 | Anil Jagtap | Project on Hold - PID - 20316 | 2026-06-26 19:16:57 +0530 | Rachna Abhyankar | Possession willbe in DEC tentatively | 2026-06-26 19:15:51 +0530 | Rachna Abhyankar | Some Image was uploaded | 2027-01-04 |  | 2027-01-11 |  | Under Construction | 2026-12-31 | 2026-06-14 | 143202 | Ravi Roy
20317 | Turnkey | May'26 | Nilesh Ghugare . | Ashar Aries | MUM - Thane | No Estimate | [8 empty] | Bhagyashree Salunkhe |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-30 | 2026-05-30 22:29 | 2026-05-31 |  | 2026-06-04 |  | 2026-06-11 |  | 2026-06-18 |  | 2026-06-25 |  | 2026-06-04 |  | 2026-06-05 |  | 2026-06-05 |  | 2026-06-06 | [5 empty] | 2026-06-12 |  | 2026-06-20 |  | 2026-06-21 |  |  |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 | [6 empty] | 2026-07-19 |  | 2026-07-28 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-31 |  |  |  | 2026-08-22 |  | 2026-08-24 |  | 2026-08-25 | [5 empty] | 2026-06-29 |  | 2026-06-07 |  | Unknown | 2026-05-30 | 2026-05-30 22:17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-30 22:30:43 +0530 | Bhagyashree Salunkhe | Some Image was uploaded | [6 empty] | 2026-06-12 |  | 2026-06-19
20322 | Turnkey | May'26 | Manisha Iyer | nandi garden | BNG - HSR | Yes | Manoj Kumar R | Akshay Ds | Kowshik | [5 empty] | Aman Kumar |  | Active | Design | DEM1 | 973695 | 133844 | 1338438 | 0 | 0 | 19 | 0 | 0 | 60895 | 389478 | 389478 |  |  | 2026-05-31 | 2026-05-31 11:42 | 2026-06-05 | 2026-06-06 11:26 | 2026-06-14 | 2026-06-14 17:33 | 2026-07-13 |  | 2026-07-20 |  | 2026-09-15 |  | 2026-06-14 | 2026-06-19 11:38 | 2026-06-15 | 2026-06-21 18:05 | 2026-06-21 | 2026-06-26 13:34 | 2026-07-08 | 2026-07-07 16:44 |  |  |  |  | 2026-07-14 |  | 2026-09-10 |  | 2026-09-11 |  |  |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 | [6 empty] | 2026-10-09 |  | 2026-10-18 |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-21 |  |  |  | 2026-11-12 |  | 2026-11-14 |  | 2026-11-15 | [5 empty] | 2026-09-19 |  | 2026-07-08 |  | Unknown | 2026-05-31 | 2026-05-31 11:37 | 1134269 | 204168 | 0 | 0 | 0 | 0 | 1113195.439 | 183815 | 2026-06-26 13:34:19 +0530 | Athul Ajaykumar | Possession Status: Renovation Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (1st week of july ) * DEM 1 will update to the sales team * 10% Payment Stage will close after finalizing the layout * B2C - Self * Civil work - yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - May '26 Campaign Silver Coin 21g PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Free Hob & Chimney Offer Free Shoerack Offer Final Closing Value Discussed: 9,73,695 Checklist terms descoping, agreement terms are cleared Â Client VOC: The client mentioned that she has civil work pending, specifically the tile work for the entire house, which is expected to take only one week. She also confirmed that this timeline had already been discussed with the designers. | 2026-06-26 12:31:16 +0530 | Aman Kumar | Civil works such as demolition, painting, and tile work are not included in the quotation. During the design phase, the designer will recommend suitable paint options to the client. Clearly mentioned to client | 2026-06-24 18:04:40 +0530 | Athul Ajaykumar |  | 2026-07-14 |  | 2026-07-21 |  | RTMI |  | 2026-06-14 | 133844 | Ravi Roy
20323 | Turnkey | May'26 | Deepika | AVANI ABODE | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2622105 | 9999 | 0 | 0 | 0 | 28 | 0 | 252212 | 262211 | 1075610 | 1022074.4 |  |  | 2026-05-30 | 2026-06-05 19:41 | 2026-06-03 | 2026-06-17 12:45 | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-06-28 |  | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-23 |  | Unknown | 2026-05-30 | 2026-05-31 12:03 | 0 | 0 | 0 | 0 | 0 | 0 | 2222123 | 399982 | 2026-06-17 12:54:16 +0530 | Rituparna Chakraborty | Some Image was uploaded | 2026-06-17 12:43:57 +0530 | Rituparna Chakraborty | Deepika and ShivanandÂ AVANI ABODE- G plus 2, Four bedrooms, Living dining kitchen. So they want a shoe unit plus utility unit in the garage for washing equipments and around 20 pairs of shoes. Once we enter the property for your needs to be highlighted with 3-D panel and some nice light, TV wall concept is shared by the client that has to be implemented with some rustic feeling and Texture Paint and stone finish has to be used. Sofa needs to be a little curved. There is a wall dividing the dining in kitchen that has to be from the living side to be highlighted with a console and wall decor. Kitchen base top and loft has to be there. Subho tiles to be put on the dadoÂ Colour combination, we can explore green brown and white glass cabinets, tall unit pantry unit. Dining area will have a small basin for hand wash vanity needs to be made on the opposite wall. Puja unit and crockery unit needs to be put the entry between the living and the dining will be arch. Six seater dining to be provided. Ground floor bedroom. This room will be used as parents bedroom for Deepikas mom. It will have a queen size bed, sliding wardrobe, dresser, and it will have some colours and wallpaper little European theme. It has wooden flooring. At joining bathroom will have a vanity unit. First floor, master bedroom, King-size bed wardrobe, dresser TV unit. There are two wardrobe, section one and walking closet, which will have solid and glass door with some tan leather laminate Inside the bedroom, we can go for either powder or Beije Kala combination needs to be minimal and functional The client wants to extend the study because they are not going to use the family area, but civil way we dont do that so partitioning idea has to be given, but that room is going to have height, manageable, work desk and bookshelf. Parents bedroom. This second bedroom in the first floor is for Shivanands parents. They want wardrobe dresser. Thats it for Bonito scope. Second floor media room, we will be having wardrobe and one TV ledge. They want rustic, but minimal concept. Also they have two young sons so the material also should be a little bit long lasting next meeting to be fixed for CP discussion. Budget is around 20 lakhs, but it will go a little bit above, which is already mentioned to the client. | 2026-06-16 13:59:57 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-28 |  | 2026-07-05
20324 | Turnkey | May'26 | Patil Prashanth | KVG Aster 2 | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 1117513 | 9999 | 0 | 0 | 0 | 43 | 0 | 101752 | 111751 | 447005 | 447005.2 |  |  | 2026-05-30 | 2026-06-02 13:05 | 2026-06-09 | 2026-06-30 13:59 | 2026-06-29 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-05-30 | 2026-05-31 17:40 | 0 | 0 | 0 | 0 | 0 | 0 | 947045 | 170468 | 2026-06-09 17:08:38 +0530 | Keerthan M | DCM: Mr. Prashanth 3BHK 4ppl Living - window behind 3 seater - no window on door wall - shoe rack outside house - tall unit, table top unit ( shoe rack-outside house) - TV unit window wall - floating unit with tall display unit and ledge on top - L shape sofa - TV unit with pooja unit (3') - Pooja back panel glass design Dining - 4 seater - round table - double door fridge near window - crockery unit, bottom , tall , topÂ - passage- photo wall Kitchen - no wall till countertop - hob in front of window - sink on hob place - check for BF counter facing living - Bottom, top, loft - countertop Common washroomÂ - MBR washroom- door position has been given from passage - Vanity unit Bedroom 1- Guest - wardrobe beside bed - foldable study unit next to door - Queen bed - wall detailing Bedroom 2 KBR - Wardrobe on bed wall - check space for queen bed with SIDE TABLES - Foldable study table MBR - wardrobe beside bed, asper ref image. - King bed (existing) - TV unit in front of bed - common wash-MBR wash - door opp to WC - Dresser in B/W wash door and MBR door Passage - 2 feet space near bedroom doors towards MBR wash - washing machine space and top storage- storage till top. Note: False ceiling - common areas and MBR | 2026-05-31 12:06:26 +0530 | Unknown | About the Customer **Callback Requested Post 3 PM** Customer is currently unavailable and requested a callback after 3:00 PM. **No Qualification Details Discussed** No interior design needs, budget, or qualification details were discussed due to customer unavailability. **WhatsApp Message Sent** Agent sent a WhatsApp message and asked the customer to save the number for future communication. **Customer Agreed to Reconnect** Customer agreed to communicate later when free. |  |  |  | 2026-07-11 |  | 2026-07-18
20325 | Turnkey | May'26 | Mr. Prashant Pandharinath Dhoble | Arihant Aspair | MUM - Thane | Yes | [8 empty] | Rahul Kumawat |  | Active | Prospect | 10% Payment | 1280153 | 9999 | 0 | 0 | 0 | 34 | 0 | 118016 | 128015 | 574501 | 449621.6 |  |  | 2026-05-31 | 2026-05-31 21:04 | 2026-05-31 | 2026-06-02 11:52 | 2026-06-11 |  | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-31 | 2026-05-31 12:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1087163 | 192990 | 2026-06-02 11:51:46 +0530 | Krutika Vernekar | DCM: 2BHKÂ 28th Floor Unit 9 NE EntryÂ Safety Door False Ceiling electrical Painting Niches to be utilised nicely .Â Can demcolish and extend as builder is giving pemissionÂ Civil to be taken care by cxÂ Living : 3 + 2Â sofa + Tv + MandirÂ Kitchen : Wall Demolition in opening + and creating an open unit.Â has dish washer + Washing Machine + mixer Kids Room : 2 separet beds that pulls like a sofa cum bed and joins 1 big place . (metioned Cx that it was not possible ) Cx still asking to check possibility . WardrobeÂ Masteroom :Â Nice Dresser to get Ready + Bed + Wardrobe + study if possibleÂ Passage : vanity + Washing Machine Budget : 10L Suggested : 15 L | [6 empty] | 2026-06-19 |  | 2026-06-26
20328 | Turnkey | May'26 | Manish Kumar | MICL Aaradhya Parkwood | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 1805605 | 9999 | 0 | 0 | 0 | 42 | 0 | 170562 | 180561 | 764076 | 680407.6 |  |  | 2026-05-31 | 2026-05-31 22:20 | 2026-06-02 | 2026-06-03 10:37 | 2026-06-07 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-06-15 |  | 2026-06-23 |  | 2026-06-24 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 | [6 empty] | 2026-07-22 |  | 2026-07-31 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-03 |  |  |  | 2026-08-25 |  | 2026-08-27 |  | 2026-08-28 | [5 empty] | 2026-07-02 |  | 2026-06-10 |  | Unknown | 2026-05-31 | 2026-05-31 22:19 | 0 | 0 | 0 | 0 | 0 | 0 | 1532461 | 273144 | 2026-06-11 10:55:18 +0530 | Yerra Bharat | CDP: Due to family emergency, client was not able to come. Have to call back in 2 days | 2026-06-09 14:12:16 +0530 | Yerra Bharat | DCM: Meeting Link 20328 - Design Consultation Meeting (DCM) with the customer | 2026-06-09 14:05:50 +0530 | Yerra Bharat | CDP: Client Confirmed, he will be coming for the re-discussion on 10 June 26, 8PM | 2026-06-15 |  | 2026-06-22
20329 | Turnkey | May'26 | Uttam Kumar | ManaDaintree | BNG - HSR | No Estimate | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-31 | 2026-05-31 13:38 | 2026-06-01 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-06-24 |  | 2026-06-25 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-07-02 |  | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-27 |  | Unknown | 2026-05-31 | 2026-05-31 13:36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-31 13:50:50 +0530 | Rajoshi Sarkar | Cx name- Uttam Kumar Native from Bihar 4BHK villa Budget- 10L Language preference - Hindi Cx came with family They don't have much requirements- Modulars- Kitchen, 2 Wardrobes, Tv unit, Nominal False ceiling, Multipurpose room for study/work. Cx is expecting some good design options mostly focusing on the budget part, previously their interior was done from Livspace for their apartment. Visited Livspace 2 months back but didnot liked anything for their Villa. | [6 empty] | 2026-07-02 |  | 2026-07-09
20330 | Turnkey | May'26 | Varun Alagati | Godrej Exquisite | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Nishtha Valawalkar |  | Active | Design | DEM1 | 908029 | 222500 | 1071474 | 0 | 0 | 30 | 0 | 0 | 0 | 343902 | 341627.2 |  |  | 2026-05-31 | 2026-05-31 13:46 | 2026-06-12 | 2026-06-12 18:24 | 2026-06-13 | 2026-06-13 16:55 | 2026-11-03 |  | 2026-11-10 |  | 2026-11-17 |  | 2026-06-13 | 2026-06-13 17:08 | 2026-06-14 | 2026-06-13 17:10 | 2026-06-13 | 2026-06-15 19:07 | 2026-06-17 | 2026-06-17 14:46 |  |  |  |  | 2026-06-22 | 2026-06-17 14:45 | 2026-11-12 |  | 2026-11-13 |  |  |  | 2026-11-20 |  | 2026-11-21 |  | 2026-12-05 |  | 2026-12-06 | [6 empty] | 2026-12-24 |  | 2027-01-02 |  | 2027-01-01 |  | 2027-01-02 |  | 2027-01-03 |  | 2027-01-05 |  |  |  | 2027-01-27 |  | 2027-01-29 |  | 2027-01-30 | [5 empty] | 2026-11-21 |  | 2026-10-30 |  | Unknown | 2026-05-31 | 2026-05-31 13:45 | 908028 | 163445 | 0 | 0 | 0 | 0 | 908028 | 163445 | 2026-07-12 00:19:27 +0530 | Rachna Abhyankar | DEM1 postponed due to cx unavailability - end of july | 2026-07-11 12:47:37 +0530 | Anil Jagtap | cx will receive the possession by October 26 | 2026-07-05 22:32:21 +0530 | Siddhi Chaphekar | DEM 1 Postponed | 2026-11-04 |  | 2026-11-11 |  | Under Construction | 2026-09-30 | 2026-06-13 | 109999 | Ravi Roy
20331 | Turnkey | May'26 | charu karande | Vrindavan elite | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar |  |  | suraj kumar | Aditya Vikram |  | Manasi Patil | Siddhesh Gujrathi | Active | Preproduction | DEM2 | 740653 | 147860 | 931639 | 0 | 0 | 12 | 0 | 0 | 0 | 351931 | 240861.6 |  |  | 2026-05-31 | 2026-05-31 22:34 | 2026-05-31 | 2026-05-31 22:35 | 2026-05-31 | 2026-05-31 22:48 | 2026-06-21 | 2026-06-21 14:29 | 2026-06-30 | 2026-06-29 13:43 | 2026-07-08 |  | 2026-05-31 | 2026-05-31 | 2026-06-01 | 2026-06-02 23:11 | 2026-06-02 | 2026-06-05 16:11 | 2026-06-10 | 2026-06-10 14:28 |  |  |  |  | 2026-06-21 | 2026-06-22 18:29 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-11 | 2026-06-21 14:24 | Site is RTMI | 2026-05-31 | 2026-05-31 16:19 | 791812 | 139827 | 0 | 0 | 0 | 0 | 789676.4391 | 130618 | 2026-06-30 13:18:30 +0530 | Batskhem Marpna | Minutes of Meeting held on Date: 30.06.2026 MOM-Â Living: Remove a shoerack, seater Kitchen-Change kitchen laminate and glass unit DBR- remove side table and keep a normal dresser MBR- remove the side table Â Puja unit design and cost to check. Check the bed size at site during CM | 2026-06-21 14:30:08 +0530 | Batskhem Marpna | Minutes of Meeting held on Date: 20.06.2026 MOM- Charu-20.06.2026 The following pointers have been covered. Dining-Â - Foldable dining - 4 seater dining - 5'4 H and 2'5" W Mandir Living- - Window seater added, Glass unit - 3 seater sofa, One wall panel one wall texture/wallpaper DBR- - Side double darwer with legs - Dressing table MBR - Side table - Bed position and wardrobe position Next meeting we will finalise all the designs including all the vanity units and we will cver material selection as well. Thanks, Batskhem | 2026-06-18 15:04:04 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-22 | 2026-06-21 14:31 | 2026-06-30 | 2026-06-29 13:46 | Under Construction | 2026-07-15
20333 | Turnkey | May'26 | Deepak jagjivandas patel | Aaradhya Parkwood | MUM - GOR | Yes | [8 empty] | Ashish Jha |  | Active | Prospect | DCM Due | 1092657 | 59999 | 0 | 0 | 0 | 39 | 0 | 49267 | 109266 | 473763 | 400362.8 |  |  | 2026-05-31 | 2026-06-06 20:06 | 2026-06-07 | 2026-06-07 20:14 | 2026-06-07 |  | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-05-31 | 2026-05-31 15:35 | 0 | 0 | 0 | 0 | 0 | 0 | 1166993.6894 | 196678 | 2026-06-07 20:17:55 +0530 | Khushi Khandelwal | DCM: 4 members Posession- June endÂ East- West facing (windows on west) Budget- 10L-12L LIVING & DINING AREA Sofa seatingÂ TV wall Shoe unit KITCHENÂ Parallel platform Base cabinetÂ wall unitÂ Appliances- Ref., Oven, Mixer juicer, Chimney, etc.Â washing machine in dry area with wall cabinet BEDROOM-01 Parent's bedroom Wardrobe with mirror on doorÂ Sofa cum bedÂ provision for iron table foldableÂ MASTER BEDROOMÂ WardrobeÂ Study tableÂ Dresser unitÂ Washroom vanityÂ NOTE- Off white, beige, Pastel green with wooden textures.Â | [6 empty] | 2026-06-18 |  | 2026-06-25
20334 | Turnkey | May'26 | Subbalakshmi Srinivasan | Highland Heaven | MUM - Thane | Yes | Shraddha Pansare | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Akshat Shrivastava |  | Prashant Panigrahi | Prasad Bhivaji Hande | Active | Preproduction | 2D | 1067829 | 194999 | 1207051 | 922660 | 0 | 4 | 0 | 0 | 0 | 486332 | 386498 |  |  | 2026-05-31 | 2026-06-02 10:05 | 2026-05-31 | 2026-06-05 17:51 | 2026-06-08 | 2026-06-06 21:35 | 2026-06-20 | 2026-06-20 17:05 | 2026-07-05 | 2026-07-07 14:09 | 2026-07-09 | 2026-07-09 19:46 | 2026-06-06 | 2026-06-06 21:48 | 2026-06-07 | 2026-06-06 22:05 | 2026-06-06 | 2026-06-09 14:38 | 2026-06-10 | 2026-06-10 12:24 |  |  |  |  | 2026-06-20 | 2026-06-23 14:13 | 2026-07-09 | 2026-07-09 11:24 | 2026-07-10 | 2026-07-09 12:23 |  |  | 2026-07-10 | 2026-07-11 19:11 | 2026-07-12 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-11 |  | 2026-06-11 | 2026-06-20 17:01 | Site is RTMI | 2026-05-31 | 2026-06-02 10:04 | 1025211 | 181839 | 994847.1718 | 174628 | 0 | 0 | 1143706.5075 | 200759 | 2026-06-17 16:56:48 +0530 | Anjali Singh | CDP: Recap: Meeting with Anjali Pratap Singh 06 June ¦ Meeting ¦ Microsoft Teams | 2026-06-17 16:56:41 +0530 | Karuna Shinde | DCM: Recap: 20334 - Design Consultation Meeting (DCM) with the customer Sunday, May 31 ¦ Meeting ¦ Microsoft Teams | 2026-06-17 16:56:34 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-21 | 2026-06-20 17:08 | 2026-07-08 | 2026-07-07 22:54 | RTMI |  | 2026-06-06 | 194999 | Ravi Roy
20335 | Sub Project |  | Chaitali Parekh | kanakia silicon valley | MUM - GOR | Yes | Preeti Agarwal | Manzoor Shaikh | Shantanu Parakh |  |  | Faraz Soudagar | Akshat Shrivastava |  |  | Siddhesh Gujrathi | Active | Preproduction | 3D Sign off | 94013 | 0 | 0 | 94013 | 0 | 1 | 0 | 0 | 0 | 75220 | 18793.2 |  |  | 2026-05-31 | 2026-07-04 17:34 | 2026-06-01 | 2026-07-04 17:34 | 2026-07-04 | 2026-07-04 17:34 | 2026-07-05 | 2026-07-04 17:35 | 2026-07-05 | 2026-07-04 17:40 | 2026-07-05 | 2026-07-05 13:31 | 2026-07-04 | 2026-07-04 17:34 | 2026-07-05 | 2026-07-04 17:34 | 2026-07-04 | 2026-07-04 17:35 | 2026-07-05 | 2026-07-04 17:35 |  |  |  |  | 2026-07-04 | 2026-07-04 17:36 | 2026-07-05 | 2026-07-04 17:40 | 2026-07-05 | 2026-07-04 17:40 |  |  | 2026-07-11 | 2026-07-14 15:33 | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-07-05 | 2026-07-04 17:35 | Unknown | 2026-05-31 | 2026-07-04 17:34 | 0 | 0 | 79672 | 14341 | 0 | 0 | 79672 | 14341 | 2026-07-11 20:33:30 +0530 | Manzoor Shaikh |  | 2026-07-11 20:32:15 +0530 | Manzoor Shaikh | Threshold Offer, the bed was discontinued. hence ordering in Sub project. | 2026-07-05 13:41:09 +0530 | Preeti Agarwal | Fabric selected | 2026-07-05 | 2026-07-04 17:36 | 2026-07-05 | 2026-07-04 17:40
20336 | Turnkey | May'26 | pritam salvi | Samarth aura | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 1582443 | 9999 | 0 | 0 | 0 | 45 | 0 | 148245 | 158244 | 672236 | 593718.4 |  |  | 2026-05-31 | 2026-05-31 15:32 | 2026-06-23 | 2026-06-25 12:27 | 2026-06-06 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-05-31 | 2026-05-31 15:32 | 0 | 0 | 0 | 0 | 0 | 0 | 1343549 | 238893 | 2026-05-31 15:34:15 +0530 | Vandana Preet | Some Image was uploaded | 2026-05-31 15:33:34 +0530 | Vandana Preet | Some Image was uploaded |  |  |  | 2026-07-06 |  | 2026-07-13
20339 | Turnkey | May'26 | Ranchod Kumar Pandya | DPS NAKAHATRA HEIGHT | MUM - GOR | Yes | Sonal Singh | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Ishrat Khan |  | Active | Preproduction | DEM2 | 1308113 | 261742 | 1642514 | 0 | 0 | 8 | 0 | 0 | 0 | 587826 | 458545.2 |  |  | 2026-05-31 | 2026-06-02 13:48 | 2026-05-31 | 2026-06-07 20:18 | 2026-06-10 | 2026-06-10 18:47 | 2026-07-07 | 2026-07-07 13:08 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-07 | 2026-06-07 19:33 | 2026-06-11 | 2026-06-09 18:38 | 2026-06-11 | 2026-06-11 15:08 | 2026-06-13 | 2026-06-13 13:08 |  |  |  |  | 2026-06-19 | 2026-07-05 15:29 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-06-14 | 2026-07-07 12:59 | Site is RTMI | 2026-05-31 | 2026-06-02 13:46 | 1394060 | 248454 | 0 | 0 | 0 | 0 | 1389836.0796 | 232984 | 2026-06-13 12:54:53 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement: Site is not accessible DEM Dates -Â DEM 1 - Cx said he will update us about the meeting in group DEM 2 - TBD DEM 3 - TBD Possession date : July 2026 Customer will make 10% after DEM 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-12 13:54:08 +0530 | Vishakha Vaishnav | Tried connecting cx , didn't answered | 2026-06-11 15:07:37 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: July Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Will update to the sales team * DEM 1 Will update to the sales team * 10% Payment Stage Tentatively scheduled for (20th June 2026) * No Civil Work Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade - Windows to Wonderful home 100% GST Waiver Free Bed Offer PM Fee Waiver (4%) May '26 Net Special Studio Offer Final Closing Value Discussed: 13,08,710 Checklist terms descoping and agreement terms are cleared | 2026-07-08 | 2026-07-07 13:11 | 2026-07-14 |  | Under Construction | 2026-07-31 | 2026-06-07 | 164251 | Ravi Roy
20341 | Turnkey | May'26 | Shilpa Tanak | Anutham | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1906197 | 9999 | 1906197 | 0 | 0 | 42 | 0 | 180621 | 190620 | 796941 | 728016.4 |  |  | 2026-05-31 | 2026-06-02 10:08 | 2026-05-31 | 2026-06-03 16:38 | 2026-06-06 | 2026-06-07 10:52 | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-06-07 |  | 2026-06-08 |  | 2026-06-08 |  | 2026-06-09 | [5 empty] | 2026-06-15 |  | 2026-06-23 |  | 2026-06-24 |  |  |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-03 |  | 2026-07-04 | [6 empty] | 2026-07-22 |  | 2026-07-31 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-03 |  |  |  | 2026-08-25 |  | 2026-08-27 |  | 2026-08-28 | [5 empty] | 2026-07-02 |  | 2026-06-10 |  | Unknown | 2026-05-31 | 2026-06-02 10:07 | 1617478 | 288719 | 0 | 0 | 0 | 0 | 1617478 | 288719 | 2026-06-09 18:11:10 +0530 | Maasoumeh Raza | CDP: The client did not proceed with the booking immediately as they requested one day to consider their decision. The client's budget was between 1518 lakhs, and the quotation provided was within the budget. The client appreciated the proposed designs and overall offering,however, they wanted additional time to evaluate whether they wished to move forward with us. | 2026-06-09 18:06:34 +0530 | Maasoumeh Raza | DCM: Recap: 20341 - Design Consultation Meeting (DCM) with the customer Sunday, May 31 ¦ Meeting ¦ Microsoft Teams | 2026-06-07 12:08:41 +0530 | Maasoumeh Raza | CDP: Recap: 20341 - Celebrity Design Presentation (CDP) with the customer Saturday, June 6 ¦ Meeting ¦ Microsoft Teams Recap: 20341 - Celebrity Design Presentation (CDP) with the customer Saturday, June 6 ¦ Meeting ¦ Microsoft Teams | 2026-06-15 |  | 2026-06-22
20342 | Turnkey | May'26 | Aroon Kotian | MICL Aaradhya Parkwood | MUM - GOR | Yes | Manisha Dubey | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 944235 | 188847 | 1323577 | 0 | 0 | 18 | 0 | 0 | 0 | 408844 | 346543.6 |  |  | 2026-05-31 | 2026-05-31 17:38 | 2026-05-31 | 2026-05-31 22:22 | 2026-05-31 | 2026-05-31 22:26 | 2026-06-27 | 2026-06-27 19:11 | 2026-07-03 |  | 2026-07-10 |  | 2026-05-31 | 2026-05-31 22:15 | 2026-06-01 | 2026-06-03 16:57 | 2026-06-03 | 2026-06-05 11:52 | 2026-06-10 | 2026-06-10 13:41 |  |  |  |  | 2026-06-16 | 2026-06-18 18:44 | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-11 | 2026-06-27 19:02 | Site is RTMI | 2026-05-31 | 2026-05-31 17:38 | 1123962 | 199614 | 0 | 0 | 0 | 0 | 1123961.9016 | 175813 | 2026-06-27 19:20:04 +0530 | Manisha Dubey | DDM1: Minutes of Meeting (MoM) Client: Mr. Arun Date: 17/06/2026 Discussion Points & Requirements: Provide a ceiling light at the entrance. Add a hidden key holder above the shoe rack unit. Increase the width of the shoe rack unit by 50 mm. Provide a foldable dining table. The Mandir will be placed on the opposite wall with a Krishna-themed design. Master Bedroom Wardrobe: Provide 3 drawers: 1 drawer for jewellery. 1 drawer for important documents. 1 additional storage drawer. Provide a dedicated locker space. Allocate storage space for an iron and ironing board. Kitchen Requirements: Provide storage space for kitchen appliances such as an air fryer, mixer, blender, and microwave. Include a wicker basket in the kitchen. Provide a rolling shutter unit. Kids' Room: Provide a single bed with storage drawers. Remove the study table from the kids' room. Provide dedicated storage space for a mop in the washroom. Provide space for a water purifier. Action Items: Update the design as per the above requirements. | 2026-06-10 13:40:30 +0530 | Vishakha Vaishnav | "Welcome call done' Initial measurement : Aligned for 12th June by 3pm DEM Dates -Â DEM 1 - Cx is available only on weekend need to check with designer DEM 2 - TBD DEM 3 - TBD Possession date : July 1st week Customer will make 10% : After dem 1 have informed this to cx Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-05 11:52:25 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: 1 July 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (8th June 2026) * DEM 1 Tentatively scheduled for (13th or 14th June ) * 10% Payment Stage Tentatively scheduled for (14th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) Free Bed Offer Free Hob & Chimney Offer Free Shoerack Offer 100% GST Waiver Final Closing Value Discussed: 9,44,235 Checklist terms descoping, agreement terms are cleared or notÂ | 2026-06-28 | 2026-06-27 19:19 | 2026-07-04 |  | Under Construction | 2026-07-01
20343 | Turnkey | May'26 | Prathamesh gade | Abhee Celestial City | BNG - HSR | Yes | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | 10% Payment | 1861739 | 9999 | 0 | 0 | 0 | 16 | 0 | 176175 | 186174 | 788217 | 701174.4 |  |  | 2026-05-31 | 2026-05-31 17:46 | 2026-06-12 | 2026-06-19 18:02 | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-05-31 | 2026-05-31 17:44 | 0 | 0 | 0 | 0 | 0 | 0 | 1577745 | 283994 | 2026-06-30 11:44:54 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-30 11:40:37 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-18 15:54:41 +0530 | Saranya Thiyagarajan | DCM: MOM Interior Design DiscussionProject DetailsProject: Abhee PropertyConfiguration: 3 BHKFacing: East FacingFamily Size: 6 MembersOccupation: IT ProfessionalsFoyerShoe rack with seating provision. Living RoomTV UnitFloating TV unit.Display shelves incorporated.Clean contemporary design.PartitionFoldable partition behind sofa seating.KitchenLayoutOpen kitchen concept.Existing kitchen wall removed.Breakfast counter with elevated serving level.Kitchen RequirementsHob placement at center.RO unit above sink.Dishwasher adjacent to sink.Provision for GAIL gas connection.No glass shutters.Bonito scope- granite countertop.Tall Storage & AppliancesFridge side half-wall to be removed.Accommodate:RefrigeratorDishwasherWashing MachineTall Unit with oven provisionRoller shutter unit.Check feasibility of locating tall unit beside refrigerator.StoragePantry unit if space permits.Base units with:2 drawers cabinetsGlossy laminate finish.Dining AreaDining6-seater dining table.Crockery UnitBase storage cabinet.Top glass display cabinet.Pooja UnitLocated near wash basin.Base storage.Upper unit with glass doors.Wash BasinNo storage below basin.Master Bedroom (MBR)WardrobeWalk-in wardrobe.Storage on both sides.Full-height mirror at center.Study UnitFoldable study table. WashroomVanity below wash basin.Mirror with behind storage.Glass shower partition.FurnitureSide tables on both sides of bed.Bedroom 2 Kids Room (11' x 13')Current RequirementTo remain largely open for now so minimal wallpaper.Furniture & StorageWardrobe on TV wall.Study table.Mirror integrated on wardrobe shutter or bedside.Design ThemeOff-white / beige / light white wallpaper.Soft neutral palette.WashroomVanity unit.Shower partition.Bedroom 3 Parents Room (14' x 12')WardrobeFull-height wardrobe.Reading nook adjacent to wardrobe.FurnitureTV unit.Study table.MirrorFull-length mirror on toilet wall.Single ledge below mirror.WashroomVanity below sink.Mirror with storage behindGlass shower partition.FinishPost-laminate finish.Glossy laminates.Budget consideration: Maximum 15 Lakhs.Balcony / UtilityJanitor unit/storage cabinet required. Points to VerifyFeasibility of refrigerator + tall unit + oven + roller shutter arrangement.Pantry unit feasibility after appliance placement.Washing machine and dishwasher positioning after removal of half-wall.Final dimensions for breakfast counter and elevated serving ledge.Pooja unit dimensions near wash basin.Walk-in wardrobe layout and circulation clearance. | 2026-07-05 |  | 2026-07-12
20344 | Turnkey | May'26 | Manish kumar | DSR Elixir | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Design | 20% Payment | 893174 | 121999 | 1223711 | 0 | 0 | 8 | 0 | 0 | 56636 | 431798 | 282741.6 |  |  | 2026-05-31 | 2026-06-02 13:09 | 2026-06-03 | 2026-06-11 16:53 | 2026-06-14 | 2026-06-17 11:31 | 2026-07-07 | 2026-07-07 11:11 | 2026-08-07 |  | 2026-08-14 |  | 2026-06-17 | 2026-06-18 11:24 | 2026-06-18 | 2026-06-18 11:39 | 2026-06-18 | 2026-06-24 11:42 | 2026-06-26 | 2026-06-26 11:45 |  |  |  |  | 2026-07-07 |  | 2026-08-09 |  | 2026-08-10 |  |  |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 | [6 empty] | 2026-09-25 |  | 2026-10-04 |  | 2026-10-03 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-07 |  |  |  | 2026-10-29 |  | 2026-10-31 |  | 2026-11-01 | [5 empty] | 2026-09-05 |  | 2026-06-27 | 2026-07-07 11:01 | Site is RTMI | 2026-05-31 | 2026-05-31 17:40 | 1037043 | 186667 | 0 | 0 | 0 | 0 | 1016391.9204 | 169321 | 2026-07-12 19:05:42 +0530 | Rajeshwari S | Client wants to have one more meeting post that he will make the payment. Expecting possession in the next month. Going on call along with DM on 14th July and close the concerns. | 2026-06-24 11:42:18 +0530 | Bency Chacko |  | 2026-06-24 11:24:11 +0530 | Bency Chacko |  | 2026-07-08 | 2026-07-07 11:15 | 2026-08-08 |  | Under Construction | 2026-08-20 | 2026-06-14 | 121999 | Ravi Roy
20346 | Turnkey | May'26 | Pranali Desai Maniar | labh safai | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | 10% Payment | 1451539 | 9999 | 1451539 | 0 | 0 | 39 | 0 | 135155 | 145154 | 633472 | 527758.8 |  |  | 2026-05-31 | 2026-05-31 18:35 | 2026-06-06 | 2026-06-06 15:27 | 2026-06-06 | 2026-06-11 21:29 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-31 | 2026-05-31 18:35 | 1230118 | 221421 | 0 | 0 | 0 | 0 | 1230118 | 221421 | 2026-06-11 21:32:50 +0530 | Yash Jain | CDP: The client said they are still exploring and will compare with other vendors as well in the market bigger shoe rack Mandir to be connected with tv unit master bedroom - proper study desk is required | 2026-06-06 23:11:17 +0530 | Yash Jain | Some Image was uploaded | 2026-06-06 23:07:57 +0530 | Yash Jain | Some Image was uploaded | 2026-06-19 |  | 2026-06-26
20348 | Turnkey | May'26 | SAFALYA MECHANICAL WORKS | LODHA AMARA | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Shreyash Kotecha |  | Active | Design | DEM1 | 1015201 | 124599 | 1246966 | 0 | 0 | 27 | 0 | 0 | 78441 | 490459 | 321702 |  |  | 2026-05-31 | 2026-05-31 20:11 | 2026-06-02 | 2026-06-02 16:05 | 2026-06-14 | 2026-06-16 13:39 | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-06-16 | 2026-06-16 18:51 | 2026-06-17 | 2026-06-17 11:13 | 2026-06-17 | 2026-06-18 14:55 | 2026-06-25 | 2026-06-25 20:23 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-07 |  | Unknown | 2026-05-31 | 2026-05-31 19:12 | 1059038 | 187927 | 0 | 0 | 0 | 0 | 1059037.4816 | 180037 | 2026-07-03 13:19:12 +0530 | Monika Pal | 2026-07-03 | 2026-06-25 20:25:02 +0530 | Anamika Dolai | Done, milestones explained. | 2026-06-20 14:50:49 +0530 | Sanjana Swami |  | 2026-07-12 |  | 2026-07-19 |  | Under Construction | 2026-08-18 | 2026-06-14 | 124599 | Ravi Roy
20350 | Turnkey | May'26 | Renu Chaubey | Pavani Mirabilia | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Piyush Kumar |  | Active | Design | DEM1 | 1701799 | 225017 | 2345881 | 0 | 0 | 29 | 0 | 0 | 115343 | 696197 | 665242 |  |  | 2026-05-31 | 2026-06-02 12:27 | 2026-05-31 | 2026-06-03 16:39 | 2026-06-13 | 2026-06-14 13:38 | 2026-07-24 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-06-14 | 2026-06-15 11:29 | 2026-06-15 | 2026-06-16 13:24 | 2026-06-16 | 2026-06-16 14:50 | 2026-06-26 | 2026-06-26 13:52 |  |  |  |  | 2026-07-25 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-07-20 |  | Unknown | 2026-05-31 | 2026-06-02 12:16 | 1988034 | 357846 | 0 | 0 | 0 | 0 | 1906924.5205 | 314873 | 2026-07-14 16:44:09 +0530 | Sayed Byahatti | DDM1: | 2026-06-28 16:09:07 +0530 | Sayed Byahatti | Minutes of Meeting held on Date: Entrance door decoration simple kind design. Plantation and design as per modern theme. | 2026-06-28 15:46:15 +0530 | Sayed Byahatti | Minutes of Meeting held on Date: | 2026-07-25 |  | 2026-08-01 |  | Under Construction | 2026-08-31 | 2026-06-13 | 225017 | Ravi Roy
20351 | Turnkey | May'26 | Sumit Mhaske | Precious imperial | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Preproduction | DEM2 | 1129196 | 289999 | 1406896 | 0 | 0 | 22 | 0 | 0 | 0 | 440778 | 398418.8 |  |  | 2026-05-31 | 2026-06-02 10:22 | 2026-05-31 | 2026-06-02 12:56 | 2026-06-07 | 2026-06-06 21:46 | 2026-06-28 | 2026-06-23 17:51 | 2026-06-27 |  | 2026-07-21 |  | 2026-06-06 | 2026-06-09 12:36 | 2026-06-07 | 2026-06-09 19:29 | 2026-06-09 | 2026-06-11 12:26 | 2026-06-23 | 2026-06-23 14:03 |  |  |  |  | 2026-06-24 | 2026-06-23 14:02 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-06-24 | 2026-06-23 14:07 | Site is RTMI | 2026-05-31 | 2026-06-02 10:22 | 1194572 | 212324 | 0 | 0 | 0 | 0 | 1194571.8921 | 200556 | 2026-07-08 12:18:02 +0530 | Harshali Bhuyar | CM needs to be plan. But the client is not responding since a week. | 2026-06-23 18:05:38 +0530 | Harshali Bhuyar | DDM1: Hi, Sharing below the minutes of meeting, Living room - TV unit design finalized, Bar unit in to me made in custom carpentry ( rotating)Sofa side wall design pendingDining wall Design pending. Crockery Design changed. Added glass shutter wall cabinet Mandir to be made in custom carpentry (Floor to ceiling )False ceiling design pending Kitchen - Loft position changed as per site conditionunit besides chimney made into glass shutter Valence panel addedflap up unit added above microwave unit2 drawer units added for onion potatoes. Master Bedroom - Wardrobe changed from shutter to Aristo sliders.Internals have been customized, accessories added.Dresser unit added at the bedside. Study unit design has been changed, wall cabinet addedTV unit addedwall concept finalized - arched wallpaper False ceiling design finalized - profile light in infinity shape Kids Bedroom - Wardrobe design has been changed , side opening unit added , glass shutter unit added.study unit design changed , Same as reference image. Wall concept finalised , Wallpaper and rafters. False ceiling design , profile lights. | 2026-06-11 12:25:55 +0530 | Athul Ajaykumar | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend ) * DEM 1 Tentatively scheduled for (Next weekend) * 20% Closed * NO civil work Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (3%) Free Bed Offer 100% GST Waiver Final Closing Value Discussed: 11,29,197 Checklist terms descoping, agreement terms are cleared | 2026-06-24 | 2026-06-23 18:04 | 2026-06-28 |  | RTMI |  | 2026-06-06 | 289999 | Ravi Roy
20352 | Turnkey | May'26 | Fahad qureshi | derria classico | MUM - GOR | Yes | Zoya Bhatkar | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Shoaib Shaikh |  | Active | Preproduction | DEM2 | 818975 | 163795 | 1101026 | 0 | 0 | 20 | 0 | 0 | 0 | 356493 | 298686.8 |  |  | 2026-05-31 | 2026-06-02 14:11 | 2026-06-02 | 2026-06-02 15:30 | 2026-06-11 | 2026-06-11 11:45 | 2026-06-26 | 2026-06-25 20:49 | 2026-07-01 |  | 2026-07-08 |  | 2026-06-11 | 2026-06-11 12:00 | 2026-06-12 | 2026-06-11 12:01 | 2026-06-11 | 2026-06-12 13:34 | 2026-06-17 | 2026-06-17 17:09 |  |  |  |  | 2026-06-26 | 2026-06-25 18:46 | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-18 | 2026-06-25 18:24 | Site is RTMI | 2026-05-31 | 2026-06-02 13:40 | 933073 | 167953 | 0 | 0 | 0 | 0 | 933072.2304 | 155965 | 2026-07-03 17:24:33 +0530 | Meet Shah | Others: | 2026-06-17 17:08:40 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Need to align asap DEM Dates -Â DEM 1 - need to align cx is available for the meeting DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% cx said that before 2d meeting he will clear the 10% due Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-13 15:03:39 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-26 | 2026-06-25 20:51 | 2026-07-02 |  | RTMI |  | 2026-06-07 | 110082 | Ravi Roy
20353 | Turnkey | May'26 | prajakta bhosale | Godrej Exquisite | MUM - Thane | Yes | [8 empty] | Rahul Kumawat |  | Active | Prospect | 10% Payment | 2423012 | 9999 | 0 | 0 | 0 | 41 | 0 | 232302 | 242301 | 1013464 | 924945.2 |  |  | 2026-05-31 | 2026-05-31 21:01 | 2026-06-03 | 2026-06-04 17:22 | 2026-06-05 |  | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-06-05 |  | 2026-06-06 |  | 2026-06-06 |  | 2026-06-07 | [5 empty] | 2026-06-13 |  | 2026-06-21 |  | 2026-06-22 |  |  |  | 2026-06-29 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-08 |  | Unknown | 2026-05-31 | 2026-05-31 21:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2055687 | 367324 | 2026-06-09 15:54:50 +0530 | Rinisha Masurkar | Some Image was uploaded | 2026-06-09 13:52:33 +0530 | Rinisha Masurkar | Recap: 20353 - Celebrity Design Presentation (CDP) with the customer 05 June ¦ Meeting ¦ Microsoft Teams Recap: 20353 - Celebrity Design Presentation (CDP) with the customer 05 June ¦ Meeting ¦ Microsoft Teams | 2026-06-04 19:17:52 +0530 | Rinisha Masurkar | Project No.: 20353 Carpet Area: 922 Sq.ft. Family Members: 3 Members (Mother-in-law visits occasionally) Floor: 23rd Floor Site Directions: To be checked during site verification. Living RoomRequirementsShoe rack at entrance.3+2 sofa seating arrangement.Provision for 65" TV / Projector.Swing provision.6-seater dining table.Minimal false ceiling only in living room.Design ConsiderationsCompact entrance foyer with concealed shoe storage and mirror panel.TV wall designed to accommodate both TV and future projector setup.Swing positioned near window for natural light and views from the 23rd floor.Dining placed adjacent to kitchen for ease of circulation.Minimal and elegant false ceiling with indirect lighting.KitchenRequirementsParallel kitchen layout.Dishwasher provision.Appliance provisions.Classy and premium aesthetic.Washing machine and dryer provision in dry balcony.Design ConsiderationsDedicated appliance garage for cleaner countertops.Tall unit for microwave/oven and pantry storage.Dishwasher placed near sink for functional workflow.Premium finishes with subtle textures and elegant hardware.Utility area planned efficiently for washing machine, dryer, and cleaning storage.Bedroom 2 (Guest / Multi-purpose Room)RequirementsWalk-in wardrobe.Dresser provision.Sofa-cum-bed.Design ConsiderationsFlexible layout to function as guest room when mother-in-law visits.Walk-in wardrobe designed with open and closed storage combination.Compact dresser integrated within wardrobe design.Sofa-cum-bed for occasional overnight guests while maintaining spaciousness.Master BedroomRequirementsQueen-size bed.Wardrobe.Dresser.Cozy corner.Design ConsiderationsFull-height wardrobe with optimized internal accessories.Dedicated dresser with storage and concealed lighting.Cozy reading/lounge corner near window.Warm and calming material palette for a comfortable retreat.Kids BedroomRequirementsStudy area.Wardrobe.Bunk bed with play area or single bed option.Design ConsiderationsDedicated study desk with overhead storage and pin-up board.Flexible furniture planning considering future growth.Option 1: Bunk bed with play/activity zone underneath.Option 2: Single bed with larger play area and storage.Ample wardrobe and toy storage solutions.Ceiling & LightingRequirementsFalse ceiling only in living room.Design ConsiderationsMinimal gypsum ceiling with cove lighting in living room.Surface-mounted or recessed lighting in bedrooms for maintenance ease.Layered lighting approach using ambient, task, and accent lighting.Budget - 20 - 23 | 2026-06-13 |  | 2026-06-20
20355 | Turnkey | May'26 | Lipsa Pattnaik | Pavani Mariabilia | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1106010 | 9999 | 1106010 | 0 | 0 | 34 | 0 | 100602 | 110601 | 442404 | 442404 |  |  | 2026-05-31 | 2026-05-31 21:26 | 2026-06-02 | 2026-06-04 12:27 | 2026-06-07 | 2026-06-11 12:02 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-05-31 | 2026-05-31 21:25 | 937296 | 168713 | 0 | 0 | 0 | 0 | 937296 | 168713 | 2026-06-03 12:27:44 +0530 | Aparna | Comment : Ramesh had a word with cx over the call , saying minimum 10L required as budget | 2026-06-03 11:59:49 +0530 | Maspi Das | Cx name : Lipsa Pattnaik Property - Pavani Mirabillia 2BHK Profession : Private sector Possession : July-Aug How many people will be staying : 2-4 Kids-Â ----- Theme : NeutralÂ Entrance -facing : East Budget : Client mentioned 5-6L CDP - 04.06.2026 at 4:30Â Foyer-Â Entrance wall design (3d wall design) Living area- Tv unit ref takenÂ Pooja unit Beside the TV unit (As bathroom wall is there, can consider Loose pooja unit as well) Sofa unit- Design complimenting the TV Wall Dining area- 4' Crockery unit(Base unit with Wall units (Glass shutters) Kitchen- Base units Wall units Lofts L-shaped 2' sink in kitchen One Rolling shutter Counter Top - Granite Utility-Â 3' base sink unit MBR- 5' Wardrobe(Sliding wardrobe) Dresser Study (Foldable) GBR- Wardrobe(Hinged) *EXTRA SHOE STORAGE INSIDE THE HOUSE-Need to PLAN* *Study unit cum workstation conider* Sink are- Counter type- Granite Base unit Wall design with lights Bathrooms- MBR - Glass partion *Regarding Vanity client will check and let us know* C.Bathroom -Â Vanity unit | 2026-06-02 13:36:48 +0530 | Ramesh Nayak | CRM - Note ::::::::---------------RGM Notes For DCM Meeting---------------:::::::: 1. Budget - Not Disclosed But I told them as per their Requirement 10-12L 2. Property Name & Possession - Pavani Mirabillia & June-2026 3. Carpet Area - 689 4. BHK - 2 BHK 5. Family Size - 2 Husband in IT Service Wife working in Ikea They are from Odisha (BBSR) Husband & Wife Design Centric. ::::::::Requirements:::::::: TV Unit with wall Panelling Puja Unit - 6.5 ft Height Vanity Base Unit 2 Sliding Wardrobe Size 6/8 Kitchen - Base, Wall & Loft Glass Partition in One Bathroom 2 Vanity Base unit in Bathroom Wall Concept - 3 Wall (Sofa + 2 Bedroom) Study Unit Utility Unit Fall Ceiling ::: Need Good Design and Good Offer ::: | 2026-06-19 |  | 2026-06-26
20358 | Turnkey | May'26 | ART PLANET PRIVATE LIMITED swamy | gee cee emrald | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Vandana Preet |  | Active | Design | DEM1 | 1988996 | 489999 | 2485228 | 0 | 0 | 12 | 0 | 0 | 0 | 711637 | 787360.4 |  |  | 2026-05-31 | 2026-05-31 21:39 | 2026-06-30 | 2026-06-20 12:04 | 2026-06-20 | 2026-06-20 12:20 | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-06-20 | 2026-06-20 16:07 | 2026-06-21 | 2026-06-21 22:12 | 2026-06-21 | 2026-07-03 15:11 | 2026-07-04 | [5 empty] | 2026-06-28 | 2026-06-20 16:07 | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-21 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-15 |  | 2026-09-20 |  |  |  | 2026-10-29 |  | 2026-10-30 |  | 2026-10-31 | [5 empty] | 2026-07-27 |  | 2026-07-05 |  | Unknown | 2026-05-31 | 2026-05-31 21:37 | 2106126 | 379102 | 0 | 0 | 0 | 0 | 2106125.2309 | 366569 | 2026-07-02 19:41:00 +0530 | Vandana Preet | Some Image was uploaded | 2026-06-27 12:47:31 +0530 | Bency Chacko |  | 2026-06-27 11:29:02 +0530 | Swami Vadnere | Some Image was uploaded | 2026-07-10 |  | 2026-07-17 |  | Under Construction | 2026-12-31 | 2026-06-19 | 248523 | Ravi Roy
20359 | Turnkey | May'26 | Sumit kasle | dhrusti emrald | MUM - Thane | Yes | Vaishnavi Sawant | Anamika Dolai | Anil Kuwar | [5 empty] | Anant Giri |  | Active | Design | 20% Payment | 1018646 | 148999 | 1387618 | 0 | 0 | 1 | 0 | 0 | 54730 | 457658 | 357258.4 |  |  | 2026-05-31 | 2026-05-31 21:49 | 2026-06-05 | 2026-06-09 18:24 | 2026-06-14 | 2026-06-14 21:19 | 2026-07-15 | 2026-07-14 12:25 | 2026-07-20 |  | 2026-07-27 |  | 2026-06-14 | 2026-06-15 11:27 | 2026-06-15 | 2026-06-16 19:41 | 2026-06-16 | 2026-06-17 12:24 | 2026-06-25 | 2026-06-25 17:05 |  |  |  |  | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-06-26 | 2026-07-14 11:10 | Site is Non-RTMI | 2026-05-31 | 2026-05-31 21:46 | 1175947 | 211670 | 0 | 0 | 0 | 0 | 1151905.2364 | 191906 | 2026-07-02 13:05:36 +0530 | Vaishnavi Sawant | Reschedule of DEM1 | 2026-06-17 12:23:43 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: September Soft Possession: July Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (This weekend) Preferred only on weekend * 10% Payment Stage Tentatively scheduled for (1st week of July ) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (4%) Free Shoerack Offer Silver Coin 21g Laminate Upgrade - May '26 Campaign 100% GST Waiver PM fee waiver (5%) Final Closing Value Discussed: 10,18,647 Checklist terms descoping and agreement terms are cleared | 2026-06-17 11:09:08 +0530 | Athul Ajaykumar |  | 2026-07-15 | 2026-07-14 12:55 | 2026-07-21 |  | Under Construction | 2026-09-30 | 2026-06-14 | 148999 | Ravi Roy
20360 | Turnkey | May'26 | RAJESH Myatra | Raj paradise | MUM - GOR | Yes | Anjali Jain | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Rashmita Das |  | Active | Preproduction | DEM2 | 1332289 | 262791 | 1808098 | 0 | 0 | 16 | 0 | 0 | 0 | 567543 | 501954.8 |  |  | 2026-05-31 | 2026-06-04 14:09 | 2026-06-04 | 2026-06-04 17:17 | 2026-06-07 | 2026-06-10 13:19 | 2026-06-28 | 2026-06-28 17:44 | 2026-07-05 |  | 2026-07-12 |  | 2026-06-06 | 2026-06-06 23:46 | 2026-06-07 | 2026-06-10 12:09 | 2026-06-11 | 2026-06-26 13:52 | 2026-06-26 | 2026-06-26 16:42 |  |  |  |  | 2026-06-29 | 2026-06-29 14:35 | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-27 | 2026-06-28 17:29 | Site is RTMI | 2026-05-31 | 2026-05-31 22:09 | 1532287 | 275811 | 0 | 0 | 0 | 0 | 1591398.847 | 255562 | 2026-06-28 17:43:48 +0530 | Anjali Jain | DDM1: Living room Added shoe storage Mandir unit - added one tray Tv unit - Back panel added Kitchen - Rolling shutter removed added double shutter unit Removed shelves for Ele b base units Corner unit need to check Bedroom1 Need to remove open unit & make it one Nish storage added internal changes wardrobe done added one glass single unit Queen bed considers Master bedroom Wardrobe internal changes done need to consider king bed | 2026-06-26 16:44:48 +0530 | Christopher Macwan | Welcome call done. Initial measurement done DEM Dates -Â DEM 1 - 27th June 2026 at 4pm DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-26 13:52:11 +0530 | Bency Chacko | Some Image was uploaded | 2026-06-29 | 2026-06-29 13:13 | 2026-07-06 |  | RTMI |  | 2026-06-06 | 262791 | Ravi Roy
20362 | Turnkey | May'26 | Geetha | independent house | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Mohammed Rasick |  | Active | Design | 20% Payment | 1680322 | 228000 | 2287477 | 0 | 0 | 27 | 0 | 0 | 108064 | 716050 | 628207.2 |  |  | 2026-05-31 | 2026-06-03 15:00 | 2026-06-03 | 2026-06-03 18:16 | 2026-06-04 | 2026-06-04 12:27 | 2026-06-19 | 2026-06-18 12:59 | 2026-10-09 |  | 2026-10-16 |  | 2026-06-04 | 2026-05-31 | 2026-06-05 | 2026-06-05 12:01 | 2026-06-05 | 2026-06-08 16:55 | 2026-06-13 | 2026-06-13 17:29 |  |  |  |  | 2026-07-10 |  | 2026-10-11 |  | 2026-10-12 |  |  |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-22 | [6 empty] | 2026-11-09 |  | 2026-11-18 |  | 2026-07-28 |  | 2026-11-18 |  | 2026-11-19 |  | 2026-11-21 |  |  |  | 2026-12-13 |  | 2026-12-15 |  | 2026-12-16 | [5 empty] | 2026-10-20 |  | 2026-06-14 | 2026-06-18 12:41 | Site is RTMI | 2026-05-31 | 2026-06-02 19:11 | 1938540 | 348937 | 0 | 0 | 0 | 0 | 1883566.1592 | 311008 | 2026-06-18 10:56:05 +0530 | Salpriyan Pm | *Geetha* Ground Floor Living Room TV unit Client scope. Plain wall Provision required for projector. Sofa back wall Explore: White wall finish, or Texture paint, or Lime wash finish. 6-seater dining table. UPS storage to be finalized after IM. Under-stair storage/design to match the overall design language. Refrigerator location to be identified. False ceiling Bonito scope. First Floor (FF) Entrance Shoe rack outside Client scope. Living Room TV unit: Center shutter to be flap-down. Left and right storage units to be drawers. Remove altar. Remove rafters and replace with paint-based ceiling design. MDF beading design. TV back wall Lime wash finish in a lighter shade. Passage area: Requires redesign/rework. Existing lower portion can be retained as it looks good. Landing space available above the staircase after the stair flight. Dining Area Prefer civil work instead of carpentry. Brick cladding Client scope. Ceiling-mounted focus lights with track/rail system. Existing design is liked and can be retained as reference. Kitchen Dishwasher inside kitchen, positioned to the right of the sink. Loft to be retained on the left wall near the door. Corner pull-out required. Master Bedroom (MBR) Queen-size bed. Mirror on the right-side wall. No wallpapers; use texture paint only. Reduce the amount of beading. Vanity design to be finalized after IM. Guest Bedroom 2-seater sofa-cum-bed required. Fourth Floor Brother's Room Hanging provision for clothes near entry. Radiant paint finish on wall. Curtain gap required on the left side. Remove loft above study table and replace with open ledges. Airbnb Unit Entry / Common Area Remove all rafters. Add decorative mirror with bottom console/table. Living Room Remove closed top unit above foldable table. Remove L-shaped ledges above. TV unit Movable bottom unit. TV back wall Plain white painted wall. Crockery Area Crockery unit Client scope. Brick cladding above platform. Crockery storage area to remain plain/minimal. Extend platform till balcony. Kitchen Shift sink to the left. Add dishwasher. Sloped roof present Chimney position to be checked. Hanging planter above breakfast counter. Bedroom Remove dresser drawer. *Jacob*(Rental) Requirement Add a crockery unit. Third Floor Kitchen Remove L-shaped layout. Reduce the number of cabinets. | 2026-06-09 19:32:52 +0530 | Keerthan M | CDP: GF living loose furnitureups storage under stare ff living and dining check for prayer unit positionpassage design need to be changedcrockery unit need to be added in design and quotationdining seater suggest to do it in civil work Bedrooms wall detailing need to be suggestedsuggest bay window to do in civil work. 4th floor loose furniture need to be suggestedcrockery unit need to be added in dining both in design and quotesdeck need to be suggested to do in civil work | 2026-06-09 17:53:35 +0530 | Keerthan M | Some Image was uploaded | 2026-06-19 | 2026-06-18 12:59 | 2026-10-10 |  | Under Construction | 2026-10-01
20364 | Turnkey | May'26 | Sahana | Sakthi Tranquill | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | Vaishali G | Vaishali G | Deekshith P | Jairam Joshi |  |  | Vishwa Hiremath | Active | Design | DEM3 | 1322745 | 184500 | 1246234 | 0 | 0 | 6 | 0 | 0 | 0 | 617903 | 520342.4 |  |  | 2026-06-06 | 2026-06-02 15:58 | 2026-06-02 | 2026-06-03 11:01 | 2026-06-06 | 2026-06-03 11:23 | 2026-06-18 | 2026-06-14 18:56 | 2026-07-08 | 2026-07-07 12:03 | 2026-07-15 |  | 2026-06-03 | 2026-05-31 | 2026-06-04 | 2026-06-03 17:49 | 2026-06-03 | 2026-06-05 11:16 | 2026-06-07 | 2026-06-07 18:38 |  |  |  |  | 2026-06-14 | 2026-06-15 16:02 | 2026-07-09 | 2026-07-09 15:48 | 2026-07-10 | 2026-07-09 17:12 |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-08 | 2026-06-14 18:54 | Site is RTMI | 2026-06-06 | 2026-06-02 15:55 | 1056130 | 190103 | 0 | 0 | 0 | 0 | 1493708.7206 | 246644 | 2026-06-16 14:04:37 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-14 16:47:25 +0530 | Rajeshwari S | Some Image was uploaded | 2026-06-07 18:40:40 +0530 | Rajeshwari S | Welcome call done along with Shibin Possession Mid of July Site is ready for Initial measurement Designer to book the slot and inform client on the same Design meeting they prefer in the week end. 10% will be paid on the first design meeting. Estimation is closed for Rs.9,21,346 | 2026-06-15 | 2026-06-14 18:58 | 2026-07-08 | 2026-07-07 12:05 | Under Construction | 2026-06-30
20365 | Turnkey | 2026-06-01 | Saksham Handu | Devanahalli, Bangalore | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 729675 | 9999 | 0 | 0 | 0 | 15 | 0 | 62969 | 72968 | 291870 | 291870 |  |  | 2026-06-02 | 2026-06-09 12:28 | 2026-06-10 | 2026-06-10 12:17 | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-06-02 | 2026-06-05 18:10 | 0 | 0 | 0 | 0 | 0 | 0 | 847191.007 | 139891 | 2026-06-16 14:11:54 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-05 12:16:02 +0530 | Rituparna Chakraborty | Some Image was uploaded | 2026-06-05 12:14:11 +0530 | Rituparna Chakraborty | DCM: Online RGM meeting 3rd june-11am Attendees: Rituparna , Saksham & Kanika 2bhk property , handover June end Both working in IT profession , not comfortable sharing company name. Majorly only 2 people will be living , but it can go up to 3/4 people if parents or guests come . Major requirements are for kitchen and 2 bedrooms Living dining nothing needs to be done right now , all will be moveable and if budget sustains they can look at studio products . Kitchen : Base , top & loft cabinet to be end to end . Washing machine and Fridge has to be accommodated. Chocolate or brown shade or base cabinet to be given Breakfast counter can be avoided Master Bedroom : Wardrobe & loft . (Need to check fire extinguisher position) Bed not in our scope . Window seating to be planned , work table will be bought out Bedroom 2 : Wardrobe & loft . (Need to check fire extinguisher position) Bed not in our scope . Living Dining (Not Priority) TV unit L or 3+2 sofa Dining table can be optional | 2026-07-08 |  | 2026-07-15
20366 | Turnkey | 2026-06-01 | Ajay R | Shobha Villa | BNG - HRBR | Yes | Faizan Sharief | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Mohammed Rasick |  | Active | Design | DEM1 | 1857352 | 1115999 | 2613457 | 0 | 0 | 30 | 0 | 0 | 0 | 30987 | 710366 |  |  | 2026-05-31 | 2026-06-09 12:22 | 2026-06-03 | 2026-06-09 12:59 | 2026-06-12 | 2026-06-09 13:05 | 2026-07-06 |  | 2027-01-01 |  | 2027-01-08 |  | 2026-06-09 | 2026-06-09 16:58 | 2026-06-10 | 2026-06-10 16:20 | 2026-06-10 | 2026-06-15 12:47 | 2026-06-17 | 2026-06-17 11:04 |  |  |  |  | 2026-06-15 | 2026-06-09 18:03 | 2027-01-03 |  | 2027-01-04 |  |  |  | 2027-01-11 |  | 2027-01-12 |  | 2027-01-13 |  | 2027-01-14 | [6 empty] | 2027-02-01 |  | 2027-02-10 |  | 2027-02-09 |  | 2027-02-10 |  | 2027-02-11 |  | 2027-02-13 |  |  |  | 2027-03-07 |  | 2027-03-09 |  | 2027-03-10 | [5 empty] | 2027-01-12 |  | 2026-07-04 |  | Unknown | 2026-05-31 | 2026-06-02 12:26 | 2214794 | 398663 | 0 | 0 | 0 | 0 | 2076523.7297 | 342873 | 2026-07-14 16:51:16 +0530 | Rajeshwari S | Non RTMI Possession expected - Dec end. IM done on 5th July. Have schedule 1st DEM on 18th July. Client confirmation awaited. Project will be placed on hold post 1st design meeting. | 2026-06-19 19:02:13 +0530 | Rajeshwari S | Welcome call done along with Design Manager - Surabhi Non RTMI Project - Villa project Possession expected end of Dec. Price protection till Feb 2027. Wants IM on 4th July @11.30am. Designer to schedule and confirm to client. Project is at Chandapura - Electronic City. Paid 60% already for price protection. | 2026-06-16 14:14:05 +0530 | Losii Athisa | Some Image was uploaded | 2026-07-07 |  | 2027-01-02 |  | Under Construction | 2027-02-28 | 2026-06-07 | 261346 | Ravi Roy
20367 | Turnkey | 2026-06-01 | Neebu | JR East Feets | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 56021 | 9999 | 0 | 0 | 0 | 43 | 0 | 0 | 1205 | 26808 | 18008.4 |  |  | 2026-05-31 | 2026-06-02 13:06 | 2026-06-01 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-05-31 | 2026-06-02 12:48 | 0 | 0 | 0 | 0 | 0 | 0 | 47476 | 8545 | [9 empty] | 2026-06-22 |  | 2026-06-29
20368 | Turnkey | 2026-06-01 | Dharmaraj B | Adarsh Greens | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 1364518 | 9999 | 1364518 | 0 | 0 | 36 | 0 | 126453 | 136452 | 551678 | 539936 |  |  | 2026-05-31 | 2026-06-02 13:07 | 2026-06-03 | 2026-06-04 12:38 | 2026-06-07 | 2026-06-09 11:39 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-06-09 |  | 2026-06-10 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | 2026-06-17 |  | 2026-06-25 |  | 2026-06-26 |  |  |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 | [6 empty] | 2026-07-24 |  | 2026-08-02 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-05 |  |  |  | 2026-08-27 |  | 2026-08-29 |  | 2026-08-30 | [5 empty] | 2026-07-04 |  | 2026-06-12 |  | Unknown | 2026-05-31 | 2026-06-02 12:48 | 1156372 | 208146 | 0 | 0 | 0 | 0 | 1156372 | 208146 | 2026-06-16 14:24:50 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-16 13:44:09 +0530 | Priyanka Gs | CDP: The CDP could not be closed as the customer had a stringent budget of 7 lakhs while expecting extensive requirements for a 3BHK home. The scope of work and expectations were significantly beyond what could be accommodated within the allocated budget. | 2026-06-09 11:38:17 +0530 | Priyanka Gs | Some Image was uploaded | 2026-06-17 |  | 2026-06-24
20369 | Turnkey | 2026-06-01 | Hardik tanna | sky Avenue | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 2607355 | 9999 | 0 | 0 | 0 | 29 | 0 | 250737 | 260736 | 1042942 | 1042942 |  |  | 2026-06-02 | 2026-06-16 12:50 | 2026-06-11 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-06-02 | 2026-06-02 15:52 | 0 | 0 | 0 | 0 | 0 | 0 | 2209623 | 397732 | 2026-07-03 16:51:46 +0530 | Meet Shah | Others: | 2026-06-11 18:56:47 +0530 | Shreya Sonavane | DCM: Entrance- name plate on left wall & shoe rack with seating on right with safety door Living room- TV unit, sofa, Mandir on kitchen left wall, dinning for 8 with crockery & bar closed unit. LEFT SIDE OF TERRACE TO BE CONVERT INTO MULTIFUNCTIONAL ROOM (STUDY ROOM), Kitchen- Breakfast counter but don't want to go with open kitchen, C shape counter also want accessibility for window, Foldable counter for access the window, required dish washer provision, wm will be in void areas MB, PB, KB - bed, wardrobe, TV unit, dresser, side table MB (BED1) KB wants window seating (Bed3) PB required attached bathroom- (bed4) GUEST (Bed2)- Common wall of living can be demolished, consider as collapsible partition with murphy bed with sofa. |  |  |  | 2026-07-04 |  | 2026-07-11
20370 | Turnkey | 2026-06-01 | Rahul Kumar Mishra | INFINITY GREEN WOODS | BNG - HSR | Yes | Kiran Agarampalli | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Hold | Preproduction | Site Readiness 1 | 1128097 | 225619.8 | 1483632 | 0 | 0 | 0 | 19 | 0 | 0 | 465714 | 436762.8 |  |  | 2026-06-02 | 2026-06-02 18:48 | 2026-06-05 | 2026-06-05 12:28 | 2026-06-05 | 2026-06-06 10:53 | 2026-06-28 | 2026-06-24 19:59 | 2026-10-05 |  | 2026-10-12 |  | 2026-06-06 | 2026-06-07 11:51 | 2026-06-07 | 2026-06-07 11:52 | 2026-06-07 | 2026-06-08 18:09 | 2026-06-09 | 2026-06-09 19:16 |  |  |  |  | 2026-06-25 | 2026-06-26 18:31 | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-06-10 | 2026-06-24 19:58 | Site is Non-RTMI | 2026-06-02 | 2026-06-02 18:39 | 1257315 | 226316 | 0 | 0 | 0 | 0 | 1232034.6276 | 203057 | 2026-06-26 18:51:27 +0530 | Akshay Ds | Some Image was uploaded | 2026-06-25 15:09:16 +0530 | Akshay Ds | Possession expected in SEP end Proejct will go on HOLD once the 10% payment is completed . | 2026-06-24 19:56:56 +0530 | Kiran Agarampalli | Discussion on 18th and 24th June Living: Pooja unit add base unit, internal with ledges Tv back panel to be added, add one ledge one top make middle unit as glass shutter entrance DB wall add mirror, with readymade console table, based on IM design the wall pattern partition behind the fridge to cover the wires sofa back wall beadings and wallpaper design with wall light Dining: Crockery design to be updated with base units Kitchen: Breakfast counter to have rafters. add carpentry paneling on side and top with ledges Loft to be aligned on tall unit sideextend the chimney panel till ceiling. sink plan for double bowl sink, heater and ro unit to be planned Utility: Dishwasher and washing machine add janitor closet Master bedroom: headboard wall design change removed dresser unit Kids room: study unit to be 6' with tall unit and wall units headboard wall design with strips design wallpaper need to make the room more designs and wall concepts | 2026-06-25 | 2026-06-25 14:38 | 2026-10-06 |  | Under Construction | 2026-09-01 | 2026-06-05 | 225619 | Ravi Roy
20371 | Turnkey | 2026-06-01 | Sunil | SBR Earth | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 2804067 | 9999 | 0 | 0 | 0 | 8 | 0 | 270408 | 280407 | 1133345 | 1109908.8 |  |  | 2026-05-30 | 2026-06-04 19:07 | 2026-06-05 | 2026-06-14 11:36 | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-05-30 | 2026-06-03 18:31 | 0 | 0 | 0 | 0 | 0 | 0 | 2376328 | 427739 | 2026-07-08 10:29:27 +0530 | Priyamvada PV | CDP: | 2026-07-08 10:28:13 +0530 | Priyamvada PV | CDP changes : 1. TV rafters, tall unit, shoe rack from ceiling level 2. FALSE ceiling to be peripheral design for sofa area 3. BEAM paneling rafters for Living passage area to be considered 4. Wall storage with fluted glass for crockery, front of sink with paneling rafters similar to living ceiling, right wooden door to cover sink 5. Tall glass shutter unit on left 6. Pooja - ledges on either sides option preferred, onyx marble to be done on CT 7. Kitchen shift tall unit next to janitor unit as 2 tall units for pantry storage 8. Fridge to be changed to single door fridge 9. Chimney panel on hob side, loft on tall unit side 10 WR in main room section with curved edge , having base storage Mirror to be shifted on wall opp to WR in vanity passage | 2026-06-14 17:08:21 +0530 | Aparna | Others: CDP meeting planned for 20th June | 2026-07-13 |  | 2026-07-20
20372 | Turnkey | 2026-06-01 | Ganesh purushottam morye | Avant Heritage | MUM - GOR | Yes | Neha Yadav | Christopher Macwan | Safalta Karkera | [5 empty] | Ashutosh Singh |  | Active | Design | DEM1 | 963454 | 118997 | 1189966 | 0 | 0 | 1 | 0 | 0 | 73694 | 412041 | 358722.4 |  |  | 2026-05-31 | 2026-06-03 18:09 | 2026-06-24 | 2026-07-12 10:55 | 2026-07-15 | 2026-07-12 14:45 | 2026-07-20 |  | 2026-07-27 |  | 2026-08-03 |  | 2026-07-12 | 2026-07-12 13:14 | 2026-07-13 | 2026-07-13 12:47 | 2026-07-13 | 2026-07-14 12:14 | 2026-07-15 | [5 empty] | 2026-07-21 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-07-16 |  | Unknown | 2026-05-31 | 2026-06-03 18:00 | 1008445 | 181520 | 0 | 0 | 0 | 0 | 993141.859 | 171374 | 2026-07-14 12:14:08 +0530 | Sanjana Swami | client's concerns are addressed | 2026-07-13 19:02:21 +0530 | Athul Ajaykumar | OB Initiated - Call is not getting connected | 2026-07-13 19:02:09 +0530 | Athul Ajaykumar | OB Initiated - Call is not getting connected | 2026-07-21 |  | 2026-07-28 |  | Under Construction | 2026-08-01
20375 | Turnkey | 2026-06-01 | Vivek Kumar | Royaal panchajanyaa | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Rajoshi Sarkar |  | Active | Design | DEM1 | 896231 | 109999 | 1237026 | 0 | 0 | 16 | 0 | 0 | 69247 | 367204 | 349780.8 |  |  | 2026-06-02 | 2026-06-04 17:23 | 2026-06-05 | 2026-06-09 11:12 | 2026-06-24 | 2026-06-25 11:29 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-06-25 | 2026-06-25 18:26 | 2026-06-26 | 2026-06-26 13:35 | 2026-06-26 | 2026-06-29 12:31 | 2026-07-14 | 2026-07-14 11:41 |  |  |  |  | 2026-07-15 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-20 |  | Unknown | 2026-06-02 | 2026-06-04 17:20 | 1050613 | 186413 | 0 | 0 | 0 | 0 | 1028771.796 | 167175 | 2026-07-14 11:45:46 +0530 | Abhinandan K S | Possession - RTMI Initial measurement is taken. Customer is ok with the Offers and timeline. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. Customer has issue with the final Net quote (Post Offer) value. There is a descrepency of Rs. 2,000 which is to be clarified by the Sales team. | 2026-06-30 15:57:59 +0530 | Gayathri Krishna | Recap: 20375 - Design Consultation Meeting (DCM) with the customer 05 June ¦ Meeting ¦ Microsoft Teams | 2026-06-30 15:57:45 +0530 | Gayathri Krishna | Some Image was uploaded | 2026-07-15 |  | 2026-07-22 |  | RTMI |  | 2026-06-23 | 109999 | Ravi Roy
20376 | Turnkey | 2026-06-01 | 4S Hitech Pharma | birla tisya | BNG - HRBR | Yes | Shivani Shet | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | 20% Payment | 1204775 | 162999 | 1633628 | 0 | 0 | 3 | 0 | 0 | 77956 | 551262 | 412557.6 |  |  | 2026-05-31 | 2026-06-05 19:40 | 2026-06-05 | 2026-06-11 15:39 | 2026-06-14 | 2026-06-12 12:30 | 2026-07-12 | 2026-07-12 15:48 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-12 | 2026-06-20 14:22 | 2026-06-13 | 2026-06-23 19:02 | 2026-06-23 | 2026-06-25 17:14 | 2026-06-28 | 2026-06-28 16:33 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-07-29 |  | 2026-06-29 | 2026-07-12 15:44 | Site is Non-RTMI | 2026-05-31 | 2026-06-03 15:56 | 1384431 | 249197 | 0 | 0 | 0 | 0 | 1365225.3805 | 225409 | 2026-06-28 16:36:54 +0530 | Rajeshwari S | Welcome call done Estimation finalized for Rs.12,04,775/- Non-RTMI project. Will be ready by Sept. There is permission for IM. Designer to schedule the IM and confirm to client. He wants meeting in the first week of July - preferably week end. Shivani to schedule 1st design meeting on 11th or 12th and confirm to client in the group. Client wants to make the 10% payment after design finalization Sending the agreement clause to him . | 2026-06-27 13:28:40 +0530 | Priyanka Gs | Some Image was uploaded | 2026-06-25 17:13:21 +0530 | Bency Chacko |  | 2026-07-13 | 2026-07-12 15:53 | 2026-07-19 |  | Under Construction | 2026-10-31 | 2026-06-11 | 162999 | Ravi Roy
20377 | Sub Project |  | Sachin Narkar | Sai Krupa | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  | Urvisha Prajapati | Rajkumar Suthar | Sandeep Tiwari |  |  | Sunil Poojary | Active | Preproduction | Site Readiness 2 | 514733 | 308840 | 0 | 0 | 514733 | 1 | 0 | 0 | 0 | 0 | 205893 |  |  | 2026-06-03 | 2026-06-29 17:49 | 2026-06-04 | 2026-06-29 17:49 | 2026-06-29 | 2026-06-29 17:49 | 2026-06-30 | 2026-06-29 17:50 | 2026-06-30 | 2026-06-29 17:51 | 2026-06-30 | 2026-06-29 17:52 | 2026-06-29 | 2026-06-29 17:49 | 2026-06-30 | 2026-06-29 17:49 | 2026-06-29 | 2026-06-29 17:49 | 2026-06-30 | 2026-06-29 17:49 |  |  |  |  | 2026-06-29 | 2026-06-29 17:50 | 2026-06-30 | 2026-06-29 17:51 | 2026-06-30 | 2026-06-29 17:51 |  |  | 2026-07-01 | 2026-07-10 20:52 | 2026-07-11 | 2026-07-11 18:52 | 2026-07-12 | 2026-07-12 11:50 | 2026-07-13 | 2026-07-14 18:27 | [5 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-30 | 2026-06-29 17:49 | Unknown | 2026-06-03 | 2026-06-29 17:49 | 0 | 0 | 0 | 0 | 620897.771 | 92652 | 620897.771 | 92652 | [9 empty] | 2026-06-30 | 2026-06-29 17:50 | 2026-06-30 | 2026-06-29 17:51
20378 | Turnkey | 2026-06-01 | SANGEETA I DSOUZA | independent house | MUM - GOR | Yes | [8 empty] | Ashish Jha |  | Active | Prospect | 10% Payment | 3070438 | 9999 | 3070438 | 0 | 0 | 29 | 0 | 297045 | 307044 | 1263929 | 1192421.2 |  |  | 2026-06-03 | 2026-06-16 18:00 | 2026-06-03 | 2026-06-16 18:01 | 2026-06-19 | 2026-06-16 20:42 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-08-05 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-30 |  | 2026-09-04 |  |  |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-03 | 2026-06-12 11:54 | 3070438 | 552678 | 0 | 0 | 0 | 0 | 3070438 | 552678 | 2026-06-16 17:40:52 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-16 17:08:37 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-16 16:52:11 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-24 |  | 2026-07-01
20379 | Turnkey | 2026-06-01 | Srinibas Achary | Sri Balaji Rose woods | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 1583960 | 9999 | 1583960 | 0 | 0 | 36 | 0 | 148397 | 158396 | 691528 | 575640 |  |  | 2026-06-03 | 2026-06-03 13:52 | 2026-06-03 | 2026-06-04 12:10 | 2026-06-07 | 2026-06-10 13:27 | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-06-03 | 2026-06-03 13:40 | 1342339 | 241621 | 0 | 0 | 0 | 0 | 1342339 | 241621 | 2026-06-16 16:25:32 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-09 17:31:52 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-04 12:08:54 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-18 |  | 2026-06-25
20380 | Turnkey | 2026-06-01 | Vaishali Ashok Kale | GeeCee Emerald | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 935755 | 233999 | 1166876 | 0 | 0 | 35 | 0 | 0 | 0 | 327454 | 374302 |  |  | 2026-06-03 | 2026-06-04 12:15 | 2026-06-03 | 2026-06-04 13:26 | 2026-06-05 | 2026-06-05 19:26 | 2027-01-05 |  | 2027-01-12 |  | 2027-01-19 |  | 2026-06-05 | 2026-06-09 13:01 | 2026-06-06 | 2026-06-10 12:39 | 2026-06-10 | 2026-06-10 14:39 | 2026-06-12 | 2026-06-12 17:05 |  |  |  |  | 2026-06-18 | 2026-06-12 17:06 | 2027-01-14 |  | 2027-01-15 |  |  |  | 2027-01-22 |  | 2027-01-23 |  | 2027-01-24 |  | 2027-01-25 | [6 empty] | 2027-02-12 |  | 2027-02-21 |  | 2027-02-20 |  | 2027-02-21 |  | 2027-02-22 |  | 2027-02-24 |  |  |  | 2027-03-18 |  | 2027-03-20 |  | 2027-03-21 | [5 empty] | 2027-01-23 |  | 2027-01-01 |  | Unknown | 2026-06-03 | 2026-06-04 12:15 | 988878 | 177998 | 0 | 0 | 0 | 0 | 988877.413 | 168436 | 2026-07-12 00:20:37 +0530 | Rachna Abhyankar | cx will confirm the date for DEM1 | 2026-07-11 12:49:06 +0530 | Anil Jagtap | cx will receive the possession by December *26 | 2026-07-07 16:57:20 +0530 | Rachna Abhyankar | DEM1 Reschedule | 2027-01-06 |  | 2027-01-13 |  | Under Construction | 2026-12-31 | 2026-06-05 | 233999 | Ravi Roy
20382 | Turnkey | 2026-06-01 | Vijay Gholve | gee cee emrald | MUM - Thane | No Estimate | [8 empty] | Foram Joshi |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-03 | 2026-06-04 12:36 | 2026-06-04 |  | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-06-26 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-21 |  | Unknown | 2026-06-03 | 2026-06-03 15:30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-03 16:34:45 +0530 | Foram Joshi | Some Image was uploaded | 2026-06-03 16:31:14 +0530 | Foram Joshi | Some Image was uploaded |  |  |  | 2026-06-26 |  | 2026-07-03
20383 | Turnkey | 2026-06-01 | Kanth Raj | MLN Enclave | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 1318677 | 9999 | 0 | 0 | 0 | 35 | 0 | 121869 | 131868 | 527471 | 527470.8 |  |  | 2026-05-31 | 2026-06-05 19:44 | 2026-06-03 | 2026-06-10 09:52 | 2026-06-13 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-06-21 |  | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-06-16 |  | Unknown | 2026-05-31 | 2026-06-03 15:59 | 0 | 0 | 0 | 0 | 0 | 0 | 1117523 | 201154 | 2026-06-16 14:18:15 +0530 | Priyanka Gs | CDP: The CDP has not been closed as the client requires additional time | 2026-06-10 11:46:42 +0530 | Priyanka Gs | Some Image was uploaded | 2026-06-10 09:51:50 +0530 | Priyanka Gs | 1. Entrance / CorridorShoe rack with integrated seating to be designed. 2. Living RoomSofa: To be finalized based on layout.TV Unit:Minimal design approach.Provision for ledges/shelves.Dedicated display space for trophies.Wall Concepts:Design concepts to be developed3. Dining AreaDining Table: 6-seater configuration.Pooja Unit:Traditional style.To be outsourced.Crockery Unit:Storage + display combination.4. Master BedroomWardrobe + Loft:Rattan shutters for wardrobe.Dresser:To be included 5. Bedroom 2 (Kids + Workspace)Study Area:Dual-purpose setup for kids and work-from-home.Wardrobe:Functional storage design.6. Parents BedroomWardrobe + Loft:Designed for easy accessibility and ample storage.7. KitchenAppliance Planning:Refrigerator space: 600 mm.RO unit: Undermount provision.Dedicated space for microwave, mixer, and air fryer.Countertop:Granite under builders scope.Utility Considerations:Cylinder space in utility area.Dishwasher:Space to be planned.Loft Storage:Additional overhead storage required.8. False CeilingDesign to include wooden rafters for aesthetic enhancement. | 2026-06-21 |  | 2026-06-28
20385 | Sub Project |  | Prashant Shekhar | Meridian Park @ The Prestige City | BNG - HSR |  | Priyanka Inchoor | Abhinandan K S | Kowshik |  |  | Nanda Kumar | Ranjith Kumar | Murali S |  | Sunil Kumar S M | Active | Production | Dispatch Due | 53079 | 53080 | 0 | 0 | 53079 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-03 | 2026-06-03 18:30 | 2026-06-04 | 2026-06-03 18:30 | 2026-06-03 | 2026-06-03 18:30 | 2026-06-04 | 2026-06-03 18:31 | 2026-06-04 | 2026-06-03 18:32 | 2026-06-04 | 2026-06-03 18:34 | 2026-06-03 | 2026-06-03 18:30 | 2026-06-04 | 2026-06-03 18:30 | 2026-06-03 | 2026-06-03 18:30 | 2026-06-04 | 2026-06-03 18:30 |  |  |  |  | 2026-06-03 | 2026-06-03 18:31 | 2026-06-04 | 2026-06-03 18:32 | 2026-06-04 | 2026-06-03 18:33 |  |  | 2026-06-05 | 2026-06-04 11:46 | 2026-06-05 | 2026-06-04 15:41 | 2026-06-05 | 2026-06-04 18:02 | 2026-06-06 | 2026-06-04 16:57 |  |  |  |  | 2026-06-10 15:16 | 2026-06-12 | 2026-06-11 21:09 | 2026-06-15 | 2026-06-13 12:24 | 2026-07-02 | 2026-06-04 16:57 | 2026-06-13 |  | 2026-06-25 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-06-04 | 2026-06-05 12:09 | 2026-06-04 | 2026-06-03 18:31 | Unknown | 2026-06-03 | 2026-06-03 18:30 | 0 | 0 | 0 | 0 | 44982 | 8096 | 44982 | 8096 | 2026-06-10 17:54:01 +0530 | Ranjith Kumar | Execution: | [6 empty] | 2026-06-04 | 2026-06-03 18:31 | 2026-06-04 | 2026-06-03 18:32
20387 | Turnkey | 2026-06-01 | Devi | Independent house | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 2369743 | 9999 | 0 | 0 | 0 | 40 | 0 | 226975 | 236974 | 1038588 | 857206.4 |  |  | 2026-06-03 | 2026-06-05 19:39 | 2026-06-16 |  | 2026-06-14 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-08 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-02 |  | 2026-09-07 |  |  |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-06-03 | 2026-06-04 17:22 | 0 | 0 | 0 | 0 | 0 | 0 | 2635187.9439 | 435103 | 2026-06-16 17:22:13 +0530 | Priyanka Gs | Some Image was uploaded | 2026-06-16 15:05:13 +0530 | Priyanka Gs | CDP has not closed as the cx would require time to explore and get back | 2026-06-16 14:37:11 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-27 |  | 2026-07-04
20388 | Turnkey | 2026-06-01 | Nirav vira | Raj niwas | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 2180771 | 9999 | 0 | 0 | 0 | 15 | 0 | 208078 | 218077 | 965869 | 778748 |  |  | 2026-05-31 | 2026-06-04 12:32 | 2026-06-05 | 2026-06-05 17:08 | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-06-28 |  | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-23 |  | Unknown | 2026-05-31 | 2026-06-03 17:38 | 0 | 0 | 0 | 0 | 0 | 0 | 1851049 | 329722 | 2026-06-30 16:09:48 +0530 | Rahul Agrawal | CDP: Â Cx was in hurry , so we discussed the layout and designs only, quote was not discussed. | 2026-06-30 15:11:26 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-13 15:21:07 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-28 |  | 2026-07-05
20395 | Turnkey | 2026-06-01 | Nilesh Ahuja | 72 west | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | Neha Singh | Neha Singh |  |  |  | Mrunali Mitkari |  | Active | Preproduction | DEM2 | 959526 | 191905 | 1263310 | 0 | 0 | 1 | 11 | 0 | 0 | 419125 | 348496.4 |  |  | 2026-06-04 | 2026-06-11 13:04 | 2026-06-01 | 2026-06-11 13:31 | 2026-06-14 | 2026-06-11 13:38 | 2026-06-23 | 2026-06-23 20:21 | 2026-07-11 |  | 2026-07-18 |  | 2026-06-10 | 2026-06-10 22:00 | 2026-06-12 | 2026-06-11 13:39 | 2026-06-11 | 2026-06-12 14:26 | 2026-06-17 | 2026-06-17 17:57 |  |  |  |  | 2026-06-23 | 2026-07-14 11:15 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-18 | 2026-06-23 20:18 | Site is RTMI | 2026-06-04 | 2026-06-04 18:10 | 1073622 | 189687 | 0 | 0 | 0 | 0 | 1073622.165 | 177700 | 2026-06-18 18:42:34 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Done DEM Dates -Â DEM 1 - Cx want the meeting on weekend by 2nd half DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% cx said that he will discuss with mrunali as it was communicated too him that after 15days payment has to be done Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-18 16:51:48 +0530 | Vishakha Vaishnav | Tried connecting cx , didn't answered | 2026-06-18 15:32:23 +0530 | Preeti Agarwal | Some Image was uploaded | 2026-06-24 | 2026-06-23 20:23 | 2026-07-12 |  | Under Construction | 2026-07-31 | 2026-06-10 | 126331 | Ravi Roy
20397 | Turnkey | 2026-06-01 | Sambath | Birla Tissya | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | DEM1 | 652499 | 69999 | 917344 | 0 | 0 | 15 | 0 | 0 | 60501 | 261000 | 260999.6 |  |  | 2026-06-05 | 2026-06-14 11:22 | 2026-06-16 | 2026-06-16 11:08 | 2026-06-19 | 2026-06-23 19:16 | 2026-07-13 |  | 2026-07-20 |  | 2026-07-27 |  | 2026-06-23 | 2026-06-27 15:06 | 2026-06-24 | 2026-06-27 15:11 | 2026-06-27 | 2026-06-30 13:07 | 2026-07-03 | 2026-07-03 12:40 |  |  |  |  | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-07-04 |  | Unknown | 2026-06-05 | 2026-06-06 13:17 | 777410 | 139933 | 0 | 0 | 0 | 0 | 763062.3014 | 125999 | 2026-07-14 17:05:12 +0530 | Rajeshwari S | Welcome call done along with designer Non RTMI Project - possession expected in Sept. end. Client not sure on IM permission from builder. He is Canada rite now. Will be back and confirm back to us on the same. 1st DM expected on 28th July. Will clear the 10% due after 28th July. Aligned with the process. | 2026-06-30 13:05:29 +0530 | Kushal S | Some Image was uploaded | 2026-06-27 17:22:44 +0530 | Bency Chacko |  | 2026-07-14 |  | 2026-07-21 |  | Under Construction | 2026-09-01 | 2026-06-14 | 69999 | Ravi Roy
20399 | Turnkey | 2026-06-01 | Rupendra Khinda | Kalpataru Vivant | MUM - GOR | Yes | Riddhi Deshpande | Reshma Melanta | Kashmira Nerurkar | [5 empty] | Manasi Patil |  | Active | Design | DEM1 | 1040797 | 212958 | 1377704 | 0 | 0 | 29 | 0 | 0 | 0 | 459338 | 368500.8 |  |  | 2026-05-31 | 2026-06-16 10:56 | 2026-06-16 | 2026-06-16 11:53 | 2026-06-19 | 2026-06-16 12:09 | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-06-06 | 2026-06-15 15:23 | 2026-06-07 | 2026-06-16 10:59 | 2026-06-17 | 2026-06-16 17:58 | 2026-06-20 | 2026-06-20 18:27 |  |  |  |  | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-08-31 |  | 2026-09-01 | [6 empty] | 2026-09-19 |  | 2026-09-28 |  | 2026-09-27 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-10-01 |  |  |  | 2026-10-23 |  | 2026-10-25 |  | 2026-10-26 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-05-31 | 2026-06-15 15:23 | 1167546 | 210158 | 0 | 0 | 0 | 0 | 1160278.2873 | 195893 | 2026-07-14 13:45:51 +0530 | Kashmira Nerurkar |  | 2026-06-25 18:55:32 +0530 | Riddhi Deshpande | DDM1: have asked for transition | 2026-06-20 18:26:14 +0530 | Reshma Melanta | Date: June 20, 2026 Topic: Project Status, Possession Timeline, and Team Onboarding Key Discussion PointsPossession Status: The Customer (CX) does not currently have possession of the flat. Tentative possession is expected around August 2026 (exact date to be confirmed). Financials: 20% of the payment has already been completed by the CX. Team Updates: The new Designer, Design Manager (DM), and Bonito Care have been successfully added to the communication group. | 2026-07-11 |  | 2026-07-18 |  | Under Construction | 2026-08-31 | 2026-06-13 | 152667 | Ravi Roy
20402 | Turnkey | 2026-06-01 | Deeraj Reddy | MYTHRI SIGNATURE | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 1689590 | 9999 | 0 | 0 | 0 | 36 | 0 | 158960 | 168959 | 715578 | 636094.4 |  |  | 2026-06-04 | 2026-06-09 12:29 | 2026-06-07 | 2026-06-09 12:32 | 2026-06-12 |  | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-06-12 |  | 2026-06-13 |  | 2026-06-13 |  | 2026-06-14 | [5 empty] | 2026-06-20 |  | 2026-06-28 |  | 2026-06-29 |  |  |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-06-15 |  | Unknown | 2026-06-04 | 2026-06-05 12:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1431856 | 257734 | 2026-06-16 15:33:47 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-16 14:19:50 +0530 | Priyanka Gs | This client is currently under follow-up. The opportunity is expected to close once the client receives an update from the builder regarding the project status and possession timeline. | 2026-06-09 11:40:46 +0530 | Priyanka Gs | Some Image was uploaded | 2026-06-20 |  | 2026-06-27
20403 | Sub Project |  | Ganesh Kadam Kadam | BDD Redevelopment, worli | MUM - Thane |  | Honey Thakkar |  | Anil Kuwar |  | Viraj Jadhav | Faizal Shaikh | Rizwan Mistry |  |  | Prasad Bhivaji Hande | Active | Preproduction | 2D | 78691 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 91717 | 0 |  |  | 2026-06-05 | 2026-06-07 13:58 | 2026-06-06 | 2026-06-07 13:58 | 2026-06-07 | 2026-06-07 13:58 | 2026-06-08 | 2026-06-07 13:58 | 2026-06-08 | 2026-06-07 13:59 | 2026-06-08 | 2026-06-07 13:59 | 2026-06-10 | 2026-06-07 13:58 | 2026-06-08 | 2026-06-07 13:58 | 2026-06-07 | 2026-06-07 13:58 | 2026-06-08 | 2026-06-07 13:58 |  |  |  |  | 2026-06-08 | 2026-06-07 13:58 | 2026-06-08 | 2026-06-07 13:59 | 2026-06-08 | 2026-06-07 13:59 |  |  | 2026-06-08 | 2026-07-07 16:08 | 2026-07-05 |  | 2026-07-08 |  | 2026-07-09 | [6 empty] | 2026-07-27 |  | 2026-08-05 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-08 |  |  |  | 2026-08-30 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | 2026-07-07 |  | 2026-06-08 | 2026-06-07 13:58 | Unknown | 2026-06-05 | 2026-06-07 13:58 | 0 | 0 | 0 | 0 | 0 | 0 | 124314 | 22376 | [9 empty] | 2026-06-08 | 2026-06-07 13:58 | 2026-06-08 | 2026-06-07 13:59
20404 | Turnkey | 2026-06-01 | Devika | Kalpatru aura | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1793951 | 9999 | 0 | 0 | 0 | 26 | 0 | 169396 | 179395 | 717580 | 717580.4 |  |  | 2026-06-05 | 2026-06-09 15:49 | 2026-06-09 | 2026-06-19 02:21 | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-21 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-08-08 |  | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-08-03 |  | Unknown | 2026-06-05 | 2026-06-05 20:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1520298 | 273653 | 2026-06-23 11:38:22 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-23 11:37:15 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-19 02:20:28 +0530 | Moksh Mehta | DCM: Client Name:- Devika Property:- Aurus Possesion Date:- Sept'26 Sq Ft:- 918 sqft No of Members : - Couple (35+), Daughter (5+) Duration of Stay: - 5-10 Yrs Budget:- 20L w/o Civil Ent: Shoe Rack (20 - 25 Pairs)PartitionWall Concepts. Living Room :- No TV Unit 3-Seater Sofa (4-5 Persons)Wall concepts.Informal Seating Area Dining Area :- Kitchen area will be only Dining area 6 Seater Dining Table.Crockery cum Bar UnitWall Concepts. Kitchen :- Guest Bedroom will be Converted to Kitchen Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos. Master Bedroom :- King Size BedWardrobe with LoftSide tableDresser UnitWorkstation Bedroom :- Single size BedWardrobe with LoftDresser with Side TableStudy TableWalk - In WR to be created in the Washroom as the same washroom will closed and will be used as the WIW Space Bathroom's Base Vanity Unit's for all Misc:- False CeilingPaintingElectrification | 2026-08-08 |  | 2026-08-15
20406 | Turnkey | 2026-06-01 | Rani rohra | MICL Aaradhya | MUM - GOR | Yes | Umang Ratnani | Reshma Melanta | Shantanu Parakh | [5 empty] | Moni Sahani |  | Active | Preproduction | DEM2 | 899029 | 179806 | 1161422 | 0 | 0 | 8 | 0 | 0 | 0 | 365331 | 353892.4 |  |  | 2026-06-05 | 2026-06-09 12:46 | 2026-06-09 | 2026-06-09 15:27 | 2026-06-12 | 2026-06-11 19:55 | 2026-07-05 | 2026-07-05 19:34 | 2026-07-11 |  | 2026-07-18 |  | 2026-06-12 | 2026-06-11 19:44 | 2026-06-12 | 2026-06-11 20:20 | 2026-06-11 | 2026-06-12 15:39 | 2026-06-16 | 2026-06-16 19:41 |  |  |  |  | 2026-07-05 | 2026-07-07 18:34 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-17 | 2026-07-05 19:12 | Site is RTMI | 2026-06-05 | 2026-06-05 16:13 | 984256 | 177166 | 0 | 0 | 0 | 0 | 979377.526 | 161825 | 2026-07-05 19:26:30 +0530 | Priyanka Murarka | DEM1- 05/07 Bedroom - Wallpaper behind bed showcase to be in front of bed Window seating with 1 base storage & 1 side tall storage Converted openable wardrobe to sliding wardrobe Added 1 sleek side storage next to wardrobe Kitchen Glass shutter on sides of chimney need to create a small platform on opposite to main platform Loft to be added on the fridge side Living room Gypsum design - saved as per reference Tv unit to have corner arch - color blocking Wall ledges to be above the workstation area To have more electrical points for table lamp, artificial lighting elements. Passage area to have arch at the entrance - need to give the designing accordingly Since there is no ceiling lights provided by builder need to create false ceiling in bedroom & living room | 2026-07-03 17:15:58 +0530 | Meet Shah | Others: | 2026-06-18 17:03:23 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : cx said that IM can be done after possession only need to cx with Priyanka patel if any chances for early IM DEM Dates -Â DEM 1 - Cx will update us in group DEM 2 - TBD DEM 3 - TBD Possession date : July 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-07-06 | 2026-07-05 19:40 | 2026-07-12 |  | Under Construction | 2026-07-04 | 2026-06-11 | 116142 | Ravi Roy
20409 | Turnkey | 2026-06-01 | SUDHAKAR KOTIAN | MICL Aaradhya Parkwood | MUM - GOR | Yes | Rajnish Mishra | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1033657 | 137527 | 1375269 | 0 | 0 | 36 | 0 | 0 | 69204 | 448709 | 378216.4 |  |  | 2026-06-05 | 2026-06-05 18:40 | 2026-06-05 | 2026-06-06 19:54 | 2026-06-07 | 2026-06-09 12:24 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-09 | 2026-06-09 16:36 | 2026-06-10 | 2026-06-09 16:52 | 2026-06-09 | 2026-06-09 18:04 | 2026-06-13 | 2026-06-13 12:39 |  |  |  |  | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-06-05 | 2026-06-05 18:39 | 1165482 | 209786 | 0 | 0 | 0 | 0 | 1144525.0822 | 186058 | 2026-07-10 15:48:13 +0530 | Vishakha Vaishnav | TRIED CONNECTING WITH CX , DIDN'T RESPONDED DROPPED MESSAGE ON WHATSAPP | 2026-06-13 12:38:43 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement: Site is not accessible DEM Dates -Â DEM 1 - Cx said that next week from tuesday he is travelling he will confirm us when can we align for the meeting DEM 2 - TBD DEM 3 - TBD Possession date : Mid july Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-09 18:03:31 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: 15th July 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible * DEM 1 After 15th July 2026 * 10% Payment Stage by 19th June 2026 *Transaction will be B2C self-funding. *No civil work planned in client's scope of work Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11,44,526 Offers Discussed During the Call: 100% GST Waiver Laminate Upgrade - Jun 26 Campaign Free Bed Offer PM fee waiver (7.5%) Final Closing Value Discussed: 10,33,657 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-19 |  | 2026-06-26 |  | Under Construction | 2026-07-15 | 2026-06-07 | 137527 | Ravi Roy
20410 |  | 2026-06-01 | HRBR |  | BNG - HRBR | Yes | Arjun M V | Rajeshwari S | Shibin Lal | Vaishali G | Vaishali G | Harshit Choudhary | Saddam Hussain Z M | Murali S | Pradeep Bhat | Abdul Shafeen | Active | Production | Production | 1223235 | 0 | 0 | 0 | 1223235 | 1 | 0 | 0 | 0 | 0 | 1223235 |  |  | 2026-06-05 | 2026-06-06 11:15 | 2026-06-06 | 2026-06-06 11:15 | 2026-06-06 | 2026-06-06 11:15 | 2026-06-07 | 2026-06-06 11:15 | 2026-06-07 | 2026-06-06 11:16 | 2026-06-20 | 2026-06-20 17:52 | 2026-06-09 | 2026-06-06 11:15 | 2026-06-07 | 2026-06-06 11:15 | 2026-06-06 | 2026-06-06 11:15 | 2026-06-07 | 2026-06-06 11:15 |  |  |  |  | 2026-06-07 | 2026-06-06 11:15 | 2026-06-19 | 2026-06-19 12:52 | 2026-06-20 | 2026-06-20 15:32 |  |  | 2026-06-21 | 2026-06-23 16:04 | 2026-06-27 | 2026-06-27 11:14 | 2026-06-28 | 2026-06-27 11:35 | 2026-06-29 | 2026-06-27 13:20 |  |  |  |  | 2026-06-27 18:07 | 2026-07-15 | 2026-07-14 21:03 | 2026-07-23 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-28 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-08 |  | 2026-08-09 | [5 empty] | 2026-06-27 | 2026-06-27 11:48 | 2026-06-07 | 2026-06-06 11:15 | Unknown | 2026-06-05 | 2026-06-06 11:15 | 0 | 0 | 0 | 0 | 1036639 | 186595 | 1036639 | 186595 | [9 empty] | 2026-06-07 | 2026-06-06 11:16 | 2026-06-07 | 2026-06-06 11:16
20415 | Turnkey | 2026-06-01 | Jyoti Goenka | Sheetal Infinity | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 6545885 | 9999 | 0 | 0 | 0 | 29 | 0 | 644590 | 654589 | 2833370 | 2403338 |  |  | 2026-06-06 | 2026-06-16 12:29 | 2026-06-06 | 2026-06-16 15:23 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-08-05 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-30 |  | 2026-09-04 |  |  |  | 2026-10-13 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-06 | 2026-06-06 16:35 | 0 | 0 | 0 | 0 | 0 | 0 | 5547360 | 998524 | 2026-06-17 16:57:54 +0530 | Pratima Kajwe | CDP: MOM Living room: Mandir position to be taken outside current indication of pooja room. Kitchen to be considered as open kitchen as the current size is less for utility purpose (3ft. outside) and sofa- dining area to be interchanged. one option of reducing space in living room, Parent's room: Increase internal room space by 2ft, to accommodate wardrobe of 10ft. TV space and flush door concept for bathroom doorCurved door concept to be taken into consideration. Master bedroom: Option 2 of bed position on bathroom wall with TV on bed wall, and cozy section of the front.Opening of master bedroom to be done via walk-in wardrobe. Daughter's bedroom Folding study table to be considered. Dressing near passage areaTV near window (standalone) Kids room Bed position to be on the bathroom wallBathroom opening to be interchanged and bedroom door to be taken behind Bathtub provisionStudy table near window and activity wall next to it. | 2026-06-17 11:48:14 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-06-17 11:47:54 +0530 | Pratima Kajwe | CDP: REC 20415 - Celebrity Design Presentation (CDP) with the customer-20260616_120837UTC-Meeting Recording.mp4 | 2026-06-24 |  | 2026-07-01
20416 | Turnkey | 2026-06-01 | Neha Keer | RUNWAL FOREST | MUM - GOR | Yes | Manisha Dubey | Manzoor Shaikh | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1276742 | 255349 | 1798938 | 0 | 0 | 28 | 0 | 0 | 0 | 573286 | 448107.2 |  |  | 2026-06-06 | 2026-06-06 14:08 | 2026-06-06 | 2026-06-16 15:25 | 2026-06-19 | 2026-06-16 16:42 | 2026-06-24 |  | 2026-08-23 |  | 2026-08-30 |  | 2026-06-16 | 2026-06-16 16:56 | 2026-06-17 | 2026-06-16 19:01 | 2026-06-16 | 2026-06-17 10:15 | 2026-06-19 | 2026-06-19 18:54 |  |  |  |  | 2026-06-25 | 2026-07-14 19:43 | 2026-08-25 |  | 2026-08-26 |  |  |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 | [6 empty] | 2026-09-23 |  | 2026-10-02 |  | 2026-10-01 |  | 2026-10-02 |  | 2026-10-03 |  | 2026-10-05 |  |  |  | 2026-10-27 |  | 2026-10-29 |  | 2026-10-30 | [5 empty] | 2026-09-03 |  | 2026-06-20 |  | Unknown | 2026-06-06 | 2026-06-06 14:07 | 1526622 | 272315 | 0 | 0 | 0 | 0 | 1495780.438 | 235887 | 2026-06-19 18:52:53 +0530 | Manzoor Shaikh | "Welcome call done. Initial measurement planned 1st week of July and post will plan the DEM1 DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : July End Customer will make 10% post LFM Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-17 10:15:22 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: July 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is not accessible. * DEM 1 Client mentioned it's planned for next week * 10% Payment Stage by 27th (after 1st DEM) *Transaction will be B2C self-funding. *Client will be doing some changes in washroom, will take the designer's advice and then plan. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 14,95,781 Offers Discussed During the Call: Design Fee Waiver (2.5%) Free Hob & Chimney Offer Laminate Upgrade - Jun 26 Campaign Free Shoerack Offer PM fee waiver (7.5%) 100% GST Waiver Final Closing Value Discussed: 12,76,743 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-16 19:32:22 +0530 | Harshaan Tiku | Some Image was uploaded | 2026-06-25 |  | 2026-08-24 |  | Under Construction | 2026-07-31 | 2026-06-16 | 179894 | Ravi Roy
20417 | Turnkey | 2026-06-01 | Saravanan P | Sun Grace | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Kaminahal Rahiman |  | Active | Preproduction | DEM2 | 1273123 | 254625 | 1558962 | 0 | 0 | 18 | 0 | 0 | 0 | 544767 | 473730.8 |  |  | 2026-06-06 | 2026-06-06 16:59 | 2026-06-20 | 2026-06-20 22:34 | 2026-06-23 | 2026-06-23 18:56 | 2026-06-30 | 2026-06-27 19:55 | 2026-07-15 |  | 2026-08-05 |  | 2026-06-23 | 2026-06-23 19:54 | 2026-06-24 | 2026-06-24 11:22 | 2026-06-24 | 2026-06-25 11:15 | 2026-06-25 | 2026-06-25 14:17 |  |  |  |  | 2026-07-01 | 2026-06-27 19:04 | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-06-26 | 2026-06-27 19:53 | Site is RTMI | 2026-06-06 | 2026-06-06 16:47 | 1321155 | 237807 | 0 | 0 | 0 | 0 | 1273123 | 229162 | 2026-06-25 11:15:24 +0530 | Sanjana Swami | Possession Status: RTMI It's a renovation property Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+10 business days. Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM already done * DEM 1 Preferred on weekends * 10% Payment Stage 15th July 2026 *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 12,73,123 Offers Discussed During the Call: 100% GST Waiver Laminate Upgrade - Jun 26 Campaign Free Hob & Chimney Offer Final Closing Value Discussed: 12,73,123 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-24 14:14:55 +0530 | Sanjana Swami |  | 2026-06-24 13:10:32 +0530 | Sanjana Swami |  | 2026-06-28 | 2026-06-27 19:56 | 2026-07-16 |  | RTMI |  | 2026-06-21 | 254625 | Ravi Roy
20418 | Sub Project |  | Swapnil Amale | Shantinath Temporary | MUM - Thane |  | Shraddha Pansare | Anamika Dolai | Sneha Kadam | [7 empty] | Active | Preproduction | 3D Sign off | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-06 | 2026-06-07 12:26 | 2026-06-07 | 2026-06-07 12:26 | 2026-06-07 | 2026-06-07 12:26 | 2026-06-08 | 2026-06-07 12:27 | 2026-06-08 | 2026-06-07 12:27 | 2026-06-08 | 2026-06-07 12:28 | 2026-06-10 | 2026-06-07 12:26 | 2026-06-08 | 2026-06-07 12:26 | 2026-06-07 | 2026-06-07 12:26 | 2026-06-08 | 2026-06-07 12:26 |  |  |  |  | 2026-06-08 | 2026-06-07 12:27 | 2026-06-08 | 2026-06-07 12:27 | 2026-06-08 | 2026-06-07 12:27 |  |  | 2026-06-08 | 2026-06-07 12:28 | 2026-06-08 | 2026-06-26 15:46 | 2026-06-27 |  | 2026-06-28 | [6 empty] | 2026-07-16 |  | 2026-07-25 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-28 |  |  |  | 2026-08-19 |  | 2026-08-21 |  | 2026-08-22 | [5 empty] | 2026-06-26 |  | 2026-06-08 | 2026-06-07 12:26 | Unknown | 2026-06-06 | 2026-06-07 12:26 | 0 | 0 | 0 | 0 | 16309.22 | 0 | 16309.22 | 0 | 2026-06-09 12:38:17 +0530 | Shraddha Pansare | Some Image was uploaded | [6 empty] | 2026-06-08 | 2026-06-07 12:27 | 2026-06-08 | 2026-06-07 12:27
20419 | Turnkey | 2026-06-01 | Mr. Sandeep | Brigade Orchads Ivory | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1055921 | 145167 | 1451673 | 0 | 0 | 21 | 0 | 0 | 66017 | 422368 | 422368.4 |  |  | 2026-06-06 | 2026-06-06 14:40 | 2026-06-13 | 2026-06-20 08:02 | 2026-06-23 | 2026-06-21 12:09 | 2026-07-11 |  | 2026-09-11 |  | 2026-09-18 |  | 2026-06-21 | 2026-06-21 12:46 | 2026-06-22 | 2026-06-24 11:23 | 2026-06-24 | 2026-06-24 12:55 | 2026-06-30 | 2026-06-30 20:54 |  |  |  |  | 2026-09-05 |  | 2026-09-13 |  | 2026-09-14 |  |  |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 | [6 empty] | 2026-10-12 |  | 2026-10-21 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-22 |  | 2026-10-24 |  |  |  | 2026-11-15 |  | 2026-11-17 |  | 2026-11-18 | [5 empty] | 2026-09-22 |  | 2026-08-31 |  | Unknown | 2026-06-06 | 2026-06-06 14:38 | 1230231 | 221441 | 0 | 0 | 0 | 0 | 1202829.553 | 198615 | 2026-06-24 12:54:41 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: July 2026 Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Client will let us know about the site accessibility for IMs * DEM 1 After IMs, client will let us know * 10% Payment Stage 4th July 2026 *Client has not yet planned any civil work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 12,02, 830 Offers Discussed During the Call: Free Shoerack Offer PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Silver Coin 21g Laminate Upgrade - Jun 26 Campaign Final Closing Value Discussed: 10,55,922 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-24 11:43:06 +0530 | Bency Chacko | Some Image was uploaded | 2026-06-24 11:42:54 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-07-12 |  | 2026-09-12 |  | Under Construction | 2026-07-31 | 2026-06-20 | 145167 | Ravi Roy
20420 | Turnkey | 2026-06-01 | Manu Garg | L&T 77 crossword | MUM - GOR | Yes | Anjali Jain | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Ashutosh Singh |  | Active | Preproduction | DEM2 | 1808306 | 328622 | 2084624 | 0 | 0 | 3 | 0 | 0 | 0 | 820959 | 658724.8 |  |  | 2026-06-06 | 2026-06-06 14:54 | 2026-06-09 | 2026-06-09 16:31 | 2026-06-21 | 2026-06-21 20:37 | 2026-07-13 | 2026-07-12 19:49 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-21 | 2026-06-21 20:21 | 2026-06-22 | 2026-06-21 21:47 | 2026-06-21 | 2026-06-24 11:19 | 2026-06-24 | 2026-06-24 19:08 |  |  |  |  | 2026-06-30 | 2026-07-12 17:50 | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-06-25 | 2026-07-12 19:30 | Site is RTMI | 2026-06-06 | 2026-06-06 14:47 | 1766630 | 317993 | 0 | 0 | 0 | 0 | 1927888.4202 | 325495 | 2026-07-12 19:42:35 +0530 | Anjali Jain | DDM1: Client swapped the position of living set, tv to be placed behind the dining table, 3d model changed on the spot to show the client Client specified about the crockery unit, to be sleek without glass finish, and on top of that on wall, wall design modified according to the proportion of tv and placement of loose furniture in living room Tall unit added for crockery, height to be reached till ceiling, loft to be added on top of it. Wall paneling to be done behind the sofa Living room unit removed as the crockery unit is completely set behind the dining Ledge to be added and light to be added below it for look Bar unit accumulated with the crockery as well Living room sleek glass unit for soviniers KitchenPoints of chimney to be checked Client needs more platform space Needs pantry tall unit and space above platform for all the appliances Site conditions to be checked for extention of platform Sonâ€™s bedroomStudy unit to be made bigger TV unit to be added along with ledges to add books Ledges to be added below the tv as well Mirror to be provided inside the wardrobe Wardrobe to be increased in length y 8â€, 3 partitions to be provided inside for coats hanging and other clothes Daughterâ€™s bedroom - Cupboards to be moved to the door wall, Console to be added below tv unit Side table to be added on one side of the wall Wardrobe internals to be remained the same Master bedroom - Window seating area, added the wall shelves on the corner Wardrobe loft to be continued on the tv wall till the door Study room - Mandir to be rotated Storage to be completely covered over the wall, with wardrobe and loft above Entire storage unit to be created with the study table Wardrobe internal â€“ storage for luggages and coats Final discussionAll the screenshot of designs and changes shared with the client Updated quotation, discussion with additional items price increase information provided to the client. Colour preference of client Daugherâ€™s room â€“ Maroon colour preffered with beading, no white lights, only warm lights, colour changing light, offwhite colour as well preffered Wall lights, check with the vendor about adding light behind the bed Laminate finishes finalised â€“ LAM SL SD 1MM 2289 CAROLINA ROVERD MC â€“ 1018 HG FC- Cherry brown Sonâ€™s bedroom color tone, we have to go for earthy colors Master bedroom â€“ Arch with wallpaper, Indian touch, beige, brown, and maroon colors Overall house to look warm and earthy False ceiling â€“ to be decided and checked after IM | 2026-06-24 19:11:45 +0530 | Christopher Macwan | Welcome call done. Initial measurement not done as would receive possession by End of November 2026 DEM Dates -Â DEM 1 - Customer wants DEM's on Weekends. Need to confirm meeting for 4th July 2026 with the designer DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of November 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-24 11:19:56 +0530 | Bency Chacko |  | 2026-07-13 | 2026-07-12 19:53 | 2026-07-19 |  | Under Construction | 2026-12-31 | 2026-06-21 | 208462 | Ravi Roy
20421 | Turnkey | 2026-06-01 | Debakshi Roy | SOBHA Neopolis | BNG - HSR | Yes | [8 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 2144514 | 9999 | 0 | 0 | 0 | 31 | 0 | 204452 | 214451 | 912923 | 802688 |  |  | 2026-06-06 | 2026-06-06 14:56 | 2026-06-06 | 2026-06-12 13:14 | 2026-06-15 |  | 2026-06-22 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-06-15 |  | 2026-06-16 |  | 2026-06-16 |  | 2026-06-17 | [5 empty] | 2026-06-23 |  | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-18 |  | Unknown | 2026-06-06 | 2026-06-06 14:47 | 0 | 0 | 0 | 0 | 0 | 0 | 1817384 | 327129 | 2026-06-12 16:45:05 +0530 | Aman Kumar | Client Observation Debakshi ¦ Sobha Neopolis (3 BHK) Mrs. Debakshi is highly design-oriented and is looking for aesthetically appealing interiors. Both husband and wife are IT professionals. The husband is interested in gaming, so we can propose an enhanced entertainment setup with a large TV unit and a dedicated gaming-friendly space. Since the client is design-centric, we can focus on premium design elements, customized finishes, and overall aesthetics across the home. The property is a 3 BHK at Sobha Neopolis, with an expected handover in September. | 2026-06-06 16:11:59 +0530 | Priyamvada PV | Some Image was uploaded | 2026-06-06 15:56:39 +0530 | Priyamvada PV | RGM Date : 06.06.26 CDP date : 13.06.26 11.30am PID:Â Name : Anirudh, Debakshi Roy From Mumbai , Kolkata Profession : IT Budget : 15L for modular furniture including lighting excluding loose furniture, painting, decorativeÂ Property : Shobha Neopolis Location : Panathur ORR Site Access Date : July'26 Site possession (Ready for Interiors): Sep'26 Main door facing : West Total Members :Â 2 Kids - Name & Age : NA Theme : Scandinavian theme (with light considered) Kitchen can be darker shade Scope of Work : Foyer - storage console with mirror design on wall Outside shoe rack - client scope TV unitÂ TV storage for large wall preferrable entire wall 75" tv size music system, playstation, channel manager (for wire) Tall decor storage Existing 3 seater sofa, godfather/accent chair (1+1)Â 4 seater rectangular table (Existing with marble top) (Sofa & dining chairs upholstery change - to be confirmed by BD scope if) Crockery Base & wall glass storage (minimal) on wall opp to kitchenÂ Balcony (Design to be shown with seating)- wont be BD scopeÂ Swing (Existing 1S)Â Kitchen L shape base units, Wall units appliances - DW, Single door fridge M/W, mixer, air fryer Utility - sink unit, WM space Storage Granite (kitchen) -BD scope Granite - (Utility ) - Builder scope Existing tilesÂ (Removal to be checked) Installation only for BD scope, supply - client scope MBR -Â (BR-1) King size bed space with 2 side tables sliding WR (no negotiation) with loft on opp of cotÂ short mirror on left of cot No study table Vanity base storage for all vanities Study room (BR- 3) Wardrobe/bookshelf (with some open units) along with workstation sofa cum bed to right of entry GBR (BR-2) queen size bed space 8'H hinged wardrobe with loft Wall mounted TVÂ Plain FC (As per ref image ) for CA, MBR Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â Â | 2026-06-23 |  | 2026-06-30
20424 | Turnkey | 2026-06-01 | S3 Printeria | GeeCee Emerald | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anant Giri |  | Hold | Design | DEM1 | 1200100 | 144999 | 1445480 | 0 | 0 | 2 | 4 | 0 | 95021 | 535392 | 424688 |  |  | 2026-06-06 | 2026-06-06 20:41 | 2026-06-12 | 2026-06-12 19:36 | 2026-06-28 | 2026-06-28 17:55 | 2027-01-03 |  | 2027-01-10 |  | 2027-01-17 |  | 2026-06-28 | 2026-06-28 23:00 | 2026-06-29 | 2026-06-28 23:02 | 2026-06-28 | 2026-07-09 12:26 | 2026-07-11 | 2026-07-10 17:29 |  |  |  |  | 2027-01-04 |  | 2027-01-12 |  | 2027-01-13 |  |  |  | 2027-01-20 |  | 2027-01-21 |  | 2027-01-22 |  | 2027-01-23 | [6 empty] | 2027-02-10 |  | 2027-02-19 |  | 2027-02-18 |  | 2027-02-19 |  | 2027-02-20 |  | 2027-02-22 |  |  |  | 2027-03-16 |  | 2027-03-18 |  | 2027-03-19 | [5 empty] | 2027-01-21 |  | 2026-12-30 |  | Unknown | 2026-06-06 | 2026-06-06 20:39 | 1227268 | 218211 | 0 | 0 | 0 | 0 | 1200100 | 213321 | 2026-07-11 12:20:50 +0530 | Anil Jagtap |  | 2026-07-10 17:36:10 +0530 | Anil Jagtap | Welcome call done : yes Meeting Dates - Sep *26 DEM 1 : Sep Possession date : December *26 10% payment aligned : December *26 Periskope Number added : yes Escalation Matrix added : yes | 2026-07-09 15:33:56 +0530 | Anant Giri | Others: | 2027-01-04 |  | 2027-01-11 |  | Under Construction | 2026-12-31 | 2026-06-28 | 144999 | Ravi Roy
20425 | Turnkey | 2026-06-01 | Parshwa Aluminium And Hardware | Aerovista | MUM - GOR | Yes | Zoya Ansari | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 1037054 | 207411 | 1465630 | 0 | 0 | 15 | 0 | 0 | 0 | 458317 | 371326.4 |  |  | 2026-06-06 | 2026-06-16 12:46 | 2026-06-06 | 2026-06-16 13:12 | 2026-06-19 | 2026-06-16 14:00 | 2026-06-28 | 2026-06-28 21:04 | 2026-07-04 |  | 2026-07-11 |  | 2026-06-14 | 2026-06-15 00:43 | 2026-06-17 | 2026-06-19 13:16 | 2026-06-19 | 2026-06-19 14:10 | 2026-06-21 | 2026-06-21 17:46 |  |  |  |  | 2026-06-28 | 2026-06-30 18:37 | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-22 | 2026-06-28 21:00 | Site is RTMI | 2026-06-06 | 2026-06-06 16:35 | 1242059 | 223570 | 0 | 0 | 0 | 0 | 1234460.039 | 195219 | 2026-06-21 17:46:00 +0530 | Vishakha Vaishnav | "Welcome call done Initial measurement : as per cx it is aligned for 25th june need to confirm with designer DEM Dates -Â DEM 1 - need to align after IM DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-20 17:23:27 +0530 | Vishakha Vaishnav | Tried connecting cx , didn't answered | 2026-06-19 14:09:45 +0530 | Athul Ajaykumar | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend) * DEM 1 Tentatively scheduled for (27th June 2026) * 10% Payment Stage will close after the layout finalization * B2B * Civil work - Yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Shoerack Offer PM fee waiver (5%) Free Hob & Chimney Offer Laminate Upgrade - Jun 26 Campaign 100% GST Waiver Design fee waiver (5%) Final Closing Value Discussed: 10,37,055 Checklist terms descoping, agreement terms are cleared Client VOC: The client informed us that complete kitchen civil work is required, which is expected to take around 10 to 15 days to complete. | 2026-06-29 | 2026-06-28 21:07 | 2026-07-05 |  | RTMI |  | 2026-06-14 | 146563 | Ravi Roy
20426 | Turnkey | 2026-06-01 | Swati Gupta | Prestige City Meridian Park | BNG - HSR | Yes | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | 10% Payment | 2281072 | 9999 | 0 | 0 | 0 | 22 | 0 | 218108 | 228107 | 953359 | 871498.8 |  |  | 2026-06-06 | 2026-06-06 19:18 | 2026-06-13 | 2026-06-20 08:11 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-06 | 2026-06-06 16:24 | 0 | 0 | 0 | 0 | 0 | 0 | 1933112 | 347960 | 2026-06-20 14:00:41 +0530 | Ankita Agarwal | CDP: Client Name: Mrs. Swati Manoj Dining AreaDiscussed shoe unit; finalization pending and to be discussed further.Pooja unit to remain in the same location as previously planned.Dining wall to feature wallpaper with beading/trims.False ceiling to be designed with a 450 mm border.No gypsum panel at the entrance area.Wallpaper design to incorporate metal strip detailing.Shoe unit design and storage requirements are still pending discussion.Crockery base unit to be extended till the end of the wall.Decorative ledges/shelves to be incorporated above the crockery unit.Master BedroomRemove the existing bed-back panel design.Introduce wall trims with wallpaper within an arch-shaped feature wall behind the bed.Overall design to maintain an elegant and modern aesthetic. | 2026-06-20 10:39:56 +0530 | Ankita Agarwal | Some Image was uploaded | 2026-06-20 10:38:55 +0530 | Ankita Agarwal | Some Image was uploaded | 2026-07-01 |  | 2026-07-08
20428 | Turnkey | 2026-06-01 | SHRIYA_MISHRA | Saranya Swarovski | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 1590496 | 9999 | 0 | 0 | 0 | 39 | 0 | 149051 | 159050 | 648708 | 623689.2 |  |  | 2026-06-06 | 2026-06-06 17:07 | 2026-06-09 | 2026-06-09 11:22 | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-07-08 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-06-25 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-20 |  | Unknown | 2026-06-06 | 2026-06-06 16:57 | 0 | 0 | 0 | 0 | 0 | 0 | 1644880.4772 | 286289 | 2026-06-16 15:54:08 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-06-09 11:24:50 +0530 | Rituparna Chakraborty | Some Image was uploaded | 2026-06-09 11:23:33 +0530 | Rituparna Chakraborty | Shriya & Manish Flap down shoe unit - 20pairs Safety door , carving on main doorÂ 3 seater + 1 seater 2 pcs+ 1 recliner TV unit position we can see both options . 60" TV , home theater system, Simple TV unit 4 seater dining , either moveable or sofa & dining seatingÂ Puja in the balcony side corner , Crockery unit Dark clr for base cabinet , no glass cabinet near hob ,backsplashÂ white , sink , dish tray, tall unit , pantry , dishwasher, counter top option ,wicker basket MBR queen bed with storage , if possible with posters like EC , Wardrobe hinge shutter, closed dresser tall & drawer, workstation Different shades of ivory & brownÂ KBR existing queen bed , wardrobe solid & fluted design , Dresser with side table .Â GBR Sofa cum bed , wardrobe , library with study table , paint patternÂ GBR balcony - barÂ KBR balcony- laundry & janitor unitÂ Living balcony - green wall , washbasinÂ PaintingÂ wardrobe lights Vanity & mirrorÂ Arches to be included at placesÂ Jamblining for kitchenÂ 14th June -1st halfÂ | 2026-06-25 |  | 2026-07-02
20429 | Turnkey | 2026-06-01 | Binia Amin Nissar Ahmed Shaikh | MICL Aaradhya Parkwood | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Rahul Kumawat |  | Active | Prospect | DCM Due | 2351636 | 9999 | 0 | 0 | 0 | 39 | 0 | 225165 | 235164 | 1045768 | 835540.4 |  |  | 2026-06-06 | 2026-06-06 20:31 | 2026-06-10 | 2026-06-10 12:38 | 2026-06-28 |  | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-06-13 |  | 2026-06-14 |  | 2026-06-14 |  | 2026-06-15 | [5 empty] | 2026-06-21 |  | 2026-06-29 |  | 2026-06-30 |  |  |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 | [6 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-08 |  | 2026-06-16 |  | Unknown | 2026-06-06 | 2026-06-06 20:30 | 0 | 0 | 0 | 0 | 0 | 0 | 1992912 | 358724 | 2026-06-10 12:38:30 +0530 | Maasoumeh Raza | DCM: Recap: 20429 - Design Consultation Meeting (DCM) with the customer Wednesday, June 10 ¦ Meeting ¦ Microsoft Teams | 2026-06-07 11:21:02 +0530 | Karuna Shinde | DCM: Â CLIENT REQUIREMENT REPORTClient Name: Biniya Amin & Nissar Ahmed Shaikh Property: Aradhya Parkwood Configuration: Jodi Flat (2BHK + 2BHK) Approx. 1300 sq.ft Possession: July Profession: Business Family Size: 3 Couples (6 Members) SCOPE OF WORK Civil work Modular furniture Wall painting , wall decor , false ceiling overall,(suggested only in living) Special Requirement: All windows to be brought inside the room layout through civil modifications Storage to be created below windows wherever possible Vastu Consideration: Prayer room direction only THEMEElegant Modern BUDGETBudget Planned: 18 20 Lakhs without white goods AREA-WISE REQUIREMENTSLiving Room 75-inch TV so tv unit accordingly Elegant 6-seater dining table Sofa arrangement as per final space planning (max seating) Shoe rack for 1518 pairs Premium yet functional design language Lounge seating KitchenModular Requirements Double kitchen planning (2x base units) Double wall unit configuration (2x wall units) Single loft level storage Appliance Planning Dishwasher provision Washing machine provision Built-in microwave unit Built-in oven unit Double-door refrigerator space Civil Modifications Extend kitchen wall as required Close Unit 4 kitchen entry to accommodate double-door refrigerator and optimize layout BedroomsAll Bedrooms Bed Side tables Wardrobe Dresser Prayer Room Dedicated prayer room in Living Room of Unit 3 Sliding partition for privacy and flexibility Bathrooms Two half-glass shower partitions (in any two bathrooms, subject to site feasibility) Windows & SafetyMandatory Requirements Mosquito mesh/screens throughout Window grills throughout Additional Requirement Window redesign with storage below wherever feasible | 2026-06-07 11:14:47 +0530 | Karuna Shinde | Some Image was uploaded | 2026-06-21 |  | 2026-06-28
20430 | Turnkey | 2026-06-01 | Aakash Sharma | Rohan Ekanta | BNG - HSR | Yes | Avishkar Sargam | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1417990 | 188507 | 1937597 | 0 | 0 | 22 | 0 | 0 | 95091 | 567196 | 567196 |  |  | 2026-06-06 | 2026-06-09 10:41 | 2026-06-06 | 2026-06-09 10:45 | 2026-06-21 | 2026-06-21 11:17 | 2026-07-19 |  | 2026-09-10 |  | 2026-09-17 |  | 2026-06-21 | 2026-06-21 18:18 | 2026-06-22 | 2026-06-21 18:19 | 2026-06-21 | 2026-06-23 13:38 | 2026-06-28 | 2026-06-28 18:23 |  |  |  |  | 2026-07-20 |  | 2026-09-12 |  | 2026-09-13 |  |  |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-23 | [6 empty] | 2026-10-11 |  | 2026-10-20 |  | 2026-10-19 |  | 2026-10-20 |  | 2026-10-21 |  | 2026-10-23 |  |  |  | 2026-11-14 |  | 2026-11-16 |  | 2026-11-17 | [5 empty] | 2026-09-21 |  | 2026-07-15 |  | Unknown | 2026-06-06 | 2026-06-06 18:04 | 1642032 | 295565 | 0 | 0 | 0 | 0 | 1597517.599 | 263788 | 2026-06-28 19:16:02 +0530 | Abhinandan K S | Call done with the Customer Possession expected by end of August 2026 Explained the project milestones and timeline Project will be on hold till after DEM 1. Design meetings to be aligned post discussing with the Cx. DEM 1 10% payment due date- 14th July 2026. | 2026-06-23 13:38:31 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: July 1 week Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (26th June 2026) * DEM 1 Tentatively scheduled for (3rd July 2026) * 10% Payment Stage will close after the DEM1 * B2C - Self * No Civil work as of now Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: 100% GST Waiver PM fee waiver (5%) Design fee waiver (5%) Free Hob & Chimney Offer Free Shoerack Offer Laminate Upgrade - Jun 26 Campaign Silver Coin 21g Final Closing Value Discussed: 14,17,991 Checklist terms descoping and agreement terms are cleared | 2026-06-23 13:20:50 +0530 | Athul Ajaykumar |  | 2026-07-20 |  | 2026-09-11 |  | Under Construction | 2026-07-08 | 2026-06-20 | 188507 | Ravi Roy
20431 | Turnkey | 2026-06-01 | Anup Yadav | Raymond 10X Habitat | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Subhan Khan |  | Active | Preproduction | DEM2 | 1092992 | 218598 | 1216050 | 0 | 0 | 10 | 0 | 0 | 0 | 484237 | 390156.8 |  |  | 2026-06-06 | 2026-06-09 13:24 | 2026-06-07 | 2026-06-09 14:08 | 2026-06-12 | 2026-06-12 11:56 | 2026-08-05 | 2026-07-05 18:50 | 2026-07-11 |  | 2026-07-18 |  | 2026-06-12 | 2026-06-12 14:19 | 2026-06-13 | 2026-06-12 14:21 | 2026-06-12 | 2026-06-12 16:57 | 2026-06-17 | 2026-06-17 14:52 |  |  |  |  | 2026-08-06 | 2026-07-02 11:44 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-07-22 |  | 2026-08-01 | 2026-07-05 18:18 | Site is RTMI | 2026-06-06 | 2026-06-06 19:24 | 1032796 | 183253 | 0 | 0 | 0 | 0 | 1037748 | 184145 | 2026-07-12 00:30:38 +0530 | Rachna Abhyankar |  | 2026-06-30 12:19:48 +0530 | Preet Karania | Minutes of Meeting (MOM) Date: 19th June PID: 20431 Client: Anup Ji Living Room Provide a sofa-cum-bed on the right wall near the entrance. Place one chair near the window. Design the TV unit and mandir on the left wall near the entrance. Provide a foldable dining table on the passage wall below the small window. Kids' Bedroom Add drawers and hydraulic storage to the platform bed. Wardrobe to have no hanging section. Divide the wardrobe storage into three equal shelf sections. Kitchen No openable shelves to be provided. Update the kitchen storage layout as discussed during the meeting. Master Bedroom Update the internal wardrobe layout as per the discussion. Revise the wall design according to the reference images shared by the client. General Remarks All room designs and elevations are to be updated as per the reference images shared by the client. Revised drawings to be submitted for client approval before proceeding with execution. Please Note :- The quotation will vary as per the addition of the components and the materials selection Thanks & regards, Preet KaraniaÂ Interior Designer | 2026-06-30 12:18:12 +0530 | Preet Karania | Some Image was uploaded | 2026-07-06 | 2026-07-05 18:52 | 2026-07-12 |  | RTMI |  | 2026-06-11 | 131604 | Ravi Roy
20432 | Turnkey | 2026-06-01 | Anil yadav | Raymond 10X | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Subhan Khan |  | Active | Preproduction | DEM2 | 1142904 | 228581 | 1271877 | 0 | 0 | 10 | 0 | 0 | 0 | 522681 | 391641.6 |  |  | 2026-06-06 | 2026-06-09 13:27 | 2026-06-07 | 2026-06-09 14:08 | 2026-06-12 | 2026-06-12 11:51 | 2026-08-05 | 2026-07-05 19:06 | 2026-07-11 |  | 2026-07-18 |  | 2026-06-12 | 2026-06-12 14:26 | 2026-06-13 | 2026-06-12 14:35 | 2026-06-12 | 2026-06-12 16:56 | 2026-06-17 | 2026-06-17 16:42 |  |  |  |  | 2026-06-29 | 2026-06-30 12:06 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-08-24 |  | 2026-08-25 | [6 empty] | 2026-09-12 |  | 2026-09-21 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-22 |  | 2026-09-24 |  |  |  | 2026-10-16 |  | 2026-10-18 |  | 2026-10-19 | [5 empty] | 2026-07-22 |  | 2026-08-01 | 2026-07-05 18:58 | Site is RTMI | 2026-06-06 | 2026-06-06 19:40 | 1080107 | 191769 | 0 | 0 | 0 | 0 | 1085103 | 192669 | 2026-07-12 00:31:03 +0530 | Rachna Abhyankar |  | 2026-06-30 12:19:20 +0530 | Preet Karania | Minutes of Meeting (MoM) Date: 19th June PID: 20432 Client: Anil Ji Living Room Sofa-cum-bed to be placed on the entrance left wall. One chair to be placed near the window. TV unit and mandir to be designed on the right entrance wall. Foldable dining table to be provided on the passage wall near the small window. Kids' Bedroom No hanging space required in the wardrobe. Wardrobe storage to be divided into three equal sections. Kitchen No openable shelves to be provided. Internal storage layout to be updated as discussed during the meeting. Master Bedroom Wardrobe internal layout to be revised. Wall design to be updated as per the clients reference images. General All designs to be revised and updated according to the reference images shared by the client. Please Note :- The quotation will vary as per the addition of the components and the materials selection Thanks & regards, Preet KaraniaÂ Interior Designer | 2026-06-30 12:18:53 +0530 | Preet Karania | Some Image was uploaded | 2026-07-06 | 2026-07-05 19:08 | 2026-07-12 |  | RTMI |  | 2026-06-11 | 137186 | Ravi Roy
20433 | Turnkey | 2026-06-01 | Peeyush Gandhi | Swastik Avighna | MUM - GOR | Yes | [8 empty] | Ashish Jha |  | Active | Prospect | 10% Payment | 1176790 | 9999 | 0 | 0 | 0 | 29 | 0 | 107680 | 117679 | 526561 | 414870.8 |  |  | 2026-06-06 | 2026-06-06 19:27 | 2026-06-16 | 2026-06-16 11:49 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-06 | 2026-06-06 19:21 | 0 | 0 | 0 | 0 | 0 | 0 | 999588 | 177202 | 2026-06-16 11:49:20 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-13 16:17:47 +0530 | Rahul Agrawal | DCM: Property Details: 1 BHK Possession: June end Occupants: 3 Members (Couple & 9-year-old daughter) Design Preferences: Minimal, peaceful color combinations. Vastu: Basic Vastu compliance (not hardcore believers). Budget: 10 Lakhs Notes: Entrance not known as of now; Site visit needed before CDP. Room-by-Room Requirements Living Sofa-cum-bed. TV unit. Mandir. 4-seater dining table. Crockery unit (with adjustment for a flour mill in the base unit). Kitchen Layout same as original layout. Base cabinets, top cabinets, and loft cabinets. Requirement: Try to place the washbasin in the common area instead of inside both washrooms. Bedroom Bed: Queen size. 1 Side table. Wardrobe with loft. Working/study table with overhead storage. Loft in the passage (to be checked on-site). Civil/Additional Works Washrooms: * Client is ready for civil work. Master bedroom WC to be shifted out of the shower partition area. Soft Civil: Electrical, False ceiling, Painting. | 2026-06-06 19:31:31 +0530 | Ashish Jha | Some Image was uploaded | 2026-06-24 |  | 2026-07-01
20434 | Turnkey | 2026-06-01 | Velkooru Sairam | Goyal orchid life | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | 10% Payment | 1178064 | 9999 | 1178064 | 0 | 0 | 31 | 0 | 107807 | 117806 | 492847 | 449604 |  |  | 2026-06-06 | 2026-06-12 12:49 | 2026-06-06 | 2026-06-12 17:31 | 2026-06-14 | 2026-06-14 12:04 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-06-06 | 2026-06-06 18:55 | 998359 | 179704 | 0 | 0 | 0 | 0 | 998359 | 179704 | 2026-06-12 12:53:02 +0530 | Janvi Nagdeo | Some Image was uploaded | 2026-06-11 15:32:05 +0530 | Palak Thakur | Some Image was uploaded | 2026-06-11 14:58:05 +0530 | Palak Thakur | DCM: (17) Calendar ¦ 20434 - Design Consultation Meeting (DCM) with the customer ¦ Microsoft Teams | 2026-06-22 |  | 2026-06-29
20435 | Turnkey | 2026-06-01 | Sabyasachi Bhuyan | Sobha Victoria Park | BNG - HRBR | Yes | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [5 empty] | Shashank Singh |  | Active | Preproduction | DEM2 | 1607836 | 237647 | 1498753 | 0 | 0 | 15 | 0 | 0 | 0 | 743933 | 626255.6 |  |  | 2026-06-06 | 2026-06-09 15:41 | 2026-06-06 | 2026-06-10 16:36 | 2026-06-16 | 2026-06-17 13:38 | 2026-06-30 | 2026-06-29 12:47 | 2026-07-14 |  | 2026-07-21 |  | 2026-06-17 | 2026-06-18 18:40 | 2026-06-18 | 2026-06-19 14:16 | 2026-06-19 | 2026-06-19 15:44 | 2026-06-24 | 2026-06-24 16:55 |  |  |  |  | 2026-06-29 | 2026-06-30 12:43 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-06-25 | 2026-06-29 12:39 | Site is RTMI | 2026-06-06 | 2026-06-07 17:17 | 1270130 | 228623 | 0 | 0 | 0 | 0 | 1662693.4584 | 289410 | 2026-06-19 15:43:41 +0530 | Athul Ajaykumar | Possession Status: RTMI Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend) * DEM 1 Tentatively scheduled for (Next weekend) * 10% Payment Stage Tentatively scheduled for (28th June 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Hob & Chimney Offer May '26 Net Special Studio Offer Laminate Upgrade - Jun 26 Campaign 100% GST Waiver PM Fee Waiver (4%) Final Closing Value Discussed: 11,88,238 Checklist terms descoping and agreement terms are cleared | 2026-06-19 14:18:36 +0530 | Shashank Singh | Some Image was uploaded | 2026-06-17 13:41:52 +0530 | Keerthan M | Some Image was uploaded | 2026-06-30 | 2026-06-29 12:47 | 2026-07-15 |  | RTMI |  | 2026-06-16 | 118824 | Ravi Roy
20436 | Turnkey | 2026-06-01 | NITU K SINGH | MICL Aaradhya Parkwood | MUM - Thane | Yes | [8 empty] | Arifa Mohammed Hussain Shaikh |  | Active | Prospect | 10% Payment | 1241855 | 9999 | 0 | 0 | 0 | 27 | 0 | 114187 | 124186 | 566746 | 426738.4 |  |  | 2026-06-06 | 2026-06-06 21:08 | 2026-06-06 | 2026-06-07 13:55 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-06-26 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-21 |  | Unknown | 2026-06-06 | 2026-06-06 20:56 | 0 | 0 | 0 | 0 | 0 | 0 | 1054662 | 187192 | 2026-06-07 13:48:50 +0530 | Bhawaya Goyal | DCM: Project DetailsClient: Nitu SinghEntrance: East FacingFamily Members: 3 (Couple + Daughter, 9 Years)Profession: Financial SectorPossession: June 2026 (Soft Possession)Move-in Target: January 2027Floor: 22nd FloorLifestyle: Frequent Family GatheringsTheme: Modern + MinimalistBudget: 10 LakhsCDP: 20th21stMeeting Time: TBS Foyer AreaRequirementsSafety DoorShoe Rack Storage Living RoomRequirementsNo Dining Table3-Seater Sofa Cum BedTV UnitElevated MandirBar Unit (1012 Bottles storage, Open + Closed Storage) KitchenRequirementsBase UnitsWall Units (Glass Shutters for crockery)Tall Pantry Unit Common Bedroom (Daughter)RequirementsSofa Cum BedWardrobe with LoftStudy TableNo Mirror Master BedroomRequirementsQueen Size BedWardrobe + Loft + MirrorSide TableWorkstationWall-Mounted TV with LedgeCombined Side Table + Dressing + Workstation WashroomsCommon WashroomVanity Unit with Storage Master WashroomVanity UnitSliding Glass Shower Partition Services Electrical PlanningPaintingFalse Ceiling | [6 empty] | 2026-06-26 |  | 2026-07-03
20437 | Turnkey | 2026-06-01 | Deepak Nadeyana | Deepak | BNG - HSR | Yes | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 1762743 | 9999 | 1762743 | 0 | 0 | 33 | 0 | 166275 | 176274 | 705097 | 705097.2 |  |  | 2026-06-06 | 2026-06-12 11:58 | 2026-06-24 | 2026-06-24 15:22 | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-06-06 | 2026-06-07 11:11 | 1493850 | 268893 | 0 | 0 | 0 | 0 | 1493850 | 268893 | 2026-06-30 13:55:28 +0530 | Nayan Reddy | CDP: All changes made as per CDP discussion Hidden door pooja room Door need vendor quote | 2026-06-30 13:53:46 +0530 | Nayan Reddy | Some Image was uploaded | 2026-06-24 15:20:41 +0530 | Nayan Reddy | DCM: MOM DeepakClient Name: Deepak CRM: Nirosha RGM Date: 17/06/2026 Move-in Date: 01/08/2026 Budget: 1013 Lakhs Property Name: Independent House Facing: East Facing Floor to Ceiling Height: 10 ft Discussion Summary3rd FloorEntrance & Living AreaNo wall required near the main entrance.Provision for a 3 ft high partition with storage cabinet near the entrance.Bedroom, Study Room, and Living Room to be merged into a single open space.No partition wall between bedroom and living area.Entire area to be designed as an open-plan living zone.C-shaped sofa preferred.Hidden door concept to be explored.Main door side window dimensions: 22" (W) 8' (H).TV unit to be planned from the main door wall up to the lift wall.Pooja RoomDesign suggestions to be provided from the designer's end.Dedicated pooja space with functional storage to be explored.Master Bedroom (MBR 11' 10')Toilet alignment to match the opposite-side toilet.Walk-in wardrobe required.Small study table required.King-size bed required.KitchenHob wall shifted to the main wall.Staircase direction confirmed as anti-clockwise.Feasibility of island kitchen concept to be checked and proposed. 4th FloorKids Bedroom (KBR)Kids-themed room design.Study unit required.Wardrobe with loft storage.Mirror required.Hall 2Bar unit required.Bedroom 3 (GBR)Scope limited to door planning/modification only. | 2026-07-08 |  | 2026-07-15
20438 | Turnkey | 2026-06-01 | Pallavi Sathyagari | Shakthi Tranquilis | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 1478935 | 9999 | 0 | 0 | 0 | 31 | 0 | 137895 | 147894 | 620212 | 562936.4 |  |  | 2026-06-06 | 2026-06-14 12:59 | 2026-06-09 | 2026-06-14 13:00 | 2026-06-16 |  | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-06 | 2026-06-14 12:50 | 0 | 0 | 0 | 0 | 0 | 0 | 1253335 | 225600 | 2026-06-24 10:42:22 +0530 | Priyamvada PV | Recap: 20438 - Design Consultation Meeting (DCM) with the customer 09 June ¦ Meeting ¦ Microsoft Teams | 2026-06-23 17:07:23 +0530 | Ankita Agarwal | CDP: No changes as per first set of design client will discuss in design discussion if proceeds | 2026-06-23 17:06:35 +0530 | Ankita Agarwal | Some Image was uploaded | 2026-06-24 |  | 2026-07-01
20439 | Turnkey | 2026-06-01 | Rahul Misra |  | BNG - HSR | Yes | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 3853583 | 9999 | 0 | 0 | 0 | 24 | 0 | 375359 | 385358 | 1569173 | 1513693.6 |  |  | 2026-05-22 | 2026-06-10 10:23 | 2026-06-14 | 2026-06-20 11:58 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-05-22 | 2026-06-08 18:49 | 0 | 0 | 0 | 0 | 0 | 0 | 3265748 | 587834 | 2026-06-23 14:41:25 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-23 12:09:41 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-23 12:08:31 +0530 | Saranya Thiyagarajan | CDP: Living Room Conceal MCB panel with a decorative shutter design and maintain wall symmetry. Add an indoor swing in the living area. Provide architrave detailing for doors/openings. Kitchen Change to a ductless chimney. Add loft storage above overhead cabinets wherever feasible. Add loft above the tall unit. Increase storage by adding one additional drawer in the base cabinet section. Utility Replace open ledges with a closed storage unit. Janitor unit to be designed: Full-height tall unit. No open display section. No skirting. Additional overhead cabinets above washing machine. Removable shelf provision for maintenance access. Master Bedroom (MBR) Add TV back panel design. Headboard paneling to continue from wall to ceiling for a grand feature wall. Move dresser to study area. Dresser to include hidden storage behind mirror. Master Bedroom Layout Revision Shift king-size bed towards the left side near balcony. Introduce a 2.5 ft partition between bed and study: Combination of glass + wooden partition wuth integrated display ledge and a hanging pendant light. Create a full-fledged study area beyond the partition. Add a mix of open shelves and closed overhead cabinets for study. Close the window portion up to the bed-end location as discussed. Walk-in Wardrobe Add architrave detailing to entrance/opening. Bedroom Niches Add loft storage above bedroom niche areas. Daughter's Bedroom Design as per the approved reference image which is with platform design ( Not included in quote ) | 2026-07-01 |  | 2026-07-08
20440 | Turnkey | 2026-06-01 | Pradeep Yelam | Godrej Exquisite | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1655407 | 9999 | 0 | 0 | 0 | 39 | 0 | 155542 | 165541 | 762493 | 561832.8 |  |  | 2026-06-06 | 2026-06-06 20:42 | 2026-06-07 | 2026-06-07 14:16 | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-21 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-08-08 |  | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-08-03 |  | Unknown | 2026-06-06 | 2026-06-06 20:38 | 0 | 0 | 0 | 0 | 0 | 0 | 1402887 | 252519 | 2026-06-07 14:11:32 +0530 | Moksh Mehta | DCM: Client Name:- Pradeep Yelam Property:- Godrej Exqusite Possesion Date:- Any time soon Sq Ft:- 722 sqft, T2-1105 No of Members : - Couple (45+), Son (17+) + Daughter (14+) Sir, is Working as Piping Engineer, Mam is Homemaker Budget:- 15L Max Ent: Shoe Rack (15 - 20 Pairs)Wall Concepts. Living Room :- TV Unit (50") with Display unit3-Seater Sofa (4-5 Persons)Wall concepts. Coffee table Dining Area :- 4 Seater Dining Table. Wall Concepts. Kitchen :- Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos. Master Bedroom :- Queen size Bed Wardrobe with Loft with DresserSide tableTV Ledge Daughter Bedroom :- 0.5 Room Sofa cum BedWardrobe with loft & DresserStudy TableMandir Unit Mid Size Bedroom :- Queen size Bed Wardrobe with LoftDresser with Side TableFolding Study Table Bathroom's Base Vanity Unit's for all Misc:- False CeilingPaintingElectrification CDP:- 20th Jun 2026 @ 10:30 am. | [6 empty] | 2026-08-08 |  | 2026-08-15
20441 | Turnkey | 2026-06-01 | Neelima Hari . | SBR Earth & Sky | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Design | 20% Payment | 1402764 | 187999 | 1496998 | 0 | 0 | 16 | 0 | 0 | 92554 | 584574 | 537637.2 |  |  | 2026-06-06 | 2026-06-09 15:42 | 2026-06-09 | 2026-06-09 19:51 | 2026-06-14 | 2026-06-18 13:32 | 2026-07-03 | 2026-06-29 12:28 | 2026-08-10 |  | 2026-08-17 |  | 2026-06-18 | 2026-06-19 18:56 | 2026-06-19 | 2026-06-22 14:47 | 2026-06-22 | 2026-06-22 17:36 | 2026-06-24 | 2026-06-24 16:59 |  |  |  |  | 2026-07-11 |  | 2026-08-12 |  | 2026-08-13 |  |  |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 | [6 empty] | 2026-09-10 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-22 |  |  |  | 2026-10-14 |  | 2026-10-16 |  | 2026-10-17 | [5 empty] | 2026-08-21 |  | 2026-06-25 | 2026-06-29 12:09 | Site is RTMI | 2026-06-06 | 2026-06-06 20:43 | 1496998 | 269459 | 0 | 0 | 0 | 0 | 1463248.6324 | 252497 | 2026-06-24 16:57:45 +0530 | Parasa Sri | Welcome call done, Initial measurements can be planned in august, Week end meeting | 2026-06-22 17:35:32 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: 1st week of August 2026 Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible * DEM 1 This weekend's 2026 * 10% Payment Stage 6th July 2026 (after 1st DEM) *No civil work planned in client's scope of work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 14,63,249 Offers Discussed During the Call: Free Hob & Chimney Offer May '26 Net Special Studio Offer Silver Coin 21g Laminate Upgrade - Jun 26 Campaign 100% GST Waiver PM fee waiver (5%) Final Closing Value Discussed: 14,02,764 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-22 14:56:56 +0530 | Shashank Singh | Some Image was uploaded | 2026-06-30 | 2026-06-29 12:30 | 2026-08-11 |  | Under Construction | 2026-08-05 | 2026-06-14 | 149700 | Ravi Roy
20442 | Turnkey | 2026-06-01 | Sneha Adiwarekar | Sriparti sky | MUM - GOR | Yes | Karan Chavda | Christopher Macwan | Safalta Karkera |  | Fareed Shaikh |  |  |  | Sanskruti Yadav |  | Active | Preproduction | Site Readiness 1 | 1282579 | 256516 | 1634769 | 0 | 0 | 3 | 0 | 0 | 0 | 563347 | 462716.4 |  |  | 2026-06-06 | 2026-06-07 11:06 | 2026-06-16 | 2026-06-16 18:10 | 2026-06-27 | 2026-06-27 18:54 | 2026-07-13 | 2026-07-12 17:03 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-26 | 2026-06-26 15:23 | 2026-06-28 | 2026-06-27 17:09 | 2026-06-28 | 2026-07-01 16:48 | 2026-07-03 | 2026-07-03 19:45 |  |  |  |  | 2026-07-09 | 2026-07-11 18:32 | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-04 | 2026-07-12 16:56 | Site is Non-RTMI | 2026-06-06 | 2026-06-07 11:01 | 1385397 | 249371 | 0 | 0 | 0 | 0 | 1343123.866 | 231764 | 2026-07-03 20:10:02 +0530 | Christopher Macwan | Welcome call done. Initial measurement - Need to confirm with the Team DEM Dates -Â DEM 1 â€“ Preferably on weekends - Tentative on 11th or 12th July @ 11:30am DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-03 19:58:43 +0530 | Christopher Macwan | Welcome call done. Initial measurement - Need to confirm with the Team DEM Dates -Â DEM 1 â€“ Preferably on weekends - Tentative on 11th or 12th July DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-01 16:46:53 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible *IMs - This weekend * DEM 1 â€“ Client will let us know * 10% Payment Stage â€“ 11th July 2026 *Client will be having civil work in his scope of work that is demolishing of wall and then shifting the door to 2nd bedroom *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (5000) May'26 100% GST waiver PM fee waiver (5%) Silver Coin Offer Laminate Upgrade Offer - June 26 Final Closing Value Discussed: â‚¹ 12,82,579 | 2026-07-13 | 2026-07-12 17:11 | 2026-07-19 |  | RTMI |  | 2026-06-26 | 163477 | Ravi Roy
20446 | Turnkey | 2026-06-01 | Samir Mehta | ** | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam |  |  | suraj kumar | Akshat Shrivastava |  | Aryan Singh | Prasad Bhivaji Hande | Active | Preproduction | DEM2 | 849427 | 169885 | 867104 | 0 | 0 | 4 | 0 | 0 | 0 | 366839 | 312703.2 |  |  | 2026-06-07 | 2026-06-16 19:28 | 2026-06-16 | 2026-06-16 19:36 | 2026-06-16 | 2026-06-17 14:16 | 2026-07-08 | 2026-07-08 11:39 | 2026-07-12 | 2026-07-11 19:51 | 2026-07-17 |  | 2026-06-17 | 2026-06-17 15:37 | 2026-06-18 | 2026-06-17 17:18 | 2026-06-17 | 2026-06-17 17:31 | 2026-06-29 | 2026-06-29 18:18 |  |  |  |  | 2026-07-08 | 2026-07-11 13:18 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-30 | 2026-07-08 11:20 | Site is RTMI | 2026-06-07 | 2026-06-16 18:19 | 1314008 | 197418 | 0 | 0 | 0 | 0 | 1287275 | 193393 | 2026-07-08 12:14:36 +0530 | Harshali Bhuyar | False ceiling design approved. wall concepts finalized. electrical layout shared. scope to be decided for master bedroom study. Civil work in progress , will take 2 weeks . Hence CM to be postponed. Electrical dwgs needed for all rooms. | 2026-06-23 18:09:46 +0530 | Moksh Mehta |  | 2026-06-20 18:08:09 +0530 | Harshali Bhuyar | MOM for 20th JuneÂ * Layout for Living room, Bedroom 1 & Bedroom 2 has been freezed.Â Â LIVING ROOM: * wall concept discussed, will share one more option.Â * will include a console without storage which can be used as a dining. * false ceiling layout frezeed * to incorporate lights and metal flat patti. * L shape sofa & maximum seating space.Â BEDROOM 1: * Aristo shutter 2 options shortlisted. * material has been selected. * to add single tall unit, study and wall cabinets in L shape.Â * Mandir will be placed along the column.Â * Wall adjacent to bed will remain plain.Â * Bed will be placed in corner. * False ceiling to be plain. BEDROOM 2: * Membrane shutter wardrobe finalized. * Bed to be kept against the window.Â * TV will be placed on the left wall in future, wall design with charcoal trims.Â * Bed headboard to be wall to wall. * Right wall 2 options shortlisted - charcoal trims OR rafters.Â * flat patti to be added on wardrobe shutters.Â * False ceiling to be plain with profile light design.Â PENDING : * Electricals (will be final during cross measurements) * Wall paintÂ * Duco paint * Wallpaper if anyÂ * Mandir design | 2026-07-09 | 2026-07-08 12:11 | 2026-07-12 | 2026-07-11 19:54 |  |  | 2026-06-16 | 155053 | Ravi Roy
20448 | Turnkey | 2026-06-01 | Amit Shingare | GeeCee Emerald | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anjan Kumar |  | Hold | Preproduction | Site Readiness 1 | 1827348 | 471554 | 2307778 | 0 | 0 | 1 | 7 | 0 | 0 | 715607 | 640187.2 |  |  | 2026-06-07 | 2026-06-07 22:44 | 2026-06-07 | 2026-06-09 13:34 | 2026-06-13 | 2026-06-14 17:58 | 2026-07-07 | 2026-07-07 17:41 | 2026-12-05 |  | 2026-12-12 |  | 2026-06-14 | 2026-06-15 11:28 | 2026-06-15 | 2026-06-16 12:26 | 2026-06-16 | 2026-06-16 18:00 | 2026-06-19 | 2026-06-19 10:57 |  |  |  |  | 2026-06-23 | 2026-06-17 12:22 | 2026-12-07 |  | 2026-12-08 |  |  |  | 2026-12-15 |  | 2026-12-16 |  | 2026-12-17 |  | 2026-12-18 | [6 empty] | 2027-01-05 |  | 2027-01-14 |  | 2027-01-13 |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-17 |  |  |  | 2027-02-08 |  | 2027-02-10 |  | 2027-02-11 | [5 empty] | 2026-12-16 |  | 2026-07-11 | 2026-07-05 12:05 | Site is Non-RTMI | 2026-06-07 | 2026-06-07 22:42 | 1955744 | 352034 | 0 | 0 | 0 | 0 | 1955743.8605 | 337472 | 2026-07-09 16:59:10 +0530 | Anil Jagtap | cx will receive the possession by November*26 | 2026-07-08 15:37:45 +0530 | Anil Jagtap | Possession - Nov *26 | 2026-07-07 18:11:21 +0530 | Parnavi Joshi | Project on hold till Nov,26 | 2026-07-08 | 2026-07-07 17:51 | 2026-12-06 |  | Under Construction | 2026-10-31 | 2026-06-14 | 471554 | Ravi Roy
20450 | Turnkey | 2026-06-01 | Meghna baberwal | Dadar | MUM - GOR | Yes | Batskhem Marpna | Vishakha Vaishnav | Kashmira Nerurkar | [5 empty] | Ashutosh Singh |  | Active | Design | DEM1 | 811335 | 209999 | 1080406 | 0 | 0 | 30 | 0 | 0 | 0 | 285890 | 315445.6 |  |  | 2026-06-07 | 2026-06-08 09:18 | 2026-06-07 | 2026-06-12 18:29 | 2026-06-15 | 2026-06-13 22:28 | 2026-06-22 |  | 2026-06-29 |  | 2026-07-06 |  | 2026-06-13 | 2026-06-13 15:53 | 2026-06-14 | 2026-06-14 13:03 | 2026-06-14 | 2026-06-15 15:07 | 2026-06-17 | 2026-06-17 17:25 |  |  |  |  | 2026-06-23 | 2026-06-18 16:23 | 2026-07-01 |  | 2026-07-02 |  |  |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 | [6 empty] | 2026-07-30 |  | 2026-08-08 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-11 |  |  |  | 2026-09-02 |  | 2026-09-04 |  | 2026-09-05 | [5 empty] | 2026-07-10 |  | 2026-06-18 |  | Unknown | 2026-06-07 | 2026-06-08 09:14 | 915599 | 164807 | 0 | 0 | 0 | 0 | 915598.7715 | 154590 | 2026-07-10 15:57:24 +0530 | Vishakha Vaishnav | IM : 14TH JULY BY 11 AM CX WANT DEM 1 ON 19TTH JULY AS SHE WILL BE TRAVELLING MEANWHILE | 2026-07-08 17:20:20 +0530 | Vishakha Vaishnav | DEM 1 : Couldn't happen bcuz cx was unable to come to office for the meeting because of rains IM : Unable to take the measurement because there was alot of stuff placed at cx's apartment | 2026-06-24 15:38:15 +0530 | Vishakha Vaishnav | DEM is aligned for 5th July by 12:00 pm | 2026-06-23 |  | 2026-06-30 |  | Under Construction | 2026-09-30 | 2026-06-13 | 108041 | Ravi Roy
20451 | Turnkey | 2026-06-01 | mohamed musthafa | brigade vellencia | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1895779 | 9999 | 1895779 | 0 | 0 | 31 | 0 | 179579 | 189578 | 779715 | 736908 |  |  | 2026-06-07 | 2026-06-07 14:31 | 2026-06-07 | 2026-06-11 09:17 | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-06-07 | 2026-06-07 14:23 | 1606592 | 289186 | 0 | 0 | 0 | 0 | 1606592 | 289186 | 2026-06-14 08:28:14 +0530 | Priyamvada PV | Musthafa CDP changes : MOM dated 13.06.26 1. Shoe rack - storage with angled mechanism of foyer required (estimate/links for same to be provided) 2. TV unit - base storage width to be reduced to 5', add 2 ottoman spaces on either sides to be considered 3. Kitchen - hand wash to be facing dining with tall unit behind 4. Kitchen- all base unit height to be increased by 6cm 5.sink unit to be shifted towards right end only with WM next to DW 6. Kitchen - Dish drainer accessory to be added 7. Kitchen hob side - dryer space to be left on left side 8. Crockery to be made single door, storage to be considered in kitchen (shift fridge to right by 1.5'W) 9. Common vanity - add base storage, increase wall storage on both vanity to 2'W 10. MBR - wardrobe on either sides of window as per plan A, add a used cloth storage on any wall 11. KBR - add curved ledges on side of wardrobe, shift sofa cum bed on right of window, study on left of window facing sofa cum bed 12. KBR - study not required (height adjustable table)- client scope, remove wallpaper from scopeÂ 13. GBR - WR on left corner with 3'H storage having drawers on right, with dresser on right corner as per option 2 shown 14. Laundry basket(F&S) storage to be planned along with dresser for MBR,KBR (in design phase) 15. Balcony - vendor details for mop unit, other storage in WPC material | 2026-06-14 07:57:44 +0530 | Priyamvada PV | Some Image was uploaded | 2026-06-11 18:57:30 +0530 | Nidhi Shaw | They are from Kerala. 3 BHK property. Budget initially they told 8-10. I clearly mentioned it will cost around 15 Lakhs depend on designs. They are having a 3-year-old girl. They liked the process very much and may proceed | 2026-06-22 |  | 2026-06-29
20452 | Turnkey | 2026-06-01 | Surekha wandge | Kamla Ridhima | MUM - GOR | Yes | Rajnish Mishra | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Ashish Jha |  | Active | Preproduction | DEM2 | 1146619 | 229324 | 1522376 | 0 | 0 | 18 | 0 | 0 | 0 | 500524 | 416770.8 |  |  | 2026-06-07 | 2026-06-11 12:28 | 2026-06-07 | 2026-06-11 18:32 | 2026-06-12 | 2026-06-12 12:39 | 2026-06-27 | 2026-06-27 20:31 | 2026-07-03 |  | 2026-07-10 |  | 2026-06-11 | 2026-06-11 17:42 | 2026-06-13 | 2026-06-14 13:53 | 2026-06-14 | 2026-06-15 14:54 | 2026-06-17 | 2026-06-17 16:52 |  |  |  |  | 2026-06-23 | 2026-06-26 15:50 | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-18 | 2026-06-27 20:21 | Site is RTMI | 2026-06-07 | 2026-06-11 12:19 | 1290149 | 232226 | 0 | 0 | 0 | 0 | 1290148.9491 | 214941 | 2026-06-18 15:23:24 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-17 17:58:04 +0530 | Rajnish Mishra | Others: Transition - 17/06/26 ** CPD design and quotation of 11,46,620 is not matching ** ** Clients Maximum Budget is 12.5 Lakh as per Hamza** Living Room Living Room Furnitures are - TV unit, Crockery Unit, Shoe Rack in quotationFurnitures in CDP files are - TV unit, Crockery unit, Shoe rack, AC pelmet, Partition with storage.Partitions is in CX scope as per HamzaDinning table is in Cx scope per HamzaSofa is in Cx scope as per hamzaAC pelmet scope to be discused later Wall Decor in CDP files are- Vertical Mirror 6" x 10' (2 NOS) with back panel. POP punning with grooving (180 SQ.ft Minimum). Decorative Wall Panel (40 Sq.ft).Gypsum wall panel 60 mm offset with grooving (20sqft)Rafters - 11 PcsTexture Paint used in Living Room 100 Sq.ft Wall Decor considered in quotation are - POP Punning - 200sq.ft - 5200/- without groove and paintRafters - 10 pc- 9010/-texture Paint - 100sq.ft - 11445/- Total - 25,655/- Services - Added in quotation Royal Luxury Emultion - 1500 sq.ft Tractor Emulstion - 480 sq.ftElectrical - 45000/- False Ceiling - 540sq.ft (Living, Master Bedroom, Kids Bedroom) Actual Floor Area as per CDP file- 540 sq.ft (Living, Kitchen, MBR and KBR) Floor Covering - 540sq.ft in quotation Cleaning charges - 2BHK - 10 to 15 lakh in quotation All Furnitures are PrelamKitchen is in membrane FinishKitchen tendum is indux tendum Accessories in Tendum unit is not considered in Model and QuotationMicrowave Unit Depth is not as per handbook standard - 300mm is considered in Model - if Cx required Microwave unit - Loft, Wall unit depth will increase of same wall.Wardrobes are Prelam - Side panel Laminates are not considered in all Wardrobes on Exposed sides in CDP file TV Unit - lamites not considered in open Cabinet and Exposed side of TV unit in CDP file | 2026-06-17 16:51:52 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Cx will get possession in week but after that there is flooring civil work planned after that IM can be aligned DEM Dates -Â DEM 1 - Cx is available for the meeting in weekdays also need to confirm with designer DEM 2 - TBD DEM 3 - TBD Possession date : June 2026 Customer will make 10% after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-28 | 2026-06-27 20:34 | 2026-07-04 |  | Under Construction | 2026-06-24 | 2026-06-11 | 152238 | Ravi Roy
20453 | Turnkey | 2026-06-01 | Neha Nimesh | Prestige Meridian Park | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Aman Kumar |  | Active | Prospect | 10% Payment | 1949636 | 9999 | 1949636 | 0 | 0 | 31 | 0 | 184965 | 194964 | 779854 | 779854.4 |  |  | 2026-06-07 | 2026-06-07 15:20 | 2026-06-09 | 2026-06-09 13:34 | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-06-07 | 2026-06-07 15:04 | 1652234 | 297402 | 0 | 0 | 0 | 0 | 1652234 | 297402 | 2026-06-14 17:27:50 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-12 17:02:08 +0530 | Aman Kumar | Client Observation Both husband and wife are IT professionals. The wife is the primary decision-maker and is actively involved in the design discussions. The clients are budget-conscious and do not want to overspend, so proposals should focus on achieving a good balance between aesthetics, functionality, and cost. | 2026-06-09 13:34:18 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-22 |  | 2026-06-29
20454 | Turnkey | 2026-06-01 | MANSOOR Khan | MICL Aaradhya Parkwood | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Subhan Khan |  | Active | Design | DEM1 | 1209706 | 159999 | 1594803 | 0 | 0 | 32 | 0 | 0 | 81942 | 538060 | 429704.4 |  |  | 2026-06-07 | 2026-06-07 22:08 | 2026-06-07 | 2026-06-09 12:24 | 2026-06-12 | 2026-06-09 19:06 | 2026-08-04 |  | 2026-08-11 |  | 2026-08-18 |  | 2026-06-12 | 2026-06-09 17:21 | 2026-06-10 | 2026-06-11 14:43 | 2026-06-11 | 2026-06-13 15:38 | 2026-07-04 | 2026-07-03 17:29 |  |  |  |  | 2026-08-05 |  | 2026-08-13 |  | 2026-08-14 |  |  |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 | [6 empty] | 2026-09-11 |  | 2026-09-20 |  | 2026-09-19 |  | 2026-09-20 |  | 2026-09-21 |  | 2026-09-23 |  |  |  | 2026-10-15 |  | 2026-10-17 |  | 2026-10-18 | [5 empty] | 2026-08-22 |  | 2026-07-04 |  | Unknown | 2026-06-07 | 2026-06-07 15:11 | 1351528 | 243275 | 0 | 0 | 0 | 0 | 1358323.898 | 226297 | 2026-07-02 19:13:02 +0530 | Anamika Dolai | DEM1 is scheduled to be on sunday dated: 5/07/26. | 2026-06-30 11:19:41 +0530 | Swami Vadnere | Some Image was uploaded | 2026-06-25 20:26:50 +0530 | Anamika Dolai | Client not responding. | 2026-08-05 |  | 2026-08-12 |  | Under Construction | 2026-07-15 | 2026-06-08 | 159999 | Ravi Roy
20455 | Turnkey | 2026-06-01 | Priyanka Sawant | Damji shamji mahavir spring | MUM - Thane | Yes | Amisha Ahuja | Anil Jagtap | Rachna Abhyankar | [5 empty] | Rahul Kumawat |  | Active | Preproduction | DEM2 | 1151697 | 288999 | 1393594 | 0 | 0 | 18 | 0 | 0 | 0 | 466057 | 396640.8 |  |  | 2026-06-07 | 2026-06-07 19:57 | 2026-06-07 | 2026-06-09 13:35 | 2026-06-14 | 2026-06-14 19:04 | 2026-07-14 | 2026-07-14 14:23 | 2026-07-20 |  | 2026-07-27 |  | 2026-06-14 | 2026-06-14 21:03 | 2026-06-15 | 2026-06-14 21:47 | 2026-06-14 | 2026-06-15 12:26 | 2026-06-17 | 2026-06-17 12:18 |  |  |  |  | 2026-06-23 | 2026-06-17 12:19 | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-07-31 |  | 2026-06-18 | 2026-06-27 11:03 | Site is RTMI | 2026-06-07 | 2026-06-07 19:56 | 1181012 | 212582 | 0 | 0 | 0 | 0 | 1181012.1938 | 207305 | 2026-07-12 10:38:11 +0530 | Amisha Ahuja |  | 2026-07-12 10:37:09 +0530 | Amisha Ahuja |  | 2026-07-12 10:36:51 +0530 | Amisha Ahuja |  | 2026-07-15 | 2026-07-14 14:28 | 2026-07-21 |  | RTMI |  | 2026-06-14 | 288999 | Ravi Roy
20456 | Turnkey | 2026-06-01 | _Fallengram_ | Rohan ekanta | BNG - HSR | Yes | [8 empty] | Muralikrishna Udupi |  | Active | Prospect | 10% Payment | 2466107 | 9999 | 0 | 0 | 0 | 34 | 0 | 236612 | 246611 | 986443 | 986442.8 |  |  | 2026-06-07 | 2026-06-07 16:19 | 2026-06-11 | 2026-06-11 12:21 | 2026-06-11 |  | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-06-11 |  | 2026-06-12 |  | 2026-06-12 |  | 2026-06-13 | [5 empty] | 2026-06-19 |  | 2026-06-27 |  | 2026-06-28 |  |  |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 |  | 2026-07-08 | [6 empty] | 2026-07-26 |  | 2026-08-04 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-07 |  |  |  | 2026-08-29 |  | 2026-08-31 |  | 2026-09-01 | [5 empty] | 2026-07-06 |  | 2026-06-14 |  | Unknown | 2026-06-07 | 2026-06-07 15:58 | 0 | 0 | 0 | 0 | 0 | 0 | 2089921 | 376185 | 2026-06-11 12:59:00 +0530 | Aparna | Spot discussion , 3bhk 15L BUDGET | 2026-06-07 15:56:21 +0530 | Unknown | About the Customer **3 BHK Property Details** Customer Shagun has a 3 BHK property with handover expected by December. The property is in Phase 3 and is for self-use. **Budget Range 8-15 Lakh** Customer is open to the starting ticket price of 7 lakh for interiors, with potential costs for a 3 BHK ranging from 8 to 15 lakh. **Tentative Experience Center Visit** Customer tentatively interested in visiting the HSR layout experience center this Saturday, pending confirmation with his wife. **WhatsApp Invite and Floor Plan Request** Agent to send details via WhatsApp and requested customer to share a floor plan after reviewing the message. |  |  |  | 2026-06-19 |  | 2026-06-26
20458 | Turnkey | 2026-06-01 | MR. Ravi tej Narayanam | One Luxuria | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1348067 | 9999 | 0 | 0 | 0 | 27 | 0 | 124808 | 134807 | 632052 | 446402 |  |  | 2026-06-07 | 2026-06-07 20:19 | 2026-06-07 | 2026-06-09 13:27 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-06-26 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-21 |  | Unknown | 2026-06-07 | 2026-06-07 20:04 | 0 | 0 | 0 | 0 | 0 | 0 | 1142430 | 205637 | 2026-06-07 20:21:38 +0530 | Bhagyashree Salunkhe | Some Image was uploaded | 2026-06-07 17:23:08 +0530 | Krutika Vernekar | DCM: Project: 2BHK Property Name: One Luxuria Possession: Ready Possession Purpose: Rental Property Budget: 13 Lakhs Suggested Budget: 13 Lakhs Priority ScopeLiving RoomTV UnitKitchenModular KitchenNo LoftBedroomsWardrobe in both bedroomsVanity unit in both bathroomsDresserNext Phase2 BedsSofaWallpaperGeneral RequirementsEnd-to-End Interior ExecutionNo False Ceiling Repainting RequiredDesign IntentRental-friendly designNeutral and timeless colour paletteDurable and low-maintenance materialsFunctional storage solutionsCost-effective execution with maximum usabilityExecution PriorityRepaintingKitchenWardrobesVanity UnitsTV UnitBedsSofaWallpaper | 2026-06-07 17:16:27 +0530 | Krutika Vernekar | CDP: 2bhk Ready posession Rented Property Living room : Tv Unit Vanity : in Both Wardrobe in 2 rooms (priority) Kitchen : With No Loft Next : 2 Beds + Wallpaper + Sofa + (End To End) No False Ceiling , Repainting Needed | 2026-06-26 |  | 2026-07-03
20459 | Turnkey | 2026-06-01 | Hemant Vichare | Dosti Eastern Bay | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar |  |  | Asif Shaikh | Akshat Shrivastava |  | Vandana Preet | Prasad Bhivaji Hande | Active | Preproduction | Hoto | 895039 | 161347 | 1080444 | 895039 | 0 | 1 | 0 | 0 | 0 | 439882 | 293810 |  |  | 2026-06-07 | 2026-06-09 12:32 | 2026-06-09 | 2026-06-09 13:41 | 2026-06-09 | 2026-06-09 14:12 | 2026-06-23 | 2026-06-23 16:32 | 2026-07-08 | 2026-07-07 17:23 | 2026-07-15 | 2026-07-14 20:26 | 2026-06-09 | 2026-06-09 19:03 | 2026-06-10 | 2026-06-12 11:56 | 2026-06-12 | 2026-06-12 17:56 | 2026-06-17 | 2026-06-17 12:09 |  |  |  |  | 2026-07-03 | 2026-06-21 15:34 | 2026-07-10 | 2026-07-12 23:15 | 2026-07-13 | 2026-07-14 08:41 |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-08-31 |  | 2026-09-01 | [6 empty] | 2026-09-19 |  | 2026-09-28 |  | 2026-08-03 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-10-01 |  |  |  | 2026-10-23 |  | 2026-10-25 |  | 2026-10-26 | [5 empty] | 2026-07-16 |  | 2026-06-18 | 2026-06-23 16:08 | Site is RTMI | 2026-06-07 | 2026-06-07 17:06 | 923275.1481 | 164813 | 1015383.9755 | 169657 | 0 | 0 | 1015383.9755 | 169657 | 2026-07-11 17:54:31 +0530 | Mehnaz Ashraf |  | 2026-07-10 19:20:48 +0530 | Mehnaz Ashraf | cross measurement done today. | 2026-07-07 17:16:45 +0530 | Mehnaz Ashraf | Quote shared with client after DEM 2, CM aligned this Friday at 11:00 AM. | 2026-06-24 | 2026-06-23 16:33 | 2026-07-08 | 2026-07-07 17:23 | Under Construction | 2026-06-20 | 2026-06-07 | 108000 | Ravi Roy
20461 | Turnkey | 2026-06-01 | Mr Ritwik Ranadive | JVMs Monica Gardens | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Foram Joshi |  | Active | Preproduction | DEM2 | 1620275 | 415328 | 2026646 | 0 | 0 | 8 | 0 | 0 | 0 | 624701 | 580246 |  |  | 2026-06-07 | 2026-06-07 22:04 | 2026-06-07 | 2026-06-09 19:26 | 2026-06-21 | 2026-06-21 21:28 | 2026-07-08 | 2026-07-08 11:02 | 2026-07-14 |  | 2026-07-21 |  | 2026-06-21 | 2026-06-21 21:40 | 2026-06-22 | 2026-06-23 11:57 | 2026-06-23 | 2026-06-23 14:46 | 2026-06-25 | 2026-06-25 12:42 |  |  |  |  | 2026-06-30 | 2026-06-25 12:41 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-06-26 | 2026-07-07 15:18 | Site is RTMI | 2026-06-07 | 2026-06-07 22:03 | 1717496 | 309149 | 0 | 0 | 0 | 0 | 1717496.1892 | 300199 | 2026-07-08 12:15:40 +0530 | Harshali Bhuyar | Minutes of Meeting held on Date: 5th July 2026 Attendees: Client & Designer Discussion: Virtual ï»¿ Based on 5th July meeting, below is a list of all the requirements that were discussed during the meeting. Initial quotation. Initial Model. Changes in wardrobe internals. Changes in kitchen. Rough discussion on false ceiling. Wall concepts for all rooms. Loose furniture scope. Material selection meeting on 12th July 2026. Thanks & Regards | 2026-07-04 15:09:44 +0530 | Harshali Bhuyar | Client is not ready to visit the center due to heavy rains, wanted to postpone it to next weekend. Have planned the meeting virtually for this sunday. | 2026-06-25 12:45:58 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-07-09 | 2026-07-08 11:10 | 2026-07-15 |  | RTMI |  | 2026-06-21 | 415328 | Ravi Roy
20463 | Turnkey | 2026-06-01 | Ratna Jat | Moonrise | MUM - GOR | Yes | Neha Yadav | Reshma Melanta | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Design | DEM1 | 3558035 | 466093 | 4660926 | 0 | 0 | 15 | 0 | 0 | 245514 | 1666038 | 1180389.6 |  |  | 2026-06-07 | 2026-06-16 12:43 | 2026-06-07 | 2026-06-23 17:29 | 2026-06-28 | 2026-06-28 12:13 | 2027-02-05 |  | 2027-02-12 |  | 2027-02-19 |  | 2026-06-28 | 2026-06-30 14:31 | 2026-06-29 | 2026-06-30 14:55 | 2026-06-30 | 2026-06-30 18:46 | 2026-07-05 | 2026-07-04 17:12 |  |  |  |  | 2027-02-06 |  | 2027-02-14 |  | 2027-02-15 |  |  |  | 2027-02-22 |  | 2027-02-23 |  | 2027-02-24 |  | 2027-02-25 | [6 empty] | 2027-03-15 |  | 2027-03-24 |  | 2027-03-23 |  | 2027-03-24 |  | 2027-03-25 |  | 2027-03-27 |  |  |  | 2027-04-18 |  | 2027-04-20 |  | 2027-04-21 | [5 empty] | 2027-02-23 |  | 2027-02-01 |  | Unknown | 2026-06-07 | 2026-06-07 18:10 | 3949937 | 710988 | 0 | 0 | 0 | 0 | 3930822.16 | 648996 | 2026-07-04 17:28:34 +0530 | Reshma Melanta | Others: CRM UPDATE PRISCOPE ADDED | 2026-07-04 17:09:32 +0530 | Reshma Melanta | Others: Minutes of Meeting (MOM) Project ID: 20463 Client Name: Ratna Jat Date: July 4, 2026 Objective: To address current project roadblocks, align on upcoming design milestones, and streamline communication channels. POSSESSION : OCT 2027 Key Discussion Points & Client FeedbackCommunication Escalation: The client expressed strong dissatisfaction regarding a lack of responsiveness to her recent calls and messages. She highlighted a gap in communication following an intensive, 8-hour design discussion previously held with Priyanka Patel. Layout Clarification: The client requested immediate clarity and a formal revert regarding the layout discussions that took place. Payment & Agenda Alignment: The client raised concerns regarding the 10% milestone payment request, noting that she cannot process payments without a clear understanding of the meeting agenda and the deliverables linked to it. | 2026-06-30 18:45:31 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: April 2027 Scope of Work: Modular + Painting + Wallpaper + Membrane (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 160+ 20+ 31 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * DEM 1 once we get the site accessibility * 10% Payment Stage 15th July 2026 Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 39,30,822 Offers Discussed During the Call: Free Shoerack Offer Design fee waiver (5%) PM fee waiver (5%) 100% GST Waiver Laminate Upgrade - Jun 26 Campaign Final Closing Value Discussed: 35,58,036 Note: New address 4101, Rivali Park- Moonrise, Rivali Park, CCI Compound,, Off W.E. Highway, Borivali East, Mumbai- 400066 | 2027-02-06 |  | 2027-02-13 |  | Under Construction | 2027-04-30 | 2026-06-27 | 466093 | Ravi Roy
20464 | Turnkey | 2026-06-01 | Deepak Sahebrao Pawar | Balaji Heights | MUM - GOR | Yes | [8 empty] | Shoaib Shaikh |  | Active | Prospect | DCM Due | 1053764 | 9999 | 1053764 | 0 | 0 | 35 | 0 | 95377 | 105376 | 462118 | 380893.6 |  |  | 2026-06-07 | 2026-06-10 12:32 | 2026-06-07 | 2026-07-02 13:34 | 2026-06-28 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-06-07 | 2026-06-10 12:31 | 895119 | 158645 | 0 | 0 | 0 | 0 | 895119 | 158645 | 2026-06-09 13:52:33 +0530 | Hamza Choudhary | DCM: Minutes of Meeting held on Date: 07-06-2026 Living Room -Sofa Set -4seater Dining -Tv unit & shelf for display -Mandir -Shoe Rack Kitchen -Base, wall & loft unit -Microwave Unit Bedroom -Wardrobe -Bed 5'x6'6" -Study Table with shelf -Side table & Dresser Unit | [6 empty] | 2026-07-13 |  | 2026-07-20
20465 | Turnkey | 2026-06-01 | JYOTHISH RAJAMOHANAN NAMBIAR | MICL Aaradhya Parkwood | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | 10% Payment | 3018470 | 9999 | 3018470 | 0 | 0 | 34 | 0 | 291848 | 301847 | 1301676 | 1113100 |  |  | 2026-06-07 | 2026-06-07 22:16 | 2026-06-07 | 2026-06-09 19:02 | 2026-06-14 | 2026-06-16 13:37 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-07 | 2026-06-07 20:33 | 2560268 | 458201 | 0 | 0 | 0 | 0 | 2560268 | 458201 | 2026-06-14 21:20:00 +0530 | Maasoumeh Raza | CDP: Recap: 20465 - Celebrity Design Presentation (CDP) with the customer Sunday, June 14 ¦ Meeting ¦ Microsoft Teams | 2026-06-09 18:58:00 +0530 | Maasoumeh Raza | DCM: Client Name: Jyotish Rajamohanan Nambiar Property Configuration: 4 BHK Family Members: 5 (Couple, Mother-in-law, Son, Daughter) + 1 Pet Dog Budget: 25 Lakhs Proposed Design Budget (CDP Meeting): 3538 Lakhs Existing Furniture: None (Complete new furniture and interiors required) Preferred Theme: Modern Traditional Entrance Foyer Shoe rack to be designed in the passage area near the entrance. Multi-purpose storage unit required for: Umbrellas 34 helmets Dog leash and pet accessories Other daily-use items Movable puffee seating required for convenience while wearing shoes. Living & Dining Area Combined living and dining space. 6-seater dining table required. Crockery unit to be incorporated. Comfortable sofa seating for family and guests. Dining area is proposed in the living room as the kitchen is located directly opposite. Additional Requirements TV unit in the dining area. Dedicated floor seating arrangement preferred by the client. Provision for washing machine and separate dryer unit near the dining area. Client would like design options for: TV unit with bar counter, or Separate bar counter arrangement if feasible. Kitchen Client intends to remove the builder-provided kitchen wall and create an open kitchen concept. L-shaped kitchen layout proposed as per client requirements. Requirements Dishwasher provision. Appliance unit. Pantry unit. Refrigerator to be placed on the wall adjacent to the common toilet. Sink to be shifted to the area currently designated for the washing machine. Hob/Burner to be positioned on the main platform. Base units, wall units, and loft storage required throughout the kitchen. Mother-in-Law's Bedroom Furniture Requirements Bed Wardrobe Side tables Mirror Attached Bathroom Vanity unit required. Son's Bedroom Furniture Requirements Queen-size bed Wardrobe Side tables Study table Attached Bathroom Vanity unit required. Daughter's Bedroom Furniture Requirements Queen-size bed Wardrobe Side table Study table with bookshelf Mirror integrated at the wardrobe end Attached Bathroom Vanity unit required. Master Bedroom (Couple) Furniture Requirements Bed Wardrobe Side tables Dedicated dressing unit Attached Bathroom Vanity unit required. Common Requirements False ceiling throughout the house. Complete painting work. Electrical planning Modern Traditional design language to be followed across all spaces. Client has shared reference images for inspiration. Client is open to alternative design concepts and would like the designer's recommendations and theme options before finalization. | 2026-06-09 18:38:27 +0530 | Maasoumeh Raza | DCM: Recap: 20465 - Design Consultation Meeting (DCM) with the customer Sunday, June 7 ¦ Meeting ¦ Microsoft Teams | 2026-06-24 |  | 2026-07-01
20466 | Turnkey | 2026-06-01 | Virender/pranav khaneja | nirman Apt | MUM - GOR | Yes | Swapnali Shedekar | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Ashish Jha |  | Hold | Design | 20% Payment | 1329360 | 259999 | 1728689 | 0 | 0 | 6 | 16 | 0 | 5873 | 591186 | 472301.6 |  |  | 2026-06-07 | 2026-06-12 13:24 | 2026-06-10 | 2026-06-13 14:39 | 2026-06-13 | 2026-06-15 11:47 | 2026-06-24 | 2026-06-23 14:07 | 2026-07-21 |  | 2026-07-28 |  | 2026-06-13 | 2026-06-13 14:11 | 2026-06-14 | 2026-06-14 12:29 | 2026-06-16 | 2026-06-15 17:47 | 2026-06-17 | 2026-06-17 15:45 |  |  |  |  | 2026-06-23 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-06-18 | 2026-06-23 12:23 | Site is RTMI | 2026-06-07 | 2026-06-12 13:19 | 1467929 | 260760 | 0 | 0 | 0 | 0 | 1467929.0788 | 244368 | 2026-06-29 16:55:55 +0530 | Vishakha Vaishnav | Some Image was uploaded | 2026-06-17 15:45:19 +0530 | Vishakha Vaishnav | "Welcome call done" Initial measurement : Can be done site is accessible need to align IM DEM Dates -Â DEM 1 - Can be done either thiis weekend or in 1st week of july DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% onÂ after dem 1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-15 17:46:03 +0530 | Athul Ajaykumar | Possession Status: Renovation Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend) * DEM 1 Tentatively scheduled for (July 1 Week) * 10% Payment Stage Tentatively scheduled for (25th June 2026) * Civil work - yes * B2C - Self Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (2.5%) Free Shoerack Offer PM fee waiver (5%) May '26 Net Special Studio Offer 100% GST Waiver Final Closing Value Discussed: 13,29,360 Checklist terms descoping, agreement terms are clearedÂ Client VOC: The client mentioned that civil work is planned, including tile work throughout the house and bathroom tiling. The client did not specify the estimated completion timeline for these activities. | 2026-06-24 | 2026-06-23 14:09 | 2026-07-22 |  | RTMI |  | 2026-06-13 | 172869 | Ravi Roy
20467 | Turnkey | 2026-06-01 | Nikhil Gaikwad | Ashford regal | MUM - Thane | Yes | [8 empty] | Rahul Kumawat |  | Active | Prospect | 10% Payment | 1351821 | 9999 | 0 | 0 | 0 | 33 | 0 | 125183 | 135182 | 628666 | 452790.4 |  |  | 2026-06-07 | 2026-06-07 19:56 | 2026-06-10 | 2026-06-12 17:24 | 2026-06-13 | 2026-06-16 13:47 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-07 | 2026-06-07 19:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1145611 | 206210 | 2026-06-17 16:59:22 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-17 16:59:00 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-16 19:31:47 +0530 | Anjali Singh | CDP: Recap: 20467 - Celebrity Design Presentation (CDP) with the customer 13 June ¦ Meeting ¦ Microsoft Teams | 2026-06-24 |  | 2026-07-01
20468 | Turnkey | 2026-06-01 | Sapna Ramani | The rising city by Hubtown | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | Onboarding Due | 1468537 | 204102 | 1468537 | 0 | 0 | 5 | 0 | 0 | 89605 | 681836 | 492993.2 |  |  | 2026-06-07 | 2026-06-09 12:47 | 2026-06-10 | 2026-06-10 18:31 | 2026-07-03 | 2026-07-10 00:51 | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-07-03 | 2026-07-03 19:18 | 2026-07-04 | 2026-07-10 12:59 | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-07 | 2026-06-07 19:51 | 1712626.844 | 272886 | 0 | 0 | 0 | 0 | 1712626.844 | 272886 | 2026-07-10 15:00:22 +0530 | Sanjana Swami | Possession Status: RTMI - Registration will be closed by July end 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM â€“ Client mentioned that she will be back after 16th July and then do the registration of the house; after that IMs can be done. * DEM 1 â€“ Tentatively scheduled for (Date) * 10% Payment Stage â€“ In the month of August after the 1st dem Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Final Closing Value Discussed: â‚¹ 14,68,537 Checklist terms - descoping, delay compensation, agreement terms are cleared or not Rejections: Approval for payment deviation is required, as the client mentioned that she wants to start with 1st dem in the month of August 2026, and she will pay after that. Didn't mention how soon after DEM 1 Client is not ready to listen to OB call and asked to email the OB points so that she can check and acknowledge them. She mentioned that she has emailed her timeline to Moni and asked to coordinate internallyâ€”kindly share the conversations that have been between SM and the customer. | 2026-07-10 13:10:33 +0530 | Moni Sahani |  | 2026-06-10 18:29:23 +0530 | Shreya Sonavane | DCM: User ResponseCustomer and Project Profile1. Name of the customer Sapna Ramani 2. Profession salaried 3. Project Name/Tower Name/Flat Number The rising city by Hubtown 4. Typology (1BHK, 2BHK, 3BHK, etc) 3bhk 5. Site Access Date 2026-06-10 6. Possession Date 2026-07-10 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 15 Customer Preferences8. Who will be living in the house? Nuclear Family 9. What activities do you usually prefer at your home ? Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) Upload reference images 14. Any absolute no-go styles colours or materials 15. Do you have any existing furniture that must be accommodated? 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? TV Focus 2. Must-have furniture or features? TV unit, Sofa 3. Choose your decor inspirations 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Dishwasher 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom No 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Study table , Dresser , TV unit 9. False Ceiling Required - Bedroom 1 No 10. Bedroom 2 - Utility Parents 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units Study Table, Dresser, TV Unit 14. False Ceiling Required - Bedroom 2 No 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Bottom Storage Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 1500000 | 2026-07-17 |  | 2026-07-24 |  |  |  | 2026-06-30 | 204103 | Ravi Roy
20470 | Turnkey | 2026-06-01 | Hemant more | Godrej exquisite | MUM - Thane | Yes |  | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Active | Design | DEM1 | 1009096 | 209999 | 1278498 | 0 | 0 | 2 | 0 | 0 | 0 | 420801 | 378296.4 |  |  | 2026-06-07 | 2026-06-09 11:42 | 2026-06-14 | 2026-06-15 19:37 | 2026-07-10 | 2026-07-10 21:21 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-10 | 2026-07-11 22:14 | 2026-07-11 | 2026-07-11 22:15 | 2026-07-11 | 2026-07-13 17:28 | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-07 | 2026-06-09 11:20 | 1083472 | 195025 | 0 | 0 | 0 | 0 | 1083472.6121 | 190187 | 2026-07-13 17:27:52 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession: September/October Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 20 Business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Site is not accessible * DEM 1 â€“ Client wants to do the DEM1 once he get the possession * 10% Payment Stage â€“ 20% also already closed Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (3%) Free Shoerack Offer May'26 100% GST waiver Silver Coin Offer Final Closing Value Discussed: 10,09,096 Checklist terms - descoping and agreement terms are cleared Client VOC: The client mentioned he will do the DEM1 once he gets the possession. Possession by September/October | 2026-07-13 17:10:40 +0530 | Athul Ajaykumar | OB Initiated - Call disconnected | 2026-07-12 22:08:56 +0530 | Anant Giri | Others: | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2026-10-31
20471 | Turnkey | 2026-06-01 | SISINDRA REDDY PASUPALA | DC Capitol II | BNG - HSR | Yes | Sreenivasulu Reddy | Akshay Ds | Kowshik | [5 empty] | Pulivarthi Nirosha |  | Active | Design | DEM1 | 1001570 | 130999 | 1407060 | 0 | 0 | 16 | 0 | 0 | 69315 | 410834 | 390422.4 |  |  | 2026-06-07 | 2026-06-12 11:57 | 2026-06-14 | 2026-06-14 13:24 | 2026-06-20 | 2026-06-21 11:21 | 2026-07-08 |  | 2026-07-15 |  | 2026-07-22 |  | 2026-06-21 | 2026-06-23 18:27 | 2026-06-22 | 2026-06-23 19:36 | 2026-06-23 | 2026-06-29 11:45 | 2026-07-03 | [5 empty] | 2026-07-09 |  | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-07-26 |  | 2026-07-04 |  | Unknown | 2026-06-07 | 2026-06-07 20:17 | 1192423 | 214636 | 0 | 0 | 0 | 0 | 1143602.902 | 188832 | 2026-06-29 11:32:26 +0530 | Sanjeev Jha | Some Image was uploaded | 2026-06-24 17:19:51 +0530 | Bency Chacko |  | 2026-06-24 17:06:56 +0530 | Pulivarthi Nirosha | Some Image was uploaded | 2026-07-09 |  | 2026-07-16 |  | Under Construction | 2026-12-31 | 2026-06-20 | 130999 | Ravi Roy
20472 | Turnkey | 2026-06-01 | Vivek Kaneri | Godrej Exquisite | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | 10% Payment | 1976685 | 9999 | 1976685 | 0 | 0 | 8 | 0 | 187670 | 197669 | 858326 | 723021.6 |  |  | 2026-06-07 | 2026-06-09 11:43 | 2026-06-24 | 2026-06-25 11:39 | 2026-06-29 | 2026-07-07 11:17 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-07-15 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-10 |  | Unknown | 2026-06-07 | 2026-06-09 11:42 | 1677465 | 299220 | 0 | 0 | 0 | 0 | 1677465 | 299220 | 2026-07-07 11:20:39 +0530 | Yerra Bharat | Others: Due to issue from the client side, meeting was taken with google meet and meeting is recorded using screen recording. Recording is uploaded into the drive. | 2026-06-30 12:56:58 +0530 | Yerra Bharat | CDP: In Living room Instead of sofa and TV unit. Need two diwan style beds on both side and need storage near the bed and no TV Unit. Pooja mandir in the NE corner facing E-W, need storage beside mandir on both sides. Console style half height storage and top storage opp to the door. M. Bedroom: queen size bed side table wardrobe with loft dresser with mirror as door foldable study with top storage and open storage for books on the side TV ledge Bedroom -2 queen size bed movable side table wardrobe with loft dresser with mirror as door foldable study with top storage and open storage for books on the side Client stated that the proposed design does not fully meet his current functional requirements. Living room requirement has changed from a sofa-cum-bed with TV unit to two diwan-style beds with storage on both sides and no TV unit. Client reiterated his requirement for a swing in the living room. It was explained that accommodating the swing along with the essential furniture would significantly affect circulation and available space. Client requested waterproofing below the living room, passage, and balcony flooring. It was explained that the current scope includes flooring replacement (excluding materials), while waterproofing is typically proposed only for wet areas. Client was not convinced and expects waterproofing to be included. Client is currently exploring options in the market and indicated that he is not ready to finalize the project at this stage. Client reviewed the commercial quotation but did not proceed with any commercial discussion during the meeting. Design Changes RequestedLiving Room Remove sofa and TV unit. Provide two diwan-style beds. Storage adjacent to both beds. No TV unit. | 2026-06-30 12:27:52 +0530 | Yerra Bharat | Some Image was uploaded | 2026-07-15 |  | 2026-07-22
20473 | Turnkey | 2026-06-01 | TARUN SURESH MAKHIJANI | Codename Rare | MUM - GOR | Yes | [8 empty] | Ashutosh Singh |  | Active | Prospect | DCM Due | 1700421 | 9999 | 0 | 0 | 0 | 37 | 0 | 160043 | 170042 | 697328 | 663009.2 |  |  | 2026-06-08 | 2026-06-08 18:25 | 2026-06-08 |  | 2026-06-10 |  | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-06-10 |  | 2026-06-11 |  | 2026-06-11 |  | 2026-06-12 | [5 empty] | 2026-06-18 |  | 2026-06-26 |  | 2026-06-27 |  |  |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-07 | [6 empty] | 2026-07-25 |  | 2026-08-03 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-06 |  |  |  | 2026-08-28 |  | 2026-08-30 |  | 2026-08-31 | [5 empty] | 2026-07-05 |  | 2026-06-13 |  | Unknown | 2026-06-08 | 2026-06-08 18:10 | 0 | 0 | 0 | 0 | 0 | 0 | 1441035 | 259386 | 2026-06-09 17:05:32 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-09 17:04:18 +0530 | Rishika Malviya | Some Image was uploaded |  |  |  | 2026-06-18 |  | 2026-06-25
20477 | Turnkey | 2026-06-01 | mukesh Jain | Agarwal florenza | MUM - GOR | Yes | [8 empty] | Ashish Jha |  | Active | Prospect | 10% Payment | 2189583 | 9999 | 2189583 | 0 | 0 | 15 | 0 | 208959 | 218958 | 875833 | 875833.2 |  |  | 2026-06-09 | 2026-06-16 18:31 | 2026-06-10 | 2026-06-30 13:57 | 2026-07-03 | 2026-06-30 14:22 | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-06-09 | 2026-06-16 12:36 | 1855579 | 334004 | 0 | 0 | 0 | 0 | 1855579 | 334004 | 2026-06-30 16:09:16 +0530 | Rahul Agrawal | CDP: They were only looking for wardrobes and kitchen , they have already hired an architect for their entire house designing , yet they havent finalised their design so they are yet to make descision regarding wardrobes and kitchen and hence they just wanted to check the quotation. | 2026-06-30 14:20:55 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-16 11:39:38 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-07-08 |  | 2026-07-15
20479 | Turnkey | 2026-06-01 | Uday K | INDEPENDENT HOUSE | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Preproduction | Site Readiness 1 | 929808 | 195999 | 1290492 | 0 | 0 | 15 | 0 | 0 | 0 | 402368 | 331441.2 |  |  | 2026-06-07 | 2026-06-11 17:07 | 2026-06-12 | 2026-06-12 17:58 | 2026-06-14 | 2026-06-14 21:06 | 2026-06-27 | 2026-06-27 19:16 | 2026-09-29 |  | 2026-10-06 |  | 2026-06-14 | 2026-06-14 13:43 | 2026-06-15 | 2026-06-17 12:05 | 2026-06-15 | 2026-06-17 17:24 | 2026-06-20 | 2026-06-20 12:47 |  |  |  |  | 2026-06-27 | 2026-06-30 16:35 | 2026-10-01 |  | 2026-10-02 |  |  |  | 2026-10-09 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 | [6 empty] | 2026-10-30 |  | 2026-11-08 |  | 2026-11-07 |  | 2026-11-08 |  | 2026-11-09 |  | 2026-11-11 |  |  |  | 2026-12-03 |  | 2026-12-05 |  | 2026-12-06 | [5 empty] | 2026-10-10 |  | 2026-06-21 | 2026-06-27 19:12 | Site is Non-RTMI | 2026-06-07 | 2026-06-09 12:56 | 1093637 | 196854 | 0 | 0 | 0 | 0 | 1065433.4254 | 175915 | 2026-06-27 18:33:44 +0530 | Ashiya Sanam | Minutes of Meeting held on Date: Title:DEM-1 Project: Client: Attendees: Objective: Discussion As discussed following are the points discussed: Living Room: 1.Pooja unit to be designer a fluted shutter with metal frames and edge profile handles. 2.For dining area wall need to keep charcoal beading and outer would be VB 30 AND INNER WOULD VB 22,and height to be matched with the pooja and door 3.Crockery unit-Wall unit to be removed and shelves to be added and right side wall to be designed as per the theme 4.Door panelling arch to be done in curved shape in wooden laminate finish 5.TV Unit-Louvers to be adjusted on both the sides equally and tv unit should start after the wall after the louvers where the side panels will be extended and back panel will will be extended , so that louvers come on top of it 6.Back panel colour to be DL 1112 7.To remove the shelves beside the TV unit 8.To go with the sofa wall image shared by cx-as custom printing 9.False ceiling to be designed as per the reference image shared in the group Kitchen: 1.Spice rack size to be 150 mm and wall unit to be 600 mm 2.Granite in bonito scope-Both crockery and kitchen-Need to check the quote once-Installation of dado tiles and granite in bonito scope 3.Wall units to have grey tinted glass with black profile 4.Inner cabinet lighting to be provided bottom on unit from back side and for wall units, grooving to be provided from the sides 5.Cutlery unit-First drawer to be cutlery tray and bottom 2 drawers will be tandem. 6.Ro Unit to be discussed as per the space 7.Gas line pipe to be moved below and to be aligned till the hob-Need to get a confirmation from builder. 8.Fridge space(62cm) to be considered and oven (49cm) space to be considered accordingly. 9.Two switch points are needed for oven and fridge 10.Shelves to be adjusted as per oven height Master Bedroom; 1.Wallpaper to be considered but designs needs to be suggested 2.Wardrobe internals-left side complete hanger rod with no partition in between , on the left side four shelves with partition and third shelf without partition 3.Dresser unit to be considered after the wardrobe 4.False ceiling to be considered-Same design as per reference image 5.Ledge to be removed for tv unit Master bedroom(Bathroom and toilet): 1.Vanity to be removed 2.shower partition to be added in the design Kids bedroom: 1.False ceiling to be considered-Same design as per reference image 2..Existing wardrobe to be kept inside the wardrobe-dimensions to be checked. 3.Left side wardrobe internal to be considered with shelves Home theatre room: 1.Box panelling to be done for curtains 2.Same size of the units Bathroom and toilet: 1.Vanity to be removed NOTE: 1.Currently Electricals are added in bonito scope 2.Painting in cx scope 3.As per the designs the quote may vary | 2026-06-20 12:47:40 +0530 | Rajeshwari S | Welcome call done along with Designer Ashiya and and Design Manager. Under construction project Possession expected in September Wants to start with the design phase and complete the layout finalization. And informed that project will go on hold after layout finalization till he gets the position Measurement can be used if the 6th floor apartment (his friend getting it done by Bonito) 1st Design meeting on 27th June Estimation closed for Rs.9,29,809/- 20% payment. Explained the payment process Aligned with the process. | 2026-06-17 17:23:08 +0530 | Sanjana Swami | Possession Status: Underconstruction Under construction completion date: client will be getting the possession within a week Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: IM Next week after getting the possession, client will let us know DEM 1 client will be available in weekdays 10% Payment Stage paid 20% Transaction will be B2C self-funding. No civil work planned in client's scope of work Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 10,65,434 Offers Discussed During the Call: Free Shoerack Offer Laminate Upgrade - Jun 26 Campaign PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Final Closing Value Discussed: 9,29,809 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-28 | 2026-06-27 19:19 | 2026-09-30 |  | Under Construction | 2026-06-17 | 2026-06-13 | 129049 | Ravi Roy
20480 | Turnkey | 2026-06-01 | Paresh K kapadia | hiranandani castalia | MUM - GOR | Yes | Khyati Bandi | Christopher Macwan | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Preproduction | DEM2 | 1257249 | 251450 | 1689426 | 0 | 0 | 10 | 0 | 0 | 0 | 591827 | 413971.6 |  |  | 2026-06-09 | 2026-06-15 15:20 | 2026-06-07 | 2026-06-16 11:40 | 2026-06-19 | 2026-06-16 11:45 | 2026-07-07 | 2026-07-07 14:34 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-16 | 2026-06-20 14:12 | 2026-06-17 | 2026-06-22 12:03 | 2026-06-22 | 2026-06-22 13:46 | 2026-06-24 | 2026-06-24 14:14 |  |  |  |  | 2026-07-07 | 2026-07-05 17:47 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-06-25 | 2026-07-05 17:46 | Site is RTMI | 2026-06-09 | 2026-06-09 14:26 | 1431717 | 257709 | 0 | 0 | 0 | 0 | 1422464.462 | 234854 | 2026-07-05 17:34:07 +0530 | Khyati Bandi | LIVING ROOM - 1. Add blue light to keep panchmukhi hanuman idol on shelf 2. Add socket above crockery unit for ironing 3. Add 2 drawers above crockery unit, height will be increased 4. Existing sofa will be there 5. Single seater swing in living area 6. Add red light on clock wall, remove clock and place shree yantra on it 7. Clock will be placed on kitchen wall 8. Add chandelier in center of living room (yellow in color) 9. Add switch and festive light in balcony 9. Curtains to be in green and white in color 10. Add sliding shutter/ Swing shutter in washing machine area 11. Add metal strip on living back wall 12. Add indirect light on both side of shreenath ji frame 6'x4'4 Mandir room - 1. Mandir width 32" depth 17" height 30" 2. Marble on top of mandir unit 3. Mandir shelf will be adjustable 4. Wardrobe depth 2' 5. Add cloth hanging unit (To keep glass containers) depth 15" 6. All shelves in wardrobe all adjustable 7. Add printed wallpaper 8. Add fan near mandir Guest bedroom - 1. remove storage behind mirror, only mirror will be placed 2. Add cloth hanging unit 3. Add hidden drawer in the wardrobe 4. Bed without storage (queen size bed) 5. Add side table MBR - 1. 1. remove storage behind mirror 2. Add cloth hanging unit with mirror on it 3. Add hidden drawers in both the wardrobes 4. Mma wardrobe - add organizer tray + hidden drawer and 3 long drawers Sir wardrobe - add locker shutter in wardrobe 5. Add side table 5. No storage in bed (queen size bed) 6. White and golden element in full home | 2026-06-24 14:23:12 +0530 | Christopher Macwan | Welcome call done along with the Designer. Initial measurement not done as would receive possession by End of October 2026 DEM Dates -Â DEM 1 - Customer will update by tomorrow 25th June for DEM1 DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of October 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-22 13:45:31 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: end of October 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 1st week of July 2026 * 10% Payment Stage by 2nd July 2026 (after 1st DEM) *Client has not yet planned for the civil work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 14,22,465 Offers Discussed During the Call: Â Design Fee Waiver (2.5%) Silver Coin 21g Free Shoerack Offer Laminate Upgrade - Jun 26 Campaign PM fee waiver (7.5%) 100% GST Waiver Final Closing Value Discussed: 12,57,250 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-08 | 2026-07-07 14:36 | 2026-07-14 |  | Under Construction | 2026-10-31 | 2026-06-15 | 168943 | Ravi Roy
20481 | Turnkey | 2026-06-01 | SHYAMAL KAPADIA | Hiranandani | MUM - GOR | Yes | Shweta Dalvi | Christopher Macwan | Safalta Karkera | [5 empty] | Rashmita Das |  | Active | Design | DEM1 | 987670 | 134379 | 1343796 | 0 | 0 | 23 | 0 | 0 | 63155 | 444711 | 345424.8 |  |  | 2026-06-09 | 2026-06-15 15:28 | 2026-06-09 | 2026-06-15 19:29 | 2026-06-18 | 2026-06-15 21:30 | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-06-15 | 2026-06-20 16:09 | 2026-06-16 | 2026-06-21 12:38 | 2026-06-21 | 2026-06-22 11:53 | 2026-06-24 | 2026-06-24 19:33 |  |  |  |  | 2026-06-30 |  | 2026-07-08 |  | 2026-07-09 |  |  |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 | [6 empty] | 2026-08-06 |  | 2026-08-15 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-18 |  |  |  | 2026-09-09 |  | 2026-09-11 |  | 2026-09-12 | [5 empty] | 2026-07-17 |  | 2026-06-25 |  | Unknown | 2026-06-09 | 2026-06-09 14:26 | 1138810 | 204985 | 0 | 0 | 0 | 0 | 1128524.275 | 186330 | 2026-06-24 19:35:17 +0530 | Christopher Macwan | Welcome call done. Initial measurement not done as would receive possession by End of October 2026 DEM Dates -Â DEM 1 - Customer will update on the group about the meeting on Sunday which will be in the middle of the week DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of October 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-22 11:52:37 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: Mid of October 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Site is not accessible. * DEM 1 5th July 2026 * 10% Payment Stage 2nd July 2026 (after 1st DEM) *No civil work planned *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11,28,525 Offers Discussed During the Call: Design Fee Waiver (2.5%) Silver Coin 21g Free Shoerack Offer Laminate Upgrade - Jun 26 Campaign PM fee waiver (7.5%) 100% GST Waiver Final Closing Value Discussed: 9,87,671 Checklist terms - descoping, delay compensation, agreement terms are clearÂ | 2026-06-21 12:55:23 +0530 | Rashmita Das | DearÂ Â Mr Kapadia Greetings from Bonito! Thank you for choosing Bonito Designs to do your home interiors. This email is with respect to your quote. It is to confirm that we have received payment of Rs. 9,999/- and Rs.1,24,380- (Total Paid -Rs.1,34,379/-)Â Please find the quotation in attachment & calculation below for your reference:- Up to 1L Laminate Upgrade - Windows to Wonderful home Quoted without GST- Rs. 11,28,525/- Quoted value with GST- Rs.13,31,659/- Special discount - Project Management fees is 10% out of this 7.5% is waived off i.e. is waived off.Rs. 70,015.5/- Special discount - Design fees is 10% out of this 2.5% is waived off i.e. is waived off.Rs. 23,338.71/- -100% GST WAIVER -FREE SHOE RACK OFFER After this, the payable value with GST Rs. 9,87,671/- May '26 Net Special Studio Offer 20K REFFERAL OVER POST 20% OF THE PAYMENT | 2026-06-30 |  | 2026-07-07 |  | Under Construction | 2026-10-15 | 2026-06-16 | 134379 | Ravi Roy
20482 | Sub Project |  | Roopa Srinivas Shetty | peepal grove | BNG - HRBR | No Estimate | Arjun M V | Rajeshwari S | Shibin Lal | [7 empty] | Active | Preproduction | 3D Sign off | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-09 | 2026-06-09 16:19 | 2026-06-10 | 2026-06-09 16:20 | 2026-06-09 | 2026-06-09 16:20 | 2026-06-10 | 2026-06-09 16:21 | 2026-06-10 | 2026-06-09 16:21 | 2026-06-10 | 2026-06-09 16:26 | 2026-06-09 | 2026-06-09 16:20 | 2026-06-10 | 2026-06-09 16:20 | 2026-06-09 | 2026-06-09 16:20 | 2026-06-10 | 2026-06-09 16:20 |  |  |  |  | 2026-06-09 | 2026-06-09 16:21 | 2026-06-10 | 2026-06-09 16:23 | 2026-06-10 | 2026-06-09 16:23 |  |  | 2026-06-10 | 2026-06-09 16:28 | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 | [6 empty] | 2026-09-09 |  | 2026-09-18 |  | 2026-09-17 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-13 |  | 2026-10-15 |  | 2026-10-16 | [5 empty] | 2026-08-20 |  | 2026-06-10 | 2026-06-09 16:20 | Unknown | 2026-06-09 | 2026-06-09 16:19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-06-10 | 2026-06-09 16:21 | 2026-06-10 | 2026-06-09 16:21
20483 | Turnkey | 2026-06-01 | Prakash Kulbe | Yashvant county | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Shreyash Kotecha |  | Hold | Preproduction | Site Readiness 1 | 1111333 | 280999 | 1376169 | 0 | 0 | 6 | 11 | 0 | 0 | 445318 | 385016.4 |  |  | 2026-06-07 | 2026-06-10 13:55 | 2026-06-11 | 2026-06-12 11:35 | 2026-06-14 | 2026-06-14 21:55 | 2026-06-29 | 2026-06-28 13:58 | 2026-09-25 |  | 2027-06-06 |  | 2026-06-14 | 2026-06-15 11:17 | 2026-06-15 | 2026-06-16 12:00 | 2026-06-16 | 2026-06-16 15:23 | 2026-06-25 | 2026-06-25 13:11 |  |  |  |  | 2026-07-01 | 2026-06-27 16:19 | 2027-06-01 |  | 2027-06-02 |  |  |  | 2027-06-09 |  | 2027-06-10 |  | 2027-06-11 |  | 2027-06-12 | [6 empty] | 2027-06-30 |  | 2027-07-09 |  | 2027-07-08 |  | 2027-07-09 |  | 2027-07-10 |  | 2027-07-12 |  |  |  | 2027-08-03 |  | 2027-08-05 |  | 2027-08-06 | [5 empty] | 2027-06-10 |  | 2026-06-26 | 2026-06-28 13:53 | Site is Non-RTMI | 2026-06-07 | 2026-06-09 16:38 | 1168530 | 207638 | 0 | 0 | 0 | 0 | 1164315.8388 | 197343 | 2026-07-14 17:39:57 +0530 | Divya Rahangdale | The project is on hold until the end of October as the site is not ready. | 2026-07-04 14:42:02 +0530 | Divya Rahangdale | Project will put on hold because site is not ready till August end. | 2026-06-28 14:02:40 +0530 | Asavari Vare | Project will put on hold post DEM because site is not ready. | 2026-06-29 | 2026-06-28 14:00 | 2026-09-26 |  | Under Construction | 2026-08-31 | 2026-06-13 | 280999 | Ravi Roy
20485 | Turnkey | 2026-06-01 | Yatin Satra | ridhi sidhi | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | [5 empty] | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1374939 | 274988 | 1794748 | 0 | 0 | 3 | 0 | 0 | 0 | 601399 | 498551.6 |  |  | 2026-06-09 | 2026-06-10 14:24 | 2026-06-10 | 2026-06-14 16:03 | 2026-06-17 | 2026-06-16 17:12 | 2026-07-02 | 2026-07-03 13:46 | 2026-07-09 |  | 2026-07-16 |  | 2026-06-16 | 2026-06-16 17:29 | 2026-06-17 | 2026-06-16 19:04 | 2026-06-16 | 2026-06-17 11:33 | 2026-06-20 | 2026-06-20 18:39 |  |  |  |  | 2026-07-03 | 2026-07-12 18:43 | 2026-07-11 |  | 2026-07-12 |  |  |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 | [6 empty] | 2026-08-09 |  | 2026-08-18 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-21 |  |  |  | 2026-09-12 |  | 2026-09-14 |  | 2026-09-15 | [5 empty] | 2026-07-20 |  | 2026-06-21 | 2026-07-02 16:56 | Site is RTMI | 2026-06-09 | 2026-06-09 18:26 | 1520973 | 273775 | 0 | 0 | 0 | 0 | 1516505.6975 | 256039 | 2026-07-12 18:49:36 +0530 | Reshma Melanta | Others: | 2026-06-20 18:38:39 +0530 | Reshma Melanta | MOM Update ¦ PID: 20485 (Yatin Satra) Project Type: RTMI Project IM (Installation/Initiation Meeting): Aligned for 23rd June 2026. DEM 1 Meeting: Client has requested this to be scheduled for the upcoming weekend, either Saturday, 27th June or Sunday, 28th June 2026 (post-IM). Project Group: New Designer, DM, and Bonito Care have been successfully added to the loop. Next Payment Milestone: 10% payment is scheduled for 27th June 2026. | 2026-06-17 11:33:25 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Planned on 18th June 2026. * DEM 1 This weekends * 10% Payment Stage by 27th June 2026 *No civil work planned in client's scope of work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 15,16,506 Offers Discussed During the Call: Laminate Upgrade - Jun 26 Campaign Free Shoerack Offer 100% GST Waiver PM fee waiver (7.5%) Final Closing Value Discussed: 13,74,939 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-04 | 2026-07-03 13:47 | 2026-07-10 |  | RTMI |  | 2026-06-14 | 179475 | Ravi Roy
20486 | Turnkey | 2026-06-01 | Ameet Kumar Das | Puranik | MUM - Thane | Yes | [8 empty] | Anant Giri |  | Active | Prospect | DCM Due | 1248596 | 9999 | 0 | 0 | 0 | 35 | 0 | 114861 | 124860 | 572956 | 425920.4 |  |  | 2026-06-09 | 2026-06-10 11:05 | 2026-06-18 | 2026-06-18 19:48 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-06-09 | 2026-06-10 10:57 | 0 | 0 | 0 | 0 | 0 | 0 | 1058132 | 190463 | 2026-06-18 19:15:53 +0530 | Hemant Sonar | DCM: Budget -10-12 lacs | 2026-06-18 19:14:11 +0530 | Hemant Sonar | DCM: Project Name: DCM * Possession: September 2026 * Client Profile: Working couple (IT professionals) Living Area * 3-seater sofa * TV unit * 4-seater dining table * Shoe unit * Safety door * Crockery unit * Balcony to be integrated and used as an extension of the living room(optional as per the site condition) Kitchen * Semi-modular kitchen * Pantry unit(optional) Bedroom 1 * Sofa-cum-bed * Niche wardrobe * Mirror on wardrobe shutter Master Bedroom * Niche wardrobe * Queen-size bed * Study unit * Dresser with mirror Store Room * Tall storage unit Additional Scope * False ceiling in living room and master bedroom * Painting work * Electrical work Note * The actual site layout and photographs differ from the provided floor plan. * Final planning and detailing will be subject to site verification and floor plan confirmation. | 2026-06-18 19:07:15 +0530 | Hemant Sonar | DCM: Possession: September 2026 Living Area * 3-seater sofa * TV unit * 4-seater dining table * Shoe unit * Safety door * Crockery unit * Balcony to be integrated and used as an extension of the living room Kitchen * Semi-modular kitchen * Pantry unit Bedroom 1 * Sofa-cum-bed * Niche wardrobe * Mirror on wardrobe shutter Master Bedroom * Niche wardrobe * Queen-size bed * Study unit * Dresser with mirror Store Room * Tall storage unit Additional Scope * False ceiling in living room & master bedroom * Painting * Electrical work NOTE - floor plan is not cleared actual floor plan & site photos are diffrent | 2026-06-29 |  | 2026-07-06
20489 | Sub Project |  | vivek | JP Barcelona | MUM - Thane |  | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | Akash Jadhav | Rizwan Mistry | Murali S |  |  | Active | Production | Dispatch Due | 207685 | 0 | 0 | 0 | 207685 | 23 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-10 | 2026-06-13 14:08 | 2026-06-11 | 2026-06-13 14:08 | 2026-06-13 | 2026-06-13 14:08 | 2026-06-14 | 2026-06-13 14:09 | 2026-06-14 | 2026-06-13 14:10 | 2026-06-14 | 2026-06-13 14:12 | 2026-06-13 | 2026-06-13 14:08 | 2026-06-14 | 2026-06-13 14:08 | 2026-06-13 | 2026-06-13 14:08 | 2026-06-14 | 2026-06-13 14:09 |  |  |  |  | 2026-06-13 | 2026-06-13 14:09 | 2026-06-14 | 2026-06-13 14:11 | 2026-06-14 | 2026-06-13 14:11 |  |  | 2026-06-14 | 2026-06-13 14:13 | 2026-06-14 | 2026-06-13 14:45 | 2026-06-14 | 2026-06-17 11:11 | 2026-06-18 | 2026-06-17 15:50 |  |  |  |  | 2026-06-17 16:16 | 2026-06-19 | 2026-06-18 19:52 | 2026-06-24 | 2026-06-22 11:19 | 2026-07-14 | 2026-06-17 15:51 | 2026-06-22 |  | 2026-07-02 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-06-13 | 2026-06-13 15:34 | 2026-06-14 | 2026-06-13 14:09 | Unknown | 2026-06-10 | 2026-06-13 14:08 | 0 | 0 | 0 | 0 | 177124 | 30561 | 177124 | 30561 | [9 empty] | 2026-06-14 | 2026-06-13 14:09 | 2026-06-14 | 2026-06-13 14:11
20490 | Turnkey | 2026-06-01 | Sandhya Krishnan | L&THe boulevard | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Preproduction | DEM2 | 2498057 | 499614 | 3194809 | 0 | 0 | 20 | 0 | 0 | 0 | 1045410 | 953032.8 |  |  | 2026-06-10 | 2026-06-10 14:26 | 2026-06-10 | 2026-06-12 13:09 | 2026-06-15 | 2026-06-15 14:31 | 2026-06-25 | 2026-06-25 12:51 | 2026-07-01 |  | 2026-07-19 |  | 2026-06-15 | 2026-06-15 14:51 | 2026-06-16 | 2026-06-16 20:30 | 2026-06-16 | 2026-06-19 12:31 | 2026-06-19 | 2026-06-19 18:50 |  |  |  |  | 2026-06-25 | 2026-06-25 18:21 | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-06-20 | 2026-06-21 13:41 | Site is RTMI | 2026-06-10 | 2026-06-10 14:25 | 2707465 | 487343 | 0 | 0 | 0 | 0 | 2663192.8316 | 449650 | 2026-06-25 19:54:40 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-25 18:56:44 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-25 18:07:15 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-26 | 2026-06-25 13:03 | 2026-07-02 |  | RTMI |  | 2026-06-14 | 318999 | Ravi Roy
20491 | Turnkey | 2026-06-01 | Ravindra Kumar Sharma | gee cee emrald | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Anant Giri |  | Hold | Preproduction | Site Readiness 1 | 2200997 | 440199 | 2965396 | 0 | 0 | 10 | 7 | 0 | 0 | 932779 | 828018.8 |  |  | 2026-06-10 | 2026-06-10 17:35 | 2026-06-14 | 2026-06-14 19:16 | 2026-06-14 | 2026-06-14 21:15 | 2026-07-06 | 2026-06-28 19:31 | 2027-01-04 |  | 2027-01-11 |  | 2026-06-14 | 2026-06-14 21:36 | 2026-06-15 | 2026-06-16 11:08 | 2026-06-16 | 2026-06-17 11:08 | 2026-06-17 | 2026-06-17 16:49 |  |  |  |  | 2026-07-07 | 2026-06-25 12:44 | 2027-01-06 |  | 2027-01-07 |  |  |  | 2027-01-14 |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 | [6 empty] | 2027-02-09 |  | 2027-03-06 |  | 2027-03-05 |  | 2027-03-06 |  | 2027-03-06 |  | 2027-03-11 |  |  |  | 2027-04-19 |  | 2027-04-20 |  | 2027-04-21 | [5 empty] | 2027-01-15 |  | 2026-07-02 | 2026-06-28 19:02 | Site is RTMI | 2026-06-10 | 2026-06-10 17:31 | 2513048 | 452348 | 0 | 0 | 0 | 0 | 2478418.171 | 409229 | 2026-07-08 15:33:41 +0530 | Anil Jagtap | Possession - Dec*26 | 2026-07-07 16:50:18 +0530 | Rachna Abhyankar | Project will be on HOLD till Dec 2026 , due to delay in possession | 2026-06-28 19:03:36 +0530 | Siddhi Chaphekar | Some Image was uploaded | 2026-06-29 | 2026-06-28 19:35 | 2027-01-05 |  | Under Construction | 2026-12-31 | 2026-06-14 | 306999 | Ravi Roy
20492 | Turnkey | 2026-06-01 | Ritesh Khandelwal | Anmol tower | MUM - GOR | Yes | [8 empty] | Saloni Sagwekar |  | Active | Prospect | 10% Payment | 1969937 | 9999 | 1969937 | 0 | 0 | 29 | 0 | 186995 | 196994 | 823082 | 752868 |  |  | 2026-06-10 | 2026-06-12 15:17 | 2026-06-10 | 2026-06-12 15:47 | 2026-06-16 | 2026-06-16 14:27 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-06-16 |  | 2026-06-17 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | 2026-06-24 |  | 2026-07-02 |  | 2026-07-03 |  |  |  | 2026-07-10 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-06-19 |  | Unknown | 2026-06-10 | 2026-06-10 17:22 | 1673822 | 296115 | 0 | 0 | 0 | 0 | 1673822 | 296115 | 2026-07-03 16:56:31 +0530 | Meet Shah | Others: | 2026-06-16 14:54:24 +0530 | Rishika Malviya | CDP: 20492 - Celebrity Design Presentation (CDP) with the customer-20260612_113334UTC-Meeting Recording.mp4 | 2026-06-16 14:54:09 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-24 |  | 2026-07-01
20499 | Turnkey | 2026-06-01 | Sankhadeep Banerjee Sankhadeep banerjee | Eden Park Prestige | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | DCM Due | 58723 | 9999 | 0 | 0 | 0 | 28 | 0 | 0 | 1746 | 23489 | 23489.2 |  |  | 2026-06-11 | 2026-06-17 12:00 | 2026-06-12 |  | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-07-20 |  | 2026-06-19 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-06-26 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-21 |  | Unknown | 2026-06-11 | 2026-06-12 18:56 | 0 | 0 | 0 | 0 | 0 | 0 | 49766 | 8957 | 2026-06-12 13:12:51 +0530 | Ramesh Nayak | ::::::::---------------RGM Notes for DCM Meeting---------------:::::::: 1.10-12L 2. Property Name & Possession - Eden Park @ The Prestige City & July-2026 3. Carpet Area - 889 4. BHK - 2 BHK 5. Family Size - 2 Husband & Wife in IT Service Husband is from Asansol (WB) & Wife from Mumbai now posted in US. | [6 empty] | 2026-06-26 |  | 2026-07-03
20504 | Turnkey | 2026-06-01 | Jisha Vikas | Adarsh Palm Acres | MUM - Thane | Yes | Harshali Bhuyar | Anamika Dolai | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Prospect | Onboarding Due | 1107927 | 148457 | 1480458 | 0 | 0 | 30 | 0 | 0 | 73128 | 503783 | 382558.8 |  |  | 2026-06-12 | 2026-06-13 11:03 | 2026-06-12 | 2026-06-13 20:57 | 2026-06-16 | 2026-06-14 11:02 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 | 2026-06-15 11:19 | 2026-06-15 | 2026-06-15 12:25 | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-06-12 | 2026-06-12 17:25 | 1254625 | 225832 | 0 | 0 | 0 | 0 | 1237320.1052 | 207976 | 2026-06-18 11:12:48 +0530 | Athul Ajaykumar | OB Initiated: Had a conversation with the client over a call. The client stated that he does not wish to proceed with Bonito and would like a refund. He also mentioned that he has already sent an email to the sales team regarding the same. | 2026-06-18 11:05:40 +0530 | Athul Ajaykumar |  | 2026-06-17 17:05:57 +0530 | Athul Ajaykumar |  | 2026-06-22 |  | 2026-06-29 |  |  |  | 2026-06-13 | 148457 | Ravi Roy
20505 | Sub Project |  | Nilesh Shivaji Chalke | Shivkrupa | MUM - GOR |  | Swapnali Shedekar | Manzoor Shaikh | Safalta Karkera | [7 empty] | Active | Preproduction | 3D Sign off | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-12 | 2026-06-12 17:50 | 2026-06-13 | 2026-06-12 17:50 | 2026-06-12 | 2026-06-12 17:51 | 2026-06-13 | 2026-06-12 17:51 | 2026-06-13 | 2026-06-12 17:53 | 2026-06-13 | 2026-06-12 17:55 | 2026-06-12 | 2026-06-12 17:51 | 2026-06-13 | 2026-06-12 17:51 | 2026-06-12 | 2026-06-12 17:51 | 2026-06-13 | 2026-06-12 17:51 |  |  |  |  | 2026-06-12 | 2026-06-12 17:52 | 2026-06-13 | 2026-06-12 17:54 | 2026-06-13 | 2026-06-12 17:54 |  |  | 2026-06-13 | 2026-06-30 20:29 | 2026-06-30 | 2026-06-30 22:30 | 2026-07-01 |  | 2026-07-02 | [6 empty] | 2026-07-20 |  | 2026-07-29 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-08-01 |  |  |  | 2026-08-23 |  | 2026-08-25 |  | 2026-08-26 | [5 empty] | 2026-06-30 |  | 2026-06-13 | 2026-06-12 17:51 | Unknown | 2026-06-12 | 2026-06-12 17:50 | 0 | 0 | 0 | 0 | 30817.8 | 0 | 30817.8 | 0 | [9 empty] | 2026-06-13 | 2026-06-12 17:52 | 2026-06-13 | 2026-06-12 17:53
20506 | Turnkey | 2026-06-01 | Karthikeyan | Abhee Celestial City | BNG - HSR | Yes | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | 10% Payment | 2016752 | 9999 | 0 | 0 | 0 | 22 | 0 | 191676 | 201675 | 839878 | 773523.2 |  |  | 2026-06-12 | 2026-06-12 15:57 | 2026-06-13 | 2026-06-16 12:47 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-06-12 | 2026-06-12 15:54 | 0 | 0 | 0 | 0 | 0 | 0 | 1709112 | 307640 | 2026-06-23 12:40:25 +0530 | Saranya Thiyagarajan | CDP: 1. Builder-need to check for shoe rack 2.Tv unit- base cabinets - shutter 3. Dining- crockery as per demo flat 4.balcony door change in MBR 5. change to pre-lam for common areas and room- except kitchen | 2026-06-23 12:40:06 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-16 15:25:40 +0530 | Saranya Thiyagarajan | Some Image was uploaded | 2026-06-27 |  | 2026-07-04
20509 | Turnkey | 2026-06-01 | tina chandroji | sunsumit Jevan mangal | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 1694319 | 9999 | 1694319 | 0 | 0 | 29 | 0 | 159433 | 169432 | 746100 | 609355.2 |  |  | 2026-06-12 | 2026-06-16 11:41 | 2026-06-16 | 2026-06-16 11:58 | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-06-28 |  | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-23 |  | Unknown | 2026-06-12 | 2026-06-12 17:32 | 1439407 | 254911 | 0 | 0 | 0 | 0 | 1439407 | 254911 | 2026-06-21 19:13:34 +0530 | Sakshi Hire | CDP: INternal of the wardrobe finalised need to update those need to update bedroom designs as per reference images cx will come for Recdp | 2026-06-21 19:12:33 +0530 | Sakshi Hire | Some Image was uploaded | 2026-06-19 11:17:08 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-06-28 |  | 2026-07-05
20510 | Sub Project |  | BINAL SHAH | hemratan | MUM - GOR |  | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  |  | Uday Yadruk | Rizwan Mistry | Murali S |  |  | Active | Production | Dispatch Due | -700 | 0 | 0 | 0 | -700 | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-12 | 2026-06-19 14:44 | 2026-06-13 | 2026-06-19 14:44 | 2026-06-19 | 2026-06-19 14:44 | 2026-06-20 | 2026-06-19 14:45 | 2026-06-20 | 2026-06-19 14:46 | 2026-06-20 | 2026-06-19 14:48 | 2026-06-19 | 2026-06-19 14:44 | 2026-06-20 | 2026-06-19 14:44 | 2026-06-19 | 2026-06-19 14:44 | 2026-06-20 | 2026-06-19 14:44 |  |  |  |  | 2026-06-19 | 2026-06-19 14:45 | 2026-06-20 | 2026-06-19 14:47 | 2026-06-20 | 2026-06-19 14:47 |  |  | 2026-06-20 | 2026-06-19 14:49 | 2026-06-20 | 2026-06-24 18:49 | 2026-06-25 | 2026-06-25 10:13 | 2026-06-26 | 2026-06-25 10:14 |  |  |  |  | 2026-06-25 12:44 | 2026-06-28 | 2026-06-27 21:26 | 2026-07-01 | 2026-06-29 10:00 | 2026-06-30 | 2026-07-08 13:09 | 2026-06-29 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-06-24 | 2026-06-24 21:13 | 2026-06-20 | 2026-06-19 14:44 | Unknown | 2026-06-12 | 2026-06-19 14:43 | 0 | 0 | 0 | 0 | 12118 | 2181 | 12118 | 2181 | 2026-06-24 15:42:31 +0530 | Avinash Jaiswal | Added offer of Rs. 15k to cover for hob charges. This is a lost customer and we have ordered hob which will be deducted from amount paid and store credit | [6 empty] | 2026-06-20 | 2026-06-19 14:45 | 2026-06-20 | 2026-06-19 14:46
20513 | Sub Project |  | preeti Gupta | nandanvan | MUM - GOR | Yes | Preeti Agarwal | Reshma Melanta | Shantanu Parakh | [7 empty] | Active | Preproduction | Hoto | 91988 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 55193 | 36795.2 |  |  | 2026-06-12 | 2026-07-04 17:31 | 2026-06-13 | 2026-07-04 17:31 | 2026-07-04 | 2026-07-04 17:31 | 2026-07-05 | 2026-07-04 17:33 | 2026-07-05 | 2026-07-04 17:37 | 2026-07-05 | 2026-07-04 17:39 | 2026-07-04 | 2026-07-04 17:32 | 2026-07-05 | 2026-07-04 17:32 | 2026-07-04 | 2026-07-04 17:32 | 2026-07-05 | 2026-07-04 17:32 |  |  |  |  | 2026-07-04 | 2026-07-04 17:33 | 2026-07-05 | 2026-07-04 17:38 | 2026-07-05 | 2026-07-04 17:38 |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-07-05 | 2026-07-04 17:32 | Unknown | 2026-06-12 | 2026-07-04 17:31 | 0 | 0 | 0 | 0 | 0 | 0 | 77956 | 14032 | [9 empty] | 2026-07-05 | 2026-07-04 17:33 | 2026-07-05 | 2026-07-04 17:37
20514 | Turnkey | 2026-06-01 | Hemant Thakker | Devhans Mahesh Krupa | MUM - Thane | Yes | [8 empty] | Aryan Singh |  | Active | Prospect | Onboarding Due | 2985728 | 309999 | 4035826 | 0 | 0 | 1 | 0 | 0 | 287147 | 1306028 | 1082554.8 |  |  | 2026-06-12 | 2026-07-09 12:46 | 2026-07-15 | 2026-07-10 21:18 | 2026-07-13 | 2026-07-10 21:26 | 2026-07-20 |  | 2026-07-27 |  | 2026-08-03 |  | 2026-07-10 | 2026-07-11 16:48 | 2026-07-11 | 2026-07-14 16:49 | 2026-07-14 |  | 2026-07-15 | [5 empty] | 2026-07-21 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-07-16 |  | Unknown | 2026-06-12 | 2026-07-07 19:04 | 3420191 | 615634 | 0 | 0 | 0 | 0 | 3358959.9438 | 589611 | 2026-07-14 17:22:46 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-12 16:35:08 +0530 | Aryan Singh |  | 2026-07-09 12:43:55 +0530 | Aryan Singh |  | 2026-07-21 |  | 2026-07-28
20516 | Turnkey | 2026-06-01 | Faizan Shaikh | Skyline | MUM - GOR | Yes | [8 empty] | Shoaib Shaikh |  | Active | Prospect | 10% Payment | 1073948 | 9999 | 1482307 | 0 | 0 | 15 | 0 | 97396 | 107395 | 476730 | 382428 |  |  | 2026-06-12 | 2026-06-30 18:40 | 2026-06-30 | 2026-06-30 18:57 | 2026-07-03 | 2026-07-01 11:14 | 2026-07-08 |  | 2026-07-15 |  | 2026-07-22 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-07-09 |  | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-07-04 |  | Unknown | 2026-06-12 | 2026-06-12 19:12 | 1256193 | 226114 | 0 | 0 | 0 | 0 | 1256192.693 | 201860 | 2026-06-30 18:57:00 +0530 | Sakshi Hire | CDP: Spot CDP 2 BHK reno property 2 tolilet & 3 balcony extention was planned in civil workin living room created sofa placement & namaz conerkitchen is whole modular1 bedroom is kids bedroommbr dedicated for couplecx has promised civil work will be done by bonito at the time of grossincluding civil cx budget was 10 lac which is not possible as per requirements | 2026-06-30 18:51:29 +0530 | Sakshi Hire | Some Image was uploaded | 2026-06-30 18:38:11 +0530 | Sakshi Hire | CDP: Recap: 20516 - Celebrity Design Presentation (CDP) with the customer 23 June ¦ Meeting ¦ Microsoft Teams | 2026-07-09 |  | 2026-07-16
20517 | Turnkey | 2026-06-01 | Arjun Bhatt | Park West Tower 8 (Cedar) | BNG - HRBR | Yes | Asmitha Saif | Parasa Sri | Shibin Lal | [5 empty] | Kushal S |  | Active | Design | DEM1 | 1964105 | 392999 | 2490582 | 0 | 0 | 11 | 0 | 0 | 0 | 818973 | 752132.8 |  |  | 2026-06-12 | 2026-06-19 12:22 | 2026-06-16 | 2026-06-19 12:24 | 2026-06-22 | 2026-06-19 12:47 | 2026-07-20 |  | 2026-07-27 |  | 2026-08-03 |  | 2026-06-19 | 2026-06-19 18:21 | 2026-06-20 | 2026-06-21 10:40 | 2026-06-21 | 2026-07-04 12:02 | 2026-07-08 | 2026-07-08 11:56 |  |  |  |  | 2026-07-21 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-19 |  | 2026-09-18 |  | 2026-09-19 |  | 2026-09-19 |  | 2026-09-21 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-28 | [5 empty] | 2026-08-07 |  | 2026-07-09 |  | Unknown | 2026-06-12 | 2026-06-15 15:04 | 2110663 | 379919 | 0 | 0 | 0 | 0 | 2031279.125 | 353538 | 2026-07-12 15:29:06 +0530 | Parasa Sri | Client needs some clarification | 2026-07-04 12:00:34 +0530 | Sanjana Swami | OB accept | 2026-07-04 11:10:06 +0530 | Kushal S | Price protection Approval | 2026-07-21 |  | 2026-07-28 |  | Under Construction | 2026-12-15 | 2026-06-18 | 206411 | Ravi Roy
20518 | Turnkey | 2026-06-01 | Shanthi | Purva Atmoshphere | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 1582507 | 9999 | 0 | 0 | 0 | 22 | 0 | 148252 | 158251 | 633003 | 633002.8 |  |  | 2026-06-12 | 2026-06-23 12:22 | 2026-06-14 |  | 2026-06-14 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-06-14 |  | 2026-06-15 |  | 2026-06-15 |  | 2026-06-16 | [5 empty] | 2026-06-22 |  | 2026-06-30 |  | 2026-07-01 |  |  |  | 2026-07-08 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-11 | [6 empty] | 2026-07-29 |  | 2026-08-07 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-10 |  |  |  | 2026-09-01 |  | 2026-09-03 |  | 2026-09-04 | [5 empty] | 2026-07-09 |  | 2026-06-17 |  | Unknown | 2026-06-12 | 2026-06-13 17:40 | 0 | 0 | 0 | 0 | 0 | 0 | 1341108 | 241399 | [9 empty] | 2026-06-22 |  | 2026-06-29
20522 | Sub Project |  | Tejas Galani | humlog chs | MUM - GOR |  | Anjali Jain | Reshma Melanta | Kashmira Nerurkar |  |  | Savita Parab | Rizwan Mistry | Murali S |  |  | Active | Production | 100% Payment | 39870 | 39871 | 0 | 0 | 57870 | 16 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-13 | 2026-06-19 11:26 | 2026-06-14 | 2026-06-19 11:26 | 2026-06-19 | 2026-06-19 11:26 | 2026-06-20 | 2026-06-19 11:27 | 2026-06-20 | 2026-06-19 11:28 | 2026-06-20 | 2026-06-19 11:30 | 2026-06-19 | 2026-06-19 11:26 | 2026-06-20 | 2026-06-19 11:26 | 2026-06-19 | 2026-06-19 11:26 | 2026-06-20 | 2026-06-19 11:26 |  |  |  |  | 2026-06-19 | 2026-06-19 11:27 | 2026-06-20 | 2026-06-19 11:29 | 2026-06-20 | 2026-06-19 11:29 |  |  | 2026-06-20 | 2026-06-23 15:48 | 2026-06-23 | 2026-06-23 17:36 | 2026-06-24 | 2026-06-24 15:11 | 2026-06-25 | 2026-06-24 15:13 |  |  |  |  | 2026-06-24 17:05 | 2026-06-28 | 2026-06-27 21:26 | 2026-07-01 | 2026-06-29 09:59 | 2026-06-30 |  | 2026-06-29 |  | 2026-07-11 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-06-23 | 2026-06-23 23:27 | 2026-06-20 | 2026-06-19 11:26 | Unknown | 2026-06-13 | 2026-06-19 11:26 | 0 | 0 | 0 | 0 | 49042 | 8827 | 49042 | 8827 | 2026-06-23 19:47:49 +0530 | Reshma Melanta | Some Image was uploaded | [6 empty] | 2026-06-20 | 2026-06-19 11:27 | 2026-06-20 | 2026-06-19 11:28
20523 | Turnkey | 2026-06-01 | CHANDANBALA PANKAJ KOTADIA | blue star | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 5933076 | 9999 | 0 | 0 | 0 | 22 | 0 | 583309 | 593308 | 2533049 | 2213411.6 |  |  | 2026-06-07 | 2026-06-23 11:55 | 2026-06-23 | 2026-06-23 11:56 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-07 | 2026-06-23 09:34 | 0 | 0 | 0 | 0 | 0 | 0 | 5028030 | 905045 | 2026-06-30 17:41:58 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-06-23 23:30:28 +0530 | Pratima Kajwe | CDP: MOM Kitchen Appliances - 45k Piano sink - 13000 Civil - 13L AC - 2L Light fittings - 1.2L Sanitary fittings - 35k Mattress - 80K Electronic Gadgets - 2L Loose furnitures - 4L Curtains - | 2026-06-23 06:21:18 +0530 | Pratima Kajwe | DCM: MOM Katodia and Family 3+3 BHKÂ 4 members in familyÂ Right side kitchen to be turned in study roomÂ Automation in house 1105 square.ft Living roomÂ Two options of layoutÂ By keeping existing balcony and taking it inside living roomÂ Occupy lift space for foyer section to beautify 6 seater dining tableÂ KitchenÂ Big fridge with monitor tech in kitchenÂ Semi modular kitchenÂ Chakki, grinder, air fryer, OTG and microwave, Toaster, bread machine, matka provision, food processor, hand blender, beaterÂ Master bedroom Walk in closet in both roomsÂ Study table in one roomÂ Provision for TVÂ Northeast corner marble mandir.Â Study roomÂ Proper office roomÂ Study table sofa seating withÂ Printer and monitor provision Additional door provision from staircase to access study area ACÂ VRV systemÂ BudgetÂ 45L | 2026-07-01 |  | 2026-07-08
20524 | Turnkey | 2026-06-01 | Piyush bhanusali | Bhumi Icon | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 1845085 | 9999 | 0 | 0 | 0 | 28 | 0 | 174510 | 184509 | 818011 | 658057.2 |  |  | 2026-06-13 | 2026-06-13 20:01 | 2026-06-13 | 2026-06-17 12:10 | 2026-06-17 |  | 2026-06-24 |  | 2026-07-01 |  | 2026-07-08 |  | 2026-06-17 |  | 2026-06-18 |  | 2026-06-18 |  | 2026-06-19 | [5 empty] | 2026-06-25 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-20 |  | Unknown | 2026-06-13 | 2026-06-13 20:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1565939 | 279145 | 2026-06-19 13:11:40 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-06-17 18:17:01 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-17 18:01:42 +0530 | Moksh Mehta | DCM LINK:- Recap: 20547 - Design Consultation Meeting (DCM) with the customer 13 June ¦ Meeting ¦ Microsoft Teams CDP LINK:- Recap: 20524 - Celebrity Design Presentation (CDP) with the customer 17 June ¦ Meeting ¦ Microsoft Teams | 2026-06-25 |  | 2026-07-02
20525 | Turnkey | 2026-06-01 | Jancy Jeba | Lodha devino | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | DCM Due | 1491340 | 9999 | 0 | 0 | 0 | 4 | 0 | 139135 | 149134 | 654726 | 538345.6 |  |  | 2026-05-30 | 2026-07-11 12:00 | 2026-06-18 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-07-19 |  | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-14 |  | Unknown | 2026-05-30 | 2026-06-18 18:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1263847 | 227492 | 2026-06-18 13:30:41 +0530 | Khushi Khandelwal | DCM: 820 sqft 5 Members Posession- Oct'26 LIVING ROOMÂ Sofa+ 3 seater dining tableÂ TV unitÂ 3 seater sofa + arm chairsÂ Storage unitÂ crockery unit next to diningÂ space between the bedroom and washroom- add pic of jesus and add storage below the painting. KITCHENÂ Base cabinetÂ Wall cabinetÂ Appliances- Microwave, Chimney,Mixer, juicer, Batter maker, Ref.Â Utility- washing machine and dishwasherÂ MASTER BEDROOM WardrobeÂ Bed-Queen sizeÂ Dresser unitÂ Side tablesÂ WorkstationÂ Color theme- Beiges brownsÂ DAUGHTER'S BEDROOMÂ WardrobeÂ Queen size bed Study unit Dresser cum side tableÂ Color theme- Lavender, Purple | 2026-06-13 12:49:04 +0530 | Unknown | About the Customer **Delayed Project Timeline** Customer's property possession is expected in October-November, with interior design planning to commence after possession. They will decide in 3-4 months. **Customer Abroad and Travel Plans** Customer is currently abroad and traveling on Sunday. Contact number provided belongs to his wife; requests coordination via her number. **Pending Visit Confirmation** Customer agreed to check with his wife regarding an experience center visit and confirm later in the evening. **Experience Center Visit Offer Declined** Agent offered a visit to the Andheri experience center with a GST waiver offer. Customer expressed difficulty visiting tomorrow due to flight preparations. **Follow-up Action** Agent will share details via WhatsApp and book a family slot once confirmed. |  |  |  | 2026-07-19 |  | 2026-07-26
20527 | Turnkey | 2026-06-01 | Ethesham Ansari | Lodha Casa Supremo | MUM - GOR | Yes | Saif Shaikh | Christopher Macwan | Shantanu Parakh | [5 empty] | Avi Thakkar |  | Active | Preproduction | DEM2 | 852335 | 170467 | 1186503 | 0 | 0 | 1 | 0 | 0 | 0 | 368586 | 313281.6 |  |  | 2026-06-13 | 2026-07-04 18:54 | 2026-06-27 | 2026-07-04 18:54 | 2026-07-07 | 2026-07-04 18:58 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-07-04 | 2026-07-04 18:30 | 2026-07-05 | 2026-07-05 15:12 | 2026-07-05 | 2026-07-06 13:06 | 2026-07-10 | 2026-07-10 18:16 |  |  |  |  | 2026-07-16 | 2026-07-12 16:04 | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-11 | 2026-07-14 19:10 | Site is RTMI | 2026-06-13 | 2026-06-27 15:16 | 1005511 | 180992 | 0 | 0 | 0 | 0 | 1005511.2482 | 161970 | 2026-07-10 18:31:15 +0530 | Christopher Macwan | Others: Welcome call done. Initial measurement not done as would receive possession by Mid July DEM Dates -Â DEM 1 â€“ tentatively 12th July as customer is not available next weekend. DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - 15th July 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-07 14:24:04 +0530 | Hamza Choudhary | CDP: 04/07/2026 AC already installed Living room Require more storage below tv unit or crockery unit partition, dining table & safety door outscope Bedroom1 Bunk bed out scope Bathrooms vanity & partition outscope | 2026-07-07 14:15:36 +0530 | Hamza Choudhary | CDP RECORDING | 2026-07-15 |  | 2026-07-22 |  | Under Construction | 2026-07-15
20529 | Turnkey | 2026-06-01 | Shailesh Patekar | Vaikunth Cluster 3 (Vidya) | MUM - Thane | Yes | Siddhi Chaphekar | Anil Jagtap | Rachna Abhyankar | [5 empty] | Nishtha Valawalkar |  | Active | Preproduction | Site Readiness 1 | 885852 | 208741 | 1043712 | 0 | 0 | 8 | 0 | 0 | 0 | 375394 | 301717.2 |  |  | 2026-06-13 | 2026-06-13 20:14 | 2026-06-17 | 2026-06-17 12:00 | 2026-06-27 | 2026-06-27 15:25 | 2026-07-06 | 2026-07-05 19:24 | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 | 2026-06-27 15:28 | 2026-06-28 | 2026-06-28 10:56 | 2026-06-28 | 2026-06-30 12:27 | 2026-07-04 | 2026-07-04 11:21 |  |  |  |  | 2026-07-05 | 2026-07-07 11:39 | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-08-28 |  | 2026-08-29 | [6 empty] | 2026-09-16 |  | 2026-09-25 |  | 2026-09-24 |  | 2026-09-25 |  | 2026-09-26 |  | 2026-09-28 |  |  |  | 2026-10-20 |  | 2026-10-22 |  | 2026-10-23 | [5 empty] | 2026-07-22 |  | 2026-07-05 | 2026-07-05 19:20 | Site is Non-RTMI | 2026-06-13 | 2026-06-13 20:13 | 886997 | 156715 | 0 | 0 | 0 | 0 | 886997.1692 | 151430 | 2026-07-12 13:33:33 +0530 | Siddhi Chaphekar | Please find the attached MOM of DEM 1 done on 11th July'26, Livingroom- Tv unit and sofa wall design will be same as as earlier discussion. Beside mandir unit u-shape wall beading will be added (paint work insiide cx-scope) Shoe unit will be movable Safety door is not in the scope Flushed door will be in paint finish with groove continue on the wall Kitchen- As per site condition aqua-guard provision will be under the sink inlet provision to be made (cx scope) if not then the microwave unit will be planned i the l corner of the platform below wall unit and above washing machine aqua guard unit will be planned. Rest will remain same. Position of the foldable chopping board will is on the opposite wall of the platform. Master bedroom- Bed back wall design will be same as earlier. Used clothes unit will be front door aligned with wardrobe and study table will be extended till wardrobe also the above units. desk will be kept foldable only. As discussed we will do material selection meeting after the initial measurements done on site. Kindly go through ,let me know if i have missed anything. Thankyou. | 2026-07-12 13:33:12 +0530 | Siddhi Chaphekar |  | 2026-07-07 16:49:33 +0530 | Rachna Abhyankar | IM will be aligned post 20th july , as they will be receiving possesion | 2026-07-06 | 2026-07-05 22:27 | 2026-07-12 |  | Under Construction | 2026-07-31 | 2026-06-27 | 208741 | Ravi Roy
20530 | Turnkey | 2026-06-01 | Pradita Sarkar Bose | Exotica | MUM - Thane | Yes | Hemant Sonar |  | Rushika More | [5 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 2139954 | 9999 | 0 | 0 | 0 | 27 | 0 | 203996 | 213995 | 889340 | 822623.6 |  |  | 2026-06-13 | 2026-06-16 11:54 | 2026-06-13 | 2026-06-16 13:33 | 2026-06-18 |  | 2026-06-25 |  | 2026-07-02 |  | 2026-07-09 |  | 2026-06-18 |  | 2026-06-19 |  | 2026-06-19 |  | 2026-06-20 | [5 empty] | 2026-06-26 |  | 2026-07-04 |  | 2026-07-05 |  |  |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 | [6 empty] | 2026-08-02 |  | 2026-08-11 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-14 |  |  |  | 2026-09-05 |  | 2026-09-07 |  | 2026-09-08 | [5 empty] | 2026-07-13 |  | 2026-06-21 |  | Unknown | 2026-06-13 | 2026-06-16 11:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1813520 | 326433 | 2026-06-13 19:28:20 +0530 | Hemant Sonar | Some Image was uploaded | 2026-06-13 18:31:40 +0530 | Hemant Sonar | DCM: Design Consultation Notes (DCM) Property: Lodha Palava Status: Possession in hand Theme: Indian Traditional (aligned with existing furniture) Budget: 1316 Lakhs Family Details * Family of 3 Â Â * Husband & Wife (Both in HR profession) Â Â * Daughter 13 years Foyer Area * Existing shoe unit to be retained * Safety door with traditional design to be provided Living Area * 3-seater sofa suggested with red fabric finish * 3-inch raised platform to be created in living area * TV unit with decorative LED ledges * Final TV unit position to be finalized during design meeting * Existing 4-seater dining table to be retained * False ceiling to be done only in living & passage area Living Balcony * Sink provision to be finalized as per site condition * Vanity unit below sink to be added Temple Area * Wooden theme mandir * Storage to be included * Wallpaper backdrop suggested Carpentry Scope Theatre Room (Converted to Guest Bedroom) * Glass partition already provided by builder * To be converted into guest bedroom * All existing furniture to be reused: Â Â * Sofa-cum-bed Â Â * Wardrobe Â Â * Study unit * Only wall dcor elements to be designed Kitchen & Utility * Fully modular kitchen * Acrylic finish for base units * Wall units in glass finish * Quartz countertop included * Dado tile installation to be considered * Breaking work already completed * Utility area to include: Â Â * Tall unit * Store room: Â Â * Full storage planning Bedrooms Daughters Bedroom * Wardrobe with 2 glass shutters * Study unit with open ledges & book storage * New queen-size bed suggested * Duct area: Â Â * Single window seating with storage * Full-size mirror provision Master Bedroom * L-shaped full glass wardrobe with black tinted glass * Existing king-size bed to be retained * Existing TV unit to be reused * Existing dresser to be reused Â Â * Mirror size to be checked and finalized on site Washrooms * Both washrooms to include: Â Â * Vanity units with mirror Additional Scope * Replacement of all laminates for existing doors * Full house painting * Electrical work as per design requirements * Full house tile work is included in (cx scope) , as discussed in the meeting Â Â * Including all washroom wall and floor tiles Remarks * Design to respect Indian traditional aesthetics while integrating modern functionality | 2026-06-13 14:35:40 +0530 | Unknown | About the Customer **2 BHK Dombivli Property - Possession Received** Customer requires interior design for a 2 BHK resale property in Dombivli, possession received and property is vacant. **Budget Confirmed at 8-10 Lakhs** Customer's budget is 8-10 lakhs, with initial discussion around 7-8 lakhs. **Location Serviceability Confirmed** Agent confirmed serviceability for Dombivli and Exotica property, addressing customer's concern. **Thane Experience Center Visit Scheduled** Experience center visit to Thane scheduled for Saturday, 11:00-11:30 AM, with 2-3 family members attending. **Follow-up: WhatsApp Invite & Reminder Call** Agent to send WhatsApp invite and provide a reminder call on Friday. | 2026-06-26 |  | 2026-07-03
20531 | Sub Project |  | Swati Anand zalte | Ajmera | MUM - GOR |  | Riddhi Deshpande | Manzoor Shaikh | Safalta Karkera |  |  | Nishant Jadhav | Sandeep Tiwari | Murali S |  | Siddhesh Gujrathi | Active | Production | Dispatch Due | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-13 | 2026-06-24 17:24 | 2026-06-14 | 2026-06-24 17:24 | 2026-06-24 | 2026-06-24 17:24 | 2026-06-25 | 2026-06-24 17:25 | 2026-06-25 | 2026-06-24 17:26 | 2026-06-25 | 2026-06-24 17:28 | 2026-06-24 | 2026-06-24 17:24 | 2026-06-25 | 2026-06-24 17:24 | 2026-06-24 | 2026-06-24 17:24 | 2026-06-25 | 2026-06-24 17:24 |  |  |  |  | 2026-06-24 | 2026-06-24 17:25 | 2026-06-25 | 2026-06-24 17:27 | 2026-06-25 | 2026-06-24 17:27 |  |  | 2026-06-25 | 2026-06-25 12:25 | 2026-06-26 | 2026-06-25 17:44 | 2026-06-26 | 2026-06-25 18:17 | 2026-06-26 | 2026-06-25 18:17 |  |  |  |  | 2026-06-27 15:37 | 2026-07-01 | 2026-06-30 20:10 | 2026-07-15 | 2026-07-13 17:54 | 2026-07-14 | 2026-07-14 10:02 | 2026-07-13 |  | 2026-07-14 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-25 |  | 2026-07-26 | [5 empty] | 2026-06-25 | 2026-06-26 16:11 | 2026-06-25 | 2026-06-24 17:25 | Unknown | 2026-06-13 | 2026-06-24 17:24 | 0 | 0 | 0 | 0 | 24836.71 | 0 | 24836.71 | 0 | 2026-07-02 11:14:52 +0530 | Nishant Jadhav | Execution: Modular installation start on 29 June 2026 smart door lock received Automation light & curtain pending final handover date will be 27 July 2026 | [6 empty] | 2026-06-25 | 2026-06-24 17:25 | 2026-06-25 | 2026-06-24 17:27
20532 | Turnkey | 2026-06-01 | Venkatesh Kailasam | s | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | 10% Payment | 1103986 | 159999 | 1497806 | 0 | 0 | 6 | 0 | 0 | 60798 | 480947 | 402241.6 |  |  | 2026-06-13 | 2026-07-08 18:18 | 2026-06-30 | 2026-07-09 19:04 | 2026-07-12 | 2026-07-09 19:08 | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-07-04 | 2026-07-06 18:30 | 2026-07-10 |  | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-13 | 2026-06-13 15:03 | 1269327 | 228478 | 0 | 0 | 0 | 0 | 1255299.5677 | 207267 | 2026-07-10 17:59:31 +0530 | Raghavendra S |  | 2026-07-09 19:15:47 +0530 | Palak Thakur | CDP MOM- Pooja Mandir- CNC is been removed as the contractor will be fixing the Tiles on wall. No Granite No Dado tiles | 2026-06-26 19:26:42 +0530 | Keerthan M | DCM: 4bhk DUPLEX Independent house 1. Living Room * TV Unit * Console Table * Bay Window Seating * Top Storage / Loft Storage * False Ceiling 2. Lobby Area * Design Suggestions for Space Under the Stairs 3. Dining Room * Wash Unit * Crockery Unit * 4-Seater Dining Table * Pooja Room / Pooja Unit 4. Kitchen * Bottom Storage * Top Storage * Loft Storage 5. Guest Bedroom * Wardrobe * Dresser Unit 6. Staircase Area * Staircase Wall Detailing 7. Parents Bedroom * Bed with Wall Detailing * TV Unit * Wardrobes * Dresser Unit 8. Master Bedroom * Wardrobes * Workstation * Dresser Unit 9. Terrace Floor * Dedicated Space for PlayStation * Storage Unit * Loft Storage | 2026-07-17 |  | 2026-07-24
20533 | Turnkey | 2026-06-01 | Priya Dubey | Pavani Mirabilia | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1833763 | 251131 | 2512769 | 0 | 0 | 23 | 0 | 0 | 115622 | 733505 | 733505.2 |  |  | 2026-06-13 | 2026-06-14 10:28 | 2026-06-13 | 2026-06-17 11:12 | 2026-06-21 | 2026-06-21 18:06 | 2026-07-19 |  | 2026-10-05 |  | 2026-10-12 |  | 2026-06-21 | 2026-06-21 18:17 | 2026-06-22 | 2026-06-21 18:18 | 2026-06-21 | 2026-06-22 17:59 | 2026-06-24 | 2026-06-24 13:23 |  |  |  |  | 2026-07-20 |  | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-07-15 |  | Unknown | 2026-06-13 | 2026-06-13 15:27 | 2129465 | 383303 | 0 | 0 | 0 | 0 | 2050748.873 | 338627 | 2026-06-26 18:14:28 +0530 | Prathyusha Elangovan | Priya Dubey MOM(26/06/26) LIVING ROOM ENTRY ADJ WALL DESIGN NEEDS TO BE CHANGED NOTHING TO BE ON THE FLOOR CROCKERY UNIT-BASE DRAWER+WALL TINTED GLASS UNIT WITH 2 SHELVES KITCHEN THERE IS NO WALL FOR POOJA ROOM NEEDS 2 OPTIONS 1-COUNTERTOP EXTENDED AND STORAGE UNITS BEHIND THE POOJA UNIT, 2-CONSTRUCTION OF WALL AND HAVING THE STORE ROOMÂ GRANITE FALSE CEILING-PLAIN WITH PROFILE LIGHTS Â MASTER BEDROOM CORNER BED WITHT STUDY TABLE ON THE WINDOW/ADJ WALL NO SEPARATE DRESSER TV -FLOOR MOUNTED+PROPER STORAGE+TALL SHUTTER ON ONE SIDE MIRROR ON THE WARDROBE SHUTTER-WALKIN WARDROBE CUSTOMIZED BED-7-8FT FALSE CEILING STUDY TABLE-3*,2' POOJA UNIT BOTTOM 3 DRAWERS-2 SMALL+1 BIG 1 BIG SHELF Â BACKGROUND-NO CNC-REFERENCE NEEDS TO BE CHECKED WITH RAJASHEKAR STUDY ROOM 2 DOOR WARDROBE STUDY TABLE-4'*3' SINGLE BED-6'*4' PASSAGE AREA NICHE AREA STORAGE+AESTHETICS(REFERENCE IMAGE) NICHE PP TO BEDROOM DOOR NEEDS TO BE MINIMAL KIDS BEDROOM STUDY UNIT- 2'5"-3 DEPTH (CORNER HAS TO E CHAMPHERED )6' WITH ALL UNITS TO BE CLOSED 6'*5' PARENTS ROOM STUDY+TV UNIT +BOTTOM STORAGE(DRAWERS) HINGED WARDROBE+LOFT STUDY WALL UNIT (SLEEK STORAGE) BALCONY-JANITOR UNIT 2 TV UNITS | 2026-06-22 20:22:37 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-06-22 17:59:16 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction completion date: September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible * DEM 1 Client will be letting us know * 10% Payment Stage after 1st DEM *Client has not planned any civil work yet *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 20,50,749 Offers Discussed During the Call: Laminate Upgrade - Jun 26 Campaign Free Hob & Chimney Offer 100% GST Waiver PM fee waiver (5%) Design fee waiver (5%) Free Shoerack Offer Silver Coin 21g Final Closing Value Discussed: 18,33,764 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-20 |  | 2026-10-06 |  | Under Construction | 2026-09-30 | 2026-06-20 | 251131 | Ravi Roy
20534 | Turnkey | 2026-06-01 | Ramakanth Kandrakota | Prestige Meridian Park | BNG - HRBR | Yes | Sagarika Venkatesh | Parasa Sri | Shibin Lal | [5 empty] | Janvi Nagdeo |  | Active | Design | DEM1 | 878430 | 119999 | 1193862 | 0 | 0 | 6 | 0 | 0 | 55687 | 351372 | 351372 |  |  | 2026-06-13 | 2026-06-14 12:46 | 2026-06-17 | 2026-06-17 18:50 | 2026-06-27 | 2026-07-04 21:11 | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-07-04 | 2026-07-05 13:30 | 2026-07-05 | 2026-07-07 17:11 | 2026-07-07 | 2026-07-09 17:37 | 2026-07-11 | 2026-07-11 18:36 |  |  |  |  | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-13 | 2026-06-13 15:38 | 1011748 | 182114 | 0 | 0 | 0 | 0 | 987115.4938 | 166667 | 2026-07-12 15:30:22 +0530 | Parasa Sri | Welcome cll done . site is not ready for IM | 2026-07-09 17:35:38 +0530 | Athul Ajaykumar | Possession Status: Under construction Soft possession: end of August possession: October End Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline (10, 10, 40, 40) Plan of Action Discussed During the Call: * IM â€“ Site is not accessible * DEM 1 â€“ Tentatively scheduled for (1st or 2nd week of August) * 10% Payment Stage â€“ Tentatively scheduled for (18th July) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (2.5%) Silver Coin Offer Free Shoe Rack Offer PM fee waiver (5%) Laminate Upgrade Offer - June 26 May '26 100% GST waiver Final Closing Value Discussed: 8,78,430 Checklist terms â€“ descoping and agreement terms are cleared | 2026-07-09 14:47:29 +0530 | Janvi Nagdeo | number added also looped in mail you can call the client today. | 2026-07-17 |  | 2026-07-24 |  | Under Construction | 2026-10-31 | 2026-06-27 | 129998 | Ravi Roy
20535 | Turnkey | 2026-06-01 | MR. KIRANKUMAR REDDY CHENNAREDDY | One Luxuria | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Subhan Khan |  | Active | Design | DEM1 | 1320983 | 264197 | 1757804 | 0 | 0 | 13 | 0 | 0 | 0 | 598528 | 458257.6 |  |  | 2026-06-13 | 2026-06-14 10:54 | 2026-06-20 | 2026-06-23 11:21 | 2026-06-27 | 2026-06-28 10:58 | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-06-28 | 2026-06-28 12:27 | 2026-06-29 | 2026-06-30 16:05 | 2026-06-30 | 2026-07-02 12:34 | 2026-07-11 | 2026-07-11 14:28 |  |  |  |  | 2026-07-17 | 2026-07-11 14:42 | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-12 | 2026-07-11 20:08 | Site is Non-RTMI | 2026-06-13 | 2026-06-13 21:45 | 1491908 | 265896 | 0 | 0 | 0 | 0 | 1491907.989 | 243679 | 2026-07-11 14:27:23 +0530 | Anamika Dolai | Welcome call done : Yes Meeting Dates - na IM date : 04/07/26 DEM 1 : 11/07/2026 Possession date : December'26 10% payment aligned : yes Periskope Number added : yes Escalation Matrix added : yes Price protection for 150 days from the NET date.: Yes | 2026-07-03 17:40:29 +0530 | Swami Vadnere | tried calling but RNR | 2026-07-02 12:32:34 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession: October (tentative) Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Tentatively scheduled for (This weekend) * DEM 1â€” will update to the sales team * 10% Payment Stage â€“ Tentatively scheduled for (11th July ) * B2C - self * Civil work - As of now Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) Design fee waiver (5%) Free Shoerack Offer May'26 100% GST waiver Final Closing Value Discussed: 13,20,983 Checklist termsâ€”descoping and agreement terms are cleared | 2026-07-13 |  | 2026-07-20 |  | Under Construction | 2026-10-31 | 2026-06-27 | 185779 | Ravi Roy
20537 | Turnkey | 2026-06-01 | Kishore Motwani | L&T 360 | MUM - Thane | Yes | Harshali Bhuyar | Divya Rahangdale | Sneha Kadam | [5 empty] | Anant Giri |  | Active | Design | DEM1 | 1299952 | 181999 | 1711646 | 0 | 0 | 15 | 0 | 0 | 77991 | 573729 | 466232.8 |  |  | 2026-06-13 | 2026-06-13 21:26 | 2026-06-13 | 2026-06-23 18:19 | 2026-06-27 | 2026-06-27 22:01 | 2026-07-13 |  | 2026-07-20 |  | 2026-07-27 |  | 2026-06-27 | 2026-06-27 22:18 | 2026-06-28 | 2026-06-28 13:14 | 2026-06-28 | 2026-06-30 14:28 | 2026-07-08 | 2026-07-08 12:39 |  |  |  |  | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-07-09 |  | Unknown | 2026-06-13 | 2026-06-13 21:24 | 1450548 | 261098 | 0 | 0 | 0 | 0 | 1452967.6195 | 233991 | 2026-07-08 13:22:10 +0530 | Divya Rahangdale | Welcome call done : Meeting Dates - TBD IM date : TBD DEM 1 : TBD Possession date : August 10% payment aligned : Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-07-07 12:06:33 +0530 | Anant Giri | Amabassito Dr Rohit | 2026-06-30 19:18:05 +0530 | Rinisha Masurkar | Some Image was uploaded | 2026-07-14 |  | 2026-07-21 |  | Under Construction | 2026-07-15 | 2026-06-27 | 181999 | Ravi Roy
20538 | Turnkey | 2026-06-01 | Punnachandra s Nayak | RUNWAL MYCITY | MUM - Thane | Yes | Honey Thakkar | Anamika Dolai | Anil Kuwar | [5 empty] | Foram Joshi |  | Active | Design | DEM1 | 948382 | 199999 | 1307675 | 0 | 0 | 18 | 0 | 0 | 0 | 372550 | 375832.8 |  |  | 2026-06-13 | 2026-06-13 16:24 | 2026-06-23 | 2026-06-23 19:22 | 2026-06-26 | 2026-06-26 19:46 | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-06-26 | 2026-06-26 20:11 | 2026-06-27 | 2026-06-26 21:53 | 2026-06-26 | 2026-06-27 16:13 | 2026-07-11 | 2026-07-10 19:55 |  |  |  |  | 2026-07-16 | 2026-07-12 19:08 | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-11 | 2026-07-14 19:32 | Site is Non-RTMI | 2026-06-13 | 2026-06-13 16:23 | 1108199 | 199475 | 0 | 0 | 0 | 0 | 1057599.9948 | 179258 | 2026-07-10 19:54:08 +0530 | Anamika Dolai | Welcome call done : YES Meeting Dates - NA IM date : NA DEM 1 : NA Possession date : na 10% payment aligned : closed Periskope Number added : yes Escalation Matrix added : yes Price protection for 150 days from the NET date. yes | 2026-06-27 16:12:10 +0530 | Athul Ajaykumar |  | 2026-06-27 13:05:29 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: September/October Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Tentatively scheduled for (4th July) * 20% alredy close * B2C - Self * Civil work - yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (2.5%) Free Bed Offer Laminate Upgrade - Jun 26 Campaign 100% GST Waiver Free Shoerack Offer Final Closing Value Discussed: 9,48,382 Checklist terms descoping, agreement terms are clearedÂ Pending: The client mentioned that civil work involving wall demolition and converting one room into a master bedroom is required. As per the client, this work falls under Bonito's scope; however, it is not reflected in the quotation. | 2026-07-19 |  | 2026-07-26 |  | Under Construction | 2026-10-31 | 2026-06-26 | 199999 | Ravi Roy
20539 | Turnkey | 2026-06-01 | Kamlesh Jain | Dosti Mezzo | MUM - Thane | Yes | [8 empty] | Rahul Kumawat |  | Active | Prospect | 10% Payment | 2519851 | 9999 | 0 | 0 | 0 | 22 | 0 | 241986 | 251985 | 1007940 | 1007940.4 |  |  | 2026-06-13 | 2026-06-13 21:27 | 2026-06-13 | 2026-06-17 18:28 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-13 | 2026-06-13 21:27 | 0 | 0 | 0 | 0 | 0 | 0 | 2135467 | 384384 | 2026-06-23 14:35:51 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-23 14:34:40 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-17 18:26:28 +0530 | Moksh Mehta | DCM: Client Name:- Kamlesh Jain Property:- Dosti Mezzo Possesion Date:- 2 Months Sq Ft:- 960 sqft No of Members : - Couple (45+), Son (17+) + Daughter (14+) Sir has Business in Jewellery, Mam is Homemaker Budget:- 15L- 20L Max Ent: Shoe Rack (15 - 20 Pairs)Wall Concepts. Living Room :- TV Unit (50") with Display unit3-Seater Sofa (4-5 Persons)Wall concepts. Dining Area :- 6 Seater Dining Table.Wall Concepts.Mandir Unit Crockery Unit Kitchen :- Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos.Crockery Unit at the Entrance Master Bedroom :- King size BedL-Shape Wardrobe with Loft Side tableTV LedgeDresser Unit Kid's Bedroom :- Single Bed x 2nosWardrobe with loftStudy TableSide table cum Dresser Parent's Bedroom :- Queen size BedWardrobe with LoftDresser with Side Table Bathroom's Base Vanity Unit's for all Misc:- False CeilingPaintingElectrification | 2026-07-01 |  | 2026-07-08
20541 | Turnkey | 2026-06-01 | Mr. Sangya Ranjan | Folium By Sumadhura | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 2890797 | 9999 | 2890797 | 0 | 0 | 15 | 0 | 279081 | 289080 | 1198958 | 1113679.6 |  |  | 2026-06-13 | 2026-06-23 12:21 | 2026-06-13 | 2026-06-30 11:48 | 2026-07-03 | 2026-06-30 12:14 | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-06-13 | 2026-06-13 17:12 | 2449828 | 440969 | 0 | 0 | 0 | 0 | 2449828 | 440969 | 2026-06-16 15:31:30 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-14 11:30:59 +0530 | Yogesh Patidar | Some Image was uploaded | 2026-06-14 11:30:27 +0530 | Yogesh Patidar | DCM: Property -Samudhara foilum Possesion -Nov - Dec Family of 2 adult and 2 kids 4yrs boy and 10 girl Existing furtniure - Sofa - 3+ 2+ 1 bench 1 queen size bed 1 king size bed Dining table 6seater -seasham wood Pooja mandirÂ Door facing -north Look and Feel -Simple elegant and to look SpaciousÂ Foyer - Shoe rack (kind of niche) Seamless lookÂ With console and mirror Dining -Â Wash basin Base unitÂ Wall unit Tall unit Living -Â Tv 55- 65inch Sound bar Router Decorative place With plain Bottom unit either from bottom and wall hangingÂ Tall unit for displayÂ False ceiling living and diningÂ Wing chair 2nos Wall beading to be used Gold elements to be usedÂ Photofrmsed with back light on front wall Dining wallÂ : paintingÂ Arch wall - with light KitchenÂ Breakfast counterÂ Fridge em Microwave Sir fryed GrinderÂ Coffee machineÂ Hob chimney Quartz - beige Tiles by builderÂ Base wall loft Breakfast counter - with storageÂ Open space to keep fruits Rolling shutter UtilityÂ Counter for non veg cooking. Cylinder unit Washing machineÂ Sink Unit to keep non veg vesselÂ Janitor unit Servant room to be used as store room To keep suitcase All 3 Bedroom wiill be : Wardrobe loft Side tableÂ Bed Dressing tableÂ Study table will be loose furnitureÂ in 2rooms All wardrobe to have bookshelfÂ with glass shutter False ceiling optional Mbr - walking wardrobe with mirror Tv unitÂ Existing wooden flooringÂ Mirror and painting behind bed Side tableÂ New bed with side table Family pictureÂ to be alligned on some walls Existing Painting to be planned Balcony - Mini garden Chair coffee table Pots and plants SwingÂ Pooja unit - Either to be used exsisting Mandir/ Mid size Mandir to be alligned as per Vastu with Minimal idols BathroomÂ Bathtub for kids Glass partition in bathroom apart from mbr Mbr - mirror led and storageÂ Toiletry storage in bed room 3 Dustbin provisionÂ Arch Shutter to be used for cabinets. Budegt -20L | 2026-07-08 |  | 2026-07-15
20542 | Turnkey | 2026-06-01 | Priyanka Sabaji Kurkute | VINAY SKY CITY | MUM - Thane | Yes | Parnavi Joshi | Anil Jagtap | Rachna Abhyankar | [5 empty] | Prashant Panigrahi |  | Active | Design | 20% Payment | 924636 | 108841 | 1088424 | 0 | 0 | 7 | 0 | 0 | 76086 | 426584 | 313124.8 |  |  | 2026-06-13 | 2026-06-16 12:43 | 2026-06-13 | 2026-06-16 13:54 | 2026-06-20 | 2026-06-20 16:23 | 2026-07-08 | 2026-07-08 19:10 | 2027-01-06 |  | 2027-01-13 |  | 2026-06-20 | 2026-06-22 10:25 | 2026-06-21 | 2026-06-22 10:25 | 2026-06-22 | 2026-06-22 13:15 | 2026-06-25 | 2026-06-25 18:14 |  |  |  |  | 2026-07-10 |  | 2027-01-08 |  | 2027-01-09 |  |  |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 |  | 2027-01-19 | [6 empty] | 2027-02-06 |  | 2027-02-15 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-16 |  | 2027-02-18 |  |  |  | 2027-03-12 |  | 2027-03-14 |  | 2027-03-15 | [5 empty] | 2027-01-17 |  | 2026-12-31 | 2026-07-04 11:30 | Site is Non-RTMI | 2026-06-13 | 2026-06-16 12:22 | 924636 | 163787 | 0 | 0 | 0 | 0 | 924636 | 163787 | 2026-07-10 19:22:16 +0530 | Anil Jagtap | The customer stated that the quotation does not match her requirements, and she is now escalating the matter. | 2026-07-05 12:33:32 +0530 | Rachna Abhyankar | Cx Vist | 2026-07-04 11:57:14 +0530 | Parnavi Joshi | M.O.M shared on group | 2026-07-09 | 2026-07-08 19:19 | 2027-01-07 |  | Under Construction | 2026-11-07 | 2026-06-20 | 108841 | Ravi Roy
20543 | Turnkey | 2026-06-01 | Preethi Kumari | Mahendra Aarya | BNG - HSR | Yes | [8 empty] | Ramesh Nayak |  | Active | Prospect | 10% Payment | 1797672 | 9999 | 0 | 0 | 0 | 25 | 0 | 169768 | 179767 | 719069 | 719068.8 |  |  | 2026-06-13 | 2026-06-14 10:26 | 2026-06-13 | 2026-06-14 10:58 | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-20 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-06-13 | 2026-06-13 17:48 | 0 | 0 | 0 | 0 | 0 | 0 | 1523451 | 274221 | 2026-06-14 11:02:25 +0530 | Maspi Das | MOM :- RGM Date : 13.06.2026 CDP date : Client needs to confirmÂ PID: 20543 Name : Preethi Kumari From - Indore Profession : IT Budget : 13-15LÂ 3BHK Property : Mahindra Arya Location : Electronic City (Phase-II) Site Access Date : July end or Aug starting Main door facing : East Total Members : 3 Kids - 1 Theme : Neutral with Pop-up in all the Bedrooms Scope of Work :Â **PERIPHERAL FALSE CEILING FOR LIVING & DINING** Living area Base unit and tall unit with Wall concept Sofa wall- Complimenting something with the TV unit design Dining area- 6 seater dining table Pooja unit - BD-VRM-2025-0677 (on MBR wall) with Crockery unit (can be considered) Bar counter (Base unit with wall designs) Kitchen- Handwash storage/sink cabinet 3' Sink unit 2' HOB Chimney Panel HOB side Lofts Wall units Base units Utility- WM & DW Wall units will be considered as PANTRY UNIT GBR- (Sage Green) Queen size bed Mirror on the wall with very minimal design and two drawers Wardrobe on the opposite wall of BED Study unit KBR- (Blue & Pink) Video shared by client (for Reference) Dresser shown (consider that) WardrobeÂ 2 Single Cot Study unit (need to consider for two kids) Window seating with loose furniture and Soft toys MBR- (Soft Lavender or Warm Beige) King size bed Wardrobe Dressing table Window seating (can plan with loose furniture, should blend with the design For all the washrooms- Vanity units | 2026-06-14 10:55:25 +0530 | Ramesh Nayak | ::::::::---------------RGM Notes For DCM Meeting---------------:::::::: 1. Budget - 12L 2. Property Name & Possession - Mahindra Arya & June-2026 3. Carpet Area - 900 4. BHK - 3 BHK 5. Family Size - 3 Husband works in IT & Wife now H/W because of Small KID Husband is from MP (Indoor) and Wife is from Chennai Wife is Design Centric Husband is ok with Wife Decision he don't have any Inputs. Her Sister-in-Law Visited us in 2019 for her Interior and they want to connect with his Brother-in-laws for Decision making. | 2026-06-14 10:25:33 +0530 | Ramesh Nayak | Some Image was uploaded | 2026-07-13 |  | 2026-07-20
20544 | Turnkey | 2026-06-01 | Snehal satam | ave maria | MUM - GOR | Yes | [8 empty] | Ashutosh Singh |  | Active | Prospect | 10% Payment | 1824508 | 9999 | 0 | 0 | 0 | 29 | 0 | 172452 | 182451 | 783992 | 675614 |  |  | 2026-06-13 | 2026-06-14 12:32 | 2026-06-13 | 2026-06-16 12:20 | 2026-06-21 | 2026-06-21 22:41 | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-06-13 | 2026-06-14 12:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1546193 | 278314 | 2026-06-21 22:44:31 +0530 | Yash Jain | CDP Notes: exchange the sofa and tv wall , remove the window seating, kitchen civil changes in client's scope common bedroom, make the mandir smaller and l shaped wardrobe with study table master bedroom change the orientation of bed with side tables and study table at one side and wardrobes | 2026-06-21 22:36:18 +0530 | Yash Jain | Some Image was uploaded | 2026-06-16 10:40:47 +0530 | Yash Jain | Some Image was uploaded | 2026-06-29 |  | 2026-07-06
20545 | Turnkey | 2026-06-01 | Nitin | Pavani Mariabilia | BNG - HSR | Yes | [8 empty] | Rajoshi Sarkar |  | Active | Prospect | DCM Due | 1445837 | 9999 | 0 | 0 | 0 | 28 | 0 | 134585 | 144584 | 631950 | 524719.2 |  |  | 2026-06-13 | 2026-06-17 19:09 | 2026-06-14 | 2026-06-18 16:38 | 2026-06-20 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-06-13 | 2026-06-17 18:45 | 0 | 0 | 0 | 0 | 0 | 0 | 1229501 | 216335 | 2026-06-14 20:09:51 +0530 | Priyamvada PV | RGM Date : 14.06.26 CDP date : Will confirm on16.06.26 if its possible for this week Traveling from Jun 20 to July 20thÂ PID: 20545 Name : Nitin, Geeta Profession: IT From : Belgavi Property - Pavani Mirabilla 2 BHK Location - Seegehalli, KR puram Site Access Date - Aug'26 Soft possession - Aug'26 Handover - Dec'26 Total Members - 2 adults + 1 kid Kid - Taksh (3yr) boy Orientation (MD facing) -Â East Budget - 8L for modular furniture Excluding loose furniture, lighting, painting, decorative items Scope of Work : Shoe rack insideÂ L shape sofa TV- 55"Â sofa back wall - minimal elegant design Dining 4 seater DT Hand wash on CVanity outsideÂ (plumbing point to be done by builder side ) paneling to cover the p=hand wash Existing hand wash position to have crockery Kitchen Sink facing window (Plumbing to be done by builder) U shape kitchen Fridge space on left wall Appliance unit next to fridge Granite - BD scope Utility WM space and storage for wall Sink unit (bigger size) Balcony mop unit (link for external cabinet to be shared) Not in BD scope MBRÂ Hinged wardrobe with loft bay window seating Study table Dresser mirror BR -2 (GBR) Study table Hinged wardrobe on either sides of bay window seating dresser Pooja unit - sleek In dining areaÂ Sit & stand - poojaÂ (check as per Vastu) Vanities -base storageÂ Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. | 2026-06-14 20:09:20 +0530 | Priyamvada PV | Some Image was uploaded |  |  |  | 2026-06-29 |  | 2026-07-06
20546 | Turnkey | 2026-06-01 | Seema Doke | Madhavi chs | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Foram Joshi |  | Active | Design | DEM1 | 1275600 | 163999 | 1582225 | 0 | 0 | 25 | 0 | 0 | 91121 | 538081 | 482398.8 |  |  | 2026-06-13 | 2026-06-13 19:44 | 2026-06-14 | 2026-06-17 14:33 | 2026-06-20 | 2026-06-18 11:50 | 2026-07-04 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-18 | 2026-06-18 12:04 | 2026-06-19 | 2026-06-18 15:17 | 2026-06-18 | 2026-06-20 12:29 | 2026-06-25 | 2026-06-25 13:23 |  |  |  |  | 2026-07-05 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-26 | 2026-06-30 12:14 | Site is RTMI | 2026-06-13 | 2026-06-13 19:30 | 1340869 | 241356 | 0 | 0 | 0 | 0 | 1313616.1291 | 229608 | 2026-06-28 12:41:43 +0530 | Asavari Vare | Minutes of Meeting held on Date:MOM - 26-06-26. Title: First Meeting Attendees: Client & contractors. Objective: Layout discussion. Based on meeting, below is a list of all the requirements that were discussed during the meeting: Civil changes planned by client Contractor was also explained during the meeting. Entire house flooring will be changed.Â The washroom's internal wall will be demolished, and a combined washroom will be created. WC position to be on living back wall rest of the washroom internal to be planned accordingly.Â The entire kitchen unit will be demolished, and a new counter will be constructed as per the design we suggest.Â In the kitchen, the niche outside will become part of the kitchen area.Â Window seating will be created in 702 flat parts in granite.Â Kitchen walls towards the living room will be demolished in both the flats.Â Window height will increase in Master bedroom.Â Layout points -Â Main entrance will be through 702 Door of floor; other door will be visible from outside however the entrance to be designed in such a way that it looks uniform & part of design.Â Sofa placement options to be created. One of the options wherein the sofa is placed on washroom side walls & TV unit on the door side wall.Dining can be 6-seater or 8-seater depending on the space available in new layout.Â Crockery unit tall storage added above window seating area in 701-unit space.Living room make provision for loose seating and table depending on space.Â Dining area wall use the decors, & existing idols & frames.Mandir to be shifting in opposite direction as existing.Â Library all units to be covered with glass doors.Kitchen loft is now extended to full wall.Â Dishwasher provision to be made as per exiting model dimensions 600MMX 600MM X 840MM.Chimney will be ducted model yet to be finalized.Sink will be a smart sink model with RO provision.Â Master Bedroom -Â No changes in the layout position will be the same as before.Â 2 side tables along with a dedicated dressing unit with storage.Â Sons room -Â Need a dressing unit & 2 side tables.Wardrobe to be sliding only as it was before.Â Washrooms - Vanity unit storage for both washrooms.Â Need a detailed design for the entire washroom.Niches area to be created in front of kitchen which will be utilized for Wash basin unit.Niche area in 702 flat near washrooms will be utilized for washing machine placement. | 2026-06-27 15:53:02 +0530 | Asavari Vare | Minutes of Meeting held on Date: 26-06-26 Based on meeting, below is a list of all the requirements that were discussed during the meeting: Initial Measurement is done.Onsite DEM 1 is completed. Client wants to see renders of entire house. Material selection for Living room, master bedroom is done. | 2026-06-25 13:25:19 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-07-05 |  | 2026-07-06 |  | RTMI |  | 2026-06-17 | 163999 | Ravi Roy
20547 | Turnkey | 2026-06-01 | Meghana Athanikar | Vishnu Apollo | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | 10% Payment | 1458525 | 9999 | 0 | 0 | 0 | 29 | 0 | 135854 | 145853 | 606094 | 560726 |  |  | 2026-06-13 | 2026-06-14 10:55 | 2026-06-13 | 2026-06-16 13:47 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-06-13 | 2026-06-13 22:08 | 0 | 0 | 0 | 0 | 0 | 0 | 1236038 | 222486 | 2026-06-23 12:10:43 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-17 18:00:25 +0530 | Moksh Mehta | DCM Link:- Recap: 20547 - Design Consultation Meeting (DCM) with the customer 13 June ¦ Meeting ¦ Microsoft Teams CDP Link:- Recap: 20547 - Design Consultation Meeting (DCM) with the customer 13 June ¦ Meeting ¦ Microsoft Teams Recap: 20547 - Design Consultation Meeting (DCM) with the customer 13 June ¦ Meeting ¦ Microsoft Teams | 2026-06-16 13:45:26 +0530 | Moksh Mehta | DCM: Client Name:- Meghana Athanikar Possesion Date:- Any time soon Sq Ft:- 850 sqft No of Members : - Single Budget:- 11L Ent: Safety Door Living Room :- TV Unit (55") TV is Existing Dining Area :- No Dining Table. Kitchen :- Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos. Master Bedroom :- Queen size BedWardrobe with Loft with DresserSide table Misc:- False CeilingPaintingElectrification | 2026-06-27 |  | 2026-07-04
20548 | Turnkey | 2026-06-01 | Swarnali suyash Shelar | Aadityaraj paradise | MUM - Thane | Yes | Asavari Vare | Divya Rahangdale | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Preproduction | Site Readiness 1 | 1092674 | 218535 | 1339407 | 0 | 0 | 7 | 0 | 0 | 0 | 437069 | 437069.6 |  |  | 2026-06-13 | 2026-06-15 19:06 | 2026-06-13 | 2026-06-15 19:13 | 2026-06-18 | 2026-06-18 11:19 | 2026-07-08 | 2026-07-08 12:29 | 2026-09-05 |  | 2026-09-12 |  | 2026-06-18 | 2026-06-18 12:05 | 2026-06-19 | 2026-06-18 13:06 | 2026-06-18 | 2026-06-18 16:25 | 2026-06-29 | 2026-06-29 11:55 |  |  |  |  | 2026-07-05 | 2026-07-06 19:04 | 2026-09-07 |  | 2026-09-08 |  |  |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 | [6 empty] | 2026-10-06 |  | 2026-10-15 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-18 |  |  |  | 2026-11-09 |  | 2026-11-11 |  | 2026-11-12 | [5 empty] | 2026-09-16 |  | 2026-06-30 | 2026-07-08 12:16 | Site is Non-RTMI | 2026-06-13 | 2026-06-15 12:39 | 1135091 | 204316 | 0 | 0 | 0 | 0 | 1115727.2958 | 196681 | 2026-07-14 17:42:18 +0530 | Divya Rahangdale | Client will receive possession by the end of August. | 2026-07-08 13:31:17 +0530 | Asavari Vare | MOM - 20548Â MOM- 05-07-26Â Foyer area paneling design modified & upgraded. Final design will depend on site conditions.Â Foldable dining tables will be minimal without any storage & in client's scope.Â Mandir will be completely in traditional theme with pillars installation on either side in the client's scope.Â Sofa back wall with traditional painting theme or artwork. Â TV back wall modified with Arches intersection design in molding with wallpaper. Floating ledges given for speaker's placement.Â Ceiling design â€“ Area above mandir to be highlighted either by grooving or wallpaper.Â Swing placement to be confirmed post site visit since currently there is no space due to placement of recliner sofa in plan. Â Kitchen Pullout 200MM Width added. Â Opposite the side wall will be with a glass door.Â Â Kids room - Â World map wallpaper behind bed back along with the beading pattern below with highlight wall paint. Â Wardrobe position as it is, the Study unit will be foldable with storage above.Â Master bedroom - Â Client has a requirement for foldable study with carcass on wall & panel opening in downwards direction â€“ Need to check feasibility for the same in custom work. Â Bed back wall with molding work in arch & wallpaper. Â Bed position is the same as kids room. Â Â Important Note - Â Currently the site is not accessible, so we need to keep the project on hold | 2026-06-29 12:03:57 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-07-09 | 2026-07-08 13:36 | 2026-09-06 |  | Under Construction | 2026-10-31 | 2026-06-17 | 137939 | Ravi Roy
20549 | Turnkey | 2026-06-01 | Sriram | Hexa Sky Line | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 954115 | 133156 | 1386126 | 0 | 0 | 4 | 0 | 0 | 57667 | 398038 | 365253.6 |  |  | 2026-06-13 | 2026-06-30 12:22 | 2026-06-18 | 2026-07-05 11:48 | 2026-07-08 | 2026-07-05 12:29 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-05 | 2026-07-07 13:03 | 2026-07-06 | 2026-07-08 15:33 | 2026-07-08 | 2026-07-11 13:36 | 2026-07-14 | 2026-07-14 19:17 |  |  |  |  | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-13 | 2026-06-13 20:18 | 1177483 | 208643 | 0 | 0 | 0 | 0 | 1113687.597 | 180587 | 2026-07-11 13:35:00 +0530 | Athul Ajaykumar | OB Accepted â€“ We have received approval for possession and the payment deviation. The client has also confirmed that they understand and accept the current offer and that it cannot be changed at a later stage. Moving the OB | 2026-07-11 10:20:10 +0530 | Muralikrishna Udupi |  | 2026-07-11 10:19:02 +0530 | Muralikrishna Udupi |  | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2027-03-31 | 2026-06-28 | 133156 | Ravi Roy
20550 | Turnkey | 2026-06-01 | Pradeep Phalke | Regency Luxeria | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | DCM Due | 1507347 | 9999 | 0 | 0 | 0 | 32 | 0 | 140736 | 150735 | 670969 | 534908.8 |  |  | 2026-06-13 | 2026-06-13 21:07 | 2026-06-17 | 2026-06-23 13:42 | 2026-06-20 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-06-13 | 2026-06-13 20:53 | 0 | 0 | 0 | 0 | 0 | 0 | 1277412 | 229934 | 2026-06-17 13:25:11 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-17 13:22:56 +0530 | Anjali Singh | DCM: Client Brief SummaryProject Details Family Size: 4 Members + GrandparentsCoupleDaughter (13 Years)Daughter (4 Years)Grandparents (frequent stay/consideration in planning)Possession: ReceivedProfession:Sir: Manufacturing Business (WFH)Ma'am: HomemakerFloor Plan: Mirror Image LayoutBudget: 1516 LakhsStretch Budget: 18 Lakhs MaxCDP: 27th at 11:00 AMLiving & Dining AreaSafety DoorShoe Rack Client Scope3-Seater Sofa + Ottoman4-Seater Dining TableTV UnitStanding Mandir UnitFunctional and clutter-free layout with adequate circulationDaughter's Bedroom(Shared by 13-year-old & 4-year-old daughters) Queen Size BedStudy UnitDresser with MirrorWardrobeDedicated Play Area for Younger DaughterFuture-ready design considering growing needsMaster BedroomQueen Size BedFull Height WardrobeDresser with MirrorStudy/Work-From-Home UnitOpen Shelves for Display & Utility StorageKitchenMicrowave ProvisionDish Tray UnitRO Unit SpaceLoft StorageFull Overhead Cabinets on Hob SideMix of Open & Closed Cabinet Formation on Opposite SideWashing Machine ProvisionAppliance Planning to be finalized during design stageWashroomsVanity Units within WashroomsFunctional Storage for Daily EssentialsDesign ConsiderationsComfortable seating and circulation for grandparentsDedicated WFH workstation in Master BedroomMaximum storage optimization within budgetClean, contemporary design language with practical family-centric planningFocus on child-friendly and future-ready spaces. | 2026-06-17 13:14:28 +0530 | Anjali Singh | Some Image was uploaded | 2026-07-04 |  | 2026-07-11
20553 | Turnkey | 2026-06-01 | Shiv Fashion(Sava chavda) | virat neelyog | MUM - GOR | Yes | Manisha Dubey | Christopher Macwan | Shantanu Parakh | [5 empty] | Ashutosh Singh |  | Active | Preproduction | DEM2 | 895144 | 177489 | 1202659 | 0 | 0 | 13 | 0 | 0 | 0 | 372853 | 344802 |  |  | 2026-06-13 | 2026-06-16 20:14 | 2026-06-16 | 2026-06-19 11:19 | 2026-06-19 | 2026-06-19 23:08 | 2026-06-27 | 2026-06-27 18:53 | 2026-07-10 | 2026-07-09 13:41 | 2026-07-15 |  | 2026-06-19 | 2026-06-19 23:10 | 2026-06-20 | 2026-06-20 01:06 | 2026-06-20 | 2026-06-20 19:29 | 2026-06-24 | 2026-06-24 18:53 |  |  |  |  | 2026-06-27 | 2026-07-02 12:29 | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-25 | 2026-06-27 18:17 | Site is RTMI | 2026-06-13 | 2026-06-14 13:14 | 1019203 | 183456 | 0 | 0 | 0 | 0 | 1027593.448 | 169675 | 2026-06-27 18:53:28 +0530 | Manisha Dubey | DDM1: Minutes of Meeting (MoM) Project: 20553 DEM-1 Date: 26/06/2026 Discussion Points: Kitchen layout revised. 1 drawer unit added with 2 drawers. One crockery tall added in kitchen. All civil work in the kitchen and bedroom will be under the client's scope. Kitchen sink will also be in the client's scope. Aquaguard storage unit to be added. Flush door required for the bedroom washroom door.Â Design to accommodate a front-load washing machine. Hidden drawer to be provided inside the wardrobe. Tall removedÂ from living area.Â PlainÂ ceiling with profile lightÂ required in living room bedroom and passage. Living area colour theme in grey . | 2026-06-24 18:50:18 +0530 | Christopher Macwan | Welcome call done. Initial measurement - Civil work is ongoing at customer's site and he would inform us 1 week in advance for IM DEM Dates -Â DEM 1 - Customer will speak to Yash and update on DEM DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-20 19:28:57 +0530 | Athul Ajaykumar |  | 2026-06-28 | 2026-06-27 18:54 | 2026-07-10 | 2026-07-09 13:45 | RTMI |  | 2026-06-19 | 120266 | Ravi Roy
20557 | Turnkey | 2026-06-01 | Sanjay Patel | L&t 77 crossroads Ghatkopar East | MUM - GOR | No Estimate | [8 empty] | Aniket Parab |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-13 | 2026-06-14 12:12 | 2026-06-20 | 2026-06-20 17:45 | 2026-06-21 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-13 | 2026-06-14 11:19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-20 17:42:09 +0530 | Khushi Khandelwal | DCM: Area- 332 sqft Members-3 Posession- Dec'26 Facing-Â BUDGET- 10L ENTRANCE-Â DINING & LIVING AREA TV unit Sofa seating or sofa cum bed Mandir unit KITCHEN- Single side platform Appliances- Ref., Microwave, Washing machine,Chimney Base unit, wall unit Loft unit BEDROOM-01 (Son's bedroom) WardrobeÂ Study tableÂ Single bed BEDROOM-02 (Master bedroom) WardrobeÂ Queen size bed Dresser | 2026-06-16 11:38:03 +0530 | Aniket Parab | Some Image was uploaded |  |  |  | 2026-07-01 |  | 2026-07-08
20558 | Turnkey | 2026-06-01 | Rachna Ravindar | Sterling Ascentia | BNG - HRBR | Yes | [8 empty] | Kaminahal Rahiman |  | Active | Prospect | Onboarding Due | 700149 | 70015 | 700149 | 0 | 0 | 5 | 0 | 0 | 70015 | 280060 | 280059.6 |  |  | 2026-06-13 | 2026-06-16 17:29 | 2026-06-27 | 2026-06-27 11:05 | 2026-06-30 | 2026-07-09 15:09 | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-07-09 | 2026-07-09 15:32 | 2026-07-10 | 2026-07-10 15:32 | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-13 | 2026-06-14 11:29 | 815005.6016 | 134576 | 0 | 0 | 0 | 0 | 815005.6016 | 134576 | 2026-07-13 18:57:54 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession: september Scope of Work: Modular + Painting (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Not sure if the site is accessible or not * DEM 1 â€“ Tentatively scheduled for (25th July) * 10% Payment Stage â€“ will close after finalizing the Layout Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Sofa Offer Free Hob & Chimney Offer Free Shoerack Offer Laminate Upgrade Offer - June 26 Design fee waiver (5%) PM fee waiver (5%) May'26 100% GST waiver Final Closing Value Discussed: 7,00,149 Checklist terms - descoping, delay compensation, agreement terms are cleared Rejections: offer discrepancy | 2026-07-13 17:37:07 +0530 | Athul Ajaykumar | OB Initiated â€“ Ringing (Dialled from official number) | 2026-07-13 17:33:44 +0530 | Athul Ajaykumar | OB Initiated â€“ Call is not getting connected. | 2026-07-17 |  | 2026-07-24 |  |  |  | 2026-06-30 | 9999 | Ravi Roy
20559 | Turnkey | 2026-06-01 | Navanit Kumar Singh | Assetz Marq 3.0 | BNG - HRBR | Yes | Priyanka R | Rajeshwari S | Shibin Lal | [5 empty] | Mohammed Rasick |  | Active | Design | DEM1 | 1550827 | 211999 | 2128837 | 0 | 0 | 18 | 0 | 0 | 98166 | 643943 | 596718.8 |  |  | 2026-06-14 | 2026-06-17 11:48 | 2026-06-21 | 2026-06-21 13:29 | 2026-06-24 | 2026-06-23 13:16 | 2026-07-12 |  | 2026-08-26 |  | 2026-09-02 |  | 2026-06-23 | 2026-06-24 18:30 | 2026-06-24 | 2026-06-26 20:11 | 2026-06-26 | 2026-06-27 18:06 | 2026-07-07 | 2026-07-03 12:49 |  |  |  |  | 2026-07-13 |  | 2026-08-28 |  | 2026-08-29 |  |  |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 | [6 empty] | 2026-09-26 |  | 2026-10-05 |  | 2026-10-04 |  | 2026-10-05 |  | 2026-10-06 |  | 2026-10-08 |  |  |  | 2026-10-30 |  | 2026-11-01 |  | 2026-11-02 | [5 empty] | 2026-09-06 |  | 2026-07-08 |  | Unknown | 2026-06-14 | 2026-06-15 15:30 | 1804099 | 324737 | 0 | 0 | 0 | 0 | 1764168.2763 | 291299 | 2026-07-14 17:41:42 +0530 | Rajeshwari S | Welcome call done along with Designer RTMI Project. Client wanted to prioritize the design phase 1st Design meeting scheduled on 16th July post that 10% payment will be done. Aligned with process | 2026-07-12 10:40:46 +0530 | Priyanka R |  | 2026-06-27 18:05:14 +0530 | Athul Ajaykumar |  | 2026-07-13 |  | 2026-08-27 |  | RTMI |  | 2026-06-21 | 211999 | Ravi Roy
20561 | Turnkey | 2026-06-01 | Saroj R Chaurasiya | Urban Grandeur | MUM - GOR | Yes | Khyati Bandi | Christopher Macwan | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Design | 20% Payment | 1027652 | 137737 | 1377369 | 0 | 0 | 7 | 0 | 0 | 67793 | 488803 | 333318.4 |  |  | 2026-06-14 | 2026-06-14 14:04 | 2026-06-14 | 2026-06-15 11:56 | 2026-06-20 | 2026-06-23 16:32 | 2026-07-08 | 2026-07-08 13:25 | 2026-07-14 |  | 2026-07-21 |  | 2026-06-23 | 2026-06-23 17:20 | 2026-06-24 | 2026-06-24 00:18 | 2026-06-24 | 2026-06-24 14:34 | 2026-06-26 | 2026-06-26 13:36 |  |  |  |  | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-06-27 | 2026-07-08 13:16 | Site is RTMI | 2026-06-14 | 2026-06-14 14:03 | 1169547 | 207822 | 0 | 0 | 0 | 0 | 1224278.206 | 190830 | 2026-07-05 13:56:36 +0530 | Khyati Bandi | LIVING AREA - 1. TV unit wall hung same as in the file 3. Add one curve panel above entrance door to keep idol 4. Mandir will be same as per CDP file Daughters room - 1. KIng size bed, curtain will be half in height 2. Full mirror on wardrobe side panel MBR - 1. Wall hung tv unit with 2 drawers 2. Wardrobe internal will be same as daughters room, add 2 hidden locker in 2 wardrobe, provision for safe in one wardrobe Add vanitites in washroom KITCHEN - 1. Remove washing machine Add rolling shutter | 2026-06-26 13:41:20 +0530 | Christopher Macwan | Welcome call done. Initial measurement - As per Rahul(Net Designer) Bonito has projects in the same Apt and DEM1 could be done with the layout which we already have. DEM Dates -Â DEM 1 - 28th June 2026 DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-24 14:34:09 +0530 | Sanjana Swami | Possession Status: RTMI Â Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+ 20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM by 26th June 2026 * DEM 1 Client will let us know * 10% Payment Stage by 4th June 2026 *No civil work planned is client's scope of work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 12,24,279 Offers Discussed During the Call: Free Shoerack Offer 100% GST Waiver Laminate Upgrade - Jun 26 Campaign Design Fee Waiver (2.5%) Free Hob & Chimney Offer PM fee waiver (7.5%) Final Closing Value Discussed: 10,27,653 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-09 | 2026-07-08 13:26 | 2026-07-15 |  | RTMI |  | 2026-06-20 | 137737 | Ravi Roy
20563 | Turnkey | 2026-06-01 | GARLAPATI VENKATA HARI SIVA PRASAD PASUPALA | DC Capitol II | BNG - HSR | No Estimate | [8 empty] | Pulivarthi Nirosha |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-14 | 2026-06-16 19:24 | 2026-06-14 | 2026-07-14 12:12 | 2026-06-19 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-08-07 |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-18 |  | 2026-07-19 | [5 empty] | 2026-07-25 |  | 2026-08-02 |  | 2026-08-03 |  |  |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 | [6 empty] | 2026-08-31 |  | 2026-09-09 |  | 2026-09-08 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-12 |  |  |  | 2026-10-04 |  | 2026-10-06 |  | 2026-10-07 | [5 empty] | 2026-08-11 |  | 2026-07-20 |  | Unknown | 2026-06-14 | 2026-06-14 18:04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-14 20:12:08 +0530 | Priyamvada PV | RGM Date : 14.06.26 CDP date : 15.07.26 PID: 20563 Name : Garlpati Venkata Siva Prasad, JeevithaÂ Profession: Hardware (Accenture) From : AP Property - DC capital 3 BHK Location - Panathur Site Access Date - June'26 Soft possession - Oct'26 Total Members - 2 adults + 2 kids Kid - 10yr boys & 8 yrs (Bhargav & Mokshagna) Orientation (MD facing) - East Budget For modular furniture - 13LÂ To be done as per requirements To be considered in Pre - Lam Excluding loose furniture, lighting, painting, decorative items Theme : Modern minimal Scope of Work : Shoe rack outside on right wall with seating LivingÂ TV - 55" Tall decor storage on either sides of TV Wall ledges L shape sofa or 3+2 Pooja unit 3'W sit & stand with storageÂ (shelves to keep frames) VenkateshwaraÂ Entry opp to wall with trims having lord/god frame 4 seater dining table Crockery base storage, wall storageÂ Preferred sliding for base (Need to check) Other option to have glass tall storage facing passage Kitchen 2'W fridge space as per Floor plan L shape kitchen base units Wall mounted RO unit Wall units loft units in u shape Utility WM space Base, wall units BR-2 (KBR) queen size bed space Hinged wardrobe with loft 1 study table with wall storage BR-1 (GBR) queen size bed space Hinged wardrobe with loft 1 study table with wall storage MBR King size bed space Foldable study with wall mounted TV space Sliding wardrobe with loft Hand wash base storage with loft Vanity storage to be checked based on site video if granite is present/ if wall wash basin is not fixed False ceiling- peripheral Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. | 2026-06-14 20:11:47 +0530 | Priyamvada PV | Some Image was uploaded |  |  |  | 2026-07-25 |  | 2026-08-01
20565 | Turnkey | 2026-06-01 | Viral Rawal | bhoomi simara | MUM - GOR | Yes | [8 empty] | Ashutosh Singh |  | Active | Prospect | 10% Payment | 2635933 | 9999 | 0 | 0 | 0 | 14 | 0 | 253594 | 263593 | 1133733 | 975013.6 |  |  | 2026-06-14 | 2026-06-14 15:35 | 2026-06-14 | 2026-06-14 17:17 | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-14 | 2026-06-14 15:34 | 0 | 0 | 0 | 0 | 0 | 0 | 2236861 | 399071 | 2026-06-30 17:03:45 +0530 | Priyanka Patel | Some Image was uploaded | 2026-06-14 17:17:02 +0530 | Priyanka Patel | DCM:1. Name of the customer 20565 - Viral Rawal 2. Profession Cosmetic Business 3. Project Name/Tower Name/Flat Number bhoomi simara 4. Typology (1BHK, 2BHK, 3BHK, etc) 3BHK 5. Site Access Date 2026-06-30 6. Possession Date 2026-06-30 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 2000000 Customer Preferences8. Who will be living in the house? Elderly Members, Joint Family, Nuclear Family, Couple 9. What activities do you usually prefer at your home ? Prayer, Pursuing Hobbies, Relaxing and Unwinding, Family Bonding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] YES 11. Mention basic vastu principles agreed for integration in design, if any YES BASIC Vastu 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) yes Upload reference images 14. Any absolute no-go styles colours or materials no dark colours 15. Do you have any existing furniture that must be accommodated? no 13. Do you want the design to reflect any personal story, cultural influence, or special memory ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack 2. How would you like your entrance to feel? 3. False ceiling required Yes Dcor & Living Room1. Whats the primary use of your living room? Entertaining guests, Multipurpose, TV Focus 2. Must-have furniture or features? TV unit, Speakers, Coffee table, Puja unit, Display unit , Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Artwork 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Dishwasher 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Kids 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Swing 8. Bedroom 1 - Additional units Bookshelf , Dresser , TV unit 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility Parents 11. Bedroom 2 - Bed Type Storage 12. Bedroom 2 - Wardrobe Style Swing 13. Bedroom 2 - Additional Units Study Table, Bookshelf, Dresser, TV Unit 14. False Ceiling Required - Bedroom 2 Yes 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? Tall Storage, Bottom Storage, Washing machine space, Dryer, Top Storage Balcony & Outdoor1. How do you intend to use your balcony? NA 2. Outdoor Mood How do you intend to use the utility Storage Miscellaneous1. Timeline related commitment made by Bonito, if any yes 2. Other commitments made by Bonito to customer, if any yes 3. What are offers committed to customers? yes 4. Move-in date confirmed with customer 2026-12-31 5. Any special occasion mentioned by the customer wrt handover date No becuase They have not visited the property 6. Additional Requirements (Mention any requirements from customer not covered in the form) no 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 2000000 | 2026-06-14 17:12:30 +0530 | Priyanka Patel | DCM: Client DetailsFamily of 4 membersCouple with 2 boys (Ages: 8 years and 2 years)Apartment on the 4th FloorCeiling Height: 11'Estimated Budget: 1520 LakhsNext Meeting: TBS (To Be Scheduled)Entrance & FoyerSafety door required.Shoe rack/storage unit.Design to follow Vastu principles.Living RoomSeating capacity for 78 people.TV size to be determined as per final layout and viewing distance.AC units to be considered within the design.Comfortable family-oriented layout with optimized circulation.Dining AreaDining table options required:Chairs optionBench + chairs combination optionDedicated crockery/storage unit.Civil modification options to be explored if feasible.MandirDedicated Mandir space.Placement as per Vastu guidelines.Kitchen & UtilityParallel kitchen platform layout.Dishwasher provision.Chakki storage provision.Washing Machine space.Janitor unit.Separate utility storage area.Separate utility sink.Sliding kitchen door.Existing servant washroom to be converted into a functional common washroom.Bedroom 1 Kids' BedroomShared bedroom for two boys.Queen-size bed.Study table.Dressing table.Side table.Future-proof design considering the children's age growth.Bedroom 2 Parents' BedroomKing-size bed.Side tables.TV unit.Dresser.Wardrobe.Window bay seating (if feasible).Attached washroom:Base vanity.Senior safety grab bar provision.Master BedroomKing-size bed.Wardrobe.Side tables.Dresser.TV unit.No study table required.AC integration to be considered within the design and ceiling planning.WashroomsBase vanity units.Senior-friendly safety grab bars where required.Functional storage solutions.Design ConsiderationsVastu-compliant planning.Functional storage across all areas.Family-friendly and child-safe design.Civil changes to be evaluated and alternative layout options to be presented where required.Balance between aesthetics, functionality, and budget.BudgetTotal Interior Budget: 1520 Lakhs (subject to final scope and civil modifications). | 2026-07-06 |  | 2026-07-13
20566 | Turnkey | 2026-06-01 | Vithal Gund | Sheth Montana | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 2767465 | 9999 | 2767465 | 0 | 0 | 22 | 0 | 266748 | 276747 | 1217073 | 996898.8 |  |  | 2026-06-14 | 2026-06-16 12:36 | 2026-06-14 | 2026-06-16 12:37 | 2026-06-19 | 2026-07-07 11:22 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-07-15 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-10 |  | Unknown | 2026-06-14 | 2026-06-14 20:59 | 2345309 | 422155 | 0 | 0 | 0 | 0 | 2345309 | 422155 | 2026-06-23 12:33:50 +0530 | Yerra Bharat | Some Image was uploaded | 2026-06-23 11:54:12 +0530 | Yerra Bharat | CDP: Recap: 20566 - Celebrity Design Presentation (CDP) with the customer Friday, June 19 ¦ Meeting ¦ Microsoft Teams | 2026-06-15 19:00:43 +0530 | Yerra Bharat | Others: Client asked for previously worked projects to look at may be from the same project location. Video or Photos. | 2026-07-15 |  | 2026-07-22
20567 | Turnkey | 2026-06-01 | Mr.Amit vallecha | Kalpataru Elitus | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 2555677 | 9999 | 0 | 0 | 0 | 16 | 0 | 245569 | 255568 | 1106797 | 937744.8 |  |  | 2026-06-14 | 2026-06-15 19:11 | 2026-06-14 | 2026-06-16 13:56 | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-07-19 |  | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-14 |  | Unknown | 2026-06-14 | 2026-06-15 19:10 | 0 | 0 | 0 | 0 | 0 | 0 | 2165828 | 389849 | 2026-06-16 12:45:23 +0530 | Bhawaya Goyal | DCM: Client Name: Amit Profession: CA (Chartered Accountant) Property: Kalpataru Elitus, Mulund Tower: B Floor: 10th Floor Budget: 2025 Lakhs CDP: 4th5th July Foyer AreaSafety doorElegant entrance treatment with wall panellingShoe storage (if space permits) Living Room3+2 sofa seating arrangementTV unit6-seater dining tableMandir unitCrockery storage with display shelvesConsole unitFunctional and spacious layout for family gatherings KitchenModular kitchen with base and wall unitsLoft storage on one sideSliding/shutter partition for utility areaDedicated janitor storageEfficient organization for daily-use appliances and cleaning essentials Guest BedroomQueen-size bedWardrobeSide tablesDressing mirrorFoldable/compact ironing table storage Bedroom 1Queen-size bedWardrobeSide tablesDressing mirrorStorage for sports equipmentTwo separate study tables for individual useAdequate shelving and storage solutions Master BedroomQueen-size bedWardrobeSide tablesDressing mirrorDedicated workstationLibrary shelving/storage for booksComfortable work-from-home setup WashroomsVanity units in all washroomsFunctional storage for toiletries and essentials Passage AreaWash basin area treatmentMirror and storage integration (if feasible)Decorative wall treatment for enhanced aesthetics ServicesFalse ceiling ElectricalPainting | 2026-06-16 12:36:15 +0530 | Bhawaya Goyal | DCM: Recap: 20567 - Design Consultation Meeting (DCM) with the customer Sunday, June 14 ¦ Meeting ¦ Microsoft Teams |  |  |  | 2026-07-19 |  | 2026-07-26
20568 | Turnkey | 2026-06-01 | Sanjay Upadhyay | Lodha Aderna | MUM - GOR | Yes | [8 empty] | Mrunali Mitkari |  | Active | Prospect | 10% Payment | 2985677 | 9999 | 0 | 0 | 0 | 22 | 0 | 288569 | 298568 | 1312130 | 1076411.2 |  |  | 2026-06-14 | 2026-06-15 15:40 | 2026-06-14 | 2026-06-16 12:02 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-06-14 | 2026-06-15 15:40 | 0 | 0 | 0 | 0 | 0 | 0 | 2533254 | 452422 | 2026-06-23 17:28:31 +0530 | Priyanka Patel | Recap: 20568 - Celebrity Design Presentation (CDP) with the customer Wednesday, June 17 ¦ Meeting ¦ Microsoft Teams CDP: Project Name/Tower Name/Flat Number Lodha Aderna Typology 3bhk Site Access Date 2026-08-31 Possession Date 2026-08-31 Customer ProfileFamily members (no. & age) 4 member Profession bussiness Key InformationMention external consultants by client e.g. civil, vastu, fengsui, others etc yes Signed off celebrity theme Abstract Luxury Upload reference images of patterns/ textures/ ambiance/ lighting/ color palette Mention Budget (excluding white goods) approved by customer basis CDP discussion (In INR Lakhs)) 3000000 Mention basic vastu principles agreed for integration in design, if any Design VisionEntrance Foyer must-haves yes partition Upload reference images Living key features and furniture must-haves yes Upload reference images Dining setup, table size and other furniture must -haves yes Upload reference images Master Bedroom bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves yes storagae Upload reference images Bedroom 2 bed type, wardrobe style, TV unit, dresser, storage and other furniture must-haves yes Upload reference images Other space/ room (if any) must-haves yes Upload reference images Kitchen layout, counter type, storage style, appliances and other must-haves yes Upload reference images Balcony: primary utility, furniture, storage, planters, other must-haves yes Upload reference images Utility/ Service Area inclusions, storage, clothes drying and other must-haves yes in utility Upload reference images Bathroom vanity style, shower curtain/ partition, storage, other must-haves yes as per site situation Upload reference images Styling and Dcor must-haves yes Space identified for signature design features and its specifics Specify if design to reflect any personal story, cultural influence or special memory MiscellaneousTimeline related commitment made by Bonito to customer, if any: yes Other commitments made by Bonito to customer, if any: yes RGM notes handed over on Pulse Yes CDP notes handed over on Pulse Yes RGM recording handed over on Pulse Yes CDP recording handed over on Pulse Yes What are offers committed to customers? yes Re-confirm the Move-in Date 2026-12-31 Re-confirm the Possession Date Any special occasion mentioned by customer wrt handover date near by diwali | 2026-06-15 15:41:42 +0530 | Ishrat Khan | Some Image was uploaded | 2026-06-14 17:10:53 +0530 | Priyanka Patel | DCM: Requirment Client DetailsFamily of 3 members + 1 petCouple, daughter (17 years old), and son (24 years old)Apartment on the 35th FloorCeiling Height: 10'6"Target Handover: Before DiwaliTotal Budget: 35 Lakhs (including civil work)Civil & Layout ModificationsBreak the wall of the existing maid's room.Maid's room to be converted into either:Storage Room, orAdditional Seating AreaExisting maid's washroom to be converted into a Powder Washroom.Epoxy flooring required in the converted maid's room.Open kitchen concept with necessary civil modifications.Bathtub provision required in the Master Washroom (civil work included).Living RoomFormal living space with:Sofa seatingTV unitFull wall-to-wall TV feature wall.Window bay seating in the living room.Glass partition near the entrance for privacy.Swing in the passageway.Indoor plants to be incorporated.AC units and curtain pelmets already planned.Design to follow Vastu principles.Kitchen & UtilityOpen kitchen layout.Kitchen ceiling to feature a sunroof/skylight effect.Utility area to include:Washing MachineDryerJanitor UnitMaster BedroomWardrobeDresserSide tablesStudy ledgeWindow bay seating (if feasible)Master washroom:BathtubCivil modifications as requiredIndoor plant provision in the SR area (if possible)Bedroom 2 Daughter's Bedroom (17 Years)Queen-size bedSide tableWardrobeDresserStudy tableBedroom 3 Son's Bedroom (24 Years)Queen-size bedSide tableWardrobeDresserStudy ledge (optional)Washroom requirements:Base vanityWall storageOpen niche on wallSliding or bifold washroom doorDesign & Technology RequirementsWarm white lighting throughout.3-in-1 lighting system.Home automation for:CurtainsLightingModern, luxurious, and functional aesthetic.Additional NotesVastu-compliant planning preferred.Space should be pet-friendly.Focus on elegant storage solutions and premium finishes within budget. | 2026-06-27 |  | 2026-07-04
20569 | Turnkey | 2026-06-01 | Dhiraj jehra | Lodha Palava phase 2 | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1624388 | 9999 | 0 | 0 | 0 | 31 | 0 | 152440 | 162439 | 658467 | 641043.6 |  |  | 2026-06-14 | 2026-06-14 21:20 | 2026-06-14 | 2026-06-17 12:09 | 2026-07-31 |  | 2026-08-07 |  | 2026-08-14 |  | 2026-08-21 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-01 |  | 2026-08-02 | [5 empty] | 2026-08-08 |  | 2026-08-16 |  | 2026-08-17 |  |  |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 | [6 empty] | 2026-09-14 |  | 2026-09-23 |  | 2026-09-22 |  | 2026-09-23 |  | 2026-09-24 |  | 2026-09-26 |  |  |  | 2026-10-18 |  | 2026-10-20 |  | 2026-10-21 | [5 empty] | 2026-08-25 |  | 2026-08-03 |  | Unknown | 2026-06-14 | 2026-06-14 21:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1378885 | 245502 | 2026-06-14 21:23:06 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-06-14 21:22:32 +0530 | Nishtha Valawalkar | 15 to 18 Lacs pre lam 30% gst pitched and march 2026 cost pitched 3 ppl will stay To Moksh in cdp, cx said 15 lacs without LF | 2026-06-14 20:55:52 +0530 | Moksh Mehta | DCM: Client Name:- Dhiraj Jehra Property:- Lodha Palava Possesion Date:- RTMI Sq Ft:- 870 sqft. Uno N - 101 No of Members : - Couple (45+) & Son (16+) Sir, is Working as Civil Engineer (Services), Mam is Teacher Son is Aspired to go with engineering Budget:- 13-14L with Civil but W/O Loose Furniture Ent: Shoe Rack (15 - 20 Pairs) Safety DoorWall Concepts. Living Room :- TV Unit (55") 3-Seater Sofa (4-5 Persons)Wall concepts. Dining Area :- 4 Seater Dining Table.Wall Concepts.Pooja & Store wall to be broken Mandir Unit without doors Kitchen :- Semi Modular Kitchen.Base - 2 nos , Wall - 2nos & Loft - 1 nos. Master Bedroom :- Queen / King size BedWardrobe Side table with DresserTV Ledge Bedroom :- 0.5 Room 1 Seater Sofa cum BedWardrobeStudy TableSliding Door for Entrance Bedroom :- Son's Bedroom Queen size BedWardrobeDresser with Side TableStudy Table Bathroom's Wall Vanity Unit's with Mirror Misc:- False CeilingPaintingElectrification | 2026-08-08 |  | 2026-08-15
20570 | Turnkey | 2026-06-01 | Bharath | Aratt Alchemy Elixir | BNG - HSR | Yes | Prathyusha Elangovan | Abhinandan K S | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1329514 | 171025 | 1736980 | 0 | 0 | 15 | 0 | 0 | 94878 | 570430 | 493180.8 |  |  | 2026-06-14 | 2026-06-14 15:51 | 2026-06-14 | 2026-06-23 13:08 | 2026-06-26 | 2026-06-24 16:33 | 2026-07-11 |  | 2026-10-05 |  | 2026-10-12 |  | 2026-06-24 | 2026-06-25 12:08 | 2026-06-25 | 2026-06-25 15:26 | 2026-06-25 | 2026-06-30 12:22 | 2026-07-08 | 2026-07-08 11:41 |  |  |  |  | 2026-07-31 |  | 2026-10-07 |  | 2026-10-08 |  |  |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-17 |  | 2026-10-18 | [6 empty] | 2026-11-05 |  | 2026-11-14 |  | 2026-11-13 |  | 2026-11-14 |  | 2026-11-15 |  | 2026-11-17 |  |  |  | 2026-12-09 |  | 2026-12-11 |  | 2026-12-12 | [5 empty] | 2026-10-16 |  | 2026-07-09 |  | Unknown | 2026-06-14 | 2026-06-14 15:50 | 1472017 | 264963 | 0 | 0 | 0 | 0 | 1449364.457 | 239312 | 2026-07-08 12:47:51 +0530 | Abhinandan K S | Possession expected by end of September 2026. Initial measurement to be planned once the builder is allowing to take the measurements. Customer is ok with the Offers. timeline and Net quote. 10% payment only if we close the DEM phase 1. Meeting dates and timings to be shared with the Customer. Customer wants proper timeline for the production and installation phases after the production kick off. Price protection extended till end of December 2026 from the CSO. | 2026-06-30 12:11:39 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-06-25 17:15:27 +0530 | Sanjana Swami | Possession Status: Under constructionÂ Under construction Completion Date: September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Site is not accessible * DEM 1 Next weekends * 10% Payment Stage by 5th July 2026 Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 14,49,365 Offers Discussed During the Call: PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Silver Coin 21g Laminate Upgrade - Jun 26 Campaign Final Closing Value Discussed: 13,29,515 Checklist terms - descoping, delay compensation, agreement terms are clear Rejection: Client mentioned he wants extended price protection till december 2026, as he is unsure about his possession | 2026-07-12 |  | 2026-10-06 |  | Under Construction | 2026-12-31 | 2026-06-23 | 171025 | Ravi Roy
20571 | Turnkey | 2026-06-01 | Akash Tamboli | Adityaraj realty ghatkopar | MUM - GOR | Yes | Shweta Dalvi | Christopher Macwan | Safalta Karkera | [5 empty] | Ashish Jha |  | Active | Design | 20% Payment | 1532381 | 154728 | 1547281 | 0 | 0 | 20 | 0 | 0 | 151748 | 669093 | 556812 |  |  | 2026-06-14 | 2026-06-16 18:20 | 2026-06-18 | 2026-06-18 18:31 | 2026-06-18 | 2026-06-18 18:55 | 2026-06-25 | 2026-06-25 15:03 | 2026-07-01 |  | 2026-07-08 |  | 2026-06-18 | 2026-06-19 18:56 | 2026-06-19 | 2026-06-20 16:40 | 2026-06-20 | 2026-06-20 20:48 | 2026-06-24 | 2026-06-24 17:21 |  |  |  |  | 2026-06-25 |  | 2026-07-03 |  | 2026-07-04 |  |  |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-14 | [6 empty] | 2026-08-01 |  | 2026-08-10 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 |  | 2026-08-13 |  |  |  | 2026-09-04 |  | 2026-09-06 |  | 2026-09-07 | [5 empty] | 2026-07-12 |  | 2026-06-25 | 2026-06-25 12:54 | Site is RTMI | 2026-06-14 | 2026-06-16 12:37 | 1313541 | 233740 | 0 | 0 | 0 | 0 | 1684359.9813 | 281682 | 2026-06-25 12:59:29 +0530 | Shweta Dalvi | Prelam Laminates have been considered. Any change in laminet selection will lead to cost escalation as the client has a tight budget. | 2026-06-25 12:31:01 +0530 | Shweta Dalvi | Additional Exclusion AC panelling is not considered.Updated Clarifications Required 9. Confirm whether AC panelling is required, as it is currently excluded from the scope. 10. Kitchen partition has been considered in the BOQ; however, the partition shown in the render differs from the scope currently considered. Final design and specifications need to be verified, and any variation between the render and the considered scope may result in a cost deviation | 2026-06-25 12:27:23 +0530 | Shweta Dalvi | Some Image was uploaded | 2026-06-26 | 2026-06-25 15:09 | 2026-07-02 |  | RTMI |  | 2026-06-19 | 154728 | Ravi Roy
20573 | Turnkey | 2026-06-01 | Avnindra Nath Thakur | Assetz 63 Degree East | BNG - HSR | Yes | Shefali | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 2339468 | 349174 | 3580839 | 0 | 0 | 11 | 0 | 0 | 118720 | 1074126 | 797448.8 |  |  | 2026-06-14 | 2026-06-16 10:32 | 2026-06-20 | 2026-06-23 12:26 | 2026-06-28 | 2026-06-30 20:27 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-06-30 | 2026-07-01 11:26 | 2026-07-01 | 2026-07-02 16:45 | 2026-07-02 | 2026-07-04 11:10 | 2026-07-14 | 2026-07-14 19:07 |  |  |  |  | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-14 | 2026-06-16 10:29 | 3034609 | 546229 | 0 | 0 | 0 | 0 | 2959105 | 532638 | 2026-07-04 11:14:19 +0530 | Sanjana Swami | Others: | 2026-07-04 11:09:01 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: 1st week of August 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 120+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible, client will get the site by August 1st week * DEM 1 â€“ preferred on weekends * 10% Payment Stage â€“ 14th July 2026 *Transaction will be B2C self-funding. *Client has not yet planned civil work Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Employee offer (33%) Bonito Atelier - Laminate Upgrade Silver Coin Offer Final Closing Value Discussed: â‚¹ 23,39,468 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-03 11:43:10 +0530 | Sanjana Swami | Onboarding Due: | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2026-08-07 | 2026-06-30 18:32 | 348175 | Ravi Roy
20574 | Turnkey | 2026-06-01 | Rajendra Patil | Asher Arize | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Subhan Khan |  | Active | Prospect | DCM Due | 1039659 | 9999 | 0 | 0 | 0 | 29 | 0 | 93967 | 103966 | 490553 | 341174 |  |  | 2026-06-14 | 2026-06-16 13:02 | 2026-06-14 | 2026-06-23 13:44 | 2026-06-14 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-06-14 | 2026-06-16 11:22 | 0 | 0 | 0 | 0 | 0 | 0 | 882618 | 157041 | 2026-06-29 15:29:35 +0530 | Karuna Shinde | Recap: 20574 - Design Consultation Meeting (DCM) with the customer Sunday, June 14 ¦ Meeting ¦ Microsoft Teams | 2026-06-29 15:29:25 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-16 11:24:34 +0530 | Subhan Khan | 21 gram Silver coin given | 2026-07-04 |  | 2026-07-11
20575 | Turnkey | 2026-06-01 | Girish Khandelwal | GeeCee Emerald | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1692068 | 9999 | 0 | 0 | 0 | 22 | 0 | 159208 | 169207 | 734771 | 618883.6 |  |  | 2026-06-14 | 2026-06-15 19:09 | 2026-06-14 | 2026-06-16 12:09 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-14 | 2026-06-15 19:08 | 0 | 0 | 0 | 0 | 0 | 0 | 1436199 | 255868 | 2026-06-23 18:33:49 +0530 | Krutika Vernekar | DCM: Minutes of Meeting (MOM)Project DetailsProject: GCUnit: 4003, Tower ACarpet Area: 1116 sq.ft.Entrance: East FacingTarget Date: 28th (Sunday)FoyerSafety door to be provided.Shoe rack with storage for 30 pairs + 4 additional pairs. Living RoomMandir unit to be incorporated.TV unit with:Integrated bookshelf.Peripheral false ceiling in the living area.Dining storage/cabinet required for additional storage.Balcony & Utility UtilityDedicated storage unit.Appliance rolling shutter for organized utility management.KitchenModular kitchen layout with maximum functional storage.Dedicated appliance unit.Storage for utensils and daily essentials.Space planning required for:MicrowaveMixerStoveRefrigeratorMaster BedroomHeadboard design only.TV unit for 55-inch TV.Common BedroomExisting 5' x 6' bed to be retained.3' wardrobe required.Kids RoomGlass partition.Window seating.Queen-size bed.Grey-green colour palette.Vanity unit.Hanging storage for clothes.Existing FurnitureAccommodate existing Diwan.Existing 3-seater sofa to be retained where feasible.Maximize utilization of existing furniture within the proposed layout.Budget 13- 15 L Suggested 18-20L | 2026-06-23 16:12:29 +0530 | Krutika Vernekar | DCM: Budget 12-15 L Suggested 18 - 20 L | 2026-06-16 12:08:22 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-07-01 |  | 2026-07-08
20577 | Turnkey | 2026-06-01 | Kunal Dhone | BC Park corp barista | MUM - GOR | Yes | Zoya Bhatkar | Christopher Macwan | Shantanu Parakh | Viraj Chavan | Viraj Chavan |  |  |  | Harshaan Tiku |  | Active | Preproduction | DEM2 | 1029568 | 205914 | 1391338 | 0 | 0 | 4 | 0 | 0 | 0 | 427264 | 396389.6 |  |  | 2026-06-14 | 2026-06-14 17:35 | 2026-06-14 | 2026-06-16 15:03 | 2026-06-21 | 2026-06-23 16:52 | 2026-07-07 | 2026-07-07 12:26 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-23 | 2026-06-23 18:16 | 2026-06-24 | 2026-06-24 00:16 | 2026-06-24 | 2026-06-24 13:04 | 2026-06-27 | 2026-06-27 11:36 |  |  |  |  | 2026-07-07 | 2026-07-11 17:34 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-06-28 | 2026-07-04 13:09 | Site is RTMI | 2026-06-14 | 2026-06-14 17:34 | 1179100 | 212238 | 0 | 0 | 0 | 0 | 1174465.918 | 185322 | 2026-07-07 12:56:17 +0530 | Zoya Bhatkar | Minutes of Meeting held on Date: 04th July 2026 Attendees: Discussion: DEM 1 ï»¿ Based on 04th July 2026 meeting, below is a list of all the requirements that were discussed during the meeting: Foyer Area Safety door with panelling Living Room L Shape with 3 Seater Sofa with recliner Open unit near Mandir Existing Storage to be provided below Book shelf tall unit 2' by 7'Glass shutter Master Bedroom Wardrobe Internals as discussed Study White Board & Soft Board Dresser Wall unit to be added TV Space to be decided Master Bedroom Washroom Wall Vanity with Mirror above shutter glass partition to be checked during CM Stage Bedroom 1 Existing Metal Wardrobe with Loft Storage White & Soft Board Lights below Study wall Unit Kitchen Main Platform Bottom Unit same as discussed during the NET Wall unit with glass shutter Sevice Same as discussed during NET | 2026-06-27 11:35:32 +0530 | Christopher Macwan | Welcome call done. Initial measurement aligned for today 27th June 2026 11:30am DEM Dates -Â DEM 1 - Will need to check with the designer for tomorrow 28th June 2026. Informed if not possible tomorrow, will check for the 1st available slot. DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-26 14:23:52 +0530 | Christopher Macwan | Called for welcome call but no answer. | 2026-07-08 | 2026-07-07 12:55 | 2026-07-14 |  | RTMI |  | 2026-06-21 | 139134 | Ravi Roy
20578 | Turnkey | 2026-06-01 | Ajinkya Sawant | Kamla Riddhima | MUM - GOR | Yes | Swapnali Shedekar | Christopher Macwan | Safalta Karkera | [5 empty] | Sanskruti Yadav |  | Active | Design | DEM1 | 1022946 | 204589 | 1286851 | 0 | 0 | 21 | 0 | 0 | 0 | 415686 | 402670.8 |  |  | 2026-06-14 | 2026-06-16 11:43 | 2026-06-14 | 2026-06-16 11:44 | 2026-06-21 | 2026-06-21 21:47 | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-21 | 2026-06-21 21:32 | 2026-06-22 | 2026-06-21 22:21 | 2026-06-21 | 2026-06-24 14:46 | 2026-06-25 | 2026-06-25 13:15 |  |  |  |  | 2026-07-01 | 2026-07-12 20:19 | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-14 | 2026-06-14 17:48 | 1090552 | 196299 | 0 | 0 | 0 | 0 | 1090551.9688 | 184130 | 2026-06-25 13:14:00 +0530 | Christopher Macwan | Welcome call done. Initial measurement not done as would receive possession by End of November 2026 DEM Dates -Â DEM 1 - Customer wants DEM1 in the 2nd weekend of July(Sunday) DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of November 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-24 14:49:07 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-06-24 14:48:30 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-07-01 |  | 2026-07-08 |  | Under Construction | 2026-11-15 | 2026-06-21 | 128685 | Ravi Roy
20579 | Turnkey | 2026-06-01 | Nadeem Ahmad | Confident Mayfair | BNG - HSR | Yes | Sayed Byahatti | Akshay Ds | Kowshik | [5 empty] | Nidhi Shaw |  | Active | Design | DEM1 | 1283406 | 182334 | 1826173 | 0 | 0 | 14 | 0 | 0 | 74347 | 513362 | 513362.4 |  |  | 2026-06-14 | 2026-06-14 18:08 | 2026-06-19 | 2026-06-19 16:36 | 2026-06-22 | 2026-06-21 18:09 | 2026-07-19 |  | 2026-09-05 |  | 2026-09-12 |  | 2026-06-21 | 2026-06-22 12:53 | 2026-06-22 | 2026-06-30 19:56 | 2026-06-30 | 2026-07-01 12:48 | 2026-07-14 | 2026-07-14 16:02 |  |  |  |  | 2026-07-20 |  | 2026-09-07 |  | 2026-09-08 |  |  |  | 2026-09-15 |  | 2026-09-16 |  | 2026-09-17 |  | 2026-09-18 | [6 empty] | 2026-10-06 |  | 2026-10-15 |  | 2026-10-14 |  | 2026-10-15 |  | 2026-10-16 |  | 2026-10-18 |  |  |  | 2026-11-09 |  | 2026-11-11 |  | 2026-11-12 | [5 empty] | 2026-09-16 |  | 2026-07-15 |  | Unknown | 2026-06-14 | 2026-06-14 18:06 | 1547604 | 278568 | 0 | 0 | 0 | 0 | 1472610.723 | 243163 | 2026-07-14 16:12:19 +0530 | Akshay Ds | Possession expected by Aug end Customer is expecting renders from the CDP, customer is following up Customer is out of bangalore, he is ready to have the meeting on next meeting | 2026-07-01 12:47:12 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: End of July or 1st week of august Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM will update to the sales team * DEM 1 will update to the sales team * 10% Payment Stage Tentatively scheduled for (10th July 2026) * B2C - Self * Civil work - NO Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Referred Customer Discount PM fee waiver (5%) Design fee waiver (5%) 100% GST Waiver Free Shoerack Offer Free Hob & Chimney Offer Silver Coin 21g Laminate Upgrade - Jun 26 Campaign Final Closing Value Discussed: 12,83,406 Checklist terms descoping and agreement terms are cleared | 2026-06-30 19:55:53 +0530 | Nidhi Shaw | Some Image was uploaded | 2026-07-20 |  | 2026-09-06 |  | Under Construction | 2026-08-15 | 2026-06-21 | 182334 | Ravi Roy
20580 | Turnkey | 2026-06-01 | Aniket Panja | L&T 360 | MUM - Thane | Yes | [8 empty] | Rahul Kumawat |  | Active | Prospect | 10% Payment | 3660543 | 9999 | 0 | 0 | 0 | 16 | 0 | 356055 | 366054 | 1562313 | 1366121.2 |  |  | 2026-06-14 | 2026-06-14 20:36 | 2026-06-14 | 2026-06-16 11:09 | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-14 | 2026-06-14 20:34 | 0 | 0 | 0 | 0 | 0 | 0 | 3102155 | 558387 | 2026-06-29 17:21:32 +0530 | Bhawaya Goyal | CDP: Special Planning RequirementExisting servant room to be divided into 2 partsPortion towards living room to be converted into MandirRemaining portion for Shoe Rack + Storage KitchenFully Modular KitchenSink on upper sideCooktop on lower sideDishwasher provisionDouble-door refrigerator spaceMicrowave provisionMixer/Small appliance storageBase cabinetsWall cabinetsLoft storage (one side only) Living Room3-Seater Sofa4-Seater Dining TableTV Unit with Open ShelvingFunctional and Vaastu-compliant layout Bedroom 1 Son's RoomQueen Size Bed with Hydraulic StorageWardrobeStudy TableDressing MirrorAdequate storage and study-focused planning Bedroom 2 Daughter's RoomQueen Size Bed with Hydraulic StorageWardrobeDressing MirrorFunctional storage solutions Study Room4 ft Study TableSingle Sofa Cum BedBooks Library / BookshelfAdditional Storage Unit Master BedroomBed Size: 5'6" x 6' with Drawer StorageWardrobeSide TablesMirror / Dressing AreaTV ProvisionComfortable circulation with Vaastu considerations ServicesFalse ceilingElectricalPainting | 2026-06-29 17:20:51 +0530 | Bhawaya Goyal | Some Image was uploaded | 2026-06-29 17:20:24 +0530 | Bhawaya Goyal | Some Image was uploaded | 2026-07-06 |  | 2026-07-13
20582 | Turnkey | 2026-06-01 | Kamal N Saini | Kanakia | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | Onboarding Due | 1189031 | 209999 | 1189031 | 0 | 0 | 1 | 0 | 0 | 27807 | 505867 | 445357.6 |  |  | 2026-06-14 | 2026-06-21 13:28 | 2026-06-20 | 2026-06-21 22:48 | 2026-07-11 | 2026-07-12 23:51 | 2026-07-20 |  | 2026-07-27 |  | 2026-08-03 |  | 2026-07-11 | 2026-07-12 23:43 | 2026-07-13 | 2026-07-14 18:32 | 2026-07-14 |  | 2026-07-15 | [5 empty] | 2026-07-21 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-07-16 |  | Unknown | 2026-06-14 | 2026-06-16 11:38 | 1360927.98 | 229775 | 0 | 0 | 0 | 0 | 1360927.98 | 229775 | 2026-07-14 18:34:27 +0530 | Sanskruti Yadav |  | 2026-07-14 12:02:29 +0530 | Yash Jain | Recap: 20582 - Celebrity Design Presentation (CDP) with the customer 11 July ¦ Meeting ¦ Microsoft Teams | 2026-07-14 12:00:10 +0530 | Yash Jain | living rm living room setup to be mirrored as per vastu for mandir Mandir in Cx scope , bottom drawers in our scope. 4-seater - Folding dining table with bench and seating in cx scope common room activites - study table sofa cum bed 2 seater in cx scope. jungle gym in cx scope. add tall unit for storage Master bedroom wardrobes besides beds with sides table. study tbale with storage . Vanity unit in both bathrooms. FC paint and eletricals in our scope with decor parts for all rooms. | 2026-07-21 |  | 2026-07-28
20583 | Turnkey | 2026-06-01 | Amar Chaudhary | One Luxuria | MUM - Thane | Yes | [8 empty] | Vandana Preet |  | Active | Prospect | 10% Payment | 2524332 | 9999 | 0 | 0 | 0 | 27 | 0 | 242434 | 252433 | 1195805 | 823660.8 |  |  | 2026-06-14 | 2026-06-16 19:21 | 2026-06-14 | 2026-06-17 15:44 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-06-14 | 2026-06-14 20:59 | 0 | 0 | 0 | 0 | 0 | 0 | 2139264 | 385067 | 2026-06-23 11:21:50 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-23 11:20:52 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-16 12:26:44 +0530 | Krutika Vernekar | DCM: Client Brief Amar ChoudharyProject: One LuxuriaConfiguration: 3 BHK Floor: 9th Floor Carpet Area: 1034 sq.ft. Possession: End of October Next Meeting: Sunday, 3:00 PM Living Room & FoyerL-Shape SofaIndian Baithak / Low Seating AreaTV Unit BOTTOM Shoe Rack (2025 Pairs Capacity)(outside)Safety DoorKitchen (Approx. 90 sq.ft.)Scope:Complete Modular KitchenCivil Modifications RequiredPlumbing Work(Cx Scope)Appliance Planning & Storage:MicrowaveWashing Machine(Front LoaD)Mixer/GrinderJuicerSandwich MakerAir FryerDedicated Appliance Storage UnitBathroomCommon Bathroom Complete Bathroom Renovation(Cx Scope )Plumbing Upgrades(Cx wants Indian Sitting + vanity Unit )Study AreaL-Shaped Study TableStorage UnitsKids BedroomStudy UnitWardrobeKing Size BedBedroomsCommon Requirements (All 3 Bedrooms)Vanity UnitWindow SeatingBalconyJhoola (Swing)(Cx Scope)Ceiling & LightingPeripheral False CeilingLighting PlanningPrepared For: Amar Choudhary Project: One Luxuria ¦ 3 BHK ¦ 1034 sq.ft. Carpet Area | 2026-06-29 |  | 2026-07-06
20584 | Turnkey | 2026-06-01 | BALIRAM RAMSADAN YADAV | One Luxuria | MUM - Thane | Yes | [8 empty] | Foram Joshi |  | Active | Prospect | 10% Payment | 1936662 | 9999 | 0 | 0 | 0 | 22 | 0 | 183667 | 193666 | 824271 | 725058.8 |  |  | 2026-06-14 | 2026-06-16 12:35 | 2026-06-14 | 2026-06-16 12:36 | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-06-14 | 2026-06-14 20:59 | 0 | 0 | 0 | 0 | 0 | 0 | 1641239 | 295423 | 2026-06-23 12:36:34 +0530 | Yerra Bharat | Some Image was uploaded | 2026-06-23 11:56:43 +0530 | Yerra Bharat | CDP: Recap: 20584 - Celebrity Design Presentation (CDP) with the customer Sunday, June 21 ¦ Meeting ¦ Microsoft Teams | 2026-06-23 10:59:11 +0530 | Yerra Bharat | CDP: Foyer Area: Shoe rack - Not required. Safety Door Living / Dining: Dining table and Storage console in the dining area is removed. Wants to keep the area clear. Living: TV unit - Wall mounted - minimal. L - sofa with center table. Kitchen: Membrane finish, without any designs. Master bedroom: King size bed with one movable side table on window side and side table attached to wardrobe which is L-shape. Mirror on the wall, with ledge in the niche area. Bedroom - 2: builder made civil changes to the windows King size bed wardrobe in the corner. Bedroom-3 No bed Only wardrobe one study with top storage and one without storage. White board beside the study Design wanted to be minimal with less groves and dust attracting elements. | 2026-06-29 |  | 2026-07-06
20585 | Turnkey | 2026-06-01 | Pinky Chouhan | JK Iris | MUM - GOR | Yes | Preeti Agarwal | Vishakha Vaishnav | Shantanu Parakh | [5 empty] | Saloni Sagwekar |  | Active | Preproduction | DEM2 | 1229183 | 245837 | 1731011 | 0 | 0 | 3 | 0 | 0 | 0 | 544030 | 439316 |  |  | 2026-06-14 | 2026-06-16 12:33 | 2026-06-14 | 2026-06-16 12:34 | 2026-06-29 | 2026-07-01 15:23 | 2026-07-13 | 2026-07-12 12:01 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-27 | 2026-06-27 23:10 | 2026-07-02 | 2026-07-03 12:21 | 2026-07-03 | 2026-07-03 18:23 | 2026-07-06 | 2026-07-05 16:42 |  |  |  |  | 2026-07-12 | 2026-07-12 15:48 | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-06 | 2026-07-12 11:00 | Site is RTMI | 2026-06-14 | 2026-06-14 20:22 | 1469978 | 261033 | 0 | 0 | 0 | 0 | 1443916.979 | 226460 | 2026-07-10 16:04:26 +0530 | Vishakha Vaishnav | CX MENTIONED ON WHATSAPP THAT SHE WON'T BE ABLE TO COME AGAIN & AGAIN AT EC FOR MEETING SO HAVE ALIGNED THE DEM 1 FOR TOMORROW BY 2PM VIRTUALLY . MATERIAL SELECTION WILL BE DOING AT ANDHERI EC REMAINING EETINGS CX WILL CONNECT WITH US VIRTUALLY | 2026-07-05 16:39:55 +0530 | Vishakha Vaishnav | Others: Welcome call done IM date : Done on 5th July DEM 1 : need to schedule for weekend Possession date : renovation property 10% payment aligned : after dem 1 Periskope Number added : yes Escalation Matrix added :yes Price protection for 150 days from the NET date | 2026-07-03 18:28:02 +0530 | Athul Ajaykumar | OB Accepted - Address is updated. Moving the OB | 2026-07-13 | 2026-07-12 12:01 | 2026-07-19 |  | RTMI |  | 2026-06-27 | 209999 | Ravi Roy
20586 | Turnkey | 2026-06-01 | Rajesh Meena | Kanakia Silicon Valley | MUM - GOR | Yes | Preeti Agarwal | Manzoor Shaikh | Shantanu Parakh | Neha Singh | Neha Singh |  |  |  | Ashutosh Singh |  | Active | Preproduction | DEM2 | 870546 | 174108 | 1154946 | 0 | 0 | 9 | 0 | 0 | 0 | 389704 | 306733.6 |  |  | 2026-06-14 | 2026-06-14 21:02 | 2026-06-14 | 2026-06-21 12:50 | 2026-06-21 | 2026-06-21 17:39 | 2026-07-08 | 2026-07-04 16:29 | 2026-07-10 |  | 2026-07-17 |  | 2026-06-21 | 2026-06-21 20:55 | 2026-06-22 | 2026-06-21 20:55 | 2026-06-21 | 2026-06-25 10:04 | 2026-06-25 | 2026-06-25 16:54 |  |  |  |  | 2026-07-04 | 2026-07-06 17:56 | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-26 | 2026-07-04 11:46 | Site is RTMI | 2026-06-14 | 2026-06-14 21:01 | 978768 | 176178 | 0 | 0 | 0 | 0 | 978767.4398 | 165248 | 2026-06-29 15:59:59 +0530 | Manzoor Shaikh | "Welcome call done along with the Designer. Initial measurement was done on 27th June 2025 DDM Dates -Â DDM 1 - TBD DDM 2 - TBD DDM 3 - TBD Possession date : RTMI Customer will make 10% post LFM Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date." | 2026-06-25 16:57:07 +0530 | Manzoor Shaikh | Some Image was uploaded | 2026-06-25 16:53:50 +0530 | Manzoor Shaikh | Called the customer for the Welcome Call along with Preeti Agarwal, however, said he is driving and requested a call back later. | 2026-07-05 | 2026-07-04 16:32 | 2026-07-11 |  | RTMI |  | 2026-06-20 | 115494 | Ravi Roy
20587 | Turnkey | 2026-06-01 | Ranjit Pannu | Aikya Roots | MUM - Thane | Yes | [8 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 1056943 | 9999 | 0 | 0 | 0 | 22 | 0 | 95695 | 105694 | 438637 | 406917.2 |  |  | 2026-06-14 | 2026-06-16 11:09 | 2026-06-16 | 2026-06-20 12:14 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-14 | 2026-06-14 21:01 | 0 | 0 | 0 | 0 | 0 | 0 | 895714 | 161228 | 2026-06-23 12:17:48 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-23 12:17:32 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-23 11:58:08 +0530 | Anjali Singh | DCM: Recap: 20587 - Design Consultation Meeting (DCM) with the customer 16 June ¦ Meeting ¦ Microsoft Teams | 2026-07-01 |  | 2026-07-08
20588 | Turnkey | 2026-06-01 | AVDHOOT RATNOBA KOYANDE Koyande | Ashar Arize | MUM - Thane | Yes | [8 empty] | Nivesh Gupta |  | Active | Prospect | 10% Payment | 1527533 | 9999 | 0 | 0 | 0 | 16 | 0 | 142754 | 152753 | 695940 | 526086.8 |  |  | 2026-06-14 | 2026-06-18 18:46 | 2026-06-18 | 2026-06-19 12:02 | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-07-07 |  | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-07-02 |  | Unknown | 2026-06-14 | 2026-06-18 12:02 | 0 | 0 | 0 | 0 | 0 | 0 | 1296576 | 230957 | 2026-06-23 11:27:06 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-23 11:26:21 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-19 12:00:19 +0530 | Krutika Vernekar | Project Brief Ashar AriseProject DetailsProject: Ashar AriseConfiguration: 2 BHKCarpet Area: 663 sq.ft.Entrance: West FacingClient DetailsFamily Members (5): HusbandWifeSonDaughter (Class 10)GrandmotherScope of WorkFoyerShoe RackDecorative wall opening with frame panel detailingSeparate Mandir with partition/cubicle designFunctional entry storageLiving RoomTV UnitFolding Dining Table (Client is inclined towards this option and is not procuring a loose dining table)3-Seater SofaKitchenCompleteÂ Semi Modular Kitchen( Base + Over Head + loft )Tall UnitWicker Basket StorageBathroomVanity UnitWashing Machine StorageUtility StorageKids' BedroomStorage BedWardrobeTall Book Storage UnitFolding Study TableDresserMaster BedroomStorage BedWardrobeDresserVanity UnitTV Unit with concealed document storageBalconyLedge StorageDecorative Wall CladdingCivil & MEP ScopePeripheral False CeilingElectrical ModificationsPaintingClient Concerns / BlockersComparing our warranty with Livspace.Budget-conscious due to previous experiences of getting interiors done twice through local carpenters.Hesitant to invest heavily again.Budget DiscussionClient Budget: 8 LakhsSuggested Budget: 15 LakhsDiscussion Strategy: Educate the client on the difference in quality, warranty, execution, and after-sales service.Demonstrate long-term value instead of only focusing on initial cost.Prioritize essential requirements first and explore phased execution or value engineering if required while maintaining design quality. | 2026-07-07 |  | 2026-07-14
20589 | Turnkey | 2026-06-01 | Rafiq shaikh | S M Emperial | MUM - GOR | Yes | Saif Shaikh | Christopher Macwan | Shantanu Parakh | [5 empty] | Aniket Parab |  | Hold | Preproduction | Site Readiness 1 | 841819 | 168364 | 1027333 | 0 | 0 | 5 | 8 | 0 | 0 | 367488 | 305966.8 |  |  | 2026-06-14 | 2026-06-16 10:25 | 2026-06-16 | 2026-06-16 15:11 | 2026-06-20 | 2026-06-20 19:45 | 2026-06-28 | 2026-06-27 19:06 | 2026-08-05 |  | 2026-08-12 |  | 2026-06-20 | 2026-06-20 18:11 | 2026-06-21 | 2026-06-21 11:28 | 2026-06-21 | 2026-06-24 15:35 | 2026-06-26 | 2026-06-26 12:28 |  |  |  |  | 2026-06-27 | 2026-07-02 12:56 | 2026-08-07 |  | 2026-08-08 |  |  |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 | [6 empty] | 2026-09-05 |  | 2026-09-14 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-17 |  |  |  | 2026-10-09 |  | 2026-10-11 |  | 2026-10-12 | [5 empty] | 2026-08-16 |  | 2026-06-27 | 2026-06-27 18:58 | Site is RTMI | 2026-06-14 | 2026-06-16 10:24 | 870621 | 156711 | 0 | 0 | 0 | 0 | 870620.4354 | 151527 | 2026-07-07 21:05:54 +0530 | Christopher Macwan | Project on hold till 31st July 2026 due to no possession | 2026-06-26 11:43:01 +0530 | Christopher Macwan | Welcome call done. Initial measurement - Customer has permission for IM and cx wants IM for 27th June 2026. Informed if available will book slot for tomorrow or else will provide an available date DEM Dates -Â DEM 1 - Customer is fine for DEM1 anytime after IM DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - September or October Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-24 15:34:39 +0530 | Athul Ajaykumar | Possession Status: Under constructionÂ Possession: September/October Soft possession: August Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (27th June 2026) * DEM 1 Tentatively scheduled for (4th July 2026) * 10% Payment Stage Tentatively scheduled for (3rd July 2026) * B2C - Self * Civil work - yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM Fee Waiver (4%) 100% GST Waiver Silver Coin 21g Final Closing Value Discussed: 8,41,819 Checklist terms descoping and agreement terms are cleared Client VOC: The client mentioned that civil work may be required, specifically the demolition of a wall in the kitchen to accommodate a crockery unit. As this is an optional scope of work, the client would like to proceed only after receiving the designer's inputs and recommendations. | 2026-06-28 | 2026-06-27 19:06 | 2026-08-06 |  | Under Construction | 2026-08-31 | 2026-06-20 | 102733 | Ravi Roy
20590 | Turnkey | 2026-06-01 | Srihari Madhav Kulkarni | piramal mahalaxmi | MUM - GOR | No Estimate | [8 empty] | Saloni Sagwekar |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-14 | 2026-06-16 12:31 | 2026-07-18 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-08-04 |  | 2026-08-11 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | 2026-07-29 |  | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-07-24 |  | Unknown | 2026-06-14 | 2026-06-16 12:26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2026-07-29 |  | 2026-08-05
20592 | Turnkey | 2026-06-01 | DHANANJAYAN n | independent house | BNG - HRBR | Yes | [8 empty] | Kushal S |  | Active | Prospect | 10% Payment | 700172 | 70017 | 1460765 | 0 | 0 | 15 | 0 | 0 | 70017 | 280069 | 280068.8 |  |  | 2026-06-14 | 2026-06-23 12:19 | 2026-06-30 | 2026-06-30 10:31 | 2026-07-03 | 2026-07-03 13:21 | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 | 2026-07-13 17:44 | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-06-14 | 2026-06-15 15:18 | 1237937 | 222828 | 0 | 0 | 0 | 0 | 815030.498 | 134581 | 2026-06-30 18:14:19 +0530 | Priyanka Gs | Some Image was uploaded | 2026-06-30 10:25:36 +0530 | Priyanka Gs | Living RoomTV Unit with optimized placement to achieve a more functional and aesthetically balanced layout.False Ceiling design with integrated lighting provisions.Overall layout planning to enhance circulation and maximize usable space.Pooja UnitDedicated Pooja Unit with storage provisions.Shutters/doors will be custom-made and supplied by the client.Design to include internal shelving and storage organization.KitchenBottom Cabinets for storage and workspace functionality.Wall Cabinets for additional storage.Loft Storage extending up to the existing chajja/site-constructed beam level.Layout to ensure efficient workflow and maximum storage utilization.Bedroom 1Wardrobe with overhead loft storage.Study Unit with desk and storage provisions.Mirror arrangement integrated with the wardrobe or dressing area.Bedroom 2Wardrobe with overhead loft storage.Study Unit with desk and storage provisions.Mirror arrangement integrated with the wardrobe or dressing area.First Floor Living AreaNo interior requirements at present.Space to be kept open for future development.Bedroom 3Wardrobe with overhead loft storage.Study Unit with desk and storage provisions.Mirror arrangement integrated with the wardrobe or dressing area.Bedroom 4Wardrobe with overhead loft storage.Study Unit with desk and storage provisions.Mirror arrangement integrated with the wardrobe or dressing area. | 2026-06-16 14:38:02 +0530 | Losii Athisa | Some Image was uploaded | 2026-07-11 |  | 2026-07-18 |  |  |  | 2026-06-30 | 9999 | Ravi Roy
20593 | Turnkey | 2026-06-01 | Kavita Sredharan | Crest oak | MUM - GOR | Yes |  |  |  |  | Fareed Shaikh |  |  |  | Mrunali Mitkari |  | Active | Prospect | DCM Due | 2223761 | 9999 | 0 | 0 | 0 | 30 | 0 | 212377 | 222376 | 908016 | 870992.8 |  |  | 2026-06-14 | 2026-06-15 15:45 | 2026-06-28 |  | 2026-06-30 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-07-22 |  | 2026-07-01 |  | 2026-07-02 |  | 2026-07-02 |  | 2026-07-03 | [5 empty] | 2026-07-09 |  | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 | [6 empty] | 2026-08-15 |  | 2026-08-24 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-27 |  |  |  | 2026-09-18 |  | 2026-09-20 |  | 2026-09-21 | [5 empty] | 2026-07-26 |  | 2026-07-04 |  | Unknown | 2026-06-14 | 2026-06-15 15:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1884543 | 339217 | 2026-06-28 18:11:49 +0530 | Shreya Sonavane | DCM: Living room- Saftey door, shoe rack outside, Partition in front of entrance, sofa existing, foldable dinning for 4, mandir on TV right wall, Tv unit, Window seating bay window, cozy seating. Not sure about crockery. Master bedroom- referance shared on wassp group(Bed, wardrobe) Kids room- mezzanine bed,tv UNIT, wardrobe, study Vanity, no FC, looking for alternative lihghting option, Parallel kitchen, | 2026-06-15 15:46:21 +0530 | Ishrat Khan | Some Image was uploaded | 2026-06-15 15:15:18 +0530 | Unknown | About the Customer **Customer Property and Budget Details** Kavita is looking for interior design for a 2 BHK in Andheri, Crest Oak, with possession expected in October and a move-in target of November/December. Her estimated budget for Mumbai is 10-15 lakhs. **Location Confirmation Required for Visit** The customer requires the Bonito Designs experience center location to be sent via WhatsApp before confirming a visit time. **Family Visit Confirmation** Customer Kavita Sridhar confirmed she will be visiting with her family. **Agent to Send Location, Customer to Confirm Time** The agent will send the experience center location via WhatsApp, after which the customer will confirm a visit time. **Existing Appointment Details** Customer has an existing confirmed appointment with Yogesh at the Andheri branch today between 5:30 PM and 6:00 PM IST. | 2026-07-09 |  | 2026-07-16
20595 | Turnkey | 2026-06-01 | Deepak Tiwari | MICL Aaradhya Parkwood | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam |  |  | Akash Jadhav | Sandeep Tiwari |  | Aryan Singh | Shailendra Mishra | Active | Preproduction | 2D | 1046884 | 209999 | 1233132 | 1046884 | 0 | 1 | 0 | 0 | 0 | 425279 | 411606.4 |  |  | 2026-06-14 | 2026-06-16 15:19 | 2026-06-16 | 2026-06-16 17:35 | 2026-06-19 | 2026-06-19 11:25 | 2026-06-25 | 2026-06-25 18:46 | 2026-07-09 | 2026-07-08 11:43 | 2026-07-10 | 2026-07-10 19:15 | 2026-06-19 | 2026-06-19 18:24 | 2026-06-20 | 2026-06-20 03:44 | 2026-06-20 | 2026-06-20 14:29 | 2026-06-25 | 2026-06-25 12:02 |  |  |  |  | 2026-06-27 | 2026-06-25 11:54 | 2026-07-09 | 2026-07-10 17:30 | 2026-07-11 | 2026-07-10 18:37 |  |  | 2026-07-12 | 2026-07-14 19:05 | 2026-07-13 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-26 | 2026-06-25 18:40 | Site is RTMI | 2026-06-14 | 2026-06-16 12:30 | 1045027 | 188104 | 1166712.1638 | 196989 | 0 | 0 | 1166712.1638 | 196989 | 2026-06-25 12:26:39 +0530 | Divya Rahangdale | Some Image was uploaded | 2026-06-23 12:18:29 +0530 | Anjali Singh | Some Image was uploaded | 2026-06-23 11:50:48 +0530 | Anjali Singh | DCM: dcm recording was not recorded as the dcm was taken on MICL site . due to network and laptop charging issue. | 2026-06-26 | 2026-06-25 18:59 | 2026-07-09 | 2026-07-08 11:48 | Under Construction | 2026-07-04 | 2026-06-18 | 133313 | Ravi Roy
20600 | Turnkey | 2026-06-01 | G. V Govarthini | Legacy saviero | BNG - HRBR | No Estimate | [8 empty] | Kaminahal Rahiman |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-14 | 2026-06-16 14:26 | 2026-07-12 |  | 2026-07-18 |  | 2026-07-22 |  | 2026-07-29 |  | 2026-08-05 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-16 |  | 2026-07-17 | [5 empty] | 2026-07-23 |  | 2026-07-31 |  | 2026-08-01 |  |  |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-11 | [6 empty] | 2026-08-29 |  | 2026-09-07 |  | 2026-09-06 |  | 2026-09-07 |  | 2026-09-08 |  | 2026-09-10 |  |  |  | 2026-10-02 |  | 2026-10-04 |  | 2026-10-05 | [5 empty] | 2026-08-09 |  | 2026-07-18 |  | Unknown | 2026-06-14 | 2026-06-16 13:09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-16 14:41:40 +0530 | Losii Athisa | Some Image was uploaded | [6 empty] | 2026-07-23 |  | 2026-07-30
20601 | Turnkey | 2026-06-01 | Suraj Saini | kanakia Beverly heights | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 1016746 | 137684 | 1376843 | 0 | 0 | 3 | 0 | 0 | 65665 | 439540 | 373857.2 |  |  | 2026-06-16 | 2026-06-21 13:25 | 2026-06-20 | 2026-06-21 13:30 | 2026-07-12 | 2026-07-12 23:53 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-12 | 2026-07-13 | 2026-07-13 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-16 | 2026-06-20 15:31 | 1166816 | 210027 | 0 | 0 | 0 | 0 | 1155938.64 | 195164 | 2026-07-14 18:35:35 +0530 | Sanskruti Yadav |  | 2026-07-12 23:49:10 +0530 | Khushi Khandelwal |  | 2026-06-21 13:24:37 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-07-20 |  | 2026-07-27
20602 | Turnkey | 2026-06-01 | Ayaz | Independent House | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 2775851 | 9999 | 0 | 0 | 0 | 29 | 0 | 267586 | 277585 | 1159473 | 1061208 |  |  | 2026-06-14 | 2026-06-16 15:52 | 2026-06-17 |  | 2026-06-21 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-06-21 |  | 2026-06-22 |  | 2026-06-22 |  | 2026-06-23 | [5 empty] | 2026-06-29 |  | 2026-07-07 |  | 2026-07-08 |  |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-24 |  | Unknown | 2026-06-14 | 2026-06-16 15:39 | 0 | 0 | 0 | 0 | 0 | 0 | 2352416 | 423435 | 2026-06-16 15:53:03 +0530 | Janvi Nagdeo | Some Image was uploaded | [6 empty] | 2026-06-29 |  | 2026-07-06
20603 | Turnkey | 2026-06-01 | Sandeep Sonam Nayak | Prestige City | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1258250 | 175811 | 1758111 | 0 | 0 | 22 | 0 | 0 | 75839 | 522922 | 483677.6 |  |  | 2026-06-16 | 2026-06-16 17:27 | 2026-06-16 | 2026-06-16 19:23 | 2026-06-20 | 2026-06-21 16:03 | 2026-07-17 |  | 2026-10-07 |  | 2026-10-14 |  | 2026-06-21 | 2026-06-22 18:33 | 2026-06-22 | 2026-06-22 20:05 | 2026-06-22 | 2026-06-23 15:25 | 2026-07-04 | 2026-07-04 19:04 |  |  |  |  | 2026-07-18 |  | 2026-10-09 |  | 2026-10-10 |  |  |  | 2026-10-17 |  | 2026-10-18 |  | 2026-10-19 |  | 2026-10-20 | [6 empty] | 2026-11-07 |  | 2026-11-16 |  | 2026-08-12 |  | 2026-11-16 |  | 2026-11-17 |  | 2026-11-19 |  |  |  | 2026-12-11 |  | 2026-12-13 |  | 2026-12-14 | [5 empty] | 2026-10-18 |  | 2026-07-13 |  | Unknown | 2026-06-16 | 2026-06-16 17:24 | 1489924 | 268186 | 0 | 0 | 0 | 0 | 1445225.432 | 238635 | 2026-07-14 18:03:47 +0530 | Purva Shiravle | Foyer combination of wall beadings discussed and finalized Dining Combination of fluted panels added Living room Combination of fluted panel, wall beadings design discussed for sofa backwall (yet to be finalized) Master bedroom Addition of tall unit beside bed Wall concept - combination of wall beading and wall light Wall ledges descoped Bedroom 2 1.Pooja unit - addition of steps in pooja unit 2.Internal of pooja unit discussed - OM CNC cutting required 3.pooja unit shutter required in glass and bells combination as per reference Guest bedroom 1.Wallconcept - beading on left side of bed required 2.ledges descoped Bathrooms 1.need sliding shower partition - yet to be confirm from backend team 2.single door vanity units converted to double door | 2026-07-09 15:08:58 +0530 | Purva Shiravle | Foyer 1.Shoe rack - descoped 2.wall concept - option needed Dining 1.Arrangement and placement of units decided 2.addition of black tinted glass in tall unit Living room 1.Addition of glass flap down units and drawer unit size increased accordingly 2.addition of metal fabrication and shelves width increased Kitchen 1.addition of 1 open unit below wall unit 2.addition of glass unit in service platform instead of solid shutter unit 3.tambour unit size increased 4.addition of wicker baskets 5. placement of sink unit changed from middle to left side 6.addition of cylinder unit instead of shutter shelf unit in cook top counter Master bedroom 1.addition of iron pullout in wardrobe 2.placement of furniture finalised 3. need hanging light provision near bed 4.addition of ledges near bedroom foyer Guest bedroom No change in design , will be procceeding as per cdp Kids room 1.Addition of pooja unit - need some references with costing in next discussion 2.study wall unit to be kept as per initial discussion Bathrooms Vanity and glass partition placement discussed and finalised Open points for next discussions: 1. wall concepts and quote discussion According to current scope of work | 2026-06-23 19:11:54 +0530 | Swati Rathod | DINING: - one tall unit to be removed - bottom and wall units to be added(crockery cum bar unit as reff) LIVING: -sofa back wall only one square beading @ centre for painting. - TV unit (tall unit to be removed and ledges to be added with metal fab) KITCHEN: - Spice Rack to be added on lift side of HOB wall below wall unit and ledges. MBR; - single tall unit (for used cloths) to be added next to tv - dresser shift to left side of bed Â GBR: - Ledges to be added @ left side of window wall OFFICE ROOM: - Pooja unit to be removed. - study unit bottom panel to be removed. | 2026-07-18 |  | 2026-10-08 |  | Under Construction | 2026-10-31 | 2026-06-20 | 175811 | Ravi Roy
20604 | Turnkey | 2026-06-01 | Sangeeta Lavti | myhna Meadows | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 2219655 | 9999 | 0 | 0 | 0 | 26 | 0 | 211967 | 221966 | 898535 | 877188.8 |  |  | 2026-06-14 | 2026-06-16 17:59 | 2026-06-16 | 2026-06-18 16:38 | 2026-06-19 |  | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-06-19 |  | 2026-06-20 |  | 2026-06-20 |  | 2026-06-21 | [5 empty] | 2026-06-27 |  | 2026-07-05 |  | 2026-07-06 |  |  |  | 2026-07-13 |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 | [6 empty] | 2026-08-03 |  | 2026-08-12 |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-15 |  |  |  | 2026-09-06 |  | 2026-09-08 |  | 2026-09-09 | [5 empty] | 2026-07-14 |  | 2026-06-22 |  | Unknown | 2026-06-14 | 2026-06-16 17:59 | 0 | 0 | 0 | 0 | 0 | 0 | 1881063 | 338591 | 2026-06-26 12:33:20 +0530 | Tiwari Sandhya | Some Image was uploaded | 2026-06-20 10:58:47 +0530 | Priyamvada PV | Some Image was uploaded | 2026-06-20 10:58:09 +0530 | Priyamvada PV | All WR to be made 8'H, lofts 2.5'H TV unit to be fixed on panel done with level to stairs (with pulout storage 3 door on left space) - custom work KitchenÂ Blind corner unit below BF counter and tall glass unit above till ceiling Wall microwave unit 3 Wall tinted glass storage to right of M/W which will be to right of tall glass door single Ledge to right of chimney Window above hob is 1.5'H Blind corner base on right of hob unit to be facing dining Oil pullout to be 8"W Hob unit to beÂ 2.5'W 2 tandem drawer unit on left wall to be added sink unit to be made 1100mmW as Double bowl sink size is 38"W Pooja with top open bottom storage- facing crockery Crockery will be tall unit with bottom drawers & top glass fluted shutters GBR - Bottom drawers 2 nos for wardrobe of 3.5'W to be added Dresser to be shifted facing door KBR Study base to be made 5.5'W with CNc cutout 2 wider wall shelves 5.5'WÂ 2 nos with CNC cutout KBR WR - 1'W open unit with 4 door wardrobe , no bottom drawers Dresser drawer not required, full length mirror panel of 3'W MBR 2 door wardrobe to be changed to separate single door wardrobes for cosmetic storage, dresser next to wardrobe single door WR of less depth on front with open unit behind next to mirror study room Remove left ledges, metal fabrication Increase study equally , make wall units with single glass shutter on extreme ends with ledges between | 2026-06-27 |  | 2026-07-04
20605 | Turnkey | 2026-06-01 | Vijay Gurwada Gurwada | Mahalaxmi Minerva | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | DCM Due | 3801937 | 9999 | 0 | 0 | 0 | 29 | 0 | 370195 | 380194 | 1520775 | 1520774.8 |  |  | 2026-06-16 | 2026-06-16 18:06 | 2026-06-16 | 2026-06-16 23:40 | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-16 | 2026-06-16 18:03 | 0 | 0 | 0 | 0 | 0 | 0 | 3221981 | 579956 | 2026-06-30 13:18:55 +0530 | Rishika Malviya | CDP: Cx will come for re-discussion on 1st of july as there were some areas left for the discussion with the commercials | 2026-06-30 13:17:08 +0530 | Rishika Malviya | Some Image was uploaded | 2026-06-19 11:04:49 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-07-06 |  | 2026-07-13
20606 | Sub Project |  | Suhas D S | Urban Temple Bell | BNG - HSR |  | Rajasekar Ranganathan | Abhinandan K S | Kowshik |  |  | Sachin I Betageri | Ranjith Kumar | Murali S |  |  | Active | Production | 100% Payment | 12800 | 0 | 0 | 0 | 12800 | 2 | 0 | 0 | 0 | 0 | 12800 |  |  | 2026-06-16 | 2026-06-26 15:18 | 2026-06-17 | 2026-06-26 15:18 | 2026-06-26 | 2026-06-26 15:18 | 2026-06-27 | 2026-06-26 15:19 | 2026-06-27 | 2026-06-26 15:21 | 2026-06-27 | 2026-06-26 15:22 | 2026-06-26 | 2026-06-26 15:18 | 2026-06-27 | 2026-06-26 15:18 | 2026-06-26 | 2026-06-26 15:18 | 2026-06-27 | 2026-06-26 15:19 |  |  |  |  | 2026-06-26 | 2026-06-26 15:20 | 2026-06-27 | 2026-06-26 15:21 | 2026-06-27 | 2026-06-26 15:21 |  |  | 2026-06-27 | 2026-06-26 15:24 | 2026-06-27 | 2026-07-03 16:44 | 2026-07-04 | 2026-07-03 19:32 | 2026-07-04 | 2026-07-03 19:32 |  |  |  |  | 2026-07-07 14:37 | 2026-07-10 | 2026-07-10 22:14 | 2026-07-15 | 2026-07-13 17:57 | 2026-07-14 |  | 2026-07-13 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-03 |  | 2026-08-04 | [5 empty] | 2026-07-03 | 2026-07-03 19:32 | 2026-06-27 | 2026-06-26 15:19 | Unknown | 2026-06-16 | 2026-06-26 15:18 | 0 | 0 | 0 | 0 | 10847 | 1952 | 10847 | 1952 | [9 empty] | 2026-06-27 | 2026-06-26 15:20 | 2026-06-27 | 2026-06-26 15:21
20609 | Turnkey | 2026-06-01 | Chetan Kumar | Independant House | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Pulivarthi Nirosha |  | Active | Prospect | 10% Payment | 1214470 | 9999 | 1214470 | 0 | 0 | 21 | 0 | 111448 | 121447 | 485788 | 485788 |  |  | 2026-06-16 | 2026-06-16 19:28 | 2026-06-19 | 2026-06-23 19:30 | 2026-06-26 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-06-16 | 2026-06-16 19:22 | 1029212 | 185258 | 0 | 0 | 0 | 0 | 1029212 | 185258 | 2026-06-23 20:10:56 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-23 20:08:58 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-23 11:26:39 +0530 | Aparna | RGM is pending cx connected for 5mins over the call, inform about requirements . CX : CHETAN BHK :7bhk Budget : 12L Prof: Business 3bedroom wardrobe , Bay window , Dresser Daughters bedroom : 2 wardrobes required 1walkin sliding wardrobe - 12ft widthswing wardrobe - 15ft widthBay window GBR : 10ft Sliding wardrobe with dresser Son bedroom : swing wardrobe 6ft | 2026-07-04 |  | 2026-07-11
20613 | Turnkey | 2026-06-01 | Arneeta Pardeshi | assetz sohos and sky | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | 10% Payment | 2306033 | 9999 | 0 | 0 | 0 | 25 | 0 | 220604 | 230603 | 968603 | 876223.2 |  |  | 2026-06-16 | 2026-06-17 13:30 | 2026-06-16 | 2026-06-18 11:57 | 2026-06-20 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-06-20 |  | 2026-06-21 |  | 2026-06-21 |  | 2026-06-22 | [5 empty] | 2026-06-28 |  | 2026-07-06 |  | 2026-07-07 |  |  |  | 2026-07-14 |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 | [6 empty] | 2026-08-04 |  | 2026-08-13 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-16 |  |  |  | 2026-09-07 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | 2026-07-15 |  | 2026-06-23 |  | Unknown | 2026-06-16 | 2026-06-16 19:55 | 0 | 0 | 0 | 0 | 0 | 0 | 1954265 | 351767 | 2026-06-18 12:36:02 +0530 | Losii Athisa | Some Image was uploaded | 2026-06-18 12:05:31 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-18 12:04:28 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-28 |  | 2026-07-05
20614 | Turnkey | 2026-06-01 | Vaishali Trivedi | Royal view apartment | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | DCM Due | 1406385 | 9999 | 0 | 0 | 0 | 22 | 0 | 130640 | 140639 | 562554 | 562554 |  |  | 2026-06-13 | 2026-06-23 12:25 | 2026-06-26 | 2026-06-26 11:43 | 2026-06-20 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-07-07 |  | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-07-02 |  | Unknown | 2026-06-13 | 2026-06-17 18:44 | 0 | 0 | 0 | 0 | 0 | 0 | 1191852 | 214533 | 2026-06-18 18:04:22 +0530 | Keerthan M | DCM: Mr. shubanshu 3BHK Living - Pooja unit with TV unit - L shape sofa -dining kitchen partition - wall detailing Dining - 6 seater dining - crockery unit Kitchen - fridge - tall unit - dish washer - bottom, top, loft - breakfast counter Bedroom 1Â - single bed - wardrobeÂ - study unit Bedroom 2 - Kids bedroom - queen bed - wardrobeÂ - study unit Â Master bedroom - King bed - wardrobe - work station - dresser | 2026-06-17 11:38:04 +0530 | Losii Athisa | Some Image was uploaded |  |  |  | 2026-07-07 |  | 2026-07-14
20617 | Turnkey | 2026-06-01 | Khyati Jay Raithatha | sattva op us | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Design | 20% Payment | 759893 | 109999 | 1090112 | 0 | 0 | 3 | 0 | 0 | 41980 | 320288 | 287626 |  |  | 2026-06-16 | 2026-06-23 12:50 | 2026-06-29 | 2026-06-29 13:36 | 2026-07-02 | 2026-07-02 16:21 | 2026-07-12 | 2026-07-12 18:38 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-30 | 2026-06-27 15:51 | 2026-07-03 | 2026-07-02 16:25 | 2026-07-02 | 2026-07-02 18:25 | 2026-07-08 | 2026-07-08 16:02 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-09 | 2026-07-12 18:21 | Site is RTMI | 2026-06-16 | 2026-06-17 11:56 | 923824 | 166288 | 0 | 0 | 0 | 0 | 901965.7448 | 148930 | 2026-07-08 16:00:28 +0530 | Rajeshwari S | Welcome call done along with Designer Client wanted Sales designer Rituparna to be available for first meeting, it was not informed that the next meetings will be done by milestone designer. IM to be scheduled and informed to client by designer Client wanted to close the designs at the earliest. site is ready for CM Client is aligned for 10% payment. | 2026-07-02 18:24:20 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession: End of July or 1st week of August Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Tentatively scheduled for (5th July) * DEM 1 â€“ Tentatively scheduled for (12th July ) * 10% Payment Stage â€“ will close after finalizing the layout * B2C - Self * Civil work - no Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Special Offer (20000) Free Shoerack Offer Laminate Upgrade Offer - June 26 Design fee waiver (5%) PM fee waiver (5%) May'26 100% GST waiver Final Closing Value Discussed: 7,59,893 Checklist terms - descoping and agreement terms are cleared | 2026-07-02 18:01:29 +0530 | Athul Ajaykumar | OB Initiated â€“ Client asked to connect back by 6:10pm (Dialled from official number) | 2026-07-13 | 2026-07-12 18:52 | 2026-07-19 |  | Under Construction | 2026-08-09 | 2026-06-23 | 109999 | Ravi Roy
20618 | Turnkey | 2026-06-01 | Namadeva Bhatar | Eon one | MUM - GOR | Yes | [8 empty] | Ashutosh Singh |  | Active | Prospect | DCM Due | 1687821 | 9999 | 0 | 0 | 0 | 28 | 0 | 158783 | 168782 | 682892 | 667364.8 |  |  | 2026-06-17 | 2026-06-17 13:20 | 2026-06-17 | 2026-06-17 14:00 | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-06-17 | 2026-06-17 13:19 | 0 | 0 | 0 | 0 | 0 | 0 | 1430357 | 257464 | 2026-06-30 18:08:43 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-06-22 20:09:27 +0530 | Pratima Kajwe | DCM: MOM Customer and Project Profile1. Name of the customer Namdev Bhatar, Sudeep, Geeta, Bhagya, Mother 2. Profession Astrologer, 3. Project Name/Tower Name/Flat Number Near Siddhivinayak temple 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK 5. Site Access Date 2026-08-31 6. Possession Date 2026-08-31 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 1000000 Customer Preferences8. Who will be living in the house? Elderly Members, Joint Family 9. What activities do you usually prefer at your home ? Family Bonding 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] Vaastu 11. Mention basic vastu principles agreed for integration in design, if any 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) In each room Upload reference images 14. Any absolute no-go styles colours or materials No dark colors, 15. Do you have any existing furniture that must be accommodated? No 13. Do you want the design to reflect any personal story, cultural influence, or special memory Open to ideas ThemeAbstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial PatternsPlease select a maximum of 2 patterns of your choice TexturesPlease select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting1. Choose your desired ambience What kind of lighting do you prefer? Color palettesPlease select a maximum of 2 color palettes of your choice Entrance & Foyer1. Any must-haves? Shoe rack, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required No Dcor & Living Room1. Whats the primary use of your living room? Multipurpose, TV Focus 2. Must-have furniture or features? TV unit, Coffee table, Puja unit, Statement Wall/ Feature, Sofa 3. Choose your decor inspirations Plants, Artwork 4. False ceiling required Yes Dining & Kitchen1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen No Bedrooms1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Sliding 3. Master Bedroom - Additional units Bookshelf , Dresser, TV unit, Study Table 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility Parents 6. Bedroom 1 - Bed Type Storage 7. Bedroom 1 - Wardrobe style Sliding 8. Bedroom 1 - Additional units Dresser , TV unit 9. False Ceiling Required - Bedroom 1 Yes 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms1. Preferred vanity style 2. What do you prefer? 3. What are your requirements for Utility Area? NA Balcony & Outdoor1. How do you intend to use your balcony? Planters 2. Outdoor Mood How do you intend to use the utility Cloths Drying Miscellaneous1. Timeline related commitment made by Bonito, if any 2. Other commitments made by Bonito to customer, if any 3. What are offers committed to customers? 4. Move-in date confirmed with customer 5. Any special occasion mentioned by the customer wrt handover date 6. Additional Requirements (Mention any requirements from customer not covered in the form) Bed with storage and curved corners and lights below it and all sizes in King size. Measurement would be allowed before possession. Kitchen space to be utilised for appliances and fridge to be kept outside the kitchen along with crockery unit. 23rd June - 10:30 am 7. Please specify the designers estimated project budget based on the scope of work, aligned with the customers requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 1500000 | 2026-06-17 13:59:11 +0530 | Pratima Kajwe | Some Image was uploaded | 2026-07-05 |  | 2026-07-12
20619 | Turnkey | 2026-06-01 | Aruna C | puneeth rajkumar housing complex | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | 10% Payment | 1496963 | 9999 | 0 | 0 | 0 | 21 | 0 | 139697 | 149696 | 635577 | 561993.2 |  |  | 2026-06-17 | 2026-06-24 13:16 | 2026-06-18 | 2026-06-24 14:59 | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-06-17 | 2026-06-24 13:15 | 0 | 0 | 0 | 0 | 0 | 0 | 1268612 | 228350 | 2026-06-25 10:32:34 +0530 | Priyamvada PV | Some Image was uploaded | 2026-06-24 21:20:55 +0530 | Priyamvada PV | MBR- HB on east facing WR on west wall (sliding WR), with dresser on right False ceiling for Living, Dining, MBR, KBR Granite for kitchen, utility to be removed Kitchen wall units in acrylic required | 2026-06-23 15:18:42 +0530 | Ravikiran K | Client name - Arunan C Location - kadubegere cross Budget - 15 lakhs Individual house 3 People staying Wife, Husband, Son and parents sometimes will be staying Husband and wife both working Son is studying 12th Kannada speaking customer | 2026-07-05 |  | 2026-07-12
20620 | Sub Project |  | Sripriya Govindarajan / Ranganath | Govinanu jodidhar atlantis | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | Arun Kumar | Arun Kumar | Banka H Suthar | Saddam Hussain Z M | Murali S |  | Vishwa Hiremath | Active | Preproduction | Procurement | 258251 | 154951 | 0 | 0 | 258251 | 7 | 0 | 0 | 0 | 0 | 103300 |  |  | 2026-06-17 | 2026-06-19 16:25 | 2026-06-18 | 2026-06-19 16:25 | 2026-06-19 | 2026-06-19 16:25 | 2026-06-20 | 2026-06-19 16:26 | 2026-06-20 | 2026-06-19 16:27 | 2026-06-20 | 2026-06-19 16:28 | 2026-06-19 | 2026-06-19 16:25 | 2026-06-20 | 2026-06-19 16:25 | 2026-06-19 | 2026-06-19 16:25 | 2026-06-20 | 2026-06-19 16:25 |  |  |  |  | 2026-06-19 | 2026-06-19 16:26 | 2026-06-20 | 2026-06-19 16:27 | 2026-06-20 | 2026-06-19 16:27 |  |  | 2026-07-01 | 2026-07-03 13:49 | 2026-07-04 | 2026-07-04 11:45 | 2026-07-05 | 2026-07-04 15:26 | 2026-07-05 | 2026-07-07 19:25 |  |  |  |  | 2026-07-08 16:17 | 2026-07-13 |  | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-25 |  |  |  | 2026-08-16 |  | 2026-08-18 |  | 2026-08-19 | [5 empty] | 2026-07-04 | 2026-07-08 16:16 | 2026-06-20 | 2026-06-19 16:26 | Unknown | 2026-06-17 | 2026-06-19 16:25 | 0 | 0 | 0 | 0 | 218856 | 39394 | 218856 | 39394 | [9 empty] | 2026-06-20 | 2026-06-19 16:26 | 2026-06-20 | 2026-06-19 16:27
20623 | Turnkey | 2026-06-01 | THILAK KUMAR | Ant meadows | BNG - HRBR | Yes | [8 empty] | Kaminahal Rahiman |  | Active | Prospect | 10% Payment | 3913749 | 9999 | 0 | 0 | 0 | 22 | 0 | 381376 | 391375 | 1798670 | 1332328.8 |  |  | 2026-06-17 | 2026-06-17 19:04 | 2026-06-18 | 2026-06-20 13:56 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-17 | 2026-06-17 18:42 | 0 | 0 | 0 | 0 | 0 | 0 | 3316736 | 597012 | 2026-06-23 12:23:33 +0530 | Yogesh Patidar | Some Image was uploaded | 2026-06-23 11:52:13 +0530 | Palak Thakur | DCM: recording updated in drive | 2026-06-23 11:52:02 +0530 | Palak Thakur | DCM: Title: Design Consultation Meeting Project No: 20623 Client: THILAK KUMAR Hi, Minutes of Meeting held on Date: <17/06/26> Attendees:palak Discussion:rgm Based on <17/06/26> meeting, below is a list of all the requirements that were discussed during the meeting: 20623 - THILAK KUMAR possession in handÂ handover - October dusshera budget 10-12 lakhsÂ foyer - design wallÂ kitchenÂ base + wall + loftÂ base c shapeÂ wall + loft l shapeÂ handless kitchen 2door fridge micro + otg unit dining 4-6 seaterÂ crockery unitÂ living roomÂ swing + sofa setÂ tv unit in frontÂ tv 75" minimal storage sound systems may comeÂ pooja roomÂ corner storageÂ seating pooja unit 2 step no storageÂ master bedroomÂ king bed wardrobe + loftÂ front small storage tableÂ corner single shutter wardrobe with no internalsÂ walk in wardrobeÂ wardrobe + loft + dresserÂ 1 base vanity in master washroom and glass partition kids bedroomÂ bunk bedÂ slideÂ wardrobe + loftÂ guest bedroomÂ sliding wardrobe + loftÂ cdp 21th sunday 3pmÂ | 2026-07-01 |  | 2026-07-08
20625 | Turnkey | 2026-06-01 | Darshan Patil | Adarsh Premia | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP | [5 empty] | Muralikrishna Udupi |  | Active | Design | DEM1 | 1794292 | 236864 | 2368636 | 0 | 0 | 22 | 0 | 0 | 121994 | 744200 | 691233.6 |  |  | 2026-06-17 | 2026-06-17 19:02 | 2026-06-18 | 2026-06-18 18:45 | 2026-06-21 | 2026-06-21 15:50 | 2026-07-14 |  | 2026-07-12 |  | 2026-08-27 |  | 2026-06-21 | 2026-06-22 12:52 | 2026-06-22 | 2026-06-23 12:25 | 2026-06-23 | 2026-06-23 18:23 | 2026-07-07 | 2026-07-07 17:17 |  |  |  |  | 2026-07-15 |  | 2026-08-22 |  | 2026-08-23 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 | [6 empty] | 2026-09-20 |  | 2026-09-29 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-02 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-27 | [5 empty] | 2026-08-31 |  | 2026-07-10 | 2026-07-07 18:27 | Site is RTMI | 2026-06-17 | 2026-06-17 19:01 | 2007319 | 361317 | 0 | 0 | 0 | 0 | 1955990.6786 | 322972 | 2026-07-07 18:28:26 +0530 | Aishwarya C | possession is in august false ceiling is done by builder the measurements will get affected in cross measurement | 2026-07-07 17:19:28 +0530 | Abhinandan K S | Possession expected by end of August 2026. Customer wants handover by end of November 2026. Clearly explained the timeline, offers and process. Design meetings to be aligned with the Customer. Customer is aligned for next 10% payment post closing the DEM phase 1. Project will be on hold after DEM 1 till the possesion. | 2026-06-23 18:21:51 +0530 | Athul Ajaykumar |  | 2026-07-15 |  | 2026-07-13 |  | Under Construction | 2026-08-31 | 2026-06-21 | 236864 | Ravi Roy
20626 | Turnkey | 2026-06-01 | Ashok Sonawane | swastik platinum | MUM - GOR | Yes | [8 empty] | Sanskruti Yadav |  | Active | Prospect | 10% Payment | 1423165 | 108999 | 0 | 0 | 0 | 0 | 0 | 33318 | 142317 | 623314 | 515218.4 |  |  | 2026-06-17 | 2026-06-19 11:11 | 2026-07-11 | 2026-07-15 00:25 | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-08-08 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-19 |  | 2026-07-20 | [5 empty] | 2026-07-26 |  | 2026-08-03 |  | 2026-08-04 |  |  |  | 2026-08-11 |  | 2026-08-12 |  | 2026-08-13 |  | 2026-08-14 | [6 empty] | 2026-09-01 |  | 2026-09-10 |  | 2026-09-09 |  | 2026-09-10 |  | 2026-09-11 |  | 2026-09-13 |  |  |  | 2026-10-05 |  | 2026-10-07 |  | 2026-10-08 | [5 empty] | 2026-08-12 |  | 2026-07-21 |  | Unknown | 2026-06-17 | 2026-06-19 11:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1206072 | 217093 | 2026-06-19 11:10:59 +0530 | Sanskruti Yadav | Some Image was uploaded | 2026-06-17 19:05:31 +0530 | Unknown | About the Customer **2BHK Vikhroli Property Details** Customer is looking for interior design for a 2BHK flat in Vikhroli, Tagore Nagar, with possession expected by the end of June. The estimated cost for a fully furnished setup is â‚¹10-12 lakhs. **Experience Center Visit Scheduled** Customer prefers to visit tomorrow around 3:00 PM after work at LIC to the Andheri experience center. **Budget Discrepancy for 2BHK** Customer has an estimated budget of â‚¹7-8 lakhs for their 2BHK, while the agent indicated the typical range is 8-10 lakhs. **Online Review Concerns Addressed** Customer was initially hesitant due to negative online reviews but was reassured by agent's explanation about Bonito's ISO certification and association with Gauri Khan. **Agent to Confirm Visit Details** Agent Swapnali to arrange complimentary pick-up/drop for the visit and send her WhatsApp number. |  |  |  | 2026-07-26 |  | 2026-08-02
20629 | Turnkey | 2026-06-01 | Jayalakshmamma | 4bhk independent house | BNG - HRBR | Yes | [8 empty] | Kaminahal Rahiman |  | Active | Prospect | DCM Due | 2473312 | 9999 | 0 | 0 | 0 | 27 | 0 | 237332 | 247331 | 1008281 | 970368.4 |  |  | 2026-06-18 | 2026-06-18 15:09 | 2026-07-08 | 2026-07-08 13:07 | 2026-06-28 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-07-11 |  | 2026-07-12 |  | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-07-19 |  | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-14 |  | Unknown | 2026-06-18 | 2026-06-18 15:07 | 0 | 0 | 0 | 0 | 0 | 0 | 2096027 | 377284 | 2026-07-08 13:02:39 +0530 | Priyanka Gs | DCM: Corridor: Shoe rack storage unit is required. Foyer Area: Storage unit along with feature wall concepts to be explored. Living Room: TV unit design with wall treatment concepts. Formal Living area to include a dedicated TV unit. Dining Area: Partition design between spaces. Decorative wall paneling concepts to be incorporated. Pooja Unit: Dedicated pooja unit to be designed. Ceiling Design: Ceiling paneling concepts to be developed for key areas. Study Area: Provision for a functional study space. Concealed Storage: Additional hidden storage solutions to be explored wherever feasible. KitchenComplete modular kitchen design with overhead loft storage. Bedroom 1Sliding wardrobe. Loft storage. Dresser unit. Cot design. Bedroom 2Sliding wardrobe. Loft storage. Dresser unit. Cot design. Bedroom 3Sliding wardrobe. Loft storage. Dresser unit. Cot design. Bedroom 4Wardrobe. Loft storage. | 2026-06-18 14:07:18 +0530 | Unknown | About the Customer **Property and Interior Needs** The customer owns a 4 BHK duplex independent house near Devanahalli, with construction and finishing complete, and is seeking interior design services for pending interior work. **Budget Hesitation** The customer is hesitant to provide a budget, describing themselves as farmers who built the house with difficulty and wish to stay within their means, seeking a 'low budget' solution. **Company Starting Price** Bonito Designs' starting price is â‚¹7 lakhs for a 2 or 3 BHK, and a significantly higher budget is needed for a 4 BHK for quality work. **Internal Review for Budget Estimate** Agent will discuss with the team to provide a rough idea of designs and possibilities based on the customer's potential budget. |  |  |  | 2026-07-19 |  | 2026-07-26
20633 | Turnkey | 2026-06-01 | Pramod Waghmare | Shristi Residency | MUM - GOR | Yes | Rajnish Mishra | Christopher Macwan | Safalta Karkera | [5 empty] | Harshaan Tiku |  | Active | Design | DEM1 | 1151692 | 162451 | 1624507 | 0 | 0 | 21 | 0 | 0 | 67887 | 495484 | 425870 |  |  | 2026-06-18 | 2026-06-18 17:44 | 2026-06-18 | 2026-06-21 19:03 | 2026-06-23 | 2026-06-23 12:51 | 2026-07-01 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-06-23 | 2026-06-23 15:25 | 2026-06-24 | 2026-06-24 00:14 | 2026-06-24 | 2026-06-24 14:12 | 2026-06-26 | 2026-06-26 11:10 |  |  |  |  | 2026-07-02 |  | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-27 |  | Unknown | 2026-06-18 | 2026-06-18 17:44 | 1378799 | 245707 | 0 | 0 | 0 | 0 | 1359412.462 | 213378 | 2026-06-26 11:09:31 +0530 | Christopher Macwan | Welcome call done. Initial measurement - Customer wants it to be done the earliest weekend and is fine with this weekend 27 or 28th June 2026. DEM Dates -Â DEM 1 - Customer wants DEM1 early weekend preferably 27th or 28th June 2026 DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-24 14:12:21 +0530 | Athul Ajaykumar |  | 2026-06-24 13:51:52 +0530 | Athul Ajaykumar | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM Tentatively scheduled for (This weekend) * DEM 1 Tentatively scheduled for (Next weekend) * 10% Payment Stage Tentatively scheduled for (3rd July 2026) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design Fee Waiver (2.5%) Free Hob & Chimney Offer Free Shoerack Offer Laminate Upgrade - Jun 26 Campaign 100% GST Waiver PM fee waiver (7.5%) Final Closing Value Discussed: 11,51,693 Checklist terms descoping and agreement terms are cleared Rejections: The client wants the handover from bonito by September 15 | 2026-07-02 |  | 2026-07-09 |  | RTMI |  | 2026-06-21 | 162451 | Ravi Roy
20636 | Sub Project |  | Leena Bhagwat /Mangesh Kadam | Giriraj | MUM - Thane |  | Asavari Vare | Divya Rahangdale | Sneha Kadam |  |  | Faraz Soudagar | Akshat Shrivastava | Murali S |  | Aakash Gaikwad | Active | Preproduction | Site Readiness 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-18 | 2026-06-30 16:48 | 2026-06-19 | 2026-06-30 16:48 | 2026-06-30 | 2026-06-30 16:48 | 2026-07-01 | 2026-06-30 16:49 | 2026-07-01 | 2026-06-30 16:50 | 2026-07-01 | 2026-06-30 16:51 | 2026-06-30 | 2026-06-30 16:48 | 2026-07-01 | 2026-06-30 16:48 | 2026-06-30 | 2026-06-30 16:48 | 2026-07-01 | 2026-06-30 16:48 |  |  |  |  | 2026-06-30 | 2026-06-30 16:49 | 2026-07-01 | 2026-06-30 16:50 | 2026-07-01 | 2026-06-30 16:50 |  |  | 2026-07-08 | 2026-07-08 17:05 | 2026-07-09 | 2026-07-09 16:10 | 2026-07-10 | 2026-07-09 16:34 | 2026-07-10 | 2026-07-09 16:34 | [5 empty] | 2026-07-28 |  | 2026-08-06 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-09 |  |  |  | 2026-08-31 |  | 2026-09-02 |  | 2026-09-03 | [5 empty] | 2026-07-09 |  | 2026-07-01 | 2026-06-30 16:48 | Unknown | 2026-06-18 | 2026-06-30 16:48 | 0 | 0 | 0 | 0 | 16309.22 | 0 | 16309.22 | 0 | [9 empty] | 2026-07-01 | 2026-06-30 16:49 | 2026-07-01 | 2026-06-30 16:50
20637 | Turnkey | 2026-06-01 | Sriram Subramaniam | Aris | BNG - HRBR | No Estimate | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-18 | 2026-06-26 12:52 | 2026-06-25 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-17 |  | 2026-09-15 |  | 2026-09-14 |  | 2026-09-15 |  | 2026-09-15 |  | 2026-09-19 |  |  |  | 2026-11-08 |  | 2026-11-09 |  | 2026-11-12 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-18 | 2026-06-18 18:18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-18 18:17:39 +0530 | Unknown | About the Customer **4 BHK Property Purchase** Customer is planning to purchase a 4 BHK apartment around 4000 sq. ft. with a budget of up to 80 lakhs, expecting complete interior solutions including a compact kitchen and all furnishings. **Property Finalization Pending** Property purchase not finalized yet but expected within the week. Property is in Kalyan Nagar (HRBR), near the experience center. **Visit Experience Center** Customer agreed to visit the HRBR experience center with family once property is finalized. **Agent to Send Details** Agent to send videos and contact details for the HRBR experience center. | [6 empty] | 2026-07-06 |  | 2026-07-13
20638 | Sub Project |  | Hemali Rathod | 34park estate | MUM - GOR | Yes | Karan Chavda | Manzoor Shaikh | Safalta Karkera |  |  | Shashwat Joshi | Rizwan Mistry |  |  | Sunil Poojary | Active | Preproduction | 2D | 807862 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 498596 | 309266 |  |  | 2026-06-18 | 2026-07-07 14:27 | 2026-06-19 | 2026-07-07 14:27 | 2026-07-07 | 2026-07-07 14:28 | 2026-07-08 | 2026-07-07 14:29 | 2026-07-08 | 2026-07-07 14:30 | 2026-07-08 | 2026-07-07 14:33 | 2026-07-07 | 2026-07-07 14:28 | 2026-07-08 | 2026-07-07 14:28 | 2026-07-07 | 2026-07-07 14:28 | 2026-07-08 | 2026-07-07 14:28 |  |  |  |  | 2026-07-07 | 2026-07-07 14:29 | 2026-07-08 | 2026-07-07 14:31 | 2026-07-08 | 2026-07-07 14:32 |  |  | 2026-07-08 | 2026-07-11 14:07 | 2026-07-10 |  | 2026-07-12 |  | 2026-07-13 | [6 empty] | 2026-07-31 |  | 2026-08-09 |  | 2026-08-08 |  | 2026-08-09 |  | 2026-08-10 |  | 2026-08-12 |  |  |  | 2026-09-03 |  | 2026-09-05 |  | 2026-09-06 | [5 empty] | 2026-07-11 |  | 2026-07-08 | 2026-07-07 14:28 | Unknown | 2026-06-18 | 2026-07-07 14:27 | 0 | 0 | 0 | 0 | 0 | 0 | 684629 | 123233 | 2026-07-07 13:38:40 +0530 | Mohammed Lal | HOTO: | [6 empty] | 2026-07-08 | 2026-07-07 14:29 | 2026-07-08 | 2026-07-07 14:30
20641 | Turnkey | 2026-06-01 | Rashi Sahay | Disha Pursuit Of Sunshine | BNG - HRBR | Yes | Sanjay Kulkarni | Parasa Sri | Surabhi Ravichandran | [5 empty] | Raghavendra S | Vishwa Hiremath | Active | Preproduction | CM | 1574441 | 310189 | 2204068 | 0 | 0 | 2 | 0 | 0 | 0 | 634476 | 629776.4 |  |  | 2026-06-17 | 2026-06-23 12:52 | 2026-06-23 | 2026-06-23 16:06 | 2026-06-26 | 2026-06-26 15:43 | 2026-07-06 | 2026-07-05 11:42 | 2026-07-14 | 2026-07-13 10:57 | 2026-07-19 |  | 2026-06-26 | 2026-06-27 15:56 | 2026-06-27 | 2026-06-27 16:14 | 2026-06-27 | 2026-06-27 17:44 | 2026-06-28 | 2026-06-28 11:31 |  |  |  |  | 2026-07-05 | 2026-07-10 14:29 | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-06-29 | 2026-07-04 10:55 | Site is RTMI | 2026-06-17 | 2026-06-19 11:18 | 1867854 | 336213 | 0 | 0 | 0 | 0 | 1789864.178 | 295549 | 2026-06-28 13:06:39 +0530 | Rituparna Chakraborty | M.O.M of design meeting - 28.06.2026 1. TV unit needs to be re-designed , few references discussed . Rashi maam will send a reference from her friend's placeÂ 2. Puja is not in our original scope , but as discussed , we will come up with some design for the sameÂ 3. Kitchen will be how we have discussedÂ 4. Bedrooms will be the same requirement wise . 5. Whole house colour will be somewhere around those off-white , beige , brown , very few pop of colorÂ 6. False ceiling in living dining & MBR | 2026-06-28 11:30:01 +0530 | Parasa Sri | Welcome call done. Initial measurement is scheduled for - june 30 Cross measurement is planned for july 10th. expecting a handover by September. | 2026-06-27 17:43:08 +0530 | Sanjana Swami | Possession Status: RTMI Project handover date: 13th Oct 2026 Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * DEM 1 29th June to 9th July 2026 * 10% Payment Stage after 1st DEM *No civil work at site *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 17,64,197 Offers Discussed During the Call: Special Offer (20000) Laminate Upgrade - Jun 26 Campaign 100% GST Waiver PM fee waiver (5%) Design fee waiver (5%) Free Shoerack Offer Final Closing Value Discussed: 15,50,894 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-06 | 2026-07-05 11:48 | 2026-07-14 | 2026-07-13 18:58 | RTMI |  | 2026-06-26 | 220407 | Ravi Roy
20644 | Sub Project |  | AG Dixit | shobha dream Garden | BNG - HRBR |  | Hemalatha D | Parasa Sri | Surabhi Ravichandran | [7 empty] | Active | Design | 60% Payment | 35244 | 0 | 0 | 0 | 35244 | 18 | 0 | 0 | 0 | 21146 | 14097.6 |  |  | 2026-06-19 | 2026-06-26 17:48 | 2026-06-20 | 2026-06-26 17:48 | 2026-06-26 | 2026-06-26 17:48 | 2026-06-27 | 2026-06-26 17:49 | 2026-06-27 | 2026-06-26 17:50 | 2026-06-27 | 2026-06-26 17:52 | 2026-06-26 | 2026-06-26 17:48 | 2026-06-27 | 2026-06-26 17:48 | 2026-06-26 | 2026-06-26 17:48 | 2026-06-27 | 2026-06-26 17:48 |  |  |  |  | 2026-06-26 | 2026-06-26 17:49 | 2026-06-27 | 2026-06-26 17:51 | 2026-06-27 | 2026-06-26 17:51 |  |  | 2026-06-27 | 2026-06-26 17:53 | 2026-06-27 | 2026-06-27 13:01 | 2026-06-28 | 2026-06-27 14:57 | 2026-06-28 | [6 empty] | 2026-07-16 |  | 2026-07-25 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-28 |  |  |  | 2026-08-19 |  | 2026-08-21 |  | 2026-08-22 | [5 empty] | 2026-06-27 |  | 2026-06-27 | 2026-06-26 17:48 | Unknown | 2026-06-19 | 2026-06-26 17:47 | 0 | 0 | 0 | 0 | 29868 | 5376 | 29868 | 5376 | [9 empty] | 2026-06-27 | 2026-06-26 17:49 | 2026-06-27 | 2026-06-26 17:51
20648 | Turnkey | 2026-06-01 | Chetan | Myhna Medows | BNG - HSR | Yes | [8 empty] | Ravikiran K |  | Active | Prospect | DCM Due | 1840375 | 9999 | 0 | 0 | 0 | 21 | 0 | 174039 | 184038 | 784613 | 687686.8 |  |  | 2026-06-19 | 2026-06-24 15:27 | 2026-06-24 |  | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-19 | 2026-06-24 15:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1559640 | 280735 | 2026-06-30 11:57:59 +0530 | Saranya Thiyagarajan | CDP: No notes | 2026-06-30 11:57:01 +0530 | Saranya Thiyagarajan | CDP: https://teams.microsoft.com/l/meetup-join/19%3ameeting_ZDY3MjIzNTAtYTM5YS00OTAxLWFlYTItZTQ0NzRmMjdjMjY4%40thread.v2/0?context=%7b%22Tid%22%3a%22dd8d0223-8a42-433c-8f23-46c4f20f35be%22%2c%22Oid%22%3a%228a9becf1-636c-45c6-975e-d5c5d9904ca2%22%7d | 2026-06-26 17:24:37 +0530 | Ravikiran K | Client name - Chetan Project: Myhna Meadows Villa Interior Design Configuration: G+2 Villa Customer is planning for rental purpose Possession: This Week Family Members: 6 (Including Parents) Budget: 15 Lakhs according to requirements and mentioned to cx Client is relative of Ms. Sangeetha customer, if this particular customer is okay with budget and design, both the customers will go ahead. | 2026-07-06 |  | 2026-07-13
20653 | Turnkey | 2026-06-01 | Raveesh SB | independent house | BNG - HRBR | No Estimate | [8 empty] | Kushal S |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-18 | 2026-06-23 12:15 | 2026-06-19 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-06-18 | 2026-06-22 10:59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-25 12:59:55 +0530 | Yogesh Patidar | RGM MOM: Its a Indepnedant house and Rennovation Project( No Civil Changes, Only Existing Cabinets to be removed) 3 People will be staying Husband works for LIC Son- Own Business Living area: Fasle ceiling to be planned Tv unit with Base and tall unit and wall back design Entrance Panelling New sofa to be Planned Exisitng TV and Sound bar to be planned. Pooja Mandir- Only Paiting to be done Kitchen Exisitng Cabinets, tiles and Granite to be removed New Modular Kitchen with existing hob and chimney Frridge to be kept outside Master Bedroom- Wardorbe with loft Study with TV Bed position to be changes with existing bed Fasle ceiling Bedroom 2 Sliding wardrobe with loft with tinted finish false ceiling existing bed Dresser Bathromm- Wall unit Door to be changed Bugdet- Informed will be more than 10Lacs | 2026-06-20 13:09:05 +0530 | Unknown | About the Customer **Budget Mismatch for Renovation** Customer's budget of 6-8 lakhs for renovation is lower than the starting price of 7 lakhs for a 2BHK, with the property being independent and having rental units. **Customer Availability Blocked** Customer is hesitant to commit to a visit due to a busy schedule with weekend weddings and work. **Visit Logistics Offer** Agent offered to arrange cabs for the customer and their family to facilitate the visit. **Follow-up via WhatsApp and Decision Pending** Agent to send service and offer details via WhatsApp; customer will review schedule and inform about potential visit times. |  |  |  | 2026-07-05 |  | 2026-07-12
20655 | Turnkey | 2026-06-01 | Priyanka Mandavkar | Raymond 10X | MUM - Thane | Yes | Karuna Shinde | Anamika Dolai | Rushika More | [5 empty] | Nishtha Valawalkar |  | Active | Prospect | 10% Payment | 1700562 | 9999 | 1700562 | 0 | 0 | 22 | 0 | 160057 | 170056 | 737134 | 623315.2 |  |  | 2026-06-20 | 2026-06-20 14:00 | 2026-06-20 | 2026-06-20 16:53 | 2026-07-05 | 2026-07-07 12:35 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-07-15 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-10 |  | Unknown | 2026-06-20 | 2026-06-20 13:55 | 1443440 | 257122 | 0 | 0 | 0 | 0 | 1443440 | 257122 | 2026-07-07 12:55:56 +0530 | Hemant Sonar | Recap: 20655 - Design Consultation Meeting (DCM) with the customer 20 June ¦ Meeting ¦ Microsoft Teams | 2026-07-07 12:38:48 +0530 | Hemant Sonar | CDP is completed. net is not done. as the client already has another quotation of â‚¹11â€“12 lakhs and wants this project to be within the same budget. He also needs some time to discuss this with his parents. | 2026-07-07 12:37:26 +0530 | Hemant Sonar | Recap: 20655 - Celebrity Design Presentation (CDP) with the customer 05 July ¦ Meeting ¦ Microsoft Teams | 2026-07-15 |  | 2026-07-22
20656 | Turnkey | 2026-06-01 | Jharna | CoEvolve Florenza | BNG - HRBR | Yes | Ashiya Sanam | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Mohammed Rasick |  | Active | Design | DEM1 | 1477274 | 186999 | 1871203 | 0 | 0 | 12 | 0 | 0 | 108456 | 624738 | 557080.8 |  |  | 2026-06-20 | 2026-06-23 12:35 | 2026-06-22 | 2026-06-25 12:12 | 2026-06-27 | 2026-06-28 12:34 | 2026-07-13 |  | 2026-07-20 |  | 2026-07-27 |  | 2026-06-28 | 2026-06-30 14:56 | 2026-06-29 | 2026-06-30 15:49 | 2026-06-30 | 2026-07-03 20:35 | 2026-07-08 | 2026-07-08 16:33 |  |  |  |  | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-07-09 |  | Unknown | 2026-06-20 | 2026-06-20 14:01 | 1585765 | 285437 | 0 | 0 | 0 | 0 | 1527804.7918 | 265909 | 2026-07-14 17:18:11 +0530 | Rajeshwari S | Welcome call done along with Designer Non RTMI Project. Possession expected in Dec end. Soft possession in August Client is little busy - will update us on IM and 1st DM on 15th July. 10% payment will be done after 1st DM. Aligned with process. | 2026-07-03 19:48:28 +0530 | Mohammed Rasick | PFA the price protection approval email | 2026-07-02 12:20:52 +0530 | Bency Chacko | OB reject - Extended price protection approval required as client's possession is expected in December 2026 and she is uncertain if we builder allow to start interior work in next month (soft possession) | 2026-07-14 |  | 2026-07-21 |  | Under Construction | 2026-12-31 | 2026-06-26 | 186999 | Ravi Roy
20657 | Turnkey | 2026-06-01 | Vikram | Legacy saviero | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | 10% Payment | 2489353 | 319999 | 3332832 | 0 | 0 | 19 | 0 | 0 | 177872 | 1041931 | 949551.2 |  |  | 2026-06-20 | 2026-06-23 12:32 | 2026-06-21 | 2026-06-26 14:35 | 2026-06-29 | 2026-07-02 17:03 | 2026-07-01 |  | 2026-07-08 |  | 2026-07-15 |  | 2026-07-02 | 2026-07-04 13:43 | 2026-07-03 |  | 2026-06-25 |  | 2026-06-26 | [5 empty] | 2026-07-02 |  | 2026-07-10 |  | 2026-07-11 |  |  |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 |  | 2026-07-21 | [6 empty] | 2026-08-08 |  | 2026-08-17 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-18 |  | 2026-08-20 |  |  |  | 2026-09-11 |  | 2026-09-13 |  | 2026-09-14 | [5 empty] | 2026-07-19 |  | 2026-06-27 |  | Unknown | 2026-06-20 | 2026-06-20 14:08 | 2824434 | 508398 | 0 | 0 | 0 | 0 | 2713706.1279 | 448083 | 2026-06-26 17:37:43 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-26 17:36:05 +0530 | Alekhya Korada | Some Image was uploaded | 2026-06-26 17:34:49 +0530 | Alekhya Korada | Some Image was uploaded | 2026-07-02 |  | 2026-07-09 |  |  |  | 2026-06-26 | 9999 | Ravi Roy
20659 | Turnkey | 2026-06-01 | Ms.Snigdha Choudhary | Pavani Mariabilia | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1216086 | 164252 | 1642519 | 0 | 0 | 16 | 0 | 0 | 78965 | 486434 | 486434.4 |  |  | 2026-06-20 | 2026-06-20 15:25 | 2026-06-20 | 2026-06-23 12:18 | 2026-06-26 | 2026-06-27 11:29 | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-06-27 | 2026-06-27 12:01 | 2026-06-28 | 2026-06-28 13:14 | 2026-06-28 | 2026-06-29 18:55 | 2026-07-04 | 2026-07-04 19:07 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-18 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-07 |  | Unknown | 2026-06-20 | 2026-06-20 15:16 | 1391966 | 250553 | 0 | 0 | 0 | 0 | 1377425.994 | 227445 | 2026-06-30 16:03:44 +0530 | Maspi Das | Some Image was uploaded | 2026-06-30 15:49:34 +0530 | Maspi Das | Recap: 20659 - Celebrity Design Presentation (CDP) with the customer 26 June ¦ Meeting ¦ Microsoft Teams Recap: 20659 - Celebrity Design Presentation (CDP) with the customer 26 June ¦ Meeting ¦ Microsoft Teams Recap: 20659 - Celebrity Design Presentation (CDP) with the customer 26 June ¦ Meeting ¦ Microsoft Teams Recap: 20659 - Celebrity Design Presentation (CDP) with the customer 26 June ¦ Meeting ¦ Microsoft Teams | 2026-06-30 15:46:15 +0530 | Maspi Das | CDP notes 26.06.2026- TV unit changes- two shutters and one drawer and one open unit in between Note- Curve needs to be added on both edges of the TV Panel on open side Crockery unit- Wall unit height got increased Wallpaper Bevelled mirror Pooja unit Height increased Pooja unit 180 degree opening hinges (need to be added) Kitchen- One wall unit got added instead of Shelf Instead of Dishwasher 4' sink unit came *Dado tiles need to check* Utility- Wall units got added both sides MBR- Dresser unit size got increased Loft on top of Dresser tall unit got added | 2026-07-12 |  | 2026-07-19 |  | RTMI |  | 2026-06-26 | 164252 | Ravi Roy
20660 | Turnkey | 2026-06-01 | Samar Abbas Hussain Sayyed | MICL Aaradhya Parkwood | MUM - GOR | No Estimate | [8 empty] | Shoaib Shaikh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-20 | 2026-07-09 17:07 | 2026-07-08 | 2026-07-09 17:08 | 2026-06-28 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-20 | 2026-06-20 15:17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-09 15:17:45 +0530 | Priyanka Patel | 1. Name of the customer 20660 Samar Abbas Hussain Sayyed 2. Profession NA 3. Project Name/Tower Name/Flat Number MICL 4. Typology (1BHK, 2BHK, 3BHK, etc) 2BHK 5. Site Access Date 2026-08-31 6. Possession Date 2026-07-31 7. Please specify the interior design budget quoted by the customer (in INR Lakhs 100000 Customer Preferences 8. Who will be living in the house? Elderly Members, Joint Family, Nuclear Family, Couple 9. What activities do you usually prefer at your home ? Prayer, Pursuing Hobbies, Relaxing and Unwinding, Family Bonding, Hosting Guests, Working From Home 10. Mention external consultant by client [Ex - Civil, Vastu, Fengsui, Others etc.] YES 11. Mention basic vastu principles agreed for integration in design, if any YES 12. Any requirement of signature design feature or space in the house (Mention Details and Reference Images) YES Upload reference images 14. Any absolute no-go styles colours or materials NO DARK COLOURS 15. Do you have any existing furniture that must be accommodated? YES 13. Do you want the design to reflect any personal story, cultural influence, or special memory YES Theme Abstract Luxe Art Deco Revival Italian Mid century Japandi Neo Industrial Patterns Please select a maximum of 2 patterns of your choice Textures Please select a maximum of 2 textures ( wall treatment) of your choice Ambience & Lighting 1. Choose your desired ambience What kind of lighting do you prefer? Color palettes Please select a maximum of 2 color palettes of your choice Entrance & Foyer 1. Any must-haves? Shoe rack, Console, Seating, Safety Door 2. How would you like your entrance to feel? 3. False ceiling required Yes DÃ©cor & Living Room 1. Whatâ€™s the primary use of your living room? Entertaining guests, TV Focus 2. Must-have furniture or features? TV unit, Speakers, Coffee table, Display unit , Sofa 3. Choose your decor inspirations NA 4. False ceiling required Yes Dining & Kitchen 1. Any special furniture? Crockery unit 2. Must-have appliances? Microwave, Fridge, Hob, Chimney, Dishwasher, Built-in Oven, Washing machine 3. Do you prefer a formal dining setup, casual breakfast counter, or both? 4. False Ceiling Requirement - Dining Yes 5. Preferred kitchen layout 6. Storage style preferred in the kitchen 7. False Ceiling Requirement - Kitchen Yes Bedrooms 1. Master Bedroom - Bed type Storage 2. Master Bedroom - Wardrobe style Swing 3. Master Bedroom - Additional units Dresser, TV unit 4. False Ceiling Required - Master Bedroom Yes 5. Bedroom 1 - Utility 6. Bedroom 1 - Bed Type 7. Bedroom 1 - Wardrobe style 8. Bedroom 1 - Additional units 9. False Ceiling Required - Bedroom 1 10. Bedroom 2 - Utility 11. Bedroom 2 - Bed Type 12. Bedroom 2 - Wardrobe Style 13. Bedroom 2 - Additional Units 14. False Ceiling Required - Bedroom 2 15. Bedroom 3 - Utility 16. Bedroom 3 - Bed Type 17. Bedroom 3 - Wardrobe Style 18. Bedroom 3 - Additional Units 19. False Ceiling Required - Bedroom 3 Bathrooms 1. Preferred vanity style 2. What do you prefer? Shower partition 3. What are your requirements for Utility Area? Tall Storage, Bottom Storage, Washing machine space Balcony & Outdoor 1. How do you intend to use your balcony? Storage 2. Outdoor Mood How do you intend to use the utility Appliances Miscellaneous 1. Timeline related commitment made by Bonito, if any YES 2. Other commitments made by Bonito to customer, if any YES 3. What are offers committed to customers? YES 4. Move-in date confirmed with customer 2026-12-30 5. Any special occasion mentioned by the customer wrt handover date NO 6. Additional Requirements (Mention any requirements from customer not covered in the form) NO 7. Please specify the designerâ€™s estimated project budget based on the scope of work, aligned with the customerâ€™s requirements (only numbers). Note - up to 1000000 - Smart Package, 10,00,000 till 15,00,000 - Select Package and Above 15,00,000 - Signature Package) 100000 | 2026-07-09 15:12:36 +0530 | Priyanka Patel | Recap: 20660 - Design Consultation Meeting (DCM) with the customer 08 July ¦ Meeting ¦ Microsoft Teams |  |  |  | 2026-07-20 |  | 2026-07-27
20661 | Turnkey | 2026-06-01 | Hemang Chowdhury | Rustomjee La Familia | MUM - Thane | Yes | Monika Pal | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 1410411 | 199999 | 1908997 | 0 | 0 | 15 | 0 | 0 | 82083 | 568204 | 560124.4 |  |  | 2026-06-20 | 2026-06-23 12:02 | 2026-06-20 | 2026-06-23 18:38 | 2026-06-27 | 2026-06-27 21:34 | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-06-27 | 2026-06-29 10:58 | 2026-06-28 | 2026-06-29 13:26 | 2026-06-29 | 2026-06-30 12:54 | 2026-07-05 | 2026-07-04 19:31 |  |  |  |  | 2026-07-10 |  | 2026-07-18 |  | 2026-07-19 |  |  |  | 2026-07-26 |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 | [6 empty] | 2026-08-16 |  | 2026-08-25 |  | 2026-08-24 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-28 |  |  |  | 2026-09-19 |  | 2026-09-21 |  | 2026-09-22 | [5 empty] | 2026-07-27 |  | 2026-07-05 |  | Site is RTMI | 2026-06-20 | 2026-06-23 12:01 | 1617794 | 291202 | 0 | 0 | 0 | 0 | 1589263.961 | 262424 | 2026-07-04 19:23:15 +0530 | Anamika Dolai | Welcome call done : Yes Meeting Dates - after 16th of July'26 IM date : na DEM 1 : 7th of August Possession date : 7th of August 10% payment aligned : explained Periskope Number added : yes Escalation Matrix added : yes Price protection for 150 days from the NET date. | 2026-07-03 13:16:36 +0530 | Monika Pal | Minutes of Meeting held on Date: 03-07-2026 | 2026-07-03 13:15:43 +0530 | Monika Pal | Minutes of Meeting held on Date: 03-07-2026 | 2026-07-10 |  | 2026-07-17 |  | Under Construction | 2026-06-30 | 2026-06-27 | 199999 | Ravi Roy
20665 | Turnkey | 2026-06-01 | Sandhya Shashi | Akshaya building | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1828170 | 9999 | 0 | 0 | 0 | 22 | 0 | 172818 | 182817 | 803380 | 659156 |  |  | 2026-06-20 | 2026-06-23 11:51 | 2026-06-20 | 2026-06-23 11:58 | 2026-06-23 |  | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-06-23 |  | 2026-06-24 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | 2026-07-01 |  | 2026-07-09 |  | 2026-07-10 |  |  |  | 2026-07-17 |  | 2026-07-18 |  | 2026-07-19 |  | 2026-07-20 | [6 empty] | 2026-08-07 |  | 2026-08-16 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 |  | 2026-08-19 |  |  |  | 2026-09-10 |  | 2026-09-12 |  | 2026-09-13 | [5 empty] | 2026-07-18 |  | 2026-06-26 |  | Unknown | 2026-06-20 | 2026-06-23 11:50 | 0 | 0 | 0 | 0 | 0 | 0 | 1549297 | 278873 | 2026-06-23 11:46:36 +0530 | Bhawaya Goyal | DCM: Recap: 20665 - Design Consultation Meeting (DCM) with the customer Saturday, June 20 ¦ Meeting ¦ Microsoft Teams | 2026-06-23 11:46:18 +0530 | Bhawaya Goyal | DCM: Project: 1 BHK Location: Chembur CDP: 28th June Time: 3:00 PM Design Style: Minimalist, Classy & Premium Theme: Warm Wooden + Beige Palette SPACE PLANNING Sliding partition between the existing 2 BHK and 1 BHK zonesCreate an informal lounge/social interaction spaceOpen up the kitchen by removing the existing partition wall (subject to site feasibility) LIVING ROOM Wooden tile flooringTV unit with provision for:SoundbarWoofers/Home Theatre SetupComfortable sofa seating BAR AREA (Feature Zone) Bar counterBar chairsDisplay shelving Memorial Display WallDedicated gallery/display wall around the bar areaIlluminated niches for memorabilia and collectiblesCombination of floating shelves and framed displaysAccent lighting to highlight showcased items KITCHEN Break kitchen BEDROOM Queen-size bedStudy tableWardrobe with rattan finish and glass elements WASHROOM Merge both washrooms into one washroom | 2026-06-20 18:05:12 +0530 | Unknown | About the Customer **Confirmed Experience Center Visit** Confirmed visit for June 19, 2026, approximately 4:30 PM to 4:45 PM with three family members. **Appointment Time Confirmation Pending** Customer Sandhya needs to confirm the exact appointment time with her husband due to a doctor's appointment and will provide confirmation tonight. **WhatsApp Invite Sent, Follow-up Action** Agent sent WhatsApp invite; customer acknowledged and will confirm appointment time by tonight. **Budget and Property Context** Customer has not set a specific budget and wants an estimate for a premium look; property is in an old building at Chheda Nagar, Chembur. **Experience Center Visit Preference and Logistics** Customer prefers visiting the Thane experience center next week; parking availability confirmed. | 2026-07-01 |  | 2026-07-08
20666 | Turnkey | 2026-06-01 | prim industries | Dynamic luma | MUM - GOR | Yes | Karan Chavda | Christopher Macwan | Safalta Karkera | [5 empty] | Avi Thakkar |  | Active | Design | DEM1 | 904211 | 125267 | 1252672 | 0 | 0 | 4 | 0 | 0 | 55575 | 407620 | 315748.8 |  |  | 2026-06-20 | 2026-06-30 15:32 | 2026-06-20 | 2026-06-30 17:35 | 2026-07-03 | 2026-07-02 14:10 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-02 | 2026-07-07 18:40 | 2026-07-03 | 2026-07-10 13:02 | 2026-07-10 | 2026-07-11 16:52 | 2026-07-14 | 2026-07-14 13:15 |  |  |  |  | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-20 | 2026-06-20 18:23 | 1061586 | 191085 | 0 | 0 | 0 | 0 | 1061586.283 | 171308 | 2026-07-14 13:17:20 +0530 | Christopher Macwan | Others: Welcome call done. Initial measurement not done as would receive possession by end of October 2026 DEM Dates -Â DEM 1 â€“ Preferred on Weekends DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - end of October 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-11 16:51:08 +0530 | Sanjana Swami | Possession Status: Under construction Under construction completion date: October 2026 Scope of Work: Modular + Painting (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * Site is not accessible. * DEM 1 â€“ Next weekends * 10% Payment Stage â€“ 21st July 2026 Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Sofa Offer May'26 100% GST waiver Free Shoerack Offer Design Fee Waiver (4%) PM fee waiver (5%) Final Closing Value Discussed: â‚¹ 9,04,211 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-11 15:31:46 +0530 | Avi Thakkar | Onboarding Due:please call back | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2026-10-31 | 2026-06-29 | 125267 | Ravi Roy
20667 | Turnkey | 2026-06-01 | Swapnil Khopkar | Sunroof | MUM - Thane | Yes | Preet Karania | Anil Jagtap | Rachna Abhyankar | [5 empty] | Vandana Preet |  | Active | Design | DEM1 | 1255350 | 252999 | 1690040 | 0 | 0 | 13 | 0 | 0 | 0 | 500211 | 502140 |  |  | 2026-06-20 | 2026-06-21 22:05 | 2026-06-20 | 2026-06-23 16:11 | 2026-06-27 | 2026-06-29 13:47 | 2026-07-08 |  | 2026-07-15 |  | 2026-07-22 |  | 2026-06-29 | 2026-06-29 14:33 | 2026-06-30 | 2026-06-29 14:35 | 2026-06-29 | 2026-07-02 14:05 | 2026-07-04 | 2026-07-03 18:13 |  |  |  |  | 2026-07-09 | 2026-07-08 14:47 | 2026-07-17 |  | 2026-07-18 |  |  |  | 2026-07-25 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-07-26 |  | 2026-07-04 |  | Unknown | 2026-06-20 | 2026-06-21 16:05 | 1432238 | 257802 | 0 | 0 | 0 | 0 | 1420224.29 | 234513 | 2026-07-12 00:23:38 +0530 | Rachna Abhyankar | DEM1 on 14th july | 2026-07-07 17:09:22 +0530 | Preet Karania |  | 2026-07-07 17:08:19 +0530 | Preet Karania |  | 2026-07-09 |  | 2026-07-16 |  | Under Construction | 2026-07-12 | 2026-06-27 | 252999 | Ravi Roy
20668 | Turnkey | 2026-06-01 | Sripal Jain | Ariha signature | MUM - GOR | Yes | [8 empty] | Ashutosh Singh |  | Active | Prospect | DCM Due | 2854138 | 9999 | 0 | 0 | 0 | 25 | 0 | 275415 | 285414 | 1198302 | 1085008.8 |  |  | 2026-06-20 | 2026-06-20 21:17 | 2026-06-21 | 2026-07-03 22:56 | 2026-07-09 |  | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-07-09 |  | 2026-07-10 |  | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-20 | 2026-06-20 21:11 | 0 | 0 | 0 | 0 | 0 | 0 | 2418761 | 435377 | 2026-06-21 22:45:31 +0530 | Yash Jain | DCM link : Recap: 20668 - Design Consultation Meeting (DCM) with the customer 21 June ¦ Meeting ¦ Microsoft Teams | 2026-06-21 21:56:54 +0530 | Yash Jain | Some Image was uploaded | 2026-06-21 21:56:33 +0530 | Yash Jain | DCM: Cx Sripal Jain 677 + 677 2 bhk layout. occupants - 2 kids , 2 grandp, 1 couple. 6th floor. RTMI. only paintwork remaining. MARBLE flooring white and grey. electrical and plumbing completed. centre single door. tv unit ,Â sofa 6 members, shoe rack outside. dining table 6 seater in lowerÂ kitchen. As per plan marked. Budget - 20 - 25L | 2026-07-17 |  | 2026-07-24
20669 | Turnkey | 2026-06-01 | Chandran Jagannathan | Seth Zuri | MUM - Thane | Yes | Harshali Bhuyar | Anamika Dolai | Sneha Kadam | [5 empty] | Prashant Panigrahi |  | Active | Design | DEM1 | 1601662 | 189999 | 1862813 | 0 | 0 | 7 | 0 | 0 | 130333 | 711311 | 570018.4 |  |  | 2026-06-20 | 2026-06-23 11:53 | 2026-06-20 | 2026-06-24 16:24 | 2026-07-05 | 2026-07-05 20:55 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-07-05 | 2026-07-07 19:04 | 2026-07-06 | 2026-07-07 19:07 | 2026-07-07 | 2026-07-08 12:29 | 2026-07-09 | [5 empty] | 2026-07-15 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-10 |  | Unknown | 2026-06-20 | 2026-06-23 11:52 | 1578655 | 284157 | 0 | 0 | 0 | 0 | 1578654.6603 | 278281 | 2026-07-08 12:28:29 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM â€“ Weekends * DEM 1 â€“ Next weekends * 10% Payment Stage â€“ after the 1st dem by 19th July 2026 *Civil work is going on at the site (tiling work), will be completed within a month. *Transactin will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (2.5%) May '26 80% GST Waiver Final Closing Value Discussed: â‚¹ 16,01,662 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-07 16:17:40 +0530 | Prashant Panigrahi | Others: | 2026-07-07 16:16:30 +0530 | Prashant Panigrahi | Others: | 2026-07-15 |  | 2026-07-22 |  | RTMI
20673 | Turnkey | 2026-06-01 | Prachi Pawar | Vighnaharta | MUM - GOR | Yes | Manisha Dubey | Christopher Macwan | Shantanu Parakh | [5 empty] | Rashmita Das |  | Active | Preproduction | DEM2 | 1297152 | 259430 | 1707079 | 0 | 0 | 3 | 0 | 0 | 0 | 569064 | 468658 |  |  | 2026-06-20 | 2026-06-30 11:47 | 2026-06-20 | 2026-06-30 12:33 | 2026-07-03 | 2026-07-01 13:52 | 2026-07-12 | 2026-07-12 19:25 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-28 | 2026-06-28 19:45 | 2026-07-02 | 2026-07-03 14:00 | 2026-07-03 | 2026-07-10 10:33 | 2026-07-12 | 2026-07-12 16:53 |  |  |  |  | 2026-07-18 | 2026-07-12 17:32 | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-13 | 2026-07-12 19:19 | Site is RTMI | 2026-06-20 | 2026-06-20 19:45 | 1449697 | 257382 | 0 | 0 | 0 | 0 | 1433576.625 | 242037 | 2026-07-12 17:01:19 +0530 | Christopher Macwan | Others: Welcome call done along with the Designer. Initial measurement not done as would receive possession in December DEM Dates -Â DEM 1 â€“ 12th July 3pm DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - 31st December 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-10 10:32:20 +0530 | Sanjana Swami |  | 2026-07-04 15:33:22 +0530 | Athul Ajaykumar | Possession Status: Under construction Possession: December Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 10 + 10 Business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Tentatively scheduled for (12th July) * DEM 1 â€“ Tentatively scheduled for (19th July) * 10% Payment Stage â€“ Tentatively scheduled for (End of july) * B2C - self * Civil work - yes Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Laminate Upgrade Offer - June 26 May'26 100% GST waiver Silver Coin Offer21g PM fee waiver (7.5%) Free Shoerack Offer Final Closing Value Discussed: â‚¹12,97,152civil Checklist terms - descoping, agreement terms are cleared Reject points: Client mentioned his possession is by December 2026, need approval for the extended price protection. Client VOC: Client mentioned that the kitchen countertop removal is a civil work and is an optional item. | 2026-07-13 | 2026-07-12 19:31 | 2026-07-19 |  | Under Construction | 2026-12-31 | 2026-06-28 | 170708 | Ravi Roy
20674 | Turnkey | 2026-06-01 | Mrs. M Sindhuja & Mr. Manohar Babu S | Pavani Mariabilia | BNG - HRBR | Yes | [8 empty] | Kaminahal Rahiman |  | Active | Prospect | Onboarding Due | 1047048 | 149999 | 1499259 | 0 | 0 | 5 | 0 | 0 | 59411 | 418819 | 418819.2 |  |  | 2026-06-20 | 2026-06-21 10:48 | 2026-06-29 | 2026-06-29 17:10 | 2026-06-30 | 2026-06-30 12:50 | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-06-30 | 2026-07-01 11:22 | 2026-07-01 | 2026-07-10 20:04 | 2026-07-10 |  | 2026-07-11 | [5 empty] | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-20 | 2026-06-21 10:46 | 1270559 | 228700 | 0 | 0 | 0 | 0 | 1192919.531 | 197018 | 2026-07-14 18:13:26 +0530 | Bency Chacko | Onboarding Due: OB reject - as the client mentioned he wants the handover before 20th October 2026, that is before Dassera | 2026-07-14 15:26:08 +0530 | Losii Athisa |  | 2026-07-13 11:35:35 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM â€“ Maybe today * DEM 1 â€“ This weekends * 10% Payment Stage â€“ 20th July 2026 (after 1st dem) *No civil work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Bonito Atelier - Studio Upgrade Silver Coin Offer Free Hob & Chimney Offer Free Shoerack Offer Design fee waiver (5%) Laminate Upgrade Offer - June 26 PM fee waiver (5%) May'26 100% GST waiver Final Closing Value Discussed: â‚¹ 10,47,048 Checklist terms - descoping, delay compensation, agreement terms are clear. Rejections: Client mentioned he wants the handover before 20th October 2026, which is before Dassera. | 2026-07-17 |  | 2026-07-24 |  |  |  | 2026-06-28 | 149999 | Ravi Roy
20676 | Turnkey | 2026-06-01 | Santhosh J Perumal | Gopalan Florenza | BNG - HSR | Yes | Swati Rathod |  | Priyanka Mathur | [5 empty] | Nidhi Shaw |  | Active | Prospect | DCM Due | 1547829 | 9999 | 0 | 0 | 0 | 24 | 0 | 144784 | 154783 | 619132 | 619131.6 |  |  | 2026-06-20 | 2026-06-21 12:44 | 2026-06-24 | 2026-06-28 16:03 | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-05 |  | 2026-07-06 | [5 empty] | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-07 |  | Unknown | 2026-06-20 | 2026-06-21 12:41 | 0 | 0 | 0 | 0 | 0 | 0 | 1311720 | 236109 | 2026-07-07 18:05:48 +0530 | Swati Rathod | CDP: | 2026-06-24 20:08:51 +0530 | Swati Rathod | Some Image was uploaded | 2026-06-24 20:08:14 +0530 | Swati Rathod | RGM Date : 24-06-2026 PID: 20676 Name : Santhosh Profession: IT Property - 2BHK Budget - 8L-9L Theme - Minimal, functional possession : 01-08-2026 Site Access Date: 01-06-2026 Total Members - 03Â Â , Kids - Daughter (11yrs) (Name : Cianne ) Orientation : West facing Floor : 8thÂ Â - window in MBR - single person office setup closed cabin in living area. - some storage in foyer - more storage space to be look after LIVING: - TV unit cum pray wall on right side as reff - 3+1+1 seater sofa or sofa cum bed - single handwash - brk fast counter (1 prs) - less depth tall unitÂ - W.M in balcony DINNING: - 4 seater KITCHEN: - 2door fridge (top&bott) - bottom unit - top unit - Loft above fridge - Granite BD scope - loft above w.m - HOB on south wall - gas unit - microwave space BEDROOM-1: (M. bedroom) - King size bed - Study with bott storage - wardrobe with loft - more storage space - sugg for laundry cloths near window. - loft above MBD door - dresser BEDROOM-2: (DBR) - Queen size bed - wardrobe with loft - study table - dresser Next Meeting Agenda 1. Presentation of the design concept for your entire home 2. SketchUp model to help you visualize furniture placements with 3D renders for living and dining 3. Estimation discussion based on current requirements Â Please note, based on this discussion, you'll be proceeding with the 10% payment to move forward with Bonito on that day. Meeting Date: 28-06-2026 | 2026-07-12 |  | 2026-07-19
20677 | Turnkey | 2026-06-01 | Reshma Nasir Husain | Trifecta Vanto | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | 10% Payment | 1878162 | 9999 | 1878162 | 0 | 0 | 10 | 0 | 177817 | 187816 | 751265 | 751264.8 |  |  | 2026-06-20 | 2026-06-21 12:40 | 2026-06-21 | 2026-06-21 18:37 | 2026-07-05 | 2026-07-05 15:28 | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-07-05 |  | 2026-07-06 |  | 2026-07-06 |  | 2026-07-07 | [5 empty] | 2026-07-13 |  | 2026-07-21 |  | 2026-07-22 |  |  |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 | [6 empty] | 2026-08-19 |  | 2026-08-28 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-31 |  |  |  | 2026-09-22 |  | 2026-09-24 |  | 2026-09-25 | [5 empty] | 2026-07-30 |  | 2026-07-08 |  | Unknown | 2026-06-20 | 2026-06-21 12:37 | 1591662 | 286499 | 0 | 0 | 0 | 0 | 1591662 | 286499 | 2026-07-05 14:57:03 +0530 | Nayan Reddy | Minutes of Meeting held on Date: 05-07-26 Attendees: Nayan Discussion: ï»¿Change all wardrobe to sliding mechanism add wall cabinet to crockery unit with glass shutter remove study table in kids' bedroom add tall unit in kids' bedroom for storage Prelam is only for loft,storage unit in kids bedroom infromed cx that we are using pre-lam need different wall concept for living room | 2026-07-05 14:51:19 +0530 | Nayan Reddy | CDP:Recap: 20677 - Celebrity Design Presentation (CDP) with the customer 04 July ¦ Meeting ¦ Microsoft Teams | 2026-06-25 12:42:38 +0530 | Nayan Reddy | Some Image was uploaded | 2026-07-13 |  | 2026-07-20
20678 | Turnkey | 2026-06-01 | SUBHADEEP DEY | MICL Aaradhya Parkwood | MUM - GOR | Yes | Khyati Bandi | Christopher Macwan | Safalta Karkera | [5 empty] | Ashish Jha |  | Hold | Preproduction | DEM2 | 943244 | 209999 | 1243693 | 0 | 0 | 0 | 15 | 0 | 0 | 390487 | 342757.6 |  |  | 2026-06-21 | 2026-06-21 13:23 | 2026-06-21 | 2026-06-21 18:55 | 2026-06-24 | 2026-06-24 12:45 | 2026-07-02 | 2026-06-28 17:40 | 2026-09-01 |  | 2026-09-08 |  | 2026-06-21 | 2026-06-21 16:48 | 2026-06-25 | 2026-06-21 19:12 | 2026-06-25 | 2026-06-23 19:07 | 2026-06-27 | 2026-06-27 13:55 |  |  |  |  | 2026-06-28 | 2026-06-30 14:05 | 2026-09-03 |  | 2026-09-04 |  |  |  | 2026-09-11 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 | [6 empty] | 2026-10-02 |  | 2026-10-11 |  | 2026-10-10 |  | 2026-10-11 |  | 2026-10-12 |  | 2026-10-14 |  |  |  | 2026-11-05 |  | 2026-11-07 |  | 2026-11-08 | [5 empty] | 2026-09-12 |  | 2026-06-28 | 2026-06-28 17:38 | Site is RTMI | 2026-06-21 | 2026-06-21 12:55 | 1056262 | 187430 | 0 | 0 | 0 | 0 | 1056261.9438 | 175637 | 2026-06-30 14:16:06 +0530 | Christopher Macwan | Some Image was uploaded | 2026-06-30 14:05:52 +0530 | Christopher Macwan |  | 2026-06-28 17:24:01 +0530 | Khyati Bandi | FOYER -Â 1. Add loft above console with wall art. 2. Add some wall art in dining table wall MBR -Â 1. Existing king size bed - 6'x7' 2. Solid color louvers behind mirror with wallpaper 3. TV size 45" GUEST ROOM -Â 1. No drawers needed in workstation 2. Height of open unit - 12" Under wall unit (workstation wall) 3. Add queen size bed with one side tableÂ 4. God frame on bed back wallÂ 5. Wooden finish in mandir and work station 6. Curtains in mandirÂ 7. Mirror on wardrobe wall between wardrobe and mandir LIVING AREA -Â 1.TV size 55" 2. Minimalist interiors KITCHEN -Â 1. all will be Glass shutter wall unit (fridge wall) 2. Add detergent holder, dustbinÂ 3. One unit to keep cylinderÂ 4. Cutlery drawer (3) under hob 5. Right side bottle pulloutÂ 6. 3 tandum drawer - 1. Cutlery 2. Cup n saucer organizer 3. Plate organizer 7. Keep 2 drawers on fridge wall 7. Swap 3 drawers with shutter unit to keep utensilsÂ | 2026-06-29 | 2026-06-28 17:41 | 2026-09-02 |  | Under Construction | 2026-07-15 | 2026-06-21 | 209999 | Ravi Roy
20679 | Turnkey | 2026-06-01 | Punit Dahima | Kalpataru Vivant | MUM - GOR | No Estimate | [8 empty] | Ashutosh Singh |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-21 | 2026-06-21 13:31 | 2026-06-21 | 2026-06-23 15:58 | 2026-06-27 |  | 2026-07-03 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-06-26 |  | 2026-06-27 |  | 2026-06-27 |  | 2026-06-28 | [5 empty] | 2026-07-04 |  | 2026-07-12 |  | 2026-07-13 |  |  |  | 2026-07-20 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 | [6 empty] | 2026-08-10 |  | 2026-08-19 |  | 2026-08-18 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-22 |  |  |  | 2026-09-13 |  | 2026-09-15 |  | 2026-09-16 | [5 empty] | 2026-07-21 |  | 2026-06-29 |  | Unknown | 2026-06-21 | 2026-06-21 13:30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-23 16:38:00 +0530 | Rahul Agrawal | Some Image was uploaded | [6 empty] | 2026-07-04 |  | 2026-07-11
20681 | Turnkey | 2026-06-01 | Sandeep Mallick | Mahendra aarya | BNG - HSR | Yes | Aishwarya C | Abhinandan K S | Soumya KP | [5 empty] | Ramesh Nayak |  | Active | Design | DEM1 | 1038065 | 149798 | 1419717 | 0 | 0 | 16 | 0 | 0 | 57815 | 424738 | 405714.4 |  |  | 2026-06-21 | 2026-06-21 13:48 | 2026-06-21 | 2026-06-21 16:12 | 2026-06-26 | 2026-06-27 16:06 | 2026-07-14 |  | 2026-07-21 |  | 2026-08-11 |  | 2026-06-27 | 2026-06-27 21:02 | 2026-06-28 | 2026-06-28 12:57 | 2026-06-28 | 2026-06-29 11:41 | 2026-07-03 | 2026-07-03 19:50 |  |  |  |  | 2026-07-15 |  | 2026-08-06 |  | 2026-08-07 |  |  |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-16 |  | 2026-08-17 | [6 empty] | 2026-09-04 |  | 2026-09-13 |  | 2026-09-12 |  | 2026-09-13 |  | 2026-09-14 |  | 2026-09-16 |  |  |  | 2026-10-08 |  | 2026-10-10 |  | 2026-10-11 | [5 empty] | 2026-08-15 |  | 2026-07-10 |  | Unknown | 2026-06-21 | 2026-06-21 13:29 | 1205645 | 214071 | 0 | 0 | 0 | 0 | 1183384.289 | 192457 | 2026-06-30 15:56:47 +0530 | Gayathri Krishna | Recap: 20681 - Design Consultation Meeting (DCM) with the customer 21 June ¦ Meeting ¦ Microsoft Teams | 2026-06-30 15:56:35 +0530 | Gayathri Krishna | Some Image was uploaded | 2026-06-30 15:56:05 +0530 | Gayathri Krishna | Recap: 20681 - Celebrity Design Presentation (CDP) with the customer 26 June ¦ Meeting ¦ Microsoft Teams | 2026-07-15 |  | 2026-07-22 |  | RTMI |  | 2026-06-26 | 149798 | Ravi Roy
20683 | Turnkey | 2026-06-01 | Rahul Shinde | Alpine Primo | MUM - GOR | Yes | Swapnali Shedekar | Christopher Macwan | Safalta Karkera | [5 empty] | Aniket Parab |  | Active | Design | DEM1 | 926347 | 131421 | 1314209 | 0 | 0 | 9 | 0 | 0 | 53848 | 391308 | 349770 |  |  | 2026-06-21 | 2026-07-04 21:20 | 2026-07-11 | 2026-07-10 18:32 | 2026-07-11 | 2026-07-10 18:57 | 2026-07-15 |  | 2026-07-22 |  | 2026-07-29 |  | 2026-06-25 | 2026-07-04 20:41 | 2026-06-26 | 2026-07-04 21:26 | 2026-07-04 | 2026-07-06 18:01 | 2026-07-10 | 2026-07-10 19:04 |  |  |  |  | 2026-07-16 |  | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-07-11 |  | Unknown | 2026-06-21 | 2026-06-21 13:43 | 1113736 | 200472 | 0 | 0 | 0 | 0 | 1113736.042 | 175292 | 2026-07-10 19:05:51 +0530 | Christopher Macwan | Others: Welcome call done. Initial measurement not done as would receive possession by end of July DEM Dates -Â DEM 1 â€“ Customer will update on the same DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - end of July 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-06 18:00:13 +0530 | Athul Ajaykumar | Possession Status: Under construction Soft possession: July end Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90 + 20 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Tentatively scheduled for (This weekend) * DEM 1 â€“ Tentatively scheduled for (Next weekend) * 10% Payment Stage â€“ Tentatively scheduled for (15th July) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Design fee waiver (5%) Free Hob & Chimney Offer PM fee waiver (5%) Free Shoe Rack Offer May '26 100% GST waiver Final Closing Value Discussed: 9,26,347 Checklist terms â€“ descoping and agreement terms are cleared Client VOC: The client mentioned that the civil work includes demolition of the washroom to convert it into a usable area and kitchen demolition; all the civil work is expected to be completed within a maximum of one month. | 2026-07-06 15:16:19 +0530 | Aniket Parab | Others: | 2026-07-16 |  | 2026-07-23 |  | Under Construction | 2026-07-31
20684 | Turnkey | 2026-06-01 | Sangeeta Jain | Lodha Aderna | MUM - GOR | Yes | Batskhem Marpna | Anamika Dolai | Kashmira Nerurkar | [5 empty] | Avi Thakkar |  | Active | Design | DEM1 | 1247991 | 159809 | 1598090 | 0 | 0 | 1 | 0 | 0 | 89789 | 536820 | 461572.4 |  |  | 2026-06-21 | 2026-07-07 12:58 | 2026-06-21 | 2026-07-07 13:18 | 2026-07-10 | 2026-07-07 16:57 | 2026-07-20 |  | 2026-07-27 |  | 2026-08-03 |  | 2026-07-07 | 2026-07-09 10:59 | 2026-07-08 | 2026-07-10 13:03 | 2026-07-10 | 2026-07-14 14:24 | 2026-07-15 | [5 empty] | 2026-07-21 |  | 2026-07-29 |  | 2026-07-30 |  |  |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 |  | 2026-08-09 | [6 empty] | 2026-08-27 |  | 2026-09-05 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-09-30 |  | 2026-10-02 |  | 2026-10-03 | [5 empty] | 2026-08-07 |  | 2026-07-16 |  | Unknown | 2026-06-21 | 2026-06-21 13:43 | 1354313 | 243776 | 0 | 0 | 0 | 0 | 1354313.4582 | 233188 | 2026-07-14 14:22:18 +0530 | Sanjana Swami | Client concerns are addressed. | 2026-07-13 14:17:42 +0530 | Avi Thakkar | Onboarding Due:the customer stated that they want to complete the design meetings as they can give the civil plans to the vendor and move ahead accordingly and also mentioned they agree on the timelines would be according to the completion of the civil work. You can have a word with their daughter Krinjal-7977218570 | 2026-07-11 16:15:35 +0530 | Athul Ajaykumar | The client gave the acknowledgement that she would proceed with the B2C transaction, and she will close the 10% after finalizing the layout. Rejection: The client is not aligned with the project timeline of 90+10+31 days (modular + painting + membrane). She expects the project handover by the end of September 2026, Additionally, the client mentioned that her civil work will take approximately 1.5 to 2 months to complete. However, she does not want to keep the project on hold and expects the interior work to progress simultaneously, which is not aligned with the project execution plan. | 2026-07-21 |  | 2026-07-28 |  | RTMI
20685 | Turnkey | 2026-06-01 | Sudhanshu Shekhar | Godrej splendor | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | DCM Due | 1512086 | 9999 | 0 | 0 | 0 | 22 | 0 | 141210 | 151209 | 638938 | 570730.4 |  |  | 2026-06-21 | 2026-06-23 12:30 | 2026-06-23 | 2026-06-23 16:19 | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-06-21 | 2026-06-21 14:18 | 0 | 0 | 0 | 0 | 0 | 0 | 1281428 | 230657 | 2026-06-26 19:32:20 +0530 | Palak Thakur | Some Image was uploaded | 2026-06-26 19:29:13 +0530 | Palak Thakur | DCM: Title: Design Consultation Meeting Project No: 20685 Client: Sudhanshu Shekhar Hi, Minutes of Meeting held on Date: <23-06/2026> Attendees:palak Discussion:rgm Based on <23-06/2026> meeting, below is a list of all the requirements that were discussed during the meeting:FINAL MOM 23-06/2026 20685 - Sudhanshu Shekhar Â Client Name:Sudhanshu Shekhar Â Property:godrej splendor bellathur road Â Floor:5th floor Â Main Door Facing:Â Â west going outside Â Possession:august after 1st week Site Measurement august Â handover before diwali Current residence near by property Total sqft 991 TYPE OF CONSTRUCTION mi one Family Details Couple and 1 daughter 11 years in bang Sir blend 360 ( it firm us ) BudgetClient Budget: 10 ALL MODULAR DESIGNRecommended Budget (as per requirements): 10-13LakhsTheme themes light colors + with a hint of fancyDesign Preferences Colors, Finishes & Lighting Kitchen: blueLiving Area:Overall Preference:Kitchen Countertop: granite may maynot be in scopeLighting:Ceiling: ;living diningDesign Requirements & Discussion PointsEXISTING FURNITURE na Bedroom MASTER BEDROOM bottom King bed Wardrobe + loft Â Dresser unit Study setup Kids bedroom /guest bedroom centre Pink color My little pony Â Study setup Wardrobe + loft Â Dresser unit LIVING ROOMÂ Pooja as marked in planTv 55"Sofa 2+1Suspended stoargeMinimal design in wall1 tall unit semiColor variation preferedUTILITY Â Double sink 2'8" Washing machine Base + wall unit KITCHEN Single sink 2 door fridge Handless Base + wall + loft Corner cylinder space Tall micro unit (mixer +griller + micro) Ro in side wall DINING 4 seater bench Wall unit crockery sleek Foyer Shoe stoarge l shape 2 lvl +wall design + seater Washrooms Partition Base unit Grill for 2 bedroom to be confirmed Pipe outside to cover with door (to check with team ) | 2026-06-21 14:18:24 +0530 | Unknown | About the Customer **2 BHK Inquiry with Budget and Possession Timeline** Customer is looking for full home interiors for a 2 BHK property at Godrej Splendour, possession expected in August or September, with a budget of 10-15 lakhs. **Experience Center Visit Required for Finalization** Customer needs to visit the experience center to finalize interior design needs. **Saturday 4 PM Appointment Booked at HRBR Layout** An appointment for the experience center visit has been booked for Saturday at 4 PM at the HRBR Layout center. **Weekend Appointment Preference Due to Work** Customer prefers weekend appointments due to work commitments on weekdays. | 2026-07-08 |  | 2026-07-15
20687 | Turnkey | 2026-06-01 | Satyam Kishore Sanjana Sharma | Ramsons Trendsquares | BNG - HSR | Yes | Purva Shiravle | Akshay Ds | Kowshik | [5 empty] | Chanakya Panigrahi |  | Active | Design | DEM1 | 2108579 | 277139 | 2771390 | 0 | 0 | 6 | 0 | 0 | 144577 | 929159 | 757704.4 |  |  | 2026-06-21 | 2026-06-21 15:01 | 2026-06-26 | 2026-06-28 12:11 | 2026-07-01 | 2026-06-30 11:25 | 2026-07-19 |  | 2027-01-05 |  | 2027-01-12 |  | 2026-06-30 | 2026-06-30 12:15 | 2026-07-01 | 2026-07-08 15:16 | 2026-07-08 | 2026-07-09 16:30 | 2026-07-14 | 2026-07-14 15:34 |  |  |  |  | 2026-07-20 |  | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 | [6 empty] | 2027-02-05 |  | 2027-02-14 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-17 |  |  |  | 2027-03-11 |  | 2027-03-13 |  | 2027-03-14 | [5 empty] | 2027-01-16 |  | 2026-07-15 |  | Unknown | 2026-06-21 | 2026-06-21 14:54 | 2348636 | 422754 | 0 | 0 | 0 | 0 | 2317603.2722 | 382664 | 2026-07-09 16:00:20 +0530 | Athul Ajaykumar | Possession Status: Under construction Under construction Completion Date: December Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 120 + 20 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline (10, 10, 40, 40) Plan of Action Discussed During the Call: * IM â€“ Site is not accessible * DEM 1 â€“ will update to the sales team * 10% Payment Stage â€“ Tentatively scheduled for (10th August) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Bonito Atelier - Studio Upgrade Bonito Atelier - Living Room Upgrade Bonito Atelier - Kitchen Upgrade Bonito Atelier - Bedroom Upgrade PM fee waiver (5%) Design fee waiver (5%) Laminate Upgrade Offer - June 26 Silver Coin Offer Final Closing Value Discussed: 21,08,579 Checklist terms â€“ descoping and agreement terms are cleared | 2026-07-09 15:33:11 +0530 | Athul Ajaykumar | OB Initiated â€“ Call disconnected | 2026-07-09 14:47:17 +0530 | Athul Ajaykumar | OB Initiated - Ringing | 2026-07-20 |  | 2027-01-06 |  | Under Construction | 2026-12-31 | 2026-06-29 | 277139 | Ravi Roy
20690 | Turnkey | 2026-06-01 | Ajay Upadhyay | Kalpatru shrishti namah | MUM - Thane | Yes | [8 empty] | Rahul Kumawat |  | Active | Prospect | 10% Payment | 2430108 | 9999 | 0 | 0 | 0 | 16 | 0 | 233012 | 243011 | 1073855 | 870231.2 |  |  | 2026-06-21 | 2026-06-21 21:00 | 2026-06-21 | 2026-06-23 16:04 | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-07-07 |  | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-07-02 |  | Unknown | 2026-06-21 | 2026-06-21 20:58 | 0 | 0 | 0 | 0 | 0 | 0 | 2059413 | 370694 | 2026-06-30 16:17:15 +0530 | Bhawaya Goyal | Some Image was uploaded | 2026-06-30 16:15:47 +0530 | Bhawaya Goyal | DCM: https://teams.cloud.microsoft/l/meetingrecap?driveId=b%219Qo4K_0m5Ea8yUSIDUhDgAB5UFEv9y1Lj_pqql4LFvzVrzYqisTRQLsAGOX7xz9E&driveItemId=01LBE7V26JRKENOE7FTZFJU5PJAMUKUYSU&sitePath=https%3A%2F%2Fbonitodesigns-my.sharepoint.com%2F%3Av%3A%2Fg%2Fpersonal%2Fmeeting_organizer_bonito_in%2FIQDJiojXE-WeSpp16QMoqmJUASEXcUc1Wp0WHxOi0TnksnM&fileUrl=https%3A%2F%2Fbonitodesigns-my.sharepoint.com%2F%3Av%3A%2Fg%2Fpersonal%2Fmeeting_organizer_bonito_in%2FIQDJiojXE-WeSpp16QMoqmJUASEXcUc1Wp0WHxOi0TnksnM&iCalUid=040000008200E00074C5B7101A82E008000000005A4A759F6501DD010000000000000000100000001349AF8DA0F71F42BA03FE3FCA85A09A&threadId=19%3Ameeting_YWM0NzAxMTAtNTFhMi00YTYwLTgzNzEtNDUzMWNlOTM3Nzc2%40thread.v2&organizerId=8a9becf1-636c-45c6-975e-d5c5d9904ca2&tenantId=dd8d0223-8a42-433c-8f23-46c4f20f35be&callId=625011da-3070-4efc-b228-febabdae7fd4&threadType=Meeting&meetingType=Scheduled&subType=RecapSharingLink_RecapChiclet | 2026-06-29 17:19:26 +0530 | Bhawaya Goyal | Some Image was uploaded | 2026-07-07 |  | 2026-07-14
20691 | Turnkey | 2026-06-01 | Anil Bhasarkar | Birla Vanya | MUM - Thane | Yes | Sakshi Pokharkar | Divya Rahangdale | Sneha Kadam | [5 empty] | Vandana Preet |  | Active | Design | DEM1 | 1407110 | 291599 | 1743483 | 0 | 0 | 13 | 0 | 0 | 0 | 609851 | 505660 |  |  | 2026-06-21 | 2026-06-21 22:02 | 2026-06-23 | 2026-06-23 19:42 | 2026-06-27 | 2026-06-27 18:09 | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-06-27 | 2026-06-27 19:46 | 2026-06-28 | 2026-06-30 13:05 | 2026-06-30 | 2026-07-02 14:09 | 2026-07-08 | 2026-07-08 12:57 |  |  |  |  | 2026-07-19 | 2026-07-08 12:51 | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-08-19 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-09 |  | Unknown | 2026-06-21 | 2026-06-21 16:03 | 1477528 | 265955 | 0 | 0 | 0 | 0 | 1477527.7635 | 253279 | 2026-07-08 13:32:35 +0530 | Divya Rahangdale | Welcome call done : Possession date : RTMI 10% payment aligned : Done Periskope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-07-02 14:03:25 +0530 | Vandana Preet | Flat no- E-201, Birla vanya, saroj apartments, Chemical Plant, Birla Vanya Entry Rd, opp. Century Rayon Company, Shahad, Mumbai, Ulhasnagar, Maharashtra 421301 | 2026-06-30 16:14:52 +0530 | Sanjana Swami |  | 2026-07-19 |  | 2026-07-26 |  | RTMI |  | 2026-06-27 | 291599 | Ravi Roy
20692 | Turnkey | 2026-06-01 | Rupali Mataghare | Godrej Exquisite | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1518131 | 9999 | 0 | 0 | 0 | 16 | 0 | 141814 | 151813 | 683842 | 530662.4 |  |  | 2026-06-21 | 2026-06-23 12:54 | 2026-06-21 | 2026-06-23 16:15 | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-06-21 | 2026-06-23 12:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1287916 | 230215 | 2026-06-30 12:33:10 +0530 | Krutika Vernekar | CDP: MOM Rupali MeetingProject: 3BHK Interior Design Client did not close the deal during the meeting.Client Budget: 10.00 Lakhs.Revised Offer Presented: 11.43 Lakhs.Client mentioned they need to discuss the proposal with their parents before making a final decision.Client's primary requirement is maximum storage, making storage planning the key design priority. | 2026-06-29 15:40:21 +0530 | Krutika Vernekar | Some Image was uploaded | 2026-06-23 11:13:02 +0530 | Maasoumeh Raza | DCM: Recap: 20692 - Design Consultation Meeting (DCM) with the customer Sunday, June 21 ¦ Meeting ¦ Microsoft Teams | 2026-07-05 |  | 2026-07-12
20693 | Turnkey | 2026-06-01 | Rudresh Kumar | Independent House | BNG - HRBR | Yes | [8 empty] | Raghavendra S |  | Active | Prospect | DCM Due | 2266285 | 9999 | 0 | 0 | 0 | 22 | 0 | 216630 | 226629 | 906514 | 906514 |  |  | 2026-06-21 | 2026-06-23 12:10 | 2026-06-27 | 2026-06-27 20:27 | 2026-06-28 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-21 | 2026-06-23 12:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1920580 | 345704 | 2026-06-27 20:29:10 +0530 | Keerthan M | Some Image was uploaded | 2026-06-27 20:23:22 +0530 | Keerthan M | DCM: Rudresh 3BHK 4ppl Entrance - ceiling work - false ceiling - full height curtains Living - TV unit with tall storage - glass shutter on washroom wall - hidden door for bedroom and toilet - suggest sofa - under stair plants Dining -Â kitchen - L shape kitchen - tall units - pantry unit - island sink towards pooja unit - bottom, top, loft GF Bedroom (Parents bedroom) - false ceiling - King cot with side table - wall panelling from floor and duco paint photo frame on wall - hanging lights - recliner and swing near walkin wall - wardrobe on left wall - sliding door with brown tinted glass - mirror on living wall - wash room vanity FF Living - near sofa need storage for fish tank - bottom and top - up to piller Bedroom 15x12 (MBR) - false ceiling - planter box open to sky - same req as PBR - swing and reading corner Bedroom 2 KBR - No window on north wall - sliding door to balcony - study unit for 2 on north wall - King bed with one side table - tall unit on piller wall - tv unit after the tall unit - walk in wardrobe Top floor - frame and shutter - on window and door wall | 2026-06-21 16:09:47 +0530 | Unknown | About the Customer **Bangalore 3.5 BHK Property Details** Customer is undergoing tiling for a 3.5 BHK duplex property in Bangalore with an estimated budget of 8-10 lakhs and is comparing quotes from multiple vendors. **Experience Center Visit Confirmed** Customer agreed to visit the Bonito Designs experience center with their wife this Saturday or Sunday. **WhatsApp Share Pending** Agent to share the experience center location and details via WhatsApp. **Comparison with Other Vendors** Customer is comparing quotes from other vendors and wants to compare quality and pricing. **Cab Facility Offered** Bonito Designs to offer cab facility for pickup and drop as part of an anniversary offer. | 2026-07-06 |  | 2026-07-13
20694 | Turnkey | 2026-06-01 | Rakesh Amoji | 4 BHK villa | BNG - HSR | Yes | Gayathri Krishna |  | Priyanka Mathur | [5 empty] | Aman Kumar |  | Active | Design | DEM1 | 2132060 | 219999 | 2848024 | 0 | 0 | 2 | 0 | 0 | 206413 | 881955 | 823692.8 |  |  | 2026-06-21 | 2026-06-21 18:04 | 2026-06-21 | 2026-06-21 18:16 | 2026-06-28 | 2026-06-30 17:23 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-06-30 | 2026-07-10 12:05 | 2026-07-01 | 2026-07-10 12:24 | 2026-07-10 | 2026-07-13 13:07 | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-21 | 2026-06-21 16:36 | 2413580 | 434444 | 0 | 0 | 0 | 0 | 2383067.087 | 393492 | 2026-07-13 13:05:21 +0530 | Sanjana Swami | received approval for extended price protection. | 2026-07-13 12:31:29 +0530 | Nidhi Shaw | Others: | 2026-07-13 10:42:54 +0530 | Bency Chacko | Onboarding Due: OB Reject - Client will pay the next 10% after the 1st DEM in August, | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2026-12-31 | 2026-06-28 | 209999 | Ravi Roy
20695 | Turnkey | 2026-06-01 | Chaitanya Hedau | L&T Rejuve 360 | MUM - Thane | Yes | Mehnaz Ashraf | Anil Jagtap | Rachna Abhyankar | [5 empty] | Nivesh Gupta |  | Active | Preproduction | Site Readiness 1 | 2025616 | 478102 | 2340516 | 0 | 0 | 8 | 0 | 0 | 0 | 779177 | 768336.8 |  |  | 2026-06-21 | 2026-06-23 11:51 | 2026-06-21 | 2026-06-23 11:54 | 2026-06-27 | 2026-06-27 15:42 | 2026-07-07 | 2026-07-07 16:58 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-27 | 2026-06-27 16:17 | 2026-06-28 | 2026-06-27 16:30 | 2026-06-27 | 2026-07-01 11:48 | 2026-07-02 | 2026-07-02 13:44 |  |  |  |  | 2026-07-07 | 2026-07-07 17:29 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-08-30 |  | 2026-08-31 | [6 empty] | 2026-09-18 |  | 2026-09-27 |  | 2026-09-26 |  | 2026-09-27 |  | 2026-09-28 |  | 2026-09-30 |  |  |  | 2026-10-22 |  | 2026-10-24 |  | 2026-10-25 | [5 empty] | 2026-07-24 |  | 2026-07-03 | 2026-07-05 17:53 | Site is Non-RTMI | 2026-06-21 | 2026-06-23 11:26 | 1985731 | 354784 | 0 | 0 | 0 | 0 | 1985730.9995 | 332076 | 2026-07-11 17:55:32 +0530 | Mehnaz Ashraf | Material selection has been done today. next meeting schedule in next weekend. | 2026-07-07 17:28:39 +0530 | Mehnaz Ashraf | On Hold. | 2026-07-07 17:16:50 +0530 | Rachna Abhyankar | Please find the attached MOM as per our DEM 1 at Thane Experience Centre , Date July 4th 2026, whatever we have finalised in the layout has written here to give you an idea regarding the same DEM1 - MOM - July 4th, 2026 Kitchen - Plain gypsum ceiling with profile design - Two dustbins under the sink required - Detergent storage near the sink required - Kitchen bottom platform - Tall appliance unit with loft - Two wicker baskets for onions and potatoes - Ceiling fan in the center of the kitchen - GTPT unit - Under-sink RO water purifier - Foyer (Entrance) - Movable shoe rack Living & Dining Area - Traditional-style mandir - Storage unit for maid's items - 6-seater dining table - L-shaped dining bench with storage - L-shaped sofa - Guest Bedroom - Full-length mirror - Storage space - Study area with one fixed desk and one foldable desk - Murphy bed - Feature wall designed around the Murphy bed Kids' Bedroom - Wardrobe with loft - Open shelves for soft toys - Height-adjustable study table - Corner bed - Small play area - Mirror - Hydraulic storage bed Master Bedroom - King-size bed - Bedside tables - Wardrobe with loft - Dressing unit - Movable table for kids' items Wardrobe Dimensions - Master bedroom: 2 ft depth - Other bedrooms: 1.5 ft depth Balcony - Attractive balcony design to be incorporated in living area Utility Area - Washing machine with storage cabinet - Space for ladder storage - Covering for exposed pipes | 2026-07-08 | 2026-07-07 17:00 | 2026-07-14 |  | Under Construction | 2026-08-01 | 2026-06-27 | 478102 | Ravi Roy
20696 | Turnkey | 2026-06-01 | MR. Nitin BALOTHA | Bhoomi Simana | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1713998 | 9999 | 0 | 0 | 0 | 22 | 0 | 161401 | 171400 | 739363 | 631835.2 |  |  | 2026-06-21 | 2026-06-23 15:25 | 2026-06-25 |  | 2026-06-21 |  | 2026-07-05 |  | 2026-07-12 |  | 2026-07-19 |  | 2026-06-28 |  | 2026-06-29 |  | 2026-06-29 |  | 2026-06-30 | [5 empty] | 2026-07-06 |  | 2026-07-14 |  | 2026-07-15 |  |  |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 | [6 empty] | 2026-08-12 |  | 2026-08-21 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-24 |  |  |  | 2026-09-15 |  | 2026-09-17 |  | 2026-09-18 | [5 empty] | 2026-07-23 |  | 2026-07-01 |  | Unknown | 2026-06-21 | 2026-06-23 15:24 | 0 | 0 | 0 | 0 | 0 | 0 | 1452541 | 261457 | [9 empty] | 2026-07-06 |  | 2026-07-13
20699 | Turnkey | 2026-06-01 | Kumar Jadhav | Rustomjee La Familia | MUM - Thane | Yes | Swami Vadnere | Anamika Dolai | Anil Kuwar | [5 empty] | Prashant Panigrahi |  | Active | Preproduction | Site Readiness 1 | 1296080 | 259216 | 1654630 | 0 | 0 | 6 | 0 | 0 | 0 | 595992 | 440871.6 |  |  | 2026-06-21 | 2026-06-23 12:05 | 2026-06-21 | 2026-06-23 16:15 | 2026-06-29 | 2026-06-29 22:48 | 2026-07-05 | 2026-07-07 16:21 | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 | 2026-06-29 22:55 | 2026-06-30 | 2026-06-30 12:12 | 2026-06-30 | 2026-06-30 14:58 | 2026-07-05 | 2026-07-04 17:15 |  |  |  |  | 2026-07-07 | 2026-07-09 12:08 | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-07-05 | 2026-07-07 16:13 | Site is Non-RTMI | 2026-06-21 | 2026-06-23 12:04 | 1404472 | 250158 | 0 | 0 | 0 | 0 | 1377781.06 | 238900 | 2026-07-04 17:17:31 +0530 | Anamika Dolai | Welcome call done : Yes Meeting Dates - 04/07/2026 IM date : NA DEM 1 : 05/07/2026 Possession date : Na 10% payment aligned : 10/07/2026 Periskope Number added : yes Escalation Matrix added : yes Price protection for 150 days from the NET date. | 2026-07-02 14:53:39 +0530 | Swami Vadnere | tried calling but no response | 2026-06-30 15:30:52 +0530 | Maasoumeh Raza | Some Image was uploaded | 2026-07-08 | 2026-07-07 16:24 | 2026-07-14 |  | Under Construction | 2026-08-07 | 2026-06-29 | 165463 | Ravi Roy
20703 | Turnkey | 2026-06-01 | Nilesh katkar | bhoomi pratishtha | MUM - GOR | Yes | [8 empty] | Moni Sahani |  | Active | Prospect | 10% Payment | 993756 | 133945 | 1339450 | 0 | 0 | 5 | 0 | 0 | 64806 | 430802 | 364203.2 |  |  | 2026-06-21 | 2026-07-09 17:24 | 2026-06-25 | 2026-07-09 19:07 | 2026-07-12 | 2026-07-10 13:46 | 2026-07-17 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-07-03 | 2026-07-03 19:26 | 2026-07-11 |  | 2026-07-11 |  | 2026-07-12 | [5 empty] | 2026-07-18 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-07-13 |  | Unknown | 2026-06-21 | 2026-06-25 14:11 | 1135127 | 204322 | 0 | 0 | 0 | 0 | 1135127.437 | 187426 | 2026-07-14 19:43:13 +0530 | Moni Sahani |  | 2026-07-13 10:38:53 +0530 | Bency Chacko | Onboarding Due: Checklist Reject - No offer emails pasted | 2026-07-08 12:42:34 +0530 | Priyanka Patel | CDP: | 2026-07-18 |  | 2026-07-25
20704 | Turnkey | 2026-06-01 | Amit Patel | Sudama Vallab | MUM - Thane | Yes | [8 empty] | Arifa Mohammed Hussain Shaikh |  | Active | Prospect | 10% Payment | 1804559 | 9999 | 0 | 0 | 0 | 3 | 0 | 170457 | 180456 | 847525 | 596122 |  |  | 2026-06-21 | 2026-06-23 12:06 | 2026-06-21 | 2026-06-24 19:28 | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-21 | 2026-06-23 11:28 | 0 | 0 | 0 | 0 | 0 | 0 | 1529287 | 275271 | 2026-07-03 11:12:23 +0530 | Anjali Singh | DCM: possesion - 1-2 months . | 2026-06-23 12:55:14 +0530 | Anjali Singh | DCM: Client Requirement Brief Amit PatelProject DetailsConfiguration: 2.5 BHKCarpet Area: 978 sq. ft.Floor: 10th Floor (current preference), alternatively 7th FloorPossession Timeline: 12 monthsFamily Members:ParentsCouple10-year-old son (Hitarth)Profession:DoctorService/JobEntrance / FoyerSafety door requiredShoe rack required (to be included in client scope discussion)No internal wall-mounted shoe rackLiving + Dining AreaRequirementsSofa seatingTV unit with display/storage units4-seater dining table2-seater swingMandir unitRecliner chairBalconyNo divider required in the main balcony connected to living/dining areaOpposite KitchenStore room requiredKitchenRequirementsAir fryer storage/provisionBase units and overhead units throughoutAdditional loft storage requiredParents' Bedroom (Behind Kitchen)Furniture & StorageQueen-size bedWardrobeDresser with mirrorAdditional storage unitsTV provision with storageSon's Room / Study Room (Hitarth)RequirementsStudy tableComputer tableWardrobeSingle bedCricket-themed elementsToy storageSoft board / white boardBalconyBalcony utilization to be considered (TBC)Master Bedroom (Couple)RequirementsQueen-size bedWardrobeTV provisionDresser with mirrorFoldable workstation / work-from-home setupBalconyStorage provision requiredAppliances Included in Budget3 TVs4 Air ConditionersRefrigeratorWashing MachineBudgetPreferred Budget: 1518 LakhsBudget includes appliancesMaximum Stretch Budget: 22 LakhsNext MeetingConcept Discussion Presentation (CDP)Tentative Schedule: Next Sunday, 3:00 PMClient will confirmThis version is ready to be shared internally with the design team or used as a client requirement document. | 2026-06-21 20:13:27 +0530 | Unknown | About the Customer **Callback Requested and Center Visit Intent** Customer is driving and requested a callback in 30 minutes. They intend to visit an experience center today. **Thane Experience Center Visit Confirmed** Customer confirmed a visit to the Thane experience center today at 5 PM with his wife and son (3 people total). **3 BHK Interior Design Needs** Customer requires interior design for a 3 BHK property, expected possession within a month, with a budget of approximately 20 lakhs. **WhatsApp Confirmation Sent** Agent confirmed appointment details and is sending a WhatsApp confirmation. | 2026-07-20 |  | 2026-07-27
20705 | Turnkey | 2026-06-01 | Azam Khan | Mira christ | MUM - Thane | Yes | [8 empty] | Subhan Khan |  | Active | Prospect | 10% Payment | 4055048 | 9999 | 4055048 | 0 | 0 | 18 | 0 | 395506 | 405505 | 1806112 | 1437926.8 |  |  | 2026-06-21 | 2026-06-21 20:55 | 2026-06-25 | 2026-06-25 11:56 | 2026-06-28 | 2026-06-27 10:40 | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-06-21 | 2026-06-21 20:37 | 3436482 | 618566 | 0 | 0 | 0 | 0 | 3436482 | 618566 | 2026-06-29 16:40:32 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-29 16:37:05 +0530 | Moksh Mehta | Some Image was uploaded | 2026-06-25 11:45:09 +0530 | Moksh Mehta | Some Image was uploaded | 2026-07-05 |  | 2026-07-12
20706 | Turnkey | 2026-06-01 | Laxmi air control Limited ( shiv kumar sharma ) sharma | L&T | MUM - GOR | Yes | Anjali Jain | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Ashutosh Singh |  | Active | Design | 20% Payment | 2535715 | 324963 | 3249634 | 0 | 0 | 3 | 0 | 0 | 182180 | 1024698 | 1003873.6 |  |  | 2026-06-21 | 2026-06-21 21:08 | 2026-06-26 | 2026-06-30 21:38 | 2026-07-03 | 2026-06-30 21:47 | 2026-07-13 | 2026-07-12 19:45 | 2026-07-18 |  | 2026-07-25 |  | 2026-06-30 | 2026-06-30 21:48 | 2026-07-01 | 2026-07-01 15:19 | 2026-07-01 | 2026-07-01 16:42 | 2026-07-04 | 2026-07-04 18:06 |  |  |  |  | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-05 | 2026-07-12 19:23 | Site is RTMI | 2026-06-21 | 2026-06-21 21:07 | 2753927 | 495706 | 0 | 0 | 0 | 0 | 2753927.1059 | 464978 | 2026-07-12 19:40:26 +0530 | Anjali Jain | DDM1: Foyer need to add one top cabinet on top of shoe rack mirror concept Kitchen need to add microwave unit remove aluminum shutter loft need to continue ref. sliding door mandir nned to add in study room drawer and shutter with cnc wooden flooring tile on tile wardrobe need to rework size false ceiling need to add in study room Living room Tv unit need to rework option need to share Bedroom 1 False ceiling profile light bedroom 2 Dresser unit final bedroom 3 Bed wall design need to share by client Bedroom 4 Dressing table need to consider as study table | 2026-07-04 18:11:11 +0530 | Christopher Macwan | Others: Welcome Call Done Welcome call done. Initial measurement done on 3rd July 2026 DEM Dates -Â DEM 1 â€“ Tentative on 8th July Wednesday 2nd Half DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-04 16:43:02 +0530 | Christopher Macwan | Called for welcome call but no answer. | 2026-07-13 | 2026-07-12 19:54 | 2026-07-19 |  | RTMI |  | 2026-06-30 | 324963 | Ravi Roy
20707 | Turnkey | 2026-06-01 | Shruti Samant | shrishti residency | MUM - GOR | Yes | [8 empty] | Harshaan Tiku |  | Active | Prospect | DCM Due | 1413574 | 9999 | 0 | 0 | 0 | 22 | 0 | 131358 | 141357 | 639213 | 491646.4 |  |  | 2026-06-21 | 2026-06-23 15:24 | 2026-06-24 | 2026-06-30 13:25 | 2026-06-27 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-06-21 | 2026-06-23 15:24 | 0 | 0 | 0 | 0 | 0 | 0 | 1200043 | 213531 | 2026-06-30 18:04:07 +0530 | Khushi Khandelwal | Some Image was uploaded | 2026-06-30 18:02:20 +0530 | Khushi Khandelwal | Some Image was uploaded | 2026-06-24 20:27:55 +0530 | Khushi Khandelwal | DCM: 2BHK AREA- 595 sqft MEMBERS- 5 POSESSION- RTMI CEILING HEIGHT- 9FT. ENTRANCE-Â Shoe unit LIVING & DINING AREA- Foldable dining- 2+2 Desk for work Sofa cum bedÂ TV unit with vertical storage n display KITCHEN- Ref. and washing on same side (service platform) Gas and sink on main platform side Appliaces- Microwave, chimney, air fryer, mixer juicer etc. Base+ wall+ Loft cabinet mandir on the main platform, small partition is needed to divide the space. MANDIR-36" WASH BASIN-36" BEDROOM-01 (Mother's bedroom) WardrobeÂ bed- queen size side table TV wall on wall with ledge foldable Study table in the niche Theme- Off white, beige tones BEDROOM-02 (Master bedroom) WardrobeÂ bed- queen size side table TV wall on wall with ledge Study table Theme-Off white, beige tones Washroom vanity in both BED AS PER VASTUÂ | 2026-07-11 |  | 2026-07-18
20708 | Turnkey | 2026-06-01 | Vishal Vatsal | SNN RAJ | BNG - HSR | Yes | [8 empty] | Nidhi Shaw |  | Active | Prospect | Onboarding Due | 1233965 | 172999 | 1726851 | 0 | 0 | 2 | 0 | 0 | 73794 | 493586 | 493586 |  |  | 2026-06-21 | 2026-07-07 11:54 | 2026-07-07 | 2026-07-08 11:18 | 2026-07-12 | 2026-07-13 12:36 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-13 | 2026-07-13 13:49 | 2026-07-14 | 2026-07-13 17:47 | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-21 | 2026-07-07 11:48 | 1463433 | 263418 | 0 | 0 | 0 | 0 | 1396299.366 | 230562 | 2026-07-14 23:16:57 +0530 | Nidhi Shaw | Others: | 2026-07-13 18:33:26 +0530 | Sanjana Swami | Possession Status: Under construction Under construction Completion Date: September 2026 Scope of Work: Modular + Painting (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM â€“ 18th July 2026 * DEM 1 â€“ 1st weekend of August 2026 * 10% Payment Stage â€“ 1st week of august (after 1st dem) *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) Design fee waiver (5%) Free Shoerack Offer Bonito Atelier - Living Room Upgrade Bonito Atelier - Kitchen Upgrade Bonito Atelier - Bedroom Upgrade Bonito Atelier - Studio Upgrade Laminate Upgrade Offer - June 26 Silver Coin Offer Final Closing Value Discussed: â‚¹ 12,33,965 Checklist terms - descoping, delay compensation are clear Agreement terms are not cleared Rejections: client mentioned that he will be paying the next 10% payment milestone by August 1st week after 1st dem. | 2026-07-13 18:13:11 +0530 | Sanjana Swami | OB initiated - number is not reachable | 2026-07-20 |  | 2026-07-27 |  |  |  | 2026-07-12 23:01 | 155660 | Nidhi Shaw
20709 | Turnkey | 2026-06-01 | Mr. MANJUNATH MASALI | Ruchira Park East | BNG - HRBR | Yes | Salpriyan Pm | Parasa Sri | Shibin Lal | [5 empty] | Kushal S |  | Active | Design | DEM1 | 917392 | 144999 | 1352286 | 0 | 0 | 6 | 0 | 0 | 38479 | 391246 | 342667.2 |  |  | 2026-06-21 | 2026-06-23 12:05 | 2026-06-25 | 2026-06-25 18:33 | 2026-06-28 | 2026-06-26 17:11 | 2026-07-17 |  | 2026-07-24 |  | 2026-07-31 |  | 2026-06-26 | 2026-06-30 11:49 | 2026-06-27 | 2026-07-07 14:50 | 2026-07-07 | 2026-07-09 16:33 | 2026-07-12 | 2026-07-12 12:34 |  |  |  |  | 2026-07-18 |  | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-07-13 |  | Unknown | 2026-06-21 | 2026-06-22 11:33 | 1148500 | 203785 | 0 | 0 | 0 | 0 | 1079120.6556 | 175236 | 2026-07-14 15:41:43 +0530 | Losii Athisa |  | 2026-07-12 12:35:24 +0530 | Parasa Sri | Welcome call done. Client is available for weekend meetings. client is checking for the initial measurement slots | 2026-07-09 16:32:45 +0530 | Athul Ajaykumar | OB Accepted - Had a word with the client. He gave the acknowledgement on call regarding the timeline. He agreed that he is okay with the timeline. Moving the OB | 2026-07-18 |  | 2026-07-25 |  | Under Construction | 2026-08-31 | 2026-06-26 | 144999 | Ravi Roy
20712 | Turnkey | 2026-06-01 | Esther | BDA Appartment | BNG - HRBR | Yes | Vishal Bandi | Parasa Sri | Surabhi Ravichandran | [5 empty] | Kushal S |  | Active | Design | DEM1 | 814029 | 83999 | 1117288 | 0 | 0 | 2 | 0 | 0 | 78807 | 353009 | 298214.4 |  |  | 2026-06-21 | 2026-06-23 11:59 | 2026-06-23 | 2026-06-25 13:00 | 2026-06-28 | 2026-07-03 13:04 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-03 | 2026-07-12 11:08 | 2026-07-04 | 2026-07-13 13:14 | 2026-07-13 | 2026-07-13 16:51 | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-21 | 2026-06-23 10:53 | 946854 | 170433 | 0 | 0 | 0 | 0 | 939196.8196 | 155075 | 2026-07-14 15:32:03 +0530 | Losii Athisa |  | 2026-07-13 16:48:35 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+10 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM â€“ This week * DEM 1 â€“ This weekends * 10% Payment Stage â€“ by 23rd July 2026 *No civil work planned *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Free Sofa Offer Free Hob & Chimney Offer Design fee waiver (5%) PM fee waiver (5%) Laminate Upgrade Offer - June 26 May'26 100% GST waiver Final Closing Value Discussed: â‚¹ 8,14,029 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-13 16:34:50 +0530 | Sanjana Swami | client is not responding | 2026-07-20 |  | 2026-07-27 |  | RTMI |  | 2026-06-30 | 9999 | Ravi Roy
20713 | Turnkey | 2026-06-01 | Akash | INFINITY GREEN WOODS | BNG - HRBR | Yes | Sandeep Madhukar Achari | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Design | DEM1 | 743680 | 94399 | 1044017 | 0 | 0 | 7 | 0 | 0 | 54337 | 326192 | 268752.4 |  |  | 2026-06-21 | 2026-06-23 12:27 | 2026-06-23 | 2026-06-23 16:17 | 2026-06-28 | 2026-06-30 12:15 | 2026-07-16 |  | 2026-07-23 |  | 2026-07-30 |  | 2026-06-30 | 2026-07-07 19:42 | 2026-07-01 | 2026-07-08 14:03 | 2026-07-08 | 2026-07-08 16:08 | 2026-07-11 | 2026-07-11 11:38 |  |  |  |  | 2026-07-17 |  | 2026-07-25 |  | 2026-07-26 |  |  |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 | [6 empty] | 2026-08-23 |  | 2026-09-01 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-04 |  |  |  | 2026-09-26 |  | 2026-09-28 |  | 2026-09-29 | [5 empty] | 2026-08-03 |  | 2026-07-12 |  | Unknown | 2026-06-21 | 2026-06-23 11:58 | 884760 | 159256 | 0 | 0 | 0 | 0 | 862514.1595 | 142412 | 2026-07-11 11:46:30 +0530 | Rajeshwari S | Welcome call done along with Sandeep Non RTMI Project. Expected possession in Sept. for IM - client will check for permission and confirm. Sandeep to cordinate on this. Design meeting is schedule in the first off on 18th July. Sandeep to confirm the timings to client Aligned with our process. informed about 10% payment. Will make the 10% payment on first meeting day. Project to go on hold after layout finalization if there is no confirmation on possession. | 2026-07-08 16:07:13 +0530 | Sanjana Swami | Possession Status: Under construction Under construction Completion Date: 1st week of September 2026 Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM â€“ Client will check with the builder for time and then let us know * DEM 1 â€“ Next weekends * 10% Payment Stage â€“ by 21st July 2026 (after 1st dem) *No civil work *Transaction will be B2C self funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: Silver Coin Offer Free Hob & Chimney Offer Free Shoerack Offer PM fee waiver (5%) May'26 100% GST waiver Laminate Upgrade Offer - June 26 Design fee waiver (5%) Final Closing Value Discussed: â‚¹ 7,43,680 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-07-08 13:58:46 +0530 | Shashank Singh | Others: Offer email | 2026-07-17 |  | 2026-07-24 |  | Under Construction | 2026-09-07 | 2026-06-28 | 9999 | Ravi Roy
20714 | Turnkey | 2026-06-01 | Mr. SUVEER KUMAR SINGH | Assetz Bloom & Dell | BNG - HRBR | Yes | Faizan Sharief | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Kaminahal Rahiman |  | Active | Design | 20% Payment | 1662272 | 274009 | 1900444 | 0 | 0 | 7 | 0 | 0 | 58445 | 715489 | 614328.8 |  |  | 2026-06-21 | 2026-06-23 12:08 | 2026-06-23 | 2026-06-23 16:23 | 2026-06-23 | 2026-06-23 18:02 | 2026-07-08 | 2026-07-08 12:18 | 2027-01-05 |  | 2027-01-12 |  | 2026-06-23 | 2026-06-24 10:54 | 2026-06-24 | 2026-06-24 11:28 | 2026-06-24 | 2026-06-24 16:42 | 2026-06-30 | 2026-06-30 18:55 |  |  |  |  | 2026-07-08 |  | 2027-01-07 |  | 2027-01-08 |  |  |  | 2027-01-15 |  | 2027-01-16 |  | 2027-01-17 |  | 2027-01-18 | [6 empty] | 2027-02-05 |  | 2027-02-14 |  | 2027-02-13 |  | 2027-02-14 |  | 2027-02-15 |  | 2027-02-17 |  |  |  | 2027-03-11 |  | 2027-03-13 |  | 2027-03-14 | [5 empty] | 2027-01-16 |  | 2026-07-01 | 2026-07-08 12:02 | Site is Non-RTMI | 2026-06-21 | 2026-06-23 12:03 | 1610546 | 289898 | 0 | 0 | 0 | 0 | 1863903.7831 | 307759 | 2026-07-14 15:34:26 +0530 | Losii Athisa |  | 2026-06-30 18:57:45 +0530 | Rajeshwari S | Welcome call done along with Surabhi and Faizan Non RTMI Project Possession expected in Oct. Price protection till Jan 2027 Estimation finalized for Rs.13,70,013/- post offers 10% will be paid on 18th July - Invoice to be raised. Client want to finalize the layout and than place the project on hold. DEM1 is scheduled 7th July - client to confirm on timings | 2026-06-30 13:02:42 +0530 | Kaminahal Rahiman | Some Image was uploaded | 2026-07-09 | 2026-07-08 12:21 | 2027-01-06 |  | Under Construction | 2026-11-30 | 2026-06-21 | 189999 | Ravi Roy
20715 | Turnkey | 2026-06-01 | Ashish Sharma | ALPINE VIVA | BNG - HRBR | Yes | [8 empty] | Shashank Singh |  | Active | Prospect | DCM Due | 1872836 | 9999 | 0 | 0 | 0 | 22 | 0 | 177285 | 187284 | 801507 | 696761.6 |  |  | 2026-06-21 | 2026-06-23 12:26 | 2026-06-23 | 2026-06-26 19:39 | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-05 |  | 2026-07-06 | [5 empty] | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-07 |  | Unknown | 2026-06-21 | 2026-06-23 12:05 | 0 | 0 | 0 | 0 | 0 | 0 | 1587149 | 285686 | 2026-06-24 11:49:16 +0530 | Keerthan M | Some Image was uploaded | 2026-06-24 11:40:12 +0530 | Keerthan M | DCM: Ashish Sharma 3BHK Duplex Foyer aquarium storage and wall detailingPartition Living TV unit with storage and shelves3+2 seater sofaUnder stairs - space for puppy Dining 6 seater tablewall detailingcrockery cum bar unit with aquariumhanging lightbeam covering Kitchen parallel kitchensink move to opp spacetop, bottom, one side loft Utility storage double bowl sinkWM, Janitor storage, PBR Queen bedwardrobe with loft and dresserconsole table FF Living work areastorage and work table MBR Male walk- in wardrobe space in FF living by making civil changesKing bedTV UnitBalcony Storage Bedroom 3 Queen bedWardrobe with dresserwall detailing | 2026-06-23 12:05:35 +0530 | Unknown | About the Customer **3BHK Interiors Needed in Bangalore** Customer is looking for full interiors for a 3BHK apartment in Whitefield, Bangalore, with possession expected in two weeks. The budget range provided is 10-15 lakhs. **Experience Center Visit Confirmation Pending** Customer is considering visiting the experience center today in the second half but needs to confirm and will inform the agent via WhatsApp. **Agent to Book Appointment and Send WhatsApp Invite** Agent needs to book an appointment and share the experience center location and visit confirmation via WhatsApp. | 2026-07-12 |  | 2026-07-19
20716 | Turnkey | 2026-06-01 | Sindhu Murthy | Nikoo homes | BNG - HRBR | Yes | Faizan Sharief | Rajeshwari S | Surabhi Ravichandran | [5 empty] | Raghavendra S |  | Active | Design | DEM1 | 1272171 | 175999 | 1765454 | 0 | 0 | 16 | 0 | 0 | 78435 | 518832 | 498904.8 |  |  | 2026-06-23 | 2026-06-23 12:34 | 2026-06-23 | 2026-06-23 13:57 | 2026-06-26 | 2026-06-23 16:01 | 2026-07-14 |  | 2026-08-07 |  | 2026-08-27 |  | 2026-06-23 | 2026-06-25 12:06 | 2026-06-24 | 2026-06-27 12:55 | 2026-06-27 | 2026-06-29 10:21 | 2026-06-30 | 2026-06-30 19:11 |  |  |  |  | 2026-07-15 |  | 2026-08-22 |  | 2026-08-23 |  |  |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-02 | [6 empty] | 2026-09-20 |  | 2026-09-29 |  | 2026-09-28 |  | 2026-09-29 |  | 2026-09-30 |  | 2026-10-02 |  |  |  | 2026-10-24 |  | 2026-10-26 |  | 2026-10-27 | [5 empty] | 2026-08-31 |  | 2026-07-10 |  | Unknown | 2026-06-23 | 2026-06-23 12:12 | 1496147 | 269306 | 0 | 0 | 0 | 0 | 1438580.653 | 237540 | 2026-06-30 19:50:31 +0530 | Rajeshwari S | Welcome call done along with Designer and DM Under construction project Expecting possession in July Client wants to start with the design phase Designer to call and confirm on the Initial measurement date and the design meeting, meanwhile she will discuss with her husband and confirm on the meeting. 10% will be paid in mid of July | 2026-06-28 18:38:27 +0530 | Raghavendra S | Updated correct address, kindly tick of the task | 2026-06-27 13:38:17 +0530 | Sanjana Swami |  | 2026-07-15 |  | 2026-08-08 |  | Under Construction | 2026-07-31 | 2026-06-21 | 175999 | Ravi Roy
20717 | Turnkey | 2026-06-01 | Madhu Biradar | 3 BHK | BNG - HRBR | No Estimate | [8 empty] | Mohammed Rasick |  | Active | Prospect | DCM Due | 0 | 9999 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-21 | 2026-06-23 12:23 | 2026-06-30 |  | 2026-06-30 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-06-21 | 2026-06-23 12:21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-14 15:28:21 +0530 | Losii Athisa |  | 2026-07-02 11:51:34 +0530 | Priyanka Gs | Recap: 20717 - Design Consultation Meeting (DCM) with the customer 30 June ¦ Meeting ¦ Microsoft Teams | 2026-06-23 12:21:06 +0530 | Unknown | About the Customer **Possession Delayed to December** Customer's property possession is delayed to December. Customer stated they will only proceed with interior design discussions once the possession date is confirmed by the builder. **Budget and Offer Awareness** Customer's budget for a 3BHK is between 10 to 15 lakhs. Customer is aware of the ongoing 15th-year anniversary offers, including GST waivers and studio vouchers. **Experience Center Visit Next Weekend** Customer agreed to visit the experience center next weekend, after confirming possession. Agent will arrange a callback for them. **Appointment Scheduled for Next Week** Customer agreed to visit the experience center the following week, not tomorrow. Agent confirmed they would share details via WhatsApp. **Follow-up in 3-4 Months** Agent proposed calling the customer back in three to four months to get an update on the possession status. | 2026-07-11 |  | 2026-07-18
20718 | Turnkey | 2026-06-01 | Yogesh Shah | Bhoomi | MUM - GOR | Yes | [8 empty] | Manasi Patil |  | Active | Prospect | 10% Payment | 2742765 | 9999 | 0 | 0 | 0 | 15 | 0 | 264278 | 274277 | 1176116 | 1018096 |  |  | 2026-06-21 | 2026-06-23 13:26 | 2026-06-30 | 2026-06-30 15:13 | 2026-06-30 |  | 2026-07-07 |  | 2026-07-14 |  | 2026-07-21 |  | 2026-06-30 |  | 2026-07-01 |  | 2026-07-01 |  | 2026-07-02 | [5 empty] | 2026-07-08 |  | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-08-23 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-24 |  | 2026-08-26 |  |  |  | 2026-09-17 |  | 2026-09-19 |  | 2026-09-20 | [5 empty] | 2026-07-25 |  | 2026-07-03 |  | Unknown | 2026-06-21 | 2026-06-23 13:25 | 0 | 0 | 0 | 0 | 0 | 0 | 2327921 | 414843 | 2026-06-30 16:08:54 +0530 | Rahul Agrawal | CDP: CX WILL TAKE DECISION AFTER A SITE VISIT OF ONGOING OR COMPLETED SITE. | 2026-06-30 15:53:52 +0530 | Rahul Agrawal | Some Image was uploaded | 2026-06-30 15:18:11 +0530 | Rahul Agrawal | DCM: Its a family of 2 (couple) daughters keeps visiting FOYER safety doorsoe rack LIVING ROOM Tv unitsingle curve sofa small crockery unit along with mandir unit 4 seating dining table KITCHEN Base cabinets top cabinets loft cabinet either side roller shutter Master Bedroom queen bed side tableswardrobes full heightedtv unit VANITY UNITS IN WASHROOM SOFT CIVIL paintingfalse ceilingelectrical BUDGET - INCLUDING CIVIL OF 40 LAKHS *THE DCM WAS CONDUCYED ON SITE VISIT, HENCE WAS NOT ABLE TO RECORD* | 2026-07-08 |  | 2026-07-15
20720 | Turnkey | 2026-06-01 | Mamta trivedi | Vidyalankar chs | MUM - GOR | Yes | Saif Shaikh | Christopher Macwan | Shantanu Parakh | [5 empty] | Manasi Patil |  | Active | Preproduction | DEM2 | 1323151 | 264630 | 1762870 | 0 | 0 | 6 | 0 | 0 | 0 | 596400 | 462121.2 |  |  | 2026-06-23 | 2026-06-25 14:11 | 2026-06-25 | 2026-06-25 18:56 | 2026-06-28 | 2026-06-25 20:11 | 2026-07-08 | 2026-07-07 21:03 | 2026-07-13 |  | 2026-07-31 |  | 2026-06-25 | 2026-06-26 17:45 | 2026-06-26 | 2026-06-26 19:33 | 2026-06-26 | 2026-06-30 19:30 | 2026-07-03 | 2026-07-03 16:16 |  |  |  |  | 2026-07-07 | 2026-07-09 10:56 | 2026-07-26 |  | 2026-07-27 |  |  |  | 2026-08-03 |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 | [6 empty] | 2026-08-24 |  | 2026-09-02 |  | 2026-09-01 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-05 |  |  |  | 2026-09-27 |  | 2026-09-29 |  | 2026-09-30 | [5 empty] | 2026-08-04 |  | 2026-07-04 | 2026-07-07 20:39 | Site is RTMI | 2026-06-23 | 2026-06-25 14:10 | 1493957 | 268912 | 0 | 0 | 0 | 0 | 1487555.9903 | 246717 | 2026-07-03 16:29:03 +0530 | Manasi Patil | Onboarding Due: | 2026-07-03 16:18:58 +0530 | Christopher Macwan | Welcome call done. Initial measurement aligned for 4th July 2026, Saturday, at 11:30am. DEM Dates -Â DEM 1 - Tentatively on Tuesday, 7th July 2026 in the 2nd half DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-30 18:08:38 +0530 | Bency Chacko | Some Image was uploaded | 2026-07-08 | 2026-07-07 21:07 | 2026-07-14 |  | RTMI |  | 2026-06-25 | 176286 | Ravi Roy
20721 | Turnkey | 2026-06-01 | SUBHLAGAN.COM PRIVATE LIMITED (Anamika Kirtania) | Dosti Mezzo | MUM - GOR | Yes | Rajnish Mishra | Christopher Macwan | Safalta Karkera | [5 empty] | Mrunali Mitkari |  | Active | Design | DEM1 | 1714108 | 236369 | 2273700 | 0 | 0 | 11 | 0 | 0 | 106453 | 754241 | 617045.2 |  |  | 2026-06-21 | 2026-07-01 13:45 | 2026-06-24 | 2026-07-02 13:07 | 2026-07-05 | 2026-07-03 14:20 | 2026-07-15 |  | 2026-07-22 |  | 2026-07-29 |  | 2026-07-03 | 2026-07-03 17:55 | 2026-07-04 | 2026-07-03 19:01 | 2026-07-03 | 2026-07-04 12:50 | 2026-07-10 | 2026-07-10 19:31 |  |  |  |  | 2026-07-16 |  | 2026-07-24 |  | 2026-07-25 |  |  |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 |  | 2026-08-04 | [6 empty] | 2026-08-22 |  | 2026-08-31 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-01 |  | 2026-09-03 |  |  |  | 2026-09-25 |  | 2026-09-27 |  | 2026-09-28 | [5 empty] | 2026-08-02 |  | 2026-07-11 |  | Site is RTMI | 2026-06-21 | 2026-06-23 16:08 | 1926864 | 346835 | 0 | 0 | 0 | 0 | 1920443.556 | 317089 | 2026-07-10 19:32:54 +0530 | Christopher Macwan | Others: Welcome call done. Initial measurement not done as would receive possession by end of July DEM Dates -Â DEM 1 â€“ weekends preferred 18th or 19th July second half(Saturday or sunday) DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - end of July 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-07 14:13:22 +0530 | Hamza Choudhary | CDP RECORDING | 2026-07-07 14:10:29 +0530 | Hamza Choudhary | DCM RECORDING | 2026-07-16 |  | 2026-07-23 |  | Under Construction | 2026-07-20 | 2026-06-30 | 9999 | Ravi Roy
20722 | Turnkey | 2026-06-01 | Shalini Satish Naik | Sonam Indraneel | MUM - GOR | Yes | Zoya Ansari | Christopher Macwan | Kashmira Nerurkar | [5 empty] | Saloni Sagwekar |  | Active | Design | DEM1 | 1908819 | 234959 | 2349590 | 0 | 0 | 5 | 0 | 0 | 146805 | 852869 | 674186 |  |  | 2026-06-23 | 2026-06-26 20:11 | 2026-07-01 | 2026-07-01 18:40 | 2026-07-04 | 2026-07-01 18:58 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-01 | 2026-07-09 19:38 | 2026-07-02 | 2026-07-09 20:03 | 2026-07-09 | 2026-07-10 18:49 | 2026-07-14 | 2026-07-14 19:14 |  |  |  |  | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-23 | 2026-06-23 18:07 | 1991178 | 358412 | 0 | 0 | 0 | 0 | 1991177.7828 | 343587 | 2026-07-14 19:18:09 +0530 | Christopher Macwan | Others: Welcome call done. Initial measurement not done as would receive possession by end of August. DEM Dates -Â DEM 1 â€“ Customer prefers DEM1 only after Initial Measurement DEM 2 - TBD DEM 3 - TBD Possession date : Future Possession - End of August 2026 Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-07-10 18:48:44 +0530 | Athul Ajaykumar | We will get permission to start the interior work after OC. OC is by August end. Moving the OB | 2026-07-10 14:12:36 +0530 | Athul Ajaykumar | Possession Status: Client has no idea regarding the possession. Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 99 + 20 Business days Detailed timelines were explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline - 10, 10, 40, 40 Plan of Action Discussed During the Call: * IM â€“ Tentatively scheduled for (13th July) * DEM 1 â€“ Tentatively scheduled for (20th July) * 20% already close * B2C - Self * Civil work â€“ Yes (small Wall demolition) Please note that the above timelines are tentative and subject to task closures and overall project progress. Offers Discussed During the Call: PM fee waiver (5%) May'26 100% GST waiver Final Closing Value Discussed: 19,08,819 Checklist terms â€“ descoping and agreement terms are cleared Rejection: The client is unsure about the possession status and stated that he will confirm it with the sales team by the end of the day. The client stated that he has made only two paymentsâ€”â‚¹9,999 and â‚¹2,24,960 (total: â‚¹2,34,959). However, the overview page incorrectly reflects three paymentsâ€”â‚¹9,999, â‚¹2,24,960, and an additional â‚¹2,24,960â€”showing a total of â‚¹4,59,919. The client reported this discrepancy. | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2026-08-31
20724 | Turnkey | 2026-06-01 | Vivek Chavan | Narang Privado | MUM - Thane | Yes | [8 empty] | Shreyash Kotecha |  | Active | Prospect | 10% Payment | 1499991 | 10000 | 0 | 0 | 0 | 6 | 0 | 139999 | 149999 | 599996 | 599996.4 |  |  | 2026-06-24 | 2026-06-24 19:01 | 2026-06-28 | 2026-06-30 11:34 | 2026-07-12 |  | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-07-12 |  | 2026-07-13 |  | 2026-07-13 |  | 2026-07-14 | [5 empty] | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-24 | 2026-06-24 18:28 | 0 | 0 | 0 | 0 | 0 | 0 | 1686904.29 | 278548 | 2026-06-30 11:12:38 +0530 | Bhawaya Goyal | Some Image was uploaded | 2026-06-30 11:12:16 +0530 | Bhawaya Goyal | DCM: Recap: 20724 - Design Consultation Meeting (DCM) with the customer Sunday, June 28 ¦ Meeting ¦ Microsoft Teams | 2026-06-30 11:11:38 +0530 | Bhawaya Goyal | DCM: Client: Vivek Chavan Configuration: 3 BHK Carpet Area: 1128 sq.ft. Profession: IT Possession: October Theme: Modern Luxury with Pastel Colours Orientation: East-facing towards Deck CDP: 5th July ¦ 3:00 PM Budget: 1518 Lakhs (excluding white goods) FoyerSafety doorDecorative wall panelling with nameplateConsole-cum-shoe rack inside foyer Living & Dining3+2 seater sofa6-seater dining tableTV unitCrockery unit with mirror and painting conceptMandirHidden panelling concept integrating the entrance to the daughter's room DeckGreen plantationSwing (if feasible) KitchenFully modular kitchenQuartz countertop (civil modification required)Base unitsWall unitsLoft storage Utility AreaWall-mounted detergent/storage cabinetFloor covering for the open utility space Parents' Bedroom (70+ Years)WardrobeQueen-size bedSide tablesDressing mirrorAccent chair Daughter's Bedroom (Ages 14 & 4)Theme: Purple/LavenderWardrobeQueen-size hydraulic/storage bedSide tableStudy tableDressing mirror Master BedroomWardrobeQueen-size hydraulic/storage bedSide tablesWorkstationDressing mirror WashroomsVanity unitsOpen shelf above WC area | 2026-07-20 |  | 2026-07-27
20725 | Sub Project |  | Shagun Agarwal | Sumadhura Folium | BNG - HSR |  | Manoj Kumar R | Akshay Ds | Kowshik |  | Sethuragavan R | Shivakumar Ms | Jairam Joshi | Murali S |  | Sunil Kumar S M | Active | Production | Production | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-06-24 | 2026-06-24 13:39 | 2026-06-25 | 2026-06-24 13:39 | 2026-06-24 | 2026-06-24 13:39 | 2026-06-25 | 2026-06-24 13:40 | 2026-06-25 | 2026-06-24 13:41 | 2026-06-25 | 2026-06-24 13:44 | 2026-06-24 | 2026-06-24 13:39 | 2026-06-25 | 2026-06-24 13:39 | 2026-06-24 | 2026-06-24 13:39 | 2026-06-25 | 2026-06-24 13:39 |  |  |  |  | 2026-06-24 | 2026-06-24 13:40 | 2026-06-25 | 2026-06-24 13:42 | 2026-06-25 | 2026-06-24 13:42 |  |  | 2026-06-25 | 2026-06-25 12:04 | 2026-06-26 | 2026-07-09 13:57 | 2026-07-10 | 2026-07-09 14:54 | 2026-07-10 | 2026-07-09 14:54 |  |  |  |  | 2026-07-09 15:40 | 2026-07-14 | 2026-07-13 20:14 | 2026-07-22 |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-27 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-07 |  | 2026-08-08 | [5 empty] | 2026-07-09 | 2026-07-09 14:20 | 2026-06-25 | 2026-06-24 13:39 | Unknown | 2026-06-24 | 2026-06-24 13:39 | 0 | 0 | 0 | 0 | 42373 | 7627 | 42373 | 7627 | [9 empty] | 2026-06-25 | 2026-06-24 13:40 | 2026-06-25 | 2026-06-24 13:41
20726 | Turnkey | 2026-06-01 | Madhukar Shilpa Tata |  | BNG - HSR |  | Muskan Agarwal | Abhinandan K S | Soumya KP |  | RaviKumar Battala | Yogeshwaran | Ranjith Kumar |  | Ravikiran K | Sunil Kumar S M | Active | Preproduction | DEM2 | 1646338 | 414404 | 2145034 | 0 | 0 | 4 | 0 | 0 | 0 | 573399 | 658535.2 |  |  | 2026-06-24 | 2026-06-24 18:02 | 2026-06-25 | 2026-06-25 15:04 | 2026-06-27 | 2026-06-27 17:36 | 2026-07-09 | 2026-07-08 18:02 | 2026-07-14 |  | 2026-07-21 |  | 2026-06-27 | 2026-06-29 10:50 | 2026-06-28 | 2026-06-29 15:35 | 2026-06-29 | 2026-07-01 13:01 | 2026-07-03 | 2026-07-03 18:45 |  |  |  |  | 2026-07-08 | 2026-07-11 16:23 | 2026-07-16 |  | 2026-07-17 |  |  |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 |  | 2026-07-27 | [6 empty] | 2026-08-14 |  | 2026-09-06 |  | 2026-09-05 |  | 2026-09-06 |  | 2026-09-06 |  | 2026-09-08 |  |  |  | 2026-10-11 |  | 2026-10-13 |  | 2026-10-15 | [5 empty] | 2026-07-25 |  | 2026-07-05 | 2026-07-08 14:17 | Site is RTMI | 2026-06-24 | 2026-06-24 17:43 | 1817825 | 327208 | 0 | 0 | 0 | 0 | 1817824.639 | 299941 | 2026-07-01 13:01:04 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: civil work (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 160 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: *Site is accessible * IM This week * DEM 1 Next week * 10% Payment Stage 11th July 2026 *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 18,17,826 Offers Discussed During the Call: Referred Customer Discount Laminate Upgrade - Jun 26 Campaign 100% GST Waiver PM fee waiver (5%) Design fee waiver (5%) Final Closing Value Discussed: 16,46,339 | 2026-06-30 18:27:00 +0530 | Sanjana Swami |  | 2026-06-30 11:18:10 +0530 | Sanjana Swami |  | 2026-07-09 | 2026-07-08 18:11 | 2026-07-15 |  | RTMI |  | 2026-06-23 | 214404 | Ravi Roy
20730 | Turnkey | 2026-06-01 | Shruti | Soho By Bren | BNG - HSR | Yes | [8 empty] | Muralikrishna Udupi |  | Active | Prospect | DCM Due | 2285790 | 9999 | 0 | 0 | 0 | 19 | 0 | 218580 | 228579 | 956970 | 871662.4 |  |  | 2026-06-24 | 2026-06-26 12:14 | 2026-06-25 |  | 2026-06-27 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-06-27 |  | 2026-06-28 |  | 2026-06-28 |  | 2026-06-29 | [5 empty] | 2026-07-05 |  | 2026-07-13 |  | 2026-07-14 |  |  |  | 2026-07-21 |  | 2026-07-22 |  | 2026-07-23 |  | 2026-07-24 | [6 empty] | 2026-08-11 |  | 2026-08-20 |  | 2026-08-19 |  | 2026-08-20 |  | 2026-08-21 |  | 2026-08-23 |  |  |  | 2026-09-14 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | 2026-07-22 |  | 2026-06-30 |  | Unknown | 2026-06-24 | 2026-06-24 17:31 | 0 | 0 | 0 | 0 | 0 | 0 | 1937110 | 348679 | 2026-06-26 16:58:20 +0530 | Rajasekar Ranganathan | Requirement Meeting MOMClient Name: Ms. Shruthi Project: Soho by Bren Expected Handover: September Family Members: 3 Adults + 1 Son Budget: To Be Finalized Furniture: Entire home to have new furniture. Entrance / FoyerShoe rack with storage for approximately 30 pairs.Decorative wall concept for the entrance.Living RoomTV unit with storage.5-seater sofa.Feature wall / wall design concept.Study AreaFolding study table.Book storage unit for approximately 80 books.Dining Area6-seater dining table.Niche pooja unit with one idol space and bottom storage.KitchenBreakfast counter with storage.Space for a single-door refrigerator.Tall unit for built-in oven.Storage for daily essentials.Utility AreaSpace for washing machine and dryer.Provision for 2 LPG cylinders.Dishwasher unit.Overhead storage above the washing machine.Granite countertop to be included.Dado tile installation.Common BathroomVanity unit with mirror cabinet.Kids Bedroom (KBR)Wardrobe cabinet.Single bed.Feature wall design.Dedicated workstation.Meditation space.Master Bedroom (MBR)Wardrobe cabinet.Dresser unit.King-size bed.Folding study/work table.Feature wall design.Attached WashroomsVanity unit with mirror.Parents Bedroom (PBR)Wardrobe with loft storage.Queen-size bed.Dressing unit.Folding study/work table.Feature wall design.BalconyOpen ledges/shelves for planters and decorative plants. | 2026-06-26 12:10:18 +0530 | Muralikrishna Udupi | IT Couple. 3bhk -Budget-13-14(Under 15 lakh). Visited Bonito 10 months back, VDNB Client. Have visited other few companies but has not got clarity. Needs a clear and transparent discussion. |  |  |  | 2026-07-05 |  | 2026-07-12
20733 | Turnkey | 2026-06-01 | Karthik Radhakrishnan |  | BNG - HSR | Yes | Vidya Sree | Akshay Ds | Soumya KP | [5 empty] | Nidhi Shaw |  | Active | Design | 20% Payment | 1150617 | 145471 | 2007050 | 0 | 0 | 4 | 0 | 0 | 84652 | 501890 | 418603.6 |  |  | 2026-06-24 | 2026-06-26 16:25 | 2026-06-25 | 2026-06-27 20:47 | 2026-06-30 | 2026-06-29 11:43 | 2026-07-15 | 2026-07-11 11:30 | 2027-04-05 |  | 2027-04-12 |  | 2026-06-29 | 2026-07-02 19:22 | 2026-06-30 | 2026-07-02 19:28 | 2026-07-02 | 2026-07-04 12:06 | 2026-07-09 | 2026-07-08 19:12 |  |  |  |  | 2026-07-11 |  | 2027-04-07 |  | 2027-04-08 |  |  |  | 2027-04-15 |  | 2027-04-16 |  | 2027-04-17 |  | 2027-04-18 | [6 empty] | 2027-05-06 |  | 2027-05-15 |  | 2027-05-14 |  | 2027-05-15 |  | 2027-05-16 |  | 2027-05-18 |  |  |  | 2027-06-09 |  | 2027-06-11 |  | 2027-06-12 | [5 empty] | 2027-04-16 |  | 2026-07-09 | 2026-07-11 11:16 | Site is Non-RTMI | 2026-06-24 | 2026-06-25 18:16 | 1700890 | 306160 | 0 | 0 | 0 | 0 | 1455372 | 261967 | 2026-07-10 11:58:07 +0530 | Vidya Sree |  | 2026-07-09 12:32:52 +0530 | Vidya Sree | Minutes of Meeting held on Date: Attendees: Discussion: Project kt from Priyamvada ï»¿ Based on meeting, below is a list of all the requirements that were discussed during the meeting: Mr.Karthik -MOM Living & Dining : 1.Addition of Display wall cabinet behind the sofa 2.Pooja unit with pullout seater (Reference to be shared by Customer ) 3.Behind sofa ,wall concept to be done as per reference image Kitchen: 1.Addition of loft above the chimney wall due to existing chajja Kids bedroom: 1.Addition of loft above the door due to existing chajja | 2026-07-04 12:05:19 +0530 | Sanjana Swami | OB accept | 2026-07-12 | 2026-07-11 11:34 | 2027-04-06 |  | Under Construction | 2027-03-05 | 2026-06-27 | 145471 | Ravi Roy
20735 | Turnkey | 2026-06-01 | R S Shantaram | Assesst 360 | BNG - HSR | Yes | [8 empty] | Chanakya Panigrahi |  | Active | Prospect | 10% Payment | 2603300 | 209999 | 2603300 | 0 | 0 | 12 | 0 | 50331 | 260330 | 1055366 | 1027274.4 |  |  | 2026-06-24 | 2026-06-24 20:06 | 2026-06-26 | 2026-07-02 08:41 | 2026-07-03 | 2026-07-07 11:12 | 2026-07-14 |  | 2026-07-21 |  | 2026-07-28 |  | 2026-07-07 |  | 2026-07-08 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | 2026-07-15 |  | 2026-07-23 |  | 2026-07-24 |  |  |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 |  | 2026-08-03 | [6 empty] | 2026-08-21 |  | 2026-08-30 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-08-31 |  | 2026-09-02 |  |  |  | 2026-09-24 |  | 2026-09-26 |  | 2026-09-27 | [5 empty] | 2026-08-01 |  | 2026-07-10 |  | Unknown | 2026-06-24 | 2026-06-24 20:04 | 2206187 | 397113 | 0 | 0 | 0 | 0 | 2206187 | 397113 | 2026-07-07 11:15:48 +0530 | Priyamvada PV | CDP changes : 1. Partition above storage open & closed (ref to be discussed) - will be done in design phase, added paneling with rafters price 2. Pooja- pillars to be at front with tall glass shutters on either sides for keeping all Ganesh collections, base storage 2.5'H- done top projection (pergola) & pillars to be in teak wood finish (custom wok) but scope not in BD 3. BF front to have light shade rafters- will be done in design phase, added paneling with rafters price 4. Utility wall storage closed instead of ledges - done 5. Utility wall storage above WM area - done 6. MBR U shape WR with glass top door in centre - done 7. Left & right WRs to have bottom drawer - done 8. Used cloth unit on left side for both rooms - done 9. MBR - option straight HB design - noted 10. KBR - study table to be removed, dresser on right of WR with glass tall unit on left above drawer for dresser storage, drawer to be extended WR to be 2.5'W - done 11. KBR HB wall paint, wallpaper, trims to be excluded 12. C vanity, PBR vanity - wall storage behind mirror space 2'Wx2'H - done 13. HT - L shape sofa cum bed space no Murphy bed, storage below TV ledge - done 14. PBR - WR behind door with loft to be added - done 15. KBR, MBR vanity- wall storage 1.2'Wx2'Hx8"D with glass shutter on either sides - done | 2026-06-28 11:17:54 +0530 | Chanakya Panigrahi | CX Name: Shantaram Profession: 60 is a Doctor Property: 4 BHK Budget: 18 Lakhs (Strict Final Budget) Possession: December 2026 Site Access: September 2026 Family Members: 4 Adults Challenging Points18L is the customer's strict final budget with very limited flexibility.Due to their busy professional schedule, they do not have time to explore the market or compare multiple vendors.Being a Bengaluru local, they are also evaluating local vendors, making pricing and value comparison important.Selling PointsPrice Protection: Lock today's pricing despite possession being in Dec'26.Holding Period: Secure the project now and start execution closer to site access in Sep'26.FOMO on 18% GST Waiver: Highlight the potential savings by onboarding before the applicable offer ends. | 2026-06-24 20:02:39 +0530 | Unknown | About the Customer **Bangalore 4 BHK Handover December** Customer Shantaram's 4 BHK property in Bangalore is scheduled for handover in December. He is interested in end-to-end interior design services for his kitchen, wardrobes, living room, and balcony. **Budget and Visit Hesitation Resolved** Customer initially hesitated on budget and experience center visit, but agreed after agent clarified pricing and benefits. **Experience Center Visit Confirmed Today 6 PM** Customer and his wife will visit the Bonito Designs experience center in HSR Layout today at 6:00 PM IST. **Floor Plan to be Shared Post Confirmation** Customer will share the floor plan via WhatsApp after receiving a confirmation message from the agent. | 2026-07-15 |  | 2026-07-22 |  |  |  | 2026-07-07 16:01 | 200000 | Varun Mandana
20738 | Turnkey | 2026-06-01 | Priti Mange | Nilkanthvihar | MUM - GOR | Yes | Neha Yadav | Vishakha Vaishnav | Safalta Karkera | [5 empty] | Saloni Sagwekar |  | Active | Design | DEM1 | 2300055 | 307440 | 3074399 | 0 | 0 | 11 | 0 | 0 | 152571 | 1021868 | 818176.4 |  |  | 2026-06-24 | 2026-06-26 20:09 | 2026-06-25 | 2026-06-30 16:37 | 2026-06-30 | 2026-07-02 17:28 | 2026-07-13 |  | 2026-07-20 |  | 2026-07-27 |  | 2026-06-29 | 2026-06-30 00:19 | 2026-07-03 | 2026-07-03 18:48 | 2026-07-03 | 2026-07-04 17:04 | 2026-07-08 | 2026-07-08 15:48 |  |  |  |  | 2026-07-14 |  | 2026-07-22 |  | 2026-07-23 |  |  |  | 2026-07-30 |  | 2026-07-31 |  | 2026-08-01 |  | 2026-08-02 | [6 empty] | 2026-08-20 |  | 2026-08-29 |  | 2026-08-28 |  | 2026-08-29 |  | 2026-08-30 |  | 2026-09-01 |  |  |  | 2026-09-23 |  | 2026-09-25 |  | 2026-09-26 | [5 empty] | 2026-07-31 |  | 2026-07-09 |  | Unknown | 2026-06-24 | 2026-06-25 11:42 | 2605423 | 468976 | 0 | 0 | 0 | 0 | 2605422.489 | 414010 | 2026-07-08 15:45:13 +0530 | Vishakha Vaishnav | Welcome call done : 8/7/2026 Meeting Dates IM date : Can be done after civil work is completed DEM 1 : need to align this week Possession date : renovation 10% payment aligned : after dem 1 Periscope Number added : Yes Escalation Matrix added : Yes Price protection for 150 days from the NET date. | 2026-07-07 16:06:10 +0530 | Pratima Kajwe | Title: Design Consultation Meeting Project No: 20738 Client: Priti Mange Hi, Minutes of Meeting (MOM) Residence Planning Discussion Client: Priti Mange Target Possession/Move-in: October 2026 Bedroom 1 Guest RoomMurphy bed with sofa arrangement. Wardrobes to be provided on both sides of the bed. Chajja area to be incorporated into the room to increase usable space. Bedroom 2 Daughters Room (20 & 16 years)Walk-in wardrobe. Queen-size bed. Dresser unit. Study table. TV unit. Bedroom 3 Parents RoomKing-size bed. Wardrobe with maximum storage capacity. TV unit. Bookshelf. Bedroom 4 Fathers RoomQueen-size bed along with an additional single bed. Wardrobe space. Dresser unit. Powder bathroom to be incorporated by utilizing a portion of the living room and creating a dedicated passage. Civil & Plumbing ModificationsBasin plumbing line to be shifted as discussed. Complete flooring replacement proposed. Civil work to be executed through an external contractor as suggested by the client. Living & Dining AreaTV unit with maximum seating capacity. Seating arrangement for approximately 810 people. Provision for an 8-seater dining table. Kitchen & MandirMandir room to be positioned on the left side. Kitchen to be positioned on the right side. Balcony and entrance extension area to be integrated into the kitchen space. Island kitchen required. Dishwasher provision to be incorporated. Mandir Area RequirementsDedicated dry storage area. Washable wall finishes for easy maintenance and cleaning of diya stains. Provision for either a marble mandir or Corian mandir. Additional RequirementsBeds in all bedrooms to be without storage. Shoe storage required for approximately 50 pairs of shoes. | 2026-07-07 16:04:50 +0530 | Pratima Kajwe | 20738 - Design Consultation Meeting (DCM) with the customer-20260625_112050UTC-Meeting Recording.mp4 | 2026-07-14 |  | 2026-07-21 |  | RTMI |  | 2026-06-30 | 307440 | Ravi Roy
20741 | Turnkey | 2026-06-01 | Dnyaneshwar Dapkekar | DOSTI WEST COUNTY | MUM - Thane | Yes | [8 empty] | Prashant Panigrahi |  | Active | Prospect | 10% Payment | 1268041 | 9999 | 0 | 0 | 0 | 16 | 0 | 116805 | 126804 | 567938 | 446494.8 |  |  | 2026-06-25 | 2026-06-25 20:04 | 2026-06-25 | 2026-06-29 14:08 | 2026-06-29 |  | 2026-07-06 |  | 2026-07-13 |  | 2026-07-20 |  | 2026-06-29 |  | 2026-06-30 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | 2026-07-07 |  | 2026-07-15 |  | 2026-07-16 |  |  |  | 2026-07-23 |  | 2026-07-24 |  | 2026-07-25 |  | 2026-07-26 | [6 empty] | 2026-08-13 |  | 2026-08-22 |  | 2026-08-21 |  | 2026-08-22 |  | 2026-08-23 |  | 2026-08-25 |  |  |  | 2026-09-16 |  | 2026-09-18 |  | 2026-09-19 | [5 empty] | 2026-07-24 |  | 2026-07-02 |  | Unknown | 2026-06-25 | 2026-06-25 20:03 | 0 | 0 | 0 | 0 | 0 | 0 | 1076854 | 191186 | 2026-06-29 11:59:31 +0530 | Krutika Vernekar | DCM: MOM Client DiscussionProject DetailsProject: Dnyaneshwar Parkview (Resale)Builder: Doshi West County Phase ECarpet Area: Approx. 664 sq.ft.Floor: 24th FloorProfession: Gas AgencyFamily Members: 6Current Residence: Bramhand Phase (Rented)Parents: 60+ yearsChildren: 2 (Ages 13 & 11)Possession Date: 1st JulyEntrance: EastWestBudgetScope: False Ceiling + Painting + Electrical + Interior WorksEstimated Budget: 1215 LakhsLiving RoomLoose shoe rack.Safety door.TV unit for 55-inch TV.3-seater sofa.3-seater dining set.KitchenMandir unit.Base units.Wall units with loft on one side.No washing machine inside the kitchen.Gas pipeline provision required.Bedroom 1 Kids' BedroomQueen-size bed with hydraulic storage.Wardrobe with loft.Side table.Mirror.Wardrobe shutters with mirror finish.Master BedroomQueen-size bed with hydraulic storage.Side tables with mirrors.Wardrobe (without loft).vanity units. | [6 empty] | 2026-07-07 |  | 2026-07-14
20743 | Turnkey | 2026-06-01 | Sudish Krishna | Legacy saviero | BNG - HRBR | Yes | [8 empty] | Mohammed Rasick |  | Active | Prospect | Onboarding Due | 1393370 | 389999 | 1918572 | 0 | 0 | 3 | 0 | 0 | 0 | 460720 | 542651.2 |  |  | 2026-06-25 | 2026-07-06 17:45 | 2026-07-02 | 2026-07-08 15:46 | 2026-07-11 | 2026-07-09 11:05 | 2026-07-18 |  | 2026-07-25 |  | 2026-08-01 |  | 2026-07-09 | 2026-07-09 11:07 | 2026-07-10 | 2026-07-12 14:40 | 2026-07-12 |  | 2026-07-13 | [5 empty] | 2026-07-19 |  | 2026-07-27 |  | 2026-07-28 |  |  |  | 2026-08-04 |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 | [6 empty] | 2026-08-25 |  | 2026-09-03 |  | 2026-09-02 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-06 |  |  |  | 2026-09-28 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | 2026-08-05 |  | 2026-07-14 |  | Unknown | 2026-06-25 | 2026-06-26 12:15 | 1625909 | 292663 | 0 | 0 | 0 | 0 | 1570707.5877 | 259356 | 2026-07-14 18:12:44 +0530 | Bency Chacko | Onboarding Due: OB reject - client is disputing that his quote value is 14L (offer email is not matching with the project value in the overview) | 2026-07-14 15:33:27 +0530 | Losii Athisa |  | 2026-07-13 11:48:29 +0530 | Sanjana Swami | client is disputing that his quote value is 14L (offer email is not matching with the project value in the overview) | 2026-07-19 |  | 2026-07-26
20746 | Turnkey | 2026-06-01 | Bilal . | khaleel mansions | BNG - HRBR | Yes | [8 empty] | Janvi Nagdeo |  | Active | Prospect | DCM Due | 1728521 | 9999 | 0 | 0 | 0 | 14 | 0 | 162853 | 172852 | 691408 | 691408.4 |  |  | 2026-06-25 | 2026-07-01 18:18 | 2026-06-26 |  | 2026-07-04 |  | 2026-07-11 |  | 2026-07-18 |  | 2026-07-25 |  | 2026-07-04 |  | 2026-07-05 |  | 2026-07-05 |  | 2026-07-06 | [5 empty] | 2026-07-12 |  | 2026-07-20 |  | 2026-07-21 |  |  |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 |  | 2026-07-31 | [6 empty] | 2026-08-18 |  | 2026-08-27 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-28 |  | 2026-08-30 |  |  |  | 2026-09-21 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | 2026-07-29 |  | 2026-07-07 |  | Unknown | 2026-06-25 | 2026-06-26 12:29 | 0 | 0 | 0 | 0 | 0 | 0 | 1464849 | 263672 | 2026-06-26 12:29:00 +0530 | Unknown | About the Customer **Customer Requirements and Budget** Customer has home interior requirements for a 3 BHK apartment in Bangalore and is considering a budget of â‚¹12 lakhs. **EMI Clarity Needed** Customer requires clarity on zero-cost EMI before visiting the experience center. **Callback and Visit Scheduled** Customer has requested a callback after an hour and will visit the experience center tomorrow evening between 7 PM and 8 PM. | [6 empty] | 2026-07-12 |  | 2026-07-19
20749 | Turnkey | 2026-06-01 | Ramnik Vashishtha | gee cee emrald | MUM - Thane | Yes | [8 empty] | Nishtha Valawalkar |  | Active | Prospect | DCM Due | 1501059 | 9999 | 0 | 0 | 0 | 19 | 0 | 140107 | 150106 | 698239 | 502608 |  |  | 2026-06-26 | 2026-06-26 14:28 | 2026-06-30 | 2026-06-30 15:35 | 2026-06-26 |  | 2026-07-10 |  | 2026-07-17 |  | 2026-07-24 |  | 2026-07-03 |  | 2026-07-04 |  | 2026-07-04 |  | 2026-07-05 | [5 empty] | 2026-07-11 |  | 2026-07-19 |  | 2026-07-20 |  |  |  | 2026-07-27 |  | 2026-07-28 |  | 2026-07-29 |  | 2026-07-30 | [6 empty] | 2026-08-17 |  | 2026-08-26 |  | 2026-08-25 |  | 2026-08-26 |  | 2026-08-27 |  | 2026-08-29 |  |  |  | 2026-09-20 |  | 2026-09-22 |  | 2026-09-23 | [5 empty] | 2026-07-28 |  | 2026-07-06 |  | Unknown | 2026-06-26 | 2026-06-26 14:25 | 0 | 0 | 0 | 0 | 0 | 0 | 1274369 | 226689 | 2026-06-30 15:31:52 +0530 | Hemant Sonar | DCM: DCM Notes * Property Type: 2 BHK * property name - gee ceeÂ * Family Members- hysband wife 2 kidsÂ * Budget: 1213 Lakhs *Possession- dec 2026 Area-wise Requirements 1. Foyer Area * Shoe storage unit to be planned. 1. Living Room * TV unit provision. * Sofa: Â Â * L-shape sofaÂ * Center table * False ceiling only in living room. * Repainting required. 1. Dining Area * 4-seater dining table planned.Â * temple as per vastu . * full glass crocery unitÂ 1. Kitchen * Appliance provisions required for: Â Â * Microwave Â Â * Mixer Â Â * Refrigerator * Modular kitchen: Â Â * Base units Â Â * Wall units Â Â * Loft cabinets 1. Master Bedroom * Queen-size bed. * openable Wardrobe. * TV ledge. * Side table. * Mirror provision (on wardrobe side panelÂ 1. Kids Bedroom * openable Wardrobe. * Study table (foldable). * Open shelves. * Queen-size bed. * Mirror with side panelÂ 1. Bathrooms * 2 vanity units (one in each bathroom). * Mirror and storage provision in both washrooms. 1. Electrical * Electrical scope. * false ceiling only in living roomÂ * re painting cdp planned on 30 th august | 2026-06-28 15:57:12 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-06-28 13:21:40 +0530 | Nishtha Valawalkar | Some Image was uploaded | 2026-07-11 |  | 2026-07-18
20750 | Turnkey | 2026-06-01 | RADHIKA . KIRAN . RAMUGADE | Rustomjee Cleon | MUM - GOR | Yes | Riddhi Deshpande | Christopher Macwan | Kashmira Nerurkar |  | Priyanka Kamble | Nilesh Patel | Rizwan Mistry |  | Saloni Sagwekar | Aakash Gaikwad | Active | Preproduction | 2D | 1212558 | 205619 | 1338265 | 1212558 | 0 | 1 | 0 | 0 | 0 | 559690 | 447249.2 |  |  | 2026-06-26 | 2026-06-26 19:19 | 2026-06-26 | 2026-06-26 19:22 | 2026-06-29 | 2026-06-26 19:57 | 2026-06-28 | 2026-06-28 16:26 | 2026-07-09 | 2026-07-08 16:39 | 2026-07-15 | 2026-07-14 12:25 | 2026-06-26 | 2026-06-26 18:23 | 2026-06-30 | 2026-06-26 19:56 | 2026-06-27 | 2026-06-27 10:47 | 2026-06-27 | 2026-06-27 17:15 |  |  |  |  | 2026-07-03 | 2026-06-28 15:56 | 2026-07-13 | 2026-07-13 18:18 | 2026-07-14 | 2026-07-13 18:18 |  |  | 2026-07-15 |  | 2026-07-16 |  | 2026-07-17 |  | 2026-07-18 | [6 empty] | 2026-08-05 |  | 2026-08-14 |  | 2026-08-13 |  | 2026-08-14 |  | 2026-08-15 |  | 2026-08-17 |  |  |  | 2026-09-08 |  | 2026-09-10 |  | 2026-09-11 | [5 empty] | 2026-07-16 |  | 2026-06-28 | 2026-06-28 16:23 | Site is RTMI | 2026-06-26 | 2026-06-26 14:44 | 1134123 | 204142 | 1301367.6343 | 218260 | 0 | 0 | 1301367.6343 | 218260 | 2026-06-28 18:16:22 +0530 | Christopher Macwan | DEM2(Material selection) scheduled for Friday, 3rd July, 3pm - 6pm | 2026-06-27 17:32:11 +0530 | Christopher Macwan | Welcome call done. Initial measurement done on 27th June 2026 DEM Dates -Â DEM 1 - Customer will update on the whatsapp group on the DEM1 DEM 2 - TBD DEM 3 - TBD Possession date : RTMI Customer will make 10% after DEM1 Periscope - Added FDM dates: TBD Price protection for 150 days from the NET date. | 2026-06-27 10:45:03 +0530 | Sanjana Swami | Possession Status: RTMI Scope of Work: Modular + Painting + Wallpaper (as per the finalized net quote and discussion with the customer) Project Timelines as per Scope: 90+20 business days Detailed timelines explained to the customer during the call, based on the finalized scope of work. Project Execution Plan: Agreement Timeline Plan of Action Discussed During the Call: * IM Today * DEM 1 30th June 2026 * 10% Payment Stage 7th July 2026 *No civil work planned in client's scope of work *Transaction will be B2C self-funding. Informed client that the above timelines are tentative and subject to task closures and overall project progress. Quotation Value Discussed During the Call: 11,10,592 Offers Discussed During the Call: PM Fee Waiver (4%) 40% PM fee waiver 100% GST Waiver Free Hob & Chimney Offer Laminate Upgrade - Jun 26 Campaign Final Closing Value Discussed: 10,28,097 Checklist terms - descoping, delay compensation, agreement terms are clear | 2026-06-29 | 2026-06-28 16:27 | 2026-07-09 | 2026-07-08 17:08 | RTMI |  | 2026-06-26 | 205619 | Ravi Roy
20752 | Turnkey | 2026-06-01 | Sanket Hundekar | Pelican Square | BNG - HRBR | Yes | Vishnu S | Rajeshwari S | Shibin Lal | [5 empty] | Shashank Singh |  | Active | Design | DEM1 | 1532813 | 209999 | 2114115 | 0 | 0 | 6 | 0 | 0 | 96564 | 613125 | 613125.2 |  |  | 2026-06-26 | 2026-06-29 19:52 | 2026-06-29 | 2026-06-29 20:27 | 2026-07-02 | 2026-06-30 19:17 | 2026-07-19 |  | 2026-07-26 |  | 2026-08-02 |  | 2026-06-30 | 2026-07-06 18:51 | 2026-07-01 | 2026-07-07 17:15 | 2026-07-07 | 2026-07-09 14:13 | 2026-07-10 | 2026-07-14 19:09 |  |  |  |  | 2026-07-20 |  | 2026-07-28 |  | 2026-07-29 |  |  |  | 2026-08-05 |  | 2026-08-06 |  | 2026-08-07 |  | 2026-08-08 | [6 empty] | 2026-08-26 |  | 2026-09-04 |  | 2026-09-03 |  | 2026-09-04 |  | 2026-09-05 |  | 2026-09-07 |  |  |  | 2026-09-29 |  | 2026-10-01 |  | 2026-10-02 | [5 empty] | 2026-08-06 |  | 2026-07-15 |  | Unknown | 2026-06-26 | 2026-06-26 18:04 | 1791623 | 322492 | 0 | 0 | 0 | 0 | 1722685.6 | 284456 | 2026-07-14 19:25:18 +0530 | Rajeshwari S | Non RTMI - Completion Date: September 2026 10% Payment - 1st week of August IM - July end and meeting in the 1st week of August. | 2026-07-14 15:35:18 +0530 | Losii Athisa |  | 2026-07-09 14:13:08 +0530 | Athul Ajaykumar | OB Accepted - had a word with client on call. Client confirmed that he will close 10% by 18th July. moving the OB | 2026-07-20 |  | 2026-07-27 |  | Under Construction | 2026-09-30 | 2026-06-29 | 9999 | Ravi Roy